## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Malda Division | Chanchal Sub-Division | Laying of Parallel/ Dedicated Pipeline, Providing Common Manifold & providing Balance FHTC for better Functionality at Bakhra Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer |  | ORD/000231/2025-2026 | 4235/MD | 29/08/2025 | 60 | M/S N. N. ENTERPRISE | 32.31 | 0 | 0
2 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer |  | ORD/000568/2020-2021 | 2464/MD | 12/10/2020 | 30 | UTTAM KUMAR GHOSH | 57.92 | 7.52 | 0
3 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bakhra Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer |  | ORD/000739/2024-2025 | 58 | 08/01/2025 | 45 | M/S N. N. ENTERPRISE | 28.26 | 0 | 0
4 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer |  | RTOR000007/2024-2025 | 3919/MD | 06/08/2024 | 0 | Resource Division | 4 | 0 | 0
5 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer |  | RTOR000078/2025-2026 | 5543/MD | 29/10/2025 | 0 | Resource Division | 4.41 | 0 | 0
6 | Malda Division | Malda Sadar Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of GOBINDAPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000058/2020-2021 | 2262/MD | 29/09/2020 | 45 | UTTAM KUMAR DUTTA | 60.07 | 103.06 | 1
7 | Malda Division | Malda Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gobindapur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000278/2024-2025 | 3198/MD | 27/06/2024 | 476 | ANJIMA CONSTRUCTION CO. | 10.56 | 0 | 0
8 | Malda Division | Malda Sadar Sub-Division | Material Requisition To Resource Division | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | RTOR000040/2025-2026 | 2817/MD | 11/06/2025 | 0 | Resource Division | 10.77 | 0 | 0
9 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Gourhanda Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Junior Engineer | ORD/000163/2025-2026 | 2876/MD | 17/06/2025 | 60 | M/S KUNDU CONSTRUCTION | 60.09 | 0 | 0
10 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOUR HANDA Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Junior Engineer | ORD/000168/2020-2021 | 2721/MD | 10/11/2020 | 45 | SUBHAS CHANDRA KESHARI | 74.49 | 45.41 | 0
11 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Gourhanda Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Junior Engineer | ORD/000850/2024-2025 | 1043/MD | 18/03/2025 | 75 | MATIUR RAHAMAN | 32.5 | 0 | 0
12 | Malda Division | Chanchal Sub-Division | Erection of Property board related to Jal Jeevan Mission works of Gourhanda & Jalalpur GP under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Junior Engineer | ORD/000946/2024-2025 | 635/MD | 19/02/2025 | 7 | BIDYUT MAHALDAR | 0.9 | 0 | 0
13 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Junior Engineer | RTOR000010/2024-2025 | 3922/MD | 06/08/2024 | 0 | Resource Division | 8.62 | 0 | 0
14 | Malda Division |  | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KADIRPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. |  |  | ORD/000029/2020-2021 | 1964/MD | 31/08/2020 | 30 | M/S KUNDU CONSTRUCTION | 39.43 | 78 | 1
15 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KADIRPUR Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000719/2023-2024 | 4768/MD | 05/12/2023 | 45 | M/S SINHA ENTERPRISE | 16.09 | 15.51 | 100
16 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000010/2025-2026 | 2584/MD | 30/05/2025 | 0 | Resource Division | 7.31 | 0 | 0
17 | Malda Division | Chanchal Sub-Division | Sinking of 01 (One) Nos. 250mm. Dia. x 200 mm. Big dia. Tube Well 131 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with 2nd Tube Well Site at Talbangura Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00673/2024-2025 | 464/DW | 25/09/2024 | 0 | A. L. ENGINEERING SOLUTION | 3.98 | 0 | 0
18 | Malda Division | Chanchal Sub-Division | Formal work order for Providing house connection under RANGHAT Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000015/2020-2021 | 2038/MD | 10/09/2020 | 120 | PROJECT INDIA | 94.64 | 8.18 | 100
19 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000558/2020-2021 | 2436/MD | 12/10/2020 | 120 | M/S TRILOCHAN CONSTRUCTION CO | 12 | 13.18 | 1
20 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHANPUR HULASPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000722/2021-2022 | 48/1/MD | 13/01/2022 | 30 | BIDYUT MAHALDAR | 0.39 | 0.39 | 100
21 | Malda Division | Chanchal Sub-Division | Laying of Parallel/Dedicated Pipeline improvement of functionality, Providing Balance FHTC and Construction of Boundary Wall of TALBANGURA Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000969/2025-2026 | 696/MD | 13/02/2026 | 75 | MANIK CHOUDHURY | 27.19 | 0 | 0
22 | Malda Division | Chanchal Sub-Division | Testing of HDPE pipe 20 mm as per IS 4984:2016 reg. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | VCH/000108/2021-2022 | 44 | 07/05/2021 | 0 | CIPET EXTN CENTRE | 0.22 | 0 | 0
23 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Nayagram, Silampur & Bahanna Bigha for installation of FHTC under Baliadanga distribution Zone of Southern Sector under Malda Arsenic Area W/S Division, PHE Dte | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000030/2023-2024 | 881/MAAD | 11/05/2023 | 30 | M/S ALISA CONSTRUCTION | 7.8 | 7.8 | 100
24 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Baliadanga Water Supply Scheme (Mouza- Silampur, Maheshpur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000113/2022-2023 | 1015/MAAD | 12/05/2022 | 60 | M/S ALISA CONSTRUCTION | 82.93 | 77.37 | 1
25 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 75 mm dia uPVC Pipe line at Sonar Para, Thana Para, Namopara, Harkatola & Maksod Tola for installation of FHTC under Baliadanga distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000159/2022-2023 | 1172/MAAD | 13/06/2022 | 45 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.76 | 4.73 | 1
26 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90 mm dia uPVC Pipe line at Hajinagar, Meheruddin Munsi Tola & Saifuddin Sardar Tola for installation of FHTC under Baliadanga distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000160/2022-2023 | 1173/MAAD | 13/06/2022 | 45 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.82 | 4.81 | 1
27 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
28 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mouza: -Baliadanga, Khaschandpur, Silampur Habitations: - Baliadanga, Gharialichak, Kaliachak, Alipur, Kalikapur for installation of FHTC under Baliadanga distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000197/2022-2023 | 1448/MAAD | 29/07/2022 | 30 | M/S MOON LIGHT CONSTRUCTION & CO. | 3.89 | 3.88 | 1
29 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | RTOR000002/2022-2023 | 1334/MAAD | 18/07/2022 | 0 | Resource Division | 12.3 | 0 | 0
30 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | RTOR000003/2021-2022 | 1789/MAAD | 26/11/2021 | 0 | Resource Division | 66.42 | 0 | 0
31 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | RTOR000009/2022-2023 | 1699/MAAD21 | 21/09/2022 | 0 | Resource Division | 6.05 | 0 | 0
32 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Baliadanga Water Supply Scheme (Mouza- Kaliachak, Habitation- Puratun Babur Hat) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000253/2022-2023 | 1831MAAD | 27/09/2022 | 45 | THREE BROTHERS CONSTRUCTION & CO. | 3.8 | 3.76 | 1
33 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Baliadanga Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Baliadanga) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000330/2021-2022 | 1733/MAAD | 24/11/2021 | 60 | M/S MOON LIGHT CONSTRUCTION & CO. | 44.98 | 44.82 | 1
34 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 200 mm, 90 mm dia UPVC Pipe line and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Rishi Para, Ghosh Para under Baliadanga distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000424/2022-2023 | 321/MAAD | 21/02/2023 | 60 | THREE BROTHERS CONSTRUCTION & CO. | 18.91 | 17.19 | 100
35 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | SUPPLY OF OFFICE FURNITURE & OTHER STATIONERY ITEM FOR OFFICE USE STATIONERY ARTICLES FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | BILL/00240/2023-2024 |  | 24/08/2023 | 0 | MALDA DISTRICT SERVICE CUM-MARKETING INDUSTRIAL CO-OPERATIVE UNION LTD. | 1.73 | 0 | 0
36 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | SUPPLY OF OFFICE FURNITURE & OTHER STATIONERY ITEM FOR OFFICE USE STATIONERY ARTICLES FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | BILL/00271/2023-2024 |  | 07/09/2023 | 0 | MALDA DISTRICT SERVICE CUM-MARKETING INDUSTRIAL CO-OPERATIVE UNION LTD. | 1.52 | 0 | 0
37 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | SUPPLY & DELIVERY OF DIFFERENT MATERIALS FOR THE DIFFERENT ON-GOING WATER SUPPLY SCHEME UNDER JJM WORKS. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | BILL/00347/2023-2024 |  | 22/09/2023 | 0 | MALDA DISTRICT SERVICE CUM-MARKETING INDUSTRIAL CO-OPERATIVE UNION LTD. | 1.52 | 0 | 0
38 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kumvira Water Supply Scheme(Habitation-Sukpara,Kumvira&Hatatpara) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000047/2022-2023 | 821/MAAD | 28/04/2022 | 60 | FUTURE | 76.04 | 75.72 | 1
39 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Nurnagar under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000138/2022-2023 | 1151/MAAD | 13/06/2022 | 15 | M/S AMIT KUMAR GUPTA | 3.9 | 3.89 | 1
40 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Bakrabad & Sabdalpur under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000139/2022-2023 | 1152/MAAD | 13/06/2022 | 15 | M/S AMIT KUMAR GUPTA | 4.16 | 4.15 | 1
41 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Sukdebpur under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000140/2022-2023 | 1153/MAAD | 13/06/2022 | 15 | M/S AMIT KUMAR GUPTA | 4.04 | 4.04 | 1
42 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Mohanpur khas & Mohanpur under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000141/2022-2023 | 1155MAAD | 13/06/2022 | 15 | M/S AMIT KUMAR GUPTA | 3.9 | 3.88 | 1
43 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Hadinagar & Neoginagar under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000142/2022-2023 | 1154/MAAD | 13/06/2022 | 15 | M/S AMIT KUMAR GUPTA | 3.93 | 3.91 | 1
44 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipe 140mm dia at Sabdalpur Guntola & others Allied works at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000190/2022-2023 | 1401/MAAD | 26/07/2022 | 45 | MAHA MAYA CONSTRUCTION | 8.18 | 7.5 | 1
45 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC Pipe Line of 90mm at Sabdalpur Jamaipara & Kubhira for under Kumbhira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000215/2022-2023 | 1463/MAAD | 29/07/2022 | 45 | FUTURE | 3.06 | 3.05 | 1
46 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC Pipe Line of 75 mm dia at Godhantola,Mahis Mandal para,Bakrabad char & Sukpara for under Kumbhira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000216/2022-2023 | 1464/MAAD | 29/07/2022 | 45 | FUTURE | 4.71 | 4.71 | 1
47 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Khasmohanpur,Kumvira under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000258/2022-2023 | 1836/MAAD | 27/09/2022 | 30 | FUTURE | 4.3 | 4.29 | 1
48 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Sabdalpur, Sukpara under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000259/2022-2023 | 1837/MAAD | 27/09/2022 | 30 | FUTURE | 4.4 | 4.39 | 1
49 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Mohanpur,Godhantola under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000260/2022-2023 | 1838/MAAD | 27/09/2022 | 30 | FUTURE | 4.13 | 4.12 | 1
50 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Hatatpara,Ghospara under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000261/2022-2023 | 1839MAAD | 27/09/2022 | 30 | FUTURE | 4.36 | 4.34 | 1
51 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Sabdalpur Guntola under command area of Kumvira Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000294/2022-2023 | 2033/MAAD | 16/11/2022 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 9.35 | 9.25 | 1
52 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipe 200mm,160mm,125mm&110mm dia at Sukpara& others Allied works at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000510/2021-2022 | 395/MAAD | 08/03/2022 | 45 | DEY CONSTRUCTION | 30.43 | 30.41 | 1
53 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipe 90mm dia at Mahonpur & others Allied works at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000515/2021-2022 | 346/MAAD | 07/03/2022 | 45 | ABHIJIT CONSTRUCTION | 3.78 | 3.74 | 1
54 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipe 90mm dia at Manoj Master para & others Allied works at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000516/2021-2022 | 347/MAAD | 07/03/2022 | 45 | MAHA MAYA CONSTRUCTION | 3.61 | 3.59 | 1
55 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kumvira Water Supply Scheme(Habitation Nurnagar, Bakhtarband, Sabdulpur, Sukdebpur, Harinagar, Niyoginagar, Mohanpur Khas, Mohanpur) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000328/2021-2022 | 1739/MAAD | 24/11/2021 | 60 | M/S AMIT KUMAR GUPTA | 59.9 | 59.86 | 1
56 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Continuation Work Order for Placing of diesel driven Car on hire basis for the official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. (for the period from 01.01.2023 to 31.12.2023)= 365 days. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000462/2022-2023 | 2389/MAAD | 30/12/2022 | 133313 | SUBRATA SAHA | 1.73 | 4.22 | 60
57 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Jalalpur) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000565/2021-2022 | 1743/MAAD | 24/11/2021 | 30 | BEE GEE CONSTRUCTION | 70 | 3.19 | 1
58 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90 mm dia uPVC Pipe line at Mahadipur Village for installation of FHTC under Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000163/2022-2023 | 1176/MAAD | 13/06/2022 | 45 | BANIK BROTHERS | 4.8 | 4.76 | 1
59 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90 mm dia uPVC Pipe line at Khirki Village for installation of FHTC under Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000164/2022-2023 | 1177/MAAD | 13/06/2022 | 45 | BANIK BROTHERS | 4.81 | 4.79 | 1
60 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 83.91 | 30
61 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Name of the Work :- Laying of 90 mm dia UPVC Pipe line at Mastarpara, Raypara of Mahadipur Village for installation of FHTC under Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000217/2022-2023 | 1465/MAAD | 29/07/2022 | 45 | BANIK BROTHERS | 3.21 | 3.2 | 1
62 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90 mm dia uPVC Pipe line at Parbatipur and Gour Mohali village for installation of FHTC under Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000270/2022-2023 | 1872/MAAD | 28/09/2022 | 45 | BANIK BROTHERS | 3.57 | 3.55 | 1
63 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Mahadipur) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000333/2021-2022 | 1738/MAAD | 24/11/2021 | 60 | BANIK BROTHERS | 56.36 | 56.15 | 1
64 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mahadipur Village for installation of FHTC under Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000477/2022-2023 | 614/MAAD | 31/03/2023 | 15 | BANIK BROTHERS | 4.46 | 4.46 | 100
65 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Garh Mahali & Khirki Village for installation of FHTC under Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000478/2022-2023 | 615/MAAD | 31/03/2023 | 15 | BANIK BROTHERS | 4.02 | 4.01 | 100
66 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer |  | ORD/000077/2020-2021 | 2465/MD | 12/10/2020 | 45 | UTTAM KUMAR GHOSH | 70.72 | 96.83 | 1
67 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Additional laying work of DI & UPVC pipe line of SADLICHAK W/S Scheme at HARISHCHANDRAPUR-II Dev. Block under Malda division.P.H.E.Dte. In the District of Malda. | Sri Susanta Saha, Assistant Engineer |  | ORD/000655/2021-2022 | 47/CSD | 14/01/2022 | 30 | BEE GEE CONSTRUCTION | 4.19 | 0 | 1
68 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer |  | RTOR000020/2025-2026 | 2824/MD | 11/06/2025 | 0 | Resource Division | 10.11 | 0 | 0
69 | Malda Division | Malda Mechanical Division | Laying of Distribution Line, Providing FHTC, Construction of Pump House at Daudpur Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000143/2024-2025 | 2902/MD | 07/06/2024 | 480 | M/S MOON LIGHT CONSTRUCTION & CO. | 93.32 | 0 | 51
70 | Malda Division | Malda Mechanical Division | Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of Daudpur Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000191/2024-2025 | 2970/MD | 10/06/2024 | 90 | BIDYUT MAHALDAR | 6.55 | 0 | 100
71 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of DAUDPUR & its adjoining mouza Water Scheme under Malda Division,PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000288/2022-2023 | 2234/MD | 16/09/2022 | 45 | M/S. TEWARI CONSTRUCTION | 6.19 | 0 | 0
72 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01 (One) Nos. 250mm. Dia. x 150mm. Big dia. Tube Well 160 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer at Daudpur Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000289/2022-2023 | 2235/MD | 16/09/2022 | 15 | SNEHASISH GHOSH | 8.09 | 0 | 100
73 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160m Deep at Daudpur PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000303/2024-2025 | 4741/MD | 11/09/2024 | 45 | A. L. ENGINEERING SOLUTION | 10.44 | 0 | 0
74 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of DAUDPUR ZONE-I Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000388/2023-2024 | 3288/MD | 23/08/2023 | 1132 | A. K. CONSTRUCTION | 151.6 | 34.14 | 60
75 | Malda Division | Malda Mechanical Division | Sinking of 200 mm (all through) Big dia. Tube Well of 160 m Deep by D.R Rig. Method using P.V.C. pipe & Filter including Supply of materials at head work site under DAUDPUR Water Supply Scheme of Chanchal-I Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000467/2024-2025 | 4822/MD | 13/09/2024 | 30 | SAUDAGAR INDIA | 10.21 | 0 | 0
76 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Daudpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000762/2024-2025 | 71 | 13/01/2025 | 45 | THREE BROTHERS CONSTRUCTION & CO | 31.61 | 0 | 0
77 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Daudpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000867/2024-2025 | 1223/MD | 26/03/2025 | 30 | M/S MADHU CONSTRUCTION | 19.79 | 0 | 0
78 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | RTOR000026/2022-2023 | 2756/MD | 22/11/2022 | 0 | Resource Division | 34.78 | 0 | 0
79 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | RTOR000079/2025-2026 | 5534/MD | 29/10/2025 | 0 | Resource Division | 4.97 | 0 | 0
80 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | RTOR000129/2023-2024 | 99/MD | 05/01/2024 | 0 | Resource Division | 4.93 | 0 | 0
81 | Malda Mechanical | Malda Mechanical Division | New service connection at daudpur w/s sch. T/W no I Under EE/ MLMD PHE DTE District - malda. (chanchal c. c. c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | BILL/03549/2023-2024 | BP-2023-24-562 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 14.26 | 0 | 0
82 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Daudpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011680) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/001796/2023-2024 | 3683/MLMD | 29/11/2023 | 971 | MUKHERJEE ART CENTRE | 29.89 | 19.34 | 76
83 | Malda Division | Malda Mechanical Division | Design, Supplying. Fabrication, Erection and Commissioning including 3 (three) months Trial Run of 40 m3/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site, Laying of Parallel/Dedicated Pipeline and Construction of Boundary Wall at head work site of DAUDPUR ZONE-I Water Supply Scheme of Chanchal-I Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000967/2025-2026 | 694/MD | 13/02/2026 | 150 | A. K. CONSTRUCTION | 52.36 | 0 | 0
84 | Malda Division | Malda Mechanical Division | Design, Supplying. Fabrication, Erection and Commissioning including 3 (three) months Trial Run of 30 m3/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal, Construction of Boundary Wall and interconnection and Laying of Parallel/Dedicated Pipeline of DAUDPUR ZONE-II Water Supply Scheme of Chanchal-I Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000968/2025-2026 | 695/MD | 13/02/2026 | 150 | VISCOUS ENGINEERS PVT. LTD. | 61.33 | 0 | 0
85 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of KARIALI ZONE-II Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000040/2023-2024 | 1947/MD | 16/05/2023 | 1136 | UTTAM KUMAR GHOSH | 399.3 | 216.91 | 75
86 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Kariali Zone-II PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000595/2024-2025 | 5599/MD | 05/11/2024 | 60 | DIPU DUTTA | 4.53 | 0 | 0
87 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000607/2024-2025 | 5603/MD | 05/11/2024 | 60 | GULJAR CONSTRUCTION | 6.93 | 0 | 0
88 | Malda Division | Malda Mechanical Division | Sinking of 200mm (all through) Big dia. Tube Well of 150m Deep at 3rd Tube well site of Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000609/2024-2025 | 5605/MD | 05/11/2024 | 45 | SAUDAGAR INDIA | 9.82 | 0 | 0
89 | Malda Division | Malda Mechanical Division | Additional Laying Distribution of UPVC Pipe line of KARIALI ZONE-II Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000612/2023-2024 | 4141/MD | 11/10/2023 | 30 | S.S.GHOSH ENTERPRISE & CO. | 2.13 | 2.11 | 80
90 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000635/2024-2025 | 5914/MD | 26/11/2024 | 611 | UTTAM KUMAR GHOSH | 27.23 | 0 | 0
91 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Kariali Zone-II Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000692/2021-2022 | 657/MD | 22/03/2022 | 15 | M/S SOBHA & CO. | 2.76 | 2.73 | 1
92 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000954/2023-2024 | 699/MD | 09/02/2024 | 933 | UTTAM KUMAR GHOSH | 16.32 | 0 | 0
93 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Kandaran Zone-II Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000955/2023-2024 | 700/MD | 09/02/2024 | 857 | UTTAM KUMAR GHOSH | 22.42 | 0 | 0
94 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000026/2025-2026 | 2827/MD | 11/06/2025 | 0 | Resource Division | 7.12 | 0 | 0
95 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000060/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 16.83 | 0 | 0
96 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000080/2025-2026 | 5550/MD | 29/10/2025 | 0 | Resource Division | 13.55 | 0 | 0
97 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000179/2023-2024 | 756/MD | 19/02/2024 | 0 | Resource Division | 4.31 | 0 | 0
98 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I of Kariali (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011264) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000682/2023-2024 | 2757/MLMD | 14/08/2023 | 180 | DEB CONSTRUCTION. | 21.59 | 12.31 | 58
99 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. (Zone-II) of Kariali PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001520/2023-2024 | 3004422637 | 22/09/2023 | 90 | W.B.S.E.D.C.LTD | 7.19 | 7.19 | 100
100 | Malda Division | Malda Mechanical Division | Placement of fund against the work for road restoration for laying pipe line for Eklakhi to Rashikpur road from 2.400 KM to 7.900 Km under AKALPUR PWSS under Malda Division,PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | BILL/00515/2024-2025 | BP-2024-25-252 | 10/09/2024 | 0 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 9.95 | 0 | 0
101 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Akalpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000209/2024-2025 | 3030/MD | 13/06/2024 | 30 | BENGAL ENGINEERING COMPANY | 15.69 | 0 | 0
102 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No-3 ( 135 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at AKALPUR Water Supply Scheme of Gazole Block .under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000309/2022-2023 | 2304/MD | 28/09/2022 | 30 | DUTTA ENTERPRISE | 9.04 | 9.03 | 1
103 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of AKALPUR Water Supply Scheme of Gazole Block. under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000345/2022-2023 | 3113/MD | 20/12/2022 | 45 | THREE BROTHERS CONSTRUCTION & CO | 6.69 | 6.67 | 0
104 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for AKALPUR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000359/2022-2023 | 2508/MD | 03/11/2022 | 45 | M/S. TEWARI CONSTRUCTION | 28.05 | 23.11 | 1
105 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Akalpur Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000598/2024-2025 | 5936/MD | 27/11/2024 | 90 | S. N. CONSTRUCTION | 42.82 | 0 | 0
106 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000016/2022-2023 | 2411/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
107 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Akalpur, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000095/2023-2024 | 3004293392 | 16/05/2023 | 90 | W.B.S.E.D.C.LTD | 5.14 | 5.14 | 0
108 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Source Augmentation Akalpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012797) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001124/2022-2023 | 507/MLMD | 20/03/2023 | 120 | SUBHAS CHANDRA KESHORI | 11.42 | 11.25 | 100
109 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of SWARUPGANJ Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000106/2023-2024 | 2333/MD | 08/06/2023 | 60 | ABANI BHUSAN GHOSH | 52.67 | 33 | 65
110 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube well site of Swarupganj Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000606/2024-2025 | 5602/MD | 05/11/2024 | 60 | BANIK BROTHERS | 6.93 | 0 | 0
111 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of SWARUPGANJ Water Supply Scheme at Chanchal-I Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000615/2022-2023 | 952/MD | 28/02/2023 | 1119 | BANIK BROTHERS | 469.75 | 257.14 | 75
112 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Swarupganj Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000756/2024-2025 | 74 | 13/01/2025 | 261 | BANIK BROTHERS | 83.72 | 0 | 0
113 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of SWARUPGANJ Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000917/2023-2024 | 379/MD | 17/01/2024 | 45 | BANIK BROTHERS | 21.73 | 0 | 0
114 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000016/2025-2026 | 2807/MD | 11/06/2025 | 0 | Resource Division | 7.34 | 0 | 0
115 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000076/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 23.46 | 0 | 0
116 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000081/2025-2026 | 5551/MD | 29/10/2025 | 0 | Resource Division | 7.34 | 0 | 0
117 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000178/2023-2024 | 755/MD | 19/02/2024 | 0 | Resource Division | 12.32 | 0 | 0
118 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Swarupganj Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013249) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000327/2023-2024 | 2329/MLMD | 26/07/2023 | 1130 | MERCURY ENGINEERING COMPANY. | 30.4 | 24.95 | 84
119 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of SWARUPGANJ, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000465/2023-2024 | 3004368721 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 5.49 | 5.49 | 100
120 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of SWARUPGANJ, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000466/2023-2024 | 3004368714 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.93 | 4.93 | 100
121 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Dakshin Bhakuria Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000185/2024-2025 | 2960/MD | 10/06/2024 | 30 | SK ENTERPRISE | 6.46 | 0 | 95
122 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of DAKSHIN BHAKURIA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000234/2023-2024 | 2707/MD | 14/07/2023 | 270 | MOTI RAHAMAN | 202.31 | 84.6 | 42
123 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of UTTAR BHAKURIA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000366/2022-2023 | 2695/MD | 17/11/2022 | 30 | ASHIS CONSTRUCTION | 9.2 | 9.2 | 80
124 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Dakshin Bhakuria Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000490/2024-2025 | 5003/MD | 27/09/2024 | 45 | M/S TEWARI CONSTRUCTION | 32.97 | 0 | 0
125 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000078/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 9.78 | 0 | 0
126 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000082/2025-2026 | 5544/MD | 29/10/2025 | 0 | Resource Division | 2.27 | 0 | 0
127 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000135/2023-2024 | 114/MD | 05/01/2024 | 0 | Resource Division | 3.7 | 0 | 0
128 | Malda Mechanical | Malda Mechanical Division | New service connection at Dakshin Bhakuria ph II PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Bhaluka c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/00757/2024-2025 | BP-2024-25-205 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.7 | 0 | 0
129 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of DAKSHIN BHAKURIA, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/02462/2023-2024 | BP-2023-24-413 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.87 | 0 | 0
130 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Dakshin Bhakuria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013248) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000314/2023-2024 | 2315/MLMD | 26/07/2023 | 837 | DAS CONSTRUCTION | 25.62 | 16.93 | 78
131 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Implementation of TALPUKUR Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000043/2023-2024 | 1899/MD | 10/05/2023 | 1202 | BANIK BROTHERS | 523.57 | 369.01 | 71
132 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tube well Site of Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000163/2024-2025 | 2938/MD | 10/06/2024 | 30 | BANIK BROTHERS | 8.99 | 0 | 100
133 | Malda Division | RWS Malda Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 60m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Talpukur Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000207/2024-2025 | 3028/MD | 13/06/2024 | 292 | BANIK BROTHERS | 28.84 | 0 | 100
134 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000662/2024-2025 | 6162/MD | 05/12/2024 | 45 | IDEAL CONSTRUCTION | 26.03 | 0 | 0
135 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work site of Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000883/2023-2024 | 159/MD | 08/01/2024 | 45 | BANIK BROTHERS | 22.15 | 21.82 | 100
136 | Malda Division | RWS Malda Sub-Division | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works of Chaksukur, Dalla, Talpukur, Aiho PWSS under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000955/2024-2025 | 644/MD | 19/02/2025 | 7 | SADHANA CONSTRUCTION | 0.81 | 0 | 0
137 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000025/2023-2024 | 1605/MD | 11/04/2023 | 0 | Resource Division | 13.49 | 0 | 0
138 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000032/2022-2023 | 3044/MD | 12/12/2022 | 0 | Resource Division | 15.84 | 0 | 0
139 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Talpukur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013199) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000240/2023-2024 | 2257/MLMD | 18/07/2023 | 954 | GHOSH BROTHERS... | 28.3 | 22.52 | 76
140 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Talpukur , Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/001906/2023-2024 | 3004501336 | 28/11/2023 | 90 | W.B.S.E.D.C.LTD | 6.96 | 6.96 | 100
141 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Talpukur , Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/001907/2023-2024 | 3004501325 | 28/11/2023 | 90 | W.B.S.E.D.C.LTD | 3.83 | 3.83 | 100
142 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
143 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of ARAZI JALSA Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000046/2023-2024 | 2008/MD | 17/05/2023 | 1108 | M/S TAPAS KUMAR CHAKRABORTY & CO | 1160.94 | 738.03 | 65
144 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 80m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Arazi Jalsha Water Supply Scheme of Gazole Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000133/2025-2026 | 2507/MD | 29/05/2025 | 339 | WIST WATER SOLUTIONS | 31.43 | 0 | 0
145 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Arazi Jalsa Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000178/2024-2025 | 2953/MD | 10/06/2024 | 30 | SIVRAM ENTERPRISE | 8.72 | 0 | 100
146 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Arazi Jalsa Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000265/2024-2025 | 3213/MD | 27/06/2024 | 551 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.89 | 0 | 70
147 | Malda Division | Malda Mechanical Division | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 10/05/2024 to 19/06/2024=41 Days). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000576/2024-2025 | 2421/MD | 09/05/2024 | 41 | TARUN KUMAR BHATTACHARYA | 0.19 | 0.26 | 0
148 | Malda Division | Malda Mechanical Division | Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 20/06/2024 to 16/12/2024=180 Days). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000577/2024-2025 | 3108/MD | 18/06/2024 | 180 | TARUN KUMAR BHATTACHARYA | 0.86 | 1.41 | 0
149 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arazi Jalsa Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000634/2024-2025 | 5913/MD | 26/11/2024 | 444 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28.74 | 0 | 0
150 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000054/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 11.31 | 0 | 0
151 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000096/2023-2024 | 29/MD | 04/01/2024 | 0 | Resource Division | 20.4 | 0 | 0
152 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Arazi Jalsa Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013468) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000505/2023-2024 | 2575/MLMD | 04/08/2023 | 756 | NIRMAN. | 26.75 | 0 | 87
153 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of ARAZI JALSA , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/001899/2023-2024 | 3004481943 | 08/11/2023 | 90 | W.B.S.E.D.C.LTD | 9.23 | 9.23 | 100
154 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of ARAZI JALSA , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/001900/2023-2024 | 3004481907 | 08/11/2023 | 90 | W.B.S.E.D.C.LTD | 4.21 | 4.21 | 100
155 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of SULTANNAGAR Water Supply Scheme at HARISHCHANDRAPUR-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000030/2023-2024 | 1845/MD | 02/05/2023 | 1245 | M/S ALISA CONSTRUCTIION | 289.64 | 159.22 | 89
156 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of SULTANNAGAR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000370/2022-2023 | 2699/MD | 17/11/2022 | 30 | ASHIS CONSTRUCTION | 9.2 | 8.55 | 1
157 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at SULTANNAGAR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000605/2022-2023 | 923/MD | 27/02/2023 | 30 | DUTTA ENTERPRISE | 10.13 | 10.13 | 100
158 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sultannagar Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000660/2024-2025 | 1261/MD | 28/03/2025 | 369 | M/S AYUSH BUILDERS | 22.7 | 0 | 0
159 | Malda Division | Malda Mechanical Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2023 to 30/06/2023). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000819/2022-2023 | 519/MSD | 30/12/2022 | 182 | ARUN KUMAR DAS | 0.86 | 1.04 | 71
160 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000013/2023-2024 | 1620/MD | 11/04/2023 | 0 | Resource Division | 10.22 | 0 | 0
161 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000037/2022-2023 | 3049/MD | 12/12/2022 | 0 | Resource Division | 25.94 | 0 | 0
162 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Sultannagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012936) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000028/2023-2024 | 785/ MLMD | 27/04/2023 | 916 | M/S SAJAHAN CHOWDHURY | 28.18 | 24.3 | 85
163 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Sultannagar PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000091/2023-2024 | 3004232824 | 17/05/2023 | 90 | W.B.S.E.D.C.LTD | 5.28 | 5.28 | 0
164 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SULTANNAGAR, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000295/2023-2024 | 3004353821 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.66 | 2.66 | 100
165 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Mekpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000054/2023-2024 | 1985/MD | 17/05/2023 | 45 | HIRAK ROY CHOUDHURY | 8.28 | 8.27 | 100
166 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Tube Well No. 3 of Mekpur Water Supply Scheme of Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000137/2025-2026 | 2615/MD | 02/06/2025 | 135 | M/S PARIMAL DAS | 17.27 | 0 | 0
167 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Tube Well No. 4 of Mekpur Water Supply Scheme of Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000138/2025-2026 | 2616/MD | 02/06/2025 | 135 | M/S PARIMAL DAS | 17.27 | 0 | 0
168 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Kadamtali Mouza under Mekpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000252/2024-2025 | 3188/MD | 27/06/2024 | 303 | MANIK CHOUDHURY | 19.96 | 0 | 100
169 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at MEKPUR Piped Water Supply Scheme (Tube Well No-3) of Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000376/2022-2023 | 2702/MD | 17/11/2022 | 30 | A. L. ENGINEERING SOLUTION | 8.42 | 8.42 | 1
170 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at MEKPUR Piped Water Supply Scheme (Tube Well No-4) of Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000377/2022-2023 | 2703/MD | 17/11/2022 | 30 | A. L. ENGINEERING SOLUTION | 8.42 | 8.42 | 1
171 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for MEKPUR Piped Water Supply Scheme (JL-15 Samsabad, JL-20 Kadamtali, JL-21 Badanpur, JL-22 Chhotapara, JL-23 Lakshmi Kandar and JL-27 Rahutgaon) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000411/2022-2023 | 2985/MD | 07/12/2022 | 45 | MANIK CHOUDHURY | 55.22 | 54.19 | 100
172 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for MEKPUR Piped Water Supply Scheme (JL-11 Tutkhan, JL-12 Goalpara, and JL-14 Gotpara) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000412/2022-2023 | 2986/MD | 07/12/2022 | 756 | M/S PARIMAL DAS | 56.72 | 53.93 | 1
173 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Mekpur Water Supply scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000843/2024-2025 | 1068/MD | 19/03/2025 | 60 | S. R. ENTERPRISE | 8.04 | 0 | 0
174 | Malda Division | Malda Mechanical Division | Extension of pipe line and replacing of damage A.C./uPVC pipe line by different dia. UPVC pipe for MEKPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000973/2023-2024 | 870/MD | 27/02/2024 | 45 | S. R. ENTERPRISE | 6.07 | 5.63 | 100
175 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Goalpara Mouza under Mekpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001012/2023-2024 | 1514/MD | 16/03/2024 | 30 | S. N. CONSTRUCTION | 11.32 | 9.01 | 100
176 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000083/2025-2026 | 5545/MD | 29/10/2025 | 0 | Resource Division | 4.62 | 0 | 0
177 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Mekpur, Old malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | BILL/02569/2023-2024 | BP-2023-24-462 | 17/01/2024 | 0 | W.B.S.E.D.C.LTD | 1.01 | 0 | 0
178 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Mekpur PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000049/2023-2024 | 3004243230 | 27/04/2023 | 90 | W.B.S.E.D.C.LTD | 4.5 | 4.5 | 0
179 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Mekpur PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000050/2023-2024 | 3004243234 | 27/04/2023 | 90 | W.B.S.E.D.C.LTD | 2.42 | 2.42 | 0
180 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III, IV & V of Source Augmentation of Mekpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014459) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001126/2022-2023 | 509/MLMD | 20/03/2023 | 120 | ORIENTAL ENGINEERING CO. | 34.55 | 20.21 | 58
181 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of SAIDPUR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000118/2023-2024 | 2320/MD | 08/06/2023 | 930 | NEOGI ENTERPRISE | 651.25 | 382.68 | 60
182 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Saidpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000155/2025-2026 | 2704/MD | 04/06/2025 | 225 | M/S ANKUSH ENTERPRISE | 29.48 | 0 | 0
183 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Saidpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000182/2024-2025 | 2957/MD | 10/06/2024 | 30 | SAYEM ENTERPRISE | 7.16 | 0 | 100
184 | Malda Division | Malda Mechanical Division | Jack Pushing of D.I. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through The HILLY- BALURGHAT Road NH 512 between GAZOLE to BALURGHAT for SAIDPUR Pipe Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000211/2025-2026 | 3746/MD | 31/07/2025 | 244 | M/S TRILOCHAN CONSTRUCTION CO | 16.44 | 0 | 0
185 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Saidpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000669/2024-2025 | 6168/MD | 05/12/2024 | 345 | ANJIMA CONSTRUCTION CO. | 22.39 | 0 | 0
186 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000048/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 20.1 | 0 | 0
187 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000084/2025-2026 | 5546/MD | 29/10/2025 | 0 | Resource Division | 3.17 | 0 | 0
188 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000158/2023-2024 | 240/MD | 10/01/2024 | 0 | Resource Division | 12.66 | 0 | 0
189 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Saidpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014263) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000491/2023-2024 | 2563/MLMD | 04/08/2023 | 787 | SUBRATA SAHA | 28.62 | 22.47 | 78
190 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Saidpur PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/001897/2023-2024 | 3004467185 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 3.87 | 3.87 | 100
191 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Saidpur PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/001898/2023-2024 | 3004467024 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 6.11 | 6.11 | 100
192 | Malda Division |  | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of BIHARI ZONE-I Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. |  |  | ORD/000130/2020-2021 | 2440/MD | 12/10/2020 | 30 | BEE GEE CONSTRUCTION | 36.34 | 31.32 | 0
193 | Malda Division |  | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIHARI ZONE-II Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. |  |  | ORD/000135/2020-2021 | 2445/MD | 12/10/2020 | 30 | M/S SABANA CONSTRUCTION | 31.87 | 33.04 | 1
194 | Malda Division |  | Laying of Parallel/ Dedicated Pipeline for better Functionality at Bihari Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000230/2025-2026 | 4234/MD | 29/08/2025 | 60 | S. R. ENTERPRISE | 12.42 | 0 | 0
195 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BIHARI ZONE-II Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000725/2023-2024 | 4774/MD | 05/12/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 10.21 | 10.2 | 98
196 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000028/2025-2026 | 2812/MD | 11/06/2025 | 0 | Resource Division | 9.75 | 0 | 0
197 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Implementation of Jotparan Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000091/2023-2024 | 1388/MAAD | 14/07/2023 | 476 | BANIK BROTHERS | 383.2 | 207.41 | 85
198 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I and Arsenic Iron Removal Plant at Jotparan Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017773) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000661/2023-2024 | 2688/MLMD | 11/08/2023 | 1074 | GHOSH BROTHERS... | 49.58 | 0 | 10
199 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Jotparan PWSS, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/001013/2023-2024 | 3004427246 | 18/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.37 | 4.37 | 100
200 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Dalal More, Gaddha More, Hindupara for Khaschandpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000009/2023-2024 | 693/MAAD | 13/04/2023 | 444 | MILLENNIUM ENTERPRISE | 87.26 | 0 | 90
201 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Khaschandpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000020/2023-2024 | 867/MAAD | 04/05/2023 | 698 | NEOGI ENTERPRISE | 168.73 | 60.34 | 85
202 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Khaschandpur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. .(2nd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000053/2023-2024 | 956/MAAD | 29/05/2023 | 583 | BEE GEE CONSTRUCTION | 218.56 | 109.16 | 85
203 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Khaschandpur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000238/2024-2025 | 1692/MAAD | 19/11/2024 | 224 | BEE GEE CONSTRUCTION | 70.37 | 0 | 0
204 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site of Khaschandpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000263/2023-2024 | 2059/MAAD | 22/11/2023 | 100 | HIRAK ROYCHOUDHURY | 5.02 | 0 | 100
205 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Khaschandpur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000318/2022-2023 | 597/MAAD | 30/03/2023 | 45 | M/S S.S. ENTERPRISE | 14.72 | 9.04 | 100
206 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Dawan Tola, Charka Tola, Maksaha Tola, Patuatola Chandpur, Haginagar Chandpur for Khaschandpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000459/2022-2023 | 575/MAAD | 28/03/2023 | 614 | M/S TRILOCHAN CONSTRUCTION CO. | 104.23 | 67.53 | 100
207 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | RTOR000011/2023-2024 | 636/MAAD | 05/04/2023 | 0 | Resource Division | 67.64 | 0 | 0
208 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Khaschandpur PWSS, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/001011/2023-2024 | 3004427011 | 18/09/2023 | 90 | W.B.S.E.D.C.LTD | 11.07 | 11.07 | 100
209 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tube Well No-I & II and Arsenic Iron Removal Plant at Khaschandpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/001731/2023-2024 | 3389/MLMD | 31/10/2023 | 1149 | GHOSH BROTHERS... | 70.55 | 0 | 0
210 | Malda Division |  | Payment for rural road damage pipe line. |  |  | BILL/00802/2024-2025 | BP-2024-25-373 | 18/11/2024 | 0 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 5 | 0 | 0
211 | Malda Division |  | Construction of Boundary Wall at 2nd Tube Well site of Dahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000126/2025-2026 | 2484/MD | 28/05/2025 | 60 | A. L. ENGINEERING SOLUTION | 6.45 | 0 | 0
212 | Malda Division |  | Construction of Boundary Wall at Head Work site of Dahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000246/2024-2025 | 3050/MD | 13/06/2024 | 654 | GOBINDA ENTERPRISE | 26.25 | 7.4 | 70
213 | Malda Division |  | Formal work order for the work of Implementation of DAHIL Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000357/2023-2024 | 3015/MD | 08/08/2023 | 1237 | GHOSH BROTHERS | 1245.3 | 483.63 | 55
214 | Malda Division |  | Construction of Boundary Wall at 3rd Tube Well Site of Dahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000666/2024-2025 | 6166/MD | 05/12/2024 | 300 | LEFT BANK CONSTRUCTION | 10.9 | 0 | 100
215 | Malda Division |  | Erection of Property board related to Jal Jeevan Mission works of Bhadar, Deotala, Mahil, Parail, Dahil & Moyna PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000951/2024-2025 | 640/MD | 19/02/2025 | 7 | S. N. CONSTRUCTION | 0.95 | 0 | 0
216 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000002/2025-2026 | 1292/MD | 03/04/2025 | 0 | Resource Division | 0.95 | 0 | 0
217 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000007/2025-2026 | 2581/MD | 30/05/2025 | 0 | Resource Division | 13.62 | 0 | 0
218 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 199/MD | 09/01/2024 | 0 | Resource Division | 13.62 | 0 | 0
219 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000198/2023-2024 | 820/MD | 21/02/2024 | 0 | Resource Division | 51.73 | 0 | 0
220 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dahil PWSS, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03214/2024-2025 | BP-2024-25-641 | 06/02/2025 | 0 | W.B.S.E.D.C.LTD | 7.48 | 0 | 0
221 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Dahil Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015609) |  |  | ORD/000352/2023-2024 | 2316/MLMD | 26/07/2023 | 120 | DEBJYOTI BASU | 43.38 | 0 | 0
222 | Malda Division |  | Laying of additional Distribution pipeline by different dia. UPVC pipe for GAZOLE ZONE-IV Piped Water Supply Scheme at Gazole Dev. Block in the District of Malda under Malda Division, PHE Dte. |  |  | ORD/000057/2025-2026 | 2257/MD | 21/05/2025 | 406 | UTTAM KUMAR GHOSH | 21.83 | 0 | 0
223 | Malda Division |  | Dismentling & Restoration of Cement Concrete road and Construction of Thrust Block for protection of pipe line within the command area for Gazole Zone-III Water Supply Scheme at Gazole Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. |  |  | ORD/000104/2025-2026 | 2275/MD | 21/05/2025 | 336 | M/S DAS CONSTRUCTION | 55.73 | 0 | 0
224 | Malda Division |  | Dismentling & Restoration of Cement Concrete road within the command area for Gazole Zone-II Water Supply Scheme at Gazole Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. |  |  | ORD/000105/2025-2026 | 2276/MD | 21/05/2025 | 240 | MILLENNIUM ENTERPRISE | 51.08 | 0 | 0
225 | Malda Division |  | Augmentation of PH-2,PH-3,PH-4 &PH-6, at GAZOLE Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000186/2025-2026 | 2955/MD | 19/06/2025 | 60 | S. M. BUILDER | 5.21 | 0 | 0
226 | Malda Division |  | Land Development, Approach Road, Boundary Wall, Improvementof Pump house for GAZOLE ZONE-III Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal |  |  | ORD/000224/2025-2026 | 4022/MD | 22/08/2025 | 195 | M/S DAS CONSTRUCTION | 55.03 | 0 | 0
227 | Malda Division |  | Additional laying of Pipe line for improvement of FHTC functionality by UPVC pipe for GAZOLE ZONE-III piped Water Supply Scheme at Gazole Dev. Block in the District of Malda under Malda Division, P.H.E.Dte. |  |  | ORD/000236/2025-2026 | 4519/MD | 12/09/2025 | 180 | M/S DAS CONSTRUCTION | 88.28 | 0 | 0
228 | Malda Division |  | Construction of Boundary Wall at Head Work site of Gazole Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000271/2024-2025 | 3200/MD | 27/06/2024 | 30 | M/S TRILOCHAN CONSTRUCTION CO | 23.16 | 0 | 100
229 | Malda Division |  | Formal work order for the work of Augmentation of GAZOLE ZONE-III Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000361/2023-2024 | 3032/MD | 09/08/2023 | 1115 | M/S DAS CONSTRUCTION | 516.04 | 96.21 | 27
230 | Malda Division |  | Formal work order for the work of Augmentation of GAZOLE ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000373/2023-2024 | 3117/MD | 11/08/2023 | 991 | M/S TRILOCHAN CONSTRUCTION CO | 405.72 | 264.79 | 60
231 | Malda Division |  | Formal work order for the work of Augmentation of Gazole Zone-IV Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000598/2023-2024 | 4326/MD | 16/10/2023 | 989 | UTTAM KUMAR GHOSH | 243.55 | 49.89 | 30
232 | Malda Division |  | Formal work order for the work of Augmentation of Gazole Zone-II Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000599/2023-2024 | 4325/MD | 16/10/2023 | 1078 | MILLENNIUM ENTERPRISR | 426.25 | 0 | 36
233 | Malda Division |  | Dedicated Pipe laying for improvement of functionality for GAZOLE ZONE-II Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000693/2025-2026 | 5923/MD | 26/11/2025 | 120 | MILLENNIUM ENTERPRISE | 94.82 | 0 | 0
234 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000722/2024-2025 | 6413/MD | 19/12/2024 | 270 | M/S TRILOCHAN CONSTRUCTION CO | 38.94 | 0 | 0
235 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000723/2024-2025 | 6414/MD | 19/12/2024 | 316 | MILLENNIUM ENTERPRISE | 73.8 | 0 | 0
236 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000724/2024-2025 | 6415/MD | 19/12/2024 | 423 | M/S DAS CONSTRUCTION | 71.69 | 0 | 0
237 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-IV Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000725/2024-2025 | 6416/MD | 19/12/2024 | 632 | UTTAM KUMAR GHOSH | 24.08 | 0 | 0
238 | Malda Division |  | Construction of Boundary Wall at Head Work Site of Gazole Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000728/2024-2025 | 6532/MD | 27/12/2024 | 447 | M/S DAS CONSTRUCTION | 19.38 | 0 | 0
239 | Malda Division |  | Erection of Property board related to Jal Jeevan Mission works of Jibjalsar, Bahirgachi, Hatnagar & Gazole PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000949/2024-2025 | 638/MD | 19/02/2025 | 7 | S. N. CONSTRUCTION | 0.95 | 0 | 0
240 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 196.39 | 0 | 0
241 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 27/MD | 04/01/2024 | 0 | Resource Division | 56.25 | 0 | 0
242 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Gazole (Zone-IV), Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02384/2025-2026 |  | 24/09/2025 | 0 | W.B.S.E.D.C.LTD | 15.83 | 0 | 0
243 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Gazole Zone-I, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03684/2023-2024 | BP-2023-24-667 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 8.1 | 0 | 0
244 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I and making compound lighting arrangement at head worksite of Gazole Zone-IV Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017388) |  |  | ORD/000668/2023-2024 | 2747/MLMD | 14/08/2023 | 1104 | BANIK BROTHERS | 13.21 | 8.94 | 67
245 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Gazol Zone-I Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. |  |  | ORD/000310/2024-2025 | 2942/MLMD | 11/09/2024 | 383 | DEY ENTERPRISE.. | 32.4 | 5.83 | 59
246 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Gazole Zone-III Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017388) |  |  | ORD/000669/2023-2024 | 2748/MLMD | 14/08/2023 | 2005 | GHOSH BROTHERS... | 40.66 | 0 | 0
247 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. IV and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Gazole Zone-II Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017388) |  |  | ORD/000751/2023-2024 | 2817/MLMD | 17/08/2023 | 2005 | H.K. DAS & CO. | 50.67 | 33.36 | 59
248 | Malda Division | Malda Mechanical Division | Placement of fund against the work for Road restoration work for laying of pipe line for Bamongala Habibpur Road (Portion from 7.00 kmp to 7.50 kmp) for Mirzapur Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | BILL/00530/2022-2023 | BP-2022-23-211 | 16/03/2023 | 0 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 3.11 | 0 | 0
249 | Malda Division | Malda Mechanical Division | Augmentation work of Pump Houses and Boundary Walls with New Construction of Boundary wall and Pump House (5.40x3.60 m) at Head work site of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000003/2025-2026 | 2413/MD | 27/05/2025 | 75 | MATIUR RAHAMAN | 38.45 | 0 | 0
250 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 300mm. Dia. x 200 mm. dia. and 140 Mtr. Deep Big dia Tube well (1 No) at Mirzapur Water Supply Scheme under Bamangola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000017/2023-2024 | 1674/MD | 18/04/2023 | 30 | A. L. ENGINEERING SOLUTION | 12.77 | 12.14 | 100
251 | Malda Division | Malda Mechanical Division | Dismentling of Concrete road and restoration of the same at different places related to laying of pipeline of Mirzapur Water Supply Scheme at Bamangola Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000075/2025-2026 | 2269/MD | 21/05/2025 | 30 | M/S KUNDU CONSTRUCTION | 35.03 | 0 | 100
252 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying Distribution pipe line for MIRZAPUR & its adjoining mouzas piped water supply at Bamongola Block in the District Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000130/2022-2023 | 1747/MD | 27/07/2022 | 60 | UTTAM KUMAR DUTTA | 163.77 | 163.77 | 100
253 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Mirzapur Piped Water Supply Scheme at Bamongola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000139/2025-2026 | 2617/MD | 02/06/2025 | 45 | ANJIMA CONSTRUCTION CO. | 13.72 | 0 | 0
254 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Mirzapur Water Supply Scheme in Bamongola block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000146/2021-2022 | 1744/MD | 15/06/2021 | 14 | HORIZEN | 2.86 | 2.28 | 1
255 | Malda Division | Malda Mechanical Division | Dismentling of Concrete road and Construction the same at different places of road connecting to LDS of Augmentation of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000152/2024-2025 | 2921/MD | 10/06/2024 | 30 | UTTAM KUMAR DUTTA | 12.53 | 12.53 | 100
256 | Malda Division | Malda Mechanical Division | Emergent work for better functionally of existing FHTC connection on different diameter Pipeline for MIRZAPUR Piped Water Supply Scheme at Bamangola Dev. Block in the District Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000194/2025-2026 | 3628/MD | 24/07/2025 | 60 | SAJEDUR RAHAMAN | 8.76 | 0 | 0
257 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) and Laying of 90 mm dia (OD) uPVC Pipeline under command area of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000224/2024-2025 | 3026/MD | 13/06/2024 | 261 | M/S KUNDU CONSTRUCTION | 89.01 | 33.68 | 90
258 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tubewell Site of Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000308/2024-2025 | 3948/MD | 07/08/2024 | 180 | GIRIDHARI CONSTRUCTION | 9.68 | 9.66 | 100
259 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 4th Tubewell Site of Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000309/2024-2025 | 3949/MD | 07/08/2024 | 45 | HIRAK ROY CHOUDHURY | 7.45 | 0 | 0
260 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 600 M3 Capacity OHR with FHTC (Mouza- Jaitan, Mirzapur, Mukuli and Salalpur) of Mirzapur Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000312/2023-2024 | 2917/MD | 31/07/2023 | 668 | MATIUR RAHAMAN | 281.67 | 265.29 | 89
261 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Mirzapur PWSS of Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000461/2023-2024 | 3394/MD | 31/08/2023 | 45 | DIPU DUTTA | 4.16 | 0 | 0
262 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 4 at Mirzapur PWSS of Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000462/2023-2024 | 3395/MD | 31/08/2023 | 45 | SARANGA SARKAR | 4.17 | 4.12 | 100
263 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of Mirzapur Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000534/2021-2022 | 2687/MD | 09/09/2021 | 7 | HORIZEN | 1.25 | 1.25 | 1
264 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 120 m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Head Work Site of Mirzapur Water Supply Scheme of Bamangola Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000601/2024-2025 | 5740/MD | 20/11/2024 | 120 | DEBAPRIYA SAHA | 45.31 | 0 | 0
265 | Malda Division | Malda Mechanical Division | Sinking of Tubewell No 3 at Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000864/2024-2025 | 1220/MD | 26/03/2025 | 45 | BABLU MANDAL | 12.17 | 0 | 0
266 | Malda Division | Malda Mechanical Division | Sinking of Tubewell No 4 at Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000865/2024-2025 | 1221/MD | 26/03/2025 | 45 | BABLU MANDAL | 12.04 | 0 | 0
267 | Malda Division | Malda Mechanical Division | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works at Mirzapur, Baherpur & Sub Surface Water based PWSS under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000937/2024-2025 | 628/MD | 19/02/2025 | 7 | RUQAIYA ENTERPRISE | 0.75 | 0 | 100
268 | Malda Division | Malda Mechanical Division | Additional Laying of different dia uPVC pipeline of Augmentation of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001031/2023-2024 | 1257/MD | 15/03/2024 | 195 | UTTAM KUMAR DUTTA | 1.88 | 0 | 100
269 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | RTOR000014/2022-2023 | 1873/MD | 16/08/2022 | 0 | Resource Division | 132.02 | 0 | 0
270 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | RTOR000018/2025-2026 | 2809/MD | 11/06/2025 | 0 | Resource Division | 30.06 | 0 | 0
271 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | RTOR000085/2025-2026 | 5552/MD | 29/10/2025 | 0 | Resource Division | 30.06 | 0 | 0
272 | Malda Mechanical | Malda Mechanical Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000086/2023-2024 | 699/MLMD | 10/04/2023 | 61 | SUBRATA SAHA | 0.29 | 0.29 | 100
273 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of Mirzapur, Bamongola C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000103/2023-2024 | 3004228411 | 26/04/2023 | 90 | W.B.S.E.D.C.LTD | 4.57 | 4.57 | 0
274 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Mirzapur, Bamongola C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000104/2023-2024 | 3004228429 | 26/04/2023 | 90 | W.B.S.E.D.C.LTD | 6.85 | 6.85 | 0
275 | Malda Mechanical | Malda Mechanical Division | Claim for purchase of fuel for hiring of inspection for different site visit use for Assistant Engineer-II ,Under Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000726/2023-2024 | 699/MLMD. | 10/04/2023 | 7 | SUBRATA SAHA | 0.46 | 0.46 | 100
276 | Malda Mechanical | Malda Mechanical Division | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of MIRZAPUR Water Supply Scheme T/W no. I in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000963/2022-2023 | 2949/MLMD | 28/12/2022 | 60 | DEY ENTERPRISE.. | 11.13 | 9.86 | 1
277 | Malda Mechanical | Malda Mechanical Division | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of MIRZAPUR Water Supply Scheme T/W no. II in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000964/2022-2023 | 2950/MLMD | 28/12/2022 | 60 | MERCURY ENGINEERING COMPANY. | 11.06 | 9.79 | 1
278 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of augmentation of MIRZAPUR Water Supply Scheme T/W no. III in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000965/2022-2023 | 2951/MLMD | 28/12/2022 | 1254 | M/S D.G.B. ENTERPRISE. | 11.25 | 8.37 | 1
279 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of augmentation of MIRZAPUR Water Supply Scheme T/W no. IV in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000966/2022-2023 | 2952/MLMD | 28/12/2022 | 811 | DILIP MAHATO. | 11.25 | 8.89 | 78
280 | Malda Mechanical | Malda Mechanical Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001147/2022-2023 | 270/MLMD | 24/02/2023 | 59 | SUBRATA SAHA | 0.29 | 0.29 | 100
281 | Malda Mechanical | Malda Mechanical Division | Claim for purchase of fuel for hiring of inspection for different site visit use for Assistant Engineer-II ,Under Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001362/2022-2023 | 270/MLMD. | 24/02/2023 | 59 | SUBRATA SAHA | 0.44 | 0.44 | 100
282 | Malda Division |  | Construction of Boundary Wall at Head Work site of Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000138/2024-2025 | 2889/MD | 07/06/2024 | 177 | USHA ENTERPRISE | 19.58 | 0 | 100
283 | Malda Division |  | Laying of Distribution system of Kaluari Piped Water Supply Scheme at Old Malda Block for west part of rail line of mouza Adatpur & Jhanjra of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000254/2024-2025 | 3190/MD | 27/06/2024 | 45 | EVEREST INFRATECH INC | 85.91 | 0 | 0
284 | Malda Division |  | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 120m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Kaluari Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. |  |  | ORD/000316/2024-2025 | 3964/MD | 07/08/2024 | 632 | USHA ENTERPRISE | 45.21 | 0 | 60
285 | Malda Division |  | Formal work order for the work of Implementation of KALUARI Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000353/2023-2024 | 3017/MD | 08/08/2023 | 1174 | USHA ENTERPRISE | 709.22 | 418.03 | 76
286 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000645/2024-2025 | 5922/MD | 26/11/2024 | 45 | USHA ENTERPRISE | 21.7 | 0 | 0
287 | Malda Division |  | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 01/01/2026 to 30/06/2026). |  |  | ORD/000851/2025-2026 | 6437/MD | 31/12/2025 | 181 | RUQAIYA ENTERPRISE | 0.86 | 0 | 0
288 | Malda Division |  | Erection of Property board related to Jal Jeevan Mission works of Sahapur, Kaluari, Sujapur, Mekpur & Mabrakpur PWSS under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000967/2024-2025 | 656/MD | 19/02/2025 | 7 | PRITAM ENTERPRISE | 0.89 | 0 | 100
289 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/001007/2023-2024 | 1190/MD | 14/03/2024 | 703 | GOBINDA ENTERPRISE | 87.47 | 0 | 0
290 | Malda Division |  | Construction of Boundary Wall at 2nd Tubewell Site of Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/001029/2023-2024 | 1255/MD | 15/03/2024 | 30 | CHARU CONSTRUCTION | 6.58 | 5.8 | 100
291 | Malda Division |  | Construction of Boundary Wall at 3rd Tubewell Site of Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/001030/2023-2024 | 1256//MD | 15/03/2024 | 30 | GOUTAM SAHA | 7.48 | 0 | 0
292 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 357/MD | 16/01/2024 | 0 | Resource Division | 76.82 | 0 | 0
293 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 819/MD | 21/02/2024 | 0 | Resource Division | 75.05 | 0 | 0
294 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Kaluari, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte |  |  | BILL/00770/2024-2025 | BP-2024-25-181 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 6.18 | 0 | 0
295 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Kaluari, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte |  |  | BILL/00771/2024-2025 | BP-2024-25-182 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.56 | 0 | 0
296 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Kaluari, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/00772/2024-2025 | BP-2024-25-183 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 8.32 | 0 | 0
297 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Kaluari Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/018421) |  |  | ORD/000677/2023-2024 | 2755/MLMD | 14/08/2023 | 1167 | HANNAN BUILDERS PVT. LTD. | 40.16 | 29.37 | 90
298 | Malda Division |  | Construction of Boundary Wall at 2nd Tube Well site of Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000181/2024-2025 | 2956/MD | 10/06/2024 | 30 | HANNAN BUILDERS PVT. LTD. | 7.92 | 0 | 0
299 | Malda Division |  | Construction of Boundary Wall at Head Work site of Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000270/2024-2025 | 3228/MD | 28/06/2024 | 30 | HANNAN BUILDERS PVT. LTD. | 27.72 | 0 | 0
300 | Malda Division |  | Formal work order for the work of Implementation of PARAHAR Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000316/2023-2024 | 2951/MD | 02/08/2023 | 1115 | HANNAN BUILDERS PVT. LTD. | 1038.77 | 658.47 | 60
301 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000633/2024-2025 | 5912/MD | 26/11/2024 | 45 | HANNAN BUILDERS PVT. LTD. | 71.72 | 0 | 0
302 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000012/2025-2026 | 2580/MD | 30/05/2025 | 0 | Resource Division | 9.19 | 0 | 0
303 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000159/2023-2024 | 239/MD | 10/01/2024 | 0 | Resource Division | 14.56 | 0 | 0
304 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 814/MD | 21/02/2024 | 0 | Resource Division | 47.82 | 0 | 0
305 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Parahar, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03696/2023-2024 | BP-2023-24-674 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.86 | 0 | 0
306 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Parahar, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03697/2023-2024 | BP-2023-24-675 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 6.41 | 0 | 0
307 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Parahar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. |  |  | ORD/000450/2024-2025 | 3730/MLMD | 26/11/2024 | 397 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 25.68 | 0 | 83
308 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 160 mm dia Pipeline at Sabjipara, Laying of rising main at Head work site and road restoration due to laying of pipe line at Chabilpara, Ailpara, Jote Daman under Jote Gopal Kagmari distribution Zone of Northern Sector under Malda Arsenic Area W/S Division, P.H.E. Dte., Malda | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000122/2024-2025 | 1253/MAAD | 24/06/2024 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.36 | 0 | 100
309 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of 150mm. big dia. Tube Well of 60 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Jote Gopal Kagmari Distribution Zone (Head Work Site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000129/2024-2025 | 1260/MAAD | 24/06/2024 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.79 | 4.63 | 100
310 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
311 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000139/2020-2021 | 1120/MAAD | 09/11/2020 | 45 | MILLENNIUM ENTERPRISE | 70.6 | 107.45 | 1
312 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Collection of House Hold Details at prescribed format in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Nagharia Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000251/2020-2021 | 88/MAAD | 15/01/2021 | 30 | M/S PARIMAL DAS | 0.52 | 1.03 | 0
313 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Transfer of funds from the account of Implementing Agencies to Singles Nodal Account (Escrow Account) under Jal Jeevan Mission. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | VCH/001219/2021-2022 | 580 | 29/03/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW ACCOUNT | 23.94 | 0 | 0
314 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Hardamnagar Water Supply Scheme at Harishchandrapur-II under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000227/2021-2022 | 2380/MD | 13/08/2021 | 30 | PARIJAT RAY | 22.39 | 20.07 | 1
315 | Malda Division | Chanchal Sub-Division | Augmentation work of Pump House and Boundary Wall of Hardamnagar Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000808/2024-2025 | 1031/MD | 18/03/2025 | 303 | ASHIS CONSTRUCTION | 17.22 | 0 | 0
316 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000064/2025-2026 | 5588/MD | 30/10/2025 | 0 | Resource Division | 5.41 | 0 | 0
317 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Road Crossing for PVC pipe line at Laxmighat Water Supply Scheme to provide FHTC under Malda Arsenic Area W/S Division P.H.E Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000096/2022-2023 | 957/MAAD | 11/05/2022 | 15 | BANIK BROTHERS | 1.99 | 1.99 | 1
318 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOPALPUR Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000173/2021-2022 | 828/MAAD | 04/06/2021 | 60 | MILLENNIUM ENTERPRISE | 170.16 | 166.29 | 1
319 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Collection of House Hold Details at prescribed format in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gopalpur,Jote Basanta,Lakshmighat Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000250/2020-2021 | 87/MAAD | 15/01/2021 | 30 | BINA CONSTRUCTION | 2.99 | 5.53 | 1
320 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JOTE BASANTA Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000288/2020-2021 | 207/MAAD | 08/02/2021 | 60 | M/S PARIMAL DAS | 112.64 | 215.03 | 1
321 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of LAKSHMIGHAT Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000289/2020-2021 | 206/MAAD | 08/02/2021 | 60 | BANIK BROTHERS | 107.79 | 197.94 | 1
322 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Jote Basanta Water Supply Scheme ( Habitation Kachari Para, Tiyor Para, Colony ,Purba Para, Lalchand Para, village Jote Basanta) at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000296/2022-2023 | 2036/MAAD | 16/11/2022 | 45 | BINA CONSTRUCTION | 7.44 | 7.15 | 1
323 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2023 to 31.12.2023) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000337/2022-2023 | 2294/MAAD | 28/12/2022 | 365 | M/S PARIMAL DAS | 1.73 | 1.85 | 100
324 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Pal Para, Budia of Jote Basanta Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000458/2021-2022 | 2033/MAAD | 29/12/2021 | 30 | M/S PARIMAL DAS | 3.98 | 3.94 | 1
325 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Budia Part of Jote Basanta Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000533/2021-2022 | 364/MAAD | 07/03/2022 | 30 | M/S PARIMAL DAS | 1.68 | 1.58 | 1
326 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Service connection Charges/ Security Deposit for Itakhola AIRP of Itakhola distribution zone under Malda Arsenic Area W/S Division. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | BILL/00238/2024-2025 | C092441964963 | 26/09/2024 | 0 | W.B.S.E.D.C.LTD | 3.81 | 0 | 0
327 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Itakhola Water Supply Scheme (Mouza- Itakhola, Habitation- Tekra) at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000032/2022-2023 | 736/MAAD | 19/04/2022 | 30 | DHRITIPALI | 2.34 | 2.26 | 1
328 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Lalapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000094/2022-2023 | 969/MAAD | 11/05/2022 | 15 | GOUTAM SAHA | 3.39 | 3.39 | 1
329 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia alongwith providing FHTCat Mahabbatpur East Zone water supply Scheme of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000095/2022-2023 | 968/MAAD | 11/05/2022 | 15 | S. R. CONSTRUCTION | 3.73 | 3.73 | 1
330 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Barachak Water Supply Scheme (Village- Parbatya) With pipe line at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000254/2022-2023 | 1832/MAAD | 27/09/2022 | 45 | DHRITIPALI | 4.22 | 4.19 | 1
331 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Lalapur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000307/2021-2022 | 1649/MAAD | 03/11/2021 | 45 | GOUTAM SAHA | 14.69 | 14.25 | 1
332 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Barachak water Supply Scheme in Gopinathpur villages within English Bazar Block in Malda District under Malda Arsenic Area Water Supply Division PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000308/2021-2022 | 1650/MAAD | 03/11/2021 | 45 | UTTAM KUMAR GHOSH | 19.1 | 16.86 | 1
333 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Itakhola Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000309/2021-2022 | 1651/MAAD | 03/11/2021 | 45 | DHRITIPALI | 7.16 | 0 | 1
334 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Itakhola Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000498/2021-2022 | 1651/MAAD | 03/11/2021 | 45 | DHRITIPALI | 10 | 6.84 | 1
335 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | RTOR000009/2021-2022 | 194/MAAD | 11/02/2022 | 0 | Resource Division | 14.54 | 0 | 0
336 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mahabbatpur (West Zone) Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000311/2021-2022 | 1653/MAAD | 03/11/2021 | 60 | USHA ENTERPRISE | 39.32 | 19.2 | 1
337 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Design, Fabrication, Supplying, Installation, Commissioning, and 3 (three) months Trial Run & 9 (nine) months Operation & Maintenance of 8 .0 CuM/Hr capacity Arsenic & Iron Elimination Plants of Gobordanga model (Pressure type) including 1 (one) Compressor Room of internal size [3.6mtr(L) x 3.00 mtr(B) x 3.15mtr(H)] and sludge disposal arrangement for Mahabbatpur (East Zone) Water Supply Scheme under Malda Arsenic Area W/S. Division, PHE Dte in the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000324/2021-2022 | 1764/MAAD | 25/11/2021 | 1346 | MERCURY ENGINEERING COMPANY | 30 | 18 | 50
338 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Talimnagar Zone-II Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000355/2021-2022 | 1724/MAAD | 18/11/2021 | 30 | S & G CONSTRUCTION | 3.82 | 3.32 | 1
339 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mahabbatpur (East Zone) Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000563/2021-2022 | 1652/MAAD | 03/11/2021 | 45 | S. R. CONSTRUCTION | 10 | 17.95 | 1
340 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
341 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) by providing branch line in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Niyamatpur ( From health sub centre towards SSK) of Niyamatpur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte.. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000263/2022-2023 | 1865/MAAD | 28/09/2022 | 45 | SUDIP DEY | 4.14 | 4.03 | 1
342 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Niamatpur Mouza of Niyamatpur Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000350/2021-2022 | 1762/MAAD | 24/11/2021 | 60 | MANIK CH. SAHA | 37.54 | 29.86 | 1
343 | Malda Division |  | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of ADHNA Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. |  |  | ORD/000055/2020-2021 | 2153/MD | 16/09/2020 | 30 | TARUN KUMAR DEY | 47.5 | 49.17 | 0
344 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Adhna Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000446/2023-2024 | 3363/MD | 29/08/2023 | 45 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 10.1 | 9.52 | 100
345 | Malda Division |  | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). |  |  | ORD/000559/2021-2022 | 522/MSD | 31/12/2021 | 2191 | UTTAM KUMAR GHOSH | 0.86 | 0 | 0
346 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Adhna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000827/2024-2025 | 842/MD | 06/03/2025 | 346 | M/S /FAIZUL HAQUE BISWAS | 30.31 | 0 | 0
347 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000005/2025-2026 | 2516/MD | 29/05/2025 | 0 | Resource Division | 7.81 | 0 | 0
348 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of GOCHIYA Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000097/2023-2024 | 2319/MD | 08/06/2023 | 365 | M/S PARIMAL DAS | 508.24 | 174.7 | 35
349 | Malda Division | Malda Mechanical Division | Sinking of 200mm. (all through) Big dia. Tube Well of 180m Deep at Head Work Site by D.R. Rig Method using P.V.C. pipe including supply of materials at GOCHIYA Water Supply Scheme of Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000651/2024-2025 | 6044/MD | 02/12/2024 | 45 | A. L. ENGINEERING SOLUTION | 10.84 | 0 | 0
350 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution pipeline in connection with Jal Jeevan Mission (JJM) at Gochiya Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000656/2024-2025 | 1259/MD | 28/03/2025 | 45 | M/S PARIMAL DAS | 48.34 | 0 | 0
351 | Malda Division | Malda Mechanical Division | Construction of Boundary,Approch road, Land development at Head Work Site and Laying of Dedicated Distribution pipe line for improvement of functionality of Gochiya Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000953/2025-2026 | 769/MD | 19/02/2026 | 60 | M/S PARIMAL DAS | 96.28 | 0 | 0
352 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000023/2023-2024 | 1608/MD | 11/04/2023 | 0 | Resource Division | 15.61 | 0 | 0
353 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000030/2022-2023 | 3042/MD | 12/12/2022 | 0 | Resource Division | 26.32 | 0 | 0
354 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of GOCHIYA PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/02540/2023-2024 | BP-2023-24-443 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.79 | 0 | 0
355 | Malda Mechanical | Malda Mechanical Division | New service connection at GOCHIYA Pwss pH NO II Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03681/2023-2024 | BP-2023-24-664 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 9.63 | 0 | 0
356 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Gochiya Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012594) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/001800/2023-2024 | 3687/MLMD | 29/11/2023 | 971 | S.P. ENTERPRISE (SILIGURI) | 26.86 | 19.53 | 80
357 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Altor Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000208/2024-2025 | 3029/MD | 13/06/2024 | 502 | SUDEB KARMAKAR | 15.69 | 0 | 0
358 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200mm. Dia ) Tube Well no-3 ( 160 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at ALTOR Water Supply Scheme of Gazole Block .under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000337/2022-2023 | 2509/MD | 03/11/2022 | 30 | A. D. D. ASSOCIATES | 9.91 | 8.39 | 100
359 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of ALTOR Water Supply Scheme of Gazole Block .under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000347/2022-2023 | 2550/MD | 03/11/2022 | 45 | SUDEB KARMAKAR | 6.69 | 6.67 | 100
360 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for ALTOR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000358/2022-2023 | 2507/MD | 03/11/2022 | 475 | M/S STAR INDIA CONSTRUTION | 40.04 | 35.34 | 1
361 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube well site of Altore Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000687/2024-2025 | 6204/MD | 09/12/2024 | 310 | MOSTAKIM ANSARI | 7.17 | 0 | 0
362 | Malda Division | Malda Mechanical Division | Augmentation of ensure proper functioning of 450 M³ capacity 20 Mtr. staging height RCC Over Head Reservoir of ALTOR Water Supply scheme under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000889/2024-2025 | 1128/MD | 21/03/2025 | 45 | GOBINDA ENTERPRISE | 8.15 | 0 | 0
363 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000017/2022-2023 | 2408/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
364 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000019/2022-2023 | 2404/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
365 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Altor, Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000294/2023-2024 | 3004279849 | 04/05/2023 | 90 | W.B.S.E.D.C.LTD | 2.87 | 2.87 | 100
366 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Altore Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012799) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000308/2023-2024 | 2310/MLMD | 26/07/2023 | 120 | JIBON GHOSH. | 11.54 | 11.22 | 100
367 | Malda Division | Malda Mechanical Division | Sinking of 200 mm ( all through) Big dia. Tube Well of 160 m Deep by D.R Rig. Method using P.V.C. pipe & Filter including Supply of materials at head work site under JIBJALSAR Water Supply Scheme of Gazole Block under Malda Division, P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000019/2025-2026 | 1691/MD | 06/05/2025 | 87 | HARUN ALL RASHID & BROTHERS | 10.09 | 0 | 100
368 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of JIBJALSAR Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000480/2022-2023 | 1126/MD | 20/03/2023 | 45 | BANIK BROTHERS | 6.57 | 6.56 | 100
369 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Implementation of JIBJALSAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000487/2022-2023 | 195/MD | 19/01/2023 | 1166 | ACHARYYA CONSTRUCTION | 25 | 19.67 | 80
370 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 180 Mtr. Deep Big dia Tube well (1 No) at JIBJALSAR Water Supply Scheme under Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000609/2022-2023 | 927/MD | 27/02/2023 | 30 | DUTTA ENTERPRISE | 10.71 | 9.54 | 100
371 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Jibjalsar Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000945/2023-2024 | 659/MD | 08/02/2024 | 631 | ACHARYYA CONSTRUCTION | 7.36 | 0 | 0
372 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000003/2023-2024 | 1580 | 10/04/2023 | 0 | Resource Division | 0.9 | 0 | 0
373 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000017/2023-2024 | 1614/MD | 11/04/2023 | 0 | Resource Division | 0.9 | 0 | 0
374 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000152/2023-2024 | 251/MD | 10/01/2024 | 0 | Resource Division | 1.03 | 0 | 0
375 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Jibjalsar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013490) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000504/2023-2024 | 2574/MLMD | 04/08/2023 | 834 | PABITRA MANDAL | 11.8 | 8.37 | 100
376 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of JIBJALSAR PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000781/2023-2024 | 3004387480 | 11/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.55 | 3.55 | 100
377 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of BETAHAL Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000294/2023-2024 | 2829/MD | 25/07/2023 | 1161 | M/S ALISA CONSTRUCTIION | 227.07 | 103.97 | 75
378 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Betahal Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000298/2024-2025 | 3444/MD | 11/07/2024 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 18.55 | 0 | 0
379 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Betahal Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000313/2024-2025 | 3953/MD | 07/08/2024 | 45 | M/S ALISA CONSTRUCTIION | 7.26 | 0 | 0
380 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of BETAHAL Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000373/2022-2023 | 2701/MD | 17/11/2022 | 30 | ASHIS CONSTRUCTION | 9.2 | 9.17 | 1
381 | Malda Division | Malda Mechanical Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at NODE POINT 246 TO 293 (DISTRIBUTION SYSTEM) between Kumedpur Station (KDPR) to Dilli Dewanganj Station (DVJ) for BETAHAL and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000476/2024-2025 | 4990/MD | 27/09/2024 | 45 | RAY CONSTRUCTION CO. | 23.18 | 0 | 0
382 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sahara Bahara Mouza of Betahal Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000735/2024-2025 | 54 | 08/01/2025 | 45 | M I CONSTRUCTION | 7.44 | 0 | 0
383 | Malda Division | Malda Mechanical Division | Laying of Distribution of UPVC Pipeline of BETAHAL Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000928/2023-2024 | 545/MD | 31/01/2024 | 517 | FUTURE | 88.28 | 61.94 | 80
384 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Sahapur, Betahal, Bejpura, Doulatpur, Talbangrua, Uttar Bhakuria PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000960/2024-2025 | 649/MD | 19/02/2025 | 7 | M/S SABANA CONSTRUCTION | 0.9 | 0 | 100
385 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000003/2024-2025 | 3916/MD | 06/08/2024 | 0 | Resource Division | 0.86 | 0 | 0
386 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000087/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 23.84 | 0 | 0
387 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000125/2023-2024 | 95/MD | 05/01/2024 | 0 | Resource Division | 7.39 | 0 | 0
388 | Malda Mechanical | Malda Mechanical Division | New service connection at Bethal PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/00756/2024-2025 | BP-2024-25-202 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 8.73 | 0 | 0
389 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II and making compound lighting arrangement at T/W no. I of Bethal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013024) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000026/2023-2024 | 784/MLMD | 27/04/2023 | 1246 | DEBAPRIYA SAHA | 26.72 | 18.98 | 84
390 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Betahal PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000093/2023-2024 | 3004232800 | 17/05/2023 | 90 | W.B.S.E.D.C.LTD | 4.96 | 4.96 | 0
391 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 Mtr. X 3.00 Mtr. Bore Hole Pump House for Tube Well No. 3 of JATRADANGA Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000241/2020-2021 | 3228MD | 28/12/2020 | 60 | M/S A. B. CONSTRUCTION | 4.74 | 4.74 | 1
392 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of JATRADANGA Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000293/2023-2024 | 2830/MD | 25/07/2023 | 270 | M/S KUNDU CONSTRUCTION | 171.22 | 70.94 | 53
393 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of JATRADANGA Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000485/2022-2023 | 1133/MD | 20/03/2023 | 45 | M/S KAMALA ENTERPRISE | 4.16 | 0 | 0
394 | Malda Division | Malda Mechanical Division | Additional Laying, Road restroration and Providing Functional Household Tap Connection (FHTC) at Jatradanga Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000498/2024-2025 | 5271/MD | 01/10/2024 | 81 | M/S KUNDU CONSTRUCTION | 28.27 | 0 | 100
395 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of JATRADANGA Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000541/2021-2022 | 2695/MD | 09/09/2021 | 7 | RADIANT | 1.25 | 1.24 | 1
396 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | RTOR000029/2023-2024 | 1809/MD | 27/04/2023 | 0 | Resource Division | 6.98 | 0 | 0
397 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | RTOR000051/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 66.49 | 0 | 0
398 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II of Augmentation of Jatradanga Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/010498) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000250/2023-2024 | 2221/MLMD | 18/07/2023 | 90 | JOY MAA SANTOSHI ENTERPRISE. | 6.42 | 0 | 0
399 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Paro Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000148/2025-2026 | 2686/MD | 04/06/2025 | 90 | VISCOUS ENGINEERS PVT. LTD. | 25.78 | 0 | 0
400 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Paro Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000166/2024-2025 | 2941/MD | 10/06/2024 | 30 | VISCOUS ENGINEERS PVT. LTD. | 8.24 | 0 | 0
401 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of PARO Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000309/2023-2024 | 2873/MD | 26/07/2023 | 980 | VISCOUS ENGINEERS PVT. LTD. | 228.95 | 112.13 | 72
402 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Paro Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000479/2024-2025 | 4994/MD | 27/09/2024 | 171 | S. R. CONSTRUCTION | 52.14 | 0 | 0
403 | Malda Division | Malda Mechanical Division | Sinking of 200mm (all through) Big dia. Tube Well of 150m Deep at 2nd Tube well site of Paro PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000788/2024-2025 | 353/MD | 30/01/2025 | 60 | ABHIJIT PAUL | 9.83 | 0 | 100
404 | Malda Division | Malda Mechanical Division | Laying of Distribution of UPVC Pipeline of PARO Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000932/2023-2024 | 598/MD | 06/02/2024 | 60 | MD. TALEB ALI | 64.62 | 54.3 | 80
405 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000018/2024-2025 | 3994/MD | 08/08/2024 | 0 | Resource Division | 7.39 | 0 | 0
406 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000089/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 12.8 | 0 | 0
407 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000132/2023-2024 | 109/MD | 05/01/2024 | 0 | Resource Division | 6.16 | 0 | 0
408 | Malda Mechanical | Malda Mechanical Division | New service connection at PARO PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/02560/2024-2025 | BP-2024-25-575 | 28/11/2024 | 0 | W.B.S.E.D.C.LTD | 4.05 | 0 | 0
409 | Malda Mechanical | Malda Mechanical Division | New service connection at PARO PWSS T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/02561/2024-2025 | BP-2024-25-576 | 28/11/2024 | 0 | W.B.S.E.D.C.LTD | 11.55 | 0 | 0
410 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Paro Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012960) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000239/2023-2024 | 2256/MLMD | 18/07/2023 | 1164 | ALPHA ENTERPRISE. | 26.3 | 0 | 43
411 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of MOBARAKPUR Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000067/2023-2024 | 2035/MD | 19/05/2023 | 1048 | SUBHAS CHANDRA KESHARI | 501.69 | 201.37 | 64
412 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Mabarakpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000168/2024-2025 | 2943/MD | 10/06/2024 | 30 | SUBHAS CHANDRA KESHARI | 8.39 | 0 | 0
413 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Mabarakpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000215/2024-2025 | 3036/MD | 13/06/2024 | 30 | SUBHAS CHANDRA KESHARI | 25.86 | 0 | 0
414 | Malda Division | Malda Mechanical Division | Dedicated/Parallel Pipe Line for better functionality and road restoration and providing balance FHTC of Mobarakpur Water Supply Scheme under Harishchandrapur -I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000691/2025-2026 | 5920/MD | 26/11/2025 | 60 | SUBHAS CHANDRA KESHARI | 28.7 | 0 | 0
415 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mabarakpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000755/2024-2025 | 73 | 13/01/2025 | 45 | SUBHAS CHANDRA KESHARI | 38.17 | 0 | 0
416 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000011/2023-2024 | 1619/MD | 11/04/2023 | 0 | Resource Division | 16.07 | 0 | 0
417 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000033/2022-2023 | 3045/MD | 12/12/2022 | 0 | Resource Division | 24.43 | 0 | 0
418 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000181/2023-2024 | 774/MD | 20/02/2024 | 0 | Resource Division | 5.54 | 0 | 0
419 | Malda Mechanical | Malda Mechanical Division | New service connection at MABARAKPURPUR Pwss pH NO II EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03676/2023-2024 | BP-2023-24-659 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 7.69 | 0 | 0
420 | Malda Mechanical | Malda Mechanical Division | New service connection at MABARAKPUR Pwss pH NO I under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03677/2023-2024 | BP-2023-24-660 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.44 | 0 | 0
421 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Mabarakpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012922) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000321/2023-2024 | 2323/MLMD | 26/07/2023 | 811 | M/S. KUNDU CONSTRACTION | 28.45 | 19.13 | 57
422 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of MABARAKPUR PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/001517/2023-2024 | 3004375733 | 01/09/2023 | 90 | W.B.S.E.D.C.LTD | 5.77 | 5.77 | 100
423 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of MABARAKPUR PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/001518/2023-2024 | 3004375650 | 01/09/2023 | 90 | W.B.S.E.D.C.LTD | 3.11 | 3.11 | 100
424 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of BAHARAL ZONE-I and II Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000362/2023-2024 | 3067/MD | 09/08/2023 | 1075 | GHOSH BROTHERS | 1160.22 | 0 | 2
425 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Baharal Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000685/2021-2022 | 650/MD | 22/03/2022 | 15 | ENVIROTECH SOLUTIONS | 4.59 | 4.59 | 100
426 | Malda Division | Malda Mechanical Division | Erection of Property board and dissemination of Property information through pipe painting related to Jal Jeevan Mission works of Bharal, Bhado, Bilaimari and Chandmoni-I & II GP under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000970/2024-2025 | 659/MD | 19/02/2025 | 7 | M/S TEWARI CONSTRUCTION | 0.97 | 0 | 0
427 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | RTOR000030/2024-2025 | 1042/MD | 18/03/2025 | 0 | Resource Division | 32.35 | 0 | 0
428 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | RTOR000071/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 90.88 | 0 | 0
429 | Malda Mechanical | Malda Mechanical Division | New service connection at Baharal PWSS Zone II T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( samsi c c c) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | BILL/02730/2024-2025 | BP-2024-25-613 | 06/02/2025 | 0 | W.B.S.E.D.C.LTD | 7 | 0 | 0
430 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Baharal (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011899) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000509/2023-2024 | 2581/MLMD | 04/08/2023 | 1143 | MERCURY ENGINEERING COMPANY. | 33.22 | 25.22 | 76
431 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Baharal (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011899) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000510/2023-2024 | 2582/MLMD | 04/08/2023 | 1160 | ANIMA ENTERPRISE | 33.36 | 25.21 | 76
432 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Rajaramchak Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000269/2024-2025 | 3227/MD | 28/06/2024 | 308 | MONDAL CONSTRUCTION | 20.25 | 0 | 0
433 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of RAJARAMCHAK Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000371/2023-2024 | 3087/MD | 10/08/2023 | 1053 | MONDAL CONSTRUCTION | 234.19 | 81.44 | 55
434 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of RAJARAMCHAK Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000682/2022-2023 | 1131/MD | 20/03/2023 | 45 | ABHIJIT PAUL | 6.57 | 5.75 | 100
435 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of RAJARAMCHAK Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000684/2022-2023 | 1136/MD | 20/03/2023 | 45 | RAJIB MANI | 4.17 | 4.14 | 100
436 | Malda Division | Malda Mechanical Division | Laying of Distribution of UPVC Pipeline of RAJARAM CHAK Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000710/2023-2024 | 4640/MD | 24/11/2023 | 857 | M/S MOON LIGHT CONSTRUCTION & CO. | 51.23 | 3.85 | 25
437 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000042/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 27.36 | 0 | 0
438 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000162/2023-2024 | 253/MD | 10/01/2024 | 0 | Resource Division | 7.85 | 0 | 0
439 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Rajaramchak, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/03685/2023-2024 | BP-2023-24-668 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.18 | 0 | 0
440 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Rajaramchak, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/03718/2023-2024 | BP-2023-24-709 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.4 | 0 | 0
441 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Rajaram Chak Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013552) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000492/2023-2024 | 2564/MLMD | 04/08/2023 | 815 | M/S. KUNDU CONSTRACTION | 28.76 | 20.65 | 88
442 | Malda Division | Malda Mechanical Division | Laying of Pipeline work for facilitating FHTC at Bahirgachi Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000145/2024-2025 | 3223/MD | 27/06/2024 | 226 | M/S NARESH KUMAR JAIN | 4.95 | 0 | 100
443 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, Pump House No.-2, Pump House No.-3, Earth filling and 3 Nos. Boundary wall at Bahirgachhi Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000184/2025-2026 | 2954/MD | 19/06/2025 | 60 | ABHIJIT PAUL | 12.95 | 0 | 0
444 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHIRGACHHI Piped Water Supply Scheme (Raikhadighi JL-23) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000697/2022-2023 | 1154/MD | 20/03/2023 | 613 | M/S KUNDU CONSTRUCTION | 46.45 | 45.14 | 80
445 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHIRGACHHI Piped Water Supply Scheme (Raikhadighi JL-24) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000704/2022-2023 | 1162/MD | 20/03/2023 | 45 | UTTAM KUMAR GHOSH | 54.79 | 49.6 | 100
446 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 (160.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at BAHIRGACHHI Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000718/2022-2023 | 1176/MD | 20/03/2023 | 30 | M/S DYNAMIC CONSTRUCTION | 10.03 | 8.79 | 100
447 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 5 (160.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at BAHIRGACHHI Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000719/2022-2023 | 1177/MD | 20/03/2023 | 30 | M/S DYNAMIC CONSTRUCTION | 10.03 | 8.05 | 100
448 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Bahirgachhi Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000729/2022-2023 | 1203/MD | 21/03/2023 | 45 | M/S. TEWARI CONSTRUCTION | 8.33 | 8.3 | 100
449 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 5th Tube Well site of Bahirgachi Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000998/2023-2024 | 1177/MD | 14/03/2024 | 30 | M/S MANDAL & SONS | 12.5 | 12.43 | 100
450 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Tubewell no. 4 site of Bahirgachi Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000999/2023-2024 | 1178/MD | 14/03/2024 | 180 | A. K. CONSTRUCTION | 17.97 | 0 | 0
451 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Tubewell no. 5 site of Bahirgachi Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001000/2023-2024 | 1179/MD | 14/03/2024 | 180 | UTTAM KUMAR GHOSH | 18 | 0 | 0
452 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 4th Tube Well site of Bahirgachi Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001023/2023-2024 | 1249/MD | 15/03/2024 | 200 | A. L. ENGINEERING SOLUTION | 9.45 | 1.8 | 100
453 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. V of Bahirgachi , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000129/2023-2024 | 3004293382 | 16/05/2023 | 90 | W.B.S.E.D.C.LTD | 3.67 | 3.67 | 34
454 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of Bahirgachi , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000130/2023-2024 | 3004293388 | 16/05/2023 | 90 | W.B.S.E.D.C.LTD | 10.01 | 10.01 | 34
455 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning & Trial operation of electro-mechanical components at T/W no IV,V,VI & VII of Source Augmentation Bahirgachi Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015614) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/002025/2023-2024 | 4764/MLMD | 29/12/2023 | 180 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 45.26 | 0 | 48
456 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Kadamtala Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000060/2023-2024 | 983/MAAD | 06/06/2023 | 665 | DIPAYAN DEY | 139.41 | 18.83 | 75
457 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Route survey & design for praparation of DPR of Kadamtola, Joteparam & Alipur Pipe Water Supply Scheme at Kaliachak-I Development Block under Malda Arsenic Area W/S Division, Phe Dte | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000230/2022-2023 | 1658/MAAD | 08/09/2022 | 10 | FUTURE | 0.99 | 0.99 | 1
458 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site and Providing Functional House Hold Tap Connection (FHTC) for Kadamtala Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000250/2024-2025 | 12/MAAD | 03/01/2025 | 60 | M/S. JHA CONSTRUCTION | 52.96 | 0 | 0
459 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 300 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Kadamtala Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (3rd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000255/2023-2024 | 1920/MAAD | 16/10/2023 | 270 | MD. TALEB ALI | 126.12 | 64.04 | 85
460 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Continuation work order for Route survey & design for praparation of DPR of Kadamtola, Joteparam & Alipur Pipe Water Supply Scheme at Kaliachak-I Development Block under Malda Arsenic Area W/S Division, Phe Dte | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000286/2022-2023 | 1669/MAAD | 12/09/2022 | 10 | FUTURE | 0.99 | 0.99 | 1
461 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Kadamtala Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000363/2022-2023 | 125/MAAD | 31/01/2023 | 45 | JOY GURU ENTERPRISE | 14.57 | 5.52 | 100
462 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System for Kadamtala Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000374/2022-2023 | 221/MAAD | 03/02/2023 | 90 | M/S. JHA CONSTRUCTION | 71 | 67.98 | 90
463 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | RTOR000009/2023-2024 | 632/MAAD | 05/04/2023 | 0 | Resource Division | 1.06 | 0 | 0
464 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I and Arsenic Iron Removal Plant at Kadamtala Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/014767) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000306/2023-2024 | 2265/MLMD | 18/07/2023 | 1074 | DEY ENTERPRISE.. | 54.08 | 40.4 | 48
465 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. of Kadamtola, Sujapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/001624/2023-2024 | 3004459313 | 11/10/2023 | 90 | W.B.S.E.D.C.LTD | 4.14 | 4.14 | 100
466 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Dakshin Mahendrapur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000175/2024-2025 | 2950/MD | 10/06/2024 | 30 | RAHANUL ALAM | 7.23 | 0 | 0
467 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Dakshin Mahendrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000220/2024-2025 | 3203/MD | 27/06/2024 | 30 | M/S EHAN ENTERPRISE | 11.45 | 0 | 0
468 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Mahendrapur Piped Water Supply scheme in Harischandrapur I Block under Malda Division PHE. Dte. (Part-I) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000560/2022-2023 | 751/MD | 17/02/2023 | 30 | RAHANUL ALAM | 11.27 | 11.22 | 100
469 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Mahendrapur Piped Water Supply scheme in Harischandrapur I Block under Malda Division PHE. Dte. (Part-II) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000567/2022-2023 | 758/MD | 17/02/2023 | 30 | M/S FOUR STAR CONSTRUCTION | 14.57 | 13.36 | 0
470 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Mahendrapur Piped Water Supply scheme in Harischandrapur I Block under Malda Division PHE. Dte. (Part-III) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000576/2022-2023 | 767/MD | 17/02/2023 | 30 | RAHANUL ALAM | 11.31 | 11.29 | 100
471 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000584/2024-2025 | 5618/MD | 06/11/2024 | 30 | RUQAIYA ENTERPRISE | 1.82 | 0 | 0
472 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 140 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of DAKSHIN MAHENDRAPUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000780/2022-2023 | 1438/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.45 | 8.39 | 95
473 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Dakhin Mahendrapur PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000905/2023-2024 | 278/MD | 11/01/2024 | 45 | S N CONSTRUCTION | 4.18 | 0 | 99
474 | Malda Division | Malda Mechanical Division | Laying of Dedicated pipe line for improvement of functionality of Dakshin Mahendrapur Piped Water Supply Scheme at harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000952/2025-2026 | 768/MD | 19/02/2026 | 60 | PRADIP KUMAR PAUL | 52.73 | 0 | 0
475 | Malda Mechanical | Malda Mechanical Division | New service connection at DAKSHIN MAHENDRAPUR T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00767/2024-2025 | BP-2024-25-193 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 6.78 | 0 | 0
476 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Dakshin Mahemdrapur Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte. (TSM/017129) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000572/2023-2024 | 2621/MLMD | 10/08/2023 | 691 | SUBRATA SAHA | 10.91 | 9.52 | 100
477 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Implementation of MATHURAPUR Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000039/2023-2024 | 1932/MD | 12/05/2023 | 1020 | A. D. ENTERPRISE | 310.11 | 111.65 | 66
478 | Malda Division | Chanchal Sub-Division | Dismentling of Concrete road and Construction the same at different places of road connecting to LDS of MATHURAPUR Water Supply Scheme ( Mouza - Mathurapur) at Chanchal-I Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000074/2025-2026 | 2268/MD | 21/05/2025 | 30 | SAHA CONSTRUCTION | 11.14 | 0 | 100
479 | Malda Division | Chanchal Sub-Division | Sinking of Tube Well, Providing FHTC, Construction of Pump House & Boundary Wall at Matiharpur Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000109/2025-2026 | 2280/MD | 21/05/2025 | 225 | M/S /FAIZUL HAQUE BISWAS | 52.25 | 0 | 0
480 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mathurapur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000514/2024-2025 | 5338/MD | 03/10/2024 | 45 | SAHA CONSTRUCTION | 63.03 | 0 | 0
481 | Malda Division | Chanchal Sub-Division | Laying of Distribution of UPVC Pipeline of MATHURAPUR Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000563/2023-2024 | 2331/MD | 08/06/2023 | 60 | SAHA CONSTRUCTION | 42.05 | 39.72 | 100
482 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Mathurapur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000866/2024-2025 | 1222/MD | 26/03/2025 | 30 | M/S MADHU CONSTRUCTION | 22.79 | 0 | 0
483 | Malda Division | Chanchal Sub-Division | Erection of Property board related to Jal Jeevan Mission works of Motiharpur and kaligram GP under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000941/2024-2025 | 630/MD | 19/02/2025 | 7 | RABIUL ISLAM | 0.8 | 0 | 100
484 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000017/2025-2026 | 2808/MD | 11/06/2025 | 0 | Resource Division | 7.49 | 0 | 0
485 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000065/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 12.83 | 0 | 0
486 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000120/2023-2024 | 90/MD | 05/01/2024 | 0 | Resource Division | 7.39 | 0 | 0
487 | Malda Mechanical | Chanchal Sub-Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of MATHURAPUR, Chanchal C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000470/2023-2024 | 3004371615 | 25/07/2023 | 90 | W.B.S.E.D.C.LTD | 9.08 | 9.08 | 100
488 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Mathurapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013453) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000497/2023-2024 | 2567/MLMD | 04/08/2023 | 1121 | DAS ENTERPRISE. | 26.54 | 11.36 | 43
489 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for DALLA Piped Water Supply Scheme (Moua-Aragacchhi, JL-No. 57) at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000736/2022-2023 | 1208/MD | 21/03/2023 | 377 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.03 | 20.79 | 100
490 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for DALLA Piped Water Supply Scheme (Mouza-Dalla, JL No. 54) at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000738/2022-2023 | 1210/MD | 21/03/2023 | 361 | TARUN KUMAR DEY | 28.46 | 26.39 | 100
491 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dalla Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000755/2022-2023 | 1303/MD | 23/03/2023 | 45 | M/S BHARATI CONSTRUCTION | 8.34 | 8.32 | 100
492 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 ( 78.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at DALLA Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000770/2022-2023 | 1428/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 6.86 | 5.98 | 100
493 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 78.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at DALLA Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000771/2022-2023 | 1429/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 6.86 | 6.17 | 100
494 | Malda Division | Malda Mechanical Division | Replacement of ( 200 mm Dia. All through) Tubewell No.-1 (75 M deep) at Head Work Site by D.R Rig. Method using P.V.C. pipe & Gravel Filter including Supply of materials at DALLA Water Supply Scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000974/2023-2024 | 871/MD | 27/02/2024 | 347 | A. L. ENGINEERING SOLUTION | 7 | 0 | 100
495 | Malda Division | Malda Mechanical Division | Devlopment of 200 mm dia. (90 Mtr. Deep) Big dia. Tube Well at Head Work Site by using suitable Air compressor at DALLA Piped Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000977/2023-2024 | 456/MD | 19/01/2024 | 7 | ABHIJIT PAUL | 0.68 | 0.68 | 100
496 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Tubewell site at Dalla Mouza of Dalla Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001018/2023-2024 | 1186/MD | 14/03/2024 | 30 | J. M. CONSTRUCTION | 11.89 | 9.92 | 75
497 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | RTOR000021/2024-2025 | 3997/MD | 08/08/2024 | 0 | Resource Division | 7.39 | 0 | 0
498 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Dalla, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | BILL/02468/2023-2024 | BP-2023-24-401 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.25 | 0 | 0
499 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III & IV of Dalla Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016720) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000560/2023-2024 | 2615/MLMD | 10/08/2023 | 180 | ANIMA ENTERPRISE | 22.09 | 22.03 | 100
500 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Dalla, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000924/2023-2024 | 3004413357 | 05/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.77 | 4.77 | 100
501 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 30m³/hr. capacity Pressure type IRON ELIMINATION Plant for providing FHTC with Construction of Blower room & backwash water disposal at Tubewell no. 3 site of Dalla Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001008/2023-2024 | 1184/MD | 14/03/2024 | 413 | MERCURY ENGINEERING COMPANY | 16.64 | 0 | 30
502 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 30m³/hr. capacity Pressure type IRON ELIMINATION Plant for providing FHTC with Construction of Blower room & backwash water disposal at Tubewell no. 4 site of Dalla Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001009/2023-2024 | 1185/MD | 14/03/2024 | 413 | MERCURY ENGINEERING COMPANY | 16.64 | 0 | 50
503 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Talsur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000173/2024-2025 | 2948/MD | 10/06/2024 | 123 | M/S ROY CONSTRUCTION | 7.81 | 3.78 | 100
504 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Talsur Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000260/2024-2025 | 3208/MD | 27/06/2024 | 368 | WATER TECH | 18.02 | 0 | 60
505 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipeline connection to Source Augmentation of Talsur Piped Water Supply scheme under Malda Division, P.H.E.Dte. (Part-I) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000562/2022-2023 | 753/MD | 17/02/2023 | 45 | M/S. TEWARI CONSTRUCTION | 48.93 | 48.8 | 98
506 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipeline connection to Source Augmentation of Talsur Piped Water Supply scheme under Malda Division PHE. Dte. (Part-II) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000571/2022-2023 | 762/MD | 17/02/2023 | 45 | M/S TRILOCHAN CONSTRUCTION CO | 93.98 | 93.55 | 98
507 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of TALSUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000583/2024-2025 | 5617/MD | 06/11/2024 | 91 | M/S ROY CONSTRUCTION | 1.26 | 0 | 99
508 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Talsur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000722/2022-2023 | 1196/MD | 21/03/2023 | 45 | M/S RAKHI ENTERPRISE | 4.18 | 4.18 | 96
509 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 150 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of TALSUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000779/2022-2023 | 1437/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 9.92 | 9.4 | 100
510 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of Talsur PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/02546/2023-2024 | BP-2023-24-447 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.26 | 0 | 0
511 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Talsur Water Supply Scheme in the District of under Malda Mechanical Division, PHE Dte.(TSM/016724) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000579/2023-2024 | 2628/MLMD | 10/08/2023 | 600 | SOVON KUMAR DAS. | 11.45 | 10.02 | 100
512 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional pipeline for Daulatpur Piped Water Supply Scheme in Harischandrapur II Block for Installation of FHTC under Malda Division PHE. Dte. (Part-I) | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000559/2022-2023 | 750/MD | 17/02/2023 | 30 | M/S FOUR STAR CONSTRUCTION | 14.54 | 14.37 | 100
513 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional pipeline Gannadia Piped Water Supply Scheme in Harischandrapur I & II Block for Installation of FHTC under Malda Division PHE. Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000561/2022-2023 | 752/MD | 17/02/2023 | 45 | PARIJAT RAY | 31.32 | 25.46 | 77
514 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional pipeline for Daulatpur Piped Water Supply Scheme in Harischandrapur II Block for Installation of FHTC under Malda Division PHE. Dte. (Part-II) | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000566/2022-2023 | 757/MD | 17/02/2023 | 30 | M/S SABANA CONSTRUCTION | 18.76 | 13.66 | 70
515 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional pipeline for Talbangura Piped Water Supply Scheme in Harischandrapur II Block for Installation of FHTC under Malda Division PHE. Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000570/2022-2023 | 761/MD | 17/02/2023 | 30 | M/S N. N. ENTERPRISE | 19.12 | 19.05 | 100
516 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional pipeline Konar Piped Water Supply Scheme in Harischandrapur I Block for Installation of FHTC under Malda Division PHE. Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000735/2022-2023 | 1214/MD | 21/03/2023 | 45 | M/S. TEWARI CONSTRUCTION | 21.7 | 21.21 | 90
517 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-IVB Piped Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000079/2023-2024 | 2094/MD | 02/06/2023 | 1153 | M/S N. C. SARKAR | 392.9 | 108.77 | 31
518 | Malda Division | Malda Mechanical Division | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (90 Mtr. Deep) for UTTAR CHANDIPUR ZONE-IVB Water Supply Scheme at T/W-1 Head Work Site of Manikchak Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000368/2023-2024 | 3057/MD | 09/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 9.17 | 8.55 | 100
519 | Malda Division | Malda Mechanical Division | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (90 Mtr. Deep) for UTTAR CHANDIPUR ZONE-IVB Water Supply Scheme at T/W-2 of Manikchak Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000369/2023-2024 | 3058/MD | 09/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 9.16 | 7.97 | 100
520 | Malda Division | Malda Mechanical Division | Formal work order for the work of Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 82.40M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-IVB Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000964/2023-2024 | 826/MD | 28/02/2024 | 480 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 197.84 | 0 | 0
521 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tubewell Site of Uttar Chandipur Zone-IV-B Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/001028/2023-2024 | 1254/MD | 15/03/2024 | 473 | A.K. AGENCY | 7.58 | 0 | 0
522 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000092/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 84.6 | 0 | 0
523 | Malda Mechanical | Malda Mechanical Division | QUOTATION PAYMENT FOR UTTARCHANDIPUR ZONE IV B T/W NO XIV UNDER MANIKCHAK CCC UNDER MALDA DISTRICT | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | BILL/01742/2024-2025 | BP-2024-25-435 | 07/08/2024 | 0 | W.B.S.E.D.C.LTD | 8.28 | 0 | 0
524 | Malda Mechanical | Malda Mechanical Division | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XIV,XV and Arsenic Iron Removal Plant at Uttar Chandipur(Zone-IV B) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019390) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000649/2023-2024 | 2683/MLMD | 11/08/2023 | 180 | A.G ENTERPRISE. | 71.71 | 0 | 0
525 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of ADINA ZONE-II Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000028/2023-2024 | 1839/MD | 02/05/2023 | 791 | M/S PARIMAL DAS | 275.44 | 140.03 | 50
526 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head work Site of Adina Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000206/2024-2025 | 3027/MD | 13/06/2024 | 80 | M/S PARIMAL DAS | 23.85 | 0 | 100
527 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Adina Zone-II Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000684/2021-2022 | 649/MD | 22/03/2022 | 15 | TECHVISION | 3.11 | 3 | 100
528 | Malda Division | Malda Mechanical Division | Augmentation of Pump House No.-2 at Adina Zone-II Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000840/2024-2025 | 1070/MD | 19/03/2025 | 60 | MAHA MAYA CONSTRUCTION | 1.81 | 0 | 0
529 | Malda Division | Malda Mechanical Division | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe for ADINA ZONE-II piped Water Supply Scheme at Gazole Dev. Block in the District of Malda under Malda Division, P.H.E.Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000993/2025-2026 | 1049/MD | 06/03/2026 | 60 | M/S PARIMAL DAS | 15.96 | 0 | 0
530 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000022/2023-2024 | 1611/MD | 11/04/2023 | 0 | Resource Division | 4.15 | 0 | 0
531 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000077/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 2.97 | 0 | 0
532 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Adina PWSS, Zone-II Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001887/2023-2024 | 3004474993 | 08/11/2023 | 90 | W.B.S.E.D.C.LTD | 5.36 | 5.36 | 100
533 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Adina Zone-II Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011890) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/002024/2023-2024 | 4763/MLMD | 29/12/2023 | 900 | M/S TRILOCHAN CONSTRUCTION CO. | 20.75 | 9.75 | 55
534 | Malda Division | Malda Mechanical Division | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB-65C/6570 for the Month of JUNE 2023 under Malda Division PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | BILL/00296/2023-2024 | BP-2023-24-159 | 18/08/2023 | 0 | UTTAM KUMAR GHOSH | 0.39 | 0 | 0
535 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of RATUA ZONE-II Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000053/2023-2024 | 1999/MD | 17/05/2023 | 960 | NIRMAN | 550.19 | 106.27 | 30
536 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 3 of Ratua Zone-II Piped Water Supply Scheme under Ratua-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000134/2025-2026 | 2508/MD | 29/05/2025 | 45 | M/S NAMITA CONSTRUCTION | 4.18 | 0 | 0
537 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Ratua Zone-II Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000600/2024-2025 | 5739/MD | 20/11/2024 | 180 | M/S TEWARI CONSTRUCTION | 72.46 | 0 | 0
538 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Ratua Zone-II Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000681/2021-2022 | 647/MD | 22/03/2022 | 15 | ENVIROTECH SOLUTIONS | 3.67 | 3.42 | 1
539 | Malda Division | Malda Mechanical Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the Assistant Engineer, Malda Division, PHE Dte. (Car-1) (Period from 01/01/2026 to 30/06/2026). | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000846/2025-2026 | 6432/MD | 31/12/2025 | 181 | UTTAM KUMAR GHOSH | 0.86 | 0 | 0
540 | Malda Division | Malda Mechanical Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the Assistant Engineer, Malda Division, PHE Dte. (Car-2) (Period from 01/01/2026 to 30/06/2026). | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000847/2025-2026 | 6433/MD | 31/12/2025 | 181 | ARUN KUMAR DAS | 0.86 | 0 | 0
541 | Malda Division | Malda Mechanical Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the Assistant Engineer, Malda Division, PHE Dte. (Period from 01/01/2025 to 30/06/2025). | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000871/2024-2025 | 6634/MD | 31/12/2024 | 181 | AMIN ENTERPRISE | 0.86 | 0 | 0
542 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Sambalpur, Gobarjona, Kadamtali & Magura PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000971/2024-2025 | 660/MD | 19/02/2025 | 7 | J. M. CONSTRUCTION | 0.73 | 0 | 0
543 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | RTOR000028/2024-2025 | 1041/MD | 18/03/2025 | 0 | Resource Division | 20.53 | 0 | 0
544 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | RTOR000070/2025-2026 | 5549/MD | 29/10/2025 | 0 | Resource Division | 1.18 | 0 | 0
545 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | RTOR000144/2023-2024 | 121/MD | 06/01/2024 | 0 | Resource Division | 54.12 | 0 | 0
546 | Malda Mechanical | Malda Mechanical Division | New service connection at RATUA (ZONE II) PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( SAMSI c c c) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | BILL/00761/2024-2025 | BP-2024-25-197 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.16 | 0 | 0
547 | Malda Mechanical | Malda Mechanical Division | New service connection at RATUA (ZONE II) PWSS T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( SAMSI c c c) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | BILL/00762/2024-2025 | BP-2024-25-198 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.6 | 0 | 0
548 | Malda Mechanical | Malda Mechanical Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000120/2024-2025 | 1200/MLMD | 02/04/2024 | 61 | SUBRATA SAHA | 0.78 | 0.76 | 100
549 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Ratua (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011274) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000507/2023-2024 | 2578/MLMD | 04/08/2023 | 1147 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 33.37 | 27.2 | 81
550 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Mahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000247/2024-2025 | 3052/MD | 13/06/2024 | 391 | J. M. CONSTRUCTION | 23.32 | 4.84 | 60
551 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000647/2024-2025 | 439/MD | 06/02/2025 | 45 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 53.22 | 0 | 0
552 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of MAHIL Piped Water Supply at Gazole Dev. Block in the District Malda under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000663/2022-2023 | 1038/MD | 13/03/2023 | 1480 | GHOSH BROTHERS | 1500.23 | 521.29 | 40
553 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000004/2023-2024 | 1583/MD | 10/04/2023 | 0 | Resource Division | 29.33 | 0 | 0
554 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000032/2023-2024 | 1804/MD | 27/04/2023 | 0 | Resource Division | 69.4 | 0 | 0
555 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000150/2023-2024 | 244/MD | 10/01/2024 | 0 | Resource Division | 23.41 | 0 | 0
556 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Mahil, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/03719/2023-2024 | BP-2023-24-708 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.96 | 0 | 0
557 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Mahil Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014388) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000383/2023-2024 | 2391/MLMD | 28/07/2023 | 824 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 42.44 | 38.43 | 91
558 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Mahil PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000718/2023-2024 | 3004390525 | 11/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.58 | 3.58 | 100
559 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Mahil PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000719/2023-2024 | 3004390616 | 11/08/2023 | 90 | W.B.S.E.D.C.LTD | 6.34 | 6.34 | 100
560 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 140 Mtr. Deep Big dia Tube well (1 Nos.) at SANJAIL Water Supply Scheme under Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000019/2023-2024 | 1676/MD | 18/04/2023 | 30 | A. L. ENGINEERING SOLUTION | 9.83 | 9.83 | 100
561 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) and Construction of Pump House in 2nd Tubewell site in connection with Jal Jeevan Mission (JJM) at Sanjail Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000174/2025-2026 | 2890/MD | 17/06/2025 | 60 | MADHUMITA ENTERPRISE | 19.36 | 0 | 0
562 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of SANJAIL & its adjoining mouza Water Scheme under Malda Division,PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000290/2022-2023 | 2236/MD | 16/09/2022 | 45 | SARIF BUILDERS | 6.14 | 6.12 | 98
563 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150mm. dia., 140 Mtr. deep Big dia Tube Well at Head Work Site by D.R. Rig method using PVC pipe & Gravel Filter including supply of Materials at Sanjail Water Supply Scheme of Old Malda Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000291/2022-2023 | 2237/MD | 16/09/2022 | 15 | M/S DEBASISH GHOSH | 8.81 | 8.44 | 100
564 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line SANJAIL its adjoining mouzas Pipe Water Supply Scheme at Old Malda Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000302/2022-2023 | 2170/MD | 21/09/2022 | 558 | M/S PARIMAL DAS | 124.75 | 123.89 | 100
565 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 100 M³ Capacity 20 mtr. staging height RCC Elevated service reservoir as per Departmental Design & drawing ( Ref FRG No-PC/-I/OHR/3/2012) including pipe connection and cost of pipes, specials delivery inlet, washout & overflow pipe etc, all complete with Geotechnical Investigation for SANJAIL Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000436/2022-2023 | 44/MD | 16/01/2023 | 180 | M/S PARIMAL DAS | 55.12 | 51.84 | 99
566 | Malda Division | Malda Mechanical Division | Emergent Earthen road restoration and earth filling exposed pipe line portion at Sanjail PWSS of Old Malda Dev. Block under Malda Division, P.H.E. Dte. In the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000766/2024-2025 | 6624 | 31/12/2024 | 30 | SARIF BUILDERS | 0.66 | 0 | 100
567 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Bamboo Pile Walling and Horizontal Road Crossing for piped water supply scheme of SANJAIL Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000789/2022-2023 | 1447/MD | 29/03/2023 | 30 | M/S PARIMAL DAS | 3.44 | 3.44 | 0
568 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Sanjail Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000886/2023-2024 | 270/MD | 11/01/2024 | 45 | M/S BHARATI CONSTRUCTION | 18.49 | 17.97 | 95
569 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of SANJAIL Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000923/2023-2024 | 455/MD | 19/01/2024 | 45 | M/S SHREE CONSORTIUM | 20.24 | 16.75 | 99
570 | Malda Division | Malda Mechanical Division | Additional UPVC pipe line for improvement of Functionality, providing balance Functional House Connection, Road restoration, land development and pathway at Head work site, Rectification of FHTC of SANJAIL Piped Water Supply Scheme under Malda Division PHE. Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000954/2025-2026 | 770/MD | 19/02/2026 | 60 | M/S PARIMAL DAS | 32.93 | 0 | 0
571 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Sanjail Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000957/2023-2024 | 705/MD | 09/02/2024 | 45 | SADHANA CONSTRUCTION | 5.8 | 0 | 65
572 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well Site of Sanjail Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/001032/2023-2024 | 1258/MD | 15/03/2024 | 443 | BINA CONSTRUCTION | 7.38 | 0 | 100
573 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | RTOR000025/2022-2023 | 2752/MD | 22/11/2022 | 0 | Resource Division | 17.38 | 0 | 0
574 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Sanjail, Old Malda CCC in the dist of Malda, Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | BILL/03566/2023-2024 | BP-2023-24-592 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 4.69 | 0 | 0
575 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Sanjail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011706) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000025/2023-2024 | 778/ MLMD | 27/04/2023 | 120 | DEVI ENTERPRISE... | 25.41 | 9.01 | 0
576 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Sanjail PWSS , Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000051/2023-2024 | 3004243252 | 27/04/2023 | 90 | W.B.S.E.D.C.LTD | 3.12 | 3.12 | 0
577 | Malda Mechanical | Malda Mechanical Division | Supply, delivery electrical accessories and installation, commissioning and trail operation of electro-mechanical components and making compound lighting arrangement at T/W no.I of Sanjail W/S Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000054/2024-2025 | 1675/MLMD | 26/06/2024 | 230 | DEVI ENTERPRISE... | 3.11 | 2.93 | 100
578 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. II of Sanjail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/002485/2023-2024 | 811/MLMD | 15/02/2024 | 180 | UTTAM KUMAR GHOSH | 10.74 | 9.01 | 83
579 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Gun Sankrul Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000058/2023-2024 | 2003/MD | 17/05/2023 | 45 | M/S. CHATTERJEE ENTERPRISE | 8.3 | 7.94 | 100
580 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Mahajibnagar Mouza under Gun Sankrul Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000148/2024-2025 | 2917/MD | 10/06/2024 | 236 | RAJIB MANI | 11.8 | 0 | 100
581 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at GUN SANKARUL Piped Water Supply Scheme (Tube Well No-3) of Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000378/2022-2023 | 2704/MD | 17/11/2022 | 30 | A. L. ENGINEERING SOLUTION | 8.52 | 8.44 | 1
582 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Pashim Banjapara-, JL- 32, Chirakuti, JL-39, Hatidubi JL-40, Bag Malancha JL-41) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000405/2022-2023 | 2988/MD | 07/12/2022 | 816 | MANAS KUMAR SAHA | 65.41 | 60.28 | 90
583 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Kuripara-, JL- 36, Bhabuk, JL-37, Paramanika JL-38) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000406/2022-2023 | 2989/MD | 07/12/2022 | 45 | KRISHNENDU DUTTA | 59.95 | 52.25 | 100
584 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 120.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at GUN SANKRUL Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000716/2022-2023 | 1174/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 8.52 | 7.66 | 100
585 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Gun Sankrul Water Supply scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000841/2024-2025 | 1069/MD | 19/03/2025 | 120 | RABIUL ISLAM | 8.08 | 0 | 100
586 | Malda Division | Malda Mechanical Division | Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Jadupur JL- 28, Kamaldighi JL-29, Dhumadighi JL-30, Gungaon JL-31, Fatepur JL-34) of Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000981/2023-2024 | 976/MD | 04/03/2024 | 211 | M/S AMIT KUMAR GUPTA | 45.81 | 42.44 | 71
587 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Bhabuk Mouza under Gun Sankrul Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001025/2023-2024 | 1251/MD | 15/03/2024 | 30 | M/S GHOSH CONSTRUCTION | 9.57 | 9.54 | 100
588 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000021/2022-2023 | 2407/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
589 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000048/2025-2026 | 5600/MD | 30/10/2025 | 0 | Resource Division | 2.24 | 0 | 0
590 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- IV of Gunsankrul, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | BILL/03512/2023-2024 | BP-2023-24-532 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 10.49 | 0 | 0
591 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Gun Sankrul PWSS , Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000052/2023-2024 | 3004243248 | 27/04/2023 | 90 | W.B.S.E.D.C.LTD | 5.61 | 5.61 | 0
592 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. IV of Source Augmentation GunSankrul Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000222/2024-2025 | 2177/MLMD | 20/08/2024 | 90 | SHREE BISHNU CONSTRUCTION | 10.62 | 10.57 | 100
593 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Gunsankrul Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014744) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001127/2022-2023 | 510/MLMD | 20/03/2023 | 180 | SHREE BISHNU CONSTRUCTION | 10.58 | 10.51 | 100
594 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of ALAL ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000048/2023-2024 | 1994/MD | 17/05/2023 | 1142 | UTTAM KUMAR DUTTA | 417.89 | 118.07 | 40
595 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of ALAL ZONE-I Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000100/2023-2024 | 2327/MD | 08/06/2023 | 60 | MD. TALEB ALI | 70.61 | 44.69 | 40
596 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Alal zone-l Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000245/2024-2025 | 3051/MD | 13/06/2024 | 713 | SAHA CONSTRUCTION | 50.08 | 16.59 | 40
597 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000262/2024-2025 | 3210/MD | 27/06/2024 | 596 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.15 | 0 | 0
598 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Alal Zone-I Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000686/2021-2022 | 651/MD | 22/03/2022 | 15 | TECHVISION | 3.42 | 3.36 | 1
599 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000715/2024-2025 | 6406/MD | 19/12/2024 | 332 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 16.46 | 0 | 0
600 | Malda Division | Malda Mechanical Division | Augmentation of Pump House-1 & Pump House-2, at ALAL Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000890/2024-2025 | 1129/MD | 21/03/2025 | 45 | ARUN MUKHERJEE | 2.42 | 0 | 0
601 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000063/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 40.31 | 0 | 0
602 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000154/2023-2024 | 246/MD | 10/01/2024 | 0 | Resource Division | 9.71 | 0 | 0
603 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Alal Zone-I, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/03717/2023-2024 | BP-2023-24-710 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.1 | 0 | 0
604 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning of electro-mechanical components at T/W no. I,II, and Supply, installation, commissioning & Trial operation of electro-mechanical components at T/W no III and making compound lighting arrangement at head worksite of Alal Zone-I Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011887) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000511/2023-2024 | 2583/MLMD | 04/08/2023 | 800 | ANIMA ENTERPRISE | 28.62 | 20.7 | 72
605 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Barkol Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000128/2025-2026 | 2485/MD | 28/05/2025 | 60 | SURAJIT MONDAL | 9.44 | 0 | 0
606 | Malda Division | RWS Malda Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000166/2020-2021 | 2719/MD | 10/11/2020 | 30 | MANAS KUMAR SAHA | 50.07 | 11.4 | 1
607 | Malda Division | RWS Malda Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000167/2020-2021 | 2720/MD | 10/11/2020 | 45 | M/S JHA CONSTRUCTION | 71.77 | 102.84 | 1
608 | Malda Division | RWS Malda Sub-Division | Sinking of 200 mm (all through) Big Dia. Tube-Well NO-02 (130 ) M Deep by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at BORKOL Water Supply Scheme of Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000454/2024-2025 | 4813/MD | 13/09/2024 | 30 | M/S DAS CONSTRUCTION | 9.07 | 0 | 100
609 | Malda Division | RWS Malda Sub-Division | Augmentation of Head work site Pump House, PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at BARKOL Water Supply scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000877/2024-2025 | 1116/MD | 21/03/2025 | 164 | FUTURE | 8.31 | 0 | 100
610 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Rajarshi Sinha, Junior Engineer | ORD/000165/2020-2021 | 2718/MD | 10/11/2020 | 30 | NIRENDRA NATH KUNDU | 58.72 | 82.4 | 1
611 | Malda Division | Chanchal Sub-Division | Extension of UPVC pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Dhanjana Madhaypara command area of Dhanjana Water Supply Scheme at Chanchal-I Block under Malda Division. PHE Dte. | Sri Susanta Saha, Assistant Engineer | Rajarshi Sinha, Junior Engineer | ORD/000611/2023-2024 | 4139/MD | 11/10/2023 | 30 | M/S BANERJEE CONSTRUCTION | 3.7 | 3.67 | 100
612 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DHANJANA Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Rajarshi Sinha, Junior Engineer | ORD/000726/2023-2024 | 4775/MD | 05/12/2023 | 45 | ANUKUL CHANDRA DAS | 7.04 | 6.63 | 100
613 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Rajarshi Sinha, Junior Engineer | RTOR000056/2025-2026 | 5597/MD | 30/10/2025 | 0 | Resource Division | 7.06 | 0 | 0
614 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Rajarshi Sinha, Junior Engineer | RTOR000109/2023-2024 | 39/MD | 04/01/2024 | 0 | Resource Division | 1.08 | 0 | 0
615 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIAGHAT Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer |  | ORD/000213/2020-2021 | 3001/MD | 10/12/2020 | 30 | A. K. CONSTRUCTION | 49.81 | 44.5 | 1
616 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer |  | RTOR000005/2024-2025 | 3917/MD | 06/08/2024 | 0 | Resource Division | 3.76 | 0 | 0
617 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer |  | RTOR000071/2025-2026 | 5535/MD | 29/10/2025 | 0 | Resource Division | 3.15 | 0 | 0
618 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90mm & 160mm dia distribution Pipeline from Firanchak to Muriwali Para for installation of FHTC under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000025/2023-2024 | 821/MAAD | 27/04/2023 | 60 | S & G CONSTRUCTION | 14.69 | 14.69 | 100
619 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sujapur Water Supply Scheme (Mouza- Chaspara) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000049/2022-2023 | 823/MAAD | 28/04/2022 | 60 | SUBHASH CHANDRA KESHARI | 52.16 | 37.86 | 100
620 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of distribution Pipe line at Bokatola, Chaspara, Brahmotra for installation of FHTC under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000086/2022-2023 | 955/MAAD | 11/05/2022 | 30 | A. K. CONSTRUCTION | 4.77 | 4.76 | 100
621 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sujapur Water Supply Scheme (Mouza- Chaspara, Habitation-Ajeiulla Biswas Para) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000145/2022-2023 | 1158/MAAD | 13/06/2022 | 45 | A. K. CONSTRUCTION | 4.79 | 4.58 | 1
622 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
623 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Chaspara, Bara Sujapur Mouzas for installation of FHTC under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000250/2022-2023 | 1828/MAAD | 27/09/2022 | 45 | A. K. CONSTRUCTION | 6.25 | 6.24 | 1
624 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying UPVC Pipe line at Chaspara under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000465/2021-2022 | 68/MAAD | 21/01/2022 | 45 | A. K. CONSTRUCTION | 4.78 | 4.77 | 100
625 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of different dia uPVC Pipe at Ajijullah Biswas Para, Makul Biswas Para near Chaspara under Sujapur distribution Zone of Southern sector under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000504/2021-2022 | 389/MAAD | 08/03/2022 | 45 | A. K. CONSTRUCTION | 14.81 | 14.46 | 1
626 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | RTOR000004/2022-2023 | 1336/MAAD | 18/07/2022 | 0 | Resource Division | 12.3 | 0 | 0
627 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sujapur Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Chota Sujapur) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000338/2021-2022 | 1747/MAAD | 24/11/2021 | 60 | A. K. CONSTRUCTION | 45.01 | 44.63 | 1
628 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90mm dia UPVC Pipe at Bishu More, Bokatola and near Naimouza Subhania High Madrasah under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000467/2021-2022 | 71/MAAD | 21/01/2022 | 45 | A. K. CONSTRUCTION | 4.81 | 4.79 | 100
629 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sadipur Water Supply Scheme (Mouza- Mobarakpur) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000055/2022-2023 | 829/MAAD | 28/04/2022 | 45 | M/S BABLU ENTERPRISE, | 11.69 | 10.08 | 1
630 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sadipur Water Supply Scheme (Mouza- Jote Anantapur, Habitation- Akandaberia, Paschim Janutola) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000119/2022-2023 | 1020/MAAD | 12/05/2022 | 45 | M/S MANDAL & SONS | 26.16 | 23.75 | 100
631 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sadipur Water Supply Scheme (Mouza- Jote Anantapur, Habitation- Bangitola) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000123/2022-2023 | 1024/MAAD | 12/05/2022 | 45 | BENGAL ENGINEERING COMPANY | 10.05 | 9.32 | 100
632 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 75 mm, 90 mm dia uPVC Pipe line at East Janutola, Barkattabad, Rishipara, Dhanuk Para, SK. Para, Bridge Para for installation of FHTC under Sadipur distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000167/2022-2023 | 1180/MAAD | 13/06/2022 | 45 | M/S TRILOCHAN CONSTRUCTION CO. | 4.83 | 4.83 | 100
633 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
634 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Sadipur Mouza for installation of FHTC under Sadipur distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000300/2022-2023 | 2040/MAAD | 16/11/2022 | 45 | M/S TRILOCHAN CONSTRUCTION CO. | 4.63 | 4.62 | 1
635 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC Pipe line at Panchkiritola for installation of FHTC under Sadipur distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000301/2022-2023 | 2041/MAAD | 16/11/2022 | 45 | M/S TRILOCHAN CONSTRUCTION CO. | 2.64 | 2.62 | 100
636 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sadipur Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Sadipur) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000336/2021-2022 | 1740/MAAD | 24/11/2021 | 60 | M/S TRILOCHAN CONSTRUCTION CO. | 56.03 | 47.35 | 1
637 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme (Mouza- Dullugram, Krishnapur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000110/2022-2023 | 1012/MAAD | 12/05/2022 | 60 | M/S ALISA CONSTRUCTION | 50.82 | 16.28 | 1
638 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme (Mouza- Khaltipur, Silampur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000111/2022-2023 | 1057/MAAD | 24/05/2022 | 60 | M/S SABANA CONSTRUCTION | 39.06 | 36.43 | 100
639 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme (Mouza- Nabinagar) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000112/2022-2023 | 1014/MAAD | 12/05/2022 | 60 | M/S ALISA CONSTRUCTION | 82.2 | 11.53 | 15
640 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 75 mm dia uPVC Pipe line at Ghoshpara, Sardar Tola, Babu Tola and Momin Para for installation of FHTC under Alinagar distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000158/2022-2023 | 1171MAAD | 13/06/2022 | 45 | M/S TRILOCHAN CONSTRUCTION CO. | 3.66 | 3.64 | 100
641 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Alinagar Mouza for installation of FHTC under Alinagar distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000245/2022-2023 | 1823MAAD | 27/09/2022 | 45 | M/S TRILOCHAN CONSTRUCTION CO. | 6.35 | 6.33 | 100
642 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Jote Dhani, Jote Param, Nabinagar, Nurnagar Mouzas for installation of FHTC under Alinagar distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000246/2022-2023 | 1824/MAAD | 27/09/2022 | 45 | M/S TRILOCHAN CONSTRUCTION CO. | 6.56 | 6.54 | 100
643 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | RTOR000001/2021-2022 | 1786/MAAD | 26/11/2021 | 0 | Resource Division | 29.65 | 0 | 0
644 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Alinagar) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000329/2021-2022 | 1741/MAAD | 24/11/2021 | 60 | M/S TRILOCHAN CONSTRUCTION CO. | 73.99 | 59.47 | 1
645 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Placing of diesel driven Car on hire basis for official use of the Executive Engineer, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2022 to 31.12.2022) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000385/2021-2022 | 2040MAAD | 29/12/2021 | 365 | NITAI PANDAY | 1.73 | 3.66 | 1
646 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
647 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Doulatpur Water Supply Scheme (Mouza- Bagbari, Doulatpur) extra pipe line at Bagbari Bundh, Doulatpur and Ganipur at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000187/2022-2023 | 1398/MAAD | 26/07/2022 | 60 | SOVON KUMAR DAS | 42.88 | 35.56 | 82
648 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Doulatpur Water Supply Scheme (Mouza- Laxmipur, Madhapur) at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000188/2022-2023 | 1399/MAAD | 26/07/2022 | 60 | PARIJAT RAY | 33.54 | 28.41 | 75
649 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Doulatpur Water Supply Scheme (Mouza- Chandipur) With pipe line at the same mouza Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000196/2022-2023 | 1534/MAAD | 05/08/2022 | 60 | SAHA CONSTRUCTION | 34 | 33.81 | 100
650 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying 63/75 mm dia Pipe at Basakpara village near Ashoke Basak house to Ramlal Chowdhury house, Protap Basak house to Shyamal Ghosh house, Sita Basak house to Ananda Basak house, Gopal Chowdhury house to Gopesh Rajak house, Suku paul house to Bijoy Mandal, Ramesh Mandal house to Sanjay Basak under Doulatpur W/S Scheme under Malda Arsenic Area W/S Division P.H.E Dte | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000208/2022-2023 | 1456/MAAD | 29/07/2022 | 45 | MAA MANASHA CONSTRUCTION | 1.68 | 1.67 | 0
651 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying UPVC pipe at Laxmighat, Laxmipur and adjoining villages for FHTC under Laxmighat Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000221/2024-2025 | 1482/MAAD | 03/09/2024 | 59 | GOUTAM SAHA | 5.4 | 1.32 | 90
652 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying UPVC pipe from PW Roads Towards Bahannabigha village for FHTC under Doulatpur Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000321/2022-2023 | 2243/MAAD | 22/12/2022 | 45 | M/S AMIT KUMAR GUPTA | 13.95 | 13.78 | 1
653 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying UPVC pipe at Bahannabigha village for FHTC under Doulatpur Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000322/2022-2023 | 2244/MAAD | 22/12/2022 | 45 | SOVON KUMAR DAS | 19.89 | 19.26 | 100
654 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying UPVC pipe at near Bagbari village for FHTC under Doulatpur Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000385/2023-2024 | 305/MAAD | 11/03/2024 | 30 | SR ENTERPRISE | 3.74 | 3.39 | 100
655 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia extra HDPE pipe at Bagbari, Doulatpur mouza for installation of FHTC under Doulatpur distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000262/2022-2023 | 1864/MAAD | 28/09/2022 | 30 | SOVON KUMAR DAS | 6.35 | 6.35 | 1
656 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanpur , Bagbari, Laxmipur, Doulatpur Mouza of Doulatpur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000340/2021-2022 | 1749/MAAD | 24/11/2021 | 60 | SOVON KUMAR DAS | 44.81 | 43.54 | 1
657 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000382/2021-2022 | 1788/MAAD | 26/11/2021 | 1 | RESOURCE DIVISION, P.H.E. DTE. | 142 | 14.2 | 0
658 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bagbari and adjoining villages under command area of Doulatpur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000382/2023-2024 | 302/MAAD | 11/03/2024 | 30 | M/S MAA TARA ENTERPRISE | 8.77 | 6.49 | 80
659 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying UPVC pipe at Rajnagar Bagbari village & adjacent areas for FHTC under Doulatpur Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000387/2023-2024 | 307/MAAD | 11/03/2024 | 30 | HIRAK ROYCHOUDHURY | 3.98 | 3.26 | 100
660 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | RTOR000004/2021-2022 | 1788/MAAD | 26/11/2021 | 0 | Resource Division | 56.12 | 0 | 0
661 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000117/2022-2023 | 1018/MAAD | 12/05/2022 | 60 | MANASH KUMAR SAHA | 69.64 | 66.7 | 1
662 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Old 16 mile,16 mile,Rameshwartola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000146/2022-2023 | 1159MAAD | 13/06/2022 | 15 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.02 | 3.99 | 1
663 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Old 16 mile,16 mile,Rameshwartola,Kamai Tola &Guruprassad Tola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000147/2022-2023 | 1160/MAAD | 13/06/2022 | 15 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.48 | 4.46 | 1
664 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at 17 Mile,17Mile rail Gate,New Tingaria,Beguntola ,Bramattatola & Kartik Tola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000148/2022-2023 | 1161MAAD | 13/06/2022 | 15 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.15 | 4.14 | 1
665 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Ghoshpara & Jallutola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000149/2022-2023 | 1162/MAAD | 13/06/2022 | 15 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.28 | 4.27 | 1
666 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Nasirtola, Guljartola, Vimagram, Mukundatola, under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000150/2022-2023 | 1163/MAAD | 13/06/2022 | 15 | M/S KUNDU CONSTRUCTION | 4.77 | 4.73 | 1
667 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Charbabupur under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000151/2022-2023 | 1164/MAAD | 13/06/2022 | 15 | MD. TALEB ALI | 4.81 | 4.8 | 1
668 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Old 16 mile under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000153/2022-2023 | 1166/MAAD | 13/06/2022 | 15 | MD. TALEB ALI | 4.54 | 4.52 | 1
669 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Tingaria under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000154/2022-2023 | 1167/MAAD | 13/06/2022 | 15 | MD. TALEB ALI | 4.41 | 4.4 | 1
670 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at New Agnutola &Charbabupur & Anarditola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000152/2022-2023 | 1165/MAAD | 13/06/2022 | 15 | MD. TALEB ALI | 4.28 | 4.27 | 1
671 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Kanchitola &VDO more under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000155/2022-2023 | 1168/MAAD | 13/06/2022 | 15 | MD. TALEB ALI | 4.4 | 4.39 | 1
672 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
673 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Gudhuyagram Village under command area of Sultanganj Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000293/2022-2023 | 2032/MAAD | 16/11/2022 | 45 | THREE BROTHERS CONSTRUCTION & CO. | 8.48 | 7.89 | 1
674 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Sultanganj,Habitation-Old 16 mile,Tingaria at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000316/2021-2022 | 1729/MAAD | 24/11/2021 | 60 | MD. TALEB ALI | 40.17 | 40.07 | 1
675 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Sultanganj,Habitation-New Tingaria,Beguntola,BramattatTola,KartikTola,Ghoshpara,Jallutola )at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000317/2021-2022 | 1731/MAAD | 24/11/2021 | 45 | M/S MOON LIGHT CONSTRUCTION & CO. | 33.14 | 33.09 | 1
676 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at lalutola, sarkartola, Birnagar,Guljartola, Jaladitola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000474/2022-2023 | 608/MAAD | 31/03/2023 | 15 | MANASH KUMAR SAHA | 5.57 | 5.54 | 0
677 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | RTOR000006/2021-2022 | 131/MAAD | 28/01/2022 | 0 | Resource Division | 6.97 | 0 | 0
678 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | RTOR000008/2021-2022 | 193/MAAD | 11/02/2022 | 0 | Resource Division | 53.98 | 0 | 0
679 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | RTOR000010/2022-2023 | 1700/MAAD | 21/09/2022 | 0 | Resource Division | 3.7 | 0 | 0
680 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Sultanganj,Habitation-Kanchitola,V.D.O more ,Agnutola,Charbabupur,Anarditola,Dinutola,Khikirbona,Kanainagar )at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000318/2021-2022 | 1730/MAAD | 24/11/2021 | 60 | MD. TALEB ALI | 38.3 | 38.25 | 1
681 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Baisnabnagar,Habitation-Old 16 mile,16 mile band,Rameshtartola,Mahajantola,KamalTola,Guruprasad Tola,17 Mile &17 mile rail Gate )at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000319/2021-2022 | 1732/MAAD | 24/11/2021 | 60 | M/S MOON LIGHT CONSTRUCTION & CO. | 48.93 | 48.83 | 1
682 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Babupur,Habitation-Nasirtola,Radhanathtola,Mukandapur,Guljartola,Hatichapa &Babupur )at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000320/2021-2022 | 1734/MAAD | 24/11/2021 | 45 | M/S KUNDU CONSTRUCTION | 33.55 | 33.46 | 1
683 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ramchandrapur Water Supply Scheme (Habitation- Ramnathpur) English Bazar Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II,Junior Engineer-III | ORD/000370/2021-2022 | 2007/MAAD | 28/12/2021 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.38 | 0.01 | 1
684 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Kamalpur Mouza (Rabidas para, Rajak para, Thakur para) under Mathurapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000097/2022-2023 | 958/MAAD | 11/05/2022 | 15 | M/S PARIMAL DAS | 4.82 | 4.81 | 1
685 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Kamalpur Mouza (Dhunia para, Pathan para, Momin para) under Mathurapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000098/2022-2023 | 959/MAAD | 11/05/2022 | 15 | M/S PARIMAL DAS | 3.26 | 3.26 | 1
686 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
687 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Repairing of pipe line by Laying of UPVC pipe line at Bistala Paschim para at Sekhpura Mouza of Mathurapur Distribution zone under Malda Arsenic Area Water Supply Division PHED. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000273/2022-2023 | 1874/MAAD | 28/09/2022 | 45 | MANIK CHOUDHURY | 5.27 | 5.26 | 1
688 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Mathurapur Mouza (Pathan para) under Mathurapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000324/2022-2023 | 2248/MAAD | 22/12/2022 | 30 | NEOGI ENTERPRISE | 4.84 | 4.84 | 1
689 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at MathurapurMouza (Dhrarmutola, Rajakpara) underMathurapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000325/2022-2023 | 2249/MAAD | 22/12/2022 | 30 | NEOGI ENTERPRISE | 4.84 | 4.84 | 1
690 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at MathurapurMouza (Kaharpara, Bochahi) underMathurapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000326/2022-2023 | 2250/MAAD | 22/12/2022 | 30 | NEOGI ENTERPRISE | 3.02 | 3.02 | 1
691 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | FHTC works for various distribution zones under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000381/2021-2022 | 1245/MAAD | 07/09/2021 | 1 | RESOURCE DIVISION, P.H.E. DTE. | 14.88 | 10.06 | 0
692 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Repairing of pipe line by Laying of UPVC pipe line at Karia Sultanpur of Mathurapur Distribution zone under Malda Arsenic Area Water Supply Division PHED. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000512/2021-2022 | 396/MAAD | 08/03/2022 | 45 | M/S STAR INDIA CONSTRUCTION | 6.78 | 6.74 | 1
693 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | RTOR000007/2021-2022 | 192/MAAD | 11/02/2022 | 0 | Resource Division | 47.26 | 0 | 0
694 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kamalpur Mouza of Mathurapur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000342/2021-2022 | 1751/MAAD | 24/11/2021 | 60 | M/S PARIMAL DAS | 59.54 | 59.5 | 1
695 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mathurapur Mouza of Mathurapur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000343/2021-2022 | 1752/MAAD | 24/11/2021 | 60 | NEOGI ENTERPRISE | 66.96 | 56.67 | 1
696 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ugritola Mouza of Mathurapur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000344/2021-2022 | 1754/MAAD | 24/11/2021 | 60 | M/S MAA TARA CONSTRUCTION | 36.86 | 35.97 | 1
697 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Karia Sultanpur Mouza of Mathurapur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000345/2021-2022 | 1758/MAAD | 24/11/2021 | 45 | M/S STAR INDIA CONSTRUCTION | 33.92 | 33.7 | 1
698 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sekhpura Mouza of Mathurapur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000380/2021-2022 | 2020/MAAD | 29/12/2021 | 60 | MANIK CHOUDHURY | 44.82 | 17.16 | 1
699 | Malda Division | Chanchal Sub-Division | Restoration of Road of KHARANGAPUR JABRA Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000210/2025-2026 | 3725/MD | 30/07/2025 | 30 | GOBINDA ENTERPRISE | 29.03 | 0 | 0
700 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Implementation of KHARANGAPUR JABRA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000232/2023-2024 | 2709/MD | 14/07/2023 | 720 | GOBINDA ENTERPRISE | 168.68 | 87.75 | 84
701 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Kharangapur Jabra Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000301/2024-2025 | 3447/MD | 11/07/2024 | 417 | GOBINDA ENTERPRISE | 29.37 | 0 | 70
702 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of KHARANGAPUR JABRA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000374/2022-2023 | 779/MD | 17/02/2023 | 30 | MERCURY ENGINEERING COMPANY | 9.2 | 9.2 | 98
703 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000057/2025-2026 | 5594/MD | 30/10/2025 | 0 | Resource Division | 3.68 | 0 | 0
704 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000074/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 11.42 | 0 | 0
705 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000133/2023-2024 | 110/MD | 05/01/2024 | 0 | Resource Division | 4.81 | 0 | 0
706 | Malda Mechanical | Chanchal Sub-Division | New service connection at KHARANGAPUR JABRA T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00766/2024-2025 | BP-2024-25-206 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.63 | 0 | 0
707 | Malda Mechanical | Chanchal Sub-Division | New service connection at KHARANGAPURJABRA PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/02562/2024-2025 | BP-2024-25-574 | 28/11/2024 | 0 | W.B.S.E.D.C.LTD | 3.75 | 0 | 0
708 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Kharangapur Jabra Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013445) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000319/2023-2024 | 2321/MLMD | 26/07/2023 | 834 | DILIP MAHATO. | 26.54 | 19.23 | 85
709 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000096/2025-2026 | 2338/MD | 22/05/2025 | 313 | M/S DAS CONSTRUCTION | 31.48 | 0 | 0
710 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000184/2024-2025 | 2959/MD | 10/06/2024 | 416 | M/S DAS CONSTRUCTION | 9.32 | 0 | 0
711 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000297/2024-2025 | 3443/MD | 11/07/2024 | 598 | M/S DAS CONSTRUCTION | 22.19 | 0 | 70
712 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of SHARANPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000368/2022-2023 | 2697/MD | 17/11/2022 | 30 | ASHIS CONSTRUCTION | 9.2 | 8.85 | 0
713 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000578/2024-2025 | 5550/MD | 29/10/2024 | 519 | M/S DAS CONSTRUCTION | 31.36 | 0 | 70
714 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of SHARANPUR Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000587/2022-2023 | 825/MD | 21/02/2023 | 1226 | M/S DAS CONSTRUCTION | 189.29 | 91.35 | 85
715 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at SAHARANPUR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000607/2022-2023 | 925/MD | 27/02/2023 | 166 | DUTTA ENTERPRISE | 10.13 | 8.9 | 100
716 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Malipakar, Dakhin Gouripur, Arjuna & Sharanpur PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000962/2024-2025 | 651/MD | 19/02/2025 | 7 | M/S SABANA CONSTRUCTION | 0.9 | 0 | 100
717 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | RTOR000001/2023-2024 | 1581 | 10/04/2023 | 0 | Resource Division | 6.65 | 0 | 0
718 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | RTOR000015/2023-2024 | 1617/MD | 11/04/2023 | 0 | Resource Division | 6.65 | 0 | 0
719 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | RTOR000036/2022-2023 | 3048/MD | 12/12/2022 | 0 | Resource Division | 17.95 | 0 | 0
720 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Sharanpur PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000302/2023-2024 | 3004302713 | 21/07/2023 | 90 | W.B.S.E.D.C.LTD | 7.5 | 7.5 | 100
721 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Sharanpur, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000421/2023-2024 | 3004368694 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.49 | 3.49 | 100
722 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Sharanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013210) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000736/2023-2024 | 2798/MLMD | 17/08/2023 | 503 | SHREE BISHNU CONSTRUCTION | 22.93 | 21.91 | 100
723 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Chhatrak Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000212/2024-2025 | 3033/MD | 13/06/2024 | 536 | M/S TRILOCHAN CONSTRUCTION CO | 26.65 | 0 | 75
724 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tubewell site of Chhatrak Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000213/2024-2025 | 3034/MD | 13/06/2024 | 30 | BIDYUT MAHALDAR | 10.41 | 0 | 0
725 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of CHHATRAK Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000369/2022-2023 | 2698/MD | 17/11/2022 | 30 | MERCURY ENGINEERING COMPANY | 9.2 | 8.82 | 0
726 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Chhatrak Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000480/2024-2025 | 4995/MD | 27/09/2024 | 45 | BIDYUT MAHALDAR | 14.99 | 0 | 0
727 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of CHHATRAK Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000594/2022-2023 | 875/MD | 22/02/2023 | 1317 | M/S TRILOCHAN CONSTRUCTION CO | 150.77 | 114.99 | 90
728 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at CHHATRAK Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000606/2022-2023 | 924/MD | 27/02/2023 | 30 | SAUDAGAR INDIA | 10.13 | 9.66 | 0
729 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000002/2023-2024 | 1584/MD | 10/04/2023 | 0 | Resource Division | 4.3 | 0 | 0
730 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000016/2023-2024 | 1613/MD | 11/04/2023 | 0 | Resource Division | 4.3 | 0 | 0
731 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000019/2024-2025 | 3995/MD | 08/08/2024 | 0 | Resource Division | 2.22 | 0 | 0
732 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000035/2022-2023 | 3047/MD | 12/12/2022 | 0 | Resource Division | 19.68 | 0 | 0
733 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Chhatrak Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012833) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000027/2023-2024 | 786/MLMD | 27/04/2023 | 914 | M/S S. S. ENTERPRISE | 25.16 | 20.05 | 85
734 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Chhatrak PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000092/2023-2024 | 3004232695 | 17/05/2023 | 90 | W.B.S.E.D.C.LTD | 5.3 | 5.3 | 0
735 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of CHHATRAK PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000301/2023-2024 | 3004302727 | 21/07/2023 | 90 | W.B.S.E.D.C.LTD | 8.02 | 8.02 | 100
736 | Malda Division | Malda Mechanical Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 4/6 to 4/7 between Old Malda Station (OLMF) to Malda Court Station (MLFC) for SAHAPUR and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/00841/2023-2024 | BP-2023-24-461 | 02/02/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 0.05 | 0 | 0
737 | Malda Division | Malda Mechanical Division | Laying of 200 mm dia HDPE water carrying pipe of chainage 327.800 of the NH-34 of Sahapur GhoshparaBypass More of Saha & Adjoining Mouza water supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/00880/2023-2024 | BP-2023-24-478 | 15/02/2024 | 0 | NATIONAL HIGHWAYS AUTHORITY OF INDIA PAYABLE AT MALDA | 0.56 | 0 | 0
738 | Malda Division | Malda Mechanical Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 4/6 to 4/7 between Old Malda Station (OLMF) to Malda Court Station (MLFC) for SAHAPUR and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/01127/2023-2024 | BP-2023-24-602 | 28/03/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 4.41 | 0 | 0
739 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of SAHAPUR Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000080/2023-2024 | 2093/MD | 02/06/2023 | 1145 | S DUTTA | 785.2 | 307.41 | 45
740 | Malda Division | Malda Mechanical Division | Formal work order for the work of Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sahapur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000136/2025-2026 | 2534/MD | 30/05/2025 | 120 | M/S DAS CONSTRUCTION | 123.11 | 0 | 0
741 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Sahapur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000203/2024-2025 | 2990/MD | 11/06/2024 | 315 | S. N. CONSTRUCTION | 24.73 | 0 | 0
742 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of SAHAPUR Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000538/2021-2022 | 2692/MD | 09/09/2021 | 7 | RADIANT | 1.72 | 1.7 | 1
743 | Malda Division | Malda Mechanical Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 4/6 to 4/7 between Old Malda Station (OLMF) to Malda Court Station (MLFC) for SAHAPUR and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000607/2023-2024 | 4111/MD | 10/10/2023 | 181 | M/S TRILOCHAN CONSTRUCTION CO | 22.05 | 0 | 0
744 | Malda Division | Malda Mechanical Division | Augmentation work of Construction of Boundary Wall at Head Work site of Sahapur Water Supply Scheme under Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000894/2024-2025 | 1224/MD | 26/03/2025 | 75 | SHREE BISHNU CONSTRUCTION | 25.15 | 0 | 0
745 | Malda Division | Malda Mechanical Division | Augmentation work of Pump House and Construction of Toilet at Head Work site Site of Sahapur Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000895/2024-2025 | 1225/MD | 26/03/2025 | 150 | M/S S. S. CONSTRUCTION | 3.73 | 0 | 0
746 | Malda Division | Malda Mechanical Division | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 1st Tube Well Site of SAHAPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000896/2024-2025 | 1226/MD | 26/03/2025 | 75 | M/S AMIT KUMAR GUPTA | 11.48 | 0 | 0
747 | Malda Division | Malda Mechanical Division | Augmentation of Boundary wall, Pump House and Construction of Toilet at 3rdd Tube Well Site of SAHAPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000897/2024-2025 | 1227/MD | 26/03/2025 | 75 | M/S AMIT KUMAR GUPTA | 5.02 | 0 | 0
748 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000021/2025-2026 | 2825/MD | 11/06/2025 | 0 | Resource Division | 23.62 | 0 | 0
749 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000055/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 104.87 | 0 | 0
750 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000186/2023-2024 | 821/MD | 21/02/2024 | 0 | Resource Division | 23.62 | 0 | 0
751 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning of electro-mechanical components at T/W no. II,III & IV of Augmentation of Sahapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013245) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000691/2023-2024 | 2766/MLMD | 14/08/2023 | 1032 | HANNAN BUILDERS PVT. LTD. | 31.15 | 26.45 | 84
752 | Malda Division | Chanchal Sub-Division | Damage pipeline | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00805/2024-2025 | BP-2024-25-378 | 18/11/2024 | 0 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 4 | 0 | 0
753 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bairat Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000094/2025-2026 | 2336/MD | 22/05/2025 | 180 | MAHA MAYA CONSTRUCTION | 26.17 | 0 | 0
754 | Malda Division | Chanchal Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 80m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Bairat Water Supply Scheme of Harishchandrapur-I Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000132/2025-2026 | 2506/MD | 29/05/2025 | 270 | USHA ENTERPRISE | 31.65 | 0 | 0
755 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Implementation of BAIRAT Piped Water Supply Scheme at Harishchandrapur-I Dev. Block of Malda District under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000534/2022-2023 | 581/MD | 09/02/2023 | 1295 | USHA ENTERPRISE | 732.14 | 589.95 | 79
756 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Bairat Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000884/2023-2024 | 160/MD | 08/01/2024 | 494 | USHA ENTERPRISE | 21.58 | 0 | 70
757 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000058/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 27.83 | 0 | 0
758 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000065/2025-2026 | 5589/MD | 30/10/2025 | 0 | Resource Division | 3.73 | 0 | 0
759 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000107/2023-2024 | 37/MD | 04/01/2024 | 0 | Resource Division | 16.2 | 0 | 0
760 | Malda Mechanical | Chanchal Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BAIRAT ,Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000293/2023-2024 | 3004353764 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 9.45 | 9.45 | 100
761 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bairat Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014439) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000374/2023-2024 | 2382/MLMD | 28/07/2023 | 1049 | M/S. KUNDU CONSTRACTION | 27.77 | 23.81 | 86
762 | Malda Mechanical | Chanchal Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Bairat, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000636/2023-2024 | 3004353771 | 08/08/2023 | 90 | W.B.S.E.D.C.LTD | 4.51 | 4.51 | 100
763 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
764 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission(JJM& Jal Swapna) at Nayagram (Baishnabnagar) under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000269/2023-2024 | 3070/MAAD | 14/12/2023 | 60 | UNITED FRIENDS UMEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD | 4.97 | 4 | 100
765 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) at Karmakarpara under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000270/2023-2024 | 3071/MAAD | 14/12/2023 | 60 | DEY CONSTRUCTIONS | 9.92 | 7.23 | 100
766 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90 mm dia & 75 mm dia UPVC pipe,Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) from 17 mile bandh to Kamartola village under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000272/2023-2024 | 3072/MAAD | 14/12/2023 | 60 | MD. TALEB ALI | 16.82 | 16.82 | 100
767 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 125 mm dia & 75 mm dia UPVC pipe,Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission(JJM& Jal Swapna) from Old 18 mile to Chamagram, Chhoto chamagram, Poladtola, Ajimtola village under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000275/2023-2024 | 3075/MAAD | 14/12/2023 | 443 | ACHARYYA CONSTRUCTION | 29.1 | 20.42 | 100
768 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at 2nd Tube Well site of Bangrua Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000188/2024-2025 | 2967/MD | 10/06/2024 | 386 | BINA CONSTRUCTION | 7.26 | 0 | 100
769 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of BANGURA Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000207/2025-2026 | 3704/MD | 29/07/2025 | 60 | M/S GHOSH CONSTRUCTION | 22.26 | 0 | 0
770 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of BANGRUA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000371/2022-2023 | 778/MD | 17/02/2023 | 30 | SAUDAGAR (INDIA) | 9.2 | 8.87 | 100
771 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Implementation of BANGRUA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000389/2023-2024 | 3289/MD | 23/08/2023 | 678 | KUNDU CONSTRUCTION | 148.48 | 0 | 65
772 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bangrua Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000573/2024-2025 | 1150/MD | 21/03/2025 | 225 | A. B. CONSTRUCTION | 26.08 | 0 | 60
773 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000017/2024-2025 | 3993/MD | 08/08/2024 | 0 | Resource Division | 3.7 | 0 | 0
774 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000088/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 6.97 | 0 | 0
775 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000124/2023-2024 | 94/MD | 05/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
776 | Malda Mechanical | Chanchal Sub-Division | New service connection at BANGRUA PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00765/2024-2025 | BP-2024-25-201 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.27 | 0 | 0
777 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bangrua Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013018) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000243/2023-2024 | 2260/MLMD | 18/07/2023 | 852 | SOUMEN ELECTRIC, | 26.41 | 20.86 | 84
778 | Malda Mechanical | Chanchal Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BANGRUA PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001018/2023-2024 | 3004401750 | 12/09/2023 | 90 | W.B.S.E.D.C.LTD | 5.47 | 5.47 | 100
779 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of CI/DI 200mm dia Pipe for overflow line & other allied works at Dharampur Distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000125/2024-2025 | 1256/MAAD | 24/06/2024 | 15 | ACHARYYA CONSTRUCTION | 1.45 | 1.35 | 60
780 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
781 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Matiharpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000154/2025-2026 | 2692/MD | 04/06/2025 | 45 | M/S ROY CONSTRUCTION | 29.35 | 0 | 0
782 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at 2nd Tube Well site of Matiharpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000189/2024-2025 | 2968/MD | 10/06/2024 | 184 | M/S ROY CONSTRUCTION | 9.24 | 0 | 99
783 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of MATIHARPUR Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000656/2022-2023 | 1010/MD | 10/03/2023 | 60 | M/S DAS CONSTRUCTION | 84.75 | 0 | 0
784 | Malda Division | Chanchal Sub-Division | Formal work order for Implementation of MATIHARPUR Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000743/2022-2023 | 1250/MD | 22/03/2023 | 1249 | RAY CONSTRUCTION CO. | 601.86 | 258.96 | 75
785 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000035/2025-2026 | 2821/MD | 11/06/2025 | 0 | Resource Division | 6.35 | 0 | 0
786 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000056/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 50.44 | 0 | 0
787 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000118/2023-2024 | 88/MD | 05/01/2024 | 0 | Resource Division | 15.4 | 0 | 0
788 | Malda Mechanical | Chanchal Sub-Division | New service connection at MOTIHARPUR PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.(CHANCHAL c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00763/2024-2025 | BP-2024-25-199 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 5.4 | 0 | 0
789 | Malda Mechanical | Chanchal Sub-Division | New service connection at motiharpur T/W no I under EE/MLMD PHE DTE Dist. malda (chanchal c. c. c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/03550/2023-2024 | BP-2023-24-563 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 9.37 | 0 | 0
790 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Matiharpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013447) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000322/2023-2024 | 2324/MLMD | 26/07/2023 | 1066 | HANNAN BUILDERS PVT. LTD. | 38.62 | 17.88 | 46
791 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Emamnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000149/2025-2026 | 2687/MD | 04/06/2025 | 225 | LAXMI ENTERPRISE | 28.8 | 0 | 0
792 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Emamnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000180/2024-2025 | 2955/MD | 10/06/2024 | 30 | MARSS INTERNATIONAL | 8.32 | 0 | 100
793 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of EMAMNAGAR Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000662/2022-2023 | 1039/MD | 13/03/2023 | 1480 | GHOSH BROTHERS | 1113.74 | 634.24 | 50
794 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Emamnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000719/2024-2025 | 6410/MD | 19/12/2024 | 466 | ABANI BHUSAN GHOSH | 52.11 | 0 | 0
795 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000009/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 113.13 | 0 | 0
796 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000151/2023-2024 | 250/MD | 10/01/2024 | 0 | Resource Division | 16.78 | 0 | 0
797 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Emamnagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014505) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000379/2023-2024 | 2387/MLMD | 28/07/2023 | 1034 | DAS ENTERPRISE. | 28.65 | 0 | 0
798 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Emamnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/001895/2023-2024 | 3004467170 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 3.8 | 3.8 | 100
799 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Emamnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/001896/2023-2024 | 3004467227 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 3.4 | 3.4 | 100
800 | Malda Division | Malda Mechanical Division | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB-04-H-8254 for the Month of MAY, JUNE and JULY 2023 under Malda Division PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | BILL/00295/2023-2024 |  | 10/08/2023 | 0 | SHABNAM ARA | 1.18 | 0 | 0
801 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of RATUA ZONE-I Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000069/2023-2024 | 2042/MD | 19/05/2023 | 1254 | STARCO CONSTRUCTIONS | 853.24 | 367.11 | 60
802 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Ratua Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000675/2024-2025 | 6200/MD | 09/12/2024 | 45 | UTTAM KUMAR GHOSH | 7.56 | 0 | 100
803 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Ratua Zone-I Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000680/2021-2022 | 646/MD | 22/03/2022 | 15 | ENVIROTECH SOLUTIONS | 4.4 | 4.17 | 1
804 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Ratua Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000689/2024-2025 | 6206/MD | 09/12/2024 | 45 | RAJA CONSTRUCTION | 4.51 | 0 | 0
805 | Malda Division | Malda Mechanical Division | Dismantling of abandoned room at Head work site of Ratua-I PWSS under Ratua-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000951/2023-2024 | 654/MD | 08/02/2024 | 30 | M/S. TEWARI CONSTRUCTION | 1.93 | 0 | 100
806 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Ratua Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/001015/2023-2024 | 1517/MD | 16/03/2024 | 835 | UTTAM KUMAR GHOSH | 79.16 | 0 | 0
807 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | RTOR000031/2024-2025 | 1040/MD | 18/03/2025 | 0 | Resource Division | 27.65 | 0 | 0
808 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | RTOR000066/2025-2026 | 5587/MD | 30/10/2025 | 0 | Resource Division | 0.62 | 0 | 0
809 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | RTOR000067/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 80.51 | 0 | 0
810 | Malda Mechanical | Malda Mechanical Division | New service connection at Ratua PWSS Zone I T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( Samsi c c c) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | BILL/02731/2024-2025 | BP-2024-25-614 | 09/01/2025 | 0 | W.B.S.E.D.C.LTD | 6.31 | 0 | 0
811 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Ratua (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011269) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000508/2023-2024 | 2579/MLMD | 04/08/2023 | 1147 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 33.64 | 27.62 | 87
812 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Augmentation of PUKHURIA Piped Water Supply Scheme at Ratua-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000062/2023-2024 | 2022/MD | 18/05/2023 | 1137 | DUTTA ENTERPRISE | 957.93 | 467.08 | 60
813 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Pukuria Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000167/2025-2026 | 5794/MD | 13/11/2025 | 60 | DUTTA ENTERPRISE | 117.25 | 0 | 0
814 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at 3rd Tube Well site of Pukuria Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000190/2024-2025 | 2969/MD | 10/06/2024 | 327 | M/S A. B. CONSTRUCTION | 7.13 | 0 | 75
815 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at 4th Tube Well site of Pukuria Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000315/2024-2025 | 3955/MD | 07/08/2024 | 45 | MAHA MAYA CONSTRUCTION | 7.12 | 0 | 100
816 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000694/2021-2022 | 659/MD | 22/03/2022 | 15 | ECO CARE | 3.71 | 3.71 | 1
817 | Malda Division | Chanchal Sub-Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 2 at Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000942/2023-2024 | 651/MD | 08/02/2024 | 45 | CHAKRABORTY & MANDAL ENTERPRISE | 4.76 | 0 | 100
818 | Malda Division | Chanchal Sub-Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 1 at Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000950/2023-2024 | 652/MD | 08/02/2024 | 45 | J. M. CONSTRUCTION | 4.76 | 0 | 0
819 | Malda Division | Chanchal Sub-Division | Erection of Property board related to Jal Jeevan Mission works of Paharpur, Sultanpur, Pukuria PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000972/2024-2025 | 661/MD | 19/02/2025 | 7 | J. M. CONSTRUCTION | 0.73 | 0 | 0
820 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000029/2024-2025 | 1039/MD | 18/03/2025 | 0 | Resource Division | 24.64 | 0 | 0
821 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000068/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 120.24 | 0 | 0
822 | Malda Mechanical | Chanchal Sub-Division | New service connection at pukuria PWSS T/W NO Iv Under EE/MLMD PHE DTE DIST. Malda.( paranpur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/02203/2024-2025 | BP-2024-25-523 | 26/09/2024 | 0 | W.B.S.E.D.C.LTD | 4.96 | 0 | 0
823 | Malda Mechanical | Chanchal Sub-Division | New service connection at PUKURIA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( Paranpur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/02204/2024-2025 | BP-2024-25-524 | 26/09/2024 | 0 | W.B.S.E.D.C.LTD | 4.77 | 0 | 0
824 | Malda Mechanical | Chanchal Sub-Division | Name of Work: Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II,III & IV and making compound lighting arrangement at Head worksite of Pukuria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011879) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000515/2023-2024 | 2580/MLMD | 04/08/2023 | 1147 | DEY ENTERPRISE.. | 44.39 | 37.04 | 92
825 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jigin Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000127/2025-2026 | 2509/MD | 29/05/2025 | 60 | ARKADEEP ENTERPRISE | 7.24 | 0 | 0
826 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of JIGIN Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000483/2022-2023 | 1129/MD | 20/03/2023 | 45 | JOYDEB SENGUPTA | 6.58 | 5.92 | 100
827 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of JIGIN Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000685/2022-2023 | 1134/MD | 20/03/2023 | 45 | M/S ROY CONSTRUCTION | 4.21 | 4.19 | 100
828 | Malda Division | Malda Mechanical Division | Formal work order for Implementation of JIGIN Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000741/2022-2023 | 1251/MD | 22/03/2023 | 590 | GOBINDA ENTERPRISE | 88.5 | 60.98 | 100
829 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000050/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 34.75 | 0 | 0
830 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Jigin Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015837) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000317/2023-2024 | 2319/MLMD | 26/07/2023 | 525 | RMD TRADING. | 26.24 | 19.04 | 78
831 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Jigin PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000779/2023-2024 | 3004387515 | 18/08/2023 | 90 | W.B.S.E.D.C.LTD | 6.63 | 6.63 | 100
832 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Jigin PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000780/2023-2024 | 3004387500 | 18/08/2023 | 90 | W.B.S.E.D.C.LTD | 10.6 | 10.6 | 100
833 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Kankot Water Supply Scheme in Ratua I Block for Installation of FHTC under Malda Division PHE. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000563/2022-2023 | 754/MD | 17/02/2023 | 30 | PRITAM ENTERPRISE | 4.76 | 4.63 | 0
834 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Kankot Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000724/2022-2023 | 1198/MD | 21/03/2023 | 45 | PRITAM ENTERPRISE | 4.16 | 0 | 0
835 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 138 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of KANKOT Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000777/2022-2023 | 1435/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.68 | 0 | 0
836 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Kankot Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte.(TSM/017203) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000574/2023-2024 | 2623/MLMD | 10/08/2023 | 1051 | M/S SABANA CONSTRUCTION | 11.44 | 9.93 | 87
837 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of ARJUNA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000194/2024-2025 | 2898/MD | 07/06/2024 | 239 | SK ENTERPRISE | 1.41 | 0 | 100
838 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipeline connection to Source Augmentation of Arjuna Piped Water Supply scheme at Harishchandrapur-II under Malda Division, P.H.E.Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000564/2022-2023 | 755/MD | 17/02/2023 | 30 | GHOSH CONSTRUCTION | 15.53 | 15.5 | 0
839 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arjuna Mouza of Arjuna Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000734/2024-2025 | 10 | 03/01/2025 | 45 | TWO BROTHERS CONSTRUCTION | 10.01 | 0 | 0
840 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Arjuna Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000749/2022-2023 | 1297/MD | 23/03/2023 | 45 | SAYEM ENTERPRISE | 4.2 | 0 | 100
841 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 138 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of ARJUNA Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000775/2022-2023 | 1433/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.68 | 8.68 | 100
842 | Malda Division | Malda Mechanical Division | Augmentation work of OHR, Pump House and Boundary Wall of Arjuna Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000860/2024-2025 | 1053/MD | 18/03/2025 | 75 | M/S KUNDU CONSTRUCTION | 28.76 | 0 | 0
843 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Arjuna PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/02547/2023-2024 | BP-2023-24-448 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.4 | 0 | 0
844 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Arjuna Water Supply Scheme in the District of under Malda Mechanical Division, PHE Dte.(TSM/016722) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000564/2023-2024 | 2617/MLMD | 10/08/2023 | 600 | NEOGI ENTERPRISE. | 10.92 | 8.12 | 100
845 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Rising main and Construction of Pump houses for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000029/2023-2024 | 1840/MD | 02/05/2023 | 45 | SARIF BUILDERS | 12.75 | 6.11 | 100
846 | Malda Division | RWS Malda Sub-Division | Dismantling of concrete for the laying of Distribution system through the concrete roads within Aiho Zone-I Piped Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000491/2024-2025 | 5004/MD | 27/09/2024 | 45 | M/S FRIENDS CONSTRUCTION & CO. | 19.96 | 4.46 | 90
847 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Distribution system for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000554/2022-2023 | 1179/MD | 21/03/2023 | 710 | M/S STAR INDIA CONSTRUTION | 85.22 | 77.39 | 100
848 | Malda Division | RWS Malda Sub-Division | Construction of R.C.C. Culvert (Approach) infront of Head Works Site of AIHO ZONE-I Piped Water Supply Scheme under Malda Division PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000613/2023-2024 | 4142/MD | 11/10/2023 | 30 | M/S STAR INDIA CONSTRUTION | 1.12 | 1.11 | 100
849 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Aiho Zone-I Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000659/2024-2025 | 1260/MD | 28/03/2025 | 134 | SIVRAM ENTERPRISE | 17.36 | 0 | 0
850 | Malda Division | RWS Malda Sub-Division | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe, Rectification of FHTC & Providing FHTC for AIHO ZONE-I piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, P.H.E.Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000671/2025-2026 | 1047/MD | 06/03/2026 | 60 | M/S /FAIZUL HAQUE BISWAS | 66.79 | 0 | 0
851 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 150 cum capacity 20 mtr. Staging height RCC OHR and Providing Household Tap Connection (FHTC) for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000672/2022-2023 | 1211/MD | 22/03/2023 | 710 | M/S FRIENDS CONSTRUCTION & CO. | 91.59 | 84.48 | 65
852 | Malda Division | RWS Malda Sub-Division | Concreting the dismantled portion of road which dismantled for the purpose of laying of Distribution system through the concrete roads within Aiho Zone-I Piped Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000776/2024-2025 | 435/MD | 06/02/2025 | 30 | M/S FRIENDS CONSTRUCTION & CO. | 54.64 | 0 | 100
853 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at AIHO ZONE-1 Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000984/2023-2024 | 979/MD | 04/03/2024 | 45 | S. R. CONSTRUCTION | 28.24 | 23.07 | 100
854 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | RTOR000067/2025-2026 | 5586/MD | 30/10/2025 | 0 | Resource Division | 8.7 | 0 | 0
855 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | RTOR000080/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 8.74 | 0 | 0
856 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Augmentation of Aiho(zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017676) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000583/2023-2024 | 2632/MLMD | 10/08/2023 | 697 | MUKHERJEE ART CENTRE | 25.83 | 0 | 0
857 | Malda Division | Malda Sadar Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHERPUR ZONE-I Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000588/2022-2023 | 828/MD | 21/02/2023 | 45 | M/S PARIMAL DAS | 82.32 | 82.32 | 98
858 | Malda Division | Malda Sadar Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHERPUR ZONE-II Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000589/2022-2023 | 1159/MD | 20/03/2023 | 45 | KRISHNENDU DUTTA | 59.38 | 52.04 | 85
859 | Malda Division | Malda Sadar Sub-Division | Augmentation of Boundary Walls and Construction of Switch Room of size 3.60 x 3.0 M of BAHERPUR ( ZONE I & II) Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000707/2024-2025 | 6389/MD | 18/12/2024 | 45 | PABITRA MANDAL | 21.71 | 0 | 0
860 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-II Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000150/2024-2025 | 2919/MD | 10/06/2024 | 386 | M/S N. C. SARKAR | 34.1 | 0 | 0
861 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-II Piped Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000382/2023-2024 | 3238/MD | 22/08/2023 | 1042 | M/S N. C. SARKAR | 442.76 | 0 | 25
862 | Malda Division | Malda Mechanical Division | Construction of Approach Road at Head Work site of Uttar Chandipur Zone-II Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000893/2023-2024 | 272/MD | 11/01/2024 | 264 | M/S N. C. SARKAR | 3.91 | 0 | 100
863 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 92.00M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-II Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000994/2023-2024 | 1278/MD | 15/03/2024 | 240 | DEBAPRIYA SAHA | 210.87 | 0 | 0
864 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000058/2025-2026 | 5595/MD | 30/10/2025 | 0 | Resource Division | 3.08 | 0 | 0
865 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000094/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 144.69 | 0 | 0
866 | Malda Mechanical | Malda Mechanical Division | QUOTATION PAYMENT FOR UTTAR CHANDIPUR ZONE II TW NO XII UNDER MANIKCHAK CCC UNDER MALDA DISTRICT | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | BILL/01684/2024-2025 | BP-2024-25-414 | 30/07/2024 | 0 | W.B.S.E.D.C.LTD | 6.98 | 0 | 0
867 | Malda Mechanical | Malda Mechanical Division | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XII and Arsenic Iron Removal Plant at Uttar Chandipur (Zone-II) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019387) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000640/2023-2024 | 2680/MLMD | 11/08/2023 | 180 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 60.44 | 3.02 | 50
868 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Augmentation of BHINGOLE Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000084/2023-2024 | 2321/MD | 08/06/2023 | 365 | M/S. TEWARI CONSTRUCTION | 123.04 | 62.58 | 87
869 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Bhingole Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000300/2024-2025 | 3446/MD | 11/07/2024 | 30 | M/S TEWARI CONSTRUCTION | 37.37 | 0 | 0
870 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bhingole Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000500/2024-2025 | 5404/MD | 21/10/2024 | 45 | MAHA MAYA CONSTRUCTION | 21.72 | 0 | 0
871 | Malda Division | Chanchal Sub-Division | Augmentation work of Pump House and Boundary Wall of Bhingole Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000847/2024-2025 | 1033/MD | 18/03/2025 | 75 | BINA CONSTRUCTION | 10.95 | 0 | 0
872 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000021/2023-2024 | 1610/MD | 11/04/2023 | 0 | Resource Division | 4.52 | 0 | 0
873 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000083/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 8.78 | 0 | 0
874 | Malda Mechanical | Chanchal Sub-Division | New service connection at BHINGOL T/W NO IV Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00768/2024-2025 | BP-2024-25-189 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.65 | 0 | 0
875 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no.II & IV and making compound lighting arrangement at H/W site Augumentation of Bhingal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017675) | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000637/2023-2024 | 2736/MLMD | 14/08/2023 | 180 | SHREE BISHNU CONSTRUCTION | 22.69 | 0 | 0
876 | Malda Mechanical | Chanchal Sub-Division | Supply, installation & commissioning of electro-mechanical components at T/W no. I, Augmentation of Bhingal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017675) | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000701/2023-2024 | 2722/MLMD | 14/08/2023 | 180 | CHOWDHURY CONCERN | 4.42 | 4.42 | 100
877 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of ADINA ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000119/2023-2024 | 2322/MD | 08/06/2023 | 1110 | M/S TRILOCHAN CONSTRUCTION CO | 348.95 | 103.12 | 35
878 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 30m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal and Construction of Boundary wall at 2nd TW site, Approach Raod at HW & 2nd TW site at Adina Zone-I Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000234/2025-2026 | 4238/MD | 29/08/2025 | 300 | VISCOUS ENGINEERS PVT. LTD. | 45.87 | 0 | 0
879 | Malda Division | Malda Mechanical Division | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe & Providing FHTC for ADINA ZONE-I piped Water Supply Scheme at Gazole Dev. Block in the District of Malda under Malda Division, P.H.E.Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000235/2025-2026 | 4518/MD | 12/09/2025 | 120 | M/S TRILOCHAN CONSTRUCTION CO | 40.45 | 0 | 0
880 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Adina Zone-I Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000683/2021-2022 | 648/MD | 22/03/2022 | 15 | TECHVISION | 3.04 | 3.01 | 1
881 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Adina Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000888/2023-2024 | 162/MD | 08/01/2024 | 219 | M/S PARIMAL DAS | 21.89 | 0 | 85
882 | Malda Division | Malda Mechanical Division | Continuation work order Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 15/12/2024 to 31/12/2024). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001032/2024-2025 | 6291/MD | 11/12/2024 | 17 | RUQAIYA ENTERPRISE | 0.08 | 0.18 | 0
883 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000075/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 34.17 | 0 | 0
884 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Adina Zone-I, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | BILL/03698/2023-2024 | BP-2023-24-676 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 8.67 | 0 | 0
885 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Adina Zone-I Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011889) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000599/2023-2024 | 2719/MLMD | 14/08/2023 | 2005 | SUNRISE ENGINEERING CORPORATION. | 28.74 | 0 | 0
886 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Mobarakpur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000128/2023-2024 | 1471/MAAD | 01/08/2023 | 45 | A ONE ENTERPRISE | 14.79 | 9.03 | 100
887 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Mobarakpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000130/2023-2024 | 1472/MAAD | 01/08/2023 | 366 | M/S EHAN ENTERPRISE | 5.02 | 0 | 100
888 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Chowdhuri Tola for Mobarakpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000131/2023-2024 | 1473/MAAD | 01/08/2023 | 90 | A. K. CONSTRUCTION | 43.94 | 36.6 | 95
889 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Jahantola, Narasinghatola, Rabiramtola for Mobarakpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000132/2023-2024 | 1474/MAAD | 01/08/2023 | 425 | GOBINDA ENTERPRISE | 42.15 | 30.07 | 92
890 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Mobarakpur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000242/2024-2025 | 1696/MAAD | 19/11/2024 | 224 | BINA CONSTRUCTION | 66.6 | 0 | 0
891 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Mobarakpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(3rd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000278/2023-2024 | 3080/MAAD | 14/12/2023 | 565 | M/S PARIMAL DAS | 168.04 | 8.55 | 80
892 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Mobarakpur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. .(3rd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000279/2023-2024 | 3081/MAAD | 14/12/2023 | 474 | M/S PARIMAL DAS | 212.51 | 63.33 | 70
893 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | RTOR000010/2023-2024 | 633/MAAD | 05/04/2023 | 0 | Resource Division | 42.92 | 0 | 0
894 | Malda Mechanical | Malda Arsenic Area W/S Division | Quotation payment for Mobarakpur PH NO 2 Under Mothabri CCC Under the district of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | BILL/02386/2025-2026 |  | 24/09/2025 | 0 | W.B.S.E.D.C.LTD | 18.44 | 0 | 0
895 | Malda Mechanical | Malda Arsenic Area W/S Division | Quotation payment for Mobarakpur PH NO 1 & AIRP Under Mothabri CCC Under the district of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | BILL/03202/2024-2025 | BP-2024-25-634 | 06/02/2025 | 0 | W.B.S.E.D.C.LTD | 10.39 | 0 | 0
896 | Malda Mechanical | Malda Arsenic Area W/S Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000059/2025-2026 | 2083/MLMD | 30/04/2025 | 61 | SUBRATA SAHA | 0.78 | 0 | 0
897 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Mabarakpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/002481/2023-2024 | 97/MLMD | 11/01/2024 | 476 | HANNAN BUILDERS PVT. LTD. | 70.67 | 24.6 | 50
898 | Malda Ars Area W/S Division |  | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Uttar Jadupur Piped Water supply scheme at Head Work Site of English Bazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda. |  |  | ORD/000140/2023-2024 | 1481/MAAD | 01/08/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 7.65 | 5.49 | 100
899 | Malda Ars Area W/S Division |  | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Uttar Jadupur Piped Water supply scheme at 2nd Site of English Bazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda. |  |  | ORD/000141/2023-2024 | 1482/MAAD | 01/08/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 7.65 | 5.11 | 100
900 | Malda Ars Area W/S Division |  | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Uttar Jadupur Piped Water supply scheme at 3rd Site of English Bazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda. |  |  | ORD/000142/2023-2024 | 1483MAAD | 01/08/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 7.65 | 5.69 | 100
901 | Malda Ars Area W/S Division |  | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 3rd Tube Well site of Uttar Jadupur Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. |  |  | ORD/000143/2023-2024 | 1485/MAAD | 01/08/2023 | 60 | GIRIDHARI CONSTRUCTION | 5 | 4.61 | 100
902 | Malda Ars Area W/S Division |  | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Uttar Jadupur Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. |  |  | ORD/000144/2023-2024 | 1484/MAAD | 01/08/2023 | 60 | DEY CONSTRUCTIONS | 5 | 4.81 | 100
903 | Malda Ars Area W/S Division |  | Laying of Distribution System at Dilalpur under Uttar Jadupur Piped Water supply scheme at English Bazar under Malda Arsenic Area W/S Division, P.H.E.Dte. |  |  | ORD/000145/2023-2024 | 1492/MAAD | 04/08/2023 | 90 | ABANI BHUSAN GHOSH | 41.08 | 26.67 | 75
904 | Malda Ars Area W/S Division |  | Laying of Distribution System at Sonatala, Kechuahi, Jaharpur, Uttar Jadupur,, Model Colony & Nayagram Uttar Jadupur Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area W/S Division, P.H.E.Dte. |  |  | ORD/000146/2023-2024 | 1493/MAAD | 04/08/2023 | 681 | FUTURE | 96.7 | 48.76 | 75
905 | Malda Ars Area W/S Division |  | Route servey & design for prepration of DPR of Uttar & Dakshin Jadupur, Purba Saidpur & Arapur Piped Water Supply Scheme at Englishbazar & Manikchak Development Block under Malda Arsenic Area W/S Division, PHE Dte. in the district of Malda. |  |  | ORD/000248/2023-2024 | 1762/MAAD | 30/09/2023 | 15 | FUTURE | 0.99 | 0.99 | 100
906 | Malda Ars Area W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 631/MAAD | 05/04/2023 | 0 | Resource Division | 147.11 | 0 | 0
907 | Malda Mechanical |  | QUOTATION PAYMENT FOR Uttar Jadupur T/W No-2 UNDER MOKDUMPUR CCC UNDER MALDA DISTRICT |  |  | BILL/00015/2024-2025 | BP-2024-25-34 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.82 | 0 | 0
908 | Malda Mechanical |  | QUOTATION PAYMENT FOR Uttar Jadupur T/W No1 UNDER MOKDUMPUR CCC UNDER MALDA DISTRICT |  |  | BILL/00016/2024-2025 | BP-2024-25-35 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 5.12 | 0 | 0
909 | Malda Ars Area W/S Division |  | Construction of 700 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Uttar Jadupur Piped Water Supply scheme at English Bazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (2nd Call) |  |  | ORD/000399/2023-2024 | 1583/MAAD | 28/08/2023 | 583 | BANIK BROTHERS | 290.34 | 0 | 10
910 | Malda Mechanical |  | QUOTATION PAYMENT FOR Uttar Jadupur T/W No-3 UNDER MOKDUMPUR CCC UNDER MALDA DISTRICT |  |  | BILL/00017/2024-2025 | BP-2024-25-36 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.82 | 0 | 0
911 | Malda Mechanical |  | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I, II & III and Arsenic Iron Removal Plant at Uttar Jadupur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017806) |  |  | ORD/000631/2023-2024 | 2678/MLMD | 11/08/2023 | 891 | WEST BENGAL ENGINEERING COMPANY. | 82.31 | 0 | 20
912 | Malda Division |  | Formal work order for the work of Augmentation of SAMSI (Zone-I & II) Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000356/2023-2024 | 3014/MD | 08/08/2023 | 1265 | DUTTA ENTERPRISE | 1066.35 | 226.63 | 38
913 | Malda Division |  | Sinking of 200 mm (all through) Big Dia. Tube-Well of 120 M Deep at Tubewell No-1of Samsi Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000455/2024-2025 | 4809/MD | 13/09/2024 | 30 | ASHIS CONSTRUCTION | 8.5 | 0 | 0
914 | Malda Division |  | Sinking of 200 mm (all through) Big Dia. Tube-Well of 120 M Deep at Tubewell No-2 of Samsi Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000456/2024-2025 | 4810/MD | 13/09/2024 | 30 | ASHIS CONSTRUCTION | 8.5 | 8.08 | 100
915 | Malda Division |  | Sinking of 200 mm (all through) Big Dia. Tube-Well of 120 M Deep at Samsi Hospital of Samsi Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000457/2024-2025 | 4811/MD | 13/09/2024 | 30 | ABHIJIT PAUL | 8.5 | 2.2 | 100
916 | Malda Division |  | Continuation work order for the work of Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/11/2023 to 30/04/2024). |  |  | ORD/000716/2023-2024 | 4428/MD | 30/10/2023 | 183 | SHABNAM ARA | 0.86 | 1.98 | 56
917 | Malda Division |  | Emergent repair work of Pump house due to sudden settling of Pump House floor in front of Samsi Hospital in Samsi Piped Water Supply Scheme on urgent basis under Malda Division, PHE Dte. in the District of Malda. |  |  | ORD/000718/2025-2026 | 3709/MD | 29/07/2025 | 180 | M/S FOUR STAR CONSTRUCTION | 0.32 | 0 | 100
918 | Malda Division |  | 1st layer Land Development Work at Head Work site of Samsi Zone-II Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000764/2024-2025 | 6622 | 31/12/2024 | 30 | M/S FOUR STAR CONSTRUCTION | 0.95 | 0 | 100
919 | Malda Division |  | Erection of Property board and dissemination of Property information through pipe painting related to Jal Jeevan Mission works of Debipur, Kahala, Mahanandatola, Ratua & Samsi GP under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000969/2024-2025 | 658/MD | 19/02/2025 | 7 | M/S TEWARI CONSTRUCTION | 0.97 | 0 | 0
920 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 358/MD | 16/01/2024 | 0 | Resource Division | 30.48 | 0 | 0
921 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 818/MD | 21/02/2024 | 0 | Resource Division | 98.17 | 0 | 0
922 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at Head worksite of Samsi (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008164) |  |  | ORD/000501/2023-2024 | 2571/MLMD | 04/08/2023 | 1172 | SUDIP DEY | 24.47 | 9.75 | 75
923 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I, II, III & IV of Samsi (Zone-I) Water Supply Scheme and making compound lighting arrangement at Head Work Site in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008164) |  |  | ORD/000502/2023-2024 | 2572/MLMD | 04/08/2023 | 1177 | GHOSH BROTHERS... | 44.09 | 0 | 0
924 | Malda Mechanical |  | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. |  |  | ORD/001771/2024-2025 | 1275/MLMD | 27/02/2025 | 61 | SUBRATA SAHA | 0.78 | 0 | 0
925 | Malda Division |  | Dedicated Pipe laying for better Functionality and Providing Balance FHTC for HATNAGAR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. Govt. of West Bengal. |  |  | ORD/000214/2025-2026 | 3771/MD | 04/08/2025 | 240 | M/S GUPTA ENTERPRISE | 91.12 | 0 | 0
926 | Malda Division |  | Land Development, Approach Road for HATNAGAR Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal |  |  | ORD/000223/2025-2026 | 4021/MD | 22/08/2025 | 240 | M/S GUPTA ENTERPRISE | 41.99 | 0 | 0
927 | Malda Division |  | Formal work order for the work of Implementation of HATNAGAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000372/2023-2024 | 3104/MD | 10/08/2023 | 1056 | M/S GUPTA ENTERPRISE | 628.84 | 399.56 | 70
928 | Malda Division |  | Formal work order for the work of Providing Functional Household Tap Connection (FHTC), Laying of Distribution Pipeline and allied works in connection with Jal Jeevan Mission (JJM) at Hatnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000770/2024-2025 | 66/MD | 13/01/2025 | 533 | M/S GUPTA ENTERPRISE | 241.12 | 0 | 20
929 | Malda Division |  | Construction of Boundary Wall at Head Work site of Hatnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000845/2024-2025 | 832/MD | 06/03/2025 | 329 | M/S GUPTA ENTERPRISE | 30.13 | 0 | 0
930 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000013/2025-2026 | 2518/MD | 29/05/2025 | 0 | Resource Division | 8.24 | 0 | 0
931 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 247/MD | 10/01/2024 | 0 | Resource Division | 8.25 | 0 | 0
932 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000195/2023-2024 | 817/MD | 21/02/2024 | 0 | Resource Division | 32.68 | 0 | 0
933 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Hatnagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/020336) |  |  | ORD/000755/2023-2024 | 2822/MLMD | 17/08/2023 | 1043 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 31.01 | 0 | 35
934 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Hatnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | ORD/001893/2023-2024 | 3004466995 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 3.46 | 3.46 | 100
935 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Hatnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | ORD/001894/2023-2024 | 3004466956 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 4.45 | 4.45 | 100
936 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of Rahimpur Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II | Junior Engineer-07 | ORD/000006/2023-2024 | 1571/MD | 10/04/2023 | 1262 | M/S GUPTA ENTERPRISE | 841.12 | 717.55 | 90
937 | Malda Division | Malda Mechanical Division | Emergent repair of pipe line of distribution system damaged by WBSEDCL for RAHIMPUR Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II | Junior Engineer-07 | ORD/000106/2025-2026 | 2277/MD | 21/05/2025 | 30 | M/S GUPTA ENTERPRISE | 0.39 | 0 | 100
938 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II | Junior Engineer-07 | ORD/000179/2024-2025 | 2954/MD | 10/06/2024 | 236 | M/S AMIT KUMAR GUPTA | 7.17 | 0 | 50
939 | Malda Division | Malda Mechanical Division | Dedicated Pipe laying for better Functionality and Providing Balance FHTC for RAHIMPUR Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II | Junior Engineer-07 | ORD/000213/2025-2026 | 3770/MD | 04/08/2025 | 301 | M/S GUPTA ENTERPRISE | 11.35 | 0 | 0
940 | Malda Division | Malda Mechanical Division | Bamboo Piling, earth filling for protection of Pipe line at different places for RAHIMPUR Piped Water Supply scheme of Gazole Block in the District of Malda under Malda Division, P.H.E.Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/000575/2024-2025 | 5499/MD | 25/10/2024 | 45 | M/S GUPTA ENTERPRISE | 9.93 | 0 | 100
941 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II | Junior Engineer-07 | ORD/000632/2024-2025 | 5911/MD | 26/11/2024 | 429 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 48.65 | 0 | 20
942 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II | Junior Engineer-07 | ORD/000844/2024-2025 | 831/MD | 06/03/2025 | 329 | M/S GUPTA ENTERPRISE | 28.39 | 0 | 60
943 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II | Junior Engineer-07 | RTOR000052/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 14.65 | 0 | 0
944 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II | Junior Engineer-07 | RTOR000099/2023-2024 | 28/MD | 04/01/2024 | 0 | Resource Division | 16.25 | 0 | 0
945 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Rahimpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015255) | Assistant Engineer - II | Junior Engineer-07 | ORD/000324/2023-2024 | 2326/MLMD | 26/07/2023 | 786 | JAL PRAVAHIKA PVT. LTD. | 28.25 | 17.5 | 84
946 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of RAHIMPUR PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/000720/2023-2024 | 3004390672 | 11/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.39 | 5.39 | 100
947 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Rahimpur PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/000772/2023-2024 | 3004390718 | 16/08/2023 | 90 | W.B.S.E.D.C.LTD | 18.35 | 18.35 | 100
948 | Malda Division |  | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Altor Water Supply Scheme of Gazole Dev. Block under Malda Division P.H.E Dte in the District of Malda. |  |  | ORD/000141/2025-2026 | 2619/MD | 02/06/2025 | 135 | M/S AMIT KUMAR GUPTA | 18.01 | 0 | 0
949 | Malda Division |  | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. |  |  | ORD/000160/2020-2021 | 2713/MAAD | 10/11/2020 | 45 | MANIK CHANDRA SAHA | 68.5 | 54.67 | 0
950 | Malda Division |  | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bibijhuti, JL. No. 58, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. |  |  | ORD/000303/2020-2021 | 283/MD | 28/01/2021 | 30 | ANUKUL CHANDRA DAS | 9.41 | 0.19 | 1
951 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Altor Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000447/2023-2024 | 3364/MD | 29/08/2023 | 45 | M/S BABLU ENTERPRISE | 18.17 | 17.75 | 80
952 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Altore Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000597/2024-2025 | 5738/MD | 20/11/2024 | 346 | SAMBHU NATH SARKAR | 42.53 | 0 | 0
953 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000072/2025-2026 | 5540/MD | 29/10/2025 | 0 | Resource Division | 10.52 | 0 | 0
954 | Malda Division | Malda Mechanical Division | New service connection at Nabagram PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.(CHANCHAL C C C) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/00095/2025-2026 | 592/Elect | 05/08/2025 | 0 | W.B.S.E.D.C.LTD | 4.42 | 0 | 0
955 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of NABAGRAM Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000027/2023-2024 | 1838/MD | 02/05/2023 | 1059 | R. K. ENTERPRISE | 587.5 | 276.78 | 80
956 | Malda Division | Malda Mechanical Division | Laying of Distribution Line, Providing FHTC, Construction of Pump House at Nabagram Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000142/2024-2025 | 2903/MD | 07/06/2024 | 685 | M/S FOUR STAR CONSTRUCTION | 92.58 | 0 | 79
957 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Nabagram Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000150/2025-2026 | 2688/MD | 04/06/2025 | 45 | MODERN CO-OPERATIVE LABOUR CONTRCT & CONSTRUCTION SOCIETY LIMITED. | 34.99 | 0 | 0
958 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Nabagram Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000158/2024-2025 | 2933/MD | 10/06/2024 | 30 | M/S BHARATI CONSTRUCTION | 7.23 | 0 | 80
959 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 80 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Nabagram Water Supply Scheme of Chanchal-I Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000197/2025-2026 | 3631/MD | 24/07/2025 | 360 | VISCOUS ENGINEERS PVT. LTD. | 31.97 | 0 | 0
960 | Malda Division | Malda Mechanical Division | Restoration of Road at Bhagabatipur Mouza of Nabagram Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000198/2025-2026 | 3632/MD | 24/07/2025 | 180 | M/S FOUR STAR CONSTRUCTION | 12.6 | 0 | 0
961 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160m Deep at Nabagram PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000304/2024-2025 | 3450/MD | 10/07/2024 | 73 | A. L. ENGINEERING SOLUTION | 10.44 | 0 | 95
962 | Malda Division | Malda Mechanical Division | Additional Laying Distribution of UPVC pipe line of NABAGRAM Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, P.H.E Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000959/2023-2024 | 710/MD | 09/02/2024 | 143 | RATAN KARMAKAR | 4.11 | 3.88 | 90
963 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000044/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 21.33 | 0 | 0
964 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000051/2025-2026 | 5593/MD | 30/10/2025 | 0 | Resource Division | 3.18 | 0 | 0
965 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000119/2023-2024 | 89/MD | 05/01/2024 | 0 | Resource Division | 18.48 | 0 | 0
966 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Nabagram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013452) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000766/2023-2024 | 2566/MLMD | 04/08/2023 | 1121 | DAS ENTERPRISE. | 29.85 | 26.01 | 87
967 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of NABAGRAM PWSS, Chanchal C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001016/2023-2024 | 3004407809 | 11/09/2023 | 90 | W.B.S.E.D.C.LTD | 12.15 | 12.15 | 100
968 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Nabagram, Chanchal C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001886/2023-2024 | 3004460870 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 3.46 | 3.46 | 100
969 | Malda Division |  | Formal work order for the work of Implementation of PARAIL Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000261/2023-2024 | 3008/MD | 07/08/2023 | 1025 | M/S TAPAS KUMAR CHAKRABORTY & CO | 1011.34 | 539.53 | 55
970 | Malda Division |  | Construction of Boundary Wall at Head Work site of Parail Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000264/2024-2025 | 3212/MD | 27/06/2024 | 701 | M/S JHA CONSTRUCTION | 26.23 | 0 | 70
971 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Parail Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000786/2024-2025 | 351/MD | 30/01/2025 | 90 | M/S TAPAS KUMAR CHAKRABORTY | 60.83 | 0 | 0
972 | Malda Division |  | Dedicated Pipe laying for better Functionality and Providing Balance FHTC and Land development for PARAIL Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000902/2025-2026 | 466/MD | 27/01/2026 | 150 | M/S TAPAS KUMAR CHAKRABORTY | 32.8 | 0 | 0
973 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000008/2025-2026 | 2582/MD | 30/05/2025 | 0 | Resource Division | 10.05 | 0 | 0
974 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 235/MD | 10/01/2024 | 0 | Resource Division | 7.35 | 0 | 0
975 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000191/2023-2024 | 813/MD | 21/02/2024 | 0 | Resource Division | 39.07 | 0 | 0
976 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Parail, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03720/2023-2024 | BP-2023-24-707 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 22.02 | 0 | 0
977 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Parail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014391) |  |  | ORD/000384/2023-2024 | 2392/MLMD | 28/07/2023 | 180 | ALPHA ENTERPRISE. | 28.69 | 0 | 0
978 | Malda Division |  | The payment to WBSRDA against the repair of damaged roads. |  |  | BILL/00732/2024-2025 |  | 11/11/2024 | 0 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 6 | 0 | 0
979 | Malda Division |  | Payment for rural road damage pipe line. |  |  | BILL/00803/2024-2025 | BP-2024-25-380 | 14/11/2024 | 0 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 6 | 0 | 0
980 | Malda Ars Area W/S Division |  | Restoration of damaged PWD road for Chainage 18.00 KM to 220..00 Km to 30.00 KM and chainage 30.00 KM to 32.50 KM in Laying of water rising main at SH-10 under Augmentation of surface water based piped water supply scheme for Malda Arsenic Area (Northern & Southern Sector). |  |  | BILL/00081/2024-2025 | C062409333417 | 11/06/2024 | 0 | EXUCUTIVE ENGINEER PWD MALDA | 54.95 | 0 | 0
981 | Malda Ars Area W/S Division |  | Payment of Wayleave facility charges ID- ER-MLDT-2024-WL-44 Station- KTJ-JMQ Mast No- 275/25-27 & 275/26-28 |  |  | BILL/00414/2024-2025 | C012536185547 | 17/01/2025 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 7.27 | 0 | 0
982 | Malda Ars Area W/S Division |  | Payment of Wayleave facility charges ID-ER-MLDT-2024-WL-43 Station- KTJ-JMQ Mast No- 276/31-33 & 277/01-02 |  |  | BILL/00415/2024-2025 | C012536178062 | 17/01/2025 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 5.75 | 0 | 0
983 | Malda Ars Area W/S Division |  | Payment of Wayleave facility charges ID- ER-MLDT-2024-WL-42 Station - KTJ - CMX Mast No- 270/30-32 & 270/29-31 |  |  | BILL/00416/2024-2025 | C012536174759 | 17/01/2025 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 14.88 | 0 | 0
984 | Malda Ars Area W/S Division |  | Quotation the shifting of LTOH line above newly constructing pipe line. |  |  | BILL/00645/2023-2024 | C022455072524 | 20/02/2024 | 0 | W.B.S.E.D.C.LTD | 0.81 | 0 | 0
985 | Malda Ars Area W/S Division |  | Supply of different DI materials for the work of "Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II& III Blocks in the district of Malda." |  |  | ORD/000134/2024-2025 | 1163/MAAD | 07/06/2024 | 265 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 76.96 | 0 | 50
986 | Malda Ars Area W/S Division |  | Surveying, Design, Engineering, Supplying, Construction, Erection, Testing, Commissioning of Raw Water Intake Jetty Structure (Fixed type) with Pump House over river Fulhar near Mathurapur connected by carriageway with Pump House & the river bank including River Bank protection, Laying of Raw Water Rising Mains, Conventional type Water Treatment Plant (treated water Capacity 87 MLD) with centralized SCADA system, Substation Buildings at Intake as well as at WTP including all Electrical and Mech. work (at Intake and WTP and Boosting Station II at Shyamdaspur), 3500 Cum capacity Clear Water Reservoir at WTP site, High Lift Pump House, Clear Water Rising Mains from WTP to Clear Water Reservoirs at Boosting Station-I( at Niamatpur) & II (at shyamdaspur) and Boosting Stations to different Zonal OHR New and Existing)sites Kaliachak-I,II and Englishbazar Block, 500 Cum capacity Clear Water Reservoir at Booster Station-I at Niamatpur under Englishbazar block and another 3500 Cum capacity Clear Water Reservoir at Boosting Station-II at Shyamdaspur under Kaliachak-II block, Internal pathway, surface Drain, Staff Quarter including all related and allied Civil, Mechanical, Electrical and Instrumentational work on EPC turnkey basis in a single package as per detail scope of work / direction of the E-I-C including 3(Three) months Trial Run along with Operation & Maintenance for 5(five) years for AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Malda Arsenic Affected Area (Northern & Southern Sector) at District Malda under Malda Arsenic Area W/S Division, PHE Dte. |  |  | ORD/000169/2023-2024 | 1527/MAAD | 14/08/2023 | 1051 | GBC INFRASTRUCTURE PRIVATE LIMITED | 30211.99 | 9119.04 | 40
987 | Malda Ars Area W/S Division |  | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.09.2023 to 02.03.2024) |  |  | ORD/000215/2023-2024 | 1552/MAAD | 18/08/2023 | 184 | UNITED ENGINEERS CORPORATION | 0.87 | 2.15 | 0
988 | Malda Ars Area W/S Division |  | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. |  |  | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 2675.2 | 30
989 | Malda Ars Area W/S Division |  | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for BRAHMONGRAM Scheme (Capacity-450 cum) in Manikchak Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". |  |  | ORD/000228/2024-2025 | 735/MAAD | 19/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100
990 | Malda Ars Area W/S Division |  | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for PASCHIMNARAYANPUR Scheme (Capacity-300 cum) in Manikchak Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". |  |  | ORD/000229/2024-2025 | 736/MAAD | 19/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 5
991 | Malda Ars Area W/S Division |  | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for UTTAR CHANDIPUR Scheme (Capacity-750 cum) in English Bazar Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". |  |  | ORD/000230/2024-2025 | 737/MAAD | 19/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 100
992 | Malda Ars Area W/S Division |  | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for SATANGAPARA Scheme (Capacity-600 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". |  |  | ORD/000231/2024-2025 | 738/MAAD | 19/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 5
993 | Malda Ars Area W/S Division |  | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for MOHABBATPUR Scheme (Capacity-500 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". |  |  | ORD/000232/2024-2025 | 739/MAAD | 19/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 5
994 | Malda Ars Area W/S Division |  | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for CHARIANANTAPUR Scheme (Capacity-500 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". |  |  | ORD/000233/2024-2025 | 740/MAAD | 19/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 5
995 | Malda Ars Area W/S Division |  | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for JAYENPUR Scheme (Capacity-400 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". |  |  | ORD/000234/2024-2025 | 814/MAAD | 22/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 5
996 | Malda Ars Area W/S Division |  | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for SULTANGANJ Scheme (Capacity-600 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". |  |  | ORD/000235/2024-2025 | 815/MAAD | 22/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 5
997 | Malda Ars Area W/S Division |  | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for BAHIRBONAScheme (Capacity-450 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". |  |  | ORD/000236/2024-2025 | 816/MAAD | 22/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 5
998 | Malda Ars Area W/S Division |  | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for MOKSADPUR Scheme (Capacity-1250 cum) in Kaliachak-I Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". |  |  | ORD/000237/2024-2025 | 817/MAAD | 22/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 1.3 | 5
999 | Malda Ars Area W/S Division |  | Continuation Work Order for Placing of diesel driven Car on hire basis for the official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. (for the period from 01.01.2024 to 30.12.2024)= 365 days. |  |  | ORD/000297/2023-2024 | 3289/MAAD | 29/12/2023 | 365 | SUBRATA SAHA | 1.73 | 4.43 | 40
1000 | Malda Ars Area W/S Division |  | Continuation Work Order for Placing of diesel driven Car on hire basis for official use of the Executive Engineer, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(for the period from 01.01.2024 to 30.12.2024)= 365 days |  |  | ORD/000298/2023-2024 | 3290/MAAD | 29/12/2023 | 365 | NITAI PANDEY | 1.73 | 3.9 | 10
1001 | Malda Ars Area W/S Division |  | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2023 to 31.12.2023) |  |  | ORD/000337/2022-2023 | 2294/MAAD | 28/12/2022 | 365 | M/S PARIMAL DAS | 1.73 | 2.57 | 100
1002 | Malda Ars Area W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 1032/MAAD | 16/05/2024 | 0 | Resource Division | 1906.64 | 0 | 0
1003 | Malda Ars Area W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000001/2025-2026 | 617/MAAD | 25/04/2025 | 0 | Resource Division | 341.21 | 0 | 0
1004 | Malda Ars Area W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 1612/MAAD | 04/10/2024 | 0 | Resource Division | 125.49 | 0 | 0
1005 | Malda Ars Area W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000002/2025-2026 | 628/MAAD | 29/04/2025 | 0 | Resource Division | 1181.07 | 0 | 0
1006 | Malda Ars Area W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 494/MAAD | 23/03/2023 | 0 | Resource Division | 13510.42 | 0 | 0
1007 | Malda Ars Area W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1716/MAAD | 21/09/2023 | 0 | Resource Division | 21.3 | 0 | 0
1008 | Malda Ars Area W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1973/MAAD | 30/10/2023 | 0 | Resource Division | 20.22 | 0 | 0
1009 | Malda Ars Area W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 216/MAAD | 23/02/2024 | 0 | Resource Division | 2555.83 | 0 | 0
1010 | Malda Mechanical |  | Quotation for Service Connection charges for bulk power supply at Sankaritolaghat intake Pumping station under Malda Mechanical Division, PHE Dte for an ultimate Contract demand of ent570KVA. |  |  | BILL/01248/2025-2026 | 124 | 07/08/2025 | 0 | W.B.S.E.D.C.LTD | 51.32 | 0 | 0
1011 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge for Bulk power supply at Mathurapur WTP, in the dist of Malda. |  |  | BILL/02383/2025-2026 |  | 24/09/2025 | 0 | W.B.S.E.D.C.LTD | 226.8 | 0 | 0
1012 | Malda Mechanical |  | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. |  |  | ORD/000068/2024-2025 | 1343/MLMD | 26/04/2024 | 61 | NITAI PANDEY | 0.78 | 0.76 | 0
1013 | Malda Mechanical |  | Formal Work Order for Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries at Boosting Pumping Station, Niyamatpur ( for Zonal OHRS of English Bazar Block) under Augmentation of Surface Water Based Piped Water Supply Scheme (Northeren Sector), District - Malda, PHE Dte. |  |  | ORD/000908/2023-2024 | 2667/MLMD | 10/08/2023 | 180 | ORIENTAL ENGINEERING CO. | 546.37 | 0 | 0
1014 | Malda Mechanical |  | Modification of existing High Lift pumping station and Sub-station at Mathurapur (for Zonal OHRS of Manikchak Block) under Augmentation of Surface Water Based Piped Water Supply Scheme (Northern Sector) Dist. Malda, PHE Dte. |  |  | ORD/001538/2023-2024 | 2669/MLMD | 10/08/2023 | 720 | WEST BENGAL ENGINEERING COMPANY. | 353.77 | 63.47 | 73
1015 | Malda Mechanical |  | Formal work order for Installation of 33KV terminal arrangement with 36KV indoor type equipments (non-extensible type) with VCB, CT, PT etc. at Sub-Station of Shyamdaspur Boosting Station for augmentation of PWSS for Malda Arsenic Affected Area at District Malda (Northern & Southern Sector). |  |  | ORD/001612/2024-2025 | 1693/MLMD | 28/03/2025 | 92 | ORIENTAL ENGINEERING CO. | 38.62 | 0 | 0
1016 | Malda Mechanical |  | Formal work order for Installation of 33KV terminal arrangement with 36KV indoor type equipments (non-extensible type) with VCB, CT, PT etc. at Sub-Station of Mathurapur WTP site for augmentation of PWSS for Malda Arsenic Affected Area at District Malda (Northern & Southern Sector). |  |  | ORD/001613/2024-2025 | 1694/MLMD | 28/03/2025 | 92 | WEST BENGAL ENGINEERING COMPANY. | 38.92 | 0 | 0
1017 | Malda Division |  | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-1) (Period from 01/07/2025 to 31/12/2025). |  |  | ORD/000283/2025-2026 | 3115/MD | 30/06/2025 | 181 | M/S FOUR STAR CONSTRUCTION | 0.86 | 0 | 90
1018 | Malda Division |  | Construction of 400 M3 Capacity, 20mtr. staging height RCC Elevated Service Reservoir as per Departmental type design (Ref :- DRG.No. PC/-I/OHR/11/2012) including delivery, inlet & overflow pipe connection etc. all complete for piped water supply scheme of BEJPURA PWSS at Harishchandrapur-II Block in the District of Malda, under Malda Division, PHE Dte. |  |  | ORD/000388/2024-2025 | 4556/MD | 30/08/2024 | 669 | NILMANI BASAK | 131.79 | 0 | 25
1019 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of UTTAR CHANDIPUR ZONE-IV A Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000034/2023-2024 | 1850/MD | 03/05/2023 | 1155 | BANIK BROTHERS | 341.23 | 78.28 | 22
1020 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Chandipur Zone-IV B Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000170/2025-2026 | 7812/MD | 11/06/2025 | 60 | BEE GEE CONSTRUCTION | 121.68 | 0 | 0
1021 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Uttar Chandipur Zone-IV A Piped Water Supply Scheme at Manikchak Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000890/2023-2024 | 164/MD | 08/01/2024 | 45 | J. M. CONSTRUCTION | 10.08 | 8.99 | 95
1022 | Malda Division | Malda Mechanical Division | Formal work order for the work of Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 75M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-IVA Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000988/2023-2024 | 1079/MD | 13/03/2024 | 624 | DUTTA ENTERPRISE | 188.41 | 0 | 0
1023 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-IV-A Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/001013/2023-2024 | 1515/MD | 16/03/2024 | 657 | BANIK BROTHERS | 28.69 | 0 | 0
1024 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-IV-B Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/001014/2023-2024 | 1516/MD | 16/03/2024 | 472 | M/S N. C. SARKAR | 26.44 | 0 | 0
1025 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000059/2025-2026 | 5583/MD | 30/10/2025 | 0 | Resource Division | 2.09 | 0 | 0
1026 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000091/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 72.43 | 0 | 0
1027 | Malda Mechanical | Malda Mechanical Division | QUOTATION PAYMENT FOR UTTARCHANDIPUR ZONE IV-A AIRP UNDER MANIKCHAK CCC UNDER MALDA DISTRICT | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | BILL/01686/2024-2025 | BP-2024-25-415 | 30/07/2024 | 0 | W.B.S.E.D.C.LTD | 5.76 | 0 | 0
1028 | Malda Mechanical | Malda Mechanical Division | Supply,delivery, installation and trial operation of Arsenic Iron Removal Plant at Uttar Chandipur (Zone-IV A) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019389) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000647/2023-2024 | 2682/MLMD | 11/08/2023 | 180 | EASTERN INDIA SALES & SERVICE. | 52.42 | 13.14 | 20
1029 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (200mm. Dia. x 150mm. Dia) Tube Well no-3 ( 70 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at PANNAPUR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000304/2022-2023 | 2299/MD | 28/09/2022 | 30 | MECHANO TRADING CO. | 5.25 | 0 | 0
1030 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of PANNAPUR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000340/2022-2023 | 3112/MD | 20/12/2022 | 45 | HIRAK ROY CHOUDHURY | 6.69 | 0 | 0
1031 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damage A.C pipe lineby different dia UPVC pipe for PANNAPUR Piped Water Supply Scheme ( Nimnail, Jahanabad) of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000364/2022-2023 | 2605/MD | 10/11/2022 | 45 | MANIK CHANDRA SAHA | 69.14 | 67.15 | 88
1032 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Pannapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000621/2024-2025 | 5791/MD | 21/11/2024 | 45 | DEY CONSTRUCTION | 36.95 | 0 | 0
1033 | Malda Division | Malda Mechanical Division | Sinking of ( 250 mm Dia. X 200 mm Dia.) Tubewell No.-3 (250 M deep) by D.R Rig. Method using P.V.C. pipe & Gravel Filter including Supply of materials at PANNAPUR Water Supply Scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000976/2023-2024 | 885/MD | 27/02/2024 | 347 | A. L. ENGINEERING SOLUTION | 14.82 | 0 | 100
1034 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | RTOR000020/2022-2023 | 2405/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
1035 | Central Drilling | Malda Mechanical Division | Resistivity survey for Sankail PWSS, Basara PWSS and Pannapur PWSS at Habibipur & Bamongola block under Malda district, CMSD-II (D), CDD, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000012/2023-2024 | 135/CMSD-II(D) | 24/05/2023 | 15 | S B S ENTERPRISE | 0.82 | 0.27 | 100
1036 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Pannapur, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | BILL/02486/2023-2024 | BP-2023-24-421 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 8.39 | 0 | 0
1037 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Pannapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012801) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000385/2023-2024 | 2393/MLMD | 28/07/2023 | 830 | SUBRATA KUMAR DAS. | 10.44 | 9.01 | 40
1038 | Malda Division | Chanchal Sub-Division | Bill for car hiring no. WB/51C/7999 for office of the Superintending Enginner, North Bengal Circle-II, PHE Dte. For the period from (01/02/2023 to 15/05/2023). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00228/2023-2024 | BP-2023-24-108 | 13/07/2023 | 0 | TARUN KUMAR BHATTACHARYA | 1.05 | 0 | 0
1039 | Malda Division | Chanchal Sub-Division | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB65C/6570, For the month of MAY, 2023. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00289/2023-2024 | BP-2023-24-143 | 09/08/2023 | 0 | UTTAM KUMAR GHOSH | 0.4 | 0 | 0
1040 | Malda Division | Chanchal Sub-Division | Diesel driven Vehicle as casual hiring basis for Monitoring of Works as and when called for | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00763/2024-2025 | BP-2024-25-390 | 05/12/2024 | 0 | SUBHANKAR SINGH | 0.26 | 0 | 0
1041 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Supply & delivery of Steel Table with Locker and Wooden Top, Office Visitors Chair and High back mesh Executive Chair for the Conference Room of District Laboratory 1st Floor and office of the Superintending Engineer, North Bengal Circle - Il under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000021/2023-2024 | 1712/MD | 20/04/2023 | 15 | M/S PARIMAL DAS | 2.42 | 2.42 | 0
1042 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of SADLICHAK Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000027/2020-2021 | 1962/MD | 31/08/2020 | 30 | BEE GEE CONSTRUCTION | 43.35 | 21.01 | 1
1043 | Malda Division | Chanchal Sub-Division | Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for DALLA Piped Water Supply Scheme (Dalla JL.-54, Aragachi JL-57) of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000046/2025-2026 | 2252/MD | 21/05/2025 | 243 | ACHARYYA CONSTRUCTION | 25.17 | 0 | 0
1044 | Malda Division | Chanchal Sub-Division | Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for GUNSANKRUL Piped Water Supply Scheme (Jadupur JL.-28, Paschim Banjhapara JL32) of Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000047/2025-2026 | 2253/MD | 21/05/2025 | 90 | RABIUL ISLAM | 22.84 | 0 | 100
1045 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BEJPURA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000056/2020-2021 | 2152/MD | 16/09/2020 | 45 | NEOGI ENTERPRISE | 68.33 | 36.27 | 1
1046 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BHAIRABPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000057/2020-2021 | 2142/MD | 16/09/2020 | 60 | SUBHAS CHANDRA KESHARI | 92.31 | 48.11 | 1
1047 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of GUN SANKRUL Water Supply Scheme at Malda Old Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000059/2020-2021 | 2261/MD | 29/09/2020 | 45 | MILLENNIUM ENTERPRISR | 74.5 | 21.23 | 0
1048 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bejpura Piped Water Supply Scheme (Phase-II) at Harischandrapur - II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000055/2022-2023 | 1487/MD | 23/06/2022 | 30 | CHARU CONSTRUCTION | 6.53 | 6.53 | 1
1049 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of JAGANNATHPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000060/2020-2021 | 2141/MD | 16/09/2020 | 45 | DEBAPRIYA SAHA | 77.59 | 32.71 | 0
1050 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KHANPUR HULASPUR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000065/2020-2021 | 2139/MD | 16/09/2020 | 45 | M/S TRILOCHAN CONSTRUCTION CO | 65.52 | 16.95 | 0
1051 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of JALALPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000067/2020-2021 | 2140/MD | 16/09/2020 | 60 | FUTURE | 116.65 | 86.06 | 0
1052 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KUTUB SAHAR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000070/2020-2021 | 2135/MD | 16/09/2020 | 90 | HANNAN BUILDERS PVT. LTD. | 145.2 | 20.4 | 1
1053 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Repairing of existing FHTC connection for Talsur Water Supply Scheme under Malda division.P.H.E.Dte. In the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000074/2022-2023 | 330/CSD | 22/06/2022 | 30 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 1.06 | 1.06 | 1
1054 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN MAHENDRAPUR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000079/2020-2021 | 2683/MD | 06/11/2020 | 45 | MADE & TRADE CO. | 85.01 | 112.26 | 0
1055 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAHARA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000080/2020-2021 | 2684/MD | 06/11/2020 | 60 | MADE & TRADE CO. | 132.4 | 29.22 | 100
1056 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAMBALPUR Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000082/2020-2021 | 2437/MD | 12/10/2020 | 60 | HANNAN BUILDERS PVT. LTD. | 156.77 | 138.24 | 1
1057 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bejpura Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000084/2025-2026 | 2282/MD | 21/05/2025 | 45 | M I CONSTRUCTION | 30.42 | 0 | 0
1058 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of TALSUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000085/2020-2021 | 2255/MD | 29/09/2020 | 90 | TARUN KUMAR BHATTACHARYA | 135.29 | 30 | 0
1059 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000085/2025-2026 | 2313/MD | 22/05/2025 | 60 | M/S JHA CONSTRUCTION | 52.11 | 0 | 0
1060 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-II Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000086/2025-2026 | 2329/MD | 22/05/2025 | 60 | SAHA CONSTRUCTION | 43.45 | 0 | 0
1061 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of RAJARAMPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000087/2020-2021 | 2263/MD | 29/09/2020 | 45 | UTTAM KUMAR DUTTA | 59.93 | 48.18 | 0
1062 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-III Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000087/2025-2026 | 2330/MD | 22/05/2025 | 60 | BEE GEE CONSTRUCTION | 43.45 | 0 | 0
1063 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-IV Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000088/2025-2026 | 2331/MD | 22/05/2025 | 60 | M/S SRINJOYEE | 8.7 | 0 | 0
1064 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Birjabhita Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000091/2025-2026 | 2333/MD | 22/05/2025 | 60 | ACHARYYA CONSTRUCTION | 52.11 | 0 | 0
1065 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BHADO Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000155/2020-2021 | 2704/MD | 10/11/2020 | 60 | GHOSH BROTHERS | 148.17 | 148.15 | 100
1066 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) with additional Laying of Distribution Pipeline at Jalalpur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000164/2025-2026 | 2877/MD | 17/06/2025 | 120 | M/S SABANA CONSTRUCTION | 37.6 | 0 | 0
1067 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Khanpur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000165/2025-2026 | 2878/MD | 17/06/2025 | 60 | BINA CONSTRUCTION | 61.93 | 0 | 0
1068 | Malda Division | Chanchal Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Different Piped Water Supply Scheme under Harishchandrapur-I & II, Chanchal-I & II Block to facilitate Har Ghar Jal under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000098/2025-2026 | 2340/MD | 22/05/2025 | 365 | M/S SABANA CONSTRUCTION | 65.08 | 0 | 0
1069 | Malda Division | Chanchal Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Different Locations under Different Piped Water Supply Scheme under Ratua-I & II Block to facilitate Har Ghar Jal under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000099/2025-2026 | 2341/MD | 22/05/2025 | 365 | M/S TEWARI CONSTRUCTION | 32.63 | 0 | 0
1070 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-II Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-II) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000122/2022-2023 | 1640/MD | 19/07/2022 | 30 | KRISHNENDU DUTTA | 26.59 | 26.43 | 1
1071 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-III Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-II) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000123/2022-2023 | 1641/MD | 19/07/2022 | 30 | UTTAM KUMAR GHOSH | 23.82 | 22.75 | 1
1072 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-III) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000124/2022-2023 | 1642/MD | 19/07/2022 | 30 | M/S AMIT KUMAR GUPTA | 16.26 | 15.32 | 1
1073 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Hiring of 1 no. diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/04/2022 to 27/09/2022) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000127/2022-2023 | 797/MD | 01/04/2022 | 180 | USHA ENTERPRISE | 0.86 | 0.45 | 1
1074 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000166/2020-2021 | 2719/MD | 10/11/2020 | 30 | MANAS KUMAR SAHA | 50.07 | 46.89 | 1
1075 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jagannathpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000171/2025-2026 | 2888/MD | 17/06/2025 | 435 | M/S SABANA CONSTRUCTION | 90.55 | 0 | 0
1076 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gobarjana Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000177/2025-2026 | 2893/MD | 17/06/2025 | 60 | J. M. CONSTRUCTION | 26 | 0 | 0
1077 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/07/2022 to 31/12/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000137/2022-2023 | 213/MSD | 30/06/2022 | 184 | UTTAM KUMAR GHOSH | 0.86 | 2.07 | 1
1078 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. (Period from 01/07/2022 to 31/12/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000141/2022-2023 | 215/MSD | 30/06/2022 | 6 | SHYAMAL KUMAR MAITRA | 0.86 | 1.6 | 1
1079 | Malda Division | Chanchal Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Different Locations under Different Piped Water Supply Scheme under Habibpur & Gazole Block to facilitate Har Ghar Jal under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000160/2025-2026 | 2880/MD | 17/06/2025 | 365 | SAMBHU NATH SARKAR | 52.09 | 0 | 0
1080 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Laying with Extension of different diameter (OD) uPVC pipe line under command area at Baherpur Zone-I Water Supply Scheme under Bamangola Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000172/2025-2026 | 2889/MD | 17/06/2025 | 60 | M/S SINHA ENTERPRISE | 43.12 | 0 | 0
1081 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Khanpur-Hulaspur Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000182/2025-2026 | 2897/MD | 17/06/2025 | 60 | M/S ROY CONSTRUCTION | 31.51 | 0 | 0
1082 | Malda Division | Chanchal Sub-Division | Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Gunkrul JL-34) of Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000199/2024-2025 | 2931/MD | 10/06/2024 | 45 | RABIUL ISLAM | 17.29 | 17.18 | 100
1083 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Balupur Zone-I Water Supply Scheme under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000225/2021-2022 | 2378/MD | 13/08/2021 | 30 | ACHARYYA CONSTRUCTION | 13.48 | 12.47 | 1
1084 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Balupur Zone-III Water Supply Scheme at Ratua-I under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000226/2021-2022 | 2379/MD | 13/08/2021 | 30 | FUTURE | 13.48 | 0 | 0
1085 | Malda Division | Chanchal Sub-Division | Laying of Parallel/ Dedicated Pipeline, Providing Common Manifold & providing Balance FHTC for better Functionality at Magura Zone-I Piped Water Supply Scheme at Ratua-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000228/2025-2026 | 4233/MD | 29/08/2025 | 60 | BEE GEE CONSTRUCTION | 51.17 | 0 | 0
1086 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/07/2023 to 31/12/2023). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000230/2023-2024 | 504/MSD | 30/06/2023 | 184 | UTTAM KUMAR GHOSH | 0.86 | 1.18 | 26
1087 | Malda Division | Chanchal Sub-Division | Laying of Parallel/ Dedicated Pipeline, Providing Common Manifold, Land Development & providing Balance FHTC for better Functionality at Mekpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000232/2025-2026 | 4236/MD | 29/08/2025 | 60 | MANIK CHOUDHURY | 91.14 | 0 | 0
1088 | Malda Division | Chanchal Sub-Division | Additional laying of Pipe line for improvement of FHTC functionality by UPVC pipe line and Construction of Boundary wall ,Aproach Raod at HW & 2nd TW site in for PERAPUR Piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, P.H.E. Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000237/2025-2026 | 4520/MD | 12/09/2025 | 292 | BANIK BROTHERS | 90.01 | 0 | 0
1089 | Malda Division | Chanchal Sub-Division | Car hiring No. WB 65 A/4911 for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000258/2022-2023 | 312/NBC-II | 01/04/2022 | 365 | USHA ENTERPRISE | 3.59 | 1.09 | 0
1090 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and allied laying work in connection with Jal Jeevan Mission (JJM) at Dahara Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000258/2024-2025 | 3206/MD | 27/06/2024 | 45 | M/S AMIT KUMAR GUPTA | 69.58 | 0 | 0
1091 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and allied laying work in connection with Jal Jeevan Mission (JJM) at Talsur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000259/2024-2025 | 3207/MD | 27/06/2024 | 443 | BEE GEE CONSTRUCTION | 88.37 | 0 | 65
1092 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Magura Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000276/2024-2025 | 3196/MD | 27/06/2024 | 45 | NATIONAL CONSTRUCTION | 26.03 | 0 | 0
1093 | Malda Division | Chanchal Sub-Division | Extension of UPVC pipe line for Providing Functional Household Tap Connection with Jal Jeevan Mission (JJM) command area of Khanpur Hulashpur Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000281/2024-2025 | 3232/MD | 28/06/2024 | 45 | BIDYUT MAHALDAR | 9.98 | 0 | 0
1094 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection under BALUPUR ZONE-II Piped Water Supply Scheme at Ratua-I Block in the district of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000346/2020-2021 | 512/MD | 09/02/2021 | 60 | JAL PRAVAHIKA PVT. LTD. | 104.87 | 5.04 | 0
1095 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Additional laying work of UPVC distribution pipe line for JALALPUR Water Supply Scheme at CHANCHAL- II Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000352/2020-2021 | 552/MD | 12/02/2021 | 30 | FUTURE | 3.33 | 5.86 | 0
1096 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Bhabanipur, JL. No. 73, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000305/2020-2021 | 285/MD | 28/01/2021 | 30 | M/S BANERJEE CONSTRUCTION | 13.56 | 17.95 | 1
1097 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Period from 01/07/2024 to 31/12/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000321/2024-2025 | 3252/MD | 28/06/2024 | 180 | ARUN KUMAR DAS | 0.86 | 1.99 | 0
1098 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-1) (Period from 01/07/2024 to 31/12/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000322/2024-2025 | 3253/MD | 28/06/2024 | 180 | SHYAMAL KUMAR MAITRA | 0.86 | 2.17 | 0
1099 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the Assistant Engineer, Malda Division, PHE Dte. (Period from 01/07/2024 to 31/12/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000324/2024-2025 | 3255/MD | 28/06/2024 | 180 | AMIN ENTERPRISE | 0.86 | 2.38 | 60
1100 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-1) (Period from 01/07/2024 to 31/12/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000325/2024-2025 | 3256/MD | 28/06/2024 | 180 | M/S FOUR STAR CONSTRUCTION | 0.86 | 2.19 | 100
1101 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-1)(Period from 01/07/2024 to 31/12/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000326/2024-2025 | 3257/MD | 28/06/2024 | 180 | M/S TEWARI CONSTRUCTION | 0.86 | 1.81 | 100
1102 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHANPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000356/2020-2021 | 554/MD | 12/02/2021 | 30 | RAY CONSTRUCTION CO. | 57.64 | 80.35 | 1
1103 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection under DAULATNAGAR Piped Water Supply Scheme at Harishchandrapur-II Block in the district of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000357/2020-2021 | 553/MD | 12/02/2021 | 60 | NEOGI ENTERPRISE | 120.32 | 119.96 | 1
1104 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of distribution pipe line for Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM) under command area of Bhado of BHADO Water Supply Scheme under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000381/2022-2023 | 2735/MD | 18/11/2022 | 30 | M/S MANDAL & SONS | 6.77 | 6.11 | 0
1105 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 15/06/2024 to 14/12/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000327/2024-2025 | 3054/MD | 14/06/2024 | 180 | RUQAIYA ENTERPRISE | 0.86 | 1.92 | 0
1106 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/07/2022 to 31/12/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000334/2022-2023 | 215/1/MSD | 30/06/2022 | 184 | ARUN KUMAR DAS | 4.5 | 2.17 | 0
1107 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Manoharpur, JL. No. 117, G.P.-Sultannagar of GANNADIA Water Supply Scheme at Harischandrapur - II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000338/2020-2021 | 447/MD | 08/02/2021 | 30 | MANIK CHOUDHURY | 37.13 | 22.88 | 0
1108 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KHANPUR HULASHPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000395/2022-2023 | 2955/MD | 07/12/2022 | 30 | BIDYUT MAHALDAR | 5.17 | 4.98 | 100
1109 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Extension of UPVC pipe line laying for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Khanpur-Hulaspur W/S Scheme at Chanchal-I Block under Malda Division. PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000403/2022-2023 | 2963/MD | 07/12/2022 | 30 | BIDYUT MAHALDAR | 7.04 | 7.03 | 100
1110 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of MOYNA Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000408/2022-2023 | 2991/MD | 07/12/2022 | 45 | S. R. CONSTRUCTION | 25.41 | 21.2 | 0
1111 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Mekpur Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000449/2023-2024 | 3366/MD | 29/08/2023 | 45 | MANIK CHOUDHURY | 16.14 | 15.87 | 90
1112 | Malda Division | Chanchal Sub-Division | Replacement of 200 mm dia. X 150 mm Dia.) Tubewell No:-2 (130 M Deep) by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at MAHAMMADPUR Water Supply Scheme of Old Malda Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000451/2024-2025 | 4807/MD | 13/09/2024 | 78 | GOBINDA ENTERPRISE | 8.29 | 0 | 100
1113 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Rajarampur Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000452/2023-2024 | 3369/MD | 29/08/2023 | 45 | M/S PRATIMA CONSTRUCTION | 16.13 | 15.46 | 100
1114 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for hiring of inspection vehicle (Motor Cab or Maruti Omni Category (Standard), Non-Air Condition, Bharat Stage-III purchased on or after 01.05.2008 with Diesel/LPG/CNG Engine) in perfectly good condition of performing a very long journey and should cover anywhere without any trouble on monthly hire basis for official use of the office of the Assistant Engineer, R.W.S. Malda Sub-Division, P.H.E. Dte. (Period from 06/01/2023 to 05/07/2023) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000437/2022-2023 | 193/RWS | 05/01/2023 | 181 | SHYAMAL KUMAR MAITRA | 0.86 | 1.61 | 15
1115 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Period from 01/09/2024 to 28/02/2025). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000444/2024-2025 | 4590/MD | 30/08/2024 | 180 | RAJENDRA PRASAD SINGH | 0.86 | 2.37 | 0
1116 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Saiyedpur Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000454/2023-2024 | 3371/MD | 29/08/2023 | 45 | S. R. CONSTRUCTION | 20.14 | 13.53 | 100
1117 | Malda Division | Chanchal Sub-Division | Laying Distribution of DI pipe line along the Bandh and other allied work of KHOPAKATI Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division P.H.E Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000473/2024-2025 | 4987/MD | 27/09/2024 | 45 | RABIUL ISLAM | 9.02 | 9.01 | 90
1118 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection under BEHERPUR ZONE-I Pipe Water Supply Scheme at Bamangola Block in the district of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000481/2020-2021 | 435/MD | 08/02/2021 | 60 | PROJECT INDIA | 126.35 | 53.22 | 100
1119 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Display Board for different schemes and CWPP sites within Chanchal-I, Ratua-I, Ratua-II, Harishchandrapur-I, Harishchandrapur-II, Manikchak, Habibpur, Old Malda and Bamongola block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000502/2024-2025 | 5275/MD | 01/10/2024 | 7 | S. M. BUILDER | 3.02 | 3.02 | 100
1120 | Malda Division | Chanchal Sub-Division | Providing car on daily hirer basis @ Rs. 12.00/km for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000503/2022-2023 | 653/CSD | 07/11/2022 | 365 | SAUDIPTA KUMAR DAS | 4.56 | 0.33 | 0
1121 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sadlichak Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000506/2024-2025 | 5409/MD | 21/10/2024 | 556 | S. N. CONSTRUCTION | 41.99 | 0 | 0
1122 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-III Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. (Phase-I) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000530/2021-2022 | 3574/MD | 20/12/2021 | 30 | GOBINDA ENTERPRISE | 19.97 | 19.47 | 1
1123 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Konar Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000509/2024-2025 | 5384/MD | 04/10/2024 | 307 | SOVON KUMAR DAS | 71.34 | 0 | 100
1124 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2023 to 30/06/2023). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000510/2022-2023 | 520/MSD | 30/12/2022 | 182 | UTTAM KUMAR GHOSH | 0.86 | 2.29 | 15
1125 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Supplying, fitting and fixing of G.I. pipes of TATA make & Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Bejpura Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000513/2021-2022 | 542/CSD | 27/10/2021 | 30 | NEOGI ENTERPRISE | 4.26 | 4.24 | 1
1126 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Supplying, fitting and fixing of G.I. pipes of TATA make & Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Jalalpur Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000514/2021-2022 | 545/CSD | 01/11/2021 | 30 | FUTURE | 4.72 | 4.6 | 1
1127 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Supplying, fitting and fixing of G.I. pipes of TATA make & Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Jalalpur Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000515/2021-2022 | 546/CSD | 01/11/2021 | 30 | FUTURE | 2.66 | 2.66 | 1
1128 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/11/2022 to 30/04/2023). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000518/2022-2023 | 2474/MD | 21/10/2022 | 365 | SHABNAM ARA | 4.5 | 3.51 | 21
1129 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. (Phase-I) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000531/2021-2022 | 3575/MD | 20/12/2021 | 30 | PABITRA MANDAL | 19.48 | 17.34 | 1
1130 | Malda Division | Chanchal Sub-Division | Continuation work order for the work of hiring of 1 no diesel vehicle in good condition (traffic authority) having licence contract carage permit from regional transport authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte (Period from 28/09/2022 to 26/03/2023) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000533/2022-2023 | 1108/MD | 20/09/2022 | 180 | USHA ENTERPRISE | 4.5 | 1.02 | 0
1131 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAHARA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000552/2020-2021 | 2684/MD | 03/12/2020 | 1 | MADE & TRADE CO. | 0 | 23.94 | 1
1132 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-II Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. (Phase-I) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000529/2021-2022 | 3573/MD | 20/12/2021 | 30 | M/S JHA CONSTRUCTION | 39.81 | 36.95 | 1
1133 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Different dia. Damaged pipe line repair on emergency basis (damage due to widening of road) in connection with annual operation maintenance and providing FHTC to villagers under MEKPUR Piped Water Supply Scheme at Old Malda Dev. block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000549/2021-2022 | 513/MSD | 31/12/2021 | 1 | A. K. CONSTRUCTION | 2.06 | 0 | 0
1134 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000557/2021-2022 | 520/MSD | 31/12/2021 | 181 | SHYAMAL KUMAR MAITRA | 0.86 | 1.2 | 1
1135 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAGURA ZONE-I Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000559/2020-2021 | 2551/MD | 15/10/2020 | 30 | MILLENNIUM ENTERPRISR | 1 | 13.37 | 1
1136 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DALLA Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000560/2020-2021 | 2438/MD | 12/10/2020 | 120 | M/S JHA CONSTRUCTION | 10 | 11.19 | 1
1137 | Malda Division | Chanchal Sub-Division | Hiring of 1 no. diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 26/06/2023 to 22/12/2023) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000562/2023-2024 | 1452/NBC-II | 21/06/2023 | 181 | USHA ENTERPRISE | 2.19 | 2.03 | 42
1138 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MOYNA Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000563/2021-2022 | 49/MD | 13/01/2022 | 60 | S. R. CONSTRUCTION | 40.3 | 39.7 | 1
1139 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Placing of Diesel Driven Car on hire basis for official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/01/2021 to 31/12/2021). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000573/2020-2021 | 3280/MD | 30/12/2020 | 365 | SHYAMAL KUMAR MAITRA | 1.73 | 1.29 | 1
1140 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Malsa Mouza of KhanpurHulaspur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000574/2024-2025 | 5485/MD | 24/10/2024 | 361 | M/S /FAIZUL HAQUE BISWAS | 26.08 | 0 | 40
1141 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHANPUR HULASPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000564/2021-2022 | 48/MD | 13/01/2022 | 21 | BIDYUT MAHALDAR | 7.56 | 6.11 | 0
1142 | Malda Division | Chanchal Sub-Division | Continuation work order for Placing of Diesel Driven Car on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/02/2021 to 30/09/2021). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000579/2020-2021 | 276/MD | 28/01/2021 | 365 | RANJIT ADHIKARY | 2.66 | 1.26 | 0
1143 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Sadlichak Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000604/2023-2024 | 3810/MD | 16/10/2023 | 30 | RABIUL ISLAM | 8.8 | 8.79 | 90
1144 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Khopakati Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000625/2024-2025 | 5832/MD | 22/11/2024 | 585 | M/S SABANA CONSTRUCTION | 55.74 | 0 | 0
1145 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Emergent installation of Sulice Valve & Construction of Sluice Valve & Repairing of FHTC for Khanpur Hulashpur Water Supply Scheme under Malda division, P.H.E. Dte. In the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000631/2021-2022 | 31/CSD | 05/01/2022 | 15 | BIDYUT MAHALDAR | 1.27 | 1.27 | 1
1146 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Additional laying work of DI & UPVC pipe line of SADLICHAK W/S Scheme at HARISHCHANDRAPUR-II Dev. Block under Malda division.P.H.E.Dte. In the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000655/2021-2022 | 47/CSD | 14/01/2022 | 30 | BEE GEE CONSTRUCTION | 4.19 | 3.9 | 1
1147 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) under commend area of Kutubsahar Water Supply Scheme of Gazole Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000658/2021-2022 | 1899/MD | 30/06/2021 | 120 | RABIUL ISLAM | 10 | 0.63 | 0
1148 | Malda Division | Chanchal Sub-Division | Car hiring No. 51C/7999 for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/03/2022 to 30/06/2022) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000704/2021-2022 | 473/MD | 25/02/2022 | 120 | TARUN KUMAR BHATTACHARYA | 0.58 | 1.04 | 1
1149 | Malda Division | Chanchal Sub-Division | Supply of Forms & Stationary articles for the use of this office. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000707/2021-2022 | 3456/MD | 06/12/2021 | 1 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 1.28 | 1.28 | 1
1150 | Malda Division | Chanchal Sub-Division | Supply of Stationary articles for the use of Malda District Laboratory. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000708/2021-2022 | 367/MD | 10/02/2022 | 1 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.35 | 0.35 | 1
1151 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) including upvc laying in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda (Phase - II). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000663/2021-2022 | 742/MD | 28/03/2022 | 30 | FUTURE | 22.06 | 21.09 | 1
1152 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Laying with Extension of different diameter (OD) uPVC pipe line under command area at Baherpur Zone-II Water Supply Scheme under Bamangola Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000668/2024-2025 | 6167/MD | 05/12/2024 | 45 | S. R. CONSTRUCTION | 63.36 | 0 | 0
1153 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Replacement of different dia A.C pipe line (damage due to widening of road) by laying of different dia UPVC pipe in connection with annual operation maintenance and providing FHTC to Villagers under RAJARAMPUR Piped Water Supply Scheme of Habibpur Dev. Block in the District of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000672/2021-2022 | 142/MSD | 31/03/2022 | 2 | SSD CONSTRUCTION | 4.84 | 4.35 | 1
1154 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Hiring of 1 no. diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/02/2022 to 31/03/2022) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000703/2021-2022 | 232/MD | 27/01/2022 | 59 | USHA ENTERPRISE | 0.28 | 0.33 | 1
1155 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000705/2021-2022 | 522/MSD | 31/12/2021 | 181 | UTTAM KUMAR GHOSH | 0.86 | 2.38 | 1
1156 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000706/2021-2022 | 521/MSD | 31/12/2021 | 365 | ARUN KUMAR DAS | 0.86 | 1.76 | 1
1157 | Malda Division | Chanchal Sub-Division | Supply of Stationary articles for the use of Malda District Laboratory. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000709/2021-2022 | 368/MD | 10/02/2022 | 1 | MALDA DISTRICT SERVICE CUM-MARKETING INDS. CO-OP UNION LTD. | 1.1 | 0.46 | 0
1158 | Malda Division | Chanchal Sub-Division | Erection of 9 nos. display Board on Swajal Gram/Har Ghar Jal Village board at different locations of Gazole, Habibpur and Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000712/2025-2026 | 3685/MD | 28/07/2025 | 180 | M D P ENTERPRISE | 0.97 | 0 | 0
1159 | Malda Division | Chanchal Sub-Division | Erection of 9 nos. display Board on Swajal Gram/Har Ghar Jal Village board at different locations of Bamongola, Old Malda and Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000713/2025-2026 | 3686/MD | 28/07/2025 | 180 | M D P ENTERPRISE | 0.97 | 0 | 0
1160 | Malda Division | Chanchal Sub-Division | Erection of 9 nos. display Board on Swajal Gram/Har Ghar Jal Village board at different locations of Ratua-I and Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000714/2025-2026 | 3687/MD | 28/07/2025 | 180 | M D P ENTERPRISE | 0.97 | 0 | 0
1161 | Malda Division | Chanchal Sub-Division | Erection of 9 nos. display Board on Swajal Gram/Har Ghar Jal Village board at different locations of Chanchal-I and Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000715/2025-2026 | 3688/MD | 28/07/2025 | 180 | M D P ENTERPRISE | 0.97 | 0 | 0
1162 | Malda Division | Chanchal Sub-Division | Erection of 9 nos. display Board on Swajal Gram/Har Ghar Jal Village board at different locations of Harishchandrapur-I and Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000716/2025-2026 | 3707/MD | 29/07/2025 | 180 | M D P ENTERPRISE | 0.97 | 0 | 0
1163 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000717/2021-2022 | 520/MSD | 31/12/2021 | 6 | SHYAMAL KUMAR MAITRA | 2.16 | 0.67 | 0
1164 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000718/2021-2022 | 521/MSD | 31/12/2021 | 181 | ARUN KUMAR DAS | 2.16 | 0.9 | 0
1165 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DALLA Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000718/2023-2024 | 4767/MD | 05/12/2023 | 45 | A. B. CONSTRUCTION | 14.09 | 13.2 | 100
1166 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KUTUB SAHAR Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000720/2023-2024 | 4769/MD | 05/12/2023 | 45 | ACHARYYA CONSTRUCTION | 12.14 | 12.14 | 100
1167 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kutub Sahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000721/2024-2025 | 6412/MD | 19/12/2024 | 555 | PABITRA MANDAL | 40.29 | 0 | 65
1168 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mihaghat Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000737/2024-2025 | 56 | 08/01/2025 | 311 | ASHIS CONSTRUCTION | 26.57 | 0 | 0
1169 | Malda Division | Chanchal Sub-Division | Carrying charges of FTK Materials from Malda District Laboratory to different Blocks Rural Hospitals at English Bazar, Manikchak, Gazole, Habibpur, Bamongola, Old Malda, Ratua-I, Ratua-II, Chanchal-I, Chanchal-II, Harischandrapur-I, Harischandrapur-II, Kaliachak - I, Kaliachak - II, Kaliachak - III Block in the district of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000719/2025-2026 | 3710/MD | 29/07/2025 | 180 | RAJA CONSTRUCTION | 0.38 | 0 | 100
1170 | Malda Division | Chanchal Sub-Division | Replacement of damaged UPVC pipe line & repairing of FHTC damaged by Tulsihatta GP For construction of Surface drain at Tulsihatta Zone-I Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000720/2025-2026 | 3711/MD | 29/07/2025 | 180 | S K BANIK | 0.78 | 0 | 100
1171 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BALUPUR ZONE-II & III Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000742/2023-2024 | 5247/MD | 22/12/2023 | 45 | M/S. TEWARI CONSTRUCTION | 56.74 | 16.52 | 40
1172 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KHOPAKATI Water Supply Scheme at Harishchandrapuir-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000743/2023-2024 | 5245/MD | 22/12/2023 | 45 | M/S FOUR STAR CONSTRUCTION | 38.41 | 37.84 | 98
1173 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 20/02/2023 to 19/08/2023). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000760/2022-2023 | 809/MD | 17/02/2023 | 180 | M/S. TEWARI CONSTRUCTION | 0.86 | 2.22 | 100
1174 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Divion, PHE Dte. (Period from 10/03/2023 to 09/08/2023). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000761/2022-2023 | 1020/MD | 10/03/2023 | 180 | M/S FOUR STAR CONSTRUCTION | 0.86 | 1.83 | 100
1175 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dahara Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000761/2024-2025 | 80 | 13/01/2025 | 45 | M/S AMIT KUMAR GUPTA | 65.21 | 0 | 1
1176 | Malda Division | Chanchal Sub-Division | Detail route survey and design & drawing of distribution network, for providing FHTC in Balupur Zone-I Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000771/2024-2025 | 271/MD | 28/01/2025 | 15 | FUTURE | 0.84 | 0.67 | 100
1177 | Malda Division | Chanchal Sub-Division | Detail route survey and design & drawing of distribution network, for providing FHTC in Balupur Zone-II Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000772/2024-2025 | 272/MD | 28/01/2025 | 15 | FUTURE | 0.84 | 0 | 100
1178 | Malda Division | Chanchal Sub-Division | Detail route survey and design & drawing of distribution network, for providing FHTC in Balupur Zone-III Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000773/2024-2025 | 273/MD | 28/01/2025 | 15 | FUTURE | 0.84 | 0 | 100
1179 | Malda Division | Chanchal Sub-Division | Placing of Diesel Driven Bolero Car on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/02/2020 to 31/01/2021) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000778/2019-2020 | 349/MD | 28/01/2020 | 0 | RANJIT ADHIKARY | 1.51 | 1.51 | 1
1180 | Malda Division | Chanchal Sub-Division | Augmentation of work to ensure proper functioning of 250 M³ Capacity 20 Mtr. Staging height RCC Over Head Reservoir of Dalla Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000832/2024-2025 | 1060/MD | 19/03/2025 | 60 | BENGAL ENGINEERING COMPANY | 8.47 | 0 | 0
1181 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Bhairabpur Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000851/2024-2025 | 1044/MD | 18/03/2025 | 289 | FUTURE | 31.16 | 0 | 100
1182 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Dakshin Mahendrapur Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000853/2024-2025 | 1046/MD | 18/03/2025 | 150 | VISCOUS ENGINEERS PVT. LTD. | 29.12 | 0 | 0
1183 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Daulatnagar Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000854/2024-2025 | 1047/MD | 18/03/2025 | 75 | M/S PARIMAL DAS | 30.45 | 0 | 0
1184 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Jalalpur Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000861/2024-2025 | 1054/MD | 18/03/2025 | 75 | M/S MOON LIGHT CONSTRUCTION & CO. | 28.53 | 0 | 0
1185 | Malda Division | Chanchal Sub-Division | Augmentation of Head work site Pump House, PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at DALLA Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000884/2024-2025 | 1123/MD | 21/03/2025 | 45 | M/S GHOSH CONSTRUCTION | 9.58 | 0 | 0
1186 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DAKSHIN MAHENDRAPUR Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000912/2023-2024 | 385/MD | 17/01/2024 | 289 | RAHANUL ALAM | 23.84 | 15.18 | 100
1187 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DAHARA Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000913/2023-2024 | 386/MD | 17/01/2024 | 45 | PARIJAT RAY | 58.89 | 58.88 | 70
1188 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2024 to 30/06/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000894/2023-2024 | 1010/MSD | 29/12/2023 | 183 | UTTAM KUMAR GHOSH | 0.86 | 2.38 | 25
1189 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Nikhrail command area of MAHANADAPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000907/2023-2024 | 285/MD | 11/01/2024 | 45 | M/S AYUSH BUILDERS | 6.37 | 6.24 | 100
1190 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2024 to 30/06/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000922/2023-2024 | 1011/MSD | 29/12/2023 | 183 | ARUN KUMAR DAS | 0.86 | 1.93 | 67
1191 | Malda Division | Chanchal Sub-Division | Continuation of work order for hiring of inspection vehicle(Motor Cab or Maruti Omni Category(Standard,Non-Air Condition, Bharat Stage-III purchase on or after 01.05.2008 with Diesel/LPG/CNG Engine)in perfectly good condition of performing a very long journey and should cover anywhere without any trouble on monthly hire basis for official use of the office of the Assistant Engineer, R.W.S. Malda Sub-Division, PHE Dte.(Period from 01.01.2024 to 30.06.2024) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000930/2023-2024 | 431/RWS | 29/12/2023 | 182 | SHYAMAL KUMAR MAITRA | 0.86 | 1.47 | 70
1192 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 20/08/2023 to 15/02/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000938/2023-2024 | 3225/MD | 18/08/2023 | 180 | M/S. TEWARI CONSTRUCTION | 0.86 | 1.96 | 90
1193 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Divion, PHE Dte. (Period from 10/08/2023 to 06/02/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000939/2023-2024 | 3029/MD | 08/08/2023 | 180 | M/S FOUR STAR CONSTRUCTION | 0.86 | 2 | 99
1194 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mekpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001011/2023-2024 | 1513/MD | 16/03/2024 | 45 | A. B. CONSTRUCTION | 26.41 | 0 | 0
1195 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gun Sankrul Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001021/2023-2024 | 1189/MD | 14/03/2024 | 383 | TARUN KUMAR DEY | 26.39 | 0 | 0
1196 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Chanchal-I & Harishchandrapur-I Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001039/2023-2024 | 892/MD | 28/02/2024 | 7 | RAHANUL ALAM | 0.85 | 0.85 | 100
1197 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Hazzabari Village of Khord Babupur Mouza under KUTUB SAHAR Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000983/2023-2024 | 978/MD | 04/03/2024 | 45 | DHRITIPALI | 12.79 | 12.26 | 100
1198 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Period from 01/03/2024 to 31/08/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000993/2023-2024 | 843/MD | 22/02/2024 | 180 | RAJENDRA PRASAD SINGH | 0.86 | 2.39 | 17
1199 | Malda Division | Chanchal Sub-Division | Continuation work order for the work of hiring of 1 no diesel vehicle in good condition (traffic authority) having licence contract carage permit from regional transport authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte (Period from 23/12/2023 to 19/06/2024) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001010/2023-2024 | 2089/NBC-II | 20/12/2023 | 180 | USHA ENTERPRISE | 0.86 | 0 | 26
1200 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001040/2023-2024 | 893/MD | 28/02/2024 | 7 | RAHANUL ALAM | 0.85 | 0.84 | 100
1201 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Ratua-I & Ratua-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001041/2023-2024 | 894/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.85 | 0.84 | 100
1202 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Ratua-I Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001042/2023-2024 | 895/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.85 | 0.85 | 100
1203 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Source Augmentation Schemes of Harishchandrapur-I & Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001043/2023-2024 | 896/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.85 | 0.84 | 100
1204 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Source Augmentation, Retrofitting Schemes and different CWPP site of Chanchal-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001044/2023-2024 | 897/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.85 | 0.84 | 100
1205 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes and different CWPP site of Old Malda Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001045/2023-2024 | 898/MD | 28/02/2024 | 7 | PRITAM ENTERPRISE | 0.85 | 0.84 | 100
1206 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Source Augmentation and Retrofitting Schemes of Habibpur Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001046/2023-2024 | 899/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.85 | 0.85 | 100
1207 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at different CWPP site of Gazole & Habibpur Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001047/2023-2024 | 900/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.85 | 0.84 | 100
1208 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001048/2023-2024 | 901/MD | 28/02/2024 | 7 | RAHANUL ALAM | 0.97 | 0.96 | 100
1209 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Bamongola Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001049/2023-2024 | 902/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.97 | 0.97 | 100
1210 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Source Augmentation Schemes of Gazole & Old Malda Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001050/2023-2024 | 903/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.97 | 0.96 | 100
1211 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at different Retrofitting Schemes of Habibpur Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001051/2023-2024 | 904/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.97 | 0.97 | 100
1212 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at different Retrofitting Schemes of Gazole Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001052/2023-2024 | 905/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.97 | 0.97 | 100
1213 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at different CWPP sites of Chanchal-I, Harishchandrapur-I & Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001053/2023-2024 | 906/MD | 28/02/2024 | 7 | RAHANUL ALAM | 0.73 | 0.72 | 100
1214 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Source Augmentation Schemes and different CWPP sites of Chanchal-I, Ratua-I & Ratua-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001054/2023-2024 | 907/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.6 | 0.59 | 100
1215 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Englishbazar & Manikchak Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001055/2023-2024 | 908/MD | 28/02/2024 | 7 | PRITAM ENTERPRISE | 0.36 | 0.36 | 100
1216 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000003/2021-2022 | 3552/MD | 26/11/2021 | 0 | Resource Division | 8.78 | 0 | 0
1217 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000004/2021-2022 | 3585/MD | 21/12/2021 | 0 | Resource Division | 6.45 | 0 | 0
1218 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000004/2025-2026 | 2515/MD | 29/05/2025 | 0 | Resource Division | 312.14 | 0 | 0
1219 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000006/2021-2022 | 456/MD | 22/02/2022 | 0 | Resource Division | 3.29 | 0 | 0
1220 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000008/2022-2023 | 1258/MD | 27/05/2022 | 0 | Resource Division | 8.01 | 0 | 0
1221 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000011/2024-2025 | 3923/MD | 06/08/2024 | 0 | Resource Division | 4.31 | 0 | 0
1222 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000013/2024-2025 | 3926/MD | 06/08/2024 | 0 | Resource Division | 5.13 | 0 | 0
1223 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000023/2024-2025 | 5970/MD | 28/11/2024 | 0 | Resource Division | 154 | 0 | 0
1224 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000025/2024-2025 | 5973/MD | 28/11/2024 | 0 | Resource Division | 154 | 0 | 0
1225 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000100/2023-2024 | 30/MD | 04/01/2024 | 0 | Resource Division | 1.23 | 0 | 0
1226 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000102/2023-2024 | 32/MD | 04/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
1227 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000110/2023-2024 | 40/MD | 04/01/2024 | 0 | Resource Division | 5.85 | 0 | 0
1228 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000111/2023-2024 | 52/MD | 04/01/2024 | 0 | Resource Division | 1.93 | 0 | 0
1229 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000113/2023-2024 | 56/MD | 04/01/2024 | 0 | Resource Division | 0.31 | 0 | 0
1230 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000176/2023-2024 | 533/MD | 30/01/2024 | 0 | Resource Division | 12.94 | 0 | 0
1231 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KADIRPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | ORD/000029/2020-2021 | 1964/MD | 31/08/2020 | 30 | M/S KUNDU CONSTRUCTION | 39.43 | 0.01 | 1
1232 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing FHTC (Functional House hold Tap Connection) of Ranghat Piped Water Supply Scheme at Chanchal-II Dev. Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | ORD/000056/2023-2024 | 1991/MD | 17/05/2023 | 15 | M/S FOUR STAR CONSTRUCTION | 9.06 | 9.06 | 100
1233 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Emergent repairing and laying of uPVC pipeline and Construction of different dia sluice valve chambers with other allied work to proper functioning of FHTC work within the command area of JAGJIBANPUR Water Supply scheme under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | ORD/000400/2022-2023 | 2960/MD | 07/12/2022 | 30 | M/S AYUSH BUILDERS | 3.64 | 3.64 | 1
1234 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme at Habibpu Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | ORD/000554/2020-2021 | 2447/MD | 12/10/2020 | 120 | MANIK CHOUDHURY | 12 | 12 | 1
1235 | Central Drilling | RWS Malda Sub-Division | PROVIDING TUBE WELL MATERIALS TO IS : 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | ORD/000065/2022-2023 | 301/CMSD-I (D) | 08/07/2022 | 15 | CHANDA ENTERPRISE | 4.69 | 4.43 | 50
1236 | Central Drilling | RWS Malda Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | ORD/000066/2022-2023 | 302/CMSD-I (D) | 08/07/2022 | 15 | CHANDA ENTERPRISE | 4.66 | 4.48 | 0
1237 | Central Drilling | RWS Malda Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITEFOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | ORD/000242/2022-2023 | 346/CMSD-I | 25/07/2022 | 15 | CHANDA ENTERPRISE | 4.66 | 3.09 | 0
1238 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Haring of Charges of the Car. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | BILL/00297/2022-2023 | BP-2022-23-304 | 09/03/2023 | 0 | M/S PARIMAL DAS | 0.22 | 0 | 0
1239 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Topographical and Hydrograpic Survey for Malda Arsenic Area Water Supply Scheme ( Northern Sector) at Sankaritolaghat, Manikchak under Malda Arsenic Area Water Supply Division, P.H.E. Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000116/2022-2023 | 693/MAAD | 12/04/2022 | 20 | INTAKE SURVEY ENGINEERING CONSORTIUM | 2.15 | 0.73 | 1
1240 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area(Mouza Shyamsundari Part Manikchak Part, Ugritola) & others Allied works at Dharampur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000121/2022-2023 | 1022/MAAD | 12/05/2022 | 60 | ACHARYYA CONSTRUCTION | 33.38 | 30.82 | 1
1241 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dharampur water supply Scheme (Mouza Dharampur, Habitation-Ranutola, New Kadamtola, Shyamsundartola, Jhaitantola, Sonapur) at Manikchak Block under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000122/2022-2023 | 1023/MAAD | 12/05/2022 | 45 | DHRITIPALI | 15.99 | 15.58 | 1
1242 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
1243 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 125 mm, 110 mm dia uPVC Pipe line at Dharampur Village under Jote Gopal Kagmari distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000191/2022-2023 | 1402/MAAD | 26/07/2022 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.7 | 9.61 | 100
1244 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000292/2021-2022 | 1339/MAAD | 14/09/2021 | 109 | SUBRATA SAHA | 0.52 | 0.24 | 1
1245 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Placing of diesel driven Car on hire basis for official use of the Executive Engineer, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000333/2020-2021 | 1409/MAAD | 31/12/2020 | 365 | NITAI PANDAY | 4.85 | 2.89 | 1
1246 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | RTOR000010/2021-2022 | 196/MAAD | 11/02/2022 | 0 | Resource Division | 20.13 | 0 | 0
1247 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Kurbanitola & Sham Mahammad Tola at Dharampur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000198/2022-2023 | 1469/MAAD | 29/07/2022 | 45 | S. R. ENTERPRISE | 4.79 | 4.4 | 1
1248 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Nawada Haddatola, Karmakartola under Dharampur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000199/2022-2023 | 1466/MAAD | 29/07/2022 | 45 | TARUN KANTI BAGCHI | 4.85 | 4.55 | 1
1249 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Continuation work order for Supply G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for Schools of English Bazar Block under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000314/2022-2023 | 2107/MAAD | 07/12/2022 | 15 | M/S PARIMAL DAS | 0.41 | 0.41 | 1
1250 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dharampur Water Supply Scheme( Mouza-Nowada , Habitation-Sonapur,Haddatola, Kurbanitola, Nawada Haddatola, Dakshin Torabalitola) at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000352/2021-2022 | 1755/MAAD | 24/11/2021 | 45 | ACHARYYA CONSTRUCTION | 15.91 | 15.48 | 1
1251 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dharampur Water Supply Scheme( Mouza-Manikchak , ShyamSundari) at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000353/2021-2022 | 1756/MAAD | 24/11/2021 | 45 | ACHARYYA CONSTRUCTION | 16.02 | 15.47 | 1
1252 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 63 mm dia. UPVC pipe and 20mm dia. HDPE pipe at different places for installation of FHTC under Dharampur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000528/2021-2022 | 359/MAAD | 07/03/2022 | 30 | ACHARYYA CONSTRUCTION | 4.82 | 4.82 | 1
1253 | Malda Division | Malda Mechanical Division | Soil Investigation and design of substructure for Over Head Reservoirs for BHALUKA FATEPUR Piped Water Supply Scheme at Harishchandapur-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00486/2022-2023 | BP-2022-23-192 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
1254 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 180 Mtr. Deep Big dia Tube well (1 No) at BHALUKA FATEPUR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000016/2023-2024 | 1673/MD | 18/04/2023 | 449 | MERCURY ENGINEERING COMPANY | 10.71 | 0 | 95
1255 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 4th Tube Well site of Bhaluka Fatepur Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000025/2022-2023 | 1192/MD | 24/05/2022 | 31 | M/S GULFAM CONSTRUCTION. | 4.78 | 0 | 0
1256 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 3rd Tube Well site of Bhaluka Fatepur Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000026/2022-2023 | 1193/MD | 24/05/2022 | 31 | M/S SRINJOYEE | 4.78 | 0 | 0
1257 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 02 (Two) Nos. 150mm. Dia. x 100mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Bhaluka Fatepur Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000046/2022-2023 | 1395/MD | 14/06/2022 | 30 | A. L. ENGINEERING SOLUTION | 10 | 0 | 0
1258 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of BHALUKA FATEPUR Piped Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000083/2023-2024 | 2173/MD | 07/06/2023 | 30 | M/S EHAN ENTERPRISE | 11.04 | 0 | 0
1259 | Malda Division | Malda Mechanical Division | Dismantling of Exsiting RCC Road and Construction of RCC Road from Bhaluka fatepur High school to Bhaluka Hospital for clear water main UPVC/DI pipe line in connection with Augmentation of Bhaluka fatepur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000122/2025-2026 | 2474/MD | 28/05/2025 | 45 | M/S SABANA CONSTRUCTION | 21.9 | 0 | 0
1260 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Bhaluka Fatepur Pipe Water Supply Scheme at Harishchandrapur-II Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000136/2022-2023 | 1828/MD | 04/08/2022 | 90 | GHOSH BROTHERS | 348.1 | 309.95 | 68
1261 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Bhaluka Fatepur Water Supply Scheme in Harischandrapur-II block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000152/2021-2022 | 1750/MD | 15/06/2021 | 14 | INDRANIL DUTTA & ACCOCIATES | 2.86 | 2.86 | 1
1262 | Malda Division | Malda Mechanical Division | Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of Bhaluka Fatepur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000174/2024-2025 | 2949/MD | 10/06/2024 | 45 | SK ENTERPRISE | 6.57 | 0 | 95
1263 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube Well site of Bhaluka Fatepur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000177/2024-2025 | 2952/MD | 10/06/2024 | 30 | SARIF BUILDERS | 9.93 | 0 | 0
1264 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 700 M3 Capacity OHR with FHTC (Mouza-Bhaluka) of Bhaluka Fatepur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000354/2023-2024 | 3020/MD | 08/08/2023 | 711 | GHOSH BROTHERS | 283.26 | 0 | 0
1265 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bhaluka Fatepur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000623/2024-2025 | 5830/MD | 22/11/2024 | 90 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD.JAGADANANDAPUR, AKHRA, KATW | 78.05 | 0 | 0
1266 | Malda Division | Malda Mechanical Division | Continuation work order for Route survey for distribution network design for augmentation of Bhaluka Fatepur Water Supply Scheme in Harischandrapur-II block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000695/2021-2022 | 1840/MD | 30/06/2021 | 14 | INDRANIL DUTTA & ACCOCIATES | 1.45 | 0 | 0
1267 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for BHALUKA FATEPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000962/2023-2024 | 715/MD | 09/02/2024 | 45 | J. M. CONSTRUCTION | 14.06 | 2.02 | 80
1268 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Bhaluka Fatepur, Kandaran Zone-I & II, Chhattrak PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000963/2024-2025 | 652/MD | 19/02/2025 | 7 | M/S SABANA CONSTRUCTION | 0.9 | 0 | 100
1269 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at BHALUKA FATEPUR Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000971/2023-2024 | 830/MD | 21/02/2024 | 45 | OLI CONSTRUCTION | 4.17 | 0 | 0
1270 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000012/2022-2023 | 1871/MD | 16/08/2022 | 0 | Resource Division | 65.9 | 0 | 0
1271 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000026/2023-2024 | 1607/MD | 11/04/2023 | 0 | Resource Division | 29.16 | 0 | 0
1272 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000037/2023-2024 | 1801 | 27/04/2023 | 0 | Resource Division | 59.54 | 0 | 0
1273 | Malda Mechanical | Malda Mechanical Division | New service connection at BHALUKA- FAFATEPUR PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( Bhaluka c.c.c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/01170/2024-2025 | BP-2024-25-351 | 24/06/2024 | 0 | W.B.S.E.D.C.LTD | 9.85 | 0 | 0
1274 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- III & IV of Bhaluka Fatepur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/009046) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000259/2023-2024 | 2232/MLMD | 19/07/2023 | 833 | A.K. SIKDAR | 21.58 | 16.52 | 77
1275 | Malda Mechanical | Malda Mechanical Division | Supply, installation & commissioning of electro-mechanical components at T/W no. I & II of Augmentation of Bhaluka Fatepur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/001058/2022-2023 | 267/MLMD | 24/02/2023 | 90 | SHREE BISHNU CONSTRUCTION | 7.97 | 5.61 | 70
1276 | Malda Division | Malda Mechanical Division | Formal work order for Augmentation of DEOTALA Piped water supply scheme for the work of Geotechnical Study,construction of 500 Cum RCC OHR,Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Gazole Dev Block under Malda Division PH Engg Dte. In the District of Malda | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000003/2022-2023 | 868/MD | 08/04/2022 | 1573 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 460.03 | 178.96 | 50
1277 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of Rising main with connection between 1st Tube well and 3 rd Tube well and condtructtion of standpost for DEOTALA Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000031/2022-2023 | 1308/MD | 01/06/2022 | 30 | JIBON GHOSH | 4.43 | 2.05 | 0
1278 | Malda Division | Malda Mechanical Division | Augmentation of Head Work Site pump House at DEOTALA Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000117/2025-2026 | 2468/MD | 28/05/2025 | 45 | S. R. ENTERPRISE | 2.06 | 0 | 100
1279 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Deotala Water Supply Scheme in Gazole block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000148/2021-2022 | 1746/MD | 15/06/2021 | 14 | HORIZEN | 2.86 | 1.78 | 1
1280 | Malda Division | Malda Mechanical Division | Dedicated Pipe laying for better Functionality and Providing Balance FHTC for Deotala Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000217/2025-2026 | 3778/MD | 04/08/2025 | 180 | MANIK CHOUDHURY | 65.09 | 0 | 0
1281 | Malda Division | Malda Mechanical Division | Sinking of 200mm (all through) Big dia. Tube Well, Construction of Pump House, Boundary wall and allied works of Deotala PWSS under Gazole Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000233/2025-2026 | 4237/MD | 29/08/2025 | 150 | HARUN ALL RASHID & BROTHERS | 55.58 | 0 | 0
1282 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Deotala Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000718/2024-2025 | 6409/MD | 19/12/2024 | 331 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 26.07 | 0 | 0
1283 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Deotala Piped Water Supply Scheme at Deotala Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000889/2023-2024 | 163/MD | 08/01/2024 | 449 | M I CONSTRUCTION | 14.99 | 0 | 100
1284 | Malda Division | Malda Mechanical Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Car-2) (Period from 01/03/2025 to 31/08/2025). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/001038/2024-2025 | 752/MD | 27/02/2025 | 181 | SINGH BROTHERS | 0.86 | 0 | 0
1285 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000004/2022-2023 | 1106/MD | 17/05/2022 | 0 | Resource Division | 37.39 | 0 | 0
1286 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000042/2022-2023 | 1585/MD | 28/03/2023 | 0 | Resource Division | 2.3 | 0 | 0
1287 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000068/2025-2026 | 5584/MD | 30/10/2025 | 0 | Resource Division | 3.06 | 0 | 0
1288 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000194/2023-2024 | 816/MD | 21/02/2024 | 0 | Resource Division | 45.08 | 0 | 0
1289 | Malda Mechanical | Malda Mechanical Division | Supply, installation and commissioning of electro-mechanical components of T/W no. II and making compound lighting arrangement at T/W no. I of Augmentation of Deotala Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/005108) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000607/2023-2024 | 2723/MLMD | 14/08/2023 | 180 | JIBU SINGHA | 14.75 | 0 | 0
1290 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Sahapur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000274/2024-2025 | 3201/MD | 27/06/2024 | 188 | ABANI BHUSAN GHOSH | 17.12 | 0 | 100
1291 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of SAHAPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000375/2022-2023 | 780/MD | 17/02/2023 | 30 | SAUDAGAR (INDIA) | 9.2 | 9.18 | 0
1292 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Implementation of SAHAPUR Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000490/2022-2023 | 594/MD | 09/02/2023 | 570 | M/S /FAIZUL HAQUE BISWAS | 57.62 | 29.26 | 90
1293 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000020/2023-2024 | 1616/MD | 11/04/2023 | 0 | Resource Division | 2.45 | 0 | 0
1294 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000020/2024-2025 | 3996/MD | 08/08/2024 | 0 | Resource Division | 2.34 | 0 | 0
1295 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000081/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 1.2 | 0 | 0
1296 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SAHAPUR ,Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000292/2023-2024 | 3004353830 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 8.31 | 8.31 | 100
1297 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Sahapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013245) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000329/2023-2024 | 2331/MLMD | 26/07/2023 | 826 | BEE GEE CONSTRUCTION. | 13.37 | 8.73 | 74
1298 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No-3 ( 135 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at PURBA BINODPUR Water Supply Scheme of Gazole Block .under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000310/2022-2023 | 2305/MD | 28/09/2022 | 30 | DUTTA ENTERPRISE | 9.06 | 9.02 | 1
1299 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of PURBA BINODPUR Water Supply Scheme of Gazole Block .under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000346/2022-2023 | 2801/MD | 24/11/2022 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.69 | 6.53 | 0
1300 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for PURBA BINODPUR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000357/2022-2023 | 2506/MD | 03/11/2022 | 530 | TARUN KUMAR DEY | 41.23 | 38.6 | 1
1301 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Purba Biniodpur Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000838/2024-2025 | 1004/MD | 12/03/2025 | 60 | SAHA CONSTRUCTION | 8.61 | 0 | 100
1302 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Purba Binodpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000996/2023-2024 | 1511/MD | 16/03/2024 | 230 | SARAJ TRADERS | 26.4 | 0 | 100
1303 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Purba Binodpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001001/2023-2024 | 1180/MD | 14/03/2024 | 530 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 10.14 | 1.61 | 60
1304 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000052/2025-2026 | 5599/MD | 30/10/2025 | 0 | Resource Division | 6.21 | 0 | 0
1305 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Purba Binodpur PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000094/2023-2024 | 3004293401 | 16/05/2023 | 90 | W.B.S.E.D.C.LTD | 3.63 | 3.63 | 0
1306 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Source Augmentation of Purba Binodpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012798) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001128/2022-2023 | 511/MLMD | 20/03/2023 | 120 | M/S PARIMAL DAS. | 10.57 | 10.36 | 100
1307 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200mm. Dia ) Tube Well no-4 & 5 ( 160 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at KUTUB SAHAR Water Supply Scheme of Gazole Block. under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000338/2022-2023 | 2510/MD | 03/11/2022 | 30 | A. D. D. ASSOCIATES | 10.01 | 8.57 | 100
1308 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of KUTUB SAHAR Water Supply Scheme of Gazole Block .under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000348/2022-2023 | 2802/MD | 24/11/2022 | 45 | MARSS INTERNATIONAL | 6.69 | 6.69 | 100
1309 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C pipe line (damage due to widening of road) by different dia UPVC pipe for KUTUB SAHAR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000361/2022-2023 | 2604/MD | 10/11/2022 | 690 | BEE GEE CONSTRUCTION | 55.12 | 45.37 | 65
1310 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Tube Well No.-5 site in connection with Source Augmentation of KUTUB SAHAR Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000366/2023-2024 | 3055/MD | 09/08/2023 | 45 | A. L. ENGINEERING SOLUTION | 4.15 | 3.94 | 100
1311 | Malda Division | Malda Mechanical Division | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well No. - 5 (160 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at KUTUB SAHAR Water Supply Scheme of Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000445/2023-2024 | 3352/MD | 29/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 11.88 | 11.63 | 100
1312 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35 m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at 5th Tube Well Site of Kutub Sahar Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000720/2024-2025 | 6411/MD | 19/12/2024 | 45 | ZEOLITE FRESH INDIA | 17.27 | 0 | 0
1313 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, Pump House No.-2, Pump House No.-3, Earth filling and 3 Nos. Boundary wall at Kutub Sahar Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000836/2024-2025 | 1072/MD | 19/03/2025 | 60 | M. S. AGENCY | 12.92 | 0 | 100
1314 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Tubewell no. 4 site of Kutubshar Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001005/2023-2024 | 1183/MD | 14/03/2024 | 180 | M/S JHA CONSTRUCTION | 17.28 | 0 | 0
1315 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Tubewell site at Khord Babupur Mouza of Kutub Sahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001006/2023-2024 | 1193/MD | 14/03/2024 | 293 | AHONA ENTERPRISE | 10.71 | 0 | 100
1316 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Tubewell site at Misipur Mouza of Kutubsahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001024/2023-2024 | 1250/MD | 15/03/2024 | 382 | SATELLITE CONSTRUCTION | 9.6 | 0 | 100
1317 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000022/2022-2023 | 2409/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
1318 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000027/2025-2026 | 2828/MD | 11/06/2025 | 0 | Resource Division | 7.85 | 0 | 0
1319 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. IV & V of Source Augmentation Kutub Sahar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014339) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000506/2023-2024 | 2577/MLMD | 04/08/2023 | 120 | MAA BHABOTARINE ENTERPRISE. | 23.05 | 22.7 | 100
1320 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Kutubsahar PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000860/2023-2024 | 3004402679 | 29/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.54 | 3.54 | 100
1321 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. V of Kutub Sahar , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001890/2023-2024 | 3004496749 | 28/11/2023 | 90 | W.B.S.E.D.C.LTD | 5.28 | 5.28 | 100
1322 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jamalpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000001/2025-2026 | 1298/MD | 04/04/2025 | 452 | UTTAM KUMAR GHOSH | 96.59 | 0 | 0
1323 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Implementation of JAMALPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000008/2023-2024 | 1570/MD | 10/04/2023 | 933 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 735.7 | 321.91 | 30
1324 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head work site of Jamalpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000488/2024-2025 | 5001/MD | 27/09/2024 | 45 | PABITRA MANDAL | 23.69 | 0 | 0
1325 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of JAMALPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000667/2022-2023 | 1061/MD | 15/03/2023 | 60 | BINA CONSTRUCTION | 51.95 | 51.95 | 100
1326 | Malda Division | RWS Malda Sub-Division | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works of Krishnapur, Horgoa, Perapur, Jamalpur & Rajarampur PWSS under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000953/2024-2025 | 642/MD | 19/02/2025 | 7 | SADHANA CONSTRUCTION | 0.8 | 0 | 0
1327 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tubewell site of Jamalpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/001033/2023-2024 | 1259/MD | 15/03/2024 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 8.5 | 0 | 0
1328 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000146/2023-2024 | 123/MD | 06/01/2024 | 0 | Resource Division | 46.72 | 0 | 0
1329 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Jamalpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013493) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000739/2023-2024 | 2800/MLMD | 17/08/2023 | 714 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 27.35 | 17.61 | 30
1330 | Malda Division | RWS Malda Sub-Division | Laying of Pipeline work at Mianagar Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000277/2024-2025 | 3197/MD | 27/06/2024 | 45 | CHARU CONSTRUCTION | 18.22 | 4.75 | 100
1331 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200mm. Dia) Tube Well no-3 (100 Mtr. deep )by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MIANAGAR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000305/2022-2023 | 2300/MD | 28/09/2022 | 30 | MECHANO TRADING CO. | 7.59 | 6.4 | 100
1332 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of MIANAGAR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000341/2022-2023 | 2548/MD | 03/11/2022 | 45 | ANJIMA CONSTRUCTION CO. | 6.69 | 6.67 | 100
1333 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for MIANAGAR Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000355/2022-2023 | 2504/MD | 03/11/2022 | 45 | DEBAPRIYA SAHA | 76.83 | 52.55 | 100
1334 | Malda Division | RWS Malda Sub-Division | Replacement of 200 mm (all through)Big Dia. Tubewell No:-1 (130MDeep) at Headwork site by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at MIANAGAR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte,in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000449/2024-2025 | 4806/MD | 13/09/2024 | 152 | JOY GURU ENTERPRISE | 9.56 | 0 | 100
1335 | Malda Division | RWS Malda Sub-Division | Augmentation of Head work site Pump House,PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at MIANAGAR Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000880/2024-2025 | 1119/MD | 21/03/2025 | 45 | CHARU CONSTRUCTION | 9.63 | 0 | 0
1336 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Mianagar Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/001027/2023-2024 | 1253/MD | 15/03/2024 | 30 | CHARU CONSTRUCTION | 9.61 | 0 | 0
1337 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000073/2025-2026 | 5541/MD | 29/10/2025 | 0 | Resource Division | 10.77 | 0 | 0
1338 | Malda Mechanical | RWS Malda Sub-Division | Quotation Payment of MIYANAGAR Under AIHO CCC Under the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/00204/2024-2025 | BP-2024-25-63 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.17 | 0 | 0
1339 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Mianagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014342) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000192/2023-2024 | 2144/MLMD | 07/07/2023 | 120 | A.S. ENGINEERING | 10.52 | 10.45 | 100
1340 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. of Mianagar, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000462/2023-2024 | 3004369303 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.64 | 4.64 | 100
1341 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of DUBA KHOSKON Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000374/2023-2024 | 3118/MD | 11/08/2023 | 509 | M/S NANDY ENTERPRISES | 904.54 | 0 | 0
1342 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at DubaKhaskon Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000726/2024-2025 | 6417/MD | 19/12/2024 | 286 | M/S MANDAL & SONS | 36.96 | 0 | 0
1343 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000038/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 15.2 | 0 | 0
1344 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000069/2025-2026 | 5585/MD | 30/10/2025 | 0 | Resource Division | 3.42 | 0 | 0
1345 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000168/2023-2024 | 249/MD | 10/01/2024 | 0 | Resource Division | 14.04 | 0 | 0
1346 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dubakhoskan, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/03688/2023-2024 | BP-2023-24-671 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.58 | 0 | 0
1347 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Dubakhoskan, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/03689/2023-2024 | BP-2023-24-672 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.51 | 0 | 0
1348 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Duba Khoskoan Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014431) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000378/2023-2024 | 2386/MLMD | 28/07/2023 | 869 | MANIK CHANDRA SAHA. | 27.39 | 19.31 | 70
1349 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of BISHANPUR Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000042/2023-2024 | 1911/MD | 11/05/2023 | 270 | A. K. CONSTRUCTION | 349.38 | 172.57 | 25
1350 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Bishanpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000216/2024-2025 | 3037/MD | 13/06/2024 | 30 | A. K. CONSTRUCTION | 25.52 | 0 | 0
1351 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Bishanpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000217/2024-2025 | 3038/MD | 13/06/2024 | 30 | A. K. CONSTRUCTION | 10.45 | 0 | 0
1352 | Malda Division | Malda Mechanical Division | Laying of Distribution of UPVC Pipeline of BISHANPUR Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000748/2023-2024 | 4995/MD | 15/12/2023 | 601 | M/S ALISA CONSTRUCTIION | 93.44 | 51.26 | 95
1353 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bishanpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000752/2024-2025 | 70 | 13/01/2025 | 180 | A. K. CONSTRUCTION | 84.78 | 0 | 0
1354 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Bhakri, Chandrapara & Dhangra Bishanpur GP under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000945/2024-2025 | 634/MD | 19/02/2025 | 7 | BIDYUT MAHALDAR | 0.9 | 0 | 0
1355 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Choupaldanga, Wari, Gochiya, Bangrua, Kharangapur Jabra, Bishanpur PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000957/2024-2025 | 646/MD | 19/02/2025 | 7 | RAHANUL ALAM | 0.95 | 0 | 100
1356 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000034/2023-2024 | 1803/MD | 27/04/2023 | 0 | Resource Division | 38.38 | 0 | 0
1357 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000123/2023-2024 | 93/MD | 05/01/2024 | 0 | Resource Division | 8.31 | 0 | 0
1358 | Malda Mechanical | Malda Mechanical Division | New service connection at BISHANPUR T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( KUSHIDA c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00234/2024-2025 | BP-2024-25-86 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.65 | 0 | 0
1359 | Malda Mechanical | Malda Mechanical Division | New service connection at BISHANPUR PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( KUSHIDA c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00235/2024-2025 | BP-2024-25-87 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 14.51 | 0 | 0
1360 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Bishanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014466) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000376/2023-2024 | 2384/MLMD | 28/07/2023 | 1068 | DAS ENTERPRISE. | 26.53 | 1.21 | 82
1361 | Malda Division | RWS Malda Sub-Division | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 2nd Tube Well Site of NEMUA Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000006/2025-2026 | 2393/MD | 26/05/2025 | 75 | SURAJIT MONDAL | 5.98 | 0 | 0
1362 | Malda Division | RWS Malda Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning,and 3 (three) months Trial Run and 40 cum/hr. capacity of Iron Elimination Plants (Pressure type) with provision of polishing unit alongwith Construction of 3.60 mtr.X 3.00 mtr Blower Room in connection with source Augmentation at 3rd Tube Well site of NEMUA Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000609/2023-2024 | 4113/MD | 10/10/2023 | 417 | DEBAPRIYA SAHA | 17.17 | 15.43 | 100
1363 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for NEMUA Piped Water Supply Scheme at Old Malda Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000701/2022-2023 | 1158/MD | 20/03/2023 | 548 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 23.88 | 18.55 | 100
1364 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 (102.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at NEMUA Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000710/2022-2023 | 1168/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 7.8 | 6.43 | 100
1365 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Nemua Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000731/2022-2023 | 1205/MD | 21/03/2023 | 45 | BINA CONSTRUCTION | 4.15 | 4.14 | 100
1366 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall and Pathway at 3rd Tube Well Site of Nemua Piped Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000965/2023-2024 | 804/MD | 21/02/2024 | 273 | GOUTAM SAHA | 8.77 | 8.72 | 60
1367 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000184/2023-2024 | 776/MD | 20/02/2024 | 0 | Resource Division | 6.16 | 0 | 0
1368 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Source Augmentation Nemua Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000319/2024-2025 | 2946/MLMD | 11/09/2024 | 90 | JOY MAA SANTOSHI ENTERPRISE. | 11.4 | 10.02 | 100
1369 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Nemua PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/001519/2023-2024 | 3004375746 | 01/09/2023 | 90 | W.B.S.E.D.C.LTD | 7.84 | 7.84 | 100
1370 | Malda Division | RWS Malda Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 20m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Sailpur Water Supply Scheme of Englishbazar Block under Malda Division P.H.E Dte in the District of Malda. (3rd Call). | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000013/2025-2026 | 2421/MD | 27/05/2025 | 180 | M/S KUNDU CONSTRUCTION | 14.62 | 0 | 0
1371 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for SAILPUR Piped Water Supply Scheme at Englishbazar Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000700/2022-2023 | 1157/MD | 20/03/2023 | 45 | S. R. CONSTRUCTION | 18.8 | 18.8 | 79
1372 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 96.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at SAILPUR Water Supply Scheme of Englishbazar Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000709/2022-2023 | 1167/MD | 20/03/2023 | 30 | ABHIJIT PAUL | 6.21 | 6.04 | 100
1373 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Sailpur Piped Water Supply Scheme at Englishbazar Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000759/2022-2023 | 1306/MD | 23/03/2023 | 45 | M/S A. B. CONSTRUCTION | 4.14 | 4.12 | 95
1374 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sailpur Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000826/2024-2025 | 703/MD | 21/02/2025 | 45 | CHARU CONSTRUCTION | 27.37 | 0 | 0
1375 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000182/2023-2024 | 775/MD | 20/02/2024 | 0 | Resource Division | 1.85 | 0 | 0
1376 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of source augmentation of Sailpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte.(TSM/016471) | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000578/2023-2024 | 2627/MLMD | 10/08/2023 | 180 | KUNDU CONSTRUCTION. | 10.52 | 10.46 | 70
1377 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Sailpur, Fulbari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/001625/2023-2024 | 3004454388 | 09/10/2023 | 90 | W.B.S.E.D.C.LTD | 7.69 | 7.69 | 100
1378 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Fatepur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000002/2025-2026 | 1305/MD | 04/04/2025 | 120 | MILLENNIUM ENTERPRISE | 105.3 | 0 | 0
1379 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Fatepur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000272/2024-2025 | 3229/MD | 28/06/2024 | 637 | THREE BROTHERS CONSTRUCTION & CO | 26.65 | 24.18 | 60
1380 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of FATEPUR and its adjoinining mouzas Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000642/2022-2023 | 1028/MD | 13/03/2023 | 1385 | GHOSH BROTHERS | 1157.58 | 181.56 | 50
1381 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000011/2025-2026 | 2585/MD | 30/05/2025 | 0 | Resource Division | 13.17 | 0 | 0
1382 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000147/2023-2024 | 124/MD | 06/01/2024 | 0 | Resource Division | 121.21 | 0 | 0
1383 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000153/2023-2024 | 243/MD | 10/01/2024 | 0 | Resource Division | 13.18 | 0 | 0
1384 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Fatepur, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/00769/2024-2025 | BP-2024-25-195 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 10.78 | 0 | 0
1385 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Fatepur, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/00776/2024-2025 | BP-2024-25-196 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 11.26 | 0 | 0
1386 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Fatepur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015785) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000380/2023-2024 | 2388/MLMD | 28/07/2023 | 180 | NUPUR CHANDRA HALDER | 42.13 | 21.89 | 51
1387 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) of capacity 52.0 Cum/ Hr at Gopalpur Water Supply Scheme Zone-I under Malda Arsenic Area W/S Division, P.H.E. Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000262/2020-2021 | 128/MAAD | 21/01/2021 | 270 | MILLENNIUM ENTERPRISE | 139.74 | 111.09 | 80
1388 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Repairing work of Existing house connection, and Laying of damage UPVC Pipeline at Budhia Dubri under Jote Basanta Distribution zone under Malda Arsenic Area Water Supply Division PHED. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000267/2022-2023 | 1869MAAD | 28/09/2022 | 45 | M/S PARIMAL DAS | 6.24 | 5.6 | 1
1389 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 42.00 M³/ Hr. capacity Iron Elimination Plant (Pressure type) for Gopalpur Zone-II Water Supply Scheme at Manikchak Dev. Block under Malda Arsenic Area Water Supply Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000452/2022-2023 | 401/MAAD | 06/03/2023 | 514 | SHREE BISHNU CONSTRUCTION | 18.65 | 9.84 | 54
1390 | Malda Mechanical | Malda Arsenic Area W/S Division | NEW SERVICE CONNECTION CHARGE FOR GOPALPUR W S SCHEME | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | BILL/01073/2023-2024 | BP-2023-24-94 | 13/07/2023 | 0 | W.B.S.E.D.C.LTD | 1.73 | 0 | 0
1391 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Arsenic Iron Removal Plant at Gopalpur (Zone-I) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000014/2023-2024 | 763/MLMD | 26/04/2023 | 180 | DILIP MAHATO. | 46.07 | 32.64 | 61
1392 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 120 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000007/2023-2024 | 692/MAAD | 13/04/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 7.38 | 6.02 | 100
1393 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 5.40 mtr.X 3.6 mtr 3rd Pump House with Water Supply and sanitary arrangement in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000008/2023-2024 | 691/MAAD | 13/04/2023 | 60 | HIND CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 6.52 | 4.94 | 100
1394 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 23.38 M³/ Hr. capacity Iron Elimination Plant (Pressure type) including construction of switch room in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme at English Bazar Dev. Block under Malda Arsenic Area Water Supply Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000048/2023-2024 | 947/MAAD | 23/05/2023 | 540 | SOVON KUMAR DAS | 15.66 | 3.03 | 100
1395 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System and other allied works at Satichura in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000221/2023-2024 | 1710/MAAD | 20/09/2023 | 90 | M/S. AYUSH BUILDERS | 11.67 | 9.38 | 75
1396 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at 3rd Pump House Site, Laying of distribution system and providing FHTC of Uttar Nazirpur Distribution Zone at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000247/2024-2025 | 1700/MAAD | 19/11/2024 | 90 | DEY CONSTRUCTION | 25.94 | 0 | 100
1397 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Route servey & design for prepration of DPR of Uttar Nazirpur, Sakullapur & Nabinagar Piped Water Supply Scheme at Englishbazar & Kaliachak - II Development Block under Malda Arsenic Area W/S Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000249/2023-2024 | 1763/MAAD | 30/09/2023 | 15 | FUTURE | 0.99 | 0.99 | 100
1398 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System and other allied works at Daibakipur & Paharipara in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000274/2023-2024 | 3074/MAAD | 14/12/2023 | 60 | MAHA MAYA CONSTRUCTION | 16.89 | 12.95 | 85
1399 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Uttar Nazirpur Water Supply Scheme (Augmentation) at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000384/2023-2024 | 304/MAAD | 11/03/2024 | 30 | PRITAM ENTERPRISE | 9.05 | 8.22 | 100
1400 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of source augmentation of Uttar Nazirpur Water Supply Scheme in the District of under Malda Mechanical Division, PHE Dte.(TSM/017480) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000582/2023-2024 | 2631/MLMD | 10/08/2023 | 180 | FUTURE | 10.51 | 10.47 | 80
1401 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Daibakipur, Uttar Nazirpur, Fulbari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000861/2023-2024 | 3004409374 | 31/08/2023 | 90 | W.B.S.E.D.C.LTD | 4.88 | 4.88 | 100
1402 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dilalbati Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000125/2025-2026 | 2483/MD | 28/05/2025 | 126 | M/S GLOBAL ENTERPRISE | 4.85 | 0 | 0
1403 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of DILALBATI Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000387/2023-2024 | 3285/MD | 23/08/2023 | 1010 | ZEST INFRACON | 155.98 | 78.75 | 50
1404 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of DILALBATI Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000681/2022-2023 | 1130/MD | 20/03/2023 | 45 | SOFIKUL ISLAM | 6.54 | 5.75 | 100
1405 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of DILALBATI Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000683/2022-2023 | 1135/MD | 20/03/2023 | 45 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 4.15 | 4.14 | 100
1406 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Saidpur, Alal Zone-I, II, III, Rahimpur, Dilalbati & Altor PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000952/2024-2025 | 641/MD | 19/02/2025 | 7 | S. N. CONSTRUCTION | 0.95 | 0 | 0
1407 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000064/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 7.53 | 0 | 0
1408 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000166/2023-2024 | 242/MD | 10/01/2024 | 0 | Resource Division | 2.56 | 0 | 0
1409 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dilalbati, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/03686/2023-2024 | BP-2023-24-669 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 19.71 | 0 | 0
1410 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Dilalbati, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/03687/2023-2024 | BP-2023-24-670 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 6.45 | 0 | 0
1411 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Dilalbati Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014129) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000499/2023-2024 | 2569/MLMD | 04/08/2023 | 907 | M/S PARIMAL DAS. | 23.98 | 14.5 | 85
1412 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Gayeshbari Piped Water supply scheme (Head Work Site & 2nd Tube Well Site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda (2nd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000137/2023-2024 | 1478/MAAD | 01/08/2023 | 45 | ASHIS CONSTRUCTION | 14.64 | 9.19 | 50
1413 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site of Gayeshbari Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000138/2023-2024 | 1479/MAAD | 01/08/2023 | 335 | PRITAM ENTERPRISE | 5.02 | 0 | 100
1414 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Gayeshbari Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000239/2024-2025 | 1693/MAAD | 19/11/2024 | 408 | M/S MOON LIGHT CONSTRUCTION & CO. | 75.67 | 0 | 0
1415 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Nayabasti, Jamirghata Station Road for Gayeshbari Piped Water supply scheme at Kaliachak-I Block under Malda Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000273/2023-2024 | 3073/MAAD | 14/12/2023 | 60 | GHOSH CONSTRUCTION | 18 | 12.77 | 100
1416 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System including Supply of all type of specials & valves for Gayeshbari Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000276/2023-2024 | 3076/MAAD | 14/12/2023 | 565 | FUTURE | 96.7 | 0 | 35
1417 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Gayeshbari Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (2ND Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000280/2023-2024 | 3082/MAAD | 14/12/2023 | 688 | MAHBUB AND SONS | 225.34 | 45.91 | 75
1418 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Gayeshbari Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. (2nd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000362/2023-2024 | 52/MAAD | 18/01/2024 | 439 | WIST WATER SOLUTIONS PRIVATE LIMITED | 166.2 | 0 | 1
1419 | Malda Mechanical | Malda Arsenic Area W/S Division | QUOTATION PAYMENT FOR GAYESHBARI W/S SCHEME PH NO 2 UNDER SUJAPUR CCC UNDER MALDA DISTRICT | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | BILL/00213/2025-2026 |  | 24/04/2025 | 0 | W.B.S.E.D.C.LTD | 10.03 | 0 | 0
1420 | Malda Mechanical | Malda Arsenic Area W/S Division | Quotation Payment for Gayeshbari under SUJAPUR CCC in the District Of Malda | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | BILL/03551/2023-2024 | BP-2023-24-564 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 7.72 | 0 | 0
1421 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Gayeshbari Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018180) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000656/2023-2024 | 2685/MLMD | 11/08/2023 | 180 | SUNRISE ENGINEERING CORPORATION. | 63.77 | 0 | 0
1422 | Malda Division | Malda Mechanical Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Period from 15/06/2024 to 14/12/2024). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/00778/2024-2025 | BP-2023-24-394 | 16/12/2024 | 0 | RUQAIYA ENTERPRISE | 0.39 | 0 | 0
1423 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of ALAL ZONE- III Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000096/2023-2024 | 2324/MD | 08/06/2023 | 1152 | SAMBHU NATH SARKAR | 283.63 | 147.49 | 85
1424 | Malda Division | Malda Mechanical Division | Dedicated Pipe laying for better Functionality and Providing Balance FHTC, Construction of Approach Road, Land development and allied work for ALAL Zone-III Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000215/2025-2026 | 3776/MD | 04/08/2025 | 60 | SAMBHU NATH SARKAR | 11.17 | 0 | 0
1425 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Alal Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000267/2024-2025 | 3214/MD | 27/06/2024 | 247 | SAMBHU NATH SARKAR | 28.48 | 0 | 100
1426 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000638/2024-2025 | 5917/MD | 26/11/2024 | 176 | ABHIJIT CONSTRUCTION | 14.16 | 0 | 100
1427 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Alal Zone-III Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000688/2021-2022 | 653/MD | 22/03/2022 | 15 | TECHVISION | 2.95 | 2.94 | 1
1428 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at ALAL ZONE-III Piped Water Supply Scheme under Gazole Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000972/2023-2024 | 831/MD | 21/02/2024 | 45 | SADHANA CONSTRUCTION | 4.16 | 4.16 | 100
1429 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000054/2025-2026 | 5601/MD | 30/10/2025 | 0 | Resource Division | 2.06 | 0 | 0
1430 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000072/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 19.37 | 0 | 0
1431 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000157/2023-2024 | 245/MD | 10/01/2024 | 0 | Resource Division | 4.42 | 0 | 0
1432 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Alal Zone-III, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/03716/2023-2024 | BP-2023-24-711 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.31 | 0 | 0
1433 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and Trial Operation of electro-mechanical components at T/W no I and Supply, installation, commissioning of electro-mechanical components at T/W no II and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at headwork site of Alal Zone-III Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011885) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000604/2023-2024 | 2721/MLMD | 14/08/2023 | 2005 | M/S TRILOCHAN CONSTRUCTION CO. | 24.32 | 0 | 47
1434 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Bakhrabad Piped Water supply scheme of Kaliachak-III Block (Head work site) under Malda arsenic Area water supply Division in the disrtict of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000133/2023-2024 | 1475/MAAD | 01/08/2023 | 45 | MD. TALEB ALI | 7.65 | 4.92 | 100
1435 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System & others allied works at Char Bakrabad under Bakhrabad Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte.(Kaliachak-III) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000134/2023-2024 | 1476/MAAD | 01/08/2023 | 60 | DEY CONSTRUCTION | 65.47 | 58.13 | 80
1436 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System & others allied works at Kumbhira under Bakhrabad Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte.(Kaliachak-III) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000135/2023-2024 | 1477/MAAD | 01/08/2023 | 366 | S. R. CONSTRUCTION | 63.18 | 62.47 | 95
1437 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 250 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Bakrabad Piped Water Supply scheme at Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000224/2023-2024 | 1733/MAAD | 22/09/2023 | 736 | MI CONSTRUCTION | 94.8 | 56.92 | 80
1438 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site , C.C road from existing road to Head works Site and Land Development Work for HWS ,Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & Jal Swapna), Laying of rising main from Tube Well Site to HWS & including supply of all specials & valves for Bakhrabad Piped Water Supply scheme at Kaliachak-III Development Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000245/2024-2025 | 1699/MAAD | 19/11/2024 | 45 | SOVON KUMAR DAS | 40.39 | 0 | 0
1439 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Bakrabad Piped Water supply scheme of Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000361/2023-2024 | 51/MAAD | 18/01/2024 | 561 | WIST WATER SOLUTIONS PRIVATE LIMITED | 131.25 | 0 | 15
1440 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | RTOR000004/2023-2024 | 626/MAAD | 05/04/2023 | 0 | Resource Division | 6.21 | 0 | 0
1441 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I and Arsenic Iron Removal Plant at Bakhrabad Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017774) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000663/2023-2024 | 2689/MLMD | 11/08/2023 | 716 | GHOSH BROTHERS... | 49.58 | 0 | 0
1442 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of Bakhrabad PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/001908/2023-2024 | 3004379428 | 01/08/2023 | 90 | W.B.S.E.D.C.LTD | 2.27 | 2.27 | 100
1443 | Malda Division |  | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of MAHAMMADPUR Water Supply Scheme at Malda Old Block under Malda Division, PHE Dte. |  |  | ORD/000028/2020-2021 | 1963/MD | 31/08/2020 | 30 | A. K. CONSTRUCTION | 25.17 | 44.97 | 0
1444 | Malda Division |  | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. |  |  | ORD/000166/2020-2021 | 2719/MD | 10/11/2020 | 30 | MANAS KUMAR SAHA | 50.07 | 12 | 1
1445 | Malda Division |  | Replacement of 200 mm dia. X 150 mm Dia.) Tubewell No:-2 (130 M Deep) by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at MAHAMMADPUR Water Supply Scheme of Old Malda Block under Malda Division, PHE Dte. |  |  | ORD/000451/2024-2025 | 4807/MD | 13/09/2024 | 78 | GOBINDA ENTERPRISE | 8.29 | 0.38 | 100
1446 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of MAHAMMADPUR Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000721/2023-2024 | 4770/MD | 05/12/2023 | 45 | M/S EHAN ENTERPRISE | 8.07 | 8.05 | 100
1447 | Malda Mechanical |  | Formal Work Order for Design, manufacture, installation and commissioning of rolling pontoon type dismantling barge along with electro-mechanical equipments on river Fulhar at lntake Station of Balupur water supply scheme under Ratua-l Block in the District of Malda under Malda Mechanical Division, PHE Dte. |  |  | ORD/002576/2023-2024 | 995/MLMD | 07/03/2024 | 184 | SUNRISE ENGINEERING CORPORATION. | 105.37 | 42.04 | 39
1448 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Implementation of SERBABAR BALARAMPUR Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000065/2023-2024 | 2019/MD | 18/05/2023 | 959 | JAHANGIR ALAM | 596.09 | 189.24 | 75
1449 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Serbabar Balarampur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000153/2025-2026 | 2691/MD | 04/06/2025 | 45 | JAHANGIR ALAM | 28.62 | 0 | 0
1450 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Serbabar Balarampur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000654/2024-2025 | 6364/MD | 17/12/2024 | 45 | JAHANGIR ALAM | 58.94 | 0 | 0
1451 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000024/2023-2024 | 1809/MD | 27/04/2023 | 0 | Resource Division | 18.28 | 0 | 0
1452 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000031/2022-2023 | 3043/MD | 12/12/2022 | 0 | Resource Division | 25.7 | 0 | 0
1453 | Malda Mechanical | Chanchal Sub-Division | New service connection at SERBABBAR BALARAMPUR PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.(CHANCHAL c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00232/2024-2025 | BP-2024-25-92 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 10.05 | 0 | 0
1454 | Malda Mechanical | Chanchal Sub-Division | New service connection at serbabbar balarampur under MLMD/PHE Dist. malda (chanchal c.c.c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/03547/2023-2024 | BP-2023-24-560 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.87 | 0 | 0
1455 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Serbabar Balarampur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013253) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000328/2023-2024 | 2330/MLMD | 26/07/2023 | 1156 | DEY ENTERPRISE.. | 28.99 | 22.29 | 84
1456 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA)at Sisa, Bhagabanpur& others Allied works at Krishnapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000120/2022-2023 | 1021/MAAD | 12/05/2022 | 45 | SUDIP DEY | 15.28 | 15.2 | 1
1457 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
1458 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Krishnapur Water Supply Scheme (Jagirtola, Krishnapur Chama, Bechutola, Rajutola, Guntola, Mandai, Mandaichaipara, Nashtola joenpur, Chakbahadurpur, Bintola, Sachitrapara, Kopatola, Krishnapur, Kacharitola & KBS) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000453/2021-2022 | 50/MAAD | 20/01/2022 | 90 | ALOK ENTERPRISE. A UNIT OF SAKET TREXIM PVT. LTD. | 206.62 | 204.34 | 100
1459 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme at Harshchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000162/2020-2021 | 3046/MD | 11/12/2020 | 30 | S DUTTA | 44.04 | 78.69 | 1
1460 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000165/2020-2021 | 2718/MD | 10/11/2020 | 30 | NIRENDRA NATH KUNDU | 58.72 | 0.33 | 1
1461 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Mouza- Dakshin Gouripur, Village-Baghuya, JL No. 167 GP-Malior-II of DAKSHIN GOURIPUR Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000382/2022-2023 | 2736/MD | 18/11/2022 | 30 | M/S SABANA CONSTRUCTION | 3.28 | 2.07 | 100
1462 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Additional laying work of DI & UPVC pipe line of SADLICHAK W/S Scheme at HARISHCHANDRAPUR-II Dev. Block under Malda division.P.H.E.Dte. In the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000655/2021-2022 | 47/CSD | 14/01/2022 | 30 | BEE GEE CONSTRUCTION | 4.19 | 0 | 1
1463 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Bodrail, JL. No. 167, G.P.-Kanturka of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000102/2020-2021 | 2298/MD | 30/09/2020 | 31 | BAKUL CHANDRA HALDAR | 2.82 | 5.03 | 0
1464 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000136/2020-2021 | 2446/MD | 12/10/2020 | 30 | KRISHNENDU DUTTA | 43.4 | 31.8 | 1
1465 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Chatra, JL. No. 29, G.P.-Aktail of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000143/2020-2021 | 2453/MD | 12/10/2020 | 30 | BENGAL ENGINEERING COMPANY | 6.92 | 11.35 | 0
1466 | Malda Division | RWS Malda Sub-Division | Stationary Bill under Malda Division, PHE Dte. n the district of Malda | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000259/2022-2023 | 1969/MD | 26/08/2022 | 1 | MALDA DISTRICT SERVICE CUM-MARKETING INDS. CO-OP UNION LTD. | 1.26 | 1.26 | 1
1467 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Detail route survey and design & drawing of distribution network, for providing FHTC in Uttar Chandipur Zone-I Water Supply scheme of Manikchak Block in the District of Malda under Malda Division, P.H.E.Dte. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000429/2022-2023 | 478/MSD | 09/12/2022 | 15 | FUTURE | 0.84 | 0.01 | 1
1468 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Sailpur Water Supply Scheme at Englishbazar Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000453/2023-2024 | 3370/MD | 29/08/2023 | 45 | BENGAL ENGINEERING COMPANY | 11.91 | 9.68 | 95
1469 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | SUPPLY OF OFFICE FURNITURE & OTHER STATIONERY ITEM FOR OFFICE USE STATIONERY ARTICLES FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | BILL/00219/2023-2024 | C082336196084 | 24/08/2023 | 0 | MALDA DISTRICT SERVICE CUM-MARKETING INDUSTRIAL CO-OPERATIVE UNION LTD. | 1.1 | 0 | 0
1470 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | SUPPLY OF THE FOLLOWING COMPUTER ACCESSORIES WITH SERVICE CHARGE FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | BILL/00239/2023-2024 |  | 24/08/2023 | 0 | DIGITEK SOLUTIONS | 0.42 | 0 | 0
1471 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | SUPPLY & DELIVERY OF DIFFERENT MATERIALS FOR THE DIFFERENT ON-GOING WATER SUPPLY SCHEME UNDER JJM WORKS. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | BILL/00346/2023-2024 |  | 22/09/2023 | 0 | DIGITEK SOLUTIONS | 0.42 | 0 | 0
1472 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000142/2020-2021 | 1129/MAAD | 11/11/2020 | 30 | BEE GEE CONSTRUCTION | 34.65 | 66.36 | 1
1473 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Sahajalalpur Water Supply Scheme (Habitation- Sarkar Para, Chowdhury Para) With pipe line at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000264/2022-2023 | 1866/MAAD | 28/09/2022 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.98 | 0 | 1
1474 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme (Mouza- Mokshedpur, Sayedpur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000042/2022-2023 | 818/MAAD | 28/04/2022 | 60 | BEE GEE CONSTRUCTION | 76.47 | 73.06 | 100
1475 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme (Mouza- Natibpur, Purba Chandpur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000043/2022-2023 | 819/MAAD | 28/04/2022 | 45 | M/S PRATIMA CONSTRUCTION | 27.81 | 23.04 | 1
1476 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme (Mouza- Selimpur, Uttar Roypur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000114/2022-2023 | 1016/MAAD | 12/05/2022 | 60 | NEOGI ENTERPRISE | 53.8 | 36.92 | 1
1477 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 75 mm dia uPVC Pipe line at Jhabri Tola, Tati Para, Colony & Chatra Para for installation of FHTC under Bamongram distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000162/2022-2023 | 1175/MAAD | 13/06/2022 | 45 | BEE GEE CONSTRUCTION | 4.82 | 4.82 | 1
1478 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
1479 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90 mm dia UPVC Pipe line at Tatipara for installation of FHTC under Bamongram Distribution Zone of Southern Sector under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000201/2022-2023 | 1449/MAAD | 29/07/2022 | 45 | SURAJIT MANDAL | 4.37 | 4.36 | 1
1480 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Placing of diesel driven Car on hire basis for the official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2022 to 31.12.2022) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000567/2021-2022 | 2041/MAAD | 29/12/2021 | 365 | SUBRATA SAHA | 4.5 | 2.1 | 1
1481 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | RTOR000013/2022-2023 | 1703/MAAD | 21/09/2022 | 0 | Resource Division | 3.08 | 0 | 0
1482 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90 mm dia UPVC Pipe line at Jhabritola, Khariyadoba for installation of FHTC under Bamongram Distribution Zone of Southern Sector under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000202/2022-2023 | 1450/MAAD | 29/07/2022 | 45 | SURAJIT MANDAL | 1.64 | 1.64 | 1
1483 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mouza: - Jalalpur, Purba Chandpur, Selimpur, Uttar Raypur for installation of FHTC under Bamangram distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000302/2022-2023 | 2034/MAAD | 16/11/2022 | 45 | BEE GEE CONSTRUCTION | 7.28 | 7.27 | 1
1484 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Jalalpur) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000331/2021-2022 | 1743/MAAD | 24/11/2021 | 60 | BEE GEE CONSTRUCTION | 56.38 | 24.8 | 1
1485 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Jalalpur) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000565/2021-2022 | 1743/MAAD | 24/11/2021 | 30 | BEE GEE CONSTRUCTION | 70 | 24.35 | 1
1486 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Topographical and Hydrograpic Survey for Malda Arsenic Area Water Supply Scheme ( Northern Sector) at Sankaritolaghat, Manikchak under Malda Arsenic Area Water Supply Division, P.H.E. Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000116/2022-2023 | 693/MAAD | 12/04/2022 | 20 | INTAKE SURVEY ENGINEERING CONSORTIUM | 2.15 | 1.36 | 1
1487 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000130/2020-2021 | 1066/MAAD | 14/10/2020 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 25.23 | 0.32 | 1
1488 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
1489 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mouza: - Jote Gopal Kagmari, Meharapur Habitations: - Krishnapur, Pathanpara, Natunpara for installation of FHTC under Jote Gopal Kagmari distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000212/2022-2023 | 1460/MAAD | 29/07/2022 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.25 | 4.25 | 100
1490 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mouza: - Ail Para, Dharampur, Jot Daman, Jote Gopal Kagmari, Habitations: - Ail Para, Dharampur, Jote Daman, Jote Mansa for installation of FHTC under Jote Gopal Kagmari distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000213/2022-2023 | 1461/MAAD | 29/07/2022 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.44 | 4.42 | 100
1491 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mouza: - Jote Daman, Habitations: - Chhabil Para for installation of FHTC under Jote Gopal Kagmari distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000214/2022-2023 | 1462/MAAD | 29/07/2022 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.85 | 3.84 | 100
1492 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000292/2021-2022 | 1339/MAAD | 14/09/2021 | 109 | SUBRATA SAHA | 0.52 | 0 | 1
1493 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2022 to 31.12.2022) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000386/2021-2022 | 2042MAAD | 29/12/2021 | 365 | M/S PARIMAL DAS | 1.73 | 1.64 | 0
1494 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Collection of House Hold Details at prescribed format in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Nazirpur, Arapur, Phulbaria, Baro Phulbari Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000249/2020-2021 | 86/MAAD | 15/01/2021 | 30 | DHRITIPALI | 2.62 | 0.44 | 1
1495 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Collection of House Hold Details at prescribed format in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sahajalalpur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000253/2020-2021 | 90/MAAD | 15/01/2021 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 0.26 | 0.26 | 1
1496 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Collection of House Hold Details at prescribed format in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dakshin Chandipur,Ramchandrapur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000254/2020-2021 | 91/MAAD | 15/01/2021 | 30 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 0.58 | 0.58 | 1
1497 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 110mm dia UPVC Pipeline at Ailpara, Supply of different dia DI Specials & other allied works under JoteGopalKagmari distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000323/2022-2023 | 2245/MAAD | 22/12/2022 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.86 | 4.84 | 100
1498 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Jote-Gopal Kagmari Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- JoteGopalkagmari) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000332/2021-2022 | 1744/MAAD | 24/11/2021 | 60 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 45.01 | 44.65 | 1
1499 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ramchandrapur Water Supply Scheme (Habitation- Ramnathpur) English Bazar Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000370/2021-2022 | 2007/MAAD | 28/12/2021 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.38 | 0.74 | 1
1500 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 160mm dia distribution Pipeline and repairing of Existing Household Tap Connection in connection with Jal Jeevan Mission (JJM) from Jote Daman Academic School to Rathbari Bazar under Jote Gopal Kagmari distribution Zone under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000444/2022-2023 | 398/MAAD | 06/03/2023 | 60 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.24 | 21.13 | 100
1501 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC Pipe line at Jote Daman & Chabilpara Village for installation of FHTC under Jote-Gopal Kagmari distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000466/2021-2022 | 70/MAAD | 21/01/2022 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.74 | 4.61 | 1
1502 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Charianantapur under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000063/2022-2023 | 995/MAAD | 10/05/2022 | 15 | GOBINDA ENTERPRISE | 4.81 | 4.8 | 1
1503 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
1504 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Nandalalpur Das para ,Chaksahedi,Ghoshpara khurshed Mondalpara under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000224/2022-2023 | 1474/MAAD | 29/07/2022 | 30 | BANIK BROTHERS | 4.76 | 4.75 | 1
1505 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Sekhpara, Nakulpara ,Tokkitola & Paglatola under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000225/2022-2023 | 1475/MAAD | 29/07/2022 | 30 | BANIK BROTHERS | 4.45 | 4.43 | 1
1506 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Charianantapur Mouza under command area of Charianantapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000291/2022-2023 | 2030MAAD | 16/11/2022 | 60 | M/S STAR INDIA CONSTRUCTION | 43.19 | 42.64 | 1
1507 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Charianantapur Water Supply Scheme(Mouza-Charianantapur)at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000321/2021-2022 | 1735/MAAD | 24/11/2021 | 60 | GOBINDA ENTERPRISE | 55.64 | 55.6 | 1
1508 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | RTOR000002/2021-2022 | 1787/MAAD | 26/11/2021 | 0 | Resource Division | 52.62 | 0 | 0
1509 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Chari Anantapur Water Supply Scheme(Mouza-Baghabanpur) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000322/2021-2022 | 1736/MAAD | 24/11/2021 | 60 | BANIK BROTHERS | 58.88 | 58.74 | 1
1510 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Charianantapur Water Supply Scheme (Mouza-Kalinagar) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000323/2021-2022 | 1737/MAAD | 24/11/2021 | 60 | BANIK BROTHERS | 37.54 | 37.43 | 1
1511 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Charinantapur kamat,Mritanjoy Tola, Subedartola, Bhimtola, Nandalalpur, Suklaltola, Pirpara & Kamarpara under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000480/2022-2023 | 617/MAAD | 31/03/2023 | 15 | M/S STAR INDIA CONSTRUCTION | 7.5 | 7.47 | 0
1512 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Kashimnagar Mouza under Biswambhar Binodpur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000031/2023-2024 | 854/MAAD | 03/05/2023 | 15 | ABANI BHUSAN GHOSH | 4.58 | 4.58 | 100
1513 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying UPVC pipe line and Providing FHTC at Harekrishna Kongar Colony and Kanchantar Binod nagar para under Boro Fulbaria W/S Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000052/2023-2024 | 951/MAAD | 23/05/2023 | 45 | TWO BROTHERS CONSTRUCTION | 4.63 | 4.16 | 100
1514 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Repairing of pipe line by Laying of UPVC pipe line at Kangso Binodpur, Madhupur, Lalbathani of Biswambhar Binodpur Distribution zone under Malda Arsenic Area Water Supply Division PHED in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) . | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000169/2022-2023 | 1182/MAAD | 13/06/2022 | 45 | M/S. JHA CONSTRUCTION | 3.38 | 3.34 | 1
1515 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
1516 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Repairing of pipe line by Laying of UPVC pipe line at Nurpur Mouza ( Dallu tola, Pyas Tola, Mandal Tola) of Biswambhar Binodpur Distribution zone under Malda Arsenic Area Water Supply Division PHED. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000192/2022-2023 | 1403/MAAD | 26/07/2022 | 45 | ABANI BHUSAN GHOSH | 24.12 | 24.11 | 1
1517 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Improvement of existing water supply pipe line of Nurpur, Tiarpara, Shamlalpara of Biswambhar Binodpur Distribution zone under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000334/2020-2021 | 511/MAAD | 10/06/2020 | 0 | KRISHNENDU DUTTA | 15.35 | 13.37 | 1
1518 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kashimnagar Mouza of BiswambharBinodpur Piped Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000346/2021-2022 | 1759/MAAD | 24/11/2021 | 45 | ABANI BHUSAN GHOSH | 31.2 | 31.04 | 100
1519 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Nurpur Mouza of Biswambhar Binodpur Piped Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000347/2021-2022 | 1753/MAAD | 24/11/2021 | 60 | NEOGI ENTERPRISE | 44.84 | 42.69 | 1
1520 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Lalbathani, KanshaBinodpur, Niranjanpur Mouza of BiswambharBinodpur Piped Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000348/2021-2022 | 1760/MAAD | 24/11/2021 | 60 | M/S. JHA CONSTRUCTION | 55.62 | 36.81 | 1
1521 | Malda Division | Malda Mechanical Division | Soil Investigation and design of substructure for ................ at Bamangola Dev. Block in Malda District. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | BILL/00280/2022-2023 |  | 31/01/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
1522 | Malda Division | Malda Mechanical Division | Soil Investigation and design of substructure for Over Head Reservoirs for Bamangram Piped Water Supply Scheme at Bamaongola Dev. Block in Malda district. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | BILL/00463/2022-2023 | BP-2022-23-188 | 02/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
1523 | Malda Division | Malda Mechanical Division | Placement of fund against the work for Road restoration work for laying of pipe line for Bamongala Habibpur Road (Portion from 7.00 kmp to 7.50 kmp) for Bamongram Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | BILL/00531/2022-2023 | BP-2022-23-210 | 16/03/2023 | 0 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 12.47 | 0 | 0
1524 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of BAMANGRAM Piped water supply scheme for the work of Geotechnical Study, construction of 500 Cum RCC OHR, Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Bamongola Dev. Block under Malda Division PH Engg.Dte. In the District of Malda | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000007/2022-2023 | 1132/MD | 20/05/2022 | 365 | M/S S. DAS & ENTERPRISE | 571.92 | 507.57 | 90
1525 | Malda Division | Malda Mechanical Division | Augmentation work of Pump Houses and Boundary Walls with New Construction of Boundary wall at Head work site of BAMANGRAM Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000009/2025-2026 | 2412/MD | 27/05/2025 | 225 | M/S BHARATI CONSTRUCTION | 33.45 | 0 | 0
1526 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 300mm. Dia. x 200mm. Big dia. Tube Well 125 Mtr. deep by Direct Rotary method using PVC pipe & Gravel Filter including supply of Materials at Bamangram Piped Water Supply Scheme of Bamangola Dev. Block under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000048/2022-2023 | 1397/MD | 14/06/2022 | 21 | SNEHASISH GHOSH | 9.71 | 9.71 | 100
1527 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Bamangram Water Supply Scheme in Bamongola block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000145/2021-2022 | 1743/MD | 15/06/2021 | 14 | HORIZEN | 2.86 | 2.45 | 1
1528 | Malda Division | Malda Mechanical Division | Laying of dedicated /Parallel pipe line for better functionality and providing balance FHTC of BAMANGRAM Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000195/2025-2026 | 3629/MD | 24/07/2025 | 60 | M/S MOON LIGHT CONSTRUCTION & CO. | 87.27 | 0 | 0
1529 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with 2nd Tube Well Site of Bamangram Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000223/2023-2024 | 2673/MD | 13/07/2023 | 45 | DEB CONSTRUCTION | 4.17 | 0 | 100
1530 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 4th Tube Well Site of Bamongram Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000310/2024-2025 | 3950/MD | 07/08/2024 | 45 | SWASTIK UDYOG | 8.01 | 0 | 0
1531 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Excess laying of HDPE (PE-80) pipe for distribution system for the Augmentation of BAMANGRAM & its adjoining mouzas piped water supply at Bamongola Dev. Block in the District Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000407/2022-2023 | 2990/MD | 07/12/2022 | 45 | BINA CONSTRUCTION | 22.62 | 22.62 | 0
1532 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House of Bamangram Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000777/2024-2025 | 294/MD | 29/01/2025 | 60 | M/S EHAN ENTERPRISE | 4.36 | 0 | 0
1533 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Bamangram Piped Water Supply Scheme at Bamongola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000958/2023-2024 | 706/MD | 09/02/2024 | 45 | M/S GHOSH CONSTRUCTION | 8.85 | 5.9 | 100
1534 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | RTOR000002/2022-2023 | 1104/MD | 17/05/2022 | 0 | Resource Division | 77.51 | 0 | 0
1535 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | RTOR000031/2025-2026 | 2830/MD | 11/06/2025 | 0 | Resource Division | 18.75 | 0 | 0
1536 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | RTOR000039/2022-2023 | 1248/MD | 22/03/2023 | 0 | Resource Division | 79.81 | 0 | 0
1537 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. of Bamongram Distribution Zone, Sujapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000131/2023-2024 | 3004335962 | 19/06/2023 | 365 | W.B.S.E.D.C.LTD | 1.3 | 1.3 | 100
1538 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Bamangram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000251/2023-2024 | 2224/MLMD | 18/07/2023 | 120 | SUBHAS CHANDRA KESHORI | 10.85 | 0 | 0
1539 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. IV of Augmentation of Bamangram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000252/2023-2024 | 2225/MLMD | 18/07/2023 | 592 | SUBHAS CHANDRA KESHORI | 12.49 | 12.27 | 100
1540 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- I of Bamangram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001096/2022-2023 | 413/MLMD | 14/03/2023 | 120 | M/S. SOMA ENTERPRISE | 7.98 | 6.95 | 1
1541 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- II of Bamangram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001097/2022-2023 | 414/MLMD | 14/03/2023 | 120 | M/S. SOMA ENTERPRISE | 7.72 | 6.68 | 1
1542 | Malda Mechanical | Malda Mechanical Division | Supply, installation, and commissioning of electro-mechanical components at T/W no. I of Augmentation of Bamongram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001797/2023-2024 | 3684/MLMD | 29/11/2023 | 180 | BANIK BROTHERS | 8.07 | 1.05 | 30
1543 | Malda Mechanical | Malda Mechanical Division | Supply, installation, and commissioning of electro-mechanical components at T/W no. II of Augmentation of Bamongram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001798/2023-2024 | 3685/MLMD | 29/11/2023 | 180 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 7.73 | 0 | 0
1544 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Implementation of KANTHALANPUR Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000035/2023-2024 | 1849/MD | 03/05/2023 | 820 | SOVON KUMAR DAS | 322.9 | 231.44 | 100
1545 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work site of Kanthalanpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000155/2024-2025 | 2924/MD | 10/06/2024 | 326 | SOVON KUMAR DAS | 35.67 | 0 | 100
1546 | Malda Division | RWS Malda Sub-Division | Laying of Distribution of UPVC Pipeline of KANTHALANPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000564/2023-2024 | 2328/MD | 08/06/2023 | 60 | UTTAM KUMAR GHOSH | 64.73 | 42.81 | 80
1547 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kanthalanpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000620/2024-2025 | 5790/MD | 21/11/2024 | 45 | DHRITIPALI | 60.57 | 0 | 0
1548 | Malda Division | RWS Malda Sub-Division | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works of Oltara, Mianagar, Kadirpur, Bhabuk, Kanthalanpur PWSS under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000954/2024-2025 | 643/MD | 19/02/2025 | 7 | DHRITIPALI | 0.88 | 0 | 0
1549 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tubewell site of Kanthalanpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/001035/2023-2024 | 1261/MD | 15/03/2024 | 413 | SOVON KUMAR DAS | 7.07 | 0 | 100
1550 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000043/2023-2024 | 1809/MD | 27/04/2023 | 0 | Resource Division | 14.46 | 0 | 0
1551 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of KANTHALANPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/02490/2023-2024 | BP-2023-24-425 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.24 | 0 | 0
1552 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of KANTHALANPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/02491/2023-2024 | BP-2023-24-426 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 7.65 | 0 | 0
1553 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Kanthalanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013454) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000381/2023-2024 | 2389/MLMD | 28/07/2023 | 1078 | HANNAN BUILDERS PVT. LTD. | 30 | 23.48 | 19
1554 | Malda Division | RWS Malda Sub-Division | Augmentation work of Boundary wall, Pump House, Blower Room, RCC Over Head Reservior and Construction Pathway & Approch Road at Head Work Site of SAIYADPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000004/2025-2026 | 2376/MD | 26/05/2025 | 75 | M/S T. K. CONSTRUCTION | 21.59 | 0 | 0
1555 | Malda Division | RWS Malda Sub-Division | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 2nd Tube Well Site of SAIYADPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000005/2025-2026 | 2288/MD | 21/05/2025 | 75 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.42 | 0 | 0
1556 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for SAIYADPUR Piped Water Supply scheme ( Kutubpur JL-79, Basudevpur JL-80,Ijjatpur ,JL-81 & Minapara JL-92 ) under Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000013/2023-2024 | 1638/MD | 12/04/2023 | 45 | SHREE BISHNU CONSTRUCTION | 56.31 | 52.38 | 90
1557 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well ( 135 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at SAIYADPUR Water Supply Scheme of Old Malda Block .under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000308/2022-2023 | 2303/MD | 28/09/2022 | 30 | DUTTA ENTERPRISE | 9 | 8.58 | 1
1558 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of SAIYADPUR Water Supply Scheme of Old Malda Block .under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000344/2022-2023 | 2549/MD | 03/11/2022 | 45 | J. M. CONSTRUCTION | 6.69 | 6.52 | 90
1559 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C pipe line by different dia UPVC pipe for SAIYADPUR Piped Water Supply Scheme (Dhalsana JL-48, Horkhorka JL-49, & Saiyadpur ) under Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000363/2022-2023 | 2603/MD | 10/11/2022 | 45 | A. K. CONSTRUCTION | 46.61 | 41.9 | 80
1560 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 4th Tubewell site of Saiyadpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000470/2024-2025 | 4883/MD | 20/09/2024 | 45 | M. S. AGENCY | 9.62 | 9.58 | 100
1561 | Malda Division | RWS Malda Sub-Division | Laying of additional pipeline for retrofitting and Installation of Functional House Connection of Saiyadpur Piped Water Supply Scheme at Old Malda Block under Malda Division PHE. Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000643/2024-2025 | 5919/MD | 26/11/2024 | 45 | SHREE BISHNU CONSTRUCTION | 88.25 | 0 | 0
1562 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 132.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at SAIYADPUR Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000717/2022-2023 | 1175/MD | 20/03/2023 | 30 | A. D. D. ASSOCIATES | 9.15 | 9.13 | 100
1563 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Saiyadpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000733/2022-2023 | 1207/MD | 21/03/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 4.15 | 4.14 | 100
1564 | Malda Division | RWS Malda Sub-Division | Erection of Property board related to Jal Jeevan Mission works of Saiyadpur, Nemua, Gun Sankrul, Barkol & Mahammadpur PWSS under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000966/2024-2025 | 655/MD | 19/02/2025 | 7 | PRITAM ENTERPRISE | 0.89 | 0 | 100
1565 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall and pathway at 3rd Tube well Site of SAIYADPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000909/2023-2024 | 287/MD | 11/01/2024 | 45 | KANAN CONSTRUCTION ENTERPRISE | 6.32 | 0 | 0
1566 | Malda Division | RWS Malda Sub-Division | Extension of pipe line and replacing of damage A.C./uPVC pipe line by different dia. UPVC pipe for SAIYEDPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000975/2023-2024 | 884/MD | 27/02/2024 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 12.59 | 12.2 | 100
1567 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000023/2022-2023 | 2410/MD | 17/10/2022 | 0 | Resource Division | 10.98 | 0 | 0
1568 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000183/2023-2024 | 777/MD | 20/02/2024 | 0 | Resource Division | 3.08 | 0 | 0
1569 | Malda Mechanical | RWS Malda Sub-Division | NEW SERVICE CONNECTION FOR TE NO. IV OF SAIYEDPUR W S SCHEME | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | BILL/01072/2023-2024 | BP-2023-24-95 | 13/07/2023 | 0 | W.B.S.E.D.C.LTD | 3.18 | 0 | 0
1570 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at T/W No.III of Saiyadpur PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000048/2023-2024 | 3004243242 | 27/04/2023 | 90 | W.B.S.E.D.C.LTD | 4.41 | 4.41 | 0
1571 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III & IV of Source Augmentation of Saiyadpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012800) | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/001129/2022-2023 | 512/MLMD | 20/03/2023 | 120 | DEVI ENTERPRISE... | 21.57 | 18.36 | 0
1572 | Malda Mechanical | RWS Malda Sub-Division | Claim for purchase of fuel for hiring of inspection for different site visit (diesel driven for official) use for Under Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/001394/2022-2023 | 917./MLMD | 12/09/2022 | 61 | MAA LAXMI FUEL STATION | 0.51 | 0.51 | 100
1573 | Malda Mechanical | RWS Malda Sub-Division | Claim for purchase of fuel for hiring of inspection for different site visit (diesel driven for official) use for AE-I, Under Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/001924/2023-2024 | 1145./MLMD | 26/06/2023 | 30 | RAMCHANDRA BASAK | 0.26 | 0.26 | 100
1574 | Malda Mechanical | RWS Malda Sub-Division | Installation, Commissioning and trail operation of electro-mechanical components at T/W no-III & IV Source Augmentation of Saiyadpur W/S Scheme in the district of Malda under Malda Mechanical Division, P.H.Engineering Directorate. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/002022/2023-2024 | 4756/MLMD | 28/12/2023 | 30 | PABITRA MANDAL | 3.01 | 1.48 | 49
1575 | Malda Division | Malda Mechanical Division | Assessment of pressure & other allied parameters of existing Pipe Network and detail study of existing Tulshihatta Zone-I PWSS to Improving the performance of water supply systems under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000101/2025-2026 | 2316/MD | 22/05/2025 | 45 | AJIVAM WATER PRIVATE LIMITED | 5 | 0 | 100
1576 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying Distribution pipe line for TULSHIHATA (ZONE-I) & its adjoining mouzas Piped Water Supply at Harishchandrapur-I Block in the District Malda under Malda Division, PHE Dte. (2nd Call). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000271/2022-2023 | 2129/MD | 16/09/2022 | 472 | BANIK BROTHERS | 168.65 | 101.34 | 100
1577 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Tulshihatta Zone-I Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000455/2023-2024 | 3372/MD | 29/08/2023 | 278 | M/S SABANA CONSTRUCTION | 80.46 | 72.04 | 100
1578 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Tulshihatta Zone-I Piped Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000689/2021-2022 | 654/MD | 22/03/2022 | 15 | M/S SOBHA & CO. | 3.42 | 3.42 | 1
1579 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Tulshihata Zone-I Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000740/2024-2025 | 60 | 08/01/2025 | 311 | M/S BABLU ENTERPRISE | 30.36 | 0 | 30
1580 | Malda Division | Malda Mechanical Division | Laying of additional at Tulshihatta Zone-I Water Supply Scheme under Harishchandrtapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000758/2024-2025 | 76 | 13/01/2025 | 251 | M/S GHOSH CONSTRUCTION | 12.42 | 0 | 100
1581 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Bbairat, Paro, Mabarakpur, Sri Chandrapur, Tulshihatta Zone-I & II, Kismat Barol PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000958/2024-2025 | 647/MD | 19/02/2025 | 7 | RAHANUL ALAM | 0.95 | 0 | 100
1582 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000009/2024-2025 | 3921/MD | 06/08/2024 | 0 | Resource Division | 4.31 | 0 | 0
1583 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000015/2022-2023 | 1874/MD | 16/08/2022 | 0 | Resource Division | 18.81 | 0 | 0
1584 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000057/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 17.88 | 0 | 0
1585 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000103/2023-2024 | 33/MD | 04/01/2024 | 0 | Resource Division | 12.32 | 0 | 0
1586 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I, II of Tulshihata (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011266) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000698/2023-2024 | 2773/MLMD | 14/08/2023 | 1212 | SUDIP DEY | 25.6 | 21.01 | 85
1587 | Malda Mechanical | Malda Mechanical Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000968/2024-2025 | 2780/MLMD | 27/08/2024 | 61 | SUBRATA SAHA | 0.78 | 0 | 100
1588 | Malda Division | Malda Mechanical Division | Bill for reimbursement of cost of Diesel and Mobil in respect of hired Vehicle Car No. WB61A/3084, For the month of June and July 2023. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00330/2023-2024 | BP-2023-24-192 | 07/09/2023 | 0 | SHYAMAL KUMAR MAITRA | 0.36 | 0 | 0
1589 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 500 M3 Capacity OHR with Soil Investigation and FHTC of CHOUPALDANGA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000044/2023-2024 | 2007/MD | 17/05/2023 | 1165 | NIRMAN | 243.67 | 59.39 | 75
1590 | Malda Division | Malda Mechanical Division | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Choupaldanga Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000063/2025-2026 | 1911/MD | 14/05/2025 | 60 | NEOGI ENTERPRISE | 104.36 | 0 | 0
1591 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Choupaldanga Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000146/2025-2026 | 2684/MD | 04/06/2025 | 150 | GIRIDHARI CONSTRUCTION | 25.91 | 0 | 0
1592 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tubewell site of Choupaldanga Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000147/2025-2026 | 2685/MD | 04/06/2025 | 211 | HARUN ALL RASHID & BROTHERS | 17.12 | 0 | 0
1593 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tubewell site of Choupaldanga Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000165/2024-2025 | 2940/MD | 10/06/2024 | 146 | M/S GHOSH CONSTRUCTION | 8.82 | 0 | 60
1594 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of CHOUPALDANGA & its adjoining mouza Water Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000298/2022-2023 | 2194/MD | 22/09/2022 | 45 | M/S EHAN ENTERPRISE | 6.67 | 6.01 | 95
1595 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 150 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of CHOUPALDANGA Water Supply Scheme at Harishchandrapur I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000326/2022-2023 | 2348/MD | 29/09/2022 | 30 | MECHANO TRADING CO. | 9.65 | 8.71 | 100
1596 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line of CHOUPALDANGA and its adjoining mouzas Pipe Water Supply Scheme at Harishchandrapur-I Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000335/2022-2023 | 2384/MD | 13/10/2022 | 811 | NEOGI ENTERPRISE | 275.7 | 217.53 | 100
1597 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (2 Nos.) at CHOUPALDANGA Water Supply Scheme under Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000677/2022-2023 | 1139/MD | 20/03/2023 | 30 | DUTTA ENTERPRISE | 20.31 | 20.05 | 95
1598 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for CHOUPALDANGA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000924/2023-2024 | 511/MD | 29/01/2024 | 383 | AHONA ENTERPRISE | 14.91 | 0 | 99
1599 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at CHOUPALDANGA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000934/2023-2024 | 579/MD | 02/02/2024 | 45 | GULJAR CONSTRUCTION | 4.19 | 0 | 100
1600 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at CHOUPALDANGA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000935/2023-2024 | 580/MD | 02/02/2024 | 45 | GULJAR CONSTRUCTION | 4.19 | 0 | 100
1601 | Malda Division | Malda Mechanical Division | Jack Pushing of D.I. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method at Gohila area of Choupaldanga Pipe Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000970/2025-2026 | 697/MD | 13/02/2026 | 25 | AHONA ENTERPRISE | 2.08 | 0 | 100
1602 | Malda Division | Malda Mechanical Division | Jack Pushing of D.I. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method at Choupaldanga Pipe Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000971/2025-2026 | 698/MD | 13/02/2026 | 25 | NEOGI ENTERPRISE | 8.32 | 0 | 100
1603 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000022/2025-2026 | 2804/MD | 11/06/2025 | 0 | Resource Division | 11.01 | 0 | 0
1604 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000024/2022-2023 | 2755/MD | 22/11/2022 | 0 | Resource Division | 53 | 0 | 0
1605 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000121/2023-2024 | 91/MD | 05/01/2024 | 0 | Resource Division | 10.44 | 0 | 0
1606 | Malda Mechanical | Malda Mechanical Division | New service connection at CHOUPALDANGA Pwss pH NO II Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03678/2023-2024 | BP-2023-24-661 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.87 | 0 | 0
1607 | Malda Mechanical | Malda Mechanical Division | New service connection at CHOUPALDANGA Pwss pH NO III Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03679/2023-2024 | BP-2023-24-662 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.06 | 0 | 0
1608 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Choupaldanga PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000300/2023-2024 | 3004302721 | 21/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.2 | 3.2 | 100
1609 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Choupaldanga Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011833) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000312/2023-2024 | 2314/MLMD | 26/07/2023 | 916 | COMBINE ENTERPRISE | 38.6 | 6.57 | 85
1610 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Hamidpur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000005/2023-2024 | 661/MAAD | 06/04/2023 | 45 | JOY GURU ENTERPRISE | 14.6 | 10.79 | 100
1611 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Paschim Tofi, Purba Tofi, Chumki Tola for Hamidpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000006/2023-2024 | 677/MAAD | 12/04/2023 | 90 | MD. TALEB ALI | 66.48 | 47.01 | 90
1612 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Nutun Tofi, Jalimtola, Sripur Colony, Sripur, Bakhrabaj ,for Hamidpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000026/2023-2024 | 836/MAAD | 02/05/2023 | 303 | M/S MOON LIGHT CONSTRUCTION & CO. | 46.85 | 35.22 | 100
1613 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Hamidpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2ND Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000103/2023-2024 | 1411/MAAD | 20/07/2023 | 712 | WIST WATER SOLUTIONS PRIVATE LIMITED | 156.58 | 0 | 15
1614 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Hamidpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000104/2023-2024 | 1409/MAAD | 20/07/2023 | 256 | M. I. CONSTRUCTION | 4.96 | 0 | 100
1615 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 450 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Hamidpur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (3rd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000219/2023-2024 | 1707/MAAD | 20/09/2023 | 468 | M/S MOON LIGHT CONSTRUCTION & CO. | 203.55 | 72.68 | 80
1616 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Route survey & design for praparation of DPR of Humidpur, Sukhdebpur & Bakhrabad Pipe Water Supply Scheme at Kaliachak-II & Kaliachak-III Development Block under Malda Arsenic Area W/S Division, Phe Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000232/2022-2023 | 1667/MAAD | 08/09/2022 | 10 | FUTURE | 0.99 | 0.99 | 1
1617 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Continuation work order for Route survey & design for praparation of DPR of Humidpur, Sukhdebpur & Bakhrabad Pipe Water Supply Scheme at Kaliachak-II & Kaliachak-III Development Block under Malda Arsenic Area W/S Division, Phe Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000287/2022-2023 | 1671/MAAD | 12/09/2022 | 10 | FUTURE | 0.99 | 0.99 | 1
1618 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | RTOR000002/2023-2024 | 624/MAAD | 05/04/2023 | 0 | Resource Division | 10.54 | 0 | 0
1619 | Malda Mechanical | Malda Arsenic Area W/S Division | Quotation Payment for Hamidpur PH NO 2 Under Mothabari CCC Under the district of MALDA | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | BILL/02732/2024-2025 | BP-2024-25-622 | 09/01/2025 | 0 | W.B.S.E.D.C.LTD | 7.36 | 0 | 0
1620 | Malda Mechanical | Malda Arsenic Area W/S Division | Quotation Payment againsts Hamidpur PH NO 1 Under Mothabri CCC Under the district of Malda | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | BILL/03201/2024-2025 |  | 20/01/2025 | 0 | W.B.S.E.D.C.LTD | 8.63 | 0 | 0
1621 | Malda Mechanical | Malda Arsenic Area W/S Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000069/2024-2025 | 1650/MLMD | 25/06/2024 | 62 | NITAI PANDEY | 0.78 | 0.77 | 0
1622 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Hamidpur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000243/2024-2025 | 1697/MAAD | 19/11/2024 | 60 | M/S MANDAL & SONS | 64 | 0 | 0
1623 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Humidpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/001732/2023-2024 | 3390/MLMD | 31/10/2023 | 789 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 62.15 | 40.3 | 30
1624 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission(JJM& Jal Swapna) at Lalutola,Khublaltola & Gosaitola village under Charianantapur pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000126/2024-2025 | 1257/MAAD | 24/06/2024 | 30 | MAHA MAYA CONSTRUCTION | 6.8 | 0 | 0
1625 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 110 mm dia & 90 mm dia UPVC pipe, Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) at Kathalbari village under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000127/2024-2025 | 1258/MAAD | 24/06/2024 | 281 | SAHA CONSTRUCTION | 34.89 | 0 | 0
1626 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
1627 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipe 160mm dia & DI pipe 250 mm dia From Dariapur WTP (Back wash OHR) to 16 mile & others Allied works of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000222/2023-2024 | 1711/MAAD | 20/09/2023 | 90 | S. R. CONSTRUCTION | 22.28 | 22.09 | 100
1628 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UVC pipe 200mm,90 mm dia at Kumvira to Nurnagar,Godhantola to munnatola & others Allied works to faciliate of house connection at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000001/2023-2024 | 622/MAAD | 05/04/2023 | 60 | MI CONSTRUCTION | 22.74 | 22.58 | 0
1629 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Godhan tola to Munnatola at Kumbhira Piped Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000037/2023-2024 | 885/MAAD | 11/05/2023 | 721 | M/S AMIT KUMAR GUPTA | 34.21 | 0 | 100
1630 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Kumbhira to Nurnagar at Kumbhira Piped Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000038/2023-2024 | 886/MAAD | 11/05/2023 | 150 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 38.78 | 6.15 | 40
1631 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Sardah, Naldahari, Chaitanna Tola & Nowda under Bholaichak water supply Zone of Southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000039/2023-2024 | 853/MAAD | 03/05/2023 | 15 | BANIK BROTHERS | 8.37 | 8.36 | 100
1632 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Repair & renovation of CI /DI Clear water main (Group-I) 750mm,700 mm,500 mm,450 mm,300 mm,250 mm) pipeline at diferrence places (Kaliachak band,Kaliachak PWD,Kaliachak Suraj Grill factory,jalalpur,Majompur bridge &Bholaichak) under Southern Sector under Malda Arsenic Area W/S Divn.PHE. Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000040/2023-2024 | 855/MAAD | 03/05/2023 | 30 | BANIK BROTHERS | 3.33 | 3.32 | 100
1633 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipe 225mm,90 mm dia at Mohanpur ,Neoginagar & others Allied works at Kumvira W/S scheme at Kaliachak -III Block under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000049/2023-2024 | 948/MAAD | 23/05/2023 | 45 | M/S SUBHASIS BHADURI | 8.83 | 7.91 | 100
1634 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipe 225mm dia at Neogi nagar & others Allied works at Kumvira W/S scheme at Kaliachak-III Block under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000050/2023-2024 | 949/MAAD | 23/05/2023 | 45 | SURAJIT MANDAL | 8.61 | 7.78 | 100
1635 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Akandabaria,Chakdomai & Umakantatola under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000064/2022-2023 | 915/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.71 | 4.7 | 1
1636 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Kalinagar, Malatipur & Zolatuli under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000065/2022-2023 | 916/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.67 | 4.66 | 1
1637 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Saharatola, Golabari & Bhagabanpur under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dt | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000066/2022-2023 | 917/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.74 | 4.73 | 1
1638 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Chakkupara, Nandalalpur & Agnutola under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000067/2022-2023 | 918/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.81 | 4.8 | 1
1639 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
1640 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipe line & Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Khuplaltola, Gosaitola under command area of Charianantapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000238/2023-2024 | 1892/MAAD | 12/10/2023 | 30 | ABHIJIT CONSTRUCTION | 9.28 | 7.6 | 100
1641 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) at Satangapara (Kashipara) & Sammohammadtola under Dariapur water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000271/2023-2024 | 3078/MAAD | 14/12/2023 | 60 | M/S EHAN ENTERPRISE | 9.86 | 9.36 | 100
1642 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of SANKAIL Water Supply Scheme of Habibpur Block. under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000343/2022-2023 | 2800/MD | 24/11/2022 | 679 | M/S N. N. ENTERPRISE | 6.68 | 0 | 100
1643 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for SANKAIL Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000365/2022-2023 | 2606/MD | 10/11/2022 | 1087 | M/S KUNDU CONSTRUCTION | 71.98 | 66.44 | 0
1644 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall of Sankail Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000485/2024-2025 | 4998/MD | 27/09/2024 | 45 | BALAJI ENGINEERS CO OPERATIVE SOCIETY LT | 10.15 | 0 | 0
1645 | Malda Division | RWS Malda Sub-Division | Replacement of (200 mm Dia. All through) Tubewell No:-1 (130 m deep) at Headwork Site by D.R Rig Method using P.V.C. pipe & Filter including Supply of materials at SANKAIL water supply scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000785/2024-2025 | 350/MD | 30/01/2025 | 30 | A. L. ENGINEERING SOLUTION | 9.06 | 0 | 0
1646 | Malda Division | RWS Malda Sub-Division | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Sankail Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000839/2024-2025 | 1071/MD | 19/03/2025 | 227 | M/S /FAIZUL HAQUE BISWAS | 9.87 | 0 | 100
1647 | Malda Division | RWS Malda Sub-Division | Sinking of ( 250 mm Dia. X 200 mm Dia.) Tubewell No.-3 (130 M deep) by D.R Rig. Method using P.V.C. pipe & Gravel Filter including Supply of materials at SANKAIL Water Supply Scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000920/2023-2024 | 381/MD | 17/01/2024 | 45 | A. L. ENGINEERING SOLUTION | 11.77 | 9.77 | 100
1648 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000033/2025-2026 | 2820/MD | 11/06/2025 | 0 | Resource Division | 11.74 | 0 | 0
1649 | Central Drilling | RWS Malda Sub-Division | Resistivity survey for Sankail PWSS, Basara PWSS and Pannapur PWSS at Habibipur & Bamongola block under Malda district, CMSD-II (D), CDD, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000012/2023-2024 | 135/CMSD-II(D) | 24/05/2023 | 15 | S B S ENTERPRISE | 0.82 | 0.27 | 100
1650 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Sankail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014344) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000387/2023-2024 | 2395/MLMD | 28/07/2023 | 1097 | SUDIP DEY | 11.1 | 0 | 30
1651 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Malior Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. (3rd Call). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000012/2025-2026 | 2420/MD | 27/05/2025 | 45 | JAHANGIR ALAM | 27.3 | 0 | 0
1652 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of MALIOR Water Supply Scheme at HarishchandrapurII Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000066/2023-2024 | 2021/MD | 18/05/2023 | 958 | JAHANGIR ALAM | 509.49 | 193.36 | 95
1653 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Malior Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000183/2024-2025 | 2958/MD | 10/06/2024 | 30 | M/S MAA TARA ENTERPRISE | 7.24 | 0 | 100
1654 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Malior Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000319/2024-2025 | 3967/MD | 07/08/2024 | 180 | SUBHAS CHANDRA KESHARI | 30.15 | 0 | 0
1655 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of MALIOR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000372/2022-2023 | 2700/MD | 17/11/2022 | 30 | SAUDAGAR (INDIA) | 9.2 | 9.2 | 100
1656 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at MALIOR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000604/2022-2023 | 922/MD | 27/02/2023 | 30 | MERCURY ENGINEERING COMPANY | 10.13 | 10.01 | 100
1657 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Malior Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000736/2024-2025 | 55 | 08/01/2025 | 311 | ABHIJIT PAUL | 28.77 | 0 | 70
1658 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Talsur, Sadlichak, Dakhin Bhakuria, Malior, Harishchandrapur Zone-I PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000961/2024-2025 | 650/MD | 19/02/2025 | 7 | M/S SABANA CONSTRUCTION | 0.9 | 0 | 100
1659 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000004/2024-2025 | 3924/MD | 06/08/2024 | 0 | Resource Division | 4.07 | 0 | 0
1660 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000014/2023-2024 | 1618/MD | 11/04/2023 | 0 | Resource Division | 17.18 | 0 | 0
1661 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000038/2022-2023 | 3050/MD | 12/12/2022 | 0 | Resource Division | 25.1 | 0 | 0
1662 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Malior Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013022) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000242/2023-2024 | 2259/MLMD | 18/07/2023 | 773 | NIRMAN. | 26.34 | 17.93 | 83
1663 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No.II of Malior PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001521/2023-2024 | 3004390586 | 15/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.33 | 4.33 | 100
1664 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of Malior PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001522/2023-2024 | 3004390575 | 15/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.14 | 4.14 | 100
1665 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of distribution Pipe line at Shrirampur, Narayanpur for installation of FHTC under Narayanpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000165/2022-2023 | 1178/MAAD | 13/06/2022 | 45 | BEE GEE CONSTRUCTION | 4.64 | 4.53 | 1
1666 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
1667 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mouza: - Narayanpur, Mojampur, Srirampur for installation of FHTC under Narayanpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000303/2022-2023 | 2042/MAAD | 16/11/2022 | 45 | BEE GEE CONSTRUCTION | 7.94 | 7.93 | 1
1668 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Narayanpur Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Narayanpur) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000335/2021-2022 | 1742/MAAD | 24/11/2021 | 60 | BEE GEE CONSTRUCTION | 56.38 | 50.64 | 1
1669 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ramchandrapur Water Supply Scheme (Habitation- Ramnathpur) English Bazar Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000370/2021-2022 | 2007/MAAD | 28/12/2021 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.38 | 0.05 | 1
1670 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | RTOR000003/2022-2023 | 1335 | 18/07/2022 | 0 | Resource Division | 12.3 | 0 | 0
1671 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 50m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Dahara Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000257/2024-2025 | 3205/MD | 27/06/2024 | 368 | WATER TECH | 20.04 | 0 | 60
1672 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of DAHARA Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-I) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000557/2022-2023 | 748/MD | 17/02/2023 | 30 | M/S AMIT KUMAR GUPTA | 46.66 | 46.38 | 95
1673 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of DAHARA Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-II) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000565/2022-2023 | 756/MD | 17/02/2023 | 45 | SUBHAS CHANDRA KESHARI | 85.86 | 85.79 | 0
1674 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of DAHARA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000579/2024-2025 | 5596/MD | 05/11/2024 | 30 | M/S AMIT KUMAR GUPTA | 1.71 | 0 | 10
1675 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dahara Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000750/2022-2023 | 1298/MD | 23/03/2023 | 45 | A. L. ENGINEERING SOLUTION | 4.19 | 4.18 | 97
1676 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Dahara Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000759/2024-2025 | 77 | 13/01/2025 | 45 | RAJIB MANI | 10.09 | 0 | 0
1677 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 200mm. Big dia Tube Well 150 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of DAHARA Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000782/2022-2023 | 1440/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 11.02 | 10.87 | 100
1678 | Malda Mechanical | Malda Mechanical Division | Quatation for new service connection at DAHARAw/s sch. T/W no III UNDER MLMD. Dist Malda. (Harishchandrapur C. C. C) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03508/2023-2024 | BP-2023-24-528 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 8.41 | 0 | 0
1679 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Dahara Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte. (TSM/016549) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/001811/2023-2024 | 3698/MLMD | 29/11/2023 | 180 | DAS CONSTRUCTION | 12.55 | 11.19 | 100
1680 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Gouripur Piped Water Supply scheme in Harischandrapur II Block under Malda Division PHE. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000577/2022-2023 | 768/MD | 17/02/2023 | 45 | SUDIPTA GHOSH | 29.67 | 0 | 0
1681 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of DAKSHIN GOURIPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000581/2024-2025 | 5615/MD | 06/11/2024 | 30 | A. H. ENTERPRISE | 1.7 | 0 | 100
1682 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Dakhin Gouripur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000637/2024-2025 | 5916/MD | 26/11/2024 | 45 | M/S ROY CONSTRUCTION | 7.68 | 0 | 100
1683 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dakshin Gouripur Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000747/2022-2023 | 1295/MD | 23/03/2023 | 45 | SAYEM ENTERPRISE | 4.18 | 4.13 | 97
1684 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 140 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of DAKSHIN GOURIPUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000778/2022-2023 | 1436/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 9.62 | 9.3 | 100
1685 | Malda Division | Malda Mechanical Division | Augmentation work of OHR, Pump House and Boundary Wall of Dakshin Gouripur Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000852/2024-2025 | 1045/MD | 18/03/2025 | 75 | M/S SABANA CONSTRUCTION | 29.57 | 0 | 0
1686 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Dakshin Gouripur, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03391/2023-2024 | BP-2023-24-501 | 01/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.07 | 0 | 0
1687 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Dakshin Gouripur Water Supply Scheme in the District of under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/001810/2023-2024 | 3697/MLMD | 29/11/2023 | 489 | SOVON KUMAR DAS. | 10.95 | 9.53 | 100
1688 | Malda Division | RWS Malda Sub-Division | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 2nd Tube Well Site of MOBARAKPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000022/2025-2026 | 1740/MD | 08/05/2025 | 222 | M/S DEY ENTERPRISE | 5.78 | 0 | 0
1689 | Malda Division | RWS Malda Sub-Division | Augmentation work of Boundary wall, Pump House, Blower Room RCC Over Head Reservoir and Construction Pathway & Approach Road at Head Work Site of MOBARAKPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000156/2025-2026 | 2707/MD | 04/06/2025 | 75 | SAHA CONSTRUCTION | 19.71 | 0 | 0
1690 | Malda Division | RWS Malda Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning,and 3 (three) months Trial Run and 25 cum/hr. capacity of Iron Elimination Plants (Pressure type) with provision of polishing unit alongwith Construction of 3.60 mtr.X 3.00 mtr Blower Room in connection with source Augmentation at 3rd Tube Well site of MABARAKPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000608/2023-2024 | 4112/MD | 10/10/2023 | 120 | M/S AMIT KUMAR GUPTA | 14.74 | 13.29 | 90
1691 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for MABARAKPUR Piped Water Supply Scheme (Moua Mabrakpur, JL No.- 123 & Mouza-Muchia, JL No. 124) at Old Malda Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000699/2022-2023 | 1156/MD | 20/03/2023 | 45 | TARUN KUMAR DEY | 41.74 | 40.94 | 100
1692 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for MABARAKPUR Piped Water Supply Scheme (Mouza- Jalkar Bithan, JL No. 115) at Old Malda Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000706/2022-2023 | 1164/MD | 20/03/2023 | 45 | AVIK KUMAR GHOSH | 27.37 | 13.46 | 85
1693 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 ( 99.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MABARAKPUR Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000707/2022-2023 | 1165/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 7.79 | 7.03 | 100
1694 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 99.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MABARAKPUR Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000708/2022-2023 | 1166/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 7.79 | 6.2 | 100
1695 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Mobarakpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000730/2022-2023 | 1204/MD | 21/03/2023 | 45 | M. S. AGENCY | 8.3 | 8.28 | 100
1696 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall and pathway at 3rd Tube well Site of MOBARAKPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000908/2023-2024 | 286/MD | 11/01/2024 | 45 | M. S. AGENCY | 7.66 | 7.61 | 100
1697 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning & Trial operation of electro-mechanical components at T/W no III & IV of Source Augmentation Mabarakpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016719) | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000700/2023-2024 | 2775/MLMD | 14/08/2023 | 180 | SUDIP DEY | 21.81 | 21.54 | 100
1698 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 4th Tube well Site of MOBARAKPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000961/2023-2024 | 712/MD | 09/02/2024 | 45 | S. R. ENTERPRISE | 6.71 | 6.7 | 100
1699 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 900 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Alipur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (2nd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000033/2023-2024 | 868/MAAD | 04/05/2023 | 698 | NEOGI ENTERPRISE | 364.29 | 67.4 | 80
1700 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 3rd Tube Well site of Alipur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000259/2023-2024 | 2056/MAAD | 22/11/2023 | 131 | BINA CONSTRUCTION | 5.02 | 4.26 | 100
1701 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site of Alipur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000260/2023-2024 | 2057/MAAD | 22/11/2023 | 161 | TARUN KANTI BAGCHI | 5.02 | 0 | 100
1702 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Alipur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000261/2023-2024 | 2058/MAAD | 22/11/2023 | 547 | MERCURY ENGINEERING COMPANY | 271.74 | 0 | 10
1703 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of Three nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Alipur Piped Water supply scheme (Head Work Site, 2nd Tube well site & 3rd Tube well site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000262/2023-2024 | 2055/MAAD | 22/11/2023 | 45 | M/S S.S. ENTERPRISE | 22.17 | 14.32 | 100
1704 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site , 2nd Tube Well Site and 3rd Tube Well Site, Laying of rising main from 2nd and 3rd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Alipur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000290/2024-2025 | 406/MAAD | 12/03/2025 | 90 | NEOGI ENTERPRISE | 125.15 | 0 | 0
1705 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System for Alipur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000379/2023-2024 | 281/MAAD | 06/03/2024 | 90 | SOFIQUL ISLAM | 166.6 | 32.41 | 30
1706 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | RTOR000013/2023-2024 | 666/MAAD | 11/04/2023 | 0 | Resource Division | 25.35 | 0 | 0
1707 | Malda Mechanical | Malda Arsenic Area W/S Division | Quotation Payment of ALIPUR T/W II for WBSEDCL Under Kaliachak CCC Under the district of MALDA | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | BILL/03525/2024-2025 | BP-2024-25-749 | 28/03/2025 | 0 | W.B.S.E.D.C.LTD | 7.71 | 0 | 0
1708 | Malda Mechanical | Malda Arsenic Area W/S Division | Quotation Payment for ALIPUR T/W III Under Kaliachak CCC Under the district of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | BILL/03526/2024-2025 | BP-2024-25-750 | 28/03/2025 | 0 | W.B.S.E.D.C.LTD | 6.72 | 0 | 0
1709 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I , II & III and Arsenic Iron Removal Plant at Alipur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000737/2023-2024 | 2614/MLMD | 10/08/2023 | 1022 | DIPALI CONSTRUCTION. | 86.14 | 0 | 32
1710 | Malda Mechanical | Malda Arsenic Area W/S Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/001770/2024-2025 | 4336/MLMD | 31/12/2024 | 59 | SUBRATA SAHA | 0.77 | 0 | 0
1711 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of KANDARAN ZONE-I Piped Water Supply Scheme at Chanchal-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000041/2023-2024 | 1910/MD | 11/05/2023 | 966 | M/S SINHA CONSTRUCTION CO. | 1071.52 | 931.95 | 93
1712 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Kandaran Zone-I Water Supply Scheme in Chanchol- II block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000147/2021-2022 | 1745/MD | 15/06/2021 | 14 | INDRANIL DUTTA & ACCOCIATES | 2.86 | 2.86 | 0
1713 | Malda Division | Malda Mechanical Division | Sinking of Tube Well No -I & Replacement of Existing Tube Well at Site No- II each of 200mm Dia all through and 180 Mtr. Deep Big Dia Tube Well at Kandaran Zone-I Piped Water Supply Scheme at Chanchal -II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000193/2025-2026 | 3692/MD | 29/07/2025 | 216 | ASHIS CONSTRUCTION | 21.23 | 0 | 50
1714 | Malda Division | Malda Mechanical Division | Restoration of pipe line by concreting of Kandaran Zone -II Water Supply Scheme under Chanchal -II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000202/2025-2026 | 3694/MD | 29/07/2025 | 275 | UTTAM KUMAR GHOSH | 41.82 | 0 | 0
1715 | Malda Division | Malda Mechanical Division | Design, Supplying. Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 100 m3/hr. & 2 No. 50 m3/hr capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Kandaran Zone-II Water Supply Scheme of Chanchal-II Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000203/2025-2026 | 3695/MD | 29/07/2025 | 300 | VISCOUS ENGINEERS PVT. LTD. | 76.69 | 0 | 0
1716 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying Distribution pipe line for KANDARON (ZONE-II) & its adjoining mouzas piped water supply at Chanchal-II Block in the District Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000585/2022-2023 | 818/MD | 20/02/2023 | 981 | UTTAM KUMAR GHOSH | 175.28 | 141.83 | 100
1717 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of OHR and providing Functional Household Tap Connection for Augmentation of Kandaran Zone -II Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000600/2023-2024 | 4321/MD | 16/10/2023 | 533 | WELFARE ENGINEERING CO-OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 187.94 | 29 | 75
1718 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kandaran Zone-I Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000828/2024-2025 | 701/MD | 21/02/2025 | 45 | M/S SINHA CONSTRUCTION CO. | 33.12 | 0 | 0
1719 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd TW site of KANDARAN ZONE-I Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/001037/2023-2024 | 1520/MD | 16/03/2024 | 406 | JUPITAR LABOUR CO-OPERATIVE CONTRACT AND CONSTRUCTION SOCIETY LTD. | 31.42 | 0 | 80
1720 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000045/2025-2026 | 2867/MD | 16/06/2025 | 0 | Resource Division | 12.57 | 0 | 0
1721 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000061/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 157.32 | 0 | 0
1722 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000126/2023-2024 | 96/MD | 05/01/2024 | 0 | Resource Division | 38.49 | 0 | 0
1723 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Augmentation of Kandaran (Zone-I I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011258) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000620/2023-2024 | 2658/MLMD | 10/08/2023 | 2005 | DILIP MAHATO. | 34.5 | 11.56 | 67
1724 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I zone-I of Kandaran PWSS, Malatipur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000782/2023-2024 | 3004382812 | 21/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.67 | 5.67 | 100
1725 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II, III & IV and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Augmentation of Kandaran (Zone- I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011258) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/001701/2023-2024 | 3424/MLMD | 01/11/2023 | 1058 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 45.31 | 33.78 | 74
1726 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Lashratalla, Madhyapara & Nabinagar for Nabinagar Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000002/2023-2024 | 639/MAAD | 06/04/2023 | 451 | DHRITIPALI | 34.15 | 25.3 | 85
1727 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Paschim Chamatola, Bankpara, Layagram, Puratun Tola for Nabinagar Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000003/2023-2024 | 640/MAAD | 06/04/2023 | 60 | SOVON KUMAR DAS | 50.45 | 39.03 | 95
1728 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Nabinagar Piped Water supply scheme (Head Work Site & 2nd Tube well Site ) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda (2nd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000105/2023-2024 | 1412/MAAD | 20/07/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 14.64 | 10.1 | 100
1729 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site of Nabinagar Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000127/2023-2024 | 1470/MAAD | 01/08/2023 | 427 | M/S A.B. CONSTRUCTION | 5.02 | 0 | 100
1730 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Nabinagar Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000241/2024-2025 | 1695/MAAD | 19/11/2024 | 30 | DHRITIPALI | 31.71 | 0 | 0
1731 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 450 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation for Nabinagar Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000264/2023-2024 | 3018/MAAD | 06/12/2023 | 573 | M/S AMIT KUMAR GUPTA | 164.67 | 51.82 | 80
1732 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Nabinagar Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. (2ND Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000277/2023-2024 | 3079/MAAD | 14/12/2023 | 365 | SOFIQUL ISLAM | 151.63 | 0 | 15
1733 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | RTOR000005/2023-2024 | 627/MAAD | 05/04/2023 | 0 | Resource Division | 26.27 | 0 | 0
1734 | Malda Mechanical | Malda Arsenic Area W/S Division | QUOTATION PAYMENT FOR NABINAGAR W/S SCHEME T/W NO 1 UNDER KALIACHAK CCC UNDER MALDA DISTRICT | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | BILL/01613/2024-2025 | BP-2024-25-397 | 29/07/2024 | 0 | W.B.S.E.D.C.LTD | 3.91 | 0 | 0
1735 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Nabinagar Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017551) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000659/2023-2024 | 2687/MLMD | 11/08/2023 | 1049 | DEY ENTERPRISE.. | 65.66 | 41.89 | 45
1736 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Nabinagar PWSS, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/001012/2023-2024 | 3004427272 | 18/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.26 | 4.26 | 100
1737 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-I Piped Water Supply Scheme at Manikchak Dev. Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000025/2023-2024 | 1752/MD | 26/04/2023 | 921 | M/S PARIMAL DAS | 154.83 | 137.46 | 85
1738 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-I Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000149/2024-2025 | 2918/MD | 10/06/2024 | 30 | M/S PARIMAL DAS | 26.22 | 0 | 0
1739 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Chandipur Zone-I Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000655/2024-2025 | 6402/MD | 19/12/2024 | 45 | M/S PARIMAL DAS | 12.41 | 0 | 0
1740 | Malda Division | Malda Mechanical Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Car-2) (Period from 01/01/2026 to 30/06/2026). | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000845/2025-2026 | 6431/MD | 31/12/2025 | 181 | SINGH BROTHERS | 0.86 | 0 | 0
1741 | Malda Division | Malda Mechanical Division | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000965/2024-2025 | 654/MD | 19/02/2025 | 7 | DHRITIPALI | 0.55 | 0 | 0
1742 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 30.00M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-I Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000991/2023-2024 | 1276/MD | 15/03/2024 | 728 | GIYASUDDIN SEKH | 133.01 | 0 | 35
1743 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000095/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 82.44 | 0 | 0
1744 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Uttar Chandipur Zone- I, Mathurapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | BILL/02568/2023-2024 | BP-2023-24-463 | 17/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.06 | 0 | 0
1745 | Malda Mechanical | Malda Mechanical Division | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XI and Arsenic Iron Removal Plant at UTTAR CHANDIPUR (ZONE-I) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019385) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000635/2023-2024 | 2679/MLMD | 11/08/2023 | 1174 | MERCURY ENGINEERING COMPANY. | 48.39 | 36.5 | 40
1746 | Malda Division | Malda Mechanical Division | Payment for rural road damage at Par Bhaluka to Ilam Paschimpara (WB 11212) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | BILL/00801/2024-2025 | BP-2024-25-374 | 18/11/2024 | 0 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 4 | 0 | 0
1747 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of SUJAPUR Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000095/2023-2024 | 2168/MD | 07/06/2023 | 1025 | NEOGI ENTERPRISE | 395.25 | 105.67 | 50
1748 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 3 of Sujapur Piped Water Supply Scheme under Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000108/2025-2026 | 2279/MD | 21/05/2025 | 90 | LAXMI ENTERPRISE | 15.16 | 0 | 0
1749 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tubewell Site of Sujapur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000151/2024-2025 | 2920/MD | 10/06/2024 | 509 | NEOGI ENTERPRISE | 21.09 | 0 | 95
1750 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Sujapur Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000317/2024-2025 | 3965/MD | 07/08/2024 | 180 | NEOGI ENTERPRISE | 30.19 | 0 | 0
1751 | Malda Division | Malda Mechanical Division | Sinking of 200 mm (all through) Big Dia. Tube-Well of 130 M Deep at Rahutgaon (JL No-27) mouza under Sujapur PWSS of Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000452/2024-2025 | 4808/MD | 13/09/2024 | 152 | NEOGI ENTERPRISE | 9.07 | 0 | 0
1752 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sujapur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/001022/2023-2024 | 1191/MD | 14/03/2024 | 45 | NEOGI ENTERPRISE | 26.42 | 0 | 0
1753 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000173/2023-2024 | 406/MD | 18/01/2024 | 0 | Resource Division | 2.22 | 0 | 0
1754 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000189/2023-2024 | 811/MD | 21/02/2024 | 0 | Resource Division | 31.08 | 0 | 0
1755 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Additional Quotation charge at TW No- I of Sujapur PWSS, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | BILL/00470/2025-2026 | 124 | 07/08/2025 | 0 | W.B.S.E.D.C.LTD | 1 | 0 | 0
1756 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Sujapur, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | BILL/00775/2024-2025 | BP-2024-25-188 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 2.94 | 0 | 0
1757 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Sujapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/018437) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000695/2023-2024 | 2770/MLMD | 14/08/2023 | 180 | M/S. KUNDU BROTHERS.. | 25.32 | 0 | 0
1758 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Kabirajtola, Chowdhury Para for Sadipur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000126/2023-2024 | 1460/MAAD | 26/07/2023 | 60 | M/S MANDAL & SONS | 1.83 | 1.6 | 100
1759 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 250mm, 200mm dia DI pipe line and Supply and delivery of all type of specials & valves at Sadipur Piped Water supply scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000128/2024-2025 | 1259/MAAD | 24/06/2024 | 30 | BINA CONSTRUCTION | 6.28 | 6.08 | 100
1760 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Sadipur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000210/2023-2024 | 1575/MAAD | 25/08/2023 | 494 | MERCURY ENGINEERING COMPANY | 156.64 | 7.83 | 40
1761 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 450 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Sadipur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda(2ND Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000218/2023-2024 | 1706/MAAD | 20/09/2023 | 650 | M/S N. C. SARKAR | 203.63 | 0 | 75
1762 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Sadipur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000244/2024-2025 | 1698/MAAD | 19/11/2024 | 60 | SHREE BISHNU CONSTRUCTION | 65.9 | 0 | 0
1763 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Sadipur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000464/2022-2023 | 553/MAAD | 24/03/2023 | 45 | A.L. ENGINEERING SOLUTION | 14.65 | 10.38 | 100
1764 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Kabirajtola, Chowdhury Para for Sadipur Piped Water supply scheme at Kaliachak-II Block under Malda Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000466/2022-2023 | 598/MAAD | 30/03/2023 | 60 | M/S MANDAL & SONS | 44.94 | 41.62 | 100
1765 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Pathan Para, Mia Para, Dhanuk Para, Barkattabad, Rishi Para, Molla Para for Sadipur Piped Water supply scheme at Kaliachak-II Block under Malda Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000468/2022-2023 | 600/MAAD | 30/03/2023 | 60 | BINA CONSTRUCTION | 43.18 | 42.39 | 100
1766 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Sadipur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000472/2022-2023 | 610/MAAD | 31/03/2023 | 422 | A.L. ENGINEERING SOLUTION | 5.02 | 0 | 0
1767 | Malda Mechanical | Malda Arsenic Area W/S Division | QUOTATION PAYMENT FOR SADIPUR W/S SCHEMEBPH NO 2 UNDER MOTHABARI CCC UNDER MALDA DISTRICT | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | BILL/00469/2025-2026 | 124 | 07/08/2025 | 0 | W.B.S.E.D.C.LTD | 4.37 | 0 | 0
1768 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Sadipur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017477) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000134/2023-2024 | 2051/MLMD | 30/06/2023 | 1260 | MERCURY ENGINEERING COMPANY. | 63.89 | 40.05 | 30
1769 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Sadipur , Mothabari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000717/2023-2024 | 3004390610 | 14/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.45 | 3.45 | 100
1770 | Malda Division |  | Formal work order for the work of Implementation of BABUPUR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000360/2023-2024 | 3033/MD | 09/08/2023 | 1023 | M/S UDYOG & CO. | 1331.07 | 671.46 | 65
1771 | Malda Division |  | Construction of Boundary Wall at 2nd Tube well site of Babupur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000676/2024-2025 | 6201/MD | 09/12/2024 | 45 | M/S GHOSH CONSTRUCTION | 7.15 | 0 | 0
1772 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Babupur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000717/2024-2025 | 6408/MD | 19/12/2024 | 423 | MANIK CHOUDHURY | 50.96 | 0 | 0
1773 | Malda Division |  | Dedicated Pipe laying for better Functionality and Providing Balance FHTC, Construction of Approach Road, Land development and allied work for BABUPUR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. Govt. of West Bengal. |  |  | ORD/000904/2025-2026 | 468/MD | 27/01/2026 | 60 | M/S UDYOG & CO. | 47.97 | 0 | 0
1774 | Malda Division |  | Erection of Property board related to Jal Jeevan Mission works of Fatepur, Paharpur, Uttar Mahinagar, Arazi Jalsa, Babupur, Rajaramchak & Emamnagar PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000950/2024-2025 | 639/MD | 19/02/2025 | 7 | S. N. CONSTRUCTION | 0.95 | 0 | 0
1775 | Malda Division |  | Erection of Jal Jeevan Mission Sign Board for Babupur and Hatnagar PWSS at Gazol block under RWS Malda Sub-Division in the district of Malda. |  |  | ORD/000974/2024-2025 | 663/MD | 19/02/2025 | 7 | S. M. BUILDER | 0.26 | 0 | 100
1776 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000001/2025-2026 | 1291/MD | 03/04/2025 | 0 | Resource Division | 28.59 | 0 | 0
1777 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000009/2025-2026 | 2583/MD | 30/05/2025 | 0 | Resource Division | 6.94 | 0 | 0
1778 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 6156/MD | 05/12/2024 | 0 | Resource Division | 12.16 | 0 | 0
1779 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000161/2023-2024 | 236/MD | 10/01/2024 | 0 | Resource Division | 19.1 | 0 | 0
1780 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 815/MD | 21/02/2024 | 0 | Resource Division | 49.72 | 0 | 0
1781 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Babupur, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03682/2023-2024 | BP-2023-24-665 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.41 | 0 | 0
1782 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Babupur, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03683/2023-2024 | BP-2023-24-666 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.75 | 0 | 0
1783 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Babupur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014434) |  |  | ORD/000375/2023-2024 | 2383/MLMD | 28/07/2023 | 180 | GHOSH BROTHERS... | 41.99 | 0 | 0
1784 | Malda Division | RWS Malda Sub-Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at (KM.-18/8-18/9) between Bulbulchandi(BBC) to Singabad(SQB) station for HARGOA and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/00189/2024-2025 | BP-2024-25-91 | 13/06/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 0.11 | 0 | 0
1785 | Malda Division | RWS Malda Sub-Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at (KM.-18/8-18/9) between Bulbulchandi(BBC) to Singabad(SQB) station for HARGOA and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/00347/2024-2025 | BP-2024-25-194 | 06/08/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 6.2 | 0 | 0
1786 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Implementation of HORGOA Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000037/2023-2024 | 1887/MD | 08/05/2023 | 694 | M/S PARIMAL DAS | 418.92 | 208.6 | 45
1787 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of HORGOA Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000098/2023-2024 | 2325/MD | 08/06/2023 | 60 | M/S S. S. ENTERPRISE | 75.74 | 39.56 | 40
1788 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tube well site of Hargoa Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000124/2025-2026 | 2482/MD | 28/05/2025 | 60 | SAYEM ENTERPRISE | 6.89 | 0 | 0
1789 | Malda Division | RWS Malda Sub-Division | Sinking of Tubewell, Providing FHTC, Construction of Pump House & Boundary wall at Horgoa Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000483/2024-2025 | 5083/MD | 27/09/2024 | 60 | M/S TECHNICO & CO | 44.88 | 0 | 0
1790 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Hargoa Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000628/2024-2025 | 5835/MD | 22/11/2024 | 313 | RABIUL ISLAM | 15.25 | 0 | 0
1791 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work Site of Hargoa Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000629/2024-2025 | 5836/MD | 22/11/2024 | 281 | M/S ANKUSH ENTERPRISE | 22.71 | 0 | 90
1792 | Malda Division | RWS Malda Sub-Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 18/9-19/0 betweenBulbulchandi (BBC) to Shingabad Station(SQB) Station for HARGOA and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000911/2023-2024 | 384/MD | 17/01/2024 | 440 | GHOSH CONSTRUCTION | 28.86 | 0 | 100
1793 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000029/2025-2026 | 2831/MD | 11/06/2025 | 0 | Resource Division | 10.56 | 0 | 0
1794 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000039/2023-2024 | 1810/MD | 27/04/2023 | 0 | Resource Division | 20.8 | 0 | 0
1795 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Horgoa, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/02463/2023-2024 | BP-2023-24-396 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 7.77 | 0 | 0
1796 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Horgoa, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/02489/2023-2024 | BP-2023-24-424 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.6 | 0 | 0
1797 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at Pole shifting at Horgoa, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/03234/2023-2024 |  | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 0.57 | 0 | 0
1798 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Horgao Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015215) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000318/2023-2024 | 2320/MLMD | 26/07/2023 | 1080 | M/S CHANDRANATH MUKHERJEE. | 26.64 | 21.71 | 80
1799 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Sakullapur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. (2ND Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000229/2023-2024 | 1816/MAAD | 05/10/2023 | 605 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 133.47 | 16.58 | 80
1800 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site and Providing Functional House Hold Tap Connection (FHTC) for Sakullapur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000240/2024-2025 | 1694/MAAD | 19/11/2024 | 45 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 31.56 | 0 | 0
1801 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 250 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Sakullapur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000376/2023-2024 | 111/MAAD | 01/02/2024 | 547 | MAHBUB AND SONS | 100.84 | 37.62 | 80
1802 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Sakullapur Piped Water supply scheme (Head Work Site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000465/2022-2023 | 554/MAAD | 24/03/2023 | 45 | MD. TALEB ALI | 7.32 | 5.64 | 100
1803 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System for Sakullapur Piped Water supply scheme at Kaliachak-II Block under Malda Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000469/2022-2023 | 611/MAAD | 31/03/2023 | 60 | M/S MOON LIGHT CONSTRUCTION & CO. | 57.45 | 54.87 | 95
1804 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | RTOR000006/2023-2024 | 629/MAAD | 05/04/2023 | 0 | Resource Division | 4.29 | 0 | 0
1805 | Malda Mechanical | Malda Arsenic Area W/S Division | Quotation payment for Sukurullapur T/W NO 1 Under Mothabari ccc under Malda district | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | BILL/03200/2024-2025 | BP-2024-25-638 | 06/02/2025 | 0 | W.B.S.E.D.C.LTD | 7.43 | 0 | 0
1806 | Malda Mechanical | Malda Arsenic Area W/S Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000124/2024-2025 | 1679/MLMD | 26/06/2024 | 62 | SUBRATA SAHA | 0.78 | 0.77 | 0
1807 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I and Arsenic Iron Removal Plant at Sukurullapur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018013) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000664/2023-2024 | 2690/MLMD | 11/08/2023 | 1212 | ANIMA ENTERPRISE | 48.84 | 28.36 | 40
1808 | Malda Division | Malda Mechanical Division | shifting of ex 63 kva &100 kva DTR at hatinda OHR site. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/01041/2024-2025 | BP-2024-25-423 | 17/03/2025 | 0 | W.B.S.E.D.C.LTD | 5.38 | 0 | 0
1809 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep at Head Work Site at HATINDA Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000110/2025-2026 | 2410/MD | 27/05/2025 | 45 | MONDAL CONSTRUCTION | 10.65 | 0 | 0
1810 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of HATINDA & its adjoining mouza Water Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000297/2022-2023 | 2193/MD | 22/09/2022 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 6.66 | 0 | 1
1811 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line of HATINDA and it's adjoining mouzas Pipe Water Supply Scheme at Chanchal-I Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000333/2022-2023 | 2372/MD | 11/10/2022 | 325 | USHA ENTERPRISE | 381.98 | 362.62 | 95
1812 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 160 Mtr. Deep Big dia Tube well (2 Nos.) at HATINDA Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000675/2022-2023 | 1138/MD | 20/03/2023 | 671 | DUTTA ENTERPRISE | 21.12 | 0 | 100
1813 | Malda Division | Malda Mechanical Division | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Hatinda Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000863/2024-2025 | 1102/MD | 20/03/2025 | 60 | USHA ENTERPRISE | 119.77 | 0 | 0
1814 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at HATINDA Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000969/2023-2024 | 828/MD | 21/02/2024 | 388 | MD. MANSUR ALI | 4.14 | 0 | 100
1815 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at HATINDA Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000970/2023-2024 | 829/MD | 21/02/2024 | 45 | MD. MANSUR ALI | 4.14 | 0 | 0
1816 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000005/2023-2024 | 1815/MD | 27/04/2023 | 0 | Resource Division | 29.46 | 0 | 0
1817 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000029/2022-2023 | 2754/MD | 22/11/2022 | 0 | Resource Division | 25.94 | 0 | 0
1818 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000115/2023-2024 | 85/MD | 05/01/2024 | 0 | Resource Division | 13.89 | 0 | 0
1819 | Malda Mechanical | Malda Mechanical Division | New service connection at Hatinda PWSS T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Kushida c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/02385/2025-2026 |  | 24/09/2025 | 0 | W.B.S.E.D.C.LTD | 3.51 | 0 | 0
1820 | Malda Mechanical | Malda Mechanical Division | Service connection charge for Hatinda P/H-II PWSS under Malda Mechanical Divsion PHE DTe. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/02663/2025-2026 |  | 10/11/2025 | 0 | W.B.S.E.D.C.LTD | 5.9 | 0 | 0
1821 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Augmentation of Hatinda Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011729) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000262/2023-2024 | 2222/MLMD | 18/07/2023 | 1164 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 42.68 | 33.54 | 78
1822 | Malda Mechanical | Malda Mechanical Division | Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/003248/2023-2024 | 3887/MLMD | 20/12/2023 | 60 | SUBRATA SAHA | 0.77 | 0.72 | 100
1823 | Malda Division | RWS Malda Sub-Division | Dismantling & Restoration of Cement Concrete Road, Construction of Trust Block for protection of pipe line within the command area for DAKSHIN BRINDABANBATI Piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | ORD/000069/2025-2026 | 2262/MD | 21/05/2025 | 30 | M/S JHA CONSTRUCTION | 4.27 | 0 | 100
1824 | Malda Division | RWS Malda Sub-Division | Replacement of 200 mm dia. all through Tube Well at Head Work site (75m Deep) by D.R. Rig. Method using P.V.C. pipe & filter including supply of materials of Dakshin Brindabanbati Piped Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. Govt. of West Bengal. | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | ORD/000080/2025-2026 | 2274/MD | 21/05/2025 | 30 | A. L. ENGINEERING SOLUTION | 6.9 | 0 | 0
1825 | Malda Division | RWS Malda Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | ORD/000134/2021-2022 | 1525/MD | 05/05/2021 | 30 | M/S DAS CONSTRUCTION | 57.24 | 71 | 1
1826 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | RTOR000039/2025-2026 | 2816/MD | 11/06/2025 | 0 | Resource Division | 10.61 | 0 | 0
1827 | Malda Division | RWS Malda Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000072/2020-2021 | 2439/MD | 12/10/2020 | 45 | M/S AMIT KUMAR GUPTA | 72.29 | 113.12 | 66
1828 | Malda Division | RWS Malda Sub-Division | Replacement of 200 mm dia. all through Tube Well at 2nd Tube Well site (130m Deep) by D.R. Rig. Method using P.V.C. pipe & filter including supply of materials of Mianagar Piped Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. Govt. of West Bengal. | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000079/2025-2026 | 2273/MD | 21/05/2025 | 94 | HARUN ALL RASHID & BROTHERS | 9.21 | 0 | 100
1829 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-III) | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000124/2022-2023 | 1642/MD | 19/07/2022 | 30 | M/S AMIT KUMAR GUPTA | 16.26 | 0.04 | 1
1830 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of MAHESHPUR Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000132/2020-2021 | 2442/MD | 12/10/2020 | 30 | M/S PRATIMA CONSTRUCTION | 14.91 | 0.06 | 1
1831 | Malda Division | RWS Malda Sub-Division | Design , Supplying, Fabrication, Erection, & Commissioning including 3 (three) months Trial Run of 25 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Mianagar Water Supply Scheme of Habibpur Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000161/2025-2026 | 2760/MD | 09/06/2025 | 431 | UTTAM KUMAR GHOSH | 15.57 | 0 | 0
1832 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000551/2020-2021 | 2439/MD | 12/10/2020 | 120 | M/S AMIT KUMAR GUPTA | 20 | 7.03 | 0
1833 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of UPVC pipe line in place of damaged portion due to the construction of PMGSY road at KANDARAN ZONE-I Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (Part-III) | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000576/2021-2022 | 36/CSD | 07/01/2022 | 20 | M/S FOUR STAR CONSTRUCTION | 4.84 | 0.22 | 1
1834 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | RTOR000032/2025-2026 | 2819/MD | 11/06/2025 | 0 | Resource Division | 10.77 | 0 | 0
1835 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Laxmipur Water Supply Scheme (Mouza- Khanpur) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000124/2022-2023 | 1025/MAAD | 12/05/2022 | 45 | BENGAL ENGINEERING COMPANY | 10.69 | 9.56 | 1
1836 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
1837 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying 63/75/90 mm dia loop Pipe line to connect Chowdhury para and Pichli village to provide sufficient drinking water though FHTC at Pichli Village and construction of approach road and boundary wall at reservoir site with allied work under Laxmighat W/S Scheme under Malda Arsenic Area W/S Division P.H.E Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000193/2022-2023 | 1404/MAAD | 26/07/2022 | 45 | FUTURE | 15.68 | 14.25 | 1
1838 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Laxmighat Water Supply Scheme (Mouza- Lakhmighat) extra pipe line at Lakhmipur village at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000295/2022-2023 | 2035/MAAD | 16/11/2022 | 45 | ANJIMA CONSTRUCTION CO. | 8.3 | 7.77 | 1
1839 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Lakshmipur Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza-Panchanandapur) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000339/2021-2022 | 1748/MAAD | 24/11/2021 | 60 | MILLENNIUM ENTERPRISE | 37.54 | 37.52 | 1
1840 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 160 mm dia UPVC Pipe line and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Michhutola, Bhagattola under Uttar Laxmipur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000453/2022-2023 | 328/MAAD | 21/02/2023 | 60 | M/S BABLU ENTERPRISE, | 21.8 | 21.72 | 100
1841 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | RTOR000005/2022-2023 | 1337/MAAD | 18/07/2022 | 0 | Resource Division | 12.3 | 0 | 0
1842 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Dhulauri ,Hunumannagar & Bedrabad under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000013/2023-2024 | 803/MAAD | 24/04/2023 | 15 | DEY CONSTRUCTION | 3.91 | 3.89 | 0
1843 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area(Mouza Laxmipur Part, Bedrabad) & others Allied works at Dariapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000044/2022-2023 | 820/MAAD | 28/04/2022 | 60 | DEY CONSTRUCTION | 53.78 | 53.59 | 1
1844 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Munshitola,Tewari Tola under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000056/2022-2023 | 908/MAAD | 10/05/2022 | 15 | DEY CONSTRUCTION | 4.81 | 4.8 | 1
1845 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Baultola, Bikkol Tola under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000057/2022-2023 | 909/MAAD | 10/05/2022 | 15 | DEY CONSTRUCTION | 1.73 | 1.72 | 1
1846 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Dariapur Mouza under command area of Dariapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000115/2022-2023 | 1017/MAAD | 12/05/2022 | 60 | M/S PARIMAL DAS | 56.47 | 56.23 | 1
1847 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
1848 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipe 90mm,75mm dia at Kochpara ,Bajapti & others Allied works at Dariapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000212/2023-2024 | 887/MAAD. | 11/05/2023 | 45 | MADHUMITA ENTERPRISE | 9.44 | 8.25 | 100
1849 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Bedrabad ,Dulauri ,Srikasti & Manasa Mandir para under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000252/2022-2023 | 1830MAAD | 27/09/2022 | 30 | DEY CONSTRUCTION | 4.07 | 4.06 | 1
1850 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC Pipe Line of 90mm &75 mm dia at Different part of Dariapur Mouza for coverage of FHTC under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000269/2022-2023 | 1871/MAAD | 28/09/2022 | 45 | M/S PARIMAL DAS | 4.49 | 4.42 | 1
1851 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Bajapti &Khochpara under command area of Dariapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000289/2022-2023 | 2029/MAAD | 16/11/2022 | 45 | M/S MOON LIGHT CONSTRUCTION & CO. | 19.84 | 19.13 | 1
1852 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Bajapti &Khochpara under command area of Dariapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000290/2022-2023 | 2005/MAAD | 11/11/2022 | 45 | M/S MOON LIGHT CONSTRUCTION & CO. | 19.84 | 0 | 1
1853 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Diferent villages under Bedrabad GP (Dhulauri,Hunumannagar,Bedrabad) under command area of Dariapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000292/2022-2023 | 2031/MAAD | 16/11/2022 | 60 | DEY CONSTRUCTION | 56.08 | 55.8 | 1
1854 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dariapur Water Supply Scheme(Mouza-Laxmipur,Baisnabnagar) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000315/2021-2022 | 1728/MAAD | 24/11/2021 | 60 | DEY CONSTRUCTION | 46.22 | 46.12 | 1
1855 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipeline at Kochpara to faciliate of House connection & others Allied works at Dariapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000359/2022-2023 | 70/MAAD | 11/01/2023 | 60 | DHRITIPALI | 6.69 | 6.57 | 0
1856 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipe 90mm dia at Srikasti,Chulkani & others Allied works at Dariapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000519/2021-2022 | 350/MAAD | 07/03/2022 | 45 | GIRIDHARI CONSTRUCTION | 2.9 | 2.88 | 1
1857 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe line of 20 mm dia at Birjutola,Sam Mahamand Tola,Laxmipur Villages Under Laxmipur GP under Dariapur distribution Zone under Malda Arsenic Area W/S Division, P.H.E.Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000532/2021-2022 | 363/MAAD | 07/03/2022 | 30 | DEY CONSTRUCTION | 4.81 | 4.77 | 1
1858 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme (Mouza- Nabinagar) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000112/2022-2023 | 1014/MAAD | 12/05/2022 | 60 | M/S ALISA CONSTRUCTION | 82.2 | 0 | 15
1859 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
1860 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Continuation Work Order for Placing of diesel driven Car on hire basis for official use of the Executive Engineer, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(for the period from 01.01.2023 to 31.12.2023)= 365 days | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000404/2022-2023 | 2330/MAAD | 28/12/2022 | 365 | NITAI PANDEY | 1.73 | 3.9 | 25
1861 | Malda Division | Malda Mechanical Division | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) and Laying of Rising Main including Specials and Valves for Gauria Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000192/2025-2026 | 3384/MD | 10/07/2025 | 180 | S DUTTA | 100.31 | 0 | 0
1862 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of GOURIA & its adjoining mouza Water Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000296/2022-2023 | 2192/MD | 22/09/2022 | 279 | RAJIB MANI | 6.69 | 4.82 | 100
1863 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 160 Mtr. deepTube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of GOURIA Water Supply Scheme at Chanchal I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000324/2022-2023 | 2346/MD | 29/09/2022 | 30 | MECHANO TRADING CO. | 9.96 | 8.77 | 100
1864 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line of GAURIA and its adjoining mouzas Pipe Water Supply Scheme at Chanchal-I Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000353/2022-2023 | 2412/MD | 17/10/2022 | 90 | S DUTTA | 374.04 | 259.84 | 92
1865 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Gauria Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000661/2024-2025 | 6196/MD | 09/12/2024 | 45 | M/S GHOSH ENTERPRISE | 7.23 | 0 | 0
1866 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 600 M3 Capacity Over Head Reservoir with Soil Investigation and FHTC of GAURIA Piped Water Supply Scheme at Chanchal-I Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000665/2022-2023 | 1036/MD | 13/03/2023 | 750 | SOVAN KUMAR ROY | 293.21 | 117.31 | 78
1867 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube Well site of Gauria Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000672/2024-2025 | 6197/MD | 09/12/2024 | 45 | M/S DYNAMIC CONSTRUCTION | 7.23 | 0 | 0
1868 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 160 Mtr. Deep Big dia Tube well (2 Nos.) at GAURIA Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000674/2022-2023 | 1137/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 21.11 | 19.4 | 50
1869 | Malda Division | Malda Mechanical Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-2) (Period from 01/01/2026 to 30/06/2026). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000849/2025-2026 | 6435/MD | 31/12/2025 | 181 | M/S FOUR STAR CONSTRUCTION | 0.86 | 0 | 30
1870 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No.- 2 at Gauria PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000891/2023-2024 | 165/MD | 08/01/2024 | 45 | SK ENTERPRISE | 4.17 | 4.17 | 100
1871 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No.- 3 at Gauria PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000892/2023-2024 | 271/MD | 11/01/2024 | 45 | S. M. BUILDER | 4.18 | 4.18 | 100
1872 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | RTOR000027/2022-2023 | 2757/MD | 22/11/2022 | 0 | Resource Division | 45.2 | 0 | 0
1873 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | RTOR000043/2025-2026 | 2869/MD | 16/06/2025 | 0 | Resource Division | 12.89 | 0 | 0
1874 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | RTOR000114/2023-2024 | 84/MD | 05/01/2024 | 0 | Resource Division | 13.46 | 0 | 0
1875 | Malda Mechanical | Malda Mechanical Division | New service connection at GAURIA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.(KUSHIDA c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | BILL/00233/2024-2025 | BP-2024-25-97 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.27 | 0 | 0
1876 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of GAURIA PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | BILL/02537/2023-2024 | BP-2023-24-440 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.22 | 0 | 0
1877 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Gauria PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000299/2023-2024 | 3004302683 | 21/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.63 | 2.63 | 100
1878 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Gauria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011717) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000316/2023-2024 | 2318/MLMD | 26/07/2023 | 1081 | DIPALI CONSTRUCTION. | 37.94 | 34.01 | 90
1879 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 600 M3 Capacity OHR with soil Investigation and FHTC of WARI Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000007/2023-2024 | 1567/MD | 10/04/2023 | 270 | SAMBHU NATH SARKAR | 288.41 | 107.97 | 42
1880 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (2 Nos.) at WARI Water Supply Scheme under Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000018/2023-2024 | 1675/MD | 18/04/2023 | 30 | SAUDAGAR INDIA | 20.31 | 18.41 | 100
1881 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000169/2024-2025 | 2944/MD | 10/06/2024 | 30 | MS ENTERPRISE | 9.33 | 0 | 5
1882 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube Well site of Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000170/2024-2025 | 2945/MD | 10/06/2024 | 30 | MS ENTERPRISE | 9.33 | 0 | 90
1883 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000218/2024-2025 | 3039/MD | 13/06/2024 | 567 | SAMBHU NATH SARKAR | 36.41 | 0 | 90
1884 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 100m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Wari Water Supply Scheme of Harishchandrapur-I Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000256/2024-2025 | 3204/MD | 27/06/2024 | 368 | WATER TECH | 35.67 | 0 | 5
1885 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of WARI & its adjoining mouza Water Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000299/2022-2023 | 2195/MD | 22/09/2022 | 45 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 6.67 | 6.59 | 97
1886 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 150 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of WARI Water Supply Scheme at Harishchandrapur I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000327/2022-2023 | 2349/MD | 29/09/2022 | 30 | MECHANO TRADING CO. | 9.65 | 8.06 | 100
1887 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line of WARI and its adjoining mouzas Pipe Water Supply Scheme at Harishchandrapur-I Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000336/2022-2023 | 2396/MD | 14/10/2022 | 90 | GHOSH BROTHERS | 379.96 | 331.28 | 85
1888 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) & Laying of additional Pipeline in connection with Jal Jeevan Mission (JJM) at Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000801/2024-2025 | 344/MD | 30/01/2025 | 426 | GOBINDA ENTERPRISE | 107.02 | 0 | 0
1889 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 2 at Wari PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000899/2023-2024 | 166/MD | 08/01/2024 | 45 | M/S SAI RAM ENTERPRISE | 4.19 | 0 | 98
1890 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Wari PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000900/2023-2024 | 273/MD | 11/01/2024 | 45 | LOKNATH ENTERPRISE | 4.19 | 4.16 | 97
1891 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for WARI Piped Water Supply Scheme at Harischandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000921/2023-2024 | 382/MD | 17/01/2024 | 271 | MAHA MAYA CONSTRUCTION | 15.4 | 7.5 | 72
1892 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000028/2022-2023 | 2753/MD | 22/11/2022 | 0 | Resource Division | 42.01 | 0 | 0
1893 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000044/2025-2026 | 2868/MD | 16/06/2025 | 0 | Resource Division | 11.04 | 0 | 0
1894 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000131/2023-2024 | 108/MD | 05/01/2024 | 0 | Resource Division | 13 | 0 | 0
1895 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of WARI PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/02543/2023-2024 | BP-2023-24-437 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.44 | 0 | 0
1896 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of WARI PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/02544/2023-2024 | BP-2023-24-438 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.56 | 0 | 0
1897 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Wari Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011955) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000330/2023-2024 | 2332/MLMD | 26/07/2023 | 796 | AHALYA ENGINEERING WORKS | 38.61 | 32.21 | 90
1898 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Wari, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000468/2023-2024 | 3004368704 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.22 | 3.22 | 100
1899 | Malda Mechanical | Malda Mechanical Division | Formal work order for the work of "Improvement of existing 2 x 250 KVA Substation (11/0.433 KV) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, PHE Dte." | Assistant Engineer - II | Junior Engineer-04 | ORD/000900/2022-2023 | 2736/MLMD | 05/12/2022 | 789 | M/S P.P. ELECTRICALS | 115.25 | 106.76 | 100
1900 | Malda Mechanical | Malda Mechanical Division | Additional work of Improvement of Existing 2 x 250 KVA Substation (11/0.433KV) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/001594/2023-2024 | 3216/MLMD | 05/10/2023 | 14 | M/S P.P. ELECTRICALS | 4.47 | 4.39 | 100
1901 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Mosimpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000021/2023-2024 | 857/MAAD | 03/05/2023 | 699 | USHA ENTERPRISE | 168.7 | 26.8 | 85
1902 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Mosimpur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. .(3rd Call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000217/2023-2024 | 1705/MAAD | 20/09/2023 | 650 | A. K. CONSTRUCTION | 211.7 | 61.54 | 80
1903 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Route survey & design for praparation of DPR of Mosimpur, Khaschandpur & Gayeshbari Pipe Water Supply Scheme at Kaliachak-I Development Block under Malda Arsenic Area W/S Division, Phe Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000231/2022-2023 | 1666/MAAD | 08/09/2022 | 10 | FUTURE | 0.99 | 0.99 | 1
1904 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Mosimpur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000252/2024-2025 | 13/MAAD | 03/01/2025 | 271 | A. K. CONSTRUCTION | 66.36 | 0 | 90
1905 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Continuation work order for Route survey & design for praparation of DPR of Mosimpur, Khaschandpur & Gayeshbari Pipe Water Supply Scheme at Kaliachak-I Development Block under Malda Arsenic Area W/S Division, Phe Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000288/2022-2023 | 1670/MAAD | 12/09/2022 | 10 | FUTURE | 0.99 | 0.99 | 1
1906 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Mosimpur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000364/2022-2023 | 155/MAAD | 02/02/2023 | 45 | A ONE ENTERPRISE | 14.72 | 10.38 | 100
1907 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Mosimpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000365/2022-2023 | 108/MAAD | 30/01/2023 | 60 | MD WARESH ALI | 5.02 | 4.7 | 100
1908 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Mosimpur Chama Para, Beltala, Biswas Para, Darga Para, Khursed Para, Wayesh Mistry Para, Balupur, Baliharpur Rilif Pukur Para for Mosimpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000375/2022-2023 | 222/MAAD | 03/02/2023 | 788 | SAHA CONSTRUCTION | 33.71 | 29.42 | 95
1909 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Mosimpur Madrasha Para, Jolakandi Para, Jolakandi Mokdompur Para, Post Office Para, School Para, Baliharpur East, Baliharpur West for Mosimpur Piped Water supply scheme at Kaliachak-I under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000377/2023-2024 | 222/MAAD | 27/02/2024 | 90 | MANIK CHOUDHURY | 3.73 | 3.7 | 90
1910 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System at Mosimpur Madrasha Para, Jolakandi Para, Jolakandi Mokdompur Para, Post Office Para, School Para, Baliharpur East, Baliharpur West for Mosimpur Piped Water supply scheme at Kaliachak-I under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd call) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000450/2022-2023 | 399/MAAD | 06/03/2023 | 514 | MANIK CHOUDHURY | 70.26 | 56.48 | 80
1911 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | RTOR000001/2023-2024 | 623/MAAD | 05/04/2023 | 0 | Resource Division | 21.69 | 0 | 0
1912 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Masimpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/015617) | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000679/2023-2024 | 2698/MLMD | 11/08/2023 | 1112 | DEY ENTERPRISE [HOWRAH] | 71.33 | 0 | 1
1913 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Masimpur, Sujapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000769/2023-2024 | 3004395276 | 16/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.97 | 5.97 | 100
1914 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Masimpur, Sujapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-II | ORD/000770/2023-2024 | 3004390333 | 10/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.17 | 3.17 | 100
1915 | Malda Division | RWS Malda Sub-Division | Placement of fund against the work for road restoration for laying pipe line for Bulbulchandi- Katlapukur road from 0552 KM to 9.943 Km under Talpukur and Krishnapur PWSS under Malda Division,PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/00513/2024-2025 | BP-2024-25-260 | 13/09/2024 | 0 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 30.66 | 0 | 0
1916 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Implementation of KRISHNAPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000010/2023-2024 | 1573/MD | 10/04/2023 | 932 | M/S MAA TARA CONSTRUCTION | 570.36 | 387.45 | 80
1917 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of KRISHNAPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000107/2023-2024 | 2334/MD | 08/06/2023 | 60 | GOBINDA ENTERPRISE | 90.08 | 85.4 | 85
1918 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tube well Site of Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000164/2024-2025 | 2939/MD | 10/06/2024 | 30 | PRITAM ENTERPRISE | 7.16 | 0 | 0
1919 | Malda Division | RWS Malda Sub-Division | Dismantling & Restoration of Cement Concrete Road with earth filling for protection of pipe line with in the commend area for Krishnapur Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000588/2024-2025 | 5622/MD | 06/11/2024 | 30 | GOBINDA ENTERPRISE | 2.46 | 0 | 100
1920 | Malda Division | RWS Malda Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70 m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Krishnapur Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000630/2024-2025 | 5837/MD | 22/11/2024 | 266 | VISCOUS ENGINEERS PVT. LTD. | 30.14 | 0 | 0
1921 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000631/2024-2025 | 5838/MD | 22/11/2024 | 175 | M/S MAA TARA CONSTRUCTION | 60.55 | 0 | 0
1922 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tube well site of Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000781/2024-2025 | 347/MD | 30/01/2025 | 90 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.18 | 0 | 0
1923 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work site of Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000887/2023-2024 | 161/MD | 08/01/2024 | 45 | GOBINDA ENTERPRISE | 18.55 | 4.84 | 100
1924 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000030/2025-2026 | 2829/MD | 11/06/2025 | 0 | Resource Division | 15.77 | 0 | 0
1925 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000041/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 13.07 | 0 | 0
1926 | Malda Mechanical | RWS Malda Sub-Division | PAYMENT FOR SHIFTING OF 11 KV OVER HEAD LINE AT THE SITE OF KRISHNAPUR PHE UNDER RATHBARI CCC UNDER MALDA DISTRICT | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/03574/2023-2024 | BP-2023-24-593 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 3.79 | 0 | 0
1927 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Krishnapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013458) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000498/2023-2024 | 2568/MLMD | 04/08/2023 | 710 | DAS ENTERPRISE. | 28.26 | 0 | 70
1928 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of KRISHNAPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/001964/2023-2024 | 3004508461 | 07/12/2023 | 90 | W.B.S.E.D.C.LTD | 3.89 | 3.89 | 100
1929 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of KRISHNAPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/001965/2023-2024 | 3004508446 | 05/12/2023 | 90 | W.B.S.E.D.C.LTD | 7.95 | 7.95 | 100
1930 | Malda Division | Malda Mechanical Division | Service Connection charge at P/H No. II of Bhadar Water Supply Scheme under Gazole C.C.C. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/00748/2023-2024 | BP-2023-24-404 | 26/12/2023 | 0 | WBSEDCL | 11.36 | 0 | 0
1931 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of BHADAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000049/2023-2024 | 1996/MD | 17/05/2023 | 715 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 336.77 | 321.92 | 85
1932 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of BHADAR Piped Water Supply Scheme at Gaole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000105/2023-2024 | 2332/MD | 08/06/2023 | 571 | M/S KUNDU CONSTRUCTION | 87.98 | 80.55 | 90
1933 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well Site of BHADAR Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000198/2024-2025 | 2930/MD | 10/06/2024 | 45 | NANDAN ENTERPRISE | 6.73 | 0 | 70
1934 | Malda Division | Malda Mechanical Division | Laying of Distribution Sysytem and Providing Functional Household Tap Connection (FHTC) of BHADAR Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000200/2024-2025 | 2928/MD | 10/06/2024 | 386 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 55.17 | 27.8 | 50
1935 | Malda Division | Malda Mechanical Division | Placing of diesel driven Car on hire basis for official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/07/2023 to 30/09/2023). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000596/2023-2024 | 487/MD | 21/06/2023 | 92 | SUBHANKAR SINGH | 0.31 | 0.31 | 100
1936 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Bhadar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000885/2023-2024 | 269/MD | 11/01/2024 | 182 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 22.49 | 17.39 | 80
1937 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000040/2023-2024 | 1810/MD | 27/04/2023 | 0 | Resource Division | 20.43 | 0 | 0
1938 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000060/2025-2026 | 5596/MD | 30/10/2025 | 0 | Resource Division | 0.84 | 0 | 0
1939 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000098/2023-2024 | 26/MD | 04/01/2024 | 0 | Resource Division | 12.71 | 0 | 0
1940 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Bhadar PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000771/2023-2024 | 3004390642 | 16/08/2023 | 90 | W.B.S.E.D.C.LTD | 16.23 | 16.23 | 100
1941 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bhadar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014278) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/001662/2023-2024 | 3340/MLMD | 30/10/2023 | 180 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 25.45 | 23.75 | 93
1942 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Sri Chandrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (3rd Call). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000011/2025-2026 | 2419/MD | 27/05/2025 | 45 | SAHA CONSTRUCTION | 27.27 | 0 | 5
1943 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of SRI CHANDRAPUR Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000031/2023-2024 | 1851/MD | 02/05/2023 | 820 | M/S ALISA CONSTRUCTIION | 389.77 | 140.31 | 65
1944 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Sri Chandrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000311/2024-2025 | 3951/MD | 07/08/2024 | 45 | M/S ALISA CONSTRUCTIION | 8.68 | 0 | 0
1945 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sri Chandrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000646/2024-2025 | 5923/MD | 26/11/2024 | 45 | M/S ALISA CONSTRUCTIION | 65.18 | 0 | 0
1946 | Malda Division | Malda Mechanical Division | Road Restoration and Laying of parallel/ dedicated pipe line for better functionality of Srichandrapur Water Supply Scheme under Harishchandrapur -I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000694/2025-2026 | 5921/MD | 26/11/2025 | 60 | KAUSHIK MAJUMDAR | 10.02 | 0 | 0
1947 | Malda Division | Malda Mechanical Division | Laying of Distribution of UPVC Pipeline of SRI CHANDRAPUR Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000705/2023-2024 | 4634/MD | 23/11/2023 | 686 | M/S TRILOCHAN CONSTRUCTION CO | 80.4 | 56.6 | 100
1948 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000036/2023-2024 | 1799/MD | 27/04/2023 | 0 | Resource Division | 42.87 | 0 | 0
1949 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000074/2025-2026 | 5536/MD | 29/10/2025 | 0 | Resource Division | 4.82 | 0 | 0
1950 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000122/2023-2024 | 92/MD | 05/01/2024 | 0 | Resource Division | 12.32 | 0 | 0
1951 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SRI CHANDRAPUR PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/02541/2023-2024 | BP-2023-24-444 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.78 | 0 | 0
1952 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SRI CHANDRAPUR PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/02542/2023-2024 | BP-2023-24-445 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 10.15 | 0 | 0
1953 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Sri Chandrapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014411) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000386/2023-2024 | 2394/MLMD | 28/07/2023 | 180 | KAMAKHYA ENTERPRISE. | 26.58 | 22.68 | 85
1954 | Malda Division | Malda Mechanical Division | Providing Balance Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000175/2025-2026 | 2891/MD | 17/06/2025 | 60 | M/S AMIT KUMAR GUPTA | 23.59 | 0 | 0
1955 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000263/2024-2025 | 3211/MD | 27/06/2024 | 551 | M/S DAS CONSTRUCTION | 33.31 | 0 | 20
1956 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000268/2024-2025 | 3226/MD | 28/06/2024 | 552 | M/S DAS CONSTRUCTION | 36.14 | 0 | 40
1957 | Malda Division | Malda Mechanical Division | Road cutting and road restoration at Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000690/2024-2025 | 6207/MD | 09/12/2024 | 388 | M/S DAS CONSTRUCTION | 5.06 | 0 | 0
1958 | Malda Division | Malda Mechanical Division | Formal work order for Implementation of Uttar Mahinagar Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000740/2022-2023 | 1252/MD | 22/03/2023 | 1249 | M/S DAS CONSTRUCTION | 239.41 | 132.61 | 70
1959 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000045/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 21.65 | 0 | 0
1960 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000164/2023-2024 | 241/MD | 10/01/2024 | 0 | Resource Division | 4.53 | 0 | 0
1961 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Uttar Mahinagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000315/2024-2025 | 2943/MLMD | 11/09/2024 | 412 | M/S SAJAHAN CHOWDHURY | 25.3 | 0 | 80
1962 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Uttar Mahinagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/001891/2023-2024 | 3004467221 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 4.05 | 4.05 | 100
1963 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Uttar Mahinagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/001892/2023-2024 | 3004467207 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 4 | 4 | 100
1964 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tubewell site of Oltara Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000161/2024-2025 | 2936/MD | 10/06/2024 | 210 | DUTTA ENTERPRISE | 7.55 | 0 | 0
1965 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 3rd Tubewell site of Oltara Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000162/2024-2025 | 2937/MD | 10/06/2024 | 210 | DUTTA ENTERPRISE | 7.55 | 0 | 0
1966 | Malda Division | RWS Malda Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 90m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Oltara Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000204/2024-2025 | 2991/MD | 11/06/2024 | 180 | M/S JHA CONSTRUCTION | 32.88 | 0 | 0
1967 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head work Site of Oltara Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000205/2024-2025 | 2992/MD | 11/06/2024 | 210 | DUTTA ENTERPRISE | 22.22 | 0 | 0
1968 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Oltara Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000714/2024-2025 | 6405/MD | 19/12/2024 | 45 | M/S JHA CONSTRUCTION | 65.17 | 0 | 0
1969 | Malda Division | RWS Malda Sub-Division | Formal work order for Implementation of OLTARA Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000742/2022-2023 | 1253/MD | 22/03/2023 | 943 | DUTTA ENTERPRISE | 919.78 | 663.66 | 85
1970 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000036/2025-2026 | 2822/MD | 11/06/2025 | 0 | Resource Division | 21.78 | 0 | 0
1971 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000075/2025-2026 | 5537/MD | 29/10/2025 | 0 | Resource Division | 21.78 | 0 | 0
1972 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000082/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 50.37 | 0 | 0
1973 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of OLTARA, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/02504/2023-2024 | BP-2023-24-419A | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 0.01 | 0 | 0
1974 | Malda Mechanical | RWS Malda Sub-Division | QUOTATION PAYMENT FOR OLTARA PH3 UNDER AIHO CCC UNDER MALDA DISTRICT | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/03564/2023-2024 | BP-2023-24-586 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 12.19 | 0 | 0
1975 | Malda Mechanical | RWS Malda Sub-Division | QUOTATION PAYMENT FOR OLTARA PH 2 UNDER AIHO CCC UNDER DISTRICT OF MALDA | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/03565/2023-2024 | BP-2023-24-585 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 12.93 | 0 | 0
1976 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Oltara Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013242) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000388/2023-2024 | 2396/MLMD | 28/07/2023 | 1063 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 43.33 | 24.67 | 60
1977 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of OLTARA, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/001966/2023-2024 | 3004508478 | 05/12/2023 | 90 | W.B.S.E.D.C.LTD | 9.14 | 9.14 | 100
1978 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 25 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Bhabuk Water Supply Scheme of Habibpur Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000142/2025-2026 | 2620/MD | 02/06/2025 | 135 | M/S AMIT KUMAR GUPTA | 15.55 | 0 | 0
1979 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (135 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at BHABUK Piped Water Supply Scheme (Tube Well No-3) of Habibpur Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000379/2022-2023 | 2705/MD | 17/11/2022 | 30 | A. L. ENGINEERING SOLUTION | 9.14 | 6.4 | 100
1980 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for BHABUK Piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000410/2022-2023 | 2984/MD | 07/12/2022 | 45 | SOVON KUMAR DAS | 43.65 | 40.92 | 1
1981 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Bhabuk Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000487/2024-2025 | 5000/MD | 27/09/2024 | 385 | M/S KUNDU CONSTRUCTION | 18.34 | 0 | 0
1982 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/11/2022 to 30/04/2023). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000518/2022-2023 | 2474/MD | 21/10/2022 | 365 | SHABNAM ARA | 4.5 | 0.4 | 21
1983 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Bhabuk Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000727/2022-2023 | 1201/MD | 21/03/2023 | 45 | M.S. ENTERPRISE | 4.17 | 4.12 | 100
1984 | Malda Division | Malda Mechanical Division | Augmentation of work to ensure proper functioning of 250 M³ Capacity 20 Mtr. Staging height RCC Over Head Reservoir of Bhabuk Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000835/2024-2025 | 1061/MD | 19/03/2025 | 60 | SADHANA CONSTRUCTION | 9.21 | 0 | 0
1985 | Malda Division | Malda Mechanical Division | Emergent Laying of different diameter UPVC Pipeline and others allied work for Gap negotiatiomn for BHABUK its adjoining mouzas Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000966/2023-2024 | 805/MD | 21/02/2024 | 663 | GOBINDA ENTERPRISE | 12.33 | 0 | 0
1986 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SOURCE AUGMENTATION of BHABUK Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001017/2023-2024 | 1519/MD | 16/03/2024 | 718 | M/S JHA CONSTRUCTION | 20.45 | 0 | 0
1987 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Bhabuk, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | BILL/02484/2023-2024 | BP-2023-24-420 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.71 | 0 | 0
1988 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Bhabuk Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014864) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000309/2023-2024 | 2311/MLMD | 26/07/2023 | 585 | SUBRATA KUMAR DAS. | 10.52 | 8.71 | 70
1989 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Uttar Bhakuria Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000273/2024-2025 | 3202/MD | 27/06/2024 | 30 | M/S SABANA CONSTRUCTION | 10.34 | 0 | 100
1990 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Implementation of UTTAR BHAKURIA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000488/2022-2023 | 196/MD | 19/01/2023 | 591 | M/S SABANA CONSTRUCTION | 39.58 | 28.08 | 90
1991 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000018/2023-2024 | 1615/MD | 11/04/2023 | 0 | Resource Division | 1.32 | 0 | 0
1992 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of UTTAR BHAKURIA PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/02545/2023-2024 | BP-2023-24-446 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.22 | 0 | 0
1993 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Uttar Bhakuria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013230) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000389/2023-2024 | 2397/MLMD | 28/07/2023 | 180 | JIBU SINGHA | 12.27 | 9.97 | 81
1994 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Sadlichalk Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000196/2024-2025 | 2900/MD | 07/06/2024 | 30 | SAYEM ENTERPRISE | 2.12 | 0 | 0
1995 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional UPVC Pipe line in connection with Source Augmentation of Sadlichak Piped Water Supply Scheme at Harishchandrapur II Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000574/2022-2023 | 765/MD | 17/02/2023 | 30 | RABIUL ISLAM | 6.89 | 6.87 | 0
1996 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 246 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of SADLICHAK Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000720/2022-2023 | 1178/MD | 20/03/2023 | 686 | JAYA ENTERPRISE | 12.03 | 0 | 95
1997 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Sadlichak Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000754/2022-2023 | 1302/MD | 23/03/2023 | 45 | SOFIKUL ISLAM | 4.19 | 0 | 0
1998 | Malda Division | Malda Mechanical Division | Augmentation work of OHR, Pump House and Boundary Wall of Sadlichak Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000807/2024-2025 | 999/MD | 12/03/2025 | 75 | SUBHAS CHANDRA KESHARI | 28.01 | 0 | 0
1999 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Sadlichak Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016501) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000581/2023-2024 | 2630/MLMD | 10/08/2023 | 1201 | FUTURE | 11.43 | 9.22 | 80
2000 | Malda Division | Malda Sadar Sub-Division | Augmentation work of Boundary wall, Pump House, Blower Room,Over Head Reservoir and Construction Pathway & Approach Road at Head Work Site of ANANDIPUR Water Supply Scheme of Englishbazar Block under Malda Division, P.H.E.Dte. in the District of Malda | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000111/2025-2026 | 2414/MD | 27/05/2025 | 75 | M/S GHOSH CONSTRUCTION | 20.21 | 0 | 0
2001 | Malda Division | Malda Sadar Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000166/2020-2021 | 2719/MD | 10/11/2020 | 30 | MANAS KUMAR SAHA | 50.07 | 8.75 | 1
2002 | Malda Division | Malda Sadar Sub-Division | Augmentation of Pump House at 2nd Tube Well Site of Anandipur Water Supply Scheme of Englishbazar Block under Malda Division, P.H.E.Dte. in the District of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000711/2024-2025 | 6381/MD | 18/12/2024 | 45 | RUQAIYA ENTERPRISE | 1.94 | 0 | 100
2003 | Malda Division | Malda Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Anandipur Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000825/2024-2025 | 702/MD | 21/02/2025 | 320 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28.05 | 0 | 0
2004 | Malda Division | Malda Sadar Sub-Division | Material Requisition To Resource Division | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | RTOR000023/2025-2026 | 2813/MD | 11/06/2025 | 0 | Resource Division | 6.93 | 0 | 0
2005 | Malda Division | Malda Sadar Sub-Division | Material Requisition To Resource Division | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | RTOR000076/2025-2026 | 5538/MD | 29/10/2025 | 0 | Resource Division | 6.93 | 0 | 0
2006 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Rampur Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000179/2025-2026 | 2894/MD | 17/06/2025 | 60 | S. N. CONSTRUCTION | 29.67 | 0 | 0
2007 | Malda Division | Chanchal Sub-Division | Replacement of existing tube well by 200x200 mm dia. and 250 M Deep by Big Dia Tube Well at 2nd Tube Well site of Rampur Piped Water Supply Scheme at Chanchal-II block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000463/2024-2025 | 4820/MD | 13/09/2024 | 92 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 13.75 | 3.43 | 100
2008 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional UPVC Pipe line in connection with Source Augmentation of Rampur Piped Water Supply Scheme, Chanchal II Block under Malda Division, P.H.E. Dte. in the District of Malda | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000573/2022-2023 | 764/MD | 17/02/2023 | 30 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 18.18 | 18.15 | 100
2009 | Malda Division | Chanchal Sub-Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Rampur Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000585/2024-2025 | 5619/MD | 06/11/2024 | 30 | M/S JHA CONSTRUCTION | 2.88 | 0 | 0
2010 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Rampur Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000753/2022-2023 | 1301/MD | 23/03/2023 | 45 | SUBINDU PRAMANIK | 4.19 | 0 | 0
2011 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well ( 250.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at Rampur Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000769/2022-2023 | 1397/MD | 28/03/2023 | 30 | A. L. ENGINEERING SOLUTION | 13.37 | 12.62 | 100
2012 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Rampur Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte. (TSM/016552) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000577/2023-2024 | 2626/MLMD | 10/08/2023 | 836 | JIBON GHOSH. | 11.42 | 10.03 | 88
2013 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bihari Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000089/2025-2026 | 2422/MD | 27/05/2025 | 60 | PRADIP KUMAR BANIK | 15.71 | 0 | 0
2014 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Bihari Zone-II Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000090/2025-2026 | 2332/MD | 22/05/2025 | 60 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 29.11 | 0 | 0
2015 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of Distribution pipe line for Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Rampur village of Bihari Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000558/2022-2023 | 749/MD | 17/02/2023 | 30 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 5.67 | 5.35 | 100
2016 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Bihari Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000721/2022-2023 | 1195/MD | 21/03/2023 | 45 | M/S MAJAF CONSTRUCTION | 4.17 | 0 | 0
2017 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 138 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of BIHARI Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000776/2022-2023 | 1434/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.68 | 0 | 0
2018 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Behari Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016679) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000566/2023-2024 | 2618/MLMD | 10/08/2023 | 180 | NEOGI ENTERPRISE. | 10.92 | 6.13 | 56
2019 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at head work site of Jotgopal Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000201/2024-2025 | 2988/MD | 11/06/2024 | 30 | SHREE BISHNU CONSTRUCTION | 24.3 | 0 | 0
2020 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Augmentation of JOTGOPAL Piped Water Supply Scheme at Englishbazar Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000235/2023-2024 | 2710/MD | 14/07/2023 | 270 | SHREE BISHNU CONSTRUCTION | 192.85 | 59.15 | 32
2021 | Malda Division | RWS Malda Sub-Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 95m Deep at Jotegopal PWSS under Englishbazar Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000255/2024-2025 | 3199/MD | 27/06/2024 | 45 | ABHIJIT PAUL | 8.36 | 2.16 | 100
2022 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of JOTGOPAL Water Supply Scheme at Englishbazar Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000484/2022-2023 | 1132/MD | 20/03/2023 | 45 | S. R. ENTERPRISE | 4.14 | 4.12 | 100
2023 | Malda Division | RWS Malda Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 01/01/2025 to 30/06/2025). | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000874/2024-2025 | 6637/MD | 31/12/2024 | 181 | RUQAIYA ENTERPRISE | 0.86 | 1.57 | 0
2024 | Malda Division | RWS Malda Sub-Division | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000948/2024-2025 | 637/MD | 19/02/2025 | 7 | M/S SAI RAM ENTERPRISE | 0.63 | 0 | 100
2025 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000030/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 9.73 | 0 | 0
2026 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000053/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 10.86 | 0 | 0
2027 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000187/2023-2024 | 822/MD | 21/02/2024 | 0 | Resource Division | 7.67 | 0 | 0
2028 | Malda Mechanical | RWS Malda Sub-Division | Quotation Payment against Jote Gopal JL NO-49 Under Fulbari ccc Under Malda District | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | BILL/03627/2023-2024 | BP-2023-24-626 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.54 | 0 | 0
2029 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Augmentation of Jotgopal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008179) | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000244/2023-2024 | 2261/MLMD | 18/07/2023 | 831 | SUBRATA KUMAR DAS. | 13.48 | 9.49 | 100
2030 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. II of Augmentation of Jotgopal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008179) | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000249/2023-2024 | 2220/MLMD | 18/07/2023 | 90 | TAPAN BISWAS. | 12.3 | 11.08 | 40
2031 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary wall including RBT fencing at arround Talimnagar Zone-I Pump house No.1 under Malda Arsenic Area Water supply Divisin PHED. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000044/2023-2024 | 943/MAAD | 23/05/2023 | 45 | MI CONSTRUCTION | 8.91 | 7.29 | 100
2032 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 25.00 M³/ Hr. capacity Iron Elimination Plant (Pressure type) for Talimnagar Water Supply Scheme at Manikchak Dev. Block under Malda Arsenic Area Water Supply Division, PHE Dte. in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000451/2022-2023 | 400/MAAD | 06/03/2023 | 180 | MANASH KUMAR SAHA | 16.01 | 13.02 | 81
2033 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System including Supply of all type of specials & valves at Saidpur Bazar Para under Purba Saidpur Piped Water Supply Scheme, Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000027/2023-2024 | 864/MAAD | 04/05/2023 | 60 | CHARU CONSTRUCTION | 13.56 | 12.4 | 100
2034 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System including Supply of all type of specials & valves at Saidpur Muslim Para under Purba Saidpur Piped Water Supply Scheme, Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000028/2023-2024 | 865/MAAD | 04/05/2023 | 60 | ABHIJIT ENTERPRISE | 9.75 | 8.71 | 100
2035 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at 1st Tube well Site Purbba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000029/2023-2024 | 866/MAAD | 04/05/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 7.47 | 4.58 | 100
2036 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System including Supply of all type of specials & valves at Maszid Para under Purba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. In the District of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000032/2023-2024 | 882/MAAD | 11/05/2023 | 298 | SUDIP DEY | 53.75 | 49.39 | 10
2037 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System including Supply of all type of specials & valves at Sahebnagar High School Para under Purba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000034/2023-2024 | 883/MAAD | 11/05/2023 | 690 | MD WARESH ALI | 19.28 | 10.51 | 55
2038 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System including Supply of all type of specials & valves from Node point at Bhakta Ballavpur (71) mouza under Purbba Saidpur Piped Water Supply Scheme, Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd Call) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000045/2023-2024 | 944/MAAD | 23/05/2023 | 60 | ANJIMA CONSTRUCTION CO. | 25.48 | 24.58 | 50
2039 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site at Purbba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000139/2023-2024 | 1480/MAAD | 01/08/2023 | 60 | MAHA MAYA CONSTRUCTION | 5.09 | 0 | 80
2040 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site at Purba Saidpur Piped Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000259/2024-2025 | 57/MAAD | 13/01/2025 | 200 | FUTURE | 26.42 | 0 | 60
2041 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Purba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000267/2023-2024 | 3017/MAAD | 06/12/2023 | 665 | ZEOLITE FRESH INDIA | 150.68 | 24.86 | 5
2042 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | RTOR000012/2023-2024 | 634/MAAD | 05/04/2023 | 0 | Resource Division | 24.86 | 0 | 0
2043 | Malda Mechanical | Malda Arsenic Area W/S Division | Quotation Payment For Purbasaidpur T/W NO 1 Under The District Of Malda Under Mathurapur CCC | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | BILL/00018/2024-2025 | BP-2024-25-43 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 5.08 | 0 | 0
2044 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 102 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Purbha Saidpur Piped Water supply scheme (2nd Tube Well Site) at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda. (2nd call) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000253/2023-2024 | 1916/MAAD | 16/10/2023 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.2 | 5.78 | 100
2045 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 400 M3 Capacity, 20mtr. staging height RCC Elevated Service Reservoir as per Departmental type design including delivery, inlet & overflow pipe connection etc. all complete for piped water supply scheme at Purba Saidpur Piped Water Supply Scheme & its adjoining mouzas of Manikchak Block in the District of Malda, under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000258/2023-2024 | 2002/MAAD | 06/11/2023 | 660 | M/S KUNDU CONSTRUCTION | 187.22 | 43.31 | 20
2046 | Malda Mechanical | Malda Arsenic Area W/S Division | Quotation Payment For Purbasaidpur T/W NO II For district of Malda Under Mathurapur CCC | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | BILL/03761/2023-2024 | BP-2023-24-731 | 28/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.54 | 0 | 0
2047 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Purba Saidpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018015) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-I | ORD/000652/2023-2024 | 2684/MLMD | 11/08/2023 | 843 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 65.01 | 31.01 | 98
2048 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of Tubewell, Laying of Distribution System and Providing Functional Household Tap connection (FHTC) of Mahishbathani Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000052/2023-2024 | 2005/MD | 17/05/2023 | 565 | M/S DAS CONSTRUCTION | 92.6 | 73.6 | 50
2049 | Malda Division | Malda Mechanical Division | Road restoration in connection with dismantling of road and renovation the same with balanced allied work to provide FHTC at Maheshbathani Piped Water Supply Scheme under Old Malda Dev Block under Malda Division, P.H.E Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000119/2025-2026 | 2471/MD | 28/05/2025 | 45 | M/S DAS CONSTRUCTION | 11.92 | 0 | 100
2050 | Malda Division | Malda Mechanical Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/07/2023 to 31/12/2023). | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000314/2023-2024 | 503/MSD | 30/06/2023 | 180 | ARUN KUMAR DAS | 0.86 | 1.93 | 100
2051 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Head Work Site of Mahishbathani Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000952/2023-2024 | 653/MD | 08/02/2024 | 45 | M/S DAS CONSTRUCTION | 4.15 | 0 | 100
2052 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000077/2025-2026 | 5542/MD | 29/10/2025 | 0 | Resource Division | 9.78 | 0 | 0
2053 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000079/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 10.94 | 0 | 0
2054 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III & IV and making compound lighting arrangement at head worksite of Augmentation of Mahishbathani Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017802) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000732/2023-2024 | 2692/MLMD | 11/08/2023 | 180 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 27.01 | 20.87 | 81
2055 | Malda Division | Chanchal Sub-Division | Harvesting and Disposal of 40(Forty) numbers of trees at Ratua-I under Executive Engineer, Malda Division, PHE Dte, Govt. of West Bengal, Phase-V (Deport- Bhaluka Road Range Lead-20km) | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | BILL/00197/2025-2026 | 539/WBFDC | 10/07/2025 | 0 | DIVISIONAL FOREST OFFICER, MALDA DIVISION | 1.65 | 0 | 0
2056 | Malda Division | Chanchal Sub-Division | Surveying, Planning, Design, Engineering, Supplying, Construction, Erection, Testing and Commissioning of Raw water Intake and Raw Water Pumping Main, WTP , Primary and Secondary Clear Water Transmission main, Boosting stations and other allied works including all Civil , Electro-Mechanical and IOT based Supervisory monitoring system for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District followed by 3(Three) months Trial Run and Subsequent Operation & Maintenance for 5(five) years | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | BILL/00442/2024-2025 | BP-2024-25-223 | 28/08/2024 | 0 | EXECUTIVE ENGINEER | 1.35 | 0 | 0
2057 | Malda Division | Chanchal Sub-Division | Harvesting and disposal of 36 number of trees at Ratua-I for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | BILL/00527/2024-2025 | BP-2024-25-253 | 11/09/2024 | 0 | EXECUTIVE ENGINEER | 1.29 | 0 | 0
2058 | Malda Division | Chanchal Sub-Division | Harvesting and disposal of 36 number of trees at Ratua-I for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | BILL/00745/2024-2025 | BP-2024-25-386 | 19/11/2024 | 0 | EXECUTIVE ENGINEER | 1.29 | 0 | 0
2059 | Malda Division | Chanchal Sub-Division | Road damaged. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | BILL/00806/2024-2025 | BP-2024-25-375 | 18/11/2024 | 0 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 2 | 0 | 0
2060 | Malda Division | Chanchal Sub-Division | Harvesting and Disposal of 30 numbers of Trees at ratua-I under Executive Engineer, Malda Division, PHE Dte., Govt. of West Bengal, Phase-IV; Deport: Bhaluka Road Range Lead-20km | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | BILL/00931/2024-2025 | BP-2024-25-413 | 28/01/2025 | 0 | DIVISIONAL FOREST OFFICER, MALDA DIVISION | 1.37 | 0 | 0
2061 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Surveying, Planning, Design, Engineering, Supplying, Construction, Erection, Testing and Commissioning of Raw water Intake and Raw Water Pumping Main, WTP , Primary and Secondary Clear Water Transmission main, Boosting stations and other allied works including all Civil , Electro-Mechanical and IOT based Supervisory monitoring system for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District followed by 3(Three) months Trial Run and Subsequent Operation & Maintenance for 5(five) years. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000375/2023-2024 | 3291/MD | 23/08/2023 | 1162 | GBC INFRASTRUCTURE PRIVATE LIMITED | 31945.95 | 1273.05 | 6
2062 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Construction of Overhead Reservoir on pile or raft foundation based on soil test report, laying of Distribution system, FHTC including pump house, boundary wall, internal road with RCC Culvert, internal pipe connection of Surface Water Based Piped Water Supply Scheme for Chanchal-II, Ratua-I & Ratua-II Block in the district of Malda Under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000380/2023-2024 | 3155/MD | 16/08/2023 | 1140 | REAN WATER TECH PRIVATE LIMITED. | 10818.5 | 1264.58 | 5
2063 | Malda Division | Chanchal Sub-Division | Construction of Flexible Bitumen Roads from Nakkatti Bridge to Y Junction of Irrigation Embankment by Bituminous work under Malda Division PHE Dte, in the District of Malda during the year 2024 - 2025. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000671/2024-2025 | 6161/MD | 05/12/2024 | 220 | M/S ANKUSH ENTERPRISE | 64.08 | 0 | 65
2064 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | RTOR000001/2024-2025 | 3836/MD | 30/07/2024 | 0 | Resource Division | 7172.16 | 0 | 0
2065 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | RTOR000024/2024-2025 | 5971/MD | 28/11/2024 | 0 | Resource Division | 345.26 | 0 | 0
2066 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | RTOR000032/2024-2025 | 1244/MD | 27/03/2025 | 0 | Resource Division | 1771.27 | 0 | 0
2067 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | RTOR000040/2022-2023 | 1811/MD | 27/04/2023 | 0 | Resource Division | 12067.76 | 0 | 0
2068 | Malda Mechanical | Chanchal Sub-Division | Shifting of LVOH(Low voltage over head) Line at jannagar WTP site under surface based PWSS of Ratua-I , II & Chanchal - II Block Dist- Malda,PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | BILL/01071/2024-2025 | BP-2024-25-295 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 3.41 | 0 | 0
2069 | Malda Mechanical | Chanchal Sub-Division | Formal Work Order for Providing Mechanical/Electrical equipment along with all related work at Boosting Pumping Station and Substation for Chanchal-II block under Surface water based PWSS of Ratua-I, Ratua-II & Chanchal-II block, Dist. Malda, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000799/2023-2024 | 2666/MLMD | 10/08/2023 | 1086 | DAS ENTERPRISE. | 603.82 | 0 | 4
2070 | Malda Mechanical | Chanchal Sub-Division | Formal Work Order for Providing Mechanical/Electrical equipment along with all related work at Boosting Pumping Station and Substation for RATUA-II block under Surface water based PWSS of Ratua-I, Ratua-II & Chanchal-II block, Dist. Malda, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000918/2023-2024 | 2668/MLMD | 10/08/2023 | 365 | ORIENTAL ENGINEERING CO. | 602.03 | 0 | 0
2071 | Malda Mechanical | Chanchal Sub-Division | Providing Mechanical/Electrical equipment along with all related work at Boosting Pumping Station and Substation for RATUA-I block under Surface water based PWSS of Ratua-I, Ratua-II & Chanchal-II block, Dist. Malda, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/001540/2023-2024 | 2670/MLMD | 10/08/2023 | 729 | WEST BENGAL ENGINEERING COMPANY. | 628.87 | 0 | 64
2072 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arbara Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000092/2025-2026 | 2334/MD | 22/05/2025 | 60 | S & G CONSTRUCTION | 28.65 | 0 | 0
2073 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Chandipur, JL. No. 40, G.P.-Bhagabanpur of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000105/2020-2021 | 2301/MD | 30/09/2020 | 31 | BIDYUT MAHALDAR | 4.45 | 7.63 | 0
2074 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Mahupaul, JL. No. 100, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000110/2020-2021 | 2306/MD | 30/09/2020 | 31 | RABIUL ISLAM | 2.82 | 3.43 | 0
2075 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village-Sadhail, JL. No. 116, G.P.- Muchia of NEMUA Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000116/2020-2021 | 2312/MD | 30/09/2020 | 31 | DEVI ENTERPRISE | 2.07 | 2.07 | 1
2076 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village-Dubol, JL. No. 93, G.P.- Daulatpur of DAULATPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000118/2020-2021 | 2314/MD | 30/09/2020 | 31 | PRITAM ENTERPRISE | 3.31 | 3.02 | 0
2077 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village-Basantapur, JL. No. 82, G.P.- Baidyapur of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000119/2020-2021 | 2315/MD | 30/09/2020 | 31 | M/S RADHA KRISHNA ENTERPRISE | 2.64 | 2.52 | 0
2078 | Malda Division | Chanchal Sub-Division | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe & FHTC for BASARA piped Water Supply Scheme at Bamongola Block in the District of Malda under Malda Division, P.H.E.Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000205/2025-2026 | 3693/MD | 29/07/2025 | 156 | MANIK CHOUDHURY | 60.11 | 0 | 0
2079 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection under MOBARAKPUR Piped Water Supply Scheme at Old Malda Block in the district of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000358/2020-2021 | 591/MD | 18/02/2021 | 60 | NIRENDRA NATH KUNDU | 125 | 30.6 | 0
2080 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dakhin Sahar Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000499/2024-2025 | 5403/MD | 21/10/2024 | 340 | GOBINDA ENTERPRISE | 65.18 | 0 | 0
2081 | Malda Division | Chanchal Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 50 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Malipakar Water Supply Scheme of Harishchandrapur-II Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000135/2025-2026 | 2510/MD | 29/05/2025 | 135 | BANIK BROTHERS | 20.04 | 0 | 0
2082 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Barijpur, JL. No. 43, G.P.-Pandua of PURBA BINODPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000138/2020-2021 | 2448/MD | 12/10/2020 | 30 | PARIJAT RAY | 41.39 | 56.13 | 0
2083 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Sankail, JL. No. 166, G.P.-Aktail of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000142/2020-2021 | 2452/MD | 12/10/2020 | 30 | M/S BABLU ENTERPRISE | 20.5 | 30.73 | 0
2084 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Daksin Sahar, JL. No. 133, G.P.-Chanchal of DAKSHIN SAHAR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000146/2020-2021 | 2456/MD | 12/10/2020 | 30 | M/S BANERJEE CONSTRUCTION | 19.18 | 13.41 | 0
2085 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Sanjib, JL. No. 136, G.P.-Chanchal of DAKSHIN SAHAR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000147/2020-2021 | 2457/MD | 12/10/2020 | 30 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.51 | 15.08 | 0
2086 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Birasthali, JL. No. 137, G.P.-Chanchal of DAKSHIN SAHAR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000148/2020-2021 | 2458/MD | 12/10/2020 | 30 | M/S. TEWARI CONSTRUCTION | 28.57 | 5.25 | 66
2087 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sankail Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000663/2024-2025 | 6163/MD | 05/12/2024 | 300 | M/S N. N. ENTERPRISE | 38.42 | 0 | 0
2088 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kankot Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000664/2024-2025 | 6164/MD | 05/12/2024 | 45 | MD WARESH ALI | 30.59 | 0 | 0
2089 | Malda Division | Chanchal Sub-Division | Laying of additional pipeline for retrofitting and Installation of Functional House Connection of Nemua Piped Water Supply Scheme at Old Malda Block under Malda Division PHE. Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000787/2024-2025 | 352/MD | 30/01/2025 | 180 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 89.7 | 0 | 34
2090 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Arbara, JL. No. 57, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000149/2020-2021 | 2459/MD | 12/10/2020 | 30 | TARUN KUMAR DEY | 31.69 | 23.11 | 0
2091 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bagunja, JL. No. 38, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000150/2020-2021 | 2460/MD | 12/10/2020 | 30 | M/S N. N. ENTERPRISE | 5.71 | 9.49 | 0
2092 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Haripur, JL. No. 20, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000151/2020-2021 | 2461/MD | 12/10/2020 | 30 | M/S STAR INDIA CONSTRUTION | 17.3 | 22.14 | 0
2093 | Malda Division | Chanchal Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Uttar Kumedpur Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000151/2025-2026 | 2689/MD | 04/06/2025 | 540 | VISCOUS ENGINEERS PVT. LTD. | 18.02 | 0 | 0
2094 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Khadiarpur, JL. No. 21, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000152/2020-2021 | 2462/MD | 12/10/2020 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.85 | 23.43 | 0
2095 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Khosalpur, JL. No. 56, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000153/2020-2021 | 2463/MD | 12/10/2020 | 30 | IDEAL CONSTRUCTION | 9.01 | 11.83 | 0
2096 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Daulatpur Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000855/2024-2025 | 1048/MD | 18/03/2025 | 75 | M/S SABANA CONSTRUCTION | 36.38 | 0 | 0
2097 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Arbara Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000858/2024-2025 | 1051/MD | 18/03/2025 | 75 | M/S ANKUSH ENTERPRISE | 32.37 | 0 | 0
2098 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000003/2025-2026 | 2579/MD | 30/05/2025 | 0 | Resource Division | 276.41 | 0 | 0
2099 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Kumedpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000187/2024-2025 | 2966/MD | 10/06/2024 | 236 | M/S DYNAMIC CONSTRUCTION | 7.44 | 0 | 100
2100 | Malda Division | Chanchal Sub-Division | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe & providing FHTC for PURBA BINODPUR piped Water Supply Scheme at Gazole Block in the District of Malda under Malda Division, P.H.E.Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000206/2025-2026 | 3722/MD | 30/07/2025 | 180 | ABHIJIT CONSTRUCTION | 17.47 | 0 | 0
2101 | Malda Division | Chanchal Sub-Division | Sinking of 200mm (all through) Big Dia Tube Well of 180m Deep at 3rd Tube Well Site and Construction of Pump House at 3rd Tube Well site Laying of dedicated/Parallel pipe line and Providing balanced FHTC under GANNADIA Piped Water Supply Scheme under at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000208/2025-2026 | 3723/MD | 30/07/2025 | 245 | HARUN ALL RASHID & BROTHERS | 39.34 | 0 | 0
2102 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Gangnadia, JL. No. 114, G.P.-Mahendrapur of GANNADIA Water Supply Scheme at Harischandrapur - II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000291/2020-2021 | 265/MD | 28/01/2021 | 30 | MANIK CHOUDHURY | 38.45 | 45.42 | 1
2103 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bansdol, JL. No. 94, G.P.- Daulatpur of DAULATPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000292/2020-2021 | 266/MD | 28/01/2021 | 30 | M/S. TEWARI CONSTRUCTION | 21.96 | 21.41 | 1
2104 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bampal Charkhi, JL. No. 51, G.P.- Chandmoni-I of KANKOT Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000293/2020-2021 | 267/MD | 28/01/2021 | 30 | MANIK CHOUDHURY | 35.11 | 16.94 | 0
2105 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000014/2024-2025 | 3993/MD | 08/08/2024 | 0 | Resource Division | 6.16 | 0 | 0
2106 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000101/2023-2024 | 31/MD | 04/01/2024 | 0 | Resource Division | 5.85 | 0 | 0
2107 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000104/2023-2024 | 34/MD | 04/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
2108 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000112/2023-2024 | 55/MD | 04/01/2024 | 0 | Resource Division | 0.62 | 0 | 0
2109 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Adampur, JL. No. 121, G.P.- Muchia of NEMUA Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000294/2020-2021 | 268/MD | 28/01/2021 | 30 | BEE GEE CONSTRUCTION | 29.13 | 53.15 | 1
2110 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Memua, JL. No. 122, G.P.- Muchia of NEMUA Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000295/2020-2021 | 269/MD | 28/01/2021 | 30 | GOBINDA ENTERPRISE | 23.19 | 45.81 | 1
2111 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Raykhandighi, JL. No. 23, G.P.-Bahirgachhi-I of BAHIRGACHHI Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000296/2020-2021 | 270/MD | 28/01/2021 | 1381 | M/S KUNDU CONSTRUCTION | 25.44 | 0 | 100
2112 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Gaushpur, JL. No. 90, G.P.- Daulatpur of MALIPAKAR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000297/2020-2021 | 271/MD | 28/01/2021 | 30 | GOBINDA ENTERPRISE | 14.36 | 25.01 | 1
2113 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Latasi, JL. No. 89, G.P.- Daulatpur of MALIPAKAR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000298/2020-2021 | 272/MD | 28/01/2021 | 30 | M/S SABANA CONSTRUCTION | 35.86 | 34.96 | 1
2114 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Basudebpur, JL. No. 150, G.P.- Sadlichak of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000299/2020-2021 | 273/MD | 28/01/2021 | 30 | MD WARESH ALI | 14.72 | 14.66 | 1
2115 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000137/2023-2024 | 112/MD | 05/01/2024 | 0 | Resource Division | 1.23 | 0 | 0
2116 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Surjyapura Tengurpura, JL. No. 151, G.P.- Sadlichak of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000300/2020-2021 | 274/MD | 28/01/2021 | 30 | A. K. CONSTRUCTION | 29.56 | 22.01 | 100
2117 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Sahabajpur, JL. No. 55, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000301/2020-2021 | 281/MD | 28/01/2021 | 30 | M/S. TEWARI CONSTRUCTION | 20.81 | 31.12 | 1
2118 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Naikanda, JL. No. 39, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000302/2020-2021 | 282/MD | 28/01/2021 | 30 | FAIZUL HAQUE BISWAS | 16.18 | 14.76 | 1
2119 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bibijhuti, JL. No. 58, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000303/2020-2021 | 283/MD | 28/01/2021 | 30 | ANUKUL CHANDRA DAS | 9.41 | 15.9 | 1
2120 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of ARBARA Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000303/2022-2023 | 2196/MD | 22/09/2022 | 30 | S & G CONSTRUCTION | 7.96 | 7.2 | 1
2121 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Rasulpur, JL. No. 71, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000304/2020-2021 | 284/MD | 28/01/2021 | 30 | A. K. SIKDAR | 8.24 | 7.88 | 1
2122 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Bhabanipur, JL. No. 73, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000305/2020-2021 | 285/MD | 28/01/2021 | 30 | M/S BANERJEE CONSTRUCTION | 13.56 | 0.58 | 1
2123 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Rampur, JL. No. 74, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000306/2020-2021 | 286/MD | 28/01/2021 | 30 | S. N. CONSTRUCTION | 16.86 | 15.79 | 1
2124 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Elam, JL. No. 75, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000307/2020-2021 | 287/MD | 28/01/2021 | 30 | ACHARYYA CONSTRUCTION | 12.36 | 0 | 1
2125 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Isadpur, JL. No. 77, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000308/2020-2021 | 288/MD | 28/01/2021 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.42 | 24.36 | 1
2126 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Kanua Bhabanipur, JL. No. 78, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000309/2020-2021 | 289/MD | 28/01/2021 | 30 | JOYDEB SENGUPTA | 6.64 | 0 | 0
2127 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Lakshmanpur, JL. No. 74, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000310/2020-2021 | 290/MD | 28/01/2021 | 30 | M/S SABANA CONSTRUCTION | 27.25 | 25.76 | 1
2128 | Malda Division | Chanchal Sub-Division | Continuation of work order for hiring of inspection vehicle (motor cab or Maruti omni category non air condition Bharat stage III purchase on or after 1.05.2008 with deiseal/LPG/CNG Engine ) in perfectly good condition of performing along journey and should cover anywhere without any trouble on monthly heir basis for official use of the office of the Assistant Engineer ,RWS Malda sub division ,PHE Dte.( Period from 06/07/2023 to 31/12/2023 ) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000310/2023-2024 | 199/RWS | 06/06/2023 | 178 | SHYAMAL KUMAR MAITRA | 0.85 | 1.65 | 55
2129 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Alampur, JL. No. 107, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000311/2020-2021 | 291/MD | 28/01/2021 | 30 | RANJIT ADHIKARY | 5.68 | 4.84 | 1
2130 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Barinda, JL. No. 95, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000312/2020-2021 | 292/MD | 28/01/2021 | 30 | GOALPAR CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 5.85 | 9.98 | 1
2131 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Harinandanbati, JL. No. 109, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000313/2020-2021 | 293/MD | 28/01/2021 | 30 | S. R. CONSTRUCTION | 15.52 | 13.97 | 1
2132 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bujurkhali, JL. No. 110, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000314/2020-2021 | 294/MD | 28/01/2021 | 1799 | GOBINDA ENTERPRISE | 14.53 | 0 | 0
2133 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Jalakar Bithan, JL. No. 115, G.P.- Muchia of MOBARAKPUR Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000315/2020-2021 | 295/MD | 28/01/2021 | 30 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 7.78 | 7.78 | 100
2134 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Teliapara, JL. No. 74, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000316/2020-2021 | 296/MD | 28/01/2021 | 30 | GOALPAR CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 5.53 | 0 | 0
2135 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Ashrafpur, JL. No. 132, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000317/2020-2021 | 297/MD | 28/01/2021 | 30 | M/S BANERJEE CONSTRUCTION | 13.91 | 0 | 0
2136 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Chhatia, JL. No. 133, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000318/2020-2021 | 298/MD | 28/01/2021 | 30 | M/S BANERJEE CONSTRUCTION | 17.51 | 0 | 0
2137 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Gopalnagar, JL. No. 80, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000319/2020-2021 | 299/MD | 28/01/2021 | 30 | S. N. CONSTRUCTION | 18.77 | 18.77 | 1
2138 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Jagdala, JL. No. 77, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000320/2020-2021 | 300/MD | 28/01/2021 | 30 | PABITRA MONDAL | 9.57 | 17.56 | 1
2139 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Parameswarpur, JL. No. 81, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000321/2020-2021 | 301/MD | 28/01/2021 | 30 | A. K. SIKDAR | 7.04 | 5.7 | 1
2140 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bhabanipur, JL. No. 75, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000322/2020-2021 | 302/MD | 28/01/2021 | 489 | MARSS INTERNATIONAL | 7.25 | 0 | 100
2141 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bhadreshwar, JL. No. 78, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000323/2020-2021 | 303/MD | 28/01/2021 | 30 | ACHARYYA CONSTRUCTION | 13.25 | 10.79 | 1
2142 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Dihatti, JL. No. 79, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000324/2020-2021 | 304/MD | 28/01/2021 | 30 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 5.93 | 2.9 | 0
2143 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Harischandrapur, JL. No. 83, G.P.- Baidyapur of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000325/2020-2021 | 305/MD | 28/01/2021 | 30 | KRISHNENDU DUTTA | 25.76 | 24.94 | 1
2144 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bhabanipur, JL. No. 85, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000326/2020-2021 | 306/MD | 28/01/2021 | 30 | RANJIT ADHIKARY | 8.8 | 0 | 0
2145 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bhabuk, JL. No. 89, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000327/2020-2021 | 307/MD | 28/01/2021 | 30 | S. R. CONSTRUCTION | 14.93 | 28.86 | 1
2146 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bhairabpur, JL. No. 86, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000328/2020-2021 | 308/MD | 28/01/2021 | 30 | CHARU CONSTRUCTION | 5.85 | 0 | 0
2147 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Jot Haricharan, JL. No. 43, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000330/2020-2021 | 310/MD | 28/01/2021 | 30 | JOY ENTERPRISE | 6.77 | 5.81 | 1
2148 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Dharmma Danga, JL. No. 44, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000331/2020-2021 | 311/MD | 28/01/2021 | 30 | MANAS KUMAR SAHA | 18.67 | 16.39 | 1
2149 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Kasba, JL. No. 45, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000332/2020-2021 | 312/MD | 28/01/2021 | 30 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 15.48 | 9.46 | 1
2150 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Manoharpur, JL. No. 117, G.P.-Sultannagar of GANNADIA Water Supply Scheme at Harischandrapur - II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000338/2020-2021 | 447/MD | 08/02/2021 | 30 | MANIK CHOUDHURY | 37.13 | 4.9 | 0
2151 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Kendua, JL. No. 54, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000339/2020-2021 | 448/MD | 08/02/2021 | 30 | FAIZUL HAQUE BISWAS | 25.78 | 24.34 | 1
2152 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Gorakhpur, JL. No. 76, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000340/2020-2021 | 449/MD | 08/02/2021 | 30 | TARUN KUMAR DEY | 27.04 | 23.08 | 1
2153 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Konar, JL. No. 73, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000341/2020-2021 | 450/MD | 08/02/2021 | 30 | M/S. TEWARI CONSTRUCTION | 25.97 | 20.69 | 0
2154 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Agra, JL. No. 84, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000342/2020-2021 | 451/MD | 08/02/2021 | 30 | M/S. TEWARI CONSTRUCTION | 25.53 | 15.46 | 1
2155 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Khatil, JL. No. 42, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000343/2020-2021 | 452/MD | 08/02/2021 | 30 | GOBINDA ENTERPRISE | 22.15 | 35.24 | 1
2156 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Muchia, JL. No. 124, G.P.-Muchia of MOBARAKPUR Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000344/2020-2021 | 509/MD | 09/02/2021 | 30 | M/S KUNDU CONSTRUCTION | 46.63 | 93.25 | 1
2157 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional pipe line and Providing FHTC connection at Uttar Rasulpur village of Rampur water supply scheme, Chanchal-II Dev. Block , Chanchal Sub-Division of PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000351/2022-2023 | 2546/MD | 03/11/2022 | 30 | ANUKUL CHANDRA DAS | 6.35 | 6.19 | 100
2158 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Restoration pipe line for Providing FHTC in connection with JJM at Birasthal along NH-81 under command area of Dakshin Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000352/2022-2023 | 2547/MD | 03/11/2022 | 30 | M/S. TEWARI CONSTRUCTION | 1.15 | 0 | 0
2159 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Kankot, JL. No. 50, G.P.-Chandmoni-I of KANKOT Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000353/2020-2021 | 557/MD | 12/02/2021 | 30 | RAY CONSTRUCTION CO. | 57.6 | 29.11 | 1
2160 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bahirgachhi, JL. No. 24, G.P.-Bahirgachhi-I of BAHIRGACHHI Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000354/2020-2021 | 556/MD | 12/02/2021 | 45 | UTTAM KUMAR GHOSH | 71.29 | 12.54 | 0
2161 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Arazi Deharul, JL. No. 21, G.P.-Bahirgachhi-II of BAHIRGACHHI Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000355/2020-2021 | 555/MD | 12/02/2021 | 30 | BEE GEE CONSTRUCTION | 52.81 | 47.96 | 1
2162 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Daulatpur, JL. No. 92, G.P.-Daulatpur of DAULATPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000360/2020-2021 | 569/MD | 15/02/2021 | 45 | M/S TRILOCHAN CONSTRUCTION CO | 84.94 | 83.13 | 1
2163 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Malipakar, JL. No. 91, G.P.-Daulatpur of MALIPAKAR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000361/2020-2021 | 568/MD | 15/02/2021 | 45 | NEOGI ENTERPRISE | 78.3 | 71 | 46
2164 | Malda Division | Chanchal Sub-Division | Extension of UPVC pipe line laying for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Uttar Arbara under command area of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division. PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000364/2023-2024 | 3053/MD | 09/08/2023 | 30 | SOFIKUL ISLAM | 3.09 | 3.08 | 100
2165 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Emergent repairing and laying of uPVC pipeline and Construction of SSP with other allied work to proper functioning of FHTC work within the command area of NEMUA Water Supply scheme under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000401/2022-2023 | 2961/MD | 07/12/2022 | 30 | SUDEB KARMAKAR | 2.09 | 0 | 0
2166 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Kumedpur, JL. No. 142, G.P.-Sadlichak of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000431/2021-2022 | 3004/MD | 07/10/2021 | 30 | FUTURE | 49.95 | 45.14 | 1
2167 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Mabrakpur Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000448/2023-2024 | 3365/MD | 29/08/2023 | 45 | GOBINDA ENTERPRISE | 36.28 | 36.26 | 100
2168 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Nemua Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000450/2023-2024 | 3367/MD | 29/08/2023 | 45 | MOMTAJ ALI | 40.32 | 22.66 | 74
2169 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Purba Binodpur Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000451/2023-2024 | 3368/MD | 29/08/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 10.11 | 9.26 | 100
2170 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) At -Bibijhuti (JL. No. 58), Naikanda (JL. No. 39) & Chandipur (JL. No. 40) G.P.-Kharba In connection of Source Augmentation of Kendua PWSS at Chanchal-I Block under Malda Division. PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000468/2023-2024 | 3458/MD | 07/09/2023 | 328 | M/S /FAIZUL HAQUE BISWAS | 33.7 | 29.55 | 100
2171 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Lalpur Bodra, JL. No. 31, G.P.-Aktail of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000550/2020-2021 | 3102/MD | 15/12/2020 | 30 | M/S SINHA ENTERPRISE | 0 | 5.61 | 1
2172 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Collection of household tap connection details through baseline household mobile's App (Jal Swapna) under commend area of Rajarampur, Mekpur, Purba Binodpur, Mianagar & Basora Piped Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000551/2021-2022 | 515/MSD | 31/12/2021 | 1 | DHRITIPALI | 0.96 | 0.96 | 1
2173 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Rampur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000571/2024-2025 | 5484/MD | 24/10/2024 | 45 | M/S JHA CONSTRUCTION | 57.8 | 0 | 0
2174 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Kankot Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000605/2023-2024 | 3811/MD | 29/09/2023 | 30 | PRITAM ENTERPRISE | 7.66 | 7.65 | 100
2175 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying and extension of uPVC Pipe Line of different diameter at Dihotti & Bhadreswar Mouza of PARAMESHWARPUR Water Supply Scheme at BAMONGOLA Block under Malda Division P.H.E. Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000659/2021-2022 | 3413/MD | 02/12/2021 | 1 | ACHARYYA CONSTRUCTION | 1.25 | 2.09 | 1
2176 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BAHIRGACHHI Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000717/2023-2024 | 4766/MD | 05/12/2023 | 229 | IDEAL CONSTRUCTION | 12.1 | 9.3 | 80
2177 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000722/2023-2024 | 4771/MD | 05/12/2023 | 45 | MD WARESH ALI | 19.7 | 19.61 | 80
2178 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Raikhadighi Mouza under BAHIRGACHHI Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000727/2024-2025 | 6418/MD | 19/12/2024 | 45 | ANUKUL CHANDRA DAS | 18.48 | 0 | 0
2179 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Malipakar Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000743/2024-2025 | 6585/MD | 31/12/2024 | 289 | M/S BABLU ENTERPRISE | 44.5 | 0 | 50
2180 | Malda Division | Chanchal Sub-Division | Laying of Dedicated / Parallel Pipeline for improvement of FHTC functionality by different dia UPVC pipe & Providing FHTC for Bhabuk Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000955/2025-2026 | 771/MD | 19/02/2026 | 60 | RATAN KARMAKAR | 9.66 | 0 | 0
2181 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/08/2023 to 31/01/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000987/2023-2024 | 2023/NBC-II | 30/08/2023 | 180 | TARUN KUMAR BHATTACHARYA | 0.86 | 0.99 | 76
2182 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at RAIKHADIGHI Mouza under BAHIRGACHI Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000997/2023-2024 | 1176/MD | 14/03/2024 | 293 | ABHIJIT ENTERPRISE | 13.25 | 3.09 | 100
2183 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Basara Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001004/2023-2024 | 1512/MD | 16/03/2024 | 168 | MANIK CHOUDHURY | 21.17 | 5.55 | 100
2184 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 23/12/2023 to 19/06/2024=180 Days). Vehicle no. WB 65A/4911. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001161/2023-2024 | 5151/MD | 21/12/2023 | 180 | USHA ENTERPRISE | 0.86 | 0.39 | 0
2185 | Malda Division | RWS Malda Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AKALPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | ORD/000163/2020-2021 | 2716/MD | 10/11/2020 | 45 | M/S AMIT KUMAR GUPTA | 73.35 | 55.98 | 40
2186 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Akalpur Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Md. Ataur Rahaman, Junior Engineer | ORD/000598/2024-2025 | 5936/MD | 27/11/2024 | 90 | S. N. CONSTRUCTION | 42.82 | 0 | 0
2187 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer |  | ORD/000164/2020-2021 | 2717/MD | 10/11/2020 | 45 | UNIVERSAL ENTERPRIESES | 70.14 | 124.54 | 1
2188 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer |  | RTOR000002/2024-2025 | 3915/MD | 06/08/2024 | 0 | Resource Division | 1.42 | 0 | 0
2189 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer |  | RTOR000041/2025-2026 | 2818/MD | 11/06/2025 | 0 | Resource Division | 8.32 | 0 | 0
2190 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of pipeline at Milki G.S. Colony & Bhabanipur in connection with Jal Jeevan Mission (JJM) to provide FHTC at Milki Distribution Zone under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000035/2023-2024 | 884/MAAD | 11/05/2023 | 60 | M/S N. N. ENTERPRISE | 7.75 | 7.74 | 100
2191 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
2192 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Khaskol Chandipur & Bhabanipur Mouza of Milki Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000189/2022-2023 | 1400/MAAD | 26/07/2022 | 60 | M/S N. N. ENTERPRISE | 27.51 | 25.07 | 100
2193 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying UPVC pipe at Laxmighat Nagrai and adjoining villages for FHTC under Laxmighat Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000216/2024-2025 | 1477/MAAD | 03/09/2024 | 59 | M/S MANDAL & SONS | 2.49 | 0.61 | 90
2194 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Repairing & Laying of pipeline at Bhabanipur & Pirpur under Bhabanipur mouza in connection with Jal Jeevan Mission (JJM), Repairing of valve Chamber & other allied works at Milki Distribution zone under Malda Arsenic Area Water Supply Division PHED. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000275/2022-2023 | 1876/MAAD | 28/09/2022 | 45 | M/S N. N. ENTERPRISE | 5.27 | 5.12 | 1
2195 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KuddibarMohonpur, Munshipara, ShyampurColoni, Madia of Milki Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000341/2021-2022 | 1750/MAAD | 24/11/2021 | 45 | M/S N. N. ENTERPRISE | 11.76 | 11.17 | 1
2196 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | RTOR000007/2022-2023 | 1339/MAAD | 18/07/2022 | 0 | Resource Division | 12.3 | 0 | 0
2197 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | RTOR000011/2022-2023 | 1701/MAAD | 21/09/2022 | 0 | Resource Division | 1.23 | 0 | 0
2198 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Madia Mouza of Milki Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000349/2021-2022 | 1761/MAAD | 24/11/2021 | 60 | BHOLANATH CONSTRUCTION | 41.21 | 41.13 | 1
2199 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kuddibari Mohonpur of Milki Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000357/2021-2022 | 1721/MAAD | 18/11/2021 | 30 | M/S N. N. ENTERPRISE | 4.79 | 4.79 | 1
2200 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sherpur Water Supply Scheme (Mouza- Chirampur, Purba Chandpur, Dakshin Debipur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000048/2022-2023 | 822/MAAD | 28/04/2022 | 60 | A. K. CONSTRUCTION | 80.44 | 73.9 | 1
2201 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
2202 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mouza: -Sherpur Habitations: - Fatekhani for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000247/2022-2023 | 1825MAAD | 27/09/2022 | 45 | A. K. CONSTRUCTION | 5.59 | 5.57 | 100
2203 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mouza: -Sherpur, Chhirampur Habitations: - Jamirgata, Chhatragachi, Mandal Para, Kamat, Jalalpur, Chhirampur for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000248/2022-2023 | 1826/MAAD | 27/09/2022 | 45 | A. K. CONSTRUCTION | 5.19 | 5.17 | 100
2204 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mouza: -Sherpur Habitations: - Sherpur for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000249/2022-2023 | 1827MAAD | 27/09/2022 | 45 | A. K. CONSTRUCTION | 6.84 | 6.82 | 100
2205 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mouza: -Sherpur, Chhirampur Habitations: - Jamirgata, Chhatragachi, Mandal Para, Kamat, Jalalpur, Chhirampur for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000266/2022-2023 | 1868/MAAD | 28/09/2022 | 30 | A. K. CONSTRUCTION | 4.87 | 4.85 | 100
2206 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of uPVC Pipe line at Dandi Gram, Jafarabad for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000503/2021-2022 | 388/MAAD | 08/03/2022 | 45 | A. K. CONSTRUCTION | 13.29 | 13.09 | 1
2207 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | RTOR000012/2022-2023 | 1702/MAAD | 21/09/2022 | 0 | Resource Division | 4.93 | 0 | 0
2208 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sherpur Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Sherpur) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000337/2021-2022 | 1746/MAAD | 24/11/2021 | 60 | A. K. CONSTRUCTION | 43.13 | 42.12 | 1
2209 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mouza: -Tap Pratappur, Habitations: - Jotkabil, Satangapara for installation of FHTC under Mothabari distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000099/2022-2023 | 949MAAD | 11/05/2022 | 15 | FUTURE | 3.78 | 3.56 | 1
2210 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 20mm dia HDPE pipe at Mouza: -Tap Pratappur, Habitations: - Amlitola, Kuttu Mandal Tola, Laxmipur, Dhulauri, Haibatola for installation of FHTC under Mothabari distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000100/2022-2023 | 950/MAAD | 11/05/2022 | 15 | FUTURE | 2.95 | 2.95 | 1
2211 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mothabari Water Supply Scheme (Mouza- Debipur & Chakpratappur) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000118/2022-2023 | 1019/MAAD | 12/05/2022 | 60 | M/S ALISA CONSTRUCTION | 51.08 | 44.59 | 1
2212 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
2213 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mothabari Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Tap Protappar) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000334/2021-2022 | 1745/MAAD | 24/11/2021 | 60 | FUTURE | 48.77 | 48.71 | 1
2214 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 75mm uPVC pipe line at Dulauri, Kuttu Mandal Tola & Satanga Para for installation of FHTC under Mothabari distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000523/2021-2022 | 354/MAAD | 07/03/2022 | 45 | FUTURE | 4.29 | 4.22 | 1
2215 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 75mm uPVC pipe line at different places for installation of FHTC under Mothabari distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | ORD/000524/2021-2022 | 355/MAAD | 07/03/2022 | 45 | FUTURE | 3.71 | 3.62 | 1
2216 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-II | RTOR000006/2022-2023 | 1338/MAAD | 18/07/2022 | 0 | Resource Division | 12.3 | 0 | 0
2217 | Malda Division | Malda Mechanical Division | Formal work order for Augmentation of TILASAN Piped water supply scheme for the work of Geotechnical Study,construction of 200 Cum RCC OHR,Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Habibpur Block under Malda Division PH Engg.Dte. In the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000004/2022-2023 | 996/MD | 22/04/2022 | 365 | UTTAM KUMAR GHOSH | 180.23 | 163.53 | 100
2218 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of Rising Main including connection of Pump No-1 & Pump No 2 and by pass arrangement for TILASAN Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000030/2022-2023 | 1307/MD | 01/06/2022 | 30 | M/S EHAN ENTERPRISE | 4.44 | 4.43 | 1
2219 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Dismantling of concrete road and Construction the same at different places of road connecting to LDS of TILASAN Piped Water Supply Scheme at Habibpur Dev. Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000081/2023-2024 | 2177/MD | 07/06/2023 | 30 | UTTAM KUMAR GHOSH | 21.68 | 21.68 | 100
2220 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Providing Functional House hold Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under Command area of Augmentation of TILASAN Piped Water Supply Scheme at Habibpur Dev. Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000082/2023-2024 | 2178//MD | 07/06/2023 | 30 | UTTAM KUMAR GHOSH | 13.35 | 12.19 | 100
2221 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of TILASAN Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000539/2021-2022 | 2693/MD | 09/09/2021 | 7 | RADIANT | 1.25 | 1.25 | 1
2222 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Dismentling of Concrete road and Construction the same from Head Work site to 2nd Tube Well Site of TILASAN Water Supply Scheme at Habibpur Dev. Block under Malda Division, P.H.E. Dte. In the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000785/2022-2023 | 1443/MD | 29/03/2023 | 30 | M/S EHAN ENTERPRISE | 3.15 | 3.15 | 100
2223 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) and Laying of 90 mm dia (OD) uPVC Pipeline under command area of AUGMENTATION OF TILASAN Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/001036/2023-2024 | 1262/MD | 15/03/2024 | 254 | SATTWIK CONSTRUCTION | 7.44 | 6.93 | 100
2224 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | RTOR000005/2022-2023 | 1107/MD | 17/05/2022 | 0 | Resource Division | 16.55 | 0 | 0
2225 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | RTOR000010/2022-2023 | 1461/MD | 22/06/2022 | 0 | Resource Division | 6.78 | 0 | 0
2226 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | RTOR000043/2022-2023 | 1587/MD | 28/03/2023 | 0 | Resource Division | 0.41 | 0 | 0
2227 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | RTOR000055/2025-2026 | 5598/MD | 30/10/2025 | 0 | Resource Division | 2.88 | 0 | 0
2228 | Central Drilling | Malda Mechanical Division | Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mecha nical Sub Division-I(D), CDD, P.H.Engineering Dte. For Supervision of JJM related works. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000220/2023-2024 | 13/CMSD-I(D) | 15/01/2024 | 198 | AJAY KUMAR | 0.94 | 1.04 | 15
2229 | Central Drilling | Malda Mechanical Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT TILASAN, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000241/2022-2023 | 347/CMSD-I | 25/07/2022 | 15 | CHANDA ENTERPRISE | 4.69 | 4.43 | 0
2230 | Central Drilling | Malda Mechanical Division | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITEFOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000242/2022-2023 | 346/CMSD-I | 25/07/2022 | 15 | CHANDA ENTERPRISE | 4.66 | 1.4 | 0
2231 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- I of Tilason Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/009047) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000253/2023-2024 | 2226/MLMD | 18/07/2023 | 839 | SUBRATA KUMAR DAS. | 10.08 | 6.06 | 30
2232 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- II of Tilason Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/009047) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000254/2023-2024 | 2227/MLMD | 18/07/2023 | 542 | JOY ENTERPRISE. | 7.57 | 0 | 25
2233 | Malda Division | Malda Mechanical Division | Bill for reimbursement of cost of Diesel and Mobile in respect of hired Vehicle Car No. WB65A/4911 for the month of May & June 2023. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00370/2023-2024 |  | 04/09/2023 | 0 | USHA ENTERPRISE | 0.41 | 0 | 0
2234 | Malda Division | Malda Mechanical Division | Soil Investigation and design of substructure for Over Head Reservoirs for UTTAR HARISHCHANDRAPUR ZONE-I Piped Water Supply Scheme at Harishchandapur-I Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00487/2022-2023 | BP-2022-23-196 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
2235 | Malda Division | Malda Mechanical Division | Placement of fund against the work for road restoration work for laying of pipe line for NH-81 to Harishchandarapur Railway Station Road under Malda Division, PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00495/2022-2023 | BP-2022-23-213 | 17/03/2023 | 0 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 1.4 | 0 | 0
2236 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01 (One) Nos. 300mm. Dia. x 200mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Uttar Harishchandrapur (Zone-I) Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000044/2022-2023 | 1393/MD | 14/06/2022 | 21 | M/S DEBASISH GHOSH | 10.83 | 0 | 96
2237 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01 (One) Nos. 300mm. Dia. x 200mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Uttar Harishchandrapur (Zone-II) Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000045/2022-2023 | 1394/MD | 14/06/2022 | 21 | SNEHASISH GHOSH | 10.82 | 10.71 | 95
2238 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at Head Work site of UTTAR HARISHCHANDRAPUR ZONE-II & its adjoining mouza Water Supply Scheme under Malda Division,PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000054/2022-2023 | 1486/MD | 23/06/2022 | 60 | S. N. CONSTRUCTION | 6.18 | 0 | 0
2239 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 4 of Uttar Harishchandrapur Zone-I PWSS under Harishchandrapur-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000107/2025-2026 | 2278/MD | 21/05/2025 | 45 | MASUMA ENTERPRISE | 4.28 | 0 | 100
2240 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Uttar Harishchandrapur Zone-I Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (2ND Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000134/2022-2023 | 1791/MD | 01/08/2022 | 1035 | PRADIP KUMAR DAS | 369.64 | 327.83 | 100
2241 | Malda Division | Malda Mechanical Division | Construction of 5.40 mtr.X 3.60 mtr Switch Room cum chlorine room at UTTAR HARISHCHANDRAPUR ZONE-II Piped Water Supply Scheme at Head Work Site under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000140/2024-2025 | 2891/MD | 07/06/2024 | 45 | KANAN CONSTRUCTION ENTERPRISE | 6.6 | 5.79 | 100
2242 | Malda Division | Malda Mechanical Division | Road restoration work related to laying of Pipeleine at Uttar Harishchandrapur Zone-I Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000159/2025-2026 | 2881/MD | 17/06/2025 | 45 | PRADIP KUMAR DAS | 56.21 | 0 | 0
2243 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Uttar Harishchandrapur Zone-I Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000210/2024-2025 | 3031/MD | 13/06/2024 | 657 | M/S GHOSH CONSTRUCTION | 10.19 | 0 | 0
2244 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Uttar Harishchandrapur Zone-II Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000211/2024-2025 | 3032/MD | 13/06/2024 | 183 | M/S. B. PAUL & COMPANY | 25.13 | 14.45 | 82
2245 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 400 M3 Capacity OHR with Soil Investigation and FHTC of UTTAR HARISHCHANDRAPUR ZONE-II Piped Water Supply Scheme at Harishchandrapur-I and II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000227/2023-2024 | 2682/MD | 13/07/2023 | 1108 | KANAN CONSTRUCTION ENTERPRISE | 229.11 | 84.59 | 65
2246 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 900 M3 Capacity OHR with FHTC (Mouza- Uttar Harishchandrapur 50% area covered) of Uttar Harishchandrapur Zone-I Piped Water Supply Scheme at Harishchandrapur-I & II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000476/2023-2024 | 3615/MD | 21/09/2023 | 468 | MAHAMAYA BURIMA ENTERPRISE | 340.61 | 68.01 | 65
2247 | Malda Division | Malda Mechanical Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at NODE POINT 80 TO 82,82 TO 83 (DISTRIBUTION SYSTEM) at Uttar Harishchandrapur Zone -II and its adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000477/2024-2025 | 4991/MD | 27/09/2024 | 45 | M/S TRILOCHAN CONSTRUCTION CO | 23.29 | 0 | 1
2248 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Uttar Harishchandrapur Zone-I Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000489/2024-2025 | 5002/MD | 27/09/2024 | 270 | SAJEDUR RAHAMAN | 34.41 | 0 | 80
2249 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Uttar Harishchandrapur Zone-II Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000509/2022-2023 | 377/MD | 31/01/2023 | 1034 | KUNDU CONSTRUCTION | 227.6 | 126.66 | 41
2250 | Malda Division | Malda Mechanical Division | Laying of Additional Pipeline HDPE in connection with Jal Jeevan Mission (JJM) at Uttar Harishchandrapur Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000624/2024-2025 | 5831/MD | 22/11/2024 | 317 | KUNDU CONSTRUCTION | 95.04 | 0 | 0
2251 | Malda Division | Malda Mechanical Division | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Harishchandrapur Zone-I Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000775/2024-2025 | 269/MD | 28/01/2025 | 518 | FUTURE | 126.38 | 0 | 50
2252 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Uttar Harishchandrapur Zone-I Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000782/2024-2025 | 348/MD | 30/01/2025 | 30 | TWO BROTHERS CONSTRUCTION | 6.1 | 0 | 100
2253 | Malda Division | Malda Mechanical Division | Laying Emergent repairing of distribution pipe line & laying of UPVC pipe line of UTTAR HARISHCHANDRAPUR water supply scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000783/2019-2020 | 856/MD | 20/03/2020 | 0 | PARIJAT RAY | 4.57 | 0 | 1
2254 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Harishchandrapur Zone-II Water Supply Scheme under Harishchandrtapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000790/2024-2025 | 355/MD | 30/01/2025 | 90 | AHONA ENTERPRISE | 40.23 | 0 | 1
2255 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Uttar Harishchandrapur Zone-I PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000903/2023-2024 | 276/MD | 11/01/2024 | 45 | M/S DUTTA ENTERPRISE | 4.18 | 0 | 0
2256 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000006/2022-2023 | 1206/MD | 24/05/2022 | 0 | Resource Division | 53.31 | 0 | 0
2257 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000019/2025-2026 | 2810/MD | 11/06/2025 | 0 | Resource Division | 25.48 | 0 | 0
2258 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000061/2025-2026 | 5590/MD | 30/10/2025 | 0 | Resource Division | 3.53 | 0 | 0
2259 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000105/2023-2024 | 35/MD | 04/01/2024 | 0 | Resource Division | 17.33 | 0 | 0
2260 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000127/2023-2024 | 97/MD | 05/01/2024 | 0 | Resource Division | 11.4 | 0 | 0
2261 | Malda Mechanical | Malda Mechanical Division | Quatation for new service connection at Uttar Harishchandrapur w/s sch. Zone I T/W no IV UNDER MLMD. Dist Malda. (Harishchandrapur C. C. C) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03507/2023-2024 | BP-2023-24-527 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 8.02 | 0 | 0
2262 | Malda Mechanical | Malda Mechanical Division | New service connection at UTTAR HARISHCHANDRAPUR PWSS Zone II T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03759/2023-2024 | BP-2023-24-730 | 28/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.42 | 0 | 0
2263 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II, III & IV and making compound lighting arrangement at T/W no. I of Augmentation of Uttar Harishandropur (Zone- I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008163) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000236/2023-2024 | 2253/MLMD | 18/07/2023 | 1136 | M/S P.P. ELECTRICALS | 50.68 | 39.6 | 82
2264 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Augmentation of Uttar Harishandropur (Zone- II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008163) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000237/2023-2024 | 2254/MLMD | 18/07/2023 | 1138 | DAS ENTERPRISE. | 21.45 | 0 | 45
2265 | Malda Division | Malda Mechanical Division | Construction of Pump House and Boundary wall at 2nd Tube well and 3rd Tube Well site with dedicated/parallel pipe line for better Functionality of FHTC under KARIALI ZONE-I Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000209/2025-2026 | 3724/MD | 30/07/2025 | 225 | VISCOUS ENGINEERS PVT. LTD. | 81.41 | 0 | 0
2266 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of KARIALI ZONE-I Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000226/2023-2024 | 2681/MD | 13/07/2023 | 1199 | KANAN CONSTRUCTION ENTERPRISE | 437.7 | 147.23 | 75
2267 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall and 5.40 mtr.X 3.6mtr Switch Room cum chlorine room at Head Work site of Kariali Zone-I Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000515/2024-2025 | 5337/MD | 03/10/2024 | 545 | M/S ANKUSH ENTERPRISE | 33.27 | 0 | 75
2268 | Malda Division | Malda Mechanical Division | Sinking of 200mm (all through) Big dia. Tube Well of 150m Deep at Head work site of Kariali Zone-I Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000608/2024-2025 | 5604/MD | 05/11/2024 | 361 | SAUDAGAR INDIA | 9.82 | 0 | 100
2269 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Kariali Zone-I Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000691/2021-2022 | 656/MD | 22/03/2022 | 15 | M/S SOBHA & CO. | 3.23 | 3.23 | 1
2270 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | RTOR000059/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 56.72 | 0 | 0
2271 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | RTOR000130/2023-2024 | 100/MD | 05/01/2024 | 0 | Resource Division | 25.06 | 0 | 0
2272 | Malda Mechanical | Malda Mechanical Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000646/2024-2025 | 2212/MLMD | 21/08/2024 | 61 | NITAI PANDEY | 0.78 | 0 | 0
2273 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning of electro-mechanical components at T/W no. I, II,III of Kariali (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011278) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000681/2023-2024 | 2756/MLMD | 14/08/2023 | 1078 | DILIP MAHATO. | 43.59 | 29.93 | 69
2274 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well no-3 ( 115 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at RAJARAMPUR Water Supply Scheme of Habibpur Block .under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000306/2022-2023 | 2301/MD | 28/09/2022 | 30 | DUTTA ENTERPRISE | 8.24 | 8.2 | 1
2275 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of RAJARAMPUR Water Supply Scheme of Habibpur Block. under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000342/2022-2023 | 3109/MD | 20/12/2022 | 45 | M/S SRINJOYEE | 6.68 | 6.49 | 1
2276 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for RAJARAMPUR Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000356/2022-2023 | 2505//MD | 03/11/2022 | 45 | GOBINDA ENTERPRISE | 43.92 | 43.21 | 100
2277 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at RAJARAMPUR Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000883/2024-2025 | 1122/MD | 21/03/2025 | 369 | THREE BROTHERS CONSTRUCTION & CO | 9.43 | 0 | 0
2278 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Rajarampur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/001019/2023-2024 | 1187/MD | 14/03/2024 | 154 | ANJIMA CONSTRUCTION CO. | 11.85 | 0 | 100
2279 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Rajarampur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/001020/2023-2024 | 1188/MD | 14/03/2024 | 293 | IDEAL CONSTRUCTION | 12.83 | 0 | 100
2280 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | RTOR000018/2022-2023 | 2406/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
2281 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Rajarampur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012802) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000030/2023-2024 | 821/MLMD | 03/05/2023 | 180 | SUDIP DEY | 11.22 | 11.05 | 98
2282 | Malda Mechanical | Malda Mechanical Division | Hiring of Inspection vehicle (Diesel driven) for official use of AE-II for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/001074/2023-2024 | 1130/MLMD | 23/06/2023 | 7 | SUBRATA SAHA | 0.86 | 0.86 | 100
2283 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H-III site of Rajarampur C.C.C Aiho in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/001150/2022-2023 | 3004231191 | 21/03/2023 | 7 | W.B.S.E.D.C.LTD | 0.71 | 0.71 | 1
2284 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of KISMAT BAROL Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000094/2023-2024 | 2115/MD | 06/06/2023 | 602 | MILLENNIUM ENTERPRISR | 463.93 | 46.69 | 52
2285 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Kismatbarol Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000167/2024-2025 | 2942/MD | 10/06/2024 | 30 | S & G CONSTRUCTION | 8.41 | 0 | 0
2286 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Kismatbarol Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000214/2024-2025 | 3035/MD | 13/06/2024 | 567 | MILLENNIUM ENTERPRISE | 28.66 | 0 | 80
2287 | Malda Division | Malda Mechanical Division | Dedicated/Parallel Pipe Line for better functionality and road restoration of Kismat Baral Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000690/2025-2026 | 5919/MD | 26/11/2025 | 60 | MILLENNIUM ENTERPRISE | 44.43 | 0 | 0
2288 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kismat Barol Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000753/2024-2025 | 72 | 13/01/2025 | 90 | M/S AMIT KUMAR GUPTA | 40.43 | 0 | 0
2289 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000012/2023-2024 | 1612/MD | 11/04/2023 | 0 | Resource Division | 14.33 | 0 | 0
2290 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000034/2022-2023 | 3046/MD | 12/12/2022 | 0 | Resource Division | 22.91 | 0 | 0
2291 | Malda Mechanical | Malda Mechanical Division | New service connection at Kismatbaral PWSS T/W NO I Under EE/MLMD PHE DTE DIST. Malda.(kushida c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00758/2024-2025 | BP-2024-25-203 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.79 | 0 | 0
2292 | Malda Mechanical | Malda Mechanical Division | New service connection at KISMATBAROL Pwss pH NO II Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03680/2023-2024 | BP-2023-24-663 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 8.14 | 0 | 0
2293 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Kismat Barol Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013044) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000320/2023-2024 | 2322/MLMD | 26/07/2023 | 120 | S. P. CONSTRUCTION | 26.28 | 13.55 | 52
2294 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Augmentation of ALAL ZONE-II Piped Water Supply Scheme at Gajol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000050/2023-2024 | 2000/MD | 17/05/2023 | 1124 | KRISHNENDU DUTTA | 357.66 | 111.79 | 50
2295 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of ALAL ZONE-II Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000099/2023-2024 | 2326/MD | 08/06/2023 | 998 | M/S. TEWARI CONSTRUCTION | 50.63 | 0 | 0
2296 | Malda Division | RWS Malda Sub-Division | Dedicated Pipe laying for better Functionality and Providing Balance FHTC, Construction of Approach Road, Land development and allied work for ALAL Zone-II Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000216/2025-2026 | 3777/MD | 04/08/2025 | 120 | MANIK CHOUDHURY | 34.6 | 0 | 0
2297 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work site of Alal Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000266/2024-2025 | 3415/MD | 09/07/2024 | 571 | KRISHNENDU DUTTA | 33.49 | 0 | 0
2298 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tube Well site of Alal Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000312/2024-2025 | 3952/MD | 07/08/2024 | 557 | KRISHNENDU DUTTA | 8.71 | 0 | 0
2299 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Alal Zone-II Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000687/2021-2022 | 652/MD | 22/03/2022 | 15 | TECHVISION | 3.33 | 3.32 | 0
2300 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000716/2024-2025 | 6407/MD | 19/12/2024 | 407 | KRISHNENDU DUTTA | 28.08 | 0 | 0
2301 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000066/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 10.65 | 0 | 0
2302 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000156/2023-2024 | 252/MD | 10/01/2024 | 0 | Resource Division | 8.7 | 0 | 0
2303 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Alal Zone-II, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/03715/2023-2024 | BP-2023-24-712 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.64 | 0 | 0
2304 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning of electro-mechanical components & Trial operation at T/W no. I & II, and making compound lighting arrangement at head worksite of Alal Zone-II Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011886) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000512/2023-2024 | 2584/MLMD | 04/08/2023 | 952 | DAS CONSTRUCTION | 25.24 | 17.75 | 70
2305 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
2306 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Laxmipur, Nagrai and adjoining villages under command area of Laxmighat Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000219/2024-2025 | 1480/MAAD | 03/09/2024 | 60 | S. N. CONSTRUCTION | 7.08 | 0 | 0
2307 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Laxmipur under command area of Laxmighat Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000220/2024-2025 | 1481/MAAD | 03/09/2024 | 576 | FUTURE | 7.08 | 0 | 0
2308 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Milki G.S. Colony under command area of Milki Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000383/2023-2024 | 303/MAAD | 11/03/2024 | 30 | M/S N. N. ENTERPRISE | 4.2 | 3.94 | 90
2309 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying UPVC pipe and installation of Street Stand post at Sekhpura purbapara under Enayetpur W/S Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000046/2023-2024 | 945/MAAD | 23/05/2023 | 45 | ABHIJIT ENTERPRISE | 3.53 | 3.44 | 0
2310 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area (Mouza Enayetpur part, Miragram) & others Allied works at Enayetpur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000051/2022-2023 | 825/MAAD | 28/04/2022 | 60 | GOBINDA ENTERPRISE | 36.64 | 34.71 | 1
2311 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Repairing of pipe line by laying of UPVC pipeline at Miragram Mouza for installation of FHTC at Enayetpur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000157/2022-2023 | 1170/MAAD | 13/06/2022 | 45 | GOBINDA ENTERPRISE | 4.82 | 4.82 | 1
2312 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
2313 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Salabadganj Paschim Para under Enayetpur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000200/2022-2023 | 1477/MAAD | 29/07/2022 | 45 | M/S. AYUSH BUILDERS | 4.77 | 4.41 | 1
2314 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bakipur (Laddutola) under Enayetpur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000223/2022-2023 | 1473/MAAD | 29/07/2022 | 45 | ABHIJIT ENTERPRISE | 4.84 | 4.48 | 1
2315 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Enayetpur Mouza for installation of FHTC under Enayetpur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000530/2021-2022 | 361/MAAD | 07/03/2022 | 30 | A. B. CONSTRUCTION | 3.03 | 3.03 | 1
2316 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 63 mm dia UPVC Pipe and 20 mm dia HDPE pipe and other allied works at Miragram for installation of House Connection under Enayetpur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000268/2022-2023 | 1870/MAAD | 28/09/2022 | 45 | GOBINDA ENTERPRISE | 3.93 | 3.77 | 1
2317 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of 90 mm dia UPVC Pipeline and other allied works at Salabadganj for installation of House Connection under Enayetpur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000272/2022-2023 | 1873/MAAD | 28/09/2022 | 45 | M/S. AYUSH BUILDERS | 2.66 | 2.38 | 1
2318 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Enayetpur Water Supply Scheme( Enayetpur mouza) at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I | ORD/000354/2021-2022 | 1757/MAAD | 24/11/2021 | 45 | A. B. CONSTRUCTION | 24.33 | 23.35 | 1
2319 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for BASARA Piped Water Supply Scheme at Bamangola Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000413/2022-2023 | 2987/MD | 07/12/2022 | 936 | M/S JHA CONSTRUCTION | 81.06 | 0 | 100
2320 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Basara Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000486/2024-2025 | 4999/MD | 27/09/2024 | 127 | JOY GURU ENTERPRISE | 10.2 | 2.48 | 100
2321 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Basara Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000728/2022-2023 | 1202/MD | 21/03/2023 | 45 | M.S. ENTERPRISE | 4.17 | 0 | 0
2322 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bujurkhali, Harinandanbati & Chandipur Mouza of Basara Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000783/2024-2025 | 349/MD | 30/01/2025 | 92 | DHRITIPALI | 21.06 | 0 | 0
2323 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Basora Water Supply scheme at Bamangola Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000829/2024-2025 | 1000/MD | 12/03/2025 | 173 | SABITA CONSTRUCTION COMPANY | 8.5 | 0 | 100
2324 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (200mm. Dia. x 150 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at BASARA Piped Water Supply Scheme (Tube Well No-3) of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000835/2022-2023 | 2706/MD | 17/11/2022 | 30 | RATAN CHANDRA SARKAR | 6.81 | 0 | 0
2325 | Malda Division | Malda Mechanical Division | Sinking of ( 200 mm Dia. X 150 mm Dia.) Tube well No.-4 (250 M deep) by D.R Rig. Method using P.V.C. Pipe & Gravel Filter including Supply of materials at BASARA Water Supply Scheme of Bamongola Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000919/2023-2024 | 380/MD | 17/01/2024 | 45 | A. L. ENGINEERING SOLUTION | 12.74 | 0 | 100
2326 | Central Drilling | Malda Mechanical Division | Resistivity survey for Sankail PWSS, Basara PWSS and Pannapur PWSS at Habibipur & Bamongola block under Malda district, CMSD-II (D), CDD, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000012/2023-2024 | 135/CMSD-II(D) | 24/05/2023 | 15 | S B S ENTERPRISE | 0.82 | 0.27 | 100
2327 | Malda Mechanical | Malda Mechanical Division | QUOTATION PAYMENT FOR PH NO 4 OF BASORA W/S SCHEME UNDER BAMONGOLA CCC UNDER MALDA DISTRICT | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | BILL/00476/2025-2026 |  | 22/05/2025 | 0 | W.B.S.E.D.C.LTD | 11.37 | 0 | 0
2328 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. IV of Basara Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015035) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000310/2023-2024 | 2312/MLMD | 26/07/2023 | 535 | JOY ENTERPRISE. | 11.01 | 3.92 | 22
2329 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Chanchal Zone-III Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000447/2024-2025 | 4734/MD | 11/09/2024 | 233 | M/S MADHU CONSTRUCTION | 19.9 | 0 | 100
2330 | Malda Division | Chanchal Sub-Division | Sinking of 200 mm (all through) Big Dia. Tube-Well of 250 M Deep at Chanchal SD Hospital Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000459/2024-2025 | 4814/MD | 13/09/2024 | 186 | M/S DAS CONSTRUCTION | 28.87 | 6.4 | 100
2331 | Malda Division | Chanchal Sub-Division | Replacement of existing tube well by 200x200 mm dia. and 250 M Deep by Big Dia Tube Well at 4th Tube Well site (Near Panchali Hostel) of Chanchal Piped Water Supply Scheme at Chanchal-I block of malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000462/2024-2025 | 4817/MD | 13/09/2024 | 300 | M/S DYNAMIC CONSTRUCTION | 13.81 | 0 | 100
2332 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Augmentation of CHANCHAL ZONE-I, ZONE-II AND ZONE-III Piped Water Supply Scheme at Chanchal-I Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000658/2022-2023 | 1026/MD | 13/03/2023 | 1111 | GHOSH BROTHERS | 1318.2 | 69.76 | 15
2333 | Malda Division | Chanchal Sub-Division | Emergent Interconnection between Existing Tube Well and Bolck office building water tank in connection of CHANCHAL Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000763/2024-2025 | 6621/MD | 31/12/2024 | 180 | BIDYUT MAHALDAR | 0.86 | 0 | 100
2334 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-2) (Period from 01/01/2025 to 30/06/2025). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000873/2024-2025 | 6636/MD | 31/12/2024 | 181 | M/S TEWARI CONSTRUCTION | 0.86 | 0 | 0
2335 | Malda Division | Chanchal Sub-Division | Laying of Distribution Sysytem of Chanchal Zone -I, II & III Piped Water Supply Scheme at Chanchal -I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000926/2023-2024 | 535/MD | 30/01/2024 | 548 | GHOSH BROTHERS | 56.98 | 0 | 35
2336 | Malda Division | Chanchal Sub-Division | Erection of Property board related to Jal Jeevan Mission works of Chanchal and Alihanda GP under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000943/2024-2025 | 631/MD | 19/02/2025 | 7 | RABIUL ISLAM | 0.83 | 0 | 100
2337 | Malda Division | Chanchal Sub-Division | Restoration of road at Chanchal Zone -III Water Supply Scheme under Chanchal -I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000964/2025-2026 | 692/MD | 13/02/2026 | 30 | SABITA CONSTRUCTION COMPANY | 13.11 | 0 | 0
2338 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000042/2025-2026 | 2866/MD | 16/06/2025 | 0 | Resource Division | 34.33 | 0 | 0
2339 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000069/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 186.59 | 0 | 0
2340 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000134/2023-2024 | 111/MD | 05/01/2024 | 0 | Resource Division | 34.35 | 0 | 0
2341 | Malda Mechanical | Chanchal Sub-Division | New service connection at CHANCHAL PWSS Zone III T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( CHANCHAL c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00236/2024-2025 | BP-2024-25-85 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.36 | 0 | 0
2342 | Malda Mechanical | Chanchal Sub-Division | New service connection at Chanchal PWSS Zone I T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( chanchal c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/02974/2024-2025 | BP-2024-25-633 | 06/02/2025 | 0 | W.B.S.E.D.C.LTD | 6.74 | 0 | 0
2343 | Malda Division | Chanchal Sub-Division | Design, Supplying. Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 100 m3/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room and backwash water disposal at head work site, Construction of Boundary Wall at head work site, Laying of Parallel/Dedicated Pipeline of CHAANCHAL ZONE-I Water Supply Scheme of Chanchal-I Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000945/2025-2026 | 690/MD | 13/02/2026 | 150 | WATER TECH | 95.49 | 0 | 0
2344 | Malda Division | Chanchal Sub-Division | Construction of approach road at OHR and 2nd Tube well site with land development, Laying of Parallel/Dedicated Pipeline for better functionality and Design, Supplying. Fabrication, Erection and Commissioning including 3 (three) months Trial Run of 100 m3/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal of CHAANCHAL ZONE-III Water Supply Scheme of Chanchal-I Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000963/2025-2026 | 691/MD | 13/02/2026 | 150 | BANIK BROTHERS | 96.1 | 0 | 0
2345 | Malda Mechanical | Chanchal Sub-Division | New service connection at CHANCHAL PWSS Zone I T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( CHANCHAL c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/03217/2024-2025 | 124 | 07/08/2025 | 0 | W.B.S.E.D.C.LTD | 4.65 | 0 | 0
2346 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning of electro-mechanical components at T/W no. I, II,III &IV of Chanchal (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011884) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000377/2023-2024 | 2385/MLMD | 28/07/2023 | 1154 | GHOSH BROTHERS... | 39.33 | 0 | 0
2347 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering and making compound lighting arrangement at T/W no. I of Chanchal (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011884) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000627/2023-2024 | 2662/MLMD | 10/08/2023 | 2005 | HANNAN BUILDERS PVT. LTD. | 35.18 | 20.93 | 60
2348 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering and making compound lighting arrangement at T/W no. I of Chanchal (zone-III) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011884) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001704/2023-2024 | 3425/MLMD | 01/11/2023 | 1058 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 33.92 | 21.99 | 65
2349 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Moyna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000677/2024-2025 | 6202/MD | 09/12/2024 | 45 | M/S /FAIZUL HAQUE BISWAS | 7.17 | 0 | 100
2350 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for MOYNA Piped Water Supply Scheme (Moua- Bade Myna, JL No. 117) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000698/2022-2023 | 1155/MD | 20/03/2023 | 879 | M/S BABLU ENTERPRISE | 22.65 | 20.58 | 37
2351 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for MOYNA Piped Water Supply Scheme (Mouza- Moyna, JL No. 119 & Mouza- Anantarapur, JL No. 120) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000705/2022-2023 | 1163/MD | 20/03/2023 | 45 | MOMTAJ ALI | 24.65 | 0 | 0
2352 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 (171.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MOYNA Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000711/2022-2023 | 1169/MD | 20/03/2023 | 30 | M/S SAHA CONSTRUCTION | 9.8 | 7.83 | 100
2353 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 (171.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MOYNA Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000712/2022-2023 | 1170/MD | 20/03/2023 | 30 | A. D. D. ASSOCIATES | 10.56 | 0 | 0
2354 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Moyna Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000732/2022-2023 | 1206/MD | 21/03/2023 | 45 | M/S /FAIZUL HAQUE BISWAS | 8.33 | 4.12 | 50
2355 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Moyna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000774/2024-2025 | 297/MD | 29/01/2025 | 45 | MOMTAJ ALI | 52.13 | 0 | 0
2356 | Malda Division | Malda Mechanical Division | Augmentation of Head Work site Pump House at MOYNA Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000885/2024-2025 | 1124/MD | 21/03/2025 | 45 | M/S /FAIZUL HAQUE BISWAS | 2.06 | 0 | 100
2357 | Malda Division | Malda Mechanical Division | Augmentation of Pump House-2 at MOYNA Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000886/2024-2025 | 1125/MD | 21/03/2025 | 45 | M/S /FAIZUL HAQUE BISWAS | 2.02 | 0 | 100
2358 | Malda Division | Malda Mechanical Division | Augmentation of ensure proper functioning of 450 M³ capacity 20 Mtr. staging height RCC Over Head Reservoir of MOYNA Water Supply scheme under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000888/2024-2025 | 1127/MD | 21/03/2025 | 45 | HIND CO-OPERATIVA LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 9.24 | 0 | 0
2359 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | RTOR000062/2025-2026 | 5591/MD | 30/10/2025 | 0 | Resource Division | 2.77 | 0 | 0
2360 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | RTOR000167/2023-2024 | 248/MD | 10/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
2361 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- IV of Moyna, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | BILL/03690/2023-2024 | BP-2023-24-673 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.28 | 0 | 0
2362 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning & Trial operation of electro-mechanical components at T/W no III & IV of Source Augmentation Moyna Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016347) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000689/2023-2024 | 2764/MLMD | 14/08/2023 | 180 | MUKHERJEE ART CENTRE | 22.53 | 17.89 | 79
2363 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Sabdalpur Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(Kaliachak-lll)(2nd Call) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | ORD/000022/2023-2024 | 984/MAAD | 06/06/2023 | 607 | MOTI RAHAMAN | 168.03 | 0 | 55
2364 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Head Work Site of Sabdalpur Piped Water supply scheme of Southern Sector in the disrtict of Malda(Kaliachak-III). (2nd Call) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | ORD/000055/2023-2024 | 964/MAAD | 31/05/2023 | 45 | ASHIS CONSTRUCTION | 7.66 | 6.34 | 100
2365 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at 2nd Site of Sabdalpur Piped Water supply scheme of Southern Sector in the disrtict of Malda (Kaliachak-III). (2nd Call) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | ORD/000056/2023-2024 | 965/MAAD | 31/05/2023 | 45 | ABHIJIT PAUL | 7.65 | 5.78 | 100
2366 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Sabdulpur Piped Water Supply Scheme of Southern Sector under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda.(Kaliachak-III) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | ORD/000057/2023-2024 | 966/MAAD | 31/05/2023 | 487 | ABHIJIT CONSTRUCTION | 5 | 4 | 100
2367 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System & others allied works at Sukdevpur under Sabdalpur Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte.(Kaliachak-III) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | ORD/000058/2023-2024 | 967/MAAD | 31/05/2023 | 90 | KRISHNENDU DUTTA | 49.45 | 0 | 0
2368 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Sabdulpur Piped Water Supply scheme at Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (3rd Call) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | ORD/000220/2023-2024 | 1708/MAAD | 20/09/2023 | 650 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 222.96 | 40.85 | 65
2369 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of Distribution System & others allied works at Sabdalpur under Sabdalpur Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte. (Kaliachak-III) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | ORD/000225/2023-2024 | 1741/MAAD | 26/09/2023 | 522 | M/S ALISA CONSTRUCTION | 64.67 | 44.17 | 15
2370 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | RTOR000008/2023-2024 | 630/MAAD | 05/04/2023 | 0 | Resource Division | 166.19 | 0 | 0
2371 | Malda Mechanical | Malda Arsenic Area W/S Division | ERECTION OF NEW HTOH LINE FOR SABDALPUR PH1 UNDER GOLAPGANJ CCC UNDER MALDA DISTRICT | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | BILL/03562/2023-2024 | BP-2023-24-588 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 3.1 | 0 | 0
2372 | Malda Mechanical | Malda Arsenic Area W/S Division | ERECTION OF HTOH FOR SABDALPUR PH 2 UNDER GOLAPGANJ CCC UNDER MALDA DISTRICT | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | BILL/03563/2023-2024 | BP-2023-24-587 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 2.45 | 0 | 0
2373 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Sabdalpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017775) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | ORD/000658/2023-2024 | 2686/MLMD | 11/08/2023 | 879 | DAS ENTERPRISE. | 76.87 | 0 | 20
2374 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at Head Work Site,2nd tubewell site , C.C road from existing road to Head works Site and Land Development Work for HWS ,Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission(JJM & Jal Swapna), Laying of rising main from Tube Well Site to HWS & including supply of all specials & valves for Sabdulpur Piped Water Supply scheme at Kaliachak-III Development Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | ORD/000253/2024-2025 | 14/MAAD | 03/01/2025 | 60 | M/S AMIT KUMAR GUPTA | 89.63 | 0 | 0
2375 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Sabdulpur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | ORD/001901/2023-2024 | 3004364396 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 6.59 | 6.59 | 100
2376 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Sabdulpur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-III | ORD/001902/2023-2024 | 3004364409 | 31/07/2023 | 90 | W.B.S.E.D.C.LTD | 5.14 | 5.14 | 100
2377 | Malda Division | Malda Mechanical Division | Laying of distribution pipe line from 3rd pump house to Malipakar mosque in connection with source Augmentation of Malipakar Piped Water Supply Scheme at Harishchandrapur-II Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000123/2025-2026 | 2475/MD | 28/05/2025 | 90 | DEY CONSTRUCTIONS | 17.98 | 0 | 100
2378 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube Well site of Malipakar Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000176/2024-2025 | 2951/MD | 10/06/2024 | 30 | BINA CONSTRUCTION | 9.07 | 0 | 0
2379 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-II) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000569/2022-2023 | 760/MD | 17/02/2023 | 30 | J. M. CONSTRUCTION | 5.95 | 5.58 | 100
2380 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-III) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000572/2022-2023 | 763/MD | 17/02/2023 | 30 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 8.87 | 8.46 | 100
2381 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000582/2024-2025 | 5616/MD | 06/11/2024 | 30 | SUN INFINITY | 1.2 | 0 | 100
2382 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-I) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000734/2022-2023 | 1213/MD | 21/03/2023 | 45 | S & G CONSTRUCTION | 20.67 | 20.32 | 100
2383 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Malipakar Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000752/2022-2023 | 1300/MD | 23/03/2023 | 45 | A.K. AGENCY | 4.18 | 4.18 | 98
2384 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 200mm. Dia. x 150mm. Big dia Tube Well 143 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of MALIPAKAR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000781/2022-2023 | 1439/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.2 | 7.64 | 100
2385 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Malipakar, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/02470/2023-2024 | BP-2023-24-394 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 9.61 | 0 | 0
2386 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Malipakar Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte.(TSM/016606) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000575/2023-2024 | 2624/MLMD | 10/08/2023 | 601 | SUBRATA KUMAR DAS. | 11.44 | 10.04 | 100
2387 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 45m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Dakhin Brindabanbati Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000320/2024-2025 | 3968/MD | 07/08/2024 | 359 | GOBINDA ENTERPRISE | 18.62 | 0 | 100
2388 | Malda Division | Malda Mechanical Division | Replacement of 200 mm dia. (all through)Tubewell No:-2 (75 M Deep by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at DAKSHIN BRINDABANBATI Water Supply Scheme of Habibpur Malda Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000461/2024-2025 | 4816/MD | 13/09/2024 | 30 | JOY GURU ENTERPRISE | 6.9 | 0 | 0
2389 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for DAKSHIN BRINDABANBATI Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000703/2022-2023 | 1161/MD | 20/03/2023 | 555 | M/S JHA CONSTRUCTION | 77.26 | 72.14 | 100
2390 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000726/2022-2023 | 1200/MD | 21/03/2023 | 45 | SURAJIT MONDAL | 4.16 | 3.99 | 100
2391 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. All through) Tube Well No - 3 (75.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at DAKSHIN BRINDABANBATI Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000773/2022-2023 | 1431/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 6.72 | 5.16 | 100
2392 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House,PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at DAKSHIN BRINDABANBATI Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000879/2024-2025 | 1118/MD | 21/03/2025 | 178 | ACHARYYA CONSTRUCTION | 9.3 | 0 | 0
2393 | Malda Division | Malda Mechanical Division | Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for DAKSHIN BRINDABANBATI Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000982/2023-2024 | 977/MD | 04/03/2024 | 45 | M/S JHA CONSTRUCTION | 44.56 | 13.58 | 85
2394 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Dakhin Brindabanbati Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/001026/2023-2024 | 1252/MD | 15/03/2024 | 535 | ACHARYYA CONSTRUCTION | 9.59 | 0 | 10
2395 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | RTOR000063/2025-2026 | 5592/MD | 30/10/2025 | 0 | Resource Division | 2.77 | 0 | 0
2396 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Dakshin Brindabanbati, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | BILL/02485/2023-2024 | BP-2023-24-427 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.65 | 0 | 0
2397 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Dakshin Brindabanbati Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/005686) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000568/2023-2024 | 2619/MLMD | 10/08/2023 | 541 | KUNDU CONSTRUCTION. | 10.61 | 10.57 | 90
2398 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Bamongram) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000376/2022-2023 | 268/MAAD | 15/02/2023 | 90 | BEE GEE CONSTRUCTION | 29.06 | 25.87 | 100
2399 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Alinagar ) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000381/2022-2023 | 239/MAAD | 09/02/2023 | 90 | M/S MOON LIGHT CONSTRUCTION & CO. | 32.97 | 30.12 | 100
2400 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Bholaichak ) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000382/2022-2023 | 240/MAAD | 09/02/2023 | 90 | FUTURE | 32.98 | 32.96 | 100
2401 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Narayanpur) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000383/2022-2023 | 241/MAAD | 09/02/2023 | 90 | M/S PARIMAL DAS | 33.02 | 32.51 | 100
2402 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Uttar Laxmipur ) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000384/2022-2023 | 243/MAAD | 09/02/2023 | 90 | DISHERY ENGINEERS CO OP SOCIETY LTD. | 32.96 | 29.67 | 100
2403 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Sattari ) Distribution Zone of Nothern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000385/2022-2023 | 242/MAAD | 09/02/2023 | 506 | SUBHAS CHANDRA KESHARI | 32.99 | 21.58 | 70
2404 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. of Bholaichak ,Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000105/2023-2024 | 3004305025/quot/03 | 29/05/2023 | 90 | W.B.S.E.D.C.LTD | 1.83 | 1.83 | 0
2405 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. of Uttar Laxmipur,Southern Zone ,Mothabari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000106/2023-2024 | 3004298515/quot/03 | 19/05/2023 | 90 | W.B.S.E.D.C.LTD | 1.83 | 1.83 | 0
2406 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. of NARAYANPUR Distribution Zone, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000291/2023-2024 | 3004364587 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.32 | 4.32 | 100
2407 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. of Alinagar Distribution Zone, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/000304/2023-2024 | 3004365949 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 1.8 | 1.8 | 100
2408 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Utar Laxmipur Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/001123/2022-2023 | 454/MLMD | 16/03/2023 | 180 | EASTERN INDIA SALES & SERVICE. | 62.77 | 60.58 | 100
2409 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Bamangram Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/001137/2022-2023 | 536/MLMD | 22/03/2023 | 180 | DEY ENTERPRISE.. | 62.79 | 60.59 | 100
2410 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Narayanpur Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/001138/2022-2023 | 537/MLMD | 22/03/2023 | 180 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 62.75 | 60.56 | 100
2411 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Bholaichak Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/001155/2022-2023 | 538/MLMD | 22/03/2023 | 919 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION. | 61.76 | 53.49 | 96
2412 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Alinagar Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/001156/2022-2023 | 539/MLMD | 22/03/2023 | 180 | DEY ENTERPRISE [HOWRAH] | 62.34 | 60.14 | 100
2413 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Sattari Distribution Zone within Malda Arsenic Area Water Supply Scheme (Northern Sector) under Malda Mechanical Division PHE Dte. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/001157/2022-2023 | 540/MLMD | 22/03/2023 | 180 | M/S P.P. ELECTRICALS | 62.79 | 60.59 | 96
2414 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge of Sattari Distribution Zone, Rathbari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/001532/2023-2024 | 3004371435 | 31/07/2023 | 90 | W.B.S.E.D.C.LTD | 1.22 | 1.22 | 100
2415 | Malda Mechanical | Malda Arsenic Area W/S Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/003453/2023-2024 | 845/MLMD | 21/02/2024 | 61 | NITAI PANDEY | 0.78 | 0.77 | 100
2416 | Malda Mechanical | Malda Arsenic Area W/S Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-03,Junior Engineer-04,Junior Engineer-II,Junior Engineer-III,Junior Engineer-IV | ORD/003482/2023-2024 | 916/MLMD | 28/02/2024 | 61 | SUBRATA SAHA | 0.78 | 0 | 100
2417 | Malda Ars Area W/S Division |  | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site at Deonapur Piped Water Supply Scheme at Kaliachak-lll Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. |  |  | ORD/000092/2023-2024 | 1376/MAAD | 13/07/2023 | 60 | TROYEE | 5 | 0 | 0
2418 | Malda Ars Area W/S Division |  | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Deonapur Piped Water supply scheme (Head Work Site) of Kaliachak -III Block under Malda Arsenic Area water Supply Division in the disrtict of Malda. |  |  | ORD/000094/2023-2024 | 1377/MAAD | 13/07/2023 | 45 | MD. TALEB ALI | 7.65 | 5.97 | 100
2419 | Malda Ars Area W/S Division |  | Laying of Distribution System for and other allied works at Ainul Hut under Deonapur Piped Water supply scheme of Kaliachak-III Block of Southern Sector at under Malda Arsenic Area W/S Division, P.H.E. Dte. |  |  | ORD/000095/2023-2024 | 1378/MAAD | 13/07/2023 | 60 | USHA ENTERPRISE | 80.37 | 66.6 | 84
2420 | Malda Ars Area W/S Division |  | Laying of Distribution System for and other allied works at Bakrabad Char under Deonapur Piped Water supply scheme of Southern Sector at under Malda Arsenic Area W/S Division, P.H.E. Dte. (Kaliachak-III). |  |  | ORD/000099/2023-2024 | 1379/MAAD | 13/07/2023 | 152 | A. B. CONSTRUCTION | 57.65 | 41.26 | 80
2421 | Malda Ars Area W/S Division |  | Laying of Distribution System for and other allied works at Thakur Das Mandalpara under Deonapur Piped Water supply scheme of Southern Sector at under Malda Arsenic Area W/S Division, P.H.E. Dte. (Kaliachak-III). |  |  | ORD/000100/2023-2024 | 1380/MAAD | 13/07/2023 | 535 | BANIK BROTHERS | 95.3 | 78.42 | 100
2422 | Malda Ars Area W/S Division |  | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Deonapur Piped Water supply scheme (2ND Site) of Kaliachak -III Block under Malda Arsenic Area water Supply Division in the disrtict of Malda. (2nd Call) |  |  | ORD/000101/2023-2024 | 1381/MAAD | 13/07/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.65 | 4.89 | 100
2423 | Malda Ars Area W/S Division |  | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Deonapur Piped Water supply scheme (3RD Site) of Kaliachak -III Block under Malda Arsenic Area water Supply Division in the disrtict of Malda.(2nd Call) |  |  | ORD/000102/2023-2024 | 1382/MAAD | 13/07/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.64 | 5.05 | 100
2424 | Malda Ars Area W/S Division |  | Route servey & design for prepration of DPR of Deonapur, Saidpur & Mobarakpur Piped Water Supply Scheme at Kaliachak - III & Kaliachak - II Development Block under Malda Arsenic Area W/S Division, PHE Dte. in the district of Malda. |  |  | ORD/000250/2023-2024 | 1764/MAAD | 30/09/2023 | 15 | FUTURE | 0.99 | 0.99 | 100
2425 | Malda Ars Area W/S Division |  | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Deonapur Piped Water supply scheme of Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. (2ND Call) |  |  | ORD/000257/2023-2024 | 1991/MAAD | 02/11/2023 | 455 | WATER TECH | 216.09 | 0 | 75
2426 | Malda Ars Area W/S Division |  | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 3rd Tube Well site of Deonapur Piped Water Supply Scheme at Kaliachak-lll Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. |  |  | ORD/000390/2023-2024 | 1375/MAAD | 13/07/2023 | 107 | MADHUMITA ENTERPRISE | 4.99 | 4.16 | 100
2427 | Malda Ars Area W/S Division |  | Construction of 700 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Deonapur Piped Water Supply scheme at Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. |  |  | ORD/000265/2023-2024 | 3025/MAAD | 07/12/2023 | 634 | BANIK BROTHERS | 299.38 | 46.62 | 60
2428 | Malda Ars Area W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 625/MAAD | 05/04/2023 | 0 | Resource Division | 190.2 | 0 | 0
2429 | Malda Mechanical |  | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I, II & III and Arsenic Iron Removal Plant at Deonapur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018102) |  |  | ORD/000666/2023-2024 | 2691/MLMD | 11/08/2023 | 1075 | GHOSH BROTHERS... | 82.34 | 0 | 0
2430 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Deonapur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | ORD/001903/2023-2024 | 3004364426 | 31/07/2023 | 90 | W.B.S.E.D.C.LTD | 6.35 | 6.35 | 100
2431 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Deonapur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | ORD/001904/2023-2024 | 3004364419 | 31/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.24 | 4.24 | 100
2432 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Deonapur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | ORD/001905/2023-2024 | 3004364433 | 31/07/2023 | 90 | W.B.S.E.D.C.LTD | 5.51 | 5.51 | 100
2433 | Malda Division |  | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | BILL/00851/2023-2024 | BP-2023-24-461 | 02/02/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 0.05 | 0 | 0
2434 | Malda Division |  | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | BILL/01128/2023-2024 | BP-2023-24-603 | 28/03/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 4.28 | 0 | 0
2435 | Malda Division |  | Construction of Boundary Wall at 2nd Tubewell site of Morgram Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000159/2024-2025 | 2934/MD | 10/06/2024 | 157 | M/S SRINJOYEE | 7.11 | 0 | 100
2436 | Malda Division |  | Construction of Boundary Wall at 3rd Tubewell site of Morgram Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000160/2024-2025 | 2935/MD | 10/06/2024 | 156 | M/S SRINJOYEE | 7.1 | 3.27 | 100
2437 | Malda Division |  | Construction of Boundary Wall at head work site of Morgram Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000202/2024-2025 | 2989/MD | 11/06/2024 | 416 | NEOGI ENTERPRISE | 25.32 | 0 | 67
2438 | Malda Division |  | Design, Fabrication, Supplying, Installing, Commissioning and 3 (three) months Trial Run of 100 m³/hr. capacity of Iron Elimination Plant (Pressure Type) with provision of polishing unit and Construction of 3.60 mtr. X 3.00 mtr. Blower room of Head Work Site of MORGRAM Water Supply Scheme of Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. |  |  | ORD/000227/2025-2026 | 4232/MD | 29/08/2025 | 60 | NEOGI ENTERPRISE | 34.98 | 0 | 0
2439 | Malda Division |  | Formal work order for the work of Implementation of MORGRAM Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000370/2023-2024 | 3107/MD | 10/08/2023 | 900 | NEOGI ENTERPRISE | 664.04 | 374.77 | 70
2440 | Malda Division |  | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Car-2) (Period from 01/09/2025 to 31/12/2025). |  |  | ORD/000507/2025-2026 | 4153/MD | 28/08/2025 | 122 | SINGH BROTHERS | 0.57 | 0 | 0
2441 | Malda Division |  | Additional laying for Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000593/2024-2025 | 5627/MD | 06/11/2024 | 30 | RAY CONSTRUCTION CO. | 6.94 | 6.6 | 100
2442 | Malda Division |  | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000606/2023-2024 | 4110/MD | 10/10/2023 | 397 | RAY CONSTRUCTION CO. | 20.07 | 0.3 | 100
2443 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Morgram Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000639/2024-2025 | 5918/MD | 26/11/2024 | 45 | NEOGI ENTERPRISE | 81.8 | 0 | 0
2444 | Malda Division |  | Erection of Property board related to Jal Jeevan Mission works of Sanjail, Meherpur, Aihorani, Morgram, Mahishbathani & Jatradanga PWSS under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000968/2024-2025 | 657/MD | 19/02/2025 | 7 | PRITAM ENTERPRISE | 0.83 | 0 | 100
2445 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000037/2025-2026 | 2823/MD | 11/06/2025 | 0 | Resource Division | 11.61 | 0 | 0
2446 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 238/MD | 10/01/2024 | 0 | Resource Division | 16.12 | 0 | 0
2447 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 810/MD | 21/02/2024 | 0 | Resource Division | 66.34 | 0 | 0
2448 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Morgram, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03509/2023-2024 | BP-2023-24-529 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 12.58 | 0 | 0
2449 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Morgram, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03510/2023-2024 | BP-2023-24-530 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 10.78 | 0 | 0
2450 | Malda Mechanical |  | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Morgram, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte |  |  | BILL/03511/2023-2024 | BP-2023-24-531 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.07 | 0 | 0
2451 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Morgram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/018419) |  |  | ORD/000752/2023-2024 | 2818/MLMD | 17/08/2023 | 1168 | MERCURY ENGINEERING COMPANY. | 36.65 | 17.98 | 87
2452 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of TULSHIHATTA ZONE-II Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000038/2023-2024 | 1885/MD | 08/05/2023 | 962 | MANIK CHANDRA SAHA | 276.32 | 111.69 | 71
2453 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 2 of Tulshihatta Zone-II Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000073/2025-2026 | 2266/MD | 21/05/2025 | 45 | M/S GLOBAL ENTERPRISE | 4.34 | 0 | 100
2454 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep of Tube Well No. 1 at Tulsihatta Zone-II of Harischandrapur - I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000456/2023-2024 | 3397/MD | 31/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 10.81 | 10.59 | 96
2455 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep of Tube Well No. 2 at Tulsihatta Zone-II of Harischandrapur - I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000457/2023-2024 | 3398/MD | 31/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 10.81 | 10.79 | 95
2456 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Tulshihata Zone-II Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000618/2024-2025 | 5742/MD | 20/11/2024 | 452 | M/S BABLU ENTERPRISE | 25.14 | 0 | 75
2457 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Tulshihatta Zone-II Piped Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000690/2021-2022 | 655/MD | 22/03/2022 | 15 | M/S SOBHA & CO. | 3.27 | 3.24 | 1
2458 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Tulshihatta Zone-II Water Supply Scheme under Harishchandrtapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000757/2024-2025 | 75 | 13/01/2025 | 45 | M/S BABLU ENTERPRISE | 24.37 | 0 | 0
2459 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000033/2023-2024 | 1806/MD | 27/04/2023 | 0 | Resource Division | 17.43 | 0 | 0
2460 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000128/2023-2024 | 98/MD | 05/01/2024 | 0 | Resource Division | 6.9 | 0 | 0
2461 | Malda Mechanical | Malda Mechanical Division | New service connection at TULSHIHATA PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03207/2024-2025 | BP-2024-25-640 | 06/02/2025 | 0 | W.B.S.E.D.C.LTD | 3.73 | 0 | 0
2462 | Malda Mechanical | Malda Mechanical Division | New service connection at TULSHIHATA PWSS Zone II T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03760/2023-2024 | BP-2023-24-729 | 28/03/2024 | 0 | W.B.S.E.D.C.LTD | 7.47 | 0 | 0
2463 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning of electro-mechanical components at T/W no. I of Tulshihata (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011277) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000699/2023-2024 | 2774/MLMD | 14/08/2023 | 1136 | SOVA ENTERPRISE. | 7.87 | 6.92 | 88
2464 | Malda Division | Chanchal Sub-Division | Submission of Bill for Hire Charges & HSD & Mobil charges of Vehicle No. - WB61A/3084 for the month of April 2023 | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00234/2023-2024 | BP-2023-24-115 | 20/07/2023 | 0 | SHYAMAL KUMAR MAITRA | 0.31 | 0 | 0
2465 | Malda Division | Chanchal Sub-Division | Submission of bill for hire charges & HSD & Mobil charges of vehicle No. WB61A/3084 for the month of May-2023. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00294/2023-2024 | BP-2023-24-147 | 10/08/2023 | 0 | SHYAMAL KUMAR MAITRA | 0.36 | 0 | 0
2466 | Malda Division | Chanchal Sub-Division | Bill for reimbursement of cost of Diesel and Mobile in respect of hired Vehicle Car No. WB65C/6570 for the month of July2023. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00369/2023-2024 | BP-2023-24-195 | 07/09/2023 | 0 | UTTAM KUMAR GHOSH | 0.4 | 0 | 0
2467 | Malda Division | Chanchal Sub-Division | Soil Investigation and design of substructure for Over Head Reservoirs for MALATIPUR Piped Water Supply Scheme at Chanchal-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00489/2022-2023 | BP-2022-23-198 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
2468 | Malda Division | Chanchal Sub-Division | Diesel driven Vehicle as casual hiring basis for Monitoring of Works as and when called for on daily basis | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00765/2024-2025 | BP-2023-24-392 | 04/12/2024 | 0 | PRASENJIT GHOSH | 0.28 | 0 | 0
2469 | Malda Division | Chanchal Sub-Division | Augmentation Pump House and Boundary Wall of Malatipur Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000130/2025-2026 | 2492/MD | 28/05/2025 | 75 | CHARU CONSTRUCTION | 16.65 | 0 | 0
2470 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Malatipur Pipe Water Supply Scheme at Chanchal-II Block in the District of Malda under Malda Division P.H.E. Dte. (2ND Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000132/2022-2023 | 1788/MD | 01/08/2022 | 823 | M/S MAA TARA CONSTRUCTION | 300.02 | 208.69 | 85
2471 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Malatipur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000166/2025-2026 | 2879/MD | 17/06/2025 | 60 | SAHA CONSTRUCTION | 56.44 | 0 | 0
2472 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000169/2025-2026 | 7811/MD | 11/06/2025 | 60 | HANNAN BUILDERS PVT. LTD. | 130.04 | 0 | 0
2473 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Construction of 400 M3 Capacity OHR with FHTC (Mouza-Harishpara, Kashipara and Gobindapara) of MALATIPUR Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000311/2023-2024 | 2914/MD | 31/07/2023 | 520 | DEEP CONSTRUCTION | 183.27 | 104.05 | 100
2474 | Malda Division | Chanchal Sub-Division | Erection of Property board related to Jal Jeevan Mission works of Kshempur & Malatipur GP under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000947/2024-2025 | 636/MD | 19/02/2025 | 7 | BIDYUT MAHALDAR | 0.82 | 0 | 0
2475 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000007/2022-2023 | 1207/MD | 24/05/2022 | 0 | Resource Division | 0.61 | 0 | 0
2476 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000012/2024-2025 | 3925/MD | 06/08/2024 | 0 | Resource Division | 8.01 | 0 | 0
2477 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000035/2023-2024 | 1801/MD | 27/04/2023 | 0 | Resource Division | 0.59 | 0 | 0
2478 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000138/2023-2024 | 113/MD | 05/01/2024 | 0 | Resource Division | 8.6 | 0 | 0
2479 | Malda Mechanical | Chanchal Sub-Division | Supply, delivery, installation and commissioning of electro-mechanical components at T/W no. I of Augmentation of Malatipur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008173) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000247/2023-2024 | 2264/MLMD | 18/07/2023 | 90 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 11.11 | 7.55 | 68
2480 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- III of Malatipur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008173) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000255/2023-2024 | 2228/MLMD | 18/07/2023 | 120 | EMCON. | 12.51 | 0 | 0
2481 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- II of Malatipur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008173) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001098/2022-2023 | 415/MLMD | 14/03/2023 | 120 | PABITRA MANDAL | 10.28 | 10.11 | 100
2482 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Perapur Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000020/2025-2026 | 1612/MD | 30/04/2025 | 180 | MANIK CHANDRA SAHA | 97.83 | 0 | 0
2483 | Malda Division |  | Construction of Boundary Wall at Head Work site of Perapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000154/2024-2025 | 2923/MD | 10/06/2024 | 751 | GHOSH CONSTRUCTION | 23.72 | 3.47 | 70
2484 | Malda Division |  | Formal work order for the work of Implementation of PERAPUR Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000358/2023-2024 | 3016/MD | 08/08/2023 | 813 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 838.31 | 146.49 | 10
2485 | Malda Division |  | Laying of Distribution of UPVC Pipeline of PERAPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000898/2024-2025 | 1214/MD | 25/03/2025 | 310 | BANIK BROTHERS | 66.48 | 0 | 0
2486 | Malda Division |  | Construction of Boundary Wall at 2nd Tubewell site of Perapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/001034/2023-2024 | 1260/MD | 15/03/2024 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 7.65 | 0 | 0
2487 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000024/2025-2026 | 2811/MD | 11/06/2025 | 0 | Resource Division | 19.79 | 0 | 0
2488 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 234/MD | 10/01/2024 | 0 | Resource Division | 17.65 | 0 | 0
2489 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 812/MD | 21/02/2024 | 0 | Resource Division | 54.03 | 0 | 0
2490 | Malda Mechanical |  | QUOTATION PAYMENT FOR PH NO 2 OF PERAPUR W/S SCHEME UNDER AIHO CCC UNDER MALDA DISTRICT |  |  | BILL/00174/2025-2026 |  | 11/04/2025 | 0 | W.B.S.E.D.C.LTD | 3.52 | 0 | 0
2491 | Malda Mechanical |  | QUOTATION PAYMENT FOR PH NO 1 OF PERAPUR W/S SCHEME UNDER AIHO CCC UNDER MALDA DISTRICT |  |  | BILL/00175/2025-2026 |  | 11/04/2025 | 0 | W.B.S.E.D.C.LTD | 7.86 | 0 | 0
2492 | Malda Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Perapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015903) |  |  | ORD/000494/2023-2024 | 2565/MLMD | 04/08/2023 | 937 | GHOSH BROTHERS... | 29.98 | 0 | 0
2493 | Malda Mechanical |  | : QUOTATION PAYMENT FOR CHARIANANTPUR SCHEME UNDER GOLAPGANJ CCC UNDER THE DISTRICT OF MALDA |  |  | BILL/02387/2025-2026 |  | 24/09/2025 | 0 | W.B.S.E.D.C.LTD | 7.07 | 0 | 0
2494 | Malda Mechanical |  | QUOTATION PAYMENT FOR SAHABAJPUR SCHEME UNDER GOLAPGANJ CCC UNDER THE DISTRICT OF MALDA |  |  | BILL/02388/2025-2026 |  | 24/09/2025 | 0 | W.B.S.E.D.C.LTD | 4.04 | 0 | 0
2495 | Malda Mechanical |  | QUOTATION PAYMENT FOR SHASHNI SCHEME UNDER GOLAPGANJ CCC UNDER THE DISTRICT OF MALDA |  |  | BILL/02389/2025-2026 |  | 24/09/2025 | 0 | W.B.S.E.D.C.LTD | 7.53 | 0 | 0
2496 | Malda Mechanical |  | QUOTATION PAYMENT FOR JAYENPUR SCHEME UNDER GOLAPGANJ CCC UNDER THE DISTRICT OF MALDA |  |  | BILL/02390/2025-2026 |  | 24/09/2025 | 0 | W.B.S.E.D.C.LTD | 13.6 | 0 | 0
2497 | Malda Mechanical |  | QUOTATION PAYMENT FOR MOHABBATPUR SCHEME UNDER GOLAPGANJ CCC UNDER THE DISTRICT OF MALDA |  |  | BILL/02391/2025-2026 |  | 24/09/2025 | 0 | W.B.S.E.D.C.LTD | 8.13 | 0 | 0
2498 | Malda Mechanical |  | QUOTATION PAYMENT FOR PARDEONAPUR SCHEME UNDER GOLAPGANJ CCC UNDER THE DISTRICT OF MALDA |  |  | BILL/02392/2025-2026 |  | 24/09/2025 | 0 | W.B.S.E.D.C.LTD | 6.57 | 0 | 0
2499 | Malda Mechanical |  | QUOTATION PAYMENT FOR SAHILPUR SCHEME UNDER GOLAPGANJ CCC UNDER THE DISTRICT OF MALDA |  |  | BILL/02393/2025-2026 |  | 24/09/2025 | 0 | W.B.S.E.D.C.LTD | 4.04 | 0 | 0
2500 | Malda Mechanical |  | QUOTATION PAYMENT FOR BAIRABONA SCHEME UNDER GOLAPGANJ CCC UNDER THE DISTRICT OF MALDA |  |  | BILL/02394/2025-2026 |  | 24/09/2025 | 0 | W.B.S.E.D.C.LTD | 7.1 | 0 | 0
2501 | Malda Mechanical |  | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 9 nos Distribution Zone (OHR SITE) within Kaliachak Block-II under Augmentation of Malda Arsenic Area W/S scheme (Northern Sector) under Malda Mechanical Division, PHE Dte. |  |  | ORD/000468/2024-2025 | 3851/MLMD | 03/12/2024 | 722 | WEST BENGAL ENGINEERING COMPANY. | 383.69 | 0 | 5
2502 | Malda Mechanical |  | Formal work order for Various electro-mechanical works for existing High Lift pumping station at Dariapur under Augmentation of Malda Arsenic Area W/S scheme (Southern Sector) under Malda Mechanical Division, PHE Dte. |  |  | ORD/000486/2024-2025 | 3911/MLMD | 06/12/2024 | 180 | ALPHA ENTERPRISE. | 153.89 | 0 | 0
2503 | Malda Mechanical |  | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 8 nos Distribution Zone (OHR SITE) within Manikchak Block under Augmentation of Malda Arsenic Area W/S scheme (Northern Sector) under Malda Mechanical Division, PHE Dte. |  |  | ORD/000469/2024-2025 | 3852/MLMD | 03/12/2024 | 180 | MACHINE SUPPLIERS SYNDICATE (P) LTD. | 341.1 | 0 | 0
2504 | Malda Mechanical |  | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 18 nos Distribution Zone (OHR SITE) within Kaliachak Block-III under Augmentation of Malda Arsenic Area W/S scheme (Southern Sector) under Malda Mechanical Division, PHE Dte. |  |  | ORD/000484/2024-2025 | 3894/MLMD | 05/12/2024 | 180 | ORIENTAL ENGINEERING CO. | 765.98 | 0 | 0
2505 | Malda Mechanical |  | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 5 nos Distribution Zone (OHR SITE) within Englishbazar Block under Augmentation of Malda Arsenic Area W/S scheme (Northern Sector) under Malda Mechanical Division, PHE Dte. |  |  | ORD/000545/2024-2025 | 4082/MLMD | 16/12/2024 | 180 | EASTERN INDIA SALES & SERVICE. | 212.97 | 0 | 0
2506 | Malda Mechanical |  | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 7 nos Distribution Zone (OHR SITE) within Kaliachak Block-I under Augmentation of Malda Arsenic Area W/S scheme (Northern Sector) under Malda Mechanical Division, PHE Dte. |  |  | ORD/000546/2024-2025 | 4083/MLMD | 16/12/2024 | 180 | CREATIVE WATER & PROCESS TECH. PVT. LTD. | 298.3 | 0 | 0
2507 | Malda Mechanical |  | Supply, Installation & commissioning of Secondary gaseous chlorination arrangement and other allied works for 2 nos Distribution Zone (OHR site) within Manikchak and English bazar Block under Augmentation of Malda Arsenic Area Water Supply Scheme (Northern Sector), under Malda Mechanical Division, PHE Dte. |  |  | ORD/001322/2024-2025 | 1084/MLMD | 12/02/2025 | 90 | SHREE BISHNU CONSTRUCTION | 81.51 | 0 | 0
2508 | Malda Division | Malda Mechanical Division | Bill for reimbursement of cost of Diesel and mobil in respect of hired vehicle Ambassador Car No.- WB-65/D2727 For the month of January, February and March 2023. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00336/2023-2024 |  | 22/08/2023 | 0 | ARUN KUMAR DAS | 0.96 | 0 | 0
2509 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 750 M3 Capacity OHR with Soil Investigation and FHTC of KHARBA Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000063/2023-2024 | 2020/MD | 18/05/2023 | 954 | SOVAN KUMAR ROY | 355.8 | 68.83 | 40
2510 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying distribution pipe line of KHARBA and it's adjoining mouzas Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte. Govt of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000068/2023-2024 | 2033/MD | 19/05/2023 | 90 | HANNAN BUILDERS PVT. LTD. | 430.15 | 384.15 | 80
2511 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000171/2024-2025 | 2946/MD | 10/06/2024 | 478 | M/S RAKHI ENTERPRISE | 8.66 | 0 | 100
2512 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube Well site of Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000172/2024-2025 | 2947/MD | 10/06/2024 | 30 | M/S GHOSH ENTERPRISE | 8.66 | 0 | 0
2513 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000219/2024-2025 | 3040/MD | 13/06/2024 | 30 | SOVAN KUMAR ROY | 24.8 | 0 | 0
2514 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of KHARBA Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000481/2022-2023 | 1127/MD | 20/03/2023 | 45 | ANUKUL CHANDRA DAS | 6.52 | 6.15 | 95
2515 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of KHARBA Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000482/2022-2023 | 1128/MD | 20/03/2023 | 45 | M/S FOUR STAR CONSTRUCTION | 4.2 | 0 | 100
2516 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 160 Mtr. Deep Big dia Tube well (2 Nos.) at KHARBA Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000676/2022-2023 | 1140/MD | 20/03/2023 | 30 | DUTTA ENTERPRISE | 21.12 | 18.31 | 95
2517 | Malda Division | Malda Mechanical Division | Resinking of 200mm (all through) Big dia. Tube Well of 130m Deep at 3rd Tube well site of Kharba PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000789/2024-2025 | 354/MD | 30/01/2025 | 60 | ABHIJIT PAUL | 9.07 | 0 | 99
2518 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Kharba PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000901/2023-2024 | 274/MD | 11/01/2024 | 45 | SABITA CONSTRUCTION COMPANY | 4.17 | 0 | 98
2519 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep at Head Work Site at Kharba under Chanchal-I under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000902/2023-2024 | 275/MD | 11/01/2024 | 45 | A. L. ENGINEERING SOLUTION | 10.64 | 9.12 | 95
2520 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Kharba and Mahanandapur GP under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000944/2024-2025 | 633/MD | 19/02/2025 | 7 | RABIUL ISLAM | 0.75 | 0 | 100
2521 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for KHARBA Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000963/2023-2024 | 716/MD | 09/02/2024 | 598 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 14.87 | 4.43 | 80
2522 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000038/2025-2026 | 2815/MD | 11/06/2025 | 0 | Resource Division | 17.03 | 0 | 0
2523 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000070/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 88.29 | 0 | 0
2524 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000116/2023-2024 | 86/MD | 05/01/2024 | 0 | Resource Division | 16.23 | 0 | 0
2525 | Malda Mechanical | Malda Mechanical Division | New service connection at KHARBA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( CHANCHAL c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/01931/2024-2025 | BP-2024-25-472 | 28/08/2024 | 0 | W.B.S.E.D.C.LTD | 4.04 | 0 | 0
2526 | Malda Mechanical | Malda Mechanical Division | New service connection at KHARBA PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Chanchal c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/01932/2024-2025 | BP-2024-25-473 | 28/08/2024 | 0 | W.B.S.E.D.C.LTD | 4.6 | 0 | 0
2527 | Malda Mechanical | Malda Mechanical Division | New service connection at kharba w/s supply sch. under EE/MLMD PHE DTE Dist. malda (chanchal c.c.c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/03548/2023-2024 | BP-2023-24-561 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.27 | 0 | 0
2528 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Augmentation of Kharba Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011882) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000263/2023-2024 | 2223/MLMD | 18/07/2023 | 1164 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 42.98 | 31.15 | 90
2529 | Malda Division |  | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. |  |  | ORD/000161/2020-2021 | 2714/MD | 10/11/2020 | 30 | NEOGI ENTERPRISE | 66.16 | 81.97 | 100
2530 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Dakshinpaka command area of MAHANANDAPUR Water Supply Scheme at Chanchal-I Block under Malda Division PHE Dte. |  |  | ORD/000363/2023-2024 | 3052/MD | 09/08/2023 | 30 | M/S AYUSH BUILDERS | 7.85 | 7.85 | 100
2531 | Malda Division |  | Extension of UPVC pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Dakshinpaka command area of MAHANANDAPUR Water Supply Scheme at Chanchal-I Block under Malda Division PHE Dte. |  |  | ORD/000365/2023-2024 | 3054MD | 09/08/2023 | 30 | M/S SRINJOYEE | 4.65 | 4.63 | 100
2532 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000034/2025-2026 | 2814/MD | 11/06/2025 | 0 | Resource Division | 7.59 | 0 | 0
2533 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 36/MD | 04/01/2024 | 0 | Resource Division | 1.58 | 0 | 0
2534 | Malda Division | Malda Sadar Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Purba Binodpur, JL. No. 44, G.P.-Pandua of PURBA BINODPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer |  | ORD/000139/2020-2021 | 2449/MD | 12/10/2020 | 30 | A. B. CONSTRUCTION | 11.75 | 21.72 | 0
2535 | Malda Division | Malda Sadar Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer |  | ORD/000159/2020-2021 | 2712/MD | 10/11/2020 | 45 | NIRENDRA NATH KUNDU | 77.09 | 70.11 | 0
2536 | Malda Division | Malda Sadar Sub-Division | Material Requisition To Resource Division | Sri Biswadip Sengupta, Assistant Engineer |  | RTOR000006/2025-2026 | 2517/MD | 29/05/2025 | 0 | Resource Division | 10.69 | 0 | 0
2537 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000130/2020-2021 | 1066/MAAD | 14/10/2020 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 25.23 | 47.08 | 1
2538 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN CHANDIPUR Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000140/2020-2021 | 1121/MAAD | 09/11/2020 | 30 | BHOLANATH CONSTRUCTION | 57.22 | 109.94 | 0
2539 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipeline &Construction of Pavement & others Allied Work at Charianantapur W/S Scheme under Malda Arsenic Area W/S Divn.PHE. Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000208/2021-2022 | 1060/MAAD | 03/08/2021 | 45 | BANIK BROTHERS | 4.78 | 0.06 | 0
2540 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ramchandrapur Water Supply Scheme (Habitation- Ramnathpur) English Bazar Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-I,Junior Engineer-IV | ORD/000370/2021-2022 | 2007/MAAD | 28/12/2021 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.38 | 5.75 | 1
2541 | Malda Division | RWS Malda Sub-Division | Submission of Bill for Hire Charges & HSD & Mobil charges of Vehicle No. - WB 04-H-8254 for the month of MAY, JUNE, JULY 2023 under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | BILL/00314/2023-2024 | BP-2023-24-157 | 18/08/2023 | 0 | SHABNAM ARA | 1.18 | 0 | 0
2542 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Augmentation of Bulbulchandi Piped water supply scheme for the work of Geotechnical Study,construction of 700 Cum RCC OHR,Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Habibpur Block in the District of Malda under Malda Division, PH Engg Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000006/2022-2023 | 1125/MD | 19/05/2022 | 365 | ACQUA CONSTRUCTION CONSORTIUM | 551.54 | 503 | 85
2543 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 110 Mtr. Deep Big dia Tube well (1 Nos.) at BULBULCHANDI Water Supply Scheme under Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000015/2023-2024 | 1672/MD | 18/04/2023 | 30 | A. L. ENGINEERING SOLUTION | 8.95 | 8.64 | 100
2544 | Malda Division | RWS Malda Sub-Division | Shifting of existing water pipeline of different dia (OD) HDPE Pipeline in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) due to New Culvert Construction along the road under command area of AUGMENTATION of BULBULCHANDI Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000144/2025-2026 | 2682/MD | 04/06/2025 | 45 | ACQUA CONSTRUCTION CONSORTIUM | 5.61 | 0 | 0
2545 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection, Dismentling of Concrete road & Restoration and Laying of Rising Main including Specials & Valves for Bulbulchandi Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000162/2025-2026 | 2761/MD | 09/06/2025 | 60 | ACQUA CONSTRUCTION CONSORTIUM | 86.98 | 0 | 0
2546 | Malda Division | RWS Malda Sub-Division | Dismentling of Concrete road and Construction the same at different places of road connecting to LDS of BULBULCHANDI Water Supply Scheme ( Mouza - Bulbulchandi, Soladanga) at Habibpur Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000302/2024-2025 | 3448/MD | 11/07/2024 | 45 | ACQUA CONSTRUCTION CONSORTIUM | 47.09 | 0 | 90
2547 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) and Laying of 90 mm dia (OD) HDPE Pipeline under command area of AUGMENTATION of BULBULCHANDI Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000617/2024-2025 | 5741/MD | 20/11/2024 | 45 | MILLENNIUM ENTERPRISE | 86.38 | 0 | 0
2548 | Malda Division | RWS Malda Sub-Division | Repairing of boundary wall and Land Development work corresponding to Tube Well No. 3 at BULBULCHANDI Piped Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000947/2023-2024 | 657/MD | 08/02/2024 | 45 | M/S GHOSH CONSTRUCTION | 2.5 | 2.49 | 100
2549 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | RTOR000003/2022-2023 | 1105/MD | 17/05/2022 | 0 | Resource Division | 81.12 | 0 | 0
2550 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | RTOR000025/2025-2026 | 2826/MD | 11/06/2025 | 0 | Resource Division | 28.92 | 0 | 0
2551 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | RTOR000041/2022-2023 | 1586/MD | 28/03/2023 | 0 | Resource Division | 6.43 | 0 | 0
2552 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | RTOR000086/2025-2026 | 5553/MD | 29/10/2025 | 0 | Resource Division | 30.36 | 0 | 0
2553 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Augmentation of Bulbulchandi Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008161) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000256/2023-2024 | 2229/MLMD | 18/07/2023 | 120 | SUDIP DEY | 14.67 | 9.18 | 20
2554 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- II of Bulbulchandi Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008161) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000257/2023-2024 | 2230/MLMD | 18/07/2023 | 604 | JOY MAA SANTOSHI ENTERPRISE. | 8.02 | 6.49 | 86
2555 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- III of Bulbulchandi Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008161) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/001099/2022-2023 | 596/MLMD | 30/03/2023 | 120 | PABITRA MANDAL | 10.76 | 10.73 | 70
2556 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA)at Balutola,Akandabaria,Charkatola,Pakakot,Umakanta,Nowda,Ramnagar,Domaichak ,Naldahari&Choyantola under command area of Bholaichak Water Supply Scheme Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000052/2022-2023 | 826/MAAD | 28/04/2022 | 60 | BANIK BROTHERS | 75.53 | 74.82 | 1
2557 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of UPVC pipe line 110mm,90mm&75mm dia at Bholaichak Raghunathtola, Domaichak Nayatola, Natun Shiv mandir para, Sahabajpur Budhamore, Sahabajpur Ghosh para,horismandal para balufaranad Sardaha & others Allied works at Bholaichak W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000053/2022-2023 | 827/MAAD | 28/04/2022 | 45 | GOBINDA ENTERPRISE | 21.46 | 21.44 | 1
2558 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Akandabaria, Chakdomai & Umakantatola under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000059/2022-2023 | 911/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.71 | 4.69 | 1
2559 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Bahirbona,Milik sultanpur under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000060/2022-2023 | 912/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.67 | 4.66 | 1
2560 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Suknagar,Fatepur under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000061/2022-2023 | 913/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.74 | 4.72 | 1
2561 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Fetepur Chaipara,Nowda under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000062/2022-2023 | 914/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.81 | 4.8 | 1
2562 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at balutola,Kazichak & Srinibashpur under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000255/2022-2023 | 1833/MAAD | 27/09/2022 | 30 | BANIK BROTHERS | 4.4 | 4.38 | 1
2563 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Balufara,Banstola & Charkatola under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000256/2022-2023 | 1834MAAD | 27/09/2022 | 30 | BANIK BROTHERS | 4 | 3.99 | 1
2564 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Ragunath Tola,Attaramtola& Ramdhantola under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000257/2022-2023 | 1835MAAD | 27/09/2022 | 30 | BANIK BROTHERS | 4.04 | 4.02 | 1
2565 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
2566 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bholaichak Water Supply Scheme (Bholaichak, Pakakot, Chakdomai, Sahabajpur Sailapur, Golapganj, Larchak, Chaklalu, Fatepur) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000378/2021-2022 | 1994/MAAD | 27/12/2021 | 90 | BANIK BROTHERS | 128.52 | 128.21 | 1
2567 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2022 to 31.12.2022) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | ORD/000566/2021-2022 | 2042/MAAD | 29/12/2021 | 365 | M/S PARIMAL DAS | 3.85 | 2.46 | 1
2568 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | RTOR000008/2022-2023 | 1340/MAAD | 18/07/2022 | 0 | Resource Division | 7.01 | 0 | 0
2569 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-III | RTOR000011/2021-2022 | 195/MAAD | 11/02/2022 | 0 | Resource Division | 38.57 | 0 | 0
2570 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Sattari under Sattari water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000091/2022-2023 | 965/MAAD | 11/05/2022 | 15 | SUDIP DEY | 4.82 | 4.8 | 1
2571 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Mobarakpur , Basantapur under Sattari water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000092/2022-2023 | 966/MAAD | 11/05/2022 | 15 | SUDIP DEY | 4.74 | 4.72 | 1
2572 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of HDPE pipe 20mm dia at Madapur , Masjidpara under Sattari water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000093/2022-2023 | 967/MAAD | 11/05/2022 | 15 | SUDIP DEY | 2.11 | 2.11 | 1
2573 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000170/2023-2024 | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 30
2574 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sattari Mouza of Sattari Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-IV | ORD/000351/2021-2022 | 1763/MAAD | 24/11/2021 | 60 | SUDIP DEY | 37.57 | 37.36 | 1
2575 | Malda Division | Malda Mechanical Division | Soil Investigation and design of substructure for Over Head Reservoirs for ARIDANGA ZONE-I Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/00488/2022-2023 | BP-2022-23-197 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
2576 | Malda Division | Malda Mechanical Division | Soil Investigation and design of substructure for Over Head Reservoirs for ARIDANGA ZONE-II Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/00490/2022-2023 | BP-2022-23-199 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
2577 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 900 M³ Capacity OHR with FHTC of Aridanga Zone-I Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000005/2023-2024 | 1572/MD | 10/04/2023 | 365 | USHA ENTERPRISE | 338.37 | 180.21 | 92
2578 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 400 M³ Capacity OHR with FHTC of ARIDANGA ZON-II Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000014/2023-2024 | 1649/MD | 13/04/2023 | 628 | UTTAM KUMAR GHOSH | 173.92 | 112.75 | 93
2579 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 4th Tube Well site of Araidanga Zone-I Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000027/2022-2023 | 1306/MD | 01/06/2022 | 30 | J. M. CONSTRUCTION | 4.76 | 0 | 0
2580 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01 (One) No. 250mm. Dia. x 150mm. Big dia. Tube Well 120 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Araidanga (Zone-I)Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000047/2022-2023 | 1396/MD | 14/06/2022 | 21 | SNEHASISH GHOSH | 6.91 | 0 | 0
2581 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Aridanga Zone-II Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000083/2025-2026 | 2281/MD | 21/05/2025 | 120 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 19.52 | 0 | 0
2582 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Araidanga (Zone-I) Pipe Water Supply Scheme at Ratua-II Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000131/2022-2023 | 1784/MD | 01/08/2022 | 60 | USHA ENTERPRISE | 282.55 | 280.52 | 100
2583 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of ARAIDANGA (Zone-II) Pipe Water Supply Scheme at Ratua-II Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000133/2022-2023 | 1789/MD | 01/08/2022 | 60 | SUBHAS CHANDRA KESHARI | 163.59 | 137.51 | 1
2584 | Malda Division | Malda Mechanical Division | Construction of Pump House (5.40 mtr.X 3.60 mtr) at Head Work Site of Augmentation of Aridanga Zone-I Piped Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000139/2024-2025 | 2890/MD | 07/06/2024 | 45 | A.K. AGENCY | 6.57 | 0 | 90
2585 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of Distribution pipe line in connection with Augmentation of Araidanga Zone-I ( node from J-69 to J-172, J-73 to 240, J-81 to 331, J-172 to J-73, 240 to J-191, 331 to J-69) Pipe Water Supply Scheme at Ratua-II Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000144/2022-2023 | 1932/MD | 23/08/2022 | 15 | SUBRATA SAHA | 6.17 | 6.17 | 1
2586 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Araidanga Zone-I Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000168/2025-2026 | 5795/MD | 13/11/2025 | 60 | M/S JHA CONSTRUCTION | 110.7 | 0 | 0
2587 | Malda Division | Malda Mechanical Division | Continuation work order for the work of Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Revisional Transport authority for office of the SE/NBC-II under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000590/2022-2023 | 1248/NBC-II | 14/11/2022 | 180 | TARUN KUMAR BHATTACHARYA | 3.79 | 2.59 | 78
2588 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of NIJGANPARANPUR under Araidanga Zone-II Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000723/2023-2024 | 4772/MD | 05/12/2023 | 45 | J. M. CONSTRUCTION | 12.15 | 12.06 | 70
2589 | Malda Division | Malda Mechanical Division | Additional Laying Distribution of UPVC Pipeline of Augmentation of ARAIDANGA ZONE-I Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000745/2023-2024 | 5248/MD | 22/12/2023 | 45 | M/S JHA CONSTRUCTION | 31.99 | 31.91 | 80
2590 | Malda Division | Malda Mechanical Division | Additional Laying Distribution of UPVC Pipeline of Augmentation of ARAIDANGA ZONE-II Piped Water Supply Scheme at Ratua-II Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000746/2023-2024 | 5250/MD | 22/12/2023 | 45 | M/S KUNDU CONSTRUCTION | 25.79 | 23.62 | 80
2591 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of ARAIDANGA ZONE-I Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000747/2023-2024 | 5249/MD | 22/12/2023 | 45 | CHARU CONSTRUCTION | 20.19 | 37.23 | 75
2592 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of ARIDANGA ZONE-II Piped Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000792/2022-2023 | 1476/MD | 30/03/2023 | 30 | UTTAM KUMAR GHOSH | 11.04 | 10.61 | 75
2593 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of ARIDANGA ZONE-I Piped Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000793/2022-2023 | 1477/MD | 30/03/2023 | 30 | CHARU CONSTRUCTION | 11.09 | 10.18 | 0
2594 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Village Uportola, Namotola, Radhanagar, Chunakhali and Paranpur under Aridanga Zone-II Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000880/2023-2024 | 155/MD | 08/01/2024 | 45 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 12.15 | 8.94 | 70
2595 | Malda Division | Malda Mechanical Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Car-2) (Period from 01/02/2025 to 31/07/2025). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001037/2024-2025 | 377/MD | 31/01/2025 | 181 | SUBRATA SAHA | 0.86 | 0 | 0
2596 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000013/2022-2023 | 1872/MD | 16/08/2022 | 0 | Resource Division | 88.26 | 0 | 0
2597 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000014/2025-2026 | 2805/MD | 11/06/2025 | 0 | Resource Division | 11.73 | 0 | 0
2598 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000027/2023-2024 | 1606/MD | 11/04/2023 | 0 | Resource Division | 31.54 | 0 | 0
2599 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000046/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 124.23 | 0 | 0
2600 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000087/2025-2026 | 5554/MD | 29/10/2025 | 0 | Resource Division | 11.73 | 0 | 0
2601 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000108/2023-2024 | 38/MD | 04/01/2024 | 0 | Resource Division | 1.85 | 0 | 0
2602 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000180/2023-2024 | 778/MD | 20/02/2024 | 0 | Resource Division | 1.23 | 0 | 0
2603 | Malda Division | Malda Mechanical Division | Placement of fund against the work for road restoration work for laying of pipe line for Aridanga Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | VCH/001010/2022-2023 | BP-2022-23-98 | 23/11/2022 | 0 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.67 | 0 | 0
2604 | Malda Mechanical | Malda Mechanical Division | Supply, delivery, installation, commissioning and trial operation of electro-mechanical components of Augmentation of Araidanga Water Supply Scheme (Zone-I) TW no IV and external illumination works at Head Works Site(Zone-I&II) in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008180) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000238/2023-2024 | 2255/MLMD | 18/07/2023 | 120 | DAS CONSTRUCTION | 19.75 | 10.22 | 52
2605 | Malda Mechanical | Malda Mechanical Division | Hiring of Inspection vehicle (Diesel driven) for official use of AE-II for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000781/2021-2022 | 1490/MLMD | 24/08/2021 | 6 | SUBRATA SAHA | 0.86 | 0 | 1
2606 | Malda Mechanical | Malda Mechanical Division | Supply and delivery of Calcium hypochlorite tablets at Araidanga & adjacent water supply schemes in the district of Malda under Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000891/2021-2022 | 1667/MLMD | 22/09/2021 | 12 | DEY ENTERPRISE.. | 0.89 | 0.89 | 1
2607 | Malda Mechanical | Malda Mechanical Division | Modification & upgradation of electro-mechanical installation work at Pump House no.- I, Zone- I of Araidanga water supply scheme in the district of Malda under Malda Mechanical; Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001125/2021-2022 | 306 /MLMD | 22/02/2022 | 30 | M/S MANABESH ROY | 7.87 | 7 | 1
2608 | Malda Mechanical | Malda Mechanical Division | Modification & upgradation of electro-mechanical installation work at Pump House no.- II, Zone- I of Araidanga water supply scheme in the district of Malda under Malda Mechanical; Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001126/2021-2022 | 307 /MLMD | 22/02/2022 | 30 | ANIMA ENTERPRISE | 7.91 | 7.41 | 1
2609 | Malda Mechanical | Malda Mechanical Division | Modification & upgradation of electro-mechanical installation work at Pump House no.- I, Zone- II of Araidanga water supply scheme in the district of Malda under Malda Mechanical; Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001127/2021-2022 | 308 /MLMD. | 22/02/2022 | 30 | DEVI ENTERPRISE... | 8.26 | 7.76 | 1
2610 | Malda Mechanical | Malda Mechanical Division | Claim for purchase of fuel for hiring of inspection vehicle (diesel driven for official) Use month of November, 2021 to September,2022, of issuance of Fuel & Lubricant to Vehicles bearing nos i) W.B-65-C 8851 ii) W.B-65-C 4392, iii) W.B-65-D 5401 for the office of the Executive Engineer,Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001419/2021-2022 | 1808/MLMD | 26/10/2021 | 30 | SHAKTI FILLING STATION | 0.62 | 0 | 1
2611 | Malda Division | RWS Malda Sub-Division | Augmentation work of Construction of Boundary Wall at Head Work site of MAHISHBATHANI Water Supply Scheme under Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000008/2025-2026 | 2411/MD | 27/05/2025 | 75 | M/S EHAN ENTERPRISE | 10.94 | 0 | 0
2612 | Malda Division | RWS Malda Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 135m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Maheshpur Water Supply Scheme of Englishbazar Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000157/2024-2025 | 2926/MD | 10/06/2024 | 295 | MERCURY ENGINEERING COMPANY | 47.11 | 0 | 18
2613 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and laying of 90 mm OD diameter UPVC Pipeline under command area of Augmentation of Maheshpur Piped Water Supply Scheme at Englishbazar Dev. Block in the District Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000196/2025-2026 | 3630/MD | 24/07/2025 | 60 | M/S STAR INDIA CONSTRUTION | 70.86 | 0 | 0
2614 | Malda Division | RWS Malda Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 01/07/2025 to 31/12/2025). | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000285/2025-2026 | 3117/MD | 30/06/2025 | 181 | RUQAIYA ENTERPRISE | 0.86 | 0 | 0
2615 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Augmentation of MAHESHPUR Piped water supply scheme for the work of Geotechnical Study,construction of 600 Cum RCC OHR, Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within English Bazar Block under Malda Division PH Engg.Dte. In the District of Malda . | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000421/2022-2023 | 3179/MD | 23/12/2022 | 1271 | M/S NIRAPADA BHATTACHARJEE | 631.46 | 568.82 | 95
2616 | Malda Division | RWS Malda Sub-Division | Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site at Maheshpur PWSS of Englishbazar Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000463/2023-2024 | 3396/MD | 31/08/2023 | 45 | SADHANA CONSTRUCTION | 6.52 | 6.28 | 100
2617 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of 300 mm. Dia. x 200 mm. dia. and 95 Mtr. Deep Big dia Tube well (2 No) at MAHESHPUR Water Supply Scheme under English Bazar Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000603/2022-2023 | 921/MD | 27/02/2023 | 555 | ASHIS CONSTRUCTION | 21.48 | 8.9 | 100
2618 | Malda Division | RWS Malda Sub-Division | Augmentation of Pump House at 2nd Tube Well Site of Maheshpur Water Supply Scheme of Englishbazar Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000709/2024-2025 | 6379/MD | 18/12/2024 | 45 | D CONSTRUCTION | 2.03 | 0 | 100
2619 | Malda Division | RWS Malda Sub-Division | Augmentation of Pump House at 3rd Tube Well Site of Maheshpur Water Supply Scheme of Englishbazar Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000710/2024-2025 | 6380/MD | 18/12/2024 | 45 | DULAL KUMAR BASAK | 1.92 | 0 | 100
2620 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Maheshpur Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000741/2024-2025 | 25/MD | 06/01/2025 | 360 | M/S STAR INDIA CONSTRUTION | 60.76 | 0 | 85
2621 | Malda Division | RWS Malda Sub-Division | Laying of Rising Main including Specials and Valves for MAHESHPUR Piped Water Supply Scheme at Englishbazar Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000914/2023-2024 | 387/MD | 17/01/2024 | 450 | S. N. CONSTRUCTION | 19.15 | 0 | 35
2622 | Malda Division | RWS Malda Sub-Division | Additional Laying of Distribution pipe line of MAHESHPUR Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000915/2023-2024 | 388/MD | 17/01/2024 | 313 | DEBAPRIYA SAHA | 37.78 | 9.95 | 100
2623 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work Site of MAHESHPUR Piped Water Supply Scheme at Englishbazar Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000916/2023-2024 | 378/MD | 17/01/2024 | 288 | M/S SRINJOYEE | 15.94 | 12.54 | 100
2624 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000028/2023-2024 | 1810/MD | 27/04/2023 | 0 | Resource Division | 28.61 | 0 | 0
2625 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000049/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 28.61 | 0 | 0
2626 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000188/2023-2024 | 823/MD | 21/02/2024 | 0 | Resource Division | 17.76 | 0 | 0
2627 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Maheshpur, Mokdumpur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000863/2023-2024 | 3004405173 | 28/08/2023 | 90 | W.B.S.E.D.C.LTD | 7.66 | 7.66 | 100
2628 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation and commissioning of electro-mechanical components at T/W no. I of Augmentation of Maheshpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/005106) | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/001675/2023-2024 | 2262/MLMD | 18/07/2023 | 592 | SUDIP DEY | 12.42 | 11.26 | 100
2629 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation and commissioning of electro-mechanical components at T/W no. II of Augmentation of Maheshpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/002486/2023-2024 | 808/MLMD | 15/02/2024 | 862 | BEE GEE CONSTRUCTION. | 12.42 | 9.73 | 35
2630 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 700 M3 Capacity OHR with Soil Investigation and FHTC of Kushida Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000009/2023-2024 | 1569/MD | 10/04/2023 | 1252 | SUBHAS CHANDRA KESHARI | 333.31 | 122.89 | 65
2631 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Kushida Pipe Water Supply Scheme at Harishchandrapur-I Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000011/2023-2024 | 1568/MD | 10/04/2023 | 1087 | SUBHAS CHANDRA KESHARI | 434.18 | 288 | 87
2632 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 3rd Tube Well site of Kushida Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000028/2022-2023 | 1195/MD | 24/05/2022 | 31 | RANJIT ADHIKARY | 4.8 | 0 | 0
2633 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 4th Tube Well site of Kushida Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000029/2022-2023 | 1196/MD | 24/05/2022 | 31 | RAHANUL ALAM | 4.8 | 0 | 1
2634 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 150m Deep at 4th Tubewell site of Kushida PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000282/2024-2025 | 3233/MD | 28/06/2024 | 90 | SAUDAGAR INDIA | 10.14 | 0 | 95
2635 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 150m Deep at 3rd Tubewell site of Kushida PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000305/2024-2025 | 3451/MD | 11/07/2024 | 227 | SAUDAGAR INDIA | 10.14 | 0 | 90
2636 | Malda Division | Malda Mechanical Division | Replacement of existing tube well by 200x200 mm dia. and 180 M Deep by Big Dia Tube Well at 2nd Tube Well site of Khusida Piped Water Supply Scheme at Harishchandrapur-I block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000464/2024-2025 | 4818/MD | 13/09/2024 | 215 | SAUDAGAR INDIA | 10.91 | 0 | 100
2637 | Malda Division | Malda Mechanical Division | Replacement of existing tube well by 200x200 mm dia. and 180 M Deep by Big Dia Tube Well at Head Work site of Kusida Piped Water Supply Scheme at Harishchandrapur-I block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000465/2024-2025 | 4819/MD | 13/09/2024 | 141 | SAUDAGAR INDIA | 10.91 | 0 | 100
2638 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kushida Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000760/2024-2025 | 81 | 13/01/2025 | 45 | SUBHAS CHANDRA KESHARI | 78.22 | 0 | 0
2639 | Malda Division | Malda Mechanical Division | Laying of Distribution pipe line in connection with Augmentation of Uttar Rampur Mouza (JL-36) under KUSHIDA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000763/2023-2024 | 5324/MD | 27/12/2023 | 60 | SUBHAS CHANDRA KESHARI | 91.57 | 18.97 | 50
2640 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at KUSHIDA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000936/2023-2024 | 581/MD | 02/02/2024 | 417 | RAHANUL ALAM | 4.19 | 0 | 95
2641 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 4 at KUSHIDA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000937/2023-2024 | 582/MD | 02/02/2024 | 273 | SR ENTERPRISE | 4.19 | 0 | 95
2642 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Khusida, Bhingol, Uttar Harishandrapur, Dakshin Mahendrapur, Konar, Rangaipur PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000956/2024-2025 | 645/MD | 19/02/2025 | 7 | RAHANUL ALAM | 0.95 | 0 | 100
2643 | Malda Division | Malda Mechanical Division | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 06/02/2024 to 30/06/2024). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001221/2023-2024 | 589/MD | 02/02/2024 | 146 | M/S FOUR STAR CONSTRUCTION | 0.71 | 1.47 | 0
2644 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000015/2025-2026 | 2806/MD | 11/06/2025 | 0 | Resource Division | 15.54 | 0 | 0
2645 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000047/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 51.58 | 0 | 0
2646 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000136/2023-2024 | 115/MD | 05/01/2024 | 0 | Resource Division | 13.49 | 0 | 0
2647 | Malda Mechanical | Malda Mechanical Division | New service connection at KUSHIDA PWSS T/W NOIII Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/02717/2024-2025 | BP-2024-25-594 | 10/12/2024 | 0 | W.B.S.E.D.C.LTD | 6.38 | 0 | 0
2648 | Malda Mechanical | Malda Mechanical Division | New service connection at kushida PWSS T/W NO IV Under EE/MLMD PHE DTE DIST. Malda.( KUSHIDA c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/02718/2024-2025 | BP-2024-25-595 | 10/12/2024 | 0 | W.B.S.E.D.C.LTD | 6.11 | 0 | 0
2649 | Malda Mechanical | Malda Mechanical Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000975/2024-2025 | 3517/MLMD | 30/10/2024 | 61 | SUBRATA SAHA | 0.78 | 0 | 100
2650 | Malda Mechanical | Malda Mechanical Division | Supply, installation, and commissioning of electro-mechanical components at T/W no. III & IV of Augmentation of Khusida Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008174) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001799/2023-2024 | 3686/MLMD | 29/11/2023 | 669 | KARMAKAR CONSTRICTION. | 25.1 | 20.64 | 100
2651 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Implementation of PUTIA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000489/2022-2023 | 593/MD | 09/02/2023 | 90 | PARIJAT RAY | 41.34 | 31.49 | 95
2652 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at PUTIA Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000608/2022-2023 | 926/MD | 27/02/2023 | 30 | DUTTA ENTERPRISE | 10.13 | 9.49 | 100
2653 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Putia Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000738/2024-2025 | 57 | 08/01/2025 | 45 | CHOWDHURY CONSTRUCTION | 1.61 | 0 | 0
2654 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Putia, Jagannathpur, Hardamnagar, Daulatnagar, Mihaghat & Bhairabpur PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000959/2024-2025 | 648/MD | 19/02/2025 | 7 | M/S SABANA CONSTRUCTION | 0.82 | 0 | 100
2655 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000006/2024-2025 | 3918/MD | 06/08/2024 | 0 | Resource Division | 0.22 | 0 | 0
2656 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000019/2023-2024 | 1609/MD | 11/04/2023 | 0 | Resource Division | 0.81 | 0 | 0
2657 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Putia, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000296/2023-2024 | 3004353826 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.3 | 3.3 | 100
2658 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Putia Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013011) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000325/2023-2024 | 2327/MLMD | 26/07/2023 | 120 | NEOGI ENTERPRISE. | 13.5 | 9.98 | 78
2659 | Malda Division | RWS Malda Sub-Division | Placement of fund against the work for road restoration for laying pipe line for Bulbulchandi- Katlapukur road from 11.645 KM to 13.904 Km and Nimbari to Harishchandrapur road from 0.00 KM to 0.889 KM under Kadirpur and Chaksukur PWSS under Malda Division,PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/00514/2024-2025 | BP-2024-25-251 | 10/09/2024 | 0 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 14.42 | 0 | 0
2660 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work Site of Chaksukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000626/2024-2025 | 5833/MD | 22/11/2024 | 45 | HANNAN BUILDERS PVT. LTD. | 19.53 | 0 | 0
2661 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Implementation of CHAKSUKUR Piped Water Supply at Habibpur Dev. Block in the District Malda under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000661/2022-2023 | 1035/MD | 13/03/2023 | 1261 | HANNAN BUILDERS PVT. LTD. | 880.48 | 656.61 | 40
2662 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tube well site of Chaksukur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000678/2024-2025 | 6203/MD | 09/12/2024 | 45 | HANNAN BUILDERS PVT. LTD. | 8.68 | 0 | 0
2663 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000006/2023-2024 | 1582/MD | 10/04/2023 | 0 | Resource Division | 17.4 | 0 | 0
2664 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000086/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 25.7 | 0 | 0
2665 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of CHAKSUKUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/02487/2023-2024 | BP-2023-24-422 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.54 | 0 | 0
2666 | Malda Mechanical | RWS Malda Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of CHAKSUKUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/02488/2023-2024 | BP-2023-24-423 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.75 | 0 | 0
2667 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chaksukur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013215) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000311/2023-2024 | 2313/MLMD | 26/07/2023 | 827 | JAL PRAVAHIKA PVT. LTD. | 29.64 | 23.63 | 75
2668 | Malda Division | Malda Mechanical Division | Sinking of 200mm. Dia. all through Big dia Tube well at 3rd Tube Well site (160.00 Mtr. deep) by D.R Rig. Method using P.V.C. pipe including supply of Materials at KHATIL Water Supply Scheme of Bamongola Dev. Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000468/2024-2025 | 4823/MD | 13/09/2024 | 152 | JOY GURU ENTERPRISE | 10.22 | 0 | 100
2669 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for KHATIL Piped Water Supply Scheme at Bamangola Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000511/2022-2023 | 414/MD | 02/02/2023 | 758 | M/S AMIT KUMAR GUPTA | 74.79 | 0 | 100
2670 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Khatil Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000756/2022-2023 | 1304/MD | 23/03/2023 | 45 | A. L. ENGINEERING SOLUTION | 4.18 | 0 | 0
2671 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 150.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at KHATIL Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000774/2022-2023 | 1432/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 7.56 | 7.48 | 100
2672 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Khatil Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000778/2024-2025 | 296/MD | 29/01/2025 | 401 | M/S ROY CONSTRUCTION | 8.52 | 0 | 0
2673 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Khatil Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/001002/2023-2024 | 1181/MD | 14/03/2024 | 30 | M/S EHAN ENTERPRISE | 10.2 | 0 | 0
2674 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Khatil Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/001003/2023-2024 | 1182/MD | 14/03/2024 | 45 | S. N. CONSTRUCTION | 21.18 | 0 | 0
2675 | Malda Mechanical | Malda Mechanical Division | QUOTATION PAYMENT FOR KHATIL T/W III UNDER BAMONGOLA CCC UNDER MALDA DISTRICT | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | BILL/00759/2024-2025 | BP-2024-25-194 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.69 | 0 | 0
2676 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Khatil Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015034) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer | ORD/000382/2023-2024 | 2390/MLMD | 28/07/2023 | 714 | NEOGI ENTERPRISE. | 11.1 | 0 | 20
2677 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Kadirpur Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000024/2023-2024 | 1714/MD | 20/04/2023 | 45 | SHANKAR PRASAD BHAGAT | 8.32 | 7.32 | 100
2678 | Malda Division | Malda Mechanical Division | Laying of Pipeline work and rectification of FHTC at Kadirpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000275/2024-2025 | 3195/MD | 27/06/2024 | 188 | M/S SINHA ENTERPRISE | 31.7 | 0 | 100
2679 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kadirpur Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000642/2024-2025 | 5945/MD | 28/11/2024 | 277 | M/S SINHA ENTERPRISE | 26.03 | 0 | 0
2680 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for KADIRPUR Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000702/2022-2023 | 1160/MD | 20/03/2023 | 45 | M/S AMIT KUMAR GUPTA | 73.06 | 71.19 | 90
2681 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 93.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at KADIRPUR Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000713/2022-2023 | 1171/MD | 20/03/2023 | 30 | ABHIJIT PAUL | 6.23 | 6.23 | 100
2682 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 4 ( 93.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at KADIRPUR Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000714/2022-2023 | 1172/MD | 20/03/2023 | 30 | ABHIJIT PAUL | 6.23 | 6.23 | 100
2683 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at KADIRPUR Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000882/2024-2025 | 1121/MD | 21/03/2025 | 189 | GHOSH CONSTRUCTION | 9.59 | 0 | 100
2684 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | RTOR000088/2025-2026 | 5555/MD | 29/10/2025 | 0 | Resource Division | 5.35 | 0 | 0
2685 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III & IV of Kadirpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016285) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000584/2023-2024 | 2633/MLMD | 10/08/2023 | 180 | TARUN KUMAR DEY | 21.12 | 20.75 | 100
2686 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Kadirpur , Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000783/2023-2024 | 3004397521 | 22/08/2023 | 90 | W.B.S.E.D.C.LTD | 6.08 | 6.08 | 100
2687 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Kadirpur, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000923/2023-2024 | 3004413382 | 05/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.01 | 4.01 | 100
2688 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000195/2024-2025 | 2899/MD | 07/06/2024 | 30 | A. L. ENGINEERING SOLUTION | 2.11 | 0 | 0
2689 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional UPVC Pipe line in connection with Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme at Harishchandrapur II Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000575/2022-2023 | 766/MD | 17/02/2023 | 30 | CHARU CONSTRUCTION | 11.7 | 11.7 | 100
2690 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Uttar Kumedpur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000751/2022-2023 | 1299/MD | 23/03/2023 | 45 | SOFIKUL ISLAM | 4.19 | 4.18 | 95
2691 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 246 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of UTTAR KUMEDPUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000783/2022-2023 | 1441/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 12.03 | 9.88 | 60
2692 | Malda Division | Malda Mechanical Division | Augmentation work of OHR, Pump House and Boundary Wall of Uttar Kumedpur Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000806/2024-2025 | 438/MD | 06/02/2025 | 75 | M/S T. K. CONSTRUCTION | 32.5 | 0 | 0
2693 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Uttar Kumedpur, Dahara, Khopakati, Sultannagar PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000964/2024-2025 | 653/MD | 19/02/2025 | 7 | M/S SABANA CONSTRUCTION | 0.9 | 0 | 100
2694 | Malda Mechanical | Malda Mechanical Division | Quatation for new service connection at Uttar Kumedpur w/s sch. T/W no III UNDER MLMD. Dist Malda. (Harishchandrapur C. C. C) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/03506/2023-2024 | BP-2023-24-526 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 13.78 | 0 | 0
2695 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Uttar Kumedpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte.(TSM/017125) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000580/2023-2024 | 2629/MLMD | 10/08/2023 | 630 | SWAPAN ENTERPRISE, | 11.31 | 0 | 100
2696 | Malda Division | Malda Mechanical Division | Interconnection between new Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Kendua Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000280/2024-2025 | 3231/MD | 28/06/2024 | 521 | M/S /FAIZUL HAQUE BISWAS | 12.28 | 7.36 | 100
2697 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of UPVC pipe line laying with Withdrawing and relaying of DI pipe line for Providing Functional Household Tap Connection (FHTC) in connection to Source Augmentation of Kendua PWSS, Chanchal I Block Malda Division PHE. Dte in The District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000568/2022-2023 | 759/MD | 17/02/2023 | 30 | M/S /FAIZUL HAQUE BISWAS | 15.08 | 14.18 | 100
2698 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Kendua Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000723/2022-2023 | 1197/MD | 21/03/2023 | 45 | RABIUL ISLAM | 4.18 | 4.18 | 100
2699 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well ( 250.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at Kendua Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000768/2022-2023 | 1398/MD | 28/03/2023 | 30 | A. L. ENGINEERING SOLUTION | 12.62 | 12.01 | 100
2700 | Malda Division | Malda Mechanical Division | Augmentation work of OHR, Pump House and Boundary Wall of Kendua Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000857/2024-2025 | 1050/MD | 18/03/2025 | 75 | M/S DAS CONSTRUCTION | 31.92 | 0 | 0
2701 | Malda Mechanical | Malda Mechanical Division | New service connection at KENDUA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( CHANCHAL c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | BILL/01933/2024-2025 | BP-2024-25-471 | 28/08/2024 | 0 | W.B.S.E.D.C.LTD | 7.33 | 0 | 0
2702 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Kendua Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016529) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000733/2023-2024 | 2693/MLMD | 11/08/2023 | 715 | DAS CONSTRUCTION | 10.97 | 8.84 | 100
2703 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 4th Tubewell site of Parameswarpur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000153/2024-2025 | 2922/MD | 10/06/2024 | 30 | M/S BISWAS CONSTRUCTION & CO | 11.18 | 11.15 | 100
2704 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for PARAMESWARPUR Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000737/2022-2023 | 1209/MD | 21/03/2023 | 45 | SOVON KUMAR DAS | 29.32 | 25.32 | 80
2705 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Parameswarpur Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000757/2022-2023 | 1305/MD | 23/03/2023 | 45 | A. L. ENGINEERING SOLUTION | 4.17 | 4.13 | 99
2706 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 (120.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at PARAMESWARPUR Water Supply Scheme of Bamongola Block under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000772/2022-2023 | 1430/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 8.85 | 8.05 | 100
2707 | Malda Division | Malda Mechanical Division | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works at Bamongram, Basara, Parameswarpur, Khatil, Ramnagar & Adatala PWSS under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000940/2024-2025 | 629/MD | 19/02/2025 | 7 | RUQAIYA ENTERPRISE | 0.74 | 0 | 100
2708 | Malda Division | Malda Mechanical Division | Laying of dedicated /Parallel pipe line for better functionality and providing balance FHTC with Supply of Sluice valve and Sluice Valve Chamber for PARAMESHWARPUR Piped Water Supply Scheme at Bamangola Dev. Block in the District Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000965/2025-2026 | 772/MD | 19/02/2026 | 60 | SATTWIK CONSTRUCTION | 16.9 | 0 | 0
2709 | Malda Mechanical | Malda Mechanical Division | QUOTATION PAYMENT FOR Parameswarpur T/W III UNDER BAMONGOLA CCC UNDER MALDA DISTRICT | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | BILL/00760/2024-2025 | BP-2024-25-192 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 5.86 | 0 | 0
2710 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. IV of Parameswarpur Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte. (TSM/016354) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000576/2023-2024 | 2625/MLMD | 10/08/2023 | 541 | SOVON KUMAR DAS. | 12.73 | 12.15 | 100
2711 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Adhna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000082/2025-2026 | 2267/MD | 21/05/2025 | 45 | M/S. B. K. ASSOCIATES | 10.13 | 0 | 0
2712 | Malda Division | Malda Mechanical Division | Replacement of 200 mm dia. all through Big Dia. Tube Well at Head Work site (150m Deep) by D.R. Rig. Method using P.V.C. pipe & filter including supply of materials of ADHNA Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000115/2025-2026 | 2466/MD | 28/05/2025 | 60 | GOBINDA ENTERPRISE | 9.82 | 0 | 0
2713 | Malda Division | Malda Mechanical Division | Sinking of 200 mm (all through) Big Dia. Tube-Well NO-02 (170 ) M Deep by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at ADHNA Water Supply Scheme of Gazol Block under Malda Division, PHE Dte, Govt. of West Bengal | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000458/2024-2025 | 4812/MD | 13/09/2024 | 156 | A. D. D. ASSOCIATES | 10.6 | 0 | 100
2714 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for ADHNA Piped Water Supply Scheme at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000556/2022-2023 | 1181/MD | 21/03/2023 | 30 | GOBINDA ENTERPRISE | 40.5 | 38.42 | 90
2715 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 150.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at ADHNA Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000715/2022-2023 | 1173/MD | 20/03/2023 | 30 | JAYA ENTERPRISE | 7.56 | 7.05 | 100
2716 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Adhna Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000725/2022-2023 | 1199/MD | 21/03/2023 | 45 | M/S GHOSH ENTERPRISE | 4.17 | 4.16 | 100
2717 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House,Pump House No.-2 ,Earth filling and 2 Nos. Boundary wall at ADHNA Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000876/2024-2025 | 1115/MD | 21/03/2025 | 194 | GOBINDA ENTERPRISE | 7.83 | 0 | 0
2718 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000089/2025-2026 | 5533/MD | 29/10/2025 | 0 | Resource Division | 1.54 | 0 | 0
2719 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Source Augmentation Adhna Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016220) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000596/2023-2024 | 2718/MLMD | 14/08/2023 | 180 | JOY ENTERPRISE. | 10.67 | 10.42 | 100
2720 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Adhna PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000778/2023-2024 | 3004387448 | 18/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.51 | 3.51 | 100
2721 | Malda Division | Malda Mechanical Division | Payment for rural road damage pipe line. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | BILL/00804/2024-2025 | BP-2024-25-377 | 18/11/2024 | 0 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 3 | 0 | 0
2722 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Meherpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000021/2025-2026 | 1611/MD | 30/04/2025 | 120 | M/S TRILOCHAN CONSTRUCTION CO | 101.92 | 0 | 0
2723 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at Meherpur Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000137/2024-2025 | 2888/MD | 07/06/2024 | 45 | MAA MANASA CONSTRUCTION | 4.15 | 0 | 0
2724 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of MEHERPUR Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000219/2023-2024 | 2683/MD | 13/07/2023 | 1051 | M/S S. D. ENTERPRISE | 307.58 | 93.42 | 75
2725 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 140 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of aterials at Heads Work Site of MEHERPUR Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000339/2022-2023 | 2511/MD | 03/11/2022 | 30 | A. D. D. ASSOCIATES | 9.34 | 8.84 | 100
2726 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying Distribution pipe line for MEHERPUR and its adjoining mouzas Piped Water Supply at Old Malda Dev. Block in the District Malda under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000660/2022-2023 | 1040/MD | 13/03/2023 | 1205 | GHOSH BROTHERS | 529.66 | 475.92 | 100
2727 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube well site of Meherpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000673/2024-2025 | 6198/MD | 09/12/2024 | 90 | RAJIB MANI | 7.52 | 0 | 0
2728 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Meherpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000674/2024-2025 | 6199/MD | 09/12/2024 | 45 | J. M. CONSTRUCTION | 7.52 | 0 | 0
2729 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | RTOR000062/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 4.83 | 0 | 0
2730 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | RTOR000090/2025-2026 | 5539/MD | 29/10/2025 | 0 | Resource Division | 26.75 | 0 | 0
2731 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Meherpur, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | BILL/00773/2024-2025 | BP-2024-25-190 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.56 | 0 | 0
2732 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Meherpur, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | BILL/00774/2024-2025 | BP-2024-25-191 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 5.84 | 0 | 0
2733 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Meherpur, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | BILL/03513/2023-2024 | BP-2023-24-533 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 18.21 | 0 | 0
2734 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Meherpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011828) | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000323/2023-2024 | 2325/MLMD | 26/07/2023 | 1166 | GHOSH BROTHERS... | 42.91 | 0 | 0
2735 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-III Piped Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000233/2023-2024 | 2708/MD | 14/07/2023 | 1175 | SOVON KUMAR DAS | 355.42 | 82.15 | 18
2736 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-III Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000253/2024-2025 | 3189/MD | 27/06/2024 | 584 | SOVON KUMAR DAS | 27.49 | 0 | 0
2737 | Malda Division | Malda Mechanical Division | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (90 Mtr. Deep) for UTTAR CHANDIPUR ZONE-III Water Supply Scheme at Head Work Site of Manikchak Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000367/2023-2024 | 3056/MD | 09/08/2023 | 480 | A. L. ENGINEERING SOLUTION | 9.16 | 2.32 | 100
2738 | Malda Division | Malda Mechanical Division | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) & rectification work in connection with Jal Jeevan Mission (JJM) at Uttar Chandipur Zone-III Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000875/2024-2025 | 1104/MD | 20/03/2025 | 345 | SOVON KUMAR DAS | 93.26 | 0 | 0
2739 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 74.50M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-III Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000995/2023-2024 | 1279/MD | 15/03/2024 | 681 | M/S DAS CONSTRUCTION | 187.88 | 0 | 0
2740 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000091/2025-2026 | 5547/MD | 29/10/2025 | 0 | Resource Division | 2.31 | 0 | 0
2741 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000093/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 60.79 | 0 | 0
2742 | Malda Mechanical | Malda Mechanical Division | QUOTATION PAYMENT FOR UTTARCHANDIPUR W/S TW NO XIII SCHEME UNDER MANIKCHAK CCC UNDER MALDA DISTRICT | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | BILL/01743/2024-2025 | BP-2024-25-436 | 07/08/2024 | 0 | W.B.S.E.D.C.LTD | 7.9 | 0 | 0
2743 | Malda Mechanical | Malda Mechanical Division | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XIII and Arsenic Iron Removal Plant at Uttar Chandipur (Zone-III) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019388) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000645/2023-2024 | 2681/MLMD | 11/08/2023 | 540 | HANNAN BUILDERS PVT. LTD. | 62.63 | 0 | 40
2744 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work site of Aiho Zone-II Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000299/2024-2025 | 3445/MD | 11/07/2024 | 210 | FUTURE | 22.09 | 0 | 100
2745 | Malda Division | RWS Malda Sub-Division | Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for Aiho Zone-II piped Water Supply scheme of Habibpur Block in the District of Malda under Malda Division, P.H.E.Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000466/2024-2025 | 4821/MD | 13/09/2024 | 45 | FUTURE | 10.04 | 0 | 100
2746 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Distribution system for Augmentation of AIHO ZONE-II Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000555/2022-2023 | 1180/MD | 21/03/2023 | 45 | FUTURE | 81.51 | 81.33 | 34
2747 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Aiho Zone-II Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000619/2024-2025 | 5789/MD | 21/11/2024 | 449 | FUTURE | 39.04 | 0 | 0
2748 | Malda Division | RWS Malda Sub-Division | Construction of 150 cum capacity 20 mtr. Staging height RCC OHR and Providing Household Tap Connection (FHTC) for Augmentation of AIHO ZONE-II Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000703/2023-2024 | 4589/MD | 22/11/2023 | 465 | FUTURE | 90.61 | 40.39 | 60
2749 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Rising main and Construction of Pump houses for Augmentation of AIHO ZONE-II Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000767/2022-2023 | 1396/MD | 28/03/2023 | 704 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 13.01 | 0 | 100
2750 | Malda Division | RWS Malda Sub-Division | Augmentation of 3 Nos. Pump House at AIHO ZONE-2 Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000878/2024-2025 | 1117/MD | 21/03/2025 | 45 | RATAN KARMAKAR | 5.36 | 0 | 0
2751 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at AIHO ZONE-2 Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000985/2023-2024 | 980/MD | 04/03/2024 | 298 | FUTURE | 32.22 | 10.48 | 100
2752 | Malda Division | RWS Malda Sub-Division | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe, Rectification of FHTC & Providing FHTC for AIHO ZONE-II piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, P.H.E.Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000992/2025-2026 | 1048/MD | 06/03/2026 | 60 | FUTURE | 24.85 | 0 | 0
2753 | Malda Division | RWS Malda Sub-Division | Continuation work order for the work of Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/05/2024 to 30/06/2024). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/001218/2023-2024 | 1440/MD | 15/03/2024 | 61 | SHABNAM ARA | 0.29 | 0.79 | 100
2754 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000084/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 11.34 | 0 | 0
2755 | Malda Mechanical | RWS Malda Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & IV and making compund lighting arrangement at Head Work site of Augmentation of Aiho(zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte.(TSM/017677) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Md. Ataur Rahaman, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000585/2023-2024 | 2634/MLMD | 10/08/2023 | 180 | MAA BHABOTARINE ENTERPRISE. | 31.38 | 23.08 | 15
2756 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Design, Fabrication, Supplying, Installation, Commissioning and 3 (three) months Trial Run and 40.00 M³/hr. capacity of Iron Elimination Plants (Pressure type) with provision of polishing unit and Construction of switch room for Arapur Water Supply Scheme at English Bazar Dev Block under Malda Arsenic Area W/S Division. (2nd Call) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000043/2023-2024 | 941/MAAD | 23/05/2023 | 180 | GOBINDA ENTERPRISE | 17.92 | 16.64 | 100
2757 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of Boundary Wall at 3rd Pump House Site, Laying of distribution system and Providing FHTC at Arapur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Part A & Part B) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000246/2024-2025 | 1701/MAAD | 19/11/2024 | 120 | ACHARYYA CONSTRUCTION | 20.59 | 0 | 100
2758 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Arapur Water Supply Scheme (Mouza- Jote, Arapur) extra pipe line at Ganipur, Jote and Ghoshpara village at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000251/2022-2023 | 1829/MAAD | 27/09/2022 | 45 | BANIK BROTHERS | 2.46 | 2.45 | 1
2759 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arapur village under command area of Arapur Water Supply Scheme at Englis Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000381/2023-2024 | 301/MAAD | 11/03/2024 | 30 | GIRIDHARI CONSTRUCTION | 7.9 | 7.67 | 100
2760 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying UPVC pipe at Arapur village for FHTC under Arapur W/S Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000426/2022-2023 | 322/MAAD | 21/02/2023 | 60 | S. N. CONSTRUCTION | 8.05 | 7.98 | 100
2761 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Laying UPVC pipe at Ghoshpara village for FHTC under Arapur W/S Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000427/2022-2023 | 323/MAAD | 21/02/2023 | 60 | M/S RADHA KRISHNA ENTERPRISE | 3.2 | 3.14 | 100
2762 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Arapur village under command area of Arapur Water Supply Scheme at Englis Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000428/2022-2023 | 324/MAAD | 21/02/2023 | 60 | S. R. CONSTRUCTION | 8.42 | 6.25 | 100
2763 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Ghoshpara village under command area of Arapur Water Supply Scheme at Englis Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000429/2022-2023 | 325/MAAD | 21/02/2023 | 60 | S. R. ENTERPRISE | 6.36 | 5.32 | 100
2764 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Construction of 3.60 mtr X 3.00 Mtr. Bore Hole pump house for Tube well no-3 at Arapur Water Supply Scheme of English Bazar Block under Malda Arsenic Area W/S Division, P.H.E.Dte. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000460/2022-2023 | 478/MAAD | 22/03/2023 | 60 | GOALPARA CO OPTV LABOUR CONTRACT AND CONSTN COCIETY LIMITED | 5.32 | 4.66 | 100
2765 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Extension of Pipe line by different dia UPVC pipe for ARAPUR Water Supply Scheme of English Bazar Dev. Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000463/2022-2023 | 552/MAAD | 24/03/2023 | 60 | ACHARYYA CONSTRUCTION | 18.74 | 16.8 | 100
2766 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Sinking of 01 (One) Nos. 250mm. Dia. x 150mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Source Augmentation of Arapur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000479/2022-2023 | 616/MAAD | 31/03/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 7.47 | 5.59 | 100
2767 | Malda Ars Area W/S Division | Malda Arsenic Area W/S Division | Material Requisition To Resource Division | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | RTOR000026/2023-2024 | 1690/MAAD | 15/09/2023 | 0 | Resource Division | 9.79 | 0 | 0
2768 | Malda Mechanical | Malda Arsenic Area W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Souce augmentation of Arapur Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte.(TSM/017481) | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000562/2023-2024 | 2616/MLMD | 10/08/2023 | 180 | S.G.ENTERPRISE | 11.52 | 11.49 | 100
2769 | Malda Mechanical | Malda Arsenic Area W/S Division | W.B.S.E.D.C.LTD Quotation charge at T/W No.III of Arapur , Fulbari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte | Assistant Engineer - II,Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-04,Junior Engineer-IV | ORD/000865/2023-2024 | 3004409400 | 31/08/2023 | 90 | W.B.S.E.D.C.LTD | 4.18 | 4.18 | 100
2770 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Nasipur Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000081/2025-2026 | 2251/MD | 21/05/2025 | 45 | MANAS KUMAR SAHA | 53.59 | 0 | 0
2771 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of NASHIPUR Piped Water Supply Scheme at Ratua-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000236/2023-2024 | 2711/MD | 14/07/2023 | 806 | MANAS KUMAR SAHA | 452.36 | 212.44 | 70
2772 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 4th Tube Well site of Nasipur Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000314/2024-2025 | 3954/MD | 07/08/2024 | 45 | RATAN KARMAKAR | 7.1 | 0 | 0
2773 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 3 at Nashipur Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000948/2023-2024 | 656/MD | 08/02/2024 | 45 | RATAN KARMAKAR | 4.76 | 0 | 0
2774 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 4 at Nashipur Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000949/2023-2024 | 655/MD | 08/02/2024 | 45 | ISMAIL ENTERPRISE | 4.76 | 0 | 0
2775 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Nasipur, Ariadanga Zone-I & II, Pirpur PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000973/2024-2025 | 662/MD | 19/02/2025 | 7 | J. M. CONSTRUCTION | 0.8 | 0 | 0
2776 | Malda Division | Malda Mechanical Division | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 16/02/2024 to 30/06/2024). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/001222/2023-2024 | 717/MD | 09/02/2024 | 136 | M/S TEWARI CONSTRUCTION | 0.64 | 1.31 | 95
2777 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | RTOR000016/2024-2025 | 3992/MD | 08/08/2024 | 0 | Resource Division | 6.16 | 0 | 0
2778 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | RTOR000073/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 50.88 | 0 | 0
2779 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | RTOR000199/2023-2024 | 833/MD | 21/02/2024 | 0 | Resource Division | 12.62 | 0 | 0
2780 | Malda Mechanical | Malda Mechanical Division | New service connection at NASIPUR Pwss pH NO II Under EE/MLMD PHE DTE DIST. Malda.(paranpur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | BILL/03721/2023-2024 | BP-2023-24-705 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.69 | 0 | 0
2781 | Malda Mechanical | Malda Mechanical Division | New service connection at NASIPUR Pwss pH NO I Under EE/MLMD PHE DTE DIST. Malda.(paranpur c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | BILL/03722/2023-2024 | BP-2023-24-706 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 8.02 | 0 | 0
2782 | Malda Mechanical | Malda Mechanical Division | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I, II, III & IV and Arsenic Iron Removal Plant at Nasipur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/011880) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000754/2023-2024 | 2821/MLMD | 17/08/2023 | 1069 | DAS CONSTRUCTION | 79.67 | 42.58 | 57
2783 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Implementation of AIHORANI Piped Water Supply Scheme at Old Malda Dev. Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000834/2022-2023 | 1500/MD | 30/03/2023 | 552 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 37.17 | 16.88 | 90
2784 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Aihorani Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000953/2023-2024 | 650/MD | 08/02/2024 | 45 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 4.3 | 3.01 | 100
2785 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | RTOR000172/2023-2024 | 405/MD | 18/01/2024 | 0 | Resource Division | 0.65 | 0 | 0
2786 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Aihorani, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | BILL/03626/2023-2024 | BP-2023-24-625 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 1.03 | 0 | 0
2787 | Malda Mechanical | Malda Mechanical Division | Supply, installation and commissioning of electro-mechanical components at T/W no. I of Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 households) of Old Malda Block in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/002490/2023-2024 | 810/MLMD | 15/02/2024 | 180 | M/S SABANA CONSTRUCTION | 6.92 | 6.7 | 100
2788 | Malda Division | Malda Mechanical Division | Submission of car hire bill on daily rate hired basis, for Office of the Assistant Engineer, Chanchal Sub-Division, P.H.E. Dte. (Period from 07-12-2022 To 02-01-2023). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | BILL/00380/2023-2024 |  | 05/09/2023 | 0 | SAUDIPTA KUMAR DAS | 0.33 | 0 | 0
2789 | Malda Division | Malda Mechanical Division | Sinking of Tubewell, Laying of Distribution Line, Providing FHTC, Construction of Pump House & Boundary wall at Alinagar Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000144/2024-2025 | 2901/MD | 07/06/2024 | 353 | SUDIP DEY | 83.78 | 0 | 85
2790 | Malda Division | Malda Mechanical Division | Laying of Parallel/ Dedicated Pipeline for better Functionality at Alinagar Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000246/2025-2026 | 4348/MD | 10/09/2025 | 440 | BANIK BROTHERS | 26.97 | 0 | 0
2791 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000505/2024-2025 | 5408/MD | 21/10/2024 | 130 | BANIK BROTHERS | 36.94 | 0 | 100
2792 | Malda Division | Malda Mechanical Division | Bamboo piing, earth filing for protection of pipe line at different places for Alinagar Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000590/2024-2025 | 5624/MD | 06/11/2024 | 30 | BANIK BROTHERS | 8.66 | 0 | 100
2793 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of ALINAGAR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000614/2022-2023 | 940/MD | 27/02/2023 | 1220 | BANIK BROTHERS | 458.54 | 345.34 | 75
2794 | Malda Division | Malda Mechanical Division | Placing of diesel driven vehicle on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000831/2022-2023 | 667/CSD | 29/12/2022 | 365 | SUDIPTA GHOSH | 0.85 | 0.33 | 37
2795 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Alinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000882/2023-2024 | 158/MD | 08/01/2024 | 45 | M/S N. N. ENTERPRISE | 14.51 | 14.51 | 100
2796 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well Site of ALINAGAR Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000980/2023-2024 | 975/MD | 04/03/2024 | 45 | BANIK BROTHERS | 9.13 | 0 | 100
2797 | Malda Division | Malda Mechanical Division | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 12/11/2023 to 09/05/2024=180 Days). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001231/2023-2024 | 4566/MD | 10/11/2023 | 180 | TARUN KUMAR BHATTACHARYA | 0.86 | 1.05 | 0
2798 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | RTOR000145/2023-2024 | 122/MD | 06/01/2024 | 0 | Resource Division | 28.48 | 0 | 0
2799 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Alinagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015847) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/000373/2023-2024 | 2381/MLMD | 28/07/2023 | 702 | M/S. KUNDU CONSTRACTION | 27.37 | 24.36 | 100
2800 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Alinagar, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001888/2023-2024 | 3004496764 | 28/11/2023 | 90 | W.B.S.E.D.C.LTD | 4.45 | 4.45 | 100
2801 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Alinagar , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Md. Ataur Rahaman, Junior Engineer | ORD/001889/2023-2024 | 3004496739 | 28/11/2023 | 90 | W.B.S.E.D.C.LTD | 4.01 | 4.01 | 100
2802 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Implementation of PASCHIM BHAGABANPUR Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000045/2023-2024 | 1995/MD | 17/05/2023 | 1140 | M/S TECHNICO & CO | 568.26 | 398.32 | 90
2803 | Malda Division | Chanchal Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Paschim Bhagabanpur Water Supply Scheme of Chanchal-I Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000318/2024-2025 | 3966/MD | 07/08/2024 | 180 | SHREE BISHNU CONSTRUCTION | 30.26 | 0 | 0
2804 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at 2nd Tube Well site of Paschim Bhagabanpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000446/2024-2025 | 4735/MD | 11/09/2024 | 30 | M/S MADHU CONSTRUCTION | 10.76 | 0 | 15
2805 | Malda Division | Chanchal Sub-Division | Sinking of Tubewell, Laying of Distribution Line, Providing FHTC, Construction of Pump House at Paschim Bhagabanpur Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000484/2024-2025 | 5084/MD | 27/09/2024 | 60 | M/S TEWARI CONSTRUCTION | 92.44 | 0 | 20
2806 | Malda Division | Chanchal Sub-Division | Erection of Property board related to Jal Jeevan Mission works of Mokdampur and Bhagabanpur GP under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000942/2024-2025 | 632/MD | 19/02/2025 | 7 | RABIUL ISLAM | 0.8 | 0 | 100
2807 | Malda Division | Chanchal Sub-Division | Additional Laying Distribution of UPVC pipe line of PASCHIM BHAGABANPUR Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, P.H.E Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000960/2023-2024 | 711/MD | 09/02/2024 | 45 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 2.15 | 2.14 | 90
2808 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000085/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 22.21 | 0 | 0
2809 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000092/2025-2026 | 5548/MD | 29/10/2025 | 0 | Resource Division | 4.98 | 0 | 0
2810 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000117/2023-2024 | 87/MD | 05/01/2024 | 0 | Resource Division | 11.09 | 0 | 0
2811 | Malda Mechanical | Chanchal Sub-Division | Additional quotation for paschim Bhagabanpur ph I DIST- MALDA .(kushida c c c) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00764/2024-2025 | BP-2024-25-204 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 0.1 | 0 | 0
2812 | Malda Mechanical | Chanchal Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of PASCHIM BHAGABANPUR PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/02538/2023-2024 | BP-2023-24-441 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.83 | 0 | 0
2813 | Malda Mechanical | Chanchal Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of PASCHIM BHAGABANPUR PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/02539/2023-2024 | BP-2023-24-442 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.34 | 0 | 0
2814 | Malda Mechanical | Chanchal Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Pascham Bhagabanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013216) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000326/2023-2024 | 2328/MLMD | 26/07/2023 | 1186 | GHOSH BROTHERS... | 28.17 | 23.28 | 86
2815 | Malda Division |  | Quotation for feasibility study report on possibility of setting up a 5.97-MLD capacity, radial collector well on Sub Surface Water based Piped Water Supply Scheme from Tangon River for Fluoride affected areas of Bamangola Block (Mouza- Berul, Jl-63, Near Bamongola Kathuadanga Primary School) towards implementation of water supply project based on Sub surface water of River Tangon. |  |  | BILL/00564/2024-2025 | BP-2024-25-284 | 23/09/2024 | 0 | INDUSTRY INSTITUTE PARTNERSHIP CELL JADAVPUR UNIVERSITY | 30.95 | 0 | 0
2816 | Malda Division |  | Sinking of 200mm (all through) Big dia. Tube Well of 150 m Deep at Tangon river bed of bamongola Sub Surface Water based PWSS for Fluride affected areas of Bamongola Block under Malda Division, P.H.E Dte in the district of Malda. (06 Nos Tube Well) |  |  | ORD/000222/2025-2026 | 4020/MD | 22/08/2025 | 180 | ASHIS CONSTRUCTION | 57.93 | 0 | 0
2817 | Malda Division |  | Formal work order for the work of Surveying, Planning, Designing, Delivery, Erection, Construction, Commissioning and Completion of all civil, electrical and mechanical works including all allied and related works of Sub- Surface Water Based Piped Water Supply Scheme in Bamangola block of Malda district followed by three (3) months trial run and five (05) year operation and maintenance. |  |  | ORD/000584/2023-2024 | 3993/MD | 06/10/2023 | 1183 | ENGINEERING PROJECTS (INDIA) LIMITED (A GOVERNMENT OF INDIA ENTERPRISE) | 12347.61 | 2046.37 | 7
2818 | Malda Division |  | Sinking of 200mm (all through) Big dia. Tube Well of 30.0 m Deep and RCC Structure for hoisting of MS Pipe for Tube well and Platform at Tangon river bed of bamongola Sub Surface Water based PWSS for Fluride affected areas of Bamongola Block under Malda Division, P.H.E Dte in the district of Malda. (10 Nos Tube Well & 20 Nos RCC Structure) |  |  | ORD/000692/2025-2026 | 5922/MD | 26/11/2025 | 120 | ASHIS CONSTRUCTION | 68.99 | 0 | 0
2819 | Malda Division |  | Sinking of 200 mm (all through) Big dia. Tube Well of 150m Deep at Sub Surface Water based PWSS from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block under Malda Division, PHE Dte. Govt. of West Bengal. |  |  | ORD/000713/2024-2025 | 270/MD | 28/01/2025 | 60 | ASHIS CONSTRUCTION | 39.3 | 0 | 0
2820 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 834/MD | 21/02/2024 | 0 | Resource Division | 3626.73 | 0 | 0
2821 | Malda Mechanical |  | Quoation Payment For Bamongola Zone-V, T/W-I Under Bamongola CCC Under the district of Malda. |  |  | BILL/00751/2024-2025 | BP-2024-25-174 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 6.26 | 0 | 0
2822 | Malda Mechanical |  | Quotation Payment For Bamongola Zone-II, T/W-1 Under Bamongola CCC Under the district of Malda. |  |  | BILL/00752/2024-2025 | BP-2024-25-175 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.94 | 0 | 0
2823 | Malda Mechanical |  | Quoation Payment For Bamongola Zone-III, T/W-I Under Bamongola CCC Under the district of Malda. |  |  | BILL/00753/2024-2025 | BP-2024-25-176 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.8 | 0 | 0
2824 | Malda Mechanical |  | Quoation Payment For Bamongola Zone-IV, T/W-I Under Bamongola CCC Under the district of Malda. |  |  | BILL/00754/2024-2025 | BP-2024-25-177 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 6.78 | 0 | 0
2825 | Malda Mechanical |  | Quotation Payment For Bamongola Zone-I, T/W-1 Under Bamongola CCC Under the district of Malda. |  |  | BILL/00755/2024-2025 | BP-2024-25-178 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 7 | 0 | 0
2826 | Malda Mechanical |  | Providing Electro-Mechanical components and Making compound lighting arrangement at Ground water based Piped W/S Scheme for different Distribution Zone at Tangon River site (zone-I & II) and Punarbhaba river site (zone-III,IV & V) under Bamongola Sub Surface Water Based Piped Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. |  |  | ORD/000734/2023-2024 | 2694/MLMD | 11/08/2023 | 1049 | DEY ENTERPRISE.. | 80.84 | 51.91 | 30
Total | [10 empty] | 1018803.03 | 65152.66