## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of villages of Kazisaha,Kapasdanga (village code 315607,315618), under MANIKNAGAR (Zone-J) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000291/2022-2023 | 1805/BD-I | 31/03/2023 | 961 | KAMIRUL SK AND CO. | 259.69 | 0 | 72
2 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kupila (Village code 314741) under Kupila Ground Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723481 (Sl-1) |  |  | ORD/001144/2021-2022 | 3675/MURD | 25/11/2021 | 1588 | M/S. SINHA & SONS | 119.26 | 0 | 75
3 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000015/2021-2022 | 395/A/MURD | 16/02/2022 | 0 | Resource Division | 11.77 | 0 | 0
4 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Malibari (Village code 314569) under Malibari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184027 in the District of Murshidabad. |  |  | ORD/001590/2021-2022 | 307/MURD | 07/02/2022 | 60 | ULTRA CONSTRUCTION. | 31.15 | 28.85 | 0
5 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000046/2021-2022 | 576/MURD | 03/03/2022 | 0 | Resource Division | 1.17 | 0 | 0
6 | Murshidabad Division |  | Additional works for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Muradpur Dair ( Village Code -314651) under Muradpur-Jalangi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723429) |  |  | ORD/000247/2021-2022 | 1681/MURD | 05/07/2021 | 60 | PRANAB KUMAR SAHA | 12.14 | 0 | 0
7 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village MURADPUR DAIR (Village Code 314651) under Muradpur-Jalangi Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block in the District of Murshidabad. |  |  | ORD/000638/2020-2021 | 3033/MURD | 07/12/2020 | 45 | PRANAB KUMAR SAHA | 19.83 | 15.06 | 1
8 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MURADPUR DAIR (Village Code 314651) under MURADPUR JALANGI Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 294 of 21-22 by EE MURD |  |  | VCH/001547/2021-2022 | 373-MSD/21-22 | 15/03/2022 | 0 | PRANAB KUMAR SAHA | 10.13 | 0 | 0
9 | Berhampore Division I | Berhampur Division I | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nasipur (Village code 314186) under Nasipur Zone-I Ground Water based Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division - I, PHE Dte.(Part-III) (Sl-02) | Assistant Engineer-I | JE | ORD/000292/2021-2022 | 1133/BD-I | 06/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 97.21 | 88.6 | 1
10 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Nasipur ( Village code-314186) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Nasipur Ground water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE | ORD/000792/2021-2022 | 2303/BD-I | 28/12/2021 | 30 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 17.79 | 14.29 | 1
11 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of village of Char Mirzapur (village code 315616), under Mirzapur (Zone-H) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000275/2023-2024 | 978/BD-I | 18/10/2023 | 90 | M/S. DAS ENTERPRISE MAHULA, DASPARA, VILL +P.O-GOPINATHPUR, MURSHIDABAD. | 43.31 | 0 | 0
12 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidabad District Under Berhampore Division-I,PHE Dte. in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000110/2024-2025 | 1446/BD-I | 04/09/2024 | 60 | PRANAB KUMAR GHOSH | 32.27 | 0 | 0
13 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mathbarenda (Village code 314480) , Patti Bahadurpur (Village code 314489) Sultanpur (Village code 314490),Madapur (Village code 314482) under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE | ORD/000100/2020-2021 | 166/BD-I | 03/02/2021 | 30 | DECON INDIA | 80.84 | 66.39 | 1
14 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000109/2024-2025 | 1444/BD-I | 04/09/2024 | 60 | BHOWMIK CONSTRUCTION | 18.28 | 0 | 0
15 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000114/2024-2025 | 1434/BD-I | 04/09/2024 | 60 | MOLLA ENTERPRISE | 34.65 | 0 | 0
16 | Berhampore Division I | Berhampur Division I | Formal Work Order for laying of balance portion and relaying of damage portion in different dia on different nodes of UPVC and DI (K-7) pipe line under Gopinathpur (Zone-B) Surface based water supply scheme under uncovered arsenic areas of Beldanga-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. (Phase-I) | Assistant Engineer-II | Junior Engineer-I | ORD/000844/2021-2022 | 100/BD-I | 01/02/2022 | 90 | C.X.CONSTRUCTION & CO. | 119.44 | 0 | 100
17 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangapur, Binkar, Mahisasthali, Gopinathpur, Gopalpur & Pulinda (Village code 315562, 315563, 315564, 315565, 315566 & 315567) under Gopinathpur (Zone-B) Water Supply Scheme of Beldanga -I Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000847/2021-2022 | 103/BD-I | 01/02/2022 | 1390 | DOBAY CONSTRUCTION | 261.58 | 162.27 | 92
18 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Prasadpur,Arazi Mathurapur,Gouripur Khastaluk, Mathurapur & Bele (Village code 314835,314836,314837,314842 & 314843) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000215/2021-2022 | 1013/BD-I | 21/06/2021 | 1440 | M/S. SUKUMAR SINHA | 53.54 | 0 | 100
19 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gauripur (Village code 315412) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000216/2021-2022 | 1014/BD-I | 21/06/2021 | 45 | SARAJIT KUMAR MAJUMDAR | 51.33 | 42.45 | 1
20 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pashchim Gobindapur,Hanribhanga & Biranpur (Village code 314844,314833 & 314834) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000217/2021-2022 | 1015/BD-I | 21/06/2021 | 60 | KAMIRUL SK AND CO. | 71.45 | 64.58 | 1
21 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Begamnagar,Bhartadoba & Palasdanga (Village code 314879,314880 & 314881) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000218/2021-2022 | 1016/BD-I | 21/06/2021 | 60 | KAMIRUL SK AND CO. | 61.91 | 50.82 | 1
22 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gopalnagar,Singa & Banoaripur (Village code 314869,314877 & 314878) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000219/2021-2022 | 1017/BD-I | 21/06/2021 | 60 | ULTRA CONSTRUCTION | 66.11 | 51.85 | 1
23 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
24 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gudhia (Village code 314870) under Begamnagar (Zone-D) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-07) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000501/2021-2022 | 1908/BD-I | 08/10/2021 | 180 | DECON INDIA | 134.39 | 82.51 | 90
25 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kalikapur,Hasnabad & Sashidharpur (Village code 314861,314862 & 314863) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000210/2021-2022 | 1008/BD-I | 21/06/2021 | 701 | M/S JAN MAHAMMAD | 77.98 | 42.16 | 100
26 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dilalpur & Baranda Sibnagar (Village code 314859 & 314860) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000211/2021-2022 | 1009/BD-I | 21/06/2021 | 60 | DECON INDIA | 88.47 | 73.95 | 0
27 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kapasdanga (Village code 314868) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000212/2021-2022 | 1010/BD-I | 21/06/2021 | 60 | M/S JAN MAHAMMAD | 68.61 | 44.6 | 1
28 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rambhadrapur & Gouribag (Village code 314839 & 314838) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000213/2021-2022 | 1011/BD-I | 21/06/2021 | 45 | SANDHAN ADHIKARY | 46.7 | 41.27 | 0
29 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bhatpara,Ramdaspur,Kamalpur & Jafrabad (Village code 314864,314865,314866 & 314867) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000214/2021-2022 | 1012/BD-I | 21/06/2021 | 60 | M/S JAN MAHAMMAD | 68.64 | 55.59 | 1
30 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ransagar, Aliganj,Akherighata ,Chirakuti,Samserganj, Noada,Akbarpur,Sabjikatra, Topkhana, Kadamsarif (Village code 314853,314854,314855,314856,314857,314858,314852,314840 & 314851) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000277/2021-2022 | 1170/BD-I | 15/07/2021 | 60 | ARINDAM MAJUMDAR | 59.21 | 49.86 | 100
31 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2024 to 31.12.2024 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000378/2023-2024 | 1280/BD-I | 27/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 1.81 | 0 | 21
32 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
33 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Aragi Kulgachi (Village code 314471) under Digha Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000097/2020-2021 | 163/BD-I | 03/02/2021 | 20 | SARAJIT KUMAR MAJUMDAR | 33.52 | 0 | 0
34 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Subarna Mrigi (Village code 314473) under Digha Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000189/2020-2021 | 842/BD-I | 23/11/2020 | 90 | PRADIP KUMAR DAS | 25.8 | 19.56 | 0
35 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Subarna Mrigi (Village Code-314473) under Digha Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000209/2020-2021 | 276/ BD-I | 15/02/2021 | 10 | DAS TRADING CO | 4.87 | 0 | 0
36 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area of Harirampur ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte.. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000072/2024-2025 | 1220/BD-I | 29/07/2024 | 30 | PRADIP DAS | 5.61 | 0 | 0
37 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Joyrampur (Village Code-314553) and others under Harirampur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000114/2021-2022 | 916/BD-I | 19/05/2021 | 20 | M/S. M.G. CONSTRUCTION | 4.31 | 2.59 | 0
38 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Harirampur (Village code 314554) under Harirampur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000195/2020-2021 | 974/BD-I | 17/12/2020 | 90 | KAMIRUL SK AND CO. | 22.63 | 42.51 | 1
39 | Berhampore Division I | Berhampur Division I | Laying of new pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Harirampur and others under Harirampur Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000414/2021-2022 | 1452/BD-I | 13/08/2021 | 10 | KAMIRUL SK AND CO. | 4.62 | 2.51 | 1
40 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at AMARKUNDU G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000406/2021-2022 | 248/LSD | 18/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.18 | 0 | 1
41 | Murshidabad Division |  | Extension of UPVC pipeline construction of RCC stand post with platform at Darerdanga under Improvement works of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. |  |  | ORD/001227/2021-2022 | 415/LSD | 27/12/2021 | 30 | SARAJIT KUMAR MAJUMDER | 3.79 | 3.78 | 1
42 | Murshidabad Division |  | Balance and allied works For Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Madhunia (Village code 315022) and under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/001578/2021-2022 | 345/MURD | 11/02/2022 | 60 | S.K. ENTERPRISE (SANDIP GHOSH) | 14.32 | 13.21 | 0
43 | Murshidabad Division |  | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bagore (Village code 315019) and under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/001772/2021-2022 | 817/MURD | 25/03/2022 | 30 | M/S. CHOWDHURY CONSTRUCTION | 12.2 | 11.81 | 0
44 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000045/2021-2022 | 542/MURD | 25/02/2022 | 0 | Resource Division | 2.47 | 0 | 0
45 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE |  |  | VCH/002041/2020-2021 | 489/W | 17/03/2021 | 0 | SAMBHUNATH ROY | 29.21 | 0 | 0
46 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilaspur Nachharerpara (314639) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District (Part-IV) |  |  | VCH/001290/2021-2022 |  | 17/02/2022 | 0 | M/S. UNIQUE BUILDERS | 74.29 | 0 | 0
47 | Murshidabad Division |  | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC |  |  | VCH/002047/2020-2021 | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0
48 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Ramchandrapur ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000141/2024-2025 | 1607/BD-I | 03/10/2024 | 30 | SUJIT CHOWDHURY | 5.13 | 0 | 0
49 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramchandrapur (Village code 314592) under Ramchandrapur Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000221/2020-2021 | 985/BD-I | 17/12/2020 | 60 | SOM CONSTRUCTION AGENCY | 16.15 | 19.07 | 1
50 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paschim Gobindapur (Village code 314448) under Gobra Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000237/2020-2021 | 66/BD-I | 18/01/2021 | 30 | JAHANGIR ALAM | 32.15 | 25.67 | 1
51 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Barbaria (Village code 314462) under Gobra Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000238/2020-2021 | 67/BD-I | 18/01/2021 | 30 | M/S SINHA & SONS | 40.34 | 35.18 | 0
52 | Murshidabad Division |  | Connection of Rising Main at Pump House No. II & Newly Sunk tubewell of Pump House No. I and other allied works under Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad |  |  | ORD/000286/2022-2023 | 275/ISD | 27/06/2022 | 30 | PARTHA PRATIM DAS | 3.74 | 3.62 | 0
53 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Harharia Chak (Village code 314806 ) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005182977 in the District of Murshidabad. (Sl No-06) |  |  | ORD/000434/2021-2022 | 2599/MURD | 25/08/2021 | 1621 | SHYAMAL KUMAR SAHA | 101.35 | 54.94 | 40
54 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION at Sadatpur(VillageCode-315671) ,Chhatiai (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000116/2024-2025 | 1451/BD-I | 04/09/2024 | 30 | K.S.ENTERPRISE (PROP. SAMIM SK.) | 3.55 | 0 | 0
55 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chhatiani (Village code 315673) under Sadhukhali Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000230/2020-2021 | 1045/BD-I | 28/12/2020 | 90 | MS RUBIET HOSSAIN | 43.95 | 39.68 | 0
56 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sadatpur (Village code 315671) under Sadhukhali Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000231/2020-2021 | 1046/BD-I | 28/12/2020 | 60 | MAHATO ENTERPRISE | 4.04 | 0 | 0
57 | Berhampore Division I | Berhampur Division I | Additional Laying works at villages within Dadpur G.P areas to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Sadhukhali Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II | Junior Engineer-II | ORD/000853/2021-2022 | 157/BD-I | 11/02/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 16.17 | 0 | 0
58 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dighirpahar (Village code 314794) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005182977 in the District of Murshidabad. (Sl No-08) |  |  | ORD/000350/2021-2022 | 2503/MURD | 17/08/2021 | 120 | SUJIT KUMAR SAHA | 70.56 | 23.56 | 1
59 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Islampur(CT) (Village code 314805) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005182977 in the District of Murshidabad. |  |  | ORD/000359/2021-2022 | 2506/MURD | 17/08/2021 | 1629 | NAYLA CONSTRUCTION | 109.99 | 0 | 40
60 | Murshidabad Division |  | Restoration work of distribution pipeline by using UPVC pipeline from Nashipur Graveyard to Kathal bariya Jumma Masjid and new construction of street stand post under Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. |  |  | ORD/002075/2021-2022 | 467/ISD | 03/09/2021 | 30 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 4.8 | 4.04 | 0
61 | Murshidabad Division |  | Extension of pipeline at uncovered habitation of Nashipur Biswaspara from Enamul Biswas house to Khalek Biswas house and Rafikul Sk house to Mokbul Mondal house at Nashipur Panthipara under command area of Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. |  |  | ORD/002102/2021-2022 | 469/ISD | 03/09/2021 | 30 | S. DUTTA | 4.7 | 3.56 | 0
62 | Murshidabad Division |  | Balance Retrofitting Work of Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under at Janardanpur & adjoining mouzas (JL NO-147) ( Village Code -315981) from the exiting distribution system of Panchthupi Water Supply Scheme (Ground Water Based) in Burwan Block under Kandi Sub Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | BILL/00257/2024-2025 | 173-MSD/2024-25 | 21/06/2024 | 0 | J.S. CONSTRUCTION | 0.05 | 0 | 0
63 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati (315980) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District, TNO- 764/2020-21/EE |  |  | BILL/00259/2024-2025 | 172-MSD/2024-25 | 21/06/2024 | 0 | SOUMYA KANTI SINHA | 1.02 | 0 | 0
64 | Murshidabad Division |  | Construction of Sluice valve chamber & laying of upvc pipeline in connection with retrofitting work at Panchthupi Village (315983) under Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000023/2022-2023 | 27/KSD | 08/04/2022 | 30 | CHAND ENTERPRISE | 4.72 | 4.38 | 100
65 | Murshidabad Division |  | Laying of distribution pipeline in connection with FHTC work at Panchthupi Village (Village Code-315983)(Mokanpara) under Panchthupi Water Supply Scheme under Kandi Sub Division , P.H.E. Dte. In the district of Murshidabad. |  |  | ORD/000226/2022-2023 | 97 / KSD | 06/06/2022 | 30 | M/S GUHA AND ROY | 4.83 | 4.72 | 1
66 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Panchthupi ( Village Code -315983) under Panchthupi Ground Based Water Supply Scheme for Arsenic Affected Area of Burwan Block, under Murshidabad Division, PHE Dte. Scheme ID 0007335523 in the District of Murshidabad. (Sl No-24) |  |  | ORD/000734/2020-2021 | 3050 / MURD | 08/12/2020 | 1850 | M/S GUHA & ROY ENTERPRISE | 113.53 | 17.96 | 90
67 | Murshidabad Division |  | Formal Work Order for Augmentation of PANCHTHUPI ZONE-III PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. |  |  | ORD/000834/2022-2023 | 740/MURD | 16/03/2023 | 1112 | TIRUPATI CONSTRUCTION | 270.65 | 6.53 | 32
68 | Murshidabad Division |  | Balance work of distribution pipeline in connection with FHTC work at Shibrambati Village under Panchthupi Water Supply Scheme under Kandi Sub Division , P.H.E. Dte. In the district of Murshidabad. |  |  | ORD/001596/2021-2022 | 374/KSD | 19/01/2022 | 30 | M/S GUHA AND ROY | 4.73 | 0 | 0
69 | Murshidabad Division |  | Laying of distribution pipeline in connection with FHTC work at Panchthupi Village (Dakshin Para & Kesi Para) under Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E. Dte. In the district of Murshidabad. |  |  | ORD/001598/2021-2022 | 376/KSD | 19/01/2022 | 30 | M/S GUHA AND ROY | 4.81 | 0 | 0
70 | Murshidabad Division |  | Laying of distribution pipeline in connection with FHTC work at Panchthupi Village (Ghosh Para) under Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E. Dte. In the district of Murshidabad. |  |  | ORD/001613/2021-2022 | 380/KSD | 19/01/2022 | 30 | M/S GUHA AND ROY | 4.51 | 0 | 0
71 | Murshidabad Division |  | Retrofitting functional hoyusehold tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Village PANCHTHUPI under PANCHTHUPI Ground Based W/S Scheme for Arsenic Affected area of Burwan Block under MSD PHE DTE. Scheme Id:0007335523 in the dist of Murshidabad. Sl. No.24 Tender no 70 SE/MC 20-21 |  |  | VCH/000037/2021-2022 | 02/MSD/21-22 | 16/07/2021 | 0 | M/S GUHA & ROY ENTERPRISE | 37.93 | 0 | 0
72 | Murshidabad Division |  | Laying of Distribution pipeline in connection with FHTC work at PANCHTHUPI Village (Ghosh Para) under PANCHTHUPI W/Sb Scheme under KSD PHE DTE. Tender no - 58 of 21-22 by AE KSD |  |  | VCH/000301/2022-2023 | 111-MSD/22-23 | 07/05/2022 | 0 | M/S GUHA & ROY ENTERPRISE | 4.5 | 0 | 0
73 | Murshidabad Division |  | BALANCE work of Distribution pipeline in connection with FHTC work at SHIBRAMBATI Village under PANCHTHUPI W/S Scheme under KSD PHE DTE. Tender no - 56 of 21-22 by AE KSD |  |  | VCH/000302/2022-2023 | 111-MSD/22-23 | 07/05/2022 | 0 | M/S GUHA & ROY ENTERPRISE | 4.73 | 0 | 0
74 | Murshidabad Division |  | Laying of Distribution pipeline in connection with FHTC work at PANCHTHUPI Village (DAKSHIN PARA AND KESI PARA) under PANCHTHUPI W/S Scheme under KSD PHE DTE. Tender no - 57of 21-22 by AE KSD |  |  | VCH/000372/2022-2023 | 143-MSD/22-23 | 11/05/2022 | 0 | M/S GUHA AND ROY | 4.81 | 0 | 0
75 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PANCHTHUPI under PANCHTHUPI Ground Water Based Water Supply Scheme for arsenic affected areas of BURWAN Block in the District of Murshidabad. Tender no - 70 of 20-21 by SE MC |  |  | VCH/001551/2021-2022 | 369-MSD/21-22 | 18/03/2022 | 0 | M/S GUHA & ROY ENTERPRISE | 49.54 | 0 | 0
76 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BALIA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000467/2021-2022 | 235/KSD | 27/08/2021 | 60 | IMAGIN COMMUNICATION | 4.17 | 0 | 0
77 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Bele Habitation under Bele Village(JL NO-152) of Bele Water Supply Scheme(Ground Water Based) under Kandi Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000547/2020-2021 | 2526/MURD | 30/09/2020 | 45 | R.M. BHATTA | 39.32 | 1.98 | 0
78 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BANPUR (Village Code.315191) under Bele Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000551/2020-2021 | 3030/MURD | 07/12/2020 | 45 | M/S. SINHA & SONS | 28.3 | 0 | 0
79 | Murshidabad Division | Kandi Sub-Division | Balance works of laying of UPVC distribution pipeline at Chandra Singha Bati village in connection of FHTC work of Bele Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001132/2021-2022 | 319/KSD | 16/11/2021 | 30 | BHOLEBABA CONSTRUCTION CO | 4.84 | 0 | 0
80 | Murshidabad Division | Kandi Sub-Division | Balance work for extension of distribution pipeline from Bainpara, Kandapara, Banur & Seikhpara area under Bele Water Supply Scheme under Kandi Sub-Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001187/2021-2022 | 321/KSD | 16/11/2021 | 30 | SUKUMAR ROY | 4.83 | 0 | 0
81 | Murshidabad Division | Kandi Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/001229/2021-2022 | 213/KSD | 11/08/2021 | 30 | IMAGIN COMMUNICATION | 3.25 | 0 | 0
82 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village CHANDBATI (Village Code- 315210) under BELE Water Supply Scheme of KHORGARM BLOCK Murshidabad District under Murshidabad Division, PHE Dte. TNO- 54/20-21/EE | ASSISTANT ENGINEER |  | VCH/000227/2021-2022 | 18-MSD / 21-22 | 10/08/2021 | 0 | M/S . SUKUMAR SINHA | 23.36 | 0 | 0
83 | Murshidabad Division | Kandi Sub-Division | BALALNCE WORK OF LAYING OF UPVC PIPE LIN E AT CHANDRASINGHA BATI IN CONNECTION OF FHTC WORK UNDER BELE WSS, TNO- 36/21-22/AEKSD | ASSISTANT ENGINEER |  | VCH/001440/2021-2022 | 340 -MSD/21-22 | 03/03/2022 | 0 | BHOLEBABA CONSTRUCTION CO | 4.84 | 0 | 0
84 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BANPUR (Village Code 315191) under BELE Ground Water Based Water Supply Scheme for arsenic affected areas of KHARGRAM Block in the District of Murshidabad. Tender no - 831 of 20-21 by EE MURD | ASSISTANT ENGINEER |  | VCH/001463/2021-2022 | 364-MSD/21-22 | 11/03/2022 | 0 | M/S. SINHA & SONS | 27.15 | 0 | 0
85 | Murshidabad Division | Kandi Sub-Division | Balance work for extention og distibution pipeline form Bainpara, Kandapara, burwan & Seikhpara area under Bele W/S Scheme under Kandi Sub Div. PHE DTE. Tender no - 41 of 21-22 by AE KSD | ASSISTANT ENGINEER |  | VCH/001478/2021-2022 | 386-MSD/21-22 | 23/03/2022 | 0 | SUKUMAR ROY | 4.82 | 0 | 0
86 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahatpur(Village code 314442) under Telia Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE | ORD/000109/2020-2021 | 176/BD-I | 03/02/2021 | 20 | KAMIRUL SK AND CO. | 12.76 | 9.51 | 1
87 | Berhampore Division I | Berhampur Division I | Additional of different dia of UPVC pipeline for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahatpur (Village code 314442) under Telia Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE | ORD/000415/2021-2022 | 1453/BD-I | 13/08/2021 | 10 | KAMIRUL SK AND CO. | 1.03 | 0 | 0
88 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Karttikpur(Village code 314220) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE | ORD/000128/2020-2021 | 204/BD-I | 04/02/2021 | 30 | SARAJIT KUMAR MAJUMDAR | 61.23 | 45.46 | 1
89 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) of 1851 nos in connection with (Jal Jeevan Mission ) and under command area of village of Debkunda ( Village Code -315602) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000111/2022-2023 | 1195/MURD | 10/05/2022 | 60 | SOURAV DEY | 82.09 | 0 | 0
90 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bishannagar ( Village Code -315605) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000287/2020-2021 | 599/MURD | 09/02/2021 | 60 | NAYLA CONSTRUCTION | 95.64 | 0 | 0
91 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Madda ( Village Code -315603)adjoining habitation under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000316/2021-2022 | 2384/MURD | 09/08/2021 | 60 | MITRA & SARKAR CONSTRUCTION | 63.64 | 61.02 | 0
92 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Madda ( Village Code -315603) & adjoining habitation (Part-I) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000317/2021-2022 | 2385/MURD | 09/08/2021 | 60 | MITRA & SARKAR CONSTRUCTION | 65.45 | 50.92 | 10
93 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dalua ( Village Code -315580) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000492/2020-2021 | 591/MURD | 09/02/2021 | 60 | S. ROY & CO. | 51.49 | 23.92 | 100
94 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Debkunda (Village code-315602) under Madda Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga-I Block of Murshidabad District under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000552/2022-2023 | 2833/MURD | 17/10/2022 | 120 | AMAL KUMAR DAS | 119.55 | 0 | 0
95 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000025/2021-2022 | 539/10/MURD | 25/02/2022 | 0 | Resource Division | 10.18 | 0 | 0
96 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BISHANNAGAR (Village Code 315605) under BELDANGA MUNICIPALITY Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-I Block in the District of Murshidabad. Tender no - 905 of 21-22 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001450/2021-2022 | 346-MSD/21-22 | 05/03/2022 | 0 | NAYLA CONSTRUCTION | 79.01 | 0 | 0
97 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bali (Village code 315524) under Bali Zone-II Ground Water Supply Scheme in Nawda Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-01) | Assistant Engineer-II | JE | ORD/000555/2021-2022 | 1886/BD-I | 07/10/2021 | 180 | SANJAY BISWAS | 248.74 | 133.42 | 85
98 | Berhampore Division I | Berhampur Division I | Formal work order for Water Supply arrangement for arsenic affected habitation with SOLAR Power connection by Construction/ installation of Community Purification Plant (CPP) unit including Tubewell (125 x50 mm dia ) with DTH (for Population 351-500 & Raw Water As concentration upto 0.15 ppm) at Different habitations [For-9 nos Unit] in different Villages of Block of Farakka ( 9 Units) under Berhampore Division-I , P.H.E. Dte. in the District of Murshidabad. (Site list S/L No 04) | Assistant Engineer-II | JE | ORD/000563/2021-2022 | 1917/BD-I | 08/10/2021 | 75 | MODERN CONSTRUCTION | 143.25 | 89.49 | 1
99 | Berhampore Division I | Berhampur Division I | Laying of Extension and parallel pipeline at Ramnachandpur village due to smooth Functioning of Functional Hosehold Tap Connection at Ramnachandpur zone-I ground Water based water Supply Scheme Under Berhampore Division-I,P.H.E Dte. | Assistant Engineer-II | JE | ORD/000008/2022-2023 | 551/BD-I | 13/05/2022 | 45 | ULTRA CONSTRUCTION | 40.55 | 29.76 | 1
100 | Berhampore Division I | Berhampur Division I | Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.06.2022 to 31.12.2022. | Assistant Engineer-II | JE | ORD/000014/2022-2023 | 628/BD-I | 30/05/2022 | 214 | SOUVIK HALDER | 1.06 | 2.56 | 1
101 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bundai Nagar (village code 315530) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000242/2021-2022 | 1852/BD-I | 07/10/2021 | 100 | SRIJON ENTERPRISE | 96.17 | 68.46 | 1
102 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Alampur (village code 315519) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000243/2021-2022 | 1853/BD-I | 07/10/2021 | 90 | SRIJON ENTERPRISE | 88.19 | 65.18 | 1
103 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kedarchandpur (village code 315518) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000244/2021-2022 | 1854/BD-I | 07/10/2021 | 100 | SRIJON ENTERPRISE | 98.62 | 63.5 | 1
104 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnachandpur (Village code 315520) under Ramnachandpur Water Supply Scheme of Nawda Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-14) | Assistant Engineer-II | JE | ORD/000580/2021-2022 | 1924/BD-I | 08/10/2021 | 180 | M/S GUHA AND ROY ENTERPRISE | 217.79 | 123.15 | 1
105 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Kedarchandpur, Bundai Nagar and Alampur (Village code-315518,315530, and 315519) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Ramnachandpur Ground water based Water supply scheme (Nawda,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-II | JE | ORD/000793/2021-2022 | 2309/BD-I | 29/12/2021 | 90 | SRIJON ENTERPRISE | 43.88 | 35.92 | 1
106 | Berhampore Division I | Berhampur Division I | Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub-Division, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer-II | JE | ORD/000871/2021-2022 | 2281/BD-I | 27/12/2021 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 1.58 | 1
107 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | JE | RTOR000010/2021-2022 | 144/BD-I | 10/02/2022 | 0 | Resource Division | 16.44 | 0 | 0
108 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of villages of Hareknagar, Andiran ,Begunbari and Chakhijli (village code 315604,315610,315608 and 315609), under BEGUNBARI (Zone-I) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHED | Assistant Engineer-II | Junior Engineer-I | ORD/000290/2022-2023 | 1804/BD-I | 31/03/2023 | 120 | SARAJIT KUMAR MAJUMDAR | 350.09 | 0 | 0
109 | Berhampore Division I | Berhampur Division I | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under DAULATABAD(Zone-F) Surface Water based Water Supply Scheme of Central Sector (Part-I) under Murshidabad -Jiaganj Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000111/2023-2024 | 440/BD-I | 12/07/2023 | 90 | A.P CONSTRUCTION | 42.93 | 0 | 0
110 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Daulatabad (Village code 315415) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000232/2021-2022 | 1819/BD-I | 05/10/2021 | 90 | PRADIP KUMAR DAS | 88.49 | 79.01 | 1
111 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Muliarazi,Harirampur and Balia Danga (Village code 315400,315401,315402) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000233/2021-2022 | 1823/BD-I | 05/10/2021 | 80 | KAMIRUL SK AND CO. | 76.53 | 39.07 | 1
112 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Purandarpur (Village code 315403) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000234/2021-2022 | 1825/BD-I | 05/10/2021 | 60 | M/S SINHA & SONS | 55.92 | 51.43 | 100
113 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dadpur (Village code 315422) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000253/2021-2022 | 1818/BD-I | 05/10/2021 | 100 | DOBAY CONSTRUCTION | 98.25 | 72.16 | 1
114 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kulbaria (Village code 315414) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000254/2021-2022 | 1820/BD-I | 05/10/2021 | 90 | USHA ENTERPRISE | 84.7 | 61.07 | 1
115 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gauripur and Ruhia (Village code 315412,315413) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000255/2021-2022 | 1821/BD-I | 05/10/2021 | 90 | MAMATA USHA ENTERPRISE | 90.65 | 40.97 | 1
116 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhanjha,Benidaspur,Garabasa,Maharajpur and Hanumanta Nagar (Village code 315407,315408,315409,315410,315411) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000256/2021-2022 | 1822/BD-I | 05/10/2021 | 100 | BANIK BROTHERS | 97.4 | 82.14 | 100
117 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Muli and Gangaprasad (Village code 315406,315423) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000257/2021-2022 | 1824/BD-I | 05/10/2021 | 20 | ROY AND ROY CONSTRUCTION | 10.62 | 8.6 | 1
118 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mukundapur and Purbagopinathpur (Village code 315416,315420) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000258/2021-2022 | 1826/BD-I | 05/10/2021 | 30 | SUDIPA SINGHA ROY | 23.87 | 18.26 | 1
119 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
120 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chutipur (village code 315419), under Doulatabad (Zone-F) Surface water based Water Supply Scheme of Central Sector Part-I for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000743/2021-2022 | 2205/BD-I | 10/12/2021 | 120 | SAMRIDDHI ASSOCIATED | 96 | 90.17 | 1
121 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Doulatabad Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE | ORD/000759/2021-2022 | 2225/BD-I | 15/12/2021 | 90 | AJOY GHOSH | 74.29 | 74.76 | 1
122 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Daulatabad to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Daulatabad Surface water based water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE | ORD/000874/2021-2022 | 244/BD-I | 03/03/2022 | 15 | MONDAL ENTERPRISE VILL. + P.O.- CHALTIA, P.S.- BERHAMPORE | 8.58 | 7.05 | 1
123 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE | RTOR000002/2021-2022 | 64/BD-I | 27/01/2022 | 0 | Resource Division | 1.24 | 0 | 0
124 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE | RTOR000006/2021-2022 | 71/BD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
125 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (1250 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Popara under Sagardighi Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000648/2023-2024 | 3713/MURD | 05/12/2023 | 60 | SANDIP KUMAR BISWAS | 44.69 | 0 | 0
126 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) of mouza Bara Jumla (Village Code-314144, Krishnaa Sail(Village Code-314143) of Putia and ajoining moujas under Ground water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj II Block & mouza Joykrishnapur (Village Code-313880), of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, and mouza Popara (Village Code-314326) of Sagardighi Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0005019109), 0001723441 & 0005184147) |  |  | ORD/001601/2021-2022 | 341/MURD | 10/02/2022 | 1111 | CHAKRABORTY CONSTRUCTION | 416 | 0 | 12
127 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 889/E/MURD | 05/04/2022 | 0 | Resource Division | 15.53 | 0 | 0
128 | Murshidabad Division |  | Supplying and Laying of 160mm dia UPVC pipe line at Dudhsar Habitaion (village -code-315521) for FHTC work under SARBANGAPUR ZONE-I Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. |  |  | ORD/000527/2020-2021 | 121/BSD | 19/02/2021 | 15 | CHATTERJEE ENTERPRISE | 4.83 | 4.82 | 0
129 | Murshidabad Division |  | Supplying and Laying of 90mm dia UPVC pipe line at Dudhsar Habitaion (village -code-315521) for FHTC work under SARBANGAPUR ZONE-I Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. (Part-II) |  |  | ORD/000528/2020-2021 | 122/BSD | 19/02/2021 | 15 | DAS CONSTRACTION | 4.83 | 4.83 | 0
130 | Murshidabad Division |  | Supplying and Laying of 110mm dia UPVC pipe line at Dudhsar Habitaion (village -code-315521) for FHTC work under SARBANGAPUR ZONE-I Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. |  |  | ORD/000529/2020-2021 | 123/BSD | 19/02/2021 | 15 | NATIONAL ENTERPRISE | 4.83 | 4.83 | 0
131 | Murshidabad Division |  | Supplying and Laying of 90mm dia UPVC pipe line at Dudhsar Habitaion (village -code-315521) for FHTC work under SARBANGAPUR ZONE-I Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. (Part-I) |  |  | ORD/000530/2020-2021 | 124/BSD | 19/02/2021 | 15 | LONDON WHARFIES | 4.85 | 4.85 | 0
132 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dudhsar (Village code 315521) under Sarbangapur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723279 in the District of Murshidabad. |  |  | ORD/000615/2020-2021 | 34/MURD | 05/01/2021 | 60 | CHATTERJEE ENTERPRISE | 19.26 | 8.94 | 0
133 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kishorpur (Village code 313961) under Kishorpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723400 in the District of Murshidabad. |  |  | ORD/001609/2021-2022 | 426/MURD | 17/02/2022 | 60 | BISWAS CONSTRUCTION | 40.15 | 38.52 | 0
134 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 889/C/MURD | 05/04/2022 | 0 | Resource Division | 5.21 | 0 | 0
135 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Nandalalpur (Village code 314628) under Barabil Raghunathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723213 in the District of Murshidabad. (Sl No-29) |  |  | ORD/000297/2020-2021 | 961/MURD | 24/03/2021 | 180 | S.M. ENTERPRISE | 50.52 | 0.32 | 1
136 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dakshin Jitpur (Village code 314713) under Garibpur (Zone-I & Zone-II) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723342 in the District of Murshidabad. |  |  | ORD/000607/2020-2021 | 322 /MURD | 28/01/2021 | 60 | MOLLA ENTERPRISE (REHENA BIBI) | 22.64 | 31.19 | 0
137 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (1173 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Santoshpur ( Village Code -314329) & Chandanbati ( Village code-314330) under Sagardighi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000641/2023-2024 | 3438/MURD | 03/11/2023 | 45 | MAA SANKARI ENTERPRISE | 36.58 | 0 | 0
138 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at HARIHARPARA G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000516/2021-2022 | 348/BSD | 27/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.17 | 4.17 | 0
139 | Murshidabad Division |  | Work of Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 22 to 23 & 125 mm Dia N.P 23 to 24 and 110 mm Dia N.P 24 to 25,N.P 25 to 26, 90mmOD N.P 26 to27,27 to 28 ;200mm dia N.P 3 to 4,N.P 19 to 20;160 mm OD N.P 21 to 22 at Kanaighat area at uncovered Habitation for smooth water supply arrangement in Kadoa W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. during COVID-19 affected period (Part-B). |  |  | ORD/001269/2021-2022 | 388/JSD | 31/12/2021 | 30 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 4.84 | 4.84 | 100
140 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Jalangi Zone-II / Part-A Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000467/2022-2023 | 2372/MURD | 16/08/2022 | 958 | MAMATA USHA ENTERPRISE | 670.9 | 395.67 | 100
141 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-II/ Part-A Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000585/2022-2023 | 3054/MURD | 17/11/2022 | 45 | MAMATA USHA ENTERPRISE | 23.58 | 18.81 | 1
142 | Murshidabad Division | Berhampur M/E Division | Allied work of OHR & HDPE Pipeline for Augmentation of Jalangi Zone-II Part-A ground water based PWSS to accommodate FHTC in Jalangi Block in the district of Murshidabad under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000761/2023-2024 | 183/MURD | 18/01/2024 | 90 | MAMATA USHA ENTERPRISE | 123.49 | 46.28 | 90
143 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000029/2024-2025 | MURD/2481/02 | 04/09/2024 | 0 | Resource Division | 24.04 | 0 | 0
144 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000035/2022-2023 | 2780/D/MURD | 01/10/2022 | 0 | Resource Division | 21.86 | 0 | 0
145 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000057/2022-2023 | 3294/MURD | 12/12/2022 | 0 | Resource Division | 21.86 | 0 | 0
146 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000157/2023-2024 | 1180/MURD/6 | 29/04/2023 | 0 | Resource Division | 143.36 | 0 | 0
147 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000332/2023-2024 | 3849/MURD/1 | 14/12/2023 | 0 | Resource Division | 1.98 | 0 | 0
148 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000351/2023-2024 | 305/MURD | 29/01/2024 | 0 | Resource Division | 22.47 | 0 | 0
149 | Berhampore Mechanical | Berhampur M/E Division | New connection charge for Jalangi W/S Scheme (Part-A) Zone-II, P/H No.-II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/00269/2023-2024 | 89/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 0.91 | 0 | 0
150 | Berhampore Mechanical | Berhampur M/E Division | New connection charge for Jalangi W/S Scheme (Part-A) Zone-II, P/H No.-I. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/00273/2023-2024 | 90/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 1.61 | 0 | 0
151 | Berhampore Mechanical | Berhampur M/E Division | addl service connection charges at sahebrampur colony ,jalangi pwss part A,,z 2, ph 2, ID 860279299 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01106/2023-2024 | 209/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 3.77 | 0 | 0
152 | Berhampore Mechanical | Berhampur M/E Division | Addl quotation for sahebrampur jalangi CCC ID860281601 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01183/2023-2024 | 247/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 11.14 | 0 | 0
153 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of JALANGI , Zone- II/Part-A ground water based water supply scheme under Block- Jalangi, Dist. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000821/2023-2024 | 3768/MEDB | 03/11/2023 | 92 | EASTERN INDIA SALES & SERVICE | 22.55 | 16.77 | 60
154 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System for Augmentation of DOGACHHI (ZONE-II) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000032/2024-2025 | 1891/MURD | 01/07/2024 | 365 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 77.48 | 0 | 40
155 | Murshidabad Division | Berhampur M/E Division | Overhauling of 350 Cum Capacity, 20 mtr staging height (Shaft Wall) R.C.C. Elevated Reservoir, Repairing of Pump House & Boundary Wall, Laying of Distribution System to accommodate of FHTC work at Alamsahi village, Balbalpara village, Laskarpur village(80%) & Mahisha Thali Village for Augmentation work of Dogachhi Zone-II Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000045/2024-2025 | 1949/MURD | 04/07/2024 | 303 | MOTI INDUSTRIES | 93.51 | 0 | 40
156 | Murshidabad Division | Berhampur M/E Division | Laying of balance work of HDPE pipe Risingmain and construction of approach road at Head Works Site of Dogachhi ( Zone-I) Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000062/2020-2021 | 282/MURD | 27/01/2021 | 30 | HARUN ALL RASHID & BROTHERS | 4.96 | 5.11 | 1
157 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dogachhi Zone -II Water Supply Scheme at Head Work Site, 2nd Site & 3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000101/2023-2024 | 1742/MURD | 06/07/2023 | 635 | NADIA TUBEWELLS | 35.34 | 0 | 33
158 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main & Distribution System (PART-B) for Augmentation of DOGACHHI (ZONE-II) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000251/2024-2025 | 229/MURD | 27/01/2025 | 90 | M/S GUNGUN CONSTRUCTION | 89.6 | 0 | 0
159 | Murshidabad Division | Berhampur M/E Division | Formal Work order for Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Dy Superintending Engineer, Murshidabad Circle,PHE Dte.[Period for 01(One) Year] for the month of April?2022 to March?2023 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000569/2022-2023 | 894/MURD | 05/04/2022 | 365 | SOUMYADIP MISRA | 4.78 | 1.83 | 1
160 | Murshidabad Division | Berhampur M/E Division | Formal work order for Construction 250 Cum OHR & Rising Main in Connection with Augmentation of Dogachhi Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Samserganj Block of Murshidabad District under Murshidabad Division, PHE.Dte. [ (i)Amount for R. Main: Rs. 6,69,620.00 & (ii) Amount for OHR : Rs. 98,29,869.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000696/2022-2023 | 134/MURD | 16/01/2023 | 365 | IOTA CONSTRUCTION | 104.46 | 0 | 0
161 | Murshidabad Division | Berhampur M/E Division | Geotechnical study of underground formation of the proposed Over Head Reservoir of Dogachhi (Zone-II) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000756/2023-2024 | 139/MURD | 16/01/2024 | 30 | IOTA CONSTRUCTION | 2.48 | 0 | 0
162 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 4.03 | 100
163 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I , II and III OF ZONE-II under Dogachhi ground water based water supply scheme under Block_ SAMSERGANJ Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000161/2023-2024 | 2087/MEDB | 19/06/2023 | 92 | ORIENTAL ENGINEERING CO. | 31.45 | 0 | 0
164 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naoda, Sahapur, Ratanpur, Betberia, Kheali, Palaighata, Jafrabad, Sattarpur, Chaitanyapur & Bhadur (Village code 315568, 315569, 315570, 315571, 315572, 315574, 315575, 315576, 315577 & 315579) under Chaitanyapur (Zone-C) Water Supply Scheme of Beldanga -I Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000848/2021-2022 | 104/BD-I | 01/02/2022 | 180 | M/S JAN MAHAMMAD | 318.48 | 300.19 | 1
165 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-I | RTOR000007/2021-2022 | 139/BD-I | 10/02/2022 | 0 | Resource Division | 28.46 | 0 | 0
166 | Murshidabad Division | Berhampur M/E Division | Construction 400 Cum OHR for Augmentation of Sekendra Ground water based Piped water supply scheme in Raghunathganj -II Block under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000002/2023-2024 | 944/MURD | 05/04/2023 | 365 | PRODEEP KUMAR GHOSH | 132.12 | 52.91 | 50
167 | Murshidabad Division | Berhampur M/E Division | Construction of Boundary wall of 60 m length and pumphouse (5.9 m x 4.825 m) at site no 4 at Sekendra Pwss in Raghunathganj-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000069/2025-2026 | 1246/MURD | 29/05/2025 | 60 | KALACHAND DAS | 19.25 | 0 | 0
168 | Murshidabad Division | Berhampur M/E Division | Providing Functional Household Tap Connections ( 200 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Taraf Rasulpur ( Village Code -314679) and Sekendra ( Village Code -314064) under P.T Rasulpur & Sekendra Ground Water Based Water Supply Scheme under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000110/2024-2025 | 2211/MURD | 02/08/2024 | 30 | PRAVAT KUMAR GHOSH | 7.3 | 0 | 0
169 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying Distribution System ,FHTC, Construction of 1 (one) no Pump House (4.25m x 3.60m with sanitary and Water Supply Arrangement), Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement and 2(two) nos Pump House repairing. Repairing of Existing OHR Part for Augmentation of SEKENDRA PWSS in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000758/2022-2023 | 445/MURD | 17/02/2023 | 846 | NAYLA CONSTRUCTION | 255.21 | 62.85 | 90
170 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000372/2023-2024 | 495/MURD/09 | 15/02/2024 | 0 | Resource Division | 33.66 | 0 | 0
171 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000554/2024-2025 | 336/MEDB | 10/02/2025 | 89 | DAS ENTERPRISE (CHOA) | 23.19 | 0 | 0
172 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hasanpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000116/2022-2023 | 1366/BD-I | 21/12/2022 | 30 | SARIFUL ISLAM | 2.49 | 2.45 | 100
173 | Berhampore Division I | Berhampur Division I | Augmentation of Hasanpur Piped water supply scheme to accommodate construction of OHR,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Swapna in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000119/2023-2024 | 831/BD-I | 01/09/2023 | 310 | A ONE CONSTRUCTION | 238.41 | 0 | 0
174 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HASANPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000889/2021-2022 | 272/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.53 | 2.53 | 0
175 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | RTOR000050/2023-2024 | 196/BD-I/1 | 09/02/2024 | 0 | Resource Division | 2.08 | 0 | 0
176 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Hasanpur ground water based water supply scheme under Block- Bhagawangola-II, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000034/2023-2024 | 3731/MEDB | 03/11/2023 | 92 | GANGULI ELECTRICAL CO. | 11.46 | 0 | 10
177 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Melanpur, Durgapur (314744, 314745, 314746, 314747, 314753, 314754, 314755, 314756 of Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000128/2022-2023 | 1211/MURD | 10/05/2022 | 60 | SOURAV DEY | 32.44 | 0 | 0
178 | Murshidabad Division | Berhampur M/E Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Melanpur (Village code 314755) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000721/2020-2021 | 532/MURD | 04/02/2021 | 60 | BHOWMIK CONSTRUCTION | 3.72 | 0 | 0
179 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Bilpachakopra (314584) of Nabipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000137/2022-2023 | 1239/MURD | 11/05/2022 | 1056 | MAMATA USHA ENTERPRISE | 33.22 | 19.56 | 100
180 | Murshidabad Division | Berhampur M/E Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bilpachakopra ( Village Code -314584) under Nabipur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184055). | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000476/2020-2021 | 575/MURD | 09/02/2021 | 60 | NOVELTY CONSTRUCTION | 29.68 | 0 | 0
181 | Berhampore Mechanical | Berhampur M/E Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation & Functional Household Tap Connections (FHTC) of Mouza Bilpachakopra (314584) Pump House No.-I and II under Nabipur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/001489/2023-2024 | 769/MEDB | 20/02/2024 | 647 | JOY BISHNU ENGINEERING CO. | 23.48 | 0 | 50
182 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Augmentation of CHANDPUR Zone-I / Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000342/2022-2023 | 1808/MURD | 11/07/2022 | 905 | MODERN CONSTRUCTION | 178.55 | 131.4 | 100
183 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (CHANDPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000844/2021-2022 | 3277/MURD | 05/10/2021 | 60 | RADIANT | 14.82 | 4.84 | 1
184 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Goghata ( Village Code -315526) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186507) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/002062/2021-2022 | 1699 / MURD | 07/07/2021 | 60 | M/S JAN MAHAMMAD | 52.35 | 19.67 | 1
185 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000297/2023-2024 | 1278/MURD/6 | 10/05/2023 | 0 | Resource Division | 34.53 | 0 | 0
186 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000347/2023-2024 | 112/MURD/04 | 11/01/2024 | 0 | Resource Division | 40.95 | 0 | 0
187 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000356/2023-2024 | 305/MURD/05 | 29/01/2024 | 0 | Resource Division | 22.9 | 0 | 0
188 | Murshidabad Division | Kandi Sub-Division | Formal Work Order ForConstruction of 100 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of JUGASWARA PWSS in Burwan Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362271S000) [(i)Amount for LDS , R.Main & FHTC: Rs.1,38,33,206.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs. 1,13,02,060.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000757/2022-2023 | 416/MURD | 15/02/2023 | 730 | SHYAMAL KUMAR SAHA | 251.3 | 75.27 | 90
189 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JUGASWARA PWSS at Head Work Site & 2nd Tube Well Site in Burwan Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000770/2022-2023 | 485/MURD | 20/02/2023 | 45 | NADIA TUBEWELLS | 16.81 | 15.07 | 100
190 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | RTOR000008/2023-2024 | 1210/MURD/37 | 02/05/2023 | 0 | Resource Division | 1.42 | 0 | 0
191 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | RTOR000346/2023-2024 | 112/MURD/03 | 11/01/2024 | 0 | Resource Division | 4.88 | 0 | 0
192 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS PH1 JUGASWARA ID 304240312 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | BILL/01418/2023-2024 | 311/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 4.88 | 0 | 0
193 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS PH 2 JUGASWARA ID 304240283 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | BILL/01419/2023-2024 | 312/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 9.89 | 0 | 0
194 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of Jugaswara ground water based water supply scheme under Block- Burwan, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000098/2023-2024 | 1889/MEDB | 16/06/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 21.23 | 14.56 | 20
195 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution system, Rising Main, Sub-soil Investigation and construction of OHR (400 cum) and construction of Boundary wall and repairing of Pump-House in connection with Augmentation of Godhanpara Zone-II water supply scheme under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000579/2022-2023 | 3032/MURD | 16/11/2022 | 1094 | M/S GUHA & ROY ENTERPRISE | 412.1 | 198.25 | 80
196 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000738/2021-2022 | 2744/MURD | 03/09/2021 | 60 | RADIANT | 11.27 | 3.76 | 0
197 | Murshidabad Division | Berhampur M/E Division | Construction of new Boundary wall with R.B.T fencing with approach road (Pump No-II) under Godhanpara Zone-II Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/002061/2021-2022 | 275/ISD. | 03/06/2021 | 60 | AJOY GHOSH | 4.52 | 4.52 | 1
198 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000049/2022-2023 | 3052/B/MURD | 17/11/2022 | 0 | Resource Division | 18.01 | 0 | 0
199 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000293/2023-2024 | 1278/MURD/11 | 10/05/2023 | 0 | Resource Division | 14.88 | 0 | 0
200 | Berhampore Mechanical | Berhampur M/E Division | Shifting of 11KV HTOH line at Godhanpara W/S scheme, P.H-I, Z-II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/00262/2023-2024 | 70/WBSEDCL-JJM | 18/07/2023 | 0 | WBSEDCL | 3.27 | 0 | 0
201 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION GODHANPARA Z2 PH3 ID 304495842 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01118/2024-2025 |  | 25/11/2024 | 0 | WBSEDCL | 8.95 | 0 | 0
202 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT GODHANPARA Z2 PH 2, ID304232744 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01224/2023-2024 | 281/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
203 | Berhampore Division I | Berhampur Division I | Laying of different dia UPVC distribution pipe Line in connection with JJM (Jal Jeevan Mission) on damaged portion and Rukunpur Satsang Kandra with alied works of Rukunpur (Zone-G) based water supply scheme under CS Part-II of BD-I, P.H.E Dte | Assistant Engineer-II | Junior Engineer-II | ORD/000015/2023-2024 | 86/BD-I | 03/05/2023 | 30 | CHATTERJEE ENTERPRISE | 2.89 | 2.81 | 100
204 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of RUKUNPUR (Village code 315481) under Rukunpur (Zone-G) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte | Assistant Engineer-II | Junior Engineer-II | ORD/000077/2020-2021 | 976/BD-I | 17/12/2020 | 180 | PRADIP KUMAR DAS | 235.52 | 246.56 | 1
205 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pratappur (Village code 315480) under Rukunpur (Zone-G) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000133/2020-2021 | 232/BD-I | 10/02/2021 | 1633 | M/S GOUTAM CHAKRABORTY | 130.13 | 103.4 | 1
206 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Biharia (Village code 315478) under Rukunpur (Zone-G) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000137/2020-2021 | 237/BD-I | 10/02/2021 | 180 | UNIVERSAL CONSTRUCTION | 160.94 | 154.25 | 0
207 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khanpur,Hamdampur,Pilkhana and Matijhil (Village code 314845,314846,314850,314848) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000223/2021-2022 | 1812/BD-I | 05/10/2021 | 100 | M/S GUHA AND ROY ENTERPRISE | 95.07 | 53.67 | 1
208 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-57C/5576 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2024 to 31.12.2024. | Assistant Engineer-II | Junior Engineer-II | ORD/000377/2023-2024 | 1282/BD-I | 27/12/2023 | 366 | SEBAYAN CONSTRUCTION | 1.81 | 0.8 | 30
209 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tehatta (village code 315479) under RUKUNPUR ( Zone - G ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000462/2021-2022 | 1835/BD-I | 05/10/2021 | 60 | PARTHA PRATIM DAS | 49.71 | 26.51 | 1
210 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-II | Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
211 | Berhampore Division I | Berhampur Division I | Additional and balance work of HDPE pipe for house service connection for retrofitting FHTC and relaying of damage and Laying of extension different dia UPVC pipeline in connection to Jal Jeevan Mission & Jal Swapna under command area of village Rukunpur ( village code-315481 ) under Rukunpur (Zone -G )Surface Water Supply Scheme of Central Sector Part-II of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000577/2021-2022 | 1846/BD-I | 07/10/2021 | 60 | DAS TRADING CO | 50.67 | 50.64 | 1
212 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-II | RTOR000029/2024-2025 | 2096/BD-I/10 | 25/11/2024 | 0 | Resource Division | 12.32 | 0 | 0
213 | Murshidabad Division | Kandi Sub-Division | Laying of UPVC pipeline from Head Work Site to Node point 16, laying of parallel line for FHTC work and Construction of approach road of UDAYCHANDPUR & Adjoining Mouzas Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000056/2024-2025 | 1987/MURD | 08/07/2024 | 450 | MARUTI CONSTRUCTION AND CO. | 76.01 | 0 | 40
214 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UDAY CHANDPUR PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte.. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000662/2022-2023 | 3407/MURD | 22/12/2022 | 45 | MAMATA USHA ENTERPRISE | 16.82 | 0 | 80
215 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of Boundwary Wall, Pump House & Laying Distribution System(PART-B) Uncovered of UDAY CHANDPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000734/2022-2023 | 385/MURD | 10/02/2023 | 964 | MARUTI CONSTRUCTION AND CO. | 158.53 | 72.82 | 35
216 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of 300 Cum OHR, Laying Distribution System (PART-A), Rising Main, FHTC, for Uncovered of UDAY CHANDPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000859/2022-2023 | 793/MURD | 21/03/2023 | 365 | M/S. SINHA & SONS | 363.73 | 0 | 10
217 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000020/2023-2024 | 1210/MURD/40 | 02/05/2023 | 0 | Resource Division | 26.76 | 0 | 0
218 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT UDAYCHANDPUR PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01621/2023-2024 | 461/WBSEDCL-JJM | 18/03/2024 | 0 | WBSEDCL | 5.84 | 0 | 0
219 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under UDAYCHANDPUR ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000047/2023-2024 | 1882/MEDB | 16/06/2023 | 92 | MENAKA ENTERPRISE | 24.41 | 0 | 0
220 | Berhampore Division I | Berhampur Division I | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Sundarpur ground water supply scheme in Bhagwabgola-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000089/2025-2026 | 949/BD-I | 18/07/2025 | 300 | M/S S. DAS & ENTERPRISE | 122.8 | 0 | 0
221 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Sundarpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000109/2022-2023 | 1439/BD-I | 16/01/2023 | 30 | M/S RAMI CONSTRUCTION | 1.81 | 0 | 100
222 | Berhampore Division I | Berhampur Division I | Balance work for the work of Augmentation of Sundarpur Piped water supply scheme to accommodate construction of Pump House ,Boundary Wall, Service Road and laying of distribution of pipeline under Jal Jeevan Mission within Bhagwangola -I Block of Murshidabad District under Berhampore Division -I PHE. Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000126/2024-2025 | 1474/BD-I | 06/09/2024 | 60 | M/S TAPAS KUMAR CHAKRABORTY | 89.63 | 0 | 0
223 | Berhampore Division I | Berhampur Division I | Formal Work order for Augmentation of Sundarpur Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000161/2022-2023 | 1447/BD-I | 17/01/2023 | 789 | M/S TAPAS KUMAR CHAKRABORTY | 397.04 | 131.89 | 80
224 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sundarpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000284/2022-2023 | 1807/BD-I | 31/03/2023 | 900 | SUJIT KUMAR SAHA | 18.01 | 0 | 50
225 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SUNDARPUR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000881/2021-2022 | 265/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.68 | 0 | 100
226 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000067/2023-2024 | 196/BD-I/14 | 09/02/2024 | 0 | Resource Division | 34.78 | 0 | 0
227 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION AT SUNDARPUR PH-I | Assistant Engineer-I | JE,Junior engineer-III | BILL/00244/2024-2025 | 110/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 7.33 | 0 | 0
228 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Sundarpur ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000045/2023-2024 | 3735/MEDB | 03/11/2023 | 182 | M/S JIT ENTERPRISE | 22.36 | 0 | 7
229 | Murshidabad Division | Berhampur M/E Division | Construction of Boundwary Wall , Pump House , PCC approach road , Land Development for Augmentation of Jorgacha PWSS in Domkol Block , Islampur Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000011/2025-2026 | 899/MURD | 23/04/2025 | 90 | EMCO CONSTRUCTION | 23 | 0 | 0
230 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jorgacha Water Supply Scheme at Head Work Site, 2nd Site site at DOMKAL Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000131/2023-2024 | 1757/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 23.58 | 8.77 | 50
231 | Murshidabad Division | Berhampur M/E Division | Formal work order for the work of Augmentation of JORGACHA Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000732/2022-2023 | 365/MURD | 09/02/2023 | 926 | ULTRA CONSTRUCTION. | 272.97 | 153.1 | 100
232 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 4.68 | 1
233 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000305/2023-2024 | 1278/MURD/14 | 10/05/2023 | 0 | Resource Division | 74.66 | 0 | 0
234 | Berhampore Mechanical | Berhampur M/E Division | JORGACHA PH-III | ASSISTANT ENGINEER-I | Junior engineer-III | BILL/01525/2023-2024 | 434/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 8.45 | 0 | 0
235 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Jorgachha ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000044/2023-2024 | 3737/MEDB | 03/11/2023 | 182 | JAGANNATH ENTERPRISE | 22.14 | 0 | 0
236 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Diar Shyampur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE | ORD/000104/2022-2023 | 1413/BD-I | 04/01/2023 | 10 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 2.36 | 1.52 | 100
237 | Berhampore Division I | Berhampur Division I | Augmentation of Diar Syampur Zone-I Piped water supply scheme to accommodate construction of OHR, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE | ORD/000148/2023-2024 | 671/BD-I | 09/08/2023 | 310 | S.K. CONSTRUCTION DEBKUNDU , P.S.- BELDANGA, | 121.57 | 0 | 0
238 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DIAR SYAMPUR ZONE-I Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000879/2021-2022 | 263/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.37 | 0 | 100
239 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE | RTOR000060/2023-2024 | 196/BD-I/7 | 09/02/2024 | 0 | Resource Division | 10.99 | 0 | 0
240 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia Replacement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SANTOSHPUR PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000658/2022-2023 | 3415/MURD | 22/12/2022 | 45 | HARUN ALL RASHID & BROTHERS | 16.64 | 0 | 80
241 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution System (PART-B), Construction of Boundary Wall & Pump house for Uncovered SANTOSHPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. [ (i) Amount for Laying Distribution System: Rs.1,54,12,147.00 & (ii) Amount for Boundary Wall & Pump House: Rs. 41,19,886.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000727/2022-2023 | 176/MURD | 18/01/2023 | 1018 | MOTI RAHAMAN | 195.28 | 0 | 35
242 | Murshidabad Division | Kandi Sub-Division | Formal work order for construction of 250 Cum OHR , Laying Distribution System (PART-A), Rising Main, FHTC, for Uncovered SANTOSHPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. [ (i) Amount for LDS , R.Main & FHTC: Rs.2,44,40,742.00 & (ii) Amount for OHR: Rs.1,03,92,477.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000764/2022-2023 | 480/MURD | 20/02/2023 | 862 | S.&P. ENTERPRISE | 348.26 | 48.67 | 15
243 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000019/2023-2024 | 1210/MURD/32 | 02/05/2023 | 0 | Resource Division | 23.42 | 0 | 0
244 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000317/2023-2024 | 1936/MURD/5 | 19/07/2023 | 0 | Resource Division | 23.42 | 0 | 0
245 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000344/2023-2024 | 112/MURD/01 | 11/01/2024 | 0 | Resource Division | 13.66 | 0 | 0
246 | Berhampore Mechanical | Kandi Sub-Division | SANTOSHPUR PH 2 C ID 304252909 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01469/2023-2024 | 363/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 3.33 | 0 | 0
247 | Berhampore Mechanical | Kandi Sub-Division | AT SANTOSHPUR PH 1 ID 304252904 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01470/2023-2024 | 364/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 4.7 | 0 | 0
248 | Berhampore Division I | Berhampur M/E Division | Augmentation of Brohmottar Manikchak Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP), boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000203/2023-2024 | 848/BD-I | 05/09/2023 | 574 | M/S TAPAS KUMAR CHAKRABORTY | 458.37 | 51.46 | 50
249 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BRAHAMOTTAR MANIKCHAK Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000262/2022-2023 | 1685/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.6 | 2.62 | 1
250 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BRAHIMOTTAR MANIKCHAK Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000280/2024-2025 | 10/BD-I | 06/01/2025 | 15 | HARUN ALL RASHID & BROTHERS | 8.92 | 0 | 0
251 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000007/2024-2025 | 1510/BD-I/1 | 12/09/2024 | 0 | Resource Division | 4.13 | 0 | 0
252 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000068/2023-2024 | 201/BD-1/9 | 10/02/2024 | 0 | Resource Division | 31.4 | 0 | 0
253 | Berhampore Mechanical | Berhampur M/E Division | Quotation for Brahamatter PH-1 Application No- 3004544380 Ref ID- 304228570 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/01170/2023-2024 | 240/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 7.62 | 0 | 0
254 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of BRAHAMOTTAR MANIKCHAK ground water based water supply scheme under Block- LALGOLA, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000060/2023-2024 | 3777/MEDB | 03/11/2023 | 92 | GANGULI ELECTRICAL CO. | 12.01 | 0 | 10
255 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000570/2024-2025 | 385/MEDB | 12/02/2025 | 89 | SAMARPITA ENGINEERING | 12.11 | 0 | 0
256 | Murshidabad Division | Berhampur Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0
257 | Murshidabad Division | Berhampur Sub-Division | Laying of Distribution System including Refixing the existing FHTCs connection on new distribution system of Basabari Ground Based piped water supply scheme of in Berhampore Block of Berhampore Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000419/2024-2025 | 511/MURD | 28/02/2025 | 60 | M/S. M.G. CONSTRUCTION | 40.27 | 0 | 0
258 | Murshidabad Division | Berhampur Sub-Division | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 75
259 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Basabari PWSS to accommodate FHTC of 673 nos household Laying Rising Main , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works, Construction of Boundary Wall of 270 m and Soil Investigation & 250 Cum Construction of OHR at Berhampore Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000550/2023-2024 | 3180/MURD | 11/10/2023 | 730 | SAMBHU NATH ROY | 223.72 | 13.35 | 10
260 | Murshidabad Division | Berhampur Sub-Division | Water Supply arrangmenet for arsenic affected habitation with SOLAR Power connection at different block under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad. (PART-C). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000593/2020-2021 | 503/MURD | 02/02/2021 | 60 | PAL TROCKNER (P) LTD. | 37.91 | 0 | 100
261 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BASABARI & CHHAIGHARI Water Supply Scheme at Head work site at BERHAMPORE Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000723/2023-2024 | 3875/MURD | 18/12/2023 | 21 | NADIA TUBEWELLS | 11.78 | 9.22 | 100
262 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chumarigacha (Village code 315340) under Basabari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723194 in the District of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000725/2020-2021 | 3122 / MURD | 09/12/2020 | 60 | TANUSHREE ENTERPRISE | 39.34 | 1.16 | 1
263 | Murshidabad Division | Berhampur Sub-Division | Laying Distribution System For Augmentation of Basabari (Part-A) PWSS of Berhampore Block under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000769/2022-2023 | 496/MURD | 21/02/2023 | 727 | SANDHAN ADHIKARI | 73.69 | 34.86 | 85
264 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 4.3 | 1
265 | Central Drilling | Berhampur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 14.42 | 11
266 | Berhampore Mechanical | Berhampur Sub-Division | BASABARI PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01520/2023-2024 | 402/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 4.36 | 0 | 0
267 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.51 | 100
268 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 231/4 & 231/5) on railway land of mouza Hafania & Connecting with existing 160 mm dia uPVC distribution main line of Hafania ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000512/2021-2022 | 2480/MURD | 16/08/2021 | 60 | M/S NIRAPADA BHATTACHARJEE | 28.91 | 25.46 | 100
269 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 230/6 & 230/7) at Hafania mouza & Connecting with existing 110 mm dia uPVC distribution main line of Hafania ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000513/2021-2022 | 2481/MURD | 16/08/2021 | 60 | M/S NIRAPADA BHATTACHARJEE | 21.58 | 19.07 | 100
270 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Ground Water Based HAFANIA (ZONE-I) PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000842/2022-2023 | 745/MURD | 16/03/2023 | 747 | PAROMITA DEB | 416.04 | 177.04 | 40
271 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000265/2023-2024 | 1230/MURD/04 | 04/05/2023 | 0 | Resource Division | 10.57 | 0 | 0
272 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
273 | Berhampore Mechanical | Berhampur M/E Division | SHIFTING OF HT LINE AT HAFANIA Z-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/00431/2024-2025 | 146/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 7.3 | 0 | 0
274 | Berhampore Mechanical | Berhampur M/E Division | HAFANIA PH-I Z-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/01436/2023-2024 | 339/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 3.64 | 0 | 0
275 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,ZONE-I under HAFANIA ground water based water supply scheme under Block_ Suti-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000126/2023-2024 | 1913/MEDB | 16/06/2023 | 92 | CONCORD ENGINEERING | 33.22 | 0 | 0
276 | Murshidabad Division | Berhampur M/E Division | Rectification work from Raturi to Kalinagar in the road of Dangapara more to Raturi via HILORA, Kalinagar Road under berhampore Division-I PWD during the year of 2023-2024. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | BILL/01020/2023-2024 | 468-MSD/2023-24 | 04/01/2024 | 0 | EXECUTIVE ENGINEER, PWD, BERHAMPORE DIVISION-I | 78.16 | 0 | 0
277 | Murshidabad Division | Berhampur M/E Division | Providing FHTC of 1415 nos. household, Laying of Rising Main, Repair & Renovation of RCC 130 Cum OHR, special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works Augmentation work of Raturi (Zone-I) PWSS in SUTI-I Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000085/2023-2024 | 1455/MURD | 01/06/2023 | 180 | R.M. BHATTA | 91.23 | 12.74 | 15
278 | Murshidabad Division | Berhampur M/E Division | Sinking of 2NOS. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Raturi Zone-II Water Supply Scheme and Bahutuli Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000105/2024-2025 | 2195/MURD | 31/07/2024 | 30 | SARKAR WATER SUPPLY AGENCY | 23.56 | 0 | 50
279 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.21 | 100
280 | Murshidabad Division | Berhampur M/E Division | Sinking of 1NO. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Raturi Zone-I Water Supply Scheme at Suti-I Block of Jangipur Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000170/2024-2025 | 2957/MURD | 11/11/2024 | 15 | GAYEN ENTERPRISE | 11.73 | 0 | 0
281 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at RATURI ZONE -I Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000713/2023-2024 | 3838/MURD | 14/12/2023 | 21 | SUJIT KUMAR SAHA | 11.79 | 8.82 | 50
282 | Murshidabad Division | Berhampur M/E Division | Allied work for Road restoration damaged during laying of pipeline of Raturi Zone-I Piped Water Supply Scheme, Suti Block, Jangipur Sub-Division under Murshidabad Division, P.H.E dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000826/2023-2024 | 769/MURD | 13/03/2024 | 30 | S. DUTTA | 48.28 | 0 | 0
283 | Murshidabad Division | Berhampur M/E Division | Laying of distribution system for Augmentation work of RATURI ZONE I Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000856/2022-2023 | 792/MURD | 21/03/2023 | 722 | S. DUTTA | 56.15 | 0 | 30
284 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000205/2023-2024 | 1210/MURD/20 | 02/05/2023 | 0 | Resource Division | 27.82 | 0 | 0
285 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II, Zone-I under RATURI ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000131/2023-2024 | 1918/MEDB | 16/06/2023 | 92 | MENAKA ENTERPRISE | 20.8 | 0 | 5
286 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
287 | Berhampore Division I | Berhampur Division I | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of RAMNACHANDPUR ZONE - IV PWSS under Jal Jeevan Mission within Nawda Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000010/2025-2026 | 598/BD-I | 22/04/2025 | 60 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 19 | 0 | 0
288 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of Ramnachandpur Zone-IV" ground water supply scheme in NAWDA Block,under Berhampore Division-I, P.H.E Dte(Capacity-52.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000033/2024-2025 | 996/BD-I | 20/06/2024 | 365 | M/S RUBIET HOSSAIN | 159.77 | 0 | 0
289 | Berhampore Division I | Berhampur Division I | Augmentation of Ramnachandpur zone_IV Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in NAWDA Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000139/2023-2024 | 622/BD-I | 03/08/2023 | 821 | AJAY MONDAL | 277.49 | 0 | 20
290 | Berhampore Division I | Berhampur Division I | Construction Pump House Cum Chlorine Room at Head Work site of RAMNACHANDPUR ZONE-IV Water Supply Scheme under Jal Jevan Mission within Nawda Block under Berhampore Division-I, PHE.Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000331/2024-2025 | 282/BD-I | 12/02/2025 | 60 | MD NAJRUL ISLAM | 7.5 | 0 | 0
291 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at RAMNACHANDPUR ZONE - IV Water Supply Scheme( 1st & 2nd TW Site) within Nawda Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000374/2024-2025 | 429/BD-I | 19/03/2025 | 30 | GENUINE | 18.02 | 0 | 0
292 | Berhampore Division I | Berhampur Division I | RAMNACHANDRAPUR ZONE-IV to accommodate construction of Boundary Wall under Jal Jivan Mission of NAWDA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000448/2023-2024 | 451/BD-I | 15/03/2024 | 539 | PRAVAT KUMAR GHOSH | 21.46 | 0 | 95
293 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | RTOR000054/2023-2024 | 196/BD-I/27 | 09/02/2024 | 0 | Resource Division | 31.44 | 0 | 0
294 | Berhampore Division I | Berhampur M/E Division | Balance works i.c.w of Existing AIRP (Modified Sujapur Sadipur Model) capacity 53.12 cum/hr at Head Work Site of Jhumra Nayagram Water Supply Scheme under JJM within Lalgola block under Berhampore Division -I, P.H.E. Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000074/2025-2026 | 841/BD-I | 23/06/2025 | 30 | GITA CONSTRUCTION | 26.5 | 0 | 0
295 | Berhampore Division I | Berhampur M/E Division | Bored Cast-in-situ_M30_grade 450 mm. dia. 22.00 m (Shaft Length) R.C.C pile for construction of OHR at Head work site of Jhumra Nayagram Ground Piped Water Supply Scheme under Jal Jeevan Mission of Lalgola Block, Murshidabad district under Berhampore Division - I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000090/2024-2025 | 1302/BD-I | 07/08/2024 | 180 | AICH CONSTRUCTION | 26.19 | 0 | 100
296 | Berhampore Division I | Berhampur M/E Division | Augmentation of Jumra Nayagram Piped water supply scheme to accommodate construction of OHR,Arsenic cum Iron Removal Plant( AIRP ),Pump house,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000210/2022-2023 | 1621/BD-I | 02/03/2023 | 310 | AICH CONSTRUCTION | 360.29 | 12.38 | 5
297 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for JUMRA NAYAGRAM Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000260/2022-2023 | 1683/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.6 | 2.6 | 1
298 | Berhampore Division I | Berhampur M/E Division | Repair And Renovation Works Of OHR (250 Cum) of Ground water supply scheme for Jumra Nayagram of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000262/2023-2024 | 984/BD-I | 30/10/2023 | 30 | AJOY GHOSH | 8.56 | 0 | 0
299 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000009/2024-2025 | 1510/BD-I/3 | 12/09/2024 | 0 | Resource Division | 2.27 | 0 | 0
300 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000069/2023-2024 | 201/BD-1/10 | 10/02/2024 | 0 | Resource Division | 43.36 | 0 | 0
301 | Berhampore Mechanical | Berhampur M/E Division | JUMRA NAYAGRAM PH-1 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/01516/2023-2024 | 400/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 5.31 | 0 | 0
302 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under JUMRA NAYAGRAM ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000064/2023-2024 | 3779/MEDB | 03/11/2023 | 92 | JAL PRAVAHIKA PVT LTD | 22.38 | 0 | 5
303 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM (PART-B) ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000542/2024-2025 | 328/MEDB | 10/02/2025 | 89 | MERCURY ENGINEERING CO | 22.71 | 0 | 0
304 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 12.59 | 20
305 | Berhampore Division I | Raghunathganj Sub-Division | Balance work of Boundary Wall at Augmentation of Udaynagar Diar PWSS of Jalangi Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000028/2024-2025 | 984/BD-I | 19/06/2024 | 45 | BISWAS CONSTRUCTION | 11.94 | 0 | 0
306 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Udaynagar Diar Piped water supply scheme to accommodate construction of Pump House ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000214/2022-2023 | 1551/BD-I | 17/02/2023 | 720 | BISWAS CONSTRUCTION | 82.74 | 27.22 | 75
307 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for UDAYNAGARDIAR Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000281/2022-2023 | 1559/BD-I | 20/02/2023 | 10 | M/S SOBHA & CO | 2.53 | 2.48 | 100
308 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000013/2023-2024 | 61/BD-1/11 | 27/04/2023 | 0 | Resource Division | 26.29 | 0 | 0
309 | Berhampore Mechanical | Raghunathganj Sub-Division | AT UDAY NAGAR DIAR PH 2 ID 304244356 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | BILL/01480/2023-2024 | 373/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 3.85 | 0 | 0
310 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based KAKRAMARI (ZONE-I) &KAKRAMARI (ZONE-II) PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000568/2023-2024 | 3288/MURD | 19/10/2023 | 180 | BIJAY CHOWDHURY | 861.6 | 0 | 35
311 | Murshidabad Division | Berhampur M/E Division | Replacing of Filter media of Existing AIRP (Modified Sujapur Sadhipur Model ) of (Capacity 120 Cum/hr.) at Kankramari Water Supply Scheme of Jangipur Sub-Division under Murshidabad Division, PHEngineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000823/2023-2024 | 744/MURD | 12/03/2024 | 60 | SUMAN ENTERPRISE AND SUMAN AQUA | 42.03 | 0 | 100
312 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 7.5 | 100
313 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000246/2023-2024 | 1219/MURD/29 | 03/05/2023 | 0 | Resource Division | 53.62 | 0 | 0
314 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
315 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MOLLA PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division,P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000742/2022-2023 | 381/MURD | 10/02/2023 | 45 | NADIA TUBEWELLS | 16.81 | 7.59 | 95
316 | Murshidabad Division | Kandi Sub-Division | Formal Work Order For Construction of 150 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of MOLLA PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362345S000) [(i)Amount for LDS , R.Main & FHTC: Rs.1,98,91,791.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs. 1,23,31,559.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000749/2022-2023 | 415/MURD | 15/02/2023 | 776 | M/S NIRAPADA BHATTACHARJEE | 322.07 | 15.96 | 5
317 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | RTOR000009/2023-2024 | 1210/MURD/42 | 02/05/2023 | 0 | Resource Division | 32.6 | 0 | 0
318 | Berhampore Mechanical | Kandi Sub-Division | AT MOLLA PH 1 ID 304252903 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | BILL/01466/2023-2024 | 358/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 3.88 | 0 | 0
319 | Berhampore Mechanical | Kandi Sub-Division | AT MOLLA PH2 ID 304252910 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | BILL/01468/2023-2024 | 359/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 5.41 | 0 | 0
320 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MOLLA ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000101/2023-2024 | 1891/MEDB | 16/06/2023 | 776 | S.P. ENTERPRISE (SILIGURI) | 23.4 | 0 | 30
321 | Murshidabad Division | Berhampur M/E Division | Augmentation of NATIAL RAJANAGAR ZONE-I ,II,& III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000366/2023-2024 | 2724/MURD | 29/08/2023 | 765 | M/S. MOHAN LAL JAIN | 2092.12 | 615.3 | 56
322 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 5.23 | 1
323 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000255/2023-2024 | 1219/MURD/40 | 03/05/2023 | 0 | Resource Division | 69.3 | 0 | 0
324 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000388/2023-2024 | 526/MURD/05 | 19/02/2024 | 0 | Resource Division | 14.88 | 0 | 0
325 | Berhampore Mechanical | Berhampur M/E Division | SHIFTING OF HT LINE AT RAJAPUR ID 860296030 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/00178/2024-2025 | 17/WBSEDCL-JJM | 16/04/2024 | 0 | WBSEDCL | 4.36 | 0 | 0
326 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Natial Rajanagar Zone-I Piped water supply scheme Block_Jalangi Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000546/2024-2025 | 350/MEDB | 10/02/2025 | 89 | KARTICK BAL | 45.27 | 0 | 0
327 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of EROALI & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362274S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000711/2022-2023 | 90/MURD | 11/01/2023 | 841 | M/S. S. DAS AND ENTERPRISE | 833.44 | 306.53 | 38
328 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 7.69 | 80
329 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000036/2023-2024 | 1004/MURD/11 | 17/04/2023 | 0 | Resource Division | 47.05 | 0 | 0
330 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000369/2023-2024 | MURD/439/1 | 08/02/2024 | 0 | Resource Division | 27.28 | 0 | 0
331 | Berhampore Mechanical | Kandi Sub-Division | POWER CONNECTION AT PWSS PH 2 EROLI ID 304250314 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00182/2024-2025 | 45/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 4.22 | 0 | 0
332 | Berhampore Mechanical | Kandi Sub-Division | Eroali PH-1 Application No- 3004536843 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01177/2023-2024 | 241/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 3.74 | 0 | 0
333 | Berhampore Mechanical | Kandi Sub-Division | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Khargram and Nawda block Under District Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000053/2025-2026 | 45/4 | 29/05/2025 | 92 | EASTERN INDIA SALES & SERVICE | 15.17 | 0 | 0
334 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under EROALI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000667/2023-2024 | 3788/MEDB | 03/11/2023 | 92 | DEBJYOTI BASU | 35.17 | 0 | 0
335 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 100 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and Boundary wall and approach road for Augmentation of Jotsundar PWSS in Raghunathganj-II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000391/2023-2024 | 2771/MURD | 01/09/2023 | 730 | M/S AFSHAN CONSTRUCTION | 265.01 | 0 | 21
336 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Raghunathganj-II of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Giriya Kismat Water supply Scheme, Jotsundar Water Supply Scheme, Giria Water Supply Scheme Zone-I & II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000562/2022-2023 | 2912/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 12.39 | 2.49 | 100
337 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jot Sundar Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Raghunathganj-II Block under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000706/2023-2024 | 3808/MURD | 12/12/2023 | 21 | NILAVA GHOSHAL (BUMBA) | 23.54 | 0 | 100
338 | Murshidabad Division | Berhampur M/E Division | Work of Interconnection of D.I pipe line between 2nd Tube well Pump house to Rising main at Jot Sundar Water Supply Scheme under Jangipur Sub-Division P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/001267/2021-2022 | 386/JSD | 31/12/2021 | 30 | SAMAR MUKHERJEE | 1.9 | 1.9 | 0
339 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000146/2023-2024 | 1167/MURD/50 | 28/04/2023 | 0 | Resource Division | 9.38 | 0 | 0
340 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Jot Sundar Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000556/2024-2025 | 338/MEDB | 10/02/2025 | 89 | HANNAN BUILDERS PVT LTD | 22.72 | 0 | 0
341 | Murshidabad Division | Berhampur M/E Division | Augmentation of MURADPUR JALANGI ZONE-III /Tenya Zone-II & Zone-III PWSS Laying Distribution System, of JALANGI /Bharatpur-II Block , under Murshidabad Division PHE. Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000375/2023-2024 | 2755/MURD | 01/09/2023 | 720 | ULTRA CONSTRUCTION. | 100.45 | 0 | 95
342 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 1.86 | 100
343 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-II | Junior engineer-III | RTOR000237/2023-2024 | 1219/MURD/25 | 03/05/2023 | 0 | Resource Division | 10.21 | 0 | 0
344 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-III under MURADPUR JALANGI ground water based water supply scheme under Block_ JALANGI Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000111/2023-2024 | 3719/MEDB | 03/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 21.43 | 0 | 0
345 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000357/2023-2024 | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 1.62 | 100
346 | Murshidabad Division | Jangipur Sub-Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
347 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | RTOR000211/2023-2024 | 1210/MURD/26 | 02/05/2023 | 0 | Resource Division | 149.38 | 0 | 0
348 | Murshidabad Division | Berhampur Sub-Division | Construction 2 (Two ) Nos Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement and 210 mtr Boundary wall at Head Work site and 55Mtr at 2nd site of Sarbangapur Zone -IB , Bara Satui & Chandkati Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000044/2024-2025 | 1930/MURD | 03/07/2024 | 477 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 52.14 | 0 | 75
349 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 1159 nos household for Augmentation work of BARA SATUI PWSS in BERHAMPORE Block under Murshidabad Division , PHE.Dte. (part_C) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000100/2023-2024 | 1699/MURD | 28/06/2023 | 277 | S. ROY & CO. | 67.64 | 0 | 0
350 | Murshidabad Division | Berhampur Sub-Division | Construction of 300 Cum OHR, Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 180 Cum capacity, Construction of Boundary Wall for Augmentation work of BARA SATUI PWSS in BERHAMPORE Block under Murshidabad Division , PHE. Dte. (part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000195/2023-2024 | 2038/MURD | 26/07/2023 | 730 | SATELLITE CONSTRUCTION | 177.33 | 0 | 0
351 | Murshidabad Division | Berhampur Sub-Division | Laying of Distribution System, Construction Pump House with sanitary and Water Supply Arrangement, Repairing & Vertical Extension of Boundary Wall, Special repair and renovation of existing Pump House and Allied Works for Augmentation work of BARA SATUI PWSS in BERHAMPORE Block under Murshidabad Division , PHE. Dte.(part _B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000196/2023-2024 | 2037/MURD | 26/07/2023 | 180 | AMIT KUMAR GUPTA | 176.87 | 0 | 0
352 | Murshidabad Division | Berhampur Sub-Division | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 75
353 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.12 | 80
354 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 5.36 | 1
355 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000016/2024-2025 | 1811/MURD/15 | 20/06/2024 | 0 | Resource Division | 8.19 | 0 | 0
356 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000212/2023-2024 | 1219/MURD/03 | 03/05/2023 | 0 | Resource Division | 22.93 | 0 | 0
357 | Central Drilling | Berhampur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
358 | Berhampore Division I | Berhampur Division I | Replacement of Filter media of Existing AIRP of (Capacity 46 Cum/hr.) with allied work at Sadhukhali Zone-I Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000012/2024-2025 | 911/BD-I | 07/06/2024 | 30 | MS BAPPA ENTERPRISE | 17 | 0 | 0
359 | Berhampore Division I | Berhampur Division I | Construction of Boundary wall at 2nd Tube Well Site of SADHUKHALI ZONE -I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000014/2025-2026 | 603/BD-I | 22/04/2025 | 45 | BARUN DUTTA | 10.19 | 0 | 0
360 | Berhampore Division I | Berhampur Division I | Formal work order for Augmentation of Sadhukhali Zone-I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000183/2022-2023 | 1658/BD-I | 13/03/2023 | 984 | NOVELTY CONSTRUCTION | 181.42 | 134.82 | 95
361 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sadhukhali Zone-I Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000242/2023-2024 | 939/BD-I | 11/10/2023 | 30 | B.R SUPPLIERS | 9 | 0 | 0
362 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SADHUKHALI Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000267/2022-2023 | 1690/BD-I | 14/03/2023 | 10 | TECHVISION | 2.67 | 2.67 | 100
363 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | RTOR000086/2023-2024 | 196/BD-I/21 | 09/02/2024 | 0 | Resource Division | 33.74 | 0 | 0
364 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-I under SADHUKHALI ground water based water supply scheme under Block_ Beldanga-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000073/2023-2024 | 4353/MEDB | 29/12/2023 | 369 | C.M. ENTERPRISE | 19.4 | 0 | 8
365 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sibnagar Zone-IV under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000060/2023-2024 | 157/BD-I | 15/05/2023 | 90 | GANGULY ENTERPRISE | 30.54 | 0 | 0
366 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Shibnagar Zone-IV village, Block:- Nawda under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000185/2023-2024 | 3046/MEDB | 02/08/2023 | 92 | TARUN KUMAR BHATTACHARYA | 6.26 | 0 | 0
367 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 4.47 | 100
368 | Murshidabad Division | Berhampur M/E Division | Augmentation of SHIBNAGAR LASKARPUR (Zone-I) Part-B & Garibpur (Zone-I) Part-B PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000440/2023-2024 | 2888/MURD | 12/09/2023 | 750 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 226.15 | 0 | 75
369 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.09 | 100
370 | Murshidabad Division | Berhampur M/E Division | Formal work order for BAURIPUNI PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000851/2022-2023 | 788/MURD | 21/03/2023 | 365 | KISMAT ARA BEGAM | 355.05 | 0 | 10
371 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000288/2023-2024 | 1230/MURD/30 | 04/05/2023 | 0 | Resource Division | 21.71 | 0 | 0
372 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000381/2023-2024 | 495/MURD/13 | 15/02/2024 | 0 | Resource Division | 7.53 | 0 | 0
373 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION BAURIPUNI PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01482/2023-2024 | 390/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 11.71 | 0 | 0
374 | Berhampore Mechanical | Berhampur M/E Division | BAURIPUNI PH-1 NEW CONNECTION | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01483/2023-2024 | 391/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 3.47 | 0 | 0
375 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BAURIPUNI ground water based water supply scheme under Block_ Suti_II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000086/2023-2024 | 1900/MEDB | 16/06/2023 | 92 | DAS ENTERPRISE ( MANGO LANE) | 33.5 | 0 | 0
376 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Durgapur zone-IV under Lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000052/2023-2024 | 151/BD-I | 15/05/2023 | 90 | RISHIKA GHOSH | 30.23 | 0 | 0
377 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Durgapur Zone-IV village, Block:- Lalgola under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000632/2023-2024 | 3659/MEDB | 03/11/2023 | 92 | DIPALI CONSTRUCTION | 6.12 | 0 | 0
378 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for PRASADPUR ZONE-III Ground Based Water Supply Scheme in Suti-II Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000051/2025-2026 | 1226/MURD | 28/05/2025 | 60 | INDRAJIT DUBEY | 19.62 | 0 | 0
379 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.05 | 100
380 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
381 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000091/2023-2024 | 1147/MURD/6 | 27/04/2023 | 0 | Resource Division | 0.55 | 0 | 0
382 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 22.63 | 11
383 | Berhampore Mechanical | Berhampur M/E Division | PRASADPUR Z-III PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01486/2023-2024 | 394/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 3.78 | 0 | 0
384 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION PRASADPUR Z-III PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01488/2023-2024 | 395/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 3.71 | 0 | 0
385 | Murshidabad Division | Kandi Sub-Division | Continuation Work Order for the work of Hiring of Maxi cab (Non- Air Condition, Bharat Stage III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months i.e. 01.08.2025 TO 31.12.2025. VEHICLE NO - WB57F2352 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000097/2025-2026 | 97/KSD | 17/07/2025 | 150 | H.MONDAL CONSTRUCTION | 0.87 | 0 | 0
386 | Murshidabad Division | Kandi Sub-Division | Augmentation of MURADPUR JALANGI ZONE-III /Tenya Zone-II & Zone-III PWSS Laying Distribution System, of JALANGI /Bharatpur-II Block , under Murshidabad Division PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000375/2023-2024 | 2755/MURD | 01/09/2023 | 720 | ULTRA CONSTRUCTION. | 100.45 | 0 | 95
387 | Murshidabad Division | Kandi Sub-Division | Continuation Work Order for the work of Hiring of Maxi cab (Non- Air Condition, Bharat Stage III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months i.e. 28.02.2025 TO 31.07.2025. VEHICLE NO - WB57F2352 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000474/2024-2025 | 41/KSD | 25/02/2025 | 150 | H.MONDAL CONSTRUCTION | 0.87 | 0 | 0
388 | Murshidabad Division | Kandi Sub-Division | Laying of Rising main , Distribution System, FHTC, OHR Repairing (Capacity 600 cum), , Sinking of Tube Well , Construction of pump house & Boundary wall and approach road for Augmentation of Tenya Zone-III PWSS in Bharatpur-II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000613/2023-2024 | 3375/MURD | 31/10/2023 | 793 | H.ENTERPRISE | 499.38 | 0 | 53
389 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000005/2023-2024 | 1004/MURD/A | 11/04/2023 | 0 | Resource Division | 122.58 | 0 | 0
390 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000029/2023-2024 | 1004/MURD/7 | 11/04/2023 | 0 | Resource Division | 42.04 | 0 | 0
391 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
392 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I A & Uttar Mahammadpur Water Supply Scheme at Head Work Site, 2nd Site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000123/2023-2024 | 1773/MURD | 06/07/2023 | 695 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 80
393 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
394 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Sankopara halt Station (TP NO 243/5 & 243/6) on railway land of mouza-Jigari kulgachi & Connecting with existing 150 mm dia Rising main line of Mahadevnagar Zone - I ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000424/2021-2022 | 2478/MURD | 16/08/2021 | 60 | DECON INDIA | 26.25 | 25.17 | 100
395 | Murshidabad Division | Berhampur M/E Division | Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 1 to 23 & N.P 25 to 33 and 110 mm Dia N.P 20 to 33,90 mm OD N.P 17 to 19 at Dakshin,Uttar Mahadebnagar & Kagchipara for smooth water supply arrangement in Mahadebnagar Zone-1 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000745/2021-2022 | 244/JSD | 27/08/2021 | 10 | PRAVAT KUMAR GHOSH | 4.86 | 0 | 0
396 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, FHTC, construction of OHR (Capacity 300 & 400 cum), Sinking of Tube Well , and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of MAHADEBNAGAR ZONE- IA,IB,IC ,IIA & IIB PWSS in Farakka Block, Murshidabad District under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000790/2023-2024 | 441/MURD | 08/02/2024 | 693 | MACKINTOSH BURN LIMITED | 1715.31 | 0 | 36
397 | Berhampore Mechanical | Berhampur M/E Division | POWER CONNECTION AT PWSS PH1 Z 1A MADEBNAGAR APPLICATION NO.3004627412 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | BILL/00188/2024-2025 | 42/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 7.09 | 0 | 0
398 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IA under Mahadebnagar ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000232/2023-2024 | 3669/MEDB | 03/11/2023 | 92 | M/S SAJAHAN CHOWDHURY | 22.78 | 0 | 70
399 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 10
400 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, 2183 nos FHTC, construction of OHR (Capacity 350 cum), Repairing of OHR , Sinking of Tube Well , Repairing of pump house, Repairing of Boundary Wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Andhua Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000755/2023-2024 | 138/MURD | 16/01/2024 | 365 | NAYLA CONSTRUCTION | 836.98 | 0 | 35
401 | Murshidabad Division | Berhampur M/E Division | Providing Functional Household Tap Connections (FHTC) 1261 nos in connection with Jal Swapna (Jal Jeevan Mission ) of Mouza Jafarganj ( Village Code -313809) under Andhua Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000898/2022-2023 | 1082/ MURD | 27/04/2022 | 45 | MARUTI CONSTRUCTION AND CO. | 62.56 | 7.17 | 0
402 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000163/2023-2024 | 1180/MURD/26 | 29/04/2023 | 0 | Resource Division | 52.49 | 0 | 0
403 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000552/2024-2025 | 334/MEDB | 10/02/2025 | 89 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 23.19 | 0 | 0
404 | Murshidabad Division | Kandi Sub-Division | Repair work of concrete road between node point 52-53 at Godapara of Panchthupi Zone -III Piped Water Supply Scheme under Jal Jeevan Mission under Kandi Sub Division, P.H.Engineering Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000158/2024-2025 | 149/KSD | 28/10/2024 | 30 | M/S BHUBAN DAS | 0.96 | 0 | 0
405 | Murshidabad Division | Kandi Sub-Division | Repair work of concrete road between node point 28-41-45-50 at Godapara of Panchthupi Zone -III Piped Water Supply Scheme under Jal Jeevan Mission under Kandi Sub Division, P.H.Engineering Dte. in the district of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000159/2024-2025 | 150/KSD | 28/10/2024 | 30 | M/S BHUBAN DAS | 0.97 | 0 | 0
406 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Augmentation of PANCHTHUPI ZONE-III PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000834/2022-2023 | 740/MURD | 16/03/2023 | 1112 | TIRUPATI CONSTRUCTION | 270.65 | 136.72 | 32
407 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000260/2023-2024 | 1230/MURD/08 | 04/05/2023 | 0 | Resource Division | 19.32 | 0 | 0
408 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 10.81 | 11
409 | Berhampore Mechanical | Kandi Sub-Division | POWER CONNECTION AT PWSS PH1 Z3 PANCHTHUPI ID 304256293 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00184/2024-2025 | 39/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 10.15 | 0 | 0
410 | Berhampore Mechanical | Kandi Sub-Division | POWER CONNECTION AT PWSS PH 2 Z 3 PANCHTHUPI ID 304256294 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00185/2024-2025 | 40/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 7.1 | 0 | 0
411 | Berhampore Mechanical | Kandi Sub-Division | ADDITIONAL QTN FOR PANCHTHUPI ZONE III PHI | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00898/2024-2025 |  | 06/09/2024 | 0 | WBSEDCL | 7.3 | 0 | 0
412 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for KADOA Zone ¿II Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000020/2025-2026 | 985/MURD | 02/05/2025 | 60 | ARINDAM MAJUMDAR | 23.01 | 0 | 0
413 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.16 | 100
414 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
415 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000088/2023-2024 | 1147/MURD/2 | 27/04/2023 | 0 | Resource Division | 26.13 | 0 | 0
416 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT KADOA Z2 PH1 ID304242107, Application NO 3004557257 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/01409/2023-2024 | 330/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 4.38 | 0 | 0
417 | Berhampore Mechanical | Berhampur M/E Division | Quotation for Kadoa PH No-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/01435/2023-2024 | 328/WBSEDCL-JJM | 06/02/2024 | 0 | WBSEDCL | 11.21 | 0 | 0
418 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-II of KADOA ground water based water supply scheme under Block- Suti-II Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000134/2023-2024 | 1921/MEDB | 16/06/2023 | 92 | A.K. SIKDAR | 11.17 | 0 | 0
419 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.16 | 100
420 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0
421 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
422 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000090/2023-2024 | 1147/MURD/5 | 27/04/2023 | 0 | Resource Division | 31.5 | 0 | 0
423 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 15.25 | 11
424 | Murshidabad Division | Kandi Sub-Division | BINDARPUR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-I of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000286/2023-2024 | 2641/MURD | 23/08/2023 | 740 | BERHAMPORE CONSTRUCTION SYNDICATE PVT. LTD. | 606.88 | 0 | 20
425 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000056/2023-2024 | 1075/MURD | 19/04/2023 | 0 | Resource Division | 31.02 | 0 | 0
426 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BINDARPUR ground water based water supply scheme under Block_ BHARATPUR-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000052/2023-2024 | 1925/MEDB | 16/06/2023 | 92 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 35.06 | 0 | 0
427 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village ACHHOAN (Village Code 315979) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. |  |  | ORD/000773/2020-2021 | 3036/MURD | 07/12/2020 | 45 | LAXMI CONSTRUCTION | 7.78 | 0 | 0
428 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotaryrig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kasiadanga Zone- I Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Raghunathganj-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000111/2023-2024 | 1753/MURD | 06/07/2023 | 21 | KALACHAND DAS | 35.27 | 25.93 | 70
429 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHORSALA and KASIADANGA ZONE - I Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000370/2023-2024 | 2722/MURD | 29/08/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0
430 | Murshidabad Division | Berhampur M/E Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
431 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 500 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Kasiadanga Zone I & II PWSS in Raghunathganj II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000552/2023-2024 | 3190/MURD | 12/10/2023 | 365 | ASTRA | 861.48 | 0 | 0
432 | Murshidabad Division | Berhampur M/E Division | Painting Boundary wall and under ground pipe line for OHR wash out water of Kashiadanga (Zone-I) Water supply Scheme under Jangipur Sub-Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000660/2020-2021 | 23/JSD | 25/01/2021 | 30 | SUJIT KR DEY | 2.24 | 2.24 | 1
433 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000043/2024-2025 | MURD/2991/02 | 13/11/2024 | 0 | Resource Division | 42.68 | 0 | 0
434 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000099/2023-2024 | 1167/MURD/8 | 28/04/2023 | 0 | Resource Division | 34.82 | 0 | 0
435 | Murshidabad Division | Berhampur M/E Division | Painting Boundary wall and under ground pipe line for OHR wash out water of Kashiadanga (Zone-I) Water supply Scheme under Jangipur Sub-Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | VCH/001068/2022-2023 |  | 29/11/2022 | 0 | SUJIT KANTI DEY | 2.24 | 0 | 0
436 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under KASIADANGA ground water based water supply scheme under Block_ RAGHUNATHGANJ-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000066/2023-2024 | 4335/MEDB | 29/12/2023 | 183 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 21.6 | 0 | 0
437 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based SIMULIA & JAULIA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-II of Kandi Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000587/2023-2024 | 3322/MURD | 22/10/2023 | 649 | VISION ENTERPRISE | 355.14 | 0 | 10
438 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 2.62 | 80
439 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional HouseHold Connection of different existing PWSS (SIMULIA & JAMULIA PWSS Scheme, Block- BHARATPUR-II to be Augmentation/Rejuvination under Murshidabad Division P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000822/2021-2022 | 3261/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.78 | 2.97 | 1
440 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000003/2023-2024 | 1004/MURD/1 | 11/04/2023 | 0 | Resource Division | 13.32 | 0 | 0
441 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II under Simulia Jaulia ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000242/2023-2024 | 3678/MEDB | 03/11/2023 | 790 | SARKAR CONSTRUCTION | 21.39 | 16.4 | 15
442 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 1.67 | 80
443 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 3.11 | 76
444 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000258/2023-2024 | 1230/MURD/01 | 04/05/2023 | 0 | Resource Division | 30.12 | 0 | 0
445 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 6.66 | 11
446 | Berhampore Mechanical | Kandi Sub-Division | ADDITIONAL QUOTATION FOR PANCHTHUPI ZONE-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01016/2024-2025 |  | 24/09/2024 | 0 | WBSEDCL | 7.3 | 0 | 0
447 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 5.56 | 11
448 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Hariganja" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-30 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000029/2024-2025 | 992/BD-I | 20/06/2024 | 365 | NATIONAL CONSTRUCTION | 142.73 | 0 | 5
449 | Berhampore Division I | Berhampur Division I | HARIGANJA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jeevan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000043/2023-2024 | 74/BD-I | 28/04/2023 | 730 | M/S SAJEDA ENTERPRISE | 141.8 | 0 | 65
450 | Berhampore Division I | Berhampur Division I | HARIGANJA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000284/2023-2024 | 1001/BD-I | 31/10/2023 | 90 | SUSHANTA MANDAL | 39.1 | 0 | 31
451 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at HARIGANJ PWSS (H/W Site) under Jal Jeevan Mission in Beldanga-II Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000381/2024-2025 | 443/BD-I | 20/03/2025 | 15 | M/S S. DAS & ENTERPRISE | 9 | 0 | 0
452 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000021/2024-2025 | 2096/BD-I/2 | 25/11/2024 | 0 | Resource Division | 5.01 | 0 | 0
453 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000029/2023-2024 | 61/BD-1/16 | 27/04/2023 | 0 | Resource Division | 12.25 | 0 | 0
454 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION AT HARIGANJ PH-I | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | BILL/00614/2024-2025 | 184/WBSEDCL-JJM | 09/08/2024 | 0 | WBSEDCL | 5.15 | 0 | 0
455 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III under HARIGANJA ground water based water supply scheme under Block_LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000023/2025-2026 | 1152/MEDB | 14/05/2025 | 92 | ASSOCIATED ELECTRICAL CO. | 10.83 | 0 | 0
456 | Murshidabad Division | Berhampur Sub-Division | Allied work of connection of Rising and Distribution main with supply of materials and construction of sluice valve chamber at Char Mahula water supply scheme under Berhampore sub division, P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000054/2024-2025 | 1985/MURD | 08/07/2024 | 60 | SUPIA CONSTRUCTION | 4.47 | 0 | 85
457 | Murshidabad Division | Berhampur Sub-Division | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 75
458 | Murshidabad Division | Berhampur Sub-Division | Augmentation of CHARMAHULA PWSS under Jal Jeevan Mission of BERHAMPORE Block, BERHAMPORE Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000528/2023-2024 | 3119/MURD | 05/10/2023 | 543 | M/S. BHABESH HALDER | 249.71 | 0 | 35
459 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) (338 Nos) in connection with (Jal Jeevan Mission ) and under command area of village Char Mahula ( Village Code - 315354) & Meliani ( Village Code -315619) under Char Mahula Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga-I Block under Murshidabad Division P.H.E Dte. . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000635/2023-2024 | 3456/MURD | 06/11/2023 | 851 | ANUPA ENTERPRISE | 12.75 | 0 | 70
460 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 4.78 | 1
461 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000017/2024-2025 | 1811/MURD/16 | 20/06/2024 | 0 | Resource Division | 20.22 | 0 | 0
462 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000152/2023-2024 | 1180/MURD/02 | 29/04/2023 | 0 | Resource Division | 18.43 | 0 | 0
463 | Central Drilling | Berhampur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 7.44 | 11
464 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Rejinagar Zone-I PWSS of accommodate with Repairing of Switch Room, Repairing of Boundary Wall, 400 CUM OHR, in Beldanga II Block within Murshidabad District under Murshidabad Division, PHE Dte. [Part B] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000527/2023-2024 | 3118/MURD | 05/10/2023 | 180 | JIT CONSTRUCTION | 155.69 | 0 | 0
465 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 279 nos household , Laying of Distribution System, Rising Main for Augmentation work of Rejinagar Zone-I PWSS within Beldanga-II Block under Murshidabad Division , PHE.Dte. ( PART - A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000584/2023-2024 | 3334/MURD | 23/10/2023 | 520 | AJAY MONDAL | 201.09 | 0 | 70
466 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.01 | 80
467 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/001641/2021-2022 | 480/MURD | 22/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 10.77 | 0
468 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000020/2024-2025 | 1811/MURD/19 | 20/06/2024 | 0 | Resource Division | 6.64 | 0 | 0
469 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000135/2023-2024 | 1167/MURD/51 | 28/04/2023 | 0 | Resource Division | 127.23 | 0 | 0
470 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-I under Rejinagar ground water based water supply scheme under Block_ Beldanga-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000236/2023-2024 | 3672/MEDB | 03/11/2023 | 92 | MASSK ENGINEERING WORKS | 33.88 | 0 | 0
471 | Murshidabad Division | Berhampur M/E Division | Allied work of construction of culvert at kadoa Zone-I 2nd T.W site and approach road for H/W site & 2nd T.W site for Augmentation work under Jangipur sub division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000067/2024-2025 | 1988/MURD | 08/07/2024 | 60 | M/S BAPPA ENTERPRISE | 16.72 | 0 | 0
472 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 2.61 | 100
473 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main, Construction Pump House with sanitary and Water Supply Arrangement (T/W-I), Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Work, Construction of Boundary Wall (For T/W-I) =100 mtrs & Repair of Boundary Wall (50m +50m) =100 m at T/W-II site for Augmentation of KADOA (Zone - I) Part-A Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. (i)Amount for Construction Part: 5,87,696.00/ (ii)Amount for Pipeline Part: 22,96,300.00/- (Attached as Annexure -XII) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000781/2022-2023 | 685/MURD | 10/03/2023 | 180 | M/S BAPPA ENTERPRISE | 28.81 | 0 | 0
474 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000196/2023-2024 | 1210/MURD/16 | 02/05/2023 | 0 | Resource Division | 7.37 | 0 | 0
475 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-I under KADOA ,Part-A ground water based water supply scheme under Block_ Suti-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000129/2023-2024 | 1916/MEDB | 16/06/2023 | 92 | S. G. TECHNICAL SERTIVCE | 35.09 | 0 | 0
476 | Murshidabad Division | Kandi Sub-Division | GUNDIRIA PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000149/2023-2024 | 1898/MURD | 17/07/2023 | 624 | MAA MANSAHA CONSTRUCTION | 119.11 | 0 | 65
477 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | RTOR000069/2023-2024 | 1075/MURD/11 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
478 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under GUNDIRIA ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000269/2023-2024 | 3706/MEDB | 03/11/2023 | 92 | M/S SAJAHAN CHOWDHURY | 21.21 | 11.7 | 35
479 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 9.49 | 20
480 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MALIPUR and Adjoining Mouzas PWSS (TW-II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (01 Nos TW) | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000060/2025-2026 | 772/BD-I | 22/05/2025 | 15 | M/S GUHA AND ROY ENTERPRISE | 9 | 0 | 0
481 | Berhampore Division I | Berhampur Division I | MALIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000099/2023-2024 | 209/BD-I | 17/05/2023 | 720 | PRANAB KUMAR GHOSH | 39.48 | 0 | 55
482 | Berhampore Division I | Berhampur Division I | MALIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. . | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000131/2023-2024 | 610/BD-I | 02/08/2023 | 900 | ROY CONSTRUCTION (AVIJIT ROY) | 85.64 | 51.33 | 90
483 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | RTOR000044/2023-2024 | 61/BD-1/30 | 27/04/2023 | 0 | Resource Division | 18.6 | 0 | 0
484 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION MALIPUR PH-1 | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | BILL/01490/2023-2024 | 372/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 5.26 | 0 | 0
485 | Murshidabad Division | Kandi Sub-Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
486 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based Surangapur Zone - II (PART -A), Salar PWSS Zone-IA, IB, IIA & IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Nowda & Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 570 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 20
487 | Murshidabad Division | Kandi Sub-Division | Augmentation of Salar PWSS Zone-IA,IB,IIA,IIB to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 4 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 4no, Construction of Boundary Wall of 600 m, Construction of 400 Cum OHR(1 no) & 300 Cum OHR(2 nos) with sub soil investigation under Jal Jeevan Mission of Bharatpur II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000647/2023-2024 | 3474/MURD | 07/11/2023 | 511 | SUJIT KUMAR SAHA | 575.6 | 0 | 10
488 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II ,Zone-IIA under Salar ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000241/2023-2024 | 3677/MEDB | 03/11/2023 | 92 | SARKAR CONSTRUCTION | 21.35 | 15.63 | 10
489 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) of 1994 nos in connection with Jal Swapna (Jal Jeevan Mission ) under command area of Village of Khidirpur ( Village Code -315469) under Kismat Emadpur Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000026/2022-2023 | 1056/MURD | 25/04/2022 | 60 | MAMATA USHA ENTERPRISE | 99.92 | 0 | 1
490 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) of 1428 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lalnagar ( Village Code -315471) under Kismat Emadpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000028/2022-2023 | 1055/MURD | 25/04/2022 | 60 | M/S GUHA & ROY ENTERPRISE | 75.91 | 0 | 0
491 | Murshidabad Division | Berhampur Sub-Division | Extension of UPVC pipeline for Functional Household Tap Connections (FHTC) under village of Baruipara (Village Code -315465) under KismatImadpur Water Supply Scheme under Berhampore Sub-Division under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000166/2022-2023 | 155/BSD | 12/04/2022 | 30 | SAMAR MUKHERJEE | 4.82 | 3.39 | 1
492 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Baruipara (Village code 315465) under Kismat Imadpur Ground Based Water Supply Scheme for Arsenic Affected Area of Hariharpara Block, under Murshidabad Division, PHE Dte. Scheme ID 5186280 in the District of Murshidabad. (Sl No-38) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000305/2020-2021 | 728/MURD | 25/02/2021 | 180 | SAMAR MUKHERJEE | 53.09 | 49.81 | 1
493 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kismat Imadpur (Village code 315468) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Hariharpara Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad.Scheme ID 5186280 (Sl-37) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000532/2020-2021 | 696/MURD | 24/02/2021 | 180 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 162.04 | 138.1 | 1
494 | Murshidabad Division | Berhampur Sub-Division | Extension of UPVC pipeline for Functional Household Tap Connections (FHTC) under village of Baruipara (Village Code -315465) under Kismat Imadpur Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000603/2022-2023 | 256/BSD | 31/05/2022 | 30 | SAMAR MUKHERJEE | 4.51 | 4.5 | 1
495 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jamalpur (Village code 315469) under Kismat Imadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Hariharpara Block, under Murshidabad Division, PHE Dte. Scheme ID - 5186280 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000614/2020-2021 | 3141 /MURD | 11/12/2020 | 60 | MEGHNA CONSTRUCTION (PROP.: ASARUL HOQUE) | 38.95 | 65.41 | 1
496 | Murshidabad Division | Berhampur Sub-Division | Boundary wall at Head works site for part (B) of Kismat Emadpur water supply Scheme under Berhampore Sub Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001839/2021-2022 | 99/BSD | 22/03/2022 | 30 | AZAD ENTERPRISE | 4.52 | 0 | 0
497 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000019/2021-2022 | 539/4/MURD | 25/02/2022 | 0 | Resource Division | 18.8 | 0 | 0
498 | Murshidabad Division | Berhampur Sub-Division | HOLDING AWARENESS PROGRESS AT DIFFERENT G.P, TNO- 339/21-22/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/000863/2021-2022 | 205-MSD/21-22 | 08/12/2021 | 0 | IMAGIN | 3.51 | 0 | 0
499 | Murshidabad Division | Kandi Sub-Division | Laying of Rising Main , Distribution System, FHTC, OHR Repairing (Capacity 450 cum), , Sinking of Tube Well , Repairing of pump house & Boundary wall and approach road for Augmentation of Tenya Zone-I PWSS in Bharatpur-II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000439/2023-2024 | 2887/MURD | 12/09/2023 | 150 | BURIMA CONSTRUCTION | 250.71 | 0 | 20
500 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 4.23 | 76
501 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000007/2023-2024 | 1004/MURD/2 | 11/04/2023 | 0 | Resource Division | 49.59 | 0 | 0
502 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
503 | Murshidabad Division |  | Last mile connectivity and providing 10197 nos Funcational House Hold Connection from Zone- IV of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. |  |  | ORD/000174/2024-2025 | 3075/MURD | 26/11/2024 | 120 | H.I.ENTERPRISE | 608.95 | 0 | 0
504 | Murshidabad Division | Berhampur M/E Division | Sinking of (300 mm x 200 mm) dia Big dia tube well 75 mtr. Deep by direct rotary rig method using UPVC Pipe and RDS filter at Village Bhasaipaikar(313879) in connection with FHTC work of Bhasaipaikar(Zone-I) Water Supply Scheme (Scheme ID- 0001723333) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | ORD/000091/2022-2023 | 237/JSD | 05/05/2022 | 30 | DIPAYAN DEY | 4.42 | 3.99 | 0
505 | Murshidabad Division | Berhampur M/E Division | Supply of UPVC Pipe and RDS filter for the work of Sinking of (300 mm x 200 mm) dia Big dia tube well at Village Bhasaipaikar(313879) in connection with FHTC work of Bhasaipaikar(Zone-I) Water Supply Scheme of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | ORD/000092/2022-2023 | 238/JSD | 05/05/2022 | 30 | DIPAYAN DEY | 4.61 | 2.32 | 0
506 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
507 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0
508 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing and Approved from the N.H.A.I Authorities including supply of 200 mm dia 8 mm thick MS Water Carrying Pipe, 600 mm dia 10 mm thick MS casing pipe and pushing of casing pipe by Hydraulic Jacking Technique method across at chainage 276+100 of the N.H- 34 of at Mouza-Ratanpur of Bhasaipaikar W/S Scheme under Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | ORD/000824/2023-2024 | 745/MURD | 12/03/2024 | 90 | M/S. GOUTAM ROY | 37 | 0 | 0
509 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | RTOR000118/2023-2024 | 1167/MURD/12 | 28/04/2023 | 0 | Resource Division | 73.37 | 0 | 0
510 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-IA under Bhasaipaikar ground water based water supply scheme under Block_ Samserganj, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | ORD/000246/2023-2024 | 3682/MEDB | 03/11/2023 | 92 | CONCORD ENGINEERING | 34.17 | 0 | 0
511 | Murshidabad Division | Berhampur M/E Division | Ground Water based piped water supply scheme for Hazipur Part- B village, Block:- Suti-II, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000214/2023-2024 | 2329/MURD | 02/08/2023 | 60 | SHIRSHENDU MUKHERJEE | 30.55 | 0 | 0
512 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-III | RTOR000228/2023-2024 | 1219/MURD/12 | 03/05/2023 | 0 | Resource Division | 14.34 | 0 | 0
513 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT HAZIPUR MINI PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-III | BILL/00518/2024-2025 |  | 10/07/2024 | 0 | WBSEDCL | 0.13 | 0 | 0
514 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT HAZIPUR MINI PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-III | BILL/00524/2024-2025 | 164/WBSEDCL-JJM | 29/07/2024 | 0 | WBSEDCL | 0.13 | 0 | 0
515 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT HAZIPUR MINI PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-III | BILL/01095/2024-2025 |  | 12/11/2024 | 0 | WBSEDCL | 0.59 | 0 | 0
516 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hazipur Part-A village, Block:- Suti-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000196/2023-2024 | 3055/MEDB | 02/08/2023 | 92 | M/S MANABESH ROY | 6.15 | 0 | 0
517 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hazipur Part-B village, Block:- Suti-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000197/2023-2024 | 3056/MEDB | 02/08/2023 | 792 | MONI ELECTRICAL WORKS | 6.27 | 0 | 20
518 | Berhampore Division I | Raghunathganj Sub-Division | Relaying of Different dia UPVC pipeline instead of damage portion in between node point (mouza - Maheswarpur, Chatra, Char Alampur) under Muktarpur ground water supply scheme of Raghunathganj Sub- Division under Berhampore Division - I, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000267/2021-2022 | 1109/BD-I | 28/06/2021 | 30 | S.P CONSTRUCTION | 35.66 | 28 | 1
519 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 12.79 | 20
520 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KRISHNAPUR DINURPARA PWSS (2nd TW Site) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidbad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000015/2025-2026 | 604/BD-I | 22/04/2025 | 15 | M/S BIMALENDU BOSE | 9.01 | 0 | 0
521 | Berhampore Division I | Berhampur M/E Division | KRISHNAPUR DINURPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000166/2023-2024 | 652/BD-I | 08/08/2023 | 850 | M/S GOUTAM CHAKRABORTY | 232.47 | 0 | 10
522 | Berhampore Division I | Berhampur M/E Division | KRISHNAPUR DINURPARA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000167/2023-2024 | 653/BD-I | 08/08/2023 | 601 | SOUMYADIP MISRA | 326.54 | 0 | 10
523 | Berhampore Division I | Berhampur M/E Division | KRISHNAPUR DINURPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000168/2023-2024 | 654/BD-I | 08/08/2023 | 549 | ULTRA CONSTRUCTION | 91.86 | 0 | 50
524 | Berhampore Division I | Berhampur M/E Division | KRISHNAPURDINURPARA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000186/2023-2024 | 730/BD-I | 16/08/2023 | 90 | M/S SWAPAN KUAMR NATH & CO | 72.82 | 13.87 | 41
525 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000098/2023-2024 | 201/BD-1/27 | 10/02/2024 | 0 | Resource Division | 34.21 | 0 | 0
526 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000112/2023-2024 | 304/BD-1/1 | 22/02/2024 | 0 | Resource Division | 21.31 | 0 | 0
527 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT KRISHNAPUR DINURPARA PH-1 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/00666/2024-2025 |  | 03/09/2024 | 0 | WBSEDCL | 3.4 | 0 | 0
528 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR DINURPARA PUMP HOUSE III , BLOCK - LALGOLA , DISTRICT - MURSHIDABAD. under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000024/2025-2026 | 1153/MEDB | 14/05/2025 | 92 | DAS ENTERPRISE (CHOA) | 11.82 | 0 | 0
529 | Murshidabad Division | Berhampur M/E Division | Allied & Balance Work for Construction of Boundary wall, Land Development ,Road restoration damaged during laying of pipeline, Path Way & Soil Test for Over Head Reservoir of Paschim Char Majhardiar & Adjoining Mouzas Water Supply Scheme in Rani Nagar-I Block of Islampur Sub-Division, under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000195/2024-2025 | 3230/MURD | 10/12/2024 | 369 | M/S. SARKAR CONSTRUCTION | 71.53 | 0 | 0
530 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 2.57 | 90
531 | Murshidabad Division | Berhampur M/E Division | Construction of Ground Water Based Paschim Char Majhardiar PWSS of accommodate FHTC(2246 Nos), Laying Distribution System, Laying Rising Main,Over Head Reservoir ( 500 CUM Capacity), Switch Room, Boundary Wall in Raninagar - II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000758/2023-2024 | 140/MURD | 16/01/2024 | 716 | M/S. SARKAR CONSTRUCTION | 468.58 | 0 | 80
532 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT PASCHIMCHAR CHAR MAJHARDIAR ID 304495841 | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01116/2024-2025 |  | 25/11/2024 | 0 | WBSEDCL | 3.4 | 0 | 0
533 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT PASCHIMCHAR CHAR MAJHARDIAR ID 304495841 | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01123/2024-2025 | 267/WBSEDCL-JJM | 28/11/2024 | 0 | WBSEDCL | 3.4 | 0 | 0
534 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under Paschim Char Majhardiar ground water based water supply scheme under Block_ Raninagar-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000657/2023-2024 | 590/MEDB | 31/01/2024 | 90 | SURAKSHA | 34.39 | 0 | 0
535 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Tenya Zone - II Water Supply Scheme and Kurulia Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000109/2023-2024 | 1751/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 27.64 | 0 | 50
536 | Murshidabad Division | Kandi Sub-Division | KURULIA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (Part-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000223/2023-2024 | 2367/MURD | 04/08/2023 | 300 | M/S. S. DAS AND ENTERPRISE | 859.33 | 0 | 40
537 | Murshidabad Division | Kandi Sub-Division | KURULIA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000576/2023-2024 | 3300/MURD | 20/10/2023 | 804 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 261.54 | 0 | 35
538 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) (1222 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Parsalika, Panchhipara & Andulia ( Village Code -315953, 315966, 315967) under Kurulia & Panchhipara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000679/2023-2024 | 3657/MURD | 29/11/2023 | 45 | S. DUTTA | 36.75 | 0 | 0
539 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000085/2023-2024 | 1129/MURD/8 | 25/04/2023 | 0 | Resource Division | 38.73 | 0 | 0
540 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT KURULIA PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/01586/2023-2024 | 428/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 3.82 | 0 | 0
541 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT KURULIA PH-2 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/01591/2023-2024 | 429/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 9.62 | 0 | 0
542 | Berhampore Mechanical | Kandi Sub-Division | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Burwan and Kandi block Under District Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000050/2025-2026 | 45/1 | 29/05/2025 | 92 | HARA PROSAD DAS | 17.87 | 0 | 0
543 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under KURULIA ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000705/2023-2024 | 2771/MEDB | 25/07/2023 | 92 | MENAKA ENTERPRISE | 35.06 | 0 | 0
544 | Murshidabad Division | Berhampur M/E Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000001/2025-2026 | 761/MURD | 02/04/2025 | 80 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0
545 | Murshidabad Division | Berhampur M/E Division | ANUP NAGAR CT PWSS to accommodate FHTC, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of SAMSERGANJ Block, Murshidabad District under Jangipur Sub Division Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000232/2023-2024 | 2404/MURD | 07/08/2023 | 180 | SUJIT KUMAR SAHA | 428.3 | 0 | 0
546 | Murshidabad Division | Berhampur M/E Division | ANUPNAGAR CT PWSS to accommodate FHTC, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of SAMSERGANJ Block, Murshidabad District under Jangipur SubDivision Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000250/2023-2024 | 2464/MURD | 09/08/2023 | 365 | M/S RUBIET HOSSAIN | 230.08 | 0 | 0
547 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 8.66 | 100
548 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000289/2023-2024 | 1230/MURD/32 | 04/05/2023 | 0 | Resource Division | 35.78 | 0 | 0
549 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
550 | Murshidabad Division | Berhampur M/E Division | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E. Dte. for 03 (Three) Months i.e. from 08.01.2025 to 07.04.2025. (Vehicle No.WB-58AX-9595). | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000232/2024-2025 | 05/LSD | 06/01/2025 | 90 | BARI ENTERPRISE | 0.44 | 0 | 0
551 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 1250 cum), Sinking of Tube Well , and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone -III PWSS in Lalgola Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000649/2023-2024 | 3475/MURD | 07/11/2023 | 545 | HANNAN BUILDERS PVT.LTD. | 1434.58 | 0 | 1
552 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-III, BHANDARA ZONE - I and SURANGAPUR ZONE -I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000700/2023-2024 | 3785/MURD | 11/12/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 35.34 | 0 | 80
553 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000101/2023-2024 | 1167/MURD/18 | 28/04/2023 | 0 | Resource Division | 49.7 | 0 | 0
554 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III ,IV & V ,Zone-III under Lalgola ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000662/2023-2024 | 3711/MEDB | 03/11/2023 | 92 | WEST BENGAL ENGINEERING CO. | 58.31 | 0 | 0
555 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 0 | 100
556 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Seikhpara PWSS of accommodate FHTC, Laying Distribution System, Laying Rising Main, Repairing & Construction of Switch Room, Repairing of Boundary Wall, Repairing of 600 CUM OHR, Construction of 400 CUM OHR in Raninagar II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000610/2023-2024 | 3373/MURD | 31/10/2023 | 609 | M/S.TAPAS KUMAR CHAKRABORTY | 1378.3 | 164.63 | 20
557 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000179/2023-2024 | 1180/MURD/23 | 29/04/2023 | 0 | Resource Division | 256.66 | 0 | 0
558 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Seikhpara ground water based water supply scheme under Block_ Raninagar-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000664/2023-2024 | 3716/MEDB | 03/11/2023 | 92 | SUNIL RABIDAS | 22.77 | 0 | 50
559 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based KAKRAMARI (ZONE-I) &KAKRAMARI (ZONE-II) PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000568/2023-2024 | 3288/MURD | 19/10/2023 | 180 | BIJAY CHOWDHURY | 861.6 | 0 | 35
560 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.89 | 100
561 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000247/2023-2024 | 1219/MURD/31 | 03/05/2023 | 0 | Resource Division | 49.41 | 0 | 0
562 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
563 | Berhampore Mechanical | Berhampur M/E Division | KANKRA MARI Z-II PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/01437/2023-2024 | 332/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 8.71 | 0 | 0
564 | Berhampore Mechanical | Berhampur M/E Division | KANKRAMARI Z-II PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/01438/2023-2024 | 333/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 5.26 | 0 | 0
565 | Murshidabad Division |  | Surveying, Sub Soil investigation , Design, Engineering, Supplying, Construction, Erection, Testing, Commissioning of Raw Water Pump House over M.S Intake barge (Floating), Bank Protection, Raw Water Rising Main, Pre Settling Tank ,Construction of 7.765 MLD capacity Water Treatment Plant based on Conventional Technologies including Administrative Building, Indoor Type Substation Building ,Electro Mechanical Works , Staff quarter & other components, Clear Water Pumping Main, Construction of 5 (Five) Nos OHRs and Distribution system for 5 nos distribution zones with DI/HDPE/UPVC pipes, House Hold Connections , on EPC turnkey basis in a single package as per detail scope of work / direction by E-I-C including 3 (Three) months Trial Run and Operation & Maintenance for 5 years for Surface Water Based BEWA piped W/S scheme in Farakka Block in the district of Murshidabad. |  |  | ORD/000714/2023-2024 | 3836/MURD | 14/12/2023 | 365 | CONCORD-SRG-(JV) | 8070 | 0 | 5
566 | Berhampore Mechanical |  | Providing Electrical Equipment for 11/0.433 KV Sub-station at Water Treatment Plant under surface based water supply scheme for Bewa and its adjoining mouzas, Block - Farraka, District - Murshidabad. |  |  | ORD/001408/2023-2024 | 107/MEDB | 17/01/2024 | 182 | CONCORD ENGINEERING | 252.48 | 0 | 0
567 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Pirojpur (Village code 314723) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723334 in the District of Murshidabad. |  |  | ORD/000114/2022-2023 | 1197/MURD | 10/05/2022 | 30 | KESHAB CHANDRA DAS | 7.33 | 7.29 | 1
568 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village MadhurKol (Village code 314724) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723334 in the District of Murshidabad. |  |  | ORD/000498/2020-2021 | 88/MURD | 08/01/2021 | 60 | GOUTAM CHAKRABORTY | 44.07 | 0 | 1
569 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Pirojpur (Village code 314723) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723334 in the District of Murshidabad. |  |  | ORD/000505/2020-2021 | 87/MURD | 08/01/2021 | 60 | GOUTAM CHAKRABORTY | 23.78 | 10.81 | 100
570 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Komnagar ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000083/2024-2025 | 1244/BD-I | 30/07/2024 | 30 | R.S. CONSTRUCTION | 9.36 | 0 | 0
571 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Komnagar (Village code 314572) under Komnagar Ground Water Supply Scheme in Raninagar-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-08) | Assistant Engineer | Junior Engineer-II | ORD/000441/2021-2022 | 968/BD-I | 07/06/2021 | 180 | S.P CONSTRUCTION | 49.3 | 34.35 | 0
572 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for JAL JEEVAN MISSION under command area of Sitesnagar ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000112/2024-2025 | 1448/BD-I | 04/09/2024 | 60 | GOUTAM KUMAR CHAUDHURI | 16.63 | 0 | 0
573 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Siteshnagar (Village code 314238) under Lalgola Ground Water Supply Scheme in Lalgola Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-10) | Assistant Engineer-I | JE | ORD/000271/2021-2022 | 1142/BD-I | 07/07/2021 | 180 | KAMIRUL SK AND CO. | 70.73 | 62 | 0
574 | Murshidabad Division |  | RESTORATION OF DAMAGED BALCK TOP AND ROAD FLANK OCCURED DUE TO CUTTING OF ROAD STRETCHES FOR LAYING OF PHE PIPELINE AT GUNANADABATI WATER SULLY SCHEME UNDER KANDI SUB DIVISION. |  |  | BILL/00622/2023-2024 | 267-MSD/2023-24 | 19/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, BERHAMPORE DIVISION-I | 4.38 | 0 | 0
575 | Murshidabad Division |  | Continuation Work Order for the work of Hiring of Maxi cab (Non- Air Condition, Bharat Stage III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months i.e. 01.10.2024 TO 27.02.2025. VEHICLE NO - WB57F2352 |  |  | ORD/000161/2024-2025 | 136/KSD | 19/09/2024 | 150 | H.MONDAL CONSTRUCTION | 0.87 | 0 | 0
576 | Murshidabad Division |  | Construction of balance portion office cum godown including sanitary and plumbing work at H.W. Site and laying of UPVC pipeline in between node point 77 to 78, 78 to 89 & 78 to 79 of Pachhipara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000530/2023-2024 | 3117/MURD | 05/10/2023 | 30 | M.I CONSTRUCTION | 13.74 | 13.58 | 70
577 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (241 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Pashupatibati & Bolpara ( Village Code -315948, 315966, 315952) under Panchhipara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000632/2023-2024 | 3437/MURD | 03/11/2023 | 30 | NATIONAL CONSTRUCTION (MD ASRAFUL SK) | 9.36 | 0 | 70
578 | Murshidabad Division |  | Continuation Work order for Hiring of 1 no of Car for official use of the AE KSD PHE DTE. Period 01.01.2022 to 31.03.2022. Work Order No 303 / BSD. DATE 15.12.2021 |  |  | VCH/000660/2022-2023 | 209-MSD/2022-23 | 15/07/2022 | 0 | SISIR KUMAR DE | 0.83 | 0 | 0
579 | Murshidabad Division |  | Continuation Work order for Hiring of 1 no of Car for official use of the AE KSD PHE DTE. Period 01.07.2021 to 03.01.2022. Work Order No 230 / BSD. DATE 02.07.2021 |  |  | VCH/000661/2022-2023 | 209-MSD/2022-23 | 15/07/2022 | 0 | SISIR KUMAR DE | 1.84 | 0 | 0
580 | Murshidabad Division |  | Continuation Work order for Hiring of 1 no of Car for official use of the AE KSD PHE DTE. Period 01.06.2021 to 03.07.2021. Work Order No 185 / BSD. DATE 30.07.2020 |  |  | VCH/000662/2022-2023 | 209-MSD/2022-23 | 15/07/2022 | 0 | SISIR KUMAR DE | 0.42 | 0 | 0
581 | Murshidabad Division |  | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Samserganj Block(Kanchantala, Dogachi-nowpara,Bhasaipaikar,Gagingar,Tinpakuria & Bogdadnagar ) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (PART-A) |  |  | ORD/000069/2021-2022 | 126 /JSD | 26/05/2021 | 30 | IMAGIN COMMUNICATION | 2.38 | 2.38 | 0
582 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) and under command area of village of Alamsahi ( Village Code -313853) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005019105). |  |  | ORD/000548/2020-2021 | 574/MURD | 09/02/2021 | 60 | BARUN DUTTA | 6.31 | 5.14 | 0
583 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Balbalpara ( Village Code -313852) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005019105) . |  |  | ORD/000624/2020-2021 | 634/MURD | 18/02/2021 | 60 | ARABINDA GHOSH | 41.65 | 0 | 0
584 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BALBALPARA (Village Code 313852) under DOGACHHI (ZONE-II) Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 927 of 21-22 by EE MURD |  |  | VCH/000017/2022-2023 | 20-MSD/22-23 | 20/04/2022 | 0 | ARABINDA GHOSH | 41.65 | 0 | 0
585 | Murshidabad Division |  | Continuation work order for Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Shakopara Station to Ballalpur Station (TP NO 247/16 & 247/18) at Bhabanipur mouza & Connecting with existing 140 mm dia UPVC distribution main line of Arjunpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. |  |  | ORD/000092/2023-2024 | 1607/MURD | 09/06/2023 | 60 | PRADIP KUMAR DAS | 3.68 | 3.68 | 0
586 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) of Mouja Bhabanipur (Village Code-313820), of Arjunpur &adjoining mouja under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District under Murshidabad Division P.H.E Dte. (Scheme ID-0005184170) |  |  | ORD/000374/2022-2023 | 2086/MURD | 27/07/2022 | 120 | DIPAYAN DEY | 88.99 | 0 | 0
587 | Murshidabad Division |  | Replacement of media for Renovation of I.E Plant at Arjunpur W/S Scheme, of Jangipur Sub-Division under Murshidabad Division P.H.E.Dte. |  |  | ORD/000564/2022-2023 | 2941/MURD | 03/11/2022 | 20 | SUMAN ENTERPRISE AND SUMAN AQUA | 10.21 | 8.65 | 1
588 | Murshidabad Division |  | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Shakopara Station to Ballalpur Station (TP NO 247/16 & 247/18) at Bhabanipur mouza & Connecting with existing 140 mm dia UPVC distribution main line of Arjunpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. |  |  | ORD/001654/2021-2022 | 508/MURD | 23/02/2022 | 60 | PRADIP KUMAR DAS | 36.8 | 36.8 | 0
589 | Murshidabad Division |  | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Shakopara Station to Ballalpur Station (TP NO 247/30 & 247/32) at Bhabanipur mouza & Connecting with existing 110 mm dia UPVC distribution main line of Arjunpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. |  |  | ORD/001655/2021-2022 | 509/MURD | 23/02/2022 | 60 | M/S GUHA & ROY ENTERPRISE | 37.5 | 23.75 | 0
590 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-19 |  |  | VCH/000984/2022-2023 | 399-MSD/22-23 | 18/11/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 6.19 | 0 | 0
591 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-24 |  |  | VCH/000986/2022-2023 | 399-MSD/22-23 | 18/11/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 2.57 | 0 | 0
592 | Murshidabad Division | Berhampur Sub-Division | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.06.2023 to 30.11.2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000084/2023-2024 | 100/HQ | 30/05/2023 | 184 | DULAL CHOWDHURY | 0.91 | 0.6 | 100
593 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of one no. Diesel Bolero/ Marshal/Ambassador car (WB57B-4454) for official use of the Assistant Engineer, Kandi Sub-Division, P.H.Engineering Dte. for 06(SIX) Months. (Period from 01.07.2023 to 31.12.2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000154/2023-2024 | 43/BSD | 23/06/2023 | 183 | SISIR KUMAR DE | 0.91 | 0 | 0
594 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Loknathpur (Village code 315681) under Loknathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID 1723426 (Sl No-35) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000295/2020-2021 | 960/MURD | 24/03/2021 | 180 | AJAY MONDAL | 68.75 | 68.5 | 1
595 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ekdala (Village code 315682)under Lokenathpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723426 in the District of Murshidabad | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000493/2020-2021 | 3142/MURD | 11/12/2020 | 60 | NATIONAL ENTERPRISE | 29.41 | 18.85 | 1
596 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Ekdala ( Village Code -315682) under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000740/2022-2023 | 267/BSD | 24/06/2022 | 953 | NATIONAL ENTERPRISE (APU GHOSH) | 4.84 | 0 | 100
597 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Loknathpur (Village Code -315681) Part-A under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000755/2022-2023 | 280/BSD | 24/06/2022 | 30 | MONDAL CONSTRUCTION | 4.59 | 4.02 | 0
598 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Loknathpur (Village Code -315681) Part-B under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000756/2022-2023 | 281/BSD | 24/06/2022 | 30 | MONDAL CONSTRUCTION | 4.73 | 4.63 | 0
599 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jainagar(Village code 315680) under Loknathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Bedanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723426 in the District of Murshidabad. (Sl No-36) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000849/2021-2022 | 3285/MURD | 05/10/2021 | 180 | M/S. BIMAL MISRA | 76.59 | 36.38 | 48
600 | Murshidabad Division | Berhampur Sub-Division | Repair and renovation work of Boundary wall at Head Work of MahamadpurWater Supply Scheme under Berhampore Sub Division, P.H.E.Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/001290/2021-2022 | 460/BSD | 15/12/2021 | 30 | ARINDAM MAJUMDAR | 4.74 | 4.13 | 100
601 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mamenpur (Village code 314732) under Mamenpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 000958860 (Sl No-13) |  |  | VCH/000022/2022-2023 | 22-MSD/22-23 | 14/04/2022 | 0 | M/S. BIMALENDU BOSE | 4.42 | 0 | 0
602 | Murshidabad Division |  | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Connection of different existing PWSS (Bhagirathpur PWSS Scheme,Block- Domkal)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 375 of 21-22 by EE MSD, and Scheme Code: 7678 |  |  | VCH/000036/2022-2023 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.73 | 0 | 0
603 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) in Connection with Jal Jeevan Mission & Jal Swapna of village of Momenpur Village Code (314732) Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District. PHE DTE Tender no-117 of 20-21 by SE / MC |  |  | VCH/000191/2021-2022 |  | 13/07/2021 | 0 | M/S. BIMALENDU BOSE | 60.35 | 0 | 0
604 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jagarpara (Village code 314183),Chamunda(Village code 314171),Janardanpur( Village code 314184), under Nasipur Zone-I Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | Assistant Engineer-I | JE | ORD/000127/2020-2021 | 203/BD-I | 04/02/2021 | 30 | TARUN KUMAR BHATTACHARYA | 79.1 | 55.03 | 1
605 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Jagarpara (Code-314183), Janardanpur (Code-314184),Chamunda(Code-314171) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000140/2024-2025 | 1606/BD-I | 03/10/2024 | 30 | PAMIR ROY | 11.94 | 0 | 0
606 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000081/2024-2025 | 1233/BD-I | 30/07/2024 | 60 | PRIME CONSTRUCTION | 28.06 | 0 | 0
607 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Egdalia(Village code 314213) under Bajipur Madhupur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000098/2020-2021 | 165/BD-I | 03/02/2021 | 20 | LAXMI CONSTRUCTION | 4.93 | 9.48 | 1
608 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Narayanpur (Village code 314214) under Bajipur Madhupur Ground Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte | Assistant Engineer-I | JE | ORD/000179/2020-2021 | 828/BD-I | 13/11/2020 | 60 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 10.28 | 12.88 | 1
609 | Berhampore Division I | Berhampur Division I | Laying of new pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Narayanpur and others under Bajipur Madhupur Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000412/2021-2022 | 1441/BD-I | 11/08/2021 | 10 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 1.16 | 0.73 | 1
610 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Sahapur, Upar Fatepur and Bajipur Madhupur (Village code-314210,314212 and 314235) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bajipur Madhupur Ground water based Water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | JE | ORD/000797/2021-2022 | 2314/BD-I | 29/12/2021 | 45 | BIJOY CHOWDHURY | 13.36 | 2.47 | 1
611 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ghoramara (Village code 315515) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723483in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000386/2020-2021 | 3143/MURD | 11/12/2020 | 60 | M/S M.S. ENTERPRISE | 31.09 | 0 | 1
612 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandabad (Village code 315517) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723483 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000550/2020-2021 | 3137/MURD | 11/12/2020 | 60 | M/S. CHOWDHURY CONSTRUCTION | 23.85 | 0 | 1
613 | Murshidabad Division | Berhampur Sub-Division | Retrofiting of Function al Household Tap Connection FHTC and allied works in connection with Jal Swapna from existing distribution system within the command area of village fatepur under Ghoramara Ground W/S Scheme for arsenic affected areas of Berhampore Block in the Dist of MSD PHE DTE. Tender no 903 of 20+-21 by EE MSD | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/000242/2021-2022 | 45-MSD / 21-22 | 31/08/2021 | 0 | M/S M.S. ENTERPRISE | 17.75 | 0 | 0
614 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village GHORAMARA (Village Code 315515) under GHORAMARA Ground Water Based Water Supply Scheme for arsenic affected areas of BERHAMPORE Block in the District of Murshidabad. Tender no - 903 of 20-21 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/001451/2021-2022 | 352-MSD/21-22 | 05/03/2022 | 0 | M/S M.S. ENTERPRISE | 11.41 | 0 | 0
615 | Murshidabad Division | Berhampur Sub-Division | EXTENSION OF DISTRIBUTION PIPELINE WITHIN THE COMMAND AREA OF BHALKUNDI WSS, TNO- 478/20-21/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/002012/2020-2021 | 473/W | 08/03/2021 | 0 | DEBASISH SARKAR | 4.64 | 0 | 0
616 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --PANCHTHUPI-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- ACHHOAN, CODE-315979, TNO- 605/2020-21/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/002013/2020-2021 | 473/W | 08/03/2021 | 0 | LAXMI CONSTRUCTION | 6.24 | 0 | 0
617 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --BHALKUNDI-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- SAMANDI , CODE-315122, TNO- 573/2020-21/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/002014/2020-2021 | 473/W | 08/03/2021 | 0 | APURBA SAHA CHOWDHURY | 16.4 | 0 | 0
618 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kharsadanga, Putijol, Sundhipur & Rajdharpara (Village code 315377, 315395, 315371 & 315375) respectively under Purba Narayanpur (Zone-B) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000142/2020-2021 | 242/BD-I | 10/02/2021 | 180 | MADE & TRADE CO. | 306.14 | 323.76 | 1
619 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naoda Panur, Tarakpur, Kaya & Purba Narayanpur (Village code 315378, 315380, 315379 & 315376) under Purba narayanpur (Zone-B) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000143/2020-2021 | 249/BD-I | 11/02/2021 | 180 | J.D.J ENTERPRISE | 393.6 | 268.7 | 1
620 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paschim Gopinathpur (Village code 315393) under Purba Narayanpur (Zone-B) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000158/2020-2021 | 296/BD-I | 19/02/2021 | 30 | M/S BIMALENDU BOSE | 9.59 | 9.18 | 1
621 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kariagachhi (Village code 315394) under Purba Narayanpur (Zone-B) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000159/2020-2021 | 297/BD-I | 19/02/2021 | 30 | A.P CONSTRUCTION | 7.15 | 6.69 | 1
622 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | Junior Engineer-I | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
623 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Uday Nagar (village code 315396) , Gar Baharampur ( village code 315388 ) and Pakuria ( village code 315381 ) under PURBONARAYANPUR ( Zone - B ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000464/2021-2022 | 1836/BD-I | 05/10/2021 | 70 | HOQUEDAR ALI | 58.64 | 0 | 0
624 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Kharsadanga, Putijol,Sundhipur and Rajdharpara (Village code-315377,315395,315371 and 315375) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Purba Narayanpur (Zone-B)Surface water based Water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | Junior Engineer-I | ORD/000791/2021-2022 | 2302/BD-I | 28/12/2021 | 90 | SOUNAK ENTERPRISE | 73.56 | 73.26 | 1
625 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. |  |  | ORD/000453/2021-2022 | 303/BSD | 13/08/2021 | 30 | IMAGIN | 4.34 | 8.67 | 0
626 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RADHARGHAT-II G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000507/2021-2022 | 342/BSD | 27/08/2021 | 30 | IMAGIN | 4.17 | 0 | 1
627 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chumarigacha (Village code 315340) under Basabari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723194 in the District of Murshidabad |  |  | ORD/000725/2020-2021 | 3122 / MURD | 09/12/2020 | 60 | TANUSHREE ENTERPRISE | 39.34 | 0.53 | 1
628 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of SAKTIPUR Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- MAHATA, CODE-315638, TNO- 538/20-21/EE |  |  | VCH/002010/2020-2021 | 473/W | 08/03/2021 | 0 | SO-FINE AQUARIUM | 11.52 | 0 | 0
629 | Murshidabad Division |  | LAYING OF UPVC PIPELINE AT JOYPUR PASCHIMPARA....BHALKUNDI Z-I WSS, TNO- 05/20-21/AEKSD |  |  | VCH/002011/2020-2021 | 473/W | 08/03/2021 | 0 | DEBASISH SARKAR | 1.6 | 0 | 0
630 | Murshidabad Division |  | EXTENSION OF DISTRIBUTION PIPELINE WITHIN THE COMMAND AREA OF BHALKUNDI WSS, TNO- 478/20-21/EE |  |  | VCH/002012/2020-2021 | 473/W | 08/03/2021 | 0 | DEBASISH SARKAR | 4.64 | 0 | 0
631 | Murshidabad Division |  | Extension of distribution system for supply of safe potable drinking water at Charakdanga Adibashi Para, Madhunia Primay School & Madhunia SSKAdibashi Para under Amarkundu Water Supply Scheme under Lalbagh Sub-Division,PHE Dte. |  |  | ORD/000884/2021-2022 | 349/LSD | 09/11/2021 | 30 | GHOSH & COMPANY | 2.74 | 2.74 | 0
632 | Murshidabad Division |  | Construction of RCC Stand Post including platforms at AmarkunduVillage, Kanakpara Village, Nandigram Village, Bagor Village & Madhunia Village under Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. |  |  | ORD/000919/2021-2022 | 362/LSD | 17/11/2021 | 30 | SARAJIT KUMAR MAJUMDER | 2.43 | 2.43 | 0
633 | Murshidabad Division |  | Extension of UPVC pipeline construction of RCC stand post with platform at Ghoshkula area (Kanakpara) under Improvement of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. |  |  | ORD/001226/2021-2022 | 414/LSD | 27/12/2021 | 30 | SANJIB KUMAR SINGHA | 4.89 | 0 | 0
634 | Murshidabad Division |  | Balance and allied works For Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sankuria (Village code 315024) and Chayan Nagar (Village code 315023) under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/001615/2021-2022 | 308/MURD | 07/02/2022 | 60 | PARTHA PRATIM DAS | 16.51 | 12.52 | 1
635 | Murshidabad Division |  | Extension of UPVC pipeline construction of RCC stand post with platform at Ghoshkula area (Kanakpara) under Improvement of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. |  |  | ORD/002073/2021-2022 | 414 /LSD | 27/12/2021 | 30 | SANJIB KUMAR SINGHA | 4.89 | 4.88 | 0
636 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BURWAN- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- GOURINAGAR , CODE-315951 , 631/2020-21/EE |  |  | VCH/002050/2020-2021 | 504/W | 22/03/2021 | 0 | KAMIRUL SK AND CO. | 9.08 | 0 | 0
637 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -JITPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - PAR RAGHUNATHPUR, CODE- 314677 , TNO- 80/20-21/SEMC |  |  | VCH/002052/2020-2021 | 504/W | 22/03/2021 | 0 | UMWELT ENGINEER PVT LTD | 36.66 | 0 | 0
638 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Upar Orahar(Village code 314444) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE | ORD/000105/2020-2021 | 171/BD-I | 03/02/2021 | 30 | KAMIRUL SK AND CO. | 50.99 | 86.53 | 0
639 | Berhampore Division I | Berhampur Division I | Laying of new UPVC pipeline with allied work for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Upar Orahar (Village code 314444) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE | ORD/000411/2021-2022 | 1440/BD-I | 11/08/2021 | 10 | KAMIRUL SK AND CO. | 4.67 | 0 | 0
640 | Berhampore Division I | Berhampur Division I | Additional laying works at village Diar Syampur (Village Code-314439) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Diar Syampur Ground Water Supply Scheme (Bhagawangola-I Block) under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | Assistant Engineer-I | JE | ORD/000007/2022-2023 | 549/BD-I | 13/05/2022 | 10 | BURIMA CONSTRUCTION | 3.37 | 2.63 | 50
641 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Diar Syampur ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000091/2024-2025 | 1303/BD-I | 07/08/2024 | 30 | DAS ENTERPRISE(GORABAZAR) | 2.91 | 0 | 0
642 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Diar Syampur (Village code 314439) under Diar Syampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000152/2020-2021 | 270/ BD-I | 12/02/2021 | 30 | BURIMA CONSTRUCTION | 44.88 | 42.38 | 1
643 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Meoakhana (Village code 314438) under Diar Syampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000239/2020-2021 | 68/BD-I | 18/01/2021 | 30 | M/S. DAS ENTERPRISE | 22.56 | 35.45 | 1
644 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Diar Syampur( Village code -314439 ) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Diar Syampur Ground water supply scheme (Bhagwangola-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | JE | ORD/000779/2021-2022 | 2294/BD-I | 28/12/2021 | 10 | AICH CONSTRUCTION | 6.77 | 0 | 0
645 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hurshi (village code 314752), under Hurshi Zone-II Ground water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000744/2021-2022 | 2206/BD-I | 10/12/2021 | 90 | SRIJON ENTERPRISE | 66.87 | 51.38 | 0
646 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Arazi Kanaipur (village code 314751), under Hurshi Zone-II Ground water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000745/2021-2022 | 2252/BD-I | 21/12/2021 | 20 | ANUPA ENTERPRISE | 5.11 | 5.03 | 1
647 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte | Assistant Engineer | Junior Engineer-II | ORD/000075/2024-2025 | 1223/BD-I | 29/07/2024 | 60 | M/S. MONDAL ENTERPRISE | 23.39 | 0 | 0
648 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khemrajpur (Village code 314761),Naodapara (Village code 314763),Srirampur(Village code 314762) under Lochanpur Ground Water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000123/2020-2021 | 199/BD-I | 04/02/2021 | 30 | M/S S.S ENTERPRISE | 71.38 | 79.87 | 1
649 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bilaspur Nachharerpara (Village code 314639) under Barabil Raghunathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723213 |  |  | ORD/000408/2021-2022 | 2537/MURD | 19/08/2021 | 180 | M/S. UNIQUE BUILDERS | 74.3 | 8.35 | 0
650 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village HARISANKARPUR (Village Code 314635) under Barabil Raghunathpur Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block in the District of Murshidabad. |  |  | ORD/000731/2020-2021 | 3032/MURD | 07/12/2020 | 45 | DOBAY CONSTRUCTION | 20.91 | 17.85 | 100
651 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harisankarpur ( Village Code -314635) [Near house of Shiltu fro Rajak Talar More] under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. |  |  | ORD/001242/2021-2022 | 49/ISD | 28/01/2022 | 30 | M/S BHATTACHARJEE & CO | 4.85 | 0 | 0
652 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harisankarpur ( Village Code -314635) [Near house of Jobarma Nanda Primary School to Subeder More] under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. |  |  | ORD/001243/2021-2022 | 50/ISD | 28/01/2022 | 30 | M/S BIREN BHATTACHARYYA | 4.85 | 0 | 0
653 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harisankarpur ( Village Code -314635) under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. |  |  | ORD/001244/2021-2022 | 51/ISD | 28/01/2022 | 30 | ABA CONTRACTOR | 4.24 | 4.24 | 0
654 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village HARISANKARPUR (Village Code 314635) under BARABIL RAGHUNATHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 127 of 21-22 by AE ISD |  |  | VCH/000299/2022-2023 | 109-MSD/22-23 | 06/05/2022 | 0 | M/S BIREN BHATTACHARYYA | 4.84 | 0 | 0
655 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village HARISANKARPUR (Village Code 314635) under BARABIL RAGHUNATHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 126 of 21-22 by AE ISD |  |  | VCH/000300/2022-2023 | 110-MSD/22-23 | 11/05/2022 | 0 | M/S BHATTACHARJEE & CO | 4.84 | 0 | 0
656 | Murshidabad Division |  | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC |  |  | VCH/002047/2020-2021 | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0
657 | Murshidabad Division | Islampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Hari Sankarpur ( Village Code -314740) under Katakobra Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005185646). | ASSISTANT ENGINEER | Junior Engineer | ORD/000293/2020-2021 | 651/MURD | 18/02/2021 | 60 | M/S SUBHA CONSTRUCTION | 43.8 | 0 | 100
658 | Murshidabad Division | Islampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Hari Sankarpur ( Village Code -314740) under Katakobra Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005185646). | ASSISTANT ENGINEER | Junior Engineer | ORD/000743/2020-2021 | 651 /MURD | 18/02/2021 | 60 | M/S SUBHA CONSTRUCTION | 43.8 | 10.32 | 1
659 | Murshidabad Division | Islampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village HARI SANKARPUR (Village code 314740) under KATAKOBRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of DOMKAL Block, under Murshidabad Division, PHE Dte. Scheme ID 0005185646 in the District of Murshidabad. Tender no 827 of 20-21 by EE MSD | ASSISTANT ENGINEER | Junior Engineer | VCH/000270/2021-2022 |  | 18/08/2021 | 0 | M/S SUBHA CONSTRUCTION | 32.45 | 0 | 0
660 | Murshidabad Division | Islampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village HARI SANKARPUR (Village code 314740) under KATAKOBRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of DOMKAL Block, under Murshidabad Division, PHE Dte. Scheme ID 0005185646 in the District of Murshidabad. Tender no 827 of 20-21 by EE MSD | ASSISTANT ENGINEER | Junior Engineer | VCH/000722/2021-2022 | 51-MSD/21-22 | 13/09/2021 | 0 | M/S SUBHA CONSTRUCTION | 32.45 | 0 | 0
661 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gopjan (Village code 315447) under Budharpara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005182920 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000001/2022-2023 | 1126/MURD | 29/04/2022 | 45 | PRATICHI ENTERPRISE | 24.48 | 0 | 40
662 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) 67 nos in connection with Jal Swapna (Jal Jeevan Mission ) including Laying of Distribution system of Raniswar( Village Code -315314) under Budharpara Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000030/2022-2023 | 1083/MURD | 27/04/2022 | 30 | DEBASISH SARKAR | 33.33 | 0 | 1
663 | Murshidabad Division | Berhampur Sub-Division | Laying distribution pipeline in connection with Jal Swapna (Jal Jeevan Mission) of Nialispara ( village code: 315317 ) and Budhorpara village of Budharpara Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000184/2022-2023 | 191/BSD | 28/04/2022 | 30 | MOBIDUR RAHAMAN | 4.67 | 4.67 | 80
664 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Nialispara ( village code: 315317 ) of Budharpara Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. For 18nos FHTC | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000193/2022-2023 | 202/BSD | 28/04/2022 | 30 | SURAJIT MONDAL | 4.81 | 4.1 | 100
665 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Nialispara ( village code: 315317 ) of Budharpara Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. For 28nos FHTC | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000194/2022-2023 | 203/BSD | 28/04/2022 | 30 | ABIDA CONSTRUCTION | 4.85 | 3.85 | 80
666 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) 69 nos in connection with Jal Swapna (Jal Jeevan Mission ) including Laying of Distribution system of Nialispara ( Village Code -315317) under Budharpara Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000195/2022-2023 | 1185/MURD | 09/05/2022 | 30 | AMAL KUMAR DAS | 37.93 | 0 | 0
667 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Budharpara (Village code 315320) under Budharpara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte.Scheme ID - 5182920 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000443/2021-2022 | 2644/MURD | 27/08/2021 | 60 | M/S. BIMALENDU BOSE | 21.87 | 0 | 0
668 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Tikiapara (Village code 315318) under Budharpara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005182920 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001468/2021-2022 | 281/MURD | 03/02/2022 | 60 | M/S SWAPAN KUMAR NATH AND CO. | 19.7 | 18.08 | 100
669 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000026/2021-2022 | 539/11/MURD | 25/02/2022 | 0 | Resource Division | 0.49 | 0 | 0
670 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
671 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
672 | Murshidabad Division | Kandi Sub-Division | Allied work for Rising main connection to OHR & AIRP in connection with FHTC work of Village of JAGTAI(Village Code-313979) under JAGTAI Water Supply Scheme (Scheme ID- 0005184165) under Jangipur Sub Division,P.H.E. Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000089/2022-2023 | 235/JSD | 05/05/2022 | 30 | MAA CONSTRUCTION | 3.84 | 3.84 | 0
673 | Murshidabad Division | Kandi Sub-Division | Allied work of laying of HDPE Pipe line for " Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) under command area of village JAGTAI (Village Code-313979)"( Bara Masjid Para) under command area of Jagtai Ground Water based Water supply scheme for Arsenic Affected Areas of Suti-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184165) in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000095/2022-2023 | 241/JSD | 05/05/2022 | 30 | MONDAL CONSTRUCTION | 4.77 | 4.7 | 0
674 | Murshidabad Division | Kandi Sub-Division | Laying of HDPE pipeline and FHTC of 191 nos. household for retrofitting works in Jagtai Ground water-based w/s scheme for arsenic affected areas of Suti-II Block under Murshidabad Division, PHE Dte. in the District of Murshidabad. (Scheme ID- 0005184165) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000173/2023-2024 | 1935/MURD | 18/07/2023 | 30 | HOQUEDAR ALI | 41.12 | 39.92 | 100
675 | Murshidabad Division | Kandi Sub-Division | EXTENSION OF PIPELINE AT AURANGABAD PHE SUB CENTRE & JAGTAI SUB CENTRE UNDER SUTI -II BLOCK | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000627/2019-2020 | 228/JSD | 15/01/2020 | 2192 | SUJIT CHOWDHURY | 1.97 | 1.94 | 100
676 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna Jal Jeevan Mission and under command area of village of JAGTAI (Village code 313979) under JAGTAI Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184165 | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001184/2021-2022 | 4023/MURD | 24/12/2021 | 180 | HOQUEDAR ALI | 91.83 | 91.45 | 1
677 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JAGTAI-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001332/2021-2022 | 51/JSD | 25/01/2022 | 30 | IMAGIN | 4.16 | 0 | 0
678 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JAGTAI-II G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001333/2021-2022 | 52/JSD | 25/01/2022 | 30 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0
679 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of AHIRON (Village code 313929) under AHIRON Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184152 |  |  | ORD/001130/2021-2022 | 3756/MURD | 01/12/2021 | 180 | DHIRENDRANATH MONDAL | 87.54 | 0 | 0
680 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village AHIRON (Village Code 313929) under AHIRON Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-I Block in the District of Murshidabad. Tender no - 116 of 21-22 by SE MC |  |  | VCH/001479/2021-2022 | 387-MSD/21-22 | 17/03/2022 | 0 | DHIRENDRANATH MONDAL | 87.54 | 0 | 0
681 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Charkamnagar Village (Code-315620), Nagar Village (Code-315622), Maklishpur Village(Code-315623) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000115/2024-2025 | 1450/BD-I | 04/09/2024 | 60 | SUDIPA SINGHA ROY | 13.53 | 0 | 0
682 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Charkamnagar (Village code 315620),Nagar (Village code 315622),Maklishpur (Village code 315623) under Charkamnagar Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-II | Junior Engineer-II | ORD/000208/2021-2022 | 1006/BD-I | 21/06/2021 | 30 | KAMIRUL SK AND CO. | 69.19 | 37.16 | 1
683 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Mohanpur Village (Code-314764), Gopinathpur Village (Code-314765) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part-C)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000106/2024-2025 | 1442/BD-I | 04/09/2024 | 60 | S.K CONSTRUCTION (SUDIP KUMAR SANYAL) | 19.16 | 0 | 0
684 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mohanpur (Village code 314764),Gopinathpur (Village code 314765) under Lochanpur Ground Water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-C) | Assistant Engineer | Junior Engineer-II | ORD/000115/2020-2021 | 187/BD-I | 04/02/2021 | 30 | DECON INDIA | 66.96 | 103.62 | 1
685 | Berhampore Division I | Raghunathganj Sub-Division | Additional Laying works at village Mohanpur (village code 314764) and Gopinathpur (village code 314765) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Lochanpur Ground water supply scheme (Raninagar-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer | Junior Engineer-II | ORD/000566/2021-2022 | 1919/BD-I | 08/10/2021 | 10 | BIMALENDU BOSE | 7.03 | 7.02 | 1
686 | Murshidabad Division | Islampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khidir Para ( Village Code -314739) under Katakobra Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005185646). | ASSISTANT ENGINEER | Junior Engineer | ORD/000513/2020-2021 | 580/MURD | 09/02/2021 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 33.55 | 33.54 | 80
687 | Murshidabad Division | Islampur Sub-Division | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Raypur (Village code-314582) under KatakobraGround Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division P.H.E Dte. (Scheme ID-0005185646) | ASSISTANT ENGINEER | Junior Engineer | ORD/000549/2022-2023 | 2765/MURD | 29/09/2022 | 120 | SOFIQUL ISLAM | 154.82 | 144.08 | 100
688 | Murshidabad Division | Islampur Sub-Division | Repairing & Renovation of the pump House No-1 & 2 under Katakopra Zone-I water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad | ASSISTANT ENGINEER | Junior Engineer | ORD/001240/2021-2022 | 46/ISD | 28/01/2022 | 60 | PRAVAT KUMAR GHOSH | 3.65 | 3.64 | 1
689 | Murshidabad Division | Islampur Sub-Division | Repairing & Renovation of the Boundary wall of pump House No-2 Both & Allied works under Katakopra Zone- I & II water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad | ASSISTANT ENGINEER | Junior Engineer | ORD/002122/2021-2022 | 48/ISD | 28/01/2022 | 30 | PARTHA RAJAK | 1.95 | 1.94 | 1
690 | Murshidabad Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village DEPUTIPAR (Village Code-314582) under GODHANPARA Ground Water Supply Scheme for Arsenic Affected Area of RANINAGAR-II BLOCK under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | VCH/000235/2021-2022 | 31-MSD / 21-22 | 27/08/2021 | 0 | M/S ROY & BOSE ENTERPRISE | 10.92 | 0 | 0
691 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Muradpur-Jalangi (Village code 314631) under Muradpur-Jalangi Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723429 in the District of Murshidabad. (Sl No-26) |  |  | ORD/000152/2020-2021 | 557/MURD | 08/02/2021 | 180 | MAMATA USHA ENTERPRISE | 144.81 | 93.66 | 0
692 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Muradpur-Jalangi (Village code 314631) under Muradpur-Jalangi Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723429 in the District of Murshidabad. (Sl No-26), TNO-107/20-21/SE-MC |  |  | VCH/000308/2022-2023 | 116-MSD/22-23 | 06/05/2022 | 0 | MAMATA USHA ENTERPRISE | 42.57 | 0 | 0
693 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Muradpur-Jalangi (Village code 314631) under Muradpur-Jalangi Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723429 in the District of Murshidabad. (Sl No-26), 557/MURD, 08/02/2021 |  |  | VCH/000778/2021-2022 | 186-MSD/21-22 | 12/11/2021 | 0 | MAMATA USHA ENTERPRISE | 35.48 | 0 | 0
694 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) laying pipeline in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Shankarpara, Rameswarpur, Nalkunda & Bhabtakharida (Village Code- 315561, 315581, 315582 and 315583 under Mahespur (ZONE-F) Water Supply Scheme in the district Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000016/2022-2023 | 946/BD-I | 23/08/2022 | 120 | DHIRENDRA NATH MONDAL | 107.44 | 0 | 0
695 | Berhampore Division I | Berhampur Division I | Laying of 150 mm dia (K-9),250 mm & 300 mm dia DI (K-7) pipeline with interconnection in between Rising Main and Distribution System and 180 mm dia ,200 mm dia&225 mm dia UPVC pipeline of unlead portion within command area of Mahespur(Zone-F) W/S scheme of Arsenic affected area of Beldanga uncovered W/S scheme under Berhampore Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000235/2023-2024 | 895/BD-I | 05/10/2023 | 30 | SANTA TRADING | 20.6 | 0 | 0
696 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Moktarpur (Village code 315321) under Sahajadpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID 1723365 in the District of Murshidabad. (Sl No-34) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000060/2021-2022 | 1231/MURD | 13/05/2021 | 180 | M/S GUHA & ROY ENTERPRISE | 80.38 | 112.3 | 1
697 | Murshidabad Division | Berhampur Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000454/2021-2022 | 304/BSD | 13/08/2021 | 30 | IMAGIN COMMUNICATION | 4.34 | 8.68 | 0
698 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Balarampur (Village code 315322)under Sahajadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of BERHAMPORE Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723365 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000462/2020-2021 | 3139/MURD | 11/12/2020 | 60 | M/S M.S. ENTERPRISE | 27.16 | 22.25 | 1
699 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bahurul (Village code 315329) under Sahajadpur Ground Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID 1723365 in the District of Murshidabad.(Sl-4) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001138/2021-2022 | 2460/MURD | 26/08/2022 | 180 | SANJAY BISWAS | 70.29 | 0 | 0
700 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sahajadpur (Village code 315326) under Sahajadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte.Scheme ID 1723365 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001142/2021-2022 | 3840/MURD | 08/12/2021 | 90 | J.S. CONSTRUCTION | 54.01 | 51.74 | 1
701 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution pipeline in connection with FHTC work at North Durgapur area of Sahajadpur village under SAHAJADPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000732/2022-2023 | 257-MSD/22-23 | 17/08/2022 | 0 | MITHUN ROY | 4.8 | 0 | 0
702 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution pipeline in connection with FHTC work at Muktarpur area of Sahajadpur village under SAHAJADPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000733/2022-2023 | 257-MSD/22-23 | 17/08/2022 | 0 | MITHUN ROY | 1.54 | 0 | 0
703 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution pipeline in connection with FHTC work at South Durgapur area of Sahajadpur village under SAHAJADPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000734/2022-2023 | 258-MSD/22-23 | 18/08/2022 | 0 | M/S GUHA AND ROY | 5 | 0 | 0
704 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution pipeline in connection with FHTC work at Muktarpur area of Sahajadpur village under SAHAJADPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000735/2022-2023 | 258-MSD/22-23 | 18/08/2022 | 0 | M/S GUHA AND ROY | 4.84 | 0 | 0
705 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Nishindra Para and adjoining habitations under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000076/2021-2022 | 1486/MURD | 21/06/2021 | 60 | PRIYANKA CONSTRUCTION | 27.85 | 0 | 1
706 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Karbala and adjoining habitations under Mahadeb Nagar(CT)( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000080/2021-2022 | 1547/MURD | 23/06/2021 | 60 | MOLLA ENTERPRISE | 27.32 | 50.69 | 0
707 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Tarapur under Mamrejpur(CT) ( Village Code -313835) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000083/2021-2022 | 1563/MURD | 24/06/2021 | 60 | SUMAN CHOWDHURY | 33.18 | 33.15 | 0
708 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Pashim Jikri & Natun Momrajpur and adjoining habitations under Mamrejpur(CT) ( Village Code -313835) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000160/2021-2022 | 1662/MURD | 02/07/2021 | 60 | MONDAL ENTERPRISE | 21.09 | 38.85 | 0
709 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Gopalnagar and adjoining habitations under Mamrejpur(CT) ( Village Code -313835) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000180/2021-2022 | 1710/MURD | 07/07/2021 | 60 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 28.28 | 24.83 | 1
710 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jaladipur and adjoining habitations under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000184/2021-2022 | 1572/MURD | 25/06/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 30.89 | 27.25 | 0
711 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dakshin Mahadev Nagar under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000203/2021-2022 | 1724/MURD | 08/07/2021 | 60 | NOVELTY CONSTRUCTION | 35.58 | 35.58 | 0
712 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Balidapukur under Mamrejpur(CT) ( Village Code -313835) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000209/2021-2022 | 1746/MURD | 09/07/2021 | 60 | RAHAMAN CONSTRUCTION | 30.9 | 27.91 | 0
713 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Maddham Mahadev Nagar under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000248/2021-2022 | 1727/MURD | 08/07/2021 | 60 | A.S. CONSTRUCTION | 31.14 | 27.21 | 0
714 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Uttar Mahadev Nagar under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000249/2021-2022 | 1726/MURD | 08/07/2021 | 60 | SARASWATI ENTERPRISE | 39.81 | 32.3 | 1
715 | Murshidabad Division |  | Allied work of laying U.P.V.C pipe line for " Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Village Nishindra Para & adjoining habitation under Mahadebnagar(CT) (Village code 313837) under Mahadebnagar Ground water Based water supply scheme for Arsenic Affected Area of Farakka Block under Murshidabad Division, P.H.E. Dte. Scheme ID-0001723329 in the District Murshidabad. |  |  | ORD/001270/2021-2022 | 389/JSD | 31/12/2021 | 30 | HERITAZE CONSTRUCTION | 4.67 | 4.67 | 0
716 | Murshidabad Division |  | Allied work of laying UPVC Pipe line for " Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) under command area of village Mahadebnagar (CT) (Village Code-313837)" under command area of Mahadevnagar Zone-I Water supply scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723329) in the district of Murshidabad. (Part-I). |  |  | ORD/001754/2021-2022 | 122/JSD | 22/03/2022 | 30 | MOTI RAHAMAN | 4.99 | 4.74 | 0
717 | Murshidabad Division |  | Allied work of laying UPVC Pipe line for " Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) under command area of village Mahadebnagar (CT) (Village Code-313837)" under command area of Mahadevnagar Zone-I Water supply scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723329) in the district of Murshidabad. (Part-II). |  |  | ORD/001755/2021-2022 | 123/JSD | 22/03/2022 | 30 | APU CONSTRUCTION | 4.98 | 4.73 | 0
718 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Nishindra Para and adjoining habitations under Mahadeb Nagar(CT) (Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | VCH/000231/2021-2022 | 27-MSD / 21-22 | 18/08/2021 | 0 | PRIYANKA CONSTRUCTION | 25.58 | 0 | 0
719 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-25 |  |  | VCH/000987/2022-2023 | 398-MSD/22-23 | 11/11/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 4.38 | 0 | 0
720 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of AURANGABAD (Village code 313981) under AURANGABAD Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte.Scheme ID 0005184162 |  |  | ORD/001155/2021-2022 | 3976/MURD | 21/12/2021 | 180 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 309.91 | 48.24 | 1
721 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 540/9/MURD | 25/02/2022 | 0 | Resource Division | 42.35 | 0 | 0
722 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with JALSWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village AURANGABAD (Village Code 313981) under AURANGABAD Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-II Block in the District of Murshidabad. TENDER NO -129 OF 21-22 SE MC |  |  | VCH/000642/2022-2023 | 253-MSD/22-23 | 11/08/2022 | 0 | S.ENTERPRISE | 67.38 | 0 | 0
723 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kanai (Village code 314674) under Jitpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID ¿ 0001723374 in the District of Murshidabad. (Sl No-10) |  |  | ORD/000263/2020-2021 | 180/MURD | 19/01/2021 | 180 | UMWELT ENGINEER PVT LTD | 81.67 | 94.41 | 1
724 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Par Raghunathpur (Village code 314677) under Jitpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723374 in the District of Murshidabad. (Sl No-11) |  |  | ORD/000264/2020-2021 | 181/MURD | 19/01/2021 | 180 | UMWELT ENGINEER PVT LTD | 79.2 | 47.39 | 0
725 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Uttar Gopalpur (Village code 314744) under Purusottampur and Jitpur Ground Water Based Water Supply Scheme under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad. |  |  | ORD/000820/2020-2021 | 031/MURD | 05/01/2021 | 60 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 9.28 | 0 | 0
726 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Radhakantapur(Village code 314670) under Jitpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723374 (Sl No-12) |  |  | ORD/000846/2021-2022 | 3286/MURD | 05/10/2021 | 180 | M/S M.S. ENTERPRISE | 51.18 | 49.14 | 1
727 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of JITPUR (Village code 314669) under JITPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723374 |  |  | ORD/001192/2021-2022 | 4024/MURD | 24/12/2021 | 180 | SUJIT KUMAR SAHA | 119 | 91.68 | 1
728 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 372 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Radhakantapur (Village code 314670) under Jitpur Ground water based water supply scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0001723374) |  |  | ORD/001735/2021-2022 | 704/MURD | 14/03/2022 | 20 | M/S M.S. ENTERPRISE | 14.28 | 12.1 | 1
729 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 21/MURD | 05/01/2022 | 0 | Resource Division | 15.08 | 0 | 0
730 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-17 |  |  | VCH/000874/2022-2023 | 361-MSD/22-23 | 19/10/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 35.91 | 0 | 0
731 | Berhampore Division I | Berhampur Division I | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under AMAIPARA (Zone-A) Surface Water based Water Supply Scheme of Central Sector (Part-I) under Murshidabad -Jiaganj Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000120/2023-2024 | 516/BD-I | 25/07/2023 | 90 | M/S. M.G. CONSTRUCTION | 102.61 | 0 | 0
732 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.01.2023 to 31.07.2023. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000172/2022-2023 | 1387/BD-I | 23/12/2022 | 212 | SOUVIK HALDER | 1.06 | 1.68 | 70
733 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub Division, PHE Dte. period for 01.01.2023 to 31.12.2023. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000184/2022-2023 | 1388/BD-I | 23/12/2022 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 4.77 | 90
734 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Tantipara (Village code 314895) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000455/2021-2022 | 1859/BD-I | 07/10/2021 | 60 | BIJOY SINGHA | 9.03 | 6.19 | 1
735 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Bahadurpur (Village code 314894) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000456/2021-2022 | 1860/BD-I | 07/10/2021 | 90 | M/S. SUKUMAR SINHA | 21.72 | 0 | 0
736 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Goljarbag (Village code 314893) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000457/2021-2022 | 1861/BD-I | 07/10/2021 | 90 | M/S. SUKUMAR SINHA | 42.48 | 0 | 0
737 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Bhrigurambati (Village code 314892) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000458/2021-2022 | 1862/BD-I | 07/10/2021 | 60 | AZAD ENTERPRISE | 12.67 | 11.77 | 1
738 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Gujasti Rampur (Village code 314898) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000460/2021-2022 | 1864/BD-I | 07/10/2021 | 60 | N.H ENTERPRISE | 13.74 | 11.84 | 1
739 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Jayenpur (Village code 314900) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000461/2021-2022 | 1865/BD-I | 07/10/2021 | 90 | AJAY MONDAL | 26.81 | 19.86 | 1
740 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
741 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dakshin Ganespur (Village code 314938) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000472/2021-2022 | 1874/BD-I | 07/10/2021 | 90 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 21.49 | 18.74 | 1
742 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Amaipara (Village code 314910) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000473/2021-2022 | 1875/BD-I | 07/10/2021 | 90 | AJAY MONDAL | 27.02 | 20.95 | 1
743 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar (Village code 314909) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000474/2021-2022 | 1876/BD-I | 07/10/2021 | 60 | GOUTAM KUMAR CHAUDHURI | 6.69 | 6.11 | 1
744 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bagdhar (Village code 314906) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000475/2021-2022 | 1877/BD-I | 07/10/2021 | 60 | MAA SANKARI ENTERPRISE | 20.03 | 17.93 | 1
745 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ambarnagar (Village code 314905) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000476/2021-2022 | 1878/BD-I | 07/10/2021 | 90 | DOBAY CONSTRUCTION | 24.01 | 19.7 | 1
746 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilkandi (Village code 314904) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000477/2021-2022 | 1879/BD-I | 07/10/2021 | 90 | SANJAY BISWAS | 33.81 | 24.37 | 90
747 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raichandpur (Village code 314902) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000478/2021-2022 | 1880/BD-I | 07/10/2021 | 90 | DOBAY CONSTRUCTION | 21.62 | 18.26 | 1
748 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Begampur (Village code 314908) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000552/2021-2022 | 1910/BD-I | 08/10/2021 | 30 | PRADIP KUMAR SAHA | 2.61 | 0 | 0
749 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Payasti Katiganga (Village code 314891) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000553/2021-2022 | 1911/BD-I | 08/10/2021 | 30 | PRAVAT KUMAR GHOSH | 2.97 | 2.27 | 1
750 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kanchannagar (Village code 314907) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000554/2021-2022 | 1912/BD-I | 08/10/2021 | 30 | ANKITA ENTERPRISE | 3.35 | 2.8 | 1
751 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sadek Sarai (Village code 314897) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000752/2021-2022 | 118/BD-I | 03/02/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 11.58 | 8.85 | 1
752 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baliapukur(Village code 314901) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000753/2021-2022 | 217/BD-I | 24/02/2022 | 45 | DAS TRADING CO | 36.42 | 27.95 | 1
753 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chaipara (Village code 314896) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000754/2021-2022 | 2209/BD-I | 10/12/2021 | 20 | PRATIMA CONSTRUCTION | 5.21 | 5 | 1
754 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chandipur(Village code 314903) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000755/2021-2022 | 2210/BD-I | 10/12/2021 | 30 | ASHIS KUMAR BHATTACHARYYA | 24.26 | 14.34 | 100
755 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Amaipara Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000757/2021-2022 | 2223/BD-I | 15/12/2021 | 90 | SOM CONSTRUCTION AGENCY | 83.92 | 83.05 | 1
756 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Narayanpur (Village code 314899) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000849/2021-2022 | 117/BD-I | 03/02/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 13.73 | 0 | 100
757 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hogaldanga (Village code 315432) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000235/2021-2022 | 1829/BD-I | 05/10/2021 | 60 | NIRMAL UDYOG | 51.89 | 0 | 0
758 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Goraipur,Sadipur and Sundalpur (Village code 315417,315418 ,315431) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000236/2021-2022 | 1830/BD-I | 05/10/2021 | 40 | M/S SINHA & SONS | 40.25 | 26.91 | 1
759 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hajidanga,Baradha,Ganti Baisnab Charan,Kaladanga and Charislampur (Village code 315434,315435 ,315437,315436,315438) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000237/2021-2022 | 1831/BD-I | 05/10/2021 | 80 | KAMIRUL SK AND CO. | 73.49 | 65.78 | 1
760 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ruharpara,Baliharpur,Habipur,Dhanaipur,Mirpur and Garamgari (Village code 315426,315427 ,315428,315429,315430,315439) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000238/2021-2022 | 1832/BD-I | 05/10/2021 | 100 | M/S GUHA AND ROY ENTERPRISE | 97.55 | 81.51 | 0
761 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nutanpara and Madanpur (Village code 315424,315425) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000239/2021-2022 | 1833/BD-I | 05/10/2021 | 80 | M/S GUHA AND ROY ENTERPRISE | 81.18 | 80.7 | 1
762 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
763 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chhayghari (Village code 315433) under Habibpur (Zone-G) Water Supply Scheme of Central Sector Part-I in Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-08) | Assistant Engineer-I | JE | ORD/000495/2021-2022 | 1885/BD-I | 07/10/2021 | 180 | M/S S.DAS & ENTERPRISE | 275.21 | 151.91 | 1
764 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nidhi Nagar Sarsabad,Char Harharia and Char Panchananpur (Village code 315440,315441,315442) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000581/2021-2022 | 1994/BD-I | 01/11/2021 | 100 | NAYLA CONSTRUCTION | 90.2 | 72.42 | 1
765 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Habibpur Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE | ORD/000760/2021-2022 | 2226/BD-I | 15/12/2021 | 90 | KUNDU CONSTRUCTION | 72.9 | 60.13 | 1
766 | Murshidabad Division | Berhampur Sub-Division | Laying of 160mm dia UPVC pipeline and road restoration work for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Mahula (village code 315354) under Char Mahula Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000153/2022-2023 | 148/BSD | 12/04/2022 | 30 | SANJIB GHOSH | 4.84 | 4.84 | 0
767 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHULA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000517/2021-2022 | 349/BSD | 27/08/2021 | 30 | IMAGIN COMMUNICATION | 4.16 | 4.16 | 0
768 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Charmahula ( Village Code-315354) under Charmahula Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. (Scheme I.D.-0001723196) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001466/2021-2022 | 279/MURD | 03/02/2022 | 60 | MAA CONSTRUCTION | 42.13 | 41.13 | 0
769 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001641/2021-2022 | 480/MURD | 22/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 0 | 0
770 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 0 | 1
771 | Murshidabad Division | Berhampur Sub-Division | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Mahula (village code 315354) under Char Mahula Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001730/2021-2022 | 91/BSD | 07/03/2022 | 15 | S. DUTTA | 4.81 | 0 | 0
772 | Murshidabad Division | Berhampur Sub-Division | Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap Connection FHTC in connection with JJM and Jal Swapna under command area of village of Char Mahula Village code 315354 under Char Mahula W/S Scheme in the dist of MSD PHE DTE. Tender no - 182 of 21-22 by AE BSD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000004/2022-2023 | 03-MSD/22-23 | 14/04/2022 | 0 | S. DUTTA | 4.81 | 0 | 0
773 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RADHARGHAT-I G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000506/2021-2022 | 341/BSD | 27/08/2021 | 30 | IMAGIN COMMUNICATION | 4.16 | 4.16 | 0
774 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) |  |  | ORD/001659/2021-2022 | 558/MURD | 28/02/2022 | 180 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0
775 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village MARADIGHI (Village Code 315674) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. |  |  | ORD/000634/2020-2021 | 3008/MURD | 04/12/2020 | 45 | SUPIA CONSTRUCTION | 11.14 | 9.93 | 0
776 | Murshidabad Division |  | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Pilkhna ( Village Code -315666) under Rejinagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. |  |  | ORD/000746/2022-2023 | 274/BSD | 24/06/2022 | 30 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 4.84 | 4.54 | 0
777 | Murshidabad Division | Lalbag Sub-Division | Laying of 200 mm dia DI pipeline from Near Shop of Nazir Sk to Jain Temple More, Lalgola including supply of specials in connection with FHTC work of Village of Lalgola (Village Code 314224 ) under Lalgola Ground Water Based Water Supply Scheme under Lalbagh Sub-Division, P.H.Engineering Dte. (Part-A). | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000097/2022-2023 | 175/LSD | 06/05/2022 | 20 | MADAN MOHAN SASMAL | 2.32 | 2.32 | 0
778 | Murshidabad Division | Lalbag Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bilbarakpara (Village code 314225) under Lalgola Ground Water Based water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005186640 in the District of Murshidabad. (Sl No-01) | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000137/2020-2021 | 559/MURD | 08/02/2021 | 180 | AQUATHERM WATER TREATMENT PVT.LTD. | 255.81 | 8.89 | 0
779 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 0 | 100
780 | Murshidabad Division | Lalbag Sub-Division | Laying of 200 mm dia DI pipeline from Near Shop to Nazir Sk to Head Work Site Lalgola. including supply of specials in connection with FHTC work of Village of Lalgola (Village Code 314224 ) Lalgola Ground Water Based Water Supply Scheme under Lalbagh Sub-Division, P.H.Engineering Dte. (248.M) (Part-B) | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000225/2022-2023 | 200/LSD | 11/05/2022 | 25 | SUGATA CHOWDHURY | 2.14 | 2.13 | 0
781 | Murshidabad Division | Lalbag Sub-Division | Laying of different dia UPVC pipeline from M.N. Academy more to Rajgurupara in connection with"Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lalgola( Village Code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000249/2022-2023 | 221/LSD | 11/05/2022 | 30 | SUGATA CHOWDHURY | 4.06 | 4.05 | 0
782 | Murshidabad Division | Lalbag Sub-Division | Restoration work by cement concrete (1:1.5:3) after laying of DI pipe in connection with FHTC work of Village of Lalgola (Village Code 314224 ) Lalgola Ground Water Based Water Supply Scheme under Lalbagh Sub-Division, P.H.Engineering Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000250/2022-2023 | 222/LSD | 11/05/2022 | 30 | MADAN MOHAN SASMAL | 3.94 | 3.91 | 0
783 | Murshidabad Division | Lalbag Sub-Division | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Krishnapur (314153) Habitation Madiapara of Lalgola & adjoining mouzas of under Ground Water Based Water Supply Scheme for Arsenic affected areas of Lalgola Block of Murshidabad District under Murshidabad Division P.H.E Dte . Part- C. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000255/2022-2023 | 227/LSD | 11/05/2022 | 30 | JYOTSNA PUTATUNDA | 4.93 | 4.8 | 0
784 | Murshidabad Division | Lalbag Sub-Division | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Lalgola (314224) of Lalgola & adjoining mouzas of under Ground Water Based Water Supply Scheme for Arsenic affected areas of Lalgola Block of Murshidabad District under Murshidabad Division P.H.E Dte . Part- E. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000256/2022-2023 | 228/LSD | 11/05/2022 | 30 | AEF ENTERPRISE | 4.84 | 3.72 | 0
785 | Murshidabad Division | Lalbag Sub-Division | Laying of diffrent dia UPVC pipe line in connection with (FHTC) work at village Krishnapur (Village Code- 314153) under Lalgola Ground Water Supply Scheme for Arsenic affected areas of Lalgola Block under Lalbagh Sub-Division under Murshidabad Division, P.H.Engineering Dte. Part-A. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000259/2022-2023 | 231/LSD | 11/05/2022 | 30 | AEF ENTERPRISE | 4.99 | 4.99 | 0
786 | Murshidabad Division | Lalbag Sub-Division | Laying of diffrent dia UPVC pipe line in connection with(FHTC) work at village Krishnapur (Village Code- 314153) under Lalgola Ground Water Supply Scheme for Arsenic affected areas of Lalgola Block under Lalbagh Sub-Division under Murshidabad Division, P.H.Engineering Dte. Part-B. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000260/2022-2023 | 232/LSD | 11/05/2022 | 30 | RIZZ ENTERPRISE | 4.56 | 4.55 | 0
787 | Murshidabad Division | Lalbag Sub-Division | Laying of diffrent dia UPVC pipe line in connection with (FHTC) work at village Lalgola (Village Code- 314224) under Lalgola Ground Water Supply Scheme for Arsenic affected areas of Lalgola Block under Lalbagh Sub-Division under Murshidabad Division, P.H.Engineering Dte. Part-A. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000261/2022-2023 | 233/LSD | 11/05/2022 | 30 | M/S JOY MA BANAMALI | 4.99 | 2.9 | 0
788 | Murshidabad Division | Lalbag Sub-Division | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Krishnapur (314153) Habitation Manic Chak of Lalgola & adjoining mouzas of under Ground Water Based Water Supply Scheme for Arsenic affected areas of Lalgola Block of Murshidabad District under Murshidabad Division P.H.E Dte . Part- C. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000265/2022-2023 | 236/LSD | 11/05/2022 | 30 | M/S.S.S. ENTERPRISE | 4.89 | 0 | 0
789 | Murshidabad Division | Lalbag Sub-Division | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Lalgola (314224) of Lalgola & adjoining mouzas of under Ground Water Based Water Supply Scheme for Arsenic affected areas of Lalgola Block of Murshidabad District under Murshidabad Division P.H.E Dte . Part- B. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000270/2022-2023 | 241/LSD | 11/05/2022 | 30 | SOUVIK HALDER | 4.98 | 0 | 0
790 | Murshidabad Division | Lalbag Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Lalgola (Village code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID 5185583 in the District of Murshidabad. (Sl No-02) | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000273/2020-2021 | 46/MURD | 06/01/2021 | 180 | BIJAY CHOWDHURY | 152 | 0 | 0
791 | Murshidabad Division | Lalbag Sub-Division | Restoration of road for laying of different dia UPVC/CI/DI pipelines in connection with FHTC work from BDO Office More to M.N. Academy Ground area under Lalgola Water Supply Scheme under Lalbagh Sub-Division P.H.E. Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000352/2022-2023 | 294/LSD | 12/07/2022 | 30 | MADAN MOHAN SASMAL | 0.96 | 0.96 | 0
792 | Murshidabad Division | Lalbag Sub-Division | Restoration of road for laying of different dia UPVC/CI/DI pipelines in connection with FHTC work from Jain Mandir to PHE OHR more via Rathbari more, Battala more & PWD (Roads) more under Lalgola Water Supply Scheme under Lalbagh Sub-Division P.H.E. Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000353/2022-2023 | 295/LSD | 12/07/2022 | 30 | SUGATA CHOWDHURY | 4.8 | 4.78 | 0
793 | Murshidabad Division | Lalbag Sub-Division | Allied work for laying of 110 mm dia upvc pipeline at Minister para-area in connection with " Retrofitting providing FHTC in connection with JJM under command area of village of Lalgola (village code-314224) under Lalgola Ground Water Based Water Supply Scheme for arsenic affected areas of Lalgola Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000660/2023-2024 | 3545/MURD | 17/11/2023 | 30 | SUGATA CHOWDHURY | 2.18 | 0 | 70
794 | Murshidabad Division | Lalbag Sub-Division | Allied work for Laying of different dia UPVC Pipeline at Radhabagh area in connection with'Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilborakopra ( Village Code 314225) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. (Part-B). | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000303/2022-2023 | 112-MSD/22-23 | 06/05/2022 | 0 | SUGATA CHOWDHURY | 4.7 | 0 | 0
795 | Murshidabad Division | Lalbag Sub-Division | Allied work for laying of different dia UPVC pipeline at radhabagh area in connection with Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILBORAKOPRA (Village Code 314225) under LALGOLA Ground Water Based Water Supply Scheme for arsenic affected areas of LALGOLA Block in the District of Murshidabad. Tender no - 59 of 21-22 by AE LSD | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000304/2022-2023 | 113-MSD/22-23 | 06/05/2022 | 0 | MADAN MOHAN SASMAL | 4.84 | 0 | 0
796 | Murshidabad Division | Lalbag Sub-Division | Allied work for laying of different dia UPVC pipeline at radhabagh area in connection with Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILBORAKOPRA (Village Code 314225) under LALGOLA Ground Water Based Water Supply Scheme for arsenic affected areas of LALGOLA Block in the District of Murshidabad. Tender no - 57 of 21-22 by AE LSD | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000306/2022-2023 | 115-MSD/22-23 | 06/05/2022 | 0 | DEB SANKER BHATTACHARYA | 4.81 | 0 | 0
797 | Murshidabad Division | Lalbag Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILBARAKPARA (Village Code 314225) under LALGOLA Ground Water Based Water Supply Scheme for arsenic affected areas of LALGOLA Block in the District of Murshidabad. Tender no - 106 of 20-21 by EE MURD | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000311/2022-2023 | 118-MSD/22-23 | 10/05/2022 | 0 | AQUATHERM WATER TREATMENT PVT.LTD. | 31.91 | 0 | 0
798 | Murshidabad Division | Lalbag Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bilbarakpara (Village code 314225) under Lalgola Ground Water Based water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005186640 in the District of Murshidabad. (Sl No-01) | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000436/2022-2023 | 168-MSD/22-23 | 17/05/2022 | 0 | AQUATHERM WATER TREATMENT PVT.LTD. | 90.43 | 0 | 0
799 | Murshidabad Division | Lalbag Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Lalgola (Village code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID 5185583 in the District of Murshidabad. (Sl No-02) | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000495/2022-2023 | 123-MSD/22-23 | 07/05/2022 | 0 | BIJAY CHOWDHURY | 37.56 | 0 | 0
800 | Murshidabad Division | Lalbag Sub-Division | Laying of different dia UPVC Pipeline form Jain Mondir to Fish Market More & H/O of Kailash Vakat to Lalgola P.S. in connection with'Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lalgola( Village Code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000532/2022-2023 | 189-MSD/22-23 | 29/06/2022 | 0 | MADAN MOHAN SASMAL | 2.98 | 0 | 0
801 | Murshidabad Division | Lalbag Sub-Division | Laying of different dia UPVC Pipeline form H/O of Niaz Biswas to H/O of Moni Saha & H/O of Helal Maulabi to Fish Market More in connection with'Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lalgola( Village Code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000533/2022-2023 | 190-MSD/22-23 | 29/06/2022 | 0 | SUGATA CHOWDHURY | 4.28 | 0 | 0
802 | Murshidabad Division | Lalbag Sub-Division | Allied work for Laying of different dia UPVC Pipeline at Krishnapur area (Near Hospital) in connection with'Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilborakopra ( Village Code 314225) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000673/2022-2023 | 214-MSD/22-23 | 20/07/2022 | 0 | PROSENJIT DAS | 4.7 | 0 | 0
803 | Murshidabad Division | Lalbag Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Lalgola (Village code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID 5185583 in the District of Murshidabad. (Sl No-02) | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000772/2022-2023 | 266-MSD/22-23 | 26/08/2022 | 0 | BIJAY CHOWDHURY | 96.48 | 0 | 0
804 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Tikar Bariakalkihara (314642),of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000116/2022-2023 | 1199/MURD | 10/05/2022 | 45 | NADIA TUBEWELLS | 16.6 | 9.31 | 100
805 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Faridpur Zone-I Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000418/2022-2023 | 2085/MURD | 27/07/2022 | 1040 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 477.83 | 370.09 | 75
806 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000025/2022-2023 | 2507/G/MURD | 31/08/2022 | 0 | Resource Division | 26.31 | 0 | 0
807 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000038/2024-2025 | MURD/2481/10 | 04/09/2024 | 0 | Resource Division | 15.32 | 0 | 0
808 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000160/2023-2024 | 1180/MURD/08 | 29/04/2023 | 0 | Resource Division | 26.31 | 0 | 0
809 | Murshidabad Division | Berhampur M/E Division | Construction of Two nos Pump House cum Chlorine Room with sanitary and Water Supply Arrangement ,Construction of Boundary Wall of 200 m, Construction of RCC approach road (3 Mtr Wide)of 100 mtr length, Laying of Rising Main, Construction of 450 Cum OHR, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works and Land Development Works for Augmentation of Malibari Water Supply scheme at Raninagar-II Block under Murshidabad Division,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000024/2024-2025 | 1816/MURD | 20/06/2024 | 560 | M/S B.M. INDUSTRIES | 282.92 | 0 | 50
810 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 100 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for MALIBARI Ground Based Water Supply Scheme in Raninagar -II Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000029/2025-2026 | 1024/MURD | 05/05/2025 | 60 | M/S. S. DAS AND ENTERPRISE | 40.44 | 0 | 0
811 | Murshidabad Division | Berhampur M/E Division | Balance & Allied Work for Laying Distribution System , FHTC of Malibari Water Supply Scheme in Raninagar-II Block ,under Murshidabad Division , PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000055/2024-2025 | 1986/MURD | 08/07/2024 | 363 | DAS TRADING CO. | 95.72 | 0 | 60
812 | Murshidabad Division | Berhampur M/E Division | Formal work order for laying Distribution System (HDPE Pipe) of for AUGMENTATION of Ground Water Based MALIBARI PWSS to Accommadate FHTC at Raninagar- II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000170/2022-2023 | 1316/MURD | 20/05/2022 | 120 | NAYLA CONSTRUCTION | 217.49 | 183.08 | 100
813 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Malibari Water Supply Scheme of 3rd TW Site under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000581/2022-2023 | 3064/MURD | 17/11/2022 | 30 | SUJIT KUMAR SAHA | 9.21 | 8.09 | 0
814 | Murshidabad Division | Berhampur M/E Division | Formal work order for Functional Household Tap Connections (FHTC) in Bilchatra & Malibari Village ( Village Code -314568 ,314569 ) in connection with Augmentation of Malibari Ground Water Based Water Supply Scheme Raninagar-II Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000686/2022-2023 | 163/MURD | 17/01/2023 | 60 | KUNDU CONSTRUCTION | 170.31 | 167.79 | 95
815 | Murshidabad Division | Berhampur M/E Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bilchatra (Village Code -314568) under Malibari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184027) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000714/2020-2021 | 581/MURD | 09/02/2021 | 60 | ULTRA CONSTRUCTION. | 27.7 | 5.11 | 1
816 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (MALIBARI PWSS Scheme, Block - Raninagar-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000831/2021-2022 | 3264/MURD | 05/10/2021 | 60 | RADIANT | 5.89 | 5.89 | 1
817 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000021/2022-2023 | 2507/C/MURD | 31/08/2022 | 0 | Resource Division | 9.22 | 0 | 0
818 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000044/2024-2025 | MURD/2991/03 | 13/11/2024 | 0 | Resource Division | 30.01 | 0 | 0
819 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000053/2022-2023 | 3052/F/MURD | 17/11/2022 | 0 | Resource Division | 23.33 | 0 | 0
820 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000110/2023-2024 | 1167/MURD/3 | 28/04/2023 | 0 | Resource Division | 27.6 | 0 | 0
821 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT MALIBARI PHI, ID304238384 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01219/2023-2024 | 287/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 12.87 | 0 | 0
822 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-III of Malibari ground water based water supply scheme under Block- Raninagar-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000833/2023-2024 | 3774/MEDB | 03/11/2023 | 92 | ARINDAM MAJUMDAR | 11.02 | 0 | 0
823 | Murshidabad Division | Berhampur M/E Division | Payment Cost of repairing road from Biswaspara (SH) to Jortala More PWD Road under Jalangi Block in Murshidabad District vide packeage no WB 13-409. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/00826/2024-2025 | 303-MSD/2024-25 | 29/08/2024 | 0 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 32.83 | 0 | 0
824 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Jalangi Zone III Part B Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000340/2022-2023 | 1806/MURD | 11/07/2022 | 150 | HOQUEDAR ALI | 149.27 | 0 | 50
825 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-III/ Part-B Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000588/2022-2023 | 3057/MURD | 17/11/2022 | 45 | NADIA TUBEWELLS | 23.55 | 20.03 | 100
826 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000020/2022-2023 | 2507/B/MURD | 31/08/2022 | 0 | Resource Division | 74.09 | 0 | 0
827 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R(Consultancy work)in connection with the Functional Household Connection of different existing PWSS(Jalangi PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | VCH/000353/2022-2023 | 183-MSD/22-23 | 13/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 16.77 | 0 | 0
828 | Berhampore Mechanical | Berhampur M/E Division | New connection charge for Jalangi W/S Scheme (Part-B) Zone-III, P/H No.-III. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/00272/2023-2024 | 92/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 0.9 | 0 | 0
829 | Berhampore Mechanical | Berhampur M/E Division | ADDL SERVICE CONNECTION CHARGES AT JOYKRISHNAPUR ,JALANGI PWSS, PART B,Z-3,PH3, ID 860279298 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01109/2023-2024 | 212/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 5.14 | 0 | 0
830 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT JALANGI PWSS Z3 PLOT LR 538 MURSHIDABAD ID 304238698 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01272/2023-2024 | 297/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 9.63 | 0 | 0
831 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of JALANGI , Zone- III/Part-B ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000830/2023-2024 | 3771/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 20.33 | 15.79 | 50
832 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Jalangi Zone II Part-B Ground Water Based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) within Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000327/2022-2023 | 1691/MURD | 28/06/2022 | 1099 | KISMAT ARA BEGAM | 131.01 | 28.2 | 75
833 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-II/ Part-B Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000586/2022-2023 | 3055/MURD | 17/11/2022 | 45 | MAMATA USHA ENTERPRISE | 23.58 | 19.41 | 1
834 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000037/2024-2025 | MURD/2481/09 | 04/09/2024 | 0 | Resource Division | 14.57 | 0 | 0
835 | Berhampore Mechanical | Berhampur M/E Division | New connection charge for Jalangi W/S Scheme (Part-B) Zone-II, P/H No.-IV. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/00268/2023-2024 | 87/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 1.35 | 0 | 0
836 | Berhampore Mechanical | Berhampur M/E Division | New connection charge for Jalangi W/S Scheme (Part-B) Zone-II, P/H No.-III. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/00270/2023-2024 | 88/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 1.27 | 0 | 0
837 | Berhampore Mechanical | Berhampur M/E Division | addl service connection charges at sahebrampur palpara jalangi pwss part b,z 2,ph 4 ID 860279296 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01105/2023-2024 | 210/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 8.59 | 0 | 0
838 | Berhampore Mechanical | Berhampur M/E Division | ADDL SERVICE CONNECTION CHARGES AT SAHEBRAMPUR BOLAITALA , JALANGI PWSS PART B,Z2,PH2 ID 860281603 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01111/2023-2024 | 211/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 7.15 | 0 | 0
839 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of JALANGI , Zone- II/Part-B ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000824/2023-2024 | 3769/MEDB | 03/11/2023 | 92 | P. K. ENGINEERING | 22.5 | 0 | 65
840 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of KARIMPUR Jalangi Zone-I( Part A) Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000358/2022-2023 | 2047/MURD | 26/07/2022 | 180 | M/S. S. DAS AND ENTERPRISE | 692.97 | 479.45 | 40
841 | Murshidabad Division | Berhampur M/E Division | Balance Work for Laying of Distribution System for Augmentation of Karimpur-Jalangi Zone-I Part-A Piped water supply scheme to accommodate FHTC (Functional House Hold Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000740/2023-2024 | 65/MURD | 08/01/2024 | 60 | S.S.INFRASTRUCTURE | 134.77 | 14.7 | 10
842 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000034/2024-2025 | MURD/2481/06 | 04/09/2024 | 0 | Resource Division | 27.07 | 0 | 0
843 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000037/2022-2023 | 2780/F/MURD | 01/10/2022 | 0 | Resource Division | 27.07 | 0 | 0
844 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000156/2023-2024 | 1180/MURD/05 | 29/04/2023 | 0 | Resource Division | 220.24 | 0 | 0
845 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-I under Karimpur-Jalangi (Part-A) ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000031/2023-2024 | 582/MEDB | 31/01/2024 | 90 | ASSOCIATED ELECTRICAL CO. | 12.41 | 0 | 0
846 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Kasba Bahadurpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000108/2022-2023 | 1361/BD-I | 21/12/2022 | 30 | KAKALI ENTERPRISE | 2.41 | 1.66 | 100
847 | Berhampore Division I | Berhampur Division I | Formal Work order for Augmentation of KASBA BAHADURPUR Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000162/2022-2023 | 1454/BD-I | 17/01/2023 | 365 | DECON INDIA | 444.11 | 216.93 | 70
848 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kasba Bahadurpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000285/2022-2023 | 1809/BD-I | 31/03/2023 | 30 | HARUN ALL RASHID & BROTHERS | 17.66 | 0 | 100
849 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000064/2023-2024 | 196/BD-I/11 | 09/02/2024 | 0 | Resource Division | 70.91 | 0 | 0
850 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION AT KASBA BAHADURPUR PH-1 | Assistant Engineer-I | JE,Junior engineer-III | BILL/00664/2024-2025 |  | 03/09/2024 | 0 | WBSEDCL | 5.46 | 0 | 0
851 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Kasba Bahadurpur ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000039/2023-2024 | 3732/MEDB | 03/11/2023 | 1300 | S.P. ENTERPRISE (BAGUIHATI) | 22.37 | 0 | 8
852 | Murshidabad Division | Berhampur M/E Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
853 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 500 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Kasiadanga Zone I & II PWSS in Raghunathganj II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000552/2023-2024 | 3190/MURD | 12/10/2023 | 365 | ASTRA | 861.48 | 0 | 0
854 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000042/2024-2025 | MURD/2991/01 | 13/11/2024 | 0 | Resource Division | 41.24 | 0 | 0
855 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000100/2023-2024 | 1167/MURD/7 | 28/04/2023 | 0 | Resource Division | 40.3 | 0 | 0
856 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under KASIADANGA ground water based water supply scheme under Block_ RAGHUNATHGANJ-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000096/2023-2024 | 4336/MEDB | 29/12/2023 | 459 | BHAGIRATHI JUTE AND HOLDINGS PVT LTD | 22.92 | 0 | 40
857 | Berhampore Division I | Berhampur Division I | Formal work order for Augmentation of HARIRAMPUR Piped water supply scheme to accommodate construction of OHR, Service Road, Laying of Design Pipe Line and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I, PHE. Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000136/2022-2023 | 1445/BD-I | 17/01/2023 | 1275 | S.K. CONSTRUCTION DEBKUNDU , P.S.- BELDANGA, | 310.02 | 0 | 65
858 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Harirampur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000169/2022-2023 | 1440/BD-I | 16/01/2023 | 30 | K.B CONSTRUCTION | 2.41 | 2.39 | 100
859 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HARIRAMPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000890/2021-2022 | 273/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.45 | 2.45 | 1
860 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | RTOR000048/2023-2024 | 196/BD-I/4 | 09/02/2024 | 0 | Resource Division | 116.19 | 0 | 0
861 | Berhampore Mechanical | Berhampur Division I | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Harirampur ground water based water supply scheme under Block- BHAGAWANGOLA-II Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/001482/2023-2024 | 761/MEDB | 20/02/2024 | 90 | ASSOCIATED ELECTRICAL CO. | 10.35 | 0 | 0
862 | Murshidabad Division | Berhampur M/E Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sinkaipur (Village code 314775) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte Scheme ID - 0005019112 in the District of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000239/2021-2022 | 1617/MURD | 28/06/2021 | 60 | DAS ENTERPRISE (PROP-DIPAK DAS) | 5.14 | 0 | 0
863 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Augmentation of SURANGAPUR Zone-II (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000501/2022-2023 | 2417/MURD | 22/08/2022 | 922 | M/S GUHA AND ROY | 343.47 | 293.96 | 100
864 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Surangapur Zone - II (PART -A), Salar PWSS Zone-IA, IB, IIA & IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Nowda & Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 570 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 20
865 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution pipe line of 280 mm dia. HDPE pipe line From Node Point J-22 to J-27 ,J-6 to J-822 & J-82 to J-83 and Laying of 150, 250 mm dia ( For casing ) at Surangapur Zone -II PWSS under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000739/2023-2024 | 53/MURD | 05/01/2024 | 30 | M/S GUHA AND ROY | 30.62 | 20.61 | 100
866 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Surangapur Zone-II Water Supply Scheme at HW Site & 2nd TW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000743/2022-2023 | 383/MURD | 10/02/2023 | 45 | MAMATA USHA ENTERPRISE | 23.58 | 20.51 | 100
867 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall at H/O site, land Development & Approach Road in connection with Augmentation of Surangapur Zone - II PWSS under Murshidabad Division , PHE Dte. Length -266 mtr. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000746/2023-2024 | 82/MURD | 09/01/2024 | 60 | BENGAL ENTERPRISE (PROP:-HADIKUL MOLLA) | 29.85 | 0 | 80
868 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (SURANGAPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000841/2021-2022 | 3274/MURD | 05/10/2021 | 60 | RADIANT | 15.07 | 5.02 | 1
869 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000010/2024-2025 | 1811/MURD/09 | 20/06/2024 | 0 | Resource Division | 38.22 | 0 | 0
870 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000099/2022-2023 | 702/MURD | 13/03/2023 | 0 | Resource Division | 48.15 | 0 | 0
871 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000174/2023-2024 | 1180/MURD/17 | 29/04/2023 | 0 | Resource Division | 48.15 | 0 | 0
872 | Berhampore Mechanical | Berhampur Sub-Division | NEW CONNECTION SURANGAPUR Z-II PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01626/2023-2024 | 483/WBSEDCL-JJM | 21/03/2024 | 0 | WBSEDCL | 12.41 | 0 | 0
873 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I, II & III under SURANGAPUR (ZONE- II ),Part-A ground water based water supply scheme under Block_ Nowda Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000042/2023-2024 | 1881/MEDB | 16/06/2023 | 92 | GHOSH BROTHERS | 33.54 | 0 | 40
874 | Berhampore Mechanical | Berhampur Sub-Division | Hiring of Diesel driven Bolero/ Equivalent four wheeler car for the official use of the Executive Engineer under Office of the Executive Engineer, Mechanical/Electrical Division, PHE Dte. In the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000655/2022-2023 | 886/AE-II/MEDB | 12/08/2022 | 121 | M/S SAJAHAN CHOWDHURY | 0.59 | 1.43 | 10
875 | Berhampore Mechanical | Berhampur Sub-Division | Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Assistant Engineer-I under Office of the Executive Engineer, Mechanical/electrical Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000694/2022-2023 | 656/AE/MEDB | 31/03/2023 | 183 | M/S SAJAHAN CHOWDHURY | 0.9 | 2.36 | 10
876 | Murshidabad Division | Kandi Sub-Division | Functional Household Tap Connection (FHTC) under Jal Jeevan Mission in the command area of NABADURGA Water Supply Scheme under Murshidabad Division, P.H.E.Dte. (PART-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000005/2023-2024 | 945/MURD | 05/04/2023 | 667 | M/S. UNIQUE BUILDERS | 152.42 | 0 | 0
877 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System of NABADURGA PWSS in Burwan Block , under Murshidabad Division ,PHE.Dte. .(PART-C) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000044/2023-2024 | 1138/MURD | 26/04/2023 | 706 | DHIRENDRANATH MONDAL | 341.13 | 0 | 60
878 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Nabadurga & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at B u r w a n Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000047/2023-2024 | 1217/MURD | 03/05/2023 | 30 | MAMATA USHA ENTERPRISE | 21.38 | 0 | 60
879 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
880 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Construction of 350 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Boundwary Wall Rising Main Connection, of NABADURGA PWSS in Burwan Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. (PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000849/2022-2023 | 782/MURD | 20/03/2023 | 365 | AMAL KUMAR DAS | 181.67 | 0 | 32
881 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | RTOR000067/2022-2023 | 1278/MURD/16 | 10/05/2023 | 0 | Resource Division | 30.04 | 0 | 0
882 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT NABADURGA PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | BILL/01593/2023-2024 | 432/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 3.72 | 0 | 0
883 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT NABADURGA PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | BILL/01594/2023-2024 | 433/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
884 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under NABADURGA ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000103/2023-2024 | 3851/MEDB | 06/11/2023 | 92 | M/S MANABESH ROY | 23.45 | 0 | 0
885 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos. of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MUNIGARM AND ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at KANDI Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000270/2023-2024 | 2588/MURD | 21/08/2023 | 21 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 80
886 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of MUNIGRAM & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall, IEP and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000715/2022-2023 | 106/MURD | 13/01/2023 | 931 | PRANAB KUMAR GHOSH | 279.43 | 0 | 30
887 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000051/2023-2024 | 1067/MURD/7 | 18/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
888 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000364/2023-2024 | MURD/439/13 | 08/02/2024 | 0 | Resource Division | 6.34 | 0 | 0
889 | Berhampore Mechanical | Kandi Sub-Division | Electric Service Connection at MUNIGRAM, Application NO.3004466957, ID 304171251 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01080/2023-2024 | 194/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 5.16 | 0 | 0
890 | Berhampore Mechanical | Kandi Sub-Division | AT MUNIGRAM PH 2 ID 304252906 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01471/2023-2024 | 362/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 4.88 | 0 | 0
891 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MUNIGRAM ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000171/2023-2024 | 2017/MEDB | 19/06/2023 | 92 | T. S. CONSTRUCTION | 22.22 | 0 | 60
892 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of SINGADDA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte.( Scheme ID -PH222362264S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000712/2022-2023 | 91/MURD | 11/01/2023 | 872 | PASCON | 565.86 | 195.21 | 39
893 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000043/2023-2024 | 1004/MURD/18 | 17/04/2023 | 0 | Resource Division | 24.48 | 0 | 0
894 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION PH 1 SINGADDA PWSS ID 30425678 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01449/2023-2024 | 342/WBSEDCL-JJM | 12/02/2024 | 0 | WBSEDCL | 5.13 | 0 | 0
895 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION PH 2 SINGADDA PWSS ID 304256291 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01450/2023-2024 | 343/WBSEDCL-JJM | 12/02/2024 | 0 | WBSEDCL | 4.78 | 0 | 0
896 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SINGADDA ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000067/2023-2024 | 1897/MEDB | 16/06/2023 | 777 | ABHISEK ENGINEERING CONCERN | 22.61 | 0 | 30
897 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 14.79 | 20
898 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Kazipara zone_II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in JALANGI Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000022/2023-2024 | 96/BD-I | 04/05/2023 | 365 | MS JAKIR HOSSAIN | 291.08 | 189.31 | 70
899 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augmentation of KAZIPARA ZONE-II PWSS of Jalangi Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000059/2024-2025 | 1136/BD-I | 15/07/2024 | 60 | U.S BUILDERS | 7.92 | 0 | 0
900 | Berhampore Division I | Raghunathganj Sub-Division | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KAJIPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000295/2022-2023 | 1777/BD-I | 27/03/2023 | 10 | M/S SOBHA & CO | 2.74 | 2.7 | 100
901 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000039/2023-2024 | 194/BD-I/8 | 09/02/2024 | 0 | Resource Division | 31.41 | 0 | 0
902 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW SERVICE CONNECTION AT KAJIPARA PH1 Z2 ID304244954 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | BILL/01505/2023-2024 | 404/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 5.18 | 0 | 0
903 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW SERVICE CONNECTION AT KAJIPARA PH2 Z2 ID 304244955 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | BILL/01507/2023-2024 | 405/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 6.56 | 0 | 0
904 | Murshidabad Division | Kandi Sub-Division | Laying of Distribution Pipeline and Land Development work at Kandra PWSS of Bharatpur-II Block, Kandi Sub-Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000007/2025-2026 | 889/MURD | 22/04/2025 | 45 | PAL CONSTRUCTION (SUBHAM PAL) | 12.06 | 0 | 0
905 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of KANDARA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte.( Scheme ID -PH222362286S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000695/2022-2023 | 89/MURD | 10/01/2023 | 365 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 649.94 | 80.17 | 18
906 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | RTOR000032/2023-2024 | 1043/MURD/2 | 17/04/2023 | 0 | Resource Division | 38.45 | 0 | 0
907 | Berhampore Mechanical | Kandi Sub-Division | New connection charge for Kandara, PWSS, P/H No.- I. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | BILL/00857/2023-2024 | 119/WBSEDCL-JJM | 27/09/2023 | 0 | WBSEDCL | 4.04 | 0 | 0
908 | Berhampore Mechanical | Kandi Sub-Division | Kandra PH-III Application No- 3004547697 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | BILL/01189/2023-2024 | 249/WBSEDCL-JJM | 16/01/2024 | 0 | WBSEDCL | 3.98 | 0 | 0
909 | Berhampore Mechanical | Kandi Sub-Division | Kandara PH-II Application No- 3004409912 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | BILL/01190/2023-2024 | 250/WBSEDCL-JJM | 16/01/2024 | 0 | WBSEDCL | 7.12 | 0 | 0
910 | Berhampore Mechanical | Kandi Sub-Division | Kandara PH-1 Application no-3004409936 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | BILL/01191/2023-2024 |  | 11/01/2024 | 0 | WBSEDCL | 4.04 | 0 | 0
911 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under KANDARA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000038/2023-2024 | 1877/MEDB | 16/06/2023 | 92 | M/S SAJAHAN CHOWDHURY | 35.2 | 20.53 | 7
912 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
913 | Berhampore Division I | Berhampur Division I | Augmentation of Mashimpur Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000029/2023-2024 | 81/BD-I | 28/04/2023 | 180 | SUJIT KUMAR SAHA | 241.41 | 73.06 | 40
914 | Berhampore Division I | Berhampur Division I | Improvement of Existing AIRP of (Capacity 51 Cum/hr.) with allied works at Mashimpur Water Supply Scheme under Jal Jeevan Mission within Beldanga - II under Berhampore Division-I, P.H.Eengineering Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000079/2025-2026 | 846/BD-I | 23/06/2025 | 30 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 6.4 | 0 | 0
915 | Berhampore Division I | Berhampur Division I | Allied works of Laying of distribution pipeline of MASHIMPUR piped water supply scheme under JJM within Beldanga-II Block in the district of Murshidabad under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000128/2024-2025 | 1478/BD-I | 06/09/2024 | 30 | SANTANU BISWAS | 16.93 | 0 | 0
916 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MASHIMPUR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000233/2022-2023 | 1591/BD-I | 28/02/2023 | 10 | TECHVISION | 2.6 | 2.6 | 0
917 | Berhampore Division I | Berhampur Division I | Proposed balance work for office room at 1st floor over AIRP pump house with staircase at Mashimpur ground water supply scheme under JJM under Berhampore Division-I, P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000442/2023-2024 | 441/BD-I | 15/03/2024 | 30 | CLASSIC CONSTRUCTION | 2.61 | 0 | 0
918 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000088/2023-2024 | 196/BD-I/22 | 09/02/2024 | 0 | Resource Division | 14.87 | 0 | 0
919 | Murshidabad Division | Berhampur M/E Division | Augmentation Work for Construction of 900 Cum OHR, Laing of Rising Main, Laing Distribution System, Construction of 3 Nos Pump House & Construction of Boundary Wall of Kankuria Jafrabad (Zone-II) PWSS under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000340/2023-2024 | 2697/MURD | 25/08/2023 | 365 | SAMIRAN KUMAR CHAKRABORTY | 446.57 | 0 | 0
920 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED PIPED WATER SYPPLY SCHEME FOR KANKURIA JAFRABAD ZONE-II BLOCK SAMSERGANJ DIST - MURSHIDABAD. . under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000562/2024-2025 | 344/MEDB | 10/02/2025 | 89 | MONI ELECTRICAL WORKS | 37.01 | 0 | 0
921 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for PRASADPUR ZONE-I Ground Based Water Supply Scheme in Suti-II Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000022/2025-2026 | 983/MURD | 02/05/2025 | 60 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 19.61 | 0 | 0
922 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.86 | 100
923 | Murshidabad Division | Berhampur M/E Division | Allied work for Laying of UPVC pipeline, Construction of Culvert and Approach road for PROSADPUR (ZONE-I) Piped Water Supply Scheme in Suti-II Block of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000194/2024-2025 | 3213/MURD | 09/12/2024 | 30 | M/S. S.S. ENTERPRISE( PROP: SANDIP SAHA) | 36.51 | 0 | 0
924 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 225/3 & 225/4) at Khanpur mouza & Connecting with existing 110 mm dia UPVC distribution main line of Prosadpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000425/2021-2022 | 2482/MURD | 16/08/2021 | 60 | DECON INDIA | 20.38 | 15.68 | 100
925 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System (Part-A) & FHTC work at Khanpur, Bhairabpur, Khidirpur, Parulia village of PROSADPUR (ZONE-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000731/2023-2024 | 18/MURD | 03/01/2024 | 729 | BISWAS ENTERPRISE (PROP. SAMIUL ISLAM)) | 84.13 | 26.59 | 41
926 | Murshidabad Division | Berhampur M/E Division | Providing FHTC to 1034 no household, Laying Distribution System, Vertical extension of Boundary wall and repairing Pump House and Overhauling of R.C.C. elevated reservoir 350 Cum capacity of staging height 20 mtr. (Shaft wall) for Augmentation work of Prosadpur (Zone-I) PWSS under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000886/2022-2023 | 905/MURD | 29/03/2023 | 887 | M/S. S.S. ENTERPRISE( PROP: SANDIP SAHA) | 139.2 | 18.09 | 50
927 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000202/2023-2024 | 1210/MURD/28 | 02/05/2023 | 0 | Resource Division | 1.51 | 0 | 0
928 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under PRASADPUR ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000081/2023-2024 | 1931/MEDB | 16/06/2023 | 92 | WEST BENGAL ENGINEERING CO. | 20.82 | 16.6 | 15
929 | Murshidabad Division | Berhampur M/E Division | Renovation of Filter media of Existing AIRP (Capacity 135 Cum/hr.) of Putia (Zone-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000033/2024-2025 | 1892/MURD | 01/07/2024 | 60 | M/S BAPPA ENTERPRISE | 47.01 | 0 | 0
930 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PUTIA ZONE - I Water Supply Scheme at Head Work Site, 2nd Site, 3 r d , 4th site at RAGHUNATHGANJ - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000115/2023-2024 | 1759/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 25.42 | 80
931 | Murshidabad Division | Berhampur M/E Division | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month from 01/03/2025 to 31/08/2025] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000513/2024-2025 | 66/JSD | 25/02/2025 | 181 | ABHIJIT MAITRA | 0.88 | 0 | 0
932 | Murshidabad Division | Berhampur M/E Division | Construction of approach road from pucca road to Head Work site of Putia Water Supply Scheme of Jangipur Sub-Division under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000656/2022-2023 | 3375/MURD | 20/12/2022 | 940 | JAMIRUL CONSTRUCTION | 4.62 | 0 | 50
933 | Murshidabad Division | Berhampur M/E Division | Repairing of 550Cum OHR and FHTC for Augmentation of PUTIA (ZONE-I) ground water based piped water supply scheme within Raghunathganj-II Block under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000779/2022-2023 | 507/MURD | 22/02/2023 | 60 | CLASSIC CONSTRUCTION (ANJAN CHATTERJEE) | 60.86 | 0 | 50
934 | Murshidabad Division | Berhampur M/E Division | Formal work order for the construction of Pump House, Vertical extension of Boundary wall and Pump House repairing , Laying Distribution System, Rising Main Connection for Augmentation of PUTIA ( ZONE-I ) Ground water based Piped water supply scheme Raghunathganj -II Block under Murshidabad Division, P.H.E. Dte. [ (i)Amount for LDS, R.Main : Rs. 1,47,25,982.00 & (ii) Amount for Vertical B.Wall Extention & P.House Repairing : Rs. 13,13,446.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000810/2022-2023 | 810/MURD | 22/03/2023 | 710 | JAYANTA KUMAR CHANDRA | 160.12 | 87.97 | 50
935 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 7.92 | 100
936 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000076/2022-2023 | 1278/MURD/19 | 10/05/2023 | 0 | Resource Division | 34.76 | 0 | 0
937 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000557/2024-2025 | 339/MEDB | 10/02/2025 | 323 | M/S S. S. ENTERPRISE (DOMKAL) | 22.79 | 0 | 60
938 | Central Drilling | Raghunathganj Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
939 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 14.93 | 20
940 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Boundary Wall With Main Entrance gate and barbed wire facing ,Service Road for approach and Pump House at Augmentation of Komnagar PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. (2nd Site)/New OHR Site | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000053/2024-2025 | 1119/BD-I | 11/07/2024 | 335 | MODERN CONSTRUCTION (DOMKAL) | 25.76 | 0 | 75
941 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Komnagar Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000122/2023-2024 | 506/BD-I | 24/07/2023 | 647 | PRATICHI ENTERPRISE | 194.85 | 96.48 | 83
942 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KOMNAGAR Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000279/2022-2023 | 1763/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.53 | 2.49 | 100
943 | Berhampore Division I | Raghunathganj Sub-Division | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Komnagar ground water supply scheme in Raninagar-II Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000288/2024-2025 | 56/BD-I | 14/01/2025 | 300 | SUMAN ENTERPRISE AND SUMAN AQUA | 122.79 | 0 | 0
944 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000009/2023-2024 | 61/BD-1/8 | 27/04/2023 | 0 | Resource Division | 29.2 | 0 | 0
945 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW SERVICE CONNECTION AT KOMNAGAR PH 1 ID 304268985 | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | BILL/01130/2024-2025 |  | 26/11/2024 | 0 | WBSEDCL | 3.49 | 0 | 0
946 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Komnagar ground water supply scheme in Raninagar-II Block Dist_Murshidabad under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000009/2025-2026 | 1133/MEDB | 13/05/2025 | 92 | M/S K.P. PRAMANIK | 39.98 | 0 | 0
947 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dhulauri Water Supply Scheme and Tejsinghapur Water Supply Schem under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000104/2023-2024 | 1746/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 100
948 | Murshidabad Division | Berhampur M/E Division | Formal work order for the Work of Augmentation of Dhulauri Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000703/2022-2023 | 350/MURD | 08/02/2023 | 180 | M/S. S. DAS AND ENTERPRISE | 419.15 | 266.85 | 48
949 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 6.91 | 1
950 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000304/2023-2024 | 1278/MURD/13 | 10/05/2023 | 0 | Resource Division | 34.6 | 0 | 0
951 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under DHULAURI ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000688/2023-2024 | 4295/MEDB | 29/12/2023 | 91 | SUBHRA ENTERPRISE | 22.13 | 0 | 0
952 | Berhampore Division I | Berhampur M/E Division | Formal work order for Augmentation of Bansgara Zone-III Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP), pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000117/2023-2024 | 463/BD-I | 17/07/2023 | 899 | SAMBHUNATH ROY | 291.11 | 0 | 15
953 | Berhampore Division I | Berhampur M/E Division | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000297/2022-2023 | 1742/BD-I | 22/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.55 | 0 | 95
954 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000082/2023-2024 | 201/BD-1/23 | 10/02/2024 | 0 | Resource Division | 66.74 | 0 | 0
955 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I and II ,Zone-III under Bansgara ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000147/2023-2024 | 632/MEDB | 02/02/2024 | 90 | M/S K.P. PRAMANIK | 22.17 | 0 | 0
956 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 28.15 | 11
957 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of ANDULBERIA ZONE-II" ground water supply scheme in BELDANGA-II Block under Berhampore Division-I, P.H.E Dte(Capacity-72.00 Cum/hr.) Type-1: Fully Gravity System with RG Filter | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000031/2024-2025 | 994/BD-I | 20/06/2024 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 197.4 | 0 | 0
958 | Berhampore Division I | Berhampur Division I | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of ANDULBERIA ZONE-II PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000042/2025-2026 | 724/BD-I | 15/05/2025 | 60 | M/S. MONDAL ENTERPRISE | 19 | 0 | 0
959 | Berhampore Division I | Berhampur Division I | Augmentation of Andulberia Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000211/2022-2023 | 1821/BD-I | 31/03/2023 | 1007 | KAMIRUL SK AND CO. | 399.58 | 91.27 | 70
960 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for ANDULBERIA Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000235/2022-2023 | 1593/BD-I | 28/02/2023 | 10 | TECHVISION | 3.15 | 2.92 | 0
961 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ANDULBERIA ZONE - II Water Supply Scheme(3rd TW Site) within Beldanga - II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000297/2024-2025 | 103/BD-I | 20/01/2025 | 15 | HARUN ALL RASHID & BROTHERS | 8.95 | 0 | 0
962 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000090/2023-2024 | 196/BD-I/24 | 09/02/2024 | 0 | Resource Division | 46.35 | 0 | 0
963 | Murshidabad Division | Kandi Sub-Division | Allied work for Construction of Pump House at Head Works Site &2nd T.W. Site,FHTC, Boundary Wall,Rising Main Connection, Laying Distribution System for Bathur PWSS in Khargram Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000038/2024-2025 | 1929/MURD | 03/07/2024 | 272 | NOVELTY CONSTRUCTION | 43.95 | 0 | 10
964 | Murshidabad Division | Kandi Sub-Division | Formal work order for construction of Pump House at Head Work Site & 2nd Tube well site ,FHTC, Boundwary Wall, Rising Main Connection, Laying Distribution System for BATHUR PWSS in Khargram Block under Murshidabad Division ,PHE.Dte [ (i)Amount for LDS , R. Main, FHTC : Rs. 73,83,365.00 &(ii) Amount for Pump House, B.Wall : Rs. 35,86,277.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000793/2022-2023 | 593/MURD | 01/03/2023 | 615 | NOVELTY CONSTRUCTION | 109.53 | 77.93 | 37
965 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000333/2023-2024 | 79 | 09/01/2024 | 0 | Resource Division | 3.37 | 0 | 0
966 | Berhampore Mechanical | Kandi Sub-Division | Service connection charge for Bathur PH-I, Appl. no.3004523927. ID- 304212545. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01094/2023-2024 | 201/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 2.66 | 0 | 0
967 | Berhampore Mechanical | Kandi Sub-Division | Service connection charge for Bathur PH-II, Appl. no.3004523910. ID- 304212540. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01095/2023-2024 | 202/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 3.43 | 0 | 0
968 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BATHUR ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000135/2023-2024 | 1923/MEDB | 16/06/2023 | 92 | JOY BISHNU ENGINEERING CO. | 21.42 | 13.32 | 20
969 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Bansgara Zone-II Piped water supply scheme to accommodate construction of Arsenic cum Iron Removal Plant(AIRP), pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer-II | ORD/000025/2023-2024 | 313/BD-I | 14/06/2023 | 892 | MODERN CONSTRUCTION | 261.29 | 48.48 | 70
970 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road, Improvement of RCC OHR and Pump House of Bansgara Zone-II PWSS under Jal Jeevan Mission within Raninagar-II block under Berhampore Division-I PHE Dte. in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer-II | ORD/000097/2025-2026 | 1014/BD-I | 06/08/2025 | 45 | GOUTAM MANDAL | 32.21 | 0 | 0
971 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA ZONE-II Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer-II | ORD/000277/2022-2023 | 1760/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.46 | 2.46 | 100
972 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer-II | RTOR000038/2023-2024 | 194/BD-I/7 | 09/02/2024 | 0 | Resource Division | 32.78 | 0 | 0
973 | Berhampore Mechanical | Raghunathganj Sub-Division | load enhancement bansgara z2 ph 1 | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer-II | BILL/01597/2023-2024 |  | 05/03/2024 | 0 | WBSEDCL | 1.8 | 0 | 0
974 | Berhampore Mechanical | Raghunathganj Sub-Division | LOAD ENHANCEMENT AT BANSGARA Z2 PH1 ID 312397840 | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer-II | BILL/01637/2023-2024 | 481/WBSEDCL-JJM | 21/03/2024 | 0 | WBSEDCL | 1.8 | 0 | 0
975 | Berhampore Mechanical | Raghunathganj Sub-Division | LOAD ENHANCEMENT BANSGARA AIRP ID 3004571720 | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer-II | BILL/01638/2023-2024 | 482/WBSEDCL-JJM | 21/03/2024 | 0 | WBSEDCL | 1.11 | 0 | 0
976 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Raninagar-II under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer-II | ORD/000538/2024-2025 | 324/MEDB | 10/02/2025 | 324 | JOGMAYA ENGINEERING | 24.94 | 0 | 25
977 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia Replacement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AMJUA PWSS at Head Work Site & 2nd Tube Well Site in Khargram Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000657/2022-2023 | 380/MURD | 10/02/2023 | 45 | SUJIT KUMAR SAHA | 16.81 | 14.08 | 100
978 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution System (PART-C), FHTC (PART-C), for Uncovered of AMJUA PWSS at AMJUA ( Village Code-315107) , CHURIGRAM ( Village Code-315108) , DURGARAMPUR ( Village Code-315109) in Khargram Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000730/2022-2023 | 339/MURD | 08/02/2023 | 90 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 146.33 | 77.64 | 34
979 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of 400 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, FHTC (PART-A), for Uncovered of AMJUA PWSS at RAHIGRAM Village in Khargram Block, Kandi Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000748/2022-2023 | 414/MURD | 15/02/2023 | 1141 | M/S.TAPAS KUMAR CHAKRABORTY | 306.3 | 68.67 | 10
980 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution System (PART-B), FHTC (PART-B), Boundary wall for Uncovered of AMJUA PWSS at UTTAR GANGARAMPUR ( Village Code-315100) , SADAL ( Village Code-315101) , BHAT KANDA ( Village Code-315102) in Khargram Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. [(i)Amount for LDS & FHTC: Rs.2,54,73,199.00 & (ii) Amount for Boundwary Wall: Rs. 31,33,915.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000759/2022-2023 | 453/MURD | 17/02/2023 | 960 | PRADIP KUMAR DAS | 285.93 | 31.09 | 5
981 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
982 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000018/2023-2024 | 1210/MURD/35 | 02/05/2023 | 0 | Resource Division | 21.05 | 0 | 0
983 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT AMJUA PH1 ID 304158525 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01129/2023-2024 | 220/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 8.29 | 0 | 0
984 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under AMJUA ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000078/2023-2024 | 3787/MEDB | 03/11/2023 | 1686 | KASHINATH PAL & CO. | 24.35 | 0 | 40
985 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution system (PART-A) at SADPUR PWSS of Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000744/2022-2023 | 382/MURD | 10/02/2023 | 811 | S.K. ENTERPRISE (SANDIP GHOSH) | 136.23 | 108.09 | 85
986 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of SADPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362342S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,30,41,399.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,56,32,356.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000761/2022-2023 | 475/MURD | 20/02/2023 | 771 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 286.71 | 16.26 | 21
987 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SADPUR PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000786/2022-2023 | 542/MURD | 24/02/2023 | 45 | INDRAJIT MAZUMDAR | 16.8 | 0 | 80
988 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000015/2023-2024 | 1210/MURD/38 | 02/05/2023 | 0 | Resource Division | 29.54 | 0 | 0
989 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000345/2023-2024 | 112/MURD/02 | 11/01/2024 | 0 | Resource Division | 11.89 | 0 | 0
990 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000367/2023-2024 | MURD/439/11 | 08/02/2024 | 0 | Resource Division | 5.94 | 0 | 0
991 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PH 1 SADPUR ID 304252899 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01465/2023-2024 | 360/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
992 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of SADPUR ground water based water supply scheme under Block- Kandi Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000102/2023-2024 | 3790/MEDB | 03/11/2023 | 668 | S. P. CONSTRUCTION | 20.89 | 0 | 40
993 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augmentation of Hurshi New PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000048/2024-2025 | 1110/BD-I | 10/07/2024 | 60 | PRADIP DAS | 8.04 | 0 | 0
994 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Hurshi Zone-I Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant( AIRP), pump house and boundary wall , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000196/2023-2024 | 844/BD-I | 05/09/2023 | 620 | M/S B.M. INDUSTRIES | 423.99 | 155.31 | 70
995 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HURSHI ZONE-I Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000268/2022-2023 | 1691/BD-I | 14/03/2023 | 10 | RADIANT | 2.6 | 2.6 | 100
996 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000004/2023-2024 | 61/BD-1/5 | 27/04/2023 | 0 | Resource Division | 49.26 | 0 | 0
997 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW SERVICE CONNECTION AT HURSHI z1 ph2 id 304247241 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | BILL/01128/2024-2025 |  | 26/11/2024 | 0 | WBSEDCL | 9.34 | 0 | 0
998 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW CONNECTION HURSHI Z-1 PH-I | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | BILL/01632/2023-2024 | 469/WBSEDCL-JJM | 19/03/2024 | 0 | WBSEDCL | 7.8 | 0 | 0
999 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , Zone-I under Hurshi ground water based water supply scheme under Block_ Raninagar-I Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000673/2023-2024 | 4297/MEDB | 29/12/2023 | 91 | SREE RADHA ELECTRICAL | 34.27 | 0 | 80
1000 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of KUMAR SANDA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362351S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000713/2022-2023 | 92/MURD | 11/01/2023 | 1086 | ACQUA CONSTRACTION CONSORTIAM | 678.7 | 0 | 20
1001 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000034/2023-2024 | 1043/MURD/9 | 17/04/2023 | 0 | Resource Division | 32.79 | 0 | 0
1002 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II and III under KUMAR SANDA ground water based water supply scheme under Block_ KANDI Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000151/2023-2024 | 2082/MEDB | 19/06/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 36.82 | 0 | 0
1003 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 250mm x 150 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHAYRAMARI Part-A and Salar Zone - IIB Water Supply Scheme as required under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000103/2023-2024 | 1744/MURD | 06/07/2023 | 14 | SARKAR WATER SUPPLY AGENCY | 9.22 | 0 | 100
1004 | Murshidabad Division | Berhampur M/E Division | Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.02.2024 to 30.05.2024) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000788/2023-2024 | 17/KSD | 16/01/2024 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 70
1005 | Murshidabad Division | Berhampur M/E Division | Formal work order for the Work of Augmentation of KHAYRAMARI PART-A Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000809/2022-2023 | 657/MURD | 06/03/2023 | 843 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 466.36 | 285.91 | 95
1006 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000032/2024-2025 | MURD/2481/04 | 04/09/2024 | 0 | Resource Division | 5.07 | 0 | 0
1007 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000178/2023-2024 | 1180/MURD/18 | 29/04/2023 | 0 | Resource Division | 179.05 | 0 | 0
1008 | Berhampore Mechanical | Berhampur M/E Division | New connection charge for Khairamari W/S Scheme (Part-A), P/H No.-II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | BILL/00276/2023-2024 | 95/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 0.7 | 0 | 0
1009 | Berhampore Mechanical | Berhampur M/E Division | ADDL SERVICE CONNECTION CHARGES KHAIRAMARI PWSS PART A PH 2,ID860281602 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01110/2023-2024 | 207/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 3.24 | 0 | 0
1010 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,Part-A under Khayramari ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000653/2023-2024 | 3687/MEDB | 03/11/2023 | 92 | SUBHRA ENTERPRISE | 11.18 | 0 | 70
1011 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of PETARI & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362276S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000717/2022-2023 | 79/MURD | 10/01/2023 | 1087 | MAMATA USHA ENTERPRISE | 754.5 | 419.23 | 60
1012 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000041/2023-2024 | 1004/MURD/16 | 17/04/2023 | 0 | Resource Division | 23.72 | 0 | 0
1013 | Berhampore Mechanical | Kandi Sub-Division | Electric Service New Connection PETARI PH- 2 PWSS Application NO. 3004404553. ID. 304120628 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01034/2023-2024 | 169/WBSEDCL-JJM | 05/12/2023 | 0 | WBSEDCL | 3.13 | 0 | 0
1014 | Berhampore Mechanical | Kandi Sub-Division | Electric Service New Connection PETARI PH-1 PWSS Application NO. 3004494692. ID. 304193611 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01035/2023-2024 | 170/WBSEDCL-JJM | 05/12/2023 | 0 | WBSEDCL | 6.35 | 0 | 0
1015 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under PETARI ground water based water supply scheme under Block_ BURWAN, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000157/2023-2024 | 2085/MEDB | 19/06/2023 | 926 | JOGMAYA ENGINEERING | 23.47 | 19.34 | 20
1016 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for KUSUMGACHI Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000023/2025-2026 | 982/MURD | 02/05/2025 | 60 | M/S SAJAHAN CHOWDHURY | 22.96 | 0 | 0
1017 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 10
1018 | Murshidabad Division | Berhampur M/E Division | Providing FHTC Connection to 800 nos household, Laying of Rising Main, Laying of Distribution System, Overhauling of RCC 180 Cum OHR, Construction Pump House with sanitary and Water Supply Arrangement (T/W-I), Special repair and renovation of existing 1 (One) Nos Pump House and Alied Works, Construction of Boundary Wall, Repair of Boundary Wall & Construction of RCC approach road for Augmentation of KUSUMGACHI Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000880/2022-2023 | 904/MURD | 29/03/2023 | 881 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 174.93 | 0 | 50
1019 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000199/2023-2024 | 1210/MURD/05 | 02/05/2023 | 0 | Resource Division | 50.19 | 0 | 0
1020 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1021 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Halalpur Zone-IV under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000070/2023-2024 | 172/BD-I | 16/05/2023 | 90 | JALALUDDIN SHAH | 22.51 | 0 | 0
1022 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Halalpur Zone-IV village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000216/2023-2024 | 3076/MEDB | 02/08/2023 | 92 | SURAKSHA | 6.3 | 0 | 0
1023 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Narayanpur under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000074/2023-2024 | 175/BD-I | 16/05/2023 | 90 | SANTANU BISWAS | 28.53 | 0 | 0
1024 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Narayanpur village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000176/2023-2024 | 3037/MEDB | 02/08/2023 | 92 | SREE RADHA ELECTRICAL | 6.32 | 0 | 0
1025 | Murshidabad Division | Berhampur M/E Division | Ground Water based piped water supply scheme for Sehalai Part- A village, Block:- Bharatpur- I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000238/2023-2024 | 2418/MURD | 08/08/2023 | 744 | M/S RELIABLE | 30.55 | 0 | 64
1026 | Murshidabad Division | Berhampur M/E Division | Ground Water based piped water supply scheme for Sehalai Part- B village, Block:- Bharatpur- I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000253/2023-2024 | 2491/MURD | 11/08/2023 | 60 | M/S. GHOSH ENTERPRISE RAJ GHOSH | 30.54 | 0 | 0
1027 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sehalai Part-A village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000210/2023-2024 | 3070/MEDB | 02/08/2023 | 92 | T. N. BANERJEE | 6.15 | 0 | 0
1028 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sehalai Part-B village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000211/2023-2024 | 3071/MEDB | 02/08/2023 | 92 | GANGULI ELECTRICAL CO. | 6.3 | 0 | 0
1029 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.87 | 100
1030 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SERPUR (CT) Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000614/2023-2024 | 3386/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 7.79 | 45
1031 | Murshidabad Division | Berhampur M/E Division | Formal work order for SERPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission, Block- SAMSERGANJ of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000794/2022-2023 | 594/MURD | 01/03/2023 | 671 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 446.76 | 38.46 | 15
1032 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000277/2023-2024 | 1230/MURD/21 | 04/05/2023 | 0 | Resource Division | 25.58 | 0 | 0
1033 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000384/2023-2024 | 495/MURD/12 | 15/02/2024 | 0 | Resource Division | 13.47 | 0 | 0
1034 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT SERPUR PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/00419/2024-2025 | 139/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 3.44 | 0 | 0
1035 | Berhampore Mechanical | Berhampur M/E Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I II & III under SERPUR(CT) ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/001479/2023-2024 | 759/MEDB | 20/02/2024 | 90 | M/S SAJAHAN CHOWDHURY | 32.53 | 0 | 0
1036 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 10
1037 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JADABPUR NIMTALA and KANKURIA JAFRABAD ZONE- I Water Supply Scheme as required at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000705/2023-2024 | 3813/MURD | 12/12/2023 | 21 | HARUN ALL RASHID & BROTHERS | 11.77 | 0 | 100
1038 | Murshidabad Division | Berhampur M/E Division | Providing FHTC Connection to 268 nos household, Laying of Rising Main, Laying of Distribution System, overhauling of RCC 45 Cum OHR, Construction of Boundary Wall (For T/W-I) =100mtr, Special repair and renovation of existing 1 (One) Nos Pump House and Allied Works and Construction of RCC approach road =140 mtr for Augmentation of Jadabpur Nimtala Piped Water Supply Scheme in Farakka Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000819/2023-2024 | 740/MURD | 12/03/2024 | 60 | PAL CONSTRUCTION | 57.61 | 15.11 | 50
1039 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000194/2023-2024 | 1210/MURD/08 | 02/05/2023 | 0 | Resource Division | 9.5 | 0 | 0
1040 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000553/2024-2025 | 335/MEDB | 10/02/2025 | 89 | QUAZI NOZRUL ISLAM (PARTNERSHIP) | 21.52 | 0 | 0
1041 | Murshidabad Division | Berhampur Sub-Division | Construction 2 (Two ) Nos Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement and 210 mtr Boundary wall at Head Work site and 55Mtr at 2nd site of Sarbangapur Zone -IB , Bara Satui & Chandkati Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000044/2024-2025 | 1930/MURD | 03/07/2024 | 477 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 52.14 | 0 | 75
1042 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for CHANDKATHI Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000044/2025-2026 | 1189/MURD | 23/05/2025 | 60 | PRADIP KUMAR DAS | 23.01 | 0 | 0
1043 | Murshidabad Division | Berhampur Sub-Division | Repair and renovation work of Boundary wall and allied work at Head Work site of Chandkathi Water Supply Scheme under Berhampore Sub Division, P.H.E.Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000192/2022-2023 | 201/BSD | 28/04/2022 | 30 | LATIFUDDIN | 4.78 | 4.16 | 1
1044 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0
1045 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandkati (Village code 315533) under Chandkati Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723218 in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000410/2020-2021 | 79/MURD | 08/01/2021 | 60 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 12.25 | 7.97 | 90
1046 | Murshidabad Division | Berhampur Sub-Division | Construction of 200 Cum OHR, Laying of Distribution System (part_A) at NODE 1 TO NODE 197, Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 168 Cum capacity of staging height 20 mtr. for Augmentation work of CHANDKATI PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. (part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000877/2022-2023 | 897/MURD | 29/03/2023 | 887 | M/S SUBHA CONSTRUCTION | 193.26 | 79.95 | 70
1047 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 986 nos household , Laying of Distribution System (Part_B) NODE 198 TO NODE 385, Repairing & Vertical Extention of Boundary Wall, Special repair and renovation of existing 1 (One) Nos Pump House and Alied Works for for Augmentation work of CHANDKATI PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. (part_B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000885/2022-2023 | 907/MURD | 29/03/2023 | 180 | DAS TRADING CO. | 136.61 | 127.44 | 90
1048 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 4.99 | 1
1049 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-III & IV under CHANDKATI ground water based water supply scheme under Block_ NAWDA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000049/2023-2024 | 1894/MEDB | 16/06/2023 | 92 | S. G. TECHNICAL SERTIVCE | 22.25 | 0 | 0
1050 | Berhampore Mechanical | Berhampur Sub-Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under CHANDKATI ground water based water supply scheme under Block_ NAWDA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000669/2023-2024 | 4293/MEDB | 29/12/2023 | 91 | DAS ENTERPRISE ( MANGO LANE) | 22.21 | 0 | 0
1051 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sonar Diar Zone-I under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000071/2023-2024 | 173/BD-I | 16/05/2023 | 90 | MAA DURGA ENTERPRISE | 30.5 | 0 | 0
1052 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sonadiar Zone-I village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000187/2023-2024 | 3048/MEDB | 02/08/2023 | 92 | HARA PROSAD DAS | 6.27 | 0 | 0
1053 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 6.62 | 1
1054 | Murshidabad Division | Berhampur M/E Division | Renovation of Modified Sujapur Sadhipur Model of AIRP (Capacity 123 Cum/hr.) at Mahadebnagar Zone I Water Supply Scheme of Farakka Block Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000248/2024-2025 | 226/MURD | 27/01/2025 | 45 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 77.24 | 0 | 0
1055 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
1056 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, FHTC, construction of OHR (Capacity 300 & 400 cum), Sinking of Tube Well , and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of MAHADEBNAGAR ZONE- IA,IB,IC ,IIA & IIB PWSS in Farakka Block, Murshidabad District under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000790/2023-2024 | 441/MURD | 08/02/2024 | 693 | MACKINTOSH BURN LIMITED | 1715.31 | 0 | 36
1057 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IC under Mahadebnagar ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000234/2023-2024 | 3671/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 22.92 | 0 | 50
1058 | Murshidabad Division | Berhampur M/E Division | Augmentation of KUPILA PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000077/2023-2024 | 1380/MURD | 22/05/2023 | 1044 | S.S. ENTERPRISE | 413.75 | 168.98 | 30
1059 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tubewell i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at P.T RASULPUR (PART - A), Kupila and Baniakhali Water Supply Scheme at DOMKAL Block under Murshidabad Division,P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000107/2023-2024 | 1749/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 10.27 | 40
1060 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Juginda, Kupila and Narsinghpur Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000109/2022-2023 | 1193/MURD | 10/05/2022 | 1360 | MAMATA USHA ENTERPRISE | 32.62 | 0 | 20
1061 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000346/2022-2023 | 1925/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 9.6 | 0 | 100
1062 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KUPILA Water Supply Scheme and Herampur Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000695/2023-2024 | 3768/MURD | 08/12/2023 | 21 | MAMATA USHA ENTERPRISE | 11.79 | 0 | 100
1063 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000149/2023-2024 | 1167/MURD/38 | 28/04/2023 | 0 | Resource Division | 5.48 | 0 | 0
1064 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000395/2023-2024 | 526/MURD/08 | 19/02/2024 | 0 | Resource Division | 2.46 | 0 | 0
1065 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION KUPILA PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01610/2023-2024 | 438/WBSEDCL-JJM | 13/03/2024 | 0 | WBSEDCL | 6 | 0 | 0
1066 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under Kupila ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000655/2023-2024 | 3689/MEDB | 03/11/2023 | 1246 | EASTERN INDIA SALES & SERVICE | 22.33 | 15.74 | 10
1067 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Durgapur zone-I under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000051/2023-2024 | 148/BD-I | 15/05/2023 | 90 | KAUSHIK MAJUMDAR | 30.23 | 0 | 0
1068 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Durgapur Zone-I village, Block:- Lalgola under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000682/2023-2024 | 3791/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0
1069 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
1070 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 14.72 | 20
1071 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of Maia Zone - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000012/2025-2026 | 599/BD-I | 22/04/2025 | 60 | SUJAUDDIN SHAIKH | 18.99 | 0 | 0
1072 | Berhampore Division I | Berhampur M/E Division | Augmentation of Maia Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000127/2023-2024 | 540/BD-I | 28/07/2023 | 608 | MD SAJAHAN ALI | 364.59 | 61.42 | 35
1073 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of Maia Zone-II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000379/2024-2025 | 441/BD-I | 20/03/2025 | 60 | SHIBAM ENTERPRISE | 19 | 0 | 0
1074 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000019/2024-2025 | 1510/BD-I/13 | 12/09/2024 | 0 | Resource Division | 7.2 | 0 | 0
1075 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000078/2023-2024 | 201/BD-1/19 | 10/02/2024 | 0 | Resource Division | 23.75 | 0 | 0
1076 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION MAIYA PH-1 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/01512/2023-2024 | 396/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 9.31 | 0 | 0
1077 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 2.58 | 100
1078 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 870 nos household , Laying of Distribution System, Rising Main for Augmentation work of Rejinagar Zone-II PWSS within Beldanga-II Block under Murshidabad Division , PHE.Dte. ( PART - A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000582/2023-2024 | 3317/MURD | 22/10/2023 | 528 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 195.25 | 0 | 85
1079 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Rejinagar Zone II PWSS of accommodate with Switch Room, Boundary Wall, 300 CUM OHR in Beldanga II Block within Murshidabad District under Murshidabad Division, PHE Dte. [ Part B ] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000583/2023-2024 | 3318/MURD | 22/10/2023 | 544 | MODERN CONSTRUCTION | 163.25 | 0 | 0
1080 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000021/2024-2025 | 1811/MURD/20 | 20/06/2024 | 0 | Resource Division | 5.36 | 0 | 0
1081 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000137/2023-2024 | 1167/MURD/42 | 28/04/2023 | 0 | Resource Division | 34.04 | 0 | 0
1082 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-II under Rejinagar ground water based water supply scheme under Block_ Beldanga_II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000237/2023-2024 | 3673/MEDB | 03/11/2023 | 92 | MASSK ENGINEERING WORKS | 22.62 | 0 | 0
1083 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Laying Distribution System of DHANDANGA PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Murshidabad Circle ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000835/2022-2023 | 741/MURD | 16/03/2023 | 747 | APORUPA CONSTRUCTION | 180.78 | 0 | 10
1084 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | RTOR000073/2023-2024 | 1075/MURD/15 | 19/04/2023 | 0 | Resource Division | 14.18 | 0 | 0
1085 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT DHANDANGA PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | BILL/00233/2024-2025 | 65/WBSEDCL-JJM | 09/05/2024 | 0 | WBSEDCL | 4.09 | 0 | 0
1086 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Dhandanga ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000268/2023-2024 | 3705/MEDB | 03/11/2023 | 92 | QUAZI NOZRUL ISLAM | 22.44 | 0 | 0
1087 | Murshidabad Division | Kandi Sub-Division | BERBARI & UJUNIA adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block-BHARATPUR-I & II of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000873/2022-2023 | 882/MURD | 28/03/2023 | 280 | BANAMALI ENTERPRISES | 224.42 | 0 | 35
1088 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | RTOR000272/2023-2024 | 1230/MURD/15 | 04/05/2023 | 0 | Resource Division | 1.09 | 0 | 0
1089 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Ujunia Sisua ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000276/2023-2024 | 3717/MEDB | 03/11/2023 | 92 | SUNIL RABIDAS | 22.54 | 13.98 | 10
1090 | Murshidabad Division | Kandi Sub-Division | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 181 Days] w. e. f 01/10/2025 to 30/03/2026. Vehicle No [WB58CA/1034] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000178/2025-2026 | 199/MSD | 25/09/2025 | 181 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.89 | 0 | 0
1091 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
1092 | Murshidabad Division | Kandi Sub-Division | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 181 Days] w.e.f 02/04/2025 to 30/09/2025. Vehicle No [WB58CA/1034] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000515/2024-2025 | 607/MSD | 28/03/2025 | 181 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.89 | 0 | 0
1093 | Murshidabad Division | Kandi Sub-Division | Augmentation of BHARATPUR (ZONE - II B) PWSS under Jal Jeevan Mission of Bharatpur-I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000759/2023-2024 | 184/MURD | 18/01/2024 | 714 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 415.23 | 0 | 43
1094 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1095 | Murshidabad Division | Kandi Sub-Division | Allied works for laying pipeline and construction of approach road for Fatepur Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000063/2024-2025 | 1978/MURD | 08/07/2024 | 542 | ABIDA CONSTRUCTION | 19.77 | 0 | 70
1096 | Murshidabad Division | Kandi Sub-Division | FATEPUR PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000141/2023-2024 | 1867/MURD | 14/07/2023 | 968 | ABIDA CONSTRUCTION | 124.31 | 0 | 65
1097 | Murshidabad Division | Kandi Sub-Division | Laying and distribution of UPVC pipeline for Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of FATEPUR ( Village Code _315310) under Fatepur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000185/2022-2023 | 192/BSD | 28/04/2022 | 30 | SURAJIT MONDAL | 4.77 | 4.65 | 100
1098 | Murshidabad Division | Kandi Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Satitara T.W- IV,V,VI, Fatepur T.W.-II, Kapasdanga T.W-II Water Supply Scheme of Burwan Block under Kandi Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000500/2024-2025 | 664/MURD | 19/03/2025 | 65 | NADIA TUBEWELLS | 70.43 | 0 | 0
1099 | Murshidabad Division | Kandi Sub-Division | Repair and renovation work of Switch room and Boundary wall at Head Work and 2nd TW site of Fatepur Water Supply Scheme under Berhampore Sub Division, P.H.E.Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001680/2021-2022 | 17/BSD | 10/01/2022 | 30 | MADAN MOHAN SASMAL | 4.85 | 4.41 | 100
1100 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000318/2023-2024 | 1936/MURD/6 | 19/07/2023 | 0 | Resource Division | 1.09 | 0 | 0
1101 | Central Drilling | Kandi Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000209/2023-2024 | 2203/CDD | 01/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 8.13 | 10
1102 | Berhampore Mechanical | Kandi Sub-Division | POWER CONNECTION AT PWSS FATEPUR PH 1 ID 304248214 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/00183/2024-2025 | 43/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
1103 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme .District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000559/2024-2025 | 341/MEDB | 10/02/2025 | 353 | ASSOCIATED ELECTRICAL CO. | 21.59 | 0 | 85
1104 | Murshidabad Division | Berhampur M/E Division | Continuation work order for Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Assistant Engineer (HQ), Murshidabad Division, P.H.E. Dte. For 06(Six) Months (on and from 01/05/2025 to 31/10/2025) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver, Taxes , Insurance , Fees etc. as applicable Excluding fuel, lubricant etc. as per order) Vehicle No.WB-58BV-8767 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000013/2025-2026 | 946/MURD | 29/04/2025 | 183 | M/S JOY MA BANAMALI | 0.9 | 0 | 20
1105 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.08 | 100
1106 | Murshidabad Division | Berhampur M/E Division | Continuation work order for Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywhere with in any trouble on daily wage basis for official used under the control of the Assistant Engineer (HQ), Murshidabad Division, P.H.E. Dte. For 06(Six) Months (on and from 01/11/2025 to 30/04/2026) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver, Taxes ,Insurance , Fees etc. as applicable Excluding fuel, lubricant etc. as per order) Vehicle No.WB-58BV-8767 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000187/2025-2026 | 2239/MURD | 31/10/2025 | 181 | M/S JOY MA BANAMALI | 0.89 | 0 | 0
1107 | Murshidabad Division | Berhampur M/E Division | Prooviding FHTC Connection to 835 nos household, Laying of Rising Main, Laying of Distribution System, Overhauling of RCC 100 Cum OHR, , construction Pump House with sanitary and Water Supply Arrangement (T/W-I) , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works & Repair of Boundary Wall (140m + 50m)=190 m at T/W-I site & T/W-II site for Augmentation of Ghora Pakhia Gangin(Zone-I) Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000197/2023-2024 | 1998/MURD | 21/07/2023 | 895 | APURBA SAHA CHOWDHURY | 179.37 | 0 | 50
1108 | Murshidabad Division | Berhampur M/E Division | Laying M.S pipe for interconnection Between A.I.R.P & O.H.R and Clearing chokage of Rising main at GHORAPAKIAGANGING Zone-I Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000825/2022-2023 | 652/MURD | 06/03/2023 | 30 | LAXMI CONSTRUCTION | 1.86 | 1.84 | 100
1109 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000192/2023-2024 | 1210/MURD/17 | 02/05/2023 | 0 | Resource Division | 34.57 | 0 | 0
1110 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under GHORA PAKHIA GANGIN ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000699/2023-2024 | 4342/MEDB | 29/12/2023 | 91 | SREE RADHA ELECTRICAL | 21.44 | 0 | 0
1111 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 10.96 | 20
1112 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PURBA GOBINDAPUR and Adjoining Mouzas PWSS (TW-II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (01 Nos TW) | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000058/2025-2026 | 770/BD-I | 22/05/2025 | 15 | M/S UNIVERSAL TRADING | 9.01 | 0 | 0
1113 | Berhampore Division I | Berhampur Division I | PURBA GOBINDAPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000095/2023-2024 | 217/BD-I | 17/05/2023 | 90 | SUPTI ENTERPRISE | 40.92 | 14.49 | 50
1114 | Berhampore Division I | Berhampur Division I | PURBA GOBINDAPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 200 cum) under Jal Jivan Mission of BHAGWANGOLA -II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000246/2023-2024 | 967/BD-I | 17/10/2023 | 840 | SAMBHUNATH ROY | 298.57 | 0 | 35
1115 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | RTOR000041/2023-2024 | 61/BD-1/33 | 27/04/2023 | 0 | Resource Division | 13.12 | 0 | 0
1116 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION AT PURBA GOBINDAPUR PH-1 | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | BILL/00243/2024-2025 | 102/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 6.06 | 0 | 0
1117 | Murshidabad Division | Kandi Sub-Division | Allied work for Construction of Boundary wall, Road repair & 1 no. Box Culvert at Kirtipur PWSS at Khargram Block under Kandi Sub-Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000062/2024-2025 | 1990/MURD | 08/07/2024 | 597 | ARIZ ENTERPRISE | 36.54 | 0 | 10
1118 | Murshidabad Division | Kandi Sub-Division | Formal work order for KIRTTIPUR & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- KHARGRAM of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000848/2022-2023 | 781/MURD | 20/03/2023 | 1144 | ARIZ ENTERPRISE | 343.69 | 98.43 | 11
1119 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000083/2023-2024 | 1129/MURD/6 | 25/04/2023 | 0 | Resource Division | 10.76 | 0 | 0
1120 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000341/2023-2024 | 79/MURD/08 | 09/01/2024 | 0 | Resource Division | 9.85 | 0 | 0
1121 | Berhampore Mechanical | Kandi Sub-Division | Electric Service Connection at KRITTIPUR PWSS PH I, Application NO.3004450962, ID 304158425 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01079/2023-2024 | 189/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 4.87 | 0 | 0
1122 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS PH2 KIRTIPUR ID304239452 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01416/2023-2024 | 304/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 3.41 | 0 | 0
1123 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Kirttipur ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000271/2023-2024 | 3709/MEDB | 03/11/2023 | 790 | WEST BENGAL ENGINEERING CO. | 22.18 | 0 | 50
1124 | Murshidabad Division |  | Allied work for Construction of Annular Combined Pile Raft Foundation for R.C.C Elevated Reservoir of Capacity 1000 Cu.M of staging height 20 Meter at Head Work site within BUZRAK FATEPUR (Zone XI) W/S Scheme, Block-Saghardighi, District-Murshidabad Under Murshidabad Division P.H.E Dte. |  |  | ORD/000068/2024-2025 | 2023/MURD | 11/07/2024 | 90 | BIJAY CHOWDHURY | 85.49 | 0 | 85
1125 | Murshidabad Division |  | Last mile connectivity and providing 6309 nos Functional House Hold Connection from Zone- XI of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. |  |  | ORD/000175/2024-2025 | 3076/MURD | 26/11/2024 | 90 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 265.37 | 0 | 0
1126 | Murshidabad Division |  | Last mile connectivity and providing 6292 nos Funcational House Hold Connection from Zone- III of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . |  |  | ORD/000330/2023-2024 | 2687/MURD | 25/08/2023 | 120 | J.S. CONSTRUCTION | 348.56 | 0 | 0
1127 | Murshidabad Division |  | Last mile connectivity and providing 7512 nos Funcational House Hold Connection from Zone- I of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte |  |  | ORD/000315/2023-2024 | 2685/MURD | 25/08/2023 | 120 | MANASH GHOSH | 376.07 | 0 | 0
1128 | Murshidabad Division |  | Last mile connectivity and providing 5090 nos Functional House Hold Connection from Zone- V of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. |  |  | ORD/000331/2023-2024 | 2688/MURD | 25/08/2023 | 120 | SARAJIT KUMAR MAJUMDER | 270.74 | 0 | 0
1129 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 2.76 | 100
1130 | Murshidabad Division | Berhampur M/E Division | Augmentation Work of Raturi Zone II Piped Water Supply Scheme to accommodate with FHTC (297 Nos), Laying of Rising Main , Laying of Distribution System , construction of 100 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000309/2023-2024 | 2699/MURD | 25/08/2023 | 560 | SAMBHU NATH ROY | 161.08 | 0 | 30
1131 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000226/2023-2024 | 1219/MURD/19 | 03/05/2023 | 0 | Resource Division | 15.13 | 0 | 0
1132 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kagram & Salar Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000048/2023-2024 | 1102/MURD | 24/04/2023 | 20 | INDRAJIT MAZUMDAR | 10.68 | 0 | 0
1133 | Murshidabad Division | Kandi Sub-Division | Continuation Work Order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage ¿ III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months.(Period From 31.05.2024 to 27.09.2024) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000079/2024-2025 | 92/KSD | 27/05/2024 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 0
1134 | Murshidabad Division | Kandi Sub-Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
1135 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based Surangapur Zone - II (PART -A), Salar PWSS Zone-IA, IB, IIA & IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Nowda & Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 570 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 20
1136 | Murshidabad Division | Kandi Sub-Division | Augmentation of Salar PWSS Zone-IA,IB,IIA,IIB to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 4 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 4no, Construction of Boundary Wall of 600 m, Construction of 400 Cum OHR(1 no) & 300 Cum OHR(2 nos) with sub soil investigation under Jal Jeevan Mission of Bharatpur II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000647/2023-2024 | 3474/MURD | 07/11/2023 | 511 | SUJIT KUMAR SAHA | 575.6 | 0 | 10
1137 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone- I A Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur -II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000718/2023-2024 | 3835/MURD | 14/12/2023 | 21 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 100
1138 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 1.67 | 80
1139 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 4.69 | 76
1140 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of SALAR ZONE 1 A Piped Water Supply Scheme Block BHARATPUR-II District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000028/2025-2026 | 1161/MEDB | 15/05/2025 | 92 | JOY BISHNU ENGINEERING CO. | 21.35 | 0 | 0
1141 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System and FHTC at Bara Biadyapur Village (Village Code-315733), Tenya Village (Village-315737), Ghoshpara Village ( Village Code- 315735), Kechunia Village (Village Code-315722), Korgram Village (Village Code- 315736) & Nowapara Village (Village Code-315734) & Repairing of Over Head Reservoir (350 Cum), Pump House & Boundary wall for Augmentation of TENYA Zone-II PWSS in BHARATPUR-II Block , under Murshidabad Division,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000041/2023-2024 | 1139/MURD | 26/04/2023 | 972 | TANUSHREE ENTERPRISE | 172.7 | 0 | 20
1142 | Murshidabad Division | Kandi Sub-Division | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.06.2025 to 30.09.2025) VEHICLE NO - WB 57E 5422 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000094/2025-2026 | 83/KSD | 21/05/2025 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 0
1143 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Tenya Zone - II Water Supply Scheme and Kurulia Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000109/2023-2024 | 1751/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 27.64 | 0 | 50
1144 | Murshidabad Division | Kandi Sub-Division | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 28.09.2024 to 31.01.2025) VEHICLE NO - WB 57E 5422 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000371/2024-2025 | 141/KSD | 26/09/2024 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 0
1145 | Murshidabad Division | Kandi Sub-Division | Augmentation of MURADPUR JALANGI ZONE-III /Tenya Zone-II & Zone-III PWSS Laying Distribution System, of JALANGI /Bharatpur-II Block , under Murshidabad Division PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000375/2023-2024 | 2755/MURD | 01/09/2023 | 720 | ULTRA CONSTRUCTION. | 100.45 | 0 | 95
1146 | Murshidabad Division | Kandi Sub-Division | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.02.2025 to 31.05.2025) VEHICLE NO - WB 57E 5422 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000389/2024-2025 | 25/KSD | 24/01/2025 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 0
1147 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 6.57 | 80
1148 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 3.5 | 76
1149 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000001/2023-2024 | 969 | 06/04/2023 | 0 | Resource Division | 28.48 | 0 | 0
1150 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000004/2023-2024 | 1004/MURD | 11/04/2023 | 0 | Resource Division | 28.48 | 0 | 0
1151 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , Zone-II under TENYA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000105/2023-2024 | 1901/MEDB | 16/06/2023 | 92 | S. G. ENTERPRISE | 33.51 | 0 | 0
1152 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
1153 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Basudevpur halt Station (TP NO 240/8 & 240/9) at Ratanpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Bhasipaikar Zone - III ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000422/2021-2022 | 2479/MURD | 16/08/2021 | 60 | ACQUA CONSTRACTION CONSORTIAM | 22.97 | 22.31 | 90
1154 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0
1155 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000122/2023-2024 | 1167/MURD/30 | 28/04/2023 | 0 | Resource Division | 33.07 | 0 | 0
1156 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-III under Bhasaipaikar ground water based water supply scheme under Block_ Samserganj ,Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000248/2023-2024 | 3660/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 34.39 | 0 | 0
1157 | Murshidabad Division | Berhampur M/E Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000001/2025-2026 | 761/MURD | 02/04/2025 | 80 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0
1158 | Murshidabad Division | Berhampur M/E Division | Balance work for Repair & Renovation of Existing AIRP (Modified Sujapur Sadhipur Model) of (Capacity 72 Cu.M/hr) at Harua Water Supply Scheme at Suti-I Block, of Jangipur Sub-Division under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000067/2025-2026 | 1243/MURD | 29/05/2025 | 60 | SUMAN ENTERPRISE AND SUMAN AQUA | 27.06 | 0 | 0
1159 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 2.73 | 100
1160 | Murshidabad Division | Berhampur M/E Division | Augmentation Work of Harua Part A Piped Water Supply Scheme to accommodate with Laying of Rising Main , Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000144/2023-2024 | 1868/MURD | 14/07/2023 | 902 | PAL CONSTRUCTION | 31 | 24 | 28
1161 | Murshidabad Division | Berhampur M/E Division | Refilling of sand layers, Activated Alumina & existing gravel for Modified Sujapur Sadipur Model after washing of AIRP allied (Capacity 72.00Cum/hr.) at Harua Water Supply Scheme under Jal Jivan Mission of Suti-I Block under Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000822/2023-2024 | 743/MURD | 12/03/2024 | 535 | SUMAN ENTERPRISE AND SUMAN AQUA | 63.59 | 0 | 50
1162 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000223/2023-2024 | 1219/MURD/22 | 03/05/2023 | 0 | Resource Division | 20.71 | 0 | 0
1163 | Berhampore Mechanical | Berhampur M/E Division | Harua PH-3 Application No- 3004555905 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/01198/2023-2024 | 275/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 8.65 | 0 | 0
1164 | Berhampore Mechanical | Berhampur M/E Division | Harua PH-1 Application No- 3004555901 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/01199/2023-2024 | 276/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 2.16 | 0 | 0
1165 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. . under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000550/2024-2025 | 332/MEDB | 10/02/2025 | 89 | QUAZI NOZRUL ISLAM (PARTNERSHIP) | 12.71 | 0 | 0
1166 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 12.05 | 20
1167 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NAMOORAHAR PWSS (2nd TW Site) under Jal Jeevan Mission in Lalgola Block under Berhampore Division-I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000003/2025-2026 | 547/BD-I | 09/04/2025 | 15 | BHOWMIK CONSTRUCTION | 8.99 | 0 | 0
1168 | Berhampore Division I | Berhampur M/E Division | NAMOORAHAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000080/2023-2024 | 732/BD-I | 16/08/2023 | 90 | MASOOM TRADERS | 34.64 | 0 | 25
1169 | Berhampore Division I | Berhampur M/E Division | NAMOORAHAR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 150 cum) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000195/2023-2024 | 746/BD-I | 17/08/2023 | 868 | M/S. UNIQUE BUILDERS | 244.5 | 0 | 10
1170 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000022/2023-2024 | 61/BD-1/28 | 27/04/2023 | 0 | Resource Division | 16.52 | 0 | 0
1171 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000118/2023-2024 | 304/BD-1/11 | 22/02/2024 | 0 | Resource Division | 6.42 | 0 | 0
1172 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III under NAMOORAHAR ground water based water supply scheme under Block_ LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000026/2025-2026 | 1159/MEDB | 15/05/2025 | 92 | MASSK ENGINEERING WORKS | 10.65 | 0 | 0
1173 | Murshidabad Division | Lalbag Sub-Division | Laying of distribution system for the left out portion of Bhandara Mouza Rising Main with DI pipe and interconnection with DI pipe at Head Work Site of Bhandara Zone - I & II Water Supply Scheme and Ancillary works in Lalbagh Sub Divisional Office under Lalbagh Sub Division, Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000090/2025-2026 | 1829/MURD | 18/08/2025 | 60 | MARUTI CONSTRUCTION AND CO. | 47.57 | 0 | 0
1174 | Murshidabad Division | Lalbag Sub-Division | Continuation Order for Hiring of Maxi cab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E. Dte. for 92 days i.e. from 01.10.2025 to 31.12.2025.(The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)(Vehicle No. WB-58AX-9595) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000153/2025-2026 | 373/LSD | 23/09/2025 | 92 | BARI ENTERPRISE | 0.45 | 0 | 0
1175 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Nabagram of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Amarkundu Water Supply Scheme, Nabagram Zone-I & II Water Supply Scheme, Panchgram Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000350/2022-2023 | 1929/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 7.92 | 2.67 | 100
1176 | Murshidabad Division | Lalbag Sub-Division | Augmentation of BHANDARA (ZONE - II A) & Augmentation of BHAGIRATHPUR PWSS under Jal Jeevan Mission of Bhagawangola-I & Domkal Block, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000623/2023-2024 | 3372/MURD | 31/10/2023 | 270 | MAMATA USHA ENTERPRISE | 902.27 | 0 | 0
1177 | Murshidabad Division | Lalbag Sub-Division | Augmentation of BHANDARA (ZONE - II B) PWSS under Jal Jeevan Mission of Bhagawangola-I Block, Lalbagh Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000853/2023-2024 | 829/MURD | 15/03/2024 | 300 | CHAKRABORTY CONSTRUCTION | 407.22 | 0 | 0
1178 | Berhampore Mechanical | Lalbag Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-II under Bhandara ground water based water supply scheme under Block_Bhagwangola - I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000648/2023-2024 | 3663/MEDB | 03/11/2023 | 92 | TARUN KUMAR BHATTACHARYA | 35.9 | 0 | 0
1179 | Berhampore Mechanical | Lalbag Sub-Division | Continuation Order Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Executive Engineer under Office of the Executive Engineer, Mechanical/Electrical Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000784/2023-2024 | 3364/AE/MEDB | 27/09/2023 | 182 | M/S SAJAHAN CHOWDHURY | 0.9 | 2.23 | 0
1180 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 4.85 | 100
1181 | Murshidabad Division | Jangipur Sub-Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 300 & 900 cum), Sinking of Tube Well and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Arjunpur Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000547/2023-2024 | 3177/MURD | 11/10/2023 | 730 | M/S. CHAKRABORTY & COMPANY | 2041.06 | 0 | 35
1182 | Murshidabad Division | Jangipur Sub-Division | Allied works for Laying of U.P.V.C Pipeline of 160 mm,125 mm & 90 mm dia at Head work site of Arjunpur Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000742/2023-2024 | 50/MURD | 05/01/2024 | 30 | SK CONSTRUCTION (NAJIR SK.) | 5.71 | 0 | 100
1183 | Murshidabad Division | Jangipur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 8.36 | 80
1184 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000139/2023-2024 | 1167/MURD/41 | 28/04/2023 | 0 | Resource Division | 25.97 | 0 | 0
1185 | Berhampore Mechanical | Jangipur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-I under ARJUNPUR ground water based water supply scheme under Block_ FARAKKA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000457/2023-2024 | 3720/MEDB | 03/11/2023 | 92 | AVINABA ENGINEERING CONCERN | 31.54 | 0 | 0
1186 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall at Sarbangapur Zone-I, P.H-2 under Sarbangapur Zone-I Water Supply Scheme under Berhampore Sub-Division , P.H.E. Dte. in the District Murshidabad. ( 55.0MTR.)_PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000752/2023-2024 | 131/MURD | 15/01/2024 | 30 | PAL CONSTRUCTION | 4.44 | 4.42 | 100
1187 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Sarbangapur Zone-IA PWSS of accommodate FHTC, Laying Distribution System, Laying Rising Main, Repairing of Switch Room, Repairing of Boundary Wall, Repairing of 450 CUM OHR in Nawda Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000753/2023-2024 | 130/MURD | 15/01/2024 | 411 | NILKAMAL BASAK | 323.16 | 0 | 70
1188 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000159/2023-2024 | 1180/MURD/27 | 29/04/2023 | 0 | Resource Division | 97.75 | 0 | 0
1189 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 200 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone- II PWSS in Lalgola Block & Mirzapur (Except Gankar Mouza) PWSS Raghunathganj-I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000612/2023-2024 | 3377/MURD | 31/10/2023 | 730 | M/S GHOSH & CO. | 1181.6 | 0 | 20
1190 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site 3RD Site at LALGOLA Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000699/2023-2024 | 3784/MURD | 11/12/2023 | 21 | GENUINE | 35.34 | 0 | 0
1191 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000126/2023-2024 | 1167/MURD/17 | 28/04/2023 | 0 | Resource Division | 30.59 | 0 | 0
1192 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-II under Lalgola ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000650/2023-2024 | 3667/MEDB | 03/11/2023 | 92 | M/S K.P. PRAMANIK | 36.25 | 28.09 | 10
1193 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Purushottampur PWSS of accommodate Laying Distribution System, in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte.PART_B | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000293/2023-2024 | 2667/MURD | 24/08/2023 | 180 | J.S. CONSTRUCTION | 346.34 | 0 | 0
1194 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 0 | 100
1195 | Murshidabad Division | Berhampur M/E Division | Construction of 250 Cum OHR, Pump House, Boundary wall & Repairing of Pump House, B.W, Rising Main Connection & FHTC for Augmentation of PURUSOTTAMPUR PWSS in Raninagar-I Block , Islampur Sub-Division under Murshidabad Division ,PHE. Dte.PART_A | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000352/2023-2024 | 2674/MURD | 24/08/2023 | 365 | M/S BIKASH ENTERPRISE | 342.01 | 0 | 0
1196 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000239/2023-2024 | 1219/MURD/18 | 03/05/2023 | 0 | Resource Division | 198.03 | 0 | 0
1197 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 20
1198 | Berhampore Division I | Berhampur M/E Division | KHAMARDIAR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000175/2023-2024 | 690/BD-I | 10/08/2023 | 180 | SARAJIT KUMAR MAJUMDAR | 289.91 | 0 | 60
1199 | Berhampore Division I | Berhampur M/E Division | KHAMARDIAR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART - A) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000176/2023-2024 | 689/BD-I | 10/08/2023 | 980 | MD MAIDUL ISLAM | 330.82 | 0 | 65
1200 | Berhampore Division I | Berhampur M/E Division | KHAMARDIAR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART -C) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000177/2023-2024 | 691/BD-I | 10/08/2023 | 900 | M/S BIMALENDU BOSE | 214.12 | 185.32 | 90
1201 | Berhampore Division I | Berhampur M/E Division | KHAMARDIAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000187/2023-2024 | 734/BD-I | 16/08/2023 | 90 | NATIONAL CONSTRUCTION | 50.37 | 0 | 25
1202 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Khamardiar Water Supply Scheme under JJM under Berhampore Division - I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000270/2024-2025 | 2331/BD-I | 30/12/2024 | 30 | KAMIRUL SK AND CO. | 18.01 | 0 | 0
1203 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000100/2023-2024 | 201/BD-1/4 | 10/02/2024 | 0 | Resource Division | 12.11 | 0 | 0
1204 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT KHAMARDIAR PH-I | ASSISTANT ENGINEER-I | Junior engineer-III | BILL/00247/2024-2025 | 100/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
1205 | Murshidabad Division | Kandi Sub-Division | Balance work for laying of CI/DI pipe line including supporting structure at Gaysabad PWSS at Bharatpur - I Block under Kandi Sub-Division, Murshidabad Division, PHE Dte in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000009/2025-2026 | 888/MURD | 22/04/2025 | 120 | M/S BHUBAN DAS | 122.18 | 0 | 0
1206 | Murshidabad Division | Kandi Sub-Division | GAYSABAD (Part-B) & adjoining mouzas PWSS to accommodate Of T/W,LDS, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000174/2023-2024 | 1992/MURD | 21/07/2023 | 795 | M/S BHUBAN DAS | 418.26 | 88.15 | 10
1207 | Murshidabad Division | Kandi Sub-Division | GAYSABAD (Part-A) & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Rising Main, FHTC work, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000202/2023-2024 | 2059/MURD | 27/07/2023 | 644 | DHIRENDRANATH MONDAL | 438.55 | 0 | 5
1208 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000055/2023-2024 | 1067/MURD/11 | 18/04/2023 | 0 | Resource Division | 77.6 | 0 | 0
1209 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1210 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT GAYSABAD PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00517/2024-2025 |  | 08/07/2024 | 0 | WBSEDCL | 4.14 | 0 | 0
1211 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT GAYSABAD PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00526/2024-2025 | 163/WBSEDCL-JJM | 29/07/2024 | 0 | WBSEDCL | 4.14 | 0 | 0
1212 | Berhampore Mechanical | Kandi Sub-Division | Electric Service Connection at GYASABAD PWSS PH I, Application NO.3004407323, ID 304123114 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01055/2023-2024 | 186/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 6.81 | 0 | 0
1213 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I , II & III under GAYSABAD ground water based water supply scheme under Block_ Bharatpur-I, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000712/2023-2024 | 4065/MEDB | 04/12/2023 | 91 | M/S SAJAHAN CHOWDHURY | 36.54 | 23.13 | 5
1214 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System (PART-C) and FHTC for KUNDAL PWSS in Burwan Block under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000178/2023-2024 | 1997/MURD | 21/07/2023 | 120 | KISMAT ARA BEGAM | 214.39 | 34.08 | 60
1215 | Murshidabad Division | Kandi Sub-Division | Construction of 450 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, for Uncovered of KUNDAL PWSS at KUNDAL (Village Code- 315846), PADMALABHBATI (Village Code- 315845) in Burwan Block , Kandi Sub-Division under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000190/2023-2024 | 1993/MURD | 21/07/2023 | 773 | M/S UNIVERSAL TRADING | 361.74 | 87.55 | 60
1216 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System (PART-B), FHTC (PART-A) , Boundary wall for Uncovered of KUNDAL PWSS at JHIKARHATI (PART) (Village Code- 315835) , KUNDAL (Village Code- 315846), PADMALABHBATI (Village Code315845) and JHIKARHATI (PART)in Burwan Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000192/2023-2024 | 2023/MURD | 25/07/2023 | 120 | DIPAYAN DEY | 182.24 | 0 | 50
1217 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kundal & adjoining mouzas Water Supply Scheme at Head Work Site, 2nd Site & 3 rd site at Burwan Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000203/2023-2024 | 2071/MURD | 28/07/2023 | 585 | NADIA TUBEWELLS | 32.03 | 0 | 60
1218 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000021/2023-2024 | 1210/MURD/39 | 02/05/2023 | 0 | Resource Division | 39.23 | 0 | 0
1219 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under KUNDAL ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000704/2023-2024 | 2770/MEDB | 25/07/2023 | 92 | JAL PRAVAHIKA PVT LTD | 35.06 | 0 | 0
1220 | Murshidabad Division | Berhampur M/E Division | Augmentation of JUGINDA (Zone - I) Piped Water Supply Scheme under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000377/2023-2024 | 2772/MURD | 01/09/2023 | 180 | PRADIP KUMAR DAS (PROPRIETORSHIP) | 600.58 | 0 | 0
1221 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-III | RTOR000206/2023-2024 | 1210/MURD/22 | 02/05/2023 | 0 | Resource Division | 133.91 | 0 | 0
1222 | Berhampore Mechanical | Berhampur M/E Division | JUGINDA PH-IV | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-III | BILL/01526/2023-2024 | 408/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 4.24 | 0 | 0
1223 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under JUGINDA ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-III | ORD/001431/2023-2024 | 4311/MEDB | 29/12/2023 | 91 | M/S DILIP MITRA | 23.67 | 0 | 0
1224 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Nabagram of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Amarkundu Water Supply Scheme, Nabagram Zone-I & II Water Supply Scheme, Panchgram Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000350/2022-2023 | 1929/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 7.92 | 2.11 | 100
1225 | Murshidabad Division | Lalbag Sub-Division | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 600 cum) and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone- IV PWSS in Lalgola Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000646/2023-2024 | 3466/MURD | 06/11/2023 | 365 | M/S. SINHA & SONS | 796.64 | 0 | 0
1226 | Murshidabad Division | Lalbag Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | RTOR000180/2023-2024 | 1180/MURD/19 | 29/04/2023 | 0 | Resource Division | 27.58 | 0 | 0
1227 | Berhampore Mechanical | Lalbag Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-IV under Lalgola ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000663/2023-2024 | 3712/MEDB | 03/11/2023 | 92 | ORIENTAL ENGINEERING CO. | 35.18 | 0 | 0
1228 | Murshidabad Division | Berhampur M/E Division | Laying Distribution System, Rising Main Connection, FHTC connections, for Augmentation of Teghari Zone-II PWSS of Raghunathganj-II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000162/2025-2026 | 2127/MURD | 23/09/2025 | 90 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 279.55 | 0 | 0
1229 | Murshidabad Division | Berhampur M/E Division | Augmentation of Teghari zone II PWSS Construction of 500 Cum OHR with subsoil investigation, Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) (1no)& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) (3 no) & construction of boundary wall of 250 mtr of Raghunathganj - II Block, under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000580/2023-2024 | 3315/MURD | 22/10/2023 | 250 | VISION ENTERPRISE | 235.76 | 0 | 0
1230 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.96 | 100
1231 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000117/2023-2024 | 1167/MURD/11 | 28/04/2023 | 0 | Resource Division | 77.93 | 0 | 0
1232 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000536/2024-2025 | 322/MEDB | 10/02/2025 | 89 | SARKAR CONSTRUCTION | 22.73 | 0 | 0
1233 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Herampur Zone-II PWSS in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte.PART_A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000311/2023-2024 | 2671/MURD | 24/08/2023 | 586 | CAPITAL CONSTRUCTION | 279.7 | 137.63 | 30
1234 | Murshidabad Division | Berhampur M/E Division | Construction of 250 Cum OHR, Pump House, Boundary wall & Repairing of Pump House for Augmentation of Herampur Zone-I PWSS in Raninagar-I Block , Islampur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000350/2023-2024 | 2672/MURD | 24/08/2023 | 769 | M/S. UNI TRADERS | 143.17 | 0 | 30
1235 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 2.84 | 100
1236 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000231/2023-2024 | 1219/MURD/13 | 03/05/2023 | 0 | Resource Division | 13.89 | 0 | 0
1237 | Berhampore Mechanical | Berhampur M/E Division | : NEW CONNECTION HERAMPUR PWSS Z2 PH1 ID 304495838 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01117/2024-2025 |  | 25/11/2024 | 0 | WBSEDCL | 4.34 | 0 | 0
1238 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000565/2024-2025 | 347/MEDB | 10/02/2025 | 89 | SUNIL RABIDAS | 21.38 | 0 | 0
1239 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 14.89 | 20
1240 | Berhampore Division I | Raghunathganj Sub-Division | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Bishnupur Zone-I ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000001/2025-2026 | 506/BD-I | 03/04/2025 | 300 | NATIONAL CONSTRUCTION | 122.54 | 0 | 90
1241 | Berhampore Division I | Raghunathganj Sub-Division | Replacement of Filter media of Existing AIRP of (Capacity 80 Cum/hr.) with allied work at Bishnupur Zone-I Water Supply Scheme under Jal Jeevan Mission of Raninagar-I under Berhampore Division-I, PHEengineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000009/2024-2025 | 903/BD-I | 06/06/2024 | 209 | SUMAN ENTERPRISE AND SUMAN AQUA | 40.09 | 0 | 85
1242 | Berhampore Division I | Raghunathganj Sub-Division | BISHNUPUR ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000085/2024-2025 | 1265/BD-I | 01/08/2024 | 300 | SHIBAM ENTERPRISE | 21.91 | 0 | 80
1243 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augmentation of Bishnupur Zone-I PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000092/2024-2025 | 1304/BD-I | 07/08/2024 | 60 | M/S BHAGIRATHI ENTERPRISE | 7.65 | 0 | 0
1244 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Bishnupur Zone-I Piped water supply scheme to accommodate construction of OHR, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000141/2023-2024 | 627/BD-I | 04/08/2023 | 1123 | NATIONAL CONSTRUCTION | 452.24 | 129.49 | 25
1245 | Berhampore Division I | Raghunathganj Sub-Division | Repair And Renovation Works Of OHR (350 Cum) of Ground Water Based Supply Scheme for Bishnupur Zone-I of Raninagar-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000250/2023-2024 | 1034/BD-I | 01/11/2023 | 30 | ARJU CONSTRUCTION | 8.5 | 0 | 100
1246 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000019/2023-2024 | 194/BD-I/5 | 09/02/2024 | 0 | Resource Division | 56.41 | 0 | 0
1247 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW CONNECTION BISHNUPUR PRATAPUR Z-I PH-II | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | BILL/01628/2023-2024 | 467/WBSEDCL-JJM | 19/03/2024 | 0 | WBSEDCL | 1.74 | 0 | 0
1248 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW CONNECTION AT BISHNUPUR PRATAPUR Z-I PH-I | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | BILL/01630/2023-2024 | 468/WBSEDCL-JJM | 19/03/2024 | 0 | WBSEDCL | 6.75 | 0 | 0
1249 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Bishnupur Zone-I ground water supply scheme in Raninagar-I Block Dist_Murshidabad under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000006/2025-2026 | 1130/MEDB | 13/05/2025 | 92 | SREE RADHA ELECTRICAL | 39.95 | 0 | 0
1250 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bagdanga (Village code 314725) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723328 in the District of Murshidabad. |  |  | ORD/000243/2020-2021 | 84/MURD | 08/01/2021 | 60 | DOBAY CONSTRUCTION | 41.95 | 41.33 | 0
1251 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dakshin Nagar ( Village Code -314728) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001723344). |  |  | ORD/000171/2020-2021 | 594/MURD | 09/02/2021 | 60 | SUJIT KUMAR SAHA | 46.24 | 8.62 | 1
1252 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jhaubaria ( Village Code -314729) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344). |  |  | ORD/000729/2020-2021 | 584/MURD | 09/02/2021 | 60 | DAS ENTERPRISE (SUBRATA DAS) | 21.07 | 4.78 | 1
1253 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dakshin Nagar ( Village Code -314728) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001723344). |  |  | ORD/000740/2020-2021 | 594 / MURD | 09/02/2021 | 60 | SUJIT KUMAR SAHA | 46.24 | 0 | 1
1254 | Murshidabad Division |  | Relaying of different dia UPVC pipeline for Balance Providing Functional Household Tap connection (FHTC) of 94 nos in connection with Jal Swapna (Jal Jeevan Mission) and under command areas of village of Jhaubaria (Village Code-314729) under Juginda Ground water based water suply scheme for Arsenic affected areas of DomkalBlock, under Murshidabad Division, P.H.E. Dte. (scheme ID- 0001723344) |  |  | ORD/001835/2021-2022 | 767/MURD | 22/03/2022 | 20 | MONDAL ENTERPRISE | 6.65 | 5.74 | 1
1255 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) of village JHAUBARIA (Village Code: 314729) under JUGINDA Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL, Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID : 0001723344) Tender no- 825 of 20-21 by EE / MURD |  |  | VCH/000189/2021-2022 | 15-MSD / 21-22 | 10/08/2021 | 0 | DAS ENTERPRISE (SUBRATA DAS) | 14.24 | 0 | 0
1256 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village DAKSHIN NAGAR (Village Code: 314728) under JUGINDA Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 003 of 20-21 by EE / MSD |  |  | VCH/000226/2021-2022 | 17-MSD / 21-22 | 13/08/2021 | 0 | SUJIT KUMAR SAHA | 36.26 | 0 | 0
1257 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mridadpur ( Village Code -314570) under Brindabanpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0005019111). |  |  | ORD/000183/2020-2021 | 597/MURD | 09/02/2021 | 60 | SANJAY BISWAS | 67.55 | 68.85 | 0
1258 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 493 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mridadpur (Village code 314570) under Brindabanpur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005019111) |  |  | ORD/001879/2021-2022 | 855/MURD | 31/03/2022 | 20 | SUBHENDRA MOHAN SARKAR | 12.24 | 0 | 100
1259 | Murshidabad Division |  | Continuation order for Holding Awarness Programme / Campaigning programs at Nowda G.P, Raypur G.P, Madhupur G.P, Sarbangapur G.P, Choa G.P, Hariharpara G.P, Mahula G.P, & Rangamati Chandpara G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. |  |  | ORD/000114/2020-2021 | 690/MURD | 23/02/2021 | 30 | S.S.INFRASTRUCTURE | 3.18 | 6.35 | 0
1260 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bagharpur Ramna (Village code 314665) under Domkal Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. (Sl No-12) |  |  | ORD/000719/2020-2021 | 3117 / MURD | 09/12/2020 | 180 | M/S NIRAPADA BHATTACHARJEE | 95.68 | 0 | 0
1261 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagharpur Ramna ( 314665 ) of Bagharpur Ramna under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) |  |  | VCH/000006/2021-2022 | 07/MSD/21-22 | 16/07/2021 | 0 | M/S NIRAPADA BHATTACHARJEE | 38.35 | 0 | 0
1262 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BAGHARPUR RAMNA (Village Code 314665) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 66 of 20-21 by SE MC |  |  | VCH/001514/2021-2022 | 402-MSD/21-22 | 23/03/2022 | 0 | M/S NIRAPADA BHATTACHARJEE | 28.13 | 0 | 0
1263 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Kulgachi (Code-314169), Bilnasipur (Code-314170), Singa (Code-314181), Salmara(Code-3174182),Haripur(Code-314185) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000108/2024-2025 | 1445/BD-I | 04/09/2024 | 60 | HI-LIGHT ELECTRONICS | 19.95 | 0 | 0
1264 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilnasipur (Village code 314170),Salmara(Village code 314182),Kulgachi( Village code 314169), Haripur( Village code 314185),Singa ( Village code 314181 ) under Nasipur Zone-I Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | Assistant Engineer-I | JE | ORD/000126/2020-2021 | 202/BD-I | 04/02/2021 | 30 | TARUN KUMAR BHATTACHARYA | 78.52 | 73.75 | 0
1265 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Telia (Village code 314466) under Telia Ground Water Supply Scheme in Bhagawangola-I Block under Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-2) | Assistant Engineer-I | JE | ORD/000499/2021-2022 | 1906/BD-I | 08/10/2021 | 180 | RAJ KUMAR MONDAL | 103.96 | 95.85 | 1
1266 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Domkal (Village code 314695) under Domkal Ground Water Based Water Supply Scheme & & Barabil Raghunathpur (Village code 314626) for Arsenic Affected Area of Domkal & Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. (Sl No-15) |  |  | ORD/000206/2020-2021 | 3110/MURD | 09/12/2020 | 180 | ARINDAM MAJUMDAR | 48.25 | 0 | 80
1267 | Murshidabad Division |  | Formal Work Order for Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Barabil Raghunathpur ( Village Code -314626) under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723213) in the District of Murshidabad.(Sl-30) |  |  | ORD/000636/2020-2021 | 525/MURD | 04/02/2021 | 180 | MITRA CONSTRUCTION | 138.32 | 14.85 | 0
1268 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village BARABIL RAGHUNATHPUR (Village Code-314626) under BARABIL RAGHUNATHPUR Ground Water Supply Scheme Arsenic Affected Area of Jalangi Block of Murshidabad District under Murshidabad Division, PHE Dte. Scheme ID 0001723213 |  |  | VCH/000236/2021-2022 | 26-MSD / 21-22 | 19/08/2021 | 0 | MITRA CONSTRUCTION | 52.92 | 0 | 0
1269 | Murshidabad Division |  | Additional work for Providing of Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village JOYRAMPUR (Village Code 314693) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 99 of 21-22 by EE MURD |  |  | VCH/001549/2021-2022 | 372-MSD/21-22 | 18/03/2022 | 0 | SAHABUDDIN BISWAS | 18.52 | 0 | 0
1270 | Murshidabad Division | Islampur Sub-Division | Providing Functional Household Tap Connections (FHTC) of 1467 nos in connection with (Jal Jeevan Mission ) and under command area of village of Juranpur ( Village Code -314720) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000204/2022-2023 | 1380/MURD | 26/05/2022 | 60 | M/S. S. DAS AND ENTERPRISE | 72.04 | 35.34 | 40
1271 | Murshidabad Division | Islampur Sub-Division | Extension of pipeline from different (Juranpur & Tekaraipur) water supply scheme forn connection of Health Centre under Domkal & Raninagar-I Block under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000319/2021-2022 | 380/1/ISD | 26/07/2021 | 30 | M/S. SAJEDA ENTERPRISE | 4.02 | 4.01 | 1
1272 | Murshidabad Division | Islampur Sub-Division | Extension of pipeline from different (Shibnagar laskarpur, juranpur, Juginda Zone-II, Tekaraipur, Garibpur Z-I, Aminabad) water supply scheme forn connection of Health Centre under Domkal & Raninagar-I Block under Islampur Sub-Division under Murshidabad Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/002124/2021-2022 | 381/1/ISD | 26/07/2021 | 30 | NABIRUL ISLAM | 4.14 | 3.95 | 0
1273 | Murshidabad Division |  | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block(Teghori, Kasiadanga,Laxmijhola & Sekhalipur) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (PART-B) |  |  | ORD/000068/2021-2022 | 125 /JSD | 25/05/2021 | 30 | S.S.INFRASTRUCTURE | 1.58 | 1.58 | 0
1274 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lakshijala ( Village Code -314127) under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) |  |  | ORD/000075/2021-2022 | 1468/MURD | 21/06/2021 | 60 | MARUTI CONSTRUCTION AND CO | 35.66 | 0 | 0
1275 | Murshidabad Division |  | Allied work for rectrofitting providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Babupur (Village Code-314126) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. |  |  | ORD/001274/2021-2022 | 391/JSD | 31/12/2021 | 30 | BENGAL ENTERPRISE | 4.83 | 0 | 0
1276 | Murshidabad Division |  | Laying of UPVC pipeline at village LAXMIJOLA WEST SIDE in connection with FHTC work under KASIADANGA (ZONE-I) W/S Scheme under JSD PHE DTE. Tender no - 55 of 21-22 by AE LSD |  |  | VCH/000029/2022-2023 | 25-MSD/22-23 | 11/04/2022 | 0 | PRADIP DAS | 4.67 | 0 | 0
1277 | Murshidabad Division |  | Laying of UPVC pipeline at village LAXMIJOLA WEST SIDE in connection with FHTC work under KASIADANGA (ZONE-I) W/S Scheme under JSD PHE DTE. Tender no - 55 of 21-22 by AE LSD |  |  | VCH/000092/2022-2023 | 25-MSD/22-23(RE | 28/04/2022 | 0 | PRADIP DAS | 4.67 | 0 | 0
1278 | Murshidabad Division |  | IEC PROGRAM AND VIDEO DOCUMENTARY AND OTHER AWARENESS WORK OF FHTC AT DIFFERENT PLACES UNDER LSD |  |  | VCH/000589/2021-2022 |  | 24/09/2021 | 0 | S.S.INFRASTRUCTURE | 9.91 | 0 | 0
1279 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00" x 4'00") which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Lalgola G.P, Paharpur G.P, Amdahara G.P, Kolan G.P, Kantanagar G.P, Mahammodpur G.P,Amarkundu G.P. & Shibpur G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. , tno- 13/21-22/AE LSD |  |  | VCH/000821/2021-2022 | 131-MSD/21-22 | 07/10/2021 | 0 | S.S.INFRASTRUCTURE | 2.32 | 0 | 0
1280 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection (FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Lalbagh Sub-Division under Murshidabad Division, P.H.E Dte. (Shibpur G.P, Amarkundu G.P, Lalgola G.P. & Bilborakopra G.P., TNO- 15/21-22/AELSD |  |  | VCH/000822/2021-2022 | 131-MSD/21-22 | 07/10/2021 | 0 | S.S.INFRASTRUCTURE | 4.34 | 0 | 0
1281 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Lalbagh Sub-Division under Murshidabad Division, P.H.E Dte.(Amdahara GP, Mahammadpur GP & Kantanagar GP), TNO-14/21-22/EE |  |  | VCH/000823/2021-2022 | 131-MSD/21-22 | 07/10/2021 | 0 | S.S.INFRASTRUCTURE | 3.26 | 0 | 0
1282 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village LAKSHIJALA (Village Code 314127) under KASIADANGA Ground Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-II Block in the District of Murshidabad. Tender no - 550 of 21-22 by EE MURD |  |  | VCH/001465/2021-2022 | 362-MSD/21-22 | 11/03/2022 | 0 | MARUTI CONSTRUCTION AND CO | 35.66 | 0 | 0
1283 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babupur ( Village Code 314126) under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001756852) |  |  | VCH/001473/2021-2022 | 380-MSD/21-22 | 16/03/2022 | 0 | BENGAL ENTERPRISE | 18.97 | 0 | 0
1284 | Murshidabad Division | Kandi Sub-Division | Laying of rising main (DI) from tube well to 300 Cum OHR and laying of distribution main (DI) from OHR to distribution system including supply of C.I. specials and restoration work of concrete road of Bahara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000003/2022-2023 | 05/KSD | 06/04/2022 | 30 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 4.85 | 4.59 | 1
1285 | Murshidabad Division | Kandi Sub-Division | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00'' x 4'00'') which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Gokarna-II G.P, Mahalandi-I G.P, Kumarsanda G.P, Jasahari Anukha-I & II G.P, Burwan- I & II G.P, Panchthupi G.P & Sohara G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000078/2021-2022 | 176/KSD | 28/05/2021 | 30 | IMAGIN | 2.61 | 2.61 | 1
1286 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAHARA (Village Code 315291) under Bahara Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000185/2020-2021 | 3021/MURD | 04/12/2020 | 45 | M/S. BIMALENDU BOSE | 25.13 | 24.83 | 0
1287 | Murshidabad Division | Kandi Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000415/2021-2022 | 215/KSD | 11/08/2021 | 30 | IMAGIN COMMUNICATION | 4.33 | 0 | 0
1288 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JASAHARI ANUKHA-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000441/2021-2022 | 225/KSD | 27/08/2021 | 60 | IMAGIN | 4.17 | 0 | 0
1289 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JASAHARI ANUKHA-II G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000457/2021-2022 | 226/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0
1290 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at GOKARNA-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000474/2021-2022 | 242/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0
1291 | Murshidabad Division | Kandi Sub-Division | Construction of valve chamber & laying of upvc pipe line including supply of C.I. specials and valves in connection with FHTC work of Bahara village (Village Code-315810) under Bahara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. (SL-01) | ASSISTANT ENGINEER |  | ORD/000517/2022-2023 | 154/KSD | 31/08/2022 | 30 | BISWAS CONSTRUCTION | 4.55 | 4.54 | 1
1292 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) of Bahara & Ghoshbati habitation under command area of Bahara village (Village Code- 315291) of Bahara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Kandi Block under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad.(SL_03) | ASSISTANT ENGINEER |  | ORD/000519/2022-2023 | 156/KSD | 31/08/2022 | 45 | SIMA ENTERPRISE | 4.84 | 4.8 | 1
1293 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village LAHARPARA (Village Code 315282) under Bahara Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000585/2020-2021 | 2880/MURD | 12/11/2020 | 45 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 32.21 | 8.94 | 0
1294 | Murshidabad Division | Kandi Sub-Division | Laying of pipe line for distribution system from node point 1B to 1C & laying of rising main from H.W Site to 2nd tube well site under Improvement work of Bahara water supply scheme under Kandi Sub Division, P.H.E.Dte in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000707/2020-2021 | 3109/MURD | 09/12/2020 | 30 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 4.84 | 4.81 | 0
1295 | Murshidabad Division | Kandi Sub-Division | Laying of different dia UPVC pipe line from node point 45 to node point 3 & node point 45 to node point 1E for distribution network with supply of materials for pipe line under Improvement work of Bahara water supply scheme under Kandi Sub Division, P.H.E.Dte in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000727/2020-2021 | 3222/MURD | 18/12/2020 | 30 | KUNTAL SAHA | 4.86 | 4.85 | 1
1296 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of BHANDIRA habitation under Bhandira (Village Code: 315292) under BAHARA Surface Water Based Water Supply Scheme for arsenic affected areas of KANDI Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 398 of 20-21 by EE / MSD | ASSISTANT ENGINEER |  | VCH/000198/2021-2022 | 08 -MSD / 21-22 | 04/08/2021 | 0 | M/S GUNGUN CONSTRUCTION | 22.54 | 0 | 0
1297 | Murshidabad Division | Kandi Sub-Division | Continuation order for Holding Awarness Programme / Campaigning programs at Chandpur-I II G.P, Bali G.P, Patikabari G.P, Madhupur G.P, Kedar Chandpur-I G.P, Khidirpur G.P, Humaipur G.P, Rampara-I G.P, Andulberia G.P, Dadpur G.P, Rampara-II G.P, Mirzapur-I & II G.P, Kumarpur Sujapur G.P, Debkunda G.P, Madda G.P, Sahajadpur G.P, Niyallishpara G.P, Satui Chowrigachha G.P, Shaktipur G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000115/2020-2021 | 691/MURD | 23/02/2021 | 30 | IMAGIN | 4.77 | 9.53 | 0
1298 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Muniadihi (Village Code- 315982) under Panchthupi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block under Murshidabad Division, P.H.E.Dte. (SL-02) | ASSISTANT ENGINEER |  | ORD/000518/2022-2023 | 155/KSD | 31/08/2022 | 45 | SARTHAK SK. | 4.81 | 3.17 | 0
1299 | Murshidabad Division | Kandi Sub-Division | Restoration work of UPVC pipeline & road restoration work including laying of CI/DI pipeline for smooth supply of drinking water at Panchthuppi Bus Stand area under Panchthuppi Water Supply Scheme under Kandi Sub-Division, P.H.E. Dte.in the District Murshidabad | ASSISTANT ENGINEER |  | ORD/001136/2021-2022 | 320/KSD | 16/11/2021 | 30 | SUPTI ENTERPRISE | 4.83 | 4.82 | 0
1300 | Murshidabad Division | Kandi Sub-Division | Balance estimate for the laying of UPVC distribution pipeline for FHTC work at Muslim Para in the Village of Muniadihi of Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E Dte.in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001189/2021-2022 | 322/KSD | 16/11/2021 | 30 | APURBA SAHA CHOWDHURY | 4.83 | 4.79 | 0
1301 | Murshidabad Division | Kandi Sub-Division | Balance estimate for the laying of UPVC distribution pipeline for FHTC work at Mirjapara & Bagdipara in the Village of Muniadihi of Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E Dte.in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001191/2021-2022 | 324/KSD | 16/11/2021 | 30 | DECON INDIA | 4.84 | 0 | 0
1302 | Murshidabad Division | Kandi Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/001230/2021-2022 | 214/KSD | 11/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.34 | 0 | 0
1303 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of Togra ( 315978 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-II ) TNO- 736/20-21/EE | ASSISTANT ENGINEER |  | VCH/000008/2021-2022 | 04/MSD/21-22 | 16/07/2021 | 0 | SUPTI ENTERPRISE | 7.26 | 0 | 0
1304 | Murshidabad Division | Kandi Sub-Division | Retrofitting functional hoyusehold tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Village MUNIADIHI under PANCHTHUPI Ground Based W/S Scheme for Arsenic Affected area of Burwan Block under MSD PHE DTE. Scheme Id:0007335523 in the dist of Murshidabad. Sl. No.23 Tender no 63 SE/MC 20-21 | ASSISTANT ENGINEER |  | VCH/000038/2021-2022 | 03/MSD/21-22 | 16/07/2021 | 0 | DECON INDIA | 23.9 | 0 | 0
1305 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Accoan of Togra (Village Code 315978) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no-736 of 20-21 by EE / MSD | ASSISTANT ENGINEER |  | VCH/000141/2021-2022 |  | 01/07/2021 | 0 | SUPTI ENTERPRISE | 7.26 | 0 | 0
1306 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with JALSWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village TOGRA (Village Code 315978) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | VCH/000534/2022-2023 | 192-MSD/22-23 | 29/06/2022 | 0 | SUPTI ENTERPRISE (PROP.DEBAPRIYA SAHA) | 3.11 | 0 | 0
1307 | Murshidabad Division | Kandi Sub-Division | Balance estimate for the laying of UPVC distribution pipeline for FHTC work at Chatterjee Para in the Village of Muniadihi of Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E Dte.in the district of Murshidabad. Tender no: 39 of 21-22 by AE KSD | ASSISTANT ENGINEER |  | VCH/001423/2021-2022 | 356-MSD/21-22 | 05/03/2022 | 0 | DECON INDIA | 4.82 | 0 | 0
1308 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MUNIADIHI under PANCHTHUPUI Ground Water Based Water Supply Scheme for arsenic affected areas of BURWAN Block under Murshidabad Div PHE DTE in the District of Murshidabad. Tender no - 63 of 20-21 by SE MC | ASSISTANT ENGINEER |  | VCH/001452/2021-2022 | 355-MSD/21-22 | 07/03/2022 | 0 | DECON INDIA | 15.99 | 0 | 0
1309 | Murshidabad Division | Kandi Sub-Division | Laying of UPVC distribution pipeline for FHTC work at Mirjapara & Bagdipara in the Village of Muniadihi Panchthupi W/S Scheme under KSD PHE DTE. Tender no - 40 of 21-22 by AE KSD | ASSISTANT ENGINEER |  | VCH/001455/2021-2022 | 354-MSD/21-22 | 05/03/2022 | 0 | DECON INDIA | 4.81 | 0 | 0
1310 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Benipur (Village code 314546) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000119/2020-2021 | 191/BD-I | 04/02/2021 | 30 | SRIJON ENTERPRISE | 92.74 | 153.74 | 1
1311 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) of 1579 nos in connection with Jal Swapna (Jal Jeevan Mission ) under Command area of Village of Selalpur, Uttar Ramna, Simla, Dhalo, Kanchanpur, Paikar & Panchanpara ( Village Code -314023,314051,314020,314036,314049,314038,314044) under Raghunathganj-I Surface Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000002/2022-2023 | 895/MURD | 05/04/2022 | 60 | MOTI RAHAMAN | 97.06 | 95.54 | 1
1312 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) of 1190 nos in connection with Jal Swapna (Jal Jeevan Mission ) under Command area of Village of Birthamba, Sendajamuar & Mandalpur ( Village Code -314006, 314007, 314008) under Raghunathganj-I Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. . |  |  | ORD/000108/2022-2023 | 1137/MURD | 02/05/2022 | 60 | PRADIP KUMAR DAS | 64.77 | 60.06 | 0
1313 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mirzapur (Village code 314057) under Surface Water Based water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. |  |  | ORD/000165/2021-2022 | 1580/MURD | 25/06/2021 | 180 | APURBA SAHA CHOWDHURY | 45.85 | 0 | 80
1314 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna Jal Jeevan Mission and Jal Swapna under command area of village of Sujapur(P) ( Village Code -313996) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. Scheme I.D.-0001756489 in the District of Murshidabad. |  |  | ORD/000194/2020-2021 | 958/MURD | 24/03/2021 | 180 | SAMBHU NATH ROY | 46.33 | 9.96 | 0
1315 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna Jal Jeevan Mission and Jal Swapna under command area of village of Dafarpur (C.T.) ( Village Code -314055) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. Scheme I.D.-0001756489 in the District of Murshidabad. |  |  | ORD/000195/2020-2021 | 959/MURD | 24/03/2021 | 180 | SAMBHU NATH ROY | 107.46 | 35.72 | 0
1316 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Rajnagar (Village code 314041) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. |  |  | ORD/000254/2021-2022 | 1653/MURD | 29/06/2021 | 90 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 45.88 | 0 | 80
1317 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Siddhikhali (Village Code 314021) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | ORD/000259/2020-2021 | 2395/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.73 | 3.26 | 0
1318 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Talai(Village code 314018) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-7) |  |  | ORD/000304/2020-2021 | 3118/MURD | 09/12/2020 | 180 | DECON INDIA | 55.72 | 17.95 | 1
1319 | Murshidabad Division |  | Allied work of pipeline and Platform at DEULI village under Raghunathganj Surface Based Water Supply Scheme for HGJ of Jangipur Sub-Division under Murshidabad Division, PHE Dte. |  |  | ORD/000476/2023-2024 | 3033/MURD | 27/09/2023 | 30 | SAMBHU NATH ROY | 6.17 | 6.17 | 100
1320 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jarur(Village code 314011) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-8) |  |  | ORD/000497/2020-2021 | 3066/MURD | 08/12/2020 | 180 | NOVELTY CONSTRUCTION | 54.9 | 9.98 | 1
1321 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village of Jethia( Village Code-314030)under Surface Water Based Water Supply Scheme form Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | ORD/000554/2020-2021 | 2527/MURD | 30/09/2020 | 45 | DEBASIS BOSE | 34.11 | 7.1 | 100
1322 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission) " from existing Distribution system within the Command area of village BAIDPUR (Village Code 314026) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | ORD/000576/2020-2021 | 2553/MURD | 01/10/2020 | 45 | S. DUTTA | 13.25 | 0 | 0
1323 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission ) "from existing Distribution system within the Command area of village JAGADANANDABATI(Village Code 314028) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad . |  |  | ORD/000620/2020-2021 | 2559 /MURD | 01/10/2020 | 45 | SUDIPA SINGHA ROY | 16.27 | 14.4 | 0
1324 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Siddhikhali(Village Code 314021) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | ORD/000630/2020-2021 | 2395/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.73 | 8.43 | 1
1325 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jarur(Village code 314011) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-8) |  |  | ORD/000649/2020-2021 | 3066 / MURD | 08/12/2020 | 180 | NOVELTY CONSTRUCTION | 54.9 | 0 | 1
1326 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village GANKAR (Village Code 314037) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | ORD/000667/2020-2021 | 2561/MURD | 01/10/2020 | 45 | DECON INDIA | 41.51 | 37.3 | 1
1327 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Natun(Village code 314043) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-5) |  |  | ORD/000669/2020-2021 | 3056/MURD | 08/12/2020 | 180 | AJAY MONDAL | 46.31 | 0 | 1
1328 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village BIJOYPUR (Village Code 314032) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | ORD/000716/2020-2021 | 2562/MURD | 01/10/2020 | 45 | SAMBHU NATH ROY | 19.69 | 15.96 | 0
1329 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Deuli(Village code 313998) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-11) |  |  | ORD/000718/2020-2021 | 3065/MURD | 08/12/2020 | 180 | SANJAY BISWAS | 57.02 | 0 | 1
1330 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission ) "from existing Distribution system within the Command area of village KULRI (Village Code 314022) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad . |  |  | ORD/000728/2020-2021 | 2554/MURD | 01/10/2020 | 45 | JAMIRUL CONSTRUCTION | 14.17 | 6.11 | 0
1331 | Murshidabad Division |  | Road Restoration work because of damaging due to laying of different dia UPVC pipe line in connection with FHTC Work at Khidirpur (Village code- 313993) under Surface water based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Jangipur Sub-Division under Murshidabad Division, P.H.E Dte in the district of Murshidabad. |  |  | ORD/000734/2023-2024 | 19/MURD | 03/01/2024 | 30 | M/S. SABANA CONSTRUCTION (PROP:MD. SAIDUR RAHAMAN) | 3.78 | 0 | 0
1332 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village BAINDA (Village Code 314003) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad |  |  | ORD/000741/2020-2021 | 2552/MURD | 01/10/2020 | 45 | SAMBHU NATH ROY | 21.88 | 9.57 | 0
1333 | Murshidabad Division |  | Work of Extension of Existing Boundary wall along with painting work at Jotkamal (Zone-I) water supply scheme , under Raghunathganj-II Block, under Jangipur Sub-Division, P.H.E. Dte in the District Murshidabad. |  |  | ORD/001264/2021-2022 | 383/JSD | 31/12/2021 | 30 | MOLLA ENTERPRISE | 4.83 | 4.68 | 1
1334 | Murshidabad Division |  | Laying of 250 mm D.I Pipe for clear water rising main by Open-Cut method from Umarpur more (Chainage 0.00 KM) to Mitrapur (Chainage 7.50 KM) along right hand flank of bituminous road,PWD for Raghunathganj Surface Water Based Water Supply Scheme (Raghunathganj-I Block) of Jangipur Sub-Division under Murshidabad Division, P.H.Engineering Dte. |  |  | ORD/001595/2021-2022 | 397/MURD | 16/02/2022 | 45 | SANJAY BISWAS | 31.87 | 20.28 | 100
1335 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000028/2021-2022 | 540/1/MURD | 25/02/2022 | 0 | Resource Division | 15.28 | 0 | 0
1336 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of KANKARIA VILLAGE OF Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I), TNO- 761/2020-21/EE |  |  | VCH/000005/2021-2022 | 01/MSD/21-22 | 15/07/2021 | 0 | MAMATA USHA ENTERPRISE | 20.68 | 0 | 0
1337 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of VILLAGE SANTOSHPUR UNDER Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District, TNO- 502/20-21/EE |  |  | VCH/000007/2021-2022 | 06/MSD/21-22 | 16/07/2021 | 0 | MODERN CONSTRUCTION | 10.59 | 0 | 0
1338 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village NATUN (Village Code 314043) and adjoining habitation under Raghunathganj-I Surface Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the District of Murshidabad. Tender no - 56 of 21-22 by SE MC |  |  | VCH/000033/2022-2023 | 34-MSD/22-23 | 14/04/2022 | 0 | AJOY MONDAL | 37.08 | 0 | 0
1339 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village SANTOSHPUR (Village Code 314045) under surface Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the District of Murshidabad. Tender no - 502 of 20-21 by EE MURD |  |  | VCH/000034/2022-2023 | 32-MSD/21-22 | 21/04/2022 | 0 | MODERN CONSTRUCTION | 2.37 | 0 | 0
1340 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION )' from existing Distribution system within the Command area of village SONATIKRI ( Village Code -313995) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | VCH/000056/2022-2023 | 72-MSD/22-23 | 26/04/2022 | 0 | J.S. CONSTRUCTION | 27.59 | 0 | 0
1341 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village JARUR (Village Code 314011) under Surface Based Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the District of Murshidabad. Tender no - 47 of 20-21 by SE MC (NEW) |  |  | VCH/000095/2022-2023 | 36-MSD/22-23 | 23/04/2022 | 0 | NOVELTY CONSTRUCTION | 5.22 | 0 | 0
1342 | Murshidabad Division |  | Laying of 200 mm dia MS Water Carring pipe with 600 mm dia MS PIPE as casing at chainge Raghunathganj Surface Water Based W/S Scheme block Raghunathganj-I Block under MSD PHE DTE. Tender no - 930 of 20-21 by EE MURD |  |  | VCH/000096/2022-2023 | 37-MSD/22-23 | 14/04/2022 | 0 | SAMBHU NATH ROY | 24.74 | 0 | 0
1343 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village Ramakantapur (Village Code- 314029) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 65 of 20-21 by SE / MC |  |  | VCH/000200/2021-2022 | 08 -MSD / 21-22 | 06/08/2021 | 0 | MS SINHA AND SONS | 39.66 | 0 | 0
1344 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) from existing distribution system within the command area of village JEETHIA (Village Code: 314030) under surface Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 488 of 20-21 by EE / MSD |  |  | VCH/000220/2021-2022 | 21-MSD / 21-22 | 13/08/2021 | 0 | DEBASIS BOSE | 15.79 | 0 | 0
1345 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village DAFARPUR (Village Code: 314055) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 113 of 20-21 by SE / MC |  |  | VCH/000221/2021-2022 | 23-MSD / 21-22 | 11/08/2021 | 0 | SAMBHU NATH ROY | 23.13 | 0 | 0
1346 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village SUJAPUR (Village Code: 313996) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 114 of 20-21 by SE / MC |  |  | VCH/000222/2021-2022 | 22-MSD / 21-22 | 11/08/2021 | 0 | SAMBHU NATH ROY | 13.29 | 0 | 0
1347 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village JARUR (Village Code: 314011) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 47 of 20-21 by SE / MC |  |  | VCH/000225/2021-2022 | 19-MSD / 21-22 | 06/08/2021 | 0 | NOVELTY CONSTRUCTION | 39.68 | 0 | 0
1348 | Murshidabad Division |  | Holding Awarness programme / Campaigning programs at Chandpur GP Radharghar I & II GP Ramnagar Bachhara GP Somprra =I GP Doulabad GP & Chhaighari GP connection with functional household tap connection FHTC under MSD PHE DTE. Tenter no 154 of 21-22 by EE |  |  | VCH/000239/2021-2022 | 33-MSD/21-22 | 23/08/2021 | 0 | IMAGIN COMMUNICATION | 3.17 | 0 | 0
1349 | Murshidabad Division |  | Holding Awarness programme / Campaigning programs at Nowda GP, Roypur GP, Madhupur GP, Sarbangpur GP, Choa GP, Hariharpara GP, Mahula GP & Rangamati Chandpara GP connection with functional household tap connection FHTC under MSD PHE DTE. Tenter no 153 of 21-22 by EE |  |  | VCH/000240/2021-2022 | 32-MSD/21-22 | 23/08/2021 | 0 | S.S.INFRASTRUCTURE | 3.18 | 0 | 0
1350 | Murshidabad Division |  | Holding Awarness Progmramme /Campaigning programms at Chandpur-I , II GP, Bali GP, Patikabari GP, Madhupur GP, Kedar Chandpur GP, Khidirpur GP, Humaipur GP, Rampara-I GP, Andulberia GP, Dadpur GP Rampara-II GP Mirjapur GP Kumarpur Sujapur GP in connection with Functional Household Tap Connection FHTC under MSD PHE DTE. Tender no 155 of 21-22 by EE |  |  | VCH/000241/2021-2022 | 34-MSD/21-22 | 23/08/2021 | 0 | IMAGIN | 4.77 | 0 | 0
1351 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Talai (Village code 314018) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. Tender no - 57 of SE/MC OF 20-21 |  |  | VCH/000269/2021-2022 | 54-MSD/21-22 | 14/09/2021 | 0 | DECON INDIA | 26.12 | 0 | 0
1352 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of SEKENDRA (Village code 314064) under SEKENDRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184141 |  |  | VCH/000292/2022-2023 | 91-MSD/22-23 | 02/05/2022 | 0 | DOBAY CONSTRUCTION | 54.19 | 0 | 0
1353 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with Jal Swapna (Jal Jeevan Mission) from existing Distribution system within the command area of village AMGACHHI (Village Code -314031) under surface Water Based Water Supply Scheme for Arsenic Affected Areas of RAGHUNATHGANJ-I Block in the Dist of MSD under Murshidabad Division P.H.E Dte. |  |  | VCH/000371/2021-2022 | 57-MSD/21-22 | 14/09/2021 | 0 | M/S. GHOSH ENTERPRISE | 4.47 | 0 | 0
1354 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna Jal Jeevan Mission and Jal Swapna under command area of village of Sujapur(P) ( Village Code -313996) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. Scheme I.D.-0001756489 in the District of Murshidabad. |  |  | VCH/000435/2022-2023 | 162-MSD/22-23 | 17/05/2022 | 0 | SAMBHU NATH ROY | 20.19 | 0 | 0
1355 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna OF DEULI VILLAGE (313998)(JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District. TNO- |  |  | VCH/000574/2021-2022 | 136-MSD/21-22 | 07/10/2021 | 0 | SANJAY BISWAS | 41.68 | 0 | 0
1356 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) RAMAKANTAPUR VILLAGE CODE 314029 of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I), TNO- 65/20-21/SE-MC |  |  | VCH/000651/2021-2022 | 125-MSD/21-22 | 07/10/2021 | 0 | M/S. SINHA & SONS | 17.47 | 0 | 0
1357 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) VILALGE NAIT BAIDHARA CODE-314004 of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I), TNO- 53/20-21/EE |  |  | VCH/000652/2021-2022 | 126-MSD/21-22 | 11/10/2021 | 0 | SANJAY BISWAS | 17.94 | 0 | 0
1358 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION )' from existing Distribution system within the Command area of village SONATIKRI ( Village Code -313995) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. 2566/MURD, 01/10/2020 |  |  | VCH/000672/2021-2022 | 175-MSD/21-22 | 02/11/2021 | 0 | J.S. CONSTRUCTION | 16.47 | 0 | 0
1359 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) VILLAGE CODE- 314009, TNO- 75/20-21/SE-MC |  |  | VCH/000777/2021-2022 | 194-MSD/21-22 | 18/11/2021 | 0 | M/S UNIVERSAL TRADING | 41.08 | 0 | 0
1360 | Murshidabad Division |  | Deposit of way leave charges for-Way leave permission for crossing of 200 mm dia water pipeline raising main through 600 mm dia MS Casing pipe under Railway track between stations Ahiron Halt & Jangipur Road at km. 216/9-217/0 under Malda Division of Eastern Railway, Way leave permission for crossing of 200 mm dia water pipeline raising main through 600 mm dia MS Casing pipe under Railway track between stations Ahiron Halt & Jangipur Road at km. 212/0-1 under Malda Division of Eastern Railway, Way leave permission for crossing of 150 mm dia water pipeline raising main through 600 mm dia MS Casing pipe under Railway track between stations Ahiron Halt & Jangipur Road at km. 210/9-211/0 under Malda Division of Eastern Railway and Way leave permission for crossing of 100 mm dia water pipeline raising main through 600 mm dia MS Casing pipe under Railway track between station Ahiron Halt & Jangipur Road at km. 204/2-3 under Malda Division of Eastern Rail. REF:MEMO NO-1050/MURD, DT- 05/04/21. |  |  | VCH/000833/2022-2023 | 292-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 32.2 | 0 | 0
1361 | Murshidabad Division |  | CONT OF AWARENESS PROGRAMME AT DIFFERENT G.PS, TNO- 57/21-22/EE |  |  | VCH/000868/2021-2022 | 205-MSD/21-22 | 08/12/2021 | 0 | IMAGIN | 3.98 | 0 | 0
1362 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of RAMNAGAR VILLAGE CODE 314056 Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District |  |  | VCH/000869/2021-2022 | 207-MSD/21-22 | 08/12/2021 | 0 | TRIDIP MAZUMDER | 25.05 | 0 | 0
1363 | Murshidabad Division |  | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. WORK ORDER NO & DT. - 223 / HQ DATE- 26/05/2022 |  |  | VCH/000967/2022-2023 | 325-MSD/22-23 | 30/09/2022 | 0 | DULAL CHOWDHURY | 0.78 | 0 | 0
1364 | Murshidabad Division |  | Continuation work order for Hiring of one no. Bolero Car/Marshal (CAR 57- 9120) Same category for official use of the Assistant Engineer, JSD, P.H.Engineering Dte. Berhampore, Murshidabad. WORK ORDER NO & DT. - 88 / JSD DATE- 22/02/2022. |  |  | VCH/000968/2022-2023 | 334-MSD/22-23 | 30/09/2022 | 0 | MANUAR HOSSAIN | 0.4 | 0 | 0
1365 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) |  |  | VCH/001289/2021-2022 |  | 17/02/2022 | 0 | S. DUTTA | 13.24 | 0 | 0
1366 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with 'Jal Swapna (Jal Jeevan Mission ) 'from existing Distribution system within the Command area of village BARALA (Village Code 314009) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. Tender no - 75 of 20-21 by SE MC |  |  | VCH/001379/2021-2022 | 330-MSD/21-22 | 25/02/2022 | 0 | M/S UNIVERSAL TRADING | 7.36 | 0 | 0
1367 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission) " from existing Distribution system within the Command area of village BAIDPUR (Village Code 314026) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. Tender no - 501 of 20-21 by EE MURD |  |  | VCH/001394/2021-2022 | 325-MSD/21-22 | 22/02/2022 | 0 | S. DUTTA | 13.24 | 0 | 0
1368 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with 'JAL SWAPNA(JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of Khidirpur(Village Code 313993) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | VCH/001395/2021-2022 | 326-MSD/21-22 | 24/02/2022 | 0 | M/S. SABANA CONSTRUCTION (PROP:MD. SAIDUR RAHAMAN) | 30.82 | 0 | 0
1369 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village NISTA (Village Code 314017) under Surface Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the District of Murshidabad. Tender no - 619 of 21-22 by EE MURD |  |  | VCH/001396/2021-2022 | 328-MSD/21-22 | 25/02/2022 | 0 | M/S. S. DAS AND ENTERPRISE | 15.54 | 0 | 0
1370 | Murshidabad Division |  | PAYMENT OF FEES OF ONLINE APPLICATION OF RAIL CROSSING PROCESS. |  |  | VCH/001462/2021-2022 | 363-MSD/21-22 | 11/03/2022 | 0 | FA & CAO EASTERN RAILWAY | 2.02 | 0 | 0
1371 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna Jal Jeevan Mission and Jal Swapna under command area of village of Dafarpur (C.T.) ( Village Code -314055) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. Scheme I.D.-0001756489 in the District of Murshidabad. |  |  | VCH/001474/2021-2022 | 383-MSD/21-22 | 17/03/2022 | 0 | SAMBHU NATH ROY | 59.53 | 0 | 0
1372 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village CHAR DAFARPUR (Village Code 314047) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block in the District of Murshidabad. Tender no - 497 of 20-21 by EE MURD |  |  | VCH/001511/2021-2022 | 409-MSD/21-22 | 23/03/2022 | 0 | GOUTAM CHAKRABORTY | 36.1 | 0 | 0
1373 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Bhagirathpur (Village Code -314699) under Bhagirathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000642/2022-2023 | 3342/MURD | 15/12/2022 | 30 | PROSENJIT DAS | 34.64 | 0 | 0
1374 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work) in connection with the Functional Household Connection of different existing PWSS (Momenpur PWSS Scheme,Block- Domkal)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 376 of 21-22 by EE MSD, and Scheme Code: 8272 |  |  | VCH/000035/2022-2023 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.88 | 0 | 0
1375 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna Mission under command area of village of BHAGIRATHPUR (VILLAGE CODE 314699) under BHAGIRATHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 105 of 20-21 by SE / MC |  |  | VCH/000219/2021-2022 | 20-MSD / 21-22 | 06/08/2021 | 0 | PROJECT INDIA | 47.31 | 0 | 0
1376 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BHAGIRATHPUR (Village Code 314699) under BHAGIRATHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 105 of 20-21 by SE MC |  |  | VCH/001458/2021-2022 | 358-MSD/21-22 | 09/03/2022 | 0 | PROJECT INDIA | 56.97 | 0 | 0
1377 | Murshidabad Division |  | SHIFTING OF HT OVERHEAD LINE BR ERECTION XLPE UG CABLE AT GHANSHYAM CHAK PUMP HOUSE NO-I, ZONE-II |  |  | BILL/00507/2022-2023 | 588-MSD/22-23 | 06/03/2023 | 0 | WBSEDCL | 3.92 | 0 | 0
1378 | Murshidabad Division |  | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block (Giria,Sekendra, Mithipur,Jotkamal,Dayarampur & Sammatinagar ) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte.(PART-A) |  |  | ORD/000066/2021-2022 | 122 /JSD | 22/05/2021 | 30 | S.S.INFRASTRUCTURE | 2.38 | 2.38 | 1
1379 | Murshidabad Division |  | Formal work order for Laying Distribution System ,FHTC, Construction of 1 (one) no Pump House (4.25m x 3.60m with sanitary and Water Supply Arrangement), Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement and 2(two) nos Pump House repairing. Repairing of Existing OHR Part for Augmentation of SEKENDRA PWSS in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE. Dte. |  |  | ORD/000758/2022-2023 | 445/MURD | 17/02/2023 | 846 | NAYLA CONSTRUCTION | 255.21 | 16.08 | 90
1380 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS SEKENDRA PWSS Scheme, Block-RAGHUNATHGAUNGE-II to be Augmention/Rejuvination under Murshidabad Division, P.H.E. Dte. |  |  | ORD/001139/2021-2022 | 3256/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 6.68 | 13.36 | 1
1381 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of SEKENDRA (Village code 314064) under SEKENDRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184141 |  |  | ORD/001188/2021-2022 | 3977/MURD | 21/12/2021 | 180 | DOBAY CONSTRUCTION | 159.44 | 80.23 | 1
1382 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000040/2021-2022 | 540/13/MURD | 25/02/2022 | 0 | Resource Division | 21.96 | 0 | 0
1383 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL- 05 |  |  | VCH/000755/2022-2023 | 309-MSD/22-23 | 29/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 13.05 | 0 | 0
1384 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) 720 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Alampur ( Village Code -313932) under Ghorapakhiagangin Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000033/2022-2023 | 1054/MURD | 25/04/2022 | 30 | PROSENJIT DAS | 34.86 | 32.33 | 0
1385 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000032/2021-2022 | 540/5/MURD | 25/02/2022 | 0 | Resource Division | 3.95 | 0 | 0
1386 | Murshidabad Division | Berhampur Sub-Division | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000055/2022-2023 | 160/BSD | 12/04/2022 | 15 | BARMAN ENTERPRISE | 4.84 | 4.84 | 0
1387 | Murshidabad Division | Berhampur Sub-Division | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000057/2022-2023 | 162BSD | 12/04/2022 | 15 | A.S. MONDAL ENTERPRISE | 4.84 | 4.84 | 0
1388 | Murshidabad Division | Berhampur Sub-Division | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-II | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000063/2022-2023 | 168/BSD | 12/04/2022 | 15 | SOUVIK HALDER | 4.86 | 4.86 | 0
1389 | Murshidabad Division | Berhampur Sub-Division | Laying of 140mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000064/2022-2023 | 169/BSD | 12/04/2022 | 15 | M/S.S.S. ENTERPRISE | 4.84 | 0 | 0
1390 | Murshidabad Division | Berhampur Sub-Division | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-I | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000065/2022-2023 | 170/BSD | 12/04/2022 | 15 | SOUNAK ENTERPRISE | 4.85 | 0 | 0
1391 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Raypur, Kanapara, Sakua, Madhupur (Village code 315531, 315541, 315542, 315532) under Surangapur Ground Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0005182885) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001339/2021-2022 | 479/MURD | 22/02/2022 | 1348 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 398.73 | 30.22 | 30
1392 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000001/2022-2023 | 889/A/MURD | 05/04/2022 | 0 | Resource Division | 58.9 | 0 | 0
1393 | Murshidabad Division | Berhampur Sub-Division | LAYING OF 140MM DIA FHTC ........ RAYPUR UNDER SURANGAPUR W/S SCHEME UNDER MSD PHE DTE. TENDER NO 213 OF 21-22 | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/000317/2022-2023 | 177-MSD/22-23 | 17/05/2022 | 0 | M/S SS ENTERPRISE (SUKESH GHOSH) | 4.84 | 0 | 0
1394 | Murshidabad Division |  | Laying of UPVC pipeline for allied works of retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Jeevan mission and Jal Swapna under command area of village of BHANDARA(village code- 314524) under Bhandara Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola-I & II Block under Murshidabad Division ,PHE Dte. in the district of Murshidabad.(Schemre ID- 0005104709) |  |  | ORD/000143/2022-2023 | 1240/MURD | 11/05/2022 | 30 | DEBASIS BOSE | 9.86 | 7.62 | 0
1395 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bhandara(Village code 314524) under Bhandara Ground Water Based water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl No-07) |  |  | ORD/000549/2020-2021 | 3047/MURD | 07/12/2020 | 180 | DEBASIS BOSE | 57.23 | 26.71 | 0
1396 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Palasi Sonadanga(Village code 314527) under Bhandara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division,PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl No-06) |  |  | ORD/000650/2020-2021 | 3131/MURD | 10/12/2020 | 180 | M/S. SINHA & SONS | 46.65 | 40.79 | 0
1397 | Murshidabad Division |  | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  |  | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1398 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at HUMAIPUR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000501/2021-2022 | 336/BSD | 27/08/2021 | 30 | IMAGIN COMMUNICATION | 4.16 | 4.16 | 0
1399 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Basabari (Village code 315340) under Basabari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723194 in the District of Murshidabad. |  |  | ORD/001156/2021-2022 | 2643 /MURD | 27/08/2021 | 60 | AZAD ENTERPRISE | 21.66 | 20.16 | 0
1400 | Murshidabad Division |  | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. for Augmentation of Ground Water Based Malibari PWSS under Murshidabad Division, PHE Dte. |  |  | ORD/001720/2021-2022 | 154/ISD | 17/03/2022 | 30 | MABCO GEOTEST ASSOCIATES | 1.48 | 1.48 | 1
1401 | Murshidabad Division | Berhampur Sub-Division | Edrakpur & Adjoining Mouzas Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nowda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000014/2023-2024 | 982/MURD | 10/04/2023 | 1124 | SANJAY BISWAS | 643.42 | 219.18 | 85
1402 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 100 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for EDRAKPUR Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000027/2025-2026 | 1021/MURD | 05/05/2025 | 60 | SANJAY BISWAS | 40.44 | 0 | 0
1403 | Murshidabad Division | Berhampur Sub-Division | Construction Pump House with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) and 55 mtr. Boundary wall at 3rd Tubewell site of Gangadhari & Edrakpur Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000102/2024-2025 | 2152/MURD | 29/07/2024 | 480 | PARUL ELECTRICAL INSTALLER | 16.6 | 0 | 80
1404 | Murshidabad Division | Berhampur Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000498/2024-2025 | 663/MURD | 19/03/2025 | 65 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0
1405 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Edrakpur Water Supply Scheme of TW-I at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000583/2022-2023 | 3067/MURD | 17/11/2022 | 30 | M/S B.R. SUPPLIERS | 10.6 | 9.98 | 100
1406 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Edrakpur PWSS Scheme, Block - Nowda) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000842/2021-2022 | 3275/MURD | 05/10/2021 | 60 | RADIANT | 6.22 | 6.22 | 1
1407 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000184/2023-2024 | 1210/MURD/01 | 02/05/2023 | 0 | Resource Division | 11.39 | 0 | 0
1408 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000349/2023-2024 | 112/MURD/06 | 11/01/2024 | 0 | Resource Division | 26.32 | 0 | 0
1409 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000354/2023-2024 | 305/MURD/3 | 29/01/2024 | 0 | Resource Division | 9.58 | 0 | 0
1410 | Berhampore Mechanical | Berhampur Sub-Division | NEW CONNECTION EDRAKPU PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01625/2023-2024 | 471/WBSEDCL-JJM | 20/03/2024 | 0 | WBSEDCL | 20.76 | 0 | 0
1411 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Edrakpur ground water based water supply scheme under Block- Nowda, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000087/2023-2024 | 1887/MEDB | 16/06/2023 | 92 | SRI KRISHNA NIRMAN | 11.66 | 7.45 | 50
1412 | Murshidabad Division | Berhampur Sub-Division | Construction Pump House with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) and 55 mtr. Boundary wall at 3rd Tubewell site of Gangadhari & Edrakpur Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000102/2024-2025 | 2152/MURD | 29/07/2024 | 480 | PARUL ELECTRICAL INSTALLER | 16.6 | 0 | 80
1413 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) of 1786 nos in connection with (Jal Jeevan Mission ) and under command area of village of Gangadhari ( Village Code -315534) under Gangadhari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000134/2022-2023 | 1232/MURD | 11/05/2022 | 60 | PRADIP KUMAR DAS | 78.92 | 19.76 | 0
1414 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Augmentation of laying Rising main & Distribution System of GANGADHARI Water Supply Scheme under Berhampore Sub-Division, Murshidabad Division, P.H.Engg Dte. In the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000172/2022-2023 | 1303/MURD | 20/05/2022 | 120 | PRADIP KUMAR DAS | 300.61 | 299.96 | 0
1415 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gangadhari Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000595/2022-2023 | 3069/MURD | 17/11/2022 | 30 | A.M. ENTERPRISE | 10.6 | 9.39 | 100
1416 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (GANGADHARI PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000843/2021-2022 | 3276/MURD | 05/10/2021 | 60 | RADIANT | 3.51 | 3.51 | 1
1417 | Murshidabad Division | Berhampur Sub-Division | Construction of 200 Cum OHR, Boundary Wall, Pump House for Augmentation of GANGADHARI PWSS in NAWDA Block, Berhampore Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000850/2023-2024 | 825/MURD | 15/03/2024 | 566 | SOM CONSTRUCTION AGENCY | 93.75 | 0 | 25
1418 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000386/2023-2024 | MURD/514 | 16/02/2024 | 0 | Resource Division | 21.35 | 0 | 0
1419 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Gangadhari ground water based water supply scheme under Block- Nowda, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000571/2024-2025 | 400/MEDB | 12/02/2025 | 89 | M/S. T.K. BASU RAY | 12.18 | 0 | 70
1420 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of Jalangi Zone-IV Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000339/2022-2023 | 1807/MURD | 11/07/2022 | 993 | H.I.ENTERPRISE | 351.37 | 180.59 | 95
1421 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-IV Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000589/2022-2023 | 3058/MURD | 17/11/2022 | 45 | NADIA TUBEWELLS | 23.55 | 17.06 | 1
1422 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000023/2022-2023 | 2507/E/MURD | 31/08/2022 | 0 | Resource Division | 12.41 | 0 | 0
1423 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000026/2024-2025 | MURD/2482 | 04/09/2024 | 0 | Resource Division | 14.2 | 0 | 0
1424 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000041/2022-2023 | 2780/J/MURD | 01/10/2022 | 0 | Resource Division | 14.2 | 0 | 0
1425 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000166/2023-2024 | 1180/MURD/12 | 29/04/2023 | 0 | Resource Division | 11.14 | 0 | 0
1426 | Berhampore Mechanical | Berhampur M/E Division | New connection charge for Jalangi W/S Scheme (Part-B) Zone-IV, P/H No.-I. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/00277/2023-2024 |  | 04/08/2023 | 0 | WBSEDCL | 0.87 | 0 | 0
1427 | Berhampore Mechanical | Berhampur M/E Division | new service connection at Arji Muradpur ID304173525 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01184/2023-2024 | 246/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 4.3 | 0 | 0
1428 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT ZONE 4 MOUZA MURADPUR JL NO 30 PLOT NO LR 748,749 MURSHIDABAD ID 304240386 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01274/2023-2024 | 296/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 12.21 | 0 | 0
1429 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of JALANGI , Zone- IV ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000831/2023-2024 | 3772/MEDB | 03/11/2023 | 605 | QUAZI NOZRUL ISLAM | 23.34 | 0 | 60
1430 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of BHAGIRATHPUR Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000335/2022-2023 | 1722/MURD | 04/07/2022 | 365 | M/S BHUBAN DAS | 331.21 | 266.5 | 65
1431 | Murshidabad Division | Berhampur M/E Division | Augmentation of BHANDARA (ZONE - II A) & Augmentation of BHAGIRATHPUR PWSS under Jal Jeevan Mission of Bhagawangola-I & Domkal Block, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000623/2023-2024 | 3372/MURD | 31/10/2023 | 270 | MAMATA USHA ENTERPRISE | 902.27 | 0 | 0
1432 | Murshidabad Division | Berhampur M/E Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 1.95 | 80
1433 | Murshidabad Division | Berhampur M/E Division | Sinking of replacement tube well of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhagirathpur Water Supply Scheme of TW-I, P.H-1 under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000953/2021-2022 | 3591/MURD | 17/11/2021 | 15 | A ONE ENTERPRISE | 8.39 | 7.2 | 1
1434 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000017/2022-2023 | 1236/MURD | 11/05/2022 | 0 | Resource Division | 46.42 | 0 | 0
1435 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000019/2022-2023 | 2507/A/MURD | 31/08/2022 | 0 | Resource Division | 11.3 | 0 | 0
1436 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000029/2022-2023 | 2508/A/MURD | 31/08/2022 | 0 | Resource Division | 1.45 | 0 | 0
1437 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000040/2024-2025 | MURD/2481/12 | 04/09/2024 | 0 | Resource Division | 19.48 | 0 | 0
1438 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000167/2023-2024 | 1180/MURD/13 | 29/04/2023 | 0 | Resource Division | 16.75 | 0 | 0
1439 | Berhampore Mechanical | Berhampur M/E Division | SHIFTING OF 11KV HT OH LINE AT BHAGIRATHPUR | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | BILL/00528/2024-2025 | 167/WBSEDCL-JJM | 29/07/2024 | 0 | WBSEDCL | 3.79 | 0 | 0
1440 | Berhampore Mechanical | Berhampur M/E Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No._I under Bhagirathpur ground water based water supply scheme under Block_ Domkal Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | ORD/001490/2023-2024 | 770/MEDB | 20/02/2024 | 90 | ANUPAMA ENGINEERING WORKS | 11.06 | 0 | 0
1441 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at The Village Of Pukhuria (Code-314547) In The Command Area Of Benipur Ground Water Supply Scheme (Part-B) Under Bhagwangola-II Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000103/2024-2025 | 1437/BD-I | 04/09/2024 | 30 | M/S ROY & BOSE ENTERPRISE | 17.87 | 0 | 0
1442 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pukhuria (Village code 314547) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000120/2020-2021 | 192/BD-I | 04/02/2021 | 30 | M/S S.S ENTERPRISE | 71.4 | 44.98 | 1
1443 | Berhampore Division I | Berhampur Division I | Commissioning of Moktarpur ground water based Pipe water Supply scheme under Jal Swapna at NAWDA Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000044/2023-2024 | 117/BD-I | 10/05/2023 | 966 | M/S GOUTAM CHAKRABORTY | 233.73 | 0 | 75
1444 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000104/2023-2024 | 201/BD-1/3 | 10/02/2024 | 0 | Resource Division | 2.51 | 0 | 0
1445 | Murshidabad Division | Berhampur M/E Division | Providing FHTCs 2500 nos household, Construction of 300 Cum OHR , Repairing & Renovation of R.C.C. elevated reservoir 450 Cum capacity of staging hight 20 mtr., Construction of Boundary Wall 50 mtr, Construction of RCC approach road of 50 mtr & Road Restoration due to laying of pipeline ,Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works ,Repair of Boundary Wall for Augmentation work of Kankuria Jafrabad (Zone-I) PWSS in Samsherganj Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000025/2024-2025 | 1815/MURD | 20/06/2024 | 502 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 295.71 | 0 | 30
1446 | Murshidabad Division | Berhampur M/E Division | Laying of pipeline at Babupur village adjacent to OHR of Kankuria Jafrabad Water Supply Scheme under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000170/2023-2024 | 1974/MURD | 20/07/2023 | 30 | JOY BISHNU ENGINEERING CO. | 2.07 | 0 | 100
1447 | Murshidabad Division | Berhampur M/E Division | Renovation of Filter Media of Existing IEP of (Capacity 45 Cum/hr.) at Kankuria Jafrabad Water Supply Scheme under Murshidabad Division , PHE engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000247/2024-2025 | 230/MURD | 27/01/2025 | 30 | M/S.DAS ENTERPRISE | 16.84 | 0 | 0
1448 | Murshidabad Division | Berhampur M/E Division | Boundary wall at 2-nd Tube Well Site of Kankuria Jafrabad Water supply Scheme under Jangipur Sub-Division, P.H.Engg. Dte. in the District of Murshidabad.Length of Boundary Wall- 96 Mtr. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000501/2020-2021 | 663/MURD | 19/02/2021 | 45 | HARUN ALL RASHID & BROTHERS | 4.49 | 4.62 | 0
1449 | Murshidabad Division | Berhampur M/E Division | Supply of UPVC pipe and RDS filter for the work of Sinking of (300 mm x 200 mm ) dia Big Dia tube well at Village Kankuria(Village Code:-313873) in connection with FHTC work of Kankuria Jafrabad Water SupplyScheme(Scheme Id:0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000530/2022-2023 | 240/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.6 | 2.62 | 1
1450 | Murshidabad Division | Berhampur M/E Division | Supply of (300 mm x 200 mm ) dia Big Dia tube well 75 mtr. Deep by direct rotary rig method using UPVC pipe and RDS filter at Village Kankuria(Village Code:-313873) in connection with FHTC work of Kankuria Jafrabad Water Supply Scheme(SchemeId:0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000531/2022-2023 | 239/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.42 | 4.01 | 1
1451 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JADABPUR NIMTALA and KANKURIA JAFRABAD ZONE- I Water Supply Scheme as required at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000705/2023-2024 | 3813/MURD | 12/12/2023 | 21 | HARUN ALL RASHID & BROTHERS | 11.77 | 0 | 100
1452 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying Distribution System and Rising Main Connection For Augmentation of Kankuria Jafrabad (Zone-I) PWSS of Samserganj Block in Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000832/2022-2023 | 719/MURD | 14/03/2023 | 120 | TARIKUL SK | 157.47 | 33.41 | 40
1453 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000039/2024-2025 | MURD/2481/11 | 04/09/2024 | 0 | Resource Division | 57.32 | 0 | 0
1454 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000077/2022-2023 | 1295/MURD/01 | 11/05/2023 | 0 | Resource Division | 11.5 | 0 | 0
1455 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
1456 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (Three) Nos of 300mm x 200 mm dia tubewell i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen(RDS) filter at SURANGAPUR PWSS (ZONE- II ) PART-B Water Supply Scheme at Head Work Site at Nawda Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000112/2023-2024 | 1754/MURD | 06/07/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 11.79 | 10.78 | 100
1457 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Augmentation of SURANGAPUR Zone-II / Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000527/2022-2023 | 2493/MURD | 30/08/2022 | 365 | SUJIT KUMAR SAHA | 203.27 | 137.54 | 85
1458 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (SURANGAPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000841/2021-2022 | 3274/MURD | 05/10/2021 | 60 | RADIANT | 15.07 | 5.02 | 1
1459 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000296/2023-2024 | 1278/MURD/9 | 10/05/2023 | 0 | Resource Division | 68.77 | 0 | 0
1460 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000348/2023-2024 | 112/MURD/05 | 11/01/2024 | 0 | Resource Division | 38.22 | 0 | 0
1461 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000352/2023-2024 | 305/MURD/01 | 29/01/2024 | 0 | Resource Division | 65.38 | 0 | 0
1462 | Murshidabad Division | Kandi Sub-Division | Balance work for repair of road, construction of approach road & land development of Hizole-I & II & Bundai Water Supply Scheme of Kandi Block under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000006/2025-2026 | 835/MURD | 11/04/2025 | 234 | M/S JATIN | 69.3 | 0 | 5
1463 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BUNDAI PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000653/2022-2023 | 3403/MURD | 22/12/2022 | 45 | M/S SUBHAJIT BISWAS | 16.8 | 0 | 75
1464 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for construction of 250 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of BUNDAI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362420S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,40,40,803.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,49,29,128.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000750/2022-2023 | 413/MURD | 15/02/2023 | 898 | M/S TRADE ASSOCIATE | 289.47 | 39.33 | 20
1465 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1466 | Murshidabad Division | Kandi Sub-Division | Balance work of road restoration damaged during laying of pipeline and laying of distribution pipe line of Bundai Piped Water Supply Scheme, Kandi Block, Kandi Sub-Division under Murshidabad Division, P.H.E dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000845/2023-2024 | 827/MURD | 15/03/2024 | 15 | PRASANTA SANA | 20.72 | 0 | 50
1467 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of Laying Distribution System (PART-A) for Augmentation of BUNDAI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362420S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000973/2022-2023 | 130./MURD | 16/01/2023 | 897 | PRASANTA SANA | 108.95 | 32.42 | 60
1468 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | RTOR000316/2023-2024 | 1936/MURD/3 | 18/07/2023 | 0 | Resource Division | 25.21 | 0 | 0
1469 | Berhampore Mechanical | Kandi Sub-Division | BUNDI PH 1 ID 304259360 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | BILL/01476/2023-2024 | 365/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 3.48 | 0 | 0
1470 | Berhampore Mechanical | Kandi Sub-Division | SHIFTING OF 11KV AT BUNDAI | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | BILL/01582/2023-2024 | 449/WBSEDCL-JJM | 15/03/2024 | 0 | WBSEDCL | 0.98 | 0 | 0
1471 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Bundi ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000085/2023-2024 | 1886/MEDB | 16/06/2023 | 92 | M/S SAJAHAN CHOWDHURY | 22.54 | 14.31 | 5
1472 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of SERPUR & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000716/2022-2023 | 78/MURD | 10/01/2023 | 1118 | RADIANT | 557.06 | 48.03 | 35
1473 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1474 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | RTOR000048/2023-2024 | 1067/MURD/3 | 18/04/2023 | 0 | Resource Division | 25.58 | 0 | 0
1475 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SERPUR ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000155/2023-2024 | 2015/MEDB | 19/06/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 23.67 | 19.11 | 50
1476 | Murshidabad Division |  | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 |  |  | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0
1477 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -PANCHTHUPI- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- JANARDHANPUR , CODE-315981 , 632 /2020-21/EE |  |  | VCH/002049/2020-2021 | 504/W | 22/03/2021 | 0 | KAMIRUL SK AND CO. | 21.08 | 0 | 0
1478 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BURWAN- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- GOURINAGAR , CODE-315951 , 631/2020-21/EE |  |  | VCH/002050/2020-2021 | 504/W | 22/03/2021 | 0 | KAMIRUL SK AND CO. | 9.08 | 0 | 0
1479 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System (PART-B), FHTC for PUNRAPARA Water Supply Scheme in Khargram Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000675/2023-2024 | 3656/MURD | 29/11/2023 | 120 | AJAY MONDAL | 270.3 | 67.27 | 30
1480 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, Boundwary Wall for PUNRAPARA PWSS in Khargram Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000844/2022-2023 | 756/MURD | 16/03/2023 | 747 | JIT CONSTRUCTION | 194.6 | 44.56 | 10
1481 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000025/2023-2024 | 1210/MURD/33 | 02/05/2023 | 0 | Resource Division | 16.9 | 0 | 0
1482 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT PURAOARA PH 1 ID 304342318 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/00357/2024-2025 | 108/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 6.06 | 0 | 0
1483 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II,III ,IV & V under PUNRAPARA ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000084/2023-2024 | 1932/MEDB | 16/06/2023 | 92 | MAHADEB ENTERPRISE | 55.86 | 0 | 0
1484 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 20
1485 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Sarkarpara Piped water supply scheme to accommodate construction of boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000224/2022-2023 | 1557/BD-I | 20/02/2023 | 1032 | AZAD ENTERPRISE | 63.96 | 33.12 | 75
1486 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SARKARPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000282/2022-2023 | 1370/BD-I | 21/12/2022 | 10 | M/S SOBHA & CO | 2.46 | 2.39 | 100
1487 | Berhampore Division I | Raghunathganj Sub-Division | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SARKARPARA Water Supply Scheme within Jalangi Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000375/2024-2025 | 430/BD-I | 19/03/2025 | 15 | TAPESH MONDAL | 11.56 | 0 | 100
1488 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000015/2023-2024 | 194/BD-I/9 | 09/02/2024 | 0 | Resource Division | 14.79 | 0 | 0
1489 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Rajarampur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000121/2022-2023 | 1678/BD-I | 14/03/2023 | 30 | SOMNATH DEY | 2.35 | 2.31 | 100
1490 | Berhampore Division I | Berhampur M/E Division | Augmentation of Rajarampur Piped water supply scheme to accommodate construction of OHR ,Pump House and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000208/2022-2023 | 1618/BD-I | 02/03/2023 | 310 | DHIRENDRA NATH MONDAL | 366.26 | 0 | 0
1491 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAJARAMPUR Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000261/2022-2023 | 1684/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.66 | 2.69 | 1
1492 | Berhampore Division I | Berhampur M/E Division | Repair And Renovation Works Of OHR (350 Cum) of Ground Water Supply Scheme for Rajarampur of Lalgola block under Berhampore Division-I PHEDte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000277/2023-2024 | 994/BD-I | 30/10/2023 | 639 | DAS CONSTRUCTION 13/1/2 UKILABAD ROAD, BERHAMPORE | 8.12 | 0 | 0
1493 | Berhampore Division I | Berhampur M/E Division | RAJARAMPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000454/2023-2024 | 457/BD-I | 15/03/2024 | 60 | MAA DURGA ENTERPRISE | 22.87 | 0 | 0
1494 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000010/2024-2025 | 1510/BD-I/4 | 12/09/2024 | 0 | Resource Division | 8.03 | 0 | 0
1495 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000080/2023-2024 | 201/BD-1/21 | 10/02/2024 | 0 | Resource Division | 50.95 | 0 | 0
1496 | Berhampore Mechanical | Berhampur M/E Division | SHIFTING OF LT OH LINE AT RAJARAMPUR PH-I | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/00429/2024-2025 |  | 27/06/2024 | 0 | WBSEDCL | 0.89 | 0 | 0
1497 | Berhampore Mechanical | Berhampur M/E Division | SHIFTING OF LT OH LINE AT RAJARAMPUR PH-I | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/00468/2024-2025 | 145/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 0.89 | 0 | 0
1498 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under RAJARAMPUR ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000068/2023-2024 | 3781/MEDB | 03/11/2023 | 92 | M/S S. R. ENTERPRISE | 23.47 | 0 | 0
1499 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room at Head Work site of MOKIMNAGAR PWSS (H/W Site & 2nd Site) under Jal Jevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000008/2025-2026 | 595/BD-I | 22/04/2025 | 60 | M/S MEGHNA CONSTRUCTION | 12.78 | 0 | 0
1500 | Berhampore Division I | Berhampur M/E Division | Augmentation of Makimnagar Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP) and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000158/2023-2024 | 682/BD-I | 10/08/2023 | 728 | M/S BIMALENDU BOSE | 427.29 | 0 | 30
1501 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MAKIMNAGAR Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000263/2022-2023 | 1686/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.59 | 2.62 | 1
1502 | Berhampore Division I | Berhampur M/E Division | Repair And Renovation Works Of OHR (180 Cum) of Ground Water Based Supply Scheme for Makimnagar of Lalgola block under Berhampore Division-I PHEDte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000274/2023-2024 | 992/BD-I | 30/10/2023 | 30 | MATIUR RAHAMAN | 8.07 | 3.67 | 65
1503 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MOKIMNAGAR Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000363/2024-2025 | 318/BD-I | 24/02/2025 | 15 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0
1504 | Berhampore Division I | Berhampur M/E Division | MAKIMNAGAR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000452/2023-2024 | 455/BD-I | 15/03/2024 | 60 | M/S UNIVERSAL TRADING | 22.87 | 0 | 50
1505 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000008/2024-2025 | 1510/BD-I/2 | 12/09/2024 | 0 | Resource Division | 6.78 | 0 | 0
1506 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000070/2023-2024 | 201/BD-1/11 | 10/02/2024 | 0 | Resource Division | 36.15 | 0 | 0
1507 | Berhampore Mechanical | Berhampur M/E Division | MAKIMNAGAR PH-1 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/01515/2023-2024 | 403/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 12.14 | 0 | 0
1508 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of MAKIMNAGAR ground water based water supply scheme under Block- LALGOLA, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000065/2023-2024 | 3780/MEDB | 03/11/2023 | 92 | JOY BISHNU ENGINEERING CO. | 11.98 | 10.05 | 10
1509 | Murshidabad Division | Berhampur M/E Division | Augmentation of MURADPUR JALANGI ZONE-I PWSS Laing Distribution System, Rising Main Connection Repairing P.H, B.W, Construction of P.H of JALANGI Block , under Murshidabad Division PHE. Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000531/2023-2024 | 3114/MURD | 05/10/2023 | 543 | ARINDAM MAJUMDAR | 187.44 | 0 | 60
1510 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 2.56 | 100
1511 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000235/2023-2024 | 1219/MURD/15 | 03/05/2023 | 0 | Resource Division | 26 | 0 | 0
1512 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000539/2024-2025 | 325/MEDB | 10/02/2025 | 89 | JOY BISHNU ENGINEERING CO. | 11.35 | 0 | 0
1513 | Murshidabad Division | Berhampur M/E Division | Augmentation of MURADPUR JALANGI ZONE-II PWSS Laing Distribution System, Rising Main Connection Repairing P.H, B.W, Construction of P.H of JALANGI Block , under Murshidabad Division PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000153/2023-2024 | 1901/MURD | 17/07/2023 | 180 | AZAD ENTERPRISE | 75.52 | 6.43 | 30
1514 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 1.87 | 100
1515 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000236/2023-2024 | 1219/MURD/27 | 03/05/2023 | 0 | Resource Division | 12.69 | 0 | 0
1516 | Murshidabad Division | Kandi Sub-Division | Allied work for KHESAR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000052/2024-2025 | 1977/MURD | 08/07/2024 | 60 | DAS TRADING CO. | 70.58 | 0 | 0
1517 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of KHESAR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000679/2022-2023 | 38/MURD | 04/01/2023 | 818 | PRADIP KUMAR DAS | 720.99 | 330.55 | 35
1518 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000045/2023-2024 | 1067/MURD | 18/04/2023 | 0 | Resource Division | 15.98 | 0 | 0
1519 | Berhampore Mechanical | Kandi Sub-Division | Electric Service Connection at KESHAR PH I, Application NO.3004403775, ID 304120001 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01058/2023-2024 | 192/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 5.11 | 0 | 0
1520 | Berhampore Mechanical | Kandi Sub-Division | Electric Service Connection at KHESAR PWSS PH II, Application NO.3004403805, ID 304120021 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01076/2023-2024 | 193/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 4.51 | 0 | 0
1521 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under KHESAR ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000149/2023-2024 | 2012/MEDB | 19/06/2023 | 927 | M/S. SUPER CONSTRUCTION | 26.01 | 11.8 | 60
1522 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 15.68 | 20
1523 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAGAR DOEMKANON ZONE-II Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000197/2022-2023 | 1380/BD-I | 22/12/2022 | 10 | RADIANT | 2.6 | 2.6 | 100
1524 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Ramnagar Doemkanun ZoneII Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000254/2022-2023 | 1660/BD-I | 13/03/2023 | 180 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 186.74 | 33.13 | 30
1525 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000016/2023-2024 | 194/BD-I/2 | 09/02/2024 | 0 | Resource Division | 30.59 | 0 | 0
1526 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW CONNECTION AT RAMNAGAR DOEMKANUN Z2 PH 2 ID 304268982 | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | BILL/01115/2024-2025 |  | 25/11/2024 | 0 | WBSEDCL | 10.13 | 0 | 0
1527 | Murshidabad Division | Berhampur M/E Division | Providing FHTC to 754 nos. household, Rising Main, Repairing Vertical extension of Boundary wall and repairing of Pump House and overhauling of R.C.C. elevated reservoir 450 Cum capacity of staging height 20 mtr. (Shaft wall) for Augmentation work of Mahesail (Zone-II) PWSS in Suti-II Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000802/2022-2023 | 564/MURD | 28/02/2023 | 180 | BISWAS ENTERPRISE. | 63.88 | 37.44 | 95
1528 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution System for Augmentation work of Mahesail (Zone-II) PWSS in Suti-II Block under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000860/2022-2023 | 806/MURD | 22/03/2023 | 180 | M/S. BIMALENDU BOSE | 190.73 | 186.94 | 100
1529 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000200/2023-2024 | 1210/MURD/27 | 02/05/2023 | 0 | Resource Division | 26.32 | 0 | 0
1530 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-II under MAHESAIL ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000698/2023-2024 | 4315/MEDB | 29/12/2023 | 91 | BHAGIRATHI JUTE AND HOLDINGS PVT LTD | 22.93 | 0 | 0
1531 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution System of MIRHATI PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Murshidabad Circle ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000854/2022-2023 | 789/MURD | 21/03/2023 | 742 | SUBHANKAR ROY | 139.07 | 62.11 | 30
1532 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000084/2023-2024 | 1129/MURD/7 | 25/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
1533 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000340/2023-2024 | 79/MURD/07 | 09/01/2024 | 0 | Resource Division | 3.63 | 0 | 0
1534 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000358/2023-2024 | MURD/439/03 | 08/02/2024 | 0 | Resource Division | 0.13 | 0 | 0
1535 | Berhampore Mechanical | Kandi Sub-Division | Electric Service Connection at MIRHATI PWSS PH I, Application NO.3004467235, ID 304171280 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01069/2023-2024 | 190/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 6.97 | 0 | 0
1536 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PH2 MIRHATI ID304239447 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01411/2023-2024 | 308/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 4.81 | 0 | 0
1537 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under MIRHATI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000273/2023-2024 | 3713/MEDB | 03/11/2023 | 790 | B. T. PROJECTS PVT. LTD. | 21.24 | 0 | 70
1538 | Murshidabad Division | Berhampur M/E Division | SITARAMPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission, Block- SAMSERGANJ of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000012/2023-2024 | 978/MURD | 10/04/2023 | 1279 | HOQUEDAR ALI | 389.19 | 86.41 | 15
1539 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.41 | 100
1540 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SITARAMPUR Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000618/2023-2024 | 3393/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 16.54 | 50
1541 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000278/2023-2024 | 1230/MURD/20 | 04/05/2023 | 0 | Resource Division | 29.01 | 0 | 0
1542 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT SITARAMPORE PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | BILL/00222/2024-2025 | 61/WBSEDCL-JJM | 06/05/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
1543 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube well in connection to Accommodate FHTC at Pump House No.-I , II & III under SITARAMPUR ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000697/2023-2024 | 3807/MEDB | 03/11/2023 | 790 | JAL PRAVAHIKA PVT LTD | 31.3 | 0 | 15
1544 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 4.75 | 100
1545 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NAPARA Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000621/2023-2024 | 3408/MURD | 02/11/2023 | 21 | TAPAN DAS | 9.28 | 7.95 | 100
1546 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sagarpara Part-A, Kohetpur and Napara Water Supply Scheme under Islampur & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000668/2022-2023 | 3409/MURD | 22/12/2022 | 45 | R.K. DRILLING SERVICES | 23.56 | 0 | 0
1547 | Murshidabad Division | Berhampur M/E Division | Formal work order for the work of NAPARA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Samserganj Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000735/2022-2023 | 376/MURD | 10/02/2023 | 902 | MANDAL CONSTRUCTION AND CO. | 241.91 | 52.73 | 45
1548 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | RTOR000268/2023-2024 | 1230/MURD/11 | 04/05/2023 | 0 | Resource Division | 22.61 | 0 | 0
1549 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | RTOR000383/2023-2024 | 495/MURD/14 | 15/02/2024 | 0 | Resource Division | 5.03 | 0 | 0
1550 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT NAPARA PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | BILL/00221/2024-2025 | 60/WBSEDCL-JJM | 06/05/2024 | 0 | WBSEDCL | 11.52 | 0 | 0
1551 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under NAPARA ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000696/2023-2024 | 3808/MEDB | 03/11/2023 | 92 | ORIENTAL ENGINEERING CO. | 20.86 | 0 | 10
1552 | Murshidabad Division | Berhampur M/E Division | Augmentation Work of Mahesail Zone-III Piped Water Supply Scheme to accommodate with FHTC (1034 Nos), Laying of Rising Main , Laying of Distribution System , construction of 350 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000256/2023-2024 | 2466/MURD | 09/08/2023 | 754 | GHOSH ENTERPRISE | 337.02 | 0 | 60
1553 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000225/2023-2024 | 1219/MURD/07 | 03/05/2023 | 0 | Resource Division | 16.33 | 0 | 0
1554 | Berhampore Mechanical | Berhampur M/E Division | MAHESAIL Z-III PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | BILL/01443/2023-2024 | 336/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 5.57 | 0 | 0
1555 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-III under MAHESAIL ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000694/2023-2024 | 3810/MEDB | 03/11/2023 | 92 | M/S JIT ENTERPRISE | 22.25 | 0 | 0
1556 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of JHILLI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000700/2022-2023 | 123/MURD | 16/01/2023 | 867 | M/S RUBIET HOSSAIN | 616.31 | 104.78 | 10
1557 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000046/2023-2024 | 1067/MURD/1 | 18/04/2023 | 0 | Resource Division | 21.94 | 0 | 0
1558 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT JHILLI PWSS PH1 ID304171275 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01126/2023-2024 | 217/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 6.95 | 0 | 0
1559 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT JHILLI PH 2 ID 304171278 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01127/2023-2024 | 218/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 10.53 | 0 | 0
1560 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at P.H. No.-I & II under JHILLI ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000708/2023-2024 | 4061/MEDB | 04/12/2023 | 91 | SREE RADHA ELECTRICAL | 24.06 | 17.74 | 50
1561 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of MARURA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte.( Scheme ID -PH222362239S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000714/2022-2023 | 93/MURD | 11/01/2023 | 365 | M/S.TAPAS KUMAR CHAKRABORTY | 815.38 | 0 | 0
1562 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000035/2023-2024 | 1043/MURD/10 | 17/04/2023 | 0 | Resource Division | 76.92 | 0 | 0
1563 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under MARURA ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000100/2023-2024 | 3789/MEDB | 03/11/2023 | 92 | A.G. ENTERPRISE | 36.83 | 0 | 0
1564 | Murshidabad Division | Kandi Sub-Division | SANTOSHPUR PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000546/2023-2024 | 3179/MURD | 11/10/2023 | 553 | GARAI INFRA PROJECT | 260.08 | 0 | 45
1565 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SANTOSHPUR ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000104/2023-2024 | 1892/MEDB | 16/06/2023 | 92 | S. P. CONSTRUCTION | 22.53 | 0 | 0
1566 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Santoshpur ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000169/2023-2024 | 2092/MEDB | 19/06/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 21.11 | 0 | 0
1567 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bharatpur Zone- I A Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur -I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000118/2023-2024 | 1770/MURD | 06/07/2023 | 21 | SUJIT KUMAR SAHA | 18.45 | 0 | 0
1568 | Murshidabad Division | Kandi Sub-Division | Augmentation of BHARATPUR (ZONE - IA) PWSS under Jal Jeevan Mission of Bharatpur Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000204/2023-2024 | 2078/MURD | 31/07/2023 | 300 | BERHAMPORE CONSTRUCTION SYNDICATE PVT. LTD. | 478.38 | 0 | 0
1569 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IA under Bharatpur ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000244/2023-2024 | 3680/MEDB | 03/11/2023 | 92 | MERCURY ENGINEERING CO | 23.01 | 0 | 8
1570 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village Malatipur (Village code 314698) under Jorgacha Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723176 in the District of Murshidabad. |  |  | ORD/000567/2020-2021 | 80/MURD | 08/01/2021 | 60 | M/S. GHOSH ENTERPRISE | 26.36 | 0 | 1
1571 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village Joragacha (Village code 314690) under Jorgacha Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723176 in the District of Murshidabad. |  |  | ORD/000568/2020-2021 | 81/MURD | 08/01/2021 | 60 | M/S. GHOSH ENTERPRISE | 30.67 | 0 | 1
1572 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MALATIPUR (Village Code 314698) under JORGACHA Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 846 of 20-21 by EE MURD |  |  | VCH/000296/2022-2023 | 106-MSD/22-23 | 07/05/2022 | 0 | M/S. GHOSH ENTERPRISE | 23.7 | 0 | 0
1573 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village JORGACHA (Village Code 314690) under JORGACHA Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 847 of 20-21 by EE MURD |  |  | VCH/001483/2021-2022 | 391-MSD/21-22 | 22/03/2022 | 0 | M/S. GHOSH ENTERPRISE | 28.9 | 0 | 0
1574 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sibnagar Zone-III under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000059/2023-2024 | 156/BD-I | 15/05/2023 | 90 | NATIONAL ENTERPRISES | 30.54 | 0 | 0
1575 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Shibnagar Zone-III village, Block:- Nawda under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000219/2023-2024 | 3078/MEDB | 02/08/2023 | 92 | M/S SAJAHAN CHOWDHURY | 6.27 | 0 | 0
1576 | Murshidabad Division | Kandi Sub-Division | SUNUTI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, BHARARPUR-I of Murshidabad District under Kandi sub division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000867/2022-2023 | 846/MURD | 24/03/2023 | 730 | M/S. BIMALENDU BOSE | 471.09 | 0 | 10
1577 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000057/2023-2024 | 1075/MURD/1 | 19/04/2023 | 0 | Resource Division | 19.17 | 0 | 0
1578 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT SUNUTI PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00404/2024-2025 |  | 28/05/2024 | 0 | WBSEDCL | 4.22 | 0 | 0
1579 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT SUNUTI PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00406/2024-2025 | 103/WBSEDCL-JJM | 06/06/2024 | 0 | WBSEDCL | 4.22 | 0 | 0
1580 | Berhampore Mechanical | Kandi Sub-Division | Sunuti PH-1 Application No- 3004528432 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01200/2023-2024 | 265/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
1581 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SUNUTI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000119/2023-2024 | 1908/MEDB | 16/06/2023 | 822 | M/S S. R. ENTERPRISE | 23.39 | 0 | 10
1582 | Murshidabad Division | Berhampur M/E Division | Laying Distribution System, Rising Main Connection, FHTC connections, Construction of 2 Nos Pump House Room, 100 Mtr Boundary Wall, for Augmentation of Aurangabad Zone-I PWSS of Suti-II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior Engineer 3,Junior engineer-III | ORD/000088/2025-2026 | 1510/MURD | 03/07/2025 | 90 | H.I.ENTERPRISE | 133.86 | 0 | 0
1583 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior Engineer 3,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.68 | 100
1584 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior Engineer 3,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 7.63 | 11
1585 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sonar Diar Zone-II under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000073/2023-2024 | 174/BD-I | 16/05/2023 | 90 | SHIBAM ENTERPRISE | 26.55 | 0 | 0
1586 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sonadiar Zone-II village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000188/2023-2024 | 3049/MEDB | 02/08/2023 | 92 | HARA PROSAD DAS | 6.27 | 0 | 0
1587 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Mohespur under Beldanga -I block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000062/2023-2024 | 159/BD-I | 15/05/2023 | 90 | TITLI ENTERPRISE | 27.81 | 0 | 0
1588 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Mohespur village, Block:- Beldanga-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000217/2023-2024 | 3079/MEDB | 02/08/2023 | 92 | DIPALI CONSTRUCTION | 6.12 | 0 | 0
1589 | Murshidabad Division | Berhampur M/E Division | CHANDNI DAHA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main ,Construction of OHR of 300 cum capacity, Construction Pump House cum Chlorine Room (5.90m x 4.1m) & Pump House (4.10m x 3.5m) with sanitary and Water Supply Arrangement) & Construction of 190 m Boundary wall under Jal Jeevan Mission of Samserganj Block, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000447/2023-2024 | 2968/MURD | 20/09/2023 | 752 | M/S GOLAM KIBRIA | 431.64 | 0 | 12
1590 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000497/2024-2025 | 660/MURD | 19/03/2025 | 90 | JOY GURU ENTERPRISE | 82.5 | 0 | 0
1591 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.62 | 100
1592 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000227/2023-2024 | 1219/MURD/14 | 03/05/2023 | 0 | Resource Division | 19.83 | 0 | 0
1593 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1594 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT CHANDNIDAHA PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/00420/2024-2025 | 141/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 10.1 | 0 | 0
1595 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT CHANDNIDAHA PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/00421/2024-2025 | 142/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 11.52 | 0 | 0
1596 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Alighata under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000049/2023-2024 | 146/BD-I | 15/05/2023 | 899 | M/S. DAS ENTERPRISE MAHULA, DASPARA, VILL +P.O-GOPINATHPUR, MURSHIDABAD. | 30.54 | 0 | 15
1597 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Alighata village, Block:- Lalgola under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000631/2023-2024 | 3158/MEDB | 08/08/2023 | 92 | ARINDAM MAJUMDAR | 6.27 | 0 | 0
1598 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sibnagar Zone-V under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000061/2023-2024 | 158/BD-I | 15/05/2023 | 90 | SUJAUDDIN SHAIKH | 23.91 | 0 | 0
1599 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Shibnagar Zone-V village, Block:- Nawda under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000186/2023-2024 | 3047/MEDB | 02/08/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0
1600 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 3.13 | 100
1601 | Murshidabad Division | Berhampur M/E Division | Renovation of Existing AIRP (Capacity 16 Cu.M/hr) for changing of filter media of 1 no Polishing Unit (2.50 m dia x 1.5 m HOS) & 1 no Primary Unit (2.50 m dia x 2.00 m HOS) and painting all vessel, pipes etc. all complete at Birendranagar (Zone-I) W/S Scheme under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000808/2023-2024 | 617/MURD | 28/02/2024 | 30 | M/S BAPPA ENTERPRISE | 16.7 | 0 | 0
1602 | Murshidabad Division | Berhampur M/E Division | Allied works for Renovation of Existing AIRP, Gobordanga Model (Capacity 16 Cu.M/hr) at Birendranagar (Zone-I) W/S Scheme in connection with Augmentation of Birendranagar (Zone-I) PWSS under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000832/2023-2024 | 782/MURD | 14/03/2024 | 20 | M/S BAPPA ENTERPRISE | 10.09 | 0 | 0
1603 | Murshidabad Division | Berhampur M/E Division | Allied works In connection with Bypass line connection from AIRP to Distribution main at Birendranagar (Zone-I) Water Supply Scheme for the work of Augmentation of Birendranagar (Zone-I) PWSS under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000838/2023-2024 | 821/MURD | 15/03/2024 | 30 | MAA CONSTRUCTION (MUJIBOR, MAJDIYA SEKHPARA) | 3.27 | 0 | 100
1604 | Murshidabad Division | Berhampur M/E Division | Work of Extension of Existing Boundary Wall and Painting of the same at Birendranagar (Zone-I) Water supply scheme , under Jangipur Sub-Division, P.H.E. Dte in the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/001275/2021-2022 | 392/JSD | 31/12/2021 | 30 | S. ROY & CO. | 4.79 | 3.9 | 0
1605 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000188/2023-2024 | 1210/MURD/21 | 02/05/2023 | 0 | Resource Division | 2.46 | 0 | 0
1606 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I II & III ,Zone-I under BIRENDRANAGAR ground water based water supply scheme under Block_ Raghunathganj-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000286/2023-2024 | 4346/MEDB | 29/12/2023 | 641 | JOGMAYA ENGINEERING | 32 | 0 | 30
1607 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for MADNA Zone-I Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000041/2025-2026 | 1156/MURD | 20/05/2025 | 60 | AUDY ENGINEERING | 23 | 0 | 0
1608 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 4.06 | 100
1609 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0
1610 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
1611 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000093/2023-2024 | 1147/MURD/8 | 27/04/2023 | 0 | Resource Division | 128.8 | 0 | 0
1612 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 7.68 | 11
1613 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
1614 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Rosora (P) Part- B village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000239/2023-2024 | 2417/MURD | 08/08/2023 | 724 | SUKUMAR ROY | 30.55 | 0 | 50
1615 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Rosora (P) Part- A village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000241/2023-2024 | 2423/MURD | 08/08/2023 | 60 | C. R. CONSTRUCTION | 30.55 | 0 | 0
1616 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Rosora (P) Part-A village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000208/2023-2024 | 3068/MEDB | 02/08/2023 | 92 | DAS ENTERPRISE (CHOA) | 6.3 | 0 | 0
1617 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Rosora (P) Part-B village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000209/2023-2024 | 3069/MEDB | 02/08/2023 | 92 | A. S. ENGINEERING | 6.32 | 0 | 0
1618 | Murshidabad Division | Berhampur M/E Division | CHANDMARI , BAHUTALI & FATELLAPUR PWSS to accommodate FHTC under Jal Jeevan Mission, Block- SUTI-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000287/2023-2024 | 3176/MURD | 11/10/2023 | 813 | CHAKRABORTY CONSTRUCTION | 2258.18 | 0 | 10
1619 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 3.26 | 100
1620 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT CHANDAMARI PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/00428/2024-2025 | 140/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 7.27 | 0 | 0
1621 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT CHANDAMARI PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/01240/2024-2025 |  | 11/12/2024 | 0 | WBSEDCL | 4.31 | 0 | 0
1622 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Chandamari ground water based water supply scheme under Block_ Suti-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000267/2023-2024 | 3704/MEDB | 03/11/2023 | 92 | QUAZI NOZRUL ISLAM | 23.68 | 0 | 0
1623 | Murshidabad Division | Islampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | Junior Engineer | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 4.47 | 100
1624 | Murshidabad Division | Islampur Sub-Division | Augmentation of SHIBNAGAR LASKARPUR (Zone-I) Part-B & Garibpur (Zone-I) Part-B PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000440/2023-2024 | 2888/MURD | 12/09/2023 | 750 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 226.15 | 0 | 75
1625 | Murshidabad Division | Islampur Sub-Division | Cleaning the chokage of AC/DI/CI/UPVC pipes in the existing pipeline by split bamboo for Garibpur Zone-II PWSS under Islampur Sub-Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000508/2023-2024 | 401/ISD | 29/09/2023 | 7 | RAJAKINI ENTERPRISE | 0.81 | 0 | 100
1626 | Murshidabad Division | Kandi Sub-Division | Allied work of Laying rising main and distribution system with FHTC including Construction Pump House Cum Chlorine Room , Boundary wall at 2nd Tube Well Site and Earth filling at both site of Padamkandi Water Supply Scheme , under Jal Jeevan Mission of KHARGRAM Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000040/2024-2025 | 1926/MURD | 03/07/2024 | 60 | ARJIMA CONSTRUCTION | 19.18 | 0 | 80
1627 | Murshidabad Division | Kandi Sub-Division | Formal work order for PADAM KANDI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of KHARGRAM Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000837/2022-2023 | 732/MURD | 15/03/2023 | 749 | APURBA SAHA CHOWDHURY | 145.12 | 74.75 | 90
1628 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II | RTOR000061/2023-2024 | 1075/MURD/5 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
1629 | Berhampore Mechanical | Kandi Sub-Division | New connection charge for Padamkandi, P/H No.- II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II | BILL/00855/2023-2024 | 121/WBSEDCL-JJM | 27/09/2023 | 0 | WBSEDCL | 4.19 | 0 | 0
1630 | Berhampore Mechanical | Kandi Sub-Division | Electric Service New Connection PADAMKANDI PH-1 PWSS Application NO. 3004403540. ID. 304119863 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II | BILL/01036/2023-2024 | 171/WBSEDCL-JJM | 05/12/2023 | 0 | WBSEDCL | 10.39 | 0 | 0
1631 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under PADAMKANDI ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000057/2023-2024 | 1927/MEDB | 16/06/2023 | 92 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 20.81 | 0 | 50
1632 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000357/2023-2024 | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 2.39 | 100
1633 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
1634 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000092/2023-2024 | 1147/MURD/7 | 27/04/2023 | 0 | Resource Division | 0.69 | 0 | 0
1635 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT BAJEGAJIPUR PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/00619/2024-2025 |  | 02/08/2024 | 0 | WBSEDCL | 4.52 | 0 | 0
1636 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT BAJEGAJIPUR PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/00632/2024-2025 | 186/WBSEDCL-JJM | 09/08/2024 | 0 | WBSEDCL | 4.52 | 0 | 0
1637 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under BAZEGAZIPUR ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000133/2023-2024 | 1920/MEDB | 16/06/2023 | 930 | SARKAR CONSTRUCTION | 21.42 | 17.54 | 10
1638 | Murshidabad Division | Kandi Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at, Dakshinkhanda Zone-IA T.W-II, III, Zone-IB T.W-II, Dakshinkhanda Zone-II T.W- I, II Water Supply Scheme of Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000506/2024-2025 | 718/MURD | 25/03/2025 | 65 | MAMATA USHA ENTERPRISE | 58.95 | 0 | 0
1639 | Murshidabad Division | Kandi Sub-Division | Augmentation of DAKSHIN KHANDA ZONE - II PWSS under Jal Jeevan Mission of Bharatpur-II Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000577/2023-2024 | 3301/MURD | 20/10/2023 | 300 | M/S GHOSH & CO. | 536.15 | 0 | 0
1640 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1641 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT DAKSHINKHANDA Z-II PH-III | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01214/2024-2025 |  | 02/12/2024 | 0 | WBSEDCL | 4.08 | 0 | 0
1642 | Murshidabad Division | Kandi Sub-Division | Construction of Pump House, Boundary Wall , Path Way of Matua PWSS in Bhratpur-II Block , KANDI Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000830/2023-2024 | 780/MURD | 14/03/2024 | 45 | SANTA TRADING | 14.19 | 0 | 90
1643 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | RTOR000217/2023-2024 | 1219/MURD/10 | 03/05/2023 | 0 | Resource Division | 0.76 | 0 | 0
1644 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT MATWA PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | BILL/00229/2024-2025 | 69/WBSEDCL-JJM | 09/05/2024 | 0 | WBSEDCL | 2.96 | 0 | 0
1645 | Berhampore Mechanical | Kandi Sub-Division | Matwa PH-1 Application no- 3004547182 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | BILL/01181/2023-2024 | 237/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 7.87 | 0 | 0
1646 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Matua ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000254/2023-2024 | 4317/MEDB | 29/12/2023 | 91 | H.K. DAS & CO. | 8.93 | 0 | 10
1647 | Murshidabad Division | Kandi Sub-Division | BERBARI & UJUNIA adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block-BHARATPUR-I & II of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000873/2022-2023 | 882/MURD | 28/03/2023 | 280 | BANAMALI ENTERPRISES | 224.42 | 0 | 35
1648 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000067/2023-2024 | 1075/MURD/9 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
1649 | Berhampore Mechanical | Kandi Sub-Division | Berbari PH-2 Application No- 3004528419 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01201/2023-2024 | 277/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.24 | 0 | 0
1650 | Berhampore Mechanical | Kandi Sub-Division | BERBARI PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01510/2023-2024 | 399/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 13.01 | 0 | 0
1651 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Ajodhya Nagar & Chumrigacha to faciliate Functional Household Tap connection(FHTC) works in connection to Jal Jeevan Mission under Bairgachi (Zone-C) surface water based Water Supply Scheme of Central Sector Part-II under Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000001/2023-2024 | 21/BD-I | 11/04/2023 | 30 | JIBENDRA NARAYAN SUKUL | 50.51 | 50.5 | 100
1652 | Berhampore Division I | Berhampur Division I | Additional laying work of 300 mm dia DI Pipe Line at pond side of near Chumrigacha Primary School due to damage of UPVC Pipe line and with allied works of Distribution pipe line under Bairgachi Surface Water based Water Supply Scheme under Berhampore Division - I, PHE Dte.in Murshidabad District | Assistant Engineer-I | Junior Engineer-I | ORD/000004/2022-2023 | 547/BD-I | 13/05/2022 | 10 | JIBENDRA NARAYAN SUKUL | 4.54 | 4.31 | 45
1653 | Berhampore Division I | Berhampur Division I | Laying of 350 mm dia DI (K-7) distribution Pipeline including allied works along with attached sheet of node point over command area of Bhakuri-I G.P under Bairgachi W/S scheme under Berhampore Division -I ,P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000009/2022-2023 | 552/BD-I | 13/05/2022 | 45 | DHIMAN SARKAR | 20.59 | 6.02 | 100
1654 | Berhampore Division I | Berhampur Division I | Laying of different dia DI pipe Line in connection with JJM (Jal Jeevan Mission) over damaged portion with allied works at Karim more and near Balarampur High School for smooth running of FHTC Work under Bairgachi (Zone-C) surface based water supply scheme under CS Part-II of BD-I, P.H.E Dte | Assistant Engineer-I | Junior Engineer-I | ORD/000014/2023-2024 | 85/BD-I | 03/05/2023 | 30 | JIBENDRA NARAYAN SUKUL | 5.69 | 4.97 | 100
1655 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.08.2025 to 31.10.2025. | Assistant Engineer-I | Junior Engineer-I | ORD/000094/2025-2026 | 991/BD-I | 31/07/2025 | 92 | SOUVIK HALDER | 0.45 | 0 | 0
1656 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.08.2023 to 31.01.2024. | Assistant Engineer-I | Junior Engineer-I | ORD/000128/2023-2024 | 517/BD-I | 25/07/2023 | 184 | SOUVIK HALDER | 0.91 | 0 | 10
1657 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Fate Sing Diar and Char Narayanpur (Village code 315364,315384) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000246/2021-2022 | 1841/BD-I | 05/10/2021 | 60 | UNIVERSE UNEMPLOYED ENGINEERS CO. OPT. & CONSTRUCTION SOCIETY LTD. | 55.84 | 18.71 | 40
1658 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baninathpur (Village code 315367) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000247/2021-2022 | 1842/BD-I | 05/10/2021 | 50 | JIBENDRA NARAYAN SUKUL | 41.36 | 41.73 | 1
1659 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bhatpara (Village code 315370) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000248/2021-2022 | 1843/BD-I | 05/10/2021 | 30 | PROSENJIT DAS | 24.41 | 21.86 | 1
1660 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.08.2024 to 31.01.2025. | Assistant Engineer-I | Junior Engineer-I | ORD/000262/2024-2025 | 1195/BD-I | 26/07/2024 | 184 | SOUVIK HALDER | 0.91 | 0 | 0
1661 | Berhampore Division I | Berhampur Division I | Laying of different dia UPVC distribution pipeline with allied works along with attached sheet of node point over command area of Chaltia village of Bhakuri-I gram panchayat under Bairgachi Water Supply Scheme,Central Sector Part-II under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000379/2021-2022 | 1463/BD-I | 16/08/2021 | 60 | MITRA & SARKAR CONSTRUCTION | 51.34 | 10.12 | 0
1662 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.02.2025 to 31.07.2025. | Assistant Engineer-I | Junior Engineer-I | ORD/000384/2024-2025 | 193/BD-I | 30/01/2025 | 181 | SOUVIK HALDER | 0.91 | 0 | 0
1663 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.02.2024 to 31.07.2024. | Assistant Engineer-I | Junior Engineer-I | ORD/000427/2023-2024 | 131/BD-I | 31/01/2024 | 182 | SOUVIK HALDER | 0.91 | 0 | 100
1664 | Berhampore Division I | Berhampur Division I | Formal Work order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under Command area of village of Haridasmati (Village code 315451) under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-06) | Assistant Engineer-I | Junior Engineer-I | ORD/000450/2021-2022 | 1882/BD-I | 07/10/2021 | 180 | DHIMAN SARKAR | 88.21 | 41.25 | 50
1665 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | Junior Engineer-I | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
1666 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Math Binkar (Village code 315366) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | Junior Engineer-I | ORD/000468/2021-2022 | 1870/BD-I | 07/10/2021 | 60 | M/S ADHIKARI CONSTRUCTION | 6.47 | 0 | 0
1667 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baikunthapur (Village code 315369) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | Junior Engineer-I | ORD/000469/2021-2022 | 1871/BD-I | 07/10/2021 | 90 | M/S BIMALENDU BOSE | 22.56 | 21.5 | 1
1668 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bairgachi Village- village code-315382, Habitation-Char Begpur (ID-0001295651) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | Junior Engineer-I | ORD/000470/2021-2022 | 1872/BD-I | 07/10/2021 | 60 | TANUSHREE ENTERPRISE | 14.92 | 0 | 0
1669 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ajodhyanagar village-Village Code-315449, Habitation-Belia khari (ID-0001295654) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID ? 0001756485 | Assistant Engineer-I | Junior Engineer-I | ORD/000471/2021-2022 | 1873/BD-I | 07/10/2021 | 90 | J.S. CONSTRUCTION | 22.08 | 21.87 | 0
1670 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mankara, Bezpara, Baragachi, Paschim Narayanpur (Village code 315365, 315368, 315382 & 315383) respectively under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-15) | Assistant Engineer-I | Junior Engineer-I | ORD/000558/2021-2022 | 1889/BD-I | 07/10/2021 | 180 | M/S S.S ENTERPRISE ALAMPUR, NODAKHALI, SOUTH 24 PARGANAS | 296.55 | 139.52 | 1
1671 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chaltia (Village code 315450) under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE.Dte. (Sl-01) | Assistant Engineer-I | Junior Engineer-I | ORD/000569/2021-2022 | 1955/BD-I | 27/10/2021 | 180 | UNICON INDIA | 267.92 | 90.56 | 1
1672 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Bairgachi Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | Junior Engineer-I | ORD/000761/2021-2022 | 2227/BD-I | 15/12/2021 | 90 | JIBENDRA NARAYAN SUKUL | 74.65 | 77.64 | 1
1673 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Bhatpara ( Village code-315370) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission & JalSwapna under Bairgachi (Zone-C) Surface water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | Junior Engineer-I | ORD/000842/2021-2022 | 98/BD-I | 01/02/2022 | 15 | MINA DAS | 8.88 | 7.63 | 1
1674 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.84 | 100
1675 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
1676 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000086/2022-2023 | 1147/MURD | 27/04/2023 | 0 | Resource Division | 32.39 | 0 | 0
1677 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000086/2023-2024 | 1147/MURD | 27/04/2023 | 0 | Resource Division | 32.39 | 0 | 0
1678 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT MAHESAIL Z-I PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | BILL/01096/2024-2025 |  | 12/11/2024 | 0 | WBSEDCL | 3.47 | 0 | 0
1679 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-I under MAHESAIL ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000130/2023-2024 | 1917/MEDB | 16/06/2023 | 92 | BHAGIRATHI JUTE AND HOLDINGS PVT LTD | 22.92 | 0 | 0
1680 | Murshidabad Division | Kandi Sub-Division | Formal work order for MANDALSAR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Khargram Block of Murshidabad District under Kandi Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000803/2022-2023 | 625/MURD | 03/03/2023 | 972 | MOTI RAHAMAN | 359.46 | 188.36 | 30
1681 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000058/2023-2024 | 1075/MURD/2 | 19/04/2023 | 0 | Resource Division | 31.87 | 0 | 0
1682 | Berhampore Mechanical | Kandi Sub-Division | POWER CONNECTION AT PWSS PH2 MANDALSARPOWER CONNECTION AT PWSS PH2 MANDALSAR ID 304250313 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/00179/2024-2025 | 44/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 7.8 | 0 | 0
1683 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS PH1 MANDALSAR ID 304239451 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01417/2023-2024 | 303/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 3.41 | 0 | 0
1684 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MANDALSAR ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000136/2023-2024 | 4309/MEDB | 29/12/2023 | 731 | JOGMAYA ENGINEERING | 21.5 | 0 | 80
1685 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490 another 91days from 21/06/2025 to 19/09/2025. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000101/2025-2026 | 122/BSD | 20/06/2025 | 91 | ABIDA CONSTRUCTION | 0.53 | 0 | 0
1686 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490 another 91days from 20/09/2025 to 19/12/2025. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000155/2025-2026 | 132/BSD | 19/09/2025 | 91 | ABIDA CONSTRUCTION | 0.53 | 0 | 0
1687 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490 another 160 days from 12/01/2025 to 20/06/2025. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000249/2024-2025 | 06/BSD | 08/01/2025 | 160 | ABIDA CONSTRUCTION | 0.93 | 0 | 0
1688 | Murshidabad Division | Berhampur Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000498/2024-2025 | 663/MURD | 19/03/2025 | 65 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0
1689 | Murshidabad Division | Berhampur Sub-Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-III, BHANDARA ZONE - I and SURANGAPUR ZONE -I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000700/2023-2024 | 3785/MURD | 11/12/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 35.34 | 0 | 80
1690 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000008/2024-2025 | 1811/MURD/07 | 20/06/2024 | 0 | Resource Division | 34.58 | 0 | 0
1691 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000171/2023-2024 | 1180/MURD/15 | 29/04/2023 | 0 | Resource Division | 61.77 | 0 | 0
1692 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000396/2023-2024 | 711/MURD | 07/03/2024 | 0 | Resource Division | 26 | 0 | 0
1693 | Berhampore Mechanical | Berhampur Sub-Division | SURANGAPUR Z-I PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01572/2023-2024 | 413/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 7.85 | 0 | 0
1694 | Berhampore Mechanical | Berhampur Sub-Division | SURANGAPURPH-1 Z-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01574/2023-2024 | 414/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
1695 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. UNDER MEDB, PHE, DTE. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000529/2024-2025 | 315/MEDB | 10/02/2025 | 259 | M/S S. S. ENTERPRISE (DOMKAL) | 37.13 | 0 | 40
1696 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000346/2022-2023 | 1925/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 9.6 | 0 | 100
1697 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000155/2023-2024 | 1180/MURD/04 | 29/04/2023 | 0 | Resource Division | 19.59 | 0 | 0
1698 | Murshidabad Division | Kandi Sub-Division | SIDDHESWARI PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000098/2023-2024 | 1721/MURD | 04/07/2023 | 638 | M/S. S. DAS AND ENTERPRISE | 443.38 | 0 | 80
1699 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SIDDHESWARI & ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000379/2023-2024 | 2776/MURD | 01/09/2023 | 21 | MAMATA USHA ENTERPRISE | 18.44 | 7.8 | 60
1700 | Murshidabad Division | Kandi Sub-Division | SIDDHESWARI PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000518/2023-2024 | 3116/MURD | 05/10/2023 | 300 | MOTI RAHAMAN | 407.86 | 0 | 10
1701 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | RTOR000066/2023-2024 | 1075/MURD/7 | 19/04/2023 | 0 | Resource Division | 20.78 | 0 | 0
1702 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under SIDDHESWARI ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000166/2023-2024 | 2299/MEDB | 04/07/2023 | 92 | DAS ENTERPRISE (CHOA) | 23.39 | 0 | 60
1703 | Murshidabad Division | Kandi Sub-Division | Sahapur (Part-A) & adjoining mouzas PWSS to accommodate Construction Tube Well, OHR, Pump House Cum Chlorine Room, Rising Main, FHTC work, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000143/2023-2024 | 1885/MURD | 17/07/2023 | 899 | HOQUEDAR ALI | 256.56 | 0 | 25
1704 | Murshidabad Division | Kandi Sub-Division | SAHAPUR (Part-B) & adjoining mouzas PWSS to accommodate Of T/W,LDS, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000147/2023-2024 | 1897/MURD | 17/07/2023 | 968 | M/S JAN MAHAMMAD | 520.42 | 0 | 20
1705 | Murshidabad Division | Kandi Sub-Division | Allied & Balance Work for Laying of Distribution System, & Road Restoration Damaged During Laying of UPVC Pipeline at different location of SAHAPUR PWSS in Bharatpur-I Block, of Kandi Sub-Division under Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000253/2024-2025 | 231/MURD | 27/01/2025 | 45 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 44.09 | 0 | 0
1706 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAHAPUR AND ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at BHARATPUR -I Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000401/2023-2024 | 2808/MURD | 05/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 100
1707 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | RTOR000054/2023-2024 | 1067/MURD/10 | 18/04/2023 | 0 | Resource Division | 52.37 | 0 | 0
1708 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT SAHAPUR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/00403/2024-2025 | 101/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
1709 | Berhampore Mechanical | Kandi Sub-Division | Quotation for Sahapur PH No-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/01434/2023-2024 | 324/WBSEDCL-JJM | 06/02/2024 | 0 | WBSEDCL | 12.71 | 0 | 0
1710 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I , II & III under SAHAPUR ground water based water supply scheme under Block_ Bharatpur-I, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000711/2023-2024 | 4064/MEDB | 04/12/2023 | 607 | CONCORD ENGINEERING | 36.55 | 0 | 5
1711 | Murshidabad Division | Berhampur M/E Division | Renovation of Filter Media of Existing Modified AIRP of (Capacity 180 Cum/hr.) at Garaimari Zone-I Water Supply Scheme of Domkal Block under Murshidabad Division, P.H.Eengineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000252/2024-2025 | 228/MURD | 27/01/2025 | 45 | SOM CONSTRUCTION AGENCY | 28.21 | 0 | 0
1712 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000346/2022-2023 | 1925/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 9.6 | 0 | 100
1713 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Garaimari PWSS of accommodate 1468 nos FHTC, Laying Distribution System, Laying Rising Main, Repairing & Construction of Switch Room, Repairing of Boundary Wall, Repairing of 800 CUM OHR, Construction of 250 Cum OHR in Domkal Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000754/2023-2024 | 120/MURD | 11/01/2024 | 647 | M/S R B CONSTRUCTION | 1797.55 | 0 | 40
1714 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT GARAIMARI Z-II PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01136/2024-2025 |  | 26/11/2024 | 0 | WBSEDCL | 4.01 | 0 | 0
1715 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT GARAIMARI Z-II PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01137/2024-2025 |  | 26/11/2024 | 0 | WBSEDCL | 7.33 | 0 | 0
1716 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under Gairamari ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000660/2023-2024 | 591/MEDB | 31/01/2024 | 1008 | M/S. SUPER CONSTRUCTION | 36 | 0 | 70
1717 | Murshidabad Division | Jangipur Sub-Division | Providing FHTC Connection to 322 nos household , Laying of Distribution System, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works for Augmentation work of Manigram Balarambati PWSS within Sagardighi Block under Murshidabad Division , PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000592/2023-2024 | 3340/MURD | 28/10/2023 | 520 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 96.91 | 0 | 45
1718 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional Household Connection of different existing PWSS MANIGRAM-BALARAMBATI PWSS Scheme, Block-SAGARDIGHI to be Augmentation/Rejuvination under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/002171/2021-2022 | 3250/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 4.48 | 4.48 | 50
1719 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000153/2023-2024 | 1180/MURD/28 | 29/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
1720 | Murshidabad Division | Kandi Sub-Division | BAIDYNATHPUR & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000222/2023-2024 | 2366/MURD | 04/08/2023 | 1001 | M/S.TAPAS KUMAR CHAKRABORTY | 867.57 | 173.07 | 10
1721 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000232/2023-2024 | 1219/MURD/16 | 03/05/2023 | 0 | Resource Division | 9.79 | 0 | 0
1722 | Berhampore Mechanical | Kandi Sub-Division | Baidyanathpur PH1 Application no-3004548117 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/01174/2023-2024 | 231/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 4.05 | 0 | 0
1723 | Berhampore Mechanical | Kandi Sub-Division | Baidyanathpur PH-2 Application No- 3004548228 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/01175/2023-2024 | 232/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 4.26 | 0 | 0
1724 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Baidynathpur ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000261/2023-2024 | 3697/MEDB | 03/11/2023 | 92 | P. K. ENGINEERING | 23.71 | 0 | 0
1725 | Murshidabad Division | Kandi Sub-Division | Kamalakantapur PWSS to accommodate FHTC of 1518 nos household under Jal Jeevan Mission of Bharatpur-I Block, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER |  | ORD/000255/2023-2024 | 2492/MURD | 11/08/2023 | 60 | RATAN DUTTA | 80.18 | 12.07 | 15
1726 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna ( Jal Jeevan Mission) Mouja Sibnagar Laskarpur (Village code 314702)under Sibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723328) |  |  | ORD/000283/2022-2023 | 1562/MURD | 16/06/2022 | 120 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 151.41 | 149.55 | 1
1727 | Murshidabad Division |  | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A |  |  | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 0 | 1
1728 | Murshidabad Division | Berhampur Sub-Division | Feasibility study to select a suitable location for proposed intake jetty for drawal of 23.00 MLD raw water from River Bhagirathi at Kumarpur, Beldanga-I Block. For surface water supply Scheme under Murshidabad Division in Murshidabad District. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | BILL/01075/2024-2025 | 380-MSD/2024-25 | 18/09/2024 | 0 | SYAMA PRASAD MOOKERJEE PORT, KOLKATA | 60.66 | 0 | 0
1729 | Murshidabad Division | Berhampur Sub-Division | Surveying, Sub Soil investigation , Design, Engineering, Supplying, Construction, Erection, Testing, Commissioning of Raw Water Pump House over M.S Intake barge (Floating), Bank Protection, Raw Water Rising Main, Construction of 22.1 MLD capacity Water Treatment Plant based on Conventional Technologies including Administrative Building, Substation Building ,Electro- Mechanical Works , Staff quarter & other components and SCADA on EPC turnkey basis in a single package as per detail scope of work / direction by E-I-C including 3 (Three) months Trial Run and Operation & Maintenance for 1(One) year for Surface Water Based piped W/S scheme in the uncovered areas of arsenic affected Beldanga-I Block in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000030/2024-2025 | 1883/MURD | 28/06/2024 | 822 | GBC INFRASTRUCTURE PRIVATE LIMITED | 4480 | 0 | 0
1730 | Murshidabad Division | Berhampur Sub-Division | Construction of 11 Nos. different Capacity OHR including Soil test (100,200,300,400,500,600,700,750,1000 Cum), Boundary Wall, 11 Nos Operator Shed cum chlorine room with sanitary and water supply arrangement, Laying of clear water Rising Main , Laying Distribution System, Service Road , Land Development and FHTC, Bypass arrangement of OHR for Surface Water Based Water Supply Scheme in the Uncovered areas of Beldanga-I Block, under MurshidabadDivision P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000611/2023-2024 | 3376/MURD | 31/10/2023 | 793 | M/S R B CONSTRUCTION | 7132.23 | 0 | 10
1731 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | RTOR000001/2024-2025 | MSD/1735 | 11/06/2024 | 0 | Resource Division | 6.55 | 0 | 0
1732 | Berhampore Mechanical | Berhampur Sub-Division | Supply delivery and installation of spares of High Lift Pumping Machineries at Beldanga WTP under MEDB, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000002/2025-2026 | 958/MEDB | 23/04/2025 | 30 | HARA PROSAD DAS | 8.24 | 0 | 0
1733 | Berhampore Mechanical | Berhampur Sub-Division | Providing Electrical Equipment for 11/0.433 KV Sub-station (LT Bulk & HT Bulk ) at Intake and WTP under Augmentation of Beldanga Surface Water Based W/S Scheme in the Dist. of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000143/2024-2025 | 1495/MEDB | 26/06/2024 | 183 | MAHADEV ENTERPRISE | 320.85 | 0 | 0
1734 | Berhampore Mechanical | Berhampur Sub-Division | Repairing & rectification of Centrifugal pumping machinery sets including other allied works at Beldanga Intake under MEDB, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000880/2023-2024 | 3388/MEDB | 09/11/2023 | 92 | CONCORD ENGINEERING | 13.92 | 0 | 0
1735 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Srinarayanpur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000494/2023-2024 | 3060/MURD | 29/09/2023 | 60 | DAS ENTERPRISE (SUBRATA DAS) | 32.43 | 0 | 0
1736 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Bansbere village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000497/2023-2024 | 3061/MURD | 29/09/2023 | 60 | AGNIBESH CHATTERJEE | 24.79 | 0 | 0
1737 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Saheb Nagar village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000499/2023-2024 | 3080/MURD | 03/10/2023 | 60 | NOBEL CONSTRUCTION | 32.52 | 0 | 0
1738 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Talbona village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000500/2023-2024 | 3081/MURD | 03/10/2023 | 60 | ARJU CONSTRUCTION | 32.52 | 0 | 0
1739 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Chak Ramprasad village, Block:- Jalangi, Islampur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000510/2023-2024 | 3082/MURD | 03/10/2023 | 60 | CHATTERJEE ENTERPRISE | 30.55 | 0 | 0
1740 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Durajjay Palsa village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000511/2023-2024 | 3100/MURD | 04/10/2023 | 60 | SOUMYA KANTI SINHA | 32.21 | 0 | 0
1741 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Kalikapur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000517/2023-2024 | 3612/MURD | 24/11/2023 | 60 | KUNTAL SAHA | 31.83 | 0 | 0
1742 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Padmalabhbati village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000519/2023-2024 | 3102/MURD | 04/10/2023 | 60 | SANJAY DUTTA | 28.02 | 0 | 0
1743 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Chak Palasi village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000521/2023-2024 | 3120/MURD | 05/10/2023 | 60 | SUJIT CHOWDHURY | 19.89 | 0 | 0
1744 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Mamudpur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000522/2023-2024 | 3121/MURD | 05/10/2023 | 60 | ASIT KUMAR ROY | 34.58 | 0 | 0
1745 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Hari Nagar village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000526/2023-2024 | 3122/MURD | 05/10/2023 | 792 | SANDESH CONSTRUCTION | 26.83 | 0 | 0
1746 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Kalidaspur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000529/2023-2024 | 3135/MURD | 06/10/2023 | 755 | M/S ROY & BOSE ENTERPRISE | 34.81 | 0 | 10
1747 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Daspara village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000548/2023-2024 | 3150/MURD | 09/10/2023 | 815 | MONDAL CONSTRUCTION | 31.8 | 0 | 70
1748 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Chak Gupura-Part- B village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000566/2023-2024 | 3276/MURD | 17/10/2023 | 60 | FIROJ AHAMMED BISWAS | 22.09 | 0 | 0
1749 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Kalidaspur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000567/2023-2024 | 3277/MURD | 17/10/2023 | 793 | JIYAUL HAQUE | 32.83 | 0 | 0
1750 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Khansama Danga village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000595/2023-2024 | 3350/MURD | 30/10/2023 | 60 | CREATIVE | 24.03 | 0 | 0
1751 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Bajitpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000598/2023-2024 | 3351/MURD | 30/10/2023 | 60 | SOUNAK ENTERPRISE | 34.62 | 0 | 0
1752 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Gopalpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000599/2023-2024 | 3352/MURD | 30/10/2023 | 60 | M/S ATISH SINHA | 30.15 | 0 | 0
1753 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Rasulpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000602/2023-2024 | 3364/MURD | 31/10/2023 | 60 | SUDIPTA GHOSH | 34.01 | 0 | 0
1754 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Katigram village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000604/2023-2024 | 3365/MURD | 31/10/2023 | 640 | M/S. BOJLUR RAHAMAN | 26.08 | 0 | 40
1755 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Srikrishnapur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000605/2023-2024 | 3366/MURD | 31/10/2023 | 60 | M/S MONDAL ASSOCIATES | 32.52 | 0 | 0
1756 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Raghunathpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000606/2023-2024 | 3367/MURD | 31/10/2023 | 60 | DEBEN RAJAK | 27.1 | 0 | 10
1757 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Gangarampur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000607/2023-2024 | 3368/MURD | 31/10/2023 | 793 | M/S HALDAR CONSTRUCTION (PROP:- ANIRBAN HALDAR ) | 32.52 | 0 | 90
1758 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT GANGARAMPUR, MOUZA RAHIGRAM PH 1 C ID 304440129 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | BILL/00998/2024-2025 |  | 11/09/2024 | 0 | WBSEDCL | 0.79 | 0 | 0
1759 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PH1 AT RAGHUNATHPUR PO SADAI PS KHARGRAM C ID 304439890 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | BILL/00999/2024-2025 |  | 11/09/2024 | 0 | WBSEDCL | 0.83 | 0 | 0
1760 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT KATIGRAM, MOUZA KATIGRAM PH 1 MOUZA GURULIA C ID 304440127 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | BILL/01000/2024-2025 |  | 11/09/2024 | 0 | WBSEDCL | 0.55 | 0 | 0
1761 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PH1 AT RAGHUNATHPUR PO SADAI PS KHARGRAM C ID 304439890 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | BILL/01001/2024-2025 | 218/WBSEDCL-JJM | 13/09/2024 | 0 | WBSEDCL | 0.83 | 0 | 0
1762 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT KATIGRAM, MOUZA KATIGRAM PH 1 PS KHARGRAM GURULIA ID 304440127 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | BILL/01002/2024-2025 | 219/WBSEDCL-JJM | 13/09/2024 | 0 | WBSEDCL | 0.55 | 0 | 0
1763 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT GANGARAMPUR, MOUZA RAHIGRAM PH 1 C ID 304440129 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | BILL/01003/2024-2025 | 220/WBSEDCL-JJM | 13/09/2024 | 0 | WBSEDCL | 0.79 | 0 | 0
1764 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT SAHEBNAGAR MINI PWSS PH 1 ID 304489077 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | BILL/01147/2024-2025 |  | 27/11/2024 | 0 | WBSEDCL | 0.67 | 0 | 0
1765 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Palasi village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000808/2023-2024 | 3627/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0
1766 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Gopalpur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000809/2023-2024 | 3634/MEDB | 03/11/2023 | 92 | SARKAR CONSTRUCTION | 6.3 | 0 | 0
1767 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kalidaspur village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000813/2023-2024 | 3637/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE (CHOA) | 6.3 | 0 | 0
1768 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Pachim Kalidaspur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000814/2023-2024 | 3638/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.3 | 0 | 0
1769 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kalikapur village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000815/2023-2024 | 3639/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.3 | 0 | 0
1770 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Katigram village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000817/2023-2024 | 3640/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.3 | 0 | 90
1771 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Khansama Danga village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000820/2023-2024 | 3642/MEDB | 03/11/2023 | 92 | MASSK ENGINEERING WORKS | 6.15 | 0 | 0
1772 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Mamudpur village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000823/2023-2024 | 3644/MEDB | 03/11/2023 | 92 | JOY BISHNU ENGINEERING CO. | 6.3 | 0 | 0
1773 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hari Nagar village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000825/2023-2024 | 3645/MEDB | 03/11/2023 | 92 | EASTERN INDIA SALES & SERVICE | 6.27 | 0 | 0
1774 | Berhampore Mechanical | Kandi Sub-Division | Name of Work: Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Pachim Srikrishnapur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000828/2023-2024 | 3647/MEDB | 03/11/2023 | 92 | ALAK KUMAR CHAKRABORTY | 6.15 | 0 | 0
1775 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Raghunathpur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000835/2023-2024 | 3649/MEDB | 03/11/2023 | 92 | S.P. ENTERPRISE (BAGUIHATI) | 6.27 | 0 | 0
1776 | Berhampore Mechanical | Kandi Sub-Division | Name of Work: Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Rasulpur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000840/2023-2024 | 3653/MEDB | 03/11/2023 | 92 | SURAKSHA | 6.3 | 0 | 0
1777 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Saheb Nagar village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000841/2023-2024 | 3654/MEDB | 03/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0
1778 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Srinarayanpur village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000843/2023-2024 | 3656/MEDB | 03/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0
1779 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Talbona village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000845/2023-2024 | 3658/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.3 | 0 | 0
1780 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Daspara village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000847/2023-2024 | 3630/MEDB | 03/11/2023 | 92 | MERCURY ENGINEERING CO | 6.33 | 0 | 0
1781 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Durajjay Palsa village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000848/2023-2024 | 3631/MEDB | 03/11/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0
1782 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Gangarampur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000849/2023-2024 | 3632/MEDB | 03/11/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 85
1783 | Berhampore Mechanical | Kandi Sub-Division | Name of Work: Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Padmalabhbati village, Block- Burwan under ground water based mini piped water supply scheme, Dist- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/001488/2023-2024 | 768/MEDB | 20/02/2024 | 90 | ARINDAM MAJUMDAR | 6.14 | 0 | 0
1784 | Murshidabad Division | Berhampur M/E Division | Construction of 700 Cum OHR, Pump House, Boundary wall & Repairing of Pump House for Augmentation of Herampur Zone-I PWSS in Raninagar-I Block , Islampur Sub-Division under Murshidabad Division ,PHE.Dte._PART_B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000297/2023-2024 | 2647/MURD | 23/08/2023 | 819 | SATELLITE CONSTRUCTION | 257.98 | 0 | 20
1785 | Murshidabad Division | Berhampur M/E Division | Augmentation Work Laying Distribution System, Rising Main Connection, FHTC of Herampur Zone-I PWS in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte. (PART - A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000572/2023-2024 | 3296/MURD | 20/10/2023 | 893 | J.S. CONSTRUCTION | 443.2 | 65.16 | 20
1786 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KUPILA Water Supply Scheme and Herampur Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000695/2023-2024 | 3768/MURD | 08/12/2023 | 21 | MAMATA USHA ENTERPRISE | 11.79 | 0 | 100
1787 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 4.44 | 100
1788 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000230/2023-2024 | 1219/MURD/20 | 03/05/2023 | 0 | Resource Division | 109.49 | 0 | 0
1789 | Berhampore Mechanical | Berhampur M/E Division | QUOTATION FOR SHIFTING OF 1 NO PHE 25KVA DTR AT HERAMPUR REF ID. 860310611 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00652/2024-2025 |  | 16/08/2024 | 0 | WBSEDCL | 7.2 | 0 | 0
1790 | Berhampore Mechanical | Berhampur M/E Division | QUOTATION FOR SHIFTING OF 1 NO PHE 25KVA DTR AT HERAMPUR REF ID. 860310611 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00654/2024-2025 | 197/WBSEDCL-JJM | 22/08/2024 | 0 | WBSEDCL | 7.2 | 0 | 0
1791 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Ramchandrapur (Habitation ID-0001294189 ) in the village of Ramchandrapur (Village code 314219) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000223/2020-2021 | 987/BD-I | 17/12/2020 | 90 | KAMIRUL SK AND CO. | 28.26 | 0 | 0
1792 | Murshidabad Division | Kandi Sub-Division | CONSTRUCTION OF ROAD FROM GOKARNA TO ASOLAMPUR, PACKAGE NO- WB-13 -365, LENG- 10.215 KM , BLOCK KANDI, IN THE DIST MUSHIDABAD | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01077/2024-2025 | 403-MSD/2024-25 | 23/09/2024 | 0 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 5.19 | 0 | 0
1793 | Murshidabad Division | Kandi Sub-Division | Laying of UPVC pipeline from Head Work Site to Node point 16, laying of parallel line for FHTC work and Construction of approach road of UDAYCHANDPUR & Adjoining Mouzas Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000056/2024-2025 | 1987/MURD | 08/07/2024 | 450 | MARUTI CONSTRUCTION AND CO. | 76.01 | 0 | 40
1794 | Murshidabad Division | Kandi Sub-Division | Construction of Boundary Wall & Pump House with sanitary & plumbing work (H.W & 4th T/W Site) of Mahalandi (Zone-I) Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000084/2024-2025 | 2088/MURD | 23/07/2024 | 60 | AHAMMED ENTERPRISE | 21.22 | 0 | 0
1795 | Murshidabad Division | Kandi Sub-Division | Laying of Distribution System (Part-A), Construction of Over Head Reservoir (400 Cum), Pump House (3rd Site), Boundary wall (3rd Site), Repairing of Pump House & Boundary wall (H.W & 2nd Site), Repairing of Over Head Reservoir (250 Cum) and accommodate FHTC work at Mahalandi Village (Village Code-315231) for Augmentation of MAHALANDI (ZONE-I) Water Supply Scheme of Kandi Block under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000471/2023-2024 | 3014/MURD | 26/09/2023 | 828 | PREKSHITA CONSTRUCTION | 248.32 | 12.19 | 10
1796 | Murshidabad Division | Kandi Sub-Division | Laying of Distribution System (Part-B) and FHTC work at Mahalandi Village (Village Code-315231) & Durlabhpur Village (Village Code-315218) for Augmentation of MAHALANDI (ZONE-I) Water Supply Scheme in Kandi Block under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000481/2023-2024 | 3052/MURD | 29/09/2023 | 693 | PRIYANKA CONSTRUCTION | 286.61 | 0 | 20
1797 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000068/2022-2023 | 1043/MURD/7 | 17/04/2023 | 0 | Resource Division | 84.58 | 0 | 0
1798 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000314/2023-2024 | 1936/MURD | 18/07/2023 | 0 | Resource Division | 84.58 | 0 | 0
1799 | Berhampore Mechanical | Kandi Sub-Division | AT MAHALANDI PH 3 ID 304239410 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01473/2023-2024 | 371/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 3.31 | 0 | 0
1800 | Berhampore Mechanical | Kandi Sub-Division | NEW SER VICE CONNECTION AT MAHALANDI PH 3 ID 304239410 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01491/2023-2024 |  | 16/02/2024 | 0 | WBSEDCL | 3.31 | 0 | 0
1801 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV ,Zone-I under MAHALANDI ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000287/2023-2024 | 583/MEDB | 31/01/2024 | 336 | CONCORD ENGINEERING | 48.03 | 0 | 40
1802 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Dakshin Hanumantanagar ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000102/2022-2023 | 1359/BD-I | 21/12/2022 | 30 | PRANAB KUMAR GHOSH | 3.8 | 0 | 72
1803 | Berhampore Division I | Berhampur Division I | Augmentation of DAKSHIN HANUMANTANAGAR Piped water supply scheme to accommodate construction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000193/2023-2024 | 744/BD-I | 17/08/2023 | 1059 | M/S SINHA & SONS | 478.03 | 0 | 45
1804 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DAKSHIN HANUMANTANAGAR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000877/2021-2022 | 261/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.77 | 0 | 100
1805 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000063/2023-2024 | 196/BD-I/10 | 09/02/2024 | 0 | Resource Division | 102.96 | 0 | 0
1806 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of DAKSHIN HANUMANTNAGAR ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000818/2023-2024 | 3767/MEDB | 03/11/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 11.19 | 0 | 10
1807 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 15.3 | 20
1808 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augmentation of Bansgara Zone-I PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000045/2024-2025 | 1068/BD-I | 03/07/2024 | 300 | MAHATO ENTERPRISE | 9 | 0 | 75
1809 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road & extension of boundary wall of Bansgara Zone-I PWSS under Jal Jeevan Mission within Raninagar-II block under Berhampore Division-I PHE Dte. in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000076/2025-2026 | 843/BD-I | 23/06/2025 | 45 | SUBHRANIL DAS | 17.81 | 0 | 0
1810 | Berhampore Division I | Raghunathganj Sub-Division | BANSGARA ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000084/2024-2025 | 1245/BD-I | 30/07/2024 | 180 | M.K.CONSTRUCTION | 22.29 | 0 | 30
1811 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of BANSGARA ZONE-I Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000142/2023-2024 | 628/BD-I | 04/08/2023 | 310 | SUNIL RABI DAS | 388.8 | 141.55 | 10
1812 | Berhampore Division I | Raghunathganj Sub-Division | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for Bansgara Zone-I of Raninagar-II block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000248/2023-2024 | 1032/BD-I | 01/11/2023 | 30 | ALOK BANERJEE ENTERPRISE | 6.83 | 0 | 80
1813 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000264/2022-2023 | 1687/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.73 | 2.76 | 1
1814 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA ZONE-I Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000276/2022-2023 | 1759/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.6 | 2.6 | 100
1815 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000011/2023-2024 | 61/BD-1/10 | 27/04/2023 | 0 | Resource Division | 30.97 | 0 | 0
1816 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000081/2023-2024 | 201/BD-1/22 | 10/02/2024 | 0 | Resource Division | 83.89 | 0 | 0
1817 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW SERVICE CONNECTION AT BANSGARA Z1 PH 1 ID 304268983 | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | BILL/01129/2024-2025 |  | 26/11/2024 | 0 | WBSEDCL | 11.36 | 0 | 0
1818 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 13.98 | 11
1819 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of RAMPARA FARIDPUR ZONE - II PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000021/2025-2026 | 638/BD-I | 25/04/2025 | 60 | MASTER CONSTRUCTION | 18.98 | 0 | 0
1820 | Berhampore Division I | Berhampur M/E Division | Improvement of Existing AIRP (Capacity 68 Cum/hr.) with allied work at Rampara Faridpur (Zone-I) Water Supply Scheme under Jal Jeevan Mission within Beldanga - II under Berhampore Division-I, P.H.Engineering Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000050/2025-2026 | 759/BD-I | 22/05/2025 | 30 | SANJAY BISWAS | 27.45 | 0 | 0
1821 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMPARA FORIDPUR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000191/2023-2024 | 720/BD-I | 14/08/2023 | 10 | TECHVISION | 2.81 | 2.81 | 100
1822 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Rampara Faridpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000253/2024-2025 | 2249/BD-I | 10/12/2024 | 30 | M/S B.R. SUPPLIERS | 9 | 0 | 0
1823 | Berhampore Division I | Berhampur M/E Division | Augmentation of Rampara Faridpur Piped water supply scheme to accommodate construction of OHR ,Arsenic cum Iron Removal Plant(AIRP) and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga -II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000288/2023-2024 | 1017/BD-I | 31/10/2023 | 793 | SANJAY BISWAS | 558.97 | 0 | 65
1824 | Berhampore Division I | Berhampur M/E Division | RAMPARA FARIDPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, under Jal Jeevan Mission within BELDANGA-II Block in the district of Murshidabad under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000382/2024-2025 | 444/BD-I | 20/03/2025 | 45 | DATA ENTERPRISE | 9.84 | 0 | 0
1825 | Berhampore Division I | Berhampur M/E Division | RAMPARA FARIDPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000456/2023-2024 | 460/BD-I | 15/03/2024 | 480 | SAHA CONSTRUCTION | 22.63 | 0 | 75
1826 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000107/2023-2024 | 201/BD-1/8 | 10/02/2024 | 0 | Resource Division | 36.69 | 0 | 0
1827 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT RAMPARA FARIDPUR PH-1 | ASSISTANT ENGINEER-I | Junior engineer-III | BILL/00615/2024-2025 | 182/WBSEDCL-JJM | 09/08/2024 | 0 | WBSEDCL | 3.66 | 0 | 0
1828 | Murshidabad Division | Berhampur M/E Division | Restoretion of Road State Highway at Najairpur to Islampore Road from chainge 0.00 kmp to 1.350 km shoulder damage amounting to Rs 637462.00 and Akheriganj to Katlamari road from chainge 8.00 km to 9.30 km. | ASSISTANT ENGINEER-I | Junior engineer-II | BILL/01231/2024-2025 | 492-MSD/2024-25 | 04/10/2024 | 0 | EXECUTIVE ENGINEER , MURSHIDABAD HIGHWAY DIVISION -I, PWD (ROADS) DIRECT. GOV OF W.B | 34.8 | 0 | 0
1829 | Murshidabad Division | Berhampur M/E Division | Engagement of Consultant for Field Data collection, pipeline network analysis by analyzing actual household demand in pipeline sections, identification of low pressure areas with in the pipe network system and proposing probable solution of the same in 2(Two) nos water supply schemes in Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000071/2024-2025 | 2022/MURD | 11/07/2024 | 45 | DHPE | 15.34 | 0 | 25
1830 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Islampur PWSS Laying Distribution System, Laying Rising Main in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte. PART_A | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000249/2023-2024 | 2465/MURD | 09/08/2023 | 719 | M/S GUHA AND ROY | 333.65 | 110.8 | 25
1831 | Murshidabad Division | Berhampur M/E Division | Augmentation of Islampur PWSS Repairing of Boundary Wall, Pump House & Existing OHR, Construction of 900 Cum OHR, P.H, B.W in Raninagar-I Block , under Murshidabad Division , PHE.Dte.PART_B | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000316/2023-2024 | 2673/MURD | 24/08/2023 | 365 | M/S. UDYOG AND CO | 335.68 | 0 | 0
1832 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000346/2022-2023 | 1925/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 9.6 | 0 | 100
1833 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Islampur PWSS of accommodate Providing Functional Household Tap Connection (1394 Nos) in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte.PART_C | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000355/2023-2024 | 2669/MURD | 24/08/2023 | 90 | M/S B.M. INDUSTRIES | 182.87 | 0 | 31
1834 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000233/2023-2024 | 1219/MURD/07 | 03/05/2023 | 0 | Resource Division | 551.66 | 0 | 0
1835 | Berhampore Mechanical | Berhampur M/E Division | LOAD ENHANCEMENT ISLAMPUR APPLICATION NO.3004629164 | ASSISTANT ENGINEER-I | Junior engineer-II | BILL/00177/2024-2025 | 13/WBSEDCL-JJM | 16/04/2024 | 0 | WBSEDCL | 0.28 | 0 | 0
1836 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under Islampur ground water based water supply scheme under Block_ Raninagar-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000661/2023-2024 | 3708/MEDB | 03/11/2023 | 92 | R.M.D TRADING | 34.48 | 0 | 0
1837 | Murshidabad Division | Kandi Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Satitara T.W- IV,V,VI, Fatepur T.W.-II, Kapasdanga T.W-II Water Supply Scheme of Burwan Block under Kandi Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000500/2024-2025 | 664/MURD | 19/03/2025 | 65 | NADIA TUBEWELLS | 70.43 | 0 | 0
1838 | Murshidabad Division | Kandi Sub-Division | Augmentation of SATITARA under Jal Jeevan Mission of BURWAN Block, Kandi Sub Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000571/2023-2024 | 3291/MURD | 19/10/2023 | 713 | M/S. S. DAS AND ENTERPRISE | 1459.34 | 142.64 | 10
1839 | Murshidabad Division | Kandi Sub-Division | Demolition of damaged R.C.C. Elevated Reservoir (Capacity 2,72,400 Ltr) at Satitara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000721/2023-2024 | 3874/MURD | 18/12/2023 | 30 | DIPAYAN DEY | 5.35 | 5.35 | 100
1840 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000370/2023-2024 | MURD/439/05 | 08/02/2024 | 0 | Resource Division | 4.1 | 0 | 0
1841 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 8 | 11
1842 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Illampur Village (Code-314175) In The Command Area Of Maiya Ground Water Supply Scheme (Part-B) Under Lalgola Block In Murshidabad District" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000104/2024-2025 | 1436/BD-I | 04/09/2024 | 30 | DAS CONSTRUCTION 13/1/2 UKILABAD ROAD, BERHAMPORE | 15.6 | 0 | 0
1843 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ilimpur (Village code 314175) under Maia Ground Water Supply Scheme of Lalgola Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000139/2020-2021 | 239/BD-I | 10/02/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 66.88 | 122.7 | 10
1844 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Kazipara Village (Code-314608) Under Command Area Of Kazipara Ground Water Supply Scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000080/2024-2025 | 1228/BD-I | 29/07/2024 | 60 | M/S S. DAS & ENTERPRISE | 74.15 | 0 | 0
1845 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kazipara (Village code 314608) under Kazipara Water Supply Scheme of Jalangi Block and village of Ramnagar Doemkanun (Village code 314578) under Ramnagar Doemkanun Water Supply Scheme of Raninagar-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000838/2021-2022 | 49/BD-I | 27/01/2022 | 180 | M/S S.DAS & ENTERPRISE | 337.04 | 0 | 1
1846 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer-II | RTOR000008/2021-2022 | 143/BD-I | 10/02/2022 | 0 | Resource Division | 13.51 | 0 | 0
1847 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) of mouza Sabdalpur ( 314704 ) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Division. PHE DTE.(SCHEME ID : 0001723328) TENDER NO 89 OF 20-21 BY SE / MC |  |  | VCH/000193/2021-2022 | 09 - MSD/21-22 | 04/08/2021 | 0 | M/S. GOUTAM CHAKRABORTY | 38.65 | 0 | 0
1848 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sabdalpur (Village code 314704) under Shibnagar Laskarpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723328 in the District of Murshidabad. (Sl No-20) |  |  | VCH/000693/2022-2023 | 218-MSD/22-23 | 27/07/2022 | 0 | M/S. GOUTAM CHAKRABORTY | 26.57 | 0 | 0
1849 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Udaynagar Diar ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | JE | ORD/000173/2024-2025 | 2038/BD-I | 12/11/2024 | 30 | SHIV SHAKTI CONSTRUCTION | 9.1 | 0 | 100
1850 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Udaynagar Diar (Village code 314613) under Udaynagar Diar Ground Water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | JE | ORD/000181/2020-2021 | 918/BD-I | 10/12/2020 | 90 | M/S S.DAS & ENTERPRISE | 34.84 | 39.5 | 0
1851 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Azimpur (Village code 314612) under Udaynagar Diar Ground Water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-09 of 2020 - 2021,SL-01). | Assistant Engineer | JE | ORD/000240/2020-2021 | 73 /BD-I | 19/01/2021 | 20 | M/S ROY & BOSE ENTERPRISE | 7.67 | 6.18 | 0
1852 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jumra Nayagram (Village Code-314190) and others under Jumra Nayagram Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000115/2021-2022 | 917/BD-I | 19/05/2021 | 20 | MODERN CONSTRUCTION | 4.63 | 0 | 0
1853 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL JEEVAN MISSION under command area Jumra Nayagram (VillageCode-314190) in Jumra Nayagram ground water supply scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000188/2024-2025 | 2196/BD-I | 02/12/2024 | 15 | MAHAMAYA ENTERPRISE | 1.95 | 0 | 0
1854 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jumra Nayagram (Village code 314190) under Jumra Nayagram Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000201/2020-2021 | 966/BD-I | 17/12/2020 | 90 | MODERN CONSTRUCTION | 43.07 | 78.14 | 1
1855 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Hurshi zone-I ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte | Assistant Engineer | Junior Engineer-II | ORD/000174/2024-2025 | 2089/BD-I | 22/11/2024 | 30 | REDSEA CONSTRUCTION | 3.79 | 0 | 0
1856 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Daulatpur (Village code 314749) under Hurshi Zone-I Ground Water Supply Scheme in Raninagar-I Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-11) | Assistant Engineer | Junior Engineer-II | ORD/000272/2021-2022 | 1143/BD-I | 07/07/2021 | 180 | KAMIRUL SK AND CO. | 71.98 | 20.6 | 0
1857 | Berhampore Division I | Raghunathganj Sub-Division | Additional Laying works at village BEGAMPUR (village code 314750) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Hurshi Zone-I Ground water supply scheme (Raninagar-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer | Junior Engineer-II | ORD/000567/2021-2022 | 1920/BD-I | 08/10/2021 | 10 | M/S SAJAHAN CHOWDHURY | 5.99 | 4.59 | 1
1858 | Murshidabad Division |  | Protection of Head work site premises by raising Boundary wall height by R.B.T fencing with Approach Road under Bilashpur Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. |  |  | ORD/001238/2021-2022 | 44/ISD | 28/01/2022 | 30 | PARUL ELECTRICAL INSTALLER | 3.95 | 3.86 | 1
1859 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --BHALKUNDI-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- SAMANDI , CODE-315122, TNO- 573/2020-21/EE |  |  | VCH/002014/2020-2021 | 473/W | 08/03/2021 | 0 | APURBA SAHA CHOWDHURY | 16.4 | 0 | 0
1860 | Murshidabad Division |  | LAND DEVELOPMENT AT HW SITE OF MAHALANDI Z-II WSS, TNO- 551/20-21/EE |  |  | VCH/002053/2020-2021 | 479/W | 12/03/2021 | 0 | APURBA SAHA CHOWDHURY | 4.76 | 0 | 0
1861 | Murshidabad Division |  | SANITARY & PLUMBING ARRANGEMENT....HW SITE OF BAHARA WSS, TNO- 06/20-21/AE-KSD |  |  | VCH/002054/2020-2021 | 479/W | 12/03/2021 | 0 | AYAN ENTERPRISE | 1.19 | 0 | 0
1862 | Murshidabad Division |  | LAYING OF UPVC PIPELINE FOR DIST SYSTEM...VULNERABLE POINT OF GOPAL NAGAR PRY.. SCHOOL.. UNDER DEULI OHR, RAGHUNATHGANJ SURFACE WSS, TNO- 072/20-21/EE |  |  | VCH/002055/2020-2021 | 479/W | 12/03/2021 | 0 | DEBASIS BOSE | 3.2 | 0 | 0
1863 | Murshidabad Division |  | HIRING OF CAR BILL FOR AE-ISD, W/O NO- 200/ISD, DT- 25/09/2020 |  |  | VCH/002056/2020-2021 | 479/W | 12/03/2021 | 0 | MADAN MOHAN SASMAL | 0.77 | 0 | 0
1864 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of ---BHALKUNDI--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - MATAI CODE- 315090 , TNO- 625/20-21/EE |  |  | VCH/002057/2020-2021 | 479/W | 12/03/2021 | 0 | M/S UNIQUE BUILDERS | 11.41 | 0 | 0
1865 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Naudaparavillage (Code-314456) In The Command Area Of Paschim Rampur Ground Water Supply Scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000101/2024-2025 | 1439/BD-I | 04/09/2024 | 30 | KUNTAL SAHA | 10.13 | 0 | 0
1866 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naodapara(Village code 314456) under Paschim Rampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-I | JE | ORD/000103/2020-2021 | 169/BD-I | 03/02/2021 | 20 | M/S SINHA & SONS | 38.69 | 29.48 | 1
1867 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Lakshminathpur (Village code 314696) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. (Sl No-01) |  |  | ORD/000349/2021-2022 | 2500/MURD | 17/08/2021 | 120 | SUJIT KUMAR SAHA | 65.1 | 64.44 | 0
1868 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 329 in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lakshminathpur (Village code 314696) under Domkal Ground water based water supply scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005184127). |  |  | ORD/001708/2021-2022 | 693/MURD | 14/03/2022 | 30 | SUJIT KUMAR SAHA | 19.11 | 0 | 1
1869 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SARBANGAPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- PARESNATHPUR , CODE-315529, TNO- 604/2020-21/EE |  |  | VCH/002015/2020-2021 | 512/W | 30/03/2021 | 0 | RATAN DUTTA | 25.78 | 0 | 0
1870 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --AMARKUNDU-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- RAINDA , CODE- 315025, TNO- 684/2020-21/EE |  |  | VCH/002019/2020-2021 | 512/W | 30/03/2021 | 0 | SAMAR MUKHERJEE | 21.62 | 0 | 0
1871 | Murshidabad Division |  | Additional works for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kalabaria ( Village Code -314662) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184127) |  |  | ORD/000299/2021-2022 | 1932/MURD | 22/07/2021 | 60 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 13.35 | 13.24 | 0
1872 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village KALABARIA (Village Code 314662) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad. |  |  | ORD/000642/2020-2021 | 2572/MURD | 01/10/2020 | 45 | NATIONAL ENTERPRISE | 20.28 | 0 | 0
1873 | Murshidabad Division |  | Balanced and Allied Works for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Domkol (Village code 314695) under Domkol Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184127 in the District of Murshidabad. |  |  | ORD/001650/2021-2022 | 309/MURD | 07/02/2022 | 60 | ARINDAM MAJUMDAR | 35.08 | 14.06 | 0
1874 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village DOMKAL (Village Code-314695) under DOMKAL Ground based Water Supply Scheme for Aesenic Affected area of Domkal Block under Murshidabad District under Murshidabad Division, PHE Dte. (Scheme Id 0005184127) in the dist of MSD. |  |  | VCH/000232/2021-2022 | 28-MSD / 21-22 | 25/08/2021 | 0 | ARINDAM MAJUMDAR | 14.32 | 0 | 0
1875 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BARABIL RAGHUNAR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 87 /2020-21/SE-MC |  |  | VCH/002023/2020-2021 | 512/W | 30/03/2021 | 0 | MITRA CONSTRUCTION | 55.47 | 0 | 0
1876 | Murshidabad Division |  | Extension of Distribution UPVC pipeline and allied works for providing balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of mouzaAzmatpur ( Village Code -314776) of Azmatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme I.D.- 0005019112). (PART-I) |  |  | ORD/000287/2022-2023 | 276/ISD | 27/06/2022 | 30 | ROY CONSTRUCTION (PROP:AVIJIT ROY) | 4.75 | 4.17 | 1
1877 | Murshidabad Division |  | Extension of Distribution UPVC pipeline and allied works for providing balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of mouzaAzmatpur ( Village Code -314776) of Azmatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme I.D.- 0005019112). (PART-II) |  |  | ORD/000328/2022-2023 | 277/ISD | 27/06/2022 | 30 | JAYANTA KUMAR ROY | 4.72 | 4.05 | 1
1878 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Natkuli (Village code 314779) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000500/2020-2021 | 3230/MURD | 22/12/2020 | 60 | PAL TROCKNER (P) LTD. | 24.64 | 0 | 1
1879 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Firojpur (Village code 314774) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000534/2020-2021 | 92/MURD | 08/01/2021 | 60 | DEBEN RAJAK | 5.58 | 0 | 1
1880 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ichhabpur (Village code 314777) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005019112 in the District of Murshidabad. |  |  | ORD/000556/2020-2021 | 326/MURD | 28/01/2021 | 60 | NOBEL CONSTRUCTION | 6.11 | 0 | 0
1881 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Firojpur (Village code 314774) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000609/2020-2021 | 92 /MURD | 08/01/2021 | 60 | DEBEN RAJAK | 5.58 | 4.68 | 1
1882 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandpur (Village code 314772) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000610/2020-2021 | 89/MURD | 08/01/2021 | 60 | HARUN ALL RASHID & BROTHERS | 7.25 | 0 | 0
1883 | Murshidabad Division |  | Laying of distribution system pipe line and connection with street stand post and Construction of soak well in connection with Dengue control for different Anganwadi Centres under Nowda Development Block 1 Chandpur kuthipara 2. Kulaichandi 3. Rathtalapara 4. Goghata uttarpara 5. Ghoghata ghatpara 6. Ghoghata halderpara 7.Chandpur Halderpara 8.Chandpur dey biswaspara. under Berhampore Sub division. P.H.E.Dte. |  |  | ORD/000742/2020-2021 | 3202/MURD | 18/12/2020 | 15 | PRANAB KUMAR GHOSH | 4.87 | 4.24 | 1
1884 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village Char Hulaspur (Village code 314770) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000784/2020-2021 | 90./MURD | 08/01/2021 | 60 | SAMRAT MAZUMDER | 6.96 | 0 | 0
1885 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Raosannagar (Village code 314771) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000785/2020-2021 | 91./MURD | 08/01/2021 | 60 | AJAY MONDAL | 9.01 | 0 | 0
1886 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village Paharpur (Village code 314773) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000786/2020-2021 | 3231/MURD | 22/12/2020 | 60 | PAL TROCKNER PVT. LTD. | 33.51 | 0 | 0
1887 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mision (JJM) from existing distribution system within the command area of Village ICHHABPUR (Village Code- 314777) under AZMATPUR Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block under Murshidabad District under Murshidabad Division, PHE Dte. Scheme id - 0005019112. Tender no- 797 of 20-21 by EE / MURD |  |  | VCH/000201/2021-2022 | 14-MSD / 21-22 | 06/08/2021 | 0 | NOBEL CONSTRUCTION | 4.66 | 0 | 0
1888 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village NATKULI (Village Code 314779) under AZMATPUR Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-I Block in the District of Murshidabad. Tender no - 941 of 20-21 by EE MURD |  |  | VCH/001485/2021-2022 | 422-MSD/21-22 | 23/03/2022 | 0 | PAL TROCKNER (P) LTD. | 20.51 | 0 | 0
1889 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Ramnagar ( Village Code -315658) under Bachhara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga_II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000082/2021-2022 | 1562/MURD | 24/06/2021 | 60 | M/S. CHOWDHURY CONSTRUCTION | 41.52 | 26.92 | 1
1890 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bidupara ( Village Code -315659) under Bachhara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000181/2021-2022 | 1568/MURD | 25/06/2021 | 60 | M/S GUHA & ROY ENTERPRISE | 36.04 | 71.85 | 1
1891 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bachhara ( Village Code -315653) under Bachhara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga_II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000182/2021-2022 | 1571/MURD | 25/06/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 68.02 | 56.21 | 1
1892 | Murshidabad Division | Berhampur Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000450/2021-2022 | 300/BSD | 13/08/2021 | 30 | IMAGIN | 4.34 | 8.68 | 0
1893 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RAMNAGAR BACHHARA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000508/2021-2022 | 343/BSD | 27/08/2021 | 30 | M/S. S. DAS AND ENTERPRISE | 4.16 | 4.16 | 1
1894 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mohammadpur ( Village Code -315650) under Bachhara Ground WaterBased Water Supply Scheme for Arsenic Affected Areas of Beldanga_II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001160/2021-2022 | 1569 /MURD | 25/06/2021 | 60 | M/S GUHA & ROY ENTERPRISE | 43.43 | 20.21 | 1
1895 | Murshidabad Division | Berhampur Sub-Division | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar (village code 315658) under Bachhara Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001732/2021-2022 | 92/BSD | 07/03/2022 | 15 | SUMAN CHOWDHURY | 4.83 | 0 | 0
1896 | Murshidabad Division | Berhampur Sub-Division | Laying of different dia (75mm & 90mm) UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar (village code 315658) under Bachhara Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001734/2021-2022 | 93/BSD | 07/03/2022 | 15 | SUMAN CHOWDHURY | 4.85 | 0 | 0
1897 | Murshidabad Division | Berhampur Sub-Division | Laying of different dia 75 mm and 90mm dia UPVC pipeline in connection providing FHTC in connection with JJM and JS under command area of vilage of Ramnagar (Village code 315658) under Bachhara W/S Scheme in MSD PH DTE. Tender no - 186 of 21-22 by AE BSD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000015/2022-2023 | 18-MSD/22-23 | 21/04/2022 | 0 | SUMAN CHOWDHURY | 4.84 | 0 | 0
1898 | Murshidabad Division | Berhampur Sub-Division | Laying of 110 mm dia UPVC pipeline in connection providing FHTC in connection with JJM and JS under command area of vilage of Ramnagar (Village code 315658) under Bachhara W/S Scheme in MSD PH DTE. Tender no - 185 of 21-22 by AE BSD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000016/2022-2023 | 17-MSD/22-23 | 21/04/2022 | 0 | SUMAN CHOWDHURY | 4.83 | 0 | 0
1899 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BACHHARA (Village Code 315653) under BACHHARA Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block in the District of Murshidabad. Tender no - 342 of 21-22 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000378/2022-2023 | 151-MSD/22-23 | 11/05/2022 | 0 | SWAPAN DAS | 39.79 | 0 | 0
1900 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village RAMNAGAR HABITATION (Village Code 315658) under BACHHARA Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block in the District of Murshidabad. Tender no - 274 of 21-22 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001464/2021-2022 | 361-MSD/21-22 | 11/03/2022 | 0 | M/S. CHOWDHURY CONSTRUCTION | 14.54 | 0 | 0
1901 | Murshidabad Division | Berhampur Sub-Division | Additional work of providing Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BIDUPARA (Village Code 315659) under BACHHARA Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block in the District of Murshidabad. Tender no - 344 of 21-22 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001550/2021-2022 | 365-MSD/21-22 | 12/03/2022 | 0 | MITHUN ROY | 26.44 | 0 | 0
1902 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Kamnagar Village (Code-315621), Saharbati Village (Code-315625) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000078/2024-2025 | 1226/BD-I | 29/07/2024 | 60 | SARKAR BROTHERS | 12.07 | 0 | 0
1903 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamnagar (Village code 315621),Saharbati (Village code 315624) under Charkamnagar Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-II | Junior Engineer-II | ORD/000122/2020-2021 | 194/BD-I | 04/02/2021 | 30 | RAJ KUMAR MONDAL | 98.71 | 98.1 | 97
1904 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Saharbati of Kamnagar G.P to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Charkamnagar Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II | Junior Engineer-II | ORD/000777/2021-2022 | 2291/BD-I | 28/12/2021 | 10 | RAJ KUMAR MONDAL | 7.63 | 7.61 | 1
1905 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhau Danga (Village code 314195), under Rajarampur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | Assistant Engineer-I | JE | ORD/000114/2020-2021 | 186/BD-I | 04/02/2021 | 20 | S. K. ENTERPRISE | 8.41 | 15.57 | 1
1906 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Jhau Danga to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Rajarampur Ground water supply scheme (Lalgola,,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | JE | ORD/000568/2021-2022 | 1921/BD-I | 08/10/2021 | 10 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 0.6 | 0.6 | 1
1907 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gobindotala(Village code 314454) ,Paschim Rampur(Village code 314455) under Paschim Rampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000099/2020-2021 | 164/BD-I | 03/02/2021 | 30 | M/S SINHA & SONS | 70.39 | 66.78 | 100
1908 | Murshidabad Division |  | HIRING OF CAR FOR JANGIPUR SUB DIVISION, PHE DTE. |  |  | BILL/00066/2022-2023 |  | 09/12/2022 | 0 | MADAN MOHAN SASMAL | 0.42 | 0 | 0
1909 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Barala (Village code 314009) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-9) |  |  | ORD/000294/2020-2021 | 48/MURD | 06/01/2021 | 180 | M/S UNIVERSAL TRADING | 63.12 | 14.5 | 100
1910 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS MITHIPUR PWSS Scheme, Block-RAGHUNATHGAUNGE-II to be Augmention/Rejuvination under Murshidabad Division, P.H.E. Dte. |  |  | ORD/001141/2021-2022 | 3252/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.65 | 11.29 | 1
1911 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of MITHIPUR (Village code 314136) under MITHIPUR Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005186173 |  |  | ORD/001154/2021-2022 | 3974/MURD | 21/12/2021 | 180 | M/S. SINHA & SONS | 108.7 | 0 | 0
1912 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000039/2021-2022 | 540/12/MURD | 25/02/2022 | 0 | Resource Division | 15.81 | 0 | 0
1913 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KASIADANGA ZONE-II PWSS Scheme, Block - Raghunathganj-II to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 419 of 21-22 by EE MURD |  |  | VCH/001369/2021-2022 | 301-MSD/21-22 | 07/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.54 | 0 | 0
1914 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KASIADANGA ZONE-II PWSS Scheme, Block - Raghunathganj-II to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 420 of 21-22 by EE MURD |  |  | VCH/001371/2021-2022 | 301-MSD/21-22 | 07/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.65 | 0 | 0
1915 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with JALSWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village JANPUR (Village Code 315676) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000187/2020-2021 | 3009/MURD | 04/12/2020 | 45 | KUNDU CONSTRUCTION | 20.35 | 0 | 0
1916 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Takipur(Village code 315667) under Rejinagar Ground Water Based water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID 1723375 in the District of Murshidabad. (Sl No-10) | ASSISTANT ENGINEER |  | ORD/000286/2020-2021 | 3049/MURD | 08/12/2020 | 180 | RAJKUMAR MONDAL | 80.54 | 39.2 | 1
1917 | Murshidabad Division | Berhampur Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000451/2021-2022 | 301/BSD | 13/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.34 | 8.67 | 0
1918 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village RAMNA DADPUR (Village Code 315668) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000461/2020-2021 | 3007/MURD | 04/12/2020 | 45 | R.R. CONSTRACTION | 31.15 | 3.74 | 0
1919 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village PILKHANA (Village Code 315666) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000482/2020-2021 | 3011/MURD | 04/12/2020 | 45 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 20.18 | 5.78 | 1
1920 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village AMARPUR (Village Code 315675) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000575/2020-2021 | 3006/MURD | 04/12/2020 | 45 | M/S. S. DAS AND ENTERPRISE | 39.98 | 0 | 0
1921 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village JAGAMOHANPUR (Village Code 315677) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000641/2020-2021 | 3010/MURD | 04/12/2020 | 45 | PARTHA BHASKAR | 15.79 | 15.79 | 1
1922 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Ramna Dadpur (Village Code -315668) Part-B under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000738/2022-2023 | 265/BSD | 24/06/2022 | 30 | R.R. CONSTRUCTION | 4.74 | 4.46 | 0
1923 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Ramna Dadpur ( Village Code -315668) Part-A under Rejinagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000739/2022-2023 | 266/BSD | 24/06/2022 | 30 | R.R. CONSTRUCTION | 4.52 | 4.47 | 0
1924 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Rajinagar (Village code 315663) under Rejinagar Ground Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHEDte. Scheme ID 0001723375 in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001150/2021-2022 | 3960/MURD | 20/12/2021 | 120 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 64.06 | 60.49 | 1
1925 | Murshidabad Division | Berhampur Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) of 208 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Janpur (Village code 315676) under Rejinagar Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad.(Scheme ID- 0001723470) | ASSISTANT ENGINEER |  | ORD/001747/2021-2022 | 784/MURD | 23/03/2022 | 20 | KUNDU CONSTRUCTION | 15 | 11.78 | 1
1926 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER |  | RTOR000023/2021-2022 | 539/8/MURD | 25/02/2022 | 0 | Resource Division | 1.14 | 0 | 0
1927 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with JALSWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village JANPUR (Village Code 315676) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. NIeT No- WBPHED/EE/MSD/03 OF 2020-2021 _SL_04, 3009/MURD | ASSISTANT ENGINEER |  | VCH/000687/2021-2022 | 169-MSD/2021-22 | 01/11/2021 | 0 | KUNDU CONSTRUCTION | 19.96 | 0 | 0
1928 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur (315668) of Rejinagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block of Murshidabad District (PART-I) | ASSISTANT ENGINEER |  | VCH/001295/2021-2022 |  | 17/02/2022 | 0 | R.R. CONSTRUCTION | 27.41 | 0 | 0
1929 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Takipur (Village code 315667) under Rejinagar Ground Water Based water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID 1723375 in the District of Murshidabad. (Sl No-10). Tender no - 52 of 21-22 by SE MC | ASSISTANT ENGINEER |  | VCH/001387/2021-2022 | 335-MSD/21-22 | 25/02/2022 | 0 | RAJKUMAR MONDAL | 35.53 | 0 | 0
1930 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village AMARPUR (Village Code 315675) under REJINAGAR Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block in the District of Murshidabad. Tender no - 618 of 21-22 by EE MURD | ASSISTANT ENGINEER |  | VCH/001427/2021-2022 | 348-MSD/21-22 | 05/03/2022 | 0 | M/S. S. DAS AND ENTERPRISE | 36.35 | 0 | 0
1931 | Murshidabad Division | Berhampur Sub-Division | Additional works for Providing Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PILKHANA (Village Code 315666) under REJINAGAR Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block under Murshidabad Division PHE DTE. Tender no - 544 of 20-21 by EE MURD | ASSISTANT ENGINEER |  | VCH/001449/2021-2022 | 349-MSD/21-22 | 05/03/2022 | 0 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 12.47 | 0 | 0
1932 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur (315668) of Rejinagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block of Murshidabad District under Murshidabad Division PHE DTE. Tender no - 830 of 20-21 by EE MURD | ASSISTANT ENGINEER |  | VCH/001457/2021-2022 | 345-MSD/21-22 | 05/03/2022 | 0 | R.R. CONSTRUCTION | 27.41 | 0 | 0
1933 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAZAESAU (Village Code 315629) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000566/2020-2021 | 3012/MURD | 04/12/2020 | 45 | SANJAY BISWAS | 26.55 | 18.03 | 0
1934 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Saktipur ( Village Code -315633) under Saktipur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, P.H.E Dte. Scheme Id - 5185583 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000764/2020-2021 | 45/MURD | 06/01/2021 | 1547 | CHAKRABORTY CONSTRUCTION | 119.73 | 0 | 45
1935 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village MAHATA (Village Code 315638) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000769/2020-2021 | 3014/MURD | 04/12/2020 | 45 | SO-FINE AQUARIUM | 12.76 | 0 | 0
1936 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with " JALSWAPNA (JAL JEEVAN MISSION)" from existing Distribution system within the Command area of village KATAIKONA (Village Code 315631) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000770/2020-2021 | 3013/MURD | 04/12/2020 | 45 | MAJUMDER CONSTRUCTION | 35.53 | 0 | 50
1937 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with " JALSWAPNA (JAL JEEVAN MISSION)" from existing Distribution system within the Command area of village MAIN(Village Code 315632) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000771/2020-2021 | 3018/MURD | 04/12/2020 | 45 | MAJUMDER CONSTRUCTION | 34.29 | 0 | 40
1938 | Murshidabad Division |  | Providing Functional Household Tap Connections ( 200 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Taraf Rasulpur ( Village Code -314679) and Sekendra ( Village Code -314064) under P.T Rasulpur & Sekendra Ground Water Based Water Supply Scheme under Murshidabad Division P.H.E Dte. |  |  | ORD/000110/2024-2025 | 2211/MURD | 02/08/2024 | 30 | PRAVAT KUMAR GHOSH | 7.3 | 0 | 0
1939 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Garaimari (Village code 314734) under Garaimari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. (Scheme ID 0005019114) |  |  | ORD/000188/2020-2021 | 665/MURD | 19/02/2021 | 180 | ALOK ENTERPRISE | 390.36 | 78.33 | 1
1940 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village GORAIMARI (Village Code 314734) under GORAIMARI Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. |  |  | VCH/001486/2021-2022 | 421-MSD/21-22 | 23/03/2022 | 0 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 137.73 | 0 | 0
1941 | Berhampore Division I | Berhampur Division I | Laying of 150 mm dia (K-9), 200 mm,250 mm & 300 mm dia DI (K-7) pipeline with interconnection in between Rising Main and Distribution System and 200 mm dia UPVC pipeline of unlead portion within command area of Dayanagar (Zone-E) W/S scheme of Arsenic affected area of Beldanga uncovered W/S scheme under Berhampore Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000244/2023-2024 | 954/BD-I | 13/10/2023 | 30 | JAMIRUL CONSTRUCTION | 33.95 | 5.88 | 10
1942 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) laying pipeline in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahespur, Ratnagopbati, Sujapur, Radhaballabhpur, Banamalipur, Harinarayanpur, Sibpur, Srikrishnapur, Arazi Giridharpur, Dayanagar, Arazi Jalalpur, Jhunka and Jalalpur under DAYANAGAR (ZONE-E) Water Supply Scheme in the district Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000282/2023-2024 | 979/BD-I | 18/10/2023 | 180 | M/S. SUKUMAR SINHA | 402.21 | 0 | 0
1943 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahadiar (Village code 314736) under Aminabad Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723383 (Sl No-6) |  |  | ORD/000288/2021-2022 | 1550/MURD | 23/06/2021 | 180 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 75.82 | 22.19 | 0
1944 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna ( Jal Jeevan Mission) under command area of Aminabad (Village code 314730), under Aminabad Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723383) |  |  | ORD/000332/2022-2023 | 1699/MURD | 29/06/2022 | 120 | M/S. BIMALENDU BOSE | 113.8 | 66.93 | 0
1945 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kuchemora (Village code 314735) under Aminabad Ground Water Supply Scheme for Arsenic Affected Area of DomkalBlock, under Murshidabad Division, PHE Dte. Scheme ID: 0001723383 (Sl-05) |  |  | ORD/000367/2021-2022 | 2533/MURD | 19/08/2021 | 180 | M/S UNIVERSAL TRADING | 89.39 | 25.99 | 0
1946 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000044/2021-2022 | 541/4/MURD | 25/02/2022 | 0 | Resource Division | 1.2 | 0 | 0
1947 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kuchemora, Sahadiar, Aminabad (314735, 314736, 314730) of Aminabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I), TNO- 112/20-21/SE-MC |  |  | VCH/000670/2021-2022 | 150-MSD/21-22 | 10/10/2021 | 0 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 53.58 | 0 | 0
1948 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2023 to 31.12.2023. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000171/2022-2023 | 1386/BD-I | 23/12/2022 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 3.88 | 100
1949 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sani Baharapara (Village code 314841) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000222/2021-2022 | 1811/BD-I | 05/10/2021 | 50 | M/S. SUKUMAR SINHA | 42.52 | 0 | 36
1950 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khanpur,Hamdampur,Pilkhana and Matijhil (Village code 314845,314846,314850,314848) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000223/2021-2022 | 1812/BD-I | 05/10/2021 | 100 | M/S GUHA AND ROY ENTERPRISE | 95.07 | 27.15 | 1
1951 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gobindapur Lakheraj,Sahamatganj and Bansbari (Village code 314826,314849,314827) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000224/2021-2022 | 1813/BD-I | 05/10/2021 | 631 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 78.62 | 66.83 | 100
1952 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kumarpara,Ukta and Ayesbag (Village code 314847,314824,314825) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000225/2021-2022 | 1814/BD-I | 05/10/2021 | 50 | KAMIRUL SK AND CO. | 45.04 | 40.31 | 1
1953 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baramganj and Tiktikipara (Village code 314828,314831) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000226/2021-2022 | 1815/BD-I | 05/10/2021 | 50 | KAMIRUL SK AND CO. | 50.58 | 42.78 | 1
1954 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kalikapur Kadamkhandi (Village code 315389) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000227/2021-2022 | 1816/BD-I | 05/10/2021 | 60 | M/S GUHA AND ROY ENTERPRISE | 59.54 | 15.67 | 1
1955 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gopinathpur and Chunakhali (Village code 314829,314830) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000228/2021-2022 | 1817/BD-I | 05/10/2021 | 90 | SANJAY BISWAS | 90.82 | 56.22 | 85
1956 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bali (Village code 314832) under Ayesbag (Zone-E) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-01) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000454/2021-2022 | 1866/BD-I | 07/10/2021 | 180 | RAJ KUMAR MONDAL | 100.22 | 86.37 | 1
1957 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
1958 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chainpara, Sanyasidanga & Talgachi (Village code 314821, 314822 & 314823) under Ayesbag (Zone-E) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-02) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000557/2021-2022 | 1888/BD-I | 07/10/2021 | 180 | M/S SINHA & SONS | 211.59 | 0 | 65
1959 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Ayesbag Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000758/2021-2022 | 2224/BD-I | 15/12/2021 | 90 | TANUSHREE ENTERPRISE | 78.96 | 76.91 | 1
1960 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS | RTOR000011/2021-2022 | 146/BD-I | 10/02/2022 | 0 | Resource Division | 4.67 | 0 | 0
1961 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Kaharpara (Habitation ID-0001294214 ) and Santalpara (Habitation ID-0001792540) in the village of Bramhottor Manikchak (Village code 314234) under Bramhottor Manikchak Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000222/2020-2021 | 986/BD-I | 17/12/2020 | 90 | MS RUBIET HOSSAIN | 42.55 | 0 | 0
1962 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Bramhottor (Habitation ID-0001294213 ) and Ilishmari (Habitation ID-0001792563) in the village of Bramhottor Manikchak (Village code 314234) under Bramhottor Manikchak Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000226/2020-2021 | 990/BD-I | 17/12/2020 | 60 | S. K. ENTERPRISE | 11.8 | 18.21 | 1
1963 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of B.M. Para,Bausmari and Bramhottor Manikchak (Habitation ID 0001792822,0001792589,0001294212) under Bramhottor Manikchak Ground Water based Water Supply Scheme in Lalgola Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000245/2021-2022 | 1855/BD-I | 07/10/2021 | 50 | KAMIRUL SK AND CO. | 48.43 | 42.31 | 1
1964 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paschim Diarmanik chak (village code 314228) under BRAHIMOTTAR MANIKCHAK Ground water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000748/2021-2022 | 2250/BD-I | 21/12/2021 | 45 | ARINDAM MAJUMDAR | 30.87 | 12.15 | 1
1965 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- A. |  |  | ORD/000234/2022-2023 | 206/LSD | 11/05/2022 | 30 | SOUNAK ENTERPRISE | 4.98 | 0 | 0
1966 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- B. |  |  | ORD/000235/2022-2023 | 207/LSD | 11/05/2022 | 30 | AMIT KUMAR SAHA | 4.91 | 0 | 0
1967 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- C. |  |  | ORD/000236/2022-2023 | 208/LSD | 11/05/2022 | 30 | SOUVIK HALDER | 4.86 | 0 | 0
1968 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Fatejanpur Diar (P) (314911) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District of Lalbagh Sub-Division under Murshidabad Division Phe Dte . Part- A. |  |  | ORD/000245/2022-2023 | 217/LSD | 11/05/2022 | 30 | SOUVIK HALDER | 4.91 | 0 | 0
1969 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Fatejanpur Diar (P) (314911) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District of Lalbagh Sub-Division under Murshidabad Division Phe Dte . Part- B. |  |  | ORD/000246/2022-2023 | 218/LSD | 11/05/2022 | 30 | SOUNAK ENTERPRISE | 4.98 | 0 | 0
1970 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- G. |  |  | ORD/000273/2022-2023 | 244/LSD | 11/05/2022 | 30 | SOUNAK ENTERPRISE | 4.98 | 0 | 0
1971 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- I. |  |  | ORD/000275/2022-2023 | 246/LSD | 11/05/2022 | 30 | SOUVIK HALDER | 4.86 | 0 | 0
1972 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- K. |  |  | ORD/000277/2022-2023 | 248/LSD | 11/05/2022 | 30 | SOUNAK ENTERPRISE | 4.75 | 0 | 0
1973 | Murshidabad Division |  | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Dahapara Dham Station ( TP NO 174/24 & 174/22) at Aminabazar Rail Gumit mouza & Connecting with existing 250 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000426/2020-2021 | 543/MURD | 05/02/2021 | 30 | M/S. GOUTAM CHAKRABORTY | 33.47 | 33.47 | 0
1974 | Murshidabad Division |  | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/26 & 179/27) at Cabin Para mouza & Connecting with existing 250 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000442/2020-2021 | 544/MURD | 05/02/2021 | 30 | J.S. CONSTRUCTION | 15.55 | 15.55 | 0
1975 | Murshidabad Division |  | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/11 & 179/10) at Bash Bagan mouza & Connecting with existing 300 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000463/2020-2021 | 545/MURD | 05/02/2021 | 30 | M/S. S. DAS AND ENTERPRISE | 12.26 | 12.26 | 0
1976 | Murshidabad Division |  | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/11 & 179/10) at Bash Bagan mouza & Connecting with existing 300 mm diaUPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. _1 |  |  | ORD/000887/2022-2023 | 407/MURD | 15/02/2023 | 30 | M/S. S. DAS AND ENTERPRISE | 12.26 | 12.26 | 0
1977 | Murshidabad Division |  | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/11 & 179/10) at Bash Bagan mouza & Connecting with existing 300 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. _2 |  |  | ORD/000888/2022-2023 | 408/MURD | 15/02/2023 | 30 | M/S. S. DAS AND ENTERPRISE | 12.26 | 12.26 | 0
1978 | Murshidabad Division |  | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/26 & 179/27) at Cabin Para mouza & Connecting with existing 250 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000889/2022-2023 | 409/MURD | 15/02/2023 | 30 | J.S. CONSTRUCTION | 15.55 | 15.55 | 0
1979 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) |  |  | ORD/001659/2021-2022 | 558/MURD | 28/02/2022 | 180 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0
1980 | Murshidabad Division |  | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 227/3 & 227/4) at Khidirpur mouza & Connecting with existing 200 mm dia uPVC distribution main line of Prosadpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. |  |  | ORD/001715/2021-2022 | 511/MURD | 23/02/2022 | 60 | PRADIP KUMAR DAS | 32.67 | 32.58 | 0
1981 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-20 |  |  | VCH/000985/2022-2023 | 400-MSD/22-23 | 18/11/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 2.57 | 0 | 0
1982 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1983 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1984 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of one no. Diesel Bolero/Marshal/Ambassador car (WB57B4454) for official use of the Assistant Engineer, Kandi Sub-Division, P. H. Engineering Dte. for 06(SIX)Months.(Period from 01.07.2022 to 31.12.2022) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000357/2022-2023 | 264/BSD | 22/06/2022 | 183 | SISIR KUMAR DE | 0.91 | 0 | 100
1985 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RAMPUR-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000518/2021-2022 | 350/BSD | 27/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.16 | 4.16 | 0
1986 | Murshidabad Division | Berhampur Sub-Division | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.12.2022 to 31.05.2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000619/2022-2023 | 326/HQ | 25/11/2022 | 181 | DULAL CHOWDHURY | 0.91 | 1.6 | 0
1987 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of one no. Diesel Bolero/Marshal/Ambassador car (WB57B4454) for official use of the Assistant Engineer, Kandi Sub-Division, P. H. Engineering Dte. for 03(Three)Months.(Period from 01.04.2022 to 30.06.2022) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001626/2021-2022 | 98/BSD | 22/03/2022 | 3 | SISIR KUMAR DE | 0.91 | 0 | 0
1988 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of 01(one) no. Diesel Bolero /Marshal Car for official use having license for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Murshidabad RWS Sub-Division, for 06(Six) months. (i.e. 01/04/2022 to 30/09/2022) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001800/2021-2022 | 151/HQ | 25/03/2022 | 6 | SISIR KUMAR DE | 0.91 | 0 | 0
1989 | Murshidabad Division | Berhampur Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) of 462 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001810/2021-2022 | 802/MURD | 24/03/2022 | 30 | M/S. UNIQUE BUILDERS | 29.37 | 0.01 | 1
1990 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village KANDIBANDHA (Village Code 315327) under SAHAJADPUR Ground Water Based Water Supply Scheme for arsenic affected areas of BERHAMPORE Block in the District of Murshidabad. Tender no - 832 of 20-21 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000728/2022-2023 | 256-MSD/22-23 | 12/08/2022 | 0 | MAJUMDER CONSTRUCTION | 9.67 | 0 | 0
1991 | Murshidabad Division | Berhampur Sub-Division | HIRING OF CAR EE-MSD, OCT-22 NOV-22 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001076/2022-2023 | 434-MSD/22-23 | 08/12/2022 | 0 | DULAL CHOWDHURY | 0.78 | 0 | 0
1992 | Murshidabad Division | Berhampur Sub-Division | HIRING OF CAR OF SE-MC | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001078/2022-2023 | 435-MSD/22-23 | 10/12/2022 | 0 | HASNA BEWA | 1.02 | 0 | 0
1993 | Murshidabad Division | Berhampur Sub-Division | HIRING OF VEHICLE OF AE-JSD...FROM 01/09/2022 TO 26/10/2022 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001101/2022-2023 | 444-MSD/22-23 | 15/12/2022 | 0 | MADAN MOHAN SASMAL | 0.42 | 0 | 0
1994 | Murshidabad Division | Berhampur Sub-Division | HIRING OF CAR FOR AE-KSD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001248/2022-2023 | 524-MSD/22-23 | 03/02/2023 | 0 | SISIR KUMAR DE | 5.4 | 0 | 0
1995 | Murshidabad Division | Berhampur Sub-Division | HIRING OF CAR FOR AE-JSD, W/O NO- 29/MURD, 06/01/2022 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001250/2022-2023 | 526-MSD/22-23 | 11/02/2023 | 0 | MADAN MOHAN SASMAL | 0.48 | 0 | 0
1996 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at CHHAIGHARI G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001193/2021-2022 | 355/LSD | 27/08/2021 | 30 | IMAGIN | 4.17 | 4.17 | 0
1997 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jadupur (Village code 315357) under Jadupur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184179 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001774/2021-2022 | 816/MURD | 25/03/2022 | 30 | M/S. CHOWDHURY CONSTRUCTION | 24.32 | 0 | 0
1998 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000020/2021-2022 | 539/5/MURD | 25/02/2022 | 0 | Resource Division | 2.92 | 0 | 0
1999 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Arazi Madhupur (Village code 315333) under Arazi Madhupur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184184 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000013/2022-2023 | 873/MURD | 01/04/2022 | 30 | M/S SAJAHAN CHOWDHURY | 35.47 | 0 | 0
2000 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Arazi Madhupur(VILLAGE CODE-315333) Ground Based piped water supply scheme of Arazi Madhupur (south portion) & its adjoining mouzas under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000154/2022-2023 | 152/BSD | 12/04/2022 | 30 | PARUL ELECTRICAL INSTALLER | 3.99 | 0 | 80
2001 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Arazi Madhupur (315333) Ground Based piped water supply scheme of south portion of the scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001785/2021-2022 | 109/BSD | 28/03/2022 | 853 | DATA ENTERPRISE | 4.29 | 0 | 90
2002 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000017/2021-2022 | 539/2/MURD | 25/02/2022 | 0 | Resource Division | 5.23 | 0 | 0
2003 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-III/ Part-A Water Supply Scheme of TW-I under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000587/2022-2023 | 3056/MURD | 17/11/2022 | 30 | MAMATA USHA ENTERPRISE | 11.79 | 10.58 | 1
2004 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of JALANGI ZONE-III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000813/2022-2023 | 671/MURD | 09/03/2023 | 906 | MAMATA USHA ENTERPRISE | 637.19 | 198.56 | 100
2005 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000245/2023-2024 | 1219/MURD/28 | 03/05/2023 | 0 | Resource Division | 65.29 | 0 | 0
2006 | Berhampore Mechanical | Berhampur M/E Division | AT JALANGI PWSS Z3 PH 1 ID 304238694 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01479/2023-2024 | 377/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 14.46 | 0 | 0
2007 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of JALANGI , Zone- III/Part-A ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000827/2023-2024 | 3770/MEDB | 03/11/2023 | 92 | SURAKSHA | 10.39 | 8.68 | 20
2008 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Balijana (Village code 314514) ,Nandanpur (Village code 314515) ,Jibanpur (Village code 314516) under Jhikra Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000111/2020-2021 | 183/BD-I | 04/02/2021 | 30 | JAHANGIR ALAM | 73.4 | 57.79 | 1
2009 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Balijana (Code-314514), Nandanpur (Code-314515), Jibanpur (Code-314516) In The Command Area Of Jhikra Ground Water Supply Scheme (Part-B)" Under Bhagwangola-II Block in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000138/2024-2025 | 1553/BD-I | 24/09/2024 | 30 | M/S. OBAIDUR RAHAMAN | 18.33 | 0 | 0
2010 | Murshidabad Division | Berhampur M/E Division | Restoration of Road which were damaged during laying of Pipeline under Islampore Sub Division PHE DTE. under Murshidabad Division PHE DTE. Ref Memo No: 488/ISD Dt. 26.09.2024 of the AE/ISD PHE DTE. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01230/2024-2025 | 493-MSD/2024-25 | 04/10/2024 | 0 | EXECUTIVE ENGINEER , MURSHIDABAD HIGHWAY DIVISION -I, PWD (ROADS) DIRECT. GOV OF W.B | 9.19 | 0 | 0
2011 | Murshidabad Division | Berhampur M/E Division | Formal work order for laying Distribution System (HDPE Pipe) of for AUGMENTATION of Ground Water Based NABIPUR PWSS to Accommadate FHTC at Raninagar- II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000043/2022-2023 | 1116/MURD | 29/04/2022 | 120 | CHAKRABORTY CONSTRUCTION | 317.51 | 74.49 | 1
2012 | Murshidabad Division | Berhampur M/E Division | Construction of One no Pump House cum Chlorine Room with sanitary and Water Supply Arrangement ,Construction of Boundary Wall of 200 m, Laying of Rising Main, Construction of 450 Cum OHR, Land Development Works at Nabipur Water Supply scheme at Raninagar-II Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000112/2024-2025 | 2302/MURD | 12/08/2024 | 250 | PRAFULLYA CONSTRUCTION | 207.59 | 0 | 0
2013 | Murshidabad Division | Berhampur M/E Division | Providing Functional Household Tap Connections (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Nabipur, Bilpachakopra (Village Code -314590,314584) under Nabipur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000641/2022-2023 | 3337/MURD | 15/12/2022 | 1080 | AZAD ENTERPRISE | 58.72 | 0 | 70
2014 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (NABIPUR PWSS Scheme, Block - Raninagar-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000830/2021-2022 | 3263/MURD | 05/10/2021 | 60 | RADIANT | 6.45 | 6.43 | 1
2015 | Murshidabad Division | Berhampur M/E Division | Formal work order for laying Distribution System (HDPE Pipe) of for AUGMENTATION of Ground Water Based NABIPUR PWSS to Accommadate FHTC at Raninagar- II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000903/2022-2023 | 1116 /MURD | 29/04/2022 | 1120 | CHAKRABORTY CONSTRUCTION | 317.51 | 118.78 | 80
2016 | Murshidabad Division | Berhampur M/E Division | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. for Augmentation of Ground Water Based Nabipur PWSS under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/001719/2021-2022 | 153/ISD | 17/03/2022 | 30 | G MITRA & ASSOCIATES | 1.48 | 1.48 | 100
2017 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000022/2022-2023 | 2507/D/MURD | 31/08/2022 | 0 | Resource Division | 11.45 | 0 | 0
2018 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000054/2022-2023 | 3052/G/MURD | 17/11/2022 | 0 | Resource Division | 23.03 | 0 | 0
2019 | Murshidabad Division | Berhampur M/E Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILPACHAKOPRA (Village Code 314584) under NABIPUR Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-II Block in the District of Murshidabad. Tender no - 54 of 20-21 by EE MURD | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | VCH/001501/2021-2022 | 36-MSD/22-23 | 23/04/2022 | 0 | NOVELTY CONSTRUCTION | 6.31 | 0 | 0
2020 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT NABIPUR PH 3, ID304232739 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01230/2023-2024 | 302/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
2021 | Murshidabad Division | Berhampur M/E Division | Allied works for Laying HDPE Pipeline & Repairing of Existing Boundary Wall and Pump House , Construction of 02(two) nos Toilet , Service road for Augmentation of Karimpur Jalangi Zone-III and Zone-I Part-B Ground water based Piped water supply scheme within Jalangi Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000002/2025-2026 | 781/MURD | 03/04/2025 | 60 | J.S. CONSTRUCTION | 41.87 | 0 | 15
2022 | Murshidabad Division | Berhampur M/E Division | Protection of Head work site premises by raising Boundary wall height by R.B.T fencing with Entrance Gate under Karimpur Jalangi (Zone-I) Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000217/2021-2022 | 276/ISD | 03/06/2021 | 60 | ROBIN ROY | 3.32 | 3.26 | 1
2023 | Murshidabad Division | Berhampur M/E Division | Renovation of Pump House No. 1 of Karimpur Jalangi (Zone-I) Water Supply Scheme under Jalangi Block within Islampur Sub Division, under Murshidabad Division, P.H.E. Dte.in the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000301/2021-2022 | 382/A/ISD | 26/07/2021 | 60 | ROBIN ROY | 2.25 | 2.23 | 1
2024 | Murshidabad Division | Berhampur M/E Division | Relaying of distribution pipeline on damaged line from Node Point 24 to 25 under command area of Karimpur Jalangi Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000307/2021-2022 | 388/ISD | 26/07/2021 | 30 | ROBIN ROY | 4.83 | 4.79 | 1
2025 | Murshidabad Division | Berhampur M/E Division | Relaying of distribution pipeline on damaged line from Node Point 21 to 22 under command area of Karimpur Jalangi Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000309/2021-2022 | 382/ISD | 26/07/2021 | 30 | R.S CONSTRUCTION (PROP- ROBIN ROY) | 4.82 | 4.79 | 1
2026 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Karimpur Jalangi Zone-I(Part-B) Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000356/2022-2023 | 1996/MURD | 21/07/2022 | 365 | M/S. BIMALENDU BOSE | 267.14 | 210.74 | 81
2027 | Murshidabad Division | Berhampur M/E Division | Balance Work for Laying of Distribution System for Augmentation of Karimpur-Jalangi Zone-I Part-A Piped water supply scheme to accommodate FHTC (Functional House Hold Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000740/2023-2024 | 65/MURD | 08/01/2024 | 60 | S.S.INFRASTRUCTURE | 134.77 | 99.88 | 10
2028 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000035/2024-2025 | MURD/2481/07 | 04/09/2024 | 0 | Resource Division | 18.05 | 0 | 0
2029 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000043/2022-2023 | 2780/L/MURD | 01/10/2022 | 0 | Resource Division | 18.05 | 0 | 0
2030 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000164/2023-2024 | 1180/MURD/10 | 29/04/2023 | 0 | Resource Division | 64.63 | 0 | 0
2031 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work) in connection with the Functional Household Connection of different existing PWSS(Karimpur- Jalangi Zone-II PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 371 of 21-22 by EE MSD. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | VCH/000354/2022-2023 | 185-MSD/22-23 | 13/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.24 | 0 | 0
2032 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work)in connection with the Functional Household Connection of different existing PWSS (Karimpur- Jalangi Zone-I PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 370 of 21-22 by EE MSD. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | VCH/000355/2022-2023 | 185-MSD/22-23 | 13/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 9.77 | 0 | 0
2033 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work)in connection with the Functional Household Connection of different existing PWSS(Karimpur- Jalangi Zone-III PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 372 of 21-22 by EE MSD. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | VCH/000356/2022-2023 | 185-MSD/22-23 | 13/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.38 | 0 | 0
2034 | Berhampore Mechanical | Berhampur M/E Division | New connection charge for Karimpur-Jalangi W/S Scheme (Part-B) Zone-I, P/H No.-IV. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00274/2023-2024 | 93/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 0.78 | 0 | 0
2035 | Berhampore Mechanical | Berhampur M/E Division | New connection charge for Karimpur-Jalangi W/S Scheme (Part-B) Zone-I, P/H No.-III. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00275/2023-2024 | 94/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 0.78 | 0 | 0
2036 | Berhampore Mechanical | Berhampur M/E Division | ADDL SERVICE CONNECTION CHARGES AT KUTUBPUR VILLAGE ,KARIMPUR JALANGI PWSS PART B, Z 1, PH 3 ID860279295 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01107/2023-2024 | 214/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 2.93 | 0 | 0
2037 | Berhampore Mechanical | Berhampur M/E Division | ADDL SERVICE CONNECTION CHARGES AT KUTUBPUR VILLAGE ,KARIMPUR PWSS PART B, Z 1, PH 4.ID 860281600 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01108/2023-2024 | 215/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 2.89 | 0 | 0
2038 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under Karimpur-Jalangi (Part-B) ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000046/2023-2024 | 3734/MEDB | 03/11/2023 | 92 | KAMAKHYA ENTERPRISE | 24.23 | 17.96 | 50
2039 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION at Sadhukali (VillageCode-315672) under command area of Sadhukhali ground water supply scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000111/2024-2025 | 1447/BD-I | 04/09/2024 | 15 | KALAM SK | 0.99 | 0 | 0
2040 | Berhampore Division I | Berhampur Division I | Formal Work order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sadhukhali (Village code 315672) under Sadhukhali Ground Water Supply Scheme in Beldanga-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-07) | Assistant Engineer-II | Junior Engineer-II | ORD/000427/2021-2022 | 1635/BD-I | 02/09/2021 | 180 | TARUN KUMAR BHATTACHARYA | 51.96 | 48.51 | 0
2041 | Berhampore Division I | Berhampur Division I | Additional Laying works at villages within Dadpur G.P areas to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Sadhukhali Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II | Junior Engineer-II | ORD/000853/2021-2022 | 157/BD-I | 11/02/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 16.17 | 0 | 0
2042 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Telia ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000105/2022-2023 | 1360/BD-I | 21/12/2022 | 661 | PRAVAT KUMAR GHOSH | 2.41 | 0 | 100
2043 | Berhampore Division I | Berhampur Division I | Formal work order for Augmentation of Telia Piped water supply scheme to accommodate construction of OHR, toilet ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000134/2022-2023 | 1446/BD-I | 17/01/2023 | 911 | MUNNA AGROTECH ENTERPRISE | 338.52 | 134.86 | 80
2044 | Berhampore Division I | Berhampur Division I | Allied work for construction of Cast-in-situ Pile (grade M30) (Shaft Length 25 Mtr.) to accommodate construction of OHR, pump house, boundary wall and road restoration of Augmentation of TELIA Piped water supply scheme under Jal Jeevan Mission and Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000157/2024-2025 | 1629/BD-I | 04/10/2024 | 177 | MUNNA AGROTECH ENTERPRISE | 50.58 | 0 | 90
2045 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for TELIA Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000883/2021-2022 | 267/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.63 | 0 | 100
2046 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000066/2023-2024 | 196/BD-I/13 | 09/02/2024 | 0 | Resource Division | 8.05 | 0 | 0
2047 | Berhampore Mechanical | Berhampur Division I | Telia Water Supply Scheme | Assistant Engineer-I | JE,Junior engineer-III | BILL/01455/2023-2024 | 348/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 4.3 | 0 | 0
2048 | Berhampore Mechanical | Berhampur Division I | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Telia ground water supply scheme in Bhagwabgola-I Block Dist_Murshidabad under MEDB PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000012/2025-2026 | 1137/MEDB | 13/05/2025 | 92 | DEY ENTERPRISE | 39.98 | 0 | 0
2049 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of TELIA ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000043/2023-2024 | 3736/MEDB | 03/11/2023 | 92 | M/S K.P. PRAMANIK | 11.45 | 9.52 | 10
2050 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Panchgachhia, Arazi Ramakantapur, Gotha, Sadikpur (313919,313910,313912,313920) of Madna Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000131/2022-2023 | 1230/MURD | 11/05/2022 | 60 | MOTI RAHAMAN | 32.62 | 0 | 0
2051 | Murshidabad Division | Berhampur M/E Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Panchgachhia (Village code 313919) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756899 in the District of Murshidabad. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000155/2020-2021 | 526/MURD | 04/02/2021 | 60 | DIPAYAN DEY | 17.32 | 0 | 0
2052 | Murshidabad Division | Berhampur Sub-Division | Allied work of Pipeline Laying of Distribution system and Construction of Pump House, Boundary Wall, of Shaktipur Zone-II Ground Based piped water supply scheme of Shaktipur Zone-II under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000042/2024-2025 | 1928/MURD | 03/07/2024 | 60 | HOQUEDAR ALI | 65.09 | 0 | 30
2053 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Augmentation of Saktipur Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Beldanga-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000516/2022-2023 | 2497/MURD | 30/08/2022 | 1007 | CHAKRABORTY CONSTRUCTION | 286.01 | 128.57 | 60
2054 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shaktipur Zone-I &II Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000598/2022-2023 | 3072/MURD | 17/11/2022 | 45 | NADIA TUBEWELLS | 21.18 | 8.11 | 1
2055 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS ( SAKTIPUR PWSS Scheme, Block - Beldanga-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000833/2021-2022 | 3266/MURD | 05/10/2021 | 60 | RADIANT | 10.43 | 2.77 | 0
2056 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000006/2024-2025 | 1811/MURD/05 | 20/06/2024 | 0 | Resource Division | 17.54 | 0 | 0
2057 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000299/2023-2024 | 1278/MURD/7 | 10/05/2023 | 0 | Resource Division | 41.67 | 0 | 0
2058 | Berhampore Mechanical | Berhampur Sub-Division | Saktipur Zone-2 Ph-1 Application No- 3004554483 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01194/2023-2024 | 253/WBSEDCL-JJM | 17/01/2024 | 0 | WBSEDCL | 3.28 | 0 | 0
2059 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I (H.W Site) at Zone-I and Pump House No.-I (H.W Site) at Zone-II of Saktipur ground water based water supply scheme under Block- Beldanga-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000164/2023-2024 | 2020/MEDB | 19/06/2023 | 92 | INDTECH ASSOCIATES | 23.14 | 0 | 8
2060 | Murshidabad Division | Berhampur M/E Division | Installation of flow measuring devices on distribution network of MITHIPUR WATER SUPPLY SCHEME OF JANGIPUR SUB-DIVISION UNDER MURSHIDABAD DIVISION, PHE DTE. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | ORD/000070/2025-2026 | 1245/MURD | 29/05/2025 | 30 | DHPE | 3.21 | 0 | 0
2061 | Murshidabad Division | Berhampur M/E Division | Engagement of Consultant for Field Data collection, pipeline network analysis by analyzing actual household demand in pipeline sections, identification of low pressure areas with in the pipe network system and proposing probable solution of the same in 2(Two) nos water supply schemes in Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | ORD/000071/2024-2025 | 2022/MURD | 11/07/2024 | 45 | DHPE | 15.34 | 0 | 25
2062 | Murshidabad Division | Berhampur M/E Division | Laying Distribution System and Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement & 2(two) nos Pump House Office cum godown repairing., for Augmentation of MITHIPUR PWSS in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | ORD/000704/2022-2023 | 145/MURD | 17/01/2023 | 90 | MONDAL ENTERPRISE | 82.55 | 69.23 | 80
2063 | Murshidabad Division | Berhampur M/E Division | Retrofitting Functional Household Tap Connection (FHTC) under Jal Jeevan Mission for command area of Augmentation MITHIPUR Water Supply Scheme in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | ORD/000705/2022-2023 | 119/MURD | 13/01/2023 | 30 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 49.44 | 49.44 | 100
2064 | Murshidabad Division | Berhampur M/E Division | Construction of 250 Cum OHR for Augmentation of Mithipur Water Supply Scheme in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | ORD/000722/2022-2023 | 172/MURD | 18/01/2023 | 1079 | SANJIB GHOSH | 94.37 | 23.79 | 100
2065 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | RTOR000025/2024-2025 | MURD/2481 | 04/09/2024 | 0 | Resource Division | 23.69 | 0 | 0
2066 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | RTOR000306/2023-2024 | 1295/MURD/06 | 11/05/2023 | 0 | Resource Division | 6.13 | 0 | 0
2067 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of MITHIPUR ground water based water supply scheme under Block- RAGHUNATHGANJ-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | ORD/000156/2023-2024 | 585/MEDB | 31/01/2024 | 90 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 12.8 | 0 | 0
2068 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of PARULIA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362284S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000693/2022-2023 | 165/MURD | 17/01/2023 | 1019 | M/S.TAPAS KUMAR CHAKRABORTY | 677.2 | 322.33 | 41
2069 | Murshidabad Division | Kandi Sub-Division | Allied work of PARULIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000741/2023-2024 | 66/MURD | 08/01/2024 | 479 | M/S.TAPAS KUMAR CHAKRABORTY | 53.37 | 0 | 10
2070 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000040/2023-2024 | 1004/MURD/15 | 17/04/2023 | 0 | Resource Division | 46.68 | 0 | 0
2071 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PH1 PARULIA PWSS ID 304187861 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01130/2023-2024 | 222/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 11.66 | 0 | 0
2072 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PARULIA PH II, ID304233543 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01215/2023-2024 | 295/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 4.74 | 0 | 0
2073 | Berhampore Mechanical | Kandi Sub-Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under PARULIA ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001428/2023-2024 | 4343/MEDB | 29/12/2023 | 611 | M/S S. S. ENTERPRISE (DOMKAL) | 23.45 | 0 | 40
2074 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Juginda, Kupila and Narsinghpur Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000109/2022-2023 | 1193/MURD | 10/05/2022 | 1360 | MAMATA USHA ENTERPRISE | 32.62 | 0 | 20
2075 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Juginda (Zone-II) Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000129/2023-2024 | 1766/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 35.34 | 32.07 | 90
2076 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. I & II of Zone-II under MOMENPUR AND OTHERS PIPED WATER SUPPLY SCHEME, BLOCK- DOMKAL DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000042/2025-2026 | 1142/MEDB | 14/05/2025 | 92 | DAS CONSTRUCTION | 22.95 | 0 | 15
2077 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Tikar Bariakalkihara (314642),of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000116/2022-2023 | 1199/MURD | 10/05/2022 | 45 | NADIA TUBEWELLS | 16.6 | 5.71 | 100
2078 | Murshidabad Division | Berhampur M/E Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Tikar Bariakalkihara ( Village Code -314642) under Faridpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184121) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000479/2020-2021 | 579/MURD | 09/02/2021 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 40.1 | 29.94 | 100
2079 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Faridpur and Indrani Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000670/2022-2023 | 3411/MURD | 22/12/2022 | 984 | R.K. DRILLING SERVICES | 8.4 | 0 | 100
2080 | Murshidabad Division | Kandi Sub-Division | Laying Distribution system, of Gunanadabati PWSS in Bharatpur-I Block of Kandi Sub-Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000183/2024-2025 | 3147/MURD | 03/12/2024 | 179 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 21.46 | 0 | 80
2081 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GUNANANDABATI PWSS at Head Work Site & 2nd Tube Well Site in Bharatpur-I Block under Kandi SubDivision, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000659/2022-2023 | 3404/MURD | 22/12/2022 | 45 | M/S D. PALIT & CO. | 16.81 | 0 | 100
2082 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution System (PART-A) of Gunanandabati PWSS at Bharatpur-I Block, Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362380S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000698/2022-2023 | 131/MURD | 16/01/2023 | 697 | HARAPRASAD DAS | 132.64 | 120.71 | 85
2083 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of 250 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of GUNANANDABATI PWSS in Bharatpur-I Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362380S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,31,40,916.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,49,38,880.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000763/2022-2023 | 479/MURD | 20/02/2023 | 365 | S.&P. ENTERPRISE | 280.74 | 0 | 0
2084 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000012/2023-2024 | 1210/MURD/43 | 02/05/2023 | 0 | Resource Division | 20.97 | 0 | 0
2085 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under GUNANANDABATI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000089/2023-2024 | 1888/MEDB | 16/06/2023 | 92 | ASHUTOSH DAS & CO. | 23.47 | 0 | 0
2086 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution system,Rising Main, Sub-soil Investigation and construction of OHR (300 cum) and construction of Boundary wall and repairing of Pump-House in connection wih Augmentation of Godhanpara Zone-I water supply scheme under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000542/2022-2023 | 2716/MURD | 26/09/2022 | 365 | M/S. TAPAS KUMAR CHAKRABORTY | 334.37 | 290.96 | 95
2087 | Murshidabad Division | Berhampur M/E Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Deputipara (Village Code -314582) under Godhanpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.EDte. (Scheme I.D.-0005186259). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000730/2020-2021 | 578/ MURD | 09/02/2021 | 60 | M/S ROY & BOSE ENTERPRISE | 17.93 | 5.38 | 1
2088 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000738/2021-2022 | 2744/MURD | 03/09/2021 | 60 | RADIANT | 11.27 | 3.76 | 0
2089 | Murshidabad Division | Berhampur M/E Division | Restoration work of pipeline by relaying of UPVC pipeline of Godhanpara area (Kacharipara Gram Node Point 46 of 47) under command area of Godhanpara Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000797/2021-2022 | 503/ISD | 25/10/2021 | 30 | DEBEN RAJAK | 4.48 | 4.47 | 1
2090 | Murshidabad Division | Berhampur M/E Division | Restoration work of pipeline by relaying of UPVC pipeline of Godhanpara area (Deputipara paniparia Gram Node Point 9 of 17(A), Raninagar Bazarpara Node Point 3(A) to 4) under command area of Godhanpara Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000860/2021-2022 | 505/ISD | 25/10/2021 | 30 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 4.79 | 4.78 | 1
2091 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000044/2022-2023 | 3037/A/MURD | 16/11/2022 | 0 | Resource Division | 31.28 | 0 | 0
2092 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000048/2022-2023 | 3052/A/MURD | 17/11/2022 | 0 | Resource Division | 12.45 | 0 | 0
2093 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000292/2023-2024 | 1278/MURD/10 | 10/05/2023 | 0 | Resource Division | 25.62 | 0 | 0
2094 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for BACHHRA ZONE-II Ground Based Water Supply Scheme in Beldanga -II Block underMurshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000031/2025-2026 | 1194/MURD | 23/05/2025 | 60 | M/S UNIVERSAL TRADING | 19.62 | 0 | 0
2095 | Murshidabad Division | Berhampur Sub-Division | Construction of 100 Cum OHR, Laying of Distribution System (part_A), Rising Main , Special repair and renovation of existing 1 (One) Nos PumpHouse and Allied Works, repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity for Augmentation work of BACHHRA ZONE-I PWSS in BELDANGA-II Block under Murshidabad Division , PHE.Dte.(part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000138/2023-2024 | 1820/MURD | 12/07/2023 | 720 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 330.74 | 0 | 5
2096 | Murshidabad Division | Berhampur Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0
2097 | Murshidabad Division | Berhampur Sub-Division | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For(05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05 (Five) Months].for the month of December 2024 to April 2025 [Vehicle No.WB25M1561] (i.e. from 01/12/2024 to 30/04/2025) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000199/2024-2025 | 3127/MURD | 30/11/2024 | 151 | M/S B K ENTERPRISE | 0.87 | 0 | 0
2098 | Murshidabad Division | Berhampur Sub-Division | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 75
2099 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 5.68 | 80
2100 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 573 nos household , Laying of Distribution System (Part_B), Repairing & Vertical Extention of Boundary Wall for Augmentation work of BACHHARA ZONE-I PWSS in Beldanga-II Block under Murshidabad Division , PHE.Dte. (part_B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000890/2022-2023 | 913/MURD | 30/03/2023 | 694 | AYUSH ENTERPRISE | 103.18 | 64.32 | 80
2101 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001641/2021-2022 | 480/MURD | 22/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 22.29 | 0
2102 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000012/2024-2025 | 1811/MURD/11 | 20/06/2024 | 0 | Resource Division | 6.03 | 0 | 0
2103 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000208/2023-2024 | 1210/MURD/24 | 02/05/2023 | 0 | Resource Division | 4.36 | 0 | 0
2104 | Berhampore Mechanical | Berhampur Sub-Division | NEW CONNECTION AT BACHRA Z-I PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/00173/2024-2025 | 18/WBSEDCL-JJM | 16/04/2024 | 0 | WBSEDCL | 3.76 | 0 | 0
2105 | Berhampore Mechanical | Berhampur Sub-Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , ZONE-I under BACHHRA ground water based water supply scheme under Block_ BELDANGA-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001473/2023-2024 | 758/MEDB | 20/02/2024 | 90 | KARTICK BAL | 36.55 | 0 | 0
2106 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Hurshi Zone-II Piped water supply scheme to accommodate construction of OHR, pump house and boundary wall , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000136/2023-2024 | 615/BD-I | 02/08/2023 | 790 | ROY AND ROY CONSTRUCTION | 246.81 | 0 | 30
2107 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HURSHI ZONE-II Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000195/2022-2023 | 1330/BD-I | 16/12/2022 | 10 | RADIANT | 2.53 | 2.53 | 100
2108 | Berhampore Division I | Raghunathganj Sub-Division | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Hurshi Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (For 2 nos. Tubewell) | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000314/2023-2024 | 1148/BD-I | 04/12/2023 | 30 | NADIA TUBEWELLS | 23.12 | 0 | 0
2109 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | RTOR000006/2023-2024 | 61/BD-1/7 | 27/04/2023 | 0 | Resource Division | 19.67 | 0 | 0
2110 | Berhampore Mechanical | Raghunathganj Sub-Division | shifting ltoh hurshi z2 ph 1 | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/01598/2023-2024 | 431/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 0.34 | 0 | 0
2111 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under Hurshi ground water based water supply scheme under Block_ Raninagar_I Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000672/2023-2024 | 4296/MEDB | 29/12/2023 | 91 | MONI ELECTRICAL WORKS | 20.92 | 0 | 0
2112 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System PART-B,FHTC for Augmentation of GOBARHATI PWSS in KANDI Block , under Murshidabad Division ,PHE.Dte.Part-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000017/2023-2024 | 991/MURD | 11/04/2023 | 120 | S.K. ENTERPRISE (SANDIP GHOSH) | 175.23 | 161.41 | 35
2113 | Murshidabad Division | Kandi Sub-Division | Construction of 350 Cum OHR, Boundwary Wall, Rising Main Connection, Laying Distribution System PART-A,FHTC for Augmentation of GOBARHATI PWSS in KANDI Block , under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000029/2023-2024 | 1087/MURD | 20/04/2023 | 730 | MOTI RAHAMAN | 301.83 | 128.16 | 25
2114 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well , 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gobarhati & Hizole Water Supply Scheme at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000034/2023-2024 | 1109/MURD | 24/04/2023 | 723 | INDRAJIT MAZUMDAR | 10.68 | 0 | 100
2115 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For(05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05 (Five) Months].for the month of May 2025 to September 2025 [Vehicle No.WB25M1561] (i.e. from 01/05/2025 to 30/09/2025) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000036/2025-2026 | 939/MURD | 29/04/2025 | 153 | M/S B K ENTERPRISE | 0.75 | 0 | 0
2116 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Executive Engineer, Murshidabad Division, P.H.E. Dte. For (06) Six Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order) [Period for 06 (Six) Months].for the month of April 2025 to October 2025 [Vehicle No.WB93B0287] (i.e. from 05/04/2025 to 04/10/2025) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000085/2025-2026 | 784/MURD | 03/04/2025 | 183 | M/S. S. DAS AND ENTERPRISE | 0.75 | 0 | 25
2117 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Deputy Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For(05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05(Five) Months i.e. from 13/07/2025 to 12/12/2025].for the month of July 2025 to December 2025 [Vehicle No.WB58AR5026] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000092/2025-2026 | 1575/MURD | 11/07/2025 | 153 | MD MUKLESUR RAHAMAN | 0.75 | 0 | 20
2118 | Murshidabad Division | Kandi Sub-Division | Construction of surface drain of length 50 m at the Head work site of Gobarhati PWSS and Southern side of Kandi Stack Yard under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000166/2023-2024 | 1971/MURD | 20/07/2023 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 3.88 | 3.85 | 100
2119 | Murshidabad Division | Kandi Sub-Division | Supplying fitting and fixing of R.B. T Concertina fencing on wall top of Gobarhati PWSS and Kandi Stack Yard under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000167/2023-2024 | 1972/MURD | 20/07/2023 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 5.14 | 4.91 | 80
2120 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover any where with in any trouble on daily wage basis for official used under the control of the Executive Engineer, Murshidabad Division, P.H.E. Dte. For (06) Six Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order) [Period for 06 (Six) Months].for the month of October 2025 to April 2026 [Vehicle No.WB93B 0287] (i.e. from 05/10/2025 to 04/04/2026) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000186/2025-2026 | 2143/MURD | 25/09/2025 | 182 | M/S. S. DAS AND ENTERPRISE | 0.89 | 0 | 0
2121 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Deputy Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For(05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05(Five) Months i.e. from 13/12/2025 to 12/05/2026].for the month of DECEMBER 2025 to MAY 2026 [Vehicle No.WB58AR5026] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000251/2025-2026 | 2560/MURD | 10/12/2025 | 151 | MD MUKLESUR RAHAMAN | 0.74 | 0 | 0
2122 | Murshidabad Division | Kandi Sub-Division | Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Deputy Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For (05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05(Five) Months i.e. from 13/02/2025 to 12/07/2025].for the month of February 2025 to July2025 [Vehicle No.WB58AR5026] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000475/2024-2025 | 390/MURD | 13/02/2025 | 150 | MD MUKLESUR RAHAMAN | 0.87 | 0 | 0
2123 | Murshidabad Division | Kandi Sub-Division | Demolition of damaged R.C.C. Elevated Reservoir (Capacity 2,72,400 Ltr) at Gokarna /Gobarhati Water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000737/2023-2024 | 61/MURD | 08/01/2024 | 30 | MD SAJAHAN ALI | 5.47 | 5.47 | 100
2124 | Murshidabad Division | Kandi Sub-Division | Construction of surface drain of length 40.35 m at the Head work site of Gobarhati PWSS and eastern side of Kandi Stack Yard under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000747/2023-2024 | 106/MURD | 10/01/2024 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 3.06 | 2.92 | 100
2125 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (GABARHATI PWSS Scheme, Block - KANDI) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/002140/2021-2022 | 3257/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 6.51 | 4.43 | 1
2126 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000065/2022-2023 | 1043/MURD/2 | 17/04/2023 | 0 | Resource Division | 8.9 | 0 | 0
2127 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000307/2023-2024 | 1295/MURD/02 | 11/05/2023 | 0 | Resource Division | 8.9 | 0 | 0
2128 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2129 | Berhampore Division I | Berhampur M/E Division | Augmentation of Bansgara Zone-I Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000024/2023-2024 | 312/BD-I | 14/06/2023 | 898 | MODERN CONSTRUCTION | 281.33 | 0 | 30
2130 | Berhampore Division I | Berhampur M/E Division | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub- Division, PHE Dte. Under Berhampore Division ¿ I, P.H.E. Dte in the district of Murshidabad. Period from 01.05.2025 to 31.10.2025 Car No- W.B-57B/5069 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000044/2025-2026 | 656/BD-I | 28/04/2025 | 183 | DEBADITYA TRANSPORT | 0.91 | 0 | 0
2131 | Berhampore Division I | Berhampur M/E Division | Balance and Allied work for Laying Rising Main (DI K-9) and Distribution System (DI-K7) including inter connection with supply of necessary CI special and valve at Head Work Site including road restoration for augmentation work of Bansgrara Zone -I Water Supply Scheme , under Jal Jeevan Mission within Lalgola block under Berhampore DIvision -I , PHE.Dte. in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000077/2025-2026 | 844/BD-I | 23/06/2025 | 180 | MODERN CONSTRUCTION | 57.56 | 0 | 80
2132 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd/3rd/4th site) and Allied Works for Bansgara ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000126/2022-2023 | 1669/BD-I | 14/03/2023 | 30 | JIYARUL SK | 4.19 | 2.35 | 100
2133 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 14.3 | 20
2134 | Berhampore Division I | Raghunathganj Sub-Division | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Dakshin Gopalpur ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000040/2025-2026 | 704/BD-I | 13/05/2025 | 300 | BISWAS ENTERPRISE (PROP. JESMIN KHATUN) | 122.64 | 0 | 0
2135 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Boundary Wall with Main Entrance gate and barbed wire facing and service road for approach at Augmentation of Dakshin Gopalpur PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000050/2024-2025 | 1113/BD-I | 10/07/2024 | 45 | KHANDAKAR CONSTRUCTION | 22.05 | 0 | 0
2136 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of DAKSHIN GOPALPUR Piped water supply scheme for laying of design pipeline, rising main and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000241/2022-2023 | 1598/BD-I | 28/02/2023 | 733 | GOUTAM CHAKRABORTY | 134.6 | 115.61 | 32
2137 | Berhampore Division I | Raghunathganj Sub-Division | Allied work of Dakshin Gopalpur Piped Water Supply Scheme for laying of Pipeline ,Rising Main, Pump House Repairing under Jal Jeevan Mission within Raninagar - I Block under Berhampore Division - I PHE Dte in Murshidabad District. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000257/2024-2025 | 2270/BD-I | 16/12/2024 | 227 | M/S GOUTAM CHAKRABORTY | 4.31 | 0 | 100
2138 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DAKSHIN GOPALPUR Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000275/2022-2023 | 1504/BD-I | 07/02/2023 | 10 | M/S SOBHA & CO | 2.67 | 2.57 | 100
2139 | Berhampore Division I | Raghunathganj Sub-Division | Continuation work order for Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub Division, PHE Dte. period for 01.01.2025 to 30.06.2025. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000287/2024-2025 | 2326/BD-I | 27/12/2024 | 182 | TARUN KUMAR BHATTACHARYA | 0.91 | 0 | 0
2140 | Berhampore Division I | Raghunathganj Sub-Division | Renovation for Modified Sujapur Sadipur Model after washing of AIRP (Capacity 29.06 Cum/hr.) at Dakshin Gopalpur Water Supply Scheme under Jal Jivan Mission of Raninagar-I Block under Raghunathganj Sub-Division under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000439/2023-2024 | 410/BD-I | 13/03/2024 | 60 | SUMAN ENTERPRISE AND SUMAN AQUA | 51.69 | 0 | 75
2141 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000020/2023-2024 | 194/BD-I/4 | 09/02/2024 | 0 | Resource Division | 36.44 | 0 | 0
2142 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Dakshin Gopalpur ground water supply scheme in Raninagar-I Block Dist_Murshidabad under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000005/2025-2026 | 1129/MEDB | 13/05/2025 | 92 | SUNIL RABIDAS | 39.97 | 0 | 0
2143 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System, Rising Main, FHTC, Repairing of Boundary Wall, Pump House & Existing OHR for Augmentation of Bhalkundi Zone-II Water at Supply Scheme in Khargram Block , under Murshidabad Division , PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000026/2023-2024 | 1066/MURD | 18/04/2023 | 682 | SAMRIDDHI ASSOCIATED | 220.85 | 44.72 | 5
2144 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhalkundi Zone - II Water Supply Scheme at Head Work Site, 2nd Site site at KHARGRAM Block under Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000110/2023-2024 | 1752/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 23.56 | 0 | 0
2145 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
2146 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 5.33 | 76
2147 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000063/2022-2023 | 1043/MURD/4 | 17/04/2023 | 0 | Resource Division | 1.46 | 0 | 0
2148 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under BHALKUNDI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000677/2023-2024 | 4300/MEDB | 29/12/2023 | 91 | SREE RADHA ELECTRICAL | 22.89 | 0 | 0
2149 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System, Rising Main Connection, FHTC, Repairing of Existing OHR, Pump House, Construction of New Boundary Wall for Augmentation of BELE Ground water based Piped water supply scheme in Khargram Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000027/2023-2024 | 1076/MURD | 19/04/2023 | 1139 | M/S. BIMALENDU BOSE | 270.95 | 28.04 | 25
2150 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bele & adjoining mouzas Water Supply Scheme at 3rd work site at K h a r g r a m Block under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000032/2023-2024 | 1107/MURD | 24/04/2023 | 20 | SARKAR WATER SUPPLY AGENCY | 10.68 | 0 | 100
2151 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
2152 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 5.33 | 76
2153 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000060/2022-2023 | 1936/MURD/1 | 18/07/2023 | 0 | Resource Division | 30.08 | 0 | 0
2154 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000315/2023-2024 | 1936/MURD/2 | 18/07/2023 | 0 | Resource Division | 2.74 | 0 | 0
2155 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under BELE ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000675/2023-2024 | 4298/MEDB | 29/12/2023 | 91 | ASSOCIATED ELECTRICAL CO. | 34.03 | 0 | 50
2156 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 2.81 | 100
2157 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based HAFANIA (ZONE-II) & KEYADANGA PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000819/2022-2023 | 801/MURD | 22/03/2023 | 831 | ATIKUL SAIKH | 367.41 | 71.99 | 100
2158 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000266/2023-2024 | 1230/MURD/09 | 04/05/2023 | 0 | Resource Division | 18.97 | 0 | 0
2159 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000375/2023-2024 | 495/MURD/06 | 15/02/2024 | 0 | Resource Division | 7.85 | 0 | 0
2160 | Berhampore Mechanical | Berhampur M/E Division | HAFANIA Z-II PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/01439/2023-2024 | 337/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 7.12 | 0 | 0
2161 | Berhampore Mechanical | Berhampur M/E Division | HAFANIA Z-II PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/01440/2023-2024 | 338/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 6.04 | 0 | 0
2162 | Berhampore Division I | Berhampur Division I | Improvement of OHR (180 Cum) Extension of Boundary Wall & Service Road for Augmentation of Ramnachandpur Zone-III PWSS within Nawda block under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000027/2024-2025 | 983/BD-I | 19/06/2024 | 60 | U.S BUILDERS | 9.46 | 0 | 0
2163 | Berhampore Division I | Berhampur Division I | Allied works of Laying of distribution pipeline of RAMNACHANDPUR ZONE-III under JJM within Nowda Block in the district of Murshidabad under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000147/2024-2025 | 1615/BD-I | 03/10/2024 | 30 | MD ENTERPRISE | 12.65 | 0 | 0
2164 | Berhampore Division I | Berhampur Division I | Augmentation of Ramnachandpur Zone-III Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000207/2022-2023 | 1622/BD-I | 02/03/2023 | 670 | SAMAR MUKHERJEE | 112.68 | 97.69 | 99
2165 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-III Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000236/2022-2023 | 1594/BD-I | 28/02/2023 | 10 | TECHVISION | 2.53 | 2.53 | 0
2166 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | RTOR000055/2023-2024 | 196/BD-I/17 | 09/02/2024 | 0 | Resource Division | 14.91 | 0 | 0
2167 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II , ZONE-III under RAMNACHANDPUR_ ground water based water supply scheme under Block_ NOWDA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000674/2023-2024 | 4344/MEDB | 29/12/2023 | 91 | SUNIL RABIDAS | 19.44 | 0 | 0
2168 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gafulia & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at B u r w a n Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000049/2023-2024 | 1218/MURD | 03/05/2023 | 30 | MAMATA USHA ENTERPRISE | 21.38 | 18.94 | 100
2169 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System (PART-B), FHTC in GAFULIA Water at Supply Scheme in Burwan Block , under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000152/2023-2024 | 1900/MURD | 17/07/2023 | 120 | MITRA CONSTRUCTION | 263.45 | 44.08 | 31
2170 | Murshidabad Division | Kandi Sub-Division | Formal work order for construction of 250 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, Boundwary Wall of GAFULIA PWSS, in Burwan Block under Murshidabad Division ,PHE.Dte. [ (i)Amount for LDS , R. Main : Rs. 52,45,981.00 & (ii) Amount for OHR, & Pump House : Rs. 1,56,36,015.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000792/2022-2023 | 592/MURD | 01/03/2023 | 853 | H.L. CONSTRUCTION (TITAN BISWAS) | 208.8 | 103.47 | 53
2171 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000073/2022-2023 | 1278/MURD/17 | 10/05/2023 | 0 | Resource Division | 27.87 | 0 | 0
2172 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000334/2023-2024 | 79/MURD/01 | 09/01/2024 | 0 | Resource Division | 12.43 | 0 | 0
2173 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000366/2023-2024 | MURD/439/10 | 08/02/2024 | 0 | Resource Division | 0.56 | 0 | 0
2174 | Berhampore Mechanical | Kandi Sub-Division | Electric Service Connection at GAFULIA RAJHAT SIULI PWSS PH II, Application NO.3004502793, ID 304199818 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01082/2023-2024 | 191/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 6.85 | 0 | 0
2175 | Berhampore Mechanical | Kandi Sub-Division | New service connection at SULI PH1 ID 304199844 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01125/2023-2024 | 225/WBSEDCL-JJM | 08/01/2024 | 0 | WBSEDCL | 5.06 | 0 | 0
2176 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under GAFULIA ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000062/2023-2024 | 4354/MEDB | 29/12/2023 | 91 | WEST BENGAL ENGINEERING CO. | 23.39 | 0 | 0
2177 | Murshidabad Division | Berhampur M/E Division | Construction of Pump House, Boundary Wall, Rising Main Connection, Laying Distribution System and FHTC & Special Reaparing of 02 (Two) Nos Pump House for Augmentation of Tekaraipara Ground water based piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) with Raninagar -I Block of Murshidabad District under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000023/2024-2025 | 1814/MURD | 20/06/2024 | 560 | S.D. PROJECT | 448.97 | 0 | 50
2178 | Murshidabad Division | Berhampur M/E Division | Rising Main Connection (D.I-K9) , Laying Distribution System (D.I-K7 & HDPE PE-100), and Balance Portion of Functional Household Tap Connection (1052 Nos) and Reconnection of Functional Household Tap Connection (4370 Nos) for Augmentation of Tekaraipara Ground water based Piped water supply scheme within Raninagar-I Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000100/2025-2026 | 1671/MURD | 24/07/2025 | 240 | S.D. PROJECT | 219.58 | 0 | 50
2179 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 2.92 | 1
2180 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 6.83 | 10
2181 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 17 | 20
2182 | Berhampore Division I | Berhampur M/E Division | AMARKUNDA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jeevan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART -A) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000027/2023-2024 | 94/BD-I | 04/05/2023 | 881 | TANUSHREE ENTERPRISE | 240.28 | 23.63 | 100
2183 | Berhampore Division I | Berhampur M/E Division | AMARKUNDA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000086/2023-2024 | 206/BD-I | 17/05/2023 | 744 | G M ENTERPRISE | 53.43 | 17.32 | 20
2184 | Berhampore Division I | Berhampur M/E Division | AMARKUNDA PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000293/2022-2023 | 1825/BD-I | 31/03/2023 | 180 | AJOY GHOSH | 96.88 | 26.05 | 20
2185 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000017/2023-2024 | 61/BD-1/35 | 27/04/2023 | 0 | Resource Division | 13.43 | 0 | 0
2186 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000108/2023-2024 | 304/BD-1/8 | 22/02/2024 | 0 | Resource Division | 9.83 | 0 | 0
2187 | Berhampore Mechanical | Berhampur M/E Division | AMARKUNDU PH-1 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/01514/2023-2024 | 398/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 9.75 | 0 | 0
2188 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000064/2024-2025 | 1193/BD-I | 25/07/2024 | 180 | SOUMEN ADHIKARY | 10.19 | 0 | 0
2189 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Rianpur (village code 315397) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Jumra Nayagram ground water supply scheme (Block-Lalgola)under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE | ORD/000076/2022-2023 | 632/BD-I | 31/05/2022 | 10 | CHATTERJEE ENTERPRISE | 8.92 | 4.55 | 1
2190 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Panisala (Village code 314191) under Jumra Nayagram Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000200/2020-2021 | 965/BD-I | 17/12/2020 | 90 | SAMBHUNATH ROY | 37.24 | 33.5 | 1
2191 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rianpur (Village code 314192) under Jumra Nayagram Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000202/2020-2021 | 968/BD-I | 17/12/2020 | 90 | JAHANGIR ALAM | 38.56 | 38.03 | 1
2192 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of MahishaThali( Village Code -313851) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005019105) |  |  | ORD/000608/2020-2021 | 598/MURD | 09/02/2021 | 60 | HARUN ALL RASHID & BROTHERS | 30.42 | 7.36 | 1
2193 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MAHISHA THALI (Village Code 313851) under DOGACHHI Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 828 of 20-21 by EE MURD |  |  | VCH/001460/2021-2022 | 360-MSD/21-22 | 10/03/2022 | 0 | HARUN-AL-RASHID & BROTHERS | 17 | 0 | 0
2194 | Berhampore Division I | Berhampur Division I | MAHISHASTHALI PWSS to accommodate FHTC, Laying Distribution System, under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000047/2023-2024 | 143/BD-I | 15/05/2023 | 893 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 96.62 | 0 | 5
2195 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MAHISASTHALI and Adjoining Mouzas PWSS (TW-I & II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-I Block under Berhampore Division-I, P.H.Engineering Dte. (02 Nos TW) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000080/2025-2026 | 847/BD-I | 23/06/2025 | 30 | WATER TECH | 17.75 | 0 | 0
2196 | Berhampore Division I | Berhampur Division I | MAHISHASTHALI PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000106/2023-2024 | 211/BD-I | 17/05/2023 | 90 | MANAB KUMAR GHOSH | 38.89 | 0 | 15
2197 | Berhampore Division I | Berhampur Division I | MAHISHASTHALI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 350 cum) under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000374/2023-2024 | 116/BD-I | 30/01/2024 | 620 | RANADHIR SINHA | 268.39 | 0 | 30
2198 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000035/2023-2024 | 61/BD-1/21 | 27/04/2023 | 0 | Resource Division | 15.38 | 0 | 0
2199 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Mahishasthali ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000656/2023-2024 | 3691/MEDB | 03/11/2023 | 92 | GOENKA ENTERPRISE | 20.9 | 0 | 0
2200 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.63 | 100
2201 | Murshidabad Division | Berhampur M/E Division | Creation of safe drinking water by Construction/ installation of CPP unit with SOLAR Power connection including Tubewell with Submersible pump (for Raw Water As concentration upto 0.15 ppm) at " Madhupur village under Rangamati Chandpara Gram Panchayat of Berhampore Block in connection with Paray Samadhan Program(UID-MSD064) under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000751/2020-2021 | 308/MURD | 28/01/2021 | 45 | ULTRA CONSTRUCTION. | 22.7 | 0 | 10
2202 | Murshidabad Division | Berhampur M/E Division | Formal work order for MADHUPUR PWSS Construction OHR, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jiban Mission, Block- SAMSERGANJ of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000822/2022-2023 | 686/MURD | 10/03/2023 | 365 | M/S KHAN CHOWDHURY BROTHERS AND CO | 224.5 | 0 | 0
2203 | Murshidabad Division | Berhampur M/E Division | MADHUPUR PWSS Construction to accommodate FHTC, Laying Distribution System , Rising Main under Jal Jivan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000874/2022-2023 | 883/MURD | 28/03/2023 | 918 | SHYAMAL KUMAR SAHA | 231.54 | 0 | 40
2204 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000287/2023-2024 | 1230/MURD/28 | 04/05/2023 | 0 | Resource Division | 33.76 | 0 | 0
2205 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2206 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Jaulia Part- A village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000215/2023-2024 | 2330/MURD | 02/08/2023 | 730 | MADAN MOHAN SASMAL | 30.55 | 20.29 | 20
2207 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Jaulia Part- B village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000219/2023-2024 | 2328/MURD | 02/08/2023 | 730 | SARTHAK SK. | 30.55 | 10.51 | 25
2208 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Jaulia Part- C village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000220/2023-2024 | 2339/MURD | 03/08/2023 | 730 | MAHATO ENTERPRISE | 30.55 | 10.15 | 10
2209 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT JAULIA PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | BILL/00232/2024-2025 | 64/WBSEDCL-JJM | 09/05/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
2210 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT JAULIA PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | BILL/00246/2024-2025 | 77/WBSEDCL-JJM | 20/05/2024 | 0 | WBSEDCL | 4.25 | 0 | 0
2211 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. II under JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II and KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000017/2025-2026 | 1141/MEDB | 14/05/2025 | 92 | M/S K.P. PRAMANIK | 11.64 | 0 | 20
2212 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000541/2024-2025 | 327/MEDB | 10/02/2025 | 89 | M/S K.P. PRAMANIK | 11.64 | 0 | 100
2213 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 1118 nos household ,Laying of Distribution System, Rising Main , Repairing & Vertical Extension of Boundary Wall, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works ,for Augmentation work of JAGAIPUR , NAWDA Block under Murshidabad Division , PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000353/2023-2024 | 2666/MURD | 24/08/2023 | 769 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 265.09 | 110.53 | 70
2214 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0
2215 | Murshidabad Division | Berhampur Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000498/2024-2025 | 663/MURD | 19/03/2025 | 65 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0
2216 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 6.59 | 1
2217 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000011/2024-2025 | 1811/MURD/10 | 20/06/2024 | 0 | Resource Division | 11.14 | 0 | 0
2218 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000220/2023-2024 | 1219/MURD/04 | 03/05/2023 | 0 | Resource Division | 26.87 | 0 | 0
2219 | Central Drilling | Berhampur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2220 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Chhalimpur under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000066/2023-2024 | 163/BD-I | 16/05/2023 | 90 | DEBJIT DAS | 22.79 | 0 | 100
2221 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chhalimpur village, Block:- Murshidabad - Jiaganj under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000182/2023-2024 | 3043/MEDB | 02/08/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0
2222 | Berhampore Division I | Raghunathganj Sub-Division | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under RAMNAGAR DOEMKANUN ,KOMNAGAR and BANSGARA ZONE-II ground Water based Water Supply Scheme under Raninagar-II Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000109/2023-2024 | 438/BD-I | 12/07/2023 | 692 | MAA CONSTRUCTION | 93.76 | 0 | 30
2223 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Egrarashi (Village code 314576) under Ramnagar Doemkanum Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000218/2020-2021 | 982/BD-I | 17/12/2020 | 60 | MAA CONSTRUCTION | 5.73 | 4.52 | 1
2224 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khastaluk (Village code 314575) under Ramnagar Doemkanum Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000219/2020-2021 | 983/BD-I | 17/12/2020 | 60 | AZAD ENTERPRISE | 11.16 | 2.24 | 1
2225 | Berhampore Division I | Raghunathganj Sub-Division | Laying of new pipeline for Providing Balanced Functional Household Tap Connection (FHTC) which is not covered by existing distribution pipeline from nearest Ground water supply scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar Khastaluk (Village code 314586) under Ramnagar Doemkanun Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000380/2021-2022 | 1464/BD-I | 16/08/2021 | 15 | SANTANU BISWAS | 8.61 | 6.57 | 0
2226 | Berhampore Division I | Raghunathganj Sub-Division | Laying of new pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khastaluk (Village code 314575) under Ramnagar Doemkanun Ground Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. (Block-Raninagar-II) | Assistant Engineer | Junior Engineer-II | ORD/000413/2021-2022 | 1442/BD-I | 11/08/2021 | 10 | AZAD ENTERPRISE | 4.61 | 3.86 | 1
2227 | Berhampore Division I | Raghunathganj Sub-Division | Continuation Work Order for Hiring of one no. Car No. W.B-51B/6299 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer, Raghunathganj Sub Division, PHE Dte. for the period from 01.04.2021 to 30.09.2021 | Assistant Engineer | Junior Engineer-II | ORD/000455/2020-2021 | 443/BD-I | 30/03/2021 | 184 | AVINABA ENGINEERING CONCERN | 0.91 | 2.11 | 1
2228 | Berhampore Division I | Raghunathganj Sub-Division | Continuation Work Order for Hiring of one no. Car No. W.B-51B/5774 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer-II, Berhampore Division-I, PHE Dte. for the period from 01.04.2021 to 30.09.2021 | Assistant Engineer | Junior Engineer-II | ORD/000456/2020-2021 | 444/ BD-I | 30/03/2021 | 184 | AVINABA ENGINEERING CONCERN | 0.91 | 2.37 | 1
2229 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kalyanpur (village code 314577) under Ramnagar Doemkanun Ground water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000749/2021-2022 | 187/BD-I | 18/02/2022 | 45 | DAS ENTERPRISE | 37.01 | 13.87 | 71
2230 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar Chhoemkanun (village code 314579) under Ramnagar Doemkanun Ground water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000750/2021-2022 | 2208/BD-I | 10/12/2021 | 120 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 89.24 | 59.76 | 1
2231 | Berhampore Division I | Raghunathganj Sub-Division | Continuation Work Order for Hiring of one no. Car No. W.B-51B/6299 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer, Raghunathganj Sub Division, PHE Dte. for the period from 01.10.2021 to 31.12.2021. | Assistant Engineer | Junior Engineer-II | ORD/000825/2021-2022 | 1779/BD-I | 30/09/2021 | 92 | AVINABA ENGINEERING CONCERN | 0.45 | 0 | 1
2232 | Berhampore Division I | Raghunathganj Sub-Division | Continuation Work Order for Hiring of one no. Car No. W.B-51B/5774 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer-II, Berhampore Division-I, PHE Dte. for the period from 01.10.2021 to 31.12.2021 | Assistant Engineer | Junior Engineer-II | ORD/000826/2021-2022 | 1780/BD-I | 30/09/2021 | 92 | AVINABA ENGINEERING CONCERN | 0.45 | 1.14 | 1
2233 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kazipara (Village code 314608) under Kazipara Water Supply Scheme of Jalangi Block and village of Ramnagar Doemkanun (Village code 314578) under Ramnagar Doemkanun Water Supply Scheme of Raninagar-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000838/2021-2022 | 49/BD-I | 27/01/2022 | 180 | M/S S.DAS & ENTERPRISE | 337.04 | 82.3 | 1
2234 | Berhampore Division I | Raghunathganj Sub-Division | Hiring of one no. Car No- W.B-57E/2525 Scorpio Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer | Junior Engineer-II | ORD/000869/2021-2022 | 2278/BD-I | 27/12/2021 | 365 | M/S SAJAHAN CHOWDHURY | 1.81 | 1.82 | 1
2235 | Berhampore Division I | Raghunathganj Sub-Division | Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer | Junior Engineer-II | ORD/000870/2021-2022 | 2279/BD-I | 27/12/2021 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 2.65 | 1
2236 | Berhampore Division I | Raghunathganj Sub-Division | Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub-Division, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer | Junior Engineer-II | ORD/000871/2021-2022 | 2281/BD-I | 27/12/2021 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 0 | 1
2237 | Berhampore Division I | Raghunathganj Sub-Division | Hiring of one no. Car No. W.B-57C/5576 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer | Junior Engineer-II | ORD/000872/2021-2022 | 2280/BD-I | 27/12/2021 | 365 | SEBAYAN CONSTRUCTION | 1.81 | 4.76 | 1
2238 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer-II | RTOR000009/2021-2022 | 140/BD-I | 10/02/2022 | 0 | Resource Division | 15.4 | 0 | 0
2239 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sibnagar Zone-I under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000057/2023-2024 | 154/BD-I | 15/05/2023 | 90 | DATA ENTERPRISE | 30.53 | 0 | 0
2240 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Shibnagar Zone-I village, Block:- Nawda under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000218/2023-2024 | 3077/MEDB | 02/08/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0
2241 | Murshidabad Division | Berhampur Sub-Division | Construction of 450 Cum OHR, Pump House with sanitary and Water Supply Arrangement , Pump House cum Blower room And Boundary Wall for Augmentation work MAHULA of Beldanga -I Block under Murshidabad Division , PHE.Dte. PART_B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III,JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | ORD/000234/2023-2024 | 2405/MURD | 07/08/2023 | 365 | ABHISHEK BHATTACHARYA | 198.86 | 0 | 0
2242 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 3199 nos household , Laying of Distribution System, Rising Main for Augmentation work MAHULA of Beldanga -I Block under Murshidabad Division , PHE.Dte. PART _A. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III,JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | ORD/000246/2023-2024 | 2467/MURD | 09/08/2023 | 180 | SARAJIT KUMAR MAJUMDER | 306.82 | 0 | 0
2243 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III,JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.29 | 80
2244 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (MOHULA PWSS Scheme, Block - Beldanga-I) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III,JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | ORD/000840/2021-2022 | 3273/MURD | 05/10/2021 | 60 | RADIANT | 10.24 | 10.24 | 1
2245 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III,JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | RTOR000218/2023-2024 | 1290/MURD/02 | 03/05/2023 | 0 | Resource Division | 0.41 | 0 | 0
2246 | Central Drilling | Berhampur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III,JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2247 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for HILORA Zone-III Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000024/2025-2026 | 984/MURD | 02/05/2025 | 60 | M/S J.S. ENTERPRISE | 22.99 | 0 | 0
2248 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.29 | 100
2249 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0
2250 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
2251 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000095/2023-2024 | 1147/MURD/10 | 27/04/2023 | 0 | Resource Division | 25.8 | 0 | 0
2252 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2253 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT HILORA Z-III PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/00516/2024-2025 |  | 08/07/2024 | 0 | WBSEDCL | 10.62 | 0 | 0
2254 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT HILORA Z-III PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/00523/2024-2025 | 165/WBSEDCL-JJM | 29/07/2024 | 0 | WBSEDCL | 10.62 | 0 | 0
2255 | Murshidabad Division | Berhampur Sub-Division | Construction Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) and 55 mtr Boundary wall at 3rd Tubewell site of Sarbangapur Zone -II Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000039/2024-2025 | 1927/MURD | 03/07/2024 | 60 | M/S S.R.K. ENTERPRISE | 16.6 | 0 | 0
2256 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for SARBANGAPUR ZONE-II Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000052/2025-2026 | 1227/MURD | 28/05/2025 | 60 | M/S.S.S. ENTERPRISE | 19.62 | 0 | 0
2257 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 193 nos household for Augmentation of SARBANGAPUR ZONE-II PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte.(Part_C) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000136/2023-2024 | 1819/MURD | 12/07/2023 | 60 | A.M. CONSTRUCTION | 21.14 | 0 | 0
2258 | Murshidabad Division | Berhampur Sub-Division | Laying of Distribution System, Rising Main for Augmentation of SARBANGAPUR ZONE-II PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division , PHE.Dte.(Part_B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000292/2023-2024 | 2646/MURD | 23/08/2023 | 709 | DOBAY CONSTRUCTION | 229.82 | 145.35 | 70
2259 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0
2260 | Murshidabad Division | Berhampur Sub-Division | Construction of 100 Cum OHR, repairing & Overhauling of R.C.C. elevated reservoir 350 Cum capacity for Augmentation of SARBANGAPUR ZONE-II PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte.(Part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000601/2023-2024 | 3345/MURD | 28/10/2023 | 730 | SHEEMAH CONSTRUCTION | 93.54 | 0 | 75
2261 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 5.77 | 1
2262 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000014/2024-2025 | 1811/MURD/13 | 20/06/2024 | 0 | Resource Division | 4.08 | 0 | 0
2263 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000214/2023-2024 | 1219/MURD/05 | 03/05/2023 | 0 | Resource Division | 46.14 | 0 | 0
2264 | Central Drilling | Berhampur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2265 | Murshidabad Division | Kandi Sub-Division | Ground Water based water supply scheme for Sujapur Part- B village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer, Estimating Section,Junior engineer-II | ORD/000209/2023-2024 | 2320/MURD | 02/08/2023 | 822 | SOUVIK HALDER | 30.54 | 0 | 60
2266 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Sujapur Part- A village, Block:- Khargram, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer, Estimating Section,Junior engineer-II | ORD/000495/2023-2024 | 3054/MURD | 29/09/2023 | 824 | M/S BHATTACHARJEE & CO | 30.55 | 0 | 42
2267 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sujapur Part-B village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer, Estimating Section,Junior engineer-II | ORD/000212/2023-2024 | 3072/MEDB | 02/08/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0
2268 | Murshidabad Division | Kandi Sub-Division | Formal work order for Augmentation of PANCHTHUPI ZONE-II PWSS to accommodate FHTC , under Jal Jeevan Mission, Block- BURWAN of Kandi Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000814/2022-2023 | 672/MURD | 09/03/2023 | 754 | IMRAN CONSTRUCTION | 416.51 | 91.54 | 5
2269 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 1.91 | 76
2270 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000259/2023-2024 | 1230/MURD/02 | 04/05/2023 | 0 | Resource Division | 36.51 | 0 | 0
2271 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 23.3 | 11
2272 | Berhampore Mechanical | Kandi Sub-Division | Electric Service Connection at SABARMBATI PWSS ph ii, Application NO.3004494928, ID 304193739 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01081/2023-2024 | 187/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 4.81 | 0 | 0
2273 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS PANCHTHUPI PH 1 Z2 ID 304247057 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01421/2023-2024 | 313/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 7.38 | 0 | 0
2274 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS PANCHTHUPI PH3 Z2 ID 304247149 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01423/2023-2024 | 325/WBSEDCL-JJM | 06/02/2024 | 0 | WBSEDCL | 7.28 | 0 | 0
2275 | Murshidabad Division | Kandi Sub-Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
2276 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based Surangapur Zone - II (PART -A), Salar PWSS Zone-IA, IB, IIA & IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Nowda & Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 570 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 20
2277 | Murshidabad Division | Kandi Sub-Division | Augmentation of Salar PWSS Zone-IA,IB,IIA,IIB to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 4 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 4no, Construction of Boundary Wall of 600 m, Construction of 400 Cum OHR(1 no) & 300 Cum OHR(2 nos) with sub soil investigation under Jal Jeevan Mission of Bharatpur II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000647/2023-2024 | 3474/MURD | 07/11/2023 | 511 | SUJIT KUMAR SAHA | 575.6 | 0 | 10
2278 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 1.62 | 80
2279 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2280 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BELIA SHYAMPUR and Adjoining Mouzas PWSS (TW-I & II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-I Block under Berhampore Division-I, P.H.Engineering Dte. (02 Nos TW) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000082/2025-2026 | 849/BD-I | 23/06/2025 | 30 | JOY GURU ENTERPRISE | 17.75 | 0 | 0
2281 | Berhampore Division I | Berhampur Division I | BELIA SYAMPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000092/2023-2024 | 214/BD-I | 17/05/2023 | 991 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 40.8 | 0 | 50
2282 | Berhampore Division I | Berhampur Division I | BELIA SYAMPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000132/2023-2024 | 611/BD-I | 02/08/2023 | 180 | ROY CONSTRUCTION (AVIJIT ROY) | 69 | 0 | 0
2283 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000033/2023-2024 | 61/BD-1/17 | 27/04/2023 | 0 | Resource Division | 11.74 | 0 | 0
2284 | Berhampore Mechanical | Berhampur Division I | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Berhampore, Bhagawangola I and II, Domkal, Samserganj, Suti I and II block Under District Murshidabad under MEDB PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000051/2025-2026 | 45/2/MEDB | 29/05/2025 | 92 | M/S SAJAHAN CHOWDHURY | 21.32 | 0 | 0
2285 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Belia Shyampur Pipe Water Supply Scheme Block - Bhagwangola-I District - Murshidabad Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000534/2024-2025 | 320/MEDB | 10/02/2025 | 89 | SUNIL RABIDAS | 21.38 | 0 | 0
2286 | Murshidabad Division | Kandi Sub-Division | MASLA PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000188/2023-2024 | 1996/MURD | 21/07/2023 | 300 | A.K. INSDUSTRIES | 239.5 | 0 | 75
2287 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000072/2023-2024 | 1075/MURD/14 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
2288 | Central Drilling | Kandi Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000209/2023-2024 | 2203/CDD | 01/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 10
2289 | Berhampore Mechanical | Kandi Sub-Division | MASLA PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01508/2023-2024 | 392/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 4.25 | 0 | 0
2290 | Berhampore Mechanical | Kandi Sub-Division | MASLA PH-2 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01509/2023-2024 | 393/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 4.28 | 0 | 0
2291 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under MASLA ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000165/2023-2024 | 2089/MEDB | 19/06/2023 | 896 | M/S S. S. ENTERPRISE (DOMKAL) | 21.56 | 15.89 | 10
2292 | Murshidabad Division | Kandi Sub-Division | Formal work order for KALGRAM & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of KHARGRAM Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000850/2022-2023 | 780/MURD | 20/03/2023 | 1278 | SOFIQUL ISLAM | 329.98 | 108.14 | 20
2293 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000060/2023-2024 | 1075/MURD/4 | 19/04/2023 | 0 | Resource Division | 20.47 | 0 | 0
2294 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT KALGRAM PH 2 ID 304158479 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01128/2023-2024 | 216/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 6.37 | 0 | 0
2295 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under KALGRAM ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000055/2023-2024 | 1926/MEDB | 16/06/2023 | 92 | BHABANI PRASAD MANNA | 21.1 | 0 | 0
2296 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHODARAMPUR (CT) AND PRASADPUR ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000369/2023-2024 | 2721/MURD | 29/08/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0
2297 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.8 | 100
2298 | Murshidabad Division | Berhampur M/E Division | Formal work order for Khodarampur CT PWSS Construction OHR, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission, Block- Raghunathganj-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000816/2022-2023 | 674/MURD | 09/03/2023 | 365 | R.K. CONSTRUCTTION | 227.03 | 0 | 0
2299 | Murshidabad Division | Berhampur M/E Division | Khodarampur CT PWSS to accommodate FHTC, Laying Distribution System, Rising Main, under Jal Jivan Mission, Block- Raghunathganj-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000894/2022-2023 | 930/MURD | 31/03/2023 | 180 | TEKNO ENTERPRISE | 345.69 | 0 | 0
2300 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000283/2023-2024 | 1230/MURD/25 | 04/05/2023 | 0 | Resource Division | 29.19 | 0 | 0
2301 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under KHODARAMPUR(CT) ground water based water supply scheme under Block_ Raghunathganj- II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/001434/2023-2024 | 4314/MEDB | 29/12/2023 | 91 | M/S S. G. ENTERPRISE | 22.57 | 0 | 0
2302 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System of AMLAI PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Bharatpur-I Block, Kandi Sub-Division of Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000438/2023-2024 | 2886/MURD | 12/09/2023 | 842 | DHIRENDRANATH MONDAL | 591.68 | 144.25 | 10
2303 | Murshidabad Division | Kandi Sub-Division | Allied & Balance Work for Laying of Distribution System, Approach Service Road, Construction of Box Culvert and Land Development of AMLAI PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Bharatpur-I Block, Kandi Sub-Division of Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000735/2023-2024 | 55/MURD | 05/01/2024 | 605 | DHIRENDRANATH MONDAL | 53.07 | 0 | 10
2304 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | RTOR000238/2023-2024 | 1219/MURD/26 | 03/05/2023 | 0 | Resource Division | 19.9 | 0 | 0
2305 | Berhampore Mechanical | Kandi Sub-Division | Quotation for Amlai PH No-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/01430/2023-2024 | 326/WBSEDCL-JJM | 06/02/2024 | 0 | WBSEDCL | 5.41 | 0 | 0
2306 | Berhampore Mechanical | Kandi Sub-Division | Quotation for Amlai PH No-2 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/01431/2023-2024 | 327/WBSEDCL-JJM | 06/02/2024 | 0 | WBSEDCL | 11.27 | 0 | 0
2307 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under AMLAI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000258/2023-2024 | 3694/MEDB | 03/11/2023 | 92 | B. T. PROJECTS PVT. LTD. | 26.12 | 0 | 0
2308 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Koasbagoas Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP), pump house and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000023/2023-2024 | 375/BD-I | 28/06/2023 | 730 | MAMATA USHA ENTERPRISE | 534.97 | 192.14 | 75
2309 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of KASBAGOAS ZONE-II PWSS under Jal Jeevan Mission within Raninagar -I Block under Berhampore Division-I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000083/2025-2026 | 875/BD-I | 01/07/2025 | 60 | TAIMUR SK | 16.51 | 0 | 0
2310 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASBAGOAS Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000269/2022-2023 | 1692/BD-I | 14/03/2023 | 10 | RADIANT | 2.67 | 2.67 | 100
2311 | Berhampore Division I | Raghunathganj Sub-Division | Construction Pump House Cum Chlorine Room at KASBAGOAS Water Supply Scheme under Jal Jevan Mission within Raninagar-I Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000325/2024-2025 | 272/BD-I | 11/02/2025 | 60 | TAIMUR SK | 7.5 | 0 | 0
2312 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000018/2023-2024 | 194/BD-I/3 | 09/02/2024 | 0 | Resource Division | 55.6 | 0 | 0
2313 | Berhampore Mechanical | Raghunathganj Sub-Division | Meter shifting kasba goas pwss | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | BILL/01596/2023-2024 | 416/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 0.28 | 0 | 0
2314 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW CONNECTION KASBAGOAS Z-I PH-II | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | BILL/01627/2023-2024 | 479/WBSEDCL-JJM | 21/03/2024 | 0 | WBSEDCL | 3.43 | 0 | 0
2315 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW CONNECTION KASBAGOAS Z-I PH-I | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | BILL/01629/2023-2024 | 480/WBSEDCL-JJM | 21/03/2024 | 0 | WBSEDCL | 10.02 | 0 | 0
2316 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under KOASBAGOAS ground water based water supply scheme under Block_ Raninagar-I Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000059/2023-2024 | 3762/MEDB | 03/11/2023 | 92 | A.G. ENTERPRISE | 35.21 | 0 | 0
2317 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall at Sarbangapur Zone-I, P.H-2 under Sarbangapur Zone-I Water Supply Scheme under Berhampore Sub-Division , P.H.E. Dte. in the District Murshidabad. (PART B- 55.0MTR.)_Part-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000024/2023-2024 | 1028/MURD | 13/04/2023 | 30 | ABA CONTRACTOR | 4.63 | 4.2 | 100
2318 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for SARBANGAPUR ZONE-I(Part -B) Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000030/2025-2026 | 1023/MURD | 05/05/2025 | 60 | TANUSHREE ENTERPRISE | 23.01 | 0 | 0
2319 | Murshidabad Division | Berhampur Sub-Division | Construction 2 (Two ) Nos Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement and 210 mtr Boundary wall at Head Work site and 55Mtr at 2nd site of Sarbangapur Zone -IB , Bara Satui & Chandkati Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000044/2024-2025 | 1930/MURD | 03/07/2024 | 477 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 52.14 | 0 | 75
2320 | Murshidabad Division | Berhampur Sub-Division | Providing 1612 nos FHTC Connection for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000051/2024-2025 | 1976/MURD | 08/07/2024 | 45 | DIPAK BHOWMIK | 84.07 | 0 | 0
2321 | Murshidabad Division | Berhampur Sub-Division | Laying of Distribution System for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte.(Part_C) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000134/2023-2024 | 1745/MURD | 06/07/2023 | 180 | BENGAL ENTERPRISE | 84.67 | 49.86 | 70
2322 | Murshidabad Division | Berhampur Sub-Division | Construction of 200 Cum OHR, Rising Main for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block, Berhampore Sub-Division under Murshidabad Division ,PHE.Dte.(Part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000226/2023-2024 | 2369/MURD | 04/08/2023 | 730 | A.S. CONSTRUCTION | 114.35 | 0 | 100
2323 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0
2324 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sarbangapur Zone -IB Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Nawda Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000708/2023-2024 | 3806/MURD | 12/12/2023 | 21 | MAMATA USHA ENTERPRISE | 18.45 | 16.05 | 100
2325 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundwary Wall , Pump House (Two nos), Construction of PCC approach road for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000846/2023-2024 | 779/MURD | 14/03/2024 | 624 | STARK ENTERPRISE | 43.61 | 0 | 70
2326 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 4.97 | 1
2327 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000018/2024-2025 | 1811/MURD/17 | 20/06/2024 | 0 | Resource Division | 9.93 | 0 | 0
2328 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000215/2023-2024 | 1219/MURD/01 | 03/05/2023 | 0 | Resource Division | 9.73 | 0 | 0
2329 | Berhampore Mechanical | Berhampur Sub-Division | NEW SERVICE CONNECTION AT SARBANGAPUR PWSS Z1 PART B PH 2 C ID 304506962 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01239/2024-2025 |  | 11/12/2024 | 0 | WBSEDCL | 3.44 | 0 | 0
2330 | Berhampore Mechanical | Berhampur Sub-Division | NEW SERVICE CONNECTION AT SARBANGAPUR PWSS Z1 PART B PH 2 C ID 304506962 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01259/2024-2025 | 333/WBSEDCL-JJM | 19/12/2024 | 0 | WBSEDCL | 3.44 | 0 | 0
2331 | Berhampore Mechanical | Berhampur Sub-Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IB under SARBANGAPUR ground water based water supply scheme under Block_Nawda Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001487/2023-2024 | 766/MEDB | 20/02/2024 | 90 | M/S SAMRIDDHI ENTERPRISE | 23.48 | 0 | 0
2332 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for MAHAMMADPUR Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000028/2025-2026 | 1022/MURD | 05/05/2025 | 60 | SUMAN ENTERPRISE AND SUMAN AQUA | 23 | 0 | 0
2333 | Murshidabad Division | Berhampur Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MAHAMMADPUR Water Supply Scheme at Head Work Site, 2nd Site & 3 r d site at Nawda Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000108/2023-2024 | 1750/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 27.67 | 17.11 | 67
2334 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0
2335 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 390 nos household , Laying of Distribution System, Rising Main , Construction of Pump House & Boundary Wall, repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity of staging height 20 mtr, Special repair and renovation of existing Pump House and Alied Works, Repairing & Vertical Extention of Boundary Wall for Augmentation work of MAHAMMADPUR PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000876/2022-2023 | 898/MURD | 29/03/2023 | 1073 | AJOY GHOSH | 171.58 | 88.59 | 40
2336 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 5.27 | 1
2337 | Murshidabad Division | Berhampur Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) of 462 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001810/2021-2022 | 802/MURD | 24/03/2022 | 30 | M/S. UNIQUE BUILDERS | 29.37 | 3.12 | 1
2338 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under MAHAMMADPUR ground water based water supply scheme under Block_ NAWDA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000124/2023-2024 | 1911/MEDB | 16/06/2023 | 92 | HANNAN BUILDERS PVT LTD | 44.47 | 0 | 70
2339 | Berhampore Division I | Berhampur M/E Division | KALIAGACHI PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000082/2023-2024 | 1258/BD-I | 22/12/2023 | 630 | SATELLITE CONSTRUCTION | 39.24 | 0 | 25
2340 | Berhampore Division I | Berhampur M/E Division | KALIAGACHI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000271/2023-2024 | 975/BD-I | 18/10/2023 | 531 | PRANAB KUMAR GHOSH | 61.78 | 0 | 25
2341 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000025/2023-2024 | 61/BD-1/22 | 27/04/2023 | 0 | Resource Division | 13.36 | 0 | 0
2342 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000117/2023-2024 | 304/BD-1/10 | 22/02/2024 | 0 | Resource Division | 2.82 | 0 | 0
2343 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Kaliagachhi Piped Water Supply Scheme Block Lalgola, District - Murshidabad. under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000528/2024-2025 | 314/MEDB | 10/02/2025 | 89 | P. K. ENGINEERING | 21.38 | 0 | 0
2344 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kelai & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000038/2023-2024 | 1105/MURD | 24/04/2023 | 30 | NADIA TUBEWELLS | 21.35 | 0 | 100
2345 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System Part-A , Rising Main Connection FHTC, for Kelai water supply scheme of Khargram Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000051/2023-2024 | 1257/MURD | 08/05/2023 | 180 | M/S CARE | 352.42 | 112.26 | 10
2346 | Murshidabad Division | Kandi Sub-Division | Formal work order for KELAI (PART-B) & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- KHARGRAM of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000843/2022-2023 | 753/MURD | 16/03/2023 | 1022 | NURTAJ SHAIKH | 217.79 | 41.04 | 18
2347 | Berhampore Mechanical | Kandi Sub-Division | SHIFTING OF 11KV AT KELAI | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01595/2023-2024 | 439/WBSEDCL-JJM | 13/03/2024 | 0 | WBSEDCL | 3.39 | 0 | 0
2348 | Berhampore Mechanical | Kandi Sub-Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Kelai ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001484/2023-2024 | 763/MEDB | 20/02/2024 | 680 | M/S S. S. ENTERPRISE (DOMKAL) | 23.25 | 0 | 40
2349 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Kharsa Part- B village, Block:- Khargram, Kandi Sub Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000230/2023-2024 | 2341/MURD | 03/08/2023 | 60 | J.S. CONSTRUCTION | 30.54 | 0 | 15
2350 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Kharsa Part- C village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000231/2023-2024 | 2342/MURD | 03/08/2023 | 60 | M/S SAJAHAN CHOWDHURY | 30.48 | 0 | 10
2351 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Kharsa Part- E village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000233/2023-2024 | 2343/MURD | 03/08/2023 | 60 | SUGATA CHOWDHURY | 30.55 | 15.27 | 10
2352 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Kharsa Part- A village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000254/2023-2024 | 2494/MURD | 11/08/2023 | 60 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 30.55 | 0 | 20
2353 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Kharsa Part- D village, Block:- Khargram, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000478/2023-2024 | 3035/MURD | 27/09/2023 | 60 | S.N. ENTERPRISE | 29.6 | 0 | 10
2354 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. II under JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II and KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000017/2025-2026 | 1141/MEDB | 14/05/2025 | 92 | M/S K.P. PRAMANIK | 11.64 | 0 | 20
2355 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works in connection to Accommodate FHTC at Kharsa Pump House-I ground water based water supply scheme under Block_ Khargram Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000500/2024-2025 | 51/MEDB | 09/01/2025 | 90 | M/S SAMRIDDHI ENTERPRISE | 11.28 | 0 | 0
2356 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works in connection to Accommodate FHTC at Kharsa Pump House-II ground water based water supply scheme under Block_ Khargram Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000501/2024-2025 | 52/MEDB | 09/01/2025 | 90 | M/S SAMRIDDHI ENTERPRISE | 11.28 | 0 | 0
2357 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BIPRA SEKHAR AND ADJOINING MOUJAS Water Supply Scheme & ALAMPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000400/2023-2024 | 2807/MURD | 05/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 100
2358 | Murshidabad Division | Kandi Sub-Division | Construction of Ground Water Based ALAMPUR AND ADJOINING MOUZAS PWSS of accommodate FHTC( 960 Nos), Laying Distribution System, Laying Rising Main,, Switch Room, Boundary Wall, 150 CUM OHR in Kandi Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000581/2023-2024 | 3316/MURD | 22/10/2023 | 710 | H.MONDAL CONSTRUCTION | 234.45 | 72.54 | 50
2359 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | RTOR000079/2023-2024 | 1129/MURD/2 | 25/04/2023 | 0 | Resource Division | 22.13 | 0 | 0
2360 | Berhampore Mechanical | Kandi Sub-Division | AT ALAMPUR PH 2 ID 304239407 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | BILL/01474/2023-2024 | 356/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 6.44 | 0 | 0
2361 | Berhampore Mechanical | Kandi Sub-Division | AT ALAMPUR PH 1 ID 304239409 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | BILL/01475/2023-2024 | 357/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 8.13 | 0 | 0
2362 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Alampur ground water based water supply scheme under Block-Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000243/2023-2024 | 3679/MEDB | 03/11/2023 | 789 | SURAKSHA | 22.8 | 0 | 70
2363 | Murshidabad Division | Berhampur Sub-Division | Construction of Approach Road , Drain and Drum sheet walling work at Rejinagar Zone - IV PWSS in Beldanga-II Block of Berhampore Sub-Division under Murshidabad P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000187/2024-2025 | 3176/MURD | 05/12/2024 | 30 | MUKTI ENTERPRISE | 15.17 | 0 | 0
2364 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 1050 nos household , Construction of 450 Cum OHR, Laying of Distribution System, Rising Main ,Construction of Boundary Wall and Pump House with sanitary and Water Supply Arrangement for Augmentation work of REJINAGAR ZONE-IV Beldanga -II Block under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000258/2023-2024 | 2469/MURD | 09/08/2023 | 1006 | M/S. S.C. CIVIL ENTERPRISES | 482.41 | 0 | 45
2365 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 2.57 | 100
2366 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000023/2024-2025 | 1811/MURD/22 | 20/06/2024 | 0 | Resource Division | 6.47 | 0 | 0
2367 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000221/2023-2024 | 1219/MURD/24 | 03/05/2023 | 0 | Resource Division | 51.16 | 0 | 0
2368 | Berhampore Mechanical | Berhampur Sub-Division | NEW CONNECTION REJINAGAR Z-IV PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | BILL/01580/2023-2024 | 421/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 3.61 | 0 | 0
2369 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IV under Rejinagar ground water based water supply scheme under Block_ Beldanga_II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000239/2023-2024 | 3675/MEDB | 03/11/2023 | 92 | SREE RADHA ELECTRICAL | 25.04 | 18.82 | 7
2370 | Murshidabad Division | Kandi Sub-Division | Construction of 600 Cum OHR, Pump House, Boundwary Wall , Rising Main Connection, Repairing of 2 nos P.H & Existing OHR for Augmentation of GOKARNA PWSS in Kandi Block , under Murshidabad Division ,PHE.Dte. (PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000030/2023-2024 | 1086/MURD | 20/04/2023 | 712 | MD SAJAHAN ALI | 327.08 | 108.91 | 80
2371 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System & Functional Household Tap Connection (FHTC) for Augmentation of GOKARNA Water Supply Scheme under Murshidabad Division, P.H.E.Dte.(PART-C) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000042/2023-2024 | 1140/MURD | 26/04/2023 | 1071 | M/S.TAPAS KUMAR CHAKRABORTY | 358.04 | 105.44 | 30
2372 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System & Functional Household Tap Connection (FHTC) for Augmentation of GOKARNA Water Supply Scheme under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000043/2023-2024 | 1141/MURD | 26/04/2023 | 1071 | M/S.TAPAS KUMAR CHAKRABORTY | 252.26 | 8.61 | 30
2373 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS GOKARNA PWSS Scheme, Block-KANDI to be Augmention/Rejuvination under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/002151/2021-2022 | 3258/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 8.11 | 8.11 | 1
2374 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000059/2022-2023 | 1043/MURD/3 | 17/04/2023 | 0 | Resource Division | 31.92 | 0 | 0
2375 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000310/2023-2024 | 1295/MURD/05 | 11/05/2023 | 0 | Resource Division | 61.11 | 0 | 0
2376 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000342/2023-2024 | 79/MURD/09 | 09/01/2024 | 0 | Resource Division | 31.88 | 0 | 0
2377 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2378 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III under Gokarna ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000225/2023-2024 | 3665/MEDB | 03/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 34.39 | 25.63 | 60
2379 | Murshidabad Division |  | Last mile connectivity and providing 7237 nos Functional House Hold Connection from Zone- XV of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . |  |  | ORD/000337/2023-2024 | 2694/MURD | 25/08/2023 | 120 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 427.97 | 0 | 0
2380 | Murshidabad Division |  | Last mile connectivity and providing 3451 nos Functional House Hold Connection from Zone- XVII of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . |  |  | ORD/000339/2023-2024 | 2696/MURD | 25/08/2023 | 120 | M/S. BIMALENDU BOSE | 206.76 | 0 | 0
2381 | Murshidabad Division |  | Last mile connectivity and providing 5696 nos Funcational House Hold Connection from Zone-VII of Surface water based BALIA water supply scheme in Sagardighi Block under Murshidabad Division PHE Dte . |  |  | ORD/000028/2024-2025 | 1848/MURD | 25/06/2024 | 120 | M/S BOSE & CO. | 334.91 | 0 | 0
2382 | Murshidabad Division |  | Last mile connectivity and providing 4285 nos Functional House Hold Connection from Zone- VI of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. |  |  | ORD/000441/2023-2024 | 2920/MURD | 14/09/2023 | 120 | DOBAY CONSTRUCTION | 244.28 | 0 | 0
2383 | Murshidabad Division |  | Last mile connectivity and providing 8317 nos Functional House Hold Connection from Zone- XII of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte |  |  | ORD/000334/2023-2024 | 2691/MURD | 25/08/2023 | 120 | MAMATA USHA ENTERPRISE | 487.03 | 0 | 0
2384 | Murshidabad Division | Kandi Sub-Division | CHHATRAPUR PWSS under Jal Jeevan Mission of BHARATPUR -I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000477/2023-2024 | 3034/MURD | 27/09/2023 | 705 | MONDAL ENTERPRISE | 133.95 | 0 | 30
2385 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000068/2023-2024 | 1075/MURD/10 | 19/04/2023 | 0 | Resource Division | 2.47 | 0 | 0
2386 | Murshidabad Division | Jangipur Sub-Division | Allied work for construction of culvert at Paschim Puranpara(CT) Zone -I H/W site and approach road for H/W site Augmentation work under Jangipur sub division P.H.E Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000104/2024-2025 | 2182/MURD | 31/07/2024 | 335 | M/S MONDAL CONSTRUCTION | 16.73 | 0 | 100
2387 | Murshidabad Division | Jangipur Sub-Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 10.44 | 100
2388 | Murshidabad Division | Jangipur Sub-Division | Paschim Punropara Zone - I PWSS to accommodate FHTC of 4363 nos household, Laying Distribution System, Laying Rising Main under Jal Jivan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (part-1) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000745/2023-2024 | 83/MURD | 09/01/2024 | 365 | M/S. BIMALENDU BOSE | 432.11 | 0 | 0
2389 | Murshidabad Division | Jangipur Sub-Division | Paschim Punropara Zone - I PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 2nos, Construction of Boundary Wall of 220 m, Construction 750 Cum OHR with sub soil investigation Jal Jivan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE. Dte. (part-B) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000748/2023-2024 | 105/MURD | 10/01/2024 | 934 | M/S. A.T.D. PROJECTS | 289.17 | 0 | 0
2390 | Murshidabad Division | Jangipur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 2.06 | 80
2391 | Central Drilling | Jangipur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2392 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System, FHTC of AOCHA water supply scheme of BHARATPUR-II Block under Murshidabad Division, PHE Dte. in the District of Murshidabad Part-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000221/2023-2024 | 2326/MURD | 02/08/2023 | 577 | M/S GUHA & ROY ENTERPRISE | 380.76 | 129.61 | 35
2393 | Murshidabad Division | Kandi Sub-Division | Construction of 500 Cum OHR, Pump House Boundary Wall, Land Development, Rising Main Connection, Laying Distribution System of AOCHA water supply scheme of BHARATPUR-II Block under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad Part-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000245/2023-2024 | 2433/MURD | 08/08/2023 | 877 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 461.64 | 0 | 10
2394 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AOCHA AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000285/2023-2024 | 2633/MURD | 23/08/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 27.64 | 7.86 | 30
2395 | Murshidabad Division | Kandi Sub-Division | Allied & Balance work for Road Restoration of Damaged During Laying of pipeline and Laying of distribution pipe line of AOCHA Piped Water Supply Scheme, Bharatpur-II Block, Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000840/2023-2024 | 818/MURD | 15/03/2024 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 33.81 | 0 | 10
2396 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT AOUCHA PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/00470/2024-2025 |  | 02/07/2024 | 0 | WBSEDCL | 3.13 | 0 | 0
2397 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT AOUCHA PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/00471/2024-2025 | 138/WBSEDCL-JJM | 09/07/2024 | 0 | WBSEDCL | 3.13 | 0 | 0
2398 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT AOCHA PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/00534/2024-2025 | 179/WBSEDCL-JJM | 06/08/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
2399 | Berhampore Mechanical | Kandi Sub-Division | SHIFTING OF 11 KV AT AOCHA | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/01581/2023-2024 | 427/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 4.29 | 0 | 0
2400 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under AOCHA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000702/2023-2024 | 2768/MEDB | 25/07/2023 | 707 | EASTERN INDIA SALES & SERVICE | 35.18 | 0 | 100
2401 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Putia Zone-II PWS accommodate FHTC, Laying Distribution System, Laying Rising Main in Raghunathganj - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000591/2023-2024 | 3343/MURD | 28/10/2023 | 365 | MARUTI CONSTRUCTION AND CO. | 143.58 | 0 | 0
2402 | Murshidabad Division | Berhampur M/E Division | Augmentation of Putia Zone - II PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 1no, Construction of Boundary Wall of 150 m & Construction of 400 Cum OHR with sub soil investigation under Jal Jeevan Mission of Raghunathganj II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000593/2023-2024 | 3341/MURD | 28/10/2023 | 365 | DADA BHAI CONSTRUCTION | 185.23 | 0 | 0
2403 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.47 | 100
2404 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000116/2023-2024 | 1167/MURD/10 | 28/04/2023 | 0 | Resource Division | 24.14 | 0 | 0
2405 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV ,Zone-II under PUTIA ground water based water supply scheme under Block_ Raghunathganj-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000458/2023-2024 | 3722/MEDB | 03/11/2023 | 3 | GHOSH BROTHERS | 41.63 | 0 | 40
2406 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 10
2407 | Murshidabad Division | Jangipur Sub-Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0
2408 | Murshidabad Division | Jangipur Sub-Division | Laying Distribution System, Rising Main, , Repairing of Boundary Wall, Pump House & Existing OHR for Augmentation of BEWA Zone-II Water at Supply Scheme in FARAKKA Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000603/2023-2024 | 3357/MURD | 30/10/2023 | 120 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 120.09 | 62.54 | 40
2409 | Murshidabad Division | Jangipur Sub-Division | Balance Work of Road restoration damaged during laying of pipeline of Bewa Zone-II Piped Water Supply Scheme, Farakka Block, Jangipur Sub-Division under Murshidabad Division, P.H.E dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000849/2023-2024 | 824/MURD | 15/03/2024 | 624 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 11.51 | 0 | 100
2410 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 0 | 100
2411 | Murshidabad Division | Berhampur M/E Division | Augmentation of AMINABAD ZONE-I Piped Water Supply Scheme under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000725/2023-2024 | 3952/MURD | 26/12/2023 | 724 | M/S GUHA & ROY ENTERPRISE | 446.08 | 212.24 | 75
2412 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000195/2023-2024 | 1210/MURD/07 | 02/05/2023 | 0 | Resource Division | 69.83 | 0 | 0
2413 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Exsisting Pump House No. I and II under BALLALPUR PIPED WATER SUPPLY SCHEME, BLOCK- FARAKKA, DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000020/2025-2026 | 1144/MEDB | 14/05/2025 | 92 | M/S SAMRIDDHI ENTERPRISE | 24.17 | 0 | 0
2414 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-I under AMINABAD ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000075/2023-2024 | 4306/MEDB | 29/12/2023 | 91 | M/S SAMRIDDHI ENTERPRISE | 34.41 | 0 | 0
2415 | Murshidabad Division | Berhampur M/E Division | SRIKANTABATI (Part A) PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- RAGHUNATHGANJ-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000280/2023-2024 | 2644/MURD | 23/08/2023 | 365 | BIJAY CHOWDHURY | 941.07 | 0 | 0
2416 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SRIKANTABATI (CT) PART- A Water Supply Scheme at Head Work Site, 2nd Site site at Raghunathganj - I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000408/2023-2024 | 2824/MURD | 07/09/2023 | 21 | M. R. ENTERPRISE | 18.54 | 0 | 0
2417 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 6.9 | 100
2418 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | RTOR000250/2023-2024 | 1219/MURD/36 | 03/05/2023 | 0 | Resource Division | 29.51 | 0 | 0
2419 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under SRIKANTABATI(CT) ,PART-A ground water based water supply scheme under Block_ Raghunathganj-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000462/2023-2024 | 3727/MEDB | 03/11/2023 | 92 | MENAKA ENTERPRISE | 33.53 | 0 | 0
2420 | Murshidabad Division | Berhampur M/E Division | DAFAHAT CT PWSS to accommodate FHTC, Laying Distribution System, Rising Main, under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE. Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000227/2023-2024 | 2403/MURD | 07/08/2023 | 720 | MOTI RAHAMAN | 378.32 | 160.41 | 95
2421 | Murshidabad Division | Berhampur M/E Division | DAFAHAT CT PWSS to accommodate 700 cum OHR ( Dept Drg No.PC-I/OHR/6/2012), 2 Nos Pump House, 2 No Boundary Wall & Path Way under Jal Jeevan Mission of Suti - II Block, Murshidabad District under Jangipur SubDivision Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000240/2023-2024 | 2410/MURD | 07/08/2023 | 725 | M/S. MAYA CONSTRUCTION | 270.75 | 13.43 | 5
2422 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at DAFAHAT (CT) Water Supply Scheme at Head Work Site, 2nd Site site at Suti -II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000403/2023-2024 | 2822/MURD | 07/09/2023 | 21 | M. R. ENTERPRISE | 27.81 | 0 | 0
2423 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 9.39 | 100
2424 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000271/2023-2024 | 1230/MURD/12 | 04/05/2023 | 0 | Resource Division | 57.56 | 0 | 0
2425 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
2426 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION DAFAHAT PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/00167/2024-2025 | 5/WBSEDCL-JJM | 09/04/2024 | 0 | WBSEDCL | 5 | 0 | 0
2427 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION DAFAHAT PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/01661/2023-2024 |  | 27/03/2024 | 0 | WBSEDCL | 5 | 0 | 0
2428 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under DAFAHAT(CT) ground water based water supply scheme under Block_ Suti- II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000459/2023-2024 | 3723/MEDB | 03/11/2023 | 881 | M/S SAJAHAN CHOWDHURY | 44.69 | 13.43 | 35
2429 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Bazeosmanpur village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000404/2023-2024 | 2829/MURD | 07/09/2023 | 60 | KALAM SK. | 24.4 | 0 | 60
2430 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Jot Sundar village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000405/2023-2024 | 2830/MURD | 07/09/2023 | 847 | FRIENDS CONSTRUCTION | 34.71 | 0 | 40
2431 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Raghupur village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000406/2023-2024 | 2832/MURD | 07/09/2023 | 60 | MINA DAS | 34.79 | 0 | 0
2432 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Chator village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000407/2023-2024 | 2834/MURD | 07/09/2023 | 725 | SUMAN ENTERPRISE AND SUMAN AQUA | 39.37 | 5.08 | 25
2433 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Lakshmipur village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000409/2023-2024 | 2828/MURD | 07/09/2023 | 847 | DEBOJYOTI CONSTRUCTION | 24.68 | 0 | 60
2434 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Kayemba village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000410/2023-2024 | 2831/MURD | 07/09/2023 | 60 | SUPIA CONSTRUCTION | 36.61 | 0 | 0
2435 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Gangin village, Block:- Suti- I, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000411/2023-2024 | 2835/MURD | 07/09/2023 | 60 | PRASANTA BISWAS | 24.4 | 0 | 0
2436 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Ramdova village, Block:- Suti- I, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000416/2023-2024 | 2836/MURD | 07/09/2023 | 847 | K. B. CONSTRUCTION (PROP.KUNTAL BHATTACHARYA) | 26.05 | 0 | 65
2437 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Raghunathpur village, Block:- Suti- I, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000417/2023-2024 | 2837/MURD | 07/09/2023 | 60 | JYOTI TRADERS | 26.44 | 0 | 0
2438 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Bamandasbati village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000419/2023-2024 | 2833/MURD | 07/09/2023 | 843 | AJOY GHOSH (PROP. SUBHASH GHOSH) | 33.55 | 0 | 50
2439 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Bhairab Danga village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000433/2023-2024 | 2869/MURD | 11/09/2023 | 60 | SAIF TRADERS | 34.71 | 0 | 0
2440 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Sudna village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000434/2023-2024 | 2871/MURD | 11/09/2023 | 60 | SO-FINE AQUARIUM | 36.59 | 0 | 50
2441 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Char Juranpur village, Block:- Domkal, Islampur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000435/2023-2024 | 2872/MURD | 11/09/2023 | 60 | R.S CONSTRUCTION (PART- ROBIN ROY) | 23.3 | 0 | 0
2442 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Balichuna village, Block:- Bharatpur-I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000436/2023-2024 | 2870/MURD | 11/09/2023 | 722 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 38.3 | 0 | 50
2443 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Nagri village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000448/2023-2024 | 2970/MURD | 20/09/2023 | 834 | DAS CONSTRACTION (MUNNA DAS) | 28.21 | 0 | 40
2444 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Par Debidaspur village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000466/2023-2024 | 2988/MURD | 21/09/2023 | 527 | PRADIP MAHATO | 37.08 | 0 | 60
2445 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Baje Chuator village, Block:- Bharatpur-I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000467/2023-2024 | 2985/MURD | 21/09/2023 | 680 | PARTHA BHASKAR | 36.59 | 0 | 10
2446 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Berbari village, Block:- Bharatpur-I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000468/2023-2024 | 2986/MURD | 21/09/2023 | 60 | PAMIR ROY | 33.05 | 0 | 0
2447 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Mas Danga village, Block:- Domkal, Islampur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000469/2023-2024 | 2987/MURD | 21/09/2023 | 60 | SHIBAM ENTERPRISE | 28.21 | 0 | 0
2448 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Jot Raghu village, Block:- Farakka, Jangipur Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000470/2023-2024 | 2984/MURD | 21/09/2023 | 833 | RAJIB SAHA | 28.21 | 0 | 30
2449 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Saheb Nagar village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000554/2023-2024 | 3215/MURD | 13/10/2023 | 811 | BISWAJIT ROY | 29.49 | 0 | 80
2450 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Bilkurul village, Block:- Bharatpur-I, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000642/2023-2024 | 3464/MURD | 06/11/2023 | 60 | SK CONSTRUCTION (NAJIR SK.) | 30.77 | 0 | 0
2451 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Abbhla village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000643/2023-2024 | 3465/MURD | 06/11/2023 | 60 | RURAL CONSTRUCTION | 31.63 | 0 | 0
2452 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Abbhla village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000797/2023-2024 | 3616/MEDB | 03/11/2023 | 92 | HARA PROSAD DAS | 6.27 | 0 | 0
2453 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Baje Chuator village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000798/2023-2024 | 3617/MEDB | 03/11/2023 | 92 | HARA PROSAD DAS | 6.27 | 0 | 0
2454 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bajitpur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000799/2023-2024 | 3618/MEDB | 03/11/2023 | 92 | JOY BISHNU ENGINEERING CO. | 6.3 | 0 | 0
2455 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Balichuna village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000800/2023-2024 | 3619/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.3 | 0 | 0
2456 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bamandasbati village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000801/2023-2024 | 3620/MEDB | 03/11/2023 | 92 | ARINDAM MAJUMDAR | 6.27 | 0 | 0
2457 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bansbere village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000802/2023-2024 | 3621/MEDB | 03/11/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0
2458 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bazeosmanpur village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000803/2023-2024 | 3622/MEDB | 03/11/2023 | 92 | M/S S. S. ENTERPRISE (DOMKAL) | 6.15 | 0 | 0
2459 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Berbari village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000804/2023-2024 | 3623/MEDB | 03/11/2023 | 92 | M/S S. S. ENTERPRISE (DOMKAL) | 6.15 | 0 | 0
2460 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bhairab Danga village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000805/2023-2024 | 3624/MEDB | 03/11/2023 | 92 | M/S S. S. ENTERPRISE (DOMKAL) | 6.15 | 0 | 0
2461 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bilkurul village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000806/2023-2024 | 3625/MEDB | 03/11/2023 | 92 | P. K. ENGINEERING | 6.14 | 0 | 0
2462 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Gupura Part-B village, Block:- Bharatpur-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000807/2023-2024 | 3626/MEDB | 03/11/2023 | 92 | P. K. ENGINEERING | 6.14 | 0 | 0
2463 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Jot Raghu village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000810/2023-2024 | 3635/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE (CHOA) | 6.3 | 0 | 0
2464 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Jot Sundar village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000811/2023-2024 | 3636/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE (CHOA) | 6.3 | 0 | 0
2465 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kayemba village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000819/2023-2024 | 3641/MEDB | 03/11/2023 | 92 | MASSK ENGINEERING WORKS | 6.15 | 0 | 0
2466 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Lakshmipur village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000822/2023-2024 | 3643/MEDB | 03/11/2023 | 92 | JOY BISHNU ENGINEERING CO. | 6.3 | 0 | 0
2467 | Berhampore Mechanical | Kandi Sub-Division | Name of Work: Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Nagri village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000826/2023-2024 | 3646/MEDB | 03/11/2023 | 92 | ALAK KUMAR CHAKRABORTY | 6.15 | 0 | 0
2468 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Par Debidaspur village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000829/2023-2024 | 3648/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0
2469 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Raghunathpur village, Block:- Suti-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000836/2023-2024 | 3650/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0
2470 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Raghupur village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000838/2023-2024 | 3651/MEDB | 03/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0
2471 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Ramdova village, Block:- Suti-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000839/2023-2024 | 3652/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.3 | 0 | 0
2472 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Saheb Nagar village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000842/2023-2024 | 3655/MEDB | 03/11/2023 | 92 | T. N. BANERJEE | 6.15 | 0 | 0
2473 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sunda village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000844/2023-2024 | 3657/MEDB | 03/11/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0
2474 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chator village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000846/2023-2024 | 3629/MEDB | 03/11/2023 | 92 | MERCURY ENGINEERING CO | 6.33 | 0 | 0
2475 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Gangin village, Block:- Suti-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000850/2023-2024 | 3633/MEDB | 03/11/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0
2476 | Murshidabad Division | Kandi Sub-Division | Construction of 700 Cum OHR, Boundary Wall, Rising Main Connection, Laying Distribution System PART-A,FHTC at Village- KHARGRAM (Vill. code- 315195) & Village- KANDURI (Vill. code- 315166) for Augmentation of KHARGRAM PWSS in Khargram Block , under Murshidabad Division ,PHE. Dte Part-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000266/2023-2024 | 2572/MURD | 18/08/2023 | 699 | M/S. S. DAS AND ENTERPRISE | 393.75 | 74.86 | 10
2477 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System PART-B and FHTC at Vill-KHARGRAM (Village Code-315195) & Vill-DURGAPUR (Village Code-315167) for Augmentation of KHARGRAM PWSS in Khargram Block, under Murshidabad Division ,PHE. Dte Part-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000268/2023-2024 | 2573/MURD | 18/08/2023 | 561 | M/S. S. DAS AND ENTERPRISE | 370.63 | 171.49 | 5
2478 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | RTOR000066/2022-2023 | 1278/MURD/15 | 10/05/2023 | 0 | Resource Division | 26.34 | 0 | 0
2479 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | RTOR000343/2023-2024 | 79/MURD/10 | 09/01/2024 | 0 | Resource Division | 28.5 | 0 | 0
2480 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | RTOR000361/2023-2024 | MURD/439/14 | 08/02/2024 | 0 | Resource Division | 25.58 | 0 | 0
2481 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of KHARGRAM ground water based water supply scheme under Block- KHARGRAM Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000056/2023-2024 | 3239/MEDB | 22/08/2023 | 679 | DAS ENTERPRISE (CHOA) | 12.27 | 0 | 40
2482 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHARJJUNA Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000289/2023-2024 | 2635/MURD | 23/08/2023 | 587 | MAMATA USHA ENTERPRISE | 27.67 | 0 | 67
2483 | Murshidabad Division | Kandi Sub-Division | KHARJJUNA & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000437/2023-2024 | 2885/MURD | 12/09/2023 | 659 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 1366.57 | 298.17 | 35
2484 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000229/2023-2024 | 1219/MURD/19 | 03/05/2023 | 0 | Resource Division | 35.82 | 0 | 0
2485 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT KHARJUNA PH 1 C ID 304391659 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/00662/2024-2025 |  | 03/09/2024 | 0 | WBSEDCL | 3.34 | 0 | 0
2486 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under KHARJJUNA ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000703/2023-2024 | 2769/MEDB | 25/07/2023 | 92 | DAS ENTERPRISE ( MANGO LANE) | 46.73 | 0 | 0
2487 | Murshidabad Division | Berhampur M/E Division | Sinking of 2NOS. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Raturi Zone-II Water Supply Scheme and Bahutuli Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000105/2024-2025 | 2195/MURD | 31/07/2024 | 30 | SARKAR WATER SUPPLY AGENCY | 23.56 | 0 | 50
2488 | Murshidabad Division | Berhampur M/E Division | CHANDMARI , BAHUTALI & FATELLAPUR PWSS to accommodate FHTC under Jal Jeevan Mission, Block- SUTI-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000287/2023-2024 | 3176/MURD | 11/10/2023 | 813 | CHAKRABORTY CONSTRUCTION | 2258.18 | 159.88 | 10
2489 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 10.98 | 100
2490 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000251/2023-2024 | 1219/MURD/36 | 03/05/2023 | 0 | Resource Division | 48.16 | 0 | 0
2491 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000376/2023-2024 | 495/MURD/05 | 15/02/2024 | 0 | Resource Division | 23.89 | 0 | 0
2492 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT BAHUTALI PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/00174/2024-2025 | 34/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 5.25 | 0 | 0
2493 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT BAHUTALI PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/00620/2024-2025 |  | 02/08/2024 | 0 | WBSEDCL | 4.4 | 0 | 0
2494 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT BAHUTULI PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/00635/2024-2025 | 189/WBSEDCL-JJM | 12/08/2024 | 0 | WBSEDCL | 4.4 | 0 | 0
2495 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT BAHUTALI PH-III | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/01241/2024-2025 |  | 11/12/2024 | 0 | WBSEDCL | 6.18 | 0 | 0
2496 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under BAHUTULI ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000285/2023-2024 | 4318/MEDB | 29/12/2023 | 91 | EASTERN INDIA SALES & SERVICE | 46.88 | 0 | 10
2497 | Berhampore Division I | Raghunathganj Sub-Division | Wayleave Facility Charge FOR Laying of 600MM Dia. Casing Pipe FOR Passing of 350MM Dia. Carrier Water Pipeline B/W KM-254/2-254/3 Between Station Ballalpur-New Farakka under Malda Division of Eastern Railway. | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-II | BILL/00296/2024-2025 | BP-2024-25-207 | 03/10/2024 | 0 | EASTERN RAILWAY MALDA DIVISION | 5.35 | 0 | 0
2498 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of different units of WTP premises of Beniagram Water Supply scheme under, Berhampore Division -I PHE.Dte. under JJM | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-II | ORD/000024/2024-2025 | 945/BD-I | 11/06/2024 | 60 | P.M CONSTRUCTION | 97.98 | 0 | 25
2499 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Beniagram Surface water based water supply scheme to accommodate construction of OHR, pump house and boundary wall, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Farakka Block of Murshidabad District under Berhampore Division-I,PHE.Dte. in the district Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-II | ORD/000200/2023-2024 | 841/BD-I | 05/09/2023 | 365 | CHAKRABORTY CONSTRUCTION | 3038.97 | 0 | 50
2500 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-II | RTOR000003/2024-2025 | 1341/BD-I/1 | 20/08/2024 | 0 | Resource Division | 89.82 | 0 | 0
2501 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-II | RTOR000040/2023-2024 | 194/BD-I/1 | 09/02/2024 | 0 | Resource Division | 89.82 | 0 | 0
2502 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Sundarpur ground water supply scheme in Bhagwabgola-I Block, Dist_Murshidabad under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-II | ORD/000013/2025-2026 | 1138/MEDB | 13/05/2025 | 92 | QUAZI NOZRUL ISLAM (PARTNERSHIP) | 39.58 | 0 | 0
2503 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing Vertical clear water pumping machinery atop extended Steel structure for feeding newly add Zone-I B and Zone-II B of Augmentation at Beniagram Surface Water Based water supply scheme. | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-II | ORD/000327/2024-2025 | 2596/MEDB | 30/09/2024 | 182 | B. T. PROJECTS PVT. LTD. | 88.81 | 0 | 0
2504 | Murshidabad Division | Lalbag Sub-Division | Laying Distribution System , FHTC for Augmentation of Bhandara Zone-I Water Supply Scheme in Bhawangola-II Block , under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000026/2024-2025 | 1841/MURD | 25/06/2024 | 554 | DHIMAN SARKAR | 336.88 | 0 | 2
2505 | Murshidabad Division | Lalbag Sub-Division | Laying of distribution system for the left out portion of Bhandara Mouza Rising Main with DI pipe and interconnection with DI pipe at Head Work Site of Bhandara Zone - I & II Water Supply Scheme and Ancillary works in Lalbagh Sub Divisional Office under Lalbagh Sub Division, Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000090/2025-2026 | 1829/MURD | 18/08/2025 | 60 | MARUTI CONSTRUCTION AND CO. | 47.57 | 0 | 0
2506 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000349/2022-2023 | 1928/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 8.78 | 2.23 | 100
2507 | Murshidabad Division | Lalbag Sub-Division | Construction of 600 Cum OHR, Rising Main, Pump House cum Chlorine Room with Sanitary and Water Supply Arrangement & Boundary Wall with R.C.C. column at Head Work Site & 2nd Tube Well Site for Augmentation of BHANDARA Zone-I Ground Based Water Supply Scheme under Bhawangola-I Block under Lalbagh Sub Division, Murshidabad Division ,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000506/2023-2024 | 3089/MURD | 03/10/2023 | 699 | NAMITA ENTERPRISE | 257.87 | 12.93 | 2
2508 | Murshidabad Division | Lalbag Sub-Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-III, BHANDARA ZONE - I and SURANGAPUR ZONE -I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000700/2023-2024 | 3785/MURD | 11/12/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 35.34 | 0 | 80
2509 | Murshidabad Division | Lalbag Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 4.51 | 80
2510 | Berhampore Mechanical | Lalbag Sub-Division | NEW CONNECTION AT BHANDARA PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | BILL/00648/2024-2025 |  | 13/08/2024 | 0 | WBSEDCL | 3.86 | 0 | 0
2511 | Berhampore Mechanical | Lalbag Sub-Division | NEW CONNECTION AT BHANDARA PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | BILL/00655/2024-2025 | 198/WBSEDCL-JJM | 22/08/2024 | 0 | WBSEDCL | 3.86 | 0 | 0
2512 | Berhampore Mechanical | Lalbag Sub-Division | NEW CONNECTION AT BHANDARA PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | BILL/00665/2024-2025 |  | 03/09/2024 | 0 | WBSEDCL | 5.5 | 0 | 0
2513 | Berhampore Mechanical | Lalbag Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under Bhandara ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000659/2023-2024 | 3701/MEDB | 03/11/2023 | 762 | A.G. ENTERPRISE | 23.33 | 0 | 12
2514 | Murshidabad Division | Berhampur Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0
2515 | Murshidabad Division | Berhampur Sub-Division | Laying Distribution System for Augmentation of Loknathpur Zone-I (Part-A) PWSS of Beldanga-II Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000267/2023-2024 | 2575/MURD | 18/08/2023 | 180 | SAMBHU NATH ROY | 239.31 | 151.16 | 85
2516 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 2.55 | 100
2517 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Loknathpur zone-I PWSS to accommodate FHTC of 922 nos household Laying Rising Main ,Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement), Construction of Boundary Wall of 250 m and Soil Investigation & 150 Cum Construction of OHR and Special repair and renovation of existing 2 (Two) Nos Pump House and Boundary wall at Beldanga-II Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000569/2023-2024 | 3290/MURD | 19/10/2023 | 365 | VISION ENTERPRISE | 215.41 | 0 | 0
2518 | Murshidabad Division | Berhampur Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Lokenathpur Zone -I Water Supply Scheme at Head Work Site, 2nd Site site at Beldanga-II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000719/2023-2024 | 3863/MURD | 15/12/2023 | 305 | KHOKAN BISWAS | 27.6 | 0 | 100
2519 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000019/2024-2025 | 1811/MURD/18 | 20/06/2024 | 0 | Resource Division | 5.51 | 0 | 0
2520 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000387/2023-2024 | 514/MURD/01 | 16/02/2024 | 0 | Resource Division | 90.69 | 0 | 0
2521 | Berhampore Mechanical | Berhampur Sub-Division | Providing , installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I, Zone-I under Loknathpur ground water based water supply scheme under Block_ Beldanga_II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000231/2023-2024 | 3668/MEDB | 03/11/2023 | 92 | M/S SAJAHAN CHOWDHURY | 11.33 | 0 | 10
2522 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Krishnapur (Code-314218), Bansgara (Code-314222) In The Command Area Of Bansgara Ground Water Supply Scheme(Part-A)" Under Lalgola Block in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000139/2024-2025 | 1554/BD-I | 24/09/2024 | 189 | TANUSHREE ENTERPRISE | 66.93 | 0 | 0
2523 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Bansgara ( Habitation ID: 0001294178) in the village of Bansgara (Village code 314222) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.¿ | Assistant Engineer-I | JE | ORD/000140/2020-2021 | 240/BD-I | 10/02/2021 | 90 | SARAJIT KUMAR MAJUMDAR | 25.45 | 24.24 | 1
2524 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Chataidubi ( Habitation ID: 0001294180) in the village of Bansgara (Village code 314222) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000141/2020-2021 | 241/BD-I | 10/02/2021 | 90 | SANJAY BISWAS | 29.77 | 22.86 | 85
2525 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Latiberpara(HabitationID: 0001294181),Naldahari ( Habitation ID: 0001294179) ,Uttar Latiberpara ( Habitation ID: 0001796720) in the village of Bansgara (Village code 314222) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000144/2020-2021 | 250/BD-I | 11/02/2021 | 90 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 32.47 | 31.99 | 0
2526 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Krishnapur village (Village code 314218) under Bansgara Ground Water Supply Scheme in Lalgola Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-13) | Assistant Engineer-I | JE | ORD/000274/2021-2022 | 1145/BD-I | 07/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 200.42 | 50.52 | 1
2527 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kusbaria (Village code 314722) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723334 |  |  | ORD/000420/2021-2022 | 2596/MURD | 25/08/2021 | 180 | M/S NIRAPADA BHATTACHARJEE | 73.51 | 68.95 | 1
2528 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Brindabanpur (Village Code -314567) under Brindabanpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005019111). |  |  | ORD/000445/2020-2021 | 582/MURD | 09/02/2021 | 60 | M/S. BIMALENDU BOSE | 64.07 | 89.41 | 0
2529 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 437 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Brindabanpur (Village code 314567) under Brindabanpur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005019111). |  |  | ORD/001798/2021-2022 | 856/MURD | 31/03/2022 | 15 | BIMALENDU BOSE | 9.64 | 9.62 | 0
2530 | Murshidabad Division |  | Repairing & Renovation of the pump House No-1 & 2 under Katakopra Zone-II water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad. |  |  | ORD/001241/2021-2022 | 47/ISD | 28/01/2022 | 60 | R.S CONSTRUCTION (PROP- ROBIN ROY) | 3.46 | 3.46 | 0
2531 | Murshidabad Division |  | Additional works for Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Azimganjagola( Village Code -314692) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184127) |  |  | ORD/000313/2021-2022 | 1725/MURD | 08/07/2021 | 60 | MAMATA USHA ENTERPRISE | 35.34 | 0 | 1
2532 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Azimganjagola(Village code 314692) under Domkal Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. (Sl No-14) |  |  | ORD/000570/2020-2021 | 3064/MURD | 08/12/2020 | 180 | MAMATA USHA ENTERPRISE | 96.39 | 29.92 | 1
2533 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-52 |  |  | VCH/000875/2022-2023 | 360-MSD/22-23 | 19/10/2022 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 3.42 | 0 | 0
2534 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-53 |  |  | VCH/000876/2022-2023 | 360-MSD/22-23 | 19/10/2022 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 4.91 | 0 | 0
2535 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-53 |  |  | VCH/000878/2022-2023 |  | 21/09/2022 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 4.91 | 0 | 0
2536 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-HWH-2021-WL-54 |  |  | VCH/000944/2022-2023 | 371-MSD/22-23 | 21/10/2022 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 4.97 | 0 | 0
2537 | Murshidabad Division |  | Additional works of Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village AZIMGANJGOLA (Village Code 314692) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 377 of 210-22 by EE MURD |  |  | VCH/001459/2021-2022 | 357-MSD/21-22 | 09/03/2022 | 0 | MAMATA USHA ENTERPRISE | 29.56 | 0 | 0
2538 | Murshidabad Division |  | Providing Functional Household Tap Connections ( 250 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Dhulauri ( Village Code -314671) under Dhulauri Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000106/2024-2025 | 2213/MURD | 02/08/2024 | 30 | SUJAUDDIN SHAIKH | 8.8 | 0 | 0
2539 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Balarambati ( Village Code -314285) under Monigram Balarambati Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005252584) |  |  | ORD/000057/2021-2022 | 1210/MURD | 10/05/2021 | 60 | TARIKUL SK | 43.33 | 43.32 | 1
2540 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Manigram (Village code 314284) under Monigram Balarambati Ground Water Based Water Supply Scheme for Arsenic Affected Area of Sagardighi Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005252584 in the District of Murshidabad. |  |  | ORD/000533/2020-2021 | 527/MURD | 04/02/2021 | 60 | AMAL KUMAR DAS | 43.9 | 43.65 | 1
2541 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000095/2024-2025 | 1307/BD-I | 07/08/2024 | 60 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 28.84 | 0 | 0
2542 | Berhampore Division I | Berhampur Division I | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dakshin Hanumantanagar (Village code 314436) under Dakshin Hanumantanagar Ground Water based Water Supply Scheme in Bhagawangola-I Block under Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-03) | Assistant Engineer-I | JE | ORD/000384/2021-2022 | 1488/BD-I | 18/08/2021 | 180 | H.I ENTERPRISE | 217.42 | 172.18 | 1
2543 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Dakhshin Hanumantanagar (Village code-314436) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Dakhshin Hanumantanagar Ground water based Water supply scheme (Bhagwangola-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-I | JE | ORD/000795/2021-2022 | 2311/BD-I | 29/12/2021 | 60 | H.I ENTERPRISE | 30.49 | 25.99 | 1
2544 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE | RTOR000012/2021-2022 | 142/BD-I | 10/02/2022 | 0 | Resource Division | 4.56 | 0 | 0
2545 | Berhampore Division I | Berhampur Division I | Additional laying works at village Daulatabad to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna for the village of Hasanpur (Habitation Id-0001294589) at village of Hasanpur (Village Code-314405) under Hasanpur Ground Water Supply Scheme (Bhagawangola-II Block) under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000006/2022-2023 | 548/BD-I | 13/05/2022 | 10 | JAHANGIR ALAM | 2.83 | 1.87 | 1
2546 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Hasanpur ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000079/2024-2025 | 1227/BD-I | 29/07/2024 | 60 | M/S JOY MA BANAMALI | 15.89 | 0 | 0
2547 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahapur and Others under Hasanpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000113/2021-2022 | 915/BD-I | 19/05/2021 | 7 | M/S J.A CONSTRUCTION | 0.77 | 0 | 0
2548 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hasanpur (Habitation ID-0001294589 ) at village of Hasanpur (Village code 314505) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000196/2020-2021 | 967/BD-I | 17/12/2020 | 90 | JAHANGIR ALAM | 21.8 | 18.01 | 35
2549 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Shibnagar (Habitation ID-0001294590 ) at village of Hasanpur (Village code 314505) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000197/2020-2021 | 975/BD-I | 17/12/2020 | 90 | KAMIRUL SK AND CO. | 24.37 | 36.68 | 1
2550 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nazirpur (Village code 314510) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000198/2020-2021 | 963/BD-I | 17/12/2020 | 60 | SWARUP KUMAR BHATTA | 8.42 | 8.28 | 1
2551 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahapur (Village code 314536) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000199/2020-2021 | 964/BD-I | 17/12/2020 | 60 | M/S J.A CONSTRUCTION | 4.46 | 0 | 0
2552 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nazirpur and others under Hasanpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000208/2020-2021 | 275/ BD-I | 15/02/2021 | 10 | SWARUP KUMAR BHATTA | 2.26 | 0.75 | 1
2553 | Berhampore Division I | Berhampur Division I | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under HASANPUR ground Water based Water Supply Scheme of Bhagawangola-II Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000272/2023-2024 | 976/BD-I | 18/10/2023 | 90 | PRAVAT KUMAR GHOSH | 11.83 | 0 | 0
2554 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Arazi Alaipur (village code 314537) under HASANPUR Ground water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000746/2021-2022 | 2260/BD-I | 22/12/2021 | 20 | KUNTAL SAHA | 6.91 | 0 | 0
2555 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) 267 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jadabpur Nimtala ( Village Code -313796) under Jadabpur Nimtala Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000031/2022-2023 | 1089/MURD | 27/04/2022 | 20 | A.P. CONSTRUCTION | 11.9 | 9.52 | 0
2556 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) 267 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jadabpur Nimtala ( Village Code -313796) under Jadabpur Nimtala Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000767/2022-2023 | 1089 /MURD | 27/04/2022 | 20 | A.P. CONSTRUCTION | 11.9 | 1.41 | 0
2557 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000029/2021-2022 | 540/2/MURD | 25/02/2022 | 0 | Resource Division | 1.47 | 0 | 0
2558 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE |  |  | VCH/002041/2020-2021 | 489/W | 17/03/2021 | 0 | SAMBHUNATH ROY | 29.21 | 0 | 0
2559 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of ---BHALKUNDI--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - MATAI CODE- 315090 , TNO- 625/20-21/EE |  |  | VCH/002057/2020-2021 | 479/W | 12/03/2021 | 0 | M/S UNIQUE BUILDERS | 11.41 | 0 | 0
2560 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Maniknagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In Murshidabad District in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000063/2024-2025 | 1204/BD-I | 26/07/2024 | 60 | AZAD ENTERPRISE | 43.72 | 0 | 0
2561 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bhundar Kismat (Village code 314468) under Bhundar Kismat Water Supply Scheme of Bhagawangola-I Block and village of Maniknagar (Village code 315606) under Maniknagar (Zone-D) Surface water based Water Supply Scheme of Beldanga-I Block of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000841/2021-2022 | 82/BD-I | 31/01/2022 | 180 | J.D.J ENTERPRISE | 248.16 | 0 | 5
2562 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kasba Bahadurpur (Village code 314488) , under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000101/2020-2021 | 167/BD-I | 03/02/2021 | 728 | M/S SINHA & SONS | 95.89 | 19.57 | 1
2563 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rasulpur (Village code 314492) , Chandipur Ramkantapur (Village code 314483) under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE | ORD/000102/2020-2021 | 168/BD-I | 03/02/2021 | 20 | KAMIRUL SK AND CO. | 33.2 | 38.46 | 1
2564 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Saaragachhi(Village code 314453),Chainpara(Village code 314457),Rameswarbati(Village code 314458),Maliapara(Village code 314452) under Paschim Rampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE | ORD/000104/2020-2021 | 170/BD-I | 03/02/2021 | 30 | M/S. SUKUMAR SINHA | 49.93 | 37.79 | 0
2565 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-58 BU-9284 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.07.2025 to 31.10.2025. | Assistant Engineer-II | Junior Engineer-II | ORD/000092/2025-2026 | 855/BD-I | 30/06/2025 | 123 | SEBAYAN CONSTRUCTION | 0.6 | 0 | 0
2566 | Berhampore Division I | Berhampur Division I | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under Pradipdanga(Zone-H) Surface Water based Water Supply Scheme of Central Sector (Part-II) under Hariharpara Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000112/2023-2024 | 441/BD-I | 12/07/2023 | 90 | S DUTTA | 48.85 | 0 | 0
2567 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II) Under Hariharpara Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000159/2024-2025 | 1647/BD-I | 23/10/2024 | 181 | NOVELTY CONSTRUCTION | 68.93 | 0 | 70
2568 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahishmara (Village code 315474) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000229/2021-2022 | 1027/BD-I | 21/06/2021 | 50 | SARAJIT KUMAR MAJUMDAR | 42.39 | 0 | 0
2569 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rampara and Bhandardaha (Village code 315475,315476) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000230/2021-2022 | 1029/BD-I | 21/06/2021 | 70 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 65.72 | 85.65 | 1
2570 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baruipara (Village code 315465) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000231/2021-2022 | 1033/BD-I | 21/06/2021 | 70 | DECON INDIA | 62.7 | 21.06 | 1
2571 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naopara,Simulia and Panch Baria (Village code 315372,315373,315374) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000249/2021-2022 | 1028/BD-I | 21/06/2021 | 80 | M/S JHA CONSTRUCTION | 76.94 | 18.86 | 1
2572 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tekpara and Jagannathpur (Village code 315472,315477) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000250/2021-2022 | 1030/BD-I | 21/06/2021 | 90 | NEOGI ENTERPRISE | 87.92 | 59.34 | 1
2573 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lal Nagar and Bil Bhandardaha (Village code 315471,315473) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000251/2021-2022 | 1031/BD-I | 21/06/2021 | 90 | SUBHAS CHANDRA KESHARI | 86.54 | 42.48 | 1
2574 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jamalpur and Pradipdanga (Village code 315469,315470) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000252/2021-2022 | 1032/BD-I | 21/06/2021 | 70 | M/S AMIT KUMAR GUPTA | 69.96 | 19.73 | 60
2575 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-58 BU-9284 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2025 to 30.06.2025. | Assistant Engineer-II | Junior Engineer-II | ORD/000273/2024-2025 | 2335/BD-I | 30/12/2024 | 182 | SEBAYAN CONSTRUCTION | 0.91 | 0 | 0
2576 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khidirpur & Simulia Jot (Village code 315466) under Pradipdanga (Zone-H)Water Supply Scheme of Central Sector Part-II in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-06) | Assistant Engineer-II | Junior Engineer-II | ORD/000424/2021-2022 | 1595/BD-I | 31/08/2021 | 180 | NAYLA CONSTRUCTION | 105.36 | 91.58 | 1
2577 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-II | Junior Engineer-II | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 1
2578 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kismat Imadpur (Village code 315468) under Pradipdanga (Zone-H) Water Supply Scheme of Central Sector Part-II in Murshidabad Jiaganj Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-05) | Assistant Engineer-II | Junior Engineer-II | ORD/000497/2021-2022 | 1904/BD-I | 08/10/2021 | 180 | MS RUBIET HOSSAIN | 176.97 | 0 | 0
2579 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Pradipdanga Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-II | Junior Engineer-II | ORD/000756/2021-2022 | 2222/BD-I | 15/12/2021 | 90 | APURBA SAHA CHOWDHURY | 82.14 | 79.33 | 1
2580 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Jamalpur and Pradipdanga (Village code-315469 and 315470) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Pradipdanga Surface water based Water supply scheme (Hariharpara,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-II | Junior Engineer-II | ORD/000786/2021-2022 | 2290/BD-I | 28/12/2021 | 20 | M/S AMIT KUMAR GUPTA | 12.67 | 8.95 | 1
2581 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nesta & Kumirdaha (Village code 314871 & 314872) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000220/2021-2022 | 1018/BD-I | 21/06/2021 | 60 | MODERN CONSTRUCTION | 80.88 | 75.59 | 85
2582 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kanksa & Hulaspur (Village code 314882 & 314885) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000221/2021-2022 | 1019/BD-I | 21/06/2021 | 60 | RAJ KUMAR MONDAL | 78.07 | 65.04 | 1
2583 | Berhampore Division I | Berhampur Division I | Laying of CI/DI pipeline and sluice valve with chamber at different places under Rampur Zone-C,central sector part-I under JJM under Berhampore Division-I ,P.H.E Dte. In the district of Murshidabad. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000258/2024-2025 | 2271/BD-I | 16/12/2024 | 30 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 5.02 | 0 | 0
2584 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Neoai Khamarpara, Purba Gobindapur & Rampur (Village code 314876,314883 & 314884) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000259/2021-2022 | 1047/BD-I | 21/06/2021 | 60 | A ONE CONSTRUCTION | 83.87 | 71.41 | 1
2585 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dangapara,Bati & Char Ramipur (Village code 314887,314888 & 314889) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000260/2021-2022 | 1048/BD-I | 21/06/2021 | 60 | BOSE & CO | 98.62 | 77.92 | 1
2586 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2025 to 31.12.2025 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000267/2024-2025 | 2328/BD-I | 27/12/2024 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 0 | 0
2587 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dharmmapur (Village code 314875) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000276/2021-2022 | 1169/BD-I | 15/07/2021 | 90 | SHYAMAL KUMAR SAHA | 84.96 | 72.88 | 1
2588 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tentulia & Char Chatra (Village code 314873 & 314874) under Rampur (Zone-C) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-03) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000294/2021-2022 | 1180/BD-I | 16/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 114.26 | 98.18 | 1
2589 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hasenpur (Village code 314886) under Rampur (Zone-C) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-04) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000295/2021-2022 | 1181/BD-I | 16/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 117.76 | 105.56 | 1
2590 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
2591 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Rampur Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000852/2021-2022 | 133/BD-I | 08/02/2022 | 90 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 79.8 | 77.93 | 100
2592 | Murshidabad Division |  | Repair and Renovation of office cum godown at Head work site for Improvement work of Bhandara Water Supply Scheme under Lalbagh Sub Division,P.H.E. Dte.in the District Murshidabad |  |  | ORD/000057/2020-2021 | 560/MURD | 08/02/2021 | 45 | ARNAB SAHA | 5.93 | 1.09 | 0
2593 | Murshidabad Division |  | Pipe connection from new tube well to rising main including supply of material at Head Work Site of Bhandara Water Supply Scheme under Lalbagh Sub-Division, under Murshidabad Division, P.H.Engineering Dte. |  |  | ORD/000077/2022-2023 | 104/LSD | 13/04/2022 | 30 | MAA CONSTRUCTION | 2.1 | 2.09 | 1
2594 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at AMDAHARA G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000403/2021-2022 | 246/LSD | 18/08/2021 | 30 | TINA ROY | 4.18 | 0 | 1
2595 | Murshidabad Division |  | Providing Functional Household Tap Connections (1296 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Balarampur (Village Code -3144756) & Palasbati (Village Code-314476) under Bhandara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhawangola I & II Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000636/2023-2024 | 3457/MURD | 06/11/2023 | 45 | SALAUDDIN MD SIRAJI | 35.76 | 0 | 0
2596 | Murshidabad Division |  | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 |  |  | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0
2597 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sundarpur(Village code 314445) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-I | JE | ORD/000106/2020-2021 | 172/BD-I | 03/02/2021 | 30 | KAMIRUL SK AND CO. | 53.12 | 92.99 | 0
2598 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sadikhanr Diar (Village code 314638) under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723213 in the District of Murshidabad |  |  | ORD/000255/2021-2022 | 1654/MURD | 29/06/2021 | 90 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 52.11 | 52.08 | 0
2599 | Murshidabad Division |  | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 |  |  | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0
2600 | Murshidabad Division |  | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC |  |  | VCH/002047/2020-2021 | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0
2601 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Bansgara ground water supply scheme within Raninagar-II block in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000096/2024-2025 | 1320/BD-I | 12/08/2024 | 60 | JEWS CONSTRUCTION &CO | 16.78 | 0 | 0
2602 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bansgara (Village code 314587) and Majhardiar (Village code 314588) under Bansgara Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000150/2020-2021 | 271/ BD-I | 12/02/2021 | 30 | M/S S.S ENTERPRISE | 79.51 | 58.68 | 0
2603 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Kantanagar ( Village Code -314437) (Part-I) & adjoining habitation under Kantanagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186155) |  |  | ORD/000323/2021-2022 | 2396/MURD | 10/08/2021 | 60 | M/S. GHOSH ENTERPRISE | 94.58 | 0 | 0
2604 | Murshidabad Division |  | Allied work for Laying of different dia UPVC Pipeline at Chaipara, Kupkandi, Kalinagar, Dararkandi, Ashan para & Tikor para area of village Kantanagar ( Village Code 314437) in connection with "Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kantanagar ( Village Code 314437) (Part-I) & adjoining habitation under Kantanagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola-I Block under Murshidabad Division P.H.E. Dte. (Scheme I.D.- 0005186155)" (Part-C). |  |  | ORD/000354/2022-2023 | 296/LSD | 12/07/2022 | 30 | DEBASISH SARKAR | 4.76 | 4.73 | 0
2605 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Kantanagar ( Village Code -314437) (Part-II) & adjoining habitation under Kantanagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.- 0005186155) |  |  | ORD/000398/2021-2022 | 2534/MURD | 19/08/2021 | 60 | J.S. CONSTRUCTION | 94.61 | 153.42 | 0
2606 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at LALGOLA G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000399/2021-2022 | 243/LSD | 18/08/2021 | 30 | IMAGIN | 4.18 | 0 | 0
2607 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BILBORAKOPRA G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000401/2021-2022 | 244/LSD | 18/08/2021 | 30 | IMAGIN COMMUNICATION | 4.18 | 0 | 0
2608 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at KANTANAGAR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000405/2021-2022 | 247/LSD | 18/08/2021 | 30 | IMAGIN | 4.18 | 0 | 1
2609 | Murshidabad Division |  | Restoration of road for laying of different dia UPVC/CI/DI pipelines at jali Bagicha area under the Improvement work of Kantanagar Water Supply Scheme under Lalbagh Sub-Division P.H.E. Dte. |  |  | ORD/001279/2021-2022 | 417/LSD | 31/12/2021 | 7 | ANUPA ENTERPRISE | 0.94 | 0.94 | 0
2610 | Murshidabad Division |  | Laying of Different dia UPVC Pipeline at Jalibagicha, Kupkandi, Kalinagar, Dararkandi, Ashan para & Tikor para area of village Kantanagar (Village Code-314437) in connection with " Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kantanagr (Village code 314437) Part-II & adjoining habitation under Kantanagar Ground water based water supply scheme for Arsenic Affected Area of Bhagwangola-I Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005186155). |  |  | ORD/001726/2021-2022 | 706/MURD | 14/03/2022 | 60 | J.S. CONSTRUCTION | 37.51 | 37.47 | 0
2611 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village KANTANAGAR (Village Code 314437) PART-I under KANTANAGAR Ground Water Based Water Supply Scheme for arsenic affected areas of BHGWANGOLA-I Block in the District of Murshidabad. Tender no - 271 of 21-22 by EE MURD |  |  | VCH/001484/2021-2022 | 392-MSD/21-22 | 23/03/2022 | 0 | M/S. GHOSH ENTERPRISE | 61.6 | 0 | 0
2612 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Raghunathganj-II Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. |  |  | ORD/001174/2021-2022 | 364/JSD | 22/12/2021 | 30 | S.S.INFRASTRUCTURE | 3.13 | 0 | 0
2613 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-I). |  |  | ORD/001752/2021-2022 | 121/JSD | 22/03/2022 | 30 | DIPAYAN DEY | 4.2 | 3.59 | 0
2614 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-III). |  |  | ORD/001760/2021-2022 | 126/JSD | 22/03/2022 | 30 | DIPAYAN DEY | 3.73 | 3.53 | 0
2615 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-IV). |  |  | ORD/001761/2021-2022 | 127/JSD | 22/03/2022 | 30 | MOTI RAHAMAN | 3.5 | 2.94 | 0
2616 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-II). |  |  | ORD/001762/2021-2022 | 128/JSD | 22/03/2022 | 30 | MURSHID ALOM | 3.87 | 3.83 | 90
2617 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000038/2021-2022 | 540/11/MURD | 25/02/2022 | 0 | Resource Division | 2.2 | 0 | 0
2618 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) of mouza Jhamra ( 314121 ) under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - I Block of Murshidabad District PHE DTE. (Scheme ID: 0001756852). Tender no 786 of 20-21 by EE |  |  | VCH/000190/2021-2022 | 16-MSD / 21-22 | 04/08/2021 | 0 | MOTI RAHAMAN | 30.49 | 0 | 0
2619 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-II ) TNO- 786/20-21/EE |  |  | VCH/000864/2021-2022 | 206-MSD/21-22 | 25/11/2021 | 0 | MOTI RAHAMAN | 2.76 | 0 | 0
2620 | Murshidabad Division |  | CONT OF AWARENESS PROGRAMME AT DIFFERENT G.PS, TNO- 06/21-22/AE-LSD |  |  | VCH/000867/2021-2022 | 205-MSD/21-22 | 08/12/2021 | 0 | IMAGIN | 2.93 | 0 | 0
2621 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
2622 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
2623 | Murshidabad Division | Kandi Sub-Division | Continuation order for Holding Awarness Programme / Campaigning programs at Chandpur G.P, Radharghat I & II G.P. Ramnagar Bachhara G.P, Sompara-I G.P, Doulatabad G.P, & Chhaighari G.P connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000112/2020-2021 | 689/MURD | 23/02/2021 | 30 | IMAGIN COMMUNICATION | 3.17 | 6.35 | 0
2624 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of Village of Harinya, Datta Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, DakshinKhanda (Nos FHTC-4251) (Village code-315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) under DAKSHINKHANDA Ground Water Based Water Supply Scheme and Kagram ( Nos FHTC-3297) (Village code-315714) under Kagram Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block, of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID 0007338400 & 0007773828) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001278/2021-2022 | 141/MURD | 19/01/2022 | 180 | M/S. S. DAS AND ENTERPRISE | 383.18 | 78.01 | 1
2625 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | RTOR000002/2021-2022 | 3632/B/MURD | 23/11/2021 | 0 | Resource Division | 18.67 | 0 | 0
2626 | Murshidabad Division | Kandi Sub-Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Khagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Murshidabad District. T NO- 626/20-21/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000004/2021-2022 | 05/MSD/21-22 | 16/07/2021 | 0 | SOUMYADIP MISRA | 15.24 | 0 | 0
2627 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhikra (Village code 314512) ,Ranitala (Village code 314513) under Jhikra Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000110/2020-2021 | 182/BD-I | 04/02/2021 | 30 | DECON INDIA | 66.83 | 91.14 | 1
2628 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramganpara (Village code 315662) under Rampara Faridpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000227/2020-2021 | 991/BD-I | 17/12/2020 | 90 | M/S S.DAS & ENTERPRISE | 38.85 | 29.89 | 75
2629 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Bikalnagar Village (Code-315678) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000107/2024-2025 | 1443/BD-I | 04/09/2024 | 60 | SUPTI ENTERPRISE | 17.42 | 0 | 0
2630 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bikal Nagar (Village code 315678), under Kashipur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | Assistant Engineer-II | Junior Engineer-I | ORD/000116/2020-2021 | 188/BD-I | 04/02/2021 | 30 | HANNAN BUILDERS PVT. LTD. | 60.34 | 49.9 | 1
2631 | Berhampore Division I | Berhampur Division I | Additional Laying works at village BIKALNAGAR( Village code-315678) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Kashipur Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II | Junior Engineer-I | ORD/000571/2021-2022 | 1923/BD-I | 08/10/2021 | 10 | AHS (R) INFRA PRIVATE LIMITED | 7.21 | 6.55 | 1
2632 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Alampur (village code 315519) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000243/2021-2022 | 1853/BD-I | 07/10/2021 | 90 | SRIJON ENTERPRISE | 88.19 | 0 | 1
2633 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Moktarpur (Village code 314766) under Moktarpur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. (Block-Raninagar-I)(Sl-06) | Assistant Engineer | Junior Engineer-II | ORD/000382/2021-2022 | 1471/BD-I | 17/08/2021 | 1454 | M/S GOUTAM CHAKRABORTY | 122.27 | 96.08 | 75
2634 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Laskarpur ( Village Code -313850) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0005019105) |  |  | ORD/000625/2020-2021 | 595/MURD | 09/02/2021 | 60 | ARABINDA GHOSH | 71.56 | 67.42 | 1
2635 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Samserganj Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. |  |  | ORD/001176/2021-2022 | 365/JSD | 22/12/2021 | 30 | IMAGIN COMMUNICATION | 2.77 | 0 | 1
2636 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of DOGACHHI (Village code 313848) under DOGACHHI under Ground Water Based Water Supply Scheme (SAMSERGANJ Block) and BAHADURPUR (Village Code-313924) under BAHADURPUR Ground Water Based Water Supply Scheme for (SUTI-I BLOCK) Arsenic Affected Areas of under Murshidabad Division, PHE Dte. |  |  | ORD/001438/2021-2022 | 557/MURD | 28/02/2022 | 180 | M/S. NANDY ENTERPRISE | 268.47 | 73.74 | 1
2637 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of DOGACHHI (Village code 313848) under DOGACHHI under Ground Water Based Water Supply Scheme (SAMSERGANJ Block) and BAHADURPUR (Village Code-313924) under BAHADURPUR Ground Water Based Water Supply Scheme for (SUTI-I BLOCK) Arsenic Affected Areas of under Murshidabad Division, PHE Dte. |  |  | ORD/002129/2021-2022 | 557 /MURD | 28/02/2022 | 180 | M/S. NANDY ENTERPRISE | 268.47 | 0 | 1
2638 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000001/2021-2022 | 3632/A/MURD | 23/11/2021 | 0 | Resource Division | 18.39 | 0 | 0
2639 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KANKURIA-JAFRABAD ZONE-I PWSS Scheme, Block - SAMSERGANJ to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 415 of 21-22 by EE MURD |  |  | VCH/001372/2021-2022 | 301-MSD/21-22 | 07/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 8.73 | 0 | 0
2640 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KANKURIA-JAFRABAD ZONE-II PWSS Scheme, Block - SAMSERGANJ to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 408 of 21-22 by EE MURD |  |  | VCH/001374/2021-2022 | 301-MSD/21-22 | 07/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.72 | 0 | 0
2641 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) laying pipeline in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Halalpur, Mohula, Binkar, Mahishasthali, Gopinathpur & Bhabta under Mohula (ZONE-A) Water Supply Scheme in the district Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000075/2022-2023 | 1641/BD-I | 09/03/2023 | 180 | M/S JAN MAHAMMAD | 558.19 | 0 | 0
2642 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sujanipara (Village code 313923) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756899 in the District of Murshidabad. |  |  | ORD/000045/2020-2021 | 528/MURD | 04/02/2021 | 60 | R.K. CONSTRUCTION | 33.78 | 0 | 0
2643 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 1837nos household under command area of village of Panchgachhia, Arazi Ramakantapur,Gotha,Sadkpur( Village Code-313919, 313910, 313912, 313920) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001756899) |  |  | ORD/000130/2022-2023 | 1214/MURD | 10/05/2022 | 60 | SWAPAN DAS | 79.18 | 0 | 1
2644 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gotha (Village code 313912) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID : 0001756899 in the District of Murshidabad. |  |  | ORD/000162/2020-2021 | 542/MURD | 05/02/2021 | 60 | SHIRSHENDU MUKHERJEE | 7.73 | 7.46 | 1
2645 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Madna(CT) (Village code 313940) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756899 in the District of Murshidabad. |  |  | ORD/000344/2021-2022 | 2476/MURD | 16/08/2021 | 60 | NOVELTY CONSTRUCTION | 39.3 | 35.25 | 1
2646 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sadikpur (Village code 313920) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756899 in the District of Murshidabad. |  |  | ORD/000514/2020-2021 | 524/MURD | 04/02/2021 | 60 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 33.02 | 32.9 | 1
2647 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Arazi Ramakantapur (Village code 313910) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756899 in the District of Murshidabad. |  |  | ORD/000564/2020-2021 | 533/MURD | 04/02/2021 | 60 | M H SUPPLIERS | 16.7 | 33.4 | 1
2648 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gotha (Village code 313912) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756899 in the District of Murshidabad. |  |  | ORD/000684/2020-2021 | 542 / MURD | 05/02/2021 | 60 | SHIRSHENDU MUKHERJEE | 7.73 | 0 | 1
2649 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PANCHGACHHIA (Village Code 313919) under MADNA Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-I Block in the District of Murshidabad. Tender no - 790 of 20-21 by EE MURD |  |  | VCH/000294/2022-2023 | 104-MSD/22-23 | 06/05/2022 | 0 | DIPAYAN DEY | 15.99 | 0 | 0
2650 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sujanipara (313923) of Madna under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District (PART-I) |  |  | VCH/001288/2021-2022 |  | 17/02/2022 | 0 | R.K. CONSTRUCTION | 33.77 | 0 | 0
2651 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village SUJANIPARA (Village Code 313923) under MADNA Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-I Block in the District of Murshidabad. Tender no - 44 of 21-22 by EE MURD |  |  | VCH/001448/2021-2022 | 350-MSD/21-22 | 04/03/2022 | 0 | R.K. CONSTRUCTION | 33.77 | 0 | 0
2652 | Berhampore Division I | Berhampur Division I | Laying of connection for supply of drinking water at Tiktikipara Baharul Ulum Madrasah Kendra in connection with JJM (Jal Jeevan Mission) under different Berhampore Block under different water supply scheme of Behampore Division-I, P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000018/2023-2024 | 89/BD-I | 03/05/2023 | 30 | SO-FINE AQUARIUM | 1.5 | 1.5 | 100
2653 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Banjetia (Village code 315445), Sibpur (Village Code 315391) & Nagpara (Village Code 315390) under Hatinagar (Zone-A) Surface Water Supply Scheme of Central Sector Part-II, Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000245/2020-2021 | 978/BD-I | 17/12/2020 | 979 | ACQUA CONSTRUCTION CONSORTIUM | 272.06 | 161.82 | 85
2654 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Janmahammadpur (Village code 315398), Ustia (Village Code-315399) & Hatinagar (Village Code-315397) under Hatinagar (Zone-A) Surface Water Supply Scheme of Central Sector Part-II, Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000246/2020-2021 | 979/BD-I | 17/12/2020 | 826 | M/S JAN MAHAMMAD | 264.94 | 91.9 | 100
2655 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Cossimbazar (Village code 315444), Sibnagar Badarpur (Village Code-315446) under Hatinagar (Zone-A) Surface Water Supply Scheme of Central Sector Part-II, Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000313/2020-2021 | 980/BD-I | 17/12/2020 | 180 | CHAKRABORTY CONSTRUCTION | 307.25 | 43.36 | 69
2656 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | Junior Engineer-I | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 1
2657 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Madapur ( village code 315392 ) under HATINAGAR ( Zone - A ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000467/2021-2022 | 1840/BD-I | 05/10/2021 | 30 | MAA CONSTRUCTION | 24.5 | 23.96 | 1
2658 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Janmahammadpur (village code 315398),Ustia(village code315399),Hatinagar (village code 315397) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Hatinagar (Zone-A) Surface water supply scheme (Block-Berhampore)under Berhampore Division-I, PHE Dte. In the District of Murshidabad. (Part-I) | Assistant Engineer-I | Junior Engineer-I | ORD/000579/2021-2022 | 1856/BD-I | 07/10/2021 | 40 | M/S JAN MAHAMMAD | 32.92 | 32.92 | 1
2659 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Banjetia, Sibpur and Nagpara (Village code-315445,315391 and 315390) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Hatinagar (Zone-A)Surface water based Water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | Junior Engineer-I | ORD/000822/2021-2022 | 11/BD-I | 05/01/2022 | 20 | ACQUA CONSTRUCTION CONSORTIUM | 25.71 | 0 | 0
2660 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-27 |  |  | BILL/00090/2022-2023 | 471-MSD/22-23 | 29/12/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 6.18 | 0 | 0
2661 | Murshidabad Division |  | Preparation of design, Drawing and approval from the N.H.A.I Authorities including supply of 200 mm dia 8 mm thick MS Water Carring Pipe, 600 mm dia 10 mm thick MS casing Pipe & Pushing of casing pipe by Hydraulic Jacking Technique Method across the Chainage 270+550 of the N.H.-34 of at Mouza-Basudebpur of Basudebpur adjoining mouza W/S Scheme & across at chainage 273+100 of the N.H.-34 of at Mouza-Joykrishnapur of Joykrishnapur W/S Scheme in Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000853/2022-2023 | 755/MURD | 16/03/2023 | 90 | SAMBHU NATH ROY | 62.1 | 36.07 | 0
2662 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) of mouza Bara Jumla (Village Code-314144, Krishnaa Sail(Village Code-314143) of Putia and ajoining moujas under Ground water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj II Block & mouza Joykrishnapur (Village Code-313880), of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, and mouza Popara (Village Code-314326) of Sagardighi Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0005019109), 0001723441 & 0005184147) |  |  | ORD/001601/2021-2022 | 341/MURD | 10/02/2022 | 1111 | CHAKRABORTY CONSTRUCTION | 416 | 0 | 12
2663 | Murshidabad Division |  | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Basudevpur halt Station (TP NO 235/8 & 235/9) on railway land of mouza Joykrishnapur & Connecting with existing 160 mm dia UPVC distribution main line of Joykrishnapur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. |  |  | ORD/001645/2021-2022 | 510/MURD | 23/02/2022 | 60 | SAMBHU NATH ROY | 27.25 | 27.25 | 0
2664 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 889/F/MURD | 05/04/2022 | 0 | Resource Division | 5.44 | 0 | 0
2665 | Murshidabad Division |  | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block (Gria,Sekendra, Mithipur,Jotkomal,Dayarampur & Samatinagar) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000017/2020-2021 | 68 /JSD | 25/02/2021 | 30 | S.S.INFRASTRUCTURE | 2.38 | 2.38 | 0
2666 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kanupur(Village code 313992) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-12) |  |  | ORD/000531/2020-2021 | 3067/MURD | 08/12/2020 | 180 | MODERN CONSTRUCTION | 75.3 | 0 | 0
2667 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Raghunathganj-I Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. |  |  | ORD/001180/2021-2022 | 367/JSD | 22/12/2021 | 30 | IMAGIN | 1.88 | 0 | 0
2668 | Murshidabad Division | Lalbag Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kolan Radhakantapur(Village code 314523) under Bhandara Ground Water Based water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl No-04) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/000261/2022-2023 | 207-MSD/22-23 | 15/07/2022 | 0 | M/S GUNGUN CONSTRUCTION | 31.97 | 0 | 0
2669 | Murshidabad Division |  | Renovation of U.P.V.C of pipe line from Shib Mandir to Kartik Mandir due to widening of Bituminous Road of Prosadpur Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. |  |  | ORD/000722/2020-2021 | 3328 / MURD | 31/12/2020 | 45 | ARJU CONSTRUCTION | 4.99 | 4.99 | 0
2670 | Murshidabad Division |  | Renovation of UPVC pipe line from Dulal kali to Kartik Mandir due to widening of Bituminous Road of Prosadpur W/S Scheme in an emergency basis under Jangipur Sub-Division under Murshidabad Division, PHE Dte. |  |  | ORD/000723/2020-2021 | 79/JSD | 26/02/2021 | 30 | T.R. CONSTRUCTION | 5 | 5 | 0
2671 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) |  |  | ORD/001659/2021-2022 | 558/MURD | 28/02/2022 | 180 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0
2672 | Murshidabad Division | Berhampur Sub-Division | Rail Bhoomi Crossing Seva (IR-RBCS) Eastern Railway Howrah Division DEMAND NOTE Application ID: ER-HWH-2023-WL-01 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00290/2023-2024 | 157-MSD/2023-24 | 28/06/2023 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 5.5 | 0 | 0
2673 | Murshidabad Division | Berhampur Sub-Division | Allied work of Laying Distribution System, Rising Main, Construction of Boundary wall, Service Road of Arazi Madhupur & adjoining moujas PWSS under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000035/2024-2025 | 1911/MURD | 02/07/2024 | 273 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 79.82 | 0 | 65
2674 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Arazi Madhupur Water Supply Scheme of TW-I at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000593/2022-2023 | 3066/MURD | 17/11/2022 | 30 | NADIA TUBEWELLS | 10.6 | 9.23 | 0
2675 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Augmentation of Arazi Madhupur & its adjoining mouzas Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Berhampore Block within Berhampore Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000604/2022-2023 | 3171/MURD | 30/11/2022 | 1036 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 200.36 | 52.82 | 80
2676 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ARAZI MADHUPUR Water Supply Scheme at 2nd Site site at BERHAMPORE Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000707/2023-2024 | 3809/MURD | 12/12/2023 | 21 | NADIA TUBEWELLS | 11.78 | 10.52 | 90
2677 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 2.79 | 80
2678 | Murshidabad Division | Berhampur Sub-Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Kanthalia Road (KTLR) Station to Karna Subarna (KNSN) (TP NO 151/33 & 151/36) at Karna Subarna Station Gumti mouza & Connecting with existing 140mm dia HDPE distribution main line of Arazi Madhupur Ground Based W/S Scheme , Berhampore Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000821/2023-2024 | 742/MURD | 12/03/2024 | 363 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 34.02 | 0 | 80
2679 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (ARAJI MADHUPUR PWSS Scheme, Block - Berhampore) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000836/2021-2022 | 3269/MURD | 05/10/2021 | 60 | RADIANT | 3.15 | 3.15 | 1
2680 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000185/2023-2024 | 1210/MURD/02 | 02/05/2023 | 0 | Resource Division | 4.99 | 0 | 0
2681 | Berhampore Mechanical | Berhampur Sub-Division | NEW CONNECTION AT ARAJI MADHUPUR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00515/2024-2025 |  | 08/07/2024 | 0 | WBSEDCL | 5.17 | 0 | 0
2682 | Berhampore Mechanical | Berhampur Sub-Division | NEW CONNECTION AT ARAJI MADHUPUR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00522/2024-2025 | 166/WBSEDCL-JJM | 29/07/2024 | 0 | WBSEDCL | 5.17 | 0 | 0
2683 | Berhampore Mechanical | Berhampur Sub-Division | Quotaion for Shifting of LT overhead line at Araji Madhupur head work site. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01261/2022-2023 | 206/WBSEDCL | 14/03/2023 | 0 | WBSEDCL | 0.79 | 0 | 0
2684 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of Faridpur Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000535/2022-2023 | 2642/MURD | 19/09/2022 | 1096 | PRADIP KUMAR DAS | 742.15 | 310.1 | 45
2685 | Murshidabad Division | Berhampur M/E Division | Restoration work of Distribution Pipeline by laying of UPVC pipe at different location of Vulnerable Area of command area of Faridpur-II W/S Scheme under Islampur Sub-Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000577/2022-2023 | 277/ISD | 03/06/2022 | 30 | SHIBAM ENTERPRISE | 4.8 | 4.75 | 1
2686 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000030/2022-2023 | 2508/B/MURD | 31/08/2022 | 0 | Resource Division | 3.41 | 0 | 0
2687 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000030/2024-2025 | MURD/2481/03 | 04/09/2024 | 0 | Resource Division | 34.04 | 0 | 0
2688 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000034/2022-2023 | 2780/C/MURD | 01/10/2022 | 0 | Resource Division | 24.7 | 0 | 0
2689 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000046/2022-2023 | 3037/C/MURD | 16/11/2022 | 0 | Resource Division | 107.03 | 0 | 0
2690 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000154/2023-2024 | 1180/MURD/03 | 29/04/2023 | 0 | Resource Division | 107.03 | 0 | 0
2691 | Berhampore Mechanical | Berhampur M/E Division | New connection charge for Faridpur W/S Scheme, Zone-II, P/H No.-II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/00271/2023-2024 | 91/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 0.8 | 0 | 0
2692 | Berhampore Mechanical | Berhampur M/E Division | Addl service connection charges ID 860279294 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01104/2023-2024 | 213/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 2.8 | 0 | 0
2693 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-II , Zone-II of Faridpur, ground water based water supply scheme under Block- Raninagar-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000832/2023-2024 | 3773/MEDB | 03/11/2023 | 92 | JOY BISHNU ENGINEERING CO. | 11.74 | 7.62 | 20
2694 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Bhundar Kismat ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000106/2022-2023 | 1362/BD-I | 21/12/2022 | 630 | GHOSH BUILDERS | 2.41 | 0 | 100
2695 | Berhampore Division I | Berhampur Division I | Augmentation of Bhundar kismat Piped water supply scheme to accommodate construction of pump house ,boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000201/2022-2023 | 1617/BD-I | 02/03/2023 | 180 | DHIRENDRA NATH MONDAL | 222.61 | 161.51 | 60
2696 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BHUNDAR KISMAT Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000885/2021-2022 | 268/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.7 | 2.7 | 0
2697 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000059/2023-2024 | 196/BD-I/6 | 09/02/2024 | 0 | Resource Division | 48.07 | 0 | 0
2698 | Berhampore Mechanical | Berhampur Division I | BHUNDAR KISMAT PWSS | Assistant Engineer-I | JE,Junior engineer-III | BILL/01451/2023-2024 | 350/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 7.83 | 0 | 0
2699 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of BUNDHAR KISMAT ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000816/2023-2024 | 3766/MEDB | 03/11/2023 | 92 | GANGULI ELECTRICAL CO. | 11.19 | 0 | 10
2700 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gokulpur Gobindapur(Village code 314659) under Baniakhai Ground Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723470 in the District of Murshidabad. |  |  | ORD/000526/2021-2022 | 2619/MURD | 26/08/2021 | 180 | M/S PARIMAL DAS | 105.05 | 0 | 1
2701 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gokulpur Gobindapur (314659) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) |  |  | VCH/001293/2021-2022 |  | 17/02/2022 | 0 | M/S PARIMAL DAS | 103.01 | 0 | 0
2702 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gokulpur Gobindapur (314659) under Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under MSD PHE DTE. Tender No - 15 of 21-22 by SE MC |  |  | VCH/001426/2021-2022 | 344-MSD/21-22 | 04/03/2022 | 0 | M/S PARIMAL DAS | 103.01 | 0 | 0
2703 | Berhampore Division I | Berhampur Division I | Balance work for the work of Laying distribution pipe line of Diar Syampur Zone-II PWSS under Jal Jeevan Mission within Bhagwangola-I block in connection with Augmentation under Berhampore Division-I,PHE.Dte. In the district of Murshidabad. | Assistant Engineer-I | JE | ORD/000055/2025-2026 | 767/BD-I | 22/05/2025 | 90 | SANDHAN ADHIKARI | 69.54 | 0 | 0
2704 | Berhampore Division I | Berhampur Division I | Augmentation of Diar Syampur Zone-II Piped water supply scheme to accommodate construction of OHR, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE | ORD/000200/2022-2023 | 1623/BD-I | 02/03/2023 | 670 | SANDHAN ADHIKARY | 152.01 | 18.84 | 40
2705 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DIAR SYAMPUR ZONE-II Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000880/2021-2022 | 264/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.44 | 0 | 100
2706 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE | RTOR000061/2023-2024 | 196/BD-I/8 | 09/02/2024 | 0 | Resource Division | 10.99 | 0 | 0
2707 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of KHAYRAMARI (Part-B) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000334/2022-2023 | 1721/MURD | 04/07/2022 | 1276 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 262.6 | 75.51 | 30
2708 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000033/2024-2025 | MURD/2481/05 | 04/09/2024 | 0 | Resource Division | 5.07 | 0 | 0
2709 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000042/2022-2023 | 2780/K/MURD | 01/10/2022 | 0 | Resource Division | 5.07 | 0 | 0
2710 | Murshidabad Division | Jangipur Sub-Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 200 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone- II PWSS in Lalgola Block & Mirzapur (Except Gankar Mouza) PWSS Raghunathganj-I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000612/2023-2024 | 3377/MURD | 31/10/2023 | 730 | M/S GHOSH & CO. | 1181.6 | 0 | 20
2711 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS MIRZAPUR (Except Gankar Mouza) PWSS Scheme,Block-Raghunathgaunge-I) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000687/2021-2022 | 2743/MURD | 03/09/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.54 | 7.54 | 1
2712 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Augmentation of SURANGAPUR Zone-I / Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000373/2022-2023 | 2087/MURD | 27/07/2022 | 365 | MOTI RAHAMAN | 222.6 | 74.47 | 50
2713 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Surangapur Zone-I Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000596/2022-2023 | 3070/MURD | 17/11/2022 | 30 | A.M. ENTERPRISE | 10.6 | 9.46 | 100
2714 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (SURANGAPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000841/2021-2022 | 3274/MURD | 05/10/2021 | 60 | RADIANT | 15.07 | 5.02 | 1
2715 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000009/2024-2025 | 1811/MURD/08 | 20/06/2024 | 0 | Resource Division | 34.58 | 0 | 0
2716 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000295/2023-2024 | 1278/MURD/1 | 10/05/2023 | 0 | Resource Division | 75.24 | 0 | 0
2717 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000353/2023-2024 | 305/MURD/02 | 29/01/2024 | 0 | Resource Division | 62.68 | 0 | 0
2718 | Central Drilling | Berhampur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2719 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Ramnapara ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000113/2022-2023 | 1410/BD-I | 04/01/2023 | 30 | KAKALI ENTERPRISE | 2.23 | 1.23 | 100
2720 | Berhampore Division I | Berhampur Division I | Augmentation of RAMNAPARA Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000190/2022-2023 | 1456/BD-I | 17/01/2023 | 180 | S.K ENTERPRISE (RANITALA) | 34.01 | 28.79 | 100
2721 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAPARA Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000887/2021-2022 | 270/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.45 | 2.41 | 1
2722 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS | RTOR000052/2023-2024 | 196/BD-I/3 | 09/02/2024 | 0 | Resource Division | 1.74 | 0 | 0
2723 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300 mm x 200 mm dia tube well i.e. TW-I, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone-I & adjoining mouzas Water Supply Scheme at Head work site & 3 r d Site at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000125/2023-2024 | 1775/MURD | 06/07/2023 | 21 | NILAVA GHOSHAL (BUMBA) | 23.52 | 20.69 | 100
2724 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Ramnarayanpara (314614) of Narasinghapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000115/2022-2023 | 1198/MURD | 10/05/2022 | 60 | NADIA TUBEWELLS | 32.63 | 27.39 | 100
2725 | Murshidabad Division | Berhampur M/E Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ramnarayanpara (Village code 314614) under Narsinghpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184090 in the District of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000507/2020-2021 | 86/MURD | 08/01/2021 | 60 | M/S. MONDAL ENTERPRISE | 12.66 | 10.39 | 0
2726 | Berhampore Mechanical | Berhampur M/E Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Ramnarayanpur (314614) Pump House No.-I and II under Narasinghpur Ground water based water supply scheme for Arsenic Affected Areas of Jalangi Block in Murshidabad District under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/001491/2023-2024 | 767/MEDB | 20/02/2024 | 90 | CHAKRABORTY MINING AND ENGINEERING | 22.9 | 0 | 0
2727 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan mission and Jal Swapna under command area of village of Pardiar (village code-314712)under Garibpur(Zone-I & Zone - II)Ground Water Based Water supply Scheme for arsenic affected areas of Domkal Block in Murshidabad District under Murshidabad Division PHE Dte.(scheme ID-0001723342) |  |  | ORD/000112/2022-2023 | 1196/MURD | 10/05/2022 | 30 | ADITYA ENTERPRISE | 11.7 | 11.74 | 1
2728 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Pardiar (Village code 314712) under Goribpur (Zone-I and Zone-II) Ground Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723342 |  |  | ORD/000951/2021-2022 | 3631/MURD | 23/11/2021 | 120 | M/S. M.G. CONSTRUCTION | 58.5 | 21.67 | 1
2729 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandpur(Village code 314711) under Garibpur (Zone I and Zone II) Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723342 |  |  | ORD/001258/2021-2022 | 3577 / MURD | 16/11/2021 | 100 | M/S BHUBAN DAS | 52.35 | 31.51 | 1
2730 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PARDIAR (Village Code 314712) under GORIBPUR (ZONE-I AND ZONE-II) Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 107 of 21-22 by SE MC |  |  | VCH/001476/2021-2022 | 385-MSD/21-22 | 16/03/2022 | 0 | M/S. M.G. CONSTRUCTION | 36.63 | 0 | 0
2731 | Murshidabad Division | Kandi Sub-Division | Balance work of Construction of Boundary wall of 55 m length at Tentulia PWSS in Kandi block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000078/2025-2026 | 1345/MURD | 11/06/2025 | 60 | AMIT KUMAR SAHA | 6.83 | 0 | 0
2732 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of TENTULIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall, IEP and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000708/2022-2023 | 122/MURD | 13/01/2023 | 808 | SOUNAK ENTERPRISE | 271.09 | 18.38 | 10
2733 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | RTOR000052/2023-2024 | 1067/MURD/8 | 18/04/2023 | 0 | Resource Division | 1.31 | 0 | 0
2734 | Berhampore Mechanical | Kandi Sub-Division | ADDITIONAL QUOTATION AMOUNT FOR MODIFIED ROUTE TO EFFECTING THE CONNECTION AT TENTULIA PH 1 ID 860320302 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | BILL/01238/2024-2025 |  | 11/12/2024 | 0 | WBSEDCL | 4.45 | 0 | 0
2735 | Berhampore Mechanical | Kandi Sub-Division | ADDITIONAL QUOTATION AMOUNT FOR MODIFIED ROUTE TO EFFECTING THE CONNECTION AT TENTULIA PH 1 ID 860320302 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | BILL/01258/2024-2025 | 338/WBSEDCL-JJM | 17/12/2024 | 0 | WBSEDCL | 4.45 | 0 | 0
2736 | Berhampore Mechanical | Kandi Sub-Division | AT TENTULIA PH 1 ID 304239411 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | BILL/01472/2023-2024 | 361/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 3.48 | 0 | 0
2737 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under TENTULIA ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000160/2023-2024 | 2018/MEDB | 19/06/2023 | 928 | S. G. ENTERPRISE | 20.29 | 0 | 50
2738 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 20
2739 | Berhampore Division I | Berhampur M/E Division | Construction Pump House Cum Chlorine Room at Head Work site of Nasipur Zone -II Water Supply Scheme under Jal Jevan Mission of Lalgola Block of Murshidabad District under Berhampore Division -I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000069/2025-2026 | 823/BD-I | 18/06/2025 | 45 | M/S B. P. ENTERPRISE | 8.47 | 0 | 50
2740 | Berhampore Division I | Berhampur M/E Division | Augmentation of Nasipur zone_II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000140/2023-2024 | 625/BD-I | 03/08/2023 | 790 | M/S BIMALENDU BOSE | 374.96 | 0 | 10
2741 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR ZONE-II Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000364/2024-2025 | 319/BD-I | 24/02/2025 | 15 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0
2742 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of NASIPUR ZONE - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000376/2024-2025 | 431/BD-I | 19/03/2025 | 60 | ABA CONTRACTOR | 18.98 | 0 | 0
2743 | Berhampore Division I | Berhampur M/E Division | NASIPUR ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000451/2023-2024 | 454/BD-I | 15/03/2024 | 60 | INDRAJIT DUBEY | 22.41 | 0 | 50
2744 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000017/2024-2025 | 1510/BD-I/11 | 12/09/2024 | 0 | Resource Division | 5.48 | 0 | 0
2745 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000075/2023-2024 | 201/BD-1/16 | 10/02/2024 | 0 | Resource Division | 303.88 | 0 | 0
2746 | Murshidabad Division | Kandi Sub-Division | Allied work for Laying Distribution System, Construction of Boundary Wall, Approach Road & Land Development of Jajan PWSS in Bhratpur-I Block , KANDI Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000835/2023-2024 | 768/MURD | 13/03/2024 | 366 | GOURANGA MONDAL | 59.79 | 0 | 10
2747 | Murshidabad Division | Kandi Sub-Division | JAJAN & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BHARATPUR-I of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000838/2022-2023 | 758/MURD | 16/03/2023 | 777 | GOURANGA MONDAL | 343.34 | 97.75 | 10
2748 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | RTOR000065/2023-2024 | 1075/MURD/8 | 19/04/2023 | 0 | Resource Division | 22.01 | 0 | 0
2749 | Berhampore Mechanical | Kandi Sub-Division | New connection jajan ph-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/00241/2024-2025 | 109/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 4.06 | 0 | 0
2750 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under JAJAN ground water based water supply scheme under Block_ BHARATPUR-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000051/2023-2024 | 1895/MEDB | 16/06/2023 | 92 | HANNAN BUILDERS PVT LTD | 22.18 | 15.62 | 10
2751 | Berhampore Division I | Berhampur Division I | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SADHUKHALI Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000005/2023-2024 | 41/BD-I | 20/04/2023 | 10 | TECHVISION | 2.63 | 2.56 | 100
2752 | Berhampore Division I | Berhampur Division I | Augmentation of Sadhukhali Zone-II Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant( AIRP ), pump house ,boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga -II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. [2nd Call for WBPHED/EE/BD-I/NIeT-20 of 2022 ¿ 2023(sl-02)] | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000126/2023-2024 | 845/BD-I | 05/09/2023 | 310 | RAJ KUMAR MONDAL | 302.11 | 0 | 0
2753 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sadhukhali Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000389/2023-2024 | 151/BD-I | 05/02/2024 | 421 | INDRAJIT MAZUMDER | 9 | 0 | 100
2754 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | RTOR000093/2023-2024 | 196/BD-I/26 | 09/02/2024 | 0 | Resource Division | 3.7 | 0 | 0
2755 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,ZONE-II of SADHUKHALI ground water based water supply scheme under Block- Beldanga-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000076/2023-2024 | 3786/MEDB | 03/11/2023 | 92 | SARKAR CONSTRUCTION | 11.37 | 0 | 7
2756 | Murshidabad Division | Berhampur Sub-Division | Construction of 100 Cum OHR, Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 65 Cum capacity for Augmentation of SUNGAI PWSS in Berhampore Block , Berhampore Sub-Division under Murshidabad Division , PHE.Dte.(Part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000146/2023-2024 | 1869/MURD | 14/07/2023 | 764 | BABLU ENTERPRISE | 94.57 | 0 | 30
2757 | Murshidabad Division | Berhampur Sub-Division | FHTC Connection to 349 nos household, Laying of Distribution System for Augmentation of SUNGAI PWSS in Berhampore Block , Berhampore Sub-Division under Murshidabad Division , PHE. Dte.(Part_B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000235/2023-2024 | 2406/MURD | 07/08/2023 | 205 | ANKITA ENTERPRISE | 58.83 | 56.15 | 60
2758 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.01 | 80
2759 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall (Fornt Side) at SUNAI Water Supply Scheme under Berhampore Sub-Division, P.H.E. Dte. in the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001213/2021-2022 | 63/BSD | 24/02/2022 | 45 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 4.85 | 0 | 100
2760 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall (East Side) at SUNGAI Water Supply Scheme under Berhampore Sub-Division, P.H.E. Dte. in the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001660/2021-2022 | 65/BSD | 24/02/2022 | 30 | PRASANTA BISWAS | 4.82 | 4.72 | 100
2761 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 3.73 | 1
2762 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall (North Side) at SUNAI Water Supply Scheme under Berhampore Sub-Division, P.H.E. Dte. in the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/002045/2021-2022 | 64/BSD | 24/02/2022 | 45 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 4.84 | 0 | 100
2763 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000015/2024-2025 | 1811/MURD/14 | 20/06/2024 | 0 | Resource Division | 2.55 | 0 | 0
2764 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000216/2023-2024 | 1219/MURD/06 | 03/05/2023 | 0 | Resource Division | 14.2 | 0 | 0
2765 | Central Drilling | Berhampur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 13.62 | 11
2766 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000357/2023-2024 | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 1.06 | 100
2767 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
2768 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000097/2023-2024 | 1147/MURD/12 | 27/04/2023 | 0 | Resource Division | 110.07 | 0 | 0
2769 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I and II ,ZONE-I under BAZEGAZIPUR ,PART-A ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000148/2023-2024 | 2080/MEDB | 19/06/2023 | 92 | M/S S. S. ENTERPRISE (DOMKAL) | 25.46 | 19.42 | 8
2770 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 14.29 | 11
2771 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of Bali Zone-III" ground water supply scheme in NAWDA Block,under Berhampore Division-I, P.H.E Dte(Capacity-57.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000030/2024-2025 | 993/BD-I | 20/06/2024 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 165.61 | 0 | 0
2772 | Berhampore Division I | Berhampur Division I | Augmentation of Bali Zone-III Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000255/2023-2024 | 972/BD-I | 18/10/2023 | 532 | BISWAJYOTI BHATTACHARYYA | 322.8 | 25.29 | 95
2773 | Berhampore Division I | Berhampur Division I | Construction Pump House Cum Chlorine Room at Head Work site of BALI ZONE-III Water Supply Scheme, under Jal Jevan Mission within Nawda Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000324/2024-2025 | 271/BD-I | 11/02/2025 | 239 | M/S MUKTI CONSTRUCTION | 8.55 | 0 | 90
2774 | Berhampore Division I | Berhampur Division I | BALI ZONE-III PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of NAWDA Block, Murshidabad District under Berhampore Division-I, PHE.Dte | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000447/2023-2024 | 450/BD-I | 15/03/2024 | 338 | ANUPA ENTERPRISE | 21.03 | 0 | 100
2775 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000057/2023-2024 | 196/BD-I/19 | 09/02/2024 | 0 | Resource Division | 18.26 | 0 | 0
2776 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Kazipara Zone_I Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000121/2023-2024 | 505/BD-I | 24/07/2023 | 180 | M/S S.DAS & ENTERPRISE | 178 | 0 | 10
2777 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KAJIPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000280/2022-2023 | 1764/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.74 | 2.74 | 100
2778 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-III | RTOR000014/2023-2024 | 61/BD-1/12 | 27/04/2023 | 0 | Resource Division | 35.26 | 0 | 0
2779 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 4.4 | 100
2780 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHORAMARA Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000619/2023-2024 | 3394/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 0 | 50
2781 | Murshidabad Division | Berhampur M/E Division | Formal work order for the work of GHORAMARA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Samserganj Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000733/2022-2023 | 375/MURD | 10/02/2023 | 365 | PRODEEP KUMAR GHOSH | 295.5 | 0 | 0
2782 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000270/2023-2024 | 1230/MURD/14 | 04/05/2023 | 0 | Resource Division | 14.54 | 0 | 0
2783 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I II & III under GHORAMARA ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000063/2023-2024 | 1929/MEDB | 16/06/2023 | 183 | ORIENTAL ENGINEERING CO. | 31.23 | 0 | 0
2784 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 60 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for FATELLAPUR Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000038/2025-2026 | 1155/MURD | 20/05/2025 | 60 | WATER TECH | 33.62 | 0 | 0
2785 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.25 | 100
2786 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at FATELLAPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000712/2023-2024 | 3837/MURD | 14/12/2023 | 21 | SUJIT KUMAR SAHA | 11.79 | 0 | 100
2787 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main & Distribution System for Augmentation of FATELLAPUR Piped Water Supply in SUTI-I Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000839/2022-2023 | 743/MURD | 16/03/2023 | 180 | RAJU ENTERPRISE | 66.32 | 19.05 | 36
2788 | Murshidabad Division | Berhampur M/E Division | Providing FHTC Connection to 1823 no household, Overhauling of RCC 350 Cum OHR & Repair of Boundary Wall =150 m at T/W-I site & T/W-II site for Augmentation of FATELLAPUR Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000878/2022-2023 | 903/MURD | 29/03/2023 | 180 | M/S M.S. ENTERPRISE | 106.37 | 0 | 0
2789 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000190/2023-2024 | 1210/MURD/18 | 02/05/2023 | 0 | Resource Division | 24.99 | 0 | 0
2790 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
2791 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under FATELLAPUR ground water based water supply scheme under Block_ Suti-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000670/2023-2024 | 4294/MEDB | 29/12/2023 | 91 | WEST BENGAL ENGINEERING CO. | 33.56 | 0 | 0
2792 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-II | Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
2793 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Swaruppur (Village code 315505) under Lochanmati (Zone-E) Water Supply Scheme of Central Sector Part-II in Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-10) | Assistant Engineer-II | Junior Engineer-II | ORD/000498/2021-2022 | 1905/BD-I | 08/10/2021 | 180 | M/S RUBIET HOSSAIN | 144.19 | 0 | 0
2794 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lochanmati Dangapara (village code 315498) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000729/2021-2022 | 2201/BD-I | 10/12/2021 | 90 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 85.79 | 81.81 | 1
2795 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sankarpur (village code 315489) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000730/2021-2022 | 2202/BD-I | 10/12/2021 | 689 | UTTAM MUKHERJEE | 76.01 | 65.33 | 87
2796 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dharampur Ramna (village code 315497) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000731/2021-2022 | 153/BD-I | 11/02/2022 | 70 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 59.15 | 41.11 | 1
2797 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Siddhi Nandi (village code 315504) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000732/2021-2022 | 241/BD-I | 03/03/2022 | 45 | PRANAB KUMAR GHOSH | 36.64 | 30.74 | 85
2798 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kaludiar (village code 315501) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000733/2021-2022 | 154/BD-I | 11/02/2022 | 45 | MUNNA AGROTECH ENTERPRISE | 34.19 | 0 | 0
2799 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tekona (village code 315492) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000734/2021-2022 | 186/BD-I | 18/02/2022 | 1279 | DAS ENTERPRISE | 32.28 | 0 | 70
2800 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramkrishnapur (village code 315490) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000736/2021-2022 | 2251/BD-I | 21/12/2021 | 45 | S DUTTA | 28.82 | 0 | 0
2801 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sundalpur (village code 315502) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000737/2021-2022 | 2204/BD-I | 10/12/2021 | 30 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 24.6 | 22.86 | 1
2802 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khamarbati (village code 315494) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000738/2021-2022 | 2253/BD-I | 21/12/2021 | 30 | RAJEN DAS | 24.27 | 22.02 | 1
2803 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dharampur (village code 315496) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000739/2021-2022 | 2304/BD-I | 28/12/2021 | 30 | SUKUMAR ROY | 22.73 | 21.68 | 1
2804 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Janarddanpur (village code 315493) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000740/2021-2022 | 155/BD-I | 11/02/2022 | 30 | ANKITA ENTERPRISE-GOPEJAN(NATHPARA) | 10.56 | 10.17 | 1
2805 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhanjha (village code 315503) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000741/2021-2022 | 242/BD-I | 03/03/2022 | 20 | ANKITA ENTERPRISE | 4.64 | 3.4 | 1
2806 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jamlabad (village code 315495) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000742/2021-2022 | 156/BD-I | 11/02/2022 | 20 | U.S BUILDERS | 7.58 | 5.6 | 1
2807 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for SIKDARPUR Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000015/2025-2026 | 962/MURD | 30/04/2025 | 60 | SAMAR MUKHERJEE | 19.62 | 0 | 0
2808 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 7.64 | 1
2809 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
2810 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 300 & 100 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Joykrishnapur Zone-I, Zone- II & Sikdarpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000557/2023-2024 | 3243/MURD | 15/10/2023 | 365 | BIJAY CHOWDHURY | 894.65 | 0 | 0
2811 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sikdarpur Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000715/2023-2024 | 3833/MURD | 14/12/2023 | 627 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 40
2812 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Sikdarpur water supply scheme in Samserganj Block of Murshidabad District under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000535/2024-2025 | 321/MEDB | 10/02/2025 | 89 | M/S S. R. ENTERPRISE | 22.71 | 0 | 0
2813 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 11.81 | 20
2814 | Berhampore Division I | Berhampur Division I | KHAGJANA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jeevan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART - A) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000011/2023-2024 | 93/BD-I | 03/05/2023 | 1079 | S.K ENTERPRISE (RANITALA) | 290.8 | 41.17 | 75
2815 | Berhampore Division I | Berhampur Division I | KHAGJANA PWSS to accommodate FHTC, Laying Distribution System,, under Jal Jeevan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000040/2023-2024 | 118/BD-I | 11/05/2023 | 180 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 96.97 | 0 | 50
2816 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHAGJANA and Adjoining Mouzas PWSS (TW - II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division - I, P.H.Engineering Dte. (01 No TW). | Assistant Engineer-I | JE,Junior engineer-III | ORD/000047/2025-2026 | 754/BD-I | 22/05/2025 | 15 | AJOY GHOSH | 9.01 | 0 | 0
2817 | Berhampore Division I | Berhampur Division I | KHAGJANA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000100/2023-2024 | 218/BD-I | 17/05/2023 | 630 | S.K ENTERPRISE (RANITALA) | 53.17 | 0 | 65
2818 | Berhampore Division I | Berhampur Division I | Allied work of Laying of Distribution system for the work of Khagjana PWSS to accommodate FHTC, OHR, Laying distribution system, Rising Main under Jal Jeevan Mission of Bhagwangola- II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (Part-A) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000165/2024-2025 | 1684/BD-I | 28/10/2024 | 155 | S.K ENTERPRISE (RANITALA) | 68.11 | 0 | 96
2819 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000027/2023-2024 | 61/BD-1/18 | 27/04/2023 | 0 | Resource Division | 11.87 | 0 | 0
2820 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION AT KHAGJANA PH-I | Assistant Engineer-I | JE,Junior engineer-III | BILL/00248/2024-2025 | 105/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 4.03 | 0 | 0
2821 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION AT KHAGJANA PH-II | Assistant Engineer-I | JE,Junior engineer-III | BILL/01138/2024-2025 |  | 26/11/2024 | 0 | WBSEDCL | 4.29 | 0 | 0
2822 | Murshidabad Division | Kandi Sub-Division | SALU & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-II of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000279/2023-2024 | 2642/MURD | 23/08/2023 | 584 | M/S. CHAKRABORTY & COMPANY | 601.12 | 173.08 | 20
2823 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | RTOR000062/2023-2024 | 1043/MURD/12 | 18/04/2023 | 0 | Resource Division | 13.2 | 0 | 0
2824 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT SALU PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/00234/2024-2025 |  | 02/05/2024 | 0 | WBSEDCL | 4.09 | 0 | 0
2825 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT SALU PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/00237/2024-2025 | 67/WBSEDCL-JJM | 09/05/2024 | 0 | WBSEDCL | 4.09 | 0 | 0
2826 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SALU ground water based water supply scheme under Block_ Bharatpur-IIDist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000117/2023-2024 | 1906/MEDB | 16/06/2023 | 92 | S. K. ENTERPRISE | 23.82 | 19.53 | 15
2827 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 8.3 | 1
2828 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
2829 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0
2830 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000119/2023-2024 | 1167/MURD/13 | 28/04/2023 | 0 | Resource Division | 122.55 | 0 | 0
2831 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-IIA under Bhasaipaikar ground water based water supply scheme under Block_ Samserganj ,Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000247/2023-2024 | 3683/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE (CHOA) | 34.39 | 28.35 | 15
2832 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Arazi Saikuli under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000063/2023-2024 | 160/BD-I | 15/05/2023 | 90 | ABA CONTRACTOR | 28.97 | 0 | 0
2833 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Arazi Saikuli village, Block:- Murshidabad - Jiaganj under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000173/2023-2024 | 3034 | 02/08/2023 | 92 | GANGULI ELECTRICAL CO. | 6.3 | 0 | 0
2834 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Paschim Gobindapur under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000068/2023-2024 | 739/BD-I | 17/08/2023 | 90 | M/S MODERN CONSTRUCTION AND CO | 23.95 | 0 | 0
2835 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Pashchim Gobindapur village, Block:- Murshidabad Jiaganj under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000647/2023-2024 | 3159/MEDB | 08/08/2023 | 92 | MITRA ASSOCIATE | 6.15 | 0 | 0
2836 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Bilgobra under Bhagwangola-I block of Murshidabad district under Berhampore division-I,P.H.E Dte | Assistant Engineer-I | JE,Junior engineer-III | ORD/000079/2023-2024 | 185/BD-I | 17/05/2023 | 90 | BIJOY SINGHA | 26.73 | 0 | 0
2837 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 2.41 | 90
2838 | Murshidabad Division | Berhampur M/E Division | Construction of Ground Water Based Gokul Chak PWSS of accommodate FHTC(834 Nos), Laying Distribution System, Laying Rising Main, Switch Room, Boundary Wall in Domkal Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000726/2023-2024 | 3953/MURD | 26/12/2023 | 573 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 108.82 | 0 | 60
2839 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATAKOBRA ZONE-I&II Water Supply Scheme and Gokul Chak Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000868/2023-2024 | 832/MURD | 15/03/2024 | 21 | NADIA TUBEWELLS | 11.78 | 0 | 100
2840 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Gokul Chak ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000652/2023-2024 | 3684/MEDB | 03/11/2023 | 92 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 22.14 | 0 | 15
2841 | Murshidabad Division | Kandi Sub-Division | Formal work order for SYAMPUR & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of BURWAN Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000858/2022-2023 | 803/MURD | 22/03/2023 | 1016 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 448.94 | 146.09 | 75
2842 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000063/2023-2024 | 1075/MURD/6 | 19/04/2023 | 0 | Resource Division | 10.59 | 0 | 0
2843 | Berhampore Mechanical | Kandi Sub-Division | Shyampur PH-1 Application no- 300454852 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01176/2023-2024 | 234/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 5.34 | 0 | 0
2844 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Syampur ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000168/2023-2024 | 2091/MEDB | 19/06/2023 | 92 | ARINDAM MAJUMDAR | 21.72 | 0 | 15
2845 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I B Water Supply Scheme at Head Work Site, 2nd Site site at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000124/2023-2024 | 1774/MURD | 06/07/2023 | 21 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 0
2846 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
2847 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, FHTC, construction of OHR (Capacity 300 & 400 cum), Sinking of Tube Well , and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of MAHADEBNAGAR ZONE- IA,IB,IC ,IIA & IIB PWSS in Farakka Block, Murshidabad District under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000790/2023-2024 | 441/MURD | 08/02/2024 | 693 | MACKINTOSH BURN LIMITED | 1715.31 | 0 | 36
2848 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000129/2023-2024 | 1167/MURD/29 | 28/04/2023 | 0 | Resource Division | 24.86 | 0 | 0
2849 | Berhampore Mechanical | Berhampur M/E Division | POWER CONNECTION AT PWSS Z 1B PH2 MAHADEBNAGAR APPLICATION NO.3004627439 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | BILL/00186/2024-2025 | 41/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 3.5 | 0 | 0
2850 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT MAHADEBNAGAR ZIB, PH1 C ID 304390379 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | BILL/00661/2024-2025 |  | 03/09/2024 | 0 | WBSEDCL | 9.48 | 0 | 0
2851 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT MAHADEBNAGAR ZIB, PH1 C ID 304390379 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | BILL/00901/2024-2025 | 215/WBSEDCL-JJM | 11/09/2024 | 0 | WBSEDCL | 9.48 | 0 | 0
2852 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IB under Mahadebnagar ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000233/2023-2024 | 3670/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 22.94 | 0 | 60
2853 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for JOYKRISHNAPUR Zone -I Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000035/2025-2026 | 1112/MURD | 15/05/2025 | 60 | IDEAS CONSULTANCY | 22.9 | 0 | 0
2854 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jaykrishnapur Zone- I & Hilora Zone-II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000133/2023-2024 | 1769/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 18.45 | 0 | 100
2855 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
2856 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 300 & 100 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Joykrishnapur Zone-I, Zone- II & Sikdarpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000557/2023-2024 | 3243/MURD | 15/10/2023 | 365 | BIJAY CHOWDHURY | 894.65 | 0 | 0
2857 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000176/2023-2024 | 1180/MURD/25 | 29/04/2023 | 0 | Resource Division | 39.84 | 0 | 0
2858 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 1.74 | 100
2859 | Murshidabad Division | Jangipur Sub-Division | Laying of Distribution System for Augmentation of KADOA (ZONE-I) Part B PWSS in SUTI-I Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000862/2022-2023 | 807/MURD | 22/03/2023 | 741 | M/S GUNGUN CONSTRUCTION | 137.96 | 79.79 | 92
2860 | Murshidabad Division | Jangipur Sub-Division | Providing FHTC Connection to 923 no household and Overhauling of RCC 450 Cum OHR for Augmentation of KADOA (ZONE-I) Part B Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000866/2022-2023 | 829/MURD | 23/03/2023 | 1099 | SAMAR MUKHERJEE | 127.28 | 8.83 | 90
2861 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000198/2023-2024 | 1210/MURD/06 | 02/05/2023 | 0 | Resource Division | 137.87 | 0 | 0
2862 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000385/2023-2024 | 495/MURD/11 | 15/02/2024 | 0 | Resource Division | 25.47 | 0 | 0
2863 | Murshidabad Division | Kandi Sub-Division | Formal work order for BHAGULIA & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000805/2022-2023 | 619/MURD | 03/03/2023 | 760 | SUMAN ENTERPRISE AND SUMAN AQUA | 183.62 | 135.79 | 50
2864 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000074/2023-2024 | 1075/MURD/16 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
2865 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000338/2023-2024 | 79/MURD/05 | 09/01/2024 | 0 | Resource Division | 3.82 | 0 | 0
2866 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000357/2023-2024 | MURD/439/02 | 08/02/2024 | 0 | Resource Division | 0.03 | 0 | 0
2867 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT TALBONA , BHAGULIA PH I, ID304233557 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01206/2023-2024 | 269/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 12.52 | 0 | 0
2868 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT BHAGULIA PH II, ID304233683 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01207/2023-2024 | 270/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 7.24 | 0 | 0
2869 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under BHAGULIA ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000264/2023-2024 | 3700/MEDB | 03/11/2023 | 790 | A.G. ENTERPRISE | 20.9 | 0 | 70
2870 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHAK RAMPRASAD and Dakshin Khanda Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000388/2023-2024 | 2778/MURD | 01/09/2023 | 14 | SARKAR WATER SUPPLY AGENCY | 9.21 | 0 | 100
2871 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 2.37 | 90
2872 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Ramprasad village, Block:- Jalangi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000687/2023-2024 | 3628/MEDB | 03/11/2023 | 92 | SREE RADHA ELECTRICAL | 6.32 | 0 | 0
2873 | Murshidabad Division | Berhampur M/E Division | Augmentation of Domkal Zone-II (Part-A) Ground Water Based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000055/2023-2024 | 1311/MURD | 11/05/2023 | 916 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 593.84 | 183.04 | 10
2874 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 4.47 | 100
2875 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of Domkal Zone-I (Part-B) & Domkal Zone - II (Part - A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000828/2022-2023 | 692/MURD | 10/03/2023 | 280 | M/S. J. A. CONSTRUCTION | 107.58 | 9.89 | 10
2876 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000254/2023-2024 | 1219/MURD/39 | 03/05/2023 | 0 | Resource Division | 78.66 | 0 | 0
2877 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT DOMKALI Z-II PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01110/2024-2025 |  | 14/11/2024 | 0 | WBSEDCL | 5.48 | 0 | 0
2878 | Berhampore Mechanical | Berhampur M/E Division | Domkal Zone-2 PH_1 Application No-3004548731 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01229/2023-2024 | 268/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 5.4 | 0 | 0
2879 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,ZONE-II, Part-A under DOMKAL ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000110/2023-2024 | 3718/MEDB | 03/11/2023 | 92 | M/S S. R. ENTERPRISE | 33.53 | 0 | 5
2880 | Murshidabad Division | Islampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER | Junior Engineer | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 0 | 100
2881 | Murshidabad Division | Islampur Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Barabil Raghunathpur Water Supply Scheme of TW-I under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000592/2022-2023 | 3062/MURD | 17/11/2022 | 30 | GENUINE | 11.75 | 8.53 | 100
2882 | Murshidabad Division | Islampur Sub-Division | Augmentation of Ground Water Based Barabil Raghunathpur zone-I PWSS to accommodate FHTC of 105 nos household, Laying Distribution System, Laying Rising Main , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works,Repair of Boundary Wall at T/W-I site & T/W-II site &Overhauling of R.C.C. elevated reservoir 350 Cum capacity of staging hight 20 mtr. for Barabil Raghunathpur ( ZONE-I ) Ground water based Piped water supply scheme at Jalangi Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000600/2023-2024 | 3355/MURD | 30/10/2023 | 150 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 155.66 | 0 | 30
2883 | Murshidabad Division | Islampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer | RTOR000161/2023-2024 | 1180/MURD/31 | 29/04/2023 | 0 | Resource Division | 55.46 | 0 | 0
2884 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for GHORAMARA Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000043/2025-2026 | 1190/MURD | 23/05/2025 | 60 | M/S. GOUTAM CHAKRABORTY | 23.01 | 0 | 0
2885 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen(RDS) filter at GHORAMARA Water Supply Scheme atHead Work Site, 2nd Site site at Nawda Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000116/2023-2024 | 1760/MURD | 06/07/2023 | 21 | SUJIT KUMAR SAHA | 18.45 | 12.97 | 100
2886 | Murshidabad Division | Berhampur Sub-Division | Balance and allied works for providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission) and under command area of village of GHORAMARA (Village Code -315515) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000165/2022-2023 | 154/BSD | 12/04/2022 | 30 | M/S M.S. ENTERPRISE | 4.69 | 4.59 | 1
2887 | Murshidabad Division | Berhampur Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0
2888 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0
2889 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 176 nos household ,Construction of 200 Cum OHR, Rising Main , for Augmentation work of GHORAMARA PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. (part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000882/2022-2023 | 906/MURD | 22/03/2023 | 1320 | PRATICHI ENTERPRISE | 120.97 | 0 | 80
2890 | Murshidabad Division | Berhampur Sub-Division | Laying of Distribution System, Repairing & Vertical Extention of Boundary Wall, Special repair and renovation of existing 1 (One) Nos Pump House and Alied Works for Augmentation work of GHORAMARA PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. (part_B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000884/2022-2023 | 901/MURD | 29/03/2023 | 917 | M/S RUBIET HOSSAIN | 172.57 | 4.85 | 20
2891 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 4.92 | 1
2892 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under GHORAMARA ground water based water supply scheme under Block_ NAWDA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000671/2023-2024 | 4347/MEDB | 29/12/2023 | 91 | BHABANI PRASAD MANNA | 33.55 | 0 | 0
2893 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 19.19 | 11
2894 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Gobindrapur" ground water supply scheme in Berhampore Block, under Berhampore Division-I, P.H.E Dte. (Capacity-34 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000036/2024-2025 | 997/BD-I | 20/06/2024 | 365 | ACQUA CONSTRUCTION CONSORTIUM | 146.58 | 0 | 0
2895 | Berhampore Division I | Berhampur Division I | GOBINDAPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000045/2023-2024 | 142/BD-I | 15/05/2023 | 1047 | DEBASISH SARKAR | 73.41 | 0 | 30
2896 | Berhampore Division I | Berhampur Division I | GOBINDAPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Berhampore Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000101/2023-2024 | 219/BD-I | 17/05/2023 | 716 | AZAD CONSTRUCTION & CO. | 40.55 | 0 | 90
2897 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GOBINDAPUR Water Supply Scheme(TW -II) within Berhampore Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000294/2024-2025 | 100/BD-I | 20/01/2025 | 180 | SUJIT KUMAR SAHA | 9.01 | 0 | 100
2898 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000025/2024-2025 | 2096/BD-I/6 | 25/11/2024 | 0 | Resource Division | 4.65 | 0 | 0
2899 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000031/2023-2024 | 61/BD-1/14 | 27/04/2023 | 0 | Resource Division | 17.81 | 0 | 0
2900 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION GOBINDAPUR PH-1 | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | BILL/01620/2023-2024 | 459/WBSEDCL-JJM | 18/03/2024 | 0 | WBSEDCL | 7.49 | 0 | 0
2901 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 11.95 | 20
2902 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KISMATTATLA and Adjoining Mouzas PWSS (TW-II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-I Block under Berhampore Division-I, P.H.Engineering Dte. (01 Nos TW). | Assistant Engineer-I | JE,Junior engineer-III | ORD/000061/2025-2026 | 773/BD-I | 22/05/2025 | 15 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 9.01 | 0 | 0
2903 | Berhampore Division I | Berhampur Division I | KISMATTATLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000093/2023-2024 | 215/BD-I | 17/05/2023 | 990 | RUDRA NARAYAN GHOSH | 40.74 | 0 | 25
2904 | Berhampore Division I | Berhampur Division I | KISMATTATLA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 150 cum) under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. [ 2ND Call for WBPHED/EE/BD-I/NIeT-30 of 2022 ¿ 2023 (sl no-02)] | Assistant Engineer-I | JE,Junior engineer-III | ORD/000125/2023-2024 | 514/BD-I | 25/07/2023 | 930 | U TURN CONSTRUCTION | 172.1 | 0 | 15
2905 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000024/2023-2024 | 61/BD-1/24 | 27/04/2023 | 0 | Resource Division | 7.05 | 0 | 0
2906 | Berhampore Mechanical | Berhampur Division I | KISMATTALA PWSS | Assistant Engineer-I | JE,Junior engineer-III | BILL/01452/2023-2024 | 345/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
2907 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Kismattatla ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000654/2023-2024 | 3688/MEDB | 03/11/2023 | 92 | EASTERN INDIA SALES & SERVICE | 20.69 | 0 | 0
2908 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Sujapur Zone-III under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000090/2023-2024 | 168/BD-I | 16/05/2023 | 90 | CHAND ENTERPRISE | 24.78 | 0 | 0
2909 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Sujapur Zone-III village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000181/2023-2024 | 3042/MEDB | 02/08/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0
2910 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.31 | 100
2911 | Murshidabad Division | Berhampur M/E Division | Formal work order for the work of ADWAITA NAGAR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jiban Mission of Samserganj Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000820/2022-2023 | 621/MURD | 03/03/2023 | 758 | ARPAN PANDIT | 342.16 | 182.24 | 40
2912 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000281/2023-2024 | 1230/MURD/23 | 04/05/2023 | 0 | Resource Division | 37.63 | 0 | 0
2913 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
2914 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT ADAIYTANAGAR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/00223/2024-2025 | 59/WBSEDCL-JJM | 06/05/2024 | 0 | WBSEDCL | 11.69 | 0 | 0
2915 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under ADWAITA ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000074/2023-2024 | 1898/MEDB | 16/06/2023 | 1021 | MENAKA ENTERPRISE | 33.56 | 0 | 8
2916 | Murshidabad Division | Kandi Sub-Division | Construction of pathway and development of land at Head work Site of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000006/2022-2023 | 08 / KSD | 06/04/2022 | 45 | BIMALENDU BOSE | 4.84 | 4.83 | 1
2917 | Murshidabad Division | Kandi Sub-Division | Supplying fitting and fixing of R.B.T Concertina fencing on wall top and construction of surface drain at Head work site of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000011/2022-2023 | 12 / KSD | 06/04/2022 | 45 | DEBJYOTI MUKHERJEE | 4.73 | 4.71 | 1
2918 | Murshidabad Division | Kandi Sub-Division | Construction of Boundary Wall & Pump House with sanitary & plumbing work (3rd & 4th T/W Site) of Mahalandi (Zone-II) Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000082/2024-2025 | 2075/MURD | 19/07/2024 | 60 | AHAMMED ENTERPRISE | 28.77 | 0 | 0
2919 | Murshidabad Division | Kandi Sub-Division | Providing FHTC Connection to 818 nos. household , Construction of 300 Cum OHR, Laying of Distribution System, Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 200 Cum capacity of staging height 20 mtr. Repairing & Vertical Extention of Boundary Wall, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works , Construction of Pump House with sanitary and Water Supply Arrangement & Boundary Wall, for Augmentation work of MAHALANDI ZONE-II Kandi Block under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000247/2023-2024 | 2468/MURD | 09/08/2023 | 876 | M/S. BIMALENDU BOSE | 451.48 | 62.97 | 10
2920 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone-II Water Supply Scheme at HW Site under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000597/2022-2023 | 3071/MURD | 17/11/2022 | 30 | A.M. ENTERPRISE | 10.6 | 9.95 | 100
2921 | Murshidabad Division | Kandi Sub-Division | Construction of boundary wall at Front side of Head work site including gate of Mahalandi (Zone-II) water supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001194/2021-2022 | 336/KSD | 30/11/2021 | 45 | A.P. CONSTRUCTION | 4.92 | 4.91 | 1
2922 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000002/2023-2024 | 1043/MURD/6 | 17/04/2023 | 0 | Resource Division | 150.69 | 0 | 0
2923 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-II of Mahalandi ground water based water supply scheme under Block- Kandi Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000284/2023-2024 | 3227/MEDB | 17/08/2023 | 92 | SURAKSHA | 11.92 | 10.54 | 60
2924 | Berhampore Division I | Berhampur Division I | Construction Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of BHAGWANGOLA PWSS under Jal Jeevan Mission within Bhagwangola-I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000006/2025-2026 | 593/BD-I | 22/04/2025 | 180 | AMAN CONSTRUCTION | 15.2 | 0 | 82
2925 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BHAGWANGOLA PWSS(TW-I&II) under Jal Jeevan Mission in Bhagwangola-I Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000018/2025-2026 | 617/BD-I | 23/04/2025 | 30 | JOY HIND TUBEWELLS | 17.99 | 0 | 0
2926 | Berhampore Division I | Berhampur Division I | BHAGWANGOLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000091/2023-2024 | 213/BD-I | 17/05/2023 | 90 | ARJIMA CONSTRUCTION | 39.48 | 0 | 0
2927 | Berhampore Division I | Berhampur Division I | BHAGWANGOLA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000115/2023-2024 | 377/BD-I | 28/06/2023 | 280 | S.D PROJECT | 160.98 | 0 | 0
2928 | Berhampore Division I | Berhampur Division I | BHAGWANGOLA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 450 cum) under Jal Jivan Mission of BHAGWANGOLA -I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000269/2023-2024 | 974/BD-I | 18/10/2023 | 280 | GIRIDHARI SAHA | 359.56 | 0 | 0
2929 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000046/2023-2024 | 61/BD-1/27 | 27/04/2023 | 0 | Resource Division | 13.43 | 0 | 0
2930 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHAGWANGOLA , BLOCK - BHAGWANGOLA -I , DISTRICT - MURSHIDABAD. under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000029/2025-2026 | 1181/MEDB | 16/05/2025 | 92 | M/S K.P. PRAMANIK | 23.66 | 0 | 0
2931 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Romnapara (Village code 314496) under Romnapara Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-09 of 2020 ¿ 2021,SL-11). | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000242/2020-2021 | 75/BD-I | 19/01/2021 | 20 | MAA CONSTRUCTION | 12.9 | 16.68 | 0
2932 | Berhampore Division I | Berhampur Division I | Additional Laying works at villages to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Ramnapara Ground water supply scheme (Bhagwangola-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000782/2021-2022 | 2297/BD-I | 28/12/2021 | 15 | MS BAPPA ENTERPRISE | 6.01 | 5 | 0
2933 | Murshidabad Division | Jangipur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ANDHUA ZONE -III Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000749/2023-2024 | 114/MURD | 11/01/2024 | 21 | HARUN ALL RASHID & BROTHERS | 23.53 | 0 | 50
2934 | Murshidabad Division | Jangipur Sub-Division | Laying of Rising main , Distribution System, 2183 nos FHTC, construction of OHR (Capacity 350 cum), Repairing of OHR , Sinking of Tube Well , Repairing of pump house, Repairing of Boundary Wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Andhua Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000755/2023-2024 | 138/MURD | 16/01/2024 | 365 | NAYLA CONSTRUCTION | 836.98 | 0 | 35
2935 | Murshidabad Division | Jangipur Sub-Division | Continuation work order for preparation of D.P.R. for Augmentation of Andhua Zone- II & Zone - III PWSS in Farakka Block in Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000879/2023-2024 | 3720/MURD | 05/12/2023 | 30 | M/S SOBHA & CO. | 4.51 | 0 | 100
2936 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000170/2023-2024 | 1180/MURD/19 | 29/04/2023 | 0 | Resource Division | 65.79 | 0 | 0
2937 | Berhampore Mechanical | Jangipur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II , Zone-III under ANDHUA ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000221/2023-2024 | 589/MEDB | 31/01/2024 | 90 | ARINDAM MAJUMDAR | 22.97 | 0 | 0
2938 | Murshidabad Division | Berhampur M/E Division | CHACHANDA PWSS to accommodate FHTC under Jal Jeevan Mission of SAMSERGANJ Block, Sub Division - Jangipur of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000451/2023-2024 | 2983/MURD | 21/09/2023 | 558 | M/S NIRAPADA BHATTACHARJEE | 567.03 | 0 | 15
2939 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 7.09 | 100
2940 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under CHACHANDA ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000679/2023-2024 | 4301/MEDB | 29/12/2023 | 91 | ORIENTAL ENGINEERING CO. | 44.71 | 0 | 0
2941 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 2.39 | 90
2942 | Murshidabad Division | Jangipur Sub-Division | Laying Distribution system, Rising Main Connection, FHTC(834 Nos) Construction of Boundary Wall , Pump House,Sinking of 300 x 200 mm dia Rig Bore Tubewell of Sikarpur PWSS in Farakka Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000744/2023-2024 | 60/MURD | 08/01/2024 | 724 | S.S. ENTERPRISE | 98.78 | 0 | 30
2943 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR and Adjoining Mouzas PWSS (TW- I, II, III & IV Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (04 Nos TW) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000062/2025-2026 | 774/BD-I | 22/05/2025 | 45 | SARKAR WATER SUPPLY AGENCY | 36.02 | 0 | 0
2944 | Berhampore Division I | Berhampur M/E Division | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000182/2023-2024 | 698/BD-I | 11/08/2023 | 180 | JAHANGIR ALAM | 263.59 | 0 | 0
2945 | Berhampore Division I | Berhampur M/E Division | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000183/2023-2024 | 701/BD-I | 11/08/2023 | 900 | RAJ KUMAR MONDAL | 193.43 | 0 | 5
2946 | Berhampore Division I | Berhampur M/E Division | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 750 cum) under Jal Jeevan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000202/2023-2024 | 846/BD-I | 05/09/2023 | 310 | JAHANGIR ALAM | 466.95 | 0 | 0
2947 | Berhampore Division I | Berhampur M/E Division | NASIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000340/2023-2024 | 1254/BD-I | 22/12/2023 | 90 | MASOOM TRADERS | 56.23 | 0 | 25
2948 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000101/2023-2024 | 201/BD-1/5 | 10/02/2024 | 0 | Resource Division | 86.32 | 0 | 0
2949 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION NASIPUR PH-1 | ASSISTANT ENGINEER-I | Junior engineer-III | BILL/01575/2023-2024 | 410/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 21.19 | 0 | 0
2950 | Murshidabad Division | Kandi Sub-Division | Indrani (Part-B) & adjoining moujas PWSS to accommodate Of T/W,LDS, Pump House Cum Chlorine Room,boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000171/2023-2024 | 1987/MURD | 21/07/2023 | 864 | J.S. CONSTRUCTION | 433.05 | 290.83 | 15
2951 | Murshidabad Division | Kandi Sub-Division | INDRANI (Part-A) & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Rising Main, FHTC work, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000172/2023-2024 | 1988/MURD | 21/07/2023 | 865 | DHIRENDRANATH MONDAL | 569.67 | 22.32 | 10
2952 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Faridpur and Indrani Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000670/2022-2023 | 3411/MURD | 22/12/2022 | 984 | R.K. DRILLING SERVICES | 8.4 | 0 | 100
2953 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
2954 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000053/2023-2024 | 1067/MURD/9 | 18/04/2023 | 0 | Resource Division | 69.6 | 0 | 0
2955 | Central Drilling | Kandi Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000209/2023-2024 | 2203/CDD | 01/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 10
2956 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE INDRANI PH1 ID304222223 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01148/2023-2024 | 227/WBSEDCL-JJM | 09/01/2024 | 0 | WBSEDCL | 4.41 | 0 | 0
2957 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT INDRANI PH III, ID304233664 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01213/2023-2024 | 291/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
2958 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT INDRANI PH II, ID304233643 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01217/2023-2024 | 292/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 14.12 | 0 | 0
2959 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I , II under INDRANI ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000710/2023-2024 | 4063/MEDB | 04/12/2023 | 91 | HARA PROSAD DAS | 23.47 | 0 | 0
2960 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III, IV under INDRANI ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000714/2023-2024 | 4068/MEDB | 04/12/2023 | 91 | DAS ENTERPRISE ( MANGO LANE) | 23.44 | 0 | 0
2961 | Berhampore Division I | Berhampur M/E Division | Augmentation of Ramnachandpur Zone-II Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Swapna in Nawda Block of Murshidabad District under Berhampore Division-I, PHE. Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000130/2023-2024 | 608/BD-I | 02/08/2023 | 1117 | KAMIRUL SK AND CO. | 583.11 | 0 | 80
2962 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000190/2023-2024 | 538/BD-I | 27/07/2023 | 10 | TECHVISION | 2.87 | 2.87 | 100
2963 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000105/2023-2024 | 201/BD-1/6 | 10/02/2024 | 0 | Resource Division | 48.66 | 0 | 0
2964 | Berhampore Mechanical | Berhampur M/E Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , Zone-II under RAMNACHANDPUR ground water based water supply scheme under Block_ NAWDA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/001429/2023-2024 | 4319/MEDB | 29/12/2023 | 91 | JAL PRAVAHIKA PVT LTD | 35.21 | 0 | 0
2965 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000349/2022-2023 | 1928/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 8.78 | 2.23 | 100
2966 | Murshidabad Division | Lalbag Sub-Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 200 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Kantanagar PWSS in Bhagwangola-I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000586/2023-2024 | 3321/MURD | 22/10/2023 | 557 | M/S GUHA AND ROY | 625.7 | 0 | 40
2967 | Murshidabad Division | Lalbag Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 2.17 | 80
2968 | Murshidabad Division | Lalbag Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | RTOR000124/2023-2024 | 1167/MURD/24 | 28/04/2023 | 0 | Resource Division | 17.33 | 0 | 0
2969 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Brindabanpur Chak (Village code 314703) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723328 in the District of Murshidabad. |  |  | ORD/000774/2020-2021 | 83./MURD | 08/01/2021 | 60 | ULTRA CONSTRUCTION. | 43.61 | 0 | 0
2970 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Construction of 300 Cum capacity 20.00 mtr staging hight RCC elevated Over Head Reservoir on pile foundation (Ref:- DRG. NO. PC-I/OHR/7/2012 & D D-II/OHR/957/III/JAN 2020) including delivery, inlet and overflow pipe connection etc all complete of BAHARA Water Supply Scheme of Kandi Sub-Division under Murshidabad Division , P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000635/2020-2021 | 3053/MURD | 08/12/2020 | 270 | ROY ENTERPRISE | 78.02 | 16.68 | 100
2971 | Murshidabad Division | Kandi Sub-Division | Development of land at Head Work Site of Bahara Water Supply Scheme under Kandi Sub-Division, P.H.Engg. Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001597/2021-2022 | 375/KSD | 19/01/2022 | 30 | ROY ENTERPRISE | 4.53 | 4.52 | 100
2972 | Murshidabad Division | Kandi Sub-Division | Construction of boundary wall at Front side of Head work site including gate & R.B.T concertina fencing on wall top of Bahara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001600/2021-2022 | 378/KSD | 19/01/2022 | 45 | ROY ENTERPRISE | 4.29 | 4.28 | 100
2973 | Murshidabad Division | Kandi Sub-Division | Continuatioin order for hiring of one no car use of the Executive Engineer Murshidabad Div PHE DTE. Vechle no 57-D - 9090. W/O - 223-HQ dated 26.05.2022 | ASSISTANT ENGINEER |  | VCH/000740/2022-2023 | 262-MSD/22-23 | 18/08/2022 | 0 | DULAL CHOWDHURY | 0.79 | 0 | 0
2974 | Murshidabad Division | Kandi Sub-Division | Work Order for hiring of one no car use of the Superintending Engineer Murshidabad Circle PHE DTE. NIB 02/MC/PHE/20-21. W/O - 289-MC dated 01.04.2021 | ASSISTANT ENGINEER |  | VCH/000741/2022-2023 | 263-MSD/22-23 | 18/08/2022 | 0 | SOUMYADIP MISRA | 1.17 | 0 | 0
2975 | Murshidabad Division | Kandi Sub-Division | Hiring of one no car use of the JSD PHE DTE. Note sheet approved date 07/01/2022. | ASSISTANT ENGINEER |  | VCH/000743/2022-2023 | 264-MSD/22-23 | 18/08/2022 | 0 | MADAN MOHAN SASMAL | 0.59 | 0 | 0
2976 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Durgapur ( Village Code -313864) under Hasimpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001723174). |  |  | ORD/000574/2020-2021 | 633/MURD | 18/02/2021 | 60 | HOQUEDAR ALI | 43.59 | 10.17 | 0
2977 | Murshidabad Division |  | Retrofitting providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of DURGAPUR (Village Code -313864) under HASIMPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block in the Dist of MSD under Murshidabad Division P.H.E Dte. Scheme ID 0001723174 |  |  | VCH/000369/2021-2022 |  | 25/08/2021 | 0 | HOQUEDAR ALI | 33.41 | 0 | 0
2978 | Murshidabad Division |  | Retrofitting providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of DURGAPUR (Village Code -313864) under HASIMPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block in the Dist of MSD under Murshidabad Division P.H.E Dte. Scheme ID 0001723174 Tender No 858/20-21/EE |  |  | VCH/000663/2021-2022 | 49- MSD / 21-22 | 13/09/2021 | 0 | HOQUEDAR ALI | 33.41 | 0 | 0
2979 | Murshidabad Division | Kandi Sub-Division | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00"x 4"00") which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Radharghat I & II G.P. Ramnagar Bachhara G.P, Sompara-I & II G.P, Doulatabad G.P, Mirzapur-I & II G.P, Kumarpur Sujapur G.P, Debkunda G.P, Madda G.P, Sahajadpur G.P & Niyallishpara G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000234/2021-2022 | 233/BSD | 14/07/2021 | 30 | S.S.INFRASTRUCTURE | 3.77 | 2.85 | 0
2980 | Murshidabad Division | Kandi Sub-Division | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00 x 4'00") which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Nowda G.P, Raypur G.P, Madhupur G.P, Sarbangapur G.P, Choa G.P, Hariharpara G.P, Mahula G.P, Rampur-I & II G.P Rangamati Chandpara G.P. Satui Chowrigachha G.P, Shaktipur G.P. & Chhaighari G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000235/2021-2022 | 142/BSD | 21/06/2021 | 30 | IMAGIN | 3.77 | 7.54 | 0
2981 | Murshidabad Division | Kandi Sub-Division | Balance Retrofitting Work of Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under at Janardanpur & adjoining mouzas (JL NO-147) ( Village Code -315981) from the exiting distribution system of Panchthupi Water Supply Scheme (Ground Water Based) in Burwan Block under Kandi Sub Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000409/2020-2021 | 534/MURD | 04/02/2021 | 60 | J.S. CONSTRUCTION | 44.75 | 88.73 | 1
2982 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village SHIBARAMBATI (Village Code 315980) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000744/2020-2021 | 3034/MURD | 07/12/2020 | 45 | SOUMYA KANTI SINHA | 18.57 | 0 | 1
2983 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-III ) TNO- 764/20-21/EE | ASSISTANT ENGINEER |  | VCH/000009/2021-2022 |  | 12/04/2021 | 0 | SOUMYA KANTI SINHA | 17.54 | 0 | 0
2984 | Murshidabad Division | Kandi Sub-Division | Safe Drinking Water Supply (Modified ATU) arrangement for Char Sarandajpur Primary School under ISD under Murshidabad Div PHE DTE. Tender no - 74 of 21-22 by AE / ISD | ASSISTANT ENGINEER |  | VCH/000697/2021-2022 | 92-MSD/2021-22 | 20/09/2021 | 0 | SARTHAK SK. | 4.76 | 0 | 0
2985 | Murshidabad Division | Kandi Sub-Division | Fault defection of Repairing or replacing the damaged material Pannel board submerssible pump existing chlorinetaror of other direc existing chlonator and other direc Mahadebnagar Z-II W/S Scheme under JSD PHE DTE. TNO- 41 of 21-22 by AE/JSD | ASSISTANT ENGINEER |  | VCH/000698/2021-2022 | 104-MSD/2021-22 | 20/09/2021 | 0 | ARYA CONSTRUCTION | 3.81 | 0 | 0
2986 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 1005 nos household under command area of village of Sekhalipara ( Village Code -314580) under Katakobra Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0005185646) |  |  | ORD/000136/2022-2023 | 1238/MURD | 11/05/2022 | 60 | BRISTI CONSTRUCTION | 52.34 | 50.08 | 1
2987 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of BAGHARPUR RAMNA (Village Code -314665) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. . Tender no - 66 of 20-21 by SE MC. |  |  | VCH/000721/2022-2023 | 254-MSD/22-23 | 12/08/2022 | 0 | M/S NIRAPADA BHATTACHARJEE | 10.04 | 0 | 0
2988 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Sarpakia (Code-314194) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000130/2024-2025 | 1529/BD-I | 19/09/2024 | 30 | M/S. THE LOTUS ENTERPRISE | 5.12 | 0 | 0
2989 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarpakhia (Village code 314194) under Rajarampur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | Assistant Engineer-I | JE | ORD/000275/2021-2022 | 1168/BD-I | 15/07/2021 | 30 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 21.65 | 19.52 | 1
2990 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Sarpakhia( Village code-314194) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Rajarampur Ground water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE | ORD/000873/2021-2022 | 243/BD-I | 03/03/2022 | 10 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 4.9 | 3.81 | 1
2991 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Makimnagar ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000065/2024-2025 | 1198/BD-I | 26/07/2024 | 60 | BURIMAA CONSTRUCTION | 12.74 | 0 | 0
2992 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mokimnagar (Village code 314172) under Mokimnagar Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000203/2020-2021 | 969/BD-I | 17/12/2020 | 90 | MS RUBIET HOSSAIN | 40.85 | 23.23 | 1
2993 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Simulia (Village code 314155) under Mokimnagar Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000204/2020-2021 | 970/BD-I | 17/12/2020 | 60 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 6.79 | 5.24 | 1
2994 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mridapur(Village code 314157) under Mokimnagar Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000205/2020-2021 | 971/BD-I | 17/12/2020 | 90 | MS RUBIET HOSSAIN | 33.94 | 28.8 | 1
2995 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kasbagoas (Village code 314795) under Kasbagoas Ground Water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000264/2020-2021 | 338/BD-I | 24/02/2021 | 120 | DOBAY CONSTRUCTION | 81.22 | 95.58 | 0
2996 | Berhampore Division I | Raghunathganj Sub-Division | Additional Laying works at village Kasbagoas (Village code-314795) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Kasbagoas Ground water based Water supply scheme (Raninagar-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer | Junior Engineer-II | ORD/000796/2021-2022 | 2312/BD-I | 29/12/2021 | 45 | BENOY DOBEY | 14.34 | 0 | 0
2997 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) (Shaikh para & Babultali ) & adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | ORD/000333/2021-2022 | 2386/MURD | 09/08/2021 | 60 | MITRA CONSTRUCTION | 98.09 | 0 | 1
2998 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (1676 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Godhanpara ( Village Code -314581) under Godhanpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000622/2023-2024 | 3398/MURD | 01/11/2023 | 60 | PRANAB KUMAR GHOSH | 58.81 | 0 | 50
2999 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (1676 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) under Godhanpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000627/2023-2024 | 3423/MURD | 02/11/2023 | 60 | SUMAN CHOWDHURY | 55.3 | 0 | 40
3000 | Murshidabad Division |  | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. |  |  | ORD/000738/2021-2022 | 2744/MURD | 03/09/2021 | 60 | RADIANT | 11.27 | 0 | 0
3001 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of villages of NAOAPUKURIA (village code 315617), under NAOAPUKURIA (Zone-K) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000039/2023-2024 | 104/BD-I | 04/05/2023 | 120 | RAJ KUMAR MONDAL | 179.66 | 0 | 0
3002 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at The Village Of Kasba Bahadurpur (Code-314488) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000099/2024-2025 | 1441/BD-I | 04/09/2024 | 362 | A.P CONSTRUCTION | 27.91 | 0 | 70
3003 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kasba Bahadurpur (Village code 314488) , under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000101/2020-2021 | 167/BD-I | 03/02/2021 | 728 | M/S SINHA & SONS | 95.89 | 116.96 | 1
3004 | Berhampore Division I | Berhampur Division I | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under KASBA BAHADURPUR ground Water based Water Supply Scheme of Bhagawangola-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000273/2023-2024 | 977/BD-I | 18/10/2023 | 90 | NAMDAR ALI | 15.83 | 0 | 0
3005 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
3006 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
3007 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) 1305 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Ballalpur ( Village Code -313811) under Ballalpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000021/2022-2023 | 1052/MURD | 25/04/2022 | 45 | TARIKUL SK | 60.99 | 54.93 | 10
3008 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | RTOR000033/2021-2022 | 540/6/MURD | 25/02/2022 | 0 | Resource Division | 7.16 | 0 | 0
3009 | Murshidabad Division | Kandi Sub-Division | Planning, design, investigation, construction, erection, installation, completion, testing and commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & iron present in ground water in diff. connection to acceptable limit as recommended by CPHEEO manual on basis of departmental process drawing (Modified Sujapur Sadipur Model) incld. 3 months Trail Run & 9 months O&M of diff. blocks in the district of Murshidabad, PHE Dte., (JAGAIPUR W/S SCHEME) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/002037/2020-2021 | 478/W | 12/03/2021 | 0 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 27.52 | 0 | 0
3010 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/002041/2020-2021 | 489/W | 17/03/2021 | 0 | SAMBHUNATH ROY | 29.21 | 0 | 0
3011 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SHIBPUR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000407/2021-2022 | 249/LSD | 18/08/2021 | 30 | IMAGIN COMMUNICATION | 4.18 | 0 | 0
3012 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (JalJeevan Mission ) "from existing Distribution system within the Command area of village AMARKUNDU (Village Code 315017) under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block in the District of Murshidabad . |  |  | ORD/000627/2020-2021 | 2570/MURD | 01/10/2020 | 45 | MAJUMDER CONSTRUCTION | 38.26 | 34.35 | 1
3013 | Murshidabad Division |  | Additional extension of UPVC pipeline at Sankuria and Madhunia (Adibashipara) under the Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division, P.H.E. Dte.in the District Murshidabad. |  |  | ORD/000918/2021-2022 | 361/LSD | 17/11/2021 | 45 | SARAJIT KUMAR MAJUMDER | 4.43 | 4.42 | 0
3014 | Murshidabad Division |  | Laying of different dia U.P.V.C Pipeline for Distribution Network (Remaining Portion) and construction of RCC Stand Post including platform at Sankuria Village under Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. |  |  | ORD/001225/2021-2022 | 413/LSD | 27/12/2021 | 30 | SARAJIT KUMAR MAJUMDER | 4.88 | 4.85 | 0
3015 | Murshidabad Division |  | Providing Balance Functional Household Tap Connection (FHTC) of 200 left out in connection with Jal Jeevan Mission and Jal Swapna under command area of village Amarkundu (Village code 315017) and under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/001806/2021-2022 | 803/MURD | 24/03/2022 | 20 | S.K. CONSTRUCTION (TABLU) | 11.79 | 0 | 0
3016 | Murshidabad Division |  | Operation & Maintenance of distribution system and allied works of Siddhikhali (Zone-III)Surface W/S Scheme Raghunathganj-I Block from 01.05.2019 to 29.02.2020 |  |  | VCH/000933/2020-2021 | 489/W | 17/03/2021 | 0 | SUDIPA SINGHA ROY | 4.99 | 0 | 0
3017 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE |  |  | VCH/002041/2020-2021 | 489/W | 17/03/2021 | 0 | SAMBHUNATH ROY | 29.21 | 0 | 0
3018 | Murshidabad Division |  | CONT WORK OF OPERATION & GUARDING OF PUMPING MACHINERY FOR MAHESAIL W/S SCHEME PH-I , TNO- 894/19-20/EE |  |  | VCH/002042/2020-2021 | 489/W | 17/03/2021 | 0 | RELIABLE ENTERPRISE | 1.41 | 0 | 0
3019 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -JITPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - PAR RAGHUNATHPUR, CODE- 314677 , TNO- 80/20-21/SEMC |  |  | VCH/002052/2020-2021 | 504/W | 22/03/2021 | 0 | UMWELT ENGINEER PVT LTD | 36.66 | 0 | 0
3020 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Basantapur(Village code 314446),Lalitakuri(Village code 314449) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE | ORD/000107/2020-2021 | 173/BD-I | 03/02/2021 | 30 | DECON INDIA | 76.45 | 32.65 | 1
3021 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Basantapur Village (Code-314446),Lalitakuri (Code-314449) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-C)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000132/2024-2025 | 1530/BD-I | 19/09/2024 | 60 | HAFIZUL SEIKH | 17.26 | 0 | 0
3022 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION for Village of Chengta (VillageCode-314463), Gobra (Village code- 314470)& Ramnagobra (Village Code-314461) under command area of Gobra ground water supply scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000160/2024-2025 | 1663/BD-I | 25/10/2024 | 30 | LAKSHMI IRON | 16.77 | 0 | 0
3023 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chengta (Village code 314463) under Gobra Ground Water based Water Supply Scheme for Bhagawangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000185/2020-2021 | 919/BD-I | 10/12/2020 | 60 | PRATICHI ENTERPRISE | 10.11 | 15.22 | 100
3024 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagobra (Village code 314461) under Gobra Ground Water based Water Supply Scheme for Bhagawangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000187/2020-2021 | 920/BD-I | 10/12/2020 | 60 | SHIBAM ENTERPRISE THAKURPARA VILL BHAKURI CHALTIA | 11.5 | 18.33 | 0
3025 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gobra (Village code 314470) under Gobra Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000236/2020-2021 | 65/BD-I | 18/01/2021 | 30 | DECON INDIA | 44.55 | 43.75 | 100
3026 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kulberia (Village code 315685) under Andulberia Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-II | Junior Engineer-II | ORD/000113/2020-2021 | 185/BD-I | 04/02/2021 | 20 | HANNAN BUILDERS PVT. LTD. | 43.67 | 31.27 | 0
3027 | Murshidabad Division |  | Additional works for Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Baniakhali( Village Code -314660) under Baniakhali Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723470) |  |  | ORD/000345/2021-2022 | 2181/MURD | 28/07/2021 | 60 | M/S NIRAPADA BHATTACHARJEE | 12.08 | 0 | 0
3028 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission ) "from existing Distribution system within the Command area of village BANIAKHALI (Village Code 314660) under Baniakhali Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad . |  |  | ORD/000594/2020-2021 | 2578/MURD | 01/10/2020 | 45 | M/S NIRAPADA BHATTACHARJEE | 35.6 | 11.13 | 1
3029 | Murshidabad Division |  | ADITIONAL WORK OF FHTC OF BANIAKHALI (314660) WSS, TNO- 641/21-22/EE, WO- 2181/MURD |  |  | VCH/000333/2022-2023 | 130-MSD/22-23 | 11/05/2022 | 0 | M/S NIRAPADA BHATTACHARJEE | 5.91 | 0 | 0
3030 | Murshidabad Division |  | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC |  |  | VCH/002047/2020-2021 | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0
3031 | Murshidabad Division |  | Providing Functional Household Tap Connections ( 665 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Manik Nagar (Village Code -314694) under Domkol Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000637/2023-2024 | 3458/MURD | 06/11/2023 | 30 | MOLLA ENTERPRISE (REHENA BIBI) | 18.71 | 0 | 0
3032 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --AMARKUNDU-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- RAINDA , CODE- 315025, TNO- 684/2020-21/EE |  |  | VCH/002019/2020-2021 | 512/W | 30/03/2021 | 0 | SAMAR MUKHERJEE | 21.62 | 0 | 0
3033 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -JURANPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- PIROJPUR , CODE-314723, TNO- 667/2020-21/EE |  |  | VCH/002021/2020-2021 | 512/W | 30/03/2021 | 0 | GOUTAM CHAKRABORTY | 10.4 | 0 | 0
3034 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BARABIL RAGHUNAR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 87 /2020-21/SE-MC |  |  | VCH/002023/2020-2021 | 512/W | 30/03/2021 | 0 | MITRA CONSTRUCTION | 55.47 | 0 | 0
3035 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ramna Etbarnagar Basantapur (Village code 314691) under Domkal Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. |  |  | ORD/000948/2021-2022 | 3615/MURD | 22/11/2021 | 100 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 53.5 | 0 | 0
3036 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village RAMNA ETBARNAGAR (Village Code 314691) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 106 of 21-22 by EE MURD |  |  | VCH/001503/2021-2022 | 410-MSD/21-22 | 22/03/2022 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 22.28 | 0 | 0
3037 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --BHALKUNDI Z-II-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE-BHALKUNDI , CODE- 315091, TNO- 43/2020-21/SEMC |  |  | VCH/002024/2020-2021 | 512/W | 30/03/2021 | 0 | M/S BHUBAN DAS | 28.84 | 0 | 0
3038 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BHANDARA--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- KOLAN RADHAKANTAPUR , CODE-314523, TNO- 50/2020-21/SE-MC |  |  | VCH/002025/2020-2021 | 512/W | 30/03/2021 | 0 | M/S GUNGUN CONSTRUCTION | 33.58 | 0 | 0
3039 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kochgiria(Village code 314481) under Bhandara Ground Based Water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl No-03) |  |  | ORD/000427/2020-2021 | 3130/MURD | 10/12/2020 | 180 | M/S OBAIDUR RAHAMAN | 54.51 | 21.97 | 70
3040 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village CHHAKA NAGAR (Village code 314478) under BHANDARA Ground water based Water Supply Scheme for Arsenic Affected Area of Bhagwangola - I & II Block, under Murshidabad Division, PHE Dte. Tender no 492 of 20-21 by EE MSD |  |  | VCH/000271/2021-2022 |  | 18/08/2021 | 0 | PRANAB KUMAR GHOSH | 21.76 | 0 | 0
3041 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village CHHAKA NAGAR (Village code 314478) under BHANDARA Ground water based Water Supply Scheme for Arsenic Affected Area of Bhagwangola - I & II Block, under Murshidabad Division, PHE Dte. Tender no 492 of 20-21 by EE MSD |  |  | VCH/000664/2021-2022 | 50- MSD / 21-22 | 14/09/2021 | 0 | PRANAB KUMAR GHOSH | 21.76 | 0 | 0
3042 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
3043 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
3044 | Murshidabad Division | Kandi Sub-Division | Laying of parallel UPVC pipeline from Masadda Shib Mandir to Masadda Durga Mandir for FHTC work of Raniara Masadda village (Village Code- 315905) of Burwan Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000007/2022-2023 | 09 / KSD | 06/04/2022 | 30 | S.K. ENTERPRISE (PROP:SHAMIM ISLAM) | 4.82 | 4.56 | 1
3045 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with JAL SWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village RANIARA MASADDA (Village Code 315905) under Burwan Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000156/2020-2021 | 3219/MURD | 18/12/2020 | 60 | DEBASISH SARKAR | 12.49 | 2.49 | 0
3046 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Rameswarpur habitation under Rameswarpur Village Code-315954(JL NO-120) Burwan Water Supply Scheme (Ground Water Based) under Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000260/2020-2021 | 2391/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.77 | 0.53 | 1
3047 | Murshidabad Division | Kandi Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000416/2021-2022 | 216/KSD | 11/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.34 | 0 | 0
3048 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BURWAN-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000462/2021-2022 | 231/KSD | 27/08/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 4.17 | 0 | 0
3049 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BURWAN-II G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000463/2021-2022 | 232/KSD | 27/08/2021 | 60 | IMAGIN COMMUNICATION | 4.17 | 0 | 0
3050 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SAHORA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000475/2021-2022 | 243/KSD | 27/08/2021 | 60 | IMAGIN | 4.17 | 0 | 0
3051 | Murshidabad Division | Kandi Sub-Division | Holding Awarness Programme / Campaigning programms at Burwan-I & II G.P, Sahora G.P, Panchthupi G.P and Sabalpur G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (Total nos of Programme = 20 nos) (Part-C). | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000555/2021-2022 | 251/KSD | 31/08/2021 | 30 | IMAGIN COMMUNICATION | 3.99 | 0 | 0
3052 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village DHANGHARA (Village Code 315950) under Burwan Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000626/2020-2021 | 3220/MURD | 18/12/2020 | 60 | DAS CONSTRACTION | 12.03 | 0 | 1
3053 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Rameswarpur habitation under Rameswarpur Village Code-315954(JL NO-120) Burwan Water Supply Scheme (Ground Water Based) under Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000629/2020-2021 | 2391/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.77 | 8.47 | 1
3054 | Murshidabad Division | Kandi Sub-Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniara Masadda (VILL CODE-315905) of Burwan under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block of Murshidabad Distric (PART-I) tNO- 791/20-21/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000266/2021-2022 | 41-MSD / 21-22 | 24/08/2021 | 0 | DEBASISH SARKAR | 9.94 | 0 | 0
3055 | Murshidabad Division | Kandi Sub-Division | Laying of parallel UPVC pipeline from Masadda Bus Stand to Masadda Shib Mandir for FHTC work of Raniara Masadda village (Village Code- 315905) of Burwan Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000536/2022-2023 | 194-MSD/22-23 | 30/06/2022 | 0 | MAA CONSTRUCTION (NAJMUL HAQUE) | 4.58 | 0 | 0
3056 | Murshidabad Division | Kandi Sub-Division | Hiring of 1 (One) no Diesel Scorpio car for fJangipur Sub Div. under MSD PHE DTE. Period 01.04.2022 to 10.06.2022 | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000554/2022-2023 | 200-MSD/2022-23 | 06/07/2022 | 0 | MADAN MOHAN SASMAL | 0.41 | 0 | 0
3057 | Murshidabad Division | Kandi Sub-Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhanghara (315950) of Burwan under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block of Murshidabad Distric (PART-I) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/001297/2021-2022 |  | 17/02/2022 | 0 | DAS CONSTRACTION | 5.48 | 0 | 0
3058 | Murshidabad Division | Kandi Sub-Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhanghara (315950) of Burwan under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block of Murshidabad Distric. Tender no - 850 of 20-21 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/001454/2021-2022 | 343-MSD/21-22 | 05/03/2022 | 0 | DAS CONSTRACTION (MUNNA DAS) | 5.48 | 0 | 0
3059 | Murshidabad Division | Kandi Sub-Division | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00'' x 4'00'') which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Balia G.P, Joypur G.P, Alugram G.P, bharatpur G.P, Sijgram G.P, Salar G.P, Simulia G.P, Kagram G.P, Talibpur G.P & Tenya Baidyapur G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000079/2021-2022 | 177/KSD | 28/05/2021 | 30 | IMAGIN COMMUNICATION | 2.9 | 2.9 | 0
3060 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) ( 1276 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Hamidhati Pilkhandi & Purba Gram ( Village Code - 315713 & 315718) under Salar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000638/2023-2024 | 3459/MURD | 06/11/2023 | 877 | SUKUMAR ROY | 40.68 | 0 | 0
3061 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ganespur (Village Code-314215) under Bajipur Madhupur Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000111/2021-2022 | 913/BD-I | 19/05/2021 | 7 | SHIBAM ENTERPRISE | 4.81 | 4.24 | 1
3062 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jot Bhikan (Village code 314211) under Bajipur Madhupur Ground Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000228/2020-2021 | 992/BD-I | 17/12/2020 | 90 | SANJAY BISWAS | 26.93 | 10.91 | 1
3063 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ganespur (Village code 314215) under Bajipur Madhupur Ground Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000229/2020-2021 | 993/BD-I | 17/12/2020 | 90 | M/S. NIRAPADA BHATTACHARJEE | 29.45 | 37.64 | 1
3064 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village Bewa (P)(Village code 313794), of Bewa Zone-II Ground Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723418) |  |  | ORD/000223/2022-2023 | 1458/MURD | 02/06/2022 | 120 | KISMAT ARA BEGUM | 104.36 | 63.06 | 0
3065 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Molladanga (Village code 314558) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000121/2020-2021 | 193/BD-I | 04/02/2021 | 30 | NIRMAL UDYOG | 50.18 | 65.92 | 1
3066 | Murshidabad Division |  | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Katlamari PWSS Scheme, Block - Raninagar-II) to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. |  |  | ORD/000739/2021-2022 | 2745/MURD | 03/09/2021 | 60 | RADIANT | 11.14 | 0 | 1
3067 | Murshidabad Division |  | Laying of HDPE (Materials grade PE-100 & Pressure Rating: PN6) pipe line & allied works of Retrofitting of Functional Household Tap Connections (FHTC) at village Bhalkundi (Village code-315091) Bhalkundi water supply scheme for FHTC work under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000025/2022-2023 | 29/KSD | 08/04/2022 | 30 | TIRUPATI CONSTRUCTION | 4.59 | 4.11 | 1
3068 | Murshidabad Division |  | Laying of HDPE (Materials grade PE -100 & Pressure Rating : PN 6) Pipe Line due to widening of PWD Roads & construction of drain at village Bhalkundi (Village Code-315091) under Bhalkundi Water Supply Scheme of Kandi Sub Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/000227/2022-2023 | 98 / KSD | 06/06/2022 | 30 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 4.83 | 4.56 | 1
3069 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Joypur (Village code 315086) under Bhalkundi (Zone-I) Ground Water Based water Supply Scheme for Arsenic Affected Area of Khargram Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154928 in the District of Murshidabad. (Sl No-08) |  |  | ORD/000306/2020-2021 | 165/MURD | 15/01/2021 | 180 | SOUMYADIP MISRA | 56.13 | 50.3 | 1
3070 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JOYPUR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000461/2021-2022 | 230/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0
3071 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village TELSUNDI (Village Code 315121) under Bhalkundi Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. |  |  | ORD/000516/2020-2021 | 3020/MURD | 04/12/2020 | 45 | M/S GUNGUN CONSTRUCTION | 19.58 | 0 | 1
3072 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAUTIPARA (Village Code 315089) under Bhalkundi Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. |  |  | ORD/000526/2020-2021 | 3026/MURD | 04/12/2020 | 45 | SOM CONSTRUCTION AGENCY | 15.45 | 0 | 0
3073 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bhalkundi(Village code 315091) under Bhalkundi (Zone-II)Ground Water Based Water Supply Scheme for Arsenic Affected Area of Khargram Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154928 in the District of Murshidabad. (Sl No-09) |  |  | ORD/000553/2020-2021 | 3045/MURD | 07/12/2020 | 180 | M/S BHUBAN DAS | 47.51 | 0 | 1
3074 | Murshidabad Division |  | Balance FHTC works of extension of distribution pipeline and restoration works of damage pipeline at Bhalkundi (Zone-II) Water Supply Scheme under Kandi Sub-Division, PHE Dte. in the district of Murshidabad |  |  | ORD/001137/2021-2022 | 318/KSD | 16/11/2021 | 30 | M/S BHUBAN DAS | 4.77 | 4.77 | 1
3075 | Murshidabad Division |  | Balance work of distribution pipeline at Shri Krishnapur Village under Bhalkundi (Zone-I) Water Supply Scheme under Kandi Sub-Division, PHE Dte. in the district of Murshidabad. |  |  | ORD/001195/2021-2022 | 337/KSD | 30/11/2021 | 30 | SOUMYADIP MISRA | 4.8 | 4.8 | 1
3076 | Murshidabad Division |  | Providing Balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of PALSANDA ( Village Code -315119) under Bhalkundi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram Block under Murshidabad Division P.H.E Dte. |  |  | ORD/001808/2021-2022 | 818/MURD | 25/03/2022 | 30 | M/S. GOURI ENTERPRISE | 9.52 | 9.38 | 1
3077 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000043/2021-2022 | 541/3/MURD | 25/02/2022 | 0 | Resource Division | 2.7 | 0 | 0
3078 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) from existing distribution system within the command area of village Palsanda (315119) of Bhalkundi under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram Block of Murshidabad District . Tender no 540 of 20-21 by EE |  |  | VCH/000596/2021-2022 | 143-MSD/21-22 | 11/10/2021 | 0 | M/S. GOURI ENTERPRISE | 32.46 | 0 | 0
3079 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with 'JALSWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BAUTIPARA (Village Code 315089) under Bhalkundi Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. Tender no - 694 of 20-21 by EE MURD |  |  | VCH/001445/2021-2022 | 334-MSD/21-22 | 05/03/2022 | 0 | SOM CONSTRUCTION AGENCY | 3.38 | 0 | 0
3080 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pratappur (village code 314757) under Bishnupur Ground Water based Water Supply Scheme in Raninagar-I Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000240/2021-2022 | 1850/BD-I | 07/10/2021 | 100 | SRIJON ENTERPRISE | 96.18 | 43.74 | 1
3081 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamalpur (village code 314778) under Bishnupur Ground Water based Water Supply Scheme in Raninagar-I Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000241/2021-2022 | 1851/BD-I | 07/10/2021 | 100 | SRIJON ENTERPRISE | 96.73 | 30.24 | 1
3082 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bishnupur (Village code 314780) under Bishnupur Ground Water Supply Scheme of Raninagar I Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-16) | Assistant Engineer | Junior Engineer-II | ORD/000451/2021-2022 | 1884/BD-I | 07/10/2021 | 180 | M/S NAYLA CONSTRUCTION | 98.17 | 83.62 | 1
3083 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer-II | RTOR000014/2021-2022 | 141/BD-I | 10/02/2022 | 0 | Resource Division | 5.82 | 0 | 0
3084 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (1216 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Brahmanigram ( Village Code -314319) & Bergram ( Village code-314328) under Sagardighi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000631/2023-2024 | 3436/MURD | 03/11/2023 | 45 | MONDAL ENTERPRISE (FERDOUS) | 38.65 | 0 | 0
3085 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Sagardighi-I Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. |  |  | ORD/001182/2021-2022 | 369/JSD | 22/12/2021 | 30 | S.S.INFRASTRUCTURE | 3.46 | 0 | 0
3086 | Murshidabad Division |  | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Samserganj Block(Protapganj,Nimtita & Chachonda) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (PART-B) |  |  | ORD/000070/2021-2022 | 127 /JSD | 27/05/2021 | 30 | IMAGIN COMMUNICATION | 1.19 | 1.19 | 0
3087 | Murshidabad Division |  | Laying of Different dia UPVC pipeline at South Krishnanagar & Krishnanagar area in connection with Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) under command area of village of Ratanpur ( Village Code -313841) & Malancha (village code-313840) under Bhasaipaikar Zone-I,II &III Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samsherganj Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001723333) |  |  | ORD/000205/2022-2023 | 1381/MURD | 26/05/2022 | 60 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 41.19 | 0 | 0
3088 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Ratanpur (Village code 313841) , Malancha (Village code 313840) ,under Bhasaipaikar Zone-I,II & III Ground Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723333) |  |  | ORD/001211/2021-2022 | 31/MURD | 06/01/2022 | 180 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 301.33 | 61.22 | 0
3089 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Bhasaipaikar (Village code 313879) under Bhasaipaikar Zone-I,II & III Ground Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723333) |  |  | ORD/001231/2021-2022 | 16/MURD | 05/01/2022 | 180 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 235.91 | 45.81 | 0
3090 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000035/2021-2022 | 540/8/MURD | 25/02/2022 | 0 | Resource Division | 67.97 | 0 | 0
3091 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Suti-II Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. |  |  | ORD/001178/2021-2022 | 366/JSD | 22/12/2021 | 30 | S.S.INFRASTRUCTURE | 3.13 | 0 | 0
3092 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kadamtala (Village code 313953) under Mahisali Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723341 in the District of Murshidabad. |  |  | ORD/001577/2021-2022 | 304/MURD | 07/02/2022 | 60 | M/S. M.G. CONSTRUCTION | 27.86 | 0 | 0
3093 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Sagarpara Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000532/2022-2023 | 2540/MURD | 02/09/2022 | 1052 | M/S GUHA AND ROY | 333.77 | 71.95 | 8
3094 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sagarpara Part-B Water Supply Scheme of TW-I,II,III at Head Work Site & 2nd Tube Well Site under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000669/2022-2023 | 3410/MURD | 22/12/2022 | 60 | R.K. DRILLING SERVICES | 35.34 | 30.68 | 90
3095 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000032/2022-2023 | 2780/A/MURD | 01/10/2022 | 0 | Resource Division | 30.95 | 0 | 0
3096 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000313/2023-2024 | 3037/MURD/2 | 27/09/2023 | 0 | Resource Division | 111.86 | 0 | 0
3097 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R(Consultancy work)in connection with the Functional Household Connection of different existing PWSS (Sagarpara PWSS Scheme,Block- Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | VCH/000736/2022-2023 | 260-MSD/22-23 | 18/08/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 11.08 | 0 | 0
3098 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION ATSAGARPARA PWSS JL NO 10 PLOT NO RS 2294,2295 MURSHIDABAD ID 304240390 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01273/2023-2024 | 301/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
3099 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT SAGARPARA PH ID 304244957 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01506/2023-2024 | 406/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 7.89 | 0 | 0
3100 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I,II & III of Sagarpara Part-B ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000837/2023-2024 | 3776/MEDB | 03/11/2023 | 668 | ORIENTAL ENGINEERING CO. | 34.92 | 0 | 0
3101 | Murshidabad Division |  | ¿ Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village Srikrishnapur (Village Code 314737) under Aminabad Ground Water Based Water Supply Scheme for arsenic affected areas of Domkol Block in the District of Murshidabad¿. |  |  | ORD/000715/2020-2021 | 3227/MURD | 22/12/2020 | 60 | PAL TROCKNER (P) LTD. | 43.57 | 38.99 | 100
3102 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Ja lSwapna under command area of village Paikmari (Village code 314672) under Dhulauri Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723245 in the District of Murshidabad. |  |  | ORD/000455/2020-2021 | 32/MURD | 05/01/2021 | 60 | MUNNA AGROTECH ENTERPRISE PRO: MIRAJUL ISLAM | 44.55 | 0 | 0
3103 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Paikmari (Village code 314672) under Dhulauri Ground Water Based Water SupplyScheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723245 in the District of Murshidabad. |  |  | ORD/000592/2020-2021 | 32/MURD | 05/01/2021 | 60 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 44.55 | 20.15 | 0
3104 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Karimpur Jalangi Zone-II Ground Water Based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000525/2022-2023 | 2495/MURD | 30/08/2022 | 1092 | NAYLA CONSTRUCTION | 296.61 | 89.41 | 30
3105 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000038/2022-2023 | 2780/G/MURD | 01/10/2022 | 0 | Resource Division | 11.59 | 0 | 0
3106 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000168/2023-2024 | 1180/MURD/14 | 29/04/2023 | 0 | Resource Division | 11.83 | 0 | 0
3107 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for Providing Balance Functional Household Tap Connection (FHTC) of 69 nos left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Syampur (Village code 314658) under Beniakhali Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad.(Scheme ID- 0001723470) |  |  | ORD/000019/2022-2023 | 878/MURD | 01/04/2022 | 30 | RAJU ENTERPRISE | 18.78 | 0 | 0
3108 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Syampur (314658) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-II), TNO- 737/2020-21/EE |  |  | VCH/000586/2021-2022 | 130-MSD/21-22 | 11/10/2021 | 0 | RAJU ENTERPRISE | 4.33 | 0 | 0
3109 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SARBANGAPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- PARESNATHPUR , CODE-315529, TNO- 604/2020-21/EE |  |  | VCH/002015/2020-2021 | 512/W | 30/03/2021 | 0 | RATAN DUTTA | 25.78 | 0 | 0
3110 | Murshidabad Division |  | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC |  |  | VCH/002047/2020-2021 | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0
3111 | Berhampore Division I | Berhampur Division I | Improvement of Existing AIRP (Modified Sujapur Sadipur Model, Capacity 30.00 cum/hr) including required allied works of GOBRA PWSS under Jal Jeevan Mission within Bhagwangola-I interconnection with Augmentation under Berhampore Division-I, P.H.E. Dte. In the districtof Murshidabad.. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000053/2025-2026 | 762/BD-I | 22/05/2025 | 30 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 9.68 | 0 | 0
3112 | Berhampore Division I | Berhampur Division I | Augmentation of GOBRA Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road,laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000194/2023-2024 | 745/BD-I | 17/08/2023 | 715 | DAS TRADING CO | 315.08 | 0 | 21
3113 | Berhampore Division I | Berhampur Division I | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after successful completion of 3 (Three) months Trial Run of "Augmentation of Gobra ground water supply scheme in Bhagwabgola-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000333/2024-2025 | 286/BD-I | 12/02/2025 | 300 | MODERN CONSTRUCTION | 122.8 | 0 | 0
3114 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for GOBRA Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000882/2021-2022 | 266/ BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.71 | 2.61 | 1
3115 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000065/2023-2024 | 196/BD-I/12 | 09/02/2024 | 0 | Resource Division | 3.11 | 0 | 0
3116 | Berhampore Mechanical | Berhampur Division I | Gobra Water Supply Scheme | Assistant Engineer-I | JE,Junior engineer-III | BILL/01456/2023-2024 | 349/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 3.07 | 0 | 0
3117 | Berhampore Mechanical | Berhampur Division I | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Gobra ground water supply scheme in Bhagwabgola-I Block Dist_Murshidabad under MEDB PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000011/2025-2026 | 1136/MEDB | 13/05/2025 | 92 | DEY ENTERPRISE (MALDA) | 39.59 | 0 | 0
3118 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of GOBRA ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000032/2023-2024 | 3730/MEDB | 03/11/2023 | 668 | SARKAR CONSTRUCTION | 11.46 | 9.53 | 15
3119 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC, Block Bhagwangola-I of Murshidabad District under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000543/2024-2025 | 329/MEDB | 10/02/2025 | 89 | MASSK ENGINEERING WORKS | 11.36 | 0 | 0
3120 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 6,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
3121 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 6,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.4 | 100
3122 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of DOGACHHI (Village code 313848) under DOGACHHI under Ground Water Based Water Supply Scheme (SAMSERGANJ Block) and BAHADURPUR (Village Code-313924) under BAHADURPUR Ground Water Based Water Supply Scheme for (SUTI-I BLOCK) Arsenic Affected Areas of under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 6,Junior engineer-III | ORD/002129/2021-2022 | 557 /MURD | 28/02/2022 | 180 | M/S. NANDY ENTERPRISE | 268.47 | 45.81 | 1
3123 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 6,Junior engineer-III | RTOR000096/2023-2024 | 1147/MURD/11 | 27/04/2023 | 0 | Resource Division | 19.36 | 0 | 0
3124 | Murshidabad Division | Berhampur M/E Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Nimtita ( Village Code -313863) under Hasimpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723174). | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000720/2020-2021 | 639/MURD | 18/02/2021 | 60 | AZAD ENTERPRISE | 25.44 | 24.27 | 1
3125 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Hasimpur ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000035/2023-2024 | 1875/MEDB | 16/06/2023 | 92 | DEY ENTERPRISE | 20.82 | 0 | 0
3126 | Murshidabad Division | Berhampur M/E Division | Allied work for Construction of Boundary Wall & Approach Road at Katlamari ZONE-II Ground water based Piped water supply scheme within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000049/2024-2025 | 1948/MURD | 04/07/2024 | 330 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 38.57 | 0 | 80
3127 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Katlamari Zone-II Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000591/2022-2023 | 3060/MURD | 17/11/2022 | 45 | GENUINE | 23.5 | 18.95 | 0
3128 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution System (part-II) and Providing Functional Household Tap Connection to 550 nos household & Sub-soil Investigation and Construction of OHR (500 cum) of Katlamari Zone -II of Islampur Sub-Division under Murshidabad Division,P.H.E Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000611/2022-2023 | 3244/MURD | 06/12/2022 | 1116 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 214.83 | 106.7 | 18
3129 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution (part-III) and Providing Functional Household Connection to 670 nos household & Construction of Boundary wall of Katlamari Zone -II of Islampur Sub Division under Murshidabad Division,P.H.E Dte.[(i)Amount for LDS & FHTC: Rs.14312870.00 & (ii)Amount for Construction of Boundary wall : Rs.897464.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000676/2022-2023 | 57/MURD | 06/01/2023 | 60 | SOM CONSTRUCTION AGENCY | 132.94 | 0 | 10
3130 | Murshidabad Division | Berhampur M/E Division | Formal work order Laying of Distribution System (part-I) , Rising Main and Providing Functional Household Tap Connection to 790 nos household & Construction of Pump House of Katlamari Zone -II of Islampur Sub-Division under Murshidabad Division,P.H.E Dte [ (i)Amount for LDS,R. Main & FHTC:: Rs.1,38,47,328.00 & (ii)Amount for Construction of Pump House : Rs.15,28,347.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000685/2022-2023 | 162/MURD | 17/01/2023 | 60 | SOUNAK ENTERPRISE | 153.68 | 80.12 | 10
3131 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Katlamari PWSS Scheme, Block - Raninagar-II) to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000739/2021-2022 | 2745/MURD | 03/09/2021 | 60 | RADIANT | 11.14 | 5.57 | 1
3132 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000052/2022-2023 | 3052/E/MURD | 17/11/2022 | 0 | Resource Division | 9.64 | 0 | 0
3133 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000103/2023-2024 | 1167/MURD | 28/04/2023 | 0 | Resource Division | 57.64 | 0 | 0
3134 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT KATLAMARI Z2 PH2, ID304232741 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01220/2023-2024 | 282/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 5.04 | 0 | 0
3135 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT KATLAMRI Z2 PH I, ID304232748 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01222/2023-2024 | 283/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.2 | 0 | 0
3136 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT KATLAMARI Z2 PH 3, ID304232745 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01225/2023-2024 | 284/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 4.37 | 0 | 0
3137 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-II under KATLAMARI ground water based water supply scheme under Block_ RANINAGAR-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000887/2023-2024 | 4051/MEDB | 01/12/2023 | 91 | M/S K.P. PRAMANIK | 34.44 | 27.94 | 20
3138 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution system,Rising Main, Sub-soil Investigation and construction of OHR (300 cum) and construction of Boundary wall and repairing of Pump-House in connection wih Augmentation of Godhanpara Zone-III water supply scheme under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000543/2022-2023 | 2729/MURD | 27/09/2022 | 1070 | PRIYANKA CONSTRUCTION | 270.88 | 183.93 | 80
3139 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Godhanpara Zone-III Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000590/2022-2023 | 3059/MURD | 17/11/2022 | 45 | GENUINE | 23.5 | 20.83 | 100
3140 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000738/2021-2022 | 2744/MURD | 03/09/2021 | 60 | RADIANT | 11.27 | 3.76 | 0
3141 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000045/2022-2023 | 3037/D/MURD | 16/11/2022 | 0 | Resource Division | 40.31 | 0 | 0
3142 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000050/2022-2023 | 3052/C/MURD | 17/11/2022 | 0 | Resource Division | 17.71 | 0 | 0
3143 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000294/2023-2024 | 1278/MURD/12 | 10/05/2023 | 0 | Resource Division | 37.4 | 0 | 0
3144 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT GODHANPARA Z3 PH I, ID304232740 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01223/2023-2024 | 286/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 6.75 | 0 | 0
3145 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works forAugmentation in connention to Accommodate FHTC at Pump House No.-I, Zone-III under Godhanpara Ground Water Based Piped Water Supply Scheme under Block- Raninagar-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000560/2024-2025 | 342/MEDB | 10/02/2025 | 89 | J. S. CONSTRUCTION | 11.36 | 0 | 0
3146 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Jhikra ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000112/2022-2023 | 1365/BD-I | 21/12/2022 | 30 | AZAD ENTERPRISE | 2.41 | 2.37 | 100
3147 | Berhampore Division I | Berhampur Division I | Augmentation of JHIKRA Piped water supply scheme to accommodate construction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000202/2022-2023 | 1615/BD-I | 02/03/2023 | 310 | KAMIRUL SK AND CO. | 418.14 | 68.93 | 35
3148 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jhikra Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000283/2022-2023 | 1806/BD-I | 31/03/2023 | 30 | SUJIT KUMAR SAHA | 8.99 | 0 | 100
3149 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for JHIKRA Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000888/2021-2022 | 271//BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.75 | 0 | 100
3150 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | RTOR000053/2023-2024 | 196/BD-I/5 | 09/02/2024 | 0 | Resource Division | 5.7 | 0 | 0
3151 | Berhampore Mechanical | Berhampur Division I | JHIKRA PWSS | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | BILL/01453/2023-2024 | 347/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 2.14 | 0 | 0
3152 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Jhikra ground water based water supply scheme under Block- Bhagwangola-II, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/001436/2023-2024 | 4320/MEDB | 29/12/2023 | 91 | A.G. ENTERPRISE | 11.17 | 0 | 0
3153 | Berhampore Division I | Berhampur Division I | Formal work order for Augmentation of Benipur Piped water supply scheme to accommodate construction of OHR, toilet, pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000138/2022-2023 | 1448/BD-I | 17/01/2023 | 1000 | KAMIRUL SK AND CO. | 472.43 | 66.33 | 40
3154 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BENIPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000174/2022-2023 | 1076/BD-I | 29/09/2022 | 10 | NATSOL CONSULTANT | 2.92 | 2.92 | 0
3155 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Benipur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000286/2022-2023 | 1810/BD-I | 31/03/2023 | 898 | SUJIT KUMAR SAHA | 18.01 | 0 | 100
3156 | Berhampore Division I | Berhampur Division I | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Benipur ground water supply scheme in Bhagwabgola-II Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000367/2024-2025 | 327/BD-I | 25/02/2025 | 300 | J.S. CONSTRUCTION | 122.8 | 0 | 0
3157 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | RTOR000001/2023-2024 | 61/BD-1/3 | 27/04/2023 | 0 | Resource Division | 36.06 | 0 | 0
3158 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION AT BENIPUR PH-I | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | BILL/00430/2024-2025 |  | 27/06/2024 | 0 | WBSEDCL | 11.24 | 0 | 0
3159 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION AT BENIPUR PH-I | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | BILL/00469/2024-2025 | 147/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 11.24 | 0 | 0
3160 | Berhampore Mechanical | Berhampur Division I | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Benipur ground water supply scheme in Bhagwabgola-II Block, Dist_Murshidabad under MEDB PHE Dte." | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000014/2025-2026 | 1139/MEDB | 13/05/2025 | 92 | DIPALI CONSTRUCTION | 39.95 | 0 | 0
3161 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of BENIPUR ground water based water supply scheme under Block- Bhagawangola- II, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000812/2023-2024 | 3765/MEDB | 03/11/2023 | 92 | TARUN KUMAR BHATTACHARYA | 25.87 | 0 | 0
3162 | Murshidabad Division | Kandi Sub-Division | Allied work of Construction of 2nos. Box Culvert, approach road at Sijgram PWSS at Bharatpur -I Block under Kandi Sub-Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000046/2024-2025 | 1893/MURD | 01/07/2024 | 242 | RIM CONSTRUCTION | 44.07 | 0 | 10
3163 | Murshidabad Division | Kandi Sub-Division | Balance work for laying of distribution pipe line and allied works of Sijgram Water Supply Scheme, Bharatpur - I Block, Kandi Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000633/2023-2024 | 3441/MURD | 03/11/2023 | 698 | JIBENDRA NARAYAN SUKUL | 28.37 | 11.97 | 50
3164 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SIJGRAM PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000660/2022-2023 | 3405/MURD | 22/12/2022 | 45 | M/S D. PALIT & CO. | 16.81 | 15.42 | 100
3165 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution System (PART -A) of SIJGRAM PWSS of Bharatpur - I Block, Kandi Sub Division under Murshidabad District, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000697/2022-2023 | 132 / MURD | 16/01/2023 | 775 | JIBENDRA NARAYAN SUKUL | 136.47 | 91.72 | 67
3166 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of SIJGRAM PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362356S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,23,22,548.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,57,06,711.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000745/2022-2023 | 412/MURD | 15/02/2023 | 1020 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 280.01 | 46.52 | 11
3167 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000013/2023-2024 | 1210/MURD/34 | 02/05/2023 | 0 | Resource Division | 42.92 | 0 | 0
3168 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT SIJGRAM PH 1 PWSS ID 304201248 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01131/2023-2024 | 221/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 5.03 | 0 | 0
3169 | Berhampore Mechanical | Kandi Sub-Division | Sijgram ph-2 Application No- 3004401470 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01180/2023-2024 | 242/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 8.65 | 0 | 0
3170 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SIJGRAM ground water based water supply scheme under Block_ Bharatpur-I, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000106/2023-2024 | 1893/MEDB | 16/06/2023 | 899 | SUNIL RABIDAS | 22.58 | 16.22 | 5
3171 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR , Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone I PWSS in Lalgola Block , Dhusaripara PWSS in Block- Samserganj, District Murshidabad of Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000544/2023-2024 | 3149/MURD | 09/10/2023 | 905 | J.S. CONSTRUCTION | 507.37 | 82.02 | 50
3172 | Murshidabad Division | Berhampur M/E Division | Preparation of D.p.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (DHUSARIPARA PWSS Scheme,Block- SAMSERGAUNGE to be Augmentation/Rejuvination under Murshidabad Division P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/002048/2021-2022 | 3251/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.94 | 5.94 | 1
3173 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000127/2023-2024 | 1167/MURD/27 | 28/04/2023 | 0 | Resource Division | 11.5 | 0 | 0
3174 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under DHUSARIPARA ground water based water supply scheme under Block_ Samsherganj, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000029/2023-2024 | 1874/MEDB | 16/06/2023 | 92 | ARINDAM MAJUMDAR | 22.1 | 0 | 0
3175 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of LOHADAHA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362288S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000707/2022-2023 | 146/MURD | 17/01/2023 | 1080 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 492.18 | 210.73 | 78
3176 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000042/2023-2024 | 1004/MURD/17 | 17/04/2023 | 0 | Resource Division | 36.62 | 0 | 0
3177 | Berhampore Mechanical | Kandi Sub-Division | Lohadaha PH-1 Application No- 3004528444 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/01202/2023-2024 | 280/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
3178 | Berhampore Mechanical | Kandi Sub-Division | Quotation for Lohadaha PH-2 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/01432/2023-2024 | 331/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 5.54 | 0 | 0
3179 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of PUNIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000692/2022-2023 | 164/MURD | 17/01/2023 | 1049 | M/S.TAPAS KUMAR CHAKRABORTY | 561.45 | 203.41 | 26
3180 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000049/2023-2024 | 1067/MURD/4 | 18/04/2023 | 0 | Resource Division | 12.28 | 0 | 0
3181 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000335/2023-2024 | 79/MURD/02 | 09/01/2024 | 0 | Resource Division | 17.24 | 0 | 0
3182 | Berhampore Mechanical | Kandi Sub-Division | Electric Service New Connection PUNIA PH- 1 PWSS Application NO. 3004403691. ID. 304119961 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01038/2023-2024 | 173/WBSEDCL-JJM | 05/12/2023 | 0 | WBSEDCL | 6.85 | 0 | 0
3183 | Berhampore Mechanical | Kandi Sub-Division | Electric Service New Connection PUNIA PH- 2 PWSS Application NO. 3004403727. ID. 304119979 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01039/2023-2024 | 174/WBSEDCL-JJM | 05/12/2023 | 0 | WBSEDCL | 4.94 | 0 | 0
3184 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under PUNIA ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000154/2023-2024 | 2014/MEDB | 19/06/2023 | 92 | M/S S. S. ENTERPRISE (DOMKAL) | 22.32 | 0 | 50
3185 | Central Drilling | Raghunathganj Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
3186 | Berhampore Division I | Raghunathganj Sub-Division | Formal work order for Augmentation of Bishnupur Zone-II Piped water supply scheme to accommodate construction of Pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000178/2022-2023 | 1541/BD-I | 16/02/2023 | 925 | NATIONAL CONSTRUCTION | 190.09 | 181.89 | 95
3187 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BISHNUPUR ZONE-II Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000270/2022-2023 | 1761/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.6 | 2.6 | 100
3188 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000021/2023-2024 | 194/BD-I/6 | 09/02/2024 | 0 | Resource Division | 42.69 | 0 | 0
3189 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-II of Bishnupur ground water based water supply scheme under Block- RANINAGAR-I Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/001435/2023-2024 | 4316/MEDB | 29/12/2023 | 91 | S.P. ENTERPRISE (BAGUIHATI) | 10.62 | 0 | 0
3190 | Berhampore Division I | Berhampur Division I | Replacement of Filter media of Existing AIRP of (Capacity 87 Cum/hr.) with allied work at Charkamnagar Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000010/2024-2025 | 905/BD-I | 07/06/2024 | 30 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 29.25 | 0 | 0
3191 | Berhampore Division I | Berhampur Division I | Construction of Boundary wall at 2nd Tube Well Site of CHARKAMNAGAR ZONE-I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000039/2025-2026 | 672/BD-I | 29/04/2025 | 45 | JAMUNA CONSTRUCTION | 10.18 | 0 | 0
3192 | Berhampore Division I | Berhampur Division I | Augmentation of Charkamnagar Piped water supply scheme to accommodate construction of OHR, Pump House, Boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000157/2023-2024 | 681/BD-I | 10/08/2023 | 990 | MERCURY ENGINEERING COMPANY | 418.24 | 0 | 7
3193 | Berhampore Division I | Berhampur Division I | Allied work for Laying of distribution pipeline of CHARKAMNAGAR and allied works within Beldanga-II Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000179/2024-2025 | 2122/BD-I | 27/11/2024 | 45 | NOVELTY CONSTRUCTION | 46.47 | 0 | 0
3194 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for CHARKAMNAGAR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000234/2022-2023 | 1592/BD-I | 28/02/2023 | 10 | TECHVISION | 2.74 | 2.74 | 0
3195 | Berhampore Division I | Berhampur Division I | Bored Cast-in-situ_ M30 _ grade 500 mm dia. R.C.C. pile for Construction of OHR at Head Work site of CHARKAMNAGAR Ground Piped Water Supply Scheme under Jal Jeevan Mission within Beldanga - II Block under Berhampore Division-I, PHE.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000332/2024-2025 | 279/BD-I | 12/02/2025 | 30 | MERCURY ENGINEERING COMPANY | 25.63 | 0 | 0
3196 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000084/2023-2024 | 196/BD-I/20 | 09/02/2024 | 0 | Resource Division | 77.09 | 0 | 0
3197 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under CHARKAMNAGAR ground water based water supply scheme under Block_ Beldanga-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000061/2023-2024 | 3778/MEDB | 26/05/2023 | 92 | WEST BENGAL ENGINEERING CO. | 35.2 | 0 | 0
3198 | Murshidabad Division | Kandi Sub-Division | HAMIDPUR & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BHARATPUR-I of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000872/2022-2023 | 872/MURD | 27/03/2023 | 857 | PRATIMA CONSTRUCTION | 159.76 | 79.99 | 5
3199 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000070/2023-2024 | 1075/MURD/12 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
3200 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT HAMIDPUR PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00401/2024-2025 | 106/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 9.71 | 0 | 0
3201 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT HAMIDPUR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00402/2024-2025 | 107/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 8.94 | 0 | 0
3202 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BIPRA SEKHAR AND ADJOINING MOUJAS Water Supply Scheme & ALAMPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000400/2023-2024 | 2807/MURD | 05/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 100
3203 | Murshidabad Division | Kandi Sub-Division | BIPRA SEKHAR PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Burwan Block , Kandi Sub-Division, of Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000863/2022-2023 | 823/MURD | 23/03/2023 | 831 | DILIP KUMAR MONDAL | 657.71 | 346.07 | 50
3204 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000234/2023-2024 | 1219/MURD/11 | 03/05/2023 | 0 | Resource Division | 21.03 | 0 | 0
3205 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS BIPRASEKHAR PH1 ID 304247611 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01425/2023-2024 | 315/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 9.43 | 0 | 0
3206 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS PH 2 BIPRASEKHAR ID 304247692 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01426/2023-2024 | 316/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 7.95 | 0 | 0
3207 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Bipra Sekhar ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000265/2023-2024 | 3702/MEDB | 03/11/2023 | 791 | M/S S. S. ENTERPRISE (DOMKAL) | 22.55 | 0 | 50
3208 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 29.67 | 20
3209 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augmentation of Ramnagar Doemkanon Zone-I (Part-B) PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000054/2024-2025 | 1120/BD-I | 11/07/2024 | 60 | S.K ENTERPRISE (RANITALA) | 7.92 | 0 | 0
3210 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of Ramnagar Doemkanun Zone-I (Part-B) PWSS under Jal Jeevan Mission within Raninagar -II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000073/2025-2026 | 840/BD-I | 23/06/2025 | 60 | PRADIP MAHATO | 19 | 0 | 0
3211 | Berhampore Division I | Raghunathganj Sub-Division | RAMNAGAR DOEMKANUN ZONE-I PART-B PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000137/2024-2025 | 1552/BD-I | 24/09/2024 | 60 | M/S B.M. INDUSTRIES | 20.64 | 0 | 0
3212 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Ramnagar Doemkanun Zone-I(Part-B) Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000179/2023-2024 | 695/BD-I | 11/08/2023 | 627 | M/S SINHA & SONS | 408.86 | 0 | 25
3213 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000010/2023-2024 | 61/BD-1/9 | 27/04/2023 | 0 | Resource Division | 57.59 | 0 | 0
3214 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW CONNECTION RAMNAGAR DEOMKANUN Z-1 PH-I | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | BILL/01631/2023-2024 | 470/WBSEDCL-JJM | 19/03/2024 | 0 | WBSEDCL | 12.56 | 0 | 0
3215 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 32.96 | 20
3216 | Berhampore Division I | Raghunathganj Sub-Division | Improvement of OHR (350 Cum) of Ground Water Based Supply Scheme for Augmentation of Ramnagar Domkanun Zone-I Part-A of Raninagar-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000003/2024-2025 | 891/BD-I | 06/06/2024 | 30 | PRAVAT KUMAR GHOSH | 8.66 | 0 | 100
3217 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of Ramnagar Doemkanun Zone- I(Part-A) PWSS under Jal Jeevan Mission within Raninagar -II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000087/2025-2026 | 876/BD-I | 01/07/2025 | 60 | BISWAS CONSTRUCTION | 18.97 | 0 | 0
3218 | Berhampore Division I | Raghunathganj Sub-Division | Allied work for Laying of Distribution pipeline of Ramnagar Doemkanon Zone - I PWSS within Raninagar - II Block under JJM of Murshidabad district under Berhampore Division - I P.H.Engg Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000123/2024-2025 | 1471/BD-I | 06/09/2024 | 225 | MAA CONSTRUCTION | 26.47 | 0 | 85
3219 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAGAR DOEMKANON ZONE-I Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000196/2022-2023 | 1379/BD-I | 22/12/2022 | 10 | RADIANT | 2.94 | 2.85 | 100
3220 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of RamnagarDoemkanun Zone_I (Part-A)Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000243/2022-2023 | 1613/BD-I | 02/03/2023 | 1080 | SUJIT KUMAR SAHA | 249.53 | 195.75 | 85
3221 | Berhampore Division I | Raghunathganj Sub-Division | Construction Pump House Cum Chlorine Room at RAMNAGAR DOEMKANUN ZONE-I Water Supply Scheme under Jal Jevan Mission within Raninagar-II Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000326/2024-2025 | 273/BD-I | 11/02/2025 | 60 | TAIMUR SK | 7.5 | 0 | 0
3222 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000037/2023-2024 | 61/BD-1/25 | 27/04/2023 | 0 | Resource Division | 29.78 | 0 | 0
3223 | Berhampore Division I | Berhampur M/E Division | Augmentation of Bajipur Madhupur Zone-II Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(Part-B) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000123/2023-2024 | 508/BD-I | 24/07/2023 | 800 | H.I ENTERPRISE | 340.79 | 0 | 44
3224 | Berhampore Division I | Berhampur M/E Division | Augmentation of Bajipur Madhupur Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(PART-A) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000181/2023-2024 | 697/BD-I | 11/08/2023 | 310 | UNIVERSE UNEMPLOYED ENGINEERS CONSTRUCTION CO. | 335.43 | 0 | 0
3225 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BAJIPUR MADHUPUR ZONE-II Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000205/2022-2023 | 1383/BD-I | 23/12/2022 | 10 | ENVIROTECH SOLUTIONS | 2.87 | 2.9 | 1
3226 | Berhampore Division I | Berhampur M/E Division | Repair And Renovation Works Of OHR (450 Cum) for Bajupur Madhupur Zone-II water supply scheme of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal Jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000359/2023-2024 | 15/BD-I | 04/01/2024 | 330 | MAA SANKARI ENTERPRISE | 8.61 | 0 | 100
3227 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000014/2024-2025 | 1510/BD-I/8 | 12/09/2024 | 0 | Resource Division | 9.8 | 0 | 0
3228 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000076/2023-2024 | 201/BD-1/17 | 10/02/2024 | 0 | Resource Division | 280.69 | 0 | 0
3229 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF BAJUPUR MADHUPUR ZONE-II PIPED WATER SUPPLY SCHEME Block - Lalgola under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000540/2024-2025 | 326/MEDB | 10/02/2025 | 89 | KARTICK BAL | 25.03 | 0 | 0
3230 | Berhampore Division I | Berhampur Division I | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-I Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000004/2023-2024 | 40/BD-I | 20/04/2023 | 10 | TECHVISION | 2.81 | 2.81 | 100
3231 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of Ramnachandpur Zone-I" ground water supply scheme in NAWDA Block, under Berhampore Division-I, P.H.E Dte(Capacity-98.00 Cum/hr.) Type-1: Fully Gravity System with RG Filter | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000038/2024-2025 | 1037/BD-I | 28/06/2024 | 365 | ACQUA CONSTRUCTION CONSORTIUM | 234.01 | 0 | 0
3232 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-I Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000192/2022-2023 | 1320/BD-I | 13/12/2022 | 10 | TECHVISION | 2.81 | 2.81 | 0
3233 | Berhampore Division I | Berhampur Division I | Augmentation of Ramnachandpur Zone_I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000250/2022-2023 | 1655/BD-I | 13/03/2023 | 752 | SOFIQUL ISLAM | 371.52 | 316.8 | 95
3234 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | RTOR000056/2023-2024 | 196/BD-I/18 | 09/02/2024 | 0 | Resource Division | 7.99 | 0 | 0
3235 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , Zone-I under RAMNACHANDPUR ground water based water supply scheme under Block_ Nowda Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000069/2023-2024 | 1883/MEDB | 16/06/2023 | 92 | CONCORD ENGINEERING | 35.22 | 0 | 0
3236 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
3237 | Berhampore Division I | Berhampur Division I | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BALI ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000003/2023-2024 | 32/BD-I | 19/04/2023 | 10 | TECHVISION | 2.81 | 2.81 | 100
3238 | Berhampore Division I | Berhampur Division I | Allied works for upgradation,Improvement and laying of Augmentation of Bali Zone-II Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000172/2024-2025 | 2037/BD-I | 12/11/2024 | 360 | S.D PROJECT | 55.74 | 0 | 60
3239 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BALI ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000238/2022-2023 | 1596/BD-I | 28/02/2023 | 10 | TECHVISION | 2.81 | 2.81 | 0
3240 | Berhampore Division I | Berhampur Division I | Construction Pump House Cum Chlorine Room at Head Work site of BALI ZONE-II Water Supply Scheme under Jal Jevan Mission within Nawda Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000299/2024-2025 | 148/BD-I | 29/01/2025 | 60 | SUPRIYA DEY | 8.77 | 0 | 60
3241 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000085/2023-2024 | 1156/BD-I | 05/12/2023 | 0 | Resource Division | 47.43 | 0 | 0
3242 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 13.15 | 20
3243 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augmentation of Lochanpur Zone-I PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000055/2024-2025 | 1125/BD-I | 11/07/2024 | 60 | KHANDAKAR CONSTRUCTION | 8.19 | 0 | 0
3244 | Berhampore Division I | Raghunathganj Sub-Division | LOCHANPUR ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000060/2024-2025 | 1175/BD-I | 25/07/2024 | 60 | DEBJIT DAS | 21.57 | 0 | 0
3245 | Berhampore Division I | Raghunathganj Sub-Division | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Lochanpur Zone-I ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000090/2025-2026 | 950/BD-I | 18/07/2025 | 300 | HARBAUER INDIA (P) LTD. | 122.79 | 0 | 0
3246 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Lochanpur Zone-I Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar -I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000180/2023-2024 | 696/BD-I | 11/08/2023 | 310 | ARABINDA GHOSH | 323.45 | 0 | 10
3247 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for LOCHANPUR ZONE-I Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000271/2022-2023 | 1762/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.6 | 2.6 | 100
3248 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000008/2023-2024 | 61/BD-1/2 | 27/04/2023 | 0 | Resource Division | 29.7 | 0 | 0
3249 | Berhampore Mechanical | Raghunathganj Sub-Division | NEW SERVICE CONNECTION AT LOCHANPUR Z1 PH 1 ID 304268981 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | BILL/01131/2024-2025 |  | 26/11/2024 | 0 | WBSEDCL | 16.76 | 0 | 0
3250 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Lochanpur Zone-I ground water supply scheme in Raninagar-I Block Dist_Murshidabad under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000007/2025-2026 | 1131/MEDB | 13/05/2025 | 92 | HARA PROSAD DAS | 39.97 | 0 | 0
3251 | Murshidabad Division | Kandi Sub-Division | Allied works for Construction of Approach road, Guard Wall and Laying UPVC Pipeline & Soil Investigation Study of Gourinagar Water Supply Scheme in Burwan Block of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000181/2024-2025 | 3144/MURD | 03/12/2024 | 180 | ABDUL JABBAR DEWAN | 27.17 | 0 | 60
3252 | Murshidabad Division | Kandi Sub-Division | Formal work order for GOURI NAGAR & adjoining mouzas PWSS to accommodate FHTC under Jal Jiban Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000798/2022-2023 | 607/MURD | 02/03/2023 | 975 | ABDUL JABBAR DEWAN | 218.13 | 104.55 | 65
3253 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000274/2023-2024 | 1230/MURD/17 | 04/05/2023 | 0 | Resource Division | 2.89 | 0 | 0
3254 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS PH1 GOURINAGAR ID 304248173 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01427/2023-2024 | 317/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 8.13 | 0 | 0
3255 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS GOURINAGAR PH2 ID 304247757 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01428/2023-2024 | 318/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 6.9 | 0 | 0
3256 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for NEWLY SUNK TUBE WELL in connection to Accommodate FHTC at Pump House No.-I & II under GOURI NAGAR ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001427/2023-2024 | 4341/MEDB | 29/12/2023 | 611 | M/S S. S. ENTERPRISE (DOMKAL) | 18.46 | 0 | 40
3257 | Murshidabad Division | Kandi Sub-Division | KOGRAM & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000013/2023-2024 | 983/MURD | 10/04/2023 | 631 | HIRANMAY GHOSH | 599.93 | 29.7 | 50
3258 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | RTOR000242/2023-2024 | 1219/MURD/17 | 03/05/2023 | 0 | Resource Division | 14.53 | 0 | 0
3259 | Berhampore Mechanical | Kandi Sub-Division | Kogram PH-2 Application No-3004543754 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | BILL/01178/2023-2024 | 238/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 4.36 | 0 | 0
3260 | Berhampore Mechanical | Kandi Sub-Division | Kogram PH-1 Application No- 3004543655 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | BILL/01179/2023-2024 | 239/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 5.47 | 0 | 0
3261 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under KOGRAM ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000689/2023-2024 | 4303/MEDB | 29/12/2023 | 91 | DAS ENTERPRISE (CHOA) | 23.66 | 0 | 60
3262 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bharatpur Zone-IB Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur - I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000117/2023-2024 | 1768/MURD | 06/07/2023 | 21 | SUJIT KUMAR SAHA | 23.58 | 0 | 0
3263 | Murshidabad Division | Kandi Sub-Division | Augmentation of BHARATPUR (ZONE - I B) PWSS under Jal Jeevan Mission of Bharatpur Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000205/2023-2024 | 2070/MURD | 28/07/2023 | 300 | BERHAMPORE CONSTRUCTION SYNDICATE PVT. LTD. | 478.38 | 0 | 0
3264 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IB under Bharatpur ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000245/2023-2024 | 3681/MEDB | 03/11/2023 | 92 | CONCORD ENGINEERING | 22.78 | 0 | 0
3265 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System ,Rising Main and Extension of Boundary Wall for Augmentation of Giria Zone -I and Zone-II Piped water supply scheme in Raghunathganj-II Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000083/2024-2025 | 2076/MURD | 19/07/2024 | 60 | M/S J.S. ENTERPRISE | 65.18 | 0 | 0
3266 | Murshidabad Division | Berhampur M/E Division | Providing FHTC to 1200 nos household and OHR Repair of 45 cum capacity for Augmentation of Giria Zone -I and Zone-II Piped water supply scheme in Raghunathganj-II Block under Murshidabad Division, PHE.Dte . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000097/2024-2025 | 2090/MURD | 23/07/2024 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 60.76 | 0 | 0
3267 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Raghunathganj-II of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Giriya Kismat Water supply Scheme, Jotsundar Water Supply Scheme, Giria Water Supply Scheme Zone-I & II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000562/2022-2023 | 2912/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 12.39 | 2.52 | 100
3268 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Giria Zone-I PWS accommodate FHTC of 2614 nos household, Laying Distribution System, Laying Rising Main,Construction of Pump House (4.10m x 3.5m with sanitary and Water Supply Arrangement) 1no, Construction of Boundary Wall of length 48 m, Repairing & maintenance of 2(two) nos Pump House ,existing boundary wall and Overhauling of R.C.C. elevated reservoir of 450 Cum capacity of staging hight 20 mtr. in Raghunathganj - II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000585/2023-2024 | 3320/MURD | 22/10/2023 | 664 | S.B. ASSOCIATES | 245.83 | 0 | 75
3269 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000115/2023-2024 | 1167/MURD/9 | 28/04/2023 | 0 | Resource Division | 5.26 | 0 | 0
3270 | Berhampore Mechanical | Berhampur M/E Division | EW SERVICE CONNECTION AT GIRIA Z1 PH3 ID 304512470 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | BILL/01223/2024-2025 | 304/WBSEDL-JJM | 06/12/2024 | 0 | WBSEDCL | 3.53 | 0 | 0
3271 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Source Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. P.H.E. Dte. under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000558/2024-2025 | 340/MEDB | 10/02/2025 | 89 | M/S SAMRIDDHI ENTERPRISE | 36.36 | 0 | 0
3272 | Murshidabad Division |  | Additional Laying and distribution of UPVC pipiline for Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of FATEPUR ( Village Code _315310) under Fatepur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. |  |  | ORD/000186/2022-2023 | 193/BSD | 28/04/2022 | 30 | S.G CONSTRUCTION , | 4.36 | 0 | 0
3273 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. |  |  | ORD/000447/2021-2022 | 297/BSD | 13/08/2021 | 30 | IMAGIN | 4.34 | 8.68 | 0
3274 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at KHIDIRPUR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000500/2021-2022 | 335/BSD | 27/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.16 | 4.16 | 0
3275 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Fatepur (Village code 315310) under Fatepur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723484 in the District of Murshidabad. |  |  | ORD/000511/2020-2021 | 78/MURD | 08/01/2021 | 60 | RELIABLE ENTERPRISE | 26.51 | 46.96 | 0
3276 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Chak Kathalia (Part-A) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000076/2023-2024 | 182/BD-I | 17/05/2023 | 910 | ANKITA ENTERPRISE-GOPEJAN(NATHPARA) | 28.45 | 0 | 82
3277 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Chak Kathalia (Part-B) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000077/2023-2024 | 183/BD-I | 17/05/2023 | 90 | PRADIP DAS | 28.45 | 0 | 60
3278 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Chak Kathalia (Part-C) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000078/2023-2024 | 184/BD-I | 17/05/2023 | 90 | GOUTAM KUMAR CHAUDHURI | 28.32 | 0 | 0
3279 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Katalia village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000175/2023-2024 | 3036/MEDB | 02/08/2023 | 92 | SREE RADHA ELECTRICAL | 6.32 | 0 | 0
3280 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Katalia village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000189/2023-2024 | 588/MEDB | 31/01/2024 | 90 | JOGMAYA ENGINEERING | 6.3 | 0 | 0
3281 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Sujapur (Part-A) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000067/2023-2024 | 165/BD-I | 16/05/2023 | 822 | MAHATO ENTERPRISE | 28.44 | 0 | 80
3282 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Sujapur (Part-B) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000069/2023-2024 | 166/BD-I | 16/05/2023 | 90 | DEBJYOTI MUKHERJEE | 27.91 | 0 | 0
3283 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Sujapur village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000178/2023-2024 | 3039/MEDB | 02/08/2023 | 92 | MERCURY ENGINEERING CO | 6.33 | 0 | 0
3284 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Sujapur Zone-I under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000046/2023-2024 | 145/BD-I | 15/05/2023 | 822 | RAWSHAN FOUNDATION | 30.49 | 0 | 80
3285 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Sujapur Zone-I village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000179/2023-2024 | 3040/MEDB | 02/08/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0
3286 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Chandabag under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000065/2023-2024 | 162/BD-I | 16/05/2023 | 90 | PRAVAT KUMAR GHOSH | 24.63 | 0 | 0
3287 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chandabag village, Block:- Murshidabad - Jiaganj under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000174/2023-2024 | 3035 | 02/08/2023 | 92 | SREE RADHA ELECTRICAL | 6.32 | 0 | 0
3288 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based GIRIA KISMAT PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000009/2023-2024 | 951/MURD | 05/04/2023 | 1002 | SUNRISE CONSTRUCTION | 354.38 | 0 | 0
3289 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Raghunathganj-II of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Giriya Kismat Water supply Scheme, Jotsundar Water Supply Scheme, Giria Water Supply Scheme Zone-I & II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000562/2022-2023 | 2912/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 12.39 | 2.48 | 100
3290 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000264/2023-2024 | 1230/MURD/05 | 04/05/2023 | 0 | Resource Division | 46.51 | 0 | 0
3291 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. under MEDB, PHE Dte." | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000568/2024-2025 | 383/MEDB | 12/02/2025 | 89 | SUNIL RABIDAS | 34.09 | 0 | 0
3292 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 3.38 | 100
3293 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 300 & 900 cum), Sinking of Tube Well and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Arjunpur Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000547/2023-2024 | 3177/MURD | 11/10/2023 | 730 | M/S. CHAKRABORTY & COMPANY | 2041.06 | 0 | 35
3294 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000142/2023-2024 | 1167/MURD/40 | 28/04/2023 | 0 | Resource Division | 3.79 | 0 | 0
3295 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT ARJUNPUR Z3 PH1 ID 304390315 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | BILL/01143/2024-2025 |  | 27/11/2024 | 0 | WBSEDCL | 5.66 | 0 | 0
3296 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,ZONE-III under ARJUNPUR ground water based water supply scheme under Block_ FARAKKA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000107/2023-2024 | 4307/MEDB | 29/12/2023 | 91 | M/S SAMRIDDHI ENTERPRISE | 34.16 | 25.37 | 60
3297 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Hallalpur Zone-I under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000094/2023-2024 | 169/BD-I | 16/05/2023 | 90 | SAMRAT MAZUMDAR | 30.5 | 0 | 0
3298 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Halalpur Zone-I village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000214/2023-2024 | 3074/MEDB | 02/08/2023 | 92 | SURAKSHA | 6.3 | 0 | 0
3299 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Hallalpur Zone-II under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000096/2023-2024 | 170/BD-I | 16/05/2023 | 90 | M/S. MONDAL ENTERPRISE 12/6/1, OLD POLICE LINE ROAD, GORABAZAR | 30.49 | 0 | 0
3300 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at CharHalalpur - Zone-II village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000177/2023-2024 | 3038/MEDB | 02/08/2023 | 92 | MERCURY ENGINEERING CO | 6.33 | 0 | 0
3301 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based JOT KAMAL (ZONE-I), JOTKAMAL (Zone-II) & JOTKAMAL (Zone-III) PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000282/2023-2024 | 2643/MURD | 23/08/2023 | 587 | M/S NIRAPADA BHATTACHARJEE | 1194.05 | 0 | 10
3302 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,JUNIOR ENGINEER 6,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 7.5 | 100
3303 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,JUNIOR ENGINEER 6,Junior engineer-II | RTOR000248/2023-2024 | 1219/MURD/34 | 03/05/2023 | 0 | Resource Division | 2.92 | 0 | 0
3304 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Juginda, Kupila and Narsinghpur Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000109/2022-2023 | 1193/MURD | 10/05/2022 | 1360 | MAMATA USHA ENTERPRISE | 32.62 | 9.38 | 20
3305 | Murshidabad Division | Berhampur M/E Division | Augmentation of NARASINGHAPUR ZONE-I PWSS Laying Distribution System, Rising Main Connection of JALANGI Block, under Murshidabad Division PHE. Dte. PART_A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000558/2023-2024 | 3219/MURD | 13/10/2023 | 180 | M/S UNIVERSAL TRADING | 273.87 | 125.7 | 20
3306 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 5.67 | 1
3307 | Murshidabad Division | Berhampur M/E Division | Construction of Pump House, Boundary wall & Providing Functional Household Tap Connection for Augmentation of Narasinghapur Zone-I PWSS in Jalangi Block , Islampur Sub-Division under Murshidabad Division , PHE. Dte. Part-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000588/2023-2024 | 3330/MURD | 23/10/2023 | 120 | TRIYA CONSTRUCTION | 105.54 | 19.51 | 30
3308 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000243/2023-2024 | 1219/MURD/21 | 03/05/2023 | 0 | Resource Division | 104.53 | 0 | 0
3309 | Berhampore Mechanical | Berhampur M/E Division | SHIFTING OF A PORTION OF DHANIRAMPUR 11 KV HTOH LINE ALONG WITH 25KVA DTR FOR NARASINGHAPUR PWSS ID 860315776 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01093/2024-2025 |  | 08/11/2024 | 0 | WBSEDCL | 3.83 | 0 | 0
3310 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV ,Zone-I under Narsinghpur ground water based water supply scheme under Block_ JALANGI Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000072/2023-2024 | 4338/MEDB | 29/12/2023 | 91 | B. T. PROJECTS PVT. LTD. | 42.78 | 0 | 0
3311 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Durgapur zone-II under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000053/2023-2024 | 149/BD-I | 15/05/2023 | 90 | DHRITIPALI | 30.23 | 0 | 0
3312 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Durgapur Zone-II village, Block:- Lalgola under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000683/2023-2024 | 3612/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0
3313 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Faridpur ( Village Code -314641) under Faridpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184121) |  |  | ORD/000300/2021-2022 | 2349/MURD | 05/08/2021 | 60 | NATIONAL CONSTRUCTION (PROP:NIZAMUL BISWAS) | 87.31 | 71.82 | 1
3314 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bhaduria Para( Village Code -314643) under Faridpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184121) |  |  | ORD/000509/2020-2021 | 655/MURD | 18/02/2021 | 60 | ASHOK KUMAR SINHA | 81.32 | 36.62 | 0
3315 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for Providing Functional Household Tap connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command areas of village of Bhaduriapara (Village Code-314643) under Faridpur Ground water based water suply scheme for Arsenic affected areas of Jalangi Block, under Murshidabad Division, P.H.E. Dte. (scheme ID- 0005184121) |  |  | ORD/001834/2021-2022 | 766/MURD | 22/03/2022 | 30 | M/S. SINHA & SONS | 36.38 | 36.07 | 0
3316 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work) inconnection with the Functional Household Connection of different existing PWSS(Faridpur Zone-II PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 369 of 21-22 by EE MSD, and Scheme Code: 7919 |  |  | VCH/000037/2022-2023 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 7.25 | 0 | 0
3317 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work) in connection with the Functional Household Connection of different existing PWSS(Faridpur Zone-I PWSS Scheme,Block-Jalangi) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 368 of 21-22 by EE MSD, and Scheme Code: 7919 |  |  | VCH/000038/2022-2023 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 5.36 | 0 | 0
3318 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION)' from existing Distribution system within the Command area of village FARIDPUR (Village Code 314641) under FARIDPUR Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 246 of 21-22 by EE MURD |  |  | VCH/001494/2021-2022 | 395-MSD/21-22 | 23/03/2022 | 0 | NATIONAL CONSTRUCTION (PROP:NIZAMUL BISWAS) | 11.79 | 0 | 0
3319 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall at JADUPUR Water Supply Scheme, Rangamati Chandpara G.P under Berhampore Sub-Division, P.H.E. Dte. in the District Murshidabad. Length-55.0Mtr. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000073/2020-2021 | 3171/MURD | 16/12/2020 | 30 | SOM CONSTRUCTION AGENCY | 4.98 | 4.98 | 100
3320 | Murshidabad Division | Berhampur Sub-Division | Relaying of pipe line at Chandpara village under command area of JADUPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000525/2020-2021 | 119/BSD | 19/02/2021 | 15 | M/S.S.S. ENTERPRISE | 4.85 | 4.85 | 0
3321 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jadupur Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000594/2022-2023 | 3068/MURD | 17/11/2022 | 30 | NADIA TUBEWELLS | 10.6 | 0 | 0
3322 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Construction 200 Cum OHR, Laying Distribution System & Rising Main in Connection with Augmentation of Jadupur Ground water based Piped water supply scheme within Berhampore Block of Murshidabad District under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000687/2022-2023 | 129/MURD | 16/01/2023 | 1061 | SOFIQUL ISLAM | 135.86 | 0 | 5
3323 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.9 | 80
3324 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (JADUPUR PWSS Scheme, Block - Berhampore) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000835/2021-2022 | 3268/MURD | 05/10/2021 | 60 | RADIANT | 2.28 | 2.28 | 1
3325 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000002/2024-2025 | 1811/MURD/01 | 20/06/2024 | 0 | Resource Division | 4.49 | 0 | 0
3326 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000106/2023-2024 | 1167/MURD/2 | 28/04/2023 | 0 | Resource Division | 3.11 | 0 | 0
3327 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Kuchiadanga under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000055/2023-2024 | 152/BD-I | 15/05/2023 | 90 | ANUPA ENTERPRISE | 22.59 | 0 | 0
3328 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kuchidanga village, Block:- Lalgola under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000685/2023-2024 | 3614/MEDB | 03/11/2023 | 92 | AVINABA ENGINEERING CONCERN | 6.26 | 0 | 0
3329 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
3330 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, FHTC, construction of OHR (Capacity 300 & 400 cum), Sinking of Tube Well , and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of MAHADEBNAGAR ZONE- IA,IB,IC ,IIA & IIB PWSS in Farakka Block, Murshidabad District under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000790/2023-2024 | 441/MURD | 08/02/2024 | 693 | MACKINTOSH BURN LIMITED | 1715.31 | 0 | 36
3331 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
3332 | Murshidabad Division | Berhampur M/E Division | BAJITPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Raghunathganj-II Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000011/2023-2024 | 959/MURD | 05/04/2023 | 850 | CHABDAR ALI TRADERS | 233.79 | 32.6 | 85
3333 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 3.11 | 100
3334 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | RTOR000275/2023-2024 | 1230/MURD/18 | 04/05/2023 | 0 | Resource Division | 29.58 | 0 | 0
3335 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | RTOR000377/2023-2024 | 495/MURD/04 | 15/02/2024 | 0 | Resource Division | 5.54 | 0 | 0
3336 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
3337 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for BAJITPUR PIPED WATER SUPPLY SCHEME. District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000555/2024-2025 | 337/MEDB | 10/02/2025 | 323 | M/S SAJAHAN CHOWDHURY | 21.38 | 0 | 60
3338 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 7.66 | 11
3339 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Katalia" ground water supply scheme in Berhampore Block, under Berhampore Division-I, P.H.E Dte. (Capacity-36 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-II | ORD/000037/2024-2025 | 1000/BD-I | 20/06/2024 | 365 | ACQUA CONSTRUCTION CONSORTIUM | 147.9 | 0 | 0
3340 | Berhampore Division I | Berhampur Division I | KATALIA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-II | ORD/000103/2023-2024 | 221/BD-I | 17/05/2023 | 865 | NURUL HASAN BISWAS | 52.76 | 0 | 66
3341 | Berhampore Division I | Berhampur Division I | KATALIA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-II | ORD/000160/2023-2024 | 685/BD-I | 10/08/2023 | 870 | C.X.CONSTRUCTION & CO. | 259.02 | 0 | 30
3342 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-II | RTOR000026/2023-2024 | 61/BD-1/20 | 27/04/2023 | 0 | Resource Division | 15.38 | 0 | 0
3343 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-II | RTOR000026/2024-2025 | 2096/BD-I/7 | 25/11/2024 | 0 | Resource Division | 8.46 | 0 | 0
3344 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 11.82 | 20
3345 | Berhampore Division I | Berhampur Division I | KULGACHI PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000089/2023-2024 | 212/BD-I | 17/05/2023 | 630 | NATIONAL CONSTRUCTION | 36.84 | 13.92 | 85
3346 | Berhampore Division I | Berhampur Division I | KULGACHI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 200 cum) under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000098/2023-2024 | 111/BD-I | 10/05/2023 | 963 | RAJ KUMAR MONDAL | 251.46 | 61.48 | 20
3347 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000045/2023-2024 | 61/BD-1/29 | 27/04/2023 | 0 | Resource Division | 12.73 | 0 | 0
3348 | Berhampore Mechanical | Berhampur Division I | KULGACHI PWSS | Assistant Engineer-I | JE,Junior engineer-III | BILL/01454/2023-2024 | 346/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 3.25 | 0 | 0
3349 | Murshidabad Division | Kandi Sub-Division | Allied work for road restoration work liable to be damaged due to pipeline laying at Parbotipur PWSS under Kandi sub-Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000037/2024-2025 | 1912/MURD | 02/07/2024 | 60 | DIPAK KUMAR GHOSH | 42.14 | 0 | 100
3350 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW- III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PARBATIPUR AND ADJOINING MOUJAS Water Supply Scheme at 3rd Site site at KANDI Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000402/2023-2024 | 2821/MURD | 07/09/2023 | 421 | INDRAJIT MAZUMDAR | 9.22 | 0 | 100
3351 | Murshidabad Division | Kandi Sub-Division | Formal work order for PARBATIPUR & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- KANDI of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000818/2022-2023 | 675/MURD | 09/03/2023 | 1029 | DIPAK KUMAR GHOSH | 467.48 | 102.08 | 25
3352 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000080/2023-2024 | 1129/MURD/3 | 25/04/2023 | 0 | Resource Division | 15.8 | 0 | 0
3353 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000339/2023-2024 | 79/MURD/06 | 09/01/2024 | 0 | Resource Division | 12.55 | 0 | 0
3354 | Berhampore Mechanical | Kandi Sub-Division | Service connection charge for Parbbatipur SM/ 16393 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01093/2023-2024 | 200/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 19.26 | 0 | 0
3355 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PARBATIPUR PH II, ID304236105 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01210/2023-2024 | 293/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 3.28 | 0 | 0
3356 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Parbbatipur ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000275/2023-2024 | 3715/MEDB | 03/11/2023 | 790 | M/S SAJAHAN CHOWDHURY | 23.87 | 19.75 | 15
3357 | Murshidabad Division | Kandi Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at, Dakshinkhanda Zone-IA T.W-II, III, Zone-IB T.W-II, Dakshinkhanda Zone-II T.W- I, II Water Supply Scheme of Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000506/2024-2025 | 718/MURD | 25/03/2025 | 65 | MAMATA USHA ENTERPRISE | 58.95 | 0 | 0
3358 | Murshidabad Division | Kandi Sub-Division | Augmentation of DAKSHIN KHANDA (ZONE -IB) PWSS under Jal Jeevan Mission of Bharatpur Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000559/2023-2024 | 3220/MURD | 13/10/2023 | 866 | J.S. CONSTRUCTION | 475 | 0 | 25
3359 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
3360 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 11.06 | 20
3361 | Berhampore Division I | Berhampur M/E Division | KESABPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000081/2023-2024 | 199/BD-I | 17/05/2023 | 951 | AZAD ENTERPRISE | 40.95 | 13.45 | 20
3362 | Berhampore Division I | Berhampur M/E Division | KESABPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main , Construction of OHR (Capacity - 200 cum ) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000172/2023-2024 | 664/BD-I | 09/08/2023 | 784 | D.N SARKAR AND SONS | 294.7 | 48.86 | 30
3363 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000043/2023-2024 | 61/BD-1/31 | 27/04/2023 | 0 | Resource Division | 15.38 | 0 | 0
3364 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000111/2023-2024 | 304/BD-1/2 | 22/02/2024 | 0 | Resource Division | 7.74 | 0 | 0
3365 | Berhampore Mechanical | Berhampur M/E Division | KESABPUR PH-1 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/01517/2023-2024 |  | 28/02/2024 | 0 | WBSEDCL | 6.22 | 0 | 0
3366 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION KESABPUR PH-1 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/01606/2023-2024 | 425/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 6.22 | 0 | 0
3367 | Murshidabad Division | Kandi Sub-Division | Providing FHTC Connection to 510 nos household , Laying of Distribution System, Rising Main ,Construction of Boundary Wall and Pump House with sanitary and Water Supply Arrangement & Construction Pump House cum Blower room cum Chlorine room with out sanitary and Water Supply Arrangement RANAGRAM PWSS KANDI Block under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000244/2023-2024 | 2432/MURD | 08/08/2023 | 180 | R.R. CONSTRUCTION | 70.39 | 0 | 30
3368 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | RTOR000028/2023-2024 | 1129/MURD | 25/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
3369 | Central Drilling | Kandi Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000209/2023-2024 | 2203/CDD | 01/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 7.59 | 10
3370 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT RANAGRAM PH I, ID304236076 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | BILL/01211/2023-2024 | 271/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 8.48 | 0 | 0
3371 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Ranagram ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000257/2023-2024 | 3693/MEDB | 03/11/2023 | 92 | B. T. PROJECTS PVT. LTD. | 21.24 | 0 | 0
3372 | Murshidabad Division | Kandi Sub-Division | BABARPUR PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000151/2023-2024 | 1899/MURD | 17/07/2023 | 120 | DIPAYAN DEY | 157.25 | 85.18 | 40
3373 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000075/2023-2024 | 1075/MURD/17 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
3374 | Central Drilling | Kandi Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000209/2023-2024 | 2203/CDD | 01/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 10
3375 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT BABARPUR PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01592/2023-2024 | 430/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 4.31 | 0 | 0
3376 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Piped Water Supply Scheme for BABARPUR AND ADJOINING MOUJAS PWSS Block Burwan of Murshidabad District under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000544/2024-2025 | 330/MEDB | 10/02/2025 | 89 | M/S G.P. ENTERPRISE | 21.38 | 0 | 0
3377 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System, Rising Main, FHTC, Repairing of Boundary Wall, Pump House & Existing OHR for Augmentation of Bhalkundi Zone-III Water at Supply Scheme in Khargram Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000028/2023-2024 | 1077/MURD | 19/04/2023 | 681 | SUJIT KUMAR SAHA | 162.99 | 59.72 | 30
3378 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhalkundi Zone-III & adjoining mouzas Water Supply Scheme at 3rd work site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000033/2023-2024 | 1108/MURD | 24/04/2023 | 20 | SARKAR WATER SUPPLY AGENCY | 10.67 | 0 | 100
3379 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
3380 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 3.06 | 76
3381 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000064/2022-2023 | 1043/MURD/5 | 17/04/2023 | 0 | Resource Division | 0.69 | 0 | 0
3382 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-III under BHALKUNDI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000678/2023-2024 | 3850/MEDB | 06/11/2023 | 92 | S. K. ENTERPRISE | 22.8 | 19.42 | 70
3383 | Murshidabad Division | Berhampur M/E Division | CHANDMARI , BAHUTALI & FATELLAPUR PWSS to accommodate FHTC under Jal Jeevan Mission, Block- SUTI-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000287/2023-2024 | 3176/MURD | 11/10/2023 | 813 | CHAKRABORTY CONSTRUCTION | 2258.18 | 0 | 10
3384 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 6.44 | 100
3385 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under FATELLAPUR(CT) ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000461/2023-2024 | 3864MEDB | 07/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 23.02 | 0 | 0
3386 | Central Drilling | Berhampur M/E Division | Continuation for Hiring of Diesel driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000057/2024-2025 | 238/S&WSD | 24/12/2024 | 182 | NAGENDRA PATRA | 0.86 | 0 | 0
3387 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 14.36 | 20
3388 | Berhampore Division I | Berhampur M/E Division | BAYRA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000118/2023-2024 | 512/BD-I | 25/07/2023 | 885 | SRIJON ENTERPRISE | 244.14 | 0 | 30
3389 | Berhampore Division I | Berhampur M/E Division | Designing, making and errection of Display Board for Scheme information by using Logo and tag line of Jal Jeevan Mission at different PWSS work sites in the district of Murshidabad under Berhampore Division-I, PHE Dte. (Block :- Raninagar - I, Raninagar - II, Beldanga - I, Beldanga - II, Jalangi & Nowda) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000134/2024-2025 | 1532/BD-I | 19/09/2024 | 30 | SUMAN ENTERPRISE AND SUMAN AQUA | 18.91 | 0 | 54
3390 | Berhampore Division I | Berhampur M/E Division | BAYRA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000137/2023-2024 | 620/BD-I | 03/08/2023 | 548 | RAJEN DAS | 55.72 | 0 | 50
3391 | Berhampore Division I | Berhampur M/E Division | BAYRA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000147/2023-2024 | 634/BD-I | 04/08/2023 | 1095 | M/S GHOSH AND CO | 383.82 | 0 | 50
3392 | Berhampore Division I | Berhampur M/E Division | BAYRA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte.. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000341/2023-2024 | 1255/BD-I | 22/12/2023 | 445 | MASOOM TRADERS | 61.36 | 0 | 30
3393 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAYRA PWSS(TW-I&II) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000378/2024-2025 | 438/BD-I | 20/03/2025 | 30 | HARUN ALL RASHID & BROTHERS | 17.97 | 0 | 0
3394 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000097/2023-2024 | 201/BD-1/26 | 10/02/2024 | 0 | Resource Division | 39.6 | 0 | 0
3395 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000109/2023-2024 | 304/BD-1/6 | 22/02/2024 | 0 | Resource Division | 24.04 | 0 | 0
3396 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION BAYRA PH-1 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/01513/2023-2024 | 388/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 6.05 | 0 | 0
3397 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BAYRA ground water based water supply scheme under Block_LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/001433/2023-2024 | 4313/MEDB | 29/12/2023 | 91 | HARA PROSAD DAS | 33.24 | 0 | 0
3398 | Murshidabad Division | Kandi Sub-Division | BHATPARA & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte.( Scheme ID -PH222362289S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000193/2023-2024 | 1989/MURD | 21/07/2023 | 365 | ASTRA | 789.69 | 0 | 0
3399 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000033/2023-2024 | 1043/MURD/3 | 17/04/2023 | 0 | Resource Division | 208.28 | 0 | 0
3400 | Berhampore Mechanical | Kandi Sub-Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BHATPARA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/001505/2023-2024 | 592/MEDB | 31/01/2024 | 90 | HANNAN BUILDERS PVT LTD | 36.83 | 0 | 0
3401 | Murshidabad Division | Berhampur M/E Division | UMARPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000206/2023-2024 | 2290/MURD | 01/08/2023 | 730 | CHAKRABORTY CONSTRUCTION | 916.93 | 52.63 | 10
3402 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UMARPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000277/2023-2024 | 2606/MURD | 22/08/2023 | 21 | INDRAJIT MAZUMDAR | 27.66 | 0 | 70
3403 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 12.12 | 100
3404 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000282/2023-2024 | 1230/MURD/24 | 04/05/2023 | 0 | Resource Division | 132.07 | 0 | 0
3405 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000379/2023-2024 | 495/MURD/02 | 15/02/2024 | 0 | Resource Division | 31.56 | 0 | 0
3406 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION UMRAPUR PH-III | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/00168/2024-2025 | 6/WBSEDCL-JJM | 09/04/2024 | 0 | WBSEDCL | 3.49 | 0 | 0
3407 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION UMRAPUR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/00169/2024-2025 | 7/WBSEDCL-JJM | 09/04/2024 | 0 | WBSEDCL | 3.73 | 0 | 0
3408 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION UMRAPUR PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/00170/2024-2025 | 8/WBSEDCL-JJM | 09/04/2024 | 0 | WBSEDCL | 3.5 | 0 | 0
3409 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION UMRAPUR PH-III | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01658/2023-2024 |  | 27/03/2024 | 0 | WBSEDCL | 3.49 | 0 | 0
3410 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION UMRAPUR PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01659/2023-2024 |  | 27/03/2024 | 0 | WBSEDCL | 3.5 | 0 | 0
3411 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION UMRAPUR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01660/2023-2024 |  | 27/03/2024 | 0 | WBSEDCL | 3.73 | 0 | 0
3412 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under UMARPUR ground water based water supply scheme under Block_ Suti_II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000456/2023-2024 | 3852/MEDB | 06/11/2023 | 92 | SURAKSHA | 34.47 | 27.47 | 10
3413 | Murshidabad Division | Berhampur M/E Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000001/2025-2026 | 761/MURD | 02/04/2025 | 80 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0
3414 | Murshidabad Division | Berhampur M/E Division | BHABKI PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- SUTI-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000224/2023-2024 | 2368/MURD | 04/08/2023 | 606 | B.B.R.C. INFRASTRUCTURE PVT. LTD. | 495.36 | 0 | 12
3415 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 6.55 | 100
3416 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000276/2023-2024 | 1230/MURD/18 | 04/05/2023 | 0 | Resource Division | 33.71 | 0 | 0
3417 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000371/2023-2024 | 495/MURD/10 | 15/02/2024 | 0 | Resource Division | 13.53 | 0 | 0
3418 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 8 | 11
3419 | Berhampore Mechanical | Berhampur M/E Division | BHABKI PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01441/2023-2024 | 334/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 7.72 | 0 | 0
3420 | Berhampore Mechanical | Berhampur M/E Division | BHABKI PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01442/2023-2024 | 335/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 6.55 | 0 | 0
3421 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 7.79 | 20
3422 | Berhampore Division I | Berhampur M/E Division | PAIKPARA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000144/2023-2024 | 631/BD-I | 04/08/2023 | 970 | H.I ENTERPRISE | 440.19 | 98.29 | 17
3423 | Berhampore Division I | Berhampur M/E Division | PAIKPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000145/2023-2024 | 632/BD-I | 04/08/2023 | 720 | SRIJON ENTERPRISE | 240.5 | 148.76 | 15
3424 | Berhampore Division I | Berhampur M/E Division | PAIKPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000146/2023-2024 | 633/BD-I | 04/08/2023 | 180 | NIRMAL UDYOG | 116.86 | 25.85 | 20
3425 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PAIKPARA Water Supply Scheme(2nd & 3rd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000328/2024-2025 | 274/BD-I | 11/02/2025 | 30 | NADIA TUBEWELLS | 17.99 | 0 | 0
3426 | Berhampore Division I | Berhampur M/E Division | PAIKPARA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000342/2023-2024 | 1256/BD-I | 22/12/2023 | 90 | SATELLITE CONSTRUCTION | 67.11 | 0 | 0
3427 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000099/2023-2024 | 201/BD-1/28 | 10/02/2024 | 0 | Resource Division | 66.86 | 0 | 0
3428 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000113/2023-2024 | 304/BD-1/3 | 22/02/2024 | 0 | Resource Division | 27.92 | 0 | 0
3429 | Berhampore Mechanical | Berhampur M/E Division | PAIKPARA PH-1 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/01518/2023-2024 | 387/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 3.3 | 0 | 0
3430 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 0 | 100
3431 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Barabil Raghunathpur zone-II PWSS to accommodate FHTC of 176 nos household, Laying Distribution System, Laying Rising Main. at Jalangi Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-A) | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000472/2023-2024 | 3030/MURD | 27/09/2023 | 606 | PRADIP KUMAR DAS (PROPRIETORSHIP) | 1039.97 | 107.6 | 90
3432 | Murshidabad Division | Berhampur M/E Division | Augmentation of Barabil Raghunathpur Zone-II PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 1no, Construction of Boundary Wall of 200 m, Construction of 400 Cum OHR(1 no) with sub soil investigation , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works, Repair of Boundary Wall at T/W-I site & T/W-II site &Overhauling of R.C.C. elevated reservoir 450 Cum capacity of staging hight 20 mtr under Jal Jeevan Mission of Jalangi Block, Murshidabad District under Murshidabad Division, PHE.Dte. (Part-B) | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000590/2023-2024 | 3332/MURD | 23/10/2023 | 766 | ORKID CONSTRUCTION | 217.95 | 0 | 50
3433 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000172/2023-2024 | 1180/MURD/22 | 29/04/2023 | 0 | Resource Division | 290.13 | 0 | 0
3434 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT BARABIL RAGHUNATHPUR PWSS JL 37 PLOT NO 171 ID 304238695 | ASSISTANT ENGINEER-I | Junior engineer-II | BILL/01270/2023-2024 | 290/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 4.27 | 0 | 0
3435 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under Barabil Raghunathpur ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000658/2023-2024 | 3699/MEDB | 09/08/2023 | 92 | R.N.S. TRADING | 23.69 | 0 | 0
3436 | Murshidabad Division | Berhampur M/E Division | Paschim Purnopara Zone - II PWSS to accommodate Laying Distribution System & Laying Rising Main under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (Part-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000480/2023-2024 | 3051/MURD | 29/09/2023 | 477 | SOFIQUL ISLAM | 293.57 | 0 | 0
3437 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000497/2024-2025 | 660/MURD | 19/03/2025 | 90 | JOY GURU ENTERPRISE | 82.5 | 0 | 0
3438 | Murshidabad Division | Berhampur M/E Division | Paschim Purnopara Zone - II PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (part C) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000573/2023-2024 | 3297/MURD | 20/10/2023 | 180 | M H SUPPLIERS | 305.91 | 0 | 0
3439 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 13.19 | 100
3440 | Murshidabad Division | Berhampur M/E Division | Paschim Purnopara Zone - II PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 2 nos, Construction of Boundary Wall of 220 m, Construction 1000 Cum OHR with sub soil investigation Jal Jeevan Mission of Suti-II Block, Murshidabad. . (Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000578/2023-2024 | 3314/MURD | 22/10/2023 | 680 | M/S. A.T.D. PROJECTS | 364.02 | 0 | 15
3441 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
3442 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01242/2024-2025 |  | 13/12/2024 | 0 | WBSEDCL | 7.82 | 0 | 0
3443 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01243/2024-2025 |  | 13/12/2024 | 0 | WBSEDCL | 10.75 | 0 | 0
3444 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-III | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01244/2024-2025 |  | 13/12/2024 | 0 | WBSEDCL | 7.42 | 0 | 0
3445 | Murshidabad Division | Berhampur M/E Division | SAHAJADPUR CT PWSS to accommodate FHTC, Laying Rising Main , OHR as per Departmental type design (Ref :- DRG.No. PC/-I/OHR/17/2012), 4 Nos Pump House, Boundary Wall (5Nos Site) , Approach Road (5Nos Site) & FHTC of SAHAJADPUR CT PWSS at RAGHUNATHGANJ-II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000228/2023-2024 | 2402/MURD | 07/08/2023 | 365 | NAYLA CONSTRUCTION | 353.57 | 0 | 0
3446 | Murshidabad Division | Berhampur M/E Division | SAHAJADPUR CT PWSS to accommodate FHTC, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jeevan Mission of Raghunathganj-II Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000229/2023-2024 | 2401/MURD | 07/08/2023 | 782 | M/S.TAPAS KUMAR CHAKRABORTY | 499.42 | 28.94 | 5
3447 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAHAJADPUR (CT) Water Supply Scheme at Head Work Site, 2nd Site site at Raghunathganj - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000398/2023-2024 | 2796/MURD | 04/09/2023 | 21 | M. R. ENTERPRISE | 18.53 | 0 | 0
3448 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 13.06 | 100
3449 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | RTOR000290/2023-2024 | 1230/MURD/31 | 04/05/2023 | 0 | Resource Division | 65.31 | 0 | 0
3450 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II , III ,IV ,V & VI under SAHAJADPUR(CT) ground water based water supply scheme under Block_ Raghunathganj-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000460/2023-2024 | 3863/MEDB | 07/11/2023 | 664 | ORIENTAL ENGINEERING CO. | 67.07 | 0 | 25
3451 | Murshidabad Division | Kandi Sub-Division | BHARWAN (Part-A) & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000175/2023-2024 | 1991/MURD | 21/07/2023 | 365 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 389 | 0 | 25
3452 | Murshidabad Division | Kandi Sub-Division | BHARWAN (Part-B) & adjoining mouzas PWSS to accommodate Of LDS, and FHTC, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000189/2023-2024 | 1990/MURD | 21/07/2023 | 180 | M/S. S. DAS AND ENTERPRISE | 672.95 | 358.69 | 40
3453 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.01 | 80
3454 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000024/2023-2024 | 1210/MURD/36 | 02/05/2023 | 0 | Resource Division | 27.73 | 0 | 0
3455 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BHARWAN ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000713/2023-2024 | 4066/MEDB | 04/12/2023 | 91 | WEST BENGAL ENGINEERING CO. | 25.76 | 0 | 0
3456 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia 2nos. Rig Bore Tube Well With Pumphouse of Mouza Radhakrishnapur, Malatipur, Khalifabaj, Sahabazpur, Paharpur, Krishnapur (314148,314149,314150,314151,314153),of Lalgola and Brindabanpur Zone - I PWSS under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000132/2022-2023 | 1202/MURD | 10/05/2022 | 60 | M/S GUHA & ROY ENTERPRISE | 30.54 | 0 | 0
3457 | Murshidabad Division | Berhampur M/E Division | Augmentation of BRINDABANPUR Zone-I Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000273/2023-2024 | 2607/MURD | 22/08/2023 | 741 | J.S. CONSTRUCTION | 288.62 | 121.98 | 10
3458 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 2.83 | 100
3459 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000262/2023-2024 | 1230/MURD/03 | 04/05/2023 | 0 | Resource Division | 20.39 | 0 | 0
3460 | Murshidabad Division | Berhampur M/E Division | CHARKA PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Raghunathganj-I Block, Jangipur Sub Division of Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000199/2023-2024 | 2058/MURD | 27/07/2023 | 280 | DECON INDIA | 482.22 | 0 | 0
3461 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 6.39 | 100
3462 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | RTOR000269/2023-2024 | 1230/MURD/13 | 04/05/2023 | 0 | Resource Division | 33.69 | 0 | 0
3463 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under CHARKA ground water based water supply scheme under Block_ Raghunathganj-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000680/2023-2024 | 4302/MEDB | 29/12/2023 | 91 | DEBJYOTI BASU | 33.53 | 0 | 0
3464 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tubewell i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at P.T RASULPUR (PART - A), Kupila and Baniakhali Water Supply Scheme at DOMKAL Block under Murshidabad Division,P.H. Engineering Dte | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000107/2023-2024 | 1749/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 0 | 40
3465 | Murshidabad Division | Berhampur M/E Division | Augmentation BANIAKHALI PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part -A) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000312/2023-2024 | 2676/MURD | 24/08/2023 | 1317 | J.S. CONSTRUCTION | 459.33 | 0 | 40
3466 | Murshidabad Division | Berhampur M/E Division | Augmentation of BANIAKHALI PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (Part-B) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000313/2023-2024 | 2677/MURD | 24/08/2023 | 600 | AEF ENTERPRISE (PROP: MAHBUB AKHTAR) | 222.14 | 29.46 | 20
3467 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold Tap Connection of 03(Three) nos existing commisioned PWSS Domkol Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Katakopra Water Supply Scheme Zone-I & II, Bhagarpur Ramna Water Supply Scheme,Baniakhali & Its Adjoining Mouzas Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000345/2022-2023 | 1924/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.09 | 0 | 100
3468 | Murshidabad Division | Berhampur M/E Division | Providing Functional Household Tap Connections ( 665 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Manik Nagar (Village Code -314694) under Domkol Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000637/2023-2024 | 3458/MURD | 06/11/2023 | 30 | MOLLA ENTERPRISE (REHENA BIBI) | 18.71 | 0 | 0
3469 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000147/2023-2024 | 1167/MURD/37 | 28/04/2023 | 0 | Resource Division | 153.51 | 0 | 0
3470 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT BANIAKHALI Z-II PH-I | ASSISTANT ENGINEER-I | Junior engineer-III | BILL/01108/2024-2025 |  | 14/11/2024 | 0 | WBSEDCL | 6.74 | 0 | 0
3471 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT BANIAKHALI Z-II PH-II | ASSISTANT ENGINEER-I | Junior engineer-III | BILL/01109/2024-2025 |  | 14/11/2024 | 0 | WBSEDCL | 5.03 | 0 | 0
3472 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Baniakhali Piped Water Supply Scheme District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000563/2024-2025 | 345/MEDB | 10/02/2025 | 89 | M/S S. S. ENTERPRISE (DOMKAL) | 21.24 | 0 | 10
3473 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 20.72 | 11
3474 | Central Drilling | Berhampur M/E Division | Hiring of Diesel Driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Mech./Elect. Planning Wing, P.H.E. Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000013/2024-2025 | 136/S&WSD | 24/06/2024 | 184 | NEMAI CHANDRA NAIYA | 0.87 | 1.36 | 0
3475 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of PALITPARA PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000009/2025-2026 | 596/BD-I | 22/04/2025 | 60 | S.K CONSTRUCTION (SUDIP KUMAR SANYAL) | 19 | 0 | 0
3476 | Berhampore Division I | Berhampur M/E Division | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Palitpara" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-111 Cum/hr.) Type-1 - Fully Gravity System with RG Filter | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000034/2024-2025 | 998/BD-I | 20/06/2024 | 730 | M/S GOUTAM CHAKRABORTY | 257.77 | 0 | 0
3477 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of PALITPARA PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000037/2025-2026 | 666/BD-I | 29/04/2025 | 60 | INDIAN TRADING CORPORATION | 19 | 0 | 0
3478 | Berhampore Division I | Berhampur M/E Division | PALITPARA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000173/2023-2024 | 686/BD-I | 10/08/2023 | 730 | SUJIT KUMAR SAHA | 401.71 | 0 | 55
3479 | Berhampore Division I | Berhampur M/E Division | PALITPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000174/2023-2024 | 687/BD-I | 10/08/2023 | 180 | BANIK BROTHERS | 89.01 | 0 | 0
3480 | Berhampore Division I | Berhampur M/E Division | PALITPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000178/2023-2024 | 688/BD-I | 10/08/2023 | 180 | M/S AMIT KUMAR GUPTA | 167.04 | 0 | 0
3481 | Berhampore Division I | Berhampur M/E Division | PALITPARA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000188/2023-2024 | 736/BD-I | 16/08/2023 | 716 | S.K CONSTRUCTION (SUDIP KUMAR SANYAL) | 72.82 | 0 | 40
3482 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000022/2024-2025 | 2096/BD-I/3 | 25/11/2024 | 0 | Resource Division | 27.02 | 0 | 0
3483 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000103/2023-2024 | 201/BD-1/2 | 10/02/2024 | 0 | Resource Division | 56.21 | 0 | 0
3484 | Murshidabad Division |  | Rail Bhoomi Crossing Seva (IR-RBCS) Eastern Railway Howrah Division DEMAND NOTE Application ID: ER-HWH-2024-WL-64 |  |  | BILL/01535/2024-2025 | 545-MSD/2024-25 | 28/10/2024 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 0.11 | 0 | 0
3485 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) 492 nos in connection with Jal Swapna (Jal Jeevan Mission ) of Mouza Sikdarpur ( Village Code -313858) under Sikdarpur & adjoining mouzas Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000049/2022-2023 | 1115/MURD | 29/04/2022 | 30 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 26.22 | 10.34 | 0
3486 | Murshidabad Division |  | Work of Laying of U.P.V.C. Pipe line at Sikdarpur Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. |  |  | ORD/002103/2021-2022 | 387 /JSD | 31/12/2021 | 30 | DEBOJYOTI CONSTRUCTION | 4.63 | 4.63 | 1
3487 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 540/3/MURD | 25/02/2022 | 0 | Resource Division | 2.7 | 0 | 0
3488 | Murshidabad Division |  | Continuation work order for Hiring of 1 no of Car for official use of the eAE LSD PHE DTE. Work Order No 261 / LSD DATE 04.03.2021 |  |  | VCH/000598/2022-2023 | 202-MSD/2022-23 | 07/07/2022 | 0 | ARINDAM MAJUMDAR | 1.08 | 0 | 0
3489 | Murshidabad Division |  | work order for Hiring of 1 no of Car for official use of the SE MC PHE DTE. Work Order No 10 / MC. DATE 05.01.2022 |  |  | VCH/000599/2022-2023 | 203-MSD/2022-23 | 07/07/2022 | 0 | HASNA BEWA | 0.62 | 0 | 0
3490 | Murshidabad Division |  | Work order for Hiring of 1 no of Car for official use of the AE JSD PHE DTE. Work Order No 302 / JSD. DATE 25.11.2021 |  |  | VCH/000638/2022-2023 | 205-MSD/2022-23 | 08/07/2022 | 0 | MANUAR HOSSAIN | 1.19 | 0 | 0
3491 | Murshidabad Division |  | Work order for Hiring of 1 no of Car for official use of the AE ISD PHE DTE. Work Order No 473 / ISD. DATE 03.09.2021 |  |  | VCH/000641/2022-2023 | 206-MSD/22-23 | 12/07/2022 | 0 | M/S SAJAHAN CHOWDHURY | 0.78 | 0 | 0
3492 | Murshidabad Division |  | HIRING OF CAR FOR SE-MC |  |  | VCH/001016/2022-2023 | 358-MSD/22-23 | 19/10/2022 | 0 | HASNA BEWA | 0.6 | 0 | 0
3493 | Murshidabad Division |  | CONTINUATION ORDER OF CAR HIRING OF AE-LSD 261/LSD DATE- 04/03/2021 |  |  | VCH/001017/2022-2023 | 359-MSD/22-23 | 19/10/2022 | 0 | ARINDAM MAJUMDAR | 0.61 | 0 | 0
3494 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Gobindapur (Village Code -314687) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) |  |  | ORD/000140/2021-2022 | 1615/MURD | 28/06/2021 | 60 | BISWAS CONSTRUCTION | 27.63 | 48.73 | 0
3495 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mamudpur ( Village Code -314685) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) |  |  | ORD/000335/2021-2022 | 2438/MURD | 12/08/2021 | 60 | JOY BISHNU ENGINEERING CO. | 28.13 | 21.24 | 0
3496 | Murshidabad Division |  | Construction of P.C.C approach road at Head work site of Juginda Zone-I Water Supply Scheme under Domkal Block within Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000796/2021-2022 | 477/ISD | 03/09/2021 | 30 | M/S SAJAHAN CHOWDHURY | 1.62 | 1.62 | 1
3497 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahebnagar (village code 314609) under KAZIPARA (Part-A) Ground water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000747/2021-2022 | 2207/BD-I | 10/12/2021 | 90 | SRIJON ENTERPRISE | 61.97 | 0 | 0
3498 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Nowda Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723172 in the District of Murshidabad. |  |  | ORD/000169/2021-2022 | 1652/MURD | 29/06/2021 | 180 | HARAPRASAD DAS | 75.04 | 115.84 | 100
3499 | Murshidabad Division |  | Providing Balance Functional Household Tap Connection (FHTC) of 462 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/001810/2021-2022 | 802/MURD | 24/03/2022 | 30 | M/S. UNIQUE BUILDERS | 29.37 | 35.83 | 1
3500 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000024/2021-2022 | 539/9/MURD | 25/02/2022 | 0 | Resource Division | 2.54 | 0 | 0
3501 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MAHAMMADPUR (Village Code 315549) under MAHAMMADPUR Ground Water Based Water Supply Scheme for arsenic affected areas of BERHAMPORE Block in the District of Murshidabad. Tender no - 04 of 20-21 by SE MC |  |  | VCH/001477/2021-2022 | 384-MSD/21-22 | 19/03/2022 | 0 | HARAPRASAD DAS | 16.56 | 0 | 0
3502 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rampara Foridpur (Village code 315664) under Rampara Foridpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-II | Junior Engineer-II | ORD/000112/2020-2021 | 184/BD-I | 04/02/2021 | 30 | DOBAY CONSTRUCTION | 98.77 | 70.91 | 1
3503 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Rampara Foridpur (Village code-315664) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Rampara Foridpur Ground water based Water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-II | Junior Engineer-II | ORD/000794/2021-2022 | 2310/BD-I | 29/12/2021 | 45 | BENOY DOBEY | 15.18 | 0 | 0
3504 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Goukhana and Others under Goukhana Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000112/2021-2022 | 914/BD-I | 19/05/2021 | 7 | N.H ENTERPRISE | 3.62 | 6.32 | 0
3505 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramna Bagsarai (Village code 314160) under Gaukhana Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000190/2020-2021 | 960/BD-I | 17/12/2020 | 60 | S.ENTERPRISE | 8.24 | 0 | 0
3506 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Deoan Sarai (Village code 314161) under Gaukhana Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000191/2020-2021 | 961/BD-I | 17/12/2020 | 90 | SAMBHUNATH ROY | 30.8 | 30.75 | 1
3507 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gaukhana (Village code 314162) under Gaukhana Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000192/2020-2021 | 972/BD-I | 17/12/2020 | 60 | N.H ENTERPRISE | 12.91 | 18.53 | 100
3508 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Laskarpur (Village code 314167) under Gaukhana Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000193/2020-2021 | 973/BD-I | 17/12/2020 | 60 | SUSHANTA MANDAL | 11.01 | 10.4 | 1
3509 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramna Bagsarai and Others under Gaukhana Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000210/2020-2021 | 277/BD-I | 15/02/2021 | 10 | S.ENTERPRISE | 2.73 | 0 | 0
3510 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raipur (Village code 315460) under Raipur (Zone-D) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-04) | Assistant Engineer-II | Junior Engineer-II | ORD/000270/2021-2022 | 1141/BD-I | 07/07/2021 | 180 | M/S JOYDEEP DASGUPTA | 79 | 73.28 | 1
3511 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-II | Junior Engineer-II | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 1
3512 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Masurdanga ( village code 315464 ) under RAIPUR ( Zone - D ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000463/2021-2022 | 1838/BD-I | 05/10/2021 | 70 | NIRMAL UDYOG | 62.56 | 0 | 0
3513 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jitarpur (village code 315461) , Harishpur (village code 315462) , Khosalpur ( village code 315463 ) , under RAIPUR ( Zone - D ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000465/2021-2022 | 1837/BD-I | 05/10/2021 | 70 | HOQUEDAR ALI | 61.23 | 41.59 | 1
3514 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nasipur ( village code 315482 ) under RAIPUR ( Zone - D ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000466/2021-2022 | 1839/BD-I | 05/10/2021 | 40 | PARTHA PRATIM DAS | 35.44 | 0 | 0
3515 | Berhampore Division I | Berhampur Division I | Laying of additional extension and parallel pipe line at Mamdalipur,Raipur and Sadananpur village due to smooth functioning of Functional Household Tap Connection (FHTC) at RAIPUR Surface Water based Water Supply Scheme of Central Sector Part - II of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000494/2021-2022 | 1881/BD-I | 07/10/2021 | 90 | M/S JOYDEEP DASGUPTA | 36.18 | 32.68 | 1
3516 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dasturpara (Village code 315484) under Raipur (Zone-D) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE.Dte. (Sl-03) | Assistant Engineer-II | Junior Engineer-II | ORD/000559/2021-2022 | 1891/BD-I | 07/10/2021 | 180 | M/S S.DAS & ENTERPRISE | 75.05 | 63.52 | 1
3517 | Berhampore Division I | Berhampur Division I | Relaying of different dia DI and UPVC distribution Pipe Line instead of damage portion in between different node point for faciliating FHTC works under Raipur Surface based Water Supply Scheme under Central Sector Part-II of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000561/2021-2022 | 1989/BD-I | 01/11/2021 | 30 | DEBASIS BOSE | 31.04 | 0 | 0
3518 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bainpur, Balarampur, Khalshi, Saharbasa, Mamlatpur, Chhota Saharbasa, Hosenpur, Jamira, Fatepur-Gobindapur & Kumipur Patharghata (Village code 315454, 315455, 315456, 315457, 315458, 315459, 315485, 315486, 315487 & 315488) under Raipur (Zone-D) Water Supply Scheme of Central Sector Part-II in Hariharpara Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-08) | Assistant Engineer-II | Junior Engineer-II | ORD/000585/2021-2022 | 2012/BD-I | 08/11/2021 | 180 | SANJAY BISWAS | 130.03 | 89.24 | 85
3519 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Raipur Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-II | Junior Engineer-II | ORD/000775/2021-2022 | 2255/BD-I | 21/12/2021 | 90 | M/S GHOSH ENTERPRISE | 77.39 | 75.21 | 1
3520 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hariharpara, Bochadanga, & Gobindapur (Village code 315483, 315452 & 315453) under RAIPUR (Zone-D) Water Supply Scheme of Central Sector Part-II inHariharpara of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000845/2021-2022 | 101/BD-I | 01/02/2022 | 180 | J.D.J ENTERPRISE | 246.75 | 0 | 0
3521 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-II | RTOR000001/2021-2022 | 62/BD-I | 27/01/2022 | 0 | Resource Division | 7.67 | 0 | 0
3522 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-II | RTOR000004/2021-2022 | 70/BD-I | 28/01/2022 | 0 | Resource Division | 2.48 | 0 | 0
3523 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-II | RTOR000028/2024-2025 | 2096/BD-I/9 | 25/11/2024 | 0 | Resource Division | 24.64 | 0 | 0
3524 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Digha (Village code 314460) under Digha Ground Water based Water Supply Scheme for Bhagwangola-I (Part-A) Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000096/2020-2021 | 162/BD-I | 03/02/2021 | 30 | M/S. SUKUMAR SINHA | 71.28 | 29.55 | 1
3525 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dighirpahar (Village code 314794) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005182977 in the District of Murshidabad. (Sl No-08) |  |  | ORD/000350/2021-2022 | 2503/MURD | 17/08/2021 | 120 | SUJIT KUMAR SAHA | 70.56 | 32.43 | 1
3526 | Murshidabad Division |  | Hiring of 01(one) no. Diesel Bolero / Marshal Car for official use having licence for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. Murshidabad for the period from 01-10-2021 to 30-09-2022 (i.e. twelve months) |  |  | ORD/001162/2021-2022 | 473/ISD. | 03/09/2021 | 365 | M/S SAJAHAN CHOWDHURY | 2.05 | 0.8 | 1
3527 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 734 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dighirpahar (Village code 314794) under Islampur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005182977). |  |  | ORD/001703/2021-2022 | 670/MURD | 10/03/2022 | 20 | NATIONAL CONSTRUCTION (MD ASRAFUL SK) | 12.64 | 12.57 | 0
3528 | Murshidabad Division |  | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 |  |  | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0
3529 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of MAIA (Village code 314146) under Maia Ground Water Supply Scheme of Lalgola Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000248/2020-2021 | 37/BD-I | 13/01/2021 | 180 | H.I ENTERPRISE | 158.61 | 212.9 | 1
3530 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Dakhsin Gopalpur ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000071/2024-2025 | 1219/BD-I | 29/07/2024 | 60 | CHATTERJEE ENTERPRISE | 15.96 | 0 | 0
3531 | Berhampore Division I | Raghunathganj Sub-Division | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under Dakshin Gopalpur ground Water based Water Supply Scheme under Raninagar -I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000108/2023-2024 | 437/BD-I | 12/07/2023 | 90 | SOMNATH DEY | 2.32 | 1.31 | 75
3532 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Gajepara (Village code 314796) under DakshinGopalpur Ground Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000180/2020-2021 | 829/BD-I | 13/11/2020 | 60 | M/S SAJAHAN CHOWDHURY | 20.51 | 30.67 | 0
3533 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of DakshinGopalpur (Village code 314797) under DakshinGopalpur Ground Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-06 of 2020 ¿ 2021,SL-06) | Assistant Engineer | Junior Engineer-II | ORD/000381/2021-2022 | 1465/BD-I | 16/08/2021 | 30 | DOBAY CONSTRUCTION | 44.57 | 27.2 | 1
3534 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village CHAR GARAMGARIDAIR(Village code 314792) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, in the District of Murshidabad. |  |  | ORD/000262/2020-2021 | 259/MURD | 25/01/2021 | 45 | AMAL KUMAR DAS | 29.36 | 0 | 0
3535 | Murshidabad Division |  | Extension of pipeline at uncovered habitation of Kanthaliapara Year Ali to Fajit Sk house via Ali Box Sk house & Jalit Sk house under command area of Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. |  |  | ORD/002128/2021-2022 | 468/ISD | 03/09/2021 | 30 | M/S. DIPTI ENTERPRISE | 3.06 | 2.17 | 0
3536 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgiri (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District. |  |  | VCH/000865/2021-2022 | 221-MSD/21-22 | 09/12/2021 | 0 | AMAL KUMAR DAS | 7.7 | 0 | 0
3537 | Murshidabad Division |  | Holding Awardness Programme FHTC |  |  | VCH/000866/2021-2022 | 208-MSD/21-22 | 08/12/2021 | 0 | IMAGIN COMMUNICATION | 3.57 | 0 | 0
3538 | Murshidabad Division |  | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 |  |  | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0
3539 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
3540 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
3541 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Nandalalpur (Village code 314628) under Barabil Raghunathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723213 in the District of Murshidabad. (Sl No-29) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000297/2020-2021 | 961/MURD | 24/03/2021 | 180 | S.M. ENTERPRISE | 50.52 | 50.15 | 1
3542 | Murshidabad Division | Kandi Sub-Division | Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 1 to 23 & N.P 25 to 33 and 110 mm Dia N.P 20 to 33,90 mm OD N.P 17 to 19 at Dakshin,Uttar Mahadebnagar & Kagchipara for smooth water supply arrangement in Mahadebnagar Zone-1 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000745/2021-2022 | 244/JSD | 27/08/2021 | 10 | PRAVAT KUMAR GHOSH | 4.86 | 0 | 0
3543 | Murshidabad Division | Kandi Sub-Division | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0
3544 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION for Village of Nalbatta (VillageCode-314801) under command area of Kosbagoas ground water supply scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000073/2024-2025 | 1221/BD-I | 29/07/2024 | 60 | SWARUP KUMAR BHATTA | 14.97 | 0 | 0
3545 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nalbatta (Village code 314801) under Kasbagoas Ground Water Supply Scheme in Raninagar-I Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-09) | Assistant Engineer | Junior Engineer-II | ORD/000425/2021-2022 | 1598/BD-I | 31/08/2021 | 180 | NOVELTY CONSTRUCTION | 58.29 | 46.21 | 1
3546 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) 1261 nos in connection with Jal Swapna (Jal Jeevan Mission ) of Mouza Jafarganj ( Village Code -313809) under Andhua Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000029/2022-2023 | 1082/MURD | 27/04/2022 | 45 | MARUTI CONSTRUCTION AND CO | 62.56 | 54.08 | 0
3547 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000034/2021-2022 | 540/7/MURD | 25/02/2022 | 0 | Resource Division | 6.92 | 0 | 0
3548 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BHANDARA--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- KOLAN RADHAKANTAPUR , CODE-314523, TNO- 50/2020-21/SE-MC |  |  | VCH/002025/2020-2021 | 512/W | 30/03/2021 | 0 | M/S GUNGUN CONSTRUCTION | 33.58 | 0 | 0
3549 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BHALKUNDI--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 539/2020-21/EE |  |  | VCH/002027/2020-2021 | 512/W | 30/03/2021 | 0 | M/S GUNGUN CONSTRUCTION | 10.66 | 0 | 0
3550 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BHANDARA-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- BHANDARA , CODE-314524, TNO- 51/2020-21/SE-MC |  |  | VCH/002029/2020-2021 | 512/W | 30/03/2021 | 0 | DEBASIS BOSE | 30.48 | 0 | 0
3551 | Murshidabad Division |  | Re-Laying of U.P.V.C pipe of 90 mm dia on damaged portion 90 mm dia U.P.C Pipe in between N.P 3(Pry. School) to N.P 12 via N.P 15 upto N.P 16(Bansabati G.P Member Loton Sara's House) for smooth water supply arrangement in Raturi Zone-2 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. |  |  | ORD/000293/2021-2022 | 198/JSD | 30/07/2021 | 30 | GAUTAM KUMAR CHAUDHURI | 3.81 | 3.81 | 1
3552 | Murshidabad Division |  | Laying of U.P.V.C New Extention pipeline of 90 mm dia in between N.P 6(Durga Mandir) to N.P 12 Upto Pond for smooth water supply arrangement in Raturi Zone-2 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. |  |  | ORD/000296/2021-2022 | 199/JSD | 30/07/2021 | 15 | GAUTAM KUMAR CHAUDHURI | 1.43 | 1.43 | 1
3553 | Murshidabad Division |  | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Jangipur Road Station to Gankar Station ( TP NO 210/09 & 211/00) at Kanupur mouza & Connecting with existing 160 mm dia UPVC distribution main line of Jarur Surface based W/S Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000465/2020-2021 | 547/MURD | 05/02/2021 | 30 | PRADIP KUMAR DAS | 39.01 | 26.23 | 100
3554 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) |  |  | ORD/001659/2021-2022 | 558/MURD | 28/02/2022 | 180 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0
3555 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 3632/C/MURD | 23/11/2021 | 0 | Resource Division | 22.88 | 0 | 0
3556 | Murshidabad Division |  | Preparation of D.P.R (Consultancy work) in connection of different existing PWSS Scheme, Block-SUTI-I to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 402 of 21-22 by EE MURD |  |  | VCH/001447/2021-2022 | 301-MSD/21-22 | 04/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.77 | 0 | 0
3557 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dighirpar( Village Code -314125) under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001756852). |  |  | ORD/000184/2020-2021 | 576/MURD | 09/02/2021 | 60 | JAMIRUL CONSTRUCTION | 41.39 | 78.52 | 0
3558 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village DIGHIRPAR (Village Code-314125) under sarface water based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the dist of Murshidabad District under Murshidabad Division, PHE Dte. Scheme ID: 0001756852 in the dist of MSD |  |  | VCH/000233/2021-2022 |  | 06/08/2021 | 0 | JAMIRUL CONSTRUCTION | 38.25 | 0 | 0
3559 | Murshidabad Division |  | CONT OF AWARENESS PROGRAMME AT DIFFERENT G.PS, TNO- 05/21-22/AE-LSD |  |  | VCH/000870/2021-2022 | 209-MSD/21-22 | 08/12/2021 | 0 | S.S.INFRASTRUCTURE | 2.12 | 0 | 0
3560 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SALAR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000468/2021-2022 | 236/KSD | 27/08/2021 | 60 | IMAGIN | 4.15 | 0 | 0
3561 | Murshidabad Division |  | Holding Awarness Programme / Campaigning programms at Salar G.P, Talibpur G.P, Kagram G.P, Tenya Baidyapur G.P and Simulia G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. (Total nos of Programme = 20 nos) (Part-D). |  |  | ORD/000556/2021-2022 | 252/KSD | 31/08/2021 | 30 | IMAGIN | 4 | 0 | 0
3562 | Murshidabad Division |  | Repairing of rising main & distribution line at Rail gate & Block road etc with construction of thrust block & laying of pipe line of new habitation of Salar Water Supply scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000871/2021-2022 | 296/KSD | 07/10/2021 | 30 | DAS CONSTRACTION (MUNNA DAS) | 4.1 | 0 | 0
3563 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of SALAR (Village code 315742) under SALAR Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte.( Scheme ID 0005252601) |  |  | ORD/001163/2021-2022 | 3975/MURD | 21/12/2021 | 180 | MAMATA USHA ENTERPRISE | 153.26 | 102.61 | 1
3564 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village SALAR (Village Code 315742) under SALAR Ground Water Based Water Supply Scheme for arsenic affected areas of BHARATPUR-II Block in the District of Murshidabad. Tender no - 127 of 21-22 by SE MC |  |  | VCH/000065/2022-2023 | 84-MSD/22-23 | 28/04/2022 | 0 | MAMATA USHA ENTERPRISE | 38.32 | 0 | 0
3565 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at The Villages Of Madhya Gobindopur (Code-314485), Maheshpur(Code-314486) In The Command Area Of Bhundar Kismat Ground Water Supply Scheme (Part-B) Under Bhagwangola-I Block)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000077/2024-2025 | 1225/BD-I | 29/07/2024 | 60 | AZAD CONSTRUCTION & CO. | 17.71 | 0 | 100
3566 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Madhya Gobindapur (Village code 314485) ,Mahespur (Village code 314486) under Bhundar Kismat Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-I | JE | ORD/000125/2020-2021 | 201/BD-I | 04/02/2021 | 30 | TARUN KUMAR BHATTACHARYA | 63.97 | 48.54 | 1
3567 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of BAUSI (Village code 314208) under Bajupur Madhupur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000149/2020-2021 | 266/ BD-I | 12/02/2021 | 180 | M/S JOGMAYA ENTERPRISE | 62.05 | 54.2 | 100
3568 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Bausi to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bajipur Madhupur water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE | ORD/000843/2021-2022 | 99/BD-I | 01/02/2022 | 20 | M/S JOGMAYA ENTERPRISE | 23.01 | 20.62 | 100
3569 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-57C/5576 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2023 to 31.12.2023. | Assistant Engineer-II | JE | ORD/000170/2022-2023 | 1385/BD-I | 23/12/2022 | 365 | SEBAYAN CONSTRUCTION | 1.81 | 3.17 | 71
3570 | Berhampore Division I | Berhampur Division I | Additional Laying works at village DAKATIAPOTA( Village code-315523) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bali Zone-I Ground water supply scheme (Nawda,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II | JE | ORD/000570/2021-2022 | 1922/BD-I | 08/10/2021 | 10 | KAMIRUL SK AND CO. | 5.29 | 5.19 | 1
3571 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
3572 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
3573 | Murshidabad Division | Kandi Sub-Division | Laying of different dia UPVC pipe line in connection with FHTC work at Dhusaripara colony village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-A). | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000085/2022-2023 | 231/JSD | 05/05/2022 | 30 | DIPAYAN DEY | 4.84 | 0 | 1
3574 | Murshidabad Division | Kandi Sub-Division | Laying of different dia UPVC pipe line in connection with FHTC work at Hasimpur, village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-B). | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000086/2022-2023 | 232/JSD | 05/05/2022 | 30 | BARMAN ENTERPRISE | 4.82 | 0 | 1
3575 | Murshidabad Division | Kandi Sub-Division | Laying of different dia UPVC pipe line in connection with FHTC work at Hasimpur, village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-C). | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000087/2022-2023 | 233/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.8 | 0 | 1
3576 | Murshidabad Division | Kandi Sub-Division | Laying of different dia UPVC pipe line in connection with FHTC work at Jyatkundu, village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-D). | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000088/2022-2023 | 234/JSD | 05/05/2022 | 30 | APU CONSTRUCTION | 4.83 | 0 | 1
3577 | Murshidabad Division | Kandi Sub-Division | Laying of different dia UPVC pipe line in connection with FHTC work at Jyatkundu, village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-E). | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000090/2022-2023 | 236/JSD | 05/05/2022 | 30 | NATIONAL CONSTRUCTION (MD ASRAFUL SK) | 4.82 | 0 | 1
3578 | Murshidabad Division | Kandi Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village RAMAKANTAPUR (Village code 314029) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756489 in the District of Murshidabad. (Sl No-1) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000762/2020-2021 | 3115/MURD | 09/12/2020 | 180 | M/S. SINHA & SONS | 65.21 | 0.58 | 100
3579 | Murshidabad Division | Kandi Sub-Division | Laying of DI pipeline and supplying of CI specials for interconnection of 2nd Tubewell site at Kankuria Jafrabad & Dogachi(zone-II) and 1st Tubewell site at Hasimpur& Bhasaipaikar(zone-I) and of Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000811/2022-2023 | 569/MURD | 28/02/2023 | 30 | MAA CONSTRUCTION | 2.6 | 2.61 | 100
3580 | Murshidabad Division | Kandi Sub-Division | Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Hasimpur ( Village Code -313861) under Hasimpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723174) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001594/2021-2022 | 398/MURD | 16/02/2022 | 60 | DIPAYAN DEY | 71.07 | 65.57 | 1
3581 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lalupur ( Village Code -313890) under Kusumgachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723224) |  |  | ORD/000506/2020-2021 | 596/MURD | 09/02/2021 | 60 | PRATAP KUMAR SINHA | 6.24 | 0 | 1
3582 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Hilora ( Village Code -313898) under Kusumgachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723224) |  |  | ORD/000512/2020-2021 | 593/MURD | 09/02/2021 | 60 | HOQUEDAR ALI | 64.7 | 0 | 1
3583 | Murshidabad Division |  | Interconnection of DI pipe line between allied balance work of ¿¿HILORA ¿..under Murshidabad Div PHE DTE. Tender no - 67 of 21-22 by AE JSD |  |  | VCH/000002/2022-2023 | 01-MSD/22-23 | 14/04/2022 | 0 | SAMAR MUKHERJEE | 4.85 | 0 | 0
3584 | Murshidabad Division |  | Construction of allied balance work of ¿¿HILORA ¿..under JSD PHE DTE. Tender no - 66 of 21-22 by AE JSD |  |  | VCH/000003/2022-2023 | 02-MSD/22-23 | 14/04/2022 | 0 | SAMAR MUKHERJEE | 4.97 | 0 | 0
3585 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village LALUPUR (Village Code: 313890) under KASUMGACHHI Ground Water Based Water Supply Scheme for arsenic affected areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID- 0001723224). Tender no- 782 of 20-21 by EE / MSD |  |  | VCH/000192/2021-2022 | 10-MSD / 21-22 | 06/08/2021 | 0 | M/S PRATAP KUMAR SINHA | 4.24 | 0 | 0
3586 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District (PART-I), tno- 895/20-21/EE |  |  | VCH/000682/2021-2022 | 171-MSD/21-22 | 28/10/2021 | 0 | HOQUEDAR ALI | 59.07 | 0 | 0
3587 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Santoshpur Village (Code-315634), Chandpur Village (Code-315635) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part-B)" Under Beldanga-II Block in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000105/2024-2025 | 1435/BD-I | 04/09/2024 | 30 | M/S ARIYAN ENTERPRISE | 14.6 | 0 | 0
3588 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Santoshpur (Village code 315634), Chandpur (Village code 315635) under Mashimpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | Assistant Engineer-II | Junior Engineer-II | ORD/000124/2020-2021 | 200/BD-I | 04/02/2021 | 20 | MD TALEB ALI | 34.35 | 0 | 0
3589 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kaimegha(Village code 314221) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-D) | Assistant Engineer-I | JE | ORD/000129/2020-2021 | 205/BD-I | 04/02/2021 | 30 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 83.83 | 81.09 | 1
3590 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bhundar Kismat (Code-314468) In The Command Area Of Bhundar Kismat Ground Water Supply Scheme (Part-A) Under Bhagwangola-I Block)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000066/2024-2025 | 1203/BD-I | 26/07/2024 | 60 | M/S S.R.K ENTERPRISE | 31.89 | 0 | 0
3591 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bhundar Kismat (Village code 314468) under Bhundar Kismat Water Supply Scheme of Bhagawangola-I Block and village of Maniknagar (Village code 315606) under Maniknagar (Zone-D) Surface water based Water Supply Scheme of Beldanga-I Block of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000841/2021-2022 | 82/BD-I | 31/01/2022 | 180 | J.D.J ENTERPRISE | 248.16 | 0 | 5
3592 | Murshidabad Division |  | Sinking of (300 mm x 200 mm) dia Big dia tube well 75 mtr. Deep by direct rotary rig method using UPVC Pipe and RDS filter at Village Kankuria (Village Code-313873) in connection with FHTC work of Kankuria Jafrabad Water Supply Scheme (Scheme ID- 0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. |  |  | ORD/000093/2022-2023 | 239/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.42 | 0 | 1
3593 | Murshidabad Division |  | Supply of UPVC Pipe and RDS filter for the work of Sinking of (300 mm x 200 mm) dia Big dia tube well at Village Kankuria (Village Code:-313873) in connection with FHTC work of Kankuria Jafrabad Water Supply Scheme (Scheme Id:-0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. |  |  | ORD/000094/2022-2023 | 240/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.6 | 0 | 1
3594 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jafrabad ( Village Code -313872) & (adjoining habitation) (Part-IV) under Kankuria & Jafrabad Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006303234) |  |  | ORD/000404/2021-2022 | 2536/MURD | 19/08/2021 | 60 | M/S. M.R. CONSTRUCTION (PROP: MASUD RANA) | 67.49 | 0 | 0
3595 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Jafrabad ( Village Code -313872 & adjoining habitation (Part-III) under Kankuria&Jafrabad Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006303234) |  |  | ORD/000409/2021-2022 | 2539/MURD | 19/08/2021 | 60 | IKON CONSTRUCTION | 80.14 | 0 | 0
3596 | Murshidabad Division |  | work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-D) |  |  | ORD/001257/2021-2022 | 377/JSD | 31/12/2021 | 30 | R.K.CONSTRUCTION(SOHEL RANA KHAN) | 4.77 | 4.76 | 0
3597 | Murshidabad Division |  | work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-A). |  |  | ORD/001259/2021-2022 | 379/JSD | 31/12/2021 | 30 | S.D PROJECT | 4.77 | 0 | 0
3598 | Murshidabad Division |  | work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-B). |  |  | ORD/001260/2021-2022 | 380/JSD | 31/12/2021 | 30 | S.D PROJECT | 4.77 | 0 | 0
3599 | Murshidabad Division |  | Work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-C) |  |  | ORD/001288/2021-2022 | 395/JSD | 31/12/2021 | 30 | M/S. SRM ENTERPRISE | 4.77 | 4.17 | 0
3600 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-E) |  |  | ORD/001749/2021-2022 | 118/JSD | 22/03/2022 | 30 | S.D PROJECT | 4.85 | 4.85 | 0
3601 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-F). |  |  | ORD/001750/2021-2022 | 119/JSD | 22/03/2022 | 30 | S.D PROJECT | 4.84 | 4.84 | 0
3602 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-H). |  |  | ORD/001751/2021-2022 | 120/JSD | 22/03/2022 | 30 | S.D PROJECT | 4.76 | 4.73 | 0
3603 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-G). |  |  | ORD/001759/2021-2022 | 125/JSD | 22/03/2022 | 30 | YOUSUF ENTERPRISE | 4.8 | 4.6 | 0
3604 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000037/2021-2022 | 540/10/MURD | 25/02/2022 | 0 | Resource Division | 12.11 | 0 | 0
3605 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) |  |  | VCH/001291/2021-2022 |  | 17/02/2022 | 0 | NILKAMAL BASAK | 91.86 | 0 | 0
3606 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of Village JAFRABAD (Village Code 313872) under KANKURIA and jafrabad Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 475 of 21-22 by EE MURD |  |  | VCH/001430/2021-2022 | 347-MSD/21-22 | 05/03/2022 | 0 | NILKAMAL BASAK | 91.86 | 0 | 0
3607 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village KANKURIA (Village Code 313873) under KANKURIA AND JAFRABAD Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 98 of 21-22 by AE JSD |  |  | VCH/001480/2021-2022 | 388-MSD/21-22 | 17/03/2022 | 0 | S.D PROJECT | 4.77 | 0 | 0
3608 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village KANKURIA (Village Code 313873) under KANKURIA AND JAFRABAD Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 98 of 21-22 by AE JSD |  |  | VCH/001481/2021-2022 | 389-MSD/21-22 | 17/03/2022 | 0 | S.D PROJECT | 4.77 | 0 | 0
3609 | Murshidabad Division |  | New laying of different dia UPVC pipeline to restore the distribution system (Besides of Sukdevmati Bridge) in Retrofitting Providing Functional House Hold Tap Connection FHTC in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Chainpara (314804) under Herampur Zone-II) Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000351/2022-2023 | 302/ISD | 20/07/2022 | 30 | PRATICHI ENTERPRISE | 3.31 | 2.86 | 0
3610 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Raghunathpur (Village code 314783) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756480 in the District of Murshidabad. |  |  | ORD/000623/2020-2021 | 321/MURD | 28/01/2021 | 60 | M/S BAPPA ENTERPRISE | 13.73 | 0 | 1
3611 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Sitanagar ( Village Code -314802) under Herampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005183990). |  |  | ORD/000717/2020-2021 | 590/MURD | 09/02/2021 | 60 | PRIYANKA CONSTRUCTION | 26.4 | 23.39 | 1
3612 | Murshidabad Division |  | Providing Balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Sitanagar ( Village Code -314802) under Herampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005183990) |  |  | ORD/001776/2021-2022 | 857/MURD | 31/03/2022 | 60 | PRIYANKA CONSTRUCTION | 49.23 | 44.68 | 0
3613 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari (Village Code -314604)(Part-I) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) |  |  | ORD/000295/2021-2022 | 2300/MURD | 02/08/2021 | 60 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 90.75 | 103.02 | 0
3614 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari ( Village Code -314604)(Part-II) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) |  |  | ORD/000334/2021-2022 | 2435/MURD | 12/08/2021 | 60 | BISWAS ENTERPRISE (PROP. JESMIN KHATUN) | 92.84 | 0 | 1
3615 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari ( Village Code -314604)(Part-III) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) |  |  | ORD/000352/2021-2022 | 2501/MURD | 17/08/2021 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 88.6 | 36.18 | 1
3616 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. |  |  | ORD/000449/2021-2022 | 299/BSD | 13/08/2021 | 30 | IMAGIN COMMUNICATION | 4.34 | 8.67 | 0
3617 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work)in connection with the Functional Household Connection of different existing PWSS (Khairamari PWSS Scheme,Block- Jalangi) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 367 of 21-22 by EE MSD, and Scheme Code: 8200 |  |  | VCH/000039/2022-2023 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 8.31 | 0 | 0
3618 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) |  |  | VCH/001294/2021-2022 |  | 17/02/2022 | 0 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 9.83 | 0 | 0
3619 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harekrishnapur ( Village Code -314624) under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) Tender no - 243 of 21-22 by EE MURD |  |  | VCH/001385/2021-2022 | 333-MSD/21-22 | 25/02/2022 | 0 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 9.83 | 0 | 0
3620 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari (Village Code -314604)(Part-I) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) Tender no - 244 of 21-22 by EE MURD |  |  | VCH/001439/2021-2022 | 338-MSD/21-22 | 03/03/2022 | 0 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 31.7 | 0 | 0
3621 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of NADAIPUR (Village code 314205) under Bajupur Madhupur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000249/2020-2021 | 921/BD-I | 11/12/2020 | 1846 | H.I ENTERPRISE | 95.04 | 18.68 | 59
3622 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahapur (Village code 315210), Upar Fatepur (Village Code 314212) & Bajupur Madhupur (Village Code 314235) under Bajupur Madhupur Ground Water Supply Scheme for Lalgola Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000299/2020-2021 | 994/BD-I | 17/12/2020 | 180 | BIJOY CHOWDHURY | 253.85 | 176.93 | 1
3623 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Sahapur, Upar Fatepur and Bajipur Madhupur (Village code-314210,314212 and 314235) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bajipur Madhupur Ground water based Water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | JE | ORD/000797/2021-2022 | 2314/BD-I | 29/12/2021 | 45 | BIJOY CHOWDHURY | 13.36 | 10.9 | 1
3624 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kashipur (Village code 315687) under Kashipur Water Supply Scheme of Beldanga II Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-13) | Assistant Engineer-II | Junior Engineer-I | ORD/000453/2021-2022 | 1867/BD-I | 07/10/2021 | 180 | TEKNO ENTERPRISE | 122.6 | 107.94 | 1
3625 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhikra (Village code 315688) under Kashipur Water Supply Scheme of Beldanga II Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-12) | Assistant Engineer-II | Junior Engineer-I | ORD/000556/2021-2022 | 1887/BD-I | 07/10/2021 | 180 | HANNAN BUILDERS PVT. LTD. | 92.96 | 90.95 | 1
3626 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Kashipur (Village code-315687) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Kashipur Ground water based Water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-II | Junior Engineer-I | ORD/000839/2021-2022 | 97/BD-I | 01/02/2022 | 30 | TEKNO ENTERPRISE | 9.18 | 8.98 | 100
3627 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Borakuli (Village code 314789) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756480 in the District of Murshidabad. |  |  | ORD/000408/2020-2021 | 325/MURD | 28/01/2021 | 60 | MADAN MOHAN SASMAL | 14.03 | 20.73 | 1
3628 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village Tekaraipur (Village code-314788) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division P.H.E Dte. (Scheme ID-0001756480) |  |  | ORD/000537/2022-2023 | 2686/MURD | 22/09/2022 | 120 | S.D. PROJECT | 132.63 | 132.24 | 100
3629 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Balumati (Village code 314790) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756480 in the District of Murshidabad. |  |  | ORD/000596/2020-2021 | 33/MURD | 05/01/2021 | 60 | DOBAY CONSTRUCTION | 36.55 | 27.86 | 1
3630 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village RAGHUNATHPUR (Village Code 314783) under TEKARAIPUR Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-II Block in the District of Murshidabad. Tender no - 695 of 20-21 by EE MURD |  |  | VCH/000295/2022-2023 | 105-MSD/22-23 | 06/05/2022 | 0 | M/S BAPPA ENTERPRISE | 13.72 | 0 | 0
3631 | Murshidabad Division |  | Laying of UPVC pipeline at Bagpur and Gantla Village for FHTC work of Gantla Village ( Village Code- 315215) of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. |  |  | ORD/000004/2022-2023 | 06 / KSD | 06/04/2022 | 30 | ABHIJIT MONDAL | 4.85 | 4.84 | 1
3632 | Murshidabad Division |  | Construction of pathway at Head work Site of Mahalandi (Zone-I) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000012/2022-2023 | 13 / KSD | 06/04/2022 | 30 | HERITAZE CONSTRUCTION | 3.92 | 3.91 | 1
3633 | Murshidabad Division |  | Laying of UPVC pipeline from Danarul Sk Shop to Gantla Ashram for FHTC work of Gantla Village (Village Code- 315215) of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. |  |  | ORD/000330/2022-2023 | 106 / KSD | 17/06/2022 | 30 | DEBJYOTI MUKHERJEE | 4.83 | 4.82 | 1
3634 | Murshidabad Division |  | Construction of surface drain and development of land at Head work Site of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000419/2022-2023 | 123/KSD | 25/07/2022 | 30 | KAKALI ENTERPRISE | 3.58 | 3.58 | 1
3635 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHALANDI-I G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000458/2021-2022 | 227/KSD | 27/08/2021 | 60 | IMAGIN COMMUNICATION | 4.17 | 0 | 0
3636 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at KUMARSANDA G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000459/2021-2022 | 228/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.15 | 0 | 0
3637 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mahalandi under Mahalandi (Zone-I)Ground Water Based Water Supply Scheme for Arsenic Affected Area of Kandi Block, under Murshidabad Division, PHE Dte. Scheme ID ¿ 0007585495 in the District of Murshidabad. |  |  | ORD/000499/2020-2021 | 692/MURD | 23/02/2021 | 180 | M/S . SUKUMAR SINHA | 113.1 | 0 | 0
3638 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal JeevanMission and Jal Swapna under command area of village Gantla under Mahalandi (Zone-II) Ground Based Water Based Water Supply Scheme for Arsenic Affected Area of Kandi Block under Murshidabad Division, PHE Dte. Scheme ID 0007585495 in the District of Murshidabad. (Sl No-20) |  |  | ORD/000515/2020-2021 | 3051/MURD | 08/12/2020 | 180 | M/S. BIMALENDU BOSE | 69.15 | 68.88 | 95
3639 | Murshidabad Division |  | Holding Awarness Programme / Campaigning programms at Jasahari Anukha-I & II G.P, Mahalandi-I G.P, Kumarsanda G.P and Gokarna-I G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (Total nos of Programme = 20 nos) (Part-A). |  |  | ORD/000553/2021-2022 | 249/KSD | 31/08/2021 | 30 | IMAGIN | 4 | 0 | 0
3640 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BELUN (Village Code : 315216) under Mahalandi Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. |  |  | ORD/000555/2020-2021 | 3038/MURD | 07/12/2020 | 1606 | PRIME CONSTRUCTION | 19.31 | 0 | 50
3641 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mahalandi under Mahalandi (Zone-I)Ground Water Based Water Supply Scheme for Arsenic Affected Area of Kandi Block, under Murshidabad Division, PHE Dte. Scheme ID 0007585495 in the District of Murshidabad. |  |  | ORD/000680/2020-2021 | 692 / MURD | 23/02/2021 | 180 | M/S . SUKUMAR SINHA | 113.1 | 60.7 | 1
3642 | Murshidabad Division |  | Laying of DI pipe in between node point 1A to 29 & supplying of C.I specials of Mahalandi (Zone-I) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the District of Murshidabad. |  |  | ORD/000771/2022-2023 | 211/KSD | 17/02/2023 | 830 | JYOTI TRADERS | 0.97 | 0 | 60
3643 | Murshidabad Division |  | Laying of UPVC pipe line from Head work site to near house of Kalimuddin Sk for drain out of OHR overflow water under Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000774/2022-2023 | 212 / KSD | 17/02/2023 | 30 | A.P. CONSTRUCTION | 0.97 | 0.97 | 1
3644 | Murshidabad Division |  | Repairing of leakage & bursting of UPVC pipe line of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000775/2022-2023 | 213 / KSD | 17/02/2023 | 30 | A.P. CONSTRUCTION | 0.96 | 0.96 | 1
3645 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. |  |  | ORD/001228/2021-2022 | 212/KSD | 11/08/2021 | 30 | IMAGIN | 4.33 | 0 | 0
3646 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Sole Para ( Village Code -315217) under Mahalandi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Kandi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0007585495) |  |  | ORD/001479/2021-2022 | 305/MURD | 07/02/2022 | 60 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 61.94 | 14.61 | 1
3647 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000041/2021-2022 | 541/1/MURD | 25/02/2022 | 0 | Resource Division | 6.96 | 0 | 0
3648 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BELUN (Village Code 315216) under MAHALANDI Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. Tender no - 476 of 21-22 by EE MURD |  |  | VCH/001491/2021-2022 | 394-MSD/21-22 | 22/03/2022 | 0 | PRIME CONSTRUCTION | 11.24 | 0 | 0
3649 | Murshidabad Division |  | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A |  |  | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 0 | 1
3650 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (2145 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Mahadeb Nagar ( Village Code -313823) under Mahadebnagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000653/2023-2024 | 3498/MURD | 08/11/2023 | 90 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 77.63 | 0 | 0
3651 | Murshidabad Division |  | Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 1 to 23 & N.P 25 to 33 and 110 mm Dia N.P 20 to 33,90 mm OD N.P 17 to 19 at Dakshin,Uttar Mahadebnagar & Kagchipara for smooth water supply arrangement in Mahadebnagar Zone-1 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. |  |  | ORD/000745/2021-2022 | 244/JSD | 27/08/2021 | 10 | PRAVAT KUMAR GHOSH | 4.86 | 4.86 | 0
3652 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Farakka Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. |  |  | ORD/001181/2021-2022 | 368/JSD | 22/12/2021 | 30 | IMAGIN | 3.1 | 0 | 0
3653 | Murshidabad Division |  | HIRING OF CAR FOR EE-MSD, MSD DIVN, W/O NO- 293/HQ, DT-29/11/2021 |  |  | VCH/000497/2022-2023 | 186-MSD/22-23 | 24/06/2022 | 0 | DULAL CHOWDHURY | 0.78 | 0 | 0
3654 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-10 |  |  | VCH/000753/2022-2023 | 289-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 6.29 | 0 | 0
3655 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-11 |  |  | VCH/000754/2022-2023 | 289-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 6.29 | 0 | 0
3656 | Murshidabad Division |  | Cleaning & Washing of pipe line at Village Bara Jumla (Village Code-314144) & Krishna Sail (Village Code- 314143) in cinnection with FHTC work under Putia Water Supply Scheme) |  |  | ORD/000315/2022-2023 | 259/JSD | 01/06/2022 | 30 | BISWAS CONSTRUCTION PAN NO : AHNPB6929M | 4.02 | 4.04 | 0
3657 | Murshidabad Division |  | Laying pipe line at village Bara Jumla (Village Code- 314144) & Krishnaa Sail (Village Code-314143) in connection with FHTC work under Putia Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, P.H.Engineering Dte.https://app2.wbphed.gov.in/phed_v3/FAF00242/openDetail01new.html |  |  | ORD/000338/2022-2023 | 274/JSD | 01/06/2022 | 30 | BISWAS CONSTRUCTION PAN NO : AHNPB6929M | 3.85 | 3.85 | 0
3658 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) of mouza Bara Jumla (Village Code-314144, Krishnaa Sail(Village Code-314143) of Putia and ajoining moujas under Ground water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj II Block & mouza Joykrishnapur (Village Code-313880), of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, and mouza Popara (Village Code-314326) of Sagardighi Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0005019109), 0001723441 & 0005184147) |  |  | ORD/001601/2021-2022 | 341/MURD | 10/02/2022 | 1111 | CHAKRABORTY CONSTRUCTION | 416 | 0 | 12
3659 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 889/D/MURD | 05/04/2022 | 0 | Resource Division | 30.5 | 0 | 0
3660 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Bhagabanbati (315342) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000118/2022-2023 | 1201/MURD | 10/05/2022 | 60 | DIPAYAN DEY | 32.59 | 9.6 | 0
3661 | Murshidabad Division | Berhampur M/E Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 810 nos household under command area of village of Bhagabanbati( Village Code -315342) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001723177) | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000219/2022-2023 | 1449/MURD | 01/06/2022 | 1127 | S. K. ENTERPRISE (PROP:SHAMIM ISLAM) | 36.57 | 0 | 0
3662 | Murshidabad Division | Jangipur Sub-Division | Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works & Repair of Boundary Wall (140m + 50m)=190 m at T/W-I site & T/W-II site and Construction of approach road of 80 m ,3 mtr wide and 150 mm depth with 1:2:4 ordinary cement concrete with 75 mm sand filling and BFS for Augmentation of Ahiron Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte.(Attached as Annexure -I) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000661/2023-2024 | 3561/MURD | 21/11/2023 | 60 | ASHEM ENTERPRISE | 8.58 | 8.54 | 100
3663 | Murshidabad Division | Jangipur Sub-Division | Laying distribution pipe lines with allied works in connection With Augmentation of Ahiron Water Supply Scheme In Suti - I Block Of Murshidabad District under Murshidabad Division,P.H.E Dte | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000688/2022-2023 | 130/MURD | 16/01/2023 | 60 | M/S RUBIET HOSSAIN | 94.31 | 0 | 0
3664 | Murshidabad Division | Jangipur Sub-Division | AHIRON & adjoining mouzas PWSS to accommodate Rising Main with allied Laying Distribution under Jal Jeevan Mission, Block- SUTI-I of JANGIPUR Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000839/2023-2024 | 822/MURD | 15/03/2024 | 60 | S. DUTTA | 6.88 | 0 | 100
3665 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000104/2023-2024 | 1167/MURD/1 | 28/04/2023 | 0 | Resource Division | 68.84 | 0 | 0
3666 | Central Drilling | Jangipur Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
3667 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) at village of Chandabad west side ( Village Code _315517) of Ghoramara Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000161/2022-2023 | 150/BSD | 12/04/2022 | 30 | M/S S.R.K.ENTERPPRISE, | 4.7 | 4.59 | 0
3668 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandabad (Village code 315517) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723483 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000591/2020-2021 | 3137/MURD | 11/12/2020 | 60 | M/S. CHOWDHURY CONSTRUCTION | 23.85 | 47.23 | 0
3669 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) at village of Chandabad east side ( Village Code _315517) of Ghoramara Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001778/2021-2022 | 107/BSD | 28/03/2022 | 30 | SUMAN CHOWDHURY | 4.82 | 4.7 | 0
3670 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sinkaipur (Village code 314775) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte Scheme ID 0005019112 in the District of Murshidabad. |  |  | ORD/001377/2021-2022 | 1617 / MURD | 28/06/2021 | 60 | DAS ENTERPRISE (PROP-DIPAK DAS) | 5.14 | 0 | 0
3671 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur (314775) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. ( PART-II ) |  |  | VCH/001296/2021-2022 |  | 17/02/2022 | 0 | DAS ENTERPRISE (PROP-DIPAK DAS) | 3.97 | 0 | 0
3672 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur (314775) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no - 241 of 21-22 by EE MURD |  |  | VCH/001456/2021-2022 | 342-MSD/21-22 | 05/03/2022 | 0 | DAS ENTERPRISE (PROP-DIPAK DAS) | 3.97 | 0 | 0
3673 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village PARASPUR (Village Code 314616) under Muradpur-Jalangi Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block in the District of Murshidabad. |  |  | ORD/000597/2020-2021 | 3031/MURD | 07/12/2020 | 45 | KALYAN CHAKROBORTY | 10.37 | 8.24 | 0
3674 | Murshidabad Division | Berhampur Sub-Division | Laying of 160mm dia UPVC pipeline and road restrostion work for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000058/2022-2023 | 163/BSD | 12/04/2022 | 15 | SUDIPTA GHOSH | 4.84 | 4.84 | 0
3675 | Murshidabad Division | Berhampur Sub-Division | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000066/2022-2023 | 171/BSD | 12/04/2022 | 15 | BARMAN ENTERPRISE | 4.83 | 4.83 | 0
3676 | Murshidabad Division | Berhampur Sub-Division | Laying of 90mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000067/2022-2023 | 172/BSD | 12/04/2022 | 15 | SOUVIK HALDER | 4.85 | 4.85 | 0
3677 | Murshidabad Division | Berhampur Sub-Division | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000068/2022-2023 | 173/BSD | 12/04/2022 | 15 | M/S SUKESH GHOSH | 4.95 | 0 | 0
3678 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at CHOA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000515/2021-2022 | 347/BSD | 27/08/2021 | 30 | IMAGIN | 4.16 | 4.16 | 0
3679 | Murshidabad Division | Berhampur Sub-Division | Relaying of UPVC pipe line from the house of Akbar Miya to the house of Yasin Sk under command area of Choa Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001611/2021-2022 | 21/BSD | 20/01/2022 | 15 | SWAPAN DAS | 4.81 | 0 | 0
3680 | Murshidabad Division | Berhampur Sub-Division | Relaying of UPVC pipeline from the house of Akbar Miya to the house of Yasin SK under command area of choa W/S Scheme under BSD PHE DTE. Tender no - 176 of 21-22 by AE BSD | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/001553/2021-2022 | 448-MSD/21-22 | 31/03/2022 | 0 | SWAPAN DAS | 4.81 | 0 | 0
3681 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Keyadanga (Village code 313966) under Keyadanga Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723355 in the District of Murshidabad. |  |  | ORD/001783/2021-2022 | 804/MURD | 24/03/2022 | 30 | AZAD ENTERPRISE | 25.19 | 21.64 | 0
3682 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 540/4/MURD | 25/02/2022 | 0 | Resource Division | 3.12 | 0 | 0
3683 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Momenpur Water Supply Scheme of 2nd TW Site under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000580/2022-2023 | 3063/MURD | 17/11/2022 | 30 | SUJIT KUMAR SAHA | 9.21 | 8.39 | 0
3684 | Murshidabad Division | Berhampur M/E Division | Formal work order Augmentation of MOMENPUR Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000655/2022-2023 | 3436/MURD | 23/12/2022 | 365 | M/S. ROY TRADING CO. | 408.18 | 117.87 | 30
3685 | Murshidabad Division | Berhampur M/E Division | Construction of approach road with earth filling at Head Work Site (T/W No. 1) under Momenpur W/s Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/001234/2021-2022 | 604/ISD | 31/12/2021 | 60 | MANAB KUMAR GHOSH | 4.49 | 0 | 1
3686 | Murshidabad Division | Berhampur M/E Division | Construction of approch road with earth filling at Head Work Site (T/W No. 1) under Momenpur W/s Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/002063/2021-2022 | 40/ISD | 28/01/2022 | 60 | MANAB KUMAR GHOSH | 4.49 | 4.47 | 1
3687 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000031/2024-2025 | MURD/2481/04 | 04/09/2024 | 0 | Resource Division | 11.73 | 0 | 0
3688 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000162/2023-2024 | 1180/MURD/09 | 29/04/2023 | 0 | Resource Division | 25.98 | 0 | 0
3689 | Murshidabad Division | Berhampur M/E Division | Repairing & Renovation of the pump House No-1 & 2 and allied works under Momenpur water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | VCH/000715/2022-2023 | 235-MSD/22-23 | 15/08/2022 | 0 | SOUVIK HALDER | 3.6 | 0 | 0
3690 | Murshidabad Division | Berhampur M/E Division | Inter connection with Tubewell and rising main etc. at Head work sites (T/W-1) &(T/W-2) Both & Allied Works Under Momenpur Water Supply scheme under Islampur Sub - Division,Murshidabad Division P.H.E Dte. In the district of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | VCH/000720/2022-2023 | 245-MSD/22-23 | 12/08/2022 | 0 | B.G. ENTERPRISE | 3.04 | 0 | 0
3691 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. I & II of Zone-II under MOMENPUR AND OTHERS PIPED WATER SUPPLY SCHEME, BLOCK- DOMKAL DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000042/2025-2026 | 1142/MEDB | 14/05/2025 | 92 | DAS CONSTRUCTION | 22.95 | 0 | 15
3692 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-II of Momenpur ground water based water supply scheme under Block- Domkal, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000048/2023-2024 | 2319/MEDB | 11/07/2023 | 92 | SRI KRISHNA NIRMAN | 11.66 | 9.51 | 10
3693 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAGAR PARA ZONE-I Water Supply Scheme at Head Work Site, 2nd Site site at Jalangi Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000389/2023-2024 | 2793/MURD | 04/09/2023 | 21 | A.M. ENTERPRISE | 27.45 | 0 | 0
3694 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of Sagarpara Part-A Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block in the District of Murshidabad under Murshidabad Division, P H Engg Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000534/2022-2023 | 2641/MURD | 19/09/2022 | 365 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 798.75 | 483.91 | 60
3695 | Murshidabad Division | Berhampur M/E Division | Allied Work of OHR & HDPE Pipe line for Augmentation of Sagarpara Part-A Ground Water Based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block in the District of Murshidabad under Murshidabad Division, P H Engg Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000750/2023-2024 | 119/MURD | 11/01/2024 | 180 | M/S.TAPAS KUMAR CHAKRABORTY | 120.98 | 53.6 | 60
3696 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000033/2022-2023 | 2780/B/MURD | 01/10/2022 | 0 | Resource Division | 20.63 | 0 | 0
3697 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000047/2022-2023 | 3037/B/MURD | 16/11/2022 | 0 | Resource Division | 118.48 | 0 | 0
3698 | Murshidabad Division | Berhampur M/E Division | Overhauling of 450 Cum Capacity, 20 mtr staging height (Shaft Wall) R.C.C. Elevated Reservoir, Repairing of Pump House & Boundary Wall, Laying of Distribution System to accommodate of FHTC work at Alamsahi village, Balbalpara village, Laskarpur, Dogachhi village(80%) & Mahisha Thali Village for Augmentation work of Dogachhi Zone-I Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000004/2025-2026 | 762/MURD | 02/04/2025 | 90 | H.MONDAL CONSTRUCTION | 89.23 | 0 | 0
3699 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dogachhi Zone - I Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000114/2023-2024 | 1756/MURD | 06/07/2023 | 21 | HARUN ALL RASHID & BROTHERS | 35.28 | 23.66 | 90
3700 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution System, Rising Main, Construction of Boundary wall , Repairing & Renovation of Pump House in connection with Augmentation of Dogachhi Zone-I Water Supply Scheme in Samsherganj Block of Murshidabad District under Murshidabad Division, PHE Dte. [(i)Amount for LDS & R.Main: Rs.1,51,21,932.00 & (ii) Amount for Construction of Boundary Wall and repairing of Pump House : Rs. 22,74,098.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000689/2022-2023 | 128/MURD | 16/01/2023 | 60 | M/S. N. ISLAM AND CO. | 173.87 | 82.98 | 40
3701 | Murshidabad Division | Berhampur M/E Division | Formal work order for Water Supply arrangmenet for arsenic affected habitation with SOLAR Power connection by Construction/ installation of Comiunity Purification Plant (CPP) unit including Tubewell (125 x 50 mm dia ) with Submersible pump (for Population 351-500 & Raw Water As concentration upto 0.15 ppm) at Diffarent habitations [For-8 nos Unit] in different Villages of Block of Suti-I (2 Nos),Shamsherganj (6 nos) under Murshidabad Division , P.H.E. Dte. in the District of Murshidabad. (SITE LIST Of S/L 15) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000862/2021-2022 | 3320/MURD | 07/10/2021 | 75 | TEKNO ENTERPRISE | 104.28 | 0 | 50
3702 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.75 | 100
3703 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | RTOR000111/2023-2024 | 1167/MURD/4 | 28/04/2023 | 0 | Resource Division | 32.69 | 0 | 0
3704 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I , II and III OF ZONE-I under Dogachhi ground water based water supply scheme under Block_ SAMSERGANJ Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000159/2023-2024 | 2086/MEDB | 19/06/2023 | 92 | M/S SAJAHAN CHOWDHURY | 31.47 | 26.12 | 10
3705 | Berhampore Division I | Berhampur M/E Division | Improvement of existing AIRP(Gober Danga Model) ( Capacity - 21.0 Cum/ Hr.) of Hazi Mahammadpur Zone-II Water supply Scheme under Jal Jeevan Mission within Lalgola block under Berhampore Division - I, P.H.E Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000078/2025-2026 | 845/BD-I | 23/06/2025 | 45 | ABIDA CONSTRUCTION | 22.63 | 0 | 0
3706 | Berhampore Division I | Berhampur M/E Division | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Hazi Mahammadpur Zone-I ground water supply scheme in Lalgola Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000088/2025-2026 | 948/BD-I | 18/07/2025 | 300 | M/S S. DAS & ENTERPRISE | 122.8 | 0 | 0
3707 | Berhampore Division I | Berhampur M/E Division | Augmentation of Hazi Mohammadpur Zone-I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000213/2022-2023 | 1550/BD-I | 17/02/2023 | 180 | N.H ENTERPRISE | 61.96 | 55.63 | 95
3708 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hazi Mohammadpur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000257/2022-2023 | 1679/BD-I | 14/03/2023 | 30 | TAHID SK | 2.41 | 2.37 | 100
3709 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HAZI MOHAMMADPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000893/2021-2022 | 278/BD-I | 08/03/2022 | 10 | ENVIROTECH SOLUTIONS | 2.46 | 2.46 | 1
3710 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000013/2024-2025 | 1510/BD-I/7 | 12/09/2024 | 0 | Resource Division | 2.3 | 0 | 0
3711 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000073/2023-2024 | 201/BD-1/14 | 10/02/2024 | 0 | Resource Division | 21.36 | 0 | 0
3712 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Hazi Mahammadpur Zone-I ground water supply scheme in Lalgola Block, Dist_Murshidabad under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000015/2025-2026 | 1150/MEDB | 14/05/2025 | 92 | JAL PRAVAHIKA PVT LTD | 39.61 | 0 | 0
3713 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of HAZI MAHAMMADPUR, Zone-I ground water based water supply scheme under Block- Lalgola, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000091/2023-2024 | 3782/MEDB | 03/11/2023 | 458 | ARINDAM MAJUMDAR | 10.45 | 0 | 10
3714 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hazi Mohammadpur Zone-II ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000119/2022-2023 | 1443/BD-I | 16/01/2023 | 10 | MIR SABNAM BEGUM | 2.37 | 2.33 | 100
3715 | Berhampore Division I | Berhampur M/E Division | Augmentation of Hazi Mohammadpur Z-II Piped water supply scheme to accommodate construction of service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000191/2022-2023 | 1457/BD-I | 17/01/2023 | 180 | MODERN CONSTRUCTION | 45.93 | 31.45 | 60
3716 | Berhampore Division I | Berhampur M/E Division | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for Hazi Mohammadpur Zone-II of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000280/2023-2024 | 997/BD-I | 30/10/2023 | 600 | TANBEER CONSTRUCTION | 6.76 | 0 | 100
3717 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HAZI MOHAMMADPUR ZONE-II Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000894/2021-2022 | 279/BD-I | 08/03/2022 | 10 | ENVIROTECH SOLUTIONS | 2.46 | 2.45 | 1
3718 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000018/2024-2025 | 1510/BD-I/12 | 12/09/2024 | 0 | Resource Division | 1.31 | 0 | 0
3719 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000074/2023-2024 | 201/BD-1/15 | 10/02/2024 | 0 | Resource Division | 15.25 | 0 | 0
3720 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Augmentation of Saktipur Zone-III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Beldanga-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000529/2022-2023 | 2539/MURD | 02/09/2022 | 365 | BIJAY CHOWDHURY | 314.93 | 0 | 2
3721 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shaktipur Zone-III Water Supply Scheme at HW Site & 2nd TW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000671/2022-2023 | 3412/MURD | 22/12/2022 | 45 | R.K. DRILLING SERVICES | 23.56 | 20.53 | 100
3722 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS ( SAKTIPUR PWSS Scheme, Block - Beldanga-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000833/2021-2022 | 3266/MURD | 05/10/2021 | 60 | RADIANT | 10.43 | 4.38 | 0
3723 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000007/2024-2025 | 1811/MURD/06 | 20/06/2024 | 0 | Resource Division | 19.32 | 0 | 0
3724 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000300/2023-2024 | 1278/MURD/8 | 10/05/2023 | 0 | Resource Division | 58.86 | 0 | 0
3725 | Berhampore Mechanical | Berhampur Sub-Division | Saktipur Zone-3 Ph- 2 Application No- 3004554555 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01196/2023-2024 | 251/WBSEDCL-JJM | 17/01/2024 | 0 | WBSEDCL | 3.11 | 0 | 0
3726 | Berhampore Mechanical | Berhampur Sub-Division | Saktipu Zone-3 Ph-1 Application No-3004554532 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01197/2023-2024 | 252/WBSEDCL-JJM | 17/01/2024 | 0 | WBSEDCL | 3.44 | 0 | 0
3727 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II at Zone-III of Saktipur ground water based water supply scheme under Block- Beldanga-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000167/2023-2024 | 2021/MEDB | 19/06/2023 | 92 | M/S K.P. PRAMANIK | 23.77 | 19.83 | 70
3728 | Murshidabad Division | Berhampur Sub-Division | Construction of Pump House with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) of 4th Tubewell ,Air Compressor Room with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) , 210 mtr Boundary wall , 86 mtr Drain and Renovation of IEP (Rapid Gravity Filter) at Chandpur W/S Scheme under Berhampore sub-Division , P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/000017/2025-2026 | 966/MURD | 30/04/2025 | 60 | MODERN CONSTRUCTION | 63.48 | 0 | 0
3729 | Murshidabad Division | Berhampur Sub-Division | Allied work for Laying of distribution system HDPE pipeline of 90 mm dia (Paralal Connection) , 110 mm dia, repairing of concrete road and Eucalyptus bulla piling for protection of pipeline at Chandpur Zone-I PWSS under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/000025/2025-2026 | 1019/MURD | 05/05/2025 | 90 | M/S. S. DAS AND ENTERPRISE | 206.9 | 0 | 30
3730 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for :Augmentation of CHANDPUR Zone-I (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/000359/2022-2023 | 2083/MURD | 27/07/2022 | 991 | TINA ROY | 355.12 | 123.76 | 85
3731 | Murshidabad Division | Berhampur Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/000498/2024-2025 | 663/MURD | 19/03/2025 | 65 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0
3732 | Murshidabad Division | Berhampur Sub-Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Chandpur Zone-I, II Water Supply Scheme at HW Site & 2nd TW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/000599/2022-2023 | 3073/MURD | 17/11/2022 | 60 | MERCURY ENGINEERING COMPANY | 31.74 | 29.25 | 100
3733 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (CHANDPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/000844/2021-2022 | 3277/MURD | 05/10/2021 | 60 | RADIANT | 14.82 | 4.84 | 1
3734 | Murshidabad Division | Berhampur Sub-Division | Repairing and Refilling of filter media with allied works of Iron Elemination Plant (I.E.P) at Chandpur W/S Scheme, under Berhampore Sub-Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/001346/2021-2022 | 12/BSD | 10/01/2022 | 15 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 4.85 | 0 | 0
3735 | Murshidabad Division | Berhampur Sub-Division | Repairing of R.C.C. elevated reservoir (375 Cum capacity) of staging hight 18.5 Mtr. At Chandpur Water Supply under Berhampore Sub Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/001647/2021-2022 | 554/MURD | 28/02/2022 | 45 | ULTRA CONSTRUCTION. | 11.25 | 4.77 | 0
3736 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | RTOR000004/2024-2025 | 1811/MURD/03 | 20/06/2024 | 0 | Resource Division | 40.95 | 0 | 0
3737 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | RTOR000302/2023-2024 | 1278/MURD/4 | 10/05/2023 | 0 | Resource Division | 92.15 | 0 | 0
3738 | Berhampore Mechanical | Berhampur Sub-Division | SERVICE CONNECTION AT CHANDPUR Z1 PH1 ID 304265806 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | BILL/00381/2024-2025 | 111/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 4.94 | 0 | 0
3739 | Berhampore Mechanical | Berhampur Sub-Division | CHANDPUR Z-I/A PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | BILL/01573/2023-2024 | 422/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 3.77 | 0 | 0
3740 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I & II, Zone-I under CHANDPUR ,PART-A ground water based water supply scheme under Block_ Nowda Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/000125/2023-2024 | 1912/MEDB | 16/06/2023 | 92 | EASTERN INDIA SALES & SERVICE | 22.32 | 15.74 | 60
3741 | Berhampore Division I | Berhampur Division I | Way leave permission for using the Railway land for laying water supply pipeline of underground Railway Track crossing of 900 mm dia M.S Casing Pipe through 600 mm dia M.S Carrier pipe by Jack Pushing/HDD method between station Dahapara -Lalbagaat KM, 173/21-22-173/23-24 in Katwa-Azimalong section of Howrah Division E. Rly. under Berhampore Division-I | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00065/2024-2025 | BP-2024-25-62 | 19/06/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 5.32 | 0 | 0
3742 | Berhampore Division I | Berhampur Division I | Way leave permission for using the Railway land for laying water supply pipeline of underground Railway Track crossing of 600 mm dia M.S Casing Pipe through 250 mm dia M.S Carrier pipe by Jack Pushing/HDD method between station NLSF-LCAE at KM, 166-33/34-166/35/36 in Katwa-Azimalong section of Howrah Division E. Rly. under Berhampore Division-I | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00066/2024-2025 | BP-2024-25-63 | 19/06/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 5.94 | 0 | 0
3743 | Berhampore Division I | Berhampur Division I | Way leave permission for using the Railway land for laying water supply pipeline of underground Railway Track crossing of 900 mm dia M.S Casing Pipe through 600 mm dia M.S Carrier pipe by Jack Pushing/HDD method between station Dahapara -Lalbagaat KM, 173/21-22-173/23-24 in Katwa-Azimalong section of Howrah Division E. Rly. under Berhampore Division-I (for Raw Water) | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00089/2024-2025 | BP-2024-25-65 | 20/06/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 5.32 | 0 | 0
3744 | Berhampore Division I | Berhampur Division I | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION NLSF-LCAE AT KM 170/27-29 & 170/28-30 IN KATWA-AZIMGANJ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00153/2024-2025 | BP-2024-25-114 | 30/07/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 7.19 | 0 | 0
3745 | Berhampore Division I | Berhampur Division I | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION JIBANTI HALT-KHAGRAGHAT AT KM 162/32-34 & 162/33-35 IN KWAE-AZ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00154/2024-2025 | BP-2024-25-115 | 30/07/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 6.32 | 0 | 0
3746 | Berhampore Division I | Berhampur Division I | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION JIBANTI HALT-KHAGRAGHAT AT KM 160/13-15 IN KATWA-AZIMGANJ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00155/2024-2025 | BP-2024-25-116 | 30/07/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 6.43 | 0 | 0
3747 | Berhampore Division I | Berhampur Division I | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION JIBANTI HALT-KHAGRAGHAT AT KM 162/32-34 & 162/33-35 IN KWAE-AZ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. (R.A-2) | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00175/2024-2025 | BP-2024-25-135 | 21/08/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 0 | 0 | 0
3748 | Berhampore Division I | Berhampur Division I | HYDRAGRAPHIC SURVEY CHARGE FOR SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART BERHAMPORE AND MURSHIDABAD JIAGANJ BLOCKS OF DISTRICT OF MURSHIDABAD | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00208/2023-2024 | BP-2023-24-127 | 15/09/2023 | 0 | SYAMA PRASAD MOOKERJEE PORT KOLKATA | 55.55 | 0 | 0
3749 | Berhampore Division I | Berhampur Division I | Consultancy charges along with the work order in respect of the project title "EIA and EMP for proposed Intake Jetty of Surface water based piped water supply scheme for entire Nabagram Block and Part of Berhampore & Murshidabad Jiaganj Blocks of District Murshidabad (IPBN) | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00313/2023-2024 | BP-2023-24-205 | 13/12/2023 | 0 | IIT CONSULTATIVE PRATICE | 5.52 | 0 | 0
3750 | Berhampore Division I | Berhampur Division I | Second Installment 20% after submission of EIA report in respect of the project title EIA and EMP for Proposed Intake Jetty of Surface water based piped water supply scheme for entire Nabagram Block and Part of Berhampore & Murshidabad Jiaganj Blocks of District Murshidabad | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00800/2023-2024 | BP-2023-24-290 | 01/03/2024 | 0 | IIT CONSULTATIVE PRATICE | 1.84 | 0 | 0
3751 | Berhampore Division I | Berhampur Division I | Third Installment 20% after submission of EIA report in respect of the project title EIA and EMP for Proposed Intake Jetty of Surface water based piped water supply scheme for entire Nabagram Block and Part of Berhampore & Murshidabad Jiaganj Blocks of District Murshidabad | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00801/2023-2024 | BP-2023-24-291 | 01/03/2024 | 0 | IIT CONSULTATIVE PRATICE | 1.84 | 0 | 0
3752 | Berhampore Division I | Berhampur Division I | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Monthly hire basis for official use for the Office of the Assistant Engineer-I,BD-I,PHE Dte. [Period for 03.07.2024 to 30.06.2025]. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000040/2024-2025 | 1047/BD-I | 02/07/2024 | 365 | AMAN CONSTRUCTION | 1.81 | 0 | 45
3753 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Monthly hire basis for official use for the Office of the Assistant Engineer-I,BD-I,PHE Dte. [Period for 01.07.2025 to 31.10.2025]. [Car No-WB-58BB/0191] | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000096/2025-2026 | 858/BD-I | 30/06/2025 | 123 | AMAN CONSTRUCTION | 0.6 | 0 | 0
3754 | Berhampore Division I | Berhampur Division I | SUPPLY, CARRIAGE , LAYING AND COMMISSIONING OF DISTRIBUTION PIPE NETWORK INCLUDING PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) AND PIPED WATER SUPPLY ARRANGEMENT FOR DIFFERENT SCHOOL ,SSK, MSK ETC.OF DIFFERENT DISTRIBUTION ZONES OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPUR AND MURSHIDABAD - JIAGANJ BLOCK OF MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION-I, PHE Dte. IN CONNECTION WITH JJM. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000283/2023-2024 | 983/BD-I | 30/10/2023 | 884 | WPIL LIMITED | 12076.79 | 0 | 16
3755 | Berhampore Division I | Berhampur Division I | Formal work order for Surveying, Planning, Designing, Delivery, Erection, Construction, Commissioning and completion in all respect of all Civil, Electrical and Mechanical works like Raw Water Intake, WTP, Raw Water Rising Main, Clear Water Rising Main (CWR at WTP to different OHR sites), OHR, Chlorine cum Switch Room, Boundary Wall etc. including all allied related and enabling works for surface water based piped water supply scheme for entire NABAGRAM Block, Part of Berhampore & Murshidabad-Jiaganj Blocks of District Murshidabad followed by 6(Six) months of Trial Run and subsequent Operation & Maintenance of 5(Five) years. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000288/2022-2023 | 1802/BD-I | 31/03/2023 | 914 | GBC INFRASTRUCTURE PVIVATE LIMITED | 15290.9 | 4627.23 | 70
3756 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | RTOR000002/2023-2024 | 61/BD-1/36 | 27/04/2023 | 0 | Resource Division | 8607.44 | 0 | 0
3757 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | RTOR000119/2023-2024 | 360/BD-1 | 05/03/2024 | 0 | Resource Division | 123.2 | 0 | 0
3758 | Berhampore Mechanical | Berhampur Division I | Bulk power connection charge for Nabagram Intake 276KVA Application No-R000012129 Con Id-950086101 | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/01060/2023-2024 | 198/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 28.06 | 0 | 0
3759 | Berhampore Mechanical | Berhampur Division I | Bulk power connection charge for Nabagram WTP 1047KVA Application No- R000012128 Con Od-950085502 | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/01067/2023-2024 | 199/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 86.39 | 0 | 0
3760 | Berhampore Mechanical | Berhampur Division I | Supply, delivery, installation & commissioning of Substation Equipments and other Accessories at Raw Water Pumping Station under Nabagram Surface Water Based W/S Scheme, Dist. Murshidabad. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000979/2023-2024 | 3861/MEDB | 07/11/2023 | 182 | ALOK ENTERPRISE | 258.96 | 141.37 | 10
3761 | Berhampore Mechanical | Berhampur Division I | Supply, delivery, installation & commissioning of Substation Equipments and other Accessories at Water Treatment Plant under Nabagram Surface Water Based W/S Scheme under MEDB, P.H.E. Dte., Dist. Murshidabad. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000980/2023-2024 | 3862/MEDB | 07/11/2023 | 542 | ORIENTAL ENGINEERING CO. | 391.5 | 0 | 5
3762 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGED ROAD DUE TO LAYING OF PHE PIPELINE OF MAHADIA-DURGAPUR ROAD FROM 0.30 KM TO 2.10 KM UNDER MSD HIGHWAY DIVISION.-II DURING THE YEAR OF 2024-25 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/01073/2024-2025 | 393-MSD/2024-25 | 19/09/2024 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 13.77 | 0 | 0
3763 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of ANDULIA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362266S000 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000694/2022-2023 | 147/MURD | 17/01/2023 | 988 | M/S. CHOWDHURY BUILDERS | 605.19 | 122.45 | 25
3764 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000037/2023-2024 | 1004/MURD/12 | 17/04/2023 | 0 | Resource Division | 24.19 | 0 | 0
3765 | Berhampore Mechanical | Kandi Sub-Division | New service connection charge for Andulia, P/H No.-II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/00538/2023-2024 | 110/WBSEDCL-JJM | 29/08/2023 | 0 | WBSEDCL | 8.54 | 0 | 0
3766 | Berhampore Mechanical | Kandi Sub-Division | New service connection charge for Andulia, P/H No.-I. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/00539/2023-2024 | 111/WBSEDCL-JJM | 29/08/2023 | 0 | WBSEDCL | 5.47 | 0 | 0
3767 | Berhampore Mechanical | Kandi Sub-Division | Electric Service Connection at ANDULIA PWSS I, Application NO.3004400021, ID 304117200 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/01083/2023-2024 | 197/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 5.47 | 0 | 0
3768 | Berhampore Mechanical | Kandi Sub-Division | SERVICE CONNECTION CHARGES AT ANDULIA PH2 ID304117291 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/01112/2023-2024 | 208/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 8.54 | 0 | 0
3769 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under ANDULIA ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000080/2023-2024 | 1884/MEDB | 16/06/2023 | 92 | HARA PROSAD DAS | 25.86 | 0 | 30
3770 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of BRAHMANDIHI & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division , PHE. Dte.( Scheme ID -PH222362353S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000677/2022-2023 | 36/MURD | 04/01/2023 | 1001 | TRANS ORGANICS (INDIA) PVT. LTD. | 526.07 | 48.34 | 20
3771 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000039/2023-2024 | 1043/MURD/14 | 17/04/2023 | 0 | Resource Division | 34.54 | 0 | 0
3772 | Berhampore Mechanical | Kandi Sub-Division | Quotation for Bamundi PH No-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01433/2023-2024 | 329/WBSEDCL-JJM | 06/02/2024 | 0 | WBSEDCL | 4.36 | 0 | 0
3773 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BRAHMANDIHI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000083/2023-2024 | 1885/MEDB | 16/06/2023 | 92 | M/S S. R. ENTERPRISE | 23.47 | 0 | 0
3774 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JASOHARI PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000652/2022-2023 | 3400/MURD | 22/12/2022 | 45 | M/S B.R. SUPPLIERS | 16.8 | 0 | 0
3775 | Murshidabad Division | Kandi Sub-Division | Formal Work Order For Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of JASOHARI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362341S000) [ (i)Amount for LDS , R. Main & FHTC: Rs. 1,91,63,541.00 & (ii) Amount for OHR,Boundwary Wall & Pump House : Rs. 1,56,48,969.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000765/2022-2023 | 481/MURD | 20/02/2023 | 365 | M/S. NANDY ENTERPRISE | 347.6 | 0 | 0
3776 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | RTOR000006/2023-2024 | 1004/MURD/8 | 11/04/2023 | 0 | Resource Division | 24.37 | 0 | 0
3777 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under JASOHARI ground water based water supply scheme under Block_ KANDI Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000150/2023-2024 | 2081/MEDB | 19/06/2023 | 92 | SARKAR CONSTRUCTION | 23.39 | 14.9 | 60
3778 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of GARULIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000690/2022-2023 | 144/MURD | 17/01/2023 | 1080 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 583.49 | 138.72 | 35
3779 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000047/2023-2024 | 1067/MURD/2 | 18/04/2023 | 0 | Resource Division | 27.8 | 0 | 0
3780 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000337/2023-2024 | 79/MURD/04 | 09/01/2024 | 0 | Resource Division | 18.58 | 0 | 0
3781 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PH2 GURULIA ID 304239443 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01412/2023-2024 | 309/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 4.29 | 0 | 0
3782 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PH1 GURULIA ID 304239442 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01413/2023-2024 | 310/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 4.23 | 0 | 0
3783 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under GARULIA ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000152/2023-2024 | 2013/MEDB | 19/06/2023 | 926 | JOGMAYA ENGINEERING | 24.48 | 19.92 | 65
3784 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for GHORAPAKHIA GANGIN Zone -II Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000016/2025-2026 | 965/MURD | 30/04/2025 | 60 | M/S. UNIQUE BUILDERS | 23.01 | 0 | 0
3785 | Murshidabad Division | Berhampur M/E Division | Sinking of 1NO. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Ghorapakhiagangin Zone-I Water Supply Scheme at Suti-I Block of Jangipur Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000111/2024-2025 | 2290/MURD | 09/08/2024 | 15 | JOY GURU ENTERPRISE | 11.67 | 0 | 95
3786 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.51 | 100
3787 | Murshidabad Division | Berhampur M/E Division | Re-Laying of U.P.V.C pipe of 90 mm dia on damaged portion in between N.P 04-05-30-07 to 06 (From Dalim Sk house to Sanaul Sk house) for smooth water supply arrangement in Ghorapakhiagangin Zone-I W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000451/2020-2021 | 13/JSD | 13/01/2021 | 30 | LAXMI CONSTRUCTION | 2.88 | 2.58 | 1
3788 | Murshidabad Division | Berhampur M/E Division | Re-Laying of U.P.V.C pipe of 90 mm dia on damaged portion in between N.P 05 to 06 (Prymary school to kriti mondal's House) for smooth water supply arrangement in Ghorapakhiagangin Zone-I W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000452/2020-2021 | 14/JSD | 13/01/2021 | 30 | DEBOJYOTI CONSTRUCTION | 1.64 | 1.56 | 1
3789 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Ahiran Halt Station to Jangipur Road Station (TP NO 217/5 & 217/6) at Ghorapakhia Gangin mouza & Connecting with existing 110 mm dia uPVC distribution main line of Ghorapakhia Gangin Zone- II ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000514/2021-2022 | 2484/MURD | 16/08/2021 | 60 | M/S. SINHA & SONS | 21.58 | 21.58 | 0
3790 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
3791 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000210/2023-2024 | 1210/MURD/13 | 02/05/2023 | 0 | Resource Division | 58.4 | 0 | 0
3792 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-II under GHORAPAKHIA GANGIN ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000121/2023-2024 | 1910/MEDB | 16/06/2023 | 92 | ARINDAM MAJUMDAR | 22.81 | 0 | 0
3793 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Dakshinkhanda Habitation under Dakshinkhanda Village Code-315710 (JL NO-99) Dakshinkhanda Water Supply Scheme (Ground Water Based) under Bharatpur-II Block in the District of Murshidabad. |  |  | ORD/000261/2020-2021 | 2392/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 9.76 | 0.12 | 1
3794 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SIMULIA G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000469/2021-2022 | 237/KSD | 27/08/2021 | 60 | IMAGIN COMMUNICATION | 4.17 | 0 | 0
3795 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Dakshinkhanda Habitation under Dakshinkhanda Village Code-315710 (JL NO-99) Dakshinkhanda Water Supply Scheme (Ground Water Based) under Bharatpur-II Block in the District of Murshidabad. |  |  | ORD/000632/2020-2021 | 2392/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 9.76 | 8.09 | 0
3796 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of Village of Harinya, Datta Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, DakshinKhanda (Nos FHTC-4251) (Village code-315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) under DAKSHINKHANDA Ground Water Based Water Supply Scheme and Kagram ( Nos FHTC-3297) (Village code-315714) under Kagram Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block, of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID 0007338400 & 0007773828) |  |  | ORD/001278/2021-2022 | 141/MURD | 19/01/2022 | 180 | M/S. S. DAS AND ENTERPRISE | 383.18 | 56.55 | 1
3797 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 3632/D/MURD | 23/11/2021 | 0 | Resource Division | 23.38 | 0 | 0
3798 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 20
3799 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Ramchandrapur Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000246/2022-2023 | 1651/BD-I | 13/03/2023 | 180 | MS BAPPA ENTERPRISE | 49.53 | 28.79 | 71
3800 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMCHANDRAPUR Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000278/2022-2023 | 1391/BD-I | 27/12/2022 | 10 | M/S SOBHA & CO | 2.46 | 2.43 | 100
3801 | Berhampore Division I | Raghunathganj Sub-Division | Repair And Renovation Works Of OHR (35 Cum) of Ground Water Based Supply Scheme for Ramchandrapur of Raninagar-II block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000301/2023-2024 | 1069/BD-I | 21/11/2023 | 30 | MADAN MOHAN SASMAL | 5.13 | 4.68 | 70
3802 | Berhampore Division I | Raghunathganj Sub-Division | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at RAMCHANDRAPUR Water Supply Scheme (1st TW site) within RANINAGAR-II Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000330/2024-2025 | 280/BD-I | 12/02/2025 | 15 | HAFIZUL SEIKH | 11.56 | 0 | 0
3803 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000012/2023-2024 | 61/BD-1/1 | 27/04/2023 | 0 | Resource Division | 13.4 | 0 | 0
3804 | Murshidabad Division | Berhampur Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0
3805 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall at Head works site for Part-C of Kodla water supply Scheme under Berhampore Sub Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000367/2020-2021 | 3271/MURD | 24/12/2020 | 30 | CHATTERJEE ENTERPRISE | 4.58 | 4.24 | 0
3806 | Murshidabad Division | Berhampur Sub-Division | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 75
3807 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Kodla PWSS to accommodate FHTC of 2000 nos household Laying Rising Main ,Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement),Construction of Boundary Wall of 250 m and Soil Investigation & 150 Cum Construction of OHR at Berhampore Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000570/2023-2024 | 3289/MURD | 19/10/2023 | 745 | MARUTI CONSTRUCTION AND CO. | 272.25 | 0 | 30
3808 | Murshidabad Division | Berhampur Sub-Division | Water Supply arrangement for arsenic affected habitation with SOLAR Power connection at different block under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad. (PART-F) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000652/2020-2021 | 506/MURD | 02/02/2021 | 60 | PAL TROCKNER (P) LTD. | 37.91 | 0 | 81
3809 | Murshidabad Division | Berhampur Sub-Division | Water Supply arrangement for arsenic affected habitation with SOLAR Power connection at different block under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad. (PART-J) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000656/2020-2021 | 511/MURD | 02/02/2021 | 60 | PAL TROCKNER (P) LTD. | 37.91 | 0 | 100
3810 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Construction of 400 CUM capacity 20.00 mtr staging height RCC elevated Over Head Reservoir on raft foundation as per drawing & design reference-PC-I/OHR/11/2012) including supply, delivery and errecting inlet and overflow pipe connection etc all complete at head work site of KODLA water supply scheme of Berhampore Sub-Division under Murshidabad Division Murshidabad District P.H.Engg Dept. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000661/2020-2021 | 3114/MURD | 09/12/2020 | 270 | M/S KAMRULA CONSTRUCTION CO. | 98.16 | 0 | 5
3811 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Laying Distribution System For Augmentation of Kodla (Part-A) PWSS of Beldanga-II Block under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000845/2022-2023 | 730/MURD | 15/03/2023 | 721 | SUDIPA SINGHA ROY | 100.66 | 0 | 50
3812 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 6.03 | 1
3813 | Central Drilling | Berhampur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
3814 | Berhampore Mechanical | Berhampur Sub-Division | KODLA PH-2 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01521/2023-2024 | 401/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 6.91 | 0 | 0
3815 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR ZONE-I PWSS (TW - III Site) within Lalgola Block under JAL JEEVAN MISSION in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (01 No TW) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000049/2025-2026 | 758/BD-I | 22/05/2025 | 15 | AZAD ENTERPRISE | 9.01 | 0 | 0
3816 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Nasipur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000117/2022-2023 | 1368/BD-I | 21/12/2022 | 30 | CHATTERJEE ENTERPRISE | 2.46 | 2.42 | 100
3817 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for NASIPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000204/2022-2023 | 1374/BD-I | 21/12/2022 | 10 | ENVIROTECH SOLUTIONS | 2.94 | 2.62 | 1
3818 | Berhampore Division I | Berhampur M/E Division | Augmentation of Nasipur Zone_I Piped water supply scheme to accommodate construction of Pump House and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000245/2022-2023 | 1625/BD-I | 02/03/2023 | 180 | DHIMAN SARKAR | 176.03 | 52.88 | 26
3819 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000012/2024-2025 | 1510/BD-I/6 | 12/09/2024 | 0 | Resource Division | 4.99 | 0 | 0
3820 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000072/2023-2024 | 201/BD-1/13 | 10/02/2024 | 0 | Resource Division | 60.04 | 0 | 0
3821 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room at Head Work Site of BAJUPUR MADHUPUR ZONE -I PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000007/2025-2026 | 594/BD-I | 22/04/2025 | 45 | JAKIR HOSSAIN PRAMANIK | 8.66 | 0 | 1
3822 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Bajipur Madhupur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000125/2022-2023 | 1671/BD-I | 14/03/2023 | 30 | JAMUNA CONSTRUCTION | 2.85 | 2.82 | 100
3823 | Berhampore Division I | Berhampur M/E Division | Augmentation of Bajipur Madhupur Zone-I Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000155/2023-2024 | 672/BD-I | 09/08/2023 | 730 | VISION ENTERPRISE | 353.85 | 0 | 10
3824 | Berhampore Division I | Berhampur M/E Division | Formal work order for Augmentation of Bajipur Madhupur Zone-I Piped water supply scheme to accommodate construction of laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000240/2022-2023 | 1597/BD-I | 28/02/2023 | 180 | SAMBHUNATH ROY | 207.9 | 140.36 | 100
3825 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BAJIPUR MADHUPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000266/2022-2023 | 1689/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 3.14 | 3.17 | 1
3826 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bajupur Madhupur Zone - I Water Supply Scheme (TW - I & II Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000365/2024-2025 | 320/BD-I | 24/02/2025 | 15 | MERCURY ENGINEERING COMPANY | 18 | 0 | 0
3827 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd TW Site of BAJUPUR MADHUPUR ZONE-I PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000380/2024-2025 | 442/BD-I | 20/03/2025 | 60 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 19 | 0 | 0
3828 | Berhampore Division I | Berhampur M/E Division | BAJUPUR MADHUPUR ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000449/2023-2024 | 452/BD-I | 15/03/2024 | 747 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 21.46 | 0 | 30
3829 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000092/2023-2024 | 201/BD-1/25 | 10/02/2024 | 0 | Resource Division | 139.52 | 0 | 0
3830 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Gaukhana ground Water Supply Scheme under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000013/2023-2024 | 60/BD-I | 25/04/2023 | 30 | SAIF TRADERS | 2.25 | 2.21 | 100
3831 | Berhampore Division I | Berhampur M/E Division | Improvement of existing AIRP(Gober Danga Model) (Capacity-21.0 Cum/ Hr.) of GAUKHANA Water supply Scheme under Jal Jeevan Mission within Lalgola block under Berhampore Division-I, P.H.E Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000068/2025-2026 | 721/BD-I | 14/05/2025 | 30 | MS GUNGUN CONSTRUCTION | 20.25 | 0 | 0
3832 | Berhampore Division I | Berhampur M/E Division | Augmentation of Gaukhana Piped water supply scheme to accommodate construction of OHR ,Arsenic cum Iron Removal Plant( AIRP) and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000153/2023-2024 | 680/BD-I | 10/08/2023 | 630 | ARABINDA GHOSH | 317.21 | 0 | 50
3833 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for GOUKHANA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000258/2022-2023 | 1681/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.46 | 2.48 | 1
3834 | Berhampore Division I | Berhampur M/E Division | GAUKHANA PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000428/2023-2024 | 328/BD-I | 29/02/2024 | 542 | SANTA TRADING | 22.94 | 0 | 60
3835 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000011/2024-2025 | 1510/BD-I/5 | 12/09/2024 | 0 | Resource Division | 3.44 | 0 | 0
3836 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000071/2023-2024 | 201/BD-1/12 | 10/02/2024 | 0 | Resource Division | 36.3 | 0 | 0
3837 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT GAUKHANA PH-I | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/00521/2024-2025 | 170/WBSEDCL-JJM | 31/07/2024 | 0 | WBSEDCL | 6.98 | 0 | 0
3838 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of GAUKHANA ground water based water supply scheme under Block- LALGOLA, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000283/2023-2024 | 3785/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE (CHOA) | 11.25 | 0 | 10
3839 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 15.12 | 20
3840 | Berhampore Division I | Raghunathganj Sub-Division | MOKTARPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | ORD/000070/2025-2026 | 824/BD-I | 18/06/2025 | 45 | BURIMAA CONSTRUCTION | 23.3 | 0 | 0
3841 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of MUKTARPUR ZONE-II PWSS under Jal Jeevan Mission within Raninagar -I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | ORD/000075/2025-2026 | 842/BD-I | 23/06/2025 | 60 | GOUTAM KUMAR CHAUDHURI | 19 | 0 | 0
3842 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augnentation of MUKTARPUR PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | ORD/000093/2024-2025 | 1306/BD-I | 07/08/2024 | 60 | M/S BHAGIRATHI ENTERPRISE | 7.65 | 0 | 0
3843 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Moktarpur Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | ORD/000205/2023-2024 | 871/BD-I | 12/09/2023 | 310 | MS RUBIET HOSSAIN | 333.41 | 0 | 0
3844 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MOKTARPUR Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | ORD/000274/2022-2023 | 1758/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.67 | 2.67 | 100
3845 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | RTOR000007/2023-2024 | 61/BD-1/7 | 27/04/2023 | 0 | Resource Division | 37.29 | 0 | 0
3846 | Berhampore Mechanical | Raghunathganj Sub-Division | AT MOKTARPUR PH 1 ID 304244961 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | BILL/01477/2023-2024 | 374/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 12.51 | 0 | 0
3847 | Berhampore Mechanical | Raghunathganj Sub-Division | AT MOKTARPUR PH 2 ID 304244960 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | BILL/01478/2023-2024 | 375/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 3.92 | 0 | 0
3848 | Berhampore Mechanical | Raghunathganj Sub-Division | load enhancement moktarpur pwss | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | BILL/01599/2023-2024 |  | 05/03/2024 | 0 | WBSEDCL | 1.03 | 0 | 0
3849 | Berhampore Mechanical | Raghunathganj Sub-Division | LOAD ENHANCEMENT OF MOKTARPUR PWSS ID 312350581 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | BILL/01624/2023-2024 | 460/WBSEDCL-JJM | 18/03/2024 | 0 | WBSEDCL | 1.03 | 0 | 0
3850 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Moktarpur ground water based water supply scheme under Block_ Nawda Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | ORD/000170/2023-2024 | 2093/MEDB | 19/06/2023 | 92 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 23.45 | 0 | 20
3851 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bati & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K a n d i Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000046/2023-2024 | 1216/MURD | 03/05/2023 | 30 | MAMATA USHA ENTERPRISE | 21.38 | 11.25 | 50
3852 | Murshidabad Division | Kandi Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) under Jal Jeevan Mission for command area of Uncovered BATI Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000706/2022-2023 | 120/MURD | 13/01/2023 | 30 | DEBASIS BOSE | 71.38 | 0 | 0
3853 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System (PART-B), Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) for Uncoveded BATI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte.for [ (i) Amount for Laying Distribution System: Rs.72,79,775.00 & (ii) Amount for Pump House: Rs. 10,55,058.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000720/2022-2023 | 121/MURD | 13/01/2023 | 838 | M/S. GOURI ENTERPRISE | 84.16 | 65.15 | 50
3854 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for construction of 200 Cum OHR,,Laying Distribution System (PART-A),Rising Main Connection, Boundwary Wall, for Uncovered of BATI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division , PHE.Dte. [(i)Amount for LDS , R.Main: Rs.1,64,06,836.00 & (ii) Amount for OHR & B. Wall : Rs. 1,25,46,499.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000766/2022-2023 | 484/MURD | 20/02/2023 | 1046 | AJAY MONDAL | 289.48 | 54.8 | 30
3855 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | RTOR000022/2023-2024 | 1210/MURD/33 | 02/05/2023 | 0 | Resource Division | 24.92 | 0 | 0
3856 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | RTOR000368/2023-2024 | MURD/439/12 | 08/02/2024 | 0 | Resource Division | 8.91 | 0 | 0
3857 | Berhampore Mechanical | Kandi Sub-Division | SHIFTING OF A PART OF EXISTING HTOH LINE AT BATI PWSS ID860318411 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | BILL/01113/2024-2025 |  | 25/11/2024 | 0 | WBSEDCL | 0.57 | 0 | 0
3858 | Berhampore Mechanical | Kandi Sub-Division | new service connection at BATI PH1 ID304200864,Application no.3004504556 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | BILL/01145/2023-2024 | 219/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 8.77 | 0 | 0
3859 | Berhampore Mechanical | Kandi Sub-Division | AT BATI PH 2 ID 304252900 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | BILL/01467/2023-2024 | 376/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 3.01 | 0 | 0
3860 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT BATI PH 2 CID 304252900 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | BILL/01492/2023-2024 |  | 16/02/2024 | 0 | WBSEDCL | 3.01 | 0 | 0
3861 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BATI ground water based water supply scheme under Block_ KANDI Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000668/2023-2024 | 4292/MEDB | 29/12/2023 | 91 | DAS ENTERPRISE ( MANGO LANE) | 22.1 | 0 | 0
3862 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.18 | 100
3863 | Murshidabad Division | Berhampur M/E Division | Formal work order for MAHENDRAPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jivan Mission of Suti-II Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000857/2022-2023 | 802/MURD | 22/03/2023 | 1016 | C.X. CONSTRUCTION & CO | 359.8 | 0 | 30
3864 | Murshidabad Division | Berhampur M/E Division | Installation of dual power based(Solar & electric) stand alone community purification plant(CWPP) FOR BALANCE 18 UNCOVERED habitations WHERE ARSENIC CONCENTRATION IS .01 TO .015 in the left out Arsenic affected habitations in the different block under Murshidabad Division P.H.E. Dte. at Murshidabad District. HABITATION-MAHENDRAPUR(4UNITS), VILLAGE-MAHENDRAPUR, BLOCK-SUTI-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/001629/2021-2022 | 459/MURD | 21/02/2022 | 45 | ULTRA CONSTRUCTION. | 51.83 | 0 | 10
3865 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000291/2023-2024 | 1230/MURD/33 | 04/05/2023 | 0 | Resource Division | 27.6 | 0 | 0
3866 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT MAHENDARPUR PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/00618/2024-2025 |  | 02/08/2024 | 0 | WBSEDCL | 3.83 | 0 | 0
3867 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT MAHENDARPUR PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/00631/2024-2025 | 187/WBSEDCL-JJM | 09/08/2024 | 0 | WBSEDCL | 3.83 | 0 | 0
3868 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT MAHENDRAPUR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | BILL/01246/2024-2025 |  | 13/12/2024 | 0 | WBSEDCL | 5.13 | 0 | 0
3869 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under MAHENDRAPUR ground water based water supply scheme under Block_ Suti-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000692/2023-2024 | 3811/MEDB | 03/11/2023 | 92 | B. T. PROJECTS PVT. LTD. | 34.2 | 0 | 0
3870 | Murshidabad Division | Berhampur M/E Division | Augmentation of NATIAL RAJANAGAR ZONE-I ,II,& III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000366/2023-2024 | 2724/MURD | 29/08/2023 | 765 | M/S. MOHAN LAL JAIN | 2092.12 | 48.17 | 56
3871 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 5.01 | 1
3872 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000256/2023-2024 | 1219/MURD/41 | 03/05/2023 | 0 | Resource Division | 31.36 | 0 | 0
3873 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000389/2023-2024 | 526/MURD/06 | 19/02/2024 | 0 | Resource Division | 14.88 | 0 | 0
3874 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000532/2024-2025 | 318/MEDB | 10/02/2025 | 89 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 46.34 | 0 | 0
3875 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Natial Rajanagar Zone-II Piped water supply scheme Block_Raninagar II Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000547/2024-2025 | 351/MEDB | 10/02/2025 | 89 | M/S S. S. ENTERPRISE (DOMKAL) | 45.27 | 0 | 0
3876 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, 2183 nos FHTC, construction of OHR (Capacity 350 cum), Repairing of OHR , Sinking of Tube Well , Repairing of pump house, Repairing of Boundary Wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Andhua Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000755/2023-2024 | 138/MURD | 16/01/2024 | 365 | NAYLA CONSTRUCTION | 836.98 | 0 | 35
3877 | Murshidabad Division | Berhampur M/E Division | Continuation work order for preparation of D.P.R. for Augmentation of Andhua Zone- II & Zone - III PWSS in Farakka Block in Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000879/2023-2024 | 3720/MURD | 05/12/2023 | 30 | M/S SOBHA & CO. | 4.51 | 0 | 100
3878 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000169/2023-2024 | 1180/MURD/21 | 29/04/2023 | 0 | Resource Division | 46.79 | 0 | 0
3879 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT ANDHUA Z2 PH 2 CID 304391007 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | BILL/01209/2024-2025 |  | 02/12/2024 | 0 | WBSEDCL | 14.3 | 0 | 0
3880 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-II under Andhua ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000220/2023-2024 | 3662/MEDB | 03/11/2023 | 92 | ARINDAM MAJUMDAR | 11.36 | 0 | 0
3881 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 8.3 | 1
3882 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
3883 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 300 & 100 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Joykrishnapur Zone-I, Zone- II & Sikdarpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000557/2023-2024 | 3243/MURD | 15/10/2023 | 365 | BIJAY CHOWDHURY | 894.65 | 0 | 0
3884 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000177/2023-2024 | 1180/MURD/24 | 29/04/2023 | 0 | Resource Division | 62.68 | 0 | 0
3885 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-II under Jaykrishnapur ground water based water supply scheme under Block_ Samserganj, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000251/2023-2024 | 3686/MEDB | 03/11/2023 | 92 | DIPALI CONSTRUCTION | 22.53 | 18.76 | 12
3886 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for LOKNATHPUR ZONE-II Ground Based Water Supply Scheme in Beldanga -II Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000037/2025-2026 | 1130/MURD | 16/05/2025 | 60 | MARUTI CONSTRUCTION AND CO. | 23.01 | 0 | 0
3887 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Loknathpur zone-II PWSS to accommodate FHTC of 600 nos household Laying Rising Main ,Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement), Construction of Boundary Wall of 170 m and Soil Investigation & 200 Cum Construction of OHR and Special repair and renovation of existing 2 (Two) Nos Pump House and Boundary wall at Berhampore Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000538/2023-2024 | 3147/MURD | 09/10/2023 | 220 | M H SUPPLIERS | 210.2 | 0 | 8
3888 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 2.84 | 80
3889 | Murshidabad Division | Berhampur Sub-Division | Laying Distribution System For Augmentation of Loknathpur Zone-II (Part-A) PWSS of Beldanga-II Block under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000868/2022-2023 | 847/MURD | 24/03/2023 | 830 | SOMA CONSTRUCTION | 154.95 | 0 | 40
3890 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/001641/2021-2022 | 480/MURD | 22/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 12.36 | 0
3891 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000024/2024-2025 | 1811/MURD/23 | 20/06/2024 | 0 | Resource Division | 7.29 | 0 | 0
3892 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000181/2023-2024 | 1180/MURD/29 | 29/04/2023 | 0 | Resource Division | 45.89 | 0 | 0
3893 | Berhampore Mechanical | Berhampur Sub-Division | NEW CONNECTION AT LOKNATHPUR Z-II PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | BILL/01577/2023-2024 | 417/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 4.52 | 0 | 0
3894 | Berhampore Mechanical | Berhampur Sub-Division | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Lalgola, Beldanga II and Bharatpur I and II block Under District Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000054/2025-2026 | 45/5 | 29/05/2025 | 92 | M/S S. S. ENTERPRISE (DOMKAL) | 16.41 | 0 | 0
3895 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-II under Loknathpur ground water based water supply scheme under Block_ Beldanga-II, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000252/2023-2024 | 3690/MEDB | 03/11/2023 | 92 | GOENKA ENTERPRISE | 33.83 | 0 | 0
3896 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of P.T.Rasulpur (Part - A) Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000797/2022-2023 | 602/MURD | 02/03/2023 | 1035 | M/S.TAPAS KUMAR CHAKRABORTY | 521.15 | 363.84 | 30
3897 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 7.53 | 1
3898 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000191/2023-2024 | 1210/MURD/12 | 02/05/2023 | 0 | Resource Division | 110.91 | 0 | 0
3899 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000393/2023-2024 | 526/MURD/03 | 19/02/2024 | 0 | Resource Division | 5.48 | 0 | 0
3900 | Berhampore Mechanical | Berhampur M/E Division | P T RASULPURE PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01522/2023-2024 | 418/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 3.99 | 0 | 0
3901 | Berhampore Mechanical | Berhampur M/E Division | P T RASULPUR PH-III | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01523/2023-2024 | 419/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 5.51 | 0 | 0
3902 | Berhampore Mechanical | Berhampur M/E Division | P T RASULPUR PH-IV | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01524/2023-2024 | 420/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 5.54 | 0 | 0
3903 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II , III ,IV & V under P.T.RASULPUR ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000112/2023-2024 | 3721/MEDB | 03/11/2023 | 669 | EASTERN INDIA SALES & SERVICE | 55.34 | 35.13 | 25
3904 | Murshidabad Division | Kandi Sub-Division | Formal work order for RAMNA BARAKHARI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission, Block- BHARATPUR-II of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000836/2022-2023 | 833/MURD | 23/03/2023 | 922 | PRIYANKA CONSTRUCTION | 483.93 | 59.94 | 7
3905 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000064/2023-2024 | 1043/MURD/7 | 19/04/2023 | 0 | Resource Division | 25.05 | 0 | 0
3906 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT RAMNABORKHARI PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00236/2024-2025 | 66/WBSEDCL-JJM | 09/05/2024 | 0 | WBSEDCL | 3.64 | 0 | 0
3907 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under RAMNA BARAKHARI ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000116/2023-2024 | 1905/MEDB | 16/06/2023 | 92 | DAS CONSTRUCTION | 22.81 | 0 | 8
3908 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Durgapur zone-III under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000054/2023-2024 | 150/BD-I | 15/05/2023 | 90 | SAHA CONSTRUCTION | 30.31 | 0 | 0
3909 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Durgapur Zone-III village, Block:- Lalgola under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000684/2023-2024 | 3613/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0
3910 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Khordda Narayanpur Part- B village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000237/2023-2024 | 2340/MURD | 03/08/2023 | 60 | CHOWDHURY CONSTRUCTION | 30.55 | 0 | 0
3911 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Khordda Narayanpur Part- A village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000257/2023-2024 | 2493/MURD | 11/08/2023 | 60 | M/S GREAT INDIA CONSTRUCTION | 30.54 | 0 | 0
3912 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Khordda Narayanpur Part-A village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000206/2023-2024 | 3066/MEDB | 02/08/2023 | 92 | M/S SAJAHAN CHOWDHURY | 6.27 | 0 | 0
3913 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Khordda Narayanpur Part-B village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000207/2023-2024 | 3067/MEDB | 02/08/2023 | 92 | JOY BISHNU ENGINEERING CO. | 6.3 | 0 | 0
3914 | Murshidabad Division | Berhampur M/E Division | Ground Water based piped water supply scheme for Gopjan (P) village, Block:- Berhampore, Berhampore Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000210/2023-2024 | 2321/MURD | 02/08/2023 | 60 | SUBHENDRA MOHAN SARKAR | 30.54 | 0 | 0
3915 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Gopjan (P) village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000191/2023-2024 | 3050/MEDB | 02/08/2023 | 92 | SARKAR CONSTRUCTION | 6.3 | 0 | 0
3916 | Murshidabad Division | Jangipur Sub-Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000001/2025-2026 | 761/MURD | 02/04/2025 | 80 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0
3917 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 1.82 | 100
3918 | Murshidabad Division | Jangipur Sub-Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
3919 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000087/2023-2024 | 1147/MURD/1 | 27/04/2023 | 0 | Resource Division | 177.04 | 0 | 0
3920 | Murshidabad Division | Berhampur M/E Division | Augmentation of Domkal Zone-II (Part-B) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000001/2023-2024 | 946/MURD | 05/04/2023 | 1002 | GOUTAM MANDAL | 337.24 | 131.01 | 60
3921 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
3922 | Berhampore Division I | Berhampur Division I | SAMASKAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000102/2023-2024 | 220/BD-I | 17/05/2023 | 960 | BINAPANI ENTERPRISE | 52.7 | 0 | 5
3923 | Berhampore Division I | Berhampur Division I | SAMASKAR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART -A) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000159/2023-2024 | 669/BD-I | 09/08/2023 | 723 | BAHETI CONSTRUCTION | 209.2 | 0 | 20
3924 | Berhampore Division I | Berhampur Division I | SAMASKAR PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000294/2022-2023 | 1824/BD-I | 31/03/2023 | 180 | ARINDAM MAJUMDAR | 109.77 | 0 | 0
3925 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000005/2023-2024 | 61/BD-1/6 | 27/04/2023 | 0 | Resource Division | 15.38 | 0 | 0
3926 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000023/2024-2025 | 2096/BD-I/4 | 25/11/2024 | 0 | Resource Division | 10 | 0 | 0
3927 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION SAMASKAR PH-I | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | BILL/01657/2023-2024 | 10/WBSEDCL-JJM | 09/04/2024 | 0 | WBSEDCL | 7.19 | 0 | 0
3928 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SAMSASKAR ground water based water supply scheme under Block_ Berhampore Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000701/2023-2024 | 4339/MEDB | 29/12/2023 | 91 | DEBJYOTI BASU | 20.87 | 0 | 10
3929 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of BRINDABANPUR ZONE-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000840/2022-2023 | 744/MURD | 16/03/2023 | 1021 | NATIONAL CONSTRUCTION (PROP:NIZAMUL BISWAS) | 487.63 | 270.52 | 45
3930 | Murshidabad Division | Berhampur M/E Division | Construction of Pump House, Boundary Wall, of BRINDABANPUR ZONE-II Ground water based Piped water supply scheme with in Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000844/2023-2024 | 778/MURD | 14/03/2024 | 524 | M/S S M ENTERPRISE | 28.51 | 0 | 65
3931 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 2.44 | 100
3932 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000263/2023-2024 | 1230/MURD/06 | 04/05/2023 | 0 | Resource Division | 4.02 | 0 | 0
3933 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION BRINDABANPUR Z2 PH2 ID304232743 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01218/2023-2024 | 266/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 4.96 | 0 | 0
3934 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT BRINDABANPUR Z2 PH I, ID304232742 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01227/2023-2024 | 267/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.88 | 0 | 0
3935 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000530/2024-2025 | 316/MEDB | 10/02/2025 | 89 | M/S SAMRIDDHI ENTERPRISE | 34.79 | 0 | 0
3936 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Brindabanpur Zone-II Piped water supply scheme Block_Raninagar II Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000545/2024-2025 | 349/MEDB | 10/02/2025 | 89 | MERCURY ENGINEERING CO | 37.15 | 0 | 0
3937 | Murshidabad Division | Kandi Sub-Division | PULIA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000097/2023-2024 | 1698/MURD | 28/06/2023 | 120 | ESCON INDIA | 134.38 | 42.88 | 10
3938 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000078/2023-2024 | 1129/MURD/1 | 25/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
3939 | Central Drilling | Kandi Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000209/2023-2024 | 2203/CDD | 01/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 10
3940 | Berhampore Mechanical | Kandi Sub-Division | Pulia PH-1 Application No-3004547904 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01172/2023-2024 | 235/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 5.22 | 0 | 0
3941 | Berhampore Mechanical | Kandi Sub-Division | Pulia PH-2 App No- 3004547976 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01173/2023-2024 | 236/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 5.46 | 0 | 0
3942 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Pulia ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000256/2023-2024 | 3692/MEDB | 03/11/2023 | 92 | ASHUTOSH DAS & CO. | 21.24 | 0 | 0
3943 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 4.02 | 100
3944 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHODARAMPUR (CT) AND PRASADPUR ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000369/2023-2024 | 2721/MURD | 29/08/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0
3945 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000497/2024-2025 | 660/MURD | 19/03/2025 | 90 | JOY GURU ENTERPRISE | 82.5 | 0 | 0
3946 | Murshidabad Division | Berhampur M/E Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
3947 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
3948 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000094/2023-2024 | 1147/MURD/9 | 27/04/2023 | 0 | Resource Division | 34.37 | 0 | 0
3949 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
3950 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BHASIPAIKAR ZONE-IIB Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000555/2023-2024 | 3194/MURD | 12/10/2023 | 21 | TAPAN DAS | 23.72 | 8.58 | 50
3951 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0
3952 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-II | Junior engineer-II | RTOR000121/2023-2024 | 1167/MURD/26 | 28/04/2023 | 0 | Resource Division | 61.81 | 0 | 0
3953 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHORSALA and KASIADANGA ZONE - I Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000370/2023-2024 | 2722/MURD | 29/08/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0
3954 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.36 | 100
3955 | Murshidabad Division | Berhampur M/E Division | Formal work order for GHORSALA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jivan Mission of raghunathganj-I Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000855/2022-2023 | 794/MURD | 21/03/2023 | 833 | DHIRENDRANATH MONDAL | 431.52 | 138.89 | 25
3956 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | RTOR000280/2023-2024 | 1230/MURD/22 | 04/05/2023 | 0 | Resource Division | 30.14 | 0 | 0
3957 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | RTOR000378/2023-2024 | 495/MURD/03 | 15/02/2024 | 0 | Resource Division | 9.2 | 0 | 0
3958 | Berhampore Mechanical | Berhampur M/E Division | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Jalangi , Raninagar I and II, Farakka, Raghunathganj I and II block Under District Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000052/2025-2026 | 45/3 | 29/05/2025 | 92 | M/S K.P. PRAMANIK | 19.57 | 0 | 0
3959 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under GHORSALA ground water based water supply scheme under Block_ Raghunathganj- I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000123/2023-2024 | 3724/MEDB | 03/11/2023 | 790 | WEST BENGAL ENGINEERING CO. | 33.53 | 0 | 30
3960 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Lahari under Bhagwangola-II block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000056/2023-2024 | 153/BD-I | 15/05/2023 | 90 | SANTA TRADING | 30.53 | 0 | 0
3961 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Lahari village, Block:- Bhagwangola-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000686/2023-2024 | 3615/MEDB | 03/11/2023 | 92 | AVINABA ENGINEERING CONCERN | 6.27 | 0 | 0
3962 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dayarampur (Village code 314617) under Narsinghpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184090 in the District of Murshidabad. |  |  | ORD/000468/2020-2021 | 531/MURD | 04/02/2021 | 60 | M/S. BIMALENDU BOSE | 44.35 | 0 | 1
3963 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baramasia (Village code 314622) under Narasinghapur Ground Water Supply Scheme for Arsenic Affected Area of Jalangi Block. under Murshidabad Division, PHE Dte. Scheme ID 0005184090 |  |  | ORD/000528/2022-2023 | 2418/MURD | 22/08/2022 | 180 | M/S. SINHA & SONS | 49.87 | 0 | 0
3964 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Baramasia (Village code 314622) under Narsinghpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184090 in the District of Murshidabad. |  |  | ORD/000578/2020-2021 | 530/MURD | 04/02/2021 | 60 | RELIABLE ENTERPRISE | 44.77 | 0 | 1
3965 | Murshidabad Division |  | Formal Work Order for ¿Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Narasinghapur (Village code 314620) under Narasinghapur Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184090 in the District of Murshidabad. (Sl No-18) |  |  | ORD/000628/2020-2021 | 697/MURD | 24/02/2021 | 180 | MANAB KUMAR GHOSH | 64.64 | 53.05 | 0
3966 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dayarampur (Village code 314617) under Narasinghapur Ground Water Supply Scheme for Arsenic Affected Area of Jalangi Block. under Murshidabad Division, PHE Dte. Scheme ID 0005184090 (SlNo-17) |  |  | ORD/001051/2021-2022 | 3684/MURD | 26/11/2021 | 180 | BENOY DOBAY | 46.91 | 46.85 | 1
3967 | Murshidabad Division |  | Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block (Giria, Sekendra, Mithipur, Jotkamal, Dayarampur, Sammatinagar, Teghari, Kasiadanga, laxmijhola & Sekhalipur) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. |  |  | ORD/001183/2021-2022 | 371/JSD | 22/12/2021 | 30 | IMAGIN | 3.99 | 0 | 1
3968 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Godagari ( Village Code -314615) under Narsinghpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184090) |  |  | ORD/001465/2021-2022 | 280/MURD | 03/02/2022 | 60 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 59.67 | 33.89 | 1
3969 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 495 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Narasinghpur (Village code 314620) under Narasinghpur Ground water based water supply scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005184090). |  |  | ORD/001723/2021-2022 | 705/MURD | 14/03/2022 | 15 | M/S. GHOSH ENTERPRISE | 12.87 | 12.42 | 1
3970 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 395/MURD | 16/02/2022 | 0 | Resource Division | 8.08 | 0 | 0
3971 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village DAYARAMPUR (Village Code 314617) under NARASINGHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 295 of 21-22 by EE MURD |  |  | VCH/001488/2021-2022 | 418-MSD/21-22 | 23/03/2022 | 0 | M/S. BIMALENDU BOSE | 32.54 | 0 | 0
3972 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village GODAGARI (Village Code 314615) under NARSINGHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 664 of 21-22 by EE MURD |  |  | VCH/001509/2021-2022 | 404-MSD/21-22 | 22/03/2022 | 0 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 26.24 | 0 | 0
3973 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 100 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for BALLALPUR Ground Based Water Supply Scheme in Farakka Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000055/2025-2026 | 1228/MURD | 28/05/2025 | 60 | MONDAL PRECISION PRIVATE LIMITED | 40.44 | 0 | 0
3974 | Murshidabad Division | Berhampur M/E Division | Providing balance Functional Household Tap Connections (FHTC) of 405 nos household in connection with Jal Jeevan Mission under command area of village of Ballalpur (Village Code -313811) under Ballalpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000165/2023-2024 | 1934/MURD | 18/07/2023 | 30 | TARIKUL SK | 14.95 | 14.95 | 100
3975 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 6.15 | 1
3976 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
3977 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main , Distribution System, 279 nos FHTC, construction of OHR (Capacity 400 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Ballalpur PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000516/2023-2024 | 3115/MURD | 05/10/2023 | 635 | M/S GANGWAL CONSTRUCTION CO | 338.54 | 0 | 50
3978 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III, IV of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Ballalpur Water Supply Scheme at Head Work Site, 2nd Site site at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000694/2023-2024 | 3780/MURD | 11/12/2023 | 21 | HARUN ALL RASHID & BROTHERS | 27.6 | 0 | 0
3979 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000175/2023-2024 | 1180/MURD/30 | 29/04/2023 | 0 | Resource Division | 91.87 | 0 | 0
3980 | Berhampore Mechanical | Berhampur M/E Division | POWER CONNECTION AT PWSS PH2 BALLALPUR APPLICATION NO.3004627376 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | BILL/00187/2024-2025 | 37/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 4.83 | 0 | 0
3981 | Berhampore Mechanical | Berhampur M/E Division | POWER CONNECTION AT PWSS PH3 BALLALPUR APPLICATION NO.3004626223 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | BILL/00189/2024-2025 | 38/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 6.08 | 0 | 0
3982 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II under Ballalpur ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000262/2023-2024 | 3698/MEDB | 03/11/2023 | 790 | P. K. ENGINEERING | 22.55 | 0 | 70
3983 | Murshidabad Division | Berhampur M/E Division | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/07/2024 to 16/01/2025. [ Vehicle No:- WB 58 CD 3758] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000090/2024-2025 | 52/JSD | 16/07/2024 | 184 | HASSAN CONSTRUCTION | 0.88 | 0 | 0
3984 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 200 cum), Sinking of Tube Well , and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Basudevpur Zone-II PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000384/2023-2024 | 2770/MURD | 01/09/2023 | 365 | M/S TRADE ASSOCIATE | 261.08 | 0 | 0
3985 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.26 | 100
3986 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
3987 | Murshidabad Division | Kandi Sub-Division | KOLLA PWSS to accommodate FHTC under Jal Jeevan Mission of Block-Bharatpur-I of Kandi Sub Division of Murshidabad District under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000018/2023-2024 | 981/MURD | 10/04/2023 | 1022 | SOM CONSTRUCTION AGENCY | 189.17 | 68.13 | 70
3988 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000071/2023-2024 | 1075/MURD/13 | 19/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
3989 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Kolla ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000272/2023-2024 | 3710/MEDB | 03/11/2023 | 92 | WEST BENGAL ENGINEERING CO. | 22.12 | 0 | 0
3990 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 4.5 | 100
3991 | Murshidabad Division | Berhampur M/E Division | Formal work order for the Work of BAHARAGACHI PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Samserganj Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000821/2022-2023 | 655/MURD | 06/03/2023 | 1032 | ARINDAM MAJUMDAR | 266.77 | 0 | 25
3992 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000273/2023-2024 | 1230/MURD/16 | 04/05/2023 | 0 | Resource Division | 21.39 | 0 | 0
3993 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I II & III under BAHARAGACHI ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000082/2023-2024 | 1899/MEDB | 16/06/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 32.57 | 25.66 | 20
3994 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.85 | 100
3995 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0
3996 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
3997 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000089/2023-2024 | 1147/MURD/3 | 27/04/2023 | 0 | Resource Division | 128.8 | 0 | 0
3998 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
3999 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under Madna ground water based water supply scheme under Block_ Suti-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000041/2023-2024 | 1878/MEDB | 16/06/2023 | 92 | M/S. SUPER CONSTRUCTION | 35.74 | 15.06 | 4
4000 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-II under MADNA ground water based water supply scheme under Block_ Siti-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000115/2023-2024 | 1904/MEDB | 16/06/2023 | 92 | JOY BISHNU ENGINEERING CO. | 23 | 0 | 0
4001 | Murshidabad Division | Kandi Sub-Division | Construction of Boundwary Wall , PCC Approach road of Basantapur PWSS in Khargram Block , Kandi Sub-Division under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000010/2025-2026 | 898/MURD | 23/04/2025 | 60 | M.R. ENTERPRISE (MD. HASANUZZAMAN) | 10.43 | 0 | 0
4002 | Murshidabad Division | Kandi Sub-Division | Construction of Pump House , Land Development Work of Basantapur PWSS in Khargram Block , Kandi Sub-Division under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000012/2025-2026 | 901/MURD | 23/04/2025 | 343 | NOBEL CONSTRUCTION | 10.68 | 0 | 50
4003 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Basantapur & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000037/2023-2024 | 1104/MURD | 24/04/2023 | 30 | NADIA TUBEWELLS | 21.35 | 8.8 | 50
4004 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BASANTPUR AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Khargram Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000290/2023-2024 | 2656/MURD | 24/08/2023 | 21 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 0
4005 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System , Rising Main Connection FHTC, Construction of Pump House & Boundary Wall for Basantapur water supply scheme of Khargram Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000892/2022-2023 | 929/MURD | 31/03/2023 | 793 | PARTHA PRATIM DAS | 61.73 | 27.49 | 30
4006 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000071/2022-2023 | 1075/MURD/7 | 19/04/2023 | 0 | Resource Division | 18.61 | 0 | 0
4007 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT BASANTIPUR PH I, ID304233690 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01212/2023-2024 | 274/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 4.96 | 0 | 0
4008 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BASANTAPUR ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000050/2023-2024 | 1924/MEDB | 16/06/2023 | 746 | MAHADEB ENTERPRISE | 20.81 | 0 | 50
4009 | Murshidabad Division | Berhampur M/E Division | COST OF RESTORATION OF ROAD CONNECTTED TO NH-34 DHULIAN PAKUR ROAD AT CH. 4.275 TO 4.600. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | BILL/01019/2024-2025 | 369-MSD/2024-20 | 12/09/2024 | 0 | MURSHIDABAD HIGHWAY DIVISION-1 | 13.3 | 0 | 0
4010 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000497/2024-2025 | 660/MURD | 19/03/2025 | 90 | JOY GURU ENTERPRISE | 82.5 | 0 | 0
4011 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.16 | 100
4012 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sagarpara Part-A, Kohetpur and Napara Water Supply Scheme under Islampur & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000668/2022-2023 | 3409/MURD | 22/12/2022 | 45 | R.K. DRILLING SERVICES | 23.56 | 0 | 0
4013 | Murshidabad Division | Berhampur M/E Division | Formal work order for the work of KOHETPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission of SAMSERGANJ Block, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000812/2022-2023 | 670/MURD | 09/03/2023 | 762 | PRAFULLYA CONSTRUCTION | 379.82 | 89.39 | 22
4014 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | RTOR000286/2023-2024 | 1230/MURD/29 | 04/05/2023 | 0 | Resource Division | 22.56 | 0 | 0
4015 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | RTOR000373/2023-2024 | 495/MURD/08 | 15/02/2024 | 0 | Resource Division | 8.37 | 0 | 0
4016 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
4017 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT KOHETPUR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | BILL/00422/2024-2025 | 143/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
4018 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT KOHETPUR PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | BILL/00423/2024-2025 | 144/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 4.92 | 0 | 0
4019 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under KOHETPUR ground water based water supply scheme under Block_ Samsedganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000690/2023-2024 | 4304/MEDB | 29/12/2023 | 91 | BHABANI PRASAD MANNA | 32.99 | 0 | 0
4020 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No of 250mm x 150 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHAYRAMARI Part-A and Salar Zone - IIB Water Supply Scheme as required under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000103/2023-2024 | 1744/MURD | 06/07/2023 | 14 | SARKAR WATER SUPPLY AGENCY | 9.22 | 0 | 100
4021 | Murshidabad Division | Kandi Sub-Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
4022 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based Surangapur Zone - II (PART -A), Salar PWSS Zone-IA, IB, IIA & IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Nowda & Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 570 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 20
4023 | Murshidabad Division | Kandi Sub-Division | Augmentation of Salar PWSS Zone-IA,IB,IIA,IIB to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 4 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 4no, Construction of Boundary Wall of 600 m, Construction of 400 Cum OHR(1 no) & 300 Cum OHR(2 nos) with sub soil investigation under Jal Jeevan Mission of Bharatpur II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000647/2023-2024 | 3474/MURD | 07/11/2023 | 511 | SUJIT KUMAR SAHA | 575.6 | 0 | 10
4024 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone- II B Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000696/2023-2024 | 3781/MURD | 11/12/2023 | 21 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 0
4025 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT SALAR Z-II/B PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/01221/2024-2025 | 299/WBSEDCL-JJM | 06/12/2024 | 0 | WBSEDCL | 6.15 | 0 | 0
4026 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II ,Zone-IIB under Salar ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000240/2023-2024 | 3676/MEDB | 03/11/2023 | 457 | DAS ENTERPRISE (CHOA) | 21.42 | 0 | 8
4027 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
4028 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0
4029 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000120/2023-2024 | 1167/MURD/25 | 28/04/2023 | 0 | Resource Division | 60.5 | 0 | 0
4030 | Berhampore Mechanical | Berhampur M/E Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II , Zone-IB under Bhasaipaikar ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/001483/2023-2024 | 762/MEDB | 20/02/2024 | 90 | SARKAR CONSTRUCTION | 23.13 | 0 | 0
4031 | Murshidabad Division | Berhampur M/E Division | Balance work of Laying Distribution System , Road Restoration and other ancillary works of Tejsinghapur Water Supply Scheme within Raninagar-II Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000073/2025-2026 | 1259/MURD | 30/05/2025 | 60 | DAS TRADING CO. | 64.29 | 0 | 0
4032 | Murshidabad Division | Berhampur M/E Division | Augmentation of TEJSINGHAPUR PWSS under Jal Jivan Mission of RANINAGAR - II Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000078/2023-2024 | 1383/MURD | 22/05/2023 | 955 | PRADIP KUMAR DAS | 294.57 | 142.98 | 86
4033 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dhulauri Water Supply Scheme and Tejsinghapur Water Supply Schem under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000104/2023-2024 | 1746/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 100
4034 | Murshidabad Division | Berhampur M/E Division | Augmentation of TEJSINGHAPUR PWSS under Jal Jeevan Mission of RANINAGAR - II Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (PART - B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000164/2023-2024 | 1933/MURD | 18/07/2023 | 898 | VOICE CONSTRUCTION | 293.06 | 0 | 35
4035 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Tajsinghapur PWSS Scheme, Block - Raninagar-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000832/2021-2022 | 3265/MURD | 05/10/2021 | 60 | RADIANT | 4.74 | 4.74 | 1
4036 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000150/2023-2024 | 1167/MURD/39 | 28/04/2023 | 0 | Resource Division | 79.35 | 0 | 0
4037 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000564/2024-2025 | 346/MEDB | 10/02/2025 | 89 | DAS ENTERPRISE (CHOA) | 23.19 | 0 | 0
4038 | Murshidabad Division | Kandi Sub-Division | Augmentation of BHARATPUR (ZONE -IIA) PWSS under Jal Jeevan Mission of Bharatpur-I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000501/2023-2024 | 3088/MURD | 03/10/2023 | 814 | SOFIQUL ISLAM | 423.46 | 0 | 50
4039 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 4.68 | 80
4040 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 4.06 | 76
4041 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 8.04 | 11
4042 | Murshidabad Division | Kandi Sub-Division | Laying UPVC Pipe line , Road Restoration & FHTCs of Dakshin Raypur PWSS in Khargram Block of Kandi Sub Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000188/2024-2025 | 3146/MURD | 03/12/2024 | 30 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 19.79 | 0 | 0
4043 | Murshidabad Division | Kandi Sub-Division | Formal work order for DAKSHIN RAYPUR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of BURWAN Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000804/2022-2023 | 623/MURD | 03/03/2023 | 730 | DIPAYAN DEY | 393.85 | 238.22 | 31
4044 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000059/2023-2024 | 1075/MURD/3 | 19/04/2023 | 0 | Resource Division | 13 | 0 | 0
4045 | Berhampore Mechanical | Kandi Sub-Division | Electric Service New Connection DAKSHIN RAYPUR PH 2 PWSS Application NO. 3004475666. ID. 304178072 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01037/2023-2024 | 172/WBSEDCL-JJM | 05/12/2023 | 0 | WBSEDCL | 9.51 | 0 | 0
4046 | Berhampore Mechanical | Kandi Sub-Division | Electric Service Connection at Dakshin Raypur PH I, Application NO.3004475701, ID 304179843 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01054/2023-2024 | 188/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 12.03 | 0 | 0
4047 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Dakshin Raypur ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000120/2023-2024 | 1909/MEDB | 16/06/2023 | 929 | M/S SAMRIDDHI ENTERPRISE | 22.82 | 16.98 | 20
4048 | Murshidabad Division |  | Last mile connectivity and providing 3874 nos Functional House Hold Connection from Zone- IX of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. |  |  | ORD/000332/2023-2024 | 2689/MURD | 25/08/2023 | 120 | SUJIT KUMAR SAHA | 223.42 | 0 | 0
4049 | Murshidabad Division |  | Last mile connectivity and providing 8231 nos Functional House Hold Connection from Zone- X of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . |  |  | ORD/000333/2023-2024 | 2690/MURD | 25/08/2023 | 120 | HANNAN BUILDERS PVT.LTD. | 475.31 | 0 | 0
4050 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 4.47 | 100
4051 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of Aminabad Zone-II Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000846/2022-2023 | 773/MURD | 17/03/2023 | 881 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 726.14 | 33.64 | 35
4052 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000197/2023-2024 | 1210/MURD/15 | 02/05/2023 | 0 | Resource Division | 37.48 | 0 | 0
4053 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT AMINABAD Z-II PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | BILL/00175/2024-2025 | 15/WBSEDCL-JJM | 16/04/2024 | 0 | WBSEDCL | 13.07 | 0 | 0
4054 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT AMINABAD Z-II PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | BILL/00176/2024-2025 | 16/WBSEDCL-JJM | 16/04/2024 | 0 | WBSEDCL | 6.25 | 0 | 0
4055 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV ,Zone-II under AMINABAD ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000077/2023-2024 | 3763/MEDB | 03/11/2023 | 92 | B. T. PROJECTS PVT. LTD. | 45.69 | 0 | 0
4056 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
4057 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 12.8 | 20
4058 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at DIAR FATEPUR PWSS under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidbad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000072/2025-2026 | 839/BD-I | 23/06/2025 | 15 | B.M. ENGINEERING & CONSTRUCTION | 8.99 | 0 | 0
4059 | Berhampore Division I | Berhampur M/E Division | DIAR FATHEPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000085/2023-2024 | 205/BD-I | 17/05/2023 | 1001 | ANKITA ENTERPRISE-GOPEJAN(NATHPARA) | 40.93 | 18.13 | 35
4060 | Berhampore Division I | Berhampur M/E Division | DIAR FATHEPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 450 cum) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000129/2023-2024 | 606/BD-I | 02/08/2023 | 787 | M/S J.S ENTERPRISE | 362.92 | 109.31 | 30
4061 | Berhampore Division I | Berhampur M/E Division | DIAR FATHEPUR PWSS to accommodate FHTC Laying distribution system under Jal Jeevan Mission of Lalgola Block Murshidabad District under Berhampore Division-I, PHE Dte. (Part-B) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000258/2023-2024 | 973/BD-I | 18/10/2023 | 622 | SWAPAN DAS | 95.38 | 0 | 30
4062 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000042/2023-2024 | 61/BD-1/32 | 27/04/2023 | 0 | Resource Division | 38.25 | 0 | 0
4063 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000110/2023-2024 | 304/BD-1/4 | 22/02/2024 | 0 | Resource Division | 19.21 | 0 | 0
4064 | Berhampore Mechanical | Berhampur M/E Division | Quotation for WBSEDCL for Diar Fatepur Application No- 3004544437 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/01171/2023-2024 | 233/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 4.89 | 0 | 0
4065 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III under DIAR FATEPUR ground water based water supply scheme under Block_ LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000027/2025-2026 | 1160/MEDB | 15/05/2025 | 92 | SAMARPITA ENGINEERING | 10.93 | 0 | 0
4066 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 6.39 | 11
4067 | Berhampore Division I | Berhampur Division I | SHUKUR PUKUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000087/2023-2024 | 207/BD-I | 17/05/2023 | 865 | ABIDA CONSTRUCTION | 40.82 | 0 | 51
4068 | Berhampore Division I | Berhampur Division I | SHUKUR PUKUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000133/2023-2024 | 612/BD-I | 02/08/2023 | 697 | NOVELTY CONSTRUCTION | 52.15 | 0 | 60
4069 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SUKURPUKUR Water Supply Scheme(2nd TW Site) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000323/2024-2025 | 262/BD-I | 07/02/2025 | 183 | SINGHA AND CO. | 9 | 0 | 100
4070 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000024/2024-2025 | 2096/BD-I/5 | 25/11/2024 | 0 | Resource Division | 3.7 | 0 | 0
4071 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000047/2023-2024 | 61/BD-1/34 | 27/04/2023 | 0 | Resource Division | 8.65 | 0 | 0
4072 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION AT SUKURPUKUR PH-1 | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | BILL/00616/2024-2025 | 183/WBSEDCL-JJM | 09/08/2024 | 0 | WBSEDCL | 10.55 | 0 | 0
4073 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHAK RAMPRASAD and Dakshin Khanda Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000388/2023-2024 | 2778/MURD | 01/09/2023 | 14 | SARKAR WATER SUPPLY AGENCY | 9.21 | 0 | 100
4074 | Murshidabad Division | Kandi Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at, Dakshinkhanda Zone-IA T.W-II, III, Zone-IB T.W-II, Dakshinkhanda Zone-II T.W- I, II Water Supply Scheme of Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000506/2024-2025 | 718/MURD | 25/03/2025 | 65 | MAMATA USHA ENTERPRISE | 58.95 | 0 | 0
4075 | Murshidabad Division | Kandi Sub-Division | Augmentation of DAKSHIN KHANDA (ZONE - IA) PWSS under Jal Jeevan Mission of Bharatpur-II Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000537/2023-2024 | 3146/MURD | 09/10/2023 | 540 | DHIRENDRANATH MONDAL | 457.09 | 34.9 | 10
4076 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.45 | 80
4077 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000018/2025-2026 | 1146/MEDB | 14/05/2025 | 92 | M/S SAJAHAN CHOWDHURY | 24.86 | 0 | 0
4078 | Murshidabad Division | Kandi Sub-Division | JAGANNATHPUR PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000659/2023-2024 | 3528/MURD | 10/11/2023 | 507 | SOUMYADIP MISRA | 367.89 | 0 | 25
4079 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | RTOR000077/2023-2024 | 1075/MURD/19 | 19/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
4080 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT JAGANNATHPUR PH I, ID304233735 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | BILL/01208/2023-2024 | 261/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 6.64 | 0 | 0
4081 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT JAGANNATHPUR PH II, ID304233698 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | BILL/01209/2023-2024 | 262/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 5.04 | 0 | 0
4082 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Jagannathpur ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000250/2023-2024 | 3685/MEDB | 03/11/2023 | 92 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 22.23 | 0 | 0
4083 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based Nagar Zone II PWSS of accommodate FHTC( 1909 Nos), Laying Distribution System, Laying Rising Main, Switch Room, Boundary Wall, 300 CUM OHR in Khargram Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000574/2023-2024 | 3299/MURD | 20/10/2023 | 773 | CREATIVE CONSTRUCTION | 394.26 | 0 | 10
4084 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Nagar Zone- II Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Khargram Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000717/2023-2024 | 3834/MURD | 14/12/2023 | 21 | MAMATA USHA ENTERPRISE | 23.59 | 16.34 | 50
4085 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000016/2023-2024 | 1004/MURD/6 | 11/04/2023 | 0 | Resource Division | 24.92 | 0 | 0
4086 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000114/2023-2024 | 1167/MURD/15 | 28/04/2023 | 0 | Resource Division | 20.22 | 0 | 0
4087 | Berhampore Mechanical | Kandi Sub-Division | POWER CONNECTION AT PWSS NAGAR PH1 Z2 ID 304250315 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00180/2024-2025 | 35/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 7.14 | 0 | 0
4088 | Berhampore Mechanical | Kandi Sub-Division | POWER CONNECTION AT PWSS PH 2 Z 2 NAGAR ID 304250316 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00181/2024-2025 | 36/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 4.13 | 0 | 0
4089 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-II under Nagar ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000274/2023-2024 | 3714/MEDB | 03/11/2023 | 92 | A.G. ENTERPRISE | 22.35 | 0 | 0
4090 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Alikpur Village (Code-315626), Mashimpur Village (Code-315627), Sekandarpur (Code-315628) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000100/2024-2025 | 1440/BD-I | 04/09/2024 | 60 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 26.67 | 0 | 0
4091 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Alikpur(Village code 315626), Mashimpur (Village code 315627),Sekandarpur(Village code 315628) under Mashimpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | Assistant Engineer-II | Junior Engineer-I | ORD/000209/2021-2022 | 1007/BD-I | 21/06/2021 | 30 | KAMIRUL SK AND CO. | 65.2 | 60.17 | 1
4092 | Murshidabad Division | Lalbag Sub-Division | Work order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Assistant Engineer, Lalbagh Sub-Division, P.H.E. Dte. For 176 Days i.e. form 08.04.2025 to 30.09.2025. (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order). (Vehicle No.WB58AX9595) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000005/2025-2026 | 133/LSD | 07/04/2025 | 176 | BARI ENTERPRISE | 0.86 | 0 | 0
4093 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000349/2022-2023 | 1928/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 8.78 | 2.23 | 100
4094 | Murshidabad Division | Lalbag Sub-Division | Laying of Rising main , Distribution System, FHTC, construction of OHR , Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone I PWSS in Lalgola Block , Dhusaripara PWSS in Block- Samserganj, District Murshidabad of Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000544/2023-2024 | 3149/MURD | 09/10/2023 | 905 | J.S. CONSTRUCTION | 507.37 | 0 | 50
4095 | Murshidabad Division | Lalbag Sub-Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-I Water Supply Scheme at Head work Site site at LALGOLA Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000698/2023-2024 | 3783/MURD | 11/12/2023 | 21 | NILAVA GHOSHAL (BUMBA) | 11.77 | 0 | 0
4096 | Murshidabad Division | Lalbag Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | RTOR000125/2023-2024 | 1167/MURD/16 | 28/04/2023 | 0 | Resource Division | 18.84 | 0 | 0
4097 | Berhampore Mechanical | Lalbag Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-I , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000551/2024-2025 | 333/MEDB | 10/02/2025 | 89 | TARUN KUMAR BHATTACHARYA | 23.74 | 0 | 0
4098 | Berhampore Mechanical | Lalbag Sub-Division | Continuation Order Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Assistant Engineer-I under Office of the Executive Engineer, Mechanical/electrical Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000782/2023-2024 | 3360/AE/MEDB | 26/09/2023 | 182 | M/S SAJAHAN CHOWDHURY | 0.9 | 2.36 | 0
4099 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 27.84 | 11
4100 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of GHOLLA PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000022/2025-2026 | 639/BD-I | 25/04/2025 | 60 | SAIF TRADERS | 19 | 0 | 0
4101 | Berhampore Division I | Berhampur M/E Division | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Gholla" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-119 Cum/hr.) Type-1 - Fully Gravity System with RG Filter | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000035/2024-2025 | 999/BD-I | 20/06/2024 | 730 | M/S GOUTAM CHAKRABORTY | 272.44 | 0 | 0
4102 | Berhampore Division I | Berhampur M/E Division | GHOLLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000150/2023-2024 | 660/BD-I | 08/08/2023 | 730 | GITA CONSTRUCTION | 69.92 | 0 | 40
4103 | Berhampore Division I | Berhampur M/E Division | Allied works for upgradation ,Improvement and laying of "GHOLLA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART A)". | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000156/2024-2025 | 1644/BD-I | 23/10/2024 | 223 | GITA CONSTRUCTION | 16.79 | 0 | 90
4104 | Berhampore Division I | Berhampur M/E Division | GHOLLA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000163/2023-2024 | 648/BD-I | 08/08/2023 | 689 | HARAPRASAD DAS | 118.61 | 0 | 65
4105 | Berhampore Division I | Berhampur M/E Division | GHOLLA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000164/2023-2024 | 647/BD-I | 08/08/2023 | 180 | M/S JHA CONSTRUCTION | 180.62 | 0 | 0
4106 | Berhampore Division I | Berhampur M/E Division | GHOLLA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART A) | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000165/2023-2024 | 649/BD-I | 08/08/2023 | 1028 | RAJ KUMAR MONDAL | 404.58 | 0 | 50
4107 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHOLLA PWSS (3rd TW Site) under Jal Jeevan Mission in Beldanga-II Block under Berhampore Division-I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000383/2024-2025 | 445/BD-I | 20/03/2025 | 15 | MARUTI CONSTRUCTION & CO. | 9.01 | 0 | 0
4108 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-II | Junior engineer-III | RTOR000020/2024-2025 | 2096/BD-I/1 | 25/11/2024 | 0 | Resource Division | 29.76 | 0 | 0
4109 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-II | Junior engineer-III | RTOR000102/2023-2024 | 201/BD-1/1 | 10/02/2024 | 0 | Resource Division | 25 | 0 | 0
4110 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT GHOLLA PH-I | ASSISTANT ENGINEER-II | Junior engineer-III | BILL/00172/2024-2025 | 14/WBSEDCL-JJM | 16/04/2024 | 0 | WBSEDCL | 5.35 | 0 | 0
4111 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 4.25 | 100
4112 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 300 & 900 cum), Sinking of Tube Well and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Arjunpur Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000547/2023-2024 | 3177/MURD | 11/10/2023 | 730 | M/S. CHAKRABORTY & COMPANY | 2041.06 | 0 | 35
4113 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000141/2023-2024 | 1210/MURD/31 | 02/05/2023 | 0 | Resource Division | 64.61 | 0 | 0
4114 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT ARJUNPUR PWSS Z2 PH1 ID 304391006 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01142/2024-2025 |  | 27/11/2024 | 0 | WBSEDCL | 4.49 | 0 | 0
4115 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II,III ,IV & V ,Zone-II under ARJUNPUR ground water based water supply scheme under Block_ FARAKKA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000693/2023-2024 | 3865/MEDB | 07/11/2023 | 92 | WEST BENGAL ENGINEERING CO. | 52.01 | 0 | 0
4116 | Murshidabad Division | Berhampur M/E Division | Augmentation of NATIAL RAJANAGAR ZONE-I ,II,& III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000366/2023-2024 | 2724/MURD | 29/08/2023 | 765 | M/S. MOHAN LAL JAIN | 2092.12 | 100 | 56
4117 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 2.75 | 1
4118 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000257/2023-2024 | 1219/MURD/42 | 03/05/2023 | 0 | Resource Division | 27.39 | 0 | 0
4119 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000390/2023-2024 | 526/MURD/07 | 19/02/2024 | 0 | Resource Division | 18.07 | 0 | 0
4120 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT NATIAL RAJA NAGAR Z3 PH 1 ID 304516689 | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01144/2024-2025 |  | 27/11/2024 | 0 | WBSEDCL | 9.36 | 0 | 0
4121 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Natial Rajnagar Zone-III Pipe Water Supply Scheme Block - Jalangi District - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000533/2024-2025 | 319/MEDB | 10/02/2025 | 291 | ORIENTAL ENGINEERING CO. | 45.45 | 0 | 20
4122 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Natialrajanagar Zone-III Piped water supply scheme Block_Jalangi Dist_Murshidabad under MEDB PHE Dte. " | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000549/2024-2025 | 352/MEDB | 10/02/2025 | 89 | M/S SAJAHAN CHOWDHURY | 45.41 | 0 | 25
4123 | Murshidabad Division | Jangipur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 90 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for HASIMPUR Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000019/2025-2026 | 964/MURD | 30/04/2025 | 60 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 37.67 | 0 | 0
4124 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 10
4125 | Murshidabad Division | Jangipur Sub-Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
4126 | Murshidabad Division | Jangipur Sub-Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Hasimpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000762/2023-2024 | 185/MURD | 18/01/2024 | 683 | SAMIRAN KUMAR CHAKRABORTY | 485.31 | 0 | 60
4127 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | RTOR000145/2023-2024 | 1210/MURD/30 | 02/05/2023 | 0 | Resource Division | 158.82 | 0 | 0
4128 | Berhampore Mechanical | Jangipur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-III & IV under Hasimpur ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000037/2023-2024 | 1876/MEDB | 16/06/2023 | 92 | ABHISEK ENGINEERING CONCERN | 20.73 | 0 | 0
4129 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based JOT KAMAL (ZONE-I), JOTKAMAL (Zone-II) & JOTKAMAL (Zone-III) PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000282/2023-2024 | 2643/MURD | 23/08/2023 | 587 | M/S NIRAPADA BHATTACHARJEE | 1194.05 | 0 | 10
4130 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.68 | 100
4131 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000249/2023-2024 | 1219/MURD/35 | 03/05/2023 | 0 | Resource Division | 45.55 | 0 | 0
4132 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Jot Kamal Zone-III Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000531/2024-2025 | 317/MEDB | 10/02/2025 | 89 | M/S SAJAHAN CHOWDHURY | 34.06 | 0 | 0
4133 | Murshidabad Division | Lalbag Sub-Division | Sinking of 300x200 mm dia 2nos. Rig Bore Tube Well With Pumphouse of Mouza Radhakrishnapur, Malatipur, Khalifabaj, Sahabazpur, Paharpur, Krishnapur (314148,314149,314150,314151,314153),of Lalgola and Brindabanpur Zone - I PWSS under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER |  | ORD/000132/2022-2023 | 1202/MURD | 10/05/2022 | 60 | M/S GUHA & ROY ENTERPRISE | 30.54 | 0 | 0
4134 | Berhampore Mechanical | Lalbag Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under Lalgola ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER |  | ORD/001437/2023-2024 | 4340/MEDB | 29/12/2023 | 91 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 21.62 | 0 | 0
4135 | Murshidabad Division | Berhampur M/E Division | BAHAGALPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000498/2023-2024 | 3053/MURD | 29/09/2023 | 731 | ASTRA | 606.64 | 170.86 | 41
4136 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 8.44 | 100
4137 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000252/2023-2024 | 1219/MURD/37 | 03/05/2023 | 0 | Resource Division | 50.34 | 0 | 0
4138 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 21.56 | 11
4139 | Berhampore Mechanical | Berhampur M/E Division | BAHAGALPUR PH-I NEW CONNECTION | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01485/2023-2024 | 424/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 4.25 | 0 | 0
4140 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION BHAGALPUR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01489/2023-2024 | 411/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 3.3 | 0 | 0
4141 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION BAHAGALPUR PH-III | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01576/2023-2024 | 412/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
4142 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION BAHAGALPUR PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01605/2023-2024 |  | 06/03/2024 | 0 | WBSEDCL | 4.25 | 0 | 0
4143 | Murshidabad Division | Berhampur M/E Division | Construction of Ground Water Based Srikantabati Part B PWSS of accommodate FHTC(2619 Nos), Laying Distribution System, Laying Rising Main, 400 CUM OHR, Switch Room, Boundary Wall in Raghunathganj- I Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000308/2023-2024 | 2675/MURD | 24/08/2023 | 365 | KEYA CONSTRUCTION | 437.95 | 0 | 0
4144 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 6.43 | 100
4145 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SRIKANTABATI PART B & JOTKAMAL ZONE -II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000620/2023-2024 | 3395/MURD | 01/11/2023 | 21 | KALACHAND DAS | 18.4 | 0 | 100
4146 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | RTOR000240/2023-2024 | 1219/MURD/32 | 03/05/2023 | 0 | Resource Division | 22.44 | 0 | 0
4147 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | RTOR000380/2023-2024 | 495/MURD/01 | 15/02/2024 | 0 | Resource Division | 16.13 | 0 | 0
4148 | Berhampore Mechanical | Berhampur M/E Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under SRIKANTABATI, PART B ground water based water supply scheme under Block_ RAGHUNATHGANJ-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000463/2023-2024 | 586/MEDB | 31/01/2024 | 90 | M/S. SUPER CONSTRUCTION | 35.75 | 0 | 0
4149 | Murshidabad Division | Berhampur M/E Division | Allied work in connection with Augmentation & Rejuvenation of Birendranagar (Zone-II) Pipe water supply scheme, Block- Raghunathganj-II, District-Murshidabad, Under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000027/2024-2025 | 1842/MURD | 25/06/2024 | 30 | M.R. ENTERPRISE (MD. HASANUZZAMAN) | 17.49 | 0 | 100
4150 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 2.8 | 100
4151 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System with FHTC to 560nos household, Rising Main, OHR Repair of 90 cum capacity, Extension of Boundary Wall &Two Nos. of Pump House Repair for Augmentation of Birendranagar (Zone-II) Pipe water supply scheme in Raghunathganj-II Block under Murshidabad Division, PHE.Dte (i)Amount for Construction Part: 15,60,995.00/ (ii)Amount for Pipeline Part: 57,32,731.00/- (Attached as Annexure -V) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000826/2022-2023 | 656/MURD | 06/03/2023 | 900 | HARUN ALL RASHID & BROTHERS | 72.21 | 20.31 | 40
4152 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000189/2023-2024 | 1210/MURD/19 | 02/05/2023 | 0 | Resource Division | 2.25 | 0 | 0
4153 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I II & III ,Zone-II under BIRENDRANAGAR ground water based water supply scheme under Block_ RAGHUNATHGANJ-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000094/2023-2024 | 4332/MEDB | 29/12/2023 | 91 | BHAGIRATHI JUTE AND HOLDINGS PVT LTD | 32.03 | 0 | 0
4154 | Murshidabad Division | Berhampur M/E Division | Laying Distribution System for Augmentation of Katakopra Zone -I & II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkol Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000172/2024-2025 | 2994/MURD | 13/11/2024 | 150 | M/S. BIMALENDU BOSE | 389.64 | 0 | 0
4155 | Murshidabad Division | Berhampur M/E Division | Augmentation KATAKOPRA (Zone -I) under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. (PART - B) | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000474/2023-2024 | 3031/MURD | 27/09/2023 | 600 | M/S HANNAN KHAN CONSTRUCTION | 300.03 | 44.39 | 15
4156 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATAKOBRA ZONE-I&II Water Supply Scheme and Gokul Chak Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000868/2023-2024 | 832/MURD | 15/03/2024 | 21 | NADIA TUBEWELLS | 11.78 | 0 | 100
4157 | Murshidabad Division | Berhampur M/E Division | Inter connection with Tubewell and rising main etc. at Head work sites of Katakopra Water Supply scheme (Katakopra Z-I & Z-II both) and allied works under Islampur Sub - Division,Murshidabad Division P.H.E Dte. In the district of Murshidabad | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001237/2021-2022 | 43/ISD | 28/01/2022 | 60 | CLASSIC CONSTRUCTION (ANJAN CHATTERJEE) | 4.33 | 4.25 | 100
4158 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000136/2023-2024 | 1167/MURD/33 | 28/04/2023 | 0 | Resource Division | 22 | 0 | 0
4159 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000140/2023-2024 | 1167/MURD/35 | 28/04/2023 | 0 | Resource Division | 198.12 | 0 | 0
4160 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT KATAKOBRA Z-I PH-I | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01098/2024-2025 |  | 13/11/2024 | 0 | WBSEDCL | 6.63 | 0 | 0
4161 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT KATAKOBRA Z-I PH-II | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01099/2024-2025 |  | 13/11/2024 | 0 | WBSEDCL | 5.81 | 0 | 0
4162 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II , Zone-I under Katakobra ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000649/2023-2024 | 3666/MEDB | 03/11/2023 | 666 | HARA PROSAD DAS | 22.58 | 0 | 15
4163 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
4164 | Berhampore Division I | Berhampur M/E Division | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of KASHIPUR ZONE-I" ground water supply scheme in BELDANGA-II Block, under Berhampore Division-I, P.H.E Dte(Capacity-30.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000032/2024-2025 | 995/BD-I | 20/06/2024 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 143.92 | 0 | 60
4165 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of KASHIPUR ZONE-I (Part-B) PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000041/2025-2026 | 722/BD-I | 15/05/2025 | 60 | PRAVAT KUMAR GHOSH | 19 | 0 | 0
4166 | Berhampore Division I | Berhampur M/E Division | Construction of Boundary wall at 2nd & 3rd Tube Well Site of KASHIPUR ZONE -I PWSS(Part-A) under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000043/2025-2026 | 725/BD-I | 15/05/2025 | 60 | HI-TECH ENGINEERS CO-OPERATIVE & CONSTRUCTION SOCIETY LTD. | 19.02 | 0 | 0
4167 | Berhampore Division I | Berhampur M/E Division | Balance work for Improvement Existing AIRP of (Capacity 126 Cum/hr) with allied work at Kashipur Zone-I water supply scheme under JJM within Beldanga-II under Berhampore Division-I, PHE Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000056/2025-2026 | 768/BD-I | 22/05/2025 | 45 | M/S SAJAHAN CHOWDHURY | 58.23 | 0 | 0
4168 | Berhampore Division I | Berhampur M/E Division | KASHIPUR ZONE-I PROPOSED PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000061/2024-2025 | 1176/BD-I | 25/07/2024 | 180 | HI-TECH ENGINEERS CO-OPERATIVE & CONSTRUCTION SOCIETY LTD. | 20.39 | 0 | 100
4169 | Berhampore Division I | Berhampur M/E Division | Replacement of Filter media of Existing AIRP of (Capacity 126 Cum/hr.) with allied work at Kashipur Zone-I Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000068/2024-2025 | 1206/BD-I | 26/07/2024 | 300 | M/S SAJAHAN CHOWDHURY | 35.07 | 0 | 80
4170 | Berhampore Division I | Berhampur M/E Division | Balance work for Laying of distribution pipeline of Kashipur Zone-I and allied works under JJM within Beldanga-II Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000081/2025-2026 | 848/BD-I | 23/06/2025 | 90 | SOUNAK ENTERPRISE | 84.84 | 0 | 0
4171 | Berhampore Division I | Berhampur M/E Division | Augmentation of Kashipur Zone-I Piped water supply scheme to accommodate construction of laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000161/2023-2024 | 668/BD-I | 09/08/2023 | 720 | MAMON ENTERPRISE AND CONSTRUCTION | 236.94 | 100.23 | 35
4172 | Berhampore Division I | Berhampur M/E Division | Augmentation of Kashipur Zone-I Piped water supply scheme to accommodate construction of OHR, laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000162/2023-2024 | 667/BD-I | 09/08/2023 | 876 | SAMIMA ENTERPRISE | 358.74 | 0 | 22
4173 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASHIPUR ZONE-I Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000189/2023-2024 | 531/BD-I | 27/07/2023 | 10 | TECHVISION | 2.87 | 2.87 | 100
4174 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KASHIPUR ZONE-I (PART-B) Water Supply Scheme (TW-I & II Site) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000293/2024-2025 | 99/BD-I | 20/01/2025 | 240 | SUJIT KUMAR SAHA | 18.02 | 0 | 100
4175 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000106/2023-2024 | 201/BD-1/7 | 10/02/2024 | 0 | Resource Division | 101.3 | 0 | 0
4176 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT KASHIPUR Z-I PH-I | ASSISTANT ENGINEER-I | Junior engineer-III | BILL/01578/2023-2024 | 409/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 5.27 | 0 | 0
4177 | Berhampore Division I | Berhampur M/E Division | Safety Checking of 9 (Nine) nos Over Head Reservoit at various places of Murshidabad District under P.H.Engineering Department, Govt of West Bengal. | ASSISTANT ENGINEER-I | Junior engineer-II | BILL/00347/2024-2025 | BP-2024-25-259 | 27/11/2024 | 0 | SRCC NIT DURGAPUR | 3.54 | 0 | 0
4178 | Berhampore Division I | Berhampur M/E Division | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer-II,BD-I,PHE Dte. [Period for 05.07.2024 to 30.06.2025.] Car No-WB58CC 9776 | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000046/2024-2025 | 1082/BD-I | 04/07/2024 | 365 | MD MUKLESUR RAHAMAN | 1.81 | 0 | 0
4179 | Berhampore Division I | Berhampur M/E Division | Consultancy for Engineering support of six numbers of Suspended OHR constructed in stages initially during 2011-2012 and after 5-6 years gap in Berhampore Division-I of PHE Dte. based on Joint Inspection, Non-destructive Test and subsequent Structural Analysis of their As Built Numerical Models in FEM Platform including Seismic Considerations. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000091/2025-2026 | 959/BD-I | 22/07/2025 | 60 | JADAVPUR UNIVERSITY | 49.21 | 0 | 0
4180 | Berhampore Division I | Berhampur M/E Division | Continuation Work order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer-II,BD-I,PHE Dte. [Period for 01.07.2025 to 31.10.2025.] Car No-WB58CC 9776 | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000095/2025-2026 | 1082/BD-I | 30/06/2025 | 123 | MD MUKLESUR RAHAMAN | 0.6 | 0 | 0
4181 | Berhampore Division I | Berhampur M/E Division | Withdrawing and Laying of different dia. D.I. pipe along NH12 from Bhakuri to Talbagan more with connection work to Rising Mains of Central Sector Part-II near Bhakuri more and Balarampur Halt Station under Berhampore Division-I, P.H.E. Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000120/2024-2025 | 1469/BD-I | 06/09/2024 | 240 | SAMBHUNATH ROY | 53.6 | 0 | 80
4182 | Berhampore Division I | Berhampur M/E Division | Improvement of existing Pump House & Construction of Boundary Wall at different head work sites for Augmentation of different PWSS within MJ & Berhampore Block under Central Sector Part-I under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000142/2024-2025 | 1610/BD-I | 03/10/2024 | 240 | M/S J.S ENTERPRISE | 85.47 | 0 | 40
4183 | Berhampore Division I | Berhampur M/E Division | Allied Work for Supply of different types of specials in connection with execution of Clear Water Rising Main, Overhead Reservoirs, Distribution Network Complete under JJM for Augmentation of Surface Water Based Piped Water Supply Scheme of CENTRAL SECTOR PART-I under BERHAMPORE DIVISION - I in the district of MURSHIDABAD. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000256/2024-2025 | 2269/BD-I | 16/12/2024 | 30 | M/S MOHAN LAL JAIN | 36.33 | 0 | 0
4184 | Berhampore Division I | Berhampur M/E Division | Allied Work for Supply of different types of specials in connection with execution of Clear Water Rising Main, Overhead Reservoirs, Distribution Network Complete under JJM for Augmentation of Surface Water Based Piped Water Supply Scheme of CENTRAL SECTOR PART-II under BERHAMPORE DIVISION - I in the district of MURSHIDABAD | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000266/2024-2025 | 2324/BD-I | 26/12/2024 | 30 | ECO PROTECTION ENGINEERS PVT LTD. | 35.3 | 0 | 0
4185 | Berhampore Division I | Berhampur M/E Division | Renovation and upgradation of all existing infrastructures (Sludge Sump House, Sludge pond, Substation Building,Boundary Wall, Clariflocculator, Flash Mixer, Inlet Well and allied Works) of Augumentation of Central Sector Part-II under JJM under Berhampore Division-I, P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000271/2024-2025 | 2333/BD-I | 30/12/2024 | 45 | CONCORD ENGINEERING | 42.16 | 0 | 0
4186 | Berhampore Division I | Berhampur M/E Division | Renovation and upgradation of all existing infrastructures (Filter House Building,Chemical House Building,Laboratory/SCADA Building,Clear Water Pump House, Clear Water Reservoir, Outhouse, Staff Quarters and allied Works) of Augumentation of Central Sector Part-II under JJM under Berhampore Division-I, P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000272/2024-2025 | 2334/BD-I | 30/12/2024 | 45 | CONCORD ENGINEERING | 59.47 | 0 | 0
4187 | Berhampore Division I | Berhampur M/E Division | Rejuvanation of 54.11 MLD Capacity Water Treatment Plant (Inlet well ,Flush Mixture,Clarifoculator, Chemical Dosing and Filter House ) at Central Sector Part-II UNDER BERHAMPORE DIVISION - I , IN THE DISTRICT MURSHIDABAD , PHE DTE . | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000432/2023-2024 | 385/BD-I | 12/03/2024 | 477 | CONCORD ENGINEERING | 296.54 | 0 | 60
4188 | Berhampore Division I | Berhampur M/E Division | Survey, Investigation, Planning, Design, Execution commissioning and completion in all respect of all Civil, Electrical and Mechanical work of 11 MLD capacity conventional water treatment plant (WTP) using River Bhagirathi as source including Intake Structures, Raw Water rising main, and Clear Water rising main upto boundary limit of WTP for the Augmentation of surface water based piped water supply scheme for Murshidabad Central Sector (Part-I) in Murshidabad District under PHE Dte. including 12 (Twelve) months of Operation and Maintenance after successful completion of 3 (Three) months Trial Run | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000434/2023-2024 | 386/BD-I | 12/03/2024 | 549 | CONCORD ENGINEERING | 3354.92 | 0 | 0
4189 | Berhampore Division I | Berhampur M/E Division | EXECUTION OF CLEAR WATER RISING MAIN, OVERHEAD RESERVOIRS WITH ALLIED WORKS, DISTRIBUTION NETWORK WITH FHTC COMPLETE FOR AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CENTRAL SECTOR PART-I OF MURSHIDABAD DISTRICT | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000435/2023-2024 | 387/BD-I | 12/03/2024 | 849 | M/S MOHAN LAL JAIN | 7952.07 | 0 | 60
4190 | Berhampore Division I | Berhampur M/E Division | EXECUTION OF CLEAR WATER RISING MAIN, OVERHEAD RESERVOIRS WITH ALLIED WORKS, DISTRIBUTION NETWORK WITH FHTC COMPLETE FOR AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CENTRAL SECTOR PART-II OF MURSHIDABAD DISTRICT | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000436/2023-2024 | 388/BD-I | 12/03/2024 | 872 | ECO PROTECTION ENGINEERS PVT LTD. | 16059.7 | 0 | 35
4191 | Berhampore Division I | Berhampur M/E Division | Rejuvanation of of 30.33 MLD Capacity Water Treatment Plant (Inlet well ,Flush Mixture ,Clarifoculator , Chemical Dosing and Filter House ) at Central Sector Part- I (At Lalbagh) Under Berhampore Division - I , In The District Murshidabad , PHE Dte . | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000437/2023-2024 | 391/BD-I | 12/03/2024 | 540 | DHIMAN SARKAR | 270.68 | 0 | 80
4192 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000001/2024-2025 | 790/BD-I | 09/05/2024 | 0 | Resource Division | 478.82 | 0 | 0
4193 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000002/2024-2025 | 1148/BD-I | 18/07/2024 | 0 | Resource Division | 817.87 | 0 | 0
4194 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000004/2024-2025 | 1341/BD-I/2 | 20/08/2024 | 0 | Resource Division | 387.17 | 0 | 0
4195 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000005/2024-2025 | 1412/BD-I | 30/08/2024 | 0 | Resource Division | 1050.72 | 0 | 0
4196 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000006/2024-2025 | 1462/BD-I | 05/09/2024 | 0 | Resource Division | 123.2 | 0 | 0
4197 | Berhampore Mechanical | Berhampur M/E Division | SHIFTING OF DTR 25KVA AT MANIKNAGAR CID 860311628 | ASSISTANT ENGINEER-I | Junior engineer-II | BILL/00663/2024-2025 |  | 03/09/2024 | 0 | WBSEDCL | 0.71 | 0 | 0
4198 | Berhampore Mechanical | Berhampur M/E Division | Providing Electrical Equipment for 11/0.433 KV Sub-station (LT Bulk & HT Bulk) at Intake and Water Treatment Plant under Augmentation of Central Sector, Part-I Surface Water Based W/S Scheme, Dist. Murshidabad | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/001569/2023-2024 | 973/MEDB | 15/03/2024 | 184 | CONCORD ENGINEERING | 239.82 | 0 | 0
4199 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Sarkarpara ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | JE | ORD/000158/2024-2025 | 1646/BD-I | 23/10/2024 | 30 | PRATAP KUMAR SINHA | 5.92 | 0 | 0
4200 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarkarpara (Village code 314647) under Sarkarpara Ground Water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-18 of 2020 ¿ 2021,SL-03). | Assistant Engineer | JE | ORD/000244/2020-2021 | 77/BD-I | 19/01/2021 | 30 | SARAJIT KUMAR MAJUMDAR | 24.4 | 16.81 | 0
4201 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahajadpur (Village code 315513) under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000138/2020-2021 | 238/BD-I | 10/02/2021 | 180 | M/S UNIVERSAL TRADING | 91.12 | 87.7 | 1
4202 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village of Joykrishnapur (Village code 315508) under Choa (Zone-F) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000145/2020-2021 | 252/BD-I | 11/02/2021 | 90 | DOBAY CONSTRUCTION | 42.77 | 34.79 | 1
4203 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of GAZNIPUR (Village code 315512)under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000146/2020-2021 | 261/ BD-I | 12/02/2021 | 180 | RAJ KUMAR MONDAL | 78.63 | 113.73 | 1
4204 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of PADMANABHPUR (Village code 315507)under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000147/2020-2021 | 264/ BD-I | 12/02/2021 | 180 | SARAJIT KUMAR MAJUMDAR | 113.25 | 67.31 | 80
4205 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of SRIPUR (Village code 315511) under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000148/2020-2021 | 265/ BD-I | 12/02/2021 | 180 | MS RUBIET HOSSAIN | 107.3 | 87.96 | 1
4206 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of CHOA (Village code 315510) under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000247/2020-2021 | 977/BD-I | 17/12/2020 | 180 | MS RUBIET HOSSAIN | 240.3 | 288.79 | 1
4207 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-II | Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
4208 | Berhampore Division I | Berhampur Division I | Additional and balance work of HDPE pipe for house service connection and relaying of damage and Laying of extension different dia UPVC pipeline in connection to Jal Jeevan Mission & Jal Swapna from Choa Thana more towards Sahebnagar & Tangramari Village and at Borakhali village and Pirtala village of Choa G.P of Choa Water Supply Scheme of Central Sector Part-II of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000578/2021-2022 | 1847/BD-I | 07/10/2021 | 50 | M/S RUBIET HOSSAIN | 44.49 | 0 | 0
4209 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-II | RTOR000027/2024-2025 | 2096/BD-I/8 | 25/11/2024 | 0 | Resource Division | 24.64 | 0 | 0
4210 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area for the Village of Kalyannagar (VillageCode-314519) , Faridpur (VillageCode-314520) & Jot sahabaj (Village Code-314521) in Faridpur ground water supply scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000082/2024-2025 | 1243/BD-I | 30/07/2024 | 30 | NOBEL CONSTRUCTION | 4.82 | 0 | 0
4211 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kalyan Nagar (Village code 314519) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000184/2020-2021 | 840/BD-I | 23/11/2020 | 60 | DOBAY CONSTRUCTION | 18.39 | 25.67 | 0
4212 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jot Sahabaj (Village code 314521) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000186/2020-2021 | 841/BD-I | 23/11/2020 | 60 | DOBAY CONSTRUCTION | 20.69 | 35.31 | 0
4213 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Foridpur (Village code 314520) under Foridpur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000207/2021-2022 | 1005/BD-I | 21/06/2021 | 20 | AICH CONSTRUCTION | 45.66 | 40.29 | 1
4214 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Foridpur (Village code-314520) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under ForidpurGround water supply scheme (Bhagwangola-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000781/2021-2022 | 2296/BD-I | 28/12/2021 | 15 | AICH CONSTRUCTION | 9.57 | 9.06 | 1
4215 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-314529) , Boalia (Village Code-314530) in Faridpur ground water supply scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000097/2024-2025 | 1369/BD-I | 22/08/2024 | 30 | ANIRBAN CHATTERJEE | 7.59 | 0 | 0
4216 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamal Chak (Village code 314529) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000182/2020-2021 | 839/BD-I | 23/11/2020 | 60 | AJAY MONDAL | 11.86 | 9.18 | 1
4217 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dhwajamat (Village code 314528) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000183/2020-2021 | 817/BD-I | 12/11/2020 | 60 | KAKALI ENTERPRISE | 10.81 | 17.54 | 1
4218 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Boalia (Village code 314530) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000188/2020-2021 | 816/BD-I | 12/11/2020 | 60 | SAMBHUNATH ROY | 19.03 | 27.25 | 1
4219 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamal Chak and others under Faridpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000207/2020-2021 | 274/ BD-I | 15/02/2021 | 10 | AJAY MONDAL | 3.12 | 1.7 | 1
4220 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dhwajamat (Village Code-314528) under Faridpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000211/2020-2021 | 278/BD-I | 15/02/2021 | 10 | KAKALI ENTERPRISE | 2.02 | 3.12 | 0
4221 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Topi Danga (Village code 314522) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-09 of 2020 ¿ 2021,SL-06). | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000241/2020-2021 | 74/BD-I | 19/01/2021 | 30 | SANDIP KUMAR BISWAS | 35.16 | 25.99 | 100
4222 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Lochanpur Village (Code-314758), Char Pirojpur Village (Code-314760) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000076/2024-2025 | 1224/BD-I | 29/07/2024 | 60 | SOM CONSTRUCTION AGENCY | 44.6 | 0 | 0
4223 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lochanpur (Village code 314758), Char Pirojpur (Village Code-314760) under Lochanpur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. (Block-Raninagar-I) (Sl-01) | Assistant Engineer | Junior Engineer-II | ORD/000383/2021-2022 | 1475/BD-I | 17/08/2021 | 1630 | M/S GOUTAM CHAKRABORTY | 121.97 | 57.28 | 1
4224 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Gopalpur Village (Code-315686) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000074/2024-2025 | 1222/BD-I | 29/07/2024 | 60 | SANTA TRADING | 25.6 | 0 | 0
4225 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gopalpur (Village code 315686) under Kashipur Ground Water Supply Scheme in Beldanga-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-12) | Assistant Engineer-II | Junior Engineer-II | ORD/000273/2021-2022 | 1144/BD-I | 07/07/2021 | 180 | KAMIRUL SK AND CO. | 70.23 | 62.88 | 0
4226 | Murshidabad Division |  | Additional works for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of JOYRAMPUR( Village Code -314693) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184127) |  |  | ORD/000072/2021-2022 | 1548/MURD | 23/06/2021 | 60 | SAHABUDDIN BISWAS | 28.24 | 0 | 0
4227 | Murshidabad Division |  | Additional works for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of MAHABUBNAGAR ( Village Code -314668) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184127) |  |  | ORD/000073/2021-2022 | 1549/MURD | 23/06/2021 | 60 | H.L. CONSTRUCTION (TITAN BISWAS) | 38.29 | 0 | 0
4228 | Murshidabad Division |  | ADDITIONAL WORKS FOR FHTC OF VILLAGE CODE MAHABUBNAGAR (CODE- 314668) UNDER DOMKAL WSS, TNO- 98/21-22/EE |  |  | VCH/000779/2021-2022 |  | 29/10/2021 | 0 | H.L. CONSTRUCTION (TITAN BISWAS) | 33.18 | 0 | 0
4229 | Murshidabad Division |  | ADDITIONAL WORKS FOR FHTC OF VILLAGE CODE MAHABUBNAGAR (CODE- 314668) UNDER DOMKAL WSS, TNO- 98/21-22/EE |  |  | VCH/000916/2021-2022 | 189-MSD/21-22 | 12/11/2021 | 0 | H.L. CONSTRUCTION (TITAN BISWAS) | 33.18 | 0 | 0
4230 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of villageMAHABUR (Village Code 314668) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. Tender no - 500 of 20-21 by EE MURD |  |  | VCH/001389/2021-2022 | 323-MSD/21-22 | 21/02/2022 | 0 | DECON INDIA | 9.57 | 0 | 0
4231 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BARABIL RAGHUNAR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 87 /2020-21/SE-MC |  |  | VCH/002023/2020-2021 | 512/W | 30/03/2021 | 0 | MITRA CONSTRUCTION | 55.47 | 0 | 0
4232 | Murshidabad Division |  | Additional works for Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of HETANPUR( Village Code -314664) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184127) |  |  | ORD/000246/2021-2022 | 1693/MURD | 06/07/2021 | 60 | SUDIPA SINGHA ROY | 13.33 | 0 | 0
4233 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with ";Jal Swapna (Jal Jeevan Mission ) "from existing Distribution system within the Command area of village HETANPUR (Village Code 314664) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad . |  |  | ORD/000552/2020-2021 | 2576/MURD | 01/10/2020 | 45 | SUDIPA SINGHA ROY | 17.38 | 0 | 0
4234 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village MASIMPUR (Village Code 314663) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad. |  |  | ORD/000643/2020-2021 | 2575/MURD | 01/10/2020 | 45 | CHATTERJEE ENTERPRISE | 19.86 | 0 | 0
4235 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Hetanpur (314664) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District(Part-VII) |  |  | VCH/001292/2021-2022 |  | 17/02/2022 | 0 | SUDIPA SINGHA ROY | 19.98 | 0 | 0
4236 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with ';Jal Swapna (Jal Jeevan Mission ) 'from existing Distribution system within the Command area of village HETANPUR (Village Code 314664) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad . Tender no - 504 of 20-21 by EE MURD |  |  | VCH/001434/2021-2022 | 337-MSD/21-22 | 03/03/2022 | 0 | SUDIPA SINGHA ROY | 13.68 | 0 | 0
4237 | Murshidabad Division |  | Additional works for Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of HETANPUR ( Village Code -314664) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. Tender no - 365 of 21-22 by EE MURD |  |  | VCH/001437/2021-2022 | 336-MSD/21-22 | 03/03/2022 | 0 | SUDIPA SINGHA ROY | 6.3 | 0 | 0
4238 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BARABIL RAGHUNAR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 87 /2020-21/SE-MC |  |  | VCH/002023/2020-2021 | 512/W | 30/03/2021 | 0 | MITRA CONSTRUCTION | 55.47 | 0 | 0
4239 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --BHALKUNDI Z-II-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE-BHALKUNDI , CODE- 315091, TNO- 43/2020-21/SEMC |  |  | VCH/002024/2020-2021 | 512/W | 30/03/2021 | 0 | M/S BHUBAN DAS | 28.84 | 0 | 0
4240 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rajabati (Village code 314552),Fulpur (Village code 314511) under Dakshin Sahar Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000117/2020-2021 | 189/BD-I | 04/02/2021 | 20 | GOUTAM CHAKRABORTY | 32.54 | 45.63 | 1
4241 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Fulpur (Code-314511), Rajabati (Code-314552) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000166/2024-2025 | 1685/BD-I | 28/10/2024 | 30 | ARJU CONSTRUCTION | 10.34 | 0 | 0
4242 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Jogopur (Code-314533), Kamari (Code-314551) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000113/2024-2025 | 1449/BD-I | 04/09/2024 | 60 | S DUTTA | 21.89 | 0 | 0
4243 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jogopur (Village code 314533),Kamari (Village code 314551) under Dakshin Sahar Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000118/2020-2021 | 190/BD-I | 04/02/2021 | 30 | DECON INDIA | 66.63 | 48.98 | 1
4244 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Paranpur Village (Code-314173), Fatepur(Code-314174) In The Command Area Of Maiya Ground Water Supply Scheme (Part-C) Under Lalgola Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000102/2024-2025 | 1438/BD-I | 04/09/2024 | 30 | ALOK BANERJEE ENTERPRISE | 8.85 | 0 | 0
4245 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paranpur(Village code 314173),Fatepur(Village code 314174) under Maia Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE | ORD/000108/2020-2021 | 174/BD-I | 03/02/2021 | 20 | SAMAR MUKHERJEE | 35.05 | 50.51 | 1
4246 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area Of village of Debaipur (Village code 314548) under Benipur Ground Water based Water Supply Scheme for Bhagwangola- II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000224/2020-2021 | 988/BD-I | 17/12/2020 | 90 | DOBAY CONSTRUCTION | 37.11 | 54.62 | 0
4247 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Saralpur (Village code 314538) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000232/2020-2021 | 38/BD-I | 13/01/2021 | 90 | JAHANGIR ALAM | 41.33 | 32.43 | 1
4248 | Murshidabad Division |  | Laying of pipe line at Nawapara Village (Village Code-315734) in connection with FHTC work at Tenya (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000022/2022-2023 | 26/KSD | 08/04/2022 | 1030 | PARTHA RAJAK | 4.52 | 0 | 1
4249 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Tenya (Village code 315737) under Tenya(Zone-I) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154932 in the District of Murshidabad. (Sl No-21) |  |  | ORD/000447/2020-2021 | 47/MURD | 06/01/2021 | 180 | CHAKRABORTY CONSTRUCTION | 58.49 | 8.07 | 1
4250 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at TENYA BAIDYAPUR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000470/2021-2022 | 238/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0
4251 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village NAWAPARA (Village Code : 315734) under Tenya Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur-II Block in the District of Murshidabad. |  |  | ORD/000579/2020-2021 | 3221/MURD | 18/12/2020 | 60 | HARUN ALL RASHID & BROTHERS | 6.26 | 5.56 | 1
4252 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village GHOSHPARA(Village Code 315735) under Tenya Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur-II Block in the District of Murshidabad. |  |  | ORD/000783/2020-2021 | 3035/MURD | 07/12/2020 | 45 | MAA DURGA ENTERPRISE | 8.95 | 0 | 0
4253 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bara Baidyapur (Village code 315733) under Tenya(Zone-II) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division,PHE Dte. Scheme ID 0006154932 in the District of Murshidabad.(sl-02) |  |  | ORD/000973/2021-2022 | 3487/MURD | 03/11/2021 | 100 | SOM CONSTRUCTION AGENCY | 45 | 16.43 | 1
4254 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bara Hati ( Village Code -315738) Korgram ( Village Code -315736) under Tenya Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006154932) |  |  | ORD/001576/2021-2022 | 306/MURD | 07/02/2022 | 60 | DAS ASSOCIATED | 38.03 | 36.83 | 100
4255 | Murshidabad Division |  | Providing Balance Functional Household Tap Connection (FHTC) of 219 left out in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ghoshpara (Village code 315735) under Tenya Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/001809/2021-2022 | 813/MURD | 25/03/2022 | 20 | MAA DURGA ENTERPRISE | 15.69 | 15.17 | 100
4256 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 889/B/MURD | 05/04/2022 | 0 | Resource Division | 5.08 | 0 | 0
4257 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna Mission (JJM) from existing distribution system within the command area of village Ghoshpara (Village code - 315735) of Tenya under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur - II Block of Murshidabad District. PHE DTE. Tender no-633 / 20-21 by EE / MURD |  |  | VCH/000199/2021-2022 | 13-MSD / 21-22 | 10/08/2021 | 0 | MAA DURGA ENTERPRISE | 6.4 | 0 | 0
4258 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and connection with Jal Jeevan Mission (JJM) under command area of Village TENYA (Village Code-315737) under TENYA (ZONE-I) Ground Water Based Water Supply Scheme for arsenic affected area of Bharatpur-II Block under Murshidabad Division, PHE Dte. |  |  | VCH/000234/2021-2022 | 29-MSD / 21-22 | 27/08/2021 | 0 | CHAKRABORTY CONSTRUCTION | 18.07 | 0 | 0
4259 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoshpara 315735 OF Tenya under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur - II Block of Murshidabad District (PART-I) TNO- 633/20-21/EE |  |  | VCH/000656/2021-2022 | 129-MSD/21-22 | 11/10/2021 | 0 | MAA DURGA ENTERPRISE | 2.49 | 0 | 0
4260 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village TENYA (Village Code 315737) under TENYA (ZONE-I) Ground Water Based Water Supply Scheme for arsenic affected areas of BHARATPUR-II Block in the District of Murshidabad. Tender no - 77 of 20-21 by SE MC |  |  | VCH/001519/2021-2022 | 427-MSD/21-22 | 31/03/2022 | 0 | CHAKRABORTY CONSTRUCTION | 11.93 | 0 | 0
4261 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Jhaubaria (Village Code -314585) under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006086670) |  |  | ORD/000290/2021-2022 | 2297/MURD | 02/08/2021 | 60 | ROY CONSTRUCTION (PROP:AVIJIT ROY) | 97.86 | 135.02 | 1
4262 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Katlamari (Village Code -314589)(Katlamari & Ramnagarpara& adjoining habitation) under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | ORD/000291/2021-2022 | 2298/MURD | 02/08/2021 | 60 | HIRANMAY GHOSH | 97.89 | 132.79 | 100
4263 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) (Kartekerpara & Lalchandabad) & adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | ORD/000437/2021-2022 | 2641/MURD | 27/08/2021 | 60 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 97.88 | 45.04 | 70
4264 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. |  |  | ORD/000448/2021-2022 | 298/BSD | 13/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.34 | 8.67 | 0
4265 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Babaltali ( Village Code -314583)( Nojorana&Panipia& adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | ORD/000489/2021-2022 | 2680/MURD | 31/08/2021 | 60 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 97.62 | 93.61 | 0
4266 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Katlamari ( Village Code -314589) (Mohongonj &Kaharpara & adjoining habitation) under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | ORD/001714/2021-2022 | 716/MURD | 15/03/2022 | 60 | SOFIQUL ISLAM | 80.52 | 66.03 | 0
4267 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing Balance Functional Household Tap Connections (FHTC) of 1180 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jhaubaria (Village code 314585) under Saikhpara Area Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0006086670). |  |  | ORD/001716/2021-2022 | 703/MURD | 14/03/2022 | 15 | AZAD ENTERPRISE | 12.2 | 11.69 | 0
4268 | Murshidabad Division |  | Extension of Distribution UPVC pipeline and providing balance Functional Household Tap Connections (FHTC) of 633 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Katlamari (Villagecode-314589)(Katlamari, Ramnagarpara & adjoining habitation) under Seikhpara Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0006086670) |  |  | ORD/001805/2021-2022 | 854/MURD | 31/03/2022 | 15 | HIRANMAY GHOSH | 8.27 | 5.7 | 100
4269 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BABALTALI (Village Code 314583) under (SAIKHPARA AND BABALTALI adjoining habitation SAIKHPARA Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-II Block in the District of Murshidabad. Tender no - 360 of 21-22 by EE MURD |  |  | VCH/001513/2021-2022 | 415-MSD/21-22 | 22/03/2022 | 0 | MITRA CONSTRUCTION | 45.89 | 0 | 0
4270 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) (Kartekerpara & Lalchandabad) & adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | VCH/001530/2021-2022 | 438-MSD/21-22 | 30/03/2022 | 0 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 51.77 | 0 | 0
4271 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Andulberia (Village code 315690) under Andulberia Ground Water Supply Scheme in Beldanga-II Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-15) | Assistant Engineer-II | Junior Engineer-I | ORD/000500/2021-2022 | 1907/BD-I | 08/10/2021 | 180 | M/S JAN MAHAMMAD | 161.38 | 161.22 | 1
4272 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nazirpur (village code 315684) under ANDULBERIA Ground Water based Water Supply Scheme in Beldanga-II Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000586/2021-2022 | 2016/BD-I | 08/11/2021 | 652 | MANASH GHOSH | 96.77 | 50.73 | 100
4273 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-I | RTOR000003/2021-2022 | 63/BD-I | 27/01/2022 | 0 | Resource Division | 13.74 | 0 | 0
4274 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-I | RTOR000005/2021-2022 | 72/BD-I | 28/01/2022 | 0 | Resource Division | 4.44 | 0 | 0
4275 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-A). |  |  | ORD/000034/2022-2023 | 167/JSD | 01/04/2022 | 30 | S.D PROJECT | 4.85 | 0 | 1
4276 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-B). |  |  | ORD/000035/2022-2023 | 168/JSD | 01/04/2022 | 30 | S.D PROJECT | 4.81 | 8.19 | 1
4277 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-C). |  |  | ORD/000036/2022-2023 | 169/JSD | 01/04/2022 | 30 | M/S G.M ENTERPRISE (MD. GOLAM MEHABUB) | 4.84 | 4.83 | 1
4278 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-D). |  |  | ORD/000037/2022-2023 | 170/JSD | 01/04/2022 | 30 | SUMAN ENTERPRISE AND SUMAN AQUA | 4.84 | 3.66 | 1
4279 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-E). |  |  | ORD/000048/2022-2023 | 178/JSD | 01/04/2022 | 30 | M/S JOY MA BANAMALI | 4.8 | 3.85 | 1
4280 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Kasiadanga (Village Code -314124) (Part-I) & adjoining habitation under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756852) |  |  | ORD/000294/2021-2022 | 2299/MURD | 02/08/2021 | 60 | KISMAT ARA BEGUM | 69.04 | 116.51 | 0
4281 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) laying pipeline in connection with under command area of village of BAHARA (Village Code-314123) & KULGACHHI (Village Code-314119) under KASIADANGA Ground water Based Water Supply Scheme for Arsenic Affected Areas of RAGHUNATHGANJ-II Block, under Murshidabad Division,PHE Dte. |  |  | ORD/000341/2022-2023 | 1837/MURD | 13/07/2022 | 150 | DHIRENDRANATH MONDAL | 192.87 | 192.68 | 0
4282 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kasiadanga ( Village Code -314124) (Part-II) & adjoining habitation under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756852) |  |  | ORD/000418/2021-2022 | 2595/MURD | 25/08/2021 | 60 | M/S. S.S. ENTERPRISE( PROP: SANDIP SAHA) | 70.36 | 67.32 | 0
4283 | Murshidabad Division |  | Laying of UPVC pipeline at village Laxmijola (East Side) in connection with FHTC work under Kasiadanga (Zone-II) Water Supply Scheme under Jangipur Sub-Division,P.H.E. Dte. in the District of Murshidabad. |  |  | ORD/001281/2021-2022 | 419./LSD | 31/12/2021 | 30 | MARUTI CONSTRUCTION AND CO | 3.8 | 0 | 70
4284 | Murshidabad Division | Berhampur Sub-Division | Physical site visit to check the okd RC overhead water tank at satitara and Gokarna at Kandi under MSD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00153/2023-2024 | 31-MSD/2023-24 | 05/05/2023 | 0 | SRCC NIT DURGAPUR | 1.18 | 0 | 0
4285 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
4286 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
4287 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kumarpur (Village code 315597) under Mahyampur Surface Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 000958825 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000034/2020-2021 | 541/MURD | 05/02/2021 | 180 | DECON INDIA | 56.35 | 23.35 | 1
4288 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Barua (P) (Village code 315619) under Mahyampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte.Scheme ID 000958825 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000182/2020-2021 | 3135/MURD | 11/12/2020 | 60 | AMAL KUMAR DAS | 41.32 | 18.65 | 1
4289 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jalalpur (Village code 315595) under Mahyampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 000958825 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000360/2021-2022 | 2535/MURD | 19/08/2021 | 60 | M/S. BIMALENDU BOSE | 19.82 | 19.72 | 0
4290 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mahyampur (Village code 315612) under Mahyampur Surface Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte.(Sl No-02) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000423/2021-2022 | 2538/MURD | 19/08/2021 | 180 | TEKNO ENTERPRISE | 216.16 | 0 | 1
4291 | Murshidabad Division | Berhampur Sub-Division | Name of Work:- Hiring of Maxi cab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte. for 01 (One) year. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000559/2022-2023 | 291/LSD | 08/07/2022 | 365 | BARI ENTERPRISE | 1.78 | 4.52 | 40
4292 | Murshidabad Division | Berhampur Sub-Division | Repairing of Rising main pipe line and allied works along the Rising main pipe line at western side of Beldanga C.R.G.S School , Diamond Nursing home, Beside Beldanga Rural Hospital and Panchraha More connection with FHTC work in the village Madda( Village Code-315603) Under Beldanga Municipality Water Supply scheme under Berhampore Sub Division P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000574/2022-2023 | 2942/MURD | 03/11/2022 | 20 | PRADIP DAS | 3.05 | 2.75 | 0
4293 | Murshidabad Division | Berhampur Sub-Division | Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2022 to 17.04.2023.[Vehicle No-WB57E7960] | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000623/2022-2023 | 205/JSD | 18/04/2022 | 365 | MAJIBUR RAHAMAN | 4.76 | 3.05 | 0
4294 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line and connection with street stand post and Construction of soat well in connection with Dengue control for different Health Sub Centre (1) Miezapur Mid section Sc 2) Mirzapur Sitalpara Sc.3) Mahyampur SC.4) Notunpara RCH SC under Berhampore Sub division. P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000736/2020-2021 | 269/BSD | 13/10/2020 | 15 | PRADIP MAHATO | 1.97 | 1.91 | 1
4295 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission under command area of village of Jalalpur (Village Code -315595) Part-B under Mahyampur surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. In the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000736/2022-2023 | 260/BSD | 31/05/2022 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 4.36 | 4.32 | 0
4296 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kumarpur (Village Code -315597) Part B under Mahyampur surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000737/2022-2023 | 262/BSD | 31/05/2022 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 4.14 | 4.1 | 0
4297 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kumarpur (Village Code -315597) Part C under Mahyampur surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000741/2022-2023 | 268/BSD | 24/06/2022 | 30 | BIJOY KUMAR SANYAL | 4.14 | 4.13 | 0
4298 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) Part-E under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000747/2022-2023 | 275/BSD | 24/06/2022 | 30 | MASTER CONSTRUCTION | 4.72 | 4.62 | 100
4299 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) Part-C under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000751/2022-2023 | 276/BSD | 24/06/2022 | 30 | NAYLA CONSTRUCTION | 4.68 | 4.37 | 100
4300 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) Part-A under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000752/2022-2023 | 277/BSD | 24/06/2022 | 30 | NAYLA CONSTRUCTION | 4.67 | 4.58 | 100
4301 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) Part-D under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000753/2022-2023 | 278/BSD | 24/06/2022 | 30 | NAYLA CONSTRUCTION | 4.67 | 4.61 | 100
4302 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) PART-B under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000754/2022-2023 | 279/BSD | 30/06/2022 | 30 | NAYLA CONSTRUCTION | 4.72 | 4.69 | 100
4303 | Murshidabad Division | Berhampur Sub-Division | Further to Hiring of one no. Mahindra & Mahindra make Bolero Diesel passenger car for official use of the Assistant Engineer, Berhampore Sub-Division,P. H. Engineering Dte. for 06(Six) Months. (Period from 01.07.2022 to 31.12.2022) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000760/2022-2023 | 283/BSD | 24/06/2022 | 183 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 0.91 | 2.22 | 0
4304 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Barua (p) (Village Code -315619) under Mahyampur Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000762/2022-2023 | 284/BSD | 24/06/2022 | 30 | MD. MASUD SK. | 4.43 | 4.27 | 100
4305 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mirzapur(Village code 315615) under Mahyampur Surface Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte. (Scheme ID 000958825) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000853/2021-2022 | 3328/MURD | 07/10/2021 | 180 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 225.77 | 0 | 0
4306 | Murshidabad Division | Berhampur Sub-Division | Hiring of 01 (One) no . Diesel Bolero /Marshal Car for official use having for contract carriage permit from the Reginal Transport Authority for the office of the Assistant Engineer , Islampur Sub-Division, P.HE Dte, Murshidabad for the period from 01/10/2022 to 31/03/2023 (i.e six months). (Vechicle No. W.B-57E-9142) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000895/2022-2023 | 415/ISD | 29/09/2022 | 181 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 2.35 | 0
4307 | Murshidabad Division | Berhampur Sub-Division | Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months (120 days) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000896/2022-2023 | 164/ISD | 31/03/2023 | 183 | HAMIDUL ISLAM | 0.69 | 1.93 | 100
4308 | Murshidabad Division | Berhampur Sub-Division | Further to Hiring of one no. Mahindra & Mahindra make Bolero Diesel passenger car for official use of the Assistant Engineer, Berhampore Sub-Division,P. H. Engineering Dte. for 06(Six) Months. (Period from 01.01.2023 to 30.06.2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000931/2022-2023 | 291/BSD | 16/12/2022 | 182 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 0.91 | 2.39 | 100
4309 | Murshidabad Division | Berhampur Sub-Division | Construction of approach road with Cement Concrete for Head works site of Loknathpur Zone-II Water Supply Scheme under Berhampore Sub-Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000965/2022-2023 | 259/BSD | 31/05/2022 | 30 | MONDAL CONSTRUCTION | 2.33 | 2.32 | 100
4310 | Murshidabad Division | Berhampur Sub-Division | Repairing And Renovation of R.C.C. elevated reservoir (1.50 Lakh Gallon capacity) of staging hight 24.0 Mtr. At Mahyampur Water Supply under Berhampore Sub Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001646/2021-2022 | 555/MURD | 28/02/2022 | 45 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 17.67 | 15.87 | 0
4311 | Murshidabad Division | Berhampur Sub-Division | Additional work of laying of distribution system pipe line for providing Funtional Household Tap connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Kumarpur (village code 315597) under Mahyampur surface Water Supply Scheme for Arsenic affected areas of Beldanga-I Block in Murshidabad Division PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001769/2021-2022 | 102/BSD | 28/03/2022 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 4.68 | 4.63 | 0
4312 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Superintending Engineer, Murshidabad Circle,PHE Dte.[Period for 01(One) Year] for the month of February 2022 to January 2023 | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/002101/2021-2022 | 168/MURD | 24/01/2022 | 365 | HASNA BEWA | 4.8 | 1.05 | 0
4313 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of Village MIRZAPUR (Village Code 315615) under MAHYAMPUR Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-I Block under Murshidabad Div Phe DTE in the District of Murshidabad. Tender no - 65 of 21-22 by SE MC | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000012/2022-2023 | 05-MSD/22-23 | 20/04/2022 | 0 | S.ENTERPRISE | 78.9 | 0 | 0
4314 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of village Kumarpur (Villagae Code 315597) under MAHYAMPUR surface based water supply scheme for arsenic affected aread of Beldanga-I Block in the dist of MSD PHE DTE. Tender no 88 of 21-21 by SE MC | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000244/2021-2022 | 35-MSD / 21-22 | 27/08/2021 | 0 | DECON INDIA | 31.77 | 0 | 0
4315 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Barua (P) (Village code 315619) under Mahyampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte.Scheme ID 000958825 in the District of Murshidabad.3135/MURD, 11/12/2020 | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000669/2021-2022 | 173-MSD/21-22 | 01/11/2021 | 0 | AMAL KUMAR DAS | 21.03 | 0 | 0
4316 | Murshidabad Division | Berhampur Sub-Division | Supply of different dia Sluice Valve, CI Specials & Different dia jeffy coupling under LSD PHE DTE. Tender no - 27 of 21-22 by AE LSD | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/001380/2021-2022 | 317-MSD/21-22 | 17/02/2022 | 0 | MADAN MOHAN SASMAL | 3.86 | 0 | 0
4317 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION)' from existing Distribution system within the Command area of village MAHYAMPUR (Village Code 315612) under MAHYAMPUR Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga-I Block in the District of Murshidabad. Tender no - 18 of 21-22 by SE MC | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/001517/2021-2022 | 425-MSD/21-22 | 31/03/2022 | 0 | TEKNO ENTERPRISE | 96.69 | 0 | 0
4318 | Murshidabad Division | Kandi Sub-Division | rESTORATION OF DAMAGE PORTION LYING OF PHE PIPE LINE OF HIZOLE UNDER MSD HIGHWAY DIV-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00960/2023-2024 |  | 12/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
4319 | Murshidabad Division | Kandi Sub-Division | Balance work for repair of road, construction of approach road & land development of Hizole-I & II & Bundai Water Supply Scheme of Kandi Block under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000006/2025-2026 | 835/MURD | 11/04/2025 | 234 | M/S JATIN | 69.3 | 0 | 5
4320 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well , 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gobarhati & Hizole Water Supply Scheme at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000034/2023-2024 | 1109/MURD | 24/04/2023 | 723 | INDRAJIT MAZUMDAR | 10.68 | 0 | 100
4321 | Murshidabad Division | Kandi Sub-Division | Allied works Pertaining to Construction of Cross Drain , Surface Drain, Office cum godown, Steel Structure Shade of Hizole-I PWSS at Kandi of Kandi-Sub Division under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000193/2024-2025 | 3211/MURD | 09/12/2024 | 357 | M/S JATIN | 53.73 | 0 | 10
4322 | Murshidabad Division | Kandi Sub-Division | Balance work for Extension of UPVC Pipeline and Road restoration work at different location of Hizole Zone -II Water Supply Scheme in Kandi Block of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000250/2024-2025 | 227/MURD | 27/01/2025 | 45 | M/S. S. DAS AND ENTERPRISE | 91.04 | 0 | 0
4323 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Laying of Distribution System & rising main including all type of specials,valves,street stand post and FHTC Work in all complete for Hizole (Zone-I) Water Supply Scheme under Murshidabad Division, P.H.Engg Dte.at Kandi Block, Murshidabad District. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000336/2022-2023 | 1723/MURD | 04/07/2022 | 120 | M/S. TAPAS KUMAR CHAKRABORTY | 676.45 | 329.64 | 1
4324 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Laying of Distribution System & rising main including all type of specials,valves,street stand post and FHTC Work in all complete for Hizole (Zone-II) Water Supply Scheme under Murshidabad Division, P.H.Engg Dte.at Kandi Block, Murshidabad District. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000355/2022-2023 | 1992/MURD | 21/07/2022 | 120 | M/S. S. DAS AND ENTERPRISE | 501.06 | 338.5 | 1
4325 | Murshidabad Division | Kandi Sub-Division | Construction of 700 Cum OHR, Boundary Wall (H.W, 2nd & 3rd Site), Pump House (H.W, 2nd & 3rd Site), Land Development (H.W, 2nd & 3rd Site) and office cum godown of HIZOLE (Zone- I) & its adjoining mouzas water supply scheme of Kandi Block under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000596/2023-2024 | 3342/MURD | 28/10/2023 | 886 | M/S JATIN | 374.61 | 52.49 | 5
4326 | Murshidabad Division | Kandi Sub-Division | Construction of 600 Cum OHR, Boundary Wall (H.W, 2nd & 3rd Site), Pump House (H.W, 2nd & 3rd Site), Land Development (H.W, 2nd & 3rd Site) and office cum godown of HIZOLE (Zone- II) & its adjoining mouzas water supply scheme of Kandi Block under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000597/2023-2024 | 3344/MURD | 28/10/2023 | 885 | M/S JATIN | 345.77 | 120.15 | 20
4327 | Murshidabad Division | Kandi Sub-Division | Sinking of 3 nos of 200 mm dia (through) and 80.0 mtr. deep tube well drilling by direct rotary method at Head work site, 2nd Site & 3rd site of Hizole( Zone-II) Water Supply Scheme of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001739/2021-2022 | 783/MURD | 23/03/2022 | 30 | NADIA TUBEWELLS | 16.75 | 16.36 | 1
4328 | Murshidabad Division | Kandi Sub-Division | Sinking of 3 nos of 200 mm dia (through) and 80.0 mtr. deep tube well drilling by direct rotary method at Head work site ,2nd Site & 3rd site of Hizole( Zone-I) Water Supply Scheme of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001756/2021-2022 | 782/MURD | 23/03/2022 | 30 | MAMATA USHA ENTERPRISE | 16.77 | 15.6 | 1
4329 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000031/2022-2023 | 2662/MURD | 20/09/2022 | 0 | Resource Division | 98.85 | 0 | 0
4330 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000039/2022-2023 | 2780/H/MURD | 01/10/2022 | 0 | Resource Division | 40.23 | 0 | 0
4331 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000056/2022-2023 | 3233/B/MURD | 02/12/2022 | 0 | Resource Division | 46.99 | 0 | 0
4332 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000098/2023-2024 | 1167/MURD/6 | 28/04/2023 | 0 | Resource Division | 99.41 | 0 | 0
4333 | Murshidabad Division | Kandi Sub-Division | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-18 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | VCH/000761/2022-2023 | 290-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 40.56 | 0 | 0
4334 | Murshidabad Division | Kandi Sub-Division | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-16 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | VCH/000762/2022-2023 | 290-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 4.08 | 0 | 0
4335 | Berhampore Mechanical | Kandi Sub-Division | Quotation for New Connection for Hizol W/S Scheme (Zone-I, Pump-II). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00002/2023-2024 | 26/DW-JJM | 10/05/2023 | 0 | WBSEDCL | 0.83 | 0 | 0
4336 | Berhampore Mechanical | Kandi Sub-Division | Quotation for New Connection for Hizol W/S Scheme (Zone-I, Pump-III). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00003/2023-2024 | 27/DW-JJM | 10/05/2023 | 0 | WBSEDCL | 0.83 | 0 | 0
4337 | Berhampore Mechanical | Kandi Sub-Division | Quotation for New Connection for Hizol W/S Scheme (Zone-I, Pump-I). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00004/2023-2024 | 28/DW-JJM | 10/05/2023 | 0 | WBSEDCL | 0.83 | 0 | 0
4338 | Berhampore Mechanical | Kandi Sub-Division | Quotation payment for New Connection (Hizol P/H No.- I). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00032/2023-2024 | 35/DW-JJM | 18/05/2023 | 0 | WBSEDCL | 0.84 | 0 | 0
4339 | Berhampore Mechanical | Kandi Sub-Division | Quotation payment for New Connection (Hizol P/H No.- III). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00033/2023-2024 | 37/DW-JJM | 18/05/2023 | 0 | WBSEDCL | 0.84 | 0 | 0
4340 | Berhampore Mechanical | Kandi Sub-Division | Quotation payment for New Connection (Hizol P/H No.- II). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00034/2023-2024 | 36/DW-JJM | 18/05/2023 | 0 | WBSEDCL | 0.84 | 0 | 0
4341 | Berhampore Mechanical | Kandi Sub-Division | SHIFTING OF 11KV AT HIZOL | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01583/2023-2024 | 450/WBSEDCL-JJM | 15/03/2024 | 0 | WBSEDCL | 0.97 | 0 | 0
4342 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I , II & III , Zone-I under Hizole ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000088/2023-2024 | 1933/MEDB | 16/06/2023 | 566 | CONCORD ENGINEERING | 33.21 | 0 | 40
4343 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.- I , II & III , Zone-II under Hizole ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000090/2023-2024 | 1934/MEDB | 16/06/2023 | 929 | M/S SAJAHAN CHOWDHURY | 33.19 | 26.68 | 42
4344 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Tungi ( Village Code -315525) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186507) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000058/2021-2022 | 1211/MURD | 10/05/2021 | 60 | MOTI RAHAMAN | 90.75 | 165.39 | 0
4345 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna ( Jal Jeevan Mission) and under command area of village of Chandpur (Village code 315552)under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000284/2022-2023 | 1561/MURD | 16/06/2022 | 1228 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 126.1 | 0 | 40
4346 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for :Augmentation of CHANDPUR Zone-I (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000359/2022-2023 | 2083/MURD | 27/07/2022 | 991 | TINA ROY | 355.12 | 41.23 | 85
4347 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Goghata ( Village Code -315526) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186507) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000435/2021-2022 | 1699/MURD | 07/07/2021 | 60 | M/S JAN MOHAMMAD | 52.35 | 0 | 40
4348 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) village of Patikabari (Village Code-315550) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000522/2022-2023 | 2498/MURD | 30/08/2022 | 120 | M/S. SINHA & SONS | 183.88 | 0 | 0
4349 | Murshidabad Division | Berhampur Sub-Division | Repairing and Refilling of filter media with allied works of Iron Elemination Plant (I.E.P) at Chandpur W/S Scheme, under Berhampore Sub-Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001345/2021-2022 | 12/BSD | 10/01/2022 | 15 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 4.85 | 0 | 0
4350 | Murshidabad Division | Berhampur Sub-Division | Providing 365 nos Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna within command area of village Tungi (Village code 315525) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nowda Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005186507 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001710/2021-2022 | 701/MURD | 14/03/2022 | 60 | MOTI RAHAMAN | 98.18 | 49.92 | 0
4351 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000022/2021-2022 | 539/7/MURD | 25/02/2022 | 0 | Resource Division | 1.46 | 0 | 0
4352 | Murshidabad Division | Berhampur Sub-Division | AND REFILLING OF FILTER MEDIA WITH ALLIED WORKS OF IEP OF CHANDPUR WSS, TNO- 143/21-22/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/000042/2022-2023 | 38-MSD/22-23 | 21/04/2022 | 0 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 4.85 | 0 | 0
4353 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 235 nos household under command area of village of Uttar Gopalpur, Molladanga, Arizpur, Purandanpur, Purushottampur, Bota,Durgapur ( Village Code-314744, 314745, 314746, 314747, 314753, 314754, 314756) under Purushottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001756484) |  |  | ORD/000129/2022-2023 | 1212/MURD | 10/05/2022 | 30 | BARMAN ENTERPRISE | 12.4 | 0 | 1
4354 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Durgapur( Village Code -314756) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar_I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756484) |  |  | ORD/000196/2021-2022 | 1747/MURD | 09/07/2021 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 52.77 | 19.02 | 1
4355 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Purushottampur (Village code 314753) under Purushottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756484 in the District of Murshidabad. (Sl No-04) |  |  | ORD/000351/2021-2022 | 2502/MURD | 17/08/2021 | 120 | SUJIT KUMAR SAHA | 85.13 | 134.17 | 1
4356 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Molladanga (Village code 314745) under Purushottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756484 |  |  | ORD/000411/2021-2022 | 2556/MURD | 23/08/2021 | 120 | M/S TRADE ASSOCIATE | 69.82 | 15.24 | 1
4357 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Arizpur (Village code 314746) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad.¿ |  |  | ORD/000565/2020-2021 | 36/MURD | 05/01/2021 | 60 | ARJU CONSTRUCTION | 5.82 | 5.43 | 1
4358 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Uttar Gopalpur (Village code 314744) under Purusottampur and Jitpur Ground Water Based Water Supply Scheme under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad. |  |  | ORD/000820/2020-2021 | 031/MURD | 05/01/2021 | 60 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 9.28 | 0 | 0
4359 | Murshidabad Division |  | Additional Works for Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of BOTA ( Village Code -314754) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756484) |  |  | ORD/001245/2021-2022 | 52/ISD | 28/01/2022 | 30 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 4.8 | 4.11 | 1
4360 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for Providing Balance Functional Household Tap Connections (FHTC) of 559 Nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Molladanga (Village code 314745) under Purusattampur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 000175684). |  |  | ORD/001701/2021-2022 | 671/MURD | 10/03/2022 | 30 | S.K. ENTERPRISE (PROP:SHAMIM ISLAM) | 17.21 | 16.53 | 1
4361 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bota, 314754 of Purushottampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PART-I), TNO- 929/20-21/EE |  |  | VCH/000655/2021-2022 | 127-MSD/21-22 | 07/10/2021 | 0 | SINHA & COMPANY | 12.65 | 0 | 0
4362 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MOLLADANGA (Village Code 314745) under PURUSOTTAMPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 17 of 21-22 by SE MC |  |  | VCH/001487/2021-2022 | 420-MSD/21-22 | 23/03/2022 | 0 | M/S TRADE ASSOCIATE | 46.29 | 0 | 0
4363 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village DURGAPUR (Village Code 314756) under PURUSOTTAMPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 291 of 20-21 by EE MURD |  |  | VCH/001510/2021-2022 | 405-MSD/21-22 | 23/03/2022 | 0 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 31.84 | 0 | 0
4364 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of village of Sarulia (village code 315611) ,Mirzapur (village code 315615)under (Zone-G) and additional remaining villages under Begunbari (Part) ,Maniknagar (Part) and Naoapukhuria (Part) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000289/2022-2023 | 1803/BD-I | 31/03/2023 | 120 | M/S GUHA & ROY | 373.58 | 0 | 0
4365 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Cossimbazar (Village code 315444), Sibnagar Badarpur (Village Code-315446) under Hatinagar (Zone-A) Surface Water Supply Scheme of Central Sector Part-II, Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000313/2020-2021 | 980/BD-I | 17/12/2020 | 180 | CHAKRABORTY CONSTRUCTION | 307.25 | 117.5 | 69
4366 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | Junior Engineer-I | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 19.13 | 1
4367 | Murshidabad Division |  | Laying of balance work of HDPE pipe Risingmain of Basudebpur Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. |  |  | ORD/000617/2020-2021 | 654/MURD | 18/02/2021 | 60 | JOY BISHNU ENGINEERING CO. | 7.91 | 7.83 | 0
4368 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (1974 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Jaladipur ( Village Code -313860) under Basudebpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000639/2023-2024 | 3440/MURD | 03/11/2023 | 60 | BHOWMIK CONSTRUCTION | 67.6 | 0 | 0
4369 | Murshidabad Division |  | Preparation of design, Drawing and approval from the N.H.A.I Authorities including supply of 200 mm dia 8 mm thick MS Water Carring Pipe, 600 mm dia 10 mm thick MS casing Pipe & Pushing of casing pipe by Hydraulic Jacking Technique Method across the Chainage 270+550 of the N.H.-34 of at Mouza-Basudebpur of Basudebpur adjoining mouza W/S Scheme & across at chainage 273+100 of the N.H.-34 of at Mouza-Joykrishnapur of Joykrishnapur W/S Scheme in Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000853/2022-2023 | 755/MURD | 16/03/2023 | 90 | SAMBHU NATH ROY | 62.1 | 26.03 | 0
4370 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL- 15 |  |  | VCH/000862/2022-2023 | 370-MSD/22-23 | 21/10/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 20.99 | 0 | 0
4371 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) of 1878 nos in connection with Jal Swapna (Jal Jeevan Mission ) under command area of Village of Sarbangapur Partrly ( Village Code -315522) under Sarbangapur Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000027/2022-2023 | 1057/MURD | 25/04/2022 | 60 | MAMATA USHA ENTERPRISE | 93.87 | 93.23 | 1
4372 | Murshidabad Division |  | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315522) under Sarbangapur Zone-I Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000075/2022-2023 | 180/BSD | 12/04/2022 | 15 | AMIT KUMAR SAHA | 4.83 | 4.83 | 1
4373 | Murshidabad Division |  | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315522) under Sarbangapur Zone-I Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000076/2022-2023 | 181/BSD | 12/04/2022 | 15 | SOUNAK ENTERPRISE | 4.86 | 4.86 | 1
4374 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sonatikri (Village code 315528) under Sarbangapur Ground Water Based water Supply Scheme for Arsenic Affected Area of Nowda Block, under Murshidabad Division, PHE Dte. Scheme ID 00051723279 in the District of Murshidabad. (Sl No-02) |  |  | ORD/000083/2020-2021 | 291/MURD | 27/01/2021 | 180 | M/S. S. DAS AND ENTERPRISE | 99.82 | 0 | 0
4375 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Pareshnathpur (Village code 315529) under Sarbangapur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723279 in the District of Murshidabad. |  |  | ORD/000215/2020-2021 | 3239/MURD | 22/12/2020 | 60 | RATAN DUTTA | 33.87 | 9.45 | 0
4376 | Murshidabad Division |  | Additional work of providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sonatikuri (village code 315528) under Sarbangapur Zone-II Water Supply Scheme of Nowda Block in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000337/2021-2022 | 2436/MURD | 12/08/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 46.04 | 0 | 0
4377 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dudhsar (Village code 315521) under Sarbangapur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723279 in the District of Murshidabad. |  |  | ORD/000540/2020-2021 | 34/MURD | 05/01/2021 | 60 | CHATTERJEE ENTERPRISE | 19.26 | 8.44 | 1
4378 | Murshidabad Division |  | Supplying and Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315522) under Sarbangapur Zone-I Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/001731/2021-2022 | 78/BSD | 07/03/2022 | 15 | SWAPAN DAS | 4.83 | 0 | 1
4379 | Murshidabad Division |  | Supplying and Laying of 160mm dia UPVC pipeline in connection providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315522) under Sarbangapur Zone-I Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/001733/2021-2022 | 79/BSD | 07/03/2022 | 15 | SWAPAN DAS | 4.85 | 0 | 1
4380 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000027/2021-2022 | 539/1/MURD | 25/02/2022 | 0 | Resource Division | 10.31 | 0 | 0
4381 | Murshidabad Division |  | Additional work of providing Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) from existing distribution system within the command area of village of Sonatikri Village Code (315528) under SARBANGAPUR ZONE-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District under Murshidabad Division, PHE Dte. tender No - 343 of 21-22 by EE |  |  | VCH/000562/2021-2022 | 118-MSD/21-22 | 05/10/2021 | 0 | M/S. S. DAS AND ENTERPRISE | 46.02 | 0 | 0
4382 | Murshidabad Division |  | Supplying and Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission and jal swapna under command area of village of Sarbangapur under Sarbangapur Zone-I W/S Scheme un MSD PHE DTE. Tender No- 178 of 2021-2022 BY AE BSD |  |  | VCH/001554/2021-2022 | 449-MSD/21-22 | 31/03/2022 | 0 | SWAPAN DAS | 4.83 | 0 | 0
4383 | Murshidabad Division |  | Supplying and Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission and jal swapna under command area of village of Sarbangapur under Sarbangapur Zone-I W/S Scheme un MSD PHE DTE. Tender No- 177 of 2021-2022 BY AE BSD |  |  | VCH/001555/2021-2022 | 449-MSD/21-22 | 31/03/2022 | 0 | SWAPAN DAS | 4.85 | 0 | 0
4384 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHAMMADPUR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000402/2021-2022 | 245/LSD | 18/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.18 | 0 | 0
4385 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Amdahara Haziganja (Village code 314497) under Bhandara Ground Water Based water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl -05) |  |  | ORD/001804/2021-2022 | 596/MURD | 03/03/2022 | 180 | M/S. S. DAS AND ENTERPRISE | 57.24 | 34.05 | 0
4386 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (963 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Jehelinagar ( Village Code -313928) & Rosanpur ( Village Code -313930) under Ghorapakhiagangin Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000634/2023-2024 | 3439/MURD | 03/11/2023 | 45 | SHIRSHENDU MUKHERJEE | 33.92 | 0 | 0
4387 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-12 |  |  | VCH/000861/2022-2023 |  | 21/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 54.26 | 0 | 0
4388 | Murshidabad Division |  | APPLICATION ID: ER-MLDT-2022-WL-12, SCHEME CODE: 9751, SCHEME NAME: GHORAPAKHIAGANGIN ZONE - II, IMIS CODE: 40019398 (SINHA AND SONS) PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-12 |  |  | VCH/001018/2022-2023 | 369-MSD/22-23 | 21/10/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 54.26 | 0 | 0
4389 | Murshidabad Division |  | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B |  |  | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 7.4 | 100
4390 | Murshidabad Division |  | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Jangipur Road Station to Gankar Station ( TP NO 210/09 & 211/00) at Kanupur mouza & Connecting with existing 160 mm dia UPVC distribution main line of Jarur Surface based W/S Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000412/2023-2024 | 2862/MURD | 08/09/2023 | 30 | PRADIP KUMAR DAS | 5.94 | 5.94 | 100
4391 | Murshidabad Division |  | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Jangipur Road Station to Gankar Station ( TP NO 210/09 & 211/00) at Kanupur mouza & Connecting with existing 160 mm dia UPVC distribution main line of Jarur Surface based W/S Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000465/2020-2021 | 547/MURD | 05/02/2021 | 30 | PRADIP KUMAR DAS | 39.01 | 12.79 | 100
4392 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHESHAIL-I G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/001337/2021-2022 | 55/JSD | 25/01/2022 | 30 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0
4393 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHESHAIL-II G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/001338/2021-2022 | 56/JSD | 25/01/2022 | 30 | IMAGIN | 4.16 | 0 | 0
4394 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Mahesail (Village code 313954) & Amuha (Village code 313955) under Mahisail Ground Based Water Supply Scheme for Arsenic Affected Areas of Suti-II Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723341) |  |  | ORD/001636/2021-2022 | 502/MURD | 23/02/2022 | 180 | DECON INDIA | 239.71 | 179.88 | 80
4395 | Murshidabad Division |  | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 180 (One Hundred Eighty) Days].For the month of 18/01/2024 to 15/07/2024. [ Vehicle No:- WB 58 BU 9284] |  |  | BILL/01159/2024-2025 | 430-MSD/2024-25 | 01/10/2024 | 0 | ABIDA CONSTRUCTION | 0.24 | 0 | 0
4396 | Murshidabad Division |  | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/04/2024 to 30/09/2024 = 120 days |  |  | BILL/01536/2024-2025 | 569-MSD/2024-25 | 26/11/2024 | 0 | HAMIDUL ISLAM | 0.35 | 0 | 0
4397 | Murshidabad Division |  | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/04/2024 to 30/09/2024 = 120 days |  |  | BILL/01537/2024-2025 | 569-MSD/2024-25 | 26/11/2024 | 0 | HAMIDUL ISLAM | 0.34 | 0 | 0
4398 | Murshidabad Division |  | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Daily hire basis for official use for the Office of the Dy Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01 (One) Year]. Period from i.e. 07/02/2024 to 05/02/2025 [Vehicle No.WB58AR/5026] |  |  | BILL/01572/2024-2025 | 575-MSD/2024-25 | 29/11/2024 | 0 | MD MUKLESUR RAHAMAN | 0.29 | 0 | 0
4399 | Murshidabad Division |  | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/07/2024 to 16/01/2025. [ Vehicle No:- WB 58 CD 3758] |  |  | BILL/01678/2024-2025 | 577-MSD/2024-25 | 29/11/2024 | 0 | HASSAN CONSTRUCTION | 0.4 | 0 | 0
4400 | Murshidabad Division |  | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte.for 06 (Six) Months i.e. from 08.07.2024 to 07.01.2025. |  |  | ORD/000034/2024-2025 | 54/LSD | 02/07/2024 | 184 | BARI ENTERPRISE | 0.89 | 0 | 0
4401 | Murshidabad Division |  | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 180 (One Hundred Eighty) Days].For the month of 16/07/2024 to 11/01/2025. [ Vehicle No:- WB 58 BU 9284] |  |  | ORD/000087/2024-2025 | 48/JSD | 15/07/2024 | 180 | ABIDA CONSTRUCTION | 0.88 | 0 | 0
4402 | Murshidabad Division |  | Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490 |  |  | ORD/000120/2024-2025 | 237/BSD | 05/08/2024 | 160 | ABIDA CONSTRUCTION | 0.93 | 0 | 0
4403 | Murshidabad Division |  | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 182 Days] w.e.f 01/11/2024 to 01/04/2025. Vehicle No [WB58CA/1034] |  |  | ORD/000165/2024-2025 | 390/MSD | 29/10/2024 | 182 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.89 | 0 | 0
4404 | Murshidabad Division |  | Continuation work order for Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Assistant Engineer (HQ), Murshidabad Division, P.H.E. Dte. For 06(Six) Months (on and from 01/11/2024 to 30/04/2025) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver, Taxes , Insurance , Fees etc. as applicable Excluding fuel, lubricant etc as per order) |  |  | ORD/000166/2024-2025 | 2911/MURD | 29/10/2024 | 182 | M/S JOY MA BANAMALI | 1.05 | 0 | 100
4405 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (323 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Tegharia ( Village Code -315683) under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga-II Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000625/2023-2024 | 3563/MURD | 21/11/2023 | 30 | ARJU CONSTRUCTION | 11.66 | 0 | 0
4406 | Murshidabad Division |  | Hiring of one no. Mahindra & Mahindra make Bolero Diesel Passenger car for official use of the Assistant Engineer, Berhampore Sub-Division, P.H.Engineering Dte. for 06 (six) Months. (Period from 01/01/2024 to 30/06/2024) |  |  | ORD/000757/2023-2024 | 128/BSD | 28/12/2023 | 183 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 0.91 | 0 | 0
4407 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Batkamari (Village code 314689) under Jorgacha Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723176 in the District of Murshidabad. Tender no - 44 of 20-21 by EE MURD |  |  | VCH/001382/2021-2022 | 332-MSD/21-22 | 25/02/2022 | 0 | DAS TRADING CO. | 22.28 | 0 | 0
4408 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
4409 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
4410 | Murshidabad Division | Berhampur Sub-Division | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangadhari (village code 315534) under Gangadhari Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000069/2022-2023 | 174/BSD | 12/04/2022 | 15 | SWAPAN DAS | 4.83 | 4.83 | 0
4411 | Murshidabad Division | Berhampur Sub-Division | Laying of 90mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangadhari (village code 315534) under Gangadhari Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000070/2022-2023 | 175/BSD | 12/04/2022 | 15 | SOUNAK ENTERPRISE | 4.84 | 4.84 | 0
4412 | Murshidabad Division | Berhampur Sub-Division | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangadhari (village code 315534) under Gangadhari Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000071/2022-2023 | 176/BSD | 12/04/2022 | 15 | M/S LOKNATH CONSTRUCTION | 4.85 | 0 | 0
4413 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) of 1786 nos in connection with (Jal Jeevan Mission ) and under command area of village of Gangadhari ( Village Code -315534) under Gangadhari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000134/2022-2023 | 1232/MURD | 11/05/2022 | 60 | PRADIP KUMAR DAS | 78.92 | 59.04 | 0
4414 | Murshidabad Division | Berhampur Sub-Division | Balanced work of Boundary wall and R.B.T fencing work at Gangadhari Water Supply Scheme under Berhampore Sub Division,Murshidabad Division P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001592/2021-2022 | 27/BSD | 14/01/2022 | 30 | MAA DURGA ENTERPRISE | 4.46 | 4.46 | 0
4415 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000021/2021-2022 | 539/6/MURD | 25/02/2022 | 0 | Resource Division | 9.82 | 0 | 0
4416 | Murshidabad Division |  | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Edrakpur (village code 315547) under Edrakpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000072/2022-2023 | 177/BSD | 12/04/2022 | 15 | SOUVIK HALDER | 4.85 | 0 | 0
4417 | Murshidabad Division |  | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Edrakpur (village code 315547) under Edrakpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000073/2022-2023 | 178/BSD | 12/04/2022 | 15 | M/S.S.S. ENTERPRISE | 4.83 | 0 | 90
4418 | Murshidabad Division |  | Laying of 90mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Edrakpur (village code 315547) under EdrakpurWater Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000074/2022-2023 | 179/BSD | 12/04/2022 | 15 | SWAPAN DAS | 4.83 | 0 | 0
4419 | Murshidabad Division |  | Supply of C.I specials to join existing AC pipe with UPVC pipe in connection with FHTC of Edrakpur piped water supply scheme of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. |  |  | ORD/000138/2022-2023 | 188/BSD | 28/04/2022 | 30 | PM CONSTRUCTION | 3.39 | 0 | 0
4420 | Murshidabad Division |  | Distribution system 110mm, 90mm and 75mm dia pipe in connection with FHTC of Edrakpur piped water supply scheme at Raghunathpur village of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. |  |  | ORD/000139/2022-2023 | 187/BSD | 28/04/2022 | 30 | RAFIKUL HASAN | 4.51 | 4.15 | 0
4421 | Murshidabad Division |  | Distribution system 110mm, 90mm and 75mm dia pipe in connection with FHTC of Edrakpur piped water supply scheme at Raghunathpur village of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. |  |  | ORD/000140/2022-2023 | 189/BSD | 28/04/2022 | 30 | RAFIKUL HASAN | 4.76 | 4.77 | 0
4422 | Murshidabad Division |  | Distribution system 110mm, 90mm and 75mm dia pipe in connection with FHTC of Edrakpur piped water supply scheme of Nawda village of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. |  |  | ORD/000183/2022-2023 | 190/BSD | 28/04/2022 | 30 | MOINAK CHATTOPADHYAY | 4.76 | 4.76 | 0
4423 | Murshidabad Division |  | Sinking of 300 X 200mm Dia Tube Well 82 mtr. Deep by D.R. Rig Method using UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) for piped water supply scheme of EDRAKPUR & its adjoining mouzas at Berhampore Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. |  |  | ORD/000187/2022-2023 | 196/BSD | 28/04/2022 | 30 | KISMAT ARA BEGAM | 3.95 | 0 | 0
4424 | Murshidabad Division |  | Supply and Delivery for Sinking of 300 X 200mm Dia Tube Well 82 mtr. Deep by D.R. Rig Method using UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) for piped water supply scheme of EDRAKPUR & its adjoining mouzas at Berhampore Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. |  |  | ORD/000188/2022-2023 | 197/BSD | 28/04/2022 | 30 | KISMAT ARA BEGAM | 4.65 | 0 | 0
4425 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) of mouza Edrakpur (Village code 315547), of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block, of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID 0005182896) |  |  | ORD/001209/2021-2022 | 17/MURD | 05/01/2022 | 180 | KISMAT ARA BEGUM | 99.02 | 94.76 | 0
4426 | Murshidabad Division |  | LAYING OF 110 MM DIA UPVC PIPELINE FOR PROVIDING FHTC IN CONNECTION WITH JJM EDRAKPUR UNDER EDRAKPUR W/S SCHEME UNDER MSD. PHE DTE TENDER NO 222 OF 21-22 AE BSD |  |  | VCH/000316/2022-2023 | 177-MSD/22-23 | 17/05/2022 | 0 | M/S SS ENTERPRISE (SUKESH GHOSH) | 4.83 | 0 | 0
4427 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
4428 | Murshidabad Division | Berhampur Sub-Division | HIRE OF CAR FOR AE-JSD, W/O NO- 52/MURD, DT-16/07/2024 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/01212/2024-2025 | 341-MSD/2024-25 | 30/08/2024 | 0 | HASSAN CONSTRUCTION | 0.33 | 0 | 0
4429 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01(One) Year] (period for i.e 07/02/2023 to 06/02/2024). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/01291/2023-2024 | 559-MSD/2023-24 | 20/02/2024 | 0 | MD MUKLESUR RAHAMAN | 0.79 | 0 | 0
4430 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte.Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/01439/2023-2024 | 630-MSD/2023-24 | 19/03/2024 | 0 | MERCHANDISE-INDIA | 2.39 | 0 | 0
4431 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 182 Days] w.e.f 03/05/2024 to 31/10/2024. Vehicle No [WB58CA/1034] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000002/2024-2025 | 158/MSD | 29/04/2024 | 182 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.89 | 0.37 | 0
4432 | Murshidabad Division | Berhampur Sub-Division | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.06.2024 to 30.11.2024) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000010/2024-2025 | 80/HQ | 31/05/2024 | 183 | DULAL CHOWDHURY | 0.91 | 0 | 30
4433 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxi cab (Non- Air Condition, Bharat Stage ¿ III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000022/2024-2025 | 77/KSD | 25/04/2024 | 150 | H.MONDAL CONSTRUCTION | 0.87 | 0 | 0
4434 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/04/2023 to 16/10/2023. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000053/2023-2024 | 437./A/JSD | 17/04/2023 | 183 | M/S JOY MA BANAMALI | 0.88 | 2.4 | 100
4435 | Murshidabad Division | Berhampur Sub-Division | Continuation Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2023 to 17.04.2024.[Vehicle No-WB57E7960] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000093/2023-2024 | 437-/AA/JSD | 17/04/2023 | 365 | MAJIBUR RAHAMAN | 4.76 | 0 | 70
4436 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 03 (three) months i.e. from 01/10/2024 to 31/12/2024 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000167/2024-2025 | 489/ISD | 30/09/2024 | 92 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.45 | 0 | 0
4437 | Murshidabad Division | Berhampur Sub-Division | Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For (05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05 (Five) Months].for the month of July2024 to November2024 [Vehicle No.WB25M1561] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000114/2024-2025 | 1887/MURD | 29/06/2024 | 150 | M/S B K ENTERPRISE | 0.87 | 0 | 100
4438 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/10/2024 to 31/03/2025 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000168/2024-2025 | 490/ISD | 30/09/2024 | 120 | HAMIDUL ISLAM | 0.69 | 0 | 0
4439 | Murshidabad Division | Berhampur Sub-Division | Hiring of one no. Mahindra & Mahindra make Bolero Diesel Passenger car for official use of the Assistant Engineer, Berhampore Sub-Division, P.H.Engineering Dte. for 06 (six) Months.(Period from 01/07/2023 to 31/12/2023 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000278/2023-2024 | 44/A/BSD | 23/06/2023 | 183 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 0.91 | 2.4 | 100
4440 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Tenya (Village code 315737) under Tenya(Zone-I) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154932 in the District of Murshidabad. (Sl No-21) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000447/2020-2021 | 47/MURD | 06/01/2021 | 180 | CHAKRABORTY CONSTRUCTION | 58.49 | 9.32 | 1
4441 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RANGAMATI CHANDPARA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000521/2021-2022 | 352/BSD | 27/08/2021 | 30 | IMAGIN | 4.17 | 4.17 | 0
4442 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of 01(one) no. Diesel Bolero /Marshal Car for official use having license for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Murshidabad RWS Sub-Division, for 06(Six) months. (i.e. 01/10/2022 to 31/03/2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000539/2022-2023 | 295./HQ | 21/09/2022 | 181 | SISIR KUMAR DE | 0.91 | 0 | 100
4443 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 0 | 90
4444 | Murshidabad Division | Berhampur Sub-Division | Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywere within any trouble on daily wage basis for official used under the control of the Assistant engineer (HQ), Murshidabad Division, P.H.E. Dte. For 1(One) year (on and from 01/11/2023 to 31/10/2024) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver , Taxes , Insurance , Fees etc..as applicable Excluding fuel, lubricant etc as per order) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000657/2023-2024 | 3381/MURD | 31/10/2023 | 365 | M/S JOY MA BANAMALI | 2.11 | 2.79 | 28
4445 | Murshidabad Division | Berhampur Sub-Division | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.12.2023 to 31.05.2024) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000703/2023-2024 | 170/HQ | 29/11/2023 | 182 | DULAL CHOWDHURY | 0.91 | 2.4 | 50
4446 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/10/2023 to 31/03/2024 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000730/2023-2024 | 403/ISD | 29/09/2023 | 182 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 1.13 | 100
4447 | Murshidabad Division | Berhampur Sub-Division | Continuation Work Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte. for 06 (Six) Months. i.e. from 08.01.2024 to 07.07.2024. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000732/2023-2024 | 02/LSD | 02/01/2024 | 182 | BARI ENTERPRISE | 0.89 | 1.1 | 51
4448 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/10/2023 to 31/03/2024 (120 days) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000751/2023-2024 | 404/ISD | 29/09/2023 | 120 | HAMIDUL ISLAM | 0.69 | 2.03 | 30
4449 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 180 (One Hundred Eighty) Days].For the month of 18/01/2024 to 15/07/2024. [ Vehicle No:- WB 58 BU 9284] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000760/2023-2024 | 892/JSD | 17/01/2024 | 180 | ABIDA CONSTRUCTION | 0.88 | 0.63 | 0
4450 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 168Days] i.e period form 17/11/2023 to 02/05/2024. Vehicle No [WB58CA/1034] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000763/2023-2024 | 398/MSD | 17/11/2023 | 168 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.82 | 1.08 | 25
4451 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Daily hire basis for official use for the Office of the Dy Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01 (One) Year]. Period from i.e. 07/02/2024 to 05/02/2025 [Vehicle No.WB58AR/5026] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000783/2023-2024 | 392/MURD | 06/02/2024 | 365 | MD MUKLESUR RAHAMAN | 2.11 | 1.35 | 50
4452 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/04/2024 to 30/09/2024 = 182 days | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000873/2023-2024 | 165/ISD | 28/03/2024 | 183 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 0 | 50
4453 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/04/2024 to 30/09/2024 = 120 days | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000874/2023-2024 | 166/ISD | 28/03/2024 | 120 | HAMIDUL ISLAM | 0.69 | 0 | 50
4454 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months. Vehicle No. WB-57E-9142 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000881/2022-2023 | 415/ISD | 29/09/2022 | 181 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 1.12 | 50
4455 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of 01(one) no. Diesel Bolero /Marshal Car for official use having license for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Murshidabad RWS Sub-Division, for 06(Six) months. (i.e. 01/04/2023 to 30/09/2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000901/2022-2023 | 55/HQ | 28/03/2023 | 184 | SISIR KUMAR DE | 0.91 | 0 | 100
4456 | Murshidabad Division | Berhampur Sub-Division | Construction of pathway & painting of boundary wall including gate at Head work Site and development of land at 2nd tubewell site of Bahara water supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001614/2021-2022 | 381 / KSD | 19/01/2022 | 30 | SUGATA CHOWDHURY | 4.82 | 4.78 | 100
4457 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) at village of FATEPUR West side ( Village Code _315310) of Fatepur Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/002071/2021-2022 | 106/BSD | 28/03/2022 | 30 | CHOWDHURY CONSTRUCTION | 4.79 | 0 | 0
4458 | Murshidabad Division | Berhampur Sub-Division |  | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/00025/2023-2024 | 48-MSD/2023-24 | 11/05/2023 | 0 | BURIMA TELECOM SYSTEM | 0.39 | 0 | 0
4459 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sungai (Village code 315363 under Sungai Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723237 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001467/2021-2022 | 278/MURD | 03/02/2022 | 60 | MAHATO ENTERPRISE | 9.29 | 9.28 | 0
4460 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
4461 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
4462 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) of 1329 nos in connection with Jal Swapna (Jal Jeevan Mission ) & Laying of Distribution system of Selamatpur ( Village Code -315421) under Selamatpur Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000047/2022-2023 | 1058/MURD | 25/04/2022 | 60 | M/S. S. DAS AND ENTERPRISE | 94.54 | 61 | 90
4463 | Murshidabad Division | Kandi Sub-Division | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000056/2022-2023 | 161/BSD | 12/04/2022 | 15 | SWAPAN DAS | 4.84 | 4.84 | 0
4464 | Murshidabad Division | Kandi Sub-Division | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000059/2022-2023 | 164/BSD | 12/04/2022 | 15 | M/S SUKESH GHOSH | 4.84 | 4.84 | 0
4465 | Murshidabad Division | Kandi Sub-Division | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000060/2022-2023 | 165/BSD | 12/04/2022 | 15 | AMIT KUMAR SAHA | 4.85 | 4.85 | 0
4466 | Murshidabad Division | Kandi Sub-Division | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000061/2022-2023 | 166/BSD | 12/04/2022 | 15 | M/S LOKENATH CONSTRUCTION | 4.83 | 0 | 0
4467 | Murshidabad Division | Kandi Sub-Division | Laying of 140mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000062/2022-2023 | 167/BSD | 12/04/2022 | 15 | SWAPAN DAS | 4.84 | 4.84 | 0
4468 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission) and Laying of Distribution system of Selamatpur ( village code: 315421 ) Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. For 35nos FHTC. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000167/2022-2023 | 156/BSD | 12/04/2022 | 30 | ALOK BANERJEE ENTERPRISE | 4.84 | 3.27 | 0
4469 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Selamatpur ( village code: 315421 ) of Ground Based piped water supply scheme under Berhampore Sub-Division, Murshidabad Division, PHE Dte. For 35 nos FHTC. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000545/2022-2023 | 156/BSD | 12/04/2022 | 30 | ALOK BANERJEE ENTERPRISE | 4.84 | 0 | 100
4470 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | RTOR000018/2021-2022 | 539/3/MURD | 25/02/2022 | 0 | Resource Division | 7.3 | 0 | 0
4471 | Murshidabad Division | Kandi Sub-Division | Laying of 110mm dia upvc ppeline FHTC .......................SELAMATPUR UNDER SELAMATPUR W/S SCHEME. TENDER NO 210 -21-22 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | VCH/000313/2022-2023 | 179-MSD/22-23 | 26/05/2022 | 0 | M/S LOKNATH CONSTRUCTION | 4.83 | 0 | 0
4472 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Jalangi Zone-I Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000343/2022-2023 | 1875/MURD | 15/07/2022 | 1165 | DOBAY CONSTRUCTION | 250.61 | 80.67 | 40
4473 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-I Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000584/2022-2023 | 3053/MURD | 17/11/2022 | 45 | MAMATA USHA ENTERPRISE | 23.58 | 21.5 | 1
4474 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000028/2024-2025 | MURD/2481/01 | 04/09/2024 | 0 | Resource Division | 13.39 | 0 | 0
4475 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000036/2022-2023 | 2780/E/MURD | 01/10/2022 | 0 | Resource Division | 13.39 | 0 | 0
4476 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000173/2023-2024 | 1180/MURD/16 | 29/04/2023 | 0 | Resource Division | 235.38 | 0 | 0
4477 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Karimpur Jalangi Zone-III Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000344/2022-2023 | 1876/MURD | 15/07/2022 | 365 | J.S. CONSTRUCTION | 194.67 | 190.87 | 90
4478 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000036/2024-2025 | MURD/2481/08 | 04/09/2024 | 0 | Resource Division | 7.57 | 0 | 0
4479 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000040/2022-2023 | 2780/I/MURD | 01/10/2022 | 0 | Resource Division | 7.57 | 0 | 0
4480 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000165/2023-2024 | 1180/MURD/11 | 29/04/2023 | 0 | Resource Division | 8.83 | 0 | 0
4481 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000183/2023-2024 | 1210/MURD/29 | 02/05/2023 | 0 | Resource Division | 10.21 | 0 | 0
4482 | Murshidabad Division | Berhampur M/E Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kadkhali ( Village Code -315657) under Bachhara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga_II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000183/2021-2022 | 1570/MURD | 25/06/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 23.43 | 0 | 0
4483 | Murshidabad Division | Berhampur M/E Division | Additional work of providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kadkhali (village code 315657) under Bachhara Water Supply Scheme of Beldanga-II Block in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000433/2021-2022 | 2594/MURD | 25/08/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 16.76 | 0 | 0
4484 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under Bachhara ground water based water supply scheme under Block_ Beldanga-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000706/2023-2024 | 4331/MEDB | 29/12/2023 | 91 | NABAUDYAG ELECTRICAL ENGINEERING CO OP. SOC. LTD. | 22.69 | 0 | 0
4485 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based JOT KAMAL (ZONE-I), JOTKAMAL (Zone-II) & JOTKAMAL (Zone-III) PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000282/2023-2024 | 2643/MURD | 23/08/2023 | 587 | M/S NIRAPADA BHATTACHARJEE | 1194.05 | 0 | 10
4486 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jotkomol Zone-II Water Supply Scheme of TW-I HW Site under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000582/2022-2023 | 3065/MURD | 17/11/2022 | 30 | M/S B.R. SUPPLIERS | 10.6 | 9.12 | 100
4487 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SRIKANTABATI PART B & JOTKAMAL ZONE -II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000620/2023-2024 | 3395/MURD | 01/11/2023 | 21 | KALACHAND DAS | 18.4 | 0 | 100
4488 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JOTKOMAL ZONE-II Water Supply Scheme as required at Suti-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000630/2023-2024 | 3425/MURD | 02/11/2023 | 21 | SUJIT KUMAR SAHA | 11.79 | 0 | 100
4489 | Murshidabad Division | Berhampur M/E Division | Renovation of Existing IEP (Capacity 58 Cu.M/hr) for changing of 01 No Iron Removal Filter media unit of (3.30 m dia x 1.50 M HOS) & 01 No Oxidation Chember of (1.00 M dia x 1.00 M HOS) and painting all vessel, pipes etc. all complete for Augumentation of JOTKOMAL ZONE-II Pipe Water supply scheme, Block-Raghunathganj-II, under Murshidabad Division P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000662/2023-2024 | 3560/MURD | 21/11/2023 | 30 | M/S BAPPA ENTERPRISE | 4.89 | 0 | 100
4490 | Murshidabad Division | Berhampur M/E Division | Allied works for Renovation of Existing IEP (Capacity 54 Cu.M/hr) at Jotkamal Zone-II W/S Scheme in connection with Augmentation of Jotkamal (Zone-II) PWSS under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000834/2023-2024 | 784/MURD | 14/03/2024 | 20 | M/S BAPPA ENTERPRISE | 11.26 | 0 | 0
4491 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.26 | 100
4492 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. II and NEW OHR SITE of Zone-II under JOTKAMAL PIPED WATER SUPPLY SCHEME, BLOCK- DOMKAL RAGHUNATHGANJ-II DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000021/2025-2026 | 1143/MEDB | 14/05/2025 | 92 | HANNAN BUILDERS PVT LTD | 22.73 | 0 | 0
4493 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Jotkamal , Zone-II ground water based water supply scheme under Block- Raghunathganj-II Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000095/2023-2024 | 3784/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE (CHOA) | 11.29 | 8.97 | 20
4494 | Murshidabad Division | Jangipur Sub-Division | Renovation of Existing AIRP (Capacity 11 Cu.M) for changing of filter media of 1 No Polishing unit (2.17 M dia x 1.50 M HOS) & 1 No Primary Unit ( 2.17 M dia x 2.00 M HOS) and painting all vessel, pipes etc. all complete for Augumentation of Dakshin Sekhhalipur Pipe Water supply scheme, Block-Raghunathganj-II, under Murshidabad Division P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000807/2023-2024 | 616/MURD | 28/02/2024 | 30 | M/S BAPPA ENTERPRISE | 13.7 | 0 | 0
4495 | Murshidabad Division | Jangipur Sub-Division | Allied works for Renovation of Existing AIRP, Gobordanga Model (Capacity 11 Cu.M/hr) at Dakhin Sekhalipur W/S Scheme in connection with Augmentation of Dakhin Sekhalipur PWSS under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000833/2023-2024 | 783/MURD | 14/03/2024 | 20 | M/S BAPPA ENTERPRISE | 7.56 | 0 | 0
4496 | Murshidabad Division | Jangipur Sub-Division | Providing Functional Household Tap Connections (FHTC) with laying of Pipeline for last mile connectivity in village Dakshin Sekhalipur (314102) & Paschim Khandua(314103) Village in connection with Augumentation of Dakshin Sekhhalipur Pipe Water supply scheme, Block-Raghunathganj-II, under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000891/2022-2023 | 914/MURD | 30/03/2023 | 120 | PROSENJIT DAS | 72.6 | 38.7 | 85
4497 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.19 | 100
4498 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | RTOR000112/2023-2024 | 1167/MURD/5 | 28/04/2023 | 0 | Resource Division | 0.33 | 0 | 0
4499 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (Jal Jeevan Mission ) and under command area of village of Bhatsala ( Village Code -314688) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) |  |  | ORD/000056/2021-2022 | 1349/MURD | 09/06/2021 | 60 | MAMON ENTERPRISE AND CONSTRUCTION (MASIUR RAHAMAN MOLLA) | 77.6 | 82.67 | 0
4500 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village Juginda (Village code 314727)under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723344) |  |  | ORD/000224/2022-2023 | 1468/MURD | 03/06/2022 | 120 | SUJIT KUMAR SAHA | 130.65 | 78.95 | 0
4501 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. |  |  | ORD/000455/2021-2022 | 305/BSD | 13/08/2021 | 30 | IMAGIN COMMUNICATION | 4.33 | 8.67 | 0
4502 | Murshidabad Division |  | Protection of Over Head Reservoir by Masonry wall & construction of entrance gate of Head work site premises under Juginda Z-I Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. |  |  | ORD/002123/2021-2022 | 475/ISD | 03/09/2021 | 60 | BISWAS CONSTRUCTION PAN NO : AHNPB6929M | 3.64 | 3.64 | 0
4503 | Murshidabad Division |  | Protection of Head work site & Pump House No-II premises by raising Boundary wall height by R.B.T fencing under Juginda Z-I Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. |  |  | ORD/002130/2021-2022 | 474/ISD | 03/09/2021 | 60 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 4.7 | 4.69 | 0
4504 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (Jal Jeevan Mission ) and under command area of village of Bhatsala ( Village Code -314688) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) TNO- 165/21-22/EE |  |  | VCH/001499/2021-2022 | 413-MSD/21-22 | 22/03/2022 | 0 | MAMON ENTERPRISE AND CONSTRUCTION (MASIUR RAHAMAN MOLLA) | 27.35 | 0 | 0
4505 | Berhampore Division I | Berhampur Division I | Improvement of Existing AIRP (Modified Sujapur Sadipur Model, Capacity 30.00 cum/hr) including required allied works of DIGHA PWSS under Jal Jeevan Mission within Bhagwangola-I inconnection with Augmentation under Berhampore Division-I , P.H.E. Dte. In the districtof Murshidabad. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000048/2025-2026 | 755/BD-I | 22/05/2025 | 30 | DEBASISH SARKAR | 24.4 | 0 | 0
4506 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Digha ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000107/2022-2023 | 1364/BD-I | 21/12/2022 | 30 | SELIM SARKAR | 2.27 | 1.73 | 100
4507 | Berhampore Division I | Berhampur Division I | Formal work order for Augmentation of DIGHA Piped water supply scheme to accommodate contruction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000135/2022-2023 | 1822/BD-I | 31/03/2023 | 642 | SUJIT KUMAR SAHA | 255.85 | 0 | 10
4508 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DIGHA Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000878/2021-2022 | 262/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.43 | 2.43 | 0
4509 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000062/2023-2024 | 196/BD-I/9 | 09/02/2024 | 0 | Resource Division | 3.75 | 0 | 0
4510 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of DIGHA ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000030/2023-2024 | 3729/MEDB | 03/11/2023 | 92 | SURAKSHA | 11.18 | 0 | 0
4511 | Berhampore Division I | Berhampur Division I | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Paschim Rampur ground water supply scheme in Bhagwangola-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-90.00 Cum/Hr.) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000017/2025-2026 | 614/BD-I | 22/04/2025 | 300 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 207.69 | 0 | 0
4512 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Rampur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000032/2023-2024 | 124/BD-I | 12/05/2023 | 30 | HARUN ALL RASHID & BROTHERS | 17.74 | 0 | 50
4513 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PASCHIMRAMPUR PWSS (TW-III Site) within BHAGWANGOLA-I Block under JAL JEEVAN MISSION in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. (01 No TW) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000063/2025-2026 | 776/BD-I | 22/05/2025 | 15 | M/S GHOSH ENTERPRISE | 9 | 0 | 0
4514 | Berhampore Division I | Berhampur Division I | Formal Work order for Augmentation of PASCHIM RAMPUR Piped water supply scheme to accommodate construction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000160/2022-2023 | 1453/BD-I | 17/01/2023 | 365 | NILKAMAL BASAK | 398.64 | 0 | 0
4515 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for PASCHIM RAMPUR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000876/2021-2022 | 260/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.82 | 0 | 100
4516 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000087/2023-2024 | 196/BD-I/15 | 09/02/2024 | 0 | Resource Division | 41.52 | 0 | 0
4517 | Berhampore Mechanical | Berhampur Division I | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Paschim Rampur ground water supply scheme in Bhagwabgola-I Block Dist_Murshidabad under MEDB PHE Dte. " | Assistant Engineer-I | JE,Junior engineer-III | ORD/000010/2025-2026 | 1134/MEDB | 13/05/2025 | 92 | M/S SAJAHAN CHOWDHURY | 49.94 | 0 | 0
4518 | Berhampore Mechanical | Berhampur Division I | Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Executive Engineer under Office of the Executive Engineer, Mechanical/electrical Division, PHE Dte. in the district of Murshidabad. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000693/2022-2023 | 658/AE/MEDB | 31/03/2023 | 183 | M/S SAJAHAN CHOWDHURY | 0.9 | 2.27 | 10
4519 | Berhampore Mechanical | Berhampur Division I | Continuation Order Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Assistant Engineer-I under Office of the Executive Engineer, Mechanical/electrical Division, PHE Dte. in the district of Murshidabad. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000758/2022-2023 | 237/MEDB | 27/01/2023 | 59 | M/S SAJAHAN CHOWDHURY | 0.29 | 0.77 | 10
4520 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of PASCHIM RAMPUR ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000834/2023-2024 | 3775/MEDB | 03/11/2023 | 92 | MERCURY ENGINEERING CO | 22.4 | 0 | 8
4521 | Berhampore Division I | Berhampur Division I | Augmentation of Dakshin Sahar Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagawangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(PART-A) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000026/2023-2024 | 103/BD-I | 04/05/2023 | 1098 | RAJ KUMAR MONDAL | 352.91 | 0 | 10
4522 | Berhampore Division I | Berhampur Division I | Augmentation of Dakshin Sahar Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagawangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(Part-B) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000105/2023-2024 | 105/BD-I | 08/05/2023 | 909 | A ONE CONSTRUCTION | 303.14 | 0 | 50
4523 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Dakshin Sahar ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000115/2022-2023 | 1412/BD-I | 04/01/2023 | 10 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 3.61 | 2.46 | 100
4524 | Berhampore Division I | Berhampur Division I | Dakshin Sahar PWSS to accommodate construction of Pump House Cum Chlorine Room, Boundary Wall and Service Road, under Jal Jivan Mission of BHAGWANGOLA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000131/2024-2025 | 1528/BD-I | 19/09/2024 | 60 | GITA CONSTRUCTION | 32.4 | 0 | 0
4525 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DAKSHIN SAHAR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000173/2022-2023 | 1077/BD-I | 29/09/2022 | 10 | NATSOL CONSULTANT | 2.71 | 2.71 | 0
4526 | Berhampore Division I | Berhampur Division I | Repair And Renovation Works Of OHR (450 Cum) forDakshinSahar water supply scheme of Bhagwangola-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000257/2023-2024 | 1027/BD-I | 01/11/2023 | 30 | DEBJIT DAS | 7.5 | 0 | 0
4527 | Berhampore Division I | Berhampur Division I | DAKSHINSAHAR PART-A PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BHAGAWANGOLA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000458/2023-2024 | 462/BD-I | 15/03/2024 | 480 | RELIABLE ENTERPRISE | 21.99 | 0 | 100
4528 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | RTOR000051/2023-2024 | 196/BD-I/2 | 09/02/2024 | 0 | Resource Division | 41.96 | 0 | 0
4529 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of DAKSHIN SAHAR ground water based water supply scheme under Block- Bhagawangola-II, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000026/2023-2024 | 3728/MEDB | 03/11/2023 | 92 | JOY BISHNU ENGINEERING CO. | 12.42 | 0 | 0
4530 | Murshidabad Division | Berhampur M/E Division | Construction of 200 Cum OHR, Pump House at Head Work Site Laying Distribution System, Rising Main Connection, FHTC Connection, for Augmentation of Ramakantapur PWSS in Suti-I Block, under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000087/2025-2026 | 2374/MURD | 19/11/2025 | 365 | MOTI RAHAMAN | 278.11 | 0 | 0
4531 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0
4532 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (RAMAKANTAPUR PWSS Scheme,Block- SUTI-I to be Augmentation/Rejuvination under Murshidabad Division P.H.E.Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/002049/2021-2022 | 3253/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.1 | 7.1 | 1
4533 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-II | Junior engineer-III | RTOR000204/2023-2024 | 1210/MURD/03 | 02/05/2023 | 0 | Resource Division | 60.48 | 0 | 0
4534 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
4535 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Ramkantapur ground water based water supply scheme under Block_ Suti-I, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000033/2023-2024 | 1879/MEDB | 16/06/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 22.77 | 0 | 0
4536 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Augmentation of Saktipur Zone-I Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Beldanga-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000540/2022-2023 | 2860/MURD | 19/10/2022 | 895 | M/S. ROY TRADING CO. | 302.59 | 189.98 | 80
4537 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shaktipur Zone-I &II Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000598/2022-2023 | 3072/MURD | 17/11/2022 | 45 | NADIA TUBEWELLS | 21.18 | 10 | 1
4538 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS ( SAKTIPUR PWSS Scheme, Block - Beldanga-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000833/2021-2022 | 3266/MURD | 05/10/2021 | 60 | RADIANT | 10.43 | 3.28 | 0
4539 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000298/2023-2024 | 1278/MURD/3 | 10/05/2023 | 0 | Resource Division | 129.08 | 0 | 0
4540 | Berhampore Mechanical | Berhampur Sub-Division | Saktipur Zone-1 Ph-1 Application No-3004554369 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01195/2023-2024 | 254/WBSEDCL-JJM | 17/01/2024 | 0 | WBSEDCL | 2.98 | 0 | 0
4541 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I (H.W Site) at Zone-I and Pump House No.-I (H.W Site) at Zone-II of Saktipur ground water based water supply scheme under Block- Beldanga-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000164/2023-2024 | 2020/MEDB | 19/06/2023 | 92 | INDTECH ASSOCIATES | 23.14 | 18.99 | 8
4542 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Augmentation of CHANDPUR Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000521/2022-2023 | 2496/MURD | 30/08/2022 | 945 | BISWAS ENTERPRISE (PROP. JESMIN KHATUN) | 388.72 | 104.3 | 80
4543 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (CHANDPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000844/2021-2022 | 3277/MURD | 05/10/2021 | 60 | RADIANT | 14.82 | 5.15 | 1
4544 | Murshidabad Division | Berhampur Sub-Division | Repair and Renovation of Pump high lift pupm house at head works site of Chandpur water supply scheme under Berhampore Sub Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001676/2021-2022 | 13/BSD | 10/01/2022 | 30 | MASUM CONSTRUCTION | 3.55 | 2.89 | 0
4545 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000005/2024-2025 | 1811/MURD/04 | 20/06/2024 | 0 | Resource Division | 21.13 | 0 | 0
4546 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000303/2023-2024 | 1278/MURD/5 | 10/05/2023 | 0 | Resource Division | 11.58 | 0 | 0
4547 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000355/2023-2024 | 305/MURD/04 | 29/01/2024 | 0 | Resource Division | 10.27 | 0 | 0
4548 | Berhampore Mechanical | Berhampur Sub-Division | CHANDPUR Z-II PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01571/2023-2024 | 426/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 22.73 | 0 | 0
4549 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No._I ,II and III ,Zone-II under Chandpur ground water based water supply scheme under Block_ Nowda Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000027/2023-2024 | 1873/MEDB | 16/06/2023 | 92 | B. T. PROJECTS PVT. LTD. | 34.2 | 0 | 0
4550 | Murshidabad Division | Berhampur M/E Division | Construction of Boundwary Wall , Pump House T.W-III , PCC approach road , Land Development for Augmentation of Katlamari PWSS in Raninagar-II Block , Islampur Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000083/2025-2026 | 1460/MURD | 26/06/2025 | 90 | SANJITA CONSTRUCTION | 22.83 | 0 | 0
4551 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATLAMARI PWSS (ZONE- I ) Water Supply Scheme at Head Work Site, 2nd Site site at Raninagar-II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000113/2023-2024 | 1755/MURD | 06/07/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 18.44 | 17 | 100
4552 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution system (Part-B) and Providing Functional Household Tap Connection to 665 nos household & Construction of Boundary Wall and repairing of Pump House of Katlamari Zone -I of Islampur Sub-Division under Murshidabad Division,P.H.E Dte [(i)Amount for LDS & FHTC: Rs.14057282.00 & (ii) Amount for Construction of Boundary Wall and repairing of Pump House : Rs. 2963929.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000601/2022-2023 | 3150/MURD | 28/11/2022 | 60 | J.S. CONSTRUCTION | 170.18 | 148.74 | 50
4553 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution system (Part-C) and Providing Functional Household Tap Connection to 670 nos household & Construction of Pump House of Katlamari Zone-I of Islampur Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000606/2022-2023 | 3191/MURD | 01/12/2022 | 1038 | ULTRA CONSTRUCTION. | 110.88 | 64.28 | 92
4554 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution system(Part-A) , Rising Main, Providing Functional Household Tap Connection to 670 nos household & Repair and Renovation of OHR of 500 cum Capacity of Katlamari Zone -I Water Supply Scheme of Islampur Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000626/2022-2023 | 3278/MURD | 09/12/2022 | 60 | ARINDAM MAJUMDAR | 135.29 | 24 | 30
4555 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Katlamari PWSS Scheme, Block - Raninagar-II) to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000739/2021-2022 | 2745/MURD | 03/09/2021 | 60 | RADIANT | 11.14 | 5.57 | 1
4556 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000051/2022-2023 | 3052/D/MURD | 17/11/2022 | 0 | Resource Division | 27.08 | 0 | 0
4557 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT KATLAMARI Z1 PH3, ID APPLICATION NO.3004548905 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01221/2023-2024 | 285/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.38 | 0 | 0
4558 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-I of KATLAMARI ground water based water supply scheme under Block- RANINAGAR-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000891/2023-2024 | 4345/MEDB | 29/12/2023 | 91 | ARINDAM MAJUMDAR | 8.96 | 0 | 0
4559 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of MAHISAR & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362278S000 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000678/2022-2023 | 37/MURD | 04/01/2023 | 1062 | NAYLA CONSTRUCTION | 611.61 | 123.44 | 50
4560 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | RTOR000038/2023-2024 | 1043/MURD/13 | 17/04/2023 | 0 | Resource Division | 26.09 | 0 | 0
4561 | Berhampore Mechanical | Kandi Sub-Division | Electric Service Connection at MAHISAR PWSS PH I, Application NO.3004403589, ID 304119890 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | BILL/01084/2023-2024 | 195/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 10.21 | 0 | 0
4562 | Berhampore Mechanical | Kandi Sub-Division | Electric Service Connection at MAHISAR PWSS PH II, Application NO.3004403661, ID 304119931 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | BILL/01085/2023-2024 | 196/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 10.29 | 0 | 0
4563 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under MAHISAR ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000153/2023-2024 | 2083/MEDB | 19/06/2023 | 926 | JOGMAYA ENGINEERING | 23.47 | 17.97 | 50
4564 | Murshidabad Division | Berhampur M/E Division | Laying of different dia U.P.V.C Pipeline for Distribution Network (Remaining Portion) and construction of RCC Stand Post including platform at Sankuria Village under Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/001225/2021-2022 | 413/LSD | 27/12/2021 | 30 | SARAJIT KUMAR MAJUMDER | 4.88 | 0 | 0
4565 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under Amarkundu ground water based water supply scheme under Block_ Nabagram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000137/2023-2024 | 1922/MEDB | 16/06/2023 | 92 | MAA TARA ENTERPRISE | 21.12 | 0 | 0
4566 | Murshidabad Division | Kandi Sub-Division | Allied & Balance Work for Laying of Distribution System, Approach Service Road, Construction of Box Culvert and Land Development of SALINDA PWSS in Bharatpur-I Block, of Kandi Sub-Division under Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000180/2024-2025 | 3143/MURD | 03/12/2024 | 90 | DHIRENDRANATH MONDAL | 38.56 | 0 | 30
4567 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250 mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SALINDA PWSS at Head Work Site & 2nd Tube Well Site in Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000667/2022-2023 | 3406/MURD | 22/12/2022 | 45 | INDRAJIT MAZUMDAR | 16.8 | 0 | 100
4568 | Murshidabad Division | Kandi Sub-Division | Formal Work Order For Laying of Distribution System (Part-A) and Construction of Boundary wall of SALINDA PWSS of Kandi Sub-Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000699/2022-2023 | 161/MURD | 17/01/2023 | 952 | TANUSHREE ENTERPRISE | 145.06 | 97.7 | 35
4569 | Murshidabad Division | Kandi Sub-Division | Formal Work Order For Laying of Distribution System (Part-B) and Construction of Pump House for Augmentation of SALINDA PWSS of Kandi Sub-Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000701/2022-2023 | 160/MURD | 16/01/2023 | 747 | SOM CONSTRUCTION AGENCY | 146.49 | 76.86 | 39
4570 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of 350 Cum OHR,Laying Distribution System (PART-C),Rising Main Connection, FHTC , for Uncovered of SALINDA PWSS in Bharatpur-II Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000729/2022-2023 | 340/MURD | 08/02/2023 | 1003 | DHIRENDRANATH MONDAL | 387.6 | 171.78 | 25
4571 | Murshidabad Division | Kandi Sub-Division | Additional & Balance Work Laying of Distribution System , Land Devolapement of SALINDA PWSS in Bharatpur-II Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000733/2023-2024 | 54/MURD | 05/01/2024 | 30 | DHIRENDRANATH MONDAL | 17.25 | 0 | 80
4572 | Murshidabad Division | Kandi Sub-Division | Construction of Pump House Cum Chlorine Room, Boundary Wall, Approach Road & Land Development of Salinda PWSS in Bhratpur-II Block , KANDI Sub-Division under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000848/2023-2024 | 823/MURD | 15/03/2024 | 60 | M/S RELIABLE | 27.67 | 0 | 0
4573 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | RTOR000017/2023-2024 | 1210/MURD/41 | 02/05/2023 | 0 | Resource Division | 46.94 | 0 | 0
4574 | Berhampore Mechanical | Kandi Sub-Division | New connection charge for Salinda PWSS, P/H No.-II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/00856/2023-2024 | 120/WBSEDCL-JJM | 27/09/2023 | 0 | WBSEDCL | 4.94 | 0 | 0
4575 | Berhampore Mechanical | Kandi Sub-Division | Salinda PH-1 Application no- 3004547659 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | BILL/01188/2023-2024 | 248/WBSEDCL-JJM | 16/01/2024 | 0 | WBSEDCL | 3.52 | 0 | 0
4576 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SALINDA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000036/2023-2024 | 1880/MEDB | 16/06/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 24.14 | 19.48 | 11
4577 | Murshidabad Division | Berhampur Sub-Division |  | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/00243/2023-2024 | 97-MSD/2023-24 | 08/06/2023 | 0 | DULAL CHOWDHURY | 0.8 | 0 | 0
4578 | Murshidabad Division | Berhampur Sub-Division | ENGAGEMENT OF CAR FOR SE-MC, PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/01173/2024-2025 | 342-MSD/2024-25 | 06/09/2024 | 0 | SOUMYADIP MISRA | 0.21 | 0 | 0
4579 | Murshidabad Division | Berhampur Sub-Division | Continuation Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2023 to 17.04.2024.[Vehicle No-WB57E7960] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000093/2023-2024 | 437-/AA/JSD | 17/04/2023 | 365 | MAJIBUR RAHAMAN | 4.76 | 2.79 | 70
4580 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000135/2023-2024 | 165/ISD | 01/04/2023 | 183 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 2.37 | 100
4581 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte. for 06 (Six) Months i.e. from 08.07.2023 to 07.01.2024. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000148/2023-2024 | 24/LSD | 30/06/2023 | 184 | BARI ENTERPRISE | 0.9 | 2.24 | 100
4582 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chhota Satui (Village code 315343) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID- 1723177 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000168/2021-2022 | 1651/MURD | 29/06/2021 | 180 | DAS TRADING CO. | 80.05 | 104.67 | 1
4583 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bara Satui (Village code 315341) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723177 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000186/2020-2021 | 3136/MURD | 11/12/2020 | 60 | UTTAM MUKHERJEE | 39.68 | 2.19 | 1
4584 | Murshidabad Division | Berhampur Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000456/2021-2022 | 306/BSD | 13/08/2021 | 30 | IMAGIN | 3.26 | 6.51 | 0
4585 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at CHOWRIGACHHA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000522/2021-2022 | 353/BSD | 27/08/2021 | 30 | TINA ROY | 4.16 | 4.16 | 1
4586 | Murshidabad Division | Berhampur Sub-Division | Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2022 to 17.04.2023.[Vehicle No-WB57E7960] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000623/2022-2023 | 205/JSD | 18/04/2022 | 365 | MAJIBUR RAHAMAN | 4.76 | 1.6 | 0
4587 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01(One) Year] (period for i.e 07/02/2023 to 06/02/2024). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000897/2022-2023 | 329/MURD | 07/02/2023 | 365 | MD MUKLESUR RAHAMAN | 4.78 | 2.45 | 1
4588 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Daily hire basis for official use for the Office of the Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01 (One) Year].for the month of April¿2023 to March¿2024 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000900/2022-2023 | 330/MURD | 07/02/2023 | 365 | SOUMYADIP MISRA | 4.78 | 3.6 | 32
4589 | Murshidabad Division | Berhampur Sub-Division | Continuation work for Hiring of 1 (one) no. Diesel Bolero/Marshal car (WB-57C 9120) for official use of the Assistant Engineer, Jangipur Sub Division, Murshidabad Division P.H.E. Dte. for the period from 01.03.2022 to 31.05.2022 (i.e) 3 (Three) months (vehicle No.-WB-57C/9120). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001722/2021-2022 | 88/JSD | 22/02/2022 | 89 | MANUAR HOSSAIN | 0.45 | 0.23 | 100
4590 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) at village of FATEPUR West side ( Village Code _315310) of Fatepur Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001777/2021-2022 | 106/BSD | 28/03/2022 | 30 | CHOWDHURY CONSTRUCTION | 4.79 | 0 | 90
4591 | Murshidabad Division | Berhampur Sub-Division | Extension of Distribution UPVC pipeline at Hanumandanga, Poradanga & Haldepara area for Providing Balance Functional Household Tap connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command areas of village of Choto Satui (Village Code-315343) under Bara Satui Ground water based water suply scheme for Arsenic affected areas of Berhampore Block, under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001807/2021-2022 | 768/MURD | 22/03/2022 | 30 | DAS TRADING CO. | 42.34 | 27.11 | 1
4592 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) at village of FATEPUR West side ( Village Code _315310) of Fatepur Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/002071/2021-2022 | 106/BSD | 28/03/2022 | 30 | CHOWDHURY CONSTRUCTION | 4.79 | 0.75 | 0
4593 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bara Satui (Village code 315341) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723177 in the District of Murshidabad.3136/MURD, 11/12/2020 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000674/2021-2022 | 172-MSD/21-22 | 01/11/2021 | 0 | UTTAM MUKHERJEE | 32.45 | 0 | 0
4594 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Faridpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000041/2023-2024 | 44/BD-I | 24/04/2023 | 30 | SUJIT KUMAR SAHA | 8.99 | 0 | 0
4595 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Foridpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000114/2022-2023 | 1411/BD-I | 04/01/2023 | 10 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 2.23 | 1.41 | 100
4596 | Berhampore Division I | Berhampur Division I | Formal work order for Augmentation of FARIDPUR Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall,service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000140/2022-2023 | 1450/BD-I | 17/01/2023 | 1045 | BIJOY CHOWDHURY | 435.9 | 224.38 | 70
4597 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for FARIDPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000886/2021-2022 | 269/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.7 | 2.7 | 1
4598 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | RTOR000049/2023-2024 | 196/BD-I/16 | 09/02/2024 | 0 | Resource Division | 38.7 | 0 | 0
4599 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Faridpur ground water based water supply scheme under Block- Bhagawangola-II, Dist. Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000058/2023-2024 | 4333/MEDB | 29/12/2023 | 91 | ASSOCIATED ELECTRICAL CO. | 11.41 | 9.48 | 20
4600 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of MAHAMMADPUR & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000710/2022-2023 | 143/MURD | 17/01/2023 | 835 | SUJIT KUMAR SAHA | 315.18 | 103.48 | 70
4601 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | RTOR000023/2023-2024 | 1067/MURD/6 | 18/04/2023 | 0 | Resource Division | 24.66 | 0 | 0
4602 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | RTOR000336/2023-2024 | 79/MURD/03 | 09/01/2024 | 0 | Resource Division | 8.45 | 0 | 0
4603 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | RTOR000350/2023-2024 | 112/MURD/07 | 11/01/2024 | 0 | Resource Division | 8.45 | 0 | 0
4604 | Berhampore Mechanical | Kandi Sub-Division | new service connection at MAHAMMADPUR PH2 ID304222150 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | BILL/01146/2023-2024 | 228/WBSEDCL-JJM | 09/01/2024 | 0 | WBSEDCL | 4.75 | 0 | 0
4605 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT MAHHAMMADPUR PH1 ID304222178 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | BILL/01147/2023-2024 | 229/WBSEDCL-JJM | 09/01/2024 | 0 | WBSEDCL | 2.7 | 0 | 0
4606 | Berhampore Mechanical | Kandi Sub-Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MAHAMMADPUR ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000158/2023-2024 | 2016/MEDB | 19/06/2023 | 92 | A.G. ENTERPRISE | 20.38 | 0 | 0
4607 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 13.14 | 11
4608 | Central Drilling | Berhampur Division I | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
4609 | Berhampore Division I | Berhampur Division I | Construction of Boundary Wall with Main Entrance gate and barbed wire facing at Augmentation of BALI ZONE-I PWSS of Nawda Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000057/2024-2025 | 1129/BD-I | 11/07/2024 | 45 | KHANDAKAR CONSTRUCTION | 18.69 | 0 | 0
4610 | Berhampore Division I | Berhampur Division I | Augmentation of Bali Zone-I Piped water supply scheme to accomodate construction of service road,repairing of Existing OHR, laying of Distribution pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000113/2023-2024 | 507/BD-I | 24/07/2023 | 180 | N.H ENTERPRISE | 56.14 | 35.79 | 50
4611 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BALI ZONE-I Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000237/2022-2023 | 1595/BD-I | 28/02/2023 | 10 | TECHVISION | 2.46 | 2.46 | 0
4612 | Berhampore Division I | Berhampur Division I | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Bali Zone-I ground water supply scheme in Nawda Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000366/2024-2025 | 322/BD-I | 24/02/2025 | 300 | M/S SAJAHAN CHOWDHURY | 122.62 | 0 | 0
4613 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000058/2023-2024 | 94/BD1 | 22/01/2024 | 0 | Resource Division | 3.29 | 0 | 0
4614 | Berhampore Mechanical | Berhampur Division I | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Bali Zone-I ground water supply scheme in Nawda Block, Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000016/2025-2026 | 1151/MEDB | 14/05/2025 | 92 | M/S SAJAHAN CHOWDHURY | 39.62 | 0 | 0
4615 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
4616 | Berhampore Division I | Berhampur Division I | Construction of Boundary wall at 2nd Tube Well Site of KASHIPUR ZONE - II PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000038/2025-2026 | 667/BD-I | 29/04/2025 | 45 | DEBEN RAJAK | 10.18 | 0 | 100
4617 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of KASHIPUR ZONE-II" ground water supply scheme in BELDANGA-II Block, under Berhampore Division-I, P.H.E Dte(Capacity-48.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Up flow Polishing | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000039/2024-2025 | 1038/BD-I | 28/06/2024 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 156.07 | 0 | 60
4618 | Berhampore Division I | Berhampur Division I | KASHIPUR ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000051/2024-2025 | 1117/BD-I | 11/07/2024 | 180 | HI-TECH ENGINEERS CO-OPERATIVE & CONSTRUCTION SOCIETY LTD. | 20.67 | 0 | 100
4619 | Berhampore Division I | Berhampur Division I | Allied Work for Road Restoration, Laying of Balance portion of UPVC and Rising Mains at Kashipur Zone-II PWSS under Jal Jeevan Mission within Beldanga-II block under Berhampore Division-I, P.H.E. Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000064/2025-2026 | 777/BD-I | 22/05/2025 | 90 | MARUTI CONSTRUCTION & CO. | 64.87 | 0 | 0
4620 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASHIPUR ZONE-II Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000232/2022-2023 | 1590/BD-I | 28/02/2023 | 10 | TECHVISION | 2.6 | 2.6 | 0
4621 | Berhampore Division I | Berhampur Division I | Augmentation of Kashipur zone_II Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000242/2022-2023 | 1599/BD-I | 28/02/2023 | 900 | MARUTI CONSTRUCTION & CO. | 150.14 | 103.96 | 95
4622 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | RTOR000091/2023-2024 | 196/BD-I/25 | 09/02/2024 | 0 | Resource Division | 48.51 | 0 | 0
4623 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 20
4624 | Berhampore Division I | Berhampur M/E Division | Augmentation of Sitesnagar Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000222/2022-2023 | 1542/BD-I | 17/02/2023 | 988 | M/S JOGMAYA ENTERPRISE | 87.18 | 0 | 30
4625 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SITESNAGAR Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000259/2022-2023 | 1682/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.53 | 2.53 | 1
4626 | Berhampore Division I | Berhampur M/E Division | Balance and allied Work Laying Rising Main with DI (K-9) and distribution system with UPVC pipe including supply of necessary special for augmentation work of Siteshnagar Water Supply Scheme , under Jal Jevan Mission under Berhampore Division -I , PHE.Dte. of LALGOLA Block of Murshidabad District. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000281/2024-2025 | 09/BD-I | 06/01/2025 | 179 | M/S. JOGMAYA ENTERPRISE | 23.22 | 0 | 30
4627 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000016/2024-2025 | 1510/BD-I/10 | 12/09/2024 | 0 | Resource Division | 2.19 | 0 | 0
4628 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000077/2023-2024 | 201/BD-1/18 | 10/02/2024 | 0 | Resource Division | 16.95 | 0 | 0
4629 | Murshidabad Division | Berhampur M/E Division | Augmentation of KISHOREPUR(PART-A) Pipe water supply scheme, to accommodate FHTC under Jal Jeevan Mission under Jangipur Sub Division Block- SUTI-II, of Murshidabad Division,District-Murshidabad PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000016/2023-2024 | 980/MURD | 10/04/2023 | 1032 | A ONE CONSTRUCTION | 203.06 | 51.89 | 50
4630 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000357/2023-2024 | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 2.46 | 100
4631 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000261/2023-2024 | 1230/MURD/07 | 04/05/2023 | 0 | Resource Division | 25.86 | 0 | 0
4632 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I & II under KISHOREPUR ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000114/2023-2024 | 1903/MEDB | 16/06/2023 | 930 | DAS CONSTRUCTION | 21.27 | 0 | 10
4633 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JITPUR (ZONE I) Water Supply Scheme at Head Work Site, 2nd Site site at DOMKAL Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000106/2023-2024 | 1748/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 100
4634 | Murshidabad Division | Berhampur M/E Division | Formal work order for the Work of Augmentation of JITPUR ZONE-I & its adjoining mouzas Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000702/2022-2023 | 124/MURD | 16/01/2023 | 180 | M/S. S. DAS AND ENTERPRISE | 488.01 | 184.14 | 15
4635 | Murshidabad Division | Berhampur M/E Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 2.62 | 80
4636 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 12.3 | 1
4637 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000186/2023-2024 | 1210/MURD/10 | 02/05/2023 | 0 | Resource Division | 2.76 | 0 | 0
4638 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000391/2023-2024 | 526/MURD/01 | 19/02/2024 | 0 | Resource Division | 9.83 | 0 | 0
4639 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under JITPUR ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000053/2023-2024 | 3760/MEDB | 03/11/2023 | 92 | JAGANNATH ENTERPRISE | 23.28 | 0 | 0
4640 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II,III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JITPUR (ZONE II) Water Supply Scheme at Head Work Site, 2nd & 3rd Site site at DOMKAL Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000105/2023-2024 | 1747/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 31.12 | 100
4641 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of JITPUR (Zone-II) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000796/2022-2023 | 603/MURD | 02/03/2023 | 1036 | M/S.TAPAS KUMAR CHAKRABORTY | 752.45 | 520.72 | 40
4642 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000182/2023-2024 | 1180/MURD/20 | 30/04/2023 | 0 | Resource Division | 30.1 | 0 | 0
4643 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000392/2023-2024 | 526/MURD/02 | 19/02/2024 | 0 | Resource Division | 6.83 | 0 | 0
4644 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT JITPUR Z-II PH-III | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01102/2024-2025 |  | 13/11/2024 | 0 | WBSEDCL | 6.3 | 0 | 0
4645 | Berhampore Mechanical | Berhampur M/E Division | Jitpur Zone-2 PH-2 Application No-3004547163 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01226/2023-2024 | 278/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 4.89 | 0 | 0
4646 | Berhampore Mechanical | Berhampur M/E Division | Jitpur Zone-2 PH-1 Application No- 3004547411 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01228/2023-2024 | 279/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 10.38 | 0 | 0
4647 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , ZONE-II under JITPUR ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000054/2023-2024 | 03/MEDB | 02/01/2024 | 91 | M/S K.P. PRAMANIK | 15.77 | 0 | 20
4648 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System, Rising Main, FHTC, Repairing of Boundary Wall, Pump House & Existing OHR for Augmentation of Bhalkundi Zone-I Water at Supply Scheme in Khargram Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000022/2023-2024 | 994/MURD | 11/04/2023 | 720 | SUJIT KUMAR SAHA | 222.84 | 125.21 | 30
4649 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
4650 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 5.33 | 76
4651 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000031/2023-2024 | 1043/MURD/1 | 17/04/2023 | 0 | Resource Division | 2.38 | 0 | 0
4652 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000062/2022-2023 | 1004/MURD/9 | 11/04/2023 | 0 | Resource Division | 2.38 | 0 | 0
4653 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under BHALKUNDI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000676/2023-2024 | 4299/MEDB | 29/12/2023 | 91 | A.K. SIKDAR | 24.12 | 0 | 0
4654 | Berhampore Division I | Berhampur M/E Division | Balance i.c.w Improvement of Existing AIRP (Modified Sujapur Sadipur Model) capacity 130.00 cum/hr at Head Work Site of Maia Zone-I Water Supply Scheme under JJM within Lalgola under Berhampore Division -I, P.H.E. Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000065/2025-2026 | 778/BD-I | 22/05/2025 | 30 | M/S J.S ENTERPRISE | 30.11 | 0 | 0
4655 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Maia ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000124/2022-2023 | 1676/BD-I | 14/03/2023 | 30 | RAJIB SAHA | 3.62 | 0 | 80
4656 | Berhampore Division I | Berhampur M/E Division | Augmentation of Maia Zone-I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000124/2023-2024 | 511/BD-I | 25/07/2023 | 900 | SOM CONSTRUCTION AGENCY | 208.44 | 0 | 20
4657 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MAIA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000265/2022-2023 | 1688/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.87 | 2.69 | 1
4658 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000015/2024-2025 | 1510/BD-I/9 | 12/09/2024 | 0 | Resource Division | 6.73 | 0 | 0
4659 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000079/2023-2024 | 201/BD-1/20 | 10/02/2024 | 0 | Resource Division | 34.89 | 0 | 0
4660 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under MAIA ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000070/2023-2024 | 4337/MEDB | 29/12/2023 | 183 | SUNIL RABIDAS | 23.45 | 15.05 | 10
4661 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room at Head Work Site of BANSGARA ZONE - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000016/2025-2026 | 613/BD-I | 22/04/2025 | 45 | BIJOY SINGHA | 8.81 | 0 | 0
4662 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd TW Site of BANSGARA ZONE - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000020/2025-2026 | 626/BD-I | 24/04/2025 | 60 | SUSHANTA MANDAL | 18.91 | 0 | 0
4663 | Berhampore Division I | Berhampur M/E Division | Augmentation of Bansgara Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000138/2023-2024 | 621/BD-I | 03/08/2023 | 310 | BURIMA CONSTRUCTION | 367.54 | 0 | 0
4664 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BANSGARA-II PWSS(TW-I&II) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000377/2024-2025 | 432/BD-I | 19/03/2025 | 30 | SARKAR WATER SUPPLY AGENCY | 18 | 0 | 0
4665 | Berhampore Division I | Berhampur M/E Division | BANSGARA ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000450/2023-2024 | 453/BD-I | 15/03/2024 | 60 | KAUSHIK MAJUMDAR | 21.78 | 0 | 0
4666 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000083/2023-2024 | 201/BD-1/24 | 10/02/2024 | 0 | Resource Division | 13.68 | 0 | 0
4667 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000537/2024-2025 | 323/MEDB | 10/02/2025 | 89 | ARINDAM MAJUMDAR | 24.68 | 0 | 0
4668 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
4669 | Berhampore Division I | Berhampur Division I | Construction of Boundary wall at 2nd & 3rd Tube Well Site of ANDULBERIYA ZONE -I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000013/2025-2026 | 600/BD-I | 22/04/2025 | 60 | AICH CONSTRUCTION | 20.36 | 0 | 0
4670 | Berhampore Division I | Berhampur Division I | Allied works of Laying of distribution pipeline of ANDULBERIA ZONE-I piped water supply scheme under JJM within Beldanga-II Block in the district of Murshidabad under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000127/2024-2025 | 1477/BD-I | 06/09/2024 | 60 | SUSHANTA MANDAL | 45.66 | 0 | 0
4671 | Berhampore Division I | Berhampur Division I | Augmentation of Andulberia Zone_I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000255/2022-2023 | 1661/BD-I | 13/03/2023 | 720 | M/S BIMALENDU BOSE | 433.78 | 279.43 | 100
4672 | Berhampore Division I | Berhampur Division I | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for ANDULBERIA Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000296/2022-2023 | 1648/BD-I | 10/03/2023 | 10 | TECHVISION | 2.81 | 2.8 | 100
4673 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | RTOR000089/2023-2024 | 196/BD-I/23 | 09/02/2024 | 0 | Resource Division | 64.29 | 0 | 0
4674 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of EKPAHARIA (Part-A) & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000718/2022-2023 | 104/MURD | 13/01/2023 | 365 | DOBAY CONSTRUCTION | 422.08 | 60.37 | 18
4675 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of EKPAHARIA( Part-B) & adjoining moujas PWSS to accommodate Construction Tube Well, Pump House Cum Chlorine Room & Blower room and Laying Distribution System under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000719/2022-2023 | 105/MURD | 13/01/2023 | 180 | MOTI RAHAMAN | 203.57 | 137.51 | 45
4676 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000050/2023-2024 | 1067/MURD/5 | 18/04/2023 | 0 | Resource Division | 25.69 | 0 | 0
4677 | Berhampore Mechanical | Kandi Sub-Division | ADDITIONAL QUOTATION AGAINST PHE EKPAHARIA WS SCHEME PH 1 ID 860313275 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01114/2024-2025 |  | 25/11/2024 | 0 | WBSEDCL | 0.82 | 0 | 0
4678 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS PH 2 EKPAHARIA ID 304247011 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01422/2023-2024 | 319/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 6.8 | 0 | 0
4679 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS PH1 EKPAHARIA ID 304248191 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01424/2023-2024 | 320/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 5.56 | 0 | 0
4680 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under EKPAHARIA ground water based water supply scheme under Block_ Burwan, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000709/2023-2024 | 4062/MEDB | 04/12/2023 | 91 | PADMA ENGINEERING CO | 24.19 | 0 | 30
4681 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System Part-A, Rising Main, Construction of 200 Cum OHR, Boundwary Wall, Pump House, for Kapasdanga water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. PART_A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000020/2023-2024 | 993/MURD | 11/04/2023 | 996 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 189.09 | 77.45 | 70
4682 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System PART-B, FHTC for Kapasdanga water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. PART_B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000023/2023-2024 | 996/MURD | 11/04/2023 | 910 | EVAN CONSTRUCTION PRIVATE LIMITED | 191.81 | 58.28 | 35
4683 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kapasdanga & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at B u r w a n Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000045/2023-2024 | 1103/MURD | 24/04/2023 | 30 | MAMATA USHA ENTERPRISE | 21.38 | 11.06 | 65
4684 | Murshidabad Division | Kandi Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Satitara T.W- IV,V,VI, Fatepur T.W.-II, Kapasdanga T.W-II Water Supply Scheme of Burwan Block under Kandi Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000500/2024-2025 | 664/MURD | 19/03/2025 | 65 | NADIA TUBEWELLS | 70.43 | 0 | 0
4685 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000070/2022-2023 | 1936/MURD/5 | 18/07/2023 | 0 | Resource Division | 17.68 | 0 | 0
4686 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PH1 KAPASDANGA ID 304239449 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01410/2023-2024 | 307/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
4687 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under KAPASDANGA ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000163/2023-2024 | 2088/MEDB | 19/06/2023 | 793 | M/S S. S. ENTERPRISE (DOMKAL) | 21.56 | 0 | 40
4688 | Central Drilling | Raghunathganj Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 12.55 | 20
4689 | Berhampore Division I | Raghunathganj Sub-Division | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Lochanpur Zone-II ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000002/2025-2026 | 508/BD-I | 03/04/2025 | 300 | NATIONAL CONSTRUCTION | 122.74 | 0 | 0
4690 | Berhampore Division I | Raghunathganj Sub-Division | Construction Service Road for approach and Pump House at Augmentation of LOCHANPUR ZONE-II PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000066/2025-2026 | 786/BD-I | 26/05/2025 | 60 | BHOLEBABA CONSTRUCTION CO | 7.34 | 0 | 0
4691 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Lochanpur Zone-II Piped water supply scheme to accommodate construction of OHR, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000154/2023-2024 | 679/BD-I | 10/08/2023 | 964 | APU CONSTRUCTION | 273.83 | 113.88 | 5
4692 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for LOCHANPUR ZONE-II Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000273/2022-2023 | 1757/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.6 | 2.6 | 100
4693 | Berhampore Division I | Raghunathganj Sub-Division | Repair And Renovation Works Of OHR (250 Cum) of Ground Water Based Supply Scheme for Lochanpur Zone-II of Raninagar-I block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000291/2023-2024 | 1038/BD-I | 03/11/2023 | 30 | BHOLE BABA CONSTRUCTION CO. | 8.02 | 0 | 100
4694 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000036/2023-2024 | 61/BD-1/23 | 27/04/2023 | 0 | Resource Division | 24.65 | 0 | 0
4695 | Berhampore Mechanical | Raghunathganj Sub-Division | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Lochanpur Zone-II ground water supply scheme in Raninagar-I Block Dist_Murshidabad under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000008/2025-2026 | 1132/MEDB | 13/05/2025 | 92 | CHOWDHURY & BASU ENTERPRISE | 39.61 | 0 | 0
4696 | Murshidabad Division | Berhampur M/E Division | Augmentation Work of Jagtai Piped Water Supply Scheme to accommodate with FHTC (1730 Nos), Laying of Rising Main , Laying of Distribution System , construction of 200 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000314/2023-2024 | 2670/MURD | 24/08/2023 | 730 | GREENLEAF CONSTRUCTION | 336.47 | 17.72 | 40
4697 | Murshidabad Division | Berhampur M/E Division | Repair of Pump Houses , Construction of toilet , Reinforced Barbed Tape (R.B.T) Concertina fencing on Boundary wall top & approach road for JAGTAI Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte.in the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000637/2022-2023 | 3167/MURD | 30/11/2022 | 30 | M/S JOY MA BANAMALI | 7.11 | 7 | 0
4698 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 7.22 | 100
4699 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000041/2024-2025 | MURD/2991 | 13/11/2024 | 0 | Resource Division | 25.25 | 0 | 0
4700 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000224/2023-2024 | 1219/MURD/29 | 03/05/2023 | 0 | Resource Division | 18.03 | 0 | 0
4701 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
4702 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for BASUDEBPUR Zone ¿I Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000021/2025-2026 | 986/MURD | 02/05/2025 | 60 | J.S. CONSTRUCTION | 23.01 | 0 | 0
4703 | Murshidabad Division | Berhampur M/E Division | Balance work of Laying of UPVC Pipe , Construction of approach road , Modification of R.C.C. Elevated Reservoir and Pump House, Boundary wall, for Augmentation of Basudevpur (Zone-I) Water Supply Scheme in Suti-I Block of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000242/2024-2025 | 191/MURD | 21/01/2025 | 223 | MOLLA ENTERPRISE | 40.58 | 0 | 35
4704 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Basudevpur Halt Station to Dhulianganga Station (TP NO 235/2 & 235/3) at Basudevpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Basudevpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000426/2021-2022 | 2483/MURD | 16/08/2021 | 60 | SANJAY BISWAS | 22.75 | 14.61 | 100
4705 | Murshidabad Division | Berhampur M/E Division | Providing FHTC Connection to 650 nos household , Repairing & Vertical Extention of Boundary Wall ,Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement & Pump House repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity of staging height 20 mtr. (Shaft wall ) for Augmentation work of Basudebpur (Zone-I) PWSS in Samsherganj Block under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000787/2022-2023 | 541/MURD | 24/02/2023 | 750 | MOLLA ENTERPRISE | 49.98 | 14.23 | 25
4706 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System for Augmentation work of Basudebpur(Zone-I) PWSS in Samsherganj Block under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000893/2022-2023 | 902/MURD | 29/03/2023 | 720 | JAI BHARAT COMMERCIAL CORPORATION | 112.15 | 41.15 | 40
4707 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 7.36 | 100
4708 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000143/2023-2024 | 1167/MURD/47 | 28/04/2023 | 0 | Resource Division | 11.06 | 0 | 0
4709 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000187/2023-2024 | 1210/MURD/23 | 02/05/2023 | 0 | Resource Division | 4.02 | 0 | 0
4710 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
4711 | Murshidabad Division | Berhampur M/E Division | SUBMISSION OF ONE NO REPAIRING ESTIMATE OF ROAD WHICH IS DAMAGED DURING PHE PIPE LINE LAYING IE. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00655/2024-2025 | 282-MSD/2024-25 | 13/08/2024 | 0 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 20.84 | 0 | 0
4712 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Narsinghpur Zone-II PWS accommodate FHTC, Laying Distribution System, Laying Rising Main in Jalangi Block within Murshidabad District under Murshidabad Division, PHE Dte. PART_A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000276/2023-2024 | 2617/MURD | 22/08/2023 | 793 | RAJKUMAR MONDAL | 202.06 | 89.34 | 55
4713 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 5.23 | 1
4714 | Murshidabad Division | Berhampur M/E Division | Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Boundary wall for Augmentation of NARASINGHAPUR Zone-II PWSS in Jalangi Block , Islampur Sub-Division under Murshidabad Division ,PHE.Dte.PART_B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000594/2023-2024 | 3333/MURD | 23/10/2023 | 555 | GOUTAM MANDAL | 142.16 | 54.71 | 40
4715 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000241/2023-2024 | 1219/MURD/23 | 03/05/2023 | 0 | Resource Division | 16.53 | 0 | 0
4716 | Berhampore Mechanical | Berhampur M/E Division | NEW SERVICE CONNECTION AT NARASINGHAPUR PWSS Z2 JL NO14 PLOT NO 970,1030,974 ID 304238697 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01271/2023-2024 | 294/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
4717 | Berhampore Mechanical | Berhampur M/E Division | AT NARASINGHAPUR PWSS Z2 PH 1 ID 304238696 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01481/2023-2024 | 448/WBSEDCL-JJM | 15/03/2024 | 0 | WBSEDCL | 9.32 | 0 | 0
4718 | Berhampore Mechanical | Berhampur M/E Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under Narsinghpur ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001508/2023-2024 | 584/MEDB | 31/01/2024 | 517 | QUAZI NOZRUL ISLAM (PARTNERSHIP) | 20.81 | 0 | 70
4719 | Murshidabad Division | Berhampur M/E Division | Augmentation of JURANPUR (PART-A) PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Sub Division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000082/2023-2024 | 1384/MURD | 22/05/2023 | 955 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 456.53 | 132.23 | 20
4720 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Juranpur ( PART-A) Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000127/2023-2024 | 1764/MURD | 06/07/2023 | 1045 | NADIA TUBEWELLS | 35.34 | 0 | 90
4721 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 1.15 | 1
4722 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000158/2023-2024 | 1180/MURD/07 | 29/04/2023 | 0 | Resource Division | 134.73 | 0 | 0
4723 | Berhampore Mechanical | Berhampur M/E Division | Juranpur PH No-IV | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01444/2023-2024 | 340/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 8.13 | 0 | 0
4724 | Berhampore Mechanical | Berhampur M/E Division | Juranpur PH No-V | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01445/2023-2024 | 341/WBSEDCL-JJM | 12/02/2024 | 0 | WBSEDCL | 4.44 | 0 | 0
4725 | Murshidabad Division | Islampur Sub-Division | Formal work order for Augmentation of P T Rasulpur (Part - B) Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000800/2022-2023 | 608/MURD | 02/03/2023 | 975 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 363.24 | 137.82 | 20
4726 | Murshidabad Division | Islampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000394/2023-2024 | 526/MURD/04 | 19/02/2024 | 0 | Resource Division | 3.66 | 0 | 0
4727 | Murshidabad Division | Islampur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shibnagar Laskarpur (Zone - I ) Part - A Water Supply Scheme at Head Work Site, 2nd Site site at Domkal Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000120/2023-2024 | 1761/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 23.58 | 9.68 | 50
4728 | Murshidabad Division | Islampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sultanpur (Village code 314726) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723328 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000242/2020-2021 | 85/MURD | 08/01/2021 | 60 | DECON INDIA | 33.63 | 5.8 | 1
4729 | Murshidabad Division | Islampur Sub-Division | Formal work order for Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part- A under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000808/2022-2023 | 622/MURD | 03/03/2023 | 180 | M/S. S. DAS AND ENTERPRISE | 508 | 351.34 | 20
4730 | Murshidabad Division | Islampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 10.28 | 1
4731 | Murshidabad Division | Islampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000207/2023-2024 | 1210/MURD/11 | 02/05/2023 | 0 | Resource Division | 147.5 | 0 | 0
4732 | Central Drilling | Berhampur Division I | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 12.75 | 20
4733 | Berhampore Division I | Berhampur Division I | Construction Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of PURBA KASHIPUR PWSS under Jal Jeevan Mission within Bhagwangola-I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000019/2025-2026 | 625/BD-I | 24/04/2025 | 60 | SHIV SHAKTI CONSTRUCTION | 18.82 | 0 | 80
4734 | Berhampore Division I | Berhampur Division I | Balance work of distribution pipe line under Jal Jeevan Mission for Purba Kashipur Piped Water Supply scheme under Berhampore Division - I , P.H.Engg Dte. In the district of Murshidabad. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000069/2024-2025 | 1207/BD-I | 26/07/2024 | 60 | MARUTI CONSTRUCTION & CO. | 42.9 | 0 | 85
4735 | Berhampore Division I | Berhampur Division I | PURBA KASIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000088/2023-2024 | 210/BD-I | 17/05/2023 | 905 | MARUTI CONSTRUCTION & CO. | 53.43 | 0 | 70
4736 | Berhampore Division I | Berhampur Division I | PURBA KASHIPUR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART - A) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000116/2023-2024 | 407/BD-I | 06/07/2023 | 1000 | SANKAR KUMAR BISWAS | 290.34 | 71.7 | 40
4737 | Berhampore Division I | Berhampur Division I | PURBA KASHIPUR PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000292/2022-2023 | 1823/BD-I | 31/03/2023 | 180 | MARUTI CONSTRUCTION & CO. | 112.84 | 0 | 85
4738 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000003/2023-2024 | 61/BD-1/4 | 27/04/2023 | 0 | Resource Division | 9.47 | 0 | 0
4739 | Berhampore Mechanical | Berhampur Division I | NEW CONNECTION AT PURBA KASHIPUR PH-I | Assistant Engineer-I | JE,Junior engineer-III | BILL/00242/2024-2025 | 104/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 5.84 | 0 | 0
4740 | Berhampore Mechanical | Berhampur Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Purba Kasipur and adjoining mouzas piped Water Supply Scheme Dist- Murshidabad under MEDB, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000019/2025-2026 | 1145/MEDB | 14/05/2025 | 92 | MONI ELECTRICAL WORKS | 22.95 | 0 | 0
4741 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
4742 | Berhampore Division I | Berhampur M/E Division | GAYESPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000048/2023-2024 | 144/BD-I | 15/05/2023 | 809 | SAPTADIP CONSTRUCTION | 58.85 | 0 | 30
4743 | Berhampore Division I | Berhampur M/E Division | GAYESPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000343/2023-2024 | 1257/BD-I | 22/12/2023 | 544 | M/S HUMAYUN BISWAS | 39.06 | 0 | 60
4744 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000032/2023-2024 | 61/BD-1/15 | 27/04/2023 | 0 | Resource Division | 6.62 | 0 | 0
4745 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000115/2023-2024 | 304/BD-1/7 | 22/02/2024 | 0 | Resource Division | 3.02 | 0 | 0
4746 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Gaysepur ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000651/2023-2024 | 3661/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE ( MANGO LANE) | 20.87 | 0 | 0
4747 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Chak Chandpara under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000075/2023-2024 | 181/BD-I | 17/05/2023 | 90 | ADITYA ENTERPRISE | 29.09 | 0 | 0
4748 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Chandpara village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000213/2023-2024 | 3073/MEDB | 02/08/2023 | 92 | ARINDAM MAJUMDAR | 6.27 | 0 | 0
4749 | Murshidabad Division | Berhampur M/E Division | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/01/2025 to 16/07/2025. [ Vehicle No:- WB 58 CD 3758] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000244/2024-2025 | 15/JSD | 17/01/2025 | 181 | HASSAN CONSTRUCTION | 0.88 | 0 | 0
4750 | Murshidabad Division | Berhampur M/E Division | Augmentation Work of Aurangabad Zone-II Piped Water Supply Scheme to accommodate with FHTC (586 Nos), Laying of Rising Main , Laying of Distribution System , construction of 600 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000294/2023-2024 | 2668/MURD | 24/08/2023 | 365 | KUNDU CONSTRUCTION | 371.15 | 0 | 0
4751 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.75 | 100
4752 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000222/2023-2024 | 1219/MURD/08 | 03/05/2023 | 0 | Resource Division | 47.69 | 0 | 0
4753 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
4754 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I A & Uttar Mahammadpur Water Supply Scheme at Head Work Site, 2nd Site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000123/2023-2024 | 1773/MURD | 06/07/2023 | 695 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 80
4755 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 6.13 | 100
4756 | Murshidabad Division | Berhampur M/E Division | Formal work order for UTTAR MAHAMMADPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission of SAMSERGANJ Block, Murshidabad District under Jangipur Sub Division Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000841/2022-2023 | 742/MURD | 16/03/2023 | 1021 | CREATIVE CONSTRUCTION | 413.33 | 0 | 20
4757 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000284/2023-2024 | 1230/MURD/27 | 04/05/2023 | 0 | Resource Division | 47.71 | 0 | 0
4758 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under UTTAR MAHAMMADPUR ground water based water supply scheme under Block_ SAMSERGANJ Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000113/2023-2024 | 1902/MEDB | 16/06/2023 | 92 | M/S. SUPER CONSTRUCTION | 34.05 | 13.72 | 10
4759 | Murshidabad Division | Berhampur M/E Division | Additional work for Laying of UPVC pipeline, Construction of Culvert and Approach road of LOKHAIPUR Piped Water Supply Scheme in Suti-II Block of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000003/2025-2026 | 783/MURD | 03/04/2025 | 45 | AZAD ENTERPRISE | 47.72 | 0 | 0
4760 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 4.13 | 100
4761 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LOKAIPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000616/2023-2024 | 3388/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 14.75 | 80
4762 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for LOKAIPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Raghunathganj-II Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000829/2022-2023 | 694/MURD | 10/03/2023 | 365 | ROY CONSTRUCTION (PROP:AVIJIT ROY) | 239.71 | 48.09 | 30
4763 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000285/2023-2024 | 1230/MURD/26 | 04/05/2023 | 0 | Resource Division | 18.15 | 0 | 0
4764 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000374/2023-2024 | 495/MURD/07 | 15/02/2024 | 0 | Resource Division | 4.1 | 0 | 0
4765 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION LOKAIPUR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/00166/2024-2025 | 9/WBSEDCL-JJM | 09/04/2024 | 0 | WBSEDCL | 4.73 | 0 | 0
4766 | Berhampore Mechanical | Berhampur M/E Division | LOKAIPUR PH-1 NEW CONNECTION | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01487/2023-2024 | 389/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 3.85 | 0 | 0
4767 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION LOKAIPUR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | BILL/01662/2023-2024 |  | 27/03/2024 | 0 | WBSEDCL | 4.73 | 0 | 0
4768 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube well in connection to Accommodate FHTC at Pump House No.-I II & III under LOKAIPUR ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000695/2023-2024 | 3809/MEDB | 03/11/2023 | 790 | DEBJYOTI BASU | 31.24 | 0 | 10
4769 | Murshidabad Division | Kandi Sub-Division | BISWANATHPUR PWSS under Jal Jeevan Mission of KHARGRAM Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000169/2023-2024 | 1975/MURD | 20/07/2023 | 590 | AMAL KUMAR DAS | 126.72 | 20.22 | 71
4770 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BISWANATHPUR Water Supply Scheme at Head Work Site, 2nd Site site at Khargram Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000387/2023-2024 | 2777/MURD | 01/09/2023 | 21 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 90
4771 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | RTOR000081/2023-2024 | 1129/MURD/4 | 25/04/2023 | 0 | Resource Division | 1.78 | 0 | 0
4772 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT BISWANATHPUR PH II, ID304233616 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | BILL/01214/2023-2024 | 262/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 7.78 | 0 | 0
4773 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT BISWANATHPUR PH I, ID304233599 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | BILL/01216/2023-2024 | 264/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.24 | 0 | 0
4774 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Biswanathpur ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000266/2023-2024 | 3703/MEDB | 03/11/2023 | 668 | M/S S. S. ENTERPRISE (DOMKAL) | 20.82 | 0 | 30
4775 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Hallalpur Zone-III under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000097/2023-2024 | 171/BD-I | 16/05/2023 | 90 | HI-LIGHT ELECTRONICS | 30.32 | 0 | 0
4776 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Halalpur Zone-III village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000215/2023-2024 | 3075/MEDB | 02/08/2023 | 92 | SURAKSHA | 6.3 | 0 | 0
4777 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Sujapur Zone-II under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000072/2023-2024 | 167/BD-I | 16/05/2023 | 90 | ALOK BANERJEE ENTERPRISE | 30.49 | 0 | 0
4778 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at CharSujapur Zone-II village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000180/2023-2024 | 3041/MEDB | 02/08/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0
4779 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sibnagar Zone-II under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000058/2023-2024 | 155/BD-I | 15/05/2023 | 90 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 30.53 | 0 | 0
4780 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Shibnagar Zone-II village, Block:- Nawda under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000184/2023-2024 | 3045/MEDB | 02/08/2023 | 92 | TARUN KUMAR BHATTACHARYA | 6.26 | 0 | 0
4781 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Arazi Narayanpur under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000050/2023-2024 | 147/BD-I | 15/05/2023 | 90 | INDRAJIT DUBEY | 28.9 | 0 | 0
4782 | Berhampore Mechanical | Berhampur M/E Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Arazi Narayanpur village, Block- Lalgola under ground water based mini piped water supply scheme, Dist- Murshidabad. under MEDB PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000681/2023-2024 | 587/MEDB | 31/01/2024 | 90 | GANGULI ELECTRICAL CO. | 6.3 | 0 | 0
4783 | Murshidabad Division | Kandi Sub-Division | Construction of 300 Cum OHR, Pump House, Boundwary Wall, Rising Main Connection & Repairing work of Existing OHR, Boundwary Wall , Pump House for Augmentation of Kagram water supply scheme of Bharatpur-II Block under Murshidabad Division, PHE Dte. PART_A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000019/2023-2024 | 992/MURD | 11/04/2023 | 721 | DALIM BISWAS ENTERPRISE | 157.49 | 45.07 | 15
4784 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kagram & Salar Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000048/2023-2024 | 1102/MURD | 24/04/2023 | 20 | INDRAJIT MAZUMDAR | 10.68 | 0 | 0
4785 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System & FHTC, for Augmentation of Kagram water supply scheme of Bharatpur-II Block under Murshidabad Division, PHE Dte. PART_B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000050/2023-2024 | 1232/MURD | 04/05/2023 | 365 | M/S NIRAPADA BHATTACHARJEE | 272.58 | 0 | 30
4786 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.06 | 80
4787 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 5.6 | 76
4788 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000030/2023-2024 | 1043/MURD | 17/04/2023 | 0 | Resource Division | 37.46 | 0 | 0
4789 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000069/2022-2023 | 1004/MURD/9 | 11/04/2023 | 0 | Resource Division | 66.52 | 0 | 0
4790 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000359/2023-2024 | MURD/439/04 | 08/02/2024 | 0 | Resource Division | 4.1 | 0 | 0
4791 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
4792 | Berhampore Mechanical | Kandi Sub-Division | NEW CONNECTION AT KAGRAM PH-III | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00231/2024-2025 | 68/WBSEDCL-JJM | 09/05/2024 | 0 | WBSEDCL | 5.22 | 0 | 0
4793 | Murshidabad Division | Berhampur M/E Division | Augmentation of GARIBPUR (Zone-II) PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000081/2023-2024 | 1381/MURD | 22/05/2023 | 280 | DOBAY CONSTRUCTION | 241.39 | 144.38 | 85
4794 | Murshidabad Division | Berhampur M/E Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. from 01/07/2025 to 31/12/2025 (WB-57E-9142) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000098/2025-2026 | 269/ISD | 30/06/2025 | 181 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 0 | 0
4795 | Murshidabad Division | Berhampur M/E Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. from 01/10/2025 to 31/03/2026 (120 days) [WB-26T-1742] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000174/2025-2026 | 390/ISD | 25/09/2025 | 181 | HAMIDUL ISLAM | 0.59 | 0 | 0
4796 | Murshidabad Division | Berhampur M/E Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.,e. from 01/01/2025 to 30/06/2025 (Vehicle No. W.B-57E-9142) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000508/2024-2025 | 626/ISD | 31/12/2024 | 181 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 0 | 0
4797 | Murshidabad Division | Berhampur M/E Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. from 01/04/2025 to 30/09/2025 (WB-26T-1742) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000534/2024-2025 | 142/ISD | 28/03/2025 | 184 | HAMIDUL ISLAM | 0.69 | 0 | 50
4798 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 4.84 | 1
4799 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000144/2023-2024 | 1167/MURD/36 | 28/04/2023 | 0 | Resource Division | 44.55 | 0 | 0
4800 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under Garibpur ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000092/2023-2024 | 3764/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 23.96 | 0 | 10
4801 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Darura under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000064/2023-2024 | 161/BD-I | 16/05/2023 | 90 | PRITAM KUMAR PAUL | 23.62 | 0 | 0
4802 | Berhampore Mechanical | Berhampur Division I | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Darura village, Block:- Murshidabad - Jiaganj under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000183/2023-2024 | 3044/MEDB | 02/08/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0
4803 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Hatisala Part- A village, Block:- Burwan, Kandi Sub Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000194/2023-2024 | 2024/MURD | 25/07/2023 | 60 | M/S S.R.K. ENTERPRISE | 30.55 | 0 | 0
4804 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Hatisala Part- B village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000212/2023-2024 | 2322/MURD | 02/08/2023 | 60 | KESHAB CHANDRA DAS | 30.54 | 0 | 0
4805 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Hatisala Part- C village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000213/2023-2024 | 2323/MURD | 02/08/2023 | 60 | M/S. MONDAL ENTERPRISE | 30.25 | 0 | 0
4806 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Hatisala Part- D village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000216/2023-2024 | 2327/MURD | 02/08/2023 | 60 | U.S BUILDERS | 30.54 | 0 | 0
4807 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hatisala Part-A village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000192/2023-2024 | 3051/MEDB | 02/08/2023 | 92 | SARKAR CONSTRUCTION | 6.3 | 0 | 0
4808 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hatisala Part-B village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000193/2023-2024 | 3052/MEDB | 02/08/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0
4809 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hatisala Part-C village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000194/2023-2024 | 3053/MEDB | 02/08/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0
4810 | Berhampore Mechanical | Kandi Sub-Division | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hatisala Part-D village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000195/2023-2024 | 3054/MEDB | 02/08/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0
4811 | Murshidabad Division |  | Laying of parallel distribution pipe line in between node point 15F to 23A and extension of distribution pipe line left & right side of canal of Alugram village (Village Code-315806) of Bharatpur water supply scheme for FHTC work under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000005/2022-2023 | 07 / KSD | 06/04/2022 | 30 | AGNIBESH CHATTERJEE | 4.84 | 4.84 | 1
4812 | Murshidabad Division |  | Extension of UPVC pipeline for FHTC work at Daspara, Ghoshpara, Kurulpara, Anchalpara, Gobardhanpara and Bagdipara in the Village of Alugram of Bharatpur Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. |  |  | ORD/000009/2022-2023 | 11 / KSD | 06/04/2022 | 30 | M/S. RAHAMAN CONSTRUCTION CO | 4.84 | 4.83 | 0
4813 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Alugram under Bharatpur Ground Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0007336059 in the District of Murshidabad. (Sl No-18) |  |  | ORD/000288/2020-2021 | 3270/MURD | 24/12/2020 | 180 | M/S . SUKUMAR SINHA | 109.97 | 129.52 | 100
4814 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at ALUGRAM G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000466/2021-2022 | 234/KSD | 27/08/2021 | 60 | IMAGIN | 4.17 | 0 | 0
4815 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SIJGRAM G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000472/2021-2022 | 240/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0
4816 | Murshidabad Division |  | Repairing of rising main pipe line including supplying of C.I specials, valves, construction of valve chamber & surface drain for the FHTC work of Bharatpur water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. (SL-04) |  |  | ORD/000520/2022-2023 | 157/KSD | 31/08/2022 | 30 | PRANAB KUMAR GHOSH | 4.77 | 4.74 | 0
4817 | Murshidabad Division |  | Holding Awarness Programme / Campaigning programms at Alugram G.P, Bharatpur G.P and Sijgram G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (Total nos of Programme = 12 nos) (Part-E). |  |  | ORD/000557/2021-2022 | 253/KSD | 31/08/2021 | 30 | S.S.INFRASTRUCTURE | 2.4 | 0 | 0
4818 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village SUNIA (Village Code 315806) under Bharatpur Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur-I Block in the District of Murshidabad. |  |  | ORD/000571/2020-2021 | 3037/MURD | 07/12/2020 | 45 | NAMDAR ALI | 8.6 | 0 | 1
4819 | Murshidabad Division |  | Supplying of C.I specials, valves & construction of valve chamber of different location for FHTC work of Alugram village of Bharatpur water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. |  |  | ORD/000627/2022-2023 | 3182/MURD | 30/11/2022 | 20 | U.S BUILDERS | 4.97 | 4.77 | 100
4820 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Madanpur Dafarpur ( Village Code -315810) under BHARATPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0007336059) |  |  | ORD/001718/2021-2022 | 731/MURD | 16/03/2022 | 45 | MOTI RAHAMAN | 40.35 | 14.97 | 45
4821 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000042/2021-2022 | 541/2/MURD | 25/02/2022 | 0 | Resource Division | 5.12 | 0 | 0
4822 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village LAKSHIJALA (Village Code 314127) under KASIADANGA Ground Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-II Block in the District of Murshidabad. Tender no - 550 of 21-22 by EE MURD |  |  | VCH/001466/2021-2022 | 366-MSD/21-22 | 11/03/2022 | 0 | NAMDAR ALI | 4.55 | 0 | 0
4823 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of Garibpur Zone-I (Part - A) Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000807/2022-2023 | 624/MURD | 03/03/2023 | 1123 | M/S. S. DAS AND ENTERPRISE | 590.43 | 412.83 | 40
4824 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 10.84 | 1
4825 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000201/2023-2024 | 1210/MURD/25 | 02/05/2023 | 0 | Resource Division | 217 | 0 | 0
4826 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 7.75 | 1
4827 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
4828 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Sankopara halt Station (TP NO 244/5 & 244/6) at Monrajpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Mahadevnagar Zone - II ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000421/2021-2022 | 2477/MURD | 16/08/2021 | 60 | ACQUA CONSTRACTION CONSORTIAM | 23.65 | 21.37 | 0
4829 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, FHTC, construction of OHR (Capacity 300 & 400 cum), Sinking of Tube Well , and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of MAHADEBNAGAR ZONE- IA,IB,IC ,IIA & IIB PWSS in Farakka Block, Murshidabad District under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000790/2023-2024 | 441/MURD | 08/02/2024 | 693 | MACKINTOSH BURN LIMITED | 1715.31 | 0 | 36
4830 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
4831 | Central Drilling | Berhampur M/E Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 92 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 10
4832 | Central Drilling | Berhampur M/E Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 7.77 | 20
4833 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SHYAMPUR PWSS (2nd TW Site) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000071/2025-2026 | 838/BD-I | 23/06/2025 | 15 | B.M. ENGINEERING & CONSTRUCTION | 9 | 0 | 0
4834 | Berhampore Division I | Berhampur M/E Division | SYAMPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000104/2023-2024 | 222/BD-I | 17/05/2023 | 639 | SKY CONSTRUCTION | 50.19 | 12.85 | 40
4835 | Berhampore Division I | Berhampur M/E Division | SYAMPUR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000171/2023-2024 | 663/BD-I | 09/08/2023 | 784 | M/S ABDUL MATIN | 290.59 | 115.52 | 30
4836 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000034/2023-2024 | 61/BD-1/19 | 27/04/2023 | 0 | Resource Division | 15.51 | 0 | 0
4837 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000114/2023-2024 | 304/BD-1/5 | 22/02/2024 | 0 | Resource Division | 7.38 | 0 | 0
4838 | Berhampore Mechanical | Berhampur M/E Division | SHYAMPUR PH-1 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | BILL/01519/2023-2024 | 397/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 6.46 | 0 | 0
4839 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III under SYAMPUR ground water based water supply scheme under Block_ LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000025/2025-2026 | 1154/MEDB | 14/05/2025 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 10.92 | 0 | 0
4840 | Murshidabad Division | Berhampur Sub-Division | Allied work of laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Maradighi ( Village Code -315674) under Rejinagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000053/2024-2025 | 1984/MURD | 08/07/2024 | 176 | SUPIA CONSTRUCTION | 15.86 | 0 | 80
4841 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 2.59 | 100
4842 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC connection to 1016 nos household , Laying of Distribution System, Rising Main for Augmentation work of Rejinagar Zone-III PWSS within Beldanga-II Block under Murshidabad Division , PHE.Dte. ( PART - A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000383/2023-2024 | 2769/MURD | 01/09/2023 | 731 | MITRA CONSTRUCTION | 159.63 | 0 | 100
4843 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Rejinagar Zone III PWSS of accommodate with Boundary Wall, 400 CUM OHR in Beldanga II Block within Murshidabad District under Murshidabad Division, PHE Dte. [ Part B ] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000589/2023-2024 | 3331/MURD | 23/10/2023 | 604 | NEW INDIA CONSTRUCTION | 188.69 | 0 | 80
4844 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 4.07 | 80
4845 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000022/2024-2025 | 1811/MURD/21 | 20/06/2024 | 0 | Resource Division | 8.44 | 0 | 0
4846 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000138/2023-2024 | 1167/MURD/48 | 28/04/2023 | 0 | Resource Division | 33.47 | 0 | 0
4847 | Berhampore Mechanical | Berhampur Sub-Division | NEW CONNECTION AT REJINAGAR Z-III PH-I | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | BILL/01579/2023-2024 | 415/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 5.8 | 0 | 0
4848 | Berhampore Mechanical | Berhampur Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II ,Zone-III under REJINAGAR ground water based water supply scheme under Block_ BELDANGA-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000238/2023-2024 | 3674/MEDB | 03/11/2023 | 92 | SREE RADHA ELECTRICAL | 21.42 | 15.21 | 6
4849 | Murshidabad Division | Islampur Sub-Division | Augmentation of JURANPUR (Part-B) PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000080/2023-2024 | 1382/MURD | 22/05/2023 | 955 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 122.02 | 30.68 | 20
4850 | Murshidabad Division | Islampur Sub-Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Juranpur ( PART-B) Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000128/2023-2024 | 1765/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 35.34 | 31.71 | 80
4851 | Murshidabad Division | Islampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 4.47 | 100
4852 | Murshidabad Division | Islampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000151/2023-2024 | 1180/MURD/01 | 29/04/2023 | 0 | Resource Division | 1.11 | 0 | 0
4853 | Murshidabad Division | Berhampur Sub-Division | Renovation of Existing IEP (Capacity 50 Cu.M/hr) for changing of 01 No Iron Removal Filter media unit of (3.30 m dia x 1.50 M HOS) & 01 No Oxidation Chamber of (1.00 M dia x 1.00 M HOS) and painting all vessel, pipes etc. all complete for Augmentation of Bachara Z-II Pipe Water supply scheme under Murshidabad Division P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000081/2024-2025 | 2074/MURD | 19/07/2024 | 30 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 4.84 | 0 | 100
4854 | Murshidabad Division | Berhampur Sub-Division | Construction of 100 Cum OHR, Laying of Distribution System (part_A) , Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity, Repairing & Vertical Extention of Boundary Wall for Augmentation work of BACHHARA ZONE-II PWSS in BELDANGA-II Block under Murshidabad Division , PHE.Dte. (part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000145/2023-2024 | 1870/MURD | 14/07/2023 | 795 | M/S. S.C. CIVIL ENTERPRISES | 280 | 80.62 | 30
4855 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 2.6 | 100
4856 | Murshidabad Division | Berhampur Sub-Division | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 75
4857 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 324 nos household , Laying of Distribution System (Part_B), Repairing & Vertical Extention of Boundary Wall for for Augmentation work of BACHHRA ZONE-II PWSS in Beldanga-II Block under Murshidabad Division , PHE.Dte. (part_B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000869/2022-2023 | 848/MURD | 24/03/2023 | 180 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 103.19 | 20.74 | 50
4858 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000013/2024-2025 | 1811/MURD/12 | 20/06/2024 | 0 | Resource Division | 1.4 | 0 | 0
4859 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000083/2022-2023 | 1278/MURD/18 | 10/05/2023 | 0 | Resource Division | 13.02 | 0 | 0
4860 | Central Drilling | Berhampur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
4861 | Berhampore Division I | Berhampur M/E Division | GOURIDASPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte.. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000084/2023-2024 | 202/BD-I | 17/05/2023 | 987 | M/S ROY & BOSE ENTERPRISE | 41.09 | 0 | 75
4862 | Berhampore Division I | Berhampur M/E Division | GOURIDASPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 150 cum) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000151/2023-2024 | 655/BD-I | 08/08/2023 | 923 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 209.18 | 0 | 85
4863 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000023/2023-2024 | 61/BD-1/26 | 27/04/2023 | 0 | Resource Division | 11.84 | 0 | 0
4864 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000116/2023-2024 | 304/BD-1/9 | 22/02/2024 | 0 | Resource Division | 4.82 | 0 | 0
4865 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Gouridaspur Piped Water Supply Scheme Block Lalgola, District - Murshidabad. under MEDB, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000567/2024-2025 | 382/MEDB | 12/02/2025 | 89 | CHAKRABORTY MINING AND ENGINEERING | 22.73 | 0 | 0
4866 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
4867 | Murshidabad Division | Kandi Sub-Division | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 450 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Nagar Zone-I PWSS in Khargram Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000575/2023-2024 | 3298/MURD | 20/10/2023 | 805 | SAMIMA ENTERPRISE | 492.21 | 0 | 10
4868 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 2.62 | 76
4869 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000014/2023-2024 | 1004/MURD/5 | 11/04/2023 | 0 | Resource Division | 62.48 | 0 | 0
4870 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000362/2023-2024 | MURD/439/07 | 08/02/2024 | 0 | Resource Division | 20.57 | 0 | 0
4871 | Central Drilling | Kandi Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 13.73 | 11
4872 | Murshidabad Division | Kandi Sub-Division | Additional work for Augmentation of Burwan (Zone-I) PWSS of accommodate FHTC, Laying of Distribution System, Road Restoration work and Land Development in Burwan Block of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000034/2025-2026 | 1111/MURD | 15/05/2025 | 60 | MOTI RAHAMAN | 87.4 | 0 | 0
4873 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based Burwan Zone-I PWSS of accommodate FHTC( 1848 Nos), Laying Distribution System, Laying Rising Main, Repairing of Switch Room, Boundary Wall, 200 CUM OHR, Repairing of 272 CUM OHR in Burwan Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000351/2023-2024 | 2678/MURD | 24/08/2023 | 586 | MOTI RAHAMAN | 360.93 | 28.89 | 10
4874 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Burwan Zone- I Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000727/2023-2024 | 3917/MURD | 21/12/2023 | 21 | MAMATA USHA ENTERPRISE | 11.79 | 0 | 0
4875 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 1.73 | 80
4876 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 4.37 | 76
4877 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000010/2023-2024 | 1004/MURD/3 | 11/04/2023 | 0 | Resource Division | 70.9 | 0 | 0
4878 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Selamatipur PWSS Scheme, Block - Berhampore) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR ENGINEER_BERHAMPORE BLOCK | ORD/000834/2021-2022 | 3267/MURD | 05/10/2021 | 60 | RADIANT | 3.23 | 3.23 | 0
4879 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR ENGINEER_BERHAMPORE BLOCK | RTOR000003/2024-2025 | 1811/MURD/02 | 20/06/2024 | 0 | Resource Division | 16.77 | 0 | 0
4880 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR ENGINEER_BERHAMPORE BLOCK | RTOR000301/2023-2024 | 1278/MURD/2 | 10/05/2023 | 0 | Resource Division | 10.58 | 0 | 0
4881 | Central Drilling | Berhampur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR ENGINEER_BERHAMPORE BLOCK | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
4882 | Berhampore Mechanical | Berhampur Sub-Division | QUOTATION FOR SHIFTING OF PHE25KVA DTR AT SALAMATPUR REF ID. 860308681 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR ENGINEER_BERHAMPORE BLOCK | BILL/00651/2024-2025 |  | 16/08/2024 | 0 | WBSEDCL | 4.47 | 0 | 0
4883 | Berhampore Mechanical | Berhampur Sub-Division | QUOTATION FOR SHIFTING OF PHE 25KVA DTR AT SALAMATPUR REF ID. 860308681 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR ENGINEER_BERHAMPORE BLOCK | BILL/00653/2024-2025 | 199/WBSEDCL-JJM | 22/08/2024 | 0 | WBSEDCL | 4.47 | 0 | 0
4884 | Murshidabad Division | Kandi Sub-Division | BADDA PWSS under Jal Jivan Mission of BURWAN Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000095/2023-2024 | 1692/MURD | 28/06/2023 | 1004 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 226.02 | 0 | 10
4885 | Murshidabad Division | Kandi Sub-Division | BADDA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. (Part A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000142/2023-2024 | 1866/MURD | 14/07/2023 | 902 | DHIRENDRANATH MONDAL | 344.64 | 256.88 | 10
4886 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BADDA AND IT'S ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000392/2023-2024 | 2794/MURD | 04/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.45 | 0 | 100
4887 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000076/2023-2024 | 1075/MURD/18 | 19/04/2023 | 0 | Resource Division | 24.74 | 0 | 0
4888 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS BADDA PH1 ID 304248207 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/01420/2023-2024 | 314/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 10.01 | 0 | 0
4889 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Badda ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000259/2023-2024 | 3695/MEDB | 03/11/2023 | 699 | ORIENTAL ENGINEERING CO. | 22.53 | 0 | 70
4890 | Murshidabad Division | Kandi Sub-Division | BADUA & adjoining mouzas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000052/2023-2024 | 1263/MURD | 08/05/2023 | 937 | TEKNO ENTERPRISE | 570.69 | 0 | 20
4891 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000244/2023-2024 | 1219/MURD/33 | 03/05/2023 | 0 | Resource Division | 18.54 | 0 | 0
4892 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Badua ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000260/2023-2024 | 3696/MEDB | 03/11/2023 | 92 | ORIENTAL ENGINEERING CO. | 23.45 | 0 | 0
4893 | Murshidabad Division | Kandi Sub-Division | GAYESPUR PWSS under Jal Jeevan Mission of KHARGRAM Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000099/2023-2024 | 1700/MURD | 28/06/2023 | 599 | SOFIQUL ISLAM | 279.31 | 86.38 | 10
4894 | Murshidabad Division | Kandi Sub-Division | Construction of Drain, Laying of UPVC pipeline and road restoration work of Gayespur Water Supply Scheme in Khargram Block of Kandi Sub-Division, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000202/2024-2025 | 3285/MURD | 16/12/2024 | 30 | DAS ENTERPRISE (SUBRATA DAS) | 38.28 | 0 | 0
4895 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GAYESPUR AND ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at Khargram Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000628/2023-2024 | 3424/MURD | 02/11/2023 | 21 | NADIA TUBEWELLS | 18.43 | 0 | 100
4896 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000082/2023-2024 | 1129/MURD/5 | 25/04/2023 | 0 | Resource Division | 13.5 | 0 | 0
4897 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PH2 GAYESHPUR ID 304239446 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01414/2023-2024 | 305/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 3.78 | 0 | 0
4898 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT PWSS PH1 GAYESHPUR ID 304239445 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/01415/2023-2024 | 306/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 10.95 | 0 | 0
4899 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for GAYESPUR AND ADJOINING MOUJAS PWSS District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000566/2024-2025 | 348/MEDB | 10/02/2025 | 89 | M/S SAJAHAN CHOWDHURY | 21.38 | 0 | 0
4900 | Murshidabad Division | Kandi Sub-Division | Construction of 200 Cum OHR, Pump House Boundwary Wall, , Rising Main Connection, Laying Distribution System of SUKURIA water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. Part-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000021/2023-2024 | 995/MURD | 11/04/2023 | 1086 | APORUPA CONSTRUCTION | 226.95 | 104.12 | 65
4901 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System, FHTC of SUKURIA water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. in the District of Murshidabad Part-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000025/2023-2024 | 1032/MURD | 13/04/2023 | 872 | DIPAYAN DEY | 188.8 | 167.11 | 10
4902 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SUKURIA AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000288/2023-2024 | 2634/MURD | 23/08/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 18.43 | 15.44 | 100
4903 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000079/2022-2023 | 1936/MURD/4 | 18/07/2023 | 0 | Resource Division | 15.94 | 0 | 0
4904 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT SUKURIA PH I, ID 304233761 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01204/2023-2024 | 272/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 6.22 | 0 | 0
4905 | Berhampore Mechanical | Kandi Sub-Division | NEW SERVICE CONNECTION AT SUKURIA PH II, ID304233502 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | BILL/01205/2023-2024 | 273/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 6.06 | 0 | 0
4906 | Berhampore Mechanical | Kandi Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SUKURIA ground water based water supply scheme under Block_ Barwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000118/2023-2024 | 1907/MEDB | 16/06/2023 | 92 | B. T. PROJECTS PVT. LTD. | 22.42 | 0 | 50
4907 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for KEYADANGA Ground Based Water Supply Scheme in Suti-II Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000053/2025-2026 | 1225/MURD | 28/05/2025 | 60 | M/S . SUKUMAR SINHA | 19.62 | 0 | 0
4908 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000357/2023-2024 | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 2.44 | 100
4909 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based HAFANIA (ZONE-II) & KEYADANGA PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000819/2022-2023 | 801/MURD | 22/03/2023 | 831 | ATIKUL SAIKH | 367.41 | 52.52 | 100
4910 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000267/2023-2024 | 1230/MURD/10 | 04/05/2023 | 0 | Resource Division | 9.94 | 0 | 0
4911 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under KEYADANGA ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000128/2023-2024 | 1915/MEDB | 16/06/2023 | 92 | SUBHRA ENTERPRISE | 21.01 | 0 | 15
4912 | Murshidabad Division |  | Permission for laying pipeline (200 mm dia) along the NH-12 within the utility corridor from Moregram to gangadda of sagardighi surface water based drinking water supply scheme block sagardighi, district-Murshidabad under Murshidabad Division, P.H.E.Dte. |  |  | BILL/01075/2023-2024 | 543-MSD/2023-24 | 16/02/2024 | 0 | CHIEF ENGINEER CIVIL MINISTRY OF ROAD TRANSPORT AND HIGHWAYS KOLKATA | 3.18 | 0 | 0
4913 | Murshidabad Division |  | Last mile connectivity and providing 1803 nos Funcational House Hold Connection from Zone- II of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. |  |  | ORD/000329/2023-2024 | 2686/MURD | 25/08/2023 | 120 | AJAY MONDAL | 114.49 | 0 | 0
4914 | Murshidabad Division |  | Last mile connectivity and providing 5600 nos Functional House Hold Connection from Zone- XIII of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . |  |  | ORD/000335/2023-2024 | 2692/MURD | 25/08/2023 | 120 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 352.9 | 0 | 0
4915 | Murshidabad Division |  | Allied work for Construction of Annular Combined Pile Raft Foundation for R.C.C Elevated Reservoir of Capacity 900 CuM of staging height 20 Meter at Head Work site within BANYESWAR(Zone-XIII) W/S Scheme, Block-Sagardighi, District-Murshidabad Under Murshidabad Division P.H.E Dte. |  |  | ORD/000836/2023-2024 | 785/MURD | 14/03/2024 | 60 | BIJAY CHOWDHURY | 84.81 | 0 | 85
4916 | Murshidabad Division |  | Last mile connectivity and providing 6918 nos Functional House Hold Connection from Zone- XIV of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte |  |  | ORD/000336/2023-2024 | 2693/MURD | 25/08/2023 | 120 | M/S GUHA AND ROY | 413.64 | 0 | 0
4917 | Murshidabad Division |  | Last mile connectivity and providing 3452 nos Functional House Hold Connection from Zone- XVI of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . |  |  | ORD/000338/2023-2024 | 2695/MURD | 25/08/2023 | 120 | TEKNO ENTERPRISE | 207.53 | 0 | 0
4918 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Hazi Mahammadpur ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000129/2024-2025 | 1479/BD-I | 06/09/2024 | 60 | MURSHID ALOM | 11.94 | 0 | 0
4919 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Hazi Mahammadpur ( Habitation ID: 0001294220) in the village of Hazi Mahammadpur (Village code 314231) under Hazi Mahammadpur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000233/2020-2021 | 1048/BD-I | 28/12/2020 | 90 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 32.81 | 30.16 | 1
4920 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area Of village of Dakshin Ashariadaha (Village code 314229) under Hazi Mohammadpur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-16 of 2020 ¿ 2021,SL-10) | Assistant Engineer-I | JE | ORD/000243/2020-2021 | 76/BD-I | 19/01/2021 | 30 | JIBENDRA NARAYAN SUKUL | 24.9 | 39.42 | 0
4921 | Murshidabad Division | Berhampur M/E Division | NEZAMPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Suti-II Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000015/2023-2024 | 979/MURD | 10/04/2023 | 723 | M/S. M.S. ENTERPRISE | 207.04 | 0 | 30
4922 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 3.83 | 100
4923 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NEZAMPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000615/2023-2024 | 3387/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 0 | 100
4924 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000279/2023-2024 | 1230/MURD/19 | 04/05/2023 | 0 | Resource Division | 15.35 | 0 | 0
4925 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT NEZAMPUR PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/00617/2024-2025 |  | 02/08/2024 | 0 | WBSEDCL | 3.92 | 0 | 0
4926 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT NEJAMPUR PH-1 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/00633/2024-2025 | 185/WBSEDCL-JJM | 09/08/2024 | 0 | WBSEDCL | 3.92 | 0 | 0
4927 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION AT NEZAMPUR PH-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | BILL/01245/2024-2025 |  | 13/12/2024 | 0 | WBSEDCL | 4.22 | 0 | 0
4928 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under NEZAMPUR ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000079/2023-2024 | 1930/MEDB | 16/06/2023 | 92 | M/S S. G. ENTERPRISE | 21 | 0 | 0
4929 | Murshidabad Division | Berhampur M/E Division | Allied work of laying of additional pipeline of 125 mm dia, Land Development, connecting road and construction of soakwell and construction of surface drain of 150 m lenth at Hilora zone 2 PWSS at suti -1 Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000021/2024-2025 | 1812/MURD | 20/06/2024 | 60 | M H SUPPLIERS | 53.94 | 0 | 0
4930 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for HILORA Zone-II Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000054/2025-2026 | 1224/MURD | 28/05/2025 | 60 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 23.01 | 0 | 0
4931 | Murshidabad Division | Berhampur M/E Division | Laying Distribution System and Road Restoration of Hilora Zone-II PWSS in Suti-I Block , Jangipur Sub-Division under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000075/2025-2026 | 1332/MURD | 10/06/2025 | 60 | PARTHA PRATIM DAS | 22.91 | 0 | 0
4932 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.23 | 100
4933 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jaykrishnapur Zone- I & Hilora Zone-II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000133/2023-2024 | 1769/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 18.45 | 0 | 100
4934 | Murshidabad Division | Berhampur M/E Division | Providing FHTC Connection to 1424 nos household, Special repair and renovation of existing 2 (Two) Nos Pump House & Alied Works and Repair of Boundary Wall (140m + 50m) =190 m at T/W-I site & T/W-II site for Augmentation of HILORA ZONE II Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000870/2022-2023 | 849/MURD | 24/03/2023 | 889 | JAMIRUL CONSTRUCTION | 79.6 | 0 | 85
4935 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main, Laying of Distribution System and Overhauling of RCC 180 Cum OHR for Augmentation of HILORA ZONE II Piped Water Supply Scheme in SUTI-I Block in Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000871/2022-2023 | 850/MURD | 24/03/2023 | 180 | M H SUPPLIERS | 71.55 | 55.99 | 70
4936 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000193/2023-2024 | 1210/MURD/09 | 02/05/2023 | 0 | Resource Division | 48.45 | 0 | 0
4937 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shibnagar Laskarpur (Zone - II ) Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000358/2023-2024 | 2701/MURD | 25/08/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 32.1 | 95
4938 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 4.43 | 100
4939 | Murshidabad Division | Berhampur M/E Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II) under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000728/2023-2024 | 4005/MURD | 28/12/2023 | 735 | M/S. BIMAL MISRA | 838.96 | 0 | 35
4940 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000209/2023-2024 | 1210/MURD/14 | 02/05/2023 | 0 | Resource Division | 241.41 | 0 | 0
4941 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION SHIBNAGAR LASKARPUR Z-II PH-I | ASSISTANT ENGINEER-I | Junior engineer-III | BILL/01613/2023-2024 | 435/WBSEDCL-JJM | 13/03/2024 | 0 | WBSEDCL | 3.81 | 0 | 0
4942 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION SHIBNAGAR LASKARPUR Z-II PH-II | ASSISTANT ENGINEER-I | Junior engineer-III | BILL/01614/2023-2024 | 436/WBSEDCL-JJM | 13/03/2024 | 0 | WBSEDCL | 6.64 | 0 | 0
4943 | Berhampore Mechanical | Berhampur M/E Division | NEW CONNECTION SHIBNAGAR LASKARPUR Z-II PH-III | ASSISTANT ENGINEER-I | Junior engineer-III | BILL/01616/2023-2024 | 437/WBSEDCL-JJM | 13/03/2024 | 0 | WBSEDCL | 6.16 | 0 | 0
4944 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II , III ,IV & V ,Zone-II under SHIBNAGAR LASKARPUR ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000691/2023-2024 | 4305/MEDB | 29/12/2023 | 91 | HARA PROSAD DAS | 55.57 | 0 | 5
4945 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000349/2022-2023 | 1928/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 8.78 | 0.43 | 100
4946 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Nabagram of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Amarkundu Water Supply Scheme, Nabagram Zone-I & II Water Supply Scheme, Panchgram Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000350/2022-2023 | 1929/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 7.92 | 2.04 | 100
4947 | Murshidabad Division | Lalbag Sub-Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 400 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Habaspur PWSS in Bhagwagola- I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000658/2023-2024 | 3516/MURD | 09/11/2023 | 874 | M/S. GOUTAM CHAKRABORTY | 717.52 | 0 | 10
4948 | Murshidabad Division | Lalbag Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | RTOR000123/2023-2024 | 1167/MURD/19 | 28/04/2023 | 0 | Resource Division | 22.34 | 0 | 0
4949 | Murshidabad Division | Berhampur M/E Division | Laying Distribution System, Rising Main Connection, Construction of OHR (Capacity 600 and 350 cum) ,Pump house cum chlorine Room , Boundary wall, Office cum Godown, approach road and Pushing of casing pipe by Hydraulic Jacking Technique method across the railway track for Augmentation of Surface Water Based Water Supply Scheme for Jiaganj Municipality and its adjoining Mouzas in Murshidabad - Jiaganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000608/2023-2024 | 3369/MURD | 31/10/2023 | 365 | M/S. S. DAS AND ENTERPRISE | 968.51 | 0 | 1
4950 | Berhampore Division I | Raghunathganj Sub-Division | Relaying of different dia UPVC Pipe line in connection with JJM (Jal Jeevan Mission) over damaged portion and Interconnection between over flow line and Delivery Line at Beniagram Zone-II OHR Site under Beniagram Surface Based water supply scheme of Zone-II of Murshidabad District under Berhampore Division-I PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000019/2023-2024 | 90/BD-I | 03/05/2023 | 30 | BABAI GHOSH | 3.05 | 3.01 | 100
4951 | Berhampore Division I | Raghunathganj Sub-Division | Continuation work order for Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub Division, PHE Dte. period for 01.01.2024 to 31.12.2024. | Assistant Engineer | Junior Engineer-I | ORD/000379/2023-2024 | 1281/BD-I | 27/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 1.81 | 0 | 33
4952 | Berhampore Division I | Raghunathganj Sub-Division | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer | Junior Engineer-I | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 1
4953 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baikunthapur, Asua, Hosenpur & Jafarganj (Village code 313816, 313817, 313818 & 313809) under Beniagram Water Supply Scheme of Farakka Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-03) | Assistant Engineer | Junior Engineer-I | ORD/000583/2021-2022 | 2010/BD-I | 08/11/2021 | 1229 | DECON INDIA | 167.27 | 134.55 | 100
4954 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Beniagram (Village code 313832) under Beniagram Water Supply Scheme of Farakka Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-05) | Assistant Engineer | Junior Engineer-I | ORD/000584/2021-2022 | 2011/BD-I | 08/11/2021 | 180 | M/S S.DAS & ENTERPRISE | 162.77 | 0 | 1
4955 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chauki, Kashinagar, Samaspur & Imamnagar (Village code 313803, 313806, 313810 & 313815) under Beniagram Water Supply Scheme of Farakka Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-07) | Assistant Engineer | Junior Engineer-I | ORD/000615/2021-2022 | 2050/BD-I | 17/11/2021 | 900 | DOBAY CONSTRUCTION | 142.86 | 118.84 | 80
4956 | Berhampore Division I | Raghunathganj Sub-Division | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Beniagram Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer-I | ORD/000762/2021-2022 | 2228/BD-I | 15/12/2021 | 90 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 71 | 68.22 | 1
4957 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer-I | RTOR000013/2021-2022 | 145/BD-I | 10/02/2022 | 0 | Resource Division | 18.66 | 0 | 0
4958 | Murshidabad Division | Kandi Sub-Division | Construction of Valve Chamber, M.S Gate, Laying Distribution System of UPVC Pipeline for Augmentation of Kamalakantapur / Bahara Water Supply Scheme in Bharatpur- I Block, of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000191/2024-2025 | 3148/MURD | 03/12/2024 | 45 | ABDUL ENTERPRISE | 45.91 | 0 | 0
4959 | Murshidabad Division | Kandi Sub-Division | Construction of Boundary wall at 1st Tubewell site of Khasra PWSS & Bahara PWSS of Kandi Block in Kandi Sub-Division under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000196/2024-2025 | 3214/MURD | 09/12/2024 | 266 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 12.9 | 0 | 5
4960 | Murshidabad Division | Kandi Sub-Division | Design, Drawing, Fabrication, Erection Iron Elimination Plant (IEP) of 45 m3/hr & 40m3/hr Capacity as per Departmental approved model including comossing trial run (3months) of 2 nos Construction of Blower Room (H.W.Site), Pump House (3rd Site), Boundary Wall (3rd Site), Laying of UPVC Pipe of Bahara Water Supply Scheme in Kandi Block of Kandi Sub Division, under Murshidabad Division P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000240/2024-2025 | 190/MURD | 21/01/2025 | 60 | ANIRUDDHYA BOSE | 94.01 | 0 | 30
4961 | Murshidabad Division | Kandi Sub-Division | Construction 200 Cum OHR, Laying Distribution System Part-A, FHTC at Brahmanpara Village (Village Code-315290), Bahara Village (Village Code-315291) & Bhandira Village (Village Code-315292), Repairing of Existing Pump house (H.W), Boundary Wall, Existing OHR for Augmentation of BAHARA Ground water based Piped water supply scheme in KANDI Block under Murshidabad Division, PHE. Dte Part-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000248/2023-2024 | 2463/MURD | 09/08/2023 | 876 | ROY ENTERPRISE | 182.7 | 37.67 | 21
4962 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System (PART-B), FHTC work at Dohalia Village (Village Code-315294), Baje Dohalia Village (Village Code-315293) & Bhandira Village (Village Code-315292) for Augmentation of of BAHARA Ground water based Piped water supply scheme in KANDI Block under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000251/2023-2024 | 2462/MURD | 09/08/2023 | 150 | M/S.S.S. ENTERPRISE | 215.67 | 0 | 20
4963 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 10.81 | 75
4964 | Murshidabad Division | Kandi Sub-Division | Development of land at Head Work Site of Bahara Water Supply Scheme under Kandi Sub-Division, P.H.Engg. Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001597/2021-2022 | 375/KSD | 19/01/2022 | 30 | ROY ENTERPRISE | 4.53 | 0 | 100
4965 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000044/2023-2024 | 1043/MURD/8 | 17/04/2023 | 0 | Resource Division | 95.05 | 0 | 0
4966 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000061/2022-2023 | 1004/MURD/9 | 11/04/2023 | 0 | Resource Division | 95.05 | 0 | 0
4967 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000360/2023-2024 | MURD/439/06 | 08/02/2024 | 0 | Resource Division | 4.9 | 0 | 0
4968 | Berhampore Mechanical | Kandi Sub-Division | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under BAHARA ground water based water supply scheme under Block_ KANDI Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001480/2023-2024 | 760/MEDB | 20/02/2024 | 90 | M/S SAJAHAN CHOWDHURY | 36.36 | 0 | 25
4969 | Murshidabad Division | Berhampur M/E Division | Allied work of Repair & Renovation of Pump House and Boundary Wall at Head Work Site of Teghari (Zone-I) Water Supply Scheme under Jangipur Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000064/2024-2025 | 2014/MURD | 11/07/2024 | 444 | AZAD ENTERPRISE | 17.13 | 0 | 80
4970 | Murshidabad Division | Berhampur M/E Division | Allied works for Laying of Rising Main & Distribution System (Part-A) of TEGHARI (ZONE-I) Water Supply Scheme of Raghunathgani-II Block in Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000163/2024-2025 | 2908/MURD | 29/10/2024 | 154 | RIDAUAN ENTERPRISE | 55.78 | 0 | 60
4971 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System for Augmentation work of Teghari (Zone-I) PWSS (PART-B) in Raghunathganj-II Block under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000177/2023-2024 | 1995/MURD | 21/07/2023 | 180 | M/S. CHOWDHURY CONSTRUCTION | 112.17 | 24.54 | 20
4972 | Murshidabad Division | Berhampur M/E Division | Providing FHTC to 2516 nos. household for Augmentation work of Teghari (Zone-I) PWSS(PART-A) in Raghunathganj-II Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000191/2023-2024 | 2022/MURD | 25/07/2023 | 180 | ARABINDA GHOSH | 124.91 | 0 | 0
4973 | Murshidabad Division | Berhampur M/E Division | Allied works for Laying of Rising Main & Distribution System (Part-B) of TEGHARI (ZONE-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000241/2024-2025 | 192/MURD | 21/01/2025 | 60 | SUMAN CHOWDHURY | 43.88 | 0 | 0
4974 | Murshidabad Division | Berhampur M/E Division | Allied work for vertical extension of head works site boundary wall , Reinforced Barbed Tape (R.B.T) Concertina fencing on Boundary wall top and construction of Wash out pipe line from OHR to pond of Teghari Water Supply Scheme of Raghunathganj-II Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000242/2023-2024 | 2409/MURD | 07/08/2023 | 30 | MOLLA ENTERPRISE | 9.43 | 9.21 | 100
4975 | Murshidabad Division | Berhampur M/E Division | Providing FHTC to 2500 nos household for Augmentation work of Teghari (Zone-I) PWSS (PART-B) in Raghunathganj-II Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000378/2023-2024 | 2756/MURD | 01/09/2023 | 845 | DEBASIS BOSE | 124.54 | 0 | 30
4976 | Murshidabad Division | Berhampur M/E Division | Allied work for Repairing & Renovation of 800 Cum Capacity and 20 mtr staging height R.C.C. Elevated Reservoir & construction of surface drain for Augmentation work of TEGHARI (Zone-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000841/2023-2024 | 819/MURD | 15/03/2024 | 60 | BABUSONA CONSTRUCTION | 10.9 | 0 | 0
4977 | Murshidabad Division | Berhampur M/E Division | Allied work for Renovation of Pump House and Boundary Wall at 2nd Site of Teghari (Zone-I) Water Supply Scheme under Jangipur Sub Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000852/2023-2024 | 828/MURD | 15/03/2024 | 30 | NIRMAN ENTERPRISE | 5.29 | 0 | 0
4978 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 4.31 | 100
4979 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000148/2023-2024 | 1167/MURD/52 | 28/04/2023 | 0 | Resource Division | 115.2 | 0 | 0
4980 | Berhampore Mechanical | Berhampur M/E Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000569/2024-2025 | 384/MEDB | 12/02/2025 | 89 | CHOWDHURY & BASU ENTERPRISE | 45.46 | 0 | 0
Total | [10 empty] | 1958564.01 | 69512.16