## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Uttar Narayanpur, Kurula Ambha of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-A) |  |  | ORD/000051/2020-2021 | 1178 /BHM | 21/09/2020 | 60 | SUNIL RABI DAS | 41.99 | 0 | 79
2 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Mara Basahar, Jagadispur of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-B) |  |  | ORD/000054/2020-2021 | 1179 /BHM | 21/09/2020 | 60 | SANJUKTA ENGINEERS | 32.72 | 28.01 | 100
3 | Birbhum Division |  | Additional Laying of UPVC Pipe line for providing FHTC at Jagadishpur & Marbasahar village under Kaluha PWSS within Birbhum Division, P.H.E. Dte. (Sl. No.3) |  |  | ORD/000848/2021-2022 | 2005/BHM | 08/12/2021 | 60 | SANJUKTA ENGINEERS | 6.82 | 0 | 50
4 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC)from existing distribution system in habitaiton of Kamapur Nutunpara under Kamalpur Mouza (Jl. NO.4) under Suri-I Block within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.01) |  |  | ORD/000002/2021-2022 | 191/BSSD | 02/06/2021 | 20 | BAMDEB CONSTRUCTION | 4.92 | 0 | 0
5 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Malian, Joka & Kamalpur of Tilpara w/s Scheme at Suri-I Block within Suri Sadar Sub Division under Birbhum Division, PHE Dte. (Sl. No.1) |  |  | ORD/000058/2020-2021 | 1420/BHM | 04/11/2020 | 45 | B.M.SARKAR | 17.18 | 13.74 | 97
6 | Birbhum Division |  | Providing functional house tap connection (FHTC) from existing distribution system within the command area of Tilpara Water Supply Scheme. |  |  | ORD/000215/2020-2021 | 1707/BHM | 23/12/2020 | 60 | RAJ KUMAR DAS | 47.57 | 20.61 | 65
7 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Araipur of Tilpara w/s Scheme at Suri I Block within Suri Sadar Sub Division under Birbhum Division, PHE Dte. (2nd Call) (Sl. No.22) |  |  | ORD/000216/2020-2021 | 1713/BHM | 23/12/2020 | 45 | PRANAB KUMAR GHOSH | 21.28 | 16.64 | 100
8 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tilpara w/s Scheme (Left out House Hold) in Suri Sadar Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.1) |  |  | ORD/000257/2021-2022 | 1506/BHM | 09/09/2021 | 60 | RAJKUMAR DAS | 39.43 | 0 | 50
9 | Birbhum Division |  | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Kalpatarupally under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl.No. -02) |  |  | ORD/000275/2021-2022 | 336/BSSD | 23/09/2021 | 20 | M/S SARADA CONSTRUCTION. | 4.02 | 0 | 100
10 | Birbhum Division |  | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Laldighipara under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 03) |  |  | ORD/000321/2021-2022 | 353/BSSD | 25/10/2021 | 20 | SACHIN KUMAR SARKAR | 3.88 | 0 | 0
11 | Birbhum Division |  | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Laldighipara under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 03) |  |  | ORD/000553/2021-2022 | 353/BSSD. | 25/10/2021 | 20 | SACHIN KUMAR SARKAR | 3.88 | 0 | 100
12 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 500cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Purandarpur W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000016/2023-2024 | 1215/BHM | 12/04/2023 | 275 | M/S GOUTAM DAS | 128.59 | 0 | 100
13 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Laying distribution system for proposed augmentation scheme for Purandarpur Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000115/2023-2024 | 2076/BHM | 08/06/2023 | 60 | M/S GOUTAM DAS | 56.35 | 0 | 100
14 | Birbhum Division | Birbhum Sadar Sub-Division | Trial Bore and Sinking of 200 mm dia. tubewell (02 nos.) 125 m. Deep fitted with M.S.E.R.W. Housing pipe and Fibre Glass Strainer on the river bank of Mayurakshi for the Augmentation of Purandarpur Piped Water Supply Scheme under Birbhum Sadar Sub-Division PHE Dte. with Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000134/2023-2024 | 2269/BHM | 13/07/2023 | 30 | PRANAB KUMAR MONDAL | 5.6 | 0 | 100
15 | Birbhum Division | Birbhum Sadar Sub-Division | Laying distribution system for proposed augmentation scheme for purandarpur piped water supply scheme under Birbhum Sadar sub division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000394/2022-2023 | 1026/BHM | 12/05/2022 | 1352 | M/S GOUTAM DAS | 387.66 | 0 | 95
16 | Birbhum Division | Birbhum Sadar Sub-Division | Annual Mtc. of pipeline (Distribution and rising main) for the water supply schemes related to the daily supply of water to the consumers under Birbhum Division, PHE Dte.¿ Purandarpur W/S Scheme (Sl. No.-06) | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000614/2020-2021 | 1826/BHM | 31/12/2020 | 365 | PRANAB KUMAR MONDAL | 2.91 | 0 | 0
17 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000005/2023-2024 | 1115/BHM | 10/04/2023 | 0 | Resource Division | 10.28 | 0 | 0
18 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000030/2022-2023 | 2290/BHM | 20/10/2022 | 0 | Resource Division | 5.93 | 0 | 0
19 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000044/2021-2022 | 215/BHM | 02/02/2022 | 0 | Resource Division | 16.6 | 0 | 0
20 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000064/2021-2022 | 489/BHM | 02/03/2022 | 0 | Resource Division | 25.74 | 0 | 0
21 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at aug. of Purandarpur PWSS. | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/02317/2023-2024 | BP-23-24-358 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.59 | 0 | 0
22 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Purandarpur water supply scheme under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000007/2023-2024 | 716/Bol.MD | 19/04/2023 | 866 | SATYAJIT GHOSH | 24.44 | 0 | 100
23 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Additional works for installation of submersible pumping machineries at Aug. of purandarpur water supply scheme Block- Suri-II under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000310/2024-2025 | 1880/BOL.MD | 05/08/2024 | 45 | SATYAJIT GHOSH | 7.27 | 0 | 100
24 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Replacement of voltage correction device at Purandarpur PH-I water supply scheme under under Bolpur Mechanical Division, PHE Dte.(Aug. of Purandarpur W/S Scehem) | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000695/2023-2024 | 1360/AE-III | 17/10/2023 | 15 | QUAZI NOZRUL ISLAM | 2.05 | 0 | 100
25 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Deriapur Water Supply Scheme within Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.1) | AE | JE3 | ORD/000019/2022-2023 | 738/BHM | 04/04/2022 | 60 | M/S GOUTAM DAS | 96 | 0 | 80
26 | Birbhum Division | Birbhum Sadar Sub-Division | Balance work for for Uttar Gobindapur area, Connecting pipe line, rest portion laying of pipe line for Functional Household Tap Connection (FHTC) of Deriapur Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000150/2023-2024 | 1979/BHM | 05/06/2023 | 45 | PINTU KHAN | 39.24 | 0 | 62
27 | Birbhum Division | Birbhum Sadar Sub-Division | Trial Bore and Sinking of 200 mm dia. 2(Two) nos.tubewell 30m. (avg.) depth fitted with PVC pipes & fittings Schedule 80 (medium duty) and Fibre Glass Strainer on the river bank of Mayurakshi under Deriapur Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, PHE Dte. (Sl. No. - 01) | AE | JE3 | ORD/000691/2021-2022 | 403/BSSD | 14/12/2021 | 15 | BHABATARAN SADHU | 4.53 | 0 | 100
28 | Birbhum Division | Birbhum Sadar Sub-Division | Laying of Distribution Main pipeline through road crossing of Suri-Sainthia via Patelnagar Road by adopting Jack Pushing method at Gournagar (Node 179-180), Punur (Node 53-54), Dhaikota (Node 2-3) and Bagdola More (Node 71-72) under Deriapur Piped Water Supply Scheme at Sainthia Development Block within Birbhum Division, PHE Dte. (SL.No.3) | AE | JE3 | ORD/000707/2021-2022 | 503/BHM | 02/03/2022 | 45 | M/S GOUTAM DAS | 28.33 | 0 | 0
29 | Birbhum Division | Birbhum Sadar Sub-Division | Supply and delivery of Sluice Valve & Duck Foot Bend for Deriapur W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.¿ (Sl. No.3) | AE | JE3 | ORD/000763/2021-2022 | 378/BHM | 21/02/2022 | 15 | SSPR VALVE MANUFACTURING PVT LTD | 6.59 | 0 | 100
30 | Birbhum Division | Birbhum Sadar Sub-Division | Structural Bridge for 200 mm dia. pipe line at Bagdola village under Deriapur Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte. (Sl. No. - 09) | AE | JE3 | ORD/001007/2022-2023 | 221/BSSD | 21/09/2022 | 30 | M/S GOUTAM DAS | 4.01 | 0 | 100
31 | Birbhum Division | Bolpur Sub-Division | Construction of Switch Room Cum Chlorine Room 3.60mtr. x 3.00mtr. Size under Piped Water Supply Scheme for CHAUHATTA Water Supply Scheme at Labpur Block under Bolpur Sub-Division, P.H.E Deptt. within Birbhum Division P.H.E. Deptt.. ( Pump House No.- III). (Sl. No.: 02). | Assistant Engineer | JE1 | ORD/000085/2022-2023 | 256/BSD | 07/07/2022 | 60 | NAZIR HOSSAIN | 4.05 | 0 | 100
32 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of Chowhata Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHE Dte. | Assistant Engineer | JE1 | ORD/000155/2022-2023 | 1850/BHM | 30/08/2022 | 60 | JDJ ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 99.46 | 0 | 80
33 | Birbhum Division | Bolpur Sub-Division | Repairing of existing road and construction of new approach road towards O.H.R. in front of Head Works site of Chowhatta Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 03) | Assistant Engineer | JE1 | ORD/000583/2021-2022 | 458/BSD | 13/12/2021 | 30 | NAZIR HOSSAIN | 1.94 | 0 | 100
34 | Birbhum Division | Bolpur Sub-Division | Laying of Distribution Pipeline with FHTC work at Chowhatta village of Chowhatta Water Supply Scheme due to CMRO Grievance (Grievance Lodging Date: 15.12.2023, Complainant Name: Sk Indadul) in Chowhatta Mohodori - I Gram Panchayet under Bolpur Sub-Division within Birbhum Division, PHE. Dte | Assistant Engineer | JE1 | ORD/000618/2023-2024 | 166/BSD | 15/02/2024 | 7 | SK.RUHUL AMIN | 0.96 | 0 | 100
35 | Birbhum Division | Bolpur Sub-Division | Supply and delivery of 80mm dia Sluice Valves, including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Chowhatta Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 04). | Assistant Engineer | JE1 | ORD/000654/2021-2022 | 37/BSD | 02/02/2022 | 15 | MAKALI ENGINEERING CORPORATION | 0.65 | 0 | 100
36 | Birbhum Division | Bolpur Sub-Division | Construction of Switch Room Cum Chlorine Room 3.60 mtr. x 3.00 mtr. Size at 2nd Tube well site of CHAUHATTA Piped Water Supply Scheme at Labpur Block under Bolpur Sub-Division , P.H.E Dte. within Birbhum Division P.H.E. Dte. (Pump House No. - 2). (Sl. No.: 8) | Assistant Engineer | JE1 | ORD/000810/2021-2022 | 328/BSD | 01/09/2021 | 60 | NAZIR HOSSAIN | 4.09 | 0 | 100
37 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Dantura under Dantura Water Supply Scheme within Birbhum Division, PHE Dte¿ (Sl. No.5) | AE | JE2 | ORD/000209/2022-2023 | 2005/BHM | 15/09/2022 | 60 | PRAVAT SARKAR | 95.17 | 0 | 100
38 | Birbhum Division | Nalhati Sub-Division | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Dantura Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000589/2022-2023 | 1014/BHM | 30/03/2023 | 60 | NUR MOBINUL ISLAM | 64.15 | 0 | 70
39 | Birbhum Division | Nalhati Sub-Division | Sinking of 200mm 90 m. deep Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at Head Work site of Dantura Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000651/2021-2022 | 130/AE/NSD | 09/03/2022 | 30 | SUNIL RABI DAS | 4.8 | 0 | 100
40 | Birbhum Division | Nalhati Sub-Division | Construction of Pump House of 5.40mtr. X 3.6mtr. Size with sanitary and water supply arrangements at DANTURA PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000663/2021-2022 | 16/AE/NSD | 17/01/2022 | 60 | SHIB GANGA CONSTRUCTION | 4.99 | 0 | 100
41 | Birbhum Division | Rampurhat Sub-Division | Allied FHTC works along with laying pipe lines at diff mouzas within BARA-AKULPUR w/s Scheme under Rampurhat Sub- Division ,Birbhum Divition P.H.E. Dte | AE | JE1 | ORD/000001/2023-2024 | 1132/BHM | 10/04/2023 | 45 | ABUL HASNAT | 6.97 | 0 | 100
42 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bara Akalpur Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte. (Sl. No.2) | AE | JE1 | ORD/000007/2022-2023 | 748/BHM | 05/04/2022 | 1060 | TAPAS KUMAR SARKHEL | 80.34 | 0 | 100
43 | Birbhum Division | Rampurhat Sub-Division | Construction of Boundary Wall at 2nd Pump House Site for Bara- Akalpur PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000537/2021-2022 | 23/RSD | 04/01/2022 | 45 | INDRAJIT SAHA | 3.23 | 0 | 100
44 | Birbhum Division | Rampurhat Sub-Division | Laying of Rising main with DI K9 for inter connection & bypass arrangement of DI pipe line for Bara- Akalpur PWSS under Rampurhat sub division under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000578/2021-2022 | 26/RSD | 04/01/2022 | 30 | TAPAS KUMAR SARKHEL | 1.76 | 0 | 100
45 | Birbhum Division | Rampurhat Sub-Division | Laying of Distribution Main pipeline through crossing of PMGSY road within Pachim Panchberia mouza (in front of Kundala K.S.G.C High School) Eastern side by adopting Jack Pushing method for Bara Akulpur PWSS under Rampurhat Sub-Division, PHE Dte. | AE | JE1 | ORD/000673/2021-2022 | 113/RSD | 07/03/2022 | 15 | M/S UNIT CONSTRUCTION | 4.96 | 0 | 0
46 | Birbhum Division | Rampurhat Sub-Division | Laying of Distribution Main pipeline through crossing of PMGSY road within Pachim Panchberia mouza (in front of Kundala K.S.G.C High School) Western side by adopting Jack Pushing method for Bara Akulpur PWSS under Rampurhat Sub-Division, PHE Dte. | AE | JE1 | ORD/000674/2021-2022 | 114/RSD | 07/03/2022 | 15 | M/S UNIT CONSTRUCTION | 4.34 | 0 | 100
47 | Birbhum Division | Rampurhat Sub-Division | Laying of HDPE Pipe line for ,Kundala, Itahata etc mouzas for providing FHTC under Bara-Akalpur Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000684/2021-2022 | 126/RSD | 11/03/2022 | 30 | M/S UNIT CONSTRUCTION | 4.94 | 0 | 100
48 | Birbhum Division | Rampurhat Sub-Division | Laying of HDPE Pipe line for Akalpur, Gumta mouzas for providing FHTC under Bara Akalpur Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000687/2021-2022 | 127/RSD | 11/03/2022 | 30 | M/S UNIT CONSTRUCTION | 4.95 | 0 | 100
49 | Birbhum Division | Rampurhat Sub-Division | Laying of HDPE Pipe line for Bara Akalpur & Benegram mouzas for providing FHTC under Bara-Akalpur Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000689/2021-2022 | 128/RSD | 11/03/2022 | 30 | M/S UNIT CONSTRUCTION | 4.97 | 0 | 100
50 | Birbhum Division | Rampurhat Sub-Division | Laying of HDPE Pipe line on right side of Sainthia Sultanpur Road for Bara Akalpur, Gumta & Akalpur mouzas for providing FHTC under Bara-Akalpur Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000690/2021-2022 | 129/RSD | 11/03/2022 | 30 | M/S UNIT CONSTRUCTION | 4.98 | 0 | 100
51 | Birbhum Division | Rampurhat Sub-Division | Laying of HDPE 160 mm dia distribution line near Head work site in Pachim Panchberia mouza under Bara Akulpur water supply scheme under Rampurhat sub division under Birbhum Division PHE Dte. | AE | JE1 | ORD/000697/2021-2022 | 111/RSD | 07/03/2022 | 30 | ALPHA PROJECT | 4.68 | 0 | 100
52 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE | JE1 | RTOR000039/2021-2022 | 217/BHM | 02/02/2022 | 0 | Resource Division | 10.17 | 0 | 0
53 | Birbhum Division | Rampurhat Sub-Division | Balance Work for Construction of High Lift Pump House Construction of Ramp,PCC Apporch Road at CWR site for Puranagram Piped Water Supply Scheme under Rampurhat Sub-Division withen Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000533/2021-2022 | 19/RSD | 04/01/2022 | 30 | GOLAM RASUL | 3.88 | 0 | 100
54 | Birbhum Division | Rampurhat Sub-Division | Construction of Boundary Wall at Puranagram CWR Site for Puranagram Piped Water Supply Scheme under Md. Bazar block under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000625/2020-2021 | 20/RSD | 11/01/2021 | 60 | GOLAM RASUL | 4.05 | 0 | 100
55 | Birbhum Division | Rampurhat Sub-Division | Construction of Boundary Wall at Puranagram Piped Water Supply Scheme under under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000637/2020-2021 | 1636/BHM | 15/12/2020 | 60 | GOLAM RASUL | 4.27 | 0 | 35
56 | Birbhum Division | Rampurhat Sub-Division | ¿Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Puratangram Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿(Sl. No.14) | AE | JE3 | ORD/000659/2020-2021 | 134/BHM | 25/01/2021 | 60 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 82.45 | 0 | 100
57 | Birbhum Division | Rampurhat Sub-Division | Additional Supply of UPVC Pipe & strainer 200 mm dia for Sinking of 09 Nos 200mm dia. X 30 mtr deep River bed Tube Well including trial bore for Puranagram Piped Water Supply Scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000666/2021-2022 | 118/RSD | 11/03/2022 | 30 | RUBAL CONSTRACTION | 1.48 | 0 | 0
58 | Birbhum Division | Birbhum Sadar Sub-Division | Trial Bore and Sinking of 200 mm dia. tubewell (02 no.) 170 m. Deep fitted with M.S.E.R.W. Housing pipe and Fibre Glass Strainer on the river bank of Mayurakshi for the Augmentation of Ahmedpur Piped Water Supply Scheme under Birbhum Sadar Sub-Division PHE Dte. with Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000119/2023-2024 | 1981/BHM | 05/06/2023 | 524 | NEEL ENTERPRISE | 6.94 | 0 | 100
59 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 700cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Ahmedpur W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000263/2023-2024 | 1103/BHM | 10/04/2023 | 275 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 152 | 0 | 20
60 | Birbhum Division | Birbhum Sadar Sub-Division | Laying distribution system including FHTC for proposed augmentation scheme for Ahmedpur Piped Water Supply Scheme, Sainthia Block, under Birbhum Division, PHE Dte. (Sl. No.6) | AE,Assistant Engineer | JE,Junior Engineer | ORD/000358/2022-2023 | 1158/BHM | 23/05/2022 | 496 | PASCON | 445.38 | 0 | 95
61 | Birbhum Division | Birbhum Sadar Sub-Division | Supply and delivery of Sluice Valve for Augmentation of Ahmadpur W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-1) | AE,Assistant Engineer | JE,Junior Engineer | ORD/000414/2023-2024 | 4292/BHM | 10/11/2023 | 30 | MAKALI ENGINEERING CORPORATION | 9 | 0 | 100
62 | Birbhum Division | Birbhum Sadar Sub-Division | Continuation work order for Supply and delivery of Sluice Valve for Augmentation of Ahmadpur W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-1) | AE,Assistant Engineer | JE,Junior Engineer | ORD/000468/2023-2024 | 500/BHM | 02/02/2024 | 30 | MAKALI ENGINEERING CORPORATION | 9 | 0 | 100
63 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000020/2022-2023 | 913/BHM | 26/04/2022 | 0 | Resource Division | 4.97 | 0 | 0
64 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000193/2023-2024 | 3274/BHM | 27/07/2023 | 0 | Resource Division | 0.34 | 0 | 0
65 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Ahmedpur water supply scheme under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000008/2023-2024 | 717/Bol.MD | 19/04/2023 | 45 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 27.19 | 0 | 0
66 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at PASCHIM NAOPARA, PHULUR & PURBA SIUR its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000189/2023-2024 | 2262/BHM | 12/07/2023 | 993 | B RAI CONSTRUCTION COMPANY | 1402.44 | 0 | 45
67 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000066/2022-2023 | 1414/BHM | 24/04/2023 | 0 | Resource Division | 18.66 | 0 | 0
68 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Purba Siur PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/02242/2023-2024 | BP-2023-24-317 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.95 | 0 | 0
69 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Purba Siur PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/02243/2023-2024 | BP-2023-24-318 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.77 | 0 | 0
70 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Purba Siur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000411/2023-2024 | 2084/Bol.MD | 22/08/2023 | 802 | STANDARD ELECTRICALS | 29.66 | 0 | 80
71 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Purba Siur PWSS under Sainthia Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | AE,Assistant Engineer | JE,Junior Engineer | ORD/001242/2023-2024 | 530/BOL.MD | 14/03/2024 | 307 | RN ELECTRO POWER PVT. LTD. | 7.54 | 0 | 100
72 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Dalima, Kahinagar & Dumurgram and its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000080/2023-2024 | 1423/BHM | 25/04/2023 | 1090 | AKASH CONSTRUCTION | 1377.29 | 0 | 16
73 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000016/2023-2024 | 1438/BHM | 25/04/2023 | 0 | Resource Division | 36.19 | 0 | 0
74 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Dalima PWSS at Murarai - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000867/2023-2024 | 3285/BOL.MD | 29/09/2023 | 550 | S.K.ELECTRICALS | 30.88 | 0 | 70
75 | Birbhum Division | Birbhum Division | Different works related to water supply scheme at ANDHARGRAM & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000031/2023-2024 | 1191/BHM | 12/04/2023 | 477 | NISITH BARAN SARKAR | 255.87 | 0 | 65
76 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | RTOR000030/2023-2024 | 1519/BHM | 26/04/2023 | 0 | Resource Division | 17.4 | 0 | 0
77 | Bolpur Mechanical | Birbhum Division | WBSEDCL quotation for Andhargram ws scheme | AE(HQ),Assistant Engineer | JE,Junior Engineer | BILL/01447/2023-2024 | BP-23-24-173 | 07/12/2023 | 0 | WBSEDCL | 4.58 | 0 | 0
78 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR ANDHARGRAM P H NO 2 WS SCHEME | AE(HQ),Assistant Engineer | JE,Junior Engineer | BILL/01450/2023-2024 | BP-23-24-174 | 07/12/2023 | 0 | WBSEDCL | 3.65 | 0 | 0
79 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Andhargram PWSS at Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000291/2023-2024 | 1497/Bol.MD | 17/07/2023 | 60 | WEST BENGAL ENGINEERING CO. | 27.21 | 0 | 80
80 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000033/2023-2024 | 1442/BHM | 25/04/2023 | 0 | Resource Division | 16.44 | 0 | 0
81 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Dakshin Kashila P/H-II Scheme in Murarai CCC under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00086/2024-2025 | BP-2024-2025-18 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.92 | 0 | 0
82 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Dakshin Kashila P/H-I Scheme in Murarai CCC under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00087/2024-2025 | BP-2024-2025-19 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.03 | 0 | 0
83 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for DAKSHIN KASHILA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000887/2023-2024 | 3290/Bol.MD | 29/09/2023 | 550 | S.K.ELECTRICALS | 30.47 | 0 | 65
84 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at MADHURA & PAIKPARA PWSS its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000045/2023-2024 | 1173/BHM | 12/04/2023 | 995 | SK ABDUL HALIM | 921.73 | 0 | 90
85 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000052/2023-2024 | 1471/BHM | 25/04/2023 | 0 | Resource Division | 113.39 | 0 | 0
86 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR MODHURA P H NO 2 | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/01712/2023-2024 | BP-23-24-238 | 29/01/2024 | 0 | WBSEDCL | 0.23 | 0 | 0
87 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR MODHURA W S P H NO I WS SCHEME | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/01778/2023-2024 | BP-23-24-239 | 29/01/2024 | 0 | WBSEDCL | 2.79 | 0 | 0
88 | Bolpur Mechanical | Nalhati Sub-Division | Operation and Guarding of pumping machinery and others at Madhura Piped water supply scheme,(Pump House No-II)Block; Nalhati-I) under Bolpur Mechanical Division,P.H.E Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000825/2024-2025 | 1078./AE-III | 29/07/2024 | 31 | INDRANI ENTERPRISE | 0.3 | 0 | 0
89 | Bolpur Mechanical | Nalhati Sub-Division | ,Operation and Guarding of pumping machinery and others at Madhura Piped Water supply Scheme (Pump House No-I(Block- Nalhati-I) under Bolpur Mechanical Division,P.H.E Dte | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000829/2024-2025 | 1077./AE-III | 29/07/2024 | 31 | INDRANI ENTERPRISE | 0.3 | 0 | 0
90 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for MADHURA piped water supply scheme, Nalhati - I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000932/2023-2024 | 3562/BOL.MD | 04/12/2023 | 60 | INDRANI ENTERPRISE | 27.43 | 0 | 80
91 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
92 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
93 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at NETURI, PAIKPARA & PAKURIA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000256/2023-2024 | 3441/BHM | 03/08/2023 | 940 | SHREE J.M. CONSTRUCTION | 1236.08 | 0 | 54
94 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000063/2022-2023 | 1418/BHM | 24/04/2023 | 0 | Resource Division | 11.04 | 0 | 0
95 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR NETURI WS SCHEME | AE,Assistant Engineer | JE,Junior Engineer | BILL/00700/2023-2024 | BP-2023-2024-60 | 02/08/2023 | 0 | WBSEDCL | 4.86 | 0 | 0
96 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR NETURI WS SCHEME P.H NO.I | AE,Assistant Engineer | JE,Junior Engineer | BILL/00704/2023-2024 | BP-2023-2024-59 | 02/08/2023 | 0 | WBSEDCL | 4.95 | 0 | 0
97 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Neturi & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000785/2022-2023 | 322/BOL.M.D | 27/03/2023 | 677 | ABHISEK ENGTNEERING CONCERN | 28.92 | 0 | 35
98 | Central Drilling | Birbhum Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well(250mm X 200mmx 150mtrs Depth) by utilising Departmental Machineries for Neturi W/S scheme (TW-I), Sainthia Block under Birbhum District , CDD,PHE DTE. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000277/2022-2023 | 1134/CDD | 04/11/2022 | 30 | C.M. ENTERPRISE | 10.99 | 0 | 0
99 | Central Drilling | Birbhum Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR NETURI W/S SCH (TW-II), SAINTHIA BLOCK, UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000343/2022-2023 | 1135/CDD | 04/11/2022 | 30 | C.M. ENTERPRISE | 10.99 | 0 | 0
100 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at LACHHIATOR, DAKSHINGRAM, SONJ & SHIBGRAM and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000385/2023-2024 | 4142/BHM | 19/10/2023 | 805 | B RAI CONSTRUCTION COMPANY | 2003.84 | 0 | 60
101 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Sonj) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000832/2022-2023 | 327/RSD | 08/09/2022 | 90 | ENVIROTECH SOLUTIONS | 3.29 | 0 | 100
102 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Sonj) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000833/2022-2023 | 428/RSD | 09/11/2022 | 90 | ENVIROTECH SOLUTIONS | 2.5 | 0 | 100
103 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000072/2023-2024 | 1465/BHM | 25/04/2023 | 0 | Resource Division | 51.71 | 0 | 0
104 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000207/2023-2024 | 207/BHM | 22/01/2024 | 0 | Resource Division | 6.16 | 0 | 0
105 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR SONJPIPED WS SCHEME PH NO.I | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01882/2023-2024 | BP-23-24-283 | 22/02/2024 | 0 | WBSEDCL | 3.74 | 0 | 0
106 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR SONJ W/S SCHEME PH-2 | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02463/2023-2024 | BP-24-25-02 | 09/04/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
107 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR SONJ W/S SCHEME PH-3 | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02466/2023-2024 | BP-24-25-01 | 09/04/2024 | 0 | WBSEDCL | 2.8 | 0 | 0
108 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Sonj PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000725/2023-2024 | 3472/Bol.MD | 07/11/2023 | 60 | HINDOL ROY | 57.29 | 0 | 40
109 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Sonj PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/001218/2023-2024 | 403/Bol.MD | 07/03/2024 | 45 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 24.55 | 0 | 80
110 | Birbhum Division | Nalhati Sub-Division | Restoration of Roads, pucca drain including Jack pushing & Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Mathkalitha piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000047/2025-2026 | 1508/BHM | 23/05/2025 | 90 | M/S GOUTAM DAS | 70.96 | 0 | 10
111 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Majhkaltia, Sahira & KANAPIUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000075/2023-2024 | 1348/BHM | 20/04/2023 | 835 | M/S GOUTAM DAS | 1594.34 | 0 | 28
112 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000015/2023-2024 | 1431/BHM | 25/04/2023 | 0 | Resource Division | 13.69 | 0 | 0
113 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR MAJHKALITHA P H NO 2 | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01709/2023-2024 | BP-23-24-161 | 29/01/2024 | 0 | WBSEDCL | 0.23 | 0 | 0
114 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR MAJHKALITHA P H NO.I WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01784/2023-2024 | BP-23-24-246 | 29/01/2024 | 0 | WBSEDCL | 3.91 | 0 | 0
115 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR MAJHKALITHA PUMP HOUSE NO-I | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02130/2023-2024 | BP-2023-24-293 | 07/03/2024 | 0 | WBSEDCL | 2.08 | 0 | 0
116 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Majhkalitha PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000909/2023-2024 | 3539/BOL.MD | 30/11/2023 | 60 | RUBY ENTERPRISE | 29.28 | 0 | 0
117 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at BHAGABATIPUR & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000003/2023-2024 | 1082/BHM | 06/04/2023 | 636 | ZEBA CONSTRUCTION | 253.52 | 0 | 100
118 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Bhagabatipur) Water Supply Scheme under Mayureswar-I Development Block | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000621/2022-2023 | 202/RSD | 08/06/2022 | 90 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 100
119 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000114/2023-2024 | 1506/BHM | 25/04/2023 | 0 | Resource Division | 10.66 | 0 | 0
120 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000202/2023-2024 | 209/BHM | 22/01/2024 | 0 | Resource Division | 3.34 | 0 | 0
121 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION MONEY FOR BHAGABATIPUR WS SCHEME | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/00722/2023-2024 | BP-2023-2024-76 | 24/08/2023 | 0 | WBSEDCL | 3.28 | 0 | 0
122 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR BHAGABATIPUR WS SCHEME | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/01241/2023-2024 | BP-23-24-121 | 12/10/2023 | 0 | WBSEDCL | 3.64 | 0 | 0
123 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR BHAGABATIPUR PUMP HOUSE NO-II | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/02078/2023-2024 | BP-2023-24-289 | 04/03/2024 | 0 | WBSEDCL | 0.9 | 0 | 0
124 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Bhagabatipur PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000348/2023-2024 | 1746/Bol.MD | 27/07/2023 | 60 | P. K. ENGINEERING | 43.95 | 0 | 30
125 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Delivery of Pumping Machinery for Bhagabatipur water supply scheme Block Mayureswar ¿I under Bolpur Mechanical Division PHE. Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001317/2023-2024 | 607/AE-III | 27/03/2024 | 7 | P. K. ENGINEERING | 1.49 | 0 | 100
126 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at GAYTHA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under Birbhum Division, PHE Dte | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000066/2023-2024 | 1311/BHM | 19/04/2023 | 275 | RAJ ASSOCIATES | 226.66 | 0 | 65
127 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Gaytha) Water Supply Scheme under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000630/2022-2023 | 229/RSD | 24/06/2022 | 45 | ECO CARE | 3.63 | 0 | 100
128 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000130/2023-2024 | 1544/BHM | 26/04/2023 | 0 | Resource Division | 13.99 | 0 | 0
129 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000222/2023-2024 | 224/BHM | 24/01/2024 | 0 | Resource Division | 4 | 0 | 0
130 | Bolpur Mechanical | Rampurhat Sub-Division | wbsedcl quotation money for gaytha p.h.no.1 pwss | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/01431/2023-2024 | BP-23-24-152 | 04/12/2023 | 0 | WBSEDCL | 2.74 | 0 | 0
131 | Bolpur Mechanical | Rampurhat Sub-Division | wbsedcl quotation money for gaytha p.h.no.2 pwss | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/01432/2023-2024 | BP-23-24-151 | 04/12/2023 | 0 | WBSEDCL | 2.36 | 0 | 0
132 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Gaytha PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000001/2024-2025 | 684./AE-III | 08/04/2024 | 14 | WEST BENGAL ENGINEERING CO. | 1.58 | 0 | 100
133 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of 16 mm² x 3 core Al.Ar. Cable of Gaytha water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. " | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000459/2024-2025 | 1307./AE-III | 28/08/2024 | 7 | SINHA ELECTRICALS | 4.87 | 0 | 100
134 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Gaytha PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000480/2023-2024 | 2232/Bol.MD | 12/09/2023 | 597 | WEST BENGAL ENGINEERING CO. | 44.34 | 0 | 40
135 | Bolpur Mechanical | Rampurhat Sub-Division | Supply delivery of voltage correction device at head work site of Gaytha PWSS in the district of Birbhum, under P.H.E. Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000535/2024-2025 | 3797/BOL.MD | 12/09/2024 | 30 | SARKAR ELECTRICAL | 6.27 | 0 | 0
136 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery ofSluice Valve & Non-Return Valve for Gaytha water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000603/2024-2025 | 1458./AE-III | 09/09/2024 | 7 | B. P. TRADING CORPORATION | 2.83 | 0 | 100
137 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
138 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000402/2023-2024 | 4139/BHM | 18/10/2023 | 896 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 0 | 60
139 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | RTOR000086/2022-2023 | 1358/BHM | 24/04/2023 | 0 | Resource Division | 119 | 0 | 0
140 | Bolpur Mechanical | Bolpur Sub-Division | WBSEDCL QUOTATION FOR Ikshudhara piped water supply scheme. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | BILL/01592/2023-2024 | BP-23-24-220 | 15/01/2024 | 0 | WBSEDCL | 6.17 | 0 | 0
141 | Bolpur Mechanical | Bolpur Sub-Division | Providing Electro-mechanical accessories and others for Ikshudhara & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000482/2023-2024 | 2239/BOL.MD. | 13/09/2023 | 627 | QUAZI NOZRUL ISLAM | 80.69 | 0 | 85
142 | Bolpur Mechanical | Bolpur Sub-Division | Supply and delivery of Starter and other materials for ikshudhara water supply scheme under Bolpur Mechanical Division PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000544/2024-2025 | 3803/BOL.MD | 12/09/2024 | 20 | STANDARD ELECTRICALS | 6.54 | 0 | 100
143 | Bolpur Mechanical | Bolpur Sub-Division | Supply and delivery of chlorinator dosing pump for ikshudhara Water Supply Project under Bolpur Mechanical Divn. P.H.E. Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000549/2024-2025 | 3818/BOL.MD | 18/09/2024 | 20 | M/S. UTTAM KUMAR CHATTERJEE | 3.24 | 0 | 100
144 | Bolpur Mechanical | Bolpur Sub-Division | Supply & delivery of submersible cable accessories at ikshudhara Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000557/2024-2025 | 3821/BOL.MD | 18/09/2024 | 20 | MITRA ENTERPRISE | 2.8 | 0 | 100
145 | Bolpur Mechanical | Bolpur Sub-Division | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/001233/2024-2025 | 4216/BOL.MD | 23/10/2024 | 200 | SATYAJIT GHOSH | 0.57 | 0 | 100
146 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
147 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
148 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at NABAGRAM, SAHAPUR & SHASPUR and its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000268/2023-2024 | 3522/BHM | 11/08/2023 | 821 | SUNIL RABI DAS | 1157.77 | 0 | 40
149 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Shaspur) Water Supply Scheme under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000623/2022-2023 | 204/RSD | 13/06/2022 | 45 | ECO CARE | 4.73 | 0 | 100
150 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000132/2023-2024 | 1555/BHM | 26/04/2023 | 0 | Resource Division | 94.6 | 0 | 0
151 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000226/2023-2024 | 220/BHM | 24/01/2024 | 0 | Resource Division | 4 | 0 | 0
152 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Shaspur TW No-I (Block-Rampurhat-II) | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02193/2023-2024 |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.73 | 0 | 0
153 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Shaspur TW No-II (Block-Rampurhat-II) | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02225/2023-2024 |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.87 | 0 | 0
154 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR SHASPUR TW-1 | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02241/2023-2024 | BP-2023-24-309 | 18/03/2024 | 0 | WBSEDCL | 2.73 | 0 | 0
155 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR SHASPUR TW-II | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02250/2023-2024 | BP-2023-24-310 | 18/03/2024 | 0 | WBSEDCL | 2.87 | 0 | 0
156 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Shaspur PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000483/2023-2024 | 2234/Bol.MD | 12/09/2023 | 658 | SINHA ELECTRICALS | 45.39 | 0 | 90
157 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of UPVC Column pipes at store for Sahapur water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000520/2024-2025 | 1452./AE-III | 09/09/2024 | 114 | S.B ENTERPRISE | 2.69 | 0 | 100
158 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
159 | Birbhum Division | Nalhati Sub-Division | Extension of pipeline (DI & HDPE) with FHTC, Restoration of Roads including Augur boring along with supply of sluice valve with construction of valve chamber for Nawapara piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000193/2025-2026 | 2143/BHM | 19/08/2025 | 90 | APORUPA CONSTRUCTION | 54.08 | 0 | 0
160 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at NAWAPARA & PRASADPUR and its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000207/2023-2024 | 3257/BHM | 26/07/2023 | 275 | MANASH GHOSH | 866.09 | 0 | 5
161 | Birbhum Division | Nalhati Sub-Division | Preparation and submission of DPR for (Nawapara) Water Supply Scheme under Nalhati-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000758/2022-2023 | 231/AE/NSD | 21/04/2022 | 45 | MS SOBHA AND CO | 4.6 | 0 | 100
162 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000111/2023-2024 | 1502/BHM | 25/04/2023 | 0 | Resource Division | 65.11 | 0 | 0
163 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR NOAPARA P H .II WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01600/2023-2024 | BP-23-24-234 | 29/01/2024 | 0 | WBSEDCL | 3.42 | 0 | 0
164 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR NOAPARA WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01601/2023-2024 | BP-23-24-233 | 15/01/2024 | 0 | WBSEDCL | 4.14 | 0 | 0
165 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Nawpara PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000463/2023-2024 | 2137/Bol.MD | 25/08/2023 | 676 | M. S. ENTERPRISE | 45.52 | 0 | 70
166 | Bolpur Mechanical | Nalhati Sub-Division | Supply and Delivery of Volage correction device, Cetrifugal Pumping Machineries and allied accessories for Nawapara PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000521/2024-2025 | 3780/BOL.MD | 12/09/2024 | 111 | S.K.ELECTRICALS | 33.77 | 0 | 50
167 | Birbhum Division | Nalhati Sub-Division | Restoration charges for laying of PHE pipeline from Chainage 9.50 KM (Barsliapukur) to 12.24 KM (end point) of Murarai Mitrapur Road under Rampurhat Highrway Sub-Division of Birbhunr Highrvay Division-1. in the District of Bir.bhurn during the year 2024-25 | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00737/2024-2025 | BP-2024-25-223 | 12/09/2024 | 0 | EXECUTIVE ENGINEER BIRBHUM HIGHWAY DIVISION-I P.W (ROADS) DIRECTORATE | 9.82 | 0 | 0
168 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at MITRAPUR & its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000277/2023-2024 | 3597/BHM | 21/08/2023 | 742 | SUNIL RABI DAS | 635.29 | 0 | 55
169 | Birbhum Division | Nalhati Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
170 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000012/2023-2024 | 1432/BHM | 25/04/2023 | 0 | Resource Division | 40.94 | 0 | 0
171 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000045/2023-2024 | 1496/BHM | 25/04/2023 | 0 | Resource Division | 40.94 | 0 | 0
172 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Mitrapur P/H-I Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00150/2024-2025 | BP-2024-2025-77 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.64 | 0 | 0
173 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for Mitrapur Water Supply Scheme P/H-II in Paikar CCC under Bolpur Mechanical division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00829/2024-2025 | BP-24-25-179 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.82 | 0 | 0
174 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Mitrapur PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000945/2023-2024 | 3306/BOL.MD | 29/09/2023 | 703 | MITRA ENTERPRISE | 30.25 | 0 | 80
175 | Birbhum Division | Birbhum Sadar Sub-Division | Submission of Wayleave/Track crossing proposal in IR-RBCS station from Dubrajpur to Chinpai (38-39) KM | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00166/2024-2025 | BP-2024-25-67 | 30/05/2024 | 0 | EASTERN RAILWAY | 5.35 | 0 | 0
176 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at MODAPA & its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000063/2023-2024 | 1303/BHM | 19/04/2023 | 743 | J.P.ENTERPRISE | 280.53 | 0 | 78
177 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000080/2022-2023 | 1399/BHM | 24/04/2023 | 0 | Resource Division | 12.63 | 0 | 0
178 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOIT ION FOR MODAPA PUMP HOUSE NO I | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01826/2023-2024 | BP-23-24-263 | 06/02/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
179 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDL QUOTATION FOR MODAPA PUMP HOUSEN NO II | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01827/2023-2024 | BP-23-24-262 | 06/02/2024 | 0 | WBSEDCL | 4.42 | 0 | 0
180 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Modapa & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/001381/2023-2024 | 2242/BOL.MD | 13/09/2023 | 60 | SWAPAN ENTERPRISE | 10.16 | 0 | 100
181 | Birbhum Division | Bolpur Sub-Division | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000084/2024-2025 | 1948/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0
182 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for KADOA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000655/2022-2023 | 155/BSD | 18/04/2022 | 180 | APEX ENGINEERING | 3.52 | 0 | 100
183 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000012/2024-2025 | 2388/BHM | 27/08/2024 | 0 | Resource Division | 6.4 | 0 | 0
184 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000154/2023-2024 | 1595/BHM | 26/04/2023 | 0 | Resource Division | 28.19 | 0 | 0
185 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Kadoa PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001124/2024-2025 | 329/BOL.MD | 19/02/2025 | 239 | OSMAN SEKH | 76.29 | 0 | 40
186 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
187 | Birbhum Division | Rampurhat Sub-Division | Different works related to Water Supply Scheme at KHAGRA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000158/2023-2024 | 2066/BHM | 08/06/2023 | 938 | MALLICK CONSTRUCTION | 243.5 | 0 | 65
188 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Khagra) Water Supply Scheme under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000564/2022-2023 | 186/RSD | 10/05/2022 | 45 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 100
189 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000046/2023-2024 | 1536/BHM | 26/04/2023 | 0 | Resource Division | 10.76 | 0 | 0
190 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000211/2023-2024 | 201/BHM | 22/01/2024 | 0 | Resource Division | 2.03 | 0 | 0
191 | Bolpur Mechanical | Rampurhat Sub-Division | New Power connection at Khagra (PH-II) PWSS, under Bolpur Mechanical Division, P.H.e.Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00075/2024-2025 | BP-2024-2025-27 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.88 | 0 | 0
192 | Bolpur Mechanical | Rampurhat Sub-Division | New Power connection at Khagra PWSS (P/H-I) under Mayureswar-II Block | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00129/2024-2025 | BP-2024-2025-56 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.9 | 0 | 0
193 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of different electrical accessories at Khagra Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000449/2024-2025 | 1300./AE-III | 27/08/2024 | 7 | QUAZI NOZRUL ISLAM | 2.96 | 0 | 100
194 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of submersible Pumping Machineries & cable at Khagra Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000605/2024-2025 | 1455./AE-III | 09/09/2024 | 7 | PRADIP KUMAR DHABAL | 2.83 | 0 | 100
195 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Khagra PWSS at Mayurreswar - II Block under Bolpur Mechanical Division PHE Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000841/2023-2024 | 3280/BOL.MD | 29/09/2023 | 611 | QUAZI NOZRUL ISLAM | 44.01 | 0 | 40
196 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at BIRCHANDRAPUR, ASURLAYA, BARATURIGRAM & KANAIPUR and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000471/2023-2024 | 505/BHM | 05/02/2024 | 603 | B RAI CONSTRUCTION COMPANY | 2071.77 | 0 | 20
197 | Birbhum Division | Rampurhat Sub-Division | Preparation & Submission of DPR for (Asuralay) Water Supply Scheme under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000561/2022-2023 | 158/RSD | 18/04/2022 | 90 | ENVIROTECH SOLUTIONS | 4.65 | 0 | 100
198 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000121/2023-2024 | 1526/BHM | 26/04/2023 | 0 | Resource Division | 17.89 | 0 | 0
199 | Bolpur Mechanical | Rampurhat Sub-Division | New service connection at Asuralaya PH-I PWSS under Bolpur Mechanical Division, P.H.E Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/00839/2024-2025 | BP-24-25-189 | 24/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.58 | 0 | 0
200 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Asuralya PWSS, P.H- II under Mollarpur CCC (Mayureswar-I Block) | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/00958/2024-2025 | BP-2024-2025-25 | 18/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.6 | 0 | 0
201 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Asuralaya PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000727/2023-2024 | 3474/Bol.MD | 07/11/2023 | 582 | S. S. ENTERPRISES | 43.56 | 0 | 50
202 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Asuralaya PWSS under Mayureswar - I Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001232/2023-2024 | 518/BOL.MD | 14/03/2024 | 60 | M/S. YOUTH ENGINEERS' ENTERPRISE | 7.62 | 0 | 60
203 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at DELORA Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000022/2023-2024 | 1192/BHM | 12/04/2023 | 1082 | M/S SANDIP CONSTRUCTION | 278.71 | 0 | 5
204 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | RTOR000077/2023-2024 | 1459/BHM | 25/04/2023 | 0 | Resource Division | 12.35 | 0 | 0
205 | Bolpur Mechanical | Bolpur Sub-Division | New Power Connection at Delora PWSS under Bolpur mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | BILL/00414/2024-2025 | BP-24-25-130 | 29/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.84 | 0 | 0
206 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
207 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at NOHANA & its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000093/2023-2024 | 1643/BHM | 02/05/2023 | 276 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 266.53 | 0 | 30
208 | Birbhum Division | Birbhum Sadar Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for NOHANA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE,Assistant Engineer | JE,Junior Engineer | ORD/000775/2022-2023 | 236/BSD | 17/06/2022 | 90 | M/S R DUTTA & CO. | 4.99 | 0 | 100
209 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000059/2022-2023 | 1412/BHM | 24/04/2023 | 0 | Resource Division | 10.86 | 0 | 0
210 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Nohana and Adjoining Moujas W/S scheme, PH-I, Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/00173/2024-2025 | BP-24-25-88 | 19/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.93 | 0 | 0
211 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Nohana and Adjoining Moujas W/S scheme, PH-II, Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/00175/2024-2025 | BP-24-25-89 | 19/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.29 | 0 | 0
212 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Quotation for new service connection at Nohana PWSS, P/H- II under Illambazar CCC | AE,Assistant Engineer | JE,Junior Engineer | BILL/01020/2024-2025 | BP-24-25-272 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.74 | 0 | 0
213 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Nohana & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000531/2023-2024 | 2172/Bol.MD | 01/09/2023 | 519 | M/S. UTTAM KUMAR CHATTERJEE | 14.97 | 0 | 80
214 | Birbhum Division | Rampurhat Sub-Division | Different works related to Water Supply Scheme at SATPALSA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000399/2023-2024 | 4135/BHM | 18/10/2023 | 809 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 394.79 | 0 | 35
215 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Satpalsa) Water Supply Scheme under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000625/2022-2023 | 211/RSD | 16/06/2022 | 45 | ENVIROTECH SOLUTIONS | 4.29 | 0 | 100
216 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000055/2023-2024 | 1454/BHM | 25/04/2023 | 0 | Resource Division | 17.5 | 0 | 0
217 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000214/2023-2024 | 232/BHM | 24/01/2024 | 0 | Resource Division | 5.5 | 0 | 0
218 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Satpalsa PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000838/2023-2024 | 3277/Bol.MD | 29/09/2023 | 60 | GHOSH ENGINEERING SYNDICATE | 44.05 | 0 | 40
219 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at BENAGRAM PIPED WATER SUPPLY SCHEME (TSM/015486) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000142/2024-2025 | 2428/BHM | 29/08/2024 | 365 | M/S. A K ENTERPRISE | 355.96 | 0 | 0
220 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BENAGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000645/2022-2023 | 171/BSD | 27/04/2022 | 90 | RADIANT | 4 | 0 | 100
221 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000038/2024-2025 | 2486/BHM | 03/09/2024 | 0 | Resource Division | 8.22 | 0 | 0
222 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000065/2023-2024 | 1469/BHM | 25/04/2023 | 0 | Resource Division | 37.92 | 0 | 0
223 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Benagram WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000961/2024-2025 | 4530/BOL.MD | 20/12/2024 | 120 | MENAKA ENTERPRISE | 73 | 0 | 0
224 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
225 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of Danghara under Danghara Water Supply Scheme within Birbhum Division, PHE Dte¿ (Sl. No.4) | AE | JE2 | ORD/000208/2022-2023 | 2002/BHM | 15/09/2022 | 60 | NUR MOBINUL ISLAM | 70.94 | 0 | 100
226 | Birbhum Division | Nalhati Sub-Division | Extension of distribution Pipe line including FHTC Work along with restoration of road of Danghara Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte (Sl.No.4) | AE | JE2 | ORD/000559/2022-2023 | 874/BHM | 21/03/2023 | 60 | QUAZI SIRAJUL ISLAM. | 29.28 | 0 | 50
227 | Birbhum Division | Nalhati Sub-Division | Sinking of 200mm 90 m. deep Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at Head Work site of Danghara Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000652/2021-2022 | 131/AE/NSD | 09/03/2022 | 30 | QUAZI SIRAJUL ISLAM. | 4.8 | 0 | 100
228 | Birbhum Division | Nalhati Sub-Division | Construction of Pump House of 5.40mtr. x 3.6mtr. size with sanitary and water supply arrangements at DHANGHARA PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000899/2021-2022 | 17/AE/NSD | 17/01/2022 | 60 | QUAZI SIRAJUL ISLAM. | 4.99 | 0 | 100
229 | Birbhum Division | Nalhati Sub-Division | Jack pushing & Augur boring along with restoration of Roads, extension of pipeline (DI & HDPE) etc including all allied works for Shitalgram piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000669/2024-2025 | 798/BHM | 24/03/2025 | 360 | M/S S. CHOUDHURY | 38.07 | 0 | 70
230 | Birbhum Division | Nalhati Sub-Division | Preparation and submission of DPR for (Shitalgram) Water Supply Scheme under Nalhati-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000760/2022-2023 | 233/AE/NSD | 21/04/2022 | 45 | MS SOBHA AND CO | 4.14 | 0 | 100
231 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000174/2023-2024 | 2175/BHM | 23/06/2023 | 0 | Resource Division | 19.69 | 0 | 0
232 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR SHITALGRAM WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01605/2023-2024 | BP-23-24-235 | 29/01/2024 | 0 | WBSEDCL | 3.62 | 0 | 0
233 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Shitalgram PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000700/2023-2024 | 2109/Bol.MD | 22/08/2023 | 60 | HINDOL ROY | 45.44 | 0 | 50
234 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at RAJPUR & its adjoining mouzas water supply scheme within RAJNAGAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000072/2023-2024 | 1346/BHM | 20/04/2023 | 796 | MUSKAN ENTERPRISE | 410.62 | 0 | 25
235 | Birbhum Division | Birbhum Sadar Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
236 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000195/2023-2024 | 3283/BHM | 27/07/2023 | 0 | Resource Division | 0.51 | 0 | 0
237 | Bolpur Mechanical | Birbhum Sadar Sub-Division | QUOTATION FOR RAJPUR PWSS AT RAJNAGAR BLOCK | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/00010/2024-2025 | BP-24-25-08 | 09/04/2024 | 0 | WBSEDCL | 9.47 | 0 | 0
238 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply & delivery of Al.Ar cable for Rajpur Piped water supply scheme under Bolpur Mechanical Division(Block-Rajnagar), PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000556/2024-2025 | 1477./AE-III | 11/09/2024 | 7 | M. S. ENTERPRISE | 4.31 | 0 | 100
239 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Rajpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000906/2023-2024 | 3550/Bol.MD | 01/12/2023 | 647 | GLACIER ENGINEERING CO. | 87.05 | 0 | 89
240 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Rajpur PWSS under Rajnagar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/001258/2023-2024 | 531/BOL.MD | 14/03/2024 | 60 | NITESH MANAGEMENT | 7.58 | 0 | 60
241 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | RTOR000165/2023-2024 | 1623/BHM | 28/04/2023 | 0 | Resource Division | 42.21 | 0 | 0
242 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for HARIDASPUR piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000292/2023-2024 | 1498/Bol.MD | 17/07/2023 | 60 | C M ENTERPRISE | 41.17 | 0 | 40
243 | Bolpur Mechanical | Birbhum Division | Supply and delivery of Column pipe and other at Haridaspur water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000412/2023-2024 | 950/AE-III | 04/07/2023 | 7 | J.K.ENGINEERING CO | 0.97 | 0 | 100
244 | Bolpur Mechanical | Birbhum Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Haridaspur PWSS under Md. Bazar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/001246/2023-2024 | 523/BOL.MD | 14/03/2024 | 60 | S. K. ENTERPRISE | 7.6 | 0 | 100
245 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at MAHESWARPUR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 | ORD/000037/2023-2024 | 1133/BHM | 10/04/2023 | 275 | GUPTA CONSTRUCTION | 339.98 | 0 | 1
246 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for MAHESHWARPUR Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer | JE1 | ORD/001138/2021-2022 | 108/BSD | 21/03/2022 | 90 | M/S R DUTTA & CO. | 2.86 | 0 | 100
247 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE1 | RTOR000118/2023-2024 | 1584/BHM | 26/04/2023 | 0 | Resource Division | 20.97 | 0 | 0
248 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer | JE1 | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
249 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at BANIOR & its adjoining mouzas water supply scheme within NALHATI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000332/2023-2024 | 3777/BHM | 08/09/2023 | 724 | TUSHAR KANTI GHOSH | 1573.21 | 0 | 12
250 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000163/2023-2024 | 1625/BHM | 28/04/2023 | 0 | Resource Division | 654.06 | 0 | 0
251 | Bolpur Mechanical | Nalhati Sub-Division | Hiring of Luxury Car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000643/2024-2025 | 1675/BOL.MD | 28/06/2024 | 121 | RAJIB GHOSH | 0.57 | 0 | 100
252 | Bolpur Mechanical | Nalhati Sub-Division | Supply & Installation of High lift pumping machineries and other allied works for Banior piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte.. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000919/2023-2024 | 3557/BOL.MD | 04/12/2023 | 302 | MACHINE SUPPLIERS SYNDUCATE (P) LTD. | 95.52 | 0 | 40
253 | Bolpur Mechanical | Nalhati Sub-Division | Supply & Installation of Low lift pumping machineries and other allied works for Banior piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000930/2023-2024 | 3560/BOL.MD | 04/12/2023 | 485 | QUAZI NOZRUL ISLAM | 74.52 | 0 | 30
254 | Bolpur Mechanical | Nalhati Sub-Division | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, P.H.E.Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001441/2023-2024 | 3317/BOL.MD | 29/09/2023 | 121 | SATYAJIT GHOSH | 0.57 | 0 | 100
255 | Bolpur Mechanical | Nalhati Sub-Division | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, P.H.E.Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001442/2023-2024 | 174/BOL.MD | 21/02/2024 | 121 | SATYAJIT GHOSH | 0.57 | 0 | 0
256 | Bolpur Mechanical | Nalhati Sub-Division | Hiring of Luxury car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division, P.H.E.Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001443/2023-2024 | 1221/BOL.MD. | 26/06/2023 | 123 | RAJIB GHOSH | 0.58 | 0 | 0
257 | Bolpur Mechanical | Nalhati Sub-Division | Hiring of Luxury Car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001444/2023-2024 | 205/Bol.MD | 27/02/2024 | 121 | RAJIB GHOSH | 0.57 | 0 | 0
258 | Birbhum Division | Bolpur Sub-Division | Construction of 250 & 150 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main, Distribution System with FHTC including different works related to SANTOSHPUR / NAWADA PALANDI /PAPURI / SAJNOR / RAYEN PIPED WATER SUPPLY SCHEME (5 Nos Scheme) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division PHE DTE. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000085/2024-2025 | 1951/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2322.64 | 0 | 5
259 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for PAPURI Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000739/2022-2023 | 269/BSD | 15/07/2022 | 90 | RADIANT | 4.94 | 0 | 100
260 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000005/2024-2025 | 2393/BHM | 27/08/2024 | 0 | Resource Division | 12.11 | 0 | 0
261 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000068/2023-2024 | 1467/BHM | 25/04/2023 | 0 | Resource Division | 36.41 | 0 | 0
262 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Papuri Water supply Scheme (T/W-I & II), Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000965/2024-2025 | 4534/BOL.MD | 20/12/2024 | 120 | PADMA ENGINEERING CO. | 73.34 | 0 | 45
263 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
264 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at KURUMBA PIPED WATER SUPPLY SCHEME (TSM016231) within LABPUR Block including supply of all Labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000568/2022-2023 | 901/BHM | 22/03/2023 | 275 | ESCON INDIA | 440.1 | 0 | 10
265 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for KURUMBA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001144/2021-2022 | 112/BSD | 25/03/2022 | 180 | APEX ENGINEERING | 3.87 | 0 | 100
266 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000032/2023-2024 | 1566/BHM | 26/04/2023 | 0 | Resource Division | 27.55 | 0 | 0
267 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000157/2023-2024 | 1600/BHM | 27/04/2023 | 0 | Resource Division | 27.55 | 0 | 0
268 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
269 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
270 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
271 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Nichinta & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000682/2022-2023 | 136/BSSD | 20/07/2022 | 45 | RADIANT | 1.16 | 0 | 100
272 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000243/2023-2024 | 424/BHM | 01/02/2024 | 0 | Resource Division | 18.31 | 0 | 0
273 | Birbhum Division | Rampurhat Sub-Division | Sinking of 200 mm dia Alll through and 25 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM, 300 CuM, 250 CuM capacity O.H.R. for Zone-I, II and III respectively, 300 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I, II and III and Providing functional household tap connection related to water supply scheme at DAKHALBATI & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | Assistant Engineer-III | JE2,Junior Engineer | ORD/000110/2024-2025 | 2117/BHM | 29/07/2024 | 365 | M/S GOUTAM DAS | 1419.03 | 0 | 15
274 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer-III | JE2,Junior Engineer | RTOR000024/2024-2025 | 2447/BHM | 30/08/2024 | 0 | Resource Division | 40.44 | 0 | 0
275 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Low lift Pumping Machinery and other allied work for DHAKALBATI and Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | JE2,Junior Engineer | ORD/000870/2023-2024 | 3377/Bol.MD | 13/10/2023 | 90 | M. S. ENTERPRISE | 65.12 | 0 | 30
276 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & Installation of High lift Pumping Mchinery and other allied work for DHAKALBATI & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | JE2,Junior Engineer | ORD/000874/2023-2024 | 3367/BOL.MD | 11/10/2023 | 90 | M. S. ENTERPRISE | 98.53 | 0 | 50
277 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at MANIKPUR PIPED WATER SUPPLY SCHEME (TSM/016147) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte.(2nd Call) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000388/2023-2024 | 4144/BHM | 19/10/2023 | 712 | M/S SAHA AND MONDAL CONSTRUCTION | 785.13 | 0 | 15
278 | Birbhum Division | Bolpur Sub-Division | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for MANIKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000949/2022-2023 | 244/BSD | 24/06/2022 | 90 | APEX ENGINEERING | 4.92 | 0 | 100
279 | Birbhum Division | Bolpur Sub-Division | Continuation work for "Preparation & Submission of additional Detail Project Report (DPR) for MANIKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.¿. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000954/2022-2023 | 301/BSD | 10/08/2022 | 180 | APEX ENGINEERING | 2.11 | 0 | 100
280 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000162/2023-2024 | 1626/BHM | 28/04/2023 | 0 | Resource Division | 103.84 | 0 | 0
281 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
282 | Birbhum Division | Central Mechanical Sub-DivisionIII | Road crossing, Repairing & restoration of damaged pipe lines & PCC roads, sluice valve chambers, Construction of 300 Cum OHR, Pump House, Laying Distribution System, Rising Main Connection including all allied works for Loba Piped Water Supply Scheme under Birbhum division, PHE Dte". | Assistant Engineer-III | Junior Engineer | ORD/000255/2025-2026 | 2828/BHM | 11/11/2025 | 365 | S S ENTERPRISE | 260.79 | 0 | 0
283 | Birbhum Division | Central Mechanical Sub-DivisionIII | Different works related to water supply scheme at CHINPAI, LOBA & PARATPUR and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000265/2023-2024 | 3476/BHM | 08/08/2023 | 816 | B RAI CONSTRUCTION COMPANY | 2497.19 | 0 | 45
284 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000072/2022-2023 | 1396/BHM | 24/04/2023 | 0 | Resource Division | 454.99 | 0 | 0
285 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing electro-mechanical accessories and others for Loba & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000384/2023-2024 | 1915/Bol.MD | 10/08/2023 | 366 | SINHA ELECTRICALS | 129.72 | 0 | 70
286 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply & delivery of different electrical accessories at Loba Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000465/2024-2025 | 1310./AE-III | 28/08/2024 | 126 | RMD TRADING | 2.78 | 0 | 100
287 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply & delivery of different electrical accessories at Loba Piped water supply scheme under Bolpur Mechanical Division P,H,E,Dte. | Assistant Engineer-III | Junior Engineer | ORD/000633/2024-2025 | 1203./AE-III | 16/08/2024 | 10 | J.K.ENGINEERING CO | 0.97 | 0 | 100
288 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply & delivery of openwell submersible pumping machinery for Loba Piped water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000835/2024-2025 | 1676./AE-III | 24/10/2024 | 7 | MASSK ENGINEERING WORKS | 2.75 | 0 | 0
289 | Birbhum Division | Rampurhat Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
290 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (CHHOTA TURIGRAM ) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000836/2022-2023 | 292/RSD | 02/09/2022 | 45 | ENVIROTECH SOLUTIONS | 3.36 | 0 | 100
291 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (CHHOTA TURIGRAM) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000837/2022-2023 | 380/RSD | 26/09/2022 | 45 | ENVIROTECH SOLUTIONS | 3.29 | 0 | 100
292 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000001/2024-2025 | 2382/BHM | 27/08/2024 | 0 | Resource Division | 14.74 | 0 | 0
293 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000047/2023-2024 | 1448/BHM | 25/04/2023 | 0 | Resource Division | 72.7 | 0 | 0
294 | Bolpur Mechanical | Rampurhat Sub-Division | Supply, Delivery and storage of different Electro-Mechanical Accessories at Chhoto Tuligram PWSS under Bolpur Mechanical Division, PHE,Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000513/2024-2025 | 3760/Bol.MD | 12/09/2024 | 111 | HINDOL ROY | 40.82 | 0 | 100
295 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Chhoto Turigram PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000843/2023-2024 | 3282/BOL.MD | 29/09/2023 | 763 | SINHA ELECTRICALS | 67.61 | 0 | 40
296 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Well and other allied works at Chototurigram PWSS under Bolpur Mechanical Division., Block - Mayureswar - II. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/001190/2023-2024 | 375/Bol.MD | 06/03/2024 | 45 | STANDARD ELECTRICALS | 7.41 | 0 | 100
297 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Well and other allied works at Chototurigram PWSS under Bolpur Mechanical Division., Block - Mayureswar - II. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/001193/2023-2024 | 377/Bol.MD | 06/03/2024 | 45 | CINZANO | 7.75 | 0 | 100
298 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at DHANASAHA, CHHATAR-BANDI, BHABANIPUR, BHUBANESWAR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer | JE1 | ORD/000384/2023-2024 | 4141/BHM | 19/10/2023 | 709 | B RAI CONSTRUCTION COMPANY | 2996.46 | 0 | 5
299 | Birbhum Division | Bolpur Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | Assistant Engineer | JE1 | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
300 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHABANIPUR Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - A) | Assistant Engineer | JE1 | ORD/000765/2022-2023 | 176/BSD | 29/04/2022 | 90 | M/S R DUTTA & CO. | 4.93 | 0 | 100
301 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHABANIPUR Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - B) | Assistant Engineer | JE1 | ORD/000766/2022-2023 | 280/BSD | 22/07/2022 | 90 | M/S R DUTTA & CO. | 4.29 | 0 | 100
302 | Bolpur Mechanical | Bolpur Sub-Division | New service connection at Bhabanipur PWSS P.H.- I (Block- Illambazar) | Assistant Engineer | JE1 | BILL/00157/2024-2025 | BP-2024-2025-86 | 14/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.93 | 0 | 0
303 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer | JE1 | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
304 | Birbhum Division | Central Mechanical Sub-DivisionIII | Sinking of 250 mm. X 200 mm Dia deep tubewell ,250 CuM capacity CWR, Pump room/ Chlorine room with/without sanitary arrangements( different size),and laying of Rising main,Distribution System (Zone -I & II ) with FHTC and different works related to SAHAPUR & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000094/2024-2025 | 2126/BHM | 30/07/2024 | 365 | KINGS & CO. | 685.99 | 0 | 20
305 | Birbhum Division | Central Mechanical Sub-DivisionIII | Soil Investigation & Construction of Over Head Reservoir of capacity 350 Cum (Zone-I) & 300 Cum (Zone-II) related to water supply scheme at SAHAPUR & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000204/2025-2026 | 2160/BHM | 20/08/2025 | 365 | ARPAN PANDIT | 215.34 | 0 | 0
306 | Birbhum Division | Central Mechanical Sub-DivisionIII | Continuation Work Order for Preparation & Submission of DPR for (SAHAPUR) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | Assistant Engineer-III | Junior Engineer | ORD/000785/2022-2023 | 285/RSD | 26/08/2022 | 45 | ECO CARE | 3.63 | 0 | 100
307 | Birbhum Division | Central Mechanical Sub-DivisionIII | Continuation Work Order for Preparation & Submission of DPR for (SAHAPUR) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | Assistant Engineer-III | Junior Engineer | ORD/000796/2022-2023 | 358/RSD | 15/09/2022 | 45 | ECO CARE | 2.91 | 0 | 100
308 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000021/2024-2025 | 2444/BHM | 30/08/2024 | 0 | Resource Division | 29.08 | 0 | 0
309 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000107/2023-2024 | 1512/BHM | 26/04/2023 | 0 | Resource Division | 154.79 | 0 | 0
310 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Quotation for new service connection at Sahapur TW No-II (Block-Rampurhat-II) | Assistant Engineer-III | Junior Engineer | BILL/02221/2023-2024 | BP-2023-24-305 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.21 | 0 | 0
311 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | WBSEDCL QUOTATION FOR SAHAPUR TW-1 | Assistant Engineer-III | Junior Engineer | BILL/02247/2023-2024 | BP-2023-24-306 | 18/03/2024 | 0 | WBSEDCL | 4.89 | 0 | 0
312 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply and delivery of 6 mm2 x3 core Al.Ar XLPE Cable for Sahapur water supply scheme.(Block-Dubrajpur) under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000370/2024-2025 | 1191./AE-III | 12/08/2024 | 10 | R.K.ENTERPRISE | 0.98 | 0 | 0
313 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing Electro-mechanical accessories and others for Sahapur PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000485/2023-2024 | 2235/Bol.MD | 12/09/2023 | 597 | QUAZI NOZRUL ISLAM | 44.39 | 0 | 50
314 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Installation of Submersible pumping Machineries at newly sunk Tube Wells and allied works at Sahapur PWSS, Block- Dubrajpur under Bolpur Mechanical Division. | Assistant Engineer-III | Junior Engineer | ORD/000541/2024-2025 | 3800/BOL.MD | 12/09/2024 | 30 | SWAPAN ENTERPRISE | 6.82 | 0 | 100
315 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply, Delivery & Installation of Submersible Pumpining Machinery at newly sunk River Bed Tube well no - 1, 2 ,3 and other allied works at Sahapur Piped water supply scheme (Block- Rampurhat II) | Assistant Engineer-III | Junior Engineer | ORD/001209/2023-2024 | 371/BOL.MD | 06/03/2024 | 30 | CINZANO | 16.91 | 0 | 100
316 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Sahapur PWSS under Dubrajpur Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001245/2023-2024 | 533/BOL.MD | 14/03/2024 | 60 | M/S.S.S. ENTERPRISE | 7.62 | 0 | 0
317 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing Electro-mechanical accessories and others for Sahapur and Adjoining moujas water supply scheme under Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001264/2023-2024 | 562/BOL.MD | 15/03/2024 | 30 | BENGAL CONSTRUCTION | 3.84 | 0 | 0
318 | Birbhum Division | Central Mechanical Sub-DivisionIII | Different works related to water supply scheme at LACHHIATOR, DAKSHINGRAM, SONJ & SHIBGRAM and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000385/2023-2024 | 4142/BHM | 19/10/2023 | 805 | B RAI CONSTRUCTION COMPANY | 2003.84 | 0 | 60
319 | Birbhum Division | Central Mechanical Sub-DivisionIII | Continuation Work Order for Preparation & Submission of DPR for (DAKSHIN GRAM) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | Assistant Engineer-III | Junior Engineer | ORD/000804/2022-2023 | 291/RSD | 02/09/2022 | 90 | ENVIROTECH SOLUTIONS | 3.43 | 0 | 100
320 | Birbhum Division | Central Mechanical Sub-DivisionIII | Continuation Work Order for Preparation & Submission of DPR for (DAKSHIN GRAM) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | Assistant Engineer-III | Junior Engineer | ORD/000805/2022-2023 | 376/RSD | 23/09/2022 | 90 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 100
321 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000074/2023-2024 | 1461/BHM | 25/04/2023 | 0 | Resource Division | 84.55 | 0 | 0
322 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000204/2023-2024 | 205/BHM | 22/01/2024 | 0 | Resource Division | 7.15 | 0 | 0
323 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Quotation For new connection at Dakshingram PWSS P/H -3 (Block- Mayureswar-I) | Assistant Engineer-III | Junior Engineer | BILL/00078/2024-2025 | BP-2024-2025-25 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.32 | 0 | 0
324 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Quotation for new connection at Dakshingram PWSS P/H-2 (Block-Mayureswar -I) | Assistant Engineer-III | Junior Engineer | BILL/00081/2024-2025 | BP-2024-2025-26 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.53 | 0 | 0
325 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | WBSEDCL QUOTATION FOR DAKSHINGRAM PUMP HOUSE NO-I | Assistant Engineer-III | Junior Engineer | BILL/02079/2023-2024 | BP-2023-24-287 | 04/03/2024 | 0 | WBSEDCL | 6.44 | 0 | 0
326 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing Electro-mechanical accessories and others for Dakshingram PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000731/2023-2024 | 3476/Bol.MD | 07/11/2023 | 60 | S.P. CONSTRUCTION | 55.2 | 0 | 40
327 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Dakhingram PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001217/2023-2024 | 402/Bol.MD | 07/03/2024 | 45 | EASTERN INDIA SALES & SERVICE | 24.53 | 0 | 0
328 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages (Murgathali, Ashna, Sundarkhela, Jahanbal) of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. |  |  | ORD/000066/2020-2021 | 1169/BHM | 21/09/2020 | 60 | PRANAB KUMAR GHOSH | 40.55 | 25.27 | 0
329 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Tilabani, Ramnagar, Dhaka, Gangapur, Aligarh of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte |  |  | ORD/000068/2020-2021 | 1168 /BHM | 21/09/2020 | 60 | M/S GOUTAM DAS | 37.14 | 29.11 | 0
330 | Birbhum Division |  | Additional work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages of Madarpur, Joypur, Talpukur, Ruhida, Ranigram, Hirapur, Mursabani, Lauberia of Aligarh Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.¿ (Sl. No.2) |  |  | ORD/000261/2022-2023 | 2152/BHM | 28/09/2022 | 60 | M/S KRIPASINDHU GHOSH & CO. | 13.95 | 0 | 100
331 | Birbhum Division |  | Additional work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villagesTilabani, Ramnagar, Dhaka, Gangapur, Aligarh of Aligarh Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000269/2022-2023 | 2177/BHM | 29/09/2022 | 60 | M/S GOUTAM DAS | 12.16 | 0 | 100
332 | Birbhum Division |  | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Rajnagar Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 10) |  |  | ORD/000405/2021-2022 | 382/BSSD | 10/12/2021 | 20 | SUBHANKAR ROY | 0.99 | 0 | 49
333 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Kayastaparaunder Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 22) |  |  | ORD/000006/2021-2022 | 199/BSSD | 15/06/2021 | 30 | B.M.SARKAR | 4.95 | 4.91 | 100
334 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Bauriparaunder Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 21) |  |  | ORD/000007/2021-2022 | 198/BSSD | 15/06/2021 | 30 | DIPAK SARKAR | 4.85 | 4.7 | 100
335 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Keotparaunder Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 23) |  |  | ORD/000008/2021-2022 | 200/BSSD | 15/06/2021 | 30 | BHABATARAN SADHU | 4.98 | 4.96 | 100
336 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Muchiparaunder Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte.(Sl. No. - 24)) |  |  | ORD/000009/2021-2022 | 201/BSSD | 15/06/2021 | 30 | ASIT GHOSH | 4.95 | 4.95 | 100
337 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Dompara & Coloney under Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 28) |  |  | ORD/000010/2021-2022 | 203/BSSD | 15/06/2021 | 30 | SACHIN KUMAR SARKAR | 4.96 | 4.96 | 100
338 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Jamrand Chasapara under Jamrand Mouza (JL No. - 136) under Khoyrasole Block, within the command area of Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 31) |  |  | ORD/000011/2021-2022 | 206 /BSSD | 15/06/2021 | 30 | SUMEN CHOWDHURY | 4.97 | 0 | 100
339 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Acharjyapara under Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte.(Sl. No. - 25) |  |  | ORD/000013/2021-2022 | 212/BSSD | 15/06/2021 | 30 | GOUTAM MONDAL | 4.95 | 4.94 | 0
340 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Dompara & Colony under Rasa Mouza (J.L. No.107) under Khoyrasole Block within the command area of RASA Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.28) |  |  | ORD/000020/2021-2022 | 203 /BSSD | 15/06/2021 | 30 | SACHIN KUMAR SARKAR | 4.96 | 0 | 0
341 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Muchipara under Rasa Mouza (J.L. No.107) under Khoyrasole Block within the command area of RASA Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.24) |  |  | ORD/000021/2021-2022 | 201 /BSSD | 15/06/2021 | 30 | ASIT GHOSH | 4.95 | 0 | 0
342 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Chasapara under RASA Mouza (J.L. No.107) under Khoyrasole Block within the command area of RASA Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.26) |  |  | ORD/000022/2021-2022 | 202/BSSD | 15/06/2021 | 30 | ARKA JYOTI GHOSH | 4.79 | 0 | 100
343 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasa in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.(Sl. No.9) |  |  | ORD/000410/2022-2023 | 2587/BHM | 22/11/2022 | 60 | HIRANMAY GHOSH | 58.98 | 0 | 49
344 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasa w/s Scheme in Suri Sadar Sub-Division under Birbhum Division, PHE Dte. (2nd Call) (Sl. No.15) |  |  | ORD/000428/2021-2022 | 2166/BHM | 24/12/2021 | 60 | RICK CONSTRUCTION | 48.67 | 0 | 100
345 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kamra, Harirampur of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.4) |  |  | ORD/000043/2020-2021 | 1238 /BHM | 28/09/2020 | 45 | UMWELT ENGINEER PVT. LTD | 29.57 | 25.51 | 0
346 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kayemba, Bara Chauki of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.5) |  |  | ORD/000047/2020-2021 | 1239/BHM | 28/09/2020 | 60 | KAZI EMDADUL HAQUE | 32.58 | 25.18 | 0
347 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Shigram of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. |  |  | ORD/000053/2020-2021 | 1177 /BHM | 21/09/2020 | 60 | M/S MD AMINUL ISLAM | 31.84 | 26.3 | 0
348 | Birbhum Division |  | Laying of Distribution System with UPVC Pipes and Providing Tap Connection for Existing School & AWC under Dunigram Mouza in Dunigram PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000075/2021-2022 | 274/RSD | 16/07/2021 | 10 | MD ABSAR ALI | 1 | 0 | 50
349 | Birbhum Division |  | Providing Tap Connection for Existing School & AWC under Shilogram, Kamra,Kayemba,Chandpara, Harirampur Mouzas in Dunigram PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000076/2021-2022 | 275/RSD | 16/07/2021 | 10 | MD ABSAR ALI | 0.99 | 0 | 50
350 | Birbhum Division |  | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Chandpara Habitation of Chandpara Village under Dunigram Gram Panchayet, Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte |  |  | ORD/000597/2020-2021 | 286/RSD | 31/12/2020 | 15 | ABUL HASNAT | 0.1 | 0 | 100
351 | Birbhum Division |  | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Chandpara Habitation of Chandpara Village under Dunigram Gram Panchayet, Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte. |  |  | ORD/000598/2020-2021 | 287/RSD | 31/12/2020 | 15 | ABUL HASNAT | 0.1 | 0 | 100
352 | Birbhum Division |  | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Kamra, Kayemba, Shilgram Habitation of Kamra, Kayemba, Shilgram Village under Dunigram Gram Panchayet, Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte. |  |  | ORD/000599/2020-2021 | 288/RSD | 31/12/2020 | 15 | ABUL HASNAT | 0.09 | 0 | 100
353 | Birbhum Division |  | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Dunigram, Harirampur Habitation of Dunigram Village under Dunigram Gram Panchayet, Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte. |  |  | ORD/000600/2020-2021 | 289/RSD | 31/12/2020 | 15 | ABUL HASNAT | 0.1 | 0 | 100
354 | Birbhum Division |  | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Different places of Mayureswar-I & Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte. |  |  | ORD/000601/2020-2021 | 290/RSD | 31/12/2020 | 15 | ABUL HASNAT | 0.07 | 0 | 100
355 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Babuijore Zone-II Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte. (2nd Call) (Sl. No.12) | AE | JE | ORD/000021/2022-2023 | 819/BHM | 13/04/2022 | 60 | PRAVAT SARKAR | 76.14 | 0 | 87
356 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area village of Barrah, Kadamdanga and Kaithi of Babuijore (Zone-II) Piped Water Supply Scheme under Birbhum Sadar Sub Division , P.H.E Dte within Birbhum Division P.H.E Dte. | AE | JE | ORD/000086/2023-2024 | 1635/BHM | 02/05/2023 | 60 | THREE MAA ENTERPRISE | 70 | 0 | 100
357 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area village of Barrah, Kadamdanga & Dhulkumro of Babuijore (Zone-II) Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No.1) | AE | JE | ORD/000293/2022-2023 | 2433/BHM | 02/11/2022 | 60 | PRAVAT SARKAR | 87.09 | 0 | 82
358 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Babuijore Zone-I Water Supply Scheme within Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.9) | AE | JE | ORD/000463/2021-2022 | 136/BHM | 25/01/2022 | 60 | HIRANMAY GHOSH | 76.5 | 0 | 100
359 | Birbhum Division | Birbhum Sadar Sub-Division | Additional work for Construction of 300 Cum Capacity and 20.0m Staging Height RCC Over Head Reservoir & Laying Distribution System including all allied Works as per departmental drawing at Zone-I of Babuijore Piped Water Supply Scheme under Birbhum Sadar Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. (2nd Phase)(Sl. No. - 05) | AE | JE | ORD/000622/2021-2022 | 402/BSSD | 14/12/2021 | 15 | SUNDAR CONSTRUCTION | 4.63 | 0 | 100
360 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of drain & repairing of Culvert for 300 mm dia. rising main crossing under Culvert at Bara village of Babuijore Piped Water Supply Scheme under Birbhum Sadar Sub-Dvision, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. (Sl. No. - 03) | AE | JE | ORD/000864/2021-2022 | 401/BSSD | 14/12/2021 | 15 | HIRANMAY GHOSH | 2.03 | 0 | 100
361 | Birbhum Division | Birbhum Sadar Sub-Division | Laying of distribution system including FHTC for village Geruapahari, J.L No.74, G.P Babuijore, Block Khorasole for ensuing draught like situation within Birbhum Division, PHE Dte.? (Sl. No.5) | AE | JE | ORD/000873/2021-2022 | 507 / BHM | 03/03/2022 | 45 | DIPAK SARKAR | 12.24 | 0 | 100
362 | Birbhum Division | Birbhum Division | Providing Functional Household Tap Connection (FHTC) for balance Household from existing distribution system within the command area of Maldanga under Maldanga Water Supply Scheme within Birbhum Division, PHE Dte. | AE(HQ) | Estimator | ORD/000092/2022-2023 | 1452/BHM | 07/07/2022 | 60 | APORUPA CONSTRUCTION | 64.41 | 0 | 100
363 | Birbhum Division | Birbhum Division | Withdrawing & restroration of 100 mm & 200 mm dia distribution & rising main pipe line at bridge crossing near Maldanga village & providing FHTC for the village of Moulpur, Bhututa & chatrama to declre "SAJAL GRAM" of Maldanga piped water supply scheme under Birbhum division P.H.E Dte. | AE(HQ) | Estimator | ORD/000154/2023-2024 | 1172/BHM | 11/04/2023 | 15 | SOURAV MONDAL | 0.98 | 0 | 100
364 | Birbhum Division | Birbhum Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maldanga Zone-I Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte¿(Sl. No.7) | AE(HQ) | Estimator | ORD/000482/2021-2022 | 278/BHM | 09/02/2022 | 60 | APORUPA CONSTRUCTION | 63.41 | 0 | 100
365 | Birbhum Division | Birbhum Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maldanga Zone-II Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.8) | AE(HQ) | Estimator | ORD/000483/2021-2022 | 281/BHM | 09/02/2022 | 60 | BIJOY KUMAR CHOUDHURY | 52.83 | 0 | 95
366 | Birbhum Division | Birbhum Division | Connection of distribution pipeline at node 6-40, rising main at MDMC main canal crossing node 147-148 & construction of sluice valve chambers & all other allied works at different locations under Maldanga Piped Water Supply Scheme of Birbhum Division, P.H.E. Dte.(Sl. No.1) | AE(HQ) | Estimator | ORD/000710/2021-2022 | 2031/BHM | 09/12/2021 | 60 | ARPAN PANDIT | 9.53 | 0 | 100
367 | Birbhum Division | Birbhum Division | Surveying, Planning etc. including obtaining permission on behalf of PHE Dte Supply, Laying & Pushing of 600 mm dia. 10 mm thick M.S Spiral Welded Casing Pipe by of Fe 410 grade as per IS: 3589-2001 Adopting Trenchless Technologies (Jack Pushing Method) under in between NH road crossing for 200 mm dia. Distribution Line at Joypur More (Node Point 25) under Maldanga W/S Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.1) | AE(HQ) | Estimator | ORD/000715/2021-2022 | 524/BHM | 11/03/2022 | 45 | MANASH GHOSH | 19.61 | 0 | 50
368 | Birbhum Division | Birbhum Division | Supply & delivery of sluice valve for Maldanga Zone-I W/S scheme under Birbhum Division, PHE Dte including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. (Sl. No.-01) | AE(HQ) | Estimator | ORD/000828/2021-2022 | 419/BHM | 24/02/2022 | 15 | BIJOY KUMAR CHOUDHURY | 0.92 | 0 | 100
369 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Belera Water Supply Scheme within Rampurhat Sub-Division, Birbhum Division, PHE Dte. (Sl. No.4) | AE | JE3 | ORD/000005/2022-2023 | 747/BHM | 05/04/2022 | 60 | S K CONSTRUTION | 73.03 | 0 | 100
370 | Birbhum Division | Rampurhat Sub-Division | Laying & distribution system with UPVC pipes including FHTC (Functional Household Tap Connection) for Belera PWSS under Birbhum, Division, PHE Dte. (Sl. No.1) | AE | JE3 | ORD/000242/2022-2023 | 2165/BHM | 28/09/2022 | 30 | OM ENTERPRISE | 34.22 | 0 | 90
371 | Birbhum Division | Rampurhat Sub-Division | Sinking of 01 Nos (1st TW) Tube well 200mm dia 90 m. deep tube well fitted with PVC pipe and fiber glass Strainer at Belera PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000694/2021-2022 | 107/RSD | 07/03/2022 | 30 | SK FAQHRUL AMIN | 4.85 | 0 | 100
372 | Birbhum Division | Rampurhat Sub-Division | Sinking of 01 Nos (3rd TW) Tube well 200mm dia 90 m. deep tube well fitted with PVC pipe and fiber glass Strainer at Belera PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000695/2021-2022 | 108/RSD | 07/03/2022 | 30 | SK FAQHRUL AMIN | 4.85 | 0 | 100
373 | Birbhum Division | Rampurhat Sub-Division | Laying of Rising main with DI pipe line for inter connection of 3 Nos TW for Belera Piped Water Supply Scheme under Rampurhat sub division under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000696/2021-2022 | 110/RSD | 07/03/2022 | 60 | MD. SHAHA JAMAL | 4.52 | 0 | 100
374 | Birbhum Division | Rampurhat Sub-Division | Supply and delivery of Sluice Valve & Duck Foot Bend for Belera W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.¿ (Sl. No.2) | AE | JE3 | ORD/000765/2021-2022 | 376/BHM | 21/02/2022 | 15 | SSPR VALVE MANUFACTURING PVT LTD | 6.71 | 0 | 100
375 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 500cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Rajnagar W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000014/2023-2024 | 1256/BHM | 17/04/2023 | 275 | M/S KRIPASINDHU GHOSH & CO. | 128.12 | 0 | 0
376 | Birbhum Division | Birbhum Sadar Sub-Division | Additional pipe line for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area except Daspara & Idgacha village of Rajnagar Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000104/2023-2024 | 1724/BHM | 12/05/2023 | 45 | UJJWAL DAS | 14.53 | 0 | 0
377 | Birbhum Division | Birbhum Sadar Sub-Division | Balance work for laying of pipe line including FHTC for augmentation of Rajnagar Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000111/2023-2024 | 1876/BHM | 31/05/2023 | 60 | OM ENTERPRISE | 56.94 | 0 | 100
378 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Bhatra, Abdullapur and adjacent area under Rajgram W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000359/2021-2022 | 592/AE/NSD | 23/11/2021 | 45 | MD ASIF ALI | 4.82 | 0 | 50
379 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of Boundary Wall with drain at Pump House & CWR of Rajnagar Piped Water Supply Scheme, under RWS Birbhum Sub-Division within Birbhum Division, P.H.E. Dte. (Sl. No.10) | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000402/2022-2023 | 32/BHM | 04/01/2023 | 45 | SYED GOLAM ZILANI | 9.18 | 0 | 100
380 | Birbhum Division | Birbhum Sadar Sub-Division | Laying distribution system for proposed augmentation scheme for Rajnagar Piped Water Supply Scheme under Rajnagar Block, under Birbhum Division, PHE Dte. (Sl. No.8) | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000502/2021-2022 | 94/BHM | 21/01/2022 | 180 | UJJWAL DAS | 315.1 | 0 | 100
381 | Birbhum Division | Birbhum Sadar Sub-Division | Trial Bore and Sinking for 03 nos. 200mm dia. Tubewell of 5m depth with horizontal strainer on the river Bed of Kuskorini under Rajnagar Piped Water Supply Scheme within Birbhum Sadar Sub-Division, P.H.E. Dte. under Birbhum Division P.H.E. Dte. (Sl. No. - 04) | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000506/2022-2023 | 270/BSSD | 11/11/2022 | 15 | INDRANIL DUTTA | 4.84 | 0 | 100
382 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system at Idgacha under Nakash village within the command area of Rajnagar Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. (Sl. No. -01) | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000577/2022-2023 | 213/BSSD | 21/09/2022 | 15 | UJJWAL DAS | 4.95 | 0 | 100
383 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system at Daspara under Nakash Village within the command area of Rajnagar Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte.(Sl. No. -07) | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000578/2022-2023 | 219/BSSD | 21/09/2022 | 15 | UJJWAL DAS | 4.98 | 0 | 100
384 | Birbhum Division | Birbhum Sadar Sub-Division | Supply & delivery of sluice valve for Augmentation of Rajnagar W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex Dist.-Birbhum under Birbhum Division, PHE Dte. (Sl. No.-01) | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000703/2021-2022 | 421/BHM | 24/02/2022 | 15 | UJJWAL DAS | 4.86 | 0 | 100
385 | Birbhum Division | Birbhum Sadar Sub-Division | Repairing of the Pump House & CWR of the Rajnagar Pipe Water Supply under RWS Birbhum Sub-Division,PHE Dte. Suri, Birbhum. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000773/2021-2022 | 33/BH | 09/03/2022 | 30 | RANJIT GHOSH | 0.76 | 0 | 50
386 | Birbhum Division | Birbhum Sadar Sub-Division | repairing of the Pump house & C.W.R of the Rajnagar Pipe Water Supply Scheme under Birbhum Division, P.H.E .Dte, Suri , Birbhum. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000832/2021-2022 | 33/BH | 09/03/2022 | 30 | RANJIT GHOSH | 0.76 | 0 | 50
387 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000006/2023-2024 | 1110/BHM | 10/04/2023 | 0 | Resource Division | 14.64 | 0 | 0
388 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000036/2021-2022 | 193/BHM | 01/02/2022 | 0 | Resource Division | 25.77 | 0 | 0
389 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000043/2021-2022 | 214/BHM | 02/02/2022 | 0 | Resource Division | 21.82 | 0 | 0
390 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000063/2021-2022 | 487/BHM | 02/03/2022 | 0 | Resource Division | 30.25 | 0 | 0
391 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply and delivery of outdoor type pump controller unit for Augmentation of Rajnagar under Ahmadpur PWSS in Rajnagar block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000059/2024-2025 | 1345/Bol.MD | 03/05/2024 | 45 | M/S. UTTAM KUMAR CHATTERJEE | 20.06 | 0 | 100
392 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others at low lift site for Augmentation of Rajnagar water supply scheme under Bolpur Mechanical Division PHE Dte | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000236/2023-2024 | 1412/Bol.MD | 10/07/2023 | 45 | AMITAVA CHAKRABORTY | 18.99 | 0 | 0
393 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply and Installation of Pumping Machineries at ISGARA Village (within Augmentation of Rajnagar PWSS) Under Bolpur Mechanical Division, PHED | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000238/2023-2024 | 1413/BOL.MD | 10/07/2023 | 30 | RAJIB GHOSH | 6.73 | 0 | 30
394 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply and Installation of Pumping Machineries at Matiara Village (within Augmentation of Rajnagar PWSS) Under Bolpur Mechanical Division, PHED. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000239/2023-2024 | 1420/Bol.MD | 10/07/2023 | 30 | M/S SANTI CONSTRUCTION | 6.68 | 0 | 0
395 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply, delivery and installation of of Voltage correction device at panchiara water supply scheme( with in Rajnagar Augmentation Water Supply , Block : Rajnagar), under Bolpur Mechanical Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000489/2023-2024 | 2245/Bol.MD | 13/09/2023 | 60 | M/S P.P ELECTRICALS | 23.98 | 0 | 30
396 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply delivery & installation of voltage correction device at Augmentation of Rajnagar water supply scheme under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000521/2023-2024 | 2264/Bol.MD | 14/09/2023 | 45 | CINZANO | 15.85 | 0 | 100
397 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply , delivery and installation of Submersible pumping machinery and others allied work at newly sunk T/W of Aligarh & Adjoining mouzas Water Supply Scheme at Aug. of Rajnagar PWSS under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000875/2024-2025 | 4344/BOL.MD | 13/11/2024 | 30 | M/S M3 SOLUTION | 8.11 | 0 | 100
398 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Replacement of voltage correction device at Khoyrasole (Churur) water supply scheme (AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME) under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/001062/2023-2024 | 33/BOL.MD | 10/01/2024 | 30 | S.DUTTA | 15.87 | 0 | 100
399 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Modification of MCC panel of Isgara Mini water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/001113/2023-2024 | 1658/AE-III | 22/12/2023 | 6 | RAJIB GHOSH | 0.16 | 0 | 100
400 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply & delivery of Cable for Aug. Rajnagar water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/001163/2023-2024 | 296/AE-III | 22/02/2024 | 10 | SATYAJIT GHOSH | 3.86 | 0 | 100
401 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply & delivery of High lift pumping machinery at store for Aug. Rajnagar and others water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/001168/2023-2024 | 300/AE-III | 22/02/2024 | 10 | SWAPAN BANERJEE | 2.75 | 0 | 100
402 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply and Delivery of Sub-Mersible Pump Controllers for Augmentation of Rajnagar water supply scheme (Block- Rajnagar) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/001169/2023-2024 | 301/AE-III | 22/02/2024 | 10 | HINDOL ROY | 4.56 | 0 | 100
403 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Testing and refilling of empty chlorine gas cylinder of Rajnagar and adjoining mouzas & Different Rural water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/001172/2023-2024 | 302/AE-III | 22/02/2024 | 247 | UNIVERSAL ENTERPRISES | 4.84 | 0 | 100
404 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Replacement of voltage correction device at Augmentation of Rajnagar water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/001199/2023-2024 | 368/BOL.MD | 06/03/2024 | 30 | GOENKA ENTERPRISE | 14.34 | 0 | 100
405 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply and Delivery of high lift pumping Machinery for Augmentation of Rajnagar and other water supply scheme under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/001311/2023-2024 | 605/AE-III | 27/03/2024 | 7 | M/S M3 SOLUTION | 2.75 | 0 | 100
406 | Birbhum Division |  | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area at Dakshin Tilpara Nutanpara, Sukantapally & Mudidangal of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte.(Sl. No. ¿ 04) |  |  | ORD/000046/2022-2023 | 90/BSSD | 27/05/2022 | 20 | RAJKUMAR DAS | 4.95 | 0 | 100
407 | Birbhum Division |  | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Laldighipara under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte.(Sl. No. -09) |  |  | ORD/000143/2022-2023 | 167/BSSD | 16/08/2022 | 20 | SACHIN KUMAR SARKAR | 2.72 | 0 | 100
408 | Birbhum Division |  | Trial Bore and Sinking of 200 mm dia. replacement tubewell 3 (Three) nos. each 39 m. Deep fitted with PVC Housing pipe and Fibre Glass Strainer on the river bank of Mayurakshi including connecting pipe line under Tilpara Piped Water Supply Scheme within Birbhum Division, PHE Dte. |  |  | ORD/000144/2024-2025 | 2506/BHM | 03/09/2024 | 45 | AMIT KUMAR ROY | 7.63 | 0 | 100
409 | Birbhum Division |  | Laying of Distribution Pipe line of Tilpara Piped Water Supply Scheme from Kalitala(Tilpara) towards PWD (Roads) office under Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. (Sl. No. - 02) |  |  | ORD/000156/2021-2022 | 273/BSSD | 06/08/2021 | 20 | UTPAL DEY | 4.92 | 0 | 0
410 | Birbhum Division |  | Laying of Distribution Pipe line of Tilpara Piped Water Supply Scheme from OHR towards Kalitala (Tilpara) under Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. (Sl. No. - 19) |  |  | ORD/000157/2021-2022 | 274/BSSD | 06/08/2021 | 20 | PUSPAJIT MONDAL | 4.94 | 0 | 100
411 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tilpara w/s Scheme (Left out House Hold) in Suri Sadar Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.1) |  |  | ORD/000257/2021-2022 | 1506/BHM | 09/09/2021 | 60 | RAJKUMAR DAS | 39.43 | 0 | 50
412 | Birbhum Division |  | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Kalpatarupally under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl.No. -02) |  |  | ORD/000275/2021-2022 | 336/BSSD | 23/09/2021 | 20 | M/S SARADA CONSTRUCTION. | 4.02 | 0 | 100
413 | Birbhum Division |  | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Kalpatarupally under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. -08) |  |  | ORD/000288/2022-2023 | 262/BSSD | 20/10/2022 | 20 | M/S SARADA CONSTRUCTION. | 2.67 | 0 | 91
414 | Birbhum Division |  | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Suri- I Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 05) |  |  | ORD/000406/2021-2022 | 380/BSSD | 10/12/2021 | 20 | AATHARVA CONSTRUCTION | 0.99 | 0 | 50
415 | Birbhum Division |  | Laying of UPVC Pipeline including all allied works for By passs arrangement at Kamalpur village for smooth supply of drinking water through existing FHTC under Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. |  |  | ORD/000493/2024-2025 | 205/BHM | 16/01/2025 | 45 | RAJ KUMAR DAS | 1.29 | 0 | 100
416 | Birbhum Division |  | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Laldighipara under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 03) |  |  | ORD/000553/2021-2022 | 353/BSSD. | 25/10/2021 | 20 | SACHIN KUMAR SARKAR | 3.88 | 0 | 100
417 | Birbhum Division |  | Extension of 75 mm dia.UPVC distribution pipe line from Hatzen Bazar Post Office Para at Zone - IV (Part-B) under Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 01) |  |  | ORD/000600/2021-2022 | 319/BSSD. | 13/09/2021 | 20 | ARPAN PANDIT | 4.09 | 0 | 0
418 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area village of Laldighipara under Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. |  |  | ORD/000611/2023-2024 | 909/BHM | 13/03/2024 | 45 | RAJKUMAR DAS | 2.89 | 0 | 100
419 | Birbhum Division | Birbhum Sadar Sub-Division | Balance work of Laying distribution pipe line, FHTC & Jack Pushing for the work at Panchra under the Panchra Piped Water Supply Scheme within Khoyrasole Development Block under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000018/2023-2024 | 1095/BHM | 06/04/2023 | 548 | MANASH GHOSH | 464.71 | 0 | 50
420 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of Panchra under Panchra Water Supply Water Supply Scheme within Birbhum Division, PHE Dte. (Sl. No.9) | AE | JE2 | ORD/000365/2022-2023 | 2773/BHM | 14/12/2022 | 60 | MANASH GHOSH | 93.92 | 0 | 65
421 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of boundary wall at Panchara OHR site of Panchara PWSS under Birbhum Sadar Sub-Division, PHE Dte. (Sl. No.09) | AE | JE2 | ORD/000662/2020-2021 | 949/BHM | 12/08/2020 | 45 | BHABANI ENTERPRISE | 4.97 | 0 | 100
422 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 700cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Khyarasole Zone I W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000012/2023-2024 | 1255/BHM | 17/04/2023 | 275 | M/S KRIPASINDHU GHOSH & CO. | 151.36 | 0 | 70
423 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 200cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Khyarasole Zone II W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000092/2023-2024 | 1646/BHM | 02/05/2023 | 276 | U TURN CONSTRUCTION | 71.24 | 0 | 89
424 | Birbhum Division | Birbhum Sadar Sub-Division | Laying distribution system including FHTC for proposed augmentation scheme for Khayrasole Zone-II Piped Water Supply Scheme, Khayrasole Block, under Birbhum Division, PHE Dte? (Sl. No.5) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000257/2022-2023 | 1149/BHM | 23/05/2022 | 180 | TIRUPATI ENTERPRISES | 229.96 | 0 | 85
425 | Birbhum Division | Birbhum Sadar Sub-Division | Balance work for Laying distribution system including FHTC for proposed augmentation scheme for Khayrasole Zone-I Piped Water Supply Scheme, Khayrasole Block, under Birbhum Division, P.H.E. Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000257/2023-2024 | 3440/BHM | 03/08/2023 | 485 | ARABINDA GUPTA | 298.61 | 0 | 52
426 | Birbhum Division | Birbhum Sadar Sub-Division | Laying distribution system including FHTC for proposed augmentation scheme for Khayrasole Zone-I Piped Water Supply Scheme, Khayrasole Block, under Birbhum Division, PHE Dte.¿ (Sl. No.4) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000274/2022-2023 | 1157/BHM | 23/05/2022 | 180 | M/S S.S. ENTERPRISE | 372.63 | 0 | 80
427 | Birbhum Division | Birbhum Sadar Sub-Division | Trial Bore and Sinking of 200 mm dia. 2(Two) nos.tubewell 30m. (avg.) depth fitted with PVC pipes & fittings Schedule 80 (medium duty) and Fibre Glass Strainer on the river bank of Ajoy under Khayrasole Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, PHE Dte. (Sl. No. -01) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000408/2022-2023 | 73/BSSD | 02/05/2022 | 15 | SK FAQHRUL AMIN | 3.8 | 0 | 100
428 | Birbhum Division | Birbhum Sadar Sub-Division | Replacement of rising main pipe line from AC Pipe line to DI K9 and concreting work in the premesis of CWR site and other allied works under Augmentation of Khayrasole Piped Water Supply Scheme (Zone-I) under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division PHE Dte.(Sl. No. -16) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000595/2022-2023 | 227/BSSD | 21/09/2022 | 20 | HIRANMAY GHOSH | 4.88 | 0 | 0
429 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of PCC Pillar for laying of 250 mm dia. rising main pipe line over Hinglow River near Pansuili for Khayrasole Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000598/2022-2023 | 1043/BHM | 31/03/2023 | 30 | HIRANMAY GHOSH | 4.55 | 0 | 100
430 | Birbhum Division | Birbhum Sadar Sub-Division | Laying of Distribution Pipe line from Dihipara Hanuman Mandir to Kendragaria Railway crossing under Khoyrasole Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. (Sl. No. - 04) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/001086/2021-2022 | 398/BSSD | 10/12/2021 | 15 | B.M.SARKAR | 4.99 | 0 | 100
431 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000021/2022-2023 | 900/BHM | 26/04/2022 | 0 | Resource Division | 9.93 | 0 | 0
432 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000033/2022-2023 | 2292/BHM | 20/10/2022 | 0 | Resource Division | 64.91 | 0 | 0
433 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000034/2022-2023 | 2556/BHM | 21/11/2022 | 0 | Resource Division | 288.93 | 0 | 0
434 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at ABHIRAMPUR, BEHIRA, SAMSA & UTTAR BANGAON and its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000082/2023-2024 | 1437/BHM | 25/04/2023 | 820 | ASHOK KUMAR GHOSH | 1446.74 | 0 | 55
435 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE2,Junior Engineer | RTOR000044/2022-2023 | 1371/BHM | 24/04/2023 | 0 | Resource Division | 50.48 | 0 | 0
436 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Abhirampur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000439/2023-2024 | 2098/Bol.MD | 22/08/2023 | 60 | MONI ELECTRICAL WORKS | 27.98 | 0 | 50
437 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
438 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at MELANPUR & its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000067/2023-2024 | 1340/BHM | 20/04/2023 | 987 | BRAHMA CONSTRUCTION COMPANY | 412.68 | 0 | 37
439 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000057/2022-2023 | 1411/BHM | 24/04/2023 | 0 | Resource Division | 19.04 | 0 | 0
440 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Melanpur PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte | AE,Assistant Engineer | JE,Junior Engineer | BILL/02239/2023-2024 | BP-2023-24-315 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.76 | 0 | 0
441 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Melanpur PWSS at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000442/2023-2024 | 2107/BOL.MD. | 22/08/2023 | 680 | M/S. DILIP MITRA | 28.74 | 0 | 50
442 | Birbhum Division | Birbhum Sadar Sub-Division | Road crossing, repairing & restoration of damaged pipe lines & PCC roads, sluice valve chambers including all allied works for Pakuria Piped Water Supply Scheme under Birbhum Division, P.H.E Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000041/2025-2026 | 1511/BHM | 23/05/2025 | 90 | SHREE J.M. CONSTRUCTION | 18.25 | 0 | 0
443 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at NETURI, PAIKPARA & PAKURIA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000256/2023-2024 | 3441/BHM | 03/08/2023 | 940 | SHREE J.M. CONSTRUCTION | 1236.08 | 0 | 54
444 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000064/2022-2023 | 1413/BHM | 24/04/2023 | 0 | Resource Division | 17.28 | 0 | 0
445 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Pakuria & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000430/2023-2024 | 2094/Bol.MD | 22/08/2023 | 60 | CHAKRABORTY MINING & ENGINERING | 28.81 | 0 | 50
446 | Birbhum Division | Nalhati Sub-Division | Different Works related to water supply scheme at Bonha & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE,Assistant Engineer | JE,JE1,Junior Engineer | ORD/000028/2023-2024 | 1216/BHM | 12/04/2023 | 749 | TAPAN KUMAR DATTA | 293.99 | 0 | 20
447 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,JE1,Junior Engineer | RTOR000039/2023-2024 | 1472/BHM | 25/04/2023 | 0 | Resource Division | 53.39 | 0 | 0
448 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for Bonha Water Supply Scheme P/H-II in Paikar CCC under Bolpur Mechanical division, PHE Dte | AE,Assistant Engineer | JE,JE1,Junior Engineer | BILL/00830/2024-2025 | BP-24-25-178 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.01 | 0 | 0
449 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR BONHA P H NO.I WS SCHEME | AE,Assistant Engineer | JE,JE1,Junior Engineer | BILL/01594/2023-2024 | BP-23-24-228 | 15/01/2024 | 0 | WBSEDCL | 3.6 | 0 | 0
450 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Bonha PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,JE1,Junior Engineer | ORD/000940/2023-2024 | 3301/BOL.MD | 29/09/2023 | 580 | QUAZI NOZRUL ISLAM | 28.83 | 0 | 60
451 | Birbhum Division | Nalhati Sub-Division | Estimate for restoration charges for laying PHE pipeline from 3.5 KM to 6.5 KM of rajgram Maharapur road under rampurhat highway sub division of Birbhum highway Division-Iin the dist of Birbhum during the year 2023-24 | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00735/2024-2025 | BP-2024-25-223 | 12/09/2024 | 0 | EXECUTIVE ENGINEER BIRBHUM HIGHWAY DIVISION-I P.W (ROADS) DIRECTORATE | 22 | 0 | 0
452 | Birbhum Division | Nalhati Sub-Division | Acceptance Cum Work Order for Supply and delivery of Sluice Valve for Mahurapur and Adjoining Mouzas PWSS under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000635/2023-2024 | 948/BHM | 14/03/2024 | 30 | MAKALI ENGINEERING CORPORATION | 9.71 | 0 | 0
453 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000018/2023-2024 | 1435/BHM | 25/04/2023 | 0 | Resource Division | 48.04 | 0 | 0
454 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for MAHURAPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000902/2023-2024 | 3297/Bol.MD | 29/09/2023 | 575 | MITRA ENTERPRISE | 30.63 | 0 | 0
455 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
456 | Birbhum Division | Nalhati Sub-Division | Extension of pipeline including restoration of roads along with balance FHTC of HARISARA W/S Scheme under Nalhati Sub-Division within Birbhum Division,PHE Dte. | AE | JE1 | ORD/000048/2023-2024 | 1314/BHM | 20/04/2023 | 60 | MD SURAJ ALI | 42.72 | 0 | 100
457 | Birbhum Division | Rampurhat Sub-Division | Providing Left out FHTC for declaration of Swajal Gram Village at Raypur & Rupganj Mouzas under Raypur Zone I Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. (Sl. No. - 01) | AE | JE3 | ORD/000163/2024-2025 | 451/RSD | 11/09/2024 | 15 | GOURANGA MONDAL | 0.75 | 0 | 0
458 | Birbhum Division | Rampurhat Sub-Division | Providing Left out FHTC for declaration of Swajal Gram Village at Gamira & Sehala Mouzas under Raypur Zone I Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. (Sl. No. - 02) | AE | JE3 | ORD/000164/2024-2025 | 452/RSD | 11/09/2024 | 15 | GOURANGA MONDAL | 0.68 | 0 | 0
459 | Birbhum Division | Rampurhat Sub-Division | Providing Left out FHTC and allied work for declaration of Swajal Gram Village at Tajpur Mouzas under Raypur Zone I Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. (Sl. No. -03) | AE | JE3 | ORD/000167/2024-2025 | 453/RSD | 11/09/2024 | 385 | SOUMEN DAS | 0.97 | 0 | 100
460 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raipur Zone-II Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.13) | AE | JE3 | ORD/000433/2021-2022 | 24/BHM | 06/01/2022 | 60 | SK ALIM | 75.03 | 0 | 97
461 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raipur Zone-I Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.12) | AE | JE3 | ORD/000480/2021-2022 | 279/BHM | 09/02/2022 | 60 | PRADIP KUMAR SHARMA | 76.52 | 0 | 50
462 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000030/2024-2025 | 2453/BHM | 30/08/2024 | 0 | Resource Division | 5.09 | 0 | 0
463 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000075/2022-2023 | 1392/BHM | 24/04/2023 | 0 | Resource Division | 54.79 | 0 | 0
464 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Gokrui & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000578/2023-2024 | 3382/Bol.MD | 16/10/2023 | 90 | SATYAJIT GHOSH | 51.95 | 0 | 0
465 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at DERPUR, KURUMSAHA & MATIARA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000056/2023-2024 | 1245/BHM | 17/04/2023 | 1074 | BRAHMA CONSTRUCTION COMPANY | 978.83 | 0 | 65
466 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000100/2023-2024 | 1480/BHM | 25/04/2023 | 0 | Resource Division | 24.21 | 0 | 0
467 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR DERPUR WS SCHEME | AE,Assistant Engineer | JE,Junior Engineer | BILL/00703/2023-2024 | BP-2023-2024-56 | 02/08/2023 | 0 | WBSEDCL | 3.31 | 0 | 0
468 | Bolpur Mechanical | Birbhum Sadar Sub-Division | QUOTATION BILL FOR DERPUR WS SCHEME | AE,Assistant Engineer | JE,Junior Engineer | BILL/01353/2023-2024 | BP-23-24-149 | 28/11/2023 | 0 | WBSEDCL | 5.48 | 0 | 0
469 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Derpur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000775/2022-2023 | 313/Bol.MD | 24/03/2023 | 739 | EMCON | 28.71 | 0 | 50
470 | Central Drilling | Birbhum Sadar Sub-Division | Hiring of Diesel driven motor cab (BS-III & Above) (Non AC) having contract carriage permit along with driver for the office of the DIC/ CMSD-I P.H.E. Dte. Under CMSD-I(D), CDD, P.H.E. Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000188/2023-2024 | 290/CMSD-I(D) | 18/12/2023 | 182 | SUJATA BHOWMICK | 0.86 | 0 | 30
471 | Central Drilling | Birbhum Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR DERPUR W/S SCH (TW-II), SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000309/2022-2023 | 1427/CDD | 29/11/2022 | 30 | C.M. ENTERPRISE | 10.49 | 0 | 0
472 | Central Drilling | Birbhum Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150 MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR DERPUR W/S SCHEME (TW-I), SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000384/2022-2023 | 1426/CDD | 29/11/2022 | 30 | C.M. ENTERPRISE | 10.49 | 0 | 0
473 | Central Drilling | Birbhum Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR DERPUR W/S SCHEME, UNDER CDD, PHE DTE. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000513/2022-2023 | 1429/CDD | 29/11/2022 | 30 | C.M. ENTERPRISE | 10.49 | 0 | 100
474 | Central Drilling | Birbhum Sadar Sub-Division | Providing drilling crews for construction of Tube Well by departmental Rig machine in Derpur (TW-IV), Block - Sainthia, Birbhum District under CDD, P.H.E. Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000530/2022-2023 | 494/CMSD-I | 28/09/2022 | 15 | C.M. ENTERPRISE | 3.77 | 0 | 100
475 | Central Drilling | Birbhum Sadar Sub-Division | Supply & Delivery of Consumables with other works at site for construction of tubewell in Derpur (TW-IV) , Block - Sainthia, Birbhum District under CDD , PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000531/2022-2023 | 493/CMSD-I | 28/09/2022 | 15 | C.M. ENTERPRISE | 2.66 | 0 | 100
476 | Central Drilling | Birbhum Sadar Sub-Division | Providing Tube well materials , conforming to IS : 12818 2010 with other works at site for construction of Tube Well in Derpur (TW-I), Block -Sainthia, Birbhum District under CDD, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000532/2022-2023 | 486/CMSD-I | 23/09/2022 | 15 | C.M. ENTERPRISE | 4.18 | 0 | 100
477 | Central Drilling | Birbhum Sadar Sub-Division | Supply & Delivery of Consumables with other works at site for construction of tubewell in Derpur (TW-II), Block - Sainthia, Birbhum District under CDD , PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000533/2022-2023 | 495/CMSD-I | 28/09/2022 | 15 | C.M. ENTERPRISE | 2.66 | 0 | 100
478 | Central Drilling | Birbhum Sadar Sub-Division | Providing drilling crews for construction of Tube Well by departmental Rig machine in Derpur (TW-II), Block Sainthia , Birbhum District under CDD, P.H.E. Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000534/2022-2023 | 487/CMSD-I | 23/09/2022 | 15 | C.M. ENTERPRISE | 3.77 | 0 | 100
479 | Central Drilling | Birbhum Sadar Sub-Division | Providing Tube well materials , conforming to IS : 12818 2010 with other works at site for construction of Tube Well in Derpur (TW-III) , Block-Sainthia, Birbhum District under CDD, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000535/2022-2023 | 488/CMSD-I | 23/09/2022 | 15 | C.M. ENTERPRISE | 4.18 | 0 | 100
480 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at ALBANDHA, BERGRAM & BIDYADHARPUR Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000387/2023-2024 | 4146/BHM | 19/10/2023 | 805 | AMAL DUTTA ROY | 1648.21 | 0 | 12
481 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | RTOR000085/2022-2023 | 1357/BHM | 24/04/2023 | 0 | Resource Division | 13.87 | 0 | 0
482 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
483 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at BANSHANKA & HATIKARA its adjoining mouzas water supply scheme within SURI - II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000038/2023-2024 | 1181/BHM | 12/04/2023 | 1041 | MAHAVIR PUMPS MFG PVT LTD | 773.9 | 0 | 5
484 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000042/2022-2023 | 1385/BHM | 24/04/2023 | 0 | Resource Division | 6.68 | 0 | 0
485 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Bansankha PH-I W/S scheme Block-Suri II under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | BILL/00126/2024-2025 | BP-2024-2025-57 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7 | 0 | 0
486 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Bansankha PH-II W/S scheme Block-Suri II under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | BILL/00131/2024-2025 | BP-2024-2025-58 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.74 | 0 | 0
487 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Banshanka & Adjoining moujas water supply scheme at Suri -II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000885/2023-2024 | 3361/Bol.MD | 10/10/2023 | 60 | M/S. S.S. ENTERPRISE | 27.27 | 0 | 45
488 | Birbhum Division | Bolpur Sub-Division | Construction of 200 CuM.capacity OHR with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements,laying Rising Main,Distribution System with FHTC and different works related to BHEPUR PIPED WATER SUPPLY SCHEME (TSM/015433) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000105/2024-2025 | 2109/BHM | 29/07/2024 | 730 | MAMATA USHA ENTERPRISE | 382.93 | 0 | 35
489 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHEPUR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000640/2022-2023 | 144/BSD | 12/04/2022 | 90 | RADIANT | 4.36 | 0 | 100
490 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000027/2024-2025 | 2450/BHM | 30/08/2024 | 0 | Resource Division | 9.25 | 0 | 0
491 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000172/2023-2024 | 2178/BHM | 23/06/2023 | 0 | Resource Division | 8.91 | 0 | 0
492 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Bhepur WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000959/2024-2025 | 4528/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.08 | 0 | 60
493 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
494 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
495 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at MATIKONA, NOHONA, SHIRSHA & CHUNPALASHI Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000278/2023-2024 | 3598/BHM | 21/08/2023 | 949 | BIPIN KUMAR SINGH | 2395.67 | 0 | 4
496 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHUNPALASHI Piped Water Supply Scheme within command area of Illambazar Development Block under Bolpur Sub-Division within Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/001145/2021-2022 | 121/BSD | 31/03/2022 | 90 | M/S R DUTTA & CO. | 4.29 | 0 | 100
497 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | RTOR000080/2023-2024 | 1533/BHM | 26/04/2023 | 0 | Resource Division | 47.92 | 0 | 0
498 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
499 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at MATIKONA, NOHONA, SHIRSHA & CHUNPALASHI Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000278/2023-2024 | 3598/BHM | 21/08/2023 | 949 | BIPIN KUMAR SINGH | 2395.67 | 0 | 4
500 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | RTOR000171/2023-2024 | 2174/BHM | 23/06/2023 | 0 | Resource Division | 136.35 | 0 | 0
501 | Bolpur Mechanical | Bolpur Sub-Division | New service connection for Nohona PWSS (Block- Illambazar) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | BILL/00136/2024-2025 | BP-2024-2025-55 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.61 | 0 | 0
502 | Bolpur Mechanical | Bolpur Sub-Division | Providing Electro-mechanical accessories and others for Nohana & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000531/2023-2024 | 2172/Bol.MD | 01/09/2023 | 519 | M/S. UTTAM KUMAR CHATTERJEE | 14.97 | 0 | 80
503 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
504 | Birbhum Division | Birbhum Sadar Sub-Division | Sinking of 150 mm. X 100 mm Dia deep tubewell , construction of 100 CuM capacity O.H.R.with soil Investigation, Pump room/ Chlorine room with/without sanitary arrangements( different size),and laying of Rising main, Laying distribution with FHTC and different works related to SEKUPUR & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE | JE3 | ORD/000104/2024-2025 | 2111/BHM | 29/07/2024 | 365 | MAMATA USHA ENTERPRISE | 243.97 | 0 | 20
505 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE3 | RTOR000026/2024-2025 | 2449/BHM | 30/08/2024 | 0 | Resource Division | 4.69 | 0 | 0
506 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE3 | RTOR000081/2022-2023 | 1403/BHM | 24/04/2023 | 0 | Resource Division | 9.14 | 0 | 0
507 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Sekupur PWSS at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | AE | JE3 | ORD/000436/2023-2024 | 2108/BOL.MD. | 22/08/2023 | 60 | QUAZI NOZRUL ISLAM | 28 | 0 | 0
508 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000031/2024-2025 | 2487/BHM | 03/09/2024 | 0 | Resource Division | 8.26 | 0 | 0
509 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000076/2022-2023 | 1394/BHM | 24/04/2023 | 0 | Resource Division | 67.88 | 0 | 0
510 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing Electro-mechanical accessories and others for Kukutia & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000936/2023-2024 | 3393/Bol.MD | 17/10/2023 | 90 | S.K.ELECTRICALS | 52.82 | 0 | 60
511 | Birbhum Division | Bolpur Sub-Division | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000084/2024-2025 | 1948/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0
512 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for PANCHPARA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000658/2022-2023 | 179/BSD | 05/05/2022 | 180 | APEX ENGINEERING | 3.87 | 0 | 100
513 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000008/2024-2025 | 2395/BHM | 27/08/2024 | 0 | Resource Division | 11.4 | 0 | 0
514 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Panchpara PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001132/2024-2025 | 333/BOL.MD | 19/02/2025 | 240 | PADMA ENGINEERING CO. | 75.59 | 0 | 50
515 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
516 | Birbhum Division | Birbhum Division | Different Works for PURBA BANKATI & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. Sl No 03 | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000509/2022-2023 | 675/BHM | 01/03/2023 | 670 | MUKHERJEE ENTERPRISE | 152.12 | 0 | 68
517 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | RTOR000038/2022-2023 | 1383/BHM | 24/04/2023 | 0 | Resource Division | 8.65 | 0 | 0
518 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR PURBA BANKATI WS SCHEME | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | BILL/01786/2023-2024 | BP-23-24-248 | 29/01/2024 | 0 | WBSEDCL | 10.18 | 0 | 0
519 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Purba Bankati & Adjoining moujas water supply scheme at Suri - I Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/001105/2023-2024 | 3314/BOL.MD | 29/09/2023 | 579 | BENGAL CONSTRUCTION | 19.05 | 0 | 45
520 | Birbhum Division | Birbhum Division | Different works related to water supply scheme at DABUK & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000004/2023-2024 | 1083/BHM | 06/04/2023 | 1000 | ZEBA CONSTRUCTION | 270.01 | 0 | 60
521 | Birbhum Division | Birbhum Division | Continuation Work Order for Preparation & Submission of DPR for (Dabuk) Water Supply Scheme under Mayureswar-I Development Block. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000624/2022-2023 | 205/RSD | 13/06/2022 | 90 | ENVIROTECH SOLUTIONS | 3.58 | 0 | 100
522 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | RTOR000113/2023-2024 | 1508/BHM | 26/04/2023 | 0 | Resource Division | 21.69 | 0 | 0
523 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | RTOR000201/2023-2024 | 199/BHM | 22/01/2024 | 0 | Resource Division | 4.13 | 0 | 0
524 | Bolpur Mechanical | Birbhum Division | New service connection at Dabuk PH-II PWSS, Mayureswar -I Block, Under Bolpur Mechanical Division , P.H.E Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | BILL/00111/2024-2025 | BP-2024-2025-52 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.01 | 0 | 0
525 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR DABUK P H NO 1 WS SCHEME UNDER BOL MD PHE DTE | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | BILL/01439/2023-2024 | BP-23-24-177 | 07/12/2023 | 0 | WBSEDCL | 3.77 | 0 | 0
526 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Dabuk PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000523/2023-2024 | 2154/Bol.MD | 28/08/2023 | 60 | M/S SAJAHAN CHOWDHURY | 44.02 | 0 | 30
527 | Bolpur Mechanical | Birbhum Division | Supply & delivery of UPVC Column pipes at store for Dabuk piped water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000585/2024-2025 | 1479./AE-III | 11/09/2024 | 7 | MAA TARA ENTERPRISE | 1.53 | 0 | 100
528 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at BAJITPUR & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (SL NO 05) | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000525/2022-2023 | 618/BHM | 27/02/2023 | 733 | S.D CONSTRUCTION | 278.84 | 0 | 60
529 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Bajitpur) Water Supply Scheme under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000563/2022-2023 | 185/RSD | 06/05/2022 | 90 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 100
530 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000098/2023-2024 | 1532/BHM | 26/04/2023 | 0 | Resource Division | 6.01 | 0 | 0
531 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000199/2023-2024 | 197/BHM | 22/01/2024 | 0 | Resource Division | 2.18 | 0 | 0
532 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION BILL FOR BAJITPUR WS SCHEME | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/01152/2023-2024 | BP-23-24-94 | 26/09/2023 | 0 | WBSEDCL | 2.93 | 0 | 0
533 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR RBAJITPUR ws scheme | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/01843/2023-2024 | BP-23-24-264 | 07/02/2024 | 0 | WBSEDCL | 1.7 | 0 | 0
534 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Bajitpur PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000350/2023-2024 | 1747/Bol.MD | 27/07/2023 | 609 | MAHADEV ENTERPRISE | 43.79 | 0 | 97
535 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of Chlorinat0r at Bajitpur Piped Water Supply Scheme under Bolpur Mechanical Division ,P.H.E. Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000369/2024-2025 | 1192./AE-III | 12/08/2024 | 10 | R.K.ENTERPRISE | 0.9 | 0 | 100
536 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of UPVC Column pipes at store for Bajitpur water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000445/2024-2025 | 1298./AE-III | 27/08/2024 | 7 | MS SM ELECTRICAL | 1.9 | 0 | 100
537 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of openwell submersible pumping machinery for Bajitpur Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000606/2024-2025 | 1457./AE-III | 09/09/2024 | 7 | M/S. UTTAM KUMAR CHATTERJEE | 2.87 | 0 | 100
538 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of Submersible Cable acceessories for Bajitpur Piped water supply scheme. under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000618/2024-2025 | 1202./AE-III | 16/08/2024 | 10 | J.K.ENGINEERING CO | 0.92 | 0 | 100
539 | Bolpur Mechanical | Rampurhat Sub-Division | Operation and Guarding of pumping machinery and others at Bajitpur warer Supply scheme,Pump House No-I under Bolpur Mechanical Division,P.H.E Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000714/2024-2025 | 1079./AE-III | 29/07/2024 | 31 | MAHADEV ENTERPRISE | 0.3 | 0 | 0
540 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Delivery of Pumping Machinery for Bajitpur Water Supply Scheme Block Mayureswar ¿I under Bolpur Mechanical Division PHE. Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001324/2023-2024 | 615/AE-III | 27/03/2024 | 7 | MAHADEV ENTERPRISE | 1.49 | 0 | 100
541 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at SHRICHANDRAPUR Piped Water Supply Scheme within Illambazar Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | Assistant Engineer | JE1 | ORD/000071/2023-2024 | 1345/BHM | 20/04/2023 | 833 | RADHARANI ENTERPRISE | 165.15 | 0 | 5
542 | Bolpur Mechanical | Bolpur Sub-Division | NEW SERVICE CONNECTION AT SHRICHNDRAPUR PWSS PH-I | Assistant Engineer | JE1 | BILL/00838/2024-2025 | BP-24-25-190 | 24/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.57 | 0 | 0
543 | Bolpur Mechanical | Bolpur Sub-Division | NEW SERVICE CONNECTION FOR AT SHRICHANDRAPUR PWSS PH-II | Assistant Engineer | JE1 | BILL/00971/2024-2025 | BP-24-25-267 | 25/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.22 | 0 | 0
544 | Bolpur Mechanical | Bolpur Sub-Division | Additional quotation for extra involvement of materials against application no - 5004294122 at Shrichandrapur PWSS, P/H- I under Illambazar CCC | Assistant Engineer | JE1 | BILL/01019/2024-2025 | BP-24-25-273 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.54 | 0 | 0
545 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer | JE1 | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
546 | Birbhum Division | Rampurhat Sub-Division | Different works related to Water Supply Scheme at DUNA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000057/2023-2024 | 1249/BHM | 17/04/2023 | 806 | CREATIVE CONSTRUCTION | 473.21 | 0 | 50
547 | Birbhum Division | Rampurhat Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
548 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (DUNA) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000838/2022-2023 | 296/RSD | 07/09/2022 | 45 | ENVIROTECH SOLUTIONS | 3.22 | 0 | 100
549 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (DUNA) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000839/2022-2023 | 423/RSD | 03/11/2022 | 45 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 100
550 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000051/2023-2024 | 1518/BHM | 26/04/2023 | 0 | Resource Division | 36.07 | 0 | 0
551 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000210/2023-2024 | 208/BHM | 22/01/2024 | 0 | Resource Division | 1.54 | 0 | 0
552 | Bolpur Mechanical | Rampurhat Sub-Division | Supply, Delivewry and storage of vacuum operated gaseous Chlorination system for Duna PWSS, Block : Mayureswar-II under Bolpur Mechanical Division.PHE.DTE. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000515/2024-2025 | 3761/Bol.MD | 12/09/2024 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 28.84 | 0 | 0
553 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Duna PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000842/2023-2024 | 3281/BOL.MD | 29/09/2023 | 702 | DEY ENTERPRISE | 55.7 | 0 | 61
554 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Duna PWSS under Mayureswar - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/001236/2023-2024 | 521/BOL.MD | 14/03/2024 | 60 | PRADIP KUMAR DHABAL | 7.62 | 0 | 0
555 | Birbhum Division | Bolpur Sub-Division | Construction of 200 CuM capacity O.H.R.with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements,laying of Rising Main,Distribution System with FHTC and different works related to RANIBAZAR PIPED WATER SUPPLY SCHEME (TSM/017432) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000160/2024-2025 | 2664/BHM | 13/09/2024 | 365 | PATHIK PABAN NANDI | 417.11 | 0 | 0
556 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for RANIBAZAR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000647/2022-2023 | 187/BSD | 11/05/2022 | 90 | RADIANT | 4 | 0 | 100
557 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | RTOR000042/2023-2024 | 1514/BHM | 26/04/2023 | 0 | Resource Division | 14.12 | 0 | 0
558 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Ranibazar WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000958/2024-2025 | 4527/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.08 | 0 | 50
559 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
560 | Birbhum Division | Rampurhat Sub-Division | Balance work for Laying & distribution system with HDPE pipes and Specials including FHTC (Functional Household Tap Connection ) at Chandipur mouza for Improvement of Tarapith piped W/S Scheme under Birbhum Division, PHE Dte. (Sl. No.15) | AE | JE1 | ORD/000494/2022-2023 | 286/BHM | 01/02/2023 | 45 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 99.59 | 0 | 0
561 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at TATINAPARA PIPED WATER SUPPLY SCHEME (TSM/015894) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte.(2nd Call) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000390/2023-2024 | 4150/BHM | 21/10/2023 | 274 | TEKNO ENTERPRISE | 606.61 | 0 | 0
562 | Birbhum Division | Bolpur Sub-Division | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for TATINAPARA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.¿. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000951/2022-2023 | 268/BSD | 15/07/2022 | 90 | APEX ENGINEERING | 4.92 | 0 | 100
563 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
564 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at Madhupur, Khamedda & Bara-Karttikchungri and its adjoining mouzas water supply scheme within Rampurhat-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000395/2023-2024 | 4163/BHM | 30/10/2023 | 560 | M/S ASHA CONSTRUCTION | 1089.94 | 0 | 40
565 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Khamedda) Water Supply Scheme under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000636/2022-2023 | 262/RSD | 27/07/2022 | 45 | ECO CARE | 4.73 | 0 | 100
566 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000087/2023-2024 | 1583/BHM | 26/04/2023 | 0 | Resource Division | 26.44 | 0 | 0
567 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000230/2023-2024 | 225/BHM | 24/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
568 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Khamedda PWSS P.H No-I (Block-Rampurhat - II), Margram CCC, WBSEDCL | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/00123/2024-2025 | BP-2024-2025-61 | 05/06/2024 | 0 | WBSEDCL | 2.75 | 0 | 0
569 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Khamedda P/H-II PWSS (Mouza- Khamedda) at Block-Rampurhat-II | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/01090/2024-2025 | BP-24-25-283 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.58 | 0 | 0
570 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Khameda PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000471/2023-2024 | 2224/Bol.MD | 12/09/2023 | 567 | HINDOL ROY | 45.7 | 0 | 50
571 | Birbhum Division | Birbhum Sadar Sub-Division | Trial Bore and Sinking of 200 mm dia. tubewell (2 nos.) 30 m. Deep fitted with M.S.E.R.W. Housing pipe and Fibre Glass Strainer on the river bank of Mayurakshi for the Augmentation of Mathpalsa Piped Water Supply Scheme under Birbhum Sadar Sub-Division PHE Dte. with Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000123/2023-2024 | 1984/BHM | 05/06/2023 | 30 | INDRAJIT DUTTA. | 3.38 | 0 | 0
572 | Birbhum Division | Birbhum Sadar Sub-Division | Balance work for laying of pipe line including FHTC for augmentation of Mathpalsa Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. . | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000132/2023-2024 | 2075/BHM | 08/06/2023 | 602 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 45.68 | 0 | 100
573 | Birbhum Division | Birbhum Sadar Sub-Division | Providing FHTC and laying of pipe line for the villages rest portion of Rongaipur & Mathpalsa & all other allied works under Augmentation of Mathpalsa Piped Water Supply Scheme, Sainthia Block under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000146/2024-2025 | 2516/BHM | 04/09/2024 | 363 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 35.86 | 0 | 70
574 | Birbhum Division | Birbhum Sadar Sub-Division | Laying distribution system including FHTC for proposed Augmentation scheme for Mathpalsa Piped Water Supply Scheme , Sainthia Block under Birbhum Dvisision PHE DTE (Sl.No.2) | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000338/2022-2023 | 1160/BHM | 23/05/2022 | 180 | APURBA MONDAL | 144.13 | 0 | 100
575 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000179/2023-2024 | 2244/BHM | 07/07/2023 | 0 | Resource Division | 2.09 | 0 | 0
576 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000192/2023-2024 | 3276/BHM | 27/07/2023 | 0 | Resource Division | 1.14 | 0 | 0
577 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Mathpalsa water supply scheme (P.H. No.-III) under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000006/2023-2024 | 715/Bol.MD | 19/04/2023 | 45 | BIRBHUM ELECTRIC WORKS | 12.72 | 0 | 60
578 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply and delivery and installation of MCC panel at NOHANA PWSS (Mathpalsa) in Sainthia block under Bolpur Mechanical Division, P.H.E. Dte | AE,Assistant Engineer | JE3,Junior Engineer | ORD/001379/2023-2024 | 561/BOL.MD | 15/03/2024 | 180 | BIRBHUM ELECTRIC WORKS | 8.74 | 0 | 100
579 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at KANKSA & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000089/2023-2024 | 1879/BHM | 31/05/2023 | 761 | PRANAB KUMAR GHOSH | 229 | 0 | 65
580 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Kanska) Water Supply Scheme under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000631/2022-2023 | 230/RSD | 27/06/2022 | 90 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 100
581 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000021/2023-2024 | 1447/BHM | 25/04/2023 | 0 | Resource Division | 5.45 | 0 | 0
582 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000203/2023-2024 | 206/BHM | 22/01/2024 | 0 | Resource Division | 3.91 | 0 | 0
583 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR KANKSA P H NO -2 WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01438/2023-2024 | BP-23-24-178 | 07/12/2023 | 0 | WBSEDCL | 3.82 | 0 | 0
584 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR PURBA KANKSA P H NO II WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01789/2023-2024 | BP-23-24-256 | 06/02/2024 | 0 | WBSEDCL | 5.76 | 0 | 0
585 | Bolpur Mechanical | Rampurhat Sub-Division | Supplly & delivery of pumping machinery Kanksa water supply scheme Block- Mayureswar-I under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000004/2024-2025 | 690./AE-III | 08/04/2024 | 14 | GOENKA ENTERPRISE | 1.48 | 0 | 100
586 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Kanksa PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000524/2023-2024 | 2155/Bol.MD | 28/08/2023 | 60 | GOENKA ENTERPRISE | 44.03 | 0 | 50
587 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at BIRCHANDRAPUR, ASURLAYA, BARATURIGRAM & KANAIPUR and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000471/2023-2024 | 505/BHM | 05/02/2024 | 603 | B RAI CONSTRUCTION COMPANY | 2071.77 | 0 | 20
588 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (BIRCHANDRAPUR) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000802/2022-2023 | 286/RSD | 29/08/2022 | 90 | ENVIROTECH SOLUTIONS | 3.5 | 0 | 100
589 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (BIRCHANDRAPUR) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000803/2022-2023 | 360/RSD | 20/09/2022 | 90 | ENVIROTECH SOLUTIONS | 3.43 | 0 | 100
590 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000125/2023-2024 | 1540/BHM | 26/04/2023 | 0 | Resource Division | 51.95 | 0 | 0
591 | Bolpur Mechanical | Rampurhat Sub-Division | New service connection charges at Birchandrapur PH-III PWSS. | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/00825/2024-2025 | BP-24-25-186 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.65 | 0 | 0
592 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Birchandrapur PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000734/2023-2024 | 3477/Bol.MD | 07/11/2023 | 602 | EASTERN INDIA SALES & SERVICE | 67.61 | 0 | 60
593 | Bolpur Mechanical | Rampurhat Sub-Division | Additional work in connection with Providing and Installation of Submersible pumping Machineries at newly sunk Tube Wells and allieds works at Birchandrapur Piped Water Supply Scheme, Block-Mayureswar-I, under Bolpur Mechanical Division. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001210/2023-2024 | 372/BOL.MD | 06/03/2024 | 30 | SARKAR ELECTRICAL | 18.22 | 0 | 77
594 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Hiring of 01(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, PHE Dte. under Birbhum Division, PHE Dte. For the period of 01.01.2025 to 30.06.2025" for another 03(Three) months i.e. 01.07.2025 to 30.09.2025. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000095/2025-2026 | 640/BSD | 20/06/2025 | 92 | RAJIYA BIBI | 0.43 | 0 | 0
595 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at ALBANDHA, BERGRAM & BIDYADHARPUR Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000387/2023-2024 | 4146/BHM | 19/10/2023 | 805 | AMAL DUTTA ROY | 1648.21 | 0 | 12
596 | Birbhum Division | Bolpur Sub-Division | Hiring of 01(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, PHE Dte. under Birbhum Division, PHE Dte. For the period of 01.01.2025 to 30.06.2025. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000543/2024-2025 | 1237/BSD | 31/12/2024 | 181 | RAJIYA BIBI | 0.85 | 0 | 0
597 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | RTOR000104/2023-2024 | 1547/BHM | 26/04/2023 | 0 | Resource Division | 219.35 | 0 | 0
598 | Bolpur Mechanical | Bolpur Sub-Division | WBSEDCL QUOTATION FOR ALBANDHA WS SCHEME | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | BILL/01591/2023-2024 | BP-23-24-221 | 15/01/2024 | 0 | WBSEDCL | 5.28 | 0 | 0
599 | Bolpur Mechanical | Bolpur Sub-Division | Providing Electro-mechanical accessories and others for Albandha & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000478/2023-2024 | 2238/BOL.MD. | 13/09/2023 | 90 | DEY ENTERPRISE | 73.35 | 0 | 50
600 | Bolpur Mechanical | Bolpur Sub-Division | Supply and delivery of column pipe for albandha water supply scheme(T/W-I) under BOL MD, PHE Dte.. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000550/2024-2025 | 3805/BOL.MD | 12/09/2024 | 20 | SATYAJIT GHOSH | 2.52 | 0 | 100
601 | Bolpur Mechanical | Bolpur Sub-Division | Supply and delivery of Submersible pump for albandha Water Supply under Bolpur Mechanical Divn. PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000552/2024-2025 | 3806/BOL.MD | 12/09/2024 | 20 | M/S. YOUTH ENGINEERS' ENTERPRISE | 2.48 | 0 | 100
602 | Bolpur Mechanical | Bolpur Sub-Division | Supply & delivery of submersible cable accessories at albandha Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000572/2024-2025 | 3843/BOL.MD | 18/09/2024 | 20 | UNITED TRADERS | 2.15 | 0 | 100
603 | Bolpur Mechanical | Bolpur Sub-Division | Supply and delivery of 80 mm UPVC standard type column pipe (Cream colour) for albandha water supply scheme(T/W-II) under BOL MD, PHE Dte.. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000815/2024-2025 | 4195/BOL.MD | 22/10/2024 | 20 | M. S. ENTERPRISE | 2.6 | 0 | 100
604 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
605 | Central Drilling | Bolpur Sub-Division | Hiring of Diesel driven motor cab (BS-III & Above) (Non AC) having contract carriage permit along with driver for the office of the DIC/ CMSD-I P.H.E. Dte. Under CMSD-I(D), CDD, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000054/2024-2025 | 378/CMSD-I | 24/12/2024 | 182 | SUJATA BHOWMICK | 0.86 | 0 | 0
606 | Birbhum Division | Rampurhat Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at DHALLA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000113/2024-2025 | 2180/BHM | 06/08/2024 | 365 | RADIANT | 497.94 | 0 | 40
607 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (DHALLA) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000787/2022-2023 | 294/RSD | 07/09/2022 | 45 | ECO CARE | 2.76 | 0 | 100
608 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (DHALLA) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000798/2022-2023 | 383/RSD | 27/09/2022 | 45 | ECO CARE | 3.27 | 0 | 100
609 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000025/2023-2024 | 1521/BHM | 26/04/2023 | 0 | Resource Division | 55.13 | 0 | 0
610 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000041/2024-2025 | 2484/BHM | 03/09/2024 | 0 | Resource Division | 13.92 | 0 | 0
611 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Dhalla PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000472/2023-2024 | 2225/Bol.MD | 12/09/2023 | 628 | QUAZI NOZRUL ISLAM | 44.4 | 0 | 30
612 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Dhalla PWSS under Illambazar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/001235/2023-2024 | 520/BOL.MD | 14/03/2024 | 60 | AMITAVA CHAKRABORTY | 7.61 | 0 | 0
613 | Birbhum Division | Bolpur Sub-Division | Construction of 250 & 150 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main, Distribution System with FHTC including different works related to SANTOSHPUR / NAWADA PALANDI /PAPURI / SAJNOR / RAYEN PIPED WATER SUPPLY SCHEME (5 Nos Scheme) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division PHE DTE. | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000085/2024-2025 | 1951/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2322.64 | 0 | 5
614 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for SANTOSHPUR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000649/2022-2023 | 209/BSD | 25/05/2022 | 90 | RADIANT | 4.73 | 0 | 100
615 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | RTOR000003/2024-2025 | 2383/BHM | 27/08/2024 | 0 | Resource Division | 10.16 | 0 | 0
616 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | RTOR000073/2023-2024 | 1464/BHM | 25/04/2023 | 0 | Resource Division | 19.69 | 0 | 0
617 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Santoshpur Water supply Scheme (T/W-I & II), Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000963/2024-2025 | 4533/BOL.MD | 20/12/2024 | 120 | PADMA ENGINEERING CO. | 73.34 | 0 | 0
618 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
619 | Birbhum Division | Rampurhat Sub-Division | Different works related to Water Supply Scheme at SULTANPUR & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000161/2023-2024 | 2065/BHM | 08/06/2023 | 1027 | M/S.SUMAN CONSTRUCTION | 575.26 | 0 | 45
620 | Birbhum Division | Rampurhat Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
621 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (SULTANPUR) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000844/2022-2023 | 334/RSD | 08/09/2022 | 45 | ENVIROTECH SOLUTIONS | 3.54 | 0 | 100
622 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (SULTANPUR) Water Supply Scheme (Part-B) under Mayureswar-II Development Block | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000845/2022-2023 | 438/RSD | 29/11/2022 | 45 | ENVIROTECH SOLUTIONS | 3.5 | 0 | 100
623 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000212/2023-2024 | 200/BHM | 22/01/2024 | 0 | Resource Division | 11.4 | 0 | 0
624 | Bolpur Mechanical | Rampurhat Sub-Division | NEW SERVICE CONNECTION AT SULTANPUR PWSS PH-I UNDER BOLPUR MECHANICAL DIVISION PHE Dte... | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00022/2024-2025 | BP-24-25-09 | 25/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.36 | 0 | 0
625 | Bolpur Mechanical | Rampurhat Sub-Division | New service connection at Sultanpur PWSS ( P/H- 3) | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00112/2024-2025 | BP-2024-2025-51 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.94 | 0 | 0
626 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for New Service connection at Sultanpur PWSS P/H-3 (Bolck- Mayureswar-II) | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00155/2024-2025 | BP-2024-2025-81 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.25 | 0 | 0
627 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Sultanpur PWSS P/H- IV (Block- Mayureswar -II) | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00156/2024-2025 | BP-2024-2025-80 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.56 | 0 | 0
628 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Sultanpur PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000836/2023-2024 | 3275/BOL.MD | 29/09/2023 | 60 | M. S. ENTERPRISE | 67.76 | 0 | 40
629 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Sultanpur PWSS, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte.. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/001220/2023-2024 | 405/Bol.MD | 07/03/2024 | 45 | SATYAJIT GHOSH | 25.78 | 0 | 40
630 | Birbhum Division | Rampurhat Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at NARAYANPUR (Zone-I & Zone-II) & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materialsunder BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000190/2024-2025 | 2769/BHM | 30/09/2024 | 730 | M/S GHOSH AND CO. | 518.25 | 0 | 20
631 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000010/2023-2024 | 1125/BHM | 10/04/2023 | 0 | Resource Division | 14.94 | 0 | 0
632 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000102/2022-2023 | 972/BHM | 27/03/2023 | 0 | Resource Division | 102.97 | 0 | 0
633 | Bolpur Mechanical | Rampurhat Sub-Division | Supply,delivery and Installation of PDB cum MCC Panel and allieds works at Mayureswar water supply scheme ( under Augmentation of Narayanpur Piped Water Supply Scheme, Block-Rampurhat-II) under Bolpur Mechanical Division, P.H.E.Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000488/2023-2024 | 2243/BOL.MD. | 13/09/2023 | 566 | UTTAM KUMAR CHATTERJEE | 15.71 | 0 | 100
634 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Delivery of Voltage Correction Devices for Augmentation of Narayanpur (Zone-II) PWSS, (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000514/2024-2025 | 3778/BOL.MD | 12/09/2024 | 30 | SINHA ELECTRICALS | 41.51 | 0 | 100
635 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and installation of Submersible pumping Machineries and HL Pumping Machineries with allied works at Augmentation of Narayanpur (Zone - II) PWSS, Block-Rampurhat- II under Bolpur Mechanical Division PHED. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000529/2023-2024 | 2117/Bol.MD | 23/08/2023 | 648 | SINHA ELECTRICALS | 98.04 | 0 | 30
636 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Delivery of Sub-Mersible Pumping Machineries for Ground Based Tube Well for Narayanpur water supply scheme (Block- Rampurhat - I) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001041/2023-2024 | 1622/AE-III | 18/12/2023 | 21 | M/S. YOUTH ENGINEERS' ENTERPRISE | 1.87 | 0 | 100
637 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Wells and allieds works at Augmentation of Narayanpur water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001211/2023-2024 | 373/BOL.MD | 06/03/2024 | 30 | QUAZI NOZRUL ISLAM | 13.39 | 0 | 70
638 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well at Augmentation of Narayanpur (Zone-II) PWSS, (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001215/2023-2024 | 400/Bol.MD | 07/03/2024 | 420 | SINHA ELECTRICALS | 79.02 | 0 | 90
639 | Birbhum Division | Rampurhat Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
640 | Birbhum Division | Rampurhat Sub-Division | Different works related to Water Supply Scheme at RAMNAGAR & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000538/2022-2023 | 903/BHM | 22/03/2023 | 741 | M/S.SUMAN CONSTRUCTION | 433.92 | 0 | 65
641 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Ramnagar) Water Supply Scheme under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000622/2022-2023 | 203/RSD | 10/06/2022 | 45 | ENVIROTECH SOLUTIONS | 4.29 | 0 | 100
642 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000095/2023-2024 | 1485/BHM | 25/04/2023 | 0 | Resource Division | 18.81 | 0 | 0
643 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000209/2023-2024 | 202/BHM | 22/01/2024 | 0 | Resource Division | 5.83 | 0 | 0
644 | Bolpur Mechanical | Rampurhat Sub-Division | NEW POWER CONNECTION AT RAMNAGAR PWSS P/H No-II | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/00127/2024-2025 | BP-2024-2025-59 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.97 | 0 | 0
645 | Bolpur Mechanical | Rampurhat Sub-Division | NEW SERVICE CONNECTION AT RAMNAGAR PWSS P/H No-III | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/00128/2024-2025 | BP-2024-2025-60 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.33 | 0 | 0
646 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR RAMNAGAR P H NO I | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/01842/2023-2024 | BP-23-24-265 | 07/02/2024 | 0 | WBSEDCL | 12.33 | 0 | 0
647 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Ramnagar PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000875/2023-2024 | 3513/Bol.MD | 24/11/2023 | 60 | ORIENTAL ENGINEERING CO. | 55.45 | 0 | 65
648 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Ramnagar PWSS under Mayureswar - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/001241/2023-2024 | 532/BOL.MD | 14/03/2024 | 60 | S.B.ENTERPRISE(BOLPUR) | 7.6 | 0 | 66
649 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
650 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
651 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Hatikata & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000671/2022-2023 | 87/BSSD | 19/05/2022 | 45 | RADIANT | 1.88 | 0 | 100
652 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000242/2023-2024 | 433/BHM | 01/02/2024 | 0 | Resource Division | 54.82 | 0 | 0
653 | Birbhum Division | Rampurhat Sub-Division | Sinking of 250 mm.X 150 mm.Dia Tube Well (2 nos) Drilling by Direct Rotary method ,Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 200 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Radipur & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division,PHE Dte | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000156/2024-2025 | 2644/BHM | 12/09/2024 | 365 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD | 379.68 | 0 | 0
654 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000045/2024-2025 | 3259/BHM | 02/12/2024 | 0 | Resource Division | 10.57 | 0 | 0
655 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000139/2023-2024 | 1576/BHM | 26/04/2023 | 0 | Resource Division | 13.07 | 0 | 0
656 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Radipur & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000928/2023-2024 | 3528/Bol.MD | 29/11/2023 | 60 | ASHIM UDYOG | 27.61 | 0 | 0
657 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Hatina, Uchpur, Narayanpur, Gopinathpur ,Basudebpur in Basudebpur w/s Scheme under Rampurhat Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl. No.2) |  |  | ORD/000159/2021-2022 | 1286/BHM | 10/08/2021 | 60 | BANERJEE CONSTRUCTION | 36.47 | 0 | 100
658 | Birbhum Division |  | Allied works for Additional Laying of UPVC Pipe line for providing FHTC at Basudebpur mouza under Basudebpur PWSS under Rampurhat Sub- Division, P.H.E. Dte. |  |  | ORD/000505/2021-2022 | 02/RSD | 04/01/2022 | 30 | BANERJEE CONSTRUCTION | 2.62 | 0 | 100
659 | Birbhum Division |  | Allied works for Additional Laying of UPVC Pipe line for providing FHTC at mouza Chotto Bataspur, Gopinathpur & Uchpur within Basudebpur PWSS under Rampurhat Sub-Division, P.H.E. Dte. |  |  | ORD/000506/2021-2022 | 03/RSD | 04/01/2022 | 30 | SOIL STORY | 4.95 | 0 | 100
660 | Birbhum Division |  | Allied works for Providing FHTC from existing distributin system at Narayanpur mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte |  |  | ORD/000508/2021-2022 | 06/RSD | 04/01/2022 | 30 | M/S BUILDWELL | 4.99 | 0 | 0
661 | Birbhum Division |  | Providing FHTC from existing distributin system at Gargara mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. |  |  | ORD/000540/2021-2022 | 27/RSD | 04/01/2022 | 30 | JAYANTA BARAL | 4.99 | 0 | 80
662 | Birbhum Division |  | Providing FHTC from existing distributin system at Pukhur Para mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. |  |  | ORD/000541/2021-2022 | 28/RSD | 04/01/2022 | 30 | ABUL HASNAT | 5 | 0 | 100
663 | Birbhum Division |  | Allied works for Providing FHTC from existing distributin system at Hatina mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. |  |  | ORD/000579/2021-2022 | 05/RSD | 04/01/2022 | 30 | M/S BUILDWELL | 4.99 | 0 | 100
664 | Birbhum Division |  | Allied works for Providing FHTC from existing distributin system at Hatina mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. |  |  | ORD/000592/2020-2021 | 05/RSD | 04/01/2021 | 30 | M/S BUILDWELL | 4.99 | 0 | 100
665 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at BANSHANKA & HATIKARA its adjoining mouzas water supply scheme within SURI - II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000038/2023-2024 | 1181/BHM | 12/04/2023 | 1041 | MAHAVIR PUMPS MFG PVT LTD | 773.9 | 0 | 5
666 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000043/2022-2023 | 1386/BHM | 24/04/2023 | 0 | Resource Division | 19.08 | 0 | 0
667 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Hatikara PWSS at Suri - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000432/2023-2024 | 2105/BOL.MD. | 22/08/2023 | 60 | HINDOL ROY | 29.37 | 0 | 60
668 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
669 | Birbhum Division | Central Mechanical Sub-DivisionIII | Sinking of Tubewell, Construction of OHR, Construction of Boundary wall, pump house and laying distribution system along with FHTC works at Augmentation of Patharchapri & its adjoining mouzas water supply scheme within Suri - I Block under Birbhum Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000386/2023-2024 | 4143/BHM | 19/10/2023 | 787 | M/S GOUTAM DAS | 513.52 | 0 | 80
670 | Birbhum Division | Central Mechanical Sub-DivisionIII | Extension of distribution pipe line from Kushmasol to Chandpur, Nichupara and English Medium School and all other allied works for augmentation of Patharchapuri Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. | Assistant Engineer-III | Junior Engineer | ORD/000520/2023-2024 | 671/BHM | 20/02/2024 | 45 | SOURAV MONDAL | 5.23 | 0 | 100
671 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000001/2023-2024 | 1116/BHM | 10/04/2023 | 0 | Resource Division | 9.43 | 0 | 0
672 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000101/2022-2023 | 971/BHM | 27/03/2023 | 0 | Resource Division | 363.95 | 0 | 0
673 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply & installation of High Lift Pumping Machinery for (Zone - I & II) with other Electro-Mechanical accessories at Augmentation of Pathar Chapri Piped Water Supply Scheme, Block-Suri - I under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000492/2023-2024 | 2247/Bol.MD | 13/09/2023 | 615 | S.K.ELECTRICALS | 29.88 | 0 | 100
674 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply and Delivery of Sub-Mersible Pumping Machineries & others for Augmentation of Patharchapuri PWSS, (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000525/2024-2025 | 3786/BOL.MD | 12/09/2024 | 80 | DEY ENTERPRISE | 50.29 | 0 | 100
675 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Dalima, Kahinagar & Dumurgram and its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000080/2023-2024 | 1423/BHM | 25/04/2023 | 1090 | AKASH CONSTRUCTION | 1377.29 | 0 | 16
676 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000019/2023-2024 | 1434/BHM | 25/04/2023 | 0 | Resource Division | 9.84 | 0 | 0
677 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Kahinagar PWSS at Murarai - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000868/2023-2024 | 3286/BOL.MD | 29/09/2023 | 60 | MASSK ENGINEERING WORKS | 27.62 | 0 | 0
678 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others at Pump House- I & II for Bahadurpur W/S Scheme (Kahinagar PWSS) at Murarai -I Block under Bolpur Mechanical Division PHE Dte | AE,Assistant Engineer | JE3,Junior Engineer | ORD/001168/2024-2025 | 464/BOL.MD | 07/03/2025 | 30 | SUNIL RABIDAS | 5.5 | 0 | 0
679 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | RTOR000091/2022-2023 | 1362/BHM | 24/04/2023 | 0 | Resource Division | 133.81 | 0 | 0
680 | Bolpur Mechanical | Bolpur Sub-Division | WBSEDCL QUOTATION FOR MOSTALA WS SCHEME | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | BILL/01593/2023-2024 | BP-23-24-219 | 15/01/2024 | 0 | WBSEDCL | 5.37 | 0 | 0
681 | Bolpur Mechanical | Bolpur Sub-Division | Providing Electro-mechanical accessories and others for Mostala & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000486/2023-2024 | 2241/BOL.MD. | 13/09/2023 | 476 | SINHA ELECTRICALS | 85.42 | 0 | 78
682 | Bolpur Mechanical | Bolpur Sub-Division | Supply & delivery of submersible cable accessories at Mostala water supply scheme T.W No-I under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000553/2024-2025 | 3820/BOL.MD | 18/09/2024 | 20 | RAJIB GHOSH | 3.07 | 0 | 100
683 | Bolpur Mechanical | Bolpur Sub-Division | Supply & delivery of submersible cable accessories at mostala water supply scheme T.W No-II under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000558/2024-2025 | 3822/BOL.MD | 18/09/2024 | 20 | STANDARD ELECTRICALS | 2.8 | 0 | 100
684 | Bolpur Mechanical | Bolpur Sub-Division | Supply and delivery of Submersible pump for ikshudhara Water Supply Scheme(T/W - I) under Bolpur Mechanical Divn. PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000604/2024-2025 | 3850/BOL.MD | 18/09/2024 | 20 | SWAPAN BANERJEE | 2.62 | 0 | 100
685 | Bolpur Mechanical | Bolpur Sub-Division | Supply and delivery of Submersible pump for ikshudhara Water Supply Scheme (T/W-II) under Bolpur Mechanical Divn. PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000655/2024-2025 | 3873/BOL.MD | 19/09/2024 | 20 | M/S. S.S. ENTERPRISE | 2.75 | 0 | 0
686 | Bolpur Mechanical | Bolpur Sub-Division | Supply and delivery of M.S. seamless column pipe for Mostala water supply Scheme under BOL MD, PHE Dte.. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000814/2024-2025 | 4194/BOL.MD | 22/10/2024 | 20 | EASTERN INDIA SALES & SERVICE | 2.94 | 0 | 100
687 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
688 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Jamrand Bauripara, Fullaichack & Bartikuri under Jamrand Mouza (JL No. - 136) under Khoyrasole Block, within the command area of Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 32)) |  |  | ORD/000012/2021-2022 | 207/BSSD | 15/06/2021 | 30 | RICK CONSTRUCTION | 4.97 | 0 | 100
689 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Jamrand Chasapara under Jamrand Mouza (JL No.-136) under Khoyrasole Block,within the command area of Jamrand Piped w/s Scheme in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte. (SL No.-31) |  |  | ORD/000014/2021-2022 | 206/BSSD | 15/06/2021 | 30 | SUMAN CHOWDHURY | 4.97 | 0 | 100
690 | Birbhum Division |  | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. (Sl. No. ¿ 01) |  |  | ORD/000045/2022-2023 | 89/BSSD | 27/05/2022 | 20 | SK FAQHRUL AMIN | 4.99 | 0 | 100
691 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Beledanga area (J.L :- 142) Habitation of Rathtala under Beledanga Mouza under Suri- Khayrasole Block, within the command area of Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 07) |  |  | ORD/000177/2021-2022 | 285/BSSD | 13/08/2021 | 30 | B.M.SARKAR | 4.04 | 0 | 100
692 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Jamrand, Matiala Bhimgara in Jamrand w/s Scheme under Suri Sadar Sub Division within Birbhum Division, PHE Dte. (Sl. No.17) |  |  | ORD/000278/2020-2021 | 1709/BHM | 23/12/2020 | 60 | RICK CONSTRUCTION | 30.49 | 10 | 100
693 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Isgara, Narayanpur, Beldanga & Rajnagar in Jamrand w/s Scheme under Suri Sadar Sub Division within Birbhum Division, PHE Dte. (Sl. No.18) |  |  | ORD/000314/2020-2021 | 1708 /BHM | 23/12/2020 | 60 | PRAVAT SARKAR | 29.59 | 22.22 | 100
694 | Birbhum Division |  | Restoration of distribution pipe line at various location nearby Kabbarsthan, Bimgarh Bus Stand etc. for smooth running of FHTC under Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte.(Sl. No. - 15) |  |  | ORD/000514/2022-2023 | 226/BSSD | 21/09/2022 | 20 | GOUTAM MONDAL | 4.91 | 0 | 100
695 | Birbhum Division |  | Relaying of UPVC distribution Pipe line due to damage for construction of drain and reconnection of existing Household Tap Connection (FHTC) from Kendragaria Gram Panchayat Office towards Sarafat Khan house under Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H. E Dte. (Sl. No. - 07) |  |  | ORD/000985/2021-2022 | 405/BSSD | 14/12/2021 | 15 | GOUTAM MONDAL | 1.28 | 0 | 100
696 | Birbhum Division |  | Sinking of replacement the tubewell of 200mm dia & 60 m. deep with PVC pipe and fibre glass Strainer at Raghunathpur (near head work side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. |  |  | ORD/000001/2022-2023 | 209/AE/NSD | 05/04/2022 | 30 | MD AMINUL ISLAM | 3.74 | 0 | 100
697 | Birbhum Division |  | Extension of 63 & 75 mm Dia. UPVC Pipe line in Miapur,Barla,Bagbari & Barmaroi habitations for providing FHTC within Raghunathpur Piped Water Supply Scheme under Nalhati Sub-Division P.H.E Dte. |  |  | ORD/000011/2022-2023 | 226/NSD | 19/04/2022 | 45 | ENAMUL ISLAM | 3.59 | 0 | 100
698 | Birbhum Division |  | Continuation Work Order for Maintenance of Tube wells, Raw water rising main pipe line and CWR for the daily supply of water to the consumers under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. as mentioned below for 03 (Three) months only (from 18.06.2022 to 17.09.2022) of Raghunathpur Water Supply Scheme. |  |  | ORD/000128/2022-2023 | 314/AE/NSD | 17/06/2022 | 92 | SHIB GANGA CONSTRUCTION | 0.7 | 0 | 100
699 | Birbhum Division |  | Collection of Household Data Through Mobile APP/Hardcopy including Geo-reference and submission of the same in soft copy against completed FHTC works at the command area of Kaitha W/S Scheme under Birbhum Division. |  |  | ORD/000209/2021-2022 | 138/BH | 19/08/2021 | 10 | ENAMUL ISLAM | 0.1 | 0.16 | 0
700 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Bikandi, Saora in Raghunathpur w/s Scheme under Nahati Sub Division within Birbhum Division, PHE Dte. (Sl. No.5) |  |  | ORD/000227/2020-2021 | 141/BHM | 05/02/2021 | 60 | QUAZI SIRAJUL ISLAM. | 34.7 | 34.7 | 100
701 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raghunathpur w/s Scheme (Left out House Hold) in Nalhati Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.10) |  |  | ORD/000258/2021-2022 | 1507/BHM | 09/09/2021 | 60 | M/S MD AMINUL ISLAM | 37.25 | 0 | 100
702 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kadya, Raghunathpur in Raghunathpur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.6) |  |  | ORD/000315/2020-2021 | 142/BHM | 05/02/2021 | 60 | M/S MD AMINUL ISLAM | 36.49 | 36.49 | 100
703 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Dharampur in Raghunathpur w/s Scheme under Nahati Sub Division within Birbhum Division, PHE Dte. (Sl. No.7) |  |  | ORD/000358/2020-2021 | 143/BHM | 05/02/2021 | 60 | G. B. CONSTRUCTION AND CO. | 41.87 | 0 | 100
704 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Tailpara in Raghunathpur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.4) |  |  | ORD/000488/2020-2021 | 78/BHM | 27/01/2021 | 60 | S R ENTERPRISE | 25.48 | 5.48 | 50
705 | Birbhum Division |  | Balance estimate for construction of boundary wall near C.W.R Site including M.S. Ornamental grill railing at Raghunathpur Water Supply Scheme under Nalhati Sub Division P.H.E. Dte. |  |  | ORD/000604/2021-2022 | 589/AE/NSD | 22/11/2021 | 30 | BHARAT CONSTRUCTION | 2.85 | 0 | 100
706 | Birbhum Division |  | Laying distribution system From NP-58 towards Dharampur(079) under Raghunathpur PWSS under Nalhati Sub Division PHED. |  |  | ORD/000616/2021-2022 | 277/A/AE/NSD | 16/04/2021 | 30 | SUNIL RABI DAS | 0.97 | 0 | 0
707 | Birbhum Division |  | Laying distribution system From NP-135 towards NP-136 under Raghunathpur PWSS under Nalhati Sub Division PHED. |  |  | ORD/000617/2021-2022 | 277/B/AE/NSD | 16/04/2021 | 30 | SUNIL RABI DAS | 0.97 | 0 | 0
708 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Miyapur, Barla, Thengapara, Bagbari raghunathpur habitation and adjacent area under Raghunathpur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000621/2021-2022 | 607/AE/NSD | 26/11/2021 | 45 | ENAMUL ISLAM | 4.82 | 0 | 100
709 | Birbhum Division |  | Work Order for Construction of boundary wall near OHR site at Raghunathpur Water Supply Scheme under Nalhati Sub-Division, PHE Dte. (Sl. No.1) |  |  | ORD/000667/2020-2021 | 1119/BHM | 09/09/2020 | 60 | MD. SHAHA JAMAL | 4.97 | 0 | 100
710 | Birbhum Division |  | Annual Maintenance of Tube wells, Raw water rising main pipe line and CWR for the daily supply of water to the consumers under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. as mentioned below for 03 (Three) months only (from 16.06.2021 to 15.09.2021) of Raghunathpur Water Supply Scheme. |  |  | ORD/000877/2021-2022 | 318/AE/NSD | 15/06/2021 | 92 | SHIB GANGA CONSTRUCTION | 0.7 | 0 | 0
711 | Birbhum Division |  | Continuation work order for Annual Maintenance of Tube wells, Raw water rising main pipe line and CWR for the daily supply of water to the consumers under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. as mentioned below for 03 (Three) months only (from 18.03.2022 to 17.06.2022) of Raghunathpur Water Supply Scheme. |  |  | ORD/000881/2021-2022 | 157/NSD | 17/03/2022 | 92 | SHIB GANGA CONSTRUCTION | 0.7 | 0 | 0
712 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Tailpara in Raghunathpur w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. (Sl. No.2) |  |  | VCH/001027/2020-2021 |  | 16/03/2021 | 0 | S R ENTERPRISE | 25.48 | 0 | 0
713 | Birbhum Division |  | Providing functional household tap connection (FHTC) from existing distribution system with the command areain the villages bilkandi saora in Raghunathpur WS Scheme (Sl.No.05) |  |  | VCH/001034/2020-2021 |  | 18/03/2021 | 0 | QUAZI SIRAJUL ISLAM. | 34.7 | 0 | 0
714 | Birbhum Division |  | Providing functional household tap connection (FHTC) from existing distribution system within the command area in the villages kadya raghunathpur in Raghunathpur WS Scheme (Sl.No.06) |  |  | VCH/001045/2020-2021 |  | 19/03/2021 | 0 | M/S MD AMINUL ISLAM | 26.68 | 0 | 0
715 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jikadda Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte (Sl. No.3) | AE | JE1 | ORD/000008/2022-2023 | 821/BHM | 13/04/2022 | 60 | KAZI EMDADUL HAQUE | 55.12 | 0 | 100
716 | Birbhum Division | Rampurhat Sub-Division | Allied works for construction of pipe culvart, land development and temporary approach road at H/W site of JHIKADDA PWSS under Rampurhat Sub Division.PHE Dte. | AE | JE1 | ORD/000534/2021-2022 | 20/RSD | 04/01/2022 | 30 | ABHOY CHARAN GHOSH | 4.74 | 0 | 100
717 | Birbhum Division | Rampurhat Sub-Division | Laying of Rising main with DI pipe line for inter connection and bypass arrangement for Jhikadda water supply scheme under Rampurhat sub division under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000535/2021-2022 | 21/RSD | 04/01/2022 | 30 | KALYAN PAL | 1.65 | 0 | 100
718 | Birbhum Division | Rampurhat Sub-Division | Construction of Boundary Wall & Internal path way at 2nd Site for JHIKADDA PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000536/2021-2022 | 22/RSD | 04/01/2022 | 45 | ABHOY CHARAN GHOSH | 4.33 | 0 | 100
719 | Birbhum Division | Rampurhat Sub-Division | Laying of HDPE Pipe line for Krishnanagar mouzas under Jhikadda Piped Water Supply Scheme under Rampurhat sub-Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000678/2021-2022 | 103/RSD | 07/03/2022 | 30 | ABHOY CHARAN GHOSH | 4.96 | 0 | 100
720 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE | JE1 | RTOR000038/2021-2022 | 216/BHM | 02/02/2022 | 0 | Resource Division | 6.64 | 0 | 0
721 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Hajarpur under Hajarpur Water Supply Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.10) | AE | JE3 | ORD/000149/2022-2023 | 1453/BHM | 07/07/2022 | 60 | SAPTADIP CONSTRUCTION | 25.25 | 0 | 100
722 | Birbhum Division | Bolpur Sub-Division | Payment for Supply of diesel | Assistant Engineer | JE1 | BILL/00270/2023-2024 | BP-2023-24-127 | 25/08/2023 | 0 | JAYRAM FILLING STATION | 0.72 | 0 | 0
723 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kamarpara & Chella of Daranda w/s Scheme at Illambazar Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (Sl. No.11) | Assistant Engineer | JE1 | ORD/000078/2020-2021 | 1425/BHM | 04/11/2020 | 45 | SYED KHORSID ALAM | 17.6 | 15.61 | 0
724 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chella, Ramnagar, Bonovilla, Lakshipur, Daronda, Dhalla, Saldanga, Usurdihi, Ushahar etc. in different locations under Daronda Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.1) | Assistant Engineer | JE1 | ORD/000122/2022-2023 | 1569/BHM | 26/07/2022 | 60 | HOQUEDAR ALI | 43.32 | 0 | 100
725 | Birbhum Division | Bolpur Sub-Division | Preparation of Audio clip single of 5 minute aand telecast the same through FM (Air) for a period of 3 month 4 times in a day under Birbhum Diviison PHE Dte. (Sl.No.02) | Assistant Engineer | JE1 | ORD/000187/2020-2021 | 1571/BHM | 07/12/2020 | 60 | IMAGIN | 0.89 | 0.89 | 0
726 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Daronda w/s Scheme (Left out House Hold) in Bolpur Sub-Division under Birbhum Division, PHE Dte. (2nd Call).¿ (Sl. No.7) | Assistant Engineer | JE1 | ORD/000426/2021-2022 | 2059/BHM | 10/12/2021 | 60 | RAJKUMAR DAS | 38.89 | 0 | 85
727 | Birbhum Division | Bolpur Sub-Division | Hiring of SWIFT DIZER (Diesel) or equivalent luxury car for office of the Assistant Engineer, Nalhati Sub - Division under Birbhum Division, PHE Dte. (Period from 01.04.2023 to 30.09.2023) 183-Days. | Assistant Engineer | JE1 | ORD/000607/2022-2023 | 130/AE/NSD | 31/03/2023 | 183 | JOY CHAND MAL | 0.86 | 0 | 85
728 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Saldanga, Dhalla, Lakshmipur, Daranda & Ramnagar of Daranda w/s Scheme at Illambazar Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No.10) | Assistant Engineer | JE1 | ORD/000609/2020-2021 | 1024/BHM | 04/11/2020 | 45 | S.S. BHATTACHARJEE. | 13.82 | 0 | 35
729 | Birbhum Division | Bolpur Sub-Division | Replacement of damaged UPVC pipe line due to widening of road from Bubahat More towards Chella along with extension of UPVC pipe line for the habitation of Halsidanga, Chella, etc. of Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 | ORD/000819/2021-2022 | 457/BSD | 13/12/2021 | 30 | S.S. BHATTACHARJEE. | 4.34 | 0 | 50
730 | Birbhum Division |  | Additional Laying of Distribution System for strengthening of Atla Water Supply Scheme for Atla Mouza under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. |  |  | ORD/000069/2022-2023 | 226/RSD | 23/06/2022 | 30 | SUMAN CHOWDHURY | 2.84 | 0 | 100
731 | Birbhum Division |  | Providing Tap Connection for Existing School & AWC in Atla PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. |  |  | ORD/000074/2021-2022 | 273/RSD | 16/07/2021 | 10 | PROLOY KUMAR MONDAL | 0.22 | 0 | 100
732 | Birbhum Division |  | Laying of Distribution System for Atla Water Supply Scheme from Mukti Hotel and Residency to Sri Sri Mohananda Brahamchari Sevasharam at Atla Mouzas under Rampurhat Sub-Division, within Birbhum Division P.H.E. Dte. |  |  | ORD/000118/2021-2022 | 291/RSD | 26/07/2021 | 30 | BIJOY KUMAR CHOUDHURY | 4.83 | 0 | 0
733 | Birbhum Division |  | Providing functional household tap connection (FHTC) from existing distribution system in kabichandrapur area under kobichandrapur under Atla mouza under Rampurhat -I block at ATLA WS scheme.(Sl.No.01) |  |  | ORD/000159/2020-2021 | 13/RSD | 11/01/2021 | 30 | SUBODH KR MANDAL | 4.98 | 4.98 | 100
734 | Birbhum Division |  | Providing functional household tap connection (FHTC) from existing distribution system in kabichandrapur area under kobichandrapur under Atla mouza under Rampurhat -I block at ATLA WS scheme.(Sl.No.02) |  |  | ORD/000160/2020-2021 | 14/RSD | 11/01/2021 | 30 | MUKADDUMUL MOULA | 4.59 | 4.51 | 100
735 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Atla W/S Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. |  |  | ORD/000172/2021-2022 | 1324/BHM | 16/08/2021 | 60 | BIJOY KUMAR CHOUDHURY | 35.94 | 0 | 99
736 | Birbhum Division |  | Providing Functional Household Tap connection (FHTC) from existing distribution system in Kabichandrapur under Kabichandrapur Habitation under Atla Mouzas under Rampurhat Sub Division PHE Dte. |  |  | ORD/000189/2020-2021 | 15/RSD | 11/01/2021 | 60 | MD NUREL HOQUE. | 4.02 | 4.02 | 0
737 | Birbhum Division |  | Sinking of 02 (Two) No 200mm dia.X 36 mtr deep Tube Well with UPVC pipe & strainer for strengthening of Atla W/S scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl.No-35) |  |  | ORD/000204/2022-2023 | 338/RSD | 08/09/2022 | 30 | SUMAN CHOWDHURY | 3.66 | 0 | 0
738 | Birbhum Division |  | Providing FHTC from existing distributin system in Junidpur, Kamdebpur and Atla mouza within Atla w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. |  |  | ORD/000380/2021-2022 | 360/RSD | 28/09/2021 | 30 | PROLOY KUMAR MONDAL | 2.21 | 0 | 0
739 | Birbhum Division |  | Allied works for Additional Laying of UPVC Pipe line for providing FHTC at Kabichandrapur (Adibasipara) at Atla Mouzas under Atla PWSS under Rampurhat SubDivision, within Birbhum Division P.H.E Dte. |  |  | ORD/000511/2021-2022 | 09/RSD | 04/01/2022 | 30 | BIJOY KUMAR CHOUDHURY | 4.98 | 0 | 100
740 | Birbhum Division |  | Allied works for Additional Laying of UPVC Pipe line for providing FHTC for Atla Water Supply Scheme at Atla Mouza Towards Tarapith Roadunder Rampurhat Sub-Division within Birbhum Division P.H.E Dte. |  |  | ORD/000512/2021-2022 | 10/RSD | 04/01/2022 | 30 | BIJOY KUMAR CHOUDHURY | 4.92 | 0 | 100
741 | Birbhum Division |  | Allied works for Additional Laying of UPVC Pipe line for providing FHTC for Atla Water Supply Scheme at Atla Mouza towards Mollarpur Road, under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. |  |  | ORD/000513/2021-2022 | 11/RSD | 04/01/2022 | 30 | BIJOY KUMAR CHOUDHURY | 2.92 | 0 | 100
742 | Birbhum Division |  | Connection with DI pipe from new Tubewell to CWR for Atla PWSS under Rampurhat Sub-Division, P.H.E Dte. |  |  | ORD/000584/2021-2022 | 68/RSD | 08/02/2022 | 30 | PROLOY KUMAR MONDAL | 0.64 | 0 | 0
743 | Birbhum Division |  | Providing functional household tap connection (FHTC) from existing distribution system in Kabichandrapur letpara area under Habitation under Atla Mouzas of Atla Water Ssupply Scheme (Sl.No.03) |  |  | VCH/001028/2020-2021 |  | 17/03/2021 | 0 | MD NUREL HOQUE. | 4.02 | 0 | 0
744 | Birbhum Division | Birbhum Sadar Sub-Division | Balance work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Data Baba Water Supply Scheme in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000099/2023-2024 | 1720/BHM | 12/05/2023 | 30 | ARPAN PANDIT | 22.34 | 0 | 100
745 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Data Baba Water Supply Scheme in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte. (2nd Call) | AE | JE2 | ORD/000317/2022-2023 | 2509/BHM | 17/11/2022 | 30 | AMIT KUMAR ROY | 38.19 | 0 | 100
746 | Birbhum Division | Birbhum Sadar Sub-Division | Extension of distribution pipe line near Nichupara Kabar Sthan, besides of Khokon House, near Imam Saheb and infornt of Gate of Park and all other allied works under Data Baba Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. (Sl. No. - 03) | AE | JE2 | ORD/000345/2022-2023 | 215/BSSD | 21/09/2022 | 15 | AMIT KUMAR ROY | 2.98 | 0 | 100
747 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at KASHIMNAGAR, KAMARKHUL & GAGANPUR and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000288/2023-2024 | 3647/BHM | 25/08/2023 | 274 | BENGAL ENGINEERING | 1204.06 | 0 | 30
748 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000057/2023-2024 | 1451/BHM | 25/04/2023 | 0 | Resource Division | 76.79 | 0 | 0
749 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Gaganpur Water Supply Scheme P/H - I in Paikar CCC under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00089/2024-2025 | BP-2024-2025-41 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.13 | 0 | 0
750 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for GAGANPUR piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000544/2023-2024 | 2140/Bol.MD | 25/08/2023 | 671 | MONI ELECTRICAL WORKS | 29.63 | 0 | 60
751 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Kamdebnala & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000061/2023-2024 | 1302/BHM | 19/04/2023 | 927 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 282.44 | 0 | 42
752 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000036/2023-2024 | 1534/BHM | 26/04/2023 | 0 | Resource Division | 12.86 | 0 | 0
753 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOITATION FOR KAMDEBNALA PH NO-I | AE,Assistant Engineer | JE1,Junior Engineer | BILL/01839/2023-2024 | BP-2023-24-269 | 07/02/2024 | 0 | WBSEDCL | 3.12 | 0 | 0
754 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for KAMDEBNALA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000900/2023-2024 | 3295/Bol.MD | 29/09/2023 | 795 | M/S. UTTAM KUMAR CHATTERJEE | 25.93 | 0 | 90
755 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Majhara & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000062/2023-2024 | 1301/BHM | 19/04/2023 | 1078 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 281.52 | 0 | 30
756 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000097/2023-2024 | 1492/BHM | 25/04/2023 | 0 | Resource Division | 20.41 | 0 | 0
757 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for MAJHARA piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000547/2023-2024 | 2143/Bol.MD | 25/08/2023 | 60 | UNIVERSAL ENTERPRISES | 25.93 | 0 | 70
758 | Bolpur Mechanical | Nalhati Sub-Division | Supply and installation of manual operated Motor control panel for Majhara water supply scheme (Amdol Pump House-I) of Murarai-II Block under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/001279/2023-2024 | 176/BMSD(D) | 18/03/2024 | 318 | QUAZI NOZRUL ISLAM | 2.66 | 0 | 100
759 | Bolpur Mechanical | Nalhati Sub-Division | Supply, delivery and installation of servo motor operated copper wound line voltage corrector for Majhara water supply scheme (Amdol Pump House-I) of Murarai-II Block under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/001280/2023-2024 | 177/BMSD(D) | 18/03/2024 | 30 | NITESH MANAGEMENT | 3.18 | 0 | 100
760 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at ABHIRAMPUR, BEHIRA, SAMSA & UTTAR BANGAON and its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000082/2023-2024 | 1437/BHM | 25/04/2023 | 820 | ASHOK KUMAR GHOSH | 1446.74 | 0 | 55
761 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000053/2022-2023 | 1368/BHM | 24/04/2023 | 0 | Resource Division | 37.96 | 0 | 0
762 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Samsa PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/00219/2024-2025 | BP-24-25-107 | 02/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3 | 0 | 0
763 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Samsa PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/01025/2024-2025 | BP-24-25-279 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.3 | 0 | 0
764 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Samsa & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000437/2023-2024 | 2096/Bol.MD | 22/08/2023 | 913 | M/S SWAPAN BANERJEE | 28.57 | 0 | 80
765 | Birbhum Division | Birbhum Sadar Sub-Division | Road crossing, repairing & restoration of damage pipe lines & PCC roads, sluice valve chambers including all allied works for Dakshin Chandipur Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000077/2025-2026 | 1638/BHM | 11/06/2025 | 293 | M/S KRIPASINDHU GHOSH & CO. | 43.46 | 0 | 80
766 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000056/2022-2023 | 1410/BHM | 24/04/2023 | 0 | Resource Division | 41.76 | 0 | 0
767 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Dakshin Chandipur PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/01024/2024-2025 | BP-24-25-276 | 06/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.1 | 0 | 0
768 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Dakshin Chandipur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000986/2023-2024 | 3307/BOL.MD | 29/09/2023 | 365 | PP CONCERN | 28.24 | 0 | 50
769 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
770 | Birbhum Division | Rampurhat Sub-Division | Allied Functional Household Tap Connection along with laying additional distribution pipeline at different mouzas under Belera Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000060/2023-2024 | 1304/BHM | 19/04/2023 | 45 | OM ENTERPRISE | 17.33 | 0 | 0
771 | Birbhum Division | Birbhum Sadar Sub-Division | Sinking of 250 X 200 mm Dia and 125 m deep tubewell, Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM capacity O.H.R. and respectively, 150 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to MAJURIA & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000188/2024-2025 | 2770/BHM | 30/09/2024 | 365 | JALPRAVAHIKA PVT. LTD. | 609.71 | 0 | 20
772 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000049/2024-2025 | 3268/BHM | 02/12/2024 | 0 | Resource Division | 15.42 | 0 | 0
773 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000078/2022-2023 | 1397/BHM | 24/04/2023 | 0 | Resource Division | 195.98 | 0 | 0
774 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Majuri & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000579/2023-2024 | 3383/Bol.MD | 16/10/2023 | 90 | SATYAJIT GHOSH | 72.19 | 0 | 0
775 | Birbhum Division | Nalhati Sub-Division | Restoration of Roads, pucca drain including Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chember for Chaiti piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000070/2025-2026 | 1594/BHM | 03/06/2025 | 90 | QUAZI SIRAJUL ISLAM | 96.35 | 0 | 0
776 | Birbhum Division | Nalhati Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
777 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Chauti & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000537/2022-2023 | 674/BHM | 01/03/2023 | 1127 | QUAZI SIRAJUL ISLAM. | 365.44 | 0 | 40
778 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE2,Junior Engineer | RTOR000038/2023-2024 | 1573/BHM | 26/04/2023 | 0 | Resource Division | 10.89 | 0 | 0
779 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Chauti P/H-II Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | BILL/00149/2024-2025 | BP-2024-2025-75 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.92 | 0 | 0
780 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Chauti P/H-I Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | BILL/00153/2024-2025 | BP-2024-2025-76 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.82 | 0 | 0
781 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Chauti PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000941/2023-2024 | 3302/BOL.MD | 29/09/2023 | 671 | MONI ELECTRICAL WORKS | 27.59 | 0 | 60
782 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | RTOR000089/2022-2023 | 1361/BHM | 24/04/2023 | 0 | Resource Division | 16.8 | 0 | 0
783 | Bolpur Mechanical | Bolpur Sub-Division | NEW SERVICE CONNECTION AT MONOHORPUR WATER SUPPLY SCHEME | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | BILL/00438/2024-2025 | BP-2024-25-141 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.41 | 0 | 0
784 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
785 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
786 | Birbhum Division | Bolpur Sub-Division | Continuation order against "Hiring of 01(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, PHE. Dte. under Birbhum Division, PHE Dte. For the period of 01.04.2023 to 30.09.2023". For another 06 (Six) months i.e. from 01.10.2024 to 31.03.2025. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000313/2024-2025 | 873/BSD | 27/09/2024 | 182 | SK AKRAM HOSSAIN | 0.86 | 0 | 0
787 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000402/2023-2024 | 4139/BHM | 18/10/2023 | 896 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 0 | 60
788 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | RTOR000087/2022-2023 | 1359/BHM | 24/04/2023 | 0 | Resource Division | 13.67 | 0 | 0
789 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
790 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at DEOASH, JASODA & JIUI and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000013/2023-2024 | 1194/BHM | 12/04/2023 | 792 | M/S. JAN MAHAMMAD | 1367.24 | 0 | 75
791 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000050/2022-2023 | 1367/BHM | 24/04/2023 | 0 | Resource Division | 17.14 | 0 | 0
792 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUIOTATION FOR JIUI PH NO-II | AE,Assistant Engineer | JE,Junior Engineer | BILL/01850/2023-2024 | BP-23-24-276 | 15/02/2024 | 0 | WBSEDCL | 5 | 0 | 0
793 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR JIUI PH I WS SCHEME | AE,Assistant Engineer | JE,Junior Engineer | BILL/02134/2023-2024 | BP-2023-24-295 | 12/03/2024 | 0 | WBSEDCL | 3.79 | 0 | 0
794 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Jiui & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000415/2023-2024 | 2087/Bol.MD | 22/08/2023 | 679 | M/S. YOUTH ENGINEERS' ENTERPRISE | 28.76 | 0 | 50
795 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at KANIOR, KOGRAM & KUSHIPUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000596/2022-2023 | 1059/BHM | 31/03/2023 | 915 | SK ALIM | 1229.19 | 0 | 25
796 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000054/2023-2024 | 1572/BHM | 26/04/2023 | 0 | Resource Division | 16.61 | 0 | 0
797 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR SKOGRAM WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01606/2023-2024 | BP-23-24-236 | 29/01/2024 | 0 | WBSEDCL | 2.85 | 0 | 0
798 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Kogram PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000913/2023-2024 | 3541/BOL.MD | 30/11/2023 | 60 | A.S.ENTERPRISE | 27.56 | 0 | 50
799 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at PASCHIM NAOPARA, PHULUR & PURBA SIUR its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000189/2023-2024 | 2262/BHM | 12/07/2023 | 993 | B RAI CONSTRUCTION COMPANY | 1402.44 | 0 | 45
800 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000065/2022-2023 | 1416/BHM | 24/04/2023 | 0 | Resource Division | 24.19 | 0 | 0
801 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Quotation deposit for Phulur Water Supply Scheme P/H-II in Sainthia CCC under Bolpur Mechanical division, PHE Dte | AE,Assistant Engineer | JE,Junior Engineer | BILL/01087/2024-2025 | BP-24-25-284 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.36 | 0 | 0
802 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUIOTATION FOR PHULUR PH NO-I | AE,Assistant Engineer | JE,Junior Engineer | BILL/01849/2023-2024 | BP-23-24-275 | 15/02/2024 | 0 | WBSEDCL | 0.53 | 0 | 0
803 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Phulur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000413/2023-2024 | 2085/Bol.MD | 22/08/2023 | 410 | MASSK ENGINEERING WORKS | 28.91 | 0 | 55
804 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amdole under Amdole Water Supply Scheme (Left out House Hold) within Birbhum Division, PHE Dte. (Sl. No.11) | AE | JE3 | ORD/000039/2022-2023 | 885/BHM | 22/04/2022 | 60 | KHANDAKAR CONSTRUCTION | 66.42 | 0 | 100
805 | Birbhum Division | Nalhati Sub-Division | ¿Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amdole Water Supply Scheme within Nalhati Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.17) | AE | JE3 | ORD/000340/2021-2022 | 1771/BHM | 29/10/2021 | 60 | UJJWAL DAS | 78.86 | 0 | 100
806 | Birbhum Division | Nalhati Sub-Division | Extension of pipeline of different left out habitations including FHTC along with 1 no. Pump House as boosting of water supply of Amdol water supply scheme under Nalhati Sub-Division, within Birbhum Division PHE Dte (Sl. No.7) | AE | JE3 | ORD/000367/2022-2023 | 2780/BHM | 14/12/2022 | 900 | KAMIRUL SK AND CO | 211.6 | 0 | 75
807 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amdole w/s Scheme (Leftout House Hold) in Nalhati Sub-Division under Birbhum Division, PHE Dte. (Sl. No.5) | AE | JE3 | ORD/000415/2021-2022 | 2098/BHM | 16/12/2021 | 60 | MD ABSAR ALI | 94.06 | 0 | 100
808 | Birbhum Division | Nalhati Sub-Division | Restoration of PCC Road, damaged by laying of pipe line at different habitations under Narottampur village (JL.No.-63) and its adjoining areas under Amdol PWSS within Nalhati Sub-Division, PHE Dte. | AE | JE3 | ORD/000625/2021-2022 | 539/AE/NSD | 08/10/2021 | 15 | TEKNO ENTERPRISE | 4.46 | 0 | 100
809 | Birbhum Division | Nalhati Sub-Division | Restoration of PCC Road, damaged by laying of pipe line at different habitations under Kalahapur village (JL.No.-56) and its adjoining areas under Amdol PWSS within Nalhati Sub-Division, PHE Dte. | AE | JE3 | ORD/000626/2021-2022 | 534/AE/NSD | 08/10/2021 | 15 | MD ABSAR ALI | 4.85 | 0 | 100
810 | Birbhum Division | Nalhati Sub-Division | Road crossing under Kalahapur village by adopting Augor Boring method along with pipe carrying structure & other ancillary works for Improvement of AMDOL PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000628/2021-2022 | 19/AE/NSD | 17/01/2022 | 30 | MD ABSAR ALI | 4.85 | 0 | 100
811 | Birbhum Division | Nalhati Sub-Division | Road crossing near Bhimpur Health Center by adopting Jack Pushing method for Improvement of AMDOL PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000629/2021-2022 | 20/NSD | 17/01/2022 | 30 | UJJWAL DAS | 4.84 | 0 | 100
812 | Birbhum Division | Nalhati Sub-Division | Extension of pipe line at Kalahapur village of Amdol Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE3 | ORD/000637/2021-2022 | 490/AE/NSD | 27/09/2021 | 45 | MD ABSAR ALI | 4.52 | 0 | 100
813 | Birbhum Division | Nalhati Sub-Division | Restoration of PCC Road, damaged by laying of pipe line at different habitations under Hariapur village (JL.No.-60) and its adjoining areas under Amdol PWSS within Nalhati Sub-Division, PHE Dte. | AE | JE3 | ORD/000782/2021-2022 | 536/AE/NSD | 08/10/2021 | 15 | UJJWAL DAS | 4.84 | 0 | 100
814 | Birbhum Division | Nalhati Sub-Division | Laying of additional distribution system at Harishpur (JL.No.-60) and its adjoining areas for proposed Improvement of Amdol Piped Water Supply Scheme under Murarai-II Block, under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000785/2021-2022 | 536/A/AE/NSD | 08/10/2021 | 45 | UJJWAL DAS | 4.98 | 0 | 0
815 | Birbhum Division | Rampurhat Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at SANDHYAJOL & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000124/2024-2025 | 2224/BHM | 12/08/2024 | 730 | SUNIL RABI DAS | 386.48 | 0 | 20
816 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Sandhyajol) Water Supply Scheme under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000634/2022-2023 | 241/RSD | 13/07/2022 | 45 | ECO CARE | 4.73 | 0 | 100
817 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000026/2023-2024 | 1568/BHM | 26/04/2023 | 0 | Resource Division | 45.61 | 0 | 0
818 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000043/2024-2025 | 2492/BHM | 03/09/2024 | 0 | Resource Division | 12.42 | 0 | 0
819 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Sandhyajol PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000475/2023-2024 | 2228/Bol.MD | 12/09/2023 | 60 | P. K. ENGINEERING | 44.41 | 0 | 0
820 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
821 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
822 | Birbhum Division | Birbhum Sadar Sub-Division | Withdrawing and re-sinking for 02 nos. working 200mm dia. Tubewell of 10 m depth with horizontal strainer on the river Bed of Ajoy under Parsundi Mini Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division P.H.E. Dte. | AE | JE | ORD/000513/2023-2024 | 654/BHM | 20/02/2024 | 45 | NEEL ENTERPRISE | 2.87 | 0 | 100
823 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Parsundi & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000855/2022-2023 | 143/BSSD | 21/07/2022 | 45 | RADIANT | 2.9 | 0 | 100
824 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000247/2023-2024 | 430/BHM | 01/02/2024 | 0 | Resource Division | 131.6 | 0 | 0
825 | Birbhum Division | Nalhati Sub-Division | Restoration of Roads, pucca drain including Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Hazaripur piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000166/2025-2026 | 2064/BHM | 12/08/2025 | 90 | M/S NATIONAL CONSTRUCTION | 61.62 | 0 | 0
826 | Birbhum Division | Nalhati Sub-Division | Different works for works related to water supply scheme at HAZARIPUR, Beloa & its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000255/2023-2024 | 3425/BHM | 02/08/2023 | 883 | M/S NATIONAL CONSTRUCTION | 1099.34 | 0 | 15
827 | Birbhum Division | Nalhati Sub-Division | Preparation and submission of DPR for (Hazaripur) Water Supply Scheme under Nalhati-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000757/2022-2023 | 222/AE/NSD | 18/04/2022 | 45 | MS SOBHA AND CO | 4.71 | 0 | 100
828 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000173/2023-2024 | 2173/BHM | 23/06/2023 | 0 | Resource Division | 25.03 | 0 | 0
829 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Hazaripur PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000462/2023-2024 | 2136/Bol.MD | 25/08/2023 | 554 | SINHA ELECTRICALS | 45.52 | 0 | 30
830 | Bolpur Mechanical | Nalhati Sub-Division | Supply and Delivery of Electro mechanical Accessories for Hazaripur PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000519/2024-2025 | 3779/BOL.MD | 12/09/2024 | 30 | KAMAKHYA ENTERPRISE | 28.62 | 0 | 100
831 | Birbhum Division | Rampurhat Sub-Division | Sinking of Rig Bored Tube well by DTH method of drilling (125 mm X 115 mm) dia including connecting main for Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District under Rampurhat Sub-Division, Birbhum Division, P.H.E Dte | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000137/2023-2024 | 2268/BHM | 13/07/2023 | 30 | JAYANTA BARAL | 4.53 | 0 | 100
832 | Birbhum Division | Rampurhat Sub-Division | Laying of Rising Main , Distribution system and Providing FHTC including all allied Works for Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat - I Block within Birbhum District. (Sl. No.8) | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000353/2022-2023 | 2689/BHM | 06/12/2022 | 60 | M/S MD AMINUL ISLAM | 98.43 | 0 | 90
833 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch Room size 5.40 mtr. X 3.65 mtr with Sanitary and water supply arrangement For Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat Sub-Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000359/2022-2023 | 447/RSD | 08/12/2022 | 45 | SUBHRANIL DAS | 4.98 | 0 | 0
834 | Birbhum Division | Rampurhat Sub-Division | Sinking of 02 Nos Tube wells 200 mm dia depth 36.0 mm each depth, fitted with PVC pipe and fiber glass Strainer at Salbani River bank for Khadamara PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000360/2022-2023 | 448/RSD | 08/12/2022 | 30 | ANKITA CHAKRABORTY | 4.68 | 0 | 100
835 | Birbhum Division | Rampurhat Sub-Division | Sinking of 01 nos. additional Tubewell, 200mm dia all through 120 mt. deep tubewell with Rising Main along with Construction of Switch Room 3.60 m X 3.0 m with Sanitary arrangement and balance FHTC for Khedamara PWSS under Rampurhat Sub-Division under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000668/2023-2024 | 1028/BHM | 15/03/2024 | 45 | M/S MD AMINUL ISLAM | 40.81 | 0 | 0
836 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOATATION FOR kHENDAMARA WS SCHEME | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/00642/2023-2024 | BP-2023-2024-54 | 17/07/2023 | 0 | WBSEDCL | 3.39 | 0 | 0
837 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR UTTAR BAKHEDAMARA WS SCHEME | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/01475/2023-2024 | BP-23-24-196 | 14/12/2023 | 0 | WBSEDCL | 1.96 | 0 | 0
838 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping machinaries at newly sunk Tube Wells and allied works at Khedamara PWSS Block-Rampurhat-I under Bolpur Mechanical Division. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000306/2023-2024 | 1501/Bol.MD | 17/07/2023 | 60 | MUKHERJEE ART CENTRE | 19.28 | 0 | 80
839 | Birbhum Division | Rampurhat Sub-Division | Retrofitting works for Providing Balance Functional Household Tap Connection (FHTC) by Sinking of 2 nos. additional Tubewells at Rukumpur & Dumra mouza (200mm dia all through & 150 Mtr Deep) along with Connecting Line, Boundary wall & related works for Sekhpur Piped Water Supply Scheme under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000657/2023-2024 | 1027/BHM | 15/03/2024 | 451 | GOLAM RASUL | 86.37 | 0 | 0
840 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE | JE | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
841 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE | JE | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
842 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at ANGORA PIPED WATER SUPPLY SCHEME (TSM/016091) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000149/2024-2025 | 2599/BHM | 10/09/2024 | 365 | CHIRANJIB DAS | 419.76 | 0 | 25
843 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for ANGORA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte". (PART - A) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000730/2022-2023 | 215/BSD | 31/05/2022 | 180 | RADIANT | 4.94 | 0 | 100
844 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000053/2024-2025 | 3266/BHM | 02/12/2024 | 0 | Resource Division | 11.22 | 0 | 0
845 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000060/2023-2024 | 1535/BHM | 26/04/2023 | 0 | Resource Division | 14.49 | 0 | 0
846 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Angora & Charkalgram Water supply Scheme, Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000968/2024-2025 | 4537/BOL.MD | 20/12/2024 | 285 | MENAKA ENTERPRISE | 73.34 | 0 | 100
847 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
848 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at BANHAT & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000571/2022-2023 | 904/BHM | 22/03/2023 | 683 | PRALAY ROY | 331.4 | 0 | 38
849 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000149/2023-2024 | 1592/BHM | 26/04/2023 | 0 | Resource Division | 18.13 | 0 | 0
850 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000216/2023-2024 | 230/BHM | 24/01/2024 | 0 | Resource Division | 0.12 | 0 | 0
851 | Bolpur Mechanical | Rampurhat Sub-Division | QUOTATION FOR BANHAT PH-II RAMPURHAT-I BLOCK | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/00008/2024-2025 | BP-24-25-06 | 09/04/2024 | 0 | WBSEDCL | 3.23 | 0 | 0
852 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR BONHAT W S P H NO I WS SCHEME | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/01782/2023-2024 | BP-23-24-249 | 29/01/2024 | 0 | WBSEDCL | 3.53 | 0 | 0
853 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Banhat & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000355/2023-2024 | 1750/Bol.MD | 27/07/2023 | 614 | PADMA ENGINEERING CO. | 27.7 | 0 | 100
854 | Birbhum Division | Bolpur Sub-Division | Construction of 150 Cum. capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, laying of Rising Main ,Distribution System with FHTC and different works related to GOALDIHI PIPED WATER SUPPLY SCHEME (TSM/016090) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer | JE2 | ORD/000133/2024-2025 | 2317/BHM | 21/08/2024 | 365 | DILIP KUMAR MONDAL | 333.62 | 0 | 0
855 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for GOALDIHI Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer | JE2 | ORD/001140/2021-2022 | 110/BSD | 22/03/2022 | 90 | RADIANT | 3.27 | 0 | 100
856 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE2 | RTOR000039/2024-2025 | 2482/BHM | 03/09/2024 | 0 | Resource Division | 6.42 | 0 | 0
857 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE2 | RTOR000063/2023-2024 | 1479/BHM | 25/04/2023 | 0 | Resource Division | 6.64 | 0 | 0
858 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Goaldihi WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer | JE2 | ORD/000970/2024-2025 | 4523/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.08 | 0 | 0
859 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer | JE2 | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
860 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at PARKUTA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000068/2023-2024 | 1341/BHM | 20/04/2023 | 183 | KAZI EMDADUL HAQUE | 118.27 | 0 | 90
861 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Perkuta) Water Supply Scheme under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000639/2022-2023 | 281/RSD | 24/08/2022 | 45 | ECO CARE | 2.18 | 0 | 100
862 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000023/2023-2024 | 1445/BHM | 25/04/2023 | 0 | Resource Division | 7.01 | 0 | 0
863 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000224/2023-2024 | 221/BHM | 24/01/2024 | 0 | Resource Division | 2.46 | 0 | 0
864 | Bolpur Mechanical | Rampurhat Sub-Division | wbsedcl quotation money for parkuta pwss | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01430/2023-2024 | BP-23-24-150 | 04/12/2023 | 0 | WBSEDCL | 3.99 | 0 | 0
865 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR PARKUTA P H NO.II WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01875/2023-2024 | BP-23-24-279 | 20/02/2024 | 0 | WBSEDCL | 4.98 | 0 | 0
866 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Parkuta PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000006/2024-2025 | 686./AE-III | 08/04/2024 | 14 | SINHA ELECTRICALS | 1.74 | 0 | 100
867 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Parkuta PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000473/2023-2024 | 2226/Bol.MD | 12/09/2023 | 565 | SINHA ELECTRICALS | 45.18 | 0 | 90
868 | Bolpur Mechanical | Rampurhat Sub-Division | Operation and Guarding of pumping machinery and others at Parkuta Piped Water supply Scheme (Pump House No-II(Block- Rampurhat-II) under Bolpur Mechanical Division,P.H.E Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000827/2024-2025 | 1091./AE-III | 29/07/2024 | 31 | STANDARD ELECTRICALS | 0.3 | 0 | 0
869 | Bolpur Mechanical | Rampurhat Sub-Division | Operation and Guarding of pumping machinery and others at Parkuta Piped Water supply Scheme (Pump House No-I(Block- Rampurhat-II) under Bolpur Mechanical Division,P.H.E Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000828/2024-2025 | 1090./AE-III | 29/07/2024 | 31 | STANDARD ELECTRICALS | 0.3 | 0 | 0
870 | Birbhum Division | Rampurhat Sub-Division | Sinking of 250 X 150 mm Dia tubewell Drilling by Direct Rotary method (Two nos), Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Majkhanda & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000123/2024-2025 | 2226/BHM | 12/08/2024 | 365 | SUNIL RABI DAS | 518.93 | 0 | 0
871 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000034/2024-2025 | 2489/BHM | 03/09/2024 | 0 | Resource Division | 16.69 | 0 | 0
872 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000148/2023-2024 | 1597/BHM | 26/04/2023 | 0 | Resource Division | 13.24 | 0 | 0
873 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Majhkanda & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000920/2023-2024 | 3527/Bol.MD | 29/11/2023 | 60 | SUBHRA ENTERPRISE | 27.83 | 0 | 30
874 | Birbhum Division | Rampurhat Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 150 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection, related to water supply scheme at Singari & its adjoining mouzas water supply scheme within Mayureswar-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000100/2024-2025 | 2105/BHM | 29/07/2024 | 365 | KAZI EMDADUL HAQUE | 270.02 | 0 | 30
875 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Singari) Water Supply Scheme under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000629/2022-2023 | 222/RSD | 23/06/2022 | 45 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 100
876 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000020/2024-2025 | 2443/BHM | 30/08/2024 | 0 | Resource Division | 5.24 | 0 | 0
877 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000106/2023-2024 | 1503/BHM | 25/04/2023 | 0 | Resource Division | 4.08 | 0 | 0
878 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Singari PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000837/2023-2024 | 3276/Bol.MD | 29/09/2023 | 60 | PADMA ENGINEERING CO. | 33.06 | 0 | 30
879 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kaluha, Malpara of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.6) |  |  | ORD/000048/2020-2021 | 1240/BHM | 28/09/2020 | 60 | PULAK KUMAR PAL | 38.12 | 34.9 | 0
880 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Uttar Narayanpur, Kurula Ambha of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-A) |  |  | ORD/000051/2020-2021 | 1178 /BHM | 21/09/2020 | 60 | SUNIL RABI DAS | 41.99 | 18.96 | 79
881 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Mara Basahar, Jagadispur of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-B) |  |  | ORD/000054/2020-2021 | 1179 /BHM | 21/09/2020 | 60 | SANJUKTA ENGINEERS | 32.72 | 26.03 | 100
882 | Birbhum Division |  | Additional Laying of UPVC Pipe line for providing FHTC at Kaluha, Dighuli & Malpara Habitations under Kaluha PWSS under Rampurhat Sub- Division, P.H.E. Dte. |  |  | ORD/000391/2021-2022 | 372/RSD | 28/09/2021 | 30 | PULAK KUMAR PAL | 3.4 | 0 | 100
883 | Birbhum Division |  | Construction of supporting arrangement for Solar pump at Uttar Narayanpur under Rampurhat Sub- division PHE Dte. |  |  | ORD/000530/2021-2022 | 18/RSD | 04/01/2022 | 30 | SHIB GANGA CONSTRUCTION | 1.54 | 0 | 100
884 | Birbhum Division |  | Additional Laying of UPVC Pipe line for providing FHTC at Jagadishpur & Marbasahar village under Kaluha PWSS within Birbhum Division, P.H.E. Dte. (Sl. No.3) |  |  | ORD/000848/2021-2022 | 2005/BHM | 08/12/2021 | 60 | SANJUKTA ENGINEERS | 6.82 | 0 | 50
885 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
886 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE2 | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
887 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Srirampur & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE2 | ORD/000663/2022-2023 | 69/BSSD | 21/04/2022 | 45 | RADIANT | 1.95 | 0 | 100
888 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE2 | RTOR000246/2023-2024 | 431/BHM | 01/02/2024 | 0 | Resource Division | 27.12 | 0 | 0
889 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
890 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
891 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Maynadal & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000676/2022-2023 | 102/BSSD | 17/06/2022 | 45 | RADIANT | 1.22 | 0 | 100
892 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000251/2023-2024 | 423/BHM | 01/02/2024 | 0 | Resource Division | 27.12 | 0 | 0
893 | Birbhum Division | Birbhum Division | Different works for CHORMARA & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000113/2023-2024 | 1878/BHM | 31/05/2023 | 794 | SPIRIT ENGINEERS CO OP SOCIETY LTD | 307.6 | 0 | 15
894 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | RTOR000035/2022-2023 | 1380/BHM | 24/04/2023 | 0 | Resource Division | 13.47 | 0 | 0
895 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Chormara PWSS at Suri - I Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000426/2023-2024 | 2103/BOL.MD. | 22/08/2023 | 60 | RMD TRADING | 27.44 | 0 | 0
896 | Bolpur Mechanical | Birbhum Division | Lowering of 5HP Submersible Pumpining Machinery at nwely yield Tube Well and other allied works at Purba Bankathi water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000838/2024-2025 | 1675./AE-III | 24/10/2024 | 21 | SATYAJIT GHOSH | 2.67 | 0 | 100
897 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at Madhupur, Khamedda & Bara-Karttikchungri and its adjoining mouzas water supply scheme within Rampurhat-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000395/2023-2024 | 4163/BHM | 30/10/2023 | 560 | M/S ASHA CONSTRUCTION | 1089.94 | 0 | 40
898 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (BARA KARTIK CHUNGRI) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000788/2022-2023 | 297/RSD | 07/09/2022 | 45 | ECO CARE | 3.13 | 0 | 100
899 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (BARA KARTIK CHUNGRI) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000800/2022-2023 | 417/RSD | 18/10/2022 | 45 | ECO CARE | 2.91 | 0 | 100
900 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (BARA KARTIK CHUNGRI) Water Supply Scheme (Part-C) under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000801/2022-2023 | 439/RSD | 29/11/2022 | 45 | ECO CARE | 1.82 | 0 | 100
901 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000092/2023-2024 | 1515/BHM | 26/04/2023 | 0 | Resource Division | 112.15 | 0 | 0
902 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000229/2023-2024 | 226/BHM | 24/01/2024 | 0 | Resource Division | 3.7 | 0 | 0
903 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION MONEY FOR BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/01589/2023-2024 | BP-23-24-223 | 15/01/2024 | 0 | WBSEDCL | 16.88 | 0 | 0
904 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Wells and allieds works at Bara Kartik Chungri Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000523/2024-2025 | 3782/BOL.MD | 12/09/2024 | 30 | ORIENTAL ENGINEERING CO. | 24.94 | 0 | 0
905 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Bara Kartik Chungri PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000990/2023-2024 | 3597/Bol.MD | 08/12/2023 | 60 | A. G. ENTERPRISE | 55.74 | 0 | 0
906 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
907 | Birbhum Division | Central Mechanical Sub-DivisionIII | Different works related to water supply scheme at BIRCHANDRAPUR, ASURLAYA, BARATURIGRAM & KANAIPUR and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | Assistant Engineer-III | Junior Engineer | ORD/000471/2023-2024 | 505/BHM | 05/02/2024 | 603 | B RAI CONSTRUCTION COMPANY | 2071.77 | 0 | 20
908 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing Electro-mechanical accessories and others for Kanaipur PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000729/2023-2024 | 3475/Bol.MD | 07/11/2023 | 601 | SINHA ELECTRICALS | 57.22 | 0 | 80
909 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing Submersible pumping machineries and other electromechanical equipments and installation at KANAIPUR PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | Assistant Engineer-III | Junior Engineer | ORD/001219/2023-2024 | 404/Bol.MD | 07/03/2024 | 45 | M. S. ENTERPRISE | 29 | 0 | 70
910 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at MADHURA & PAIKPARA PWSS its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000045/2023-2024 | 1173/BHM | 12/04/2023 | 995 | SK ABDUL HALIM | 921.73 | 0 | 90
911 | Birbhum Division | Nalhati Sub-Division | Hiring of SWIFT DZIRE (diesel) registered luxury car for the office of the Assistant Engineer, Nalhati Sub-Division P.H.E. Dte. for 24 hours service including Driver and the cost of fuel & lubricants as per terms & condition with effect from 01.04.2024 to 30.09.2024. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000699/2023-2024 | 57/NSD | 14/03/2024 | 183 | JOY CHAND MAL | 0.86 | 0 | 0
912 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000067/2022-2023 | 1415/BHM | 24/04/2023 | 0 | Resource Division | 6.36 | 0 | 0
913 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR PAIKPARA W S P H NO I WS SCHEME | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/01780/2023-2024 | BP-23-24-243 | 29/01/2024 | 0 | WBSEDCL | 6.08 | 0 | 0
914 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR PAIKPARA W S P H NO II WS SCHEME | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/01781/2023-2024 | BP-23-24-244 | 29/01/2024 | 0 | WBSEDCL | 0.23 | 0 | 0
915 | Bolpur Mechanical | Nalhati Sub-Division | New service connection at Paikpara PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/02244/2023-2024 | BP-2023-24-313 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.94 | 0 | 0
916 | Bolpur Mechanical | Nalhati Sub-Division | New service connection at Paikpara PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/02245/2023-2024 | BP-2023-24-314 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.79 | 0 | 0
917 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Paikpara PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000905/2023-2024 | 3538/BOL.MD | 30/11/2023 | 549 | BIRBHUM ELECTRIC WORKS | 27.38 | 0 | 70
918 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at BHALIAN, BANGJITA & BIRSINGHA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000047/2023-2024 | 1258/BHM | 17/04/2023 | 806 | NAUTANDAS AND CO | 1377.28 | 0 | 35
919 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE2,Junior Engineer | RTOR000045/2022-2023 | 1372/BHM | 24/04/2023 | 0 | Resource Division | 15.09 | 0 | 0
920 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Quotation deposit for Banjita Water Supply Scheme P/H-II in Suri East CCC under Bolpur Mechanical division, PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | BILL/01010/2024-2025 | BP-24-25-271 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.28 | 0 | 0
921 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION BANGJITA PIPED WATER SUPPLY SCHEME. | AE,Assistant Engineer | JE2,Junior Engineer | BILL/01874/2023-2024 | BP-23-24-277 | 15/02/2024 | 0 | WBSEDCL | 5.41 | 0 | 0
922 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Bangjita & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000417/2023-2024 | 2089/Bol.MD | 22/08/2023 | 60 | INDTECH ASSOCIATES | 28.7 | 0 | 50
923 | Birbhum Division | Nalhati Sub-Division | Restoration of Roads, pucca drain including Jack pushing & Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Beloa piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000199/2025-2026 | 2135/BHM | 18/08/2025 | 180 | M/S S. CHOUDHURY | 53.37 | 0 | 70
924 | Birbhum Division | Nalhati Sub-Division | Different works for works related to water supply scheme at HAZARIPUR, Beloa & its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000255/2023-2024 | 3425/BHM | 02/08/2023 | 883 | M/S NATIONAL CONSTRUCTION | 1099.34 | 0 | 15
925 | Birbhum Division | Nalhati Sub-Division | Preparation and submission of DPR for (Beloa) Water Supply Scheme under Nalhati-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000756/2022-2023 | 219/AE/NSD | 18/04/2022 | 45 | MS SOBHA AND CO | 4.92 | 0 | 100
926 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000108/2023-2024 | 1511/BHM | 26/04/2023 | 0 | Resource Division | 55.88 | 0 | 0
927 | Bolpur Mechanical | Nalhati Sub-Division | Quotation for new service connection at Beloa TW No-III (Block-Nalhati-II) | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00034/2024-2025 | BP-24-25-12 | 25/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.38 | 0 | 0
928 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR BELOA P H .II WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01602/2023-2024 | BP-23-24-161 | 15/01/2024 | 0 | WBSEDCL | 3.73 | 0 | 0
929 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR BELOA WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01603/2023-2024 | BP-23-24-231 | 15/01/2024 | 0 | WBSEDCL | 4.7 | 0 | 0
930 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Beloa PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000461/2023-2024 | 2135/Bol.MD | 25/08/2023 | 554 | QUAZI NOZRUL ISLAM | 56.05 | 0 | 40
931 | Bolpur Mechanical | Nalhati Sub-Division | Supply and Delivery of Valves, Cetrifugal Pumping Machineries and allied accessories for Beloa PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000522/2024-2025 | 3781/BOL.MD | 12/09/2024 | 30 | SATYAJIT GHOSH | 32.39 | 0 | 0
932 | Birbhum Division | Rampurhat Sub-Division | Allied works for Providing FHTC from existing distribution system under Kot Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000105/2023-2024 | 2059/BHM | 08/06/2023 | 405 | SAPTADIP CONSTRUCTION | 54.29 | 0 | 91
933 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kot w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-4) | AE | JE1 | ORD/000851/2021-2022 | 1323/ BHM | 16/08/2021 | 60 | M/S GOUTAM DAS | 93.02 | 0 | 65
934 | Birbhum Division | Rampurhat Sub-Division | Supply and delivery of Sluice Valve & Duck Foot Bend for Kot W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.? (Sl. No.4) | AE | JE1 | ORD/000865/2021-2022 | 377/BHM | 21/02/2022 | 15 | SSPR VALVE MANUFACTURING PVT LTD | 6.99 | 0 | 100
935 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Dunigram of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. |  |  | ORD/000050/2020-2021 | 1176 /BHM | 21/09/2020 | 60 | QUAZI SIRAJUL ISLAM. | 38.07 | 35.58 | 0
936 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Chandanpara) of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte |  |  | ORD/000052/2020-2021 | 1175 /BHM | 21/09/2020 | 60 | MD ABSAR ALI | 34.27 | 31.42 | 0
937 | Birbhum Division |  | Providing Tap Connection for Existing School & AWC under Shilogram, Kamra,Kayemba,Chandpara, Harirampur Mouzas in Dunigram PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000076/2021-2022 | 275/RSD | 16/07/2021 | 10 | MD ABSAR ALI | 0.99 | 0 | 50
938 | Birbhum Division |  | Laying & distribution system with UPVC pipes including FHTC (Functional Household Tap Connection) for Belera PWSS under Birbhum, Division, PHE Dte |  |  | ORD/000396/2022-2023 | 2165./BHM | 28/09/2022 | 30 | OM ENTERPRISE | 34.22 | 0 | 30
939 | Birbhum Division |  | Supply of one no. diesel driven car(Diesel) on hire basis office uses for the officials of the Assistant Engineer, RWS, Birbhum Sub-Division, PHE Dte. (Period from 01.01.2024 to 27.06.2024) |  |  | ORD/000616/2023-2024 | 481/RWS | 28/12/2023 | 179 | AADIL CONSTRUCTION | 0.85 | 0 | 52
940 | Birbhum Division | Bolpur Sub-Division | Additional Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Hateserandi of Hateserandi Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 01). | Assistant Engineer | JE2 | ORD/000048/2022-2023 | 188/BSD | 11/05/2022 | 30 | BISWARUP GHOSH | 3.68 | 0 | 100
941 | Birbhum Division | Bolpur Sub-Division | Retrofitting of pipe lines at Habitation Natungram for Providing sufficient water to Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Hateserandi of Hateserandi Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 05). | Assistant Engineer | JE2 | ORD/000049/2022-2023 | 186/BSD | 11/05/2022 | 30 | PRATICK KUMAR GHOSH | 4.43 | 0 | 100
942 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Hateserandi w/s Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-7) | Assistant Engineer | JE2 | ORD/000248/2021-2022 | 1462/BHM | 02/09/2021 | 60 | BISWARUP GHOSH | 42.56 | 0 | 98
943 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system for left out Households of the village Hate-Serandi under Hate-Serandi Water Supply Scheme of Bolpur Sub-Division under Birbhum Division, PHED. | Assistant Engineer | JE2 | ORD/000409/2021-2022 | 448/BSD | 10/12/2021 | 30 | BISWARUP GHOSH | 4.85 | 0 | 100
944 | Birbhum Division | Bolpur Sub-Division | Retrofitting of pipe lines at Paschimpara, Daspara, Thanderpar and Dakshinpara for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of the village Hate-Serandi under Hate-Serandi Water Supply Scheme of Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE2 | ORD/000410/2021-2022 | 450/BSD | 10/12/2021 | 30 | PRATICK KUMAR GHOSH | 4.14 | 0 | 100
945 | Birbhum Division | Bolpur Sub-Division | Additional pipe line works against laying distribution system of Hate Sarandi Piped Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, P.H.E. Dte | Assistant Engineer | JE2 | ORD/000666/2020-2021 | 586 /BHM | 09/06/2020 | 30 | GOUTAM DAS | 4.97 | 0 | 100
946 | Birbhum Division | Bolpur Sub-Division | Retrofitting of parallel pipe lines From Node point 34 to Node point 16 for Providing sufficient water to Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages HateSerandi of HateSerandi Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 11). | Assistant Engineer | JE2 | ORD/000708/2021-2022 | 53/BSD | 17/02/2022 | 30 | BISWARUP GHOSH | 4.43 | 0 | 100
947 | Birbhum Division | Bolpur Sub-Division | Supply and delivery of 80mm. dia. Sluice Valves, including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Hateserandi Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 01). | Assistant Engineer | JE2 | ORD/000802/2021-2022 | 26/BSD | 21/01/2022 | 15 | M/S GOUTAM DAS | 0.65 | 0 | 100
948 | Birbhum Division | Bolpur Sub-Division | Construction of Boundary Wall with Drain at west side of HateSerandi OHR site of HateSerandi Scheme under Bolpur Sub-Division within Birbhum Division PHE Dte. (Length 55 Mtr.) (Part -II). (Sl. No.: 10). | Assistant Engineer | JE2 | ORD/000821/2021-2022 | 59/BSD | 22/02/2022 | 60 | PRATICK KUMAR GHOSH | 4.85 | 0 | 100
949 | Birbhum Division | Bolpur Sub-Division | ¿Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bipratikuri w/s Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.4) | Assistant Engineer | JE1 ,JE4 | ORD/000305/2021-2022 | 1693/BHM | 07/10/2021 | 60 | M/S KRIPASINDHU GHOSH & CO. | 72.44 | 0 | 100
950 | Birbhum Division | Bolpur Sub-Division | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) in Lalbazar, Malitpur, Saripa and Talbana within the Command area of Bipratikuri Water Supply Scheme (Phase-I) for Swajal Gram under Labpur Block of Bolpur Sub-Division within Birbhum Division, P.H.E. Deptt. (Sl. No.5) | Assistant Engineer | JE1 ,JE4 | ORD/000491/2022-2023 | 288/BHM | 01/02/2023 | 45 | M/S KRIPASINDHU GHOSH & CO. | 21.33 | 0 | 100
951 | Birbhum Division | Bolpur Sub-Division | Supply and delivery of 80mm dia Sluice Valves, including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Bipratikuri Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED.. (Sl. No.: 02). | Assistant Engineer | JE1 ,JE4 | ORD/000658/2021-2022 | 36/BSD | 02/02/2022 | 15 | MAKALI ENGINEERING CORPORATION | 0.65 | 0 | 100
952 | Birbhum Division | Bolpur Sub-Division | Laying, Fitting, Fixing and jointing of Rising Main from 1st & 2nd Tube-well to O.H.R of D.I. (K-9) pipe at Bipratikuri Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. 02) | Assistant Engineer | JE1 ,JE4 | ORD/000701/2021-2022 | 242/BSD | 16/07/2021 | 30 | SYED HASMAT ALI | 2.71 | 0 | 100
953 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing additional Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VI under Suri-I, Suri-II & Sainthia Piped Water Supply Scheme within Birbhum Sadar Sub Division Birbhum Division, P.H.E Dte. | AE | JE2 | ORD/000039/2023-2024 | 1160/BHM | 11/04/2023 | 45 | MD. HASIN | 12.73 | 0 | 100
954 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-II under Suri-I, Suri-II & Sainthia Water Supply Scheme within Birbhum Division, PHE Dte¿ (Sl. No.2) | AE | JE2 | ORD/000043/2022-2023 | 1062/BHM | 13/05/2022 | 60 | APURBA MONDAL | 59.53 | 0 | 100
955 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV & V under Suri-I, Suri-II & Sainthia W/S Scheme Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000052/2023-2024 | 1259/BHM | 17/04/2023 | 45 | PRANAB KUMAR GHOSH | 24.87 | 0 | 100
956 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-I under Suri-I, Suri-II & Sainthia Water Supply Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.1) | AE | JE2 | ORD/000061/2022-2023 | 1063/BHM | 13/05/2022 | 60 | SYED KHORSID ALAM | 59.55 | 0 | 72
957 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-III under Suri-I, Suri-II & Sainthia W/S Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000088/2023-2024 | 1634/BHM | 02/05/2023 | 45 | M/S BUILDWELL | 19 | 0 | 100
958 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing additional Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV under Suri-I, Suri-II and Sainthia Water Supply Scheme Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000091/2023-2024 | 1642/BHM | 02/05/2023 | 45 | S R ENTERPRISE | 8.37 | 0 | 100
959 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing additional Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV under Suri-I, Suri-II and Sainthia Water Supply Scheme Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000094/2023-2024 | 1641/BHM | 02/05/2023 | 45 | SAKTI ENTERPRISE | 7.04 | 0 | 100
960 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area for village of Deshalpur, Gopalpur, Maliha, Ekdala, Haripur, Khosnatore, Jamal, Fathepur and Kubirpur (Zone-IV) under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No.6) | AE | JE2 | ORD/000276/2022-2023 | 2218/BHM | 13/10/2022 | 60 | THREE MAA ENTERPRISE | 51.45 | 0 | 100
961 | Birbhum Division | Birbhum Sadar Sub-Division | ¿Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VIII under Suri-I, Suri-II & Sainthia Water Supply Scheme within Birbhum Sadar Sub- Division Birbhum Division, PHE Dte.¿(Sl. No.6) | AE | JE2 | ORD/000341/2021-2022 | 1773/BHM | 28/10/2021 | 60 | M/S GOUTAM DAS | 79.89 | 0 | 100
962 | Birbhum Division | Birbhum Sadar Sub-Division | ¿Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-V under Suri-I, Suri-II & Sainthia Water Supply Scheme Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte.¿(Sl. No.3) | AE | JE2 | ORD/000342/2021-2022 | 1772/BHM | 29/10/2021 | 60 | PRANAB KUMAR GHOSH | 79.83 | 0 | 100
963 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VII under Suri-I, Suri-II & Sainthia Water Supply Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.5) | AE | JE2 | ORD/000343/2021-2022 | 1774/BHM | 29/10/2021 | 60 | M/S KRIPASINDHU GHOSH & CO. | 79.85 | 0 | 100
964 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area for village of Monpur, Kulera, Kukurdihi & Kendua (Zone-III) under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000350/2022-2023 | 2652/BHM | 01/12/2022 | 45 | AVIJIT CHANDA | 17.72 | 0 | 0
965 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VI under Suri-I, Suri-II & Sainthia Water Supply Scheme within Birbhum Sadar Sub- Division Birbhum Division, PHE Dte.¿(Sl. No.4) | AE | JE2 | ORD/000352/2021-2022 | 1820/BHM | 03/11/2021 | 60 | MD. HASIN | 79.86 | 0 | 100
966 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system with the command area of Zone-II under Suri-I, Suri-II & Sainthia Water Supply Scheme with Birbhum Sadar Sub Division Birbhum Division, P.H.E Dte. | AE | JE2 | ORD/000352/2022-2023 | 2654/BHM | 01/12/2022 | 45 | APURBA MONDAL | 17.61 | 0 | 100
967 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV under Suri-I, Suri-II & Sainthia Water Supply Scheme Birbhum Sadar Sub=Division within Birbhum Division, P.H.E. Dte. (Sl. No. 2) | AE | JE2 | ORD/000357/2021-2022 | 1851/BHM | 09/11/2021 | 60 | SAKTI ENTERPRISE | 79.88 | 0 | 100
968 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Suri- I Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 05) | AE | JE2 | ORD/000406/2021-2022 | 380/BSSD | 10/12/2021 | 20 | AATHARVA CONSTRUCTION | 0.99 | 0 | 50
969 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone III under Suri-I, Suri II & Sainthia Water Supply Scheme under Birbhum Sadar Sub- Division within Birbhum Division, PHE Dte. (2nd Call). (Sl. No.11) | AE | JE2 | ORD/000427/2021-2022 | 2170/BHM | 28/12/2021 | 60 | M/S BUILDWELL | 79.48 | 0 | 100
970 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Sainthia Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 07) | AE | JE2 | ORD/000432/2021-2022 | 400/BSSD | 14/12/2021 | 20 | SUBHRADIP SARKAR | 0.99 | 0 | 50
971 | Birbhum Division | Birbhum Sadar Sub-Division | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Hatzen Bazar Dutta Para, Co-Operative Coloney & Hatzen Bazar Das Para at Zone-IV under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 04) | AE | JE2 | ORD/000456/2021-2022 | 06/BSSD | 17/01/2022 | 20 | INDRANIL DUTTA | 4.56 | 0 | 100
972 | Birbhum Division | Birbhum Sadar Sub-Division | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Hatzen Bazar Post Office Para at Zone-IV under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 05) | AE | JE2 | ORD/000457/2021-2022 | 07/BSSD | 17/01/2022 | 20 | PRANAB KUMAR MONDAL | 4.56 | 0 | 100
973 | Birbhum Division | Birbhum Sadar Sub-Division | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Hatzen Bazar Goala Para at Zone-IV under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 03) | AE | JE2 | ORD/000461/2021-2022 | 05/BSSD | 17/01/2022 | 20 | PUSPAJIT MONDAL | 4.58 | 0 | 100
974 | Birbhum Division | Birbhum Sadar Sub-Division | Extension of 75 mm dia.UPVC distribution pipe line from Hatzen Bazar Dutta Para at Zone - IV (Part-B) under Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 02) | AE | JE2 | ORD/000517/2021-2022 | 320/BSSD. | 13/09/2021 | 20 | DIPAK SARKAR | 4.09 | 0 | 100
975 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system with the command area of Zone-VII under Suri-I, Suri-II & Sainthia Water Supply Scheme with Birbhum Sadar Sub Division Birbhum Division, P.H.E Dte. | AE | JE2 | ORD/000599/2022-2023 | 1044/BHM | 31/03/2023 | 45 | ARKA JYOTI GHOSH | 20.49 | 0 | 100
976 | Birbhum Division | Birbhum Sadar Sub-Division | Extension of 75 mm dia.UPVC distribution pipe line from Hatzen Bazar Post Office Para at Zone - IV (Part-B) under Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 01) | AE | JE2 | ORD/000601/2021-2022 | 319/BSSD.. | 13/09/2021 | 20 | ARPAN PANDIT | 4.09 | 0 | 100
977 | Birbhum Division | Birbhum Sadar Sub-Division | Extension of 75 mm dia.UPVC distribution pipe line from Hatzen Bazar Co-Operative Coloney at Zone - IV (Part-B) under Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 04) | AE | JE2 | ORD/000602/2021-2022 | 322/BSSD. | 13/09/2021 | 20 | RANJIT GHOSH | 4.09 | 0 | 100
978 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VIII under Suri-I, Suri-II and Sainthia Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, P.H.E Dte. | AE | JE2 | ORD/000605/2022-2023 | 1049/BHM | 31/03/2023 | 45 | M/S GOUTAM DAS | 29.73 | 0 | 100
979 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Hatzen Bazar Dutta Para, Co-Operative Coloney & Hatzen Bazar Das Para at Zone-IV under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 04) | AE | JE2 | ORD/000644/2022-2023 | 298/BSSD | 15/12/2022 | 20 | NEEL ENTERPRISE | 1 | 0 | 0
980 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Balance FHTC for the villages of Karimpur & rest portion of Dhalla, Kunuri & all other allied works for Zone-II of Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II & Sainthia Block within Birbhum Division, P.H.E. Dte. | AE | JE2 | ORD/000692/2023-2024 | 1039/BHM | 15/03/2024 | 30 | PRONAB KUMAR DEY | 11.79 | 0 | 85
981 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area for village of Monpur, Kulera, Kukurdihi & Kendua (Zone-III) under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000695/2023-2024 | 1043/BHM | 15/03/2024 | 443 | ANIRUDDHA FARUQUE | 20.12 | 0 | 100
982 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of Operator Cum Switch Room 5.00mtr. X 4.00mtr.Size at Zone-IV for the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block under Birbhum Sadar Sub-Division, PHE Dte. within Birbhum Division, P.H.E. Dte (Sl. No.04) | AE | JE2 | ORD/000862/2021-2022 | 1083/BHM | 02/07/2021 | 75 | PRANAB KUMAR MONDAL | 4.96 | 0 | 100
983 | Birbhum Division | Bolpur Sub-Division | Restoration of Road & Balance Laying of Pipeline through Jack pushing Near (Illambazar Traffic More, Illambazar Post Office, Payer School along the NH Road) at Illambazar PWSS due to Laying of Rising & Distribution Pipeline within Bolpur Sub-Division under Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000042/2025-2026 | 1595/BHM | 03/06/2025 | 180 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 309.11 | 0 | 10
984 | Birbhum Division | Bolpur Sub-Division | Repairing and renovation of the Boundary Wall of Labpur Zone-II Water Supply Scheme at Laghata under RWS, Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. Suri, Birbhum(Phase-I) Sl.No.-1. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000095/2022-2023 | 130/BH | 15/06/2022 | 45 | SOURAV MONDAL | 4.23 | 0 | 0
985 | Birbhum Division | Bolpur Sub-Division | Laying distribution system with FHTC for proposed augmentation scheme for Illambazar Piped Water Supply Scheme, Illambazar Block, under Birbhum Division, PHE Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000095/2024-2025 | 2113/BHM | 29/07/2024 | 430 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 625.69 | 0 | 10
986 | Birbhum Division | Bolpur Sub-Division | Repairing of damage pipeline due to construction of Drain work, restoration of road, repairing of FHTC, construction of valve chamber and repairing of pump house boundary wall within the command area of Illambazar, Batikar, Nachansaha, Tinor, Joydev-Kenduli PWSS of Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000121/2025-2026 | 724/BSD | 31/07/2025 | 30 | APURBA MONDAL | 7.09 | 0 | 0
987 | Birbhum Division | Bolpur Sub-Division | Construction of Pump House at Head Work Sites of Zone-II under Augmentation of Kirnahar Water Supply Scheme with laying of rising main from TW- 1 and TW- 2 to CWR and repairing of CWR, Boundary Wall including development of land at Parota under Bolpur Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000170/2024-2025 | 2710/BHM | 24/09/2024 | 90 | ARABINDA GHOSH | 12.71 | 0 | 100
988 | Birbhum Division | Bolpur Sub-Division | Road restoration work for augmentation scheme for Kirnahar Zone- I Piped Water Supply Scheme, Nanoor Block, under Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000191/2025-2026 | 2131/BHM | 18/08/2025 | 90 | TEKNO ENTERPRISE | 15.02 | 0 | 0
989 | Birbhum Division | Bolpur Sub-Division | Road restoration work for augmentation scheme for Kirnahar Zone-Il Piped Water Supply Scheme, Nanoor Block, under Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000195/2025-2026 | 2127/BHM | 18/08/2025 | 90 | M/S ASHA CONSTRUCTION | 16.77 | 0 | 0
990 | Birbhum Division | Bolpur Sub-Division | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Illmbazar W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing)? (Sl. No.2) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000237/2022-2023 | 20003/BHM | 22/09/2022 | 273 | APURBA MONDAL | 185.75 | 0 | 0
991 | Birbhum Division | Bolpur Sub-Division | Construction of 750cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Kirnahar Zone-I W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing)¿ (Sl. No.8) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000241/2022-2023 | 2769/BHM | 14/12/2022 | 274 | TEKNO ENTERPRISE | 165.61 | 0 | 97
992 | Birbhum Division | Bolpur Sub-Division | Construction of 750cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Chandidas W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000251/2022-2023 | 2592/BHM | 23/11/2022 | 273 | CHIRANJIB DAS | 165.15 | 0 | 95
993 | Birbhum Division | Bolpur Sub-Division | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Labhpur Zone-II W/S Scheme under Birbhum Division, PHE Dte. (As per Departmental Drawing) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000252/2022-2023 | 2466/BHM | 11/11/2022 | 273 | SATYANARAYAN ENGINEER'S CO-OP.SOCIETY LTD. | 185.52 | 0 | 20
994 | Birbhum Division | Bolpur Sub-Division | Laying distribution system for proposed augmentation scheme for Labpur (Zone - I) Piped Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000303/2022-2023 | 1028/BHM | 12/05/2022 | 180 | ROY ENTERPRISE | 420.9 | 0 | 100
995 | Birbhum Division | Bolpur Sub-Division | Providing Balance Functional Tap Connection (FHTC) from existing distribution system within the command area for Augmentation of Joydev- Kendhuli Water Supply Scheme (For Swajal Gram) within Bolpur Sub - Division PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000313/2022-2023 | 2498/BHM | 17/11/2022 | 45 | RANJIT GHOSH | 13.69 | 0 | 100
996 | Birbhum Division | Bolpur Sub-Division | Laying distribution system including all types of specials valves street stand post and functional household connection all complete for Augmentation of Chandidas Nanoor Water Supply Scheme in Nanoor Block under Birbhum Division PHE Dte. (Sl.No.4) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000339/2022-2023 | 1070/BHM | 13/05/2022 | 963 | G.D. CONSTRUCTION & CO | 484.01 | 0 | 88
997 | Birbhum Division | Bolpur Sub-Division | Supply and delivery of Sluice Valve for Augmentation of Labpur Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-5) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000344/2023-2024 | 3945/BHM | 03/10/2023 | 30 | KALPANA VALVES MFG CO PVT LTD | 8.68 | 0 | 100
998 | Birbhum Division | Bolpur Sub-Division | Supply and delivery of Sluice Valve for Augmentation of Kirnahar Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-3) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000345/2023-2024 | 3952/BHM | 03/10/2023 | 30 | RAMESH AND SHANTI ENGINEERING WORKS | 8.19 | 0 | 100
999 | Birbhum Division | Bolpur Sub-Division | Supply and delivery of Sluice Valve for Augmentation of Labpur Zone-I W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-4) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000346/2023-2024 | 3951/BHM | 03/10/2023 | 30 | RAMESH AND SHANTI ENGINEERING WORKS | 7.69 | 0 | 100
1000 | Birbhum Division | Bolpur Sub-Division | Supply and delivery of Sluice Valve for Augmentation of Kirnahar Zone-I W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-2) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000347/2023-2024 | 3946/BHM | 03/10/2023 | 30 | SSPR VALVE MANUFACTURING PVT LTD | 9.43 | 0 | 100
1001 | Birbhum Division | Bolpur Sub-Division | Laying of Inter-Connection Pipe Line From T/W No. - 3 to OHR & Repairing of Old Staff Room for the Purpose of Pannel Room of Tubewell No.- 3 Under Tinor W/S Scheme of Bolpur Sub-Division with-In Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000434/2024-2025 | 3433/BHM | 16/12/2024 | 45 | MS AD ENTERPRISE | 1.8 | 0 | 0
1002 | Birbhum Division | Bolpur Sub-Division | Continuation work order for Supply and delivery of Sluice Valve for Augmentation of Labpur Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000454/2023-2024 | 21/BHM | 04/01/2024 | 30 | KALPANA VALVES MFG CO PVT LTD | 8.68 | 0 | 100
1003 | Birbhum Division | Bolpur Sub-Division | Continuation work order for Supply and delivery of Sluice Valve for Augmentation of Labpur Zone-I W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-4) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000466/2023-2024 | 485/BHM | 02/02/2024 | 30 | RAMESH AND SHANTI ENGINEERING WORKS | 7.69 | 0 | 100
1004 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for Supply and delivery of Sluice Valve for Augmentation of Kirnahar Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-3) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000469/2023-2024 | 503/BHM | 02/02/2024 | 30 | RAMESH AND SHANTI ENGINEERING WORKS | 8.19 | 0 | 100
1005 | Birbhum Division | Bolpur Sub-Division | Laying of Distribution system for proposed Augmetation Scheme for Kirnahar ( Zone - II ) and Chandidas Nanoor water Supply scheme on Katowa - Suri Road from Ch. 20.5 to 22.4 km and Naoor - Basapara Road From Node point J34 to J186, J186 to J124, J124 to J33, J33 to J200, J200 to J16, J16 to J9 and J9 to J5 ( by HDD Process with Mechanical Devices and Machinaries required for Treanchless Pipe within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.5) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000508/2022-2023 | 92/BHM | 10/01/2023 | 75 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 148.83 | 0 | 100
1006 | Birbhum Division | Bolpur Sub-Division | Laying of rising main from new Tubewell at Plot No.-5016, JL No. 65, Mouja-Chandidas Nanoor, Block- Nanoor to newly constructed OHR at Head Works site and construction of 1 no. Pump House (Size - 3.0 M x 3.6 M) along with boundary wall (Length - 30 Mtr.) under Augmentation of Chandisas Nanoor PWSS within Bolpur Sub-Division under Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000526/2024-2025 | 258/BHM | 21/01/2025 | 60 | MS KAZIMEHERUDDIN | 8.24 | 0 | 80
1007 | Birbhum Division | Bolpur Sub-Division | Sinking of 02 (Two) no. 250 mm x 200 mm dia. 250 Mtr deep Tube well by Direct Rotary Rig method for Augmentation of Kirnahar Zone - II Water Supply Scheme at Parota Mouja under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No.5) (2nd Call) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000532/2022-2023 | 662/BHM | 28/02/2023 | 30 | ANIRUDDHA FARUQUE | 34.05 | 0 | 100
1008 | Birbhum Division | Bolpur Sub-Division | Laying of Rising Mains from TW-III and TW-IV to OHR in Labpur Zone-II Augmentation Scheme at Labpur Block within Bolpur Sub-Division under BIRBHUM Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000576/2024-2025 | 438/BHM | 10/02/2025 | 60 | ARNAB CHANDRA | 5.88 | 0 | 0
1009 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for Supply and delivery of Sluice Valve for Augmentation of Kirnahar Zone-I W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-2) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000607/2023-2024 | 907/BHM | 13/03/2024 | 30 | SSPR VALVE MANUFACTURING PVT LTD | 9.43 | 0 | 100
1010 | Birbhum Division | Bolpur Sub-Division | Annual Mtc. of pipeline (Distribution and rising main) for the water supply schemes related to the daily supply of water to the consumers under Birbhum Division, PHE Dte.¿ Chandidas Nanoor Water Supply Scheme (Sl. No.-26) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000634/2020-2021 | 1842/BHM | 31/12/2020 | 12 | MS KAZIMEHERUDDIN | 2.98 | 0 | 0
1011 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) for AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Labpur Zone-I & Zone-II Water Supply Scheme within Labpur Block under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 08). | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000648/2021-2022 | 71/BSD | 03/03/2022 | 10 | ANKITA CHAKRABORTY | 1.09 | 0 | 50
1012 | Birbhum Division | Bolpur Sub-Division | Repairing & Renovation of Pump House No.1, boundary wall, construction of drain, painting of pump house & boundary wall etc. of Labpur(Zone-I)W/S scheme situated at Dwarka under Bolpur Sub-Division, within Birbhum Division,PHE Dte.(Sl.No.03) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000720/2021-2022 | 55BH | 17/03/2022 | 90 | SYED HASMAT ALI | 4.01 | 0 | 0
1013 | Birbhum Division | Bolpur Sub-Division | Repairing & Renovation of 2 nos. Pump House with operator room, store room, etc. with coloring of Labpur(Zone-II) W/S Scheme under RWS,Birbhum Sub-Division within Birbhum Division, PHE Dte.(Sl.No.-01) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000722/2021-2022 | 53/BH | 17/03/2022 | 90 | ARNAB CHANDRA | 4.53 | 0 | 100
1014 | Birbhum Division | Bolpur Sub-Division | Repairing & Renovation of Pump House, construction of Approach road with culvert,etc. of Labpur (zone-II) W/S Scheme situated at Laghata under RWS Birbhum Sub-Division within Birrbhum Division,PHE Dte.(Sl No. 02) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000727/2021-2022 | 54/BH | 17/03/2022 | 90 | ANIRUDDHA FARUQUE | 2.31 | 0 | 100
1015 | Birbhum Division | Bolpur Sub-Division | Repairing & Renovation of Pump House No.2 & Boundary Wall at Dwarka of Labpur(Zone-I) Water Supply Scheme under RWS Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000776/2021-2022 | 38/BH | 09/03/2022 | 30 | ARPAN PANDIT | 2.34 | 0 | 100
1016 | Birbhum Division | Bolpur Sub-Division | Distribution System Relating to Augmentation of Joydev-Kenduli Water Supply Scheme , Block Illambazar, District, Birbhum, under Birbhum Division, PHE Dte. (Sl. No. - 04) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000784/2021-2022 | 1729/BHM | 25/10/2021 | 120 | PRANAB KUMAR GHOSH | 84.66 | 0 | 45
1017 | Birbhum Division | Bolpur Sub-Division | Allied works for Dismantling of PCC road for Laying of Distribution pipeline and inter-connection to existing pipe line of TINOR Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, Public Health Engineering Department. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000915/2022-2023 | 282/BSD | 25/07/2022 | 20 | G.D. CONSTRUCTION & CO | 4.55 | 0 | 0
1018 | Birbhum Division | Bolpur Sub-Division | Allied works for Dismantling of PCC road for Laying of Distribution pipeline and inter-connection to existing pipeline of Joydev Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, P.H.E. Deptt. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000936/2022-2023 | 238/BSD | 17/06/2022 | 15 | PRANAB KUMAR GHOSH | 4.84 | 0 | 100
1019 | Birbhum Division | Bolpur Sub-Division | Laying Distribution System for proposed augmentation Scheme for Kirnahar (Zone-II) piped Water Supply Scheme under Nanoor Block, under Birbhum Division, PHE Dte. (Sl. -06) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000949/2021-2022 | 648/BHM | 25/03/2022 | 1225 | M/S ASHA CONSTRUCTION | 325.5 | 0 | 70
1020 | Birbhum Division | Bolpur Sub-Division | Distribution System Relating To Augmentation Of Joydev-Kenduli Water Supply Scheme, Block -Illambazar, District - Birbhum, Under Birbhum Division, P.H.E. Dte.. (Sl. No.-4) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000964/2021-2022 | 1724/BHM | 25/10/2021 | 120 | PRANAB KUMAR GHOSH | 84.66 | 0 | 62
1021 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | RTOR000007/2023-2024 | 1112/BHM | 10/04/2023 | 0 | Resource Division | 34.68 | 0 | 0
1022 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | RTOR000015/2022-2023 | 909/BHM | 26/04/2022 | 0 | Resource Division | 21.38 | 0 | 0
1023 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | RTOR000025/2022-2023 | 2206/BHM | 12/10/2022 | 0 | Resource Division | 82.06 | 0 | 0
1024 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | RTOR000031/2022-2023 | 2293/BHM | 20/10/2022 | 0 | Resource Division | 68.75 | 0 | 0
1025 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | RTOR000068/2021-2022 | 595/BHM | 09/03/2022 | 0 | Resource Division | 751.34 | 0 | 0
1026 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | RTOR000177/2023-2024 | 2072/BHM | 14/06/2023 | 0 | Resource Division | 43.12 | 0 | 0
1027 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | RTOR000184/2023-2024 | 2279/BHM | 13/07/2023 | 0 | Resource Division | 142.55 | 0 | 0
1028 | Birbhum Division | Bolpur Sub-Division | Materials Payment | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | VCH/001323/2021-2022 | BP-2021-22-355 | 14/03/2022 | 0 | RESOURCES DIVISION | 602.7 | 0 | 0
1029 | Bolpur Mechanical | Bolpur Sub-Division | NEW SERVICE CONNECTION FOR KIRNAHAR WATER SUPPPLY SCHEME Z0NE-I, PH-I. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | BILL/00072/2024-2025 | BP-2024-2025-32 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.08 | 0 | 0
1030 | Bolpur Mechanical | Bolpur Sub-Division | NEW SERVICE CONNECTION FOR KIRNAHAR WATER SUPPLY SCHEME ZONE-I, PH-II. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | BILL/00229/2024-2025 | BP-24-25-112 | 02/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.38 | 0 | 0
1031 | Bolpur Mechanical | Bolpur Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Lavpur Zone - I Water Supply Scheme under Bolpur Mechanical Division PHE Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000242/2023-2024 | 1432/Bol.MD | 11/07/2023 | 45 | MITRA ENTERPRISE | 18.87 | 0 | 70
1032 | Bolpur Mechanical | Bolpur Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Lavpur Zone - II Water Supply Scheme under Bolpur Mechanical Division PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000246/2023-2024 | 1433/Bol.MD | 11/07/2023 | 45 | M/S SWAPAN BANERJEE | 28.36 | 0 | 70
1033 | Bolpur Mechanical | Bolpur Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Kirnahar Zone - I Water Supply Scheme under Bolpur Mechanical Division PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000249/2023-2024 | 1434/Bol.MD | 11/07/2023 | 448 | SINHA ELECTRICALS | 19.43 | 0 | 100
1034 | Bolpur Mechanical | Bolpur Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Kirnahar Zone - II Water Supply Scheme under Bolpur Mechanical Division PHE Dte.. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000250/2023-2024 | 1435/Bol.MD | 11/07/2023 | 45 | EASTERN INDIA SALES & SERVICE | 18.86 | 0 | 72
1035 | Bolpur Mechanical | Bolpur Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 300 Mtrs. Depth ) by utilising Hired Rig Machine at Bipratikuri PWSS (at defunct 2nd tube well site) , Block - Labhpur, (under Retrofitting of Lavpur Block) under Bolpur Mechanical Division, P.H.E. Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000337/2023-2024 | 1645/Bol.MD | 25/07/2023 | 60 | SATYAJIT GHOSH | 21.43 | 0 | 100
1036 | Bolpur Mechanical | Bolpur Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 300 Mtrs. Depth ) by utilising Hired Rig Machine at Kirnahar Zone - I PWSS (at Debogram) , Block - Nanoor, (under Augmentation of 6 nos. schemes of Lavpur PWSS, Illambazar PWSS, Joydev Kenduli PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS) under Bolpur Mechanical Division, P.H.E. Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000338/2023-2024 | 1646/Bol.MD | 25/07/2023 | 60 | SATYAJIT GHOSH | 42.86 | 0 | 100
1037 | Bolpur Mechanical | Bolpur Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 300 Mtrs. Depth ) by utilising Hired Rig Machine at Lavpur Zone - I & Zone - II PWSS (at Dwarka & Zone - II at Head Works site) , Block - Lavpur, (under Augmentation of 6 nos. schemes of Lavpur PWSS, Illambazar PWSS, Joydev Kenduli PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS) under Bolpur Mechanical Division, P.H.E. Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000339/2023-2024 | 1647/Bol.MD | 25/07/2023 | 60 | SATYAJIT GHOSH | 42.86 | 0 | 100
1038 | Bolpur Mechanical | Bolpur Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 300 Mtrs. Depth ) by utilising Hired Rig Machine at Illambazar and Tinoor PWSS (at Head Works site) , Block - Illambazar (under Augmentation of 6 nos. schemes of Lavpur PWSS, Illambazar PWSS, Joydev Kenduli PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS) under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000340/2023-2024 | 1648/Bol.MD | 25/07/2023 | 60 | SATYAJIT GHOSH | 42.86 | 0 | 100
1039 | Bolpur Mechanical | Bolpur Sub-Division | Providing Electro-mechanical accessories including other allied works for Augmentation of ILLAMBAZAR PWSS under Bolpur Mechanical Division PHE Dte. Block : Illambazar, Dist : Birbhum. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000493/2023-2024 | 2248/Bol.MD | 13/09/2023 | 60 | EASTERN INDIA SALES & SERVICE | 30.28 | 0 | 60
1040 | Bolpur Mechanical | Bolpur Sub-Division | Providing Electro-mechanical accessories including other allied works for Augmentation of TINOOR Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. Block : Illambazar, Dist : Birbhum. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000494/2023-2024 | 2249/Bol.MD | 13/09/2023 | 60 | DEY ENTERPRISE | 21.4 | 0 | 0
1041 | Bolpur Mechanical | Bolpur Sub-Division | Supply and installation of Pumps and other electro-mechanical accessories for Augmentation of Nanoor water supply scheme T.W. No.- 1 under Bolpur Mechanical Division PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000495/2023-2024 | 2250/Bol.MD | 13/09/2023 | 60 | STANDARD ELECTRICALS | 5.78 | 0 | 100
1042 | Bolpur Mechanical | Bolpur Sub-Division | Providing Electro-mechanical accessories including other allied works for Augmentation of JOYDEV-KENDULI Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. Block : Illambazar, Dist : Birbhum. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000984/2023-2024 | 3600/BOL.MD | 12/12/2023 | 90 | RSA ENTERPRISE | 21.19 | 0 | 0
1043 | Bolpur Mechanical | Bolpur Sub-Division | Supply & Installation of Motor control Panels at the Kirnahar Water Supply Scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,JE2 ,JE3 ,JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/001260/2023-2024 | 559/BOL.MD | 15/03/2024 | 30 | SINHA ELECTRICALS | 2.92 | 0 | 100
1044 | Birbhum Division | Rampurhat Sub-Division | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for 1 no OHR site at Augmentation of Mollarpur Zone-II Piped Water Supply Scheme under Rampurhat Sub-Division within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000025/2022-2023 | 174/RSD | 29/04/2022 | 30 | GEOCON INDIA | 0.99 | 0 | 100
1045 | Birbhum Division | Rampurhat Sub-Division | Additional Laying distribution system at different mouzas including Functional Household Tap Connection under Augmentation of Hatgacha Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000032/2023-2024 | 1097/BHM | 06/04/2023 | 90 | S S ENTERPRISE | 273.65 | 0 | 50
1046 | Birbhum Division | Rampurhat Sub-Division | Sinking of 01 Nos Tube well 200 mm dia 96 m. deep tube well fitted with PVC pipe and fiber glass Strainer at Augmentation of Mollarpur Zone-II PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000034/2022-2023 | 184/RSD | 02/05/2022 | 30 | HARUN AR RASHID | 4.97 | 0 | 100
1047 | Birbhum Division | Rampurhat Sub-Division | Laying distribution system for proposed augmentation scheme for Mayureswar Piped Water Supply Scheme, Mayureswar-II Block under Birbhum Division, PHE Dte. (Sl. No.2) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000040/2022-2023 | 1010/BHM | 11/05/2022 | 1061 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 502.2 | 0 | 100
1048 | Birbhum Division | Rampurhat Sub-Division | Additional Laying distribution system at different mouzas, including the Functional Household Tap Connection under Augmentation of Mollarpur Zone I (Part-B & C) Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000040/2025-2026 | 1452/BHM | 19/05/2025 | 181 | M/S GOUTAM DAS | 121.47 | 0 | 40
1049 | Birbhum Division | Rampurhat Sub-Division | Laying distribution system including functional household connection for proposed Augmentation of Hatgacha Piped Water Supply Scheme in Md. Bazar Block under Birbhum Division, P.H.E Dte.¿ (Sl. No.1) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000041/2022-2023 | 1027/BHM | 12/05/2022 | 180 | S S ENTERPRISE | 428.01 | 0 | 100
1050 | Birbhum Division | Rampurhat Sub-Division | Miscellaneous works including painting, earthling, repairing of entrance gate etc at head work site at Kharasinpur of OHR, Boundary Wall etc of Mollarpur Zone-II at Mollarpur Zone -II PWSS under Rampurhat Sub Division P.H.E Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000055/2023-2024 | 1254/BHM | 17/04/2023 | 45 | MD SURAJ ALI | 3.15 | 0 | 100
1051 | Birbhum Division | Rampurhat Sub-Division | Laying distribution system for proposed augmentation scheme for Mollarpur Zone-II Piped Water Supply Scheme, Block-Mayureswar-I under Birbhum Division, PHE Dte. (Sl. No.3) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000060/2022-2023 | 1152/BHM | 23/05/2022 | 719 | SUNIL RABI DAS | 401.72 | 0 | 100
1052 | Birbhum Division | Rampurhat Sub-Division | Repairing and Renovation of R.C.C. Over Head Reservoir for Md. Bazar Piped Water Supply Scheme, under Birbhum Division, P.H.E. Dte.(Sl. No.05) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000062/2022-2023 | 89/BH | 05/05/2022 | 30 | BHASKAR MANDAL | 4.05 | 0 | 100
1053 | Birbhum Division | Rampurhat Sub-Division | Repairing Work Of Bishnupur 1 No Pump House & 2 No Pump House Unedr RWS,Birbhum Sub-Division,PHE Dte, Within Birbhum Division,PHE Dte.(Sl. No.02) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000065/2022-2023 | 87/BH | 05/05/2022 | 20 | RIPAN CONSTRUCTION | 2.72 | 0 | 0
1054 | Birbhum Division | Rampurhat Sub-Division | Distribution System within the command area of Bishnupur Water Supply Scheme (Baswa Latpara & Lalitakundu Purba Para) under RWS Birbhum Sub-Division, within Birbhum Division, PHE Dte.(Sl. No.06) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000080/2022-2023 | 135/BH | 15/06/2022 | 30 | BIJOY KUMAR CHOUDHURY | 4.58 | 0 | 100
1055 | Birbhum Division | Rampurhat Sub-Division | Distribution System including providing Functional Household Tap Connection(FHTC) at Lalitakundu Paschim Par within the command area of Bishnupur Water Supply Scheme Under RWS Birbhum Sub-Division,within Birbhum Division,PHE Dte.(Sl. No.07) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000081/2022-2023 | 136/BH | 15/06/2022 | 30 | BIJOY KUMAR CHOUDHURY | 4.71 | 0 | 50
1056 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection(FHTC) at Baswa Lat Para within the command area of Bishnupur Water Supply Scheme under RWS Birbhum Sub-Divition within Birbhum Division PHE Dte.(Sl. No.09) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000088/2022-2023 | 138/BH | 15/06/2022 | 20 | BIJOY KUMAR CHOUDHURY | 3.6 | 0 | 50
1057 | Birbhum Division | Rampurhat Sub-Division | Allied Work in connection with Laying of UPVC pipe line at Kharia village for Md. Bazar Piped Water Supply Scheme under RWS Birbhum Sub Division,within Birbhum Division PHEDte ,Suri, Birbhum..(Sl. No.04) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000089/2022-2023 | 133/BH | 15/06/2022 | 20 | SAI BABA CONSTRUCTION | 0.94 | 0 | 100
1058 | Birbhum Division | Rampurhat Sub-Division | Allied work for balance portions of Laying distribution system for proposed augmentation scheme of Md.Bazar Piped Water Supply Scheme under Md.Bazar Block, Sinking of 200 mm dia. tubewell (03 nos.) 28 m. Deep fitted with PVC Housing pipe and Fibre Glass Strainer with connecting pipe line with surging of existing 2 (Two) nos. Tube well including renovation of boundary wall at Head Work Site of Md. Bazar Piped Water Supply Scheme under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000118/2023-2024 | 2079/BHM | 08/06/2023 | 60 | M/S GOUTAM DAS | 52.61 | 0 | 100
1059 | Birbhum Division | Rampurhat Sub-Division | Sinking of 03 (Three) Nos Tubewell 200 mm X 200 mm dia X180m. deep tubewells by Rotary Rig including connecting rising main at Augmentation of Mollarpur Zone-I (Part-C) PWSS under Rampurhat Sub-Division within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000118/2025-2026 | 634/RSD | 15/07/2025 | 60 | PULAK KUMAR PAL | 38.38 | 0 | 0
1060 | Birbhum Division | Rampurhat Sub-Division | Repairing Work Of Bishnupur 1 No Pump House & 2 No Pump House Unedr RWS,Birbhum Sub-Division,PHE Dte, Within Birbhum Division,PHE Dte.(Sl. No.02) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000146/2022-2023 | 87/BH | 05/05/2022 | 20 | RIPAN CONSTRUCTION | 2.73 | 0 | 0
1061 | Birbhum Division | Rampurhat Sub-Division | Additional Laying distribution system at different mouzas including Functional Household Tap Connection under Augmentation of Mollarpur Zone-I (Part-A) Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000173/2024-2025 | 2630/BHM | 12/09/2024 | 454 | M/S GOUTAM DAS | 90.71 | 0 | 55
1062 | Birbhum Division | Rampurhat Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) by Adopting Jack Pushing Technique for laying Additional distribution system and Laying of Rising Main under Mollarpur Zone-II Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000174/2024-2025 | 2730/BHM | 25/09/2024 | 446 | SUNIL RABI DAS | 96 | 0 | 30
1063 | Birbhum Division | Rampurhat Sub-Division | Sinking of 02 nos. (01 Additional + 01 Replaced) Tube well (200mm dia, all through 150 mt. Deep) along with Rising Main and Construction of 01 no. Pump House for Mollarpur Zone-II PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000175/2024-2025 | 2729/BHM | 25/09/2024 | 272 | SUNIL RABI DAS | 23.99 | 0 | 70
1064 | Birbhum Division | Rampurhat Sub-Division | Sinking of 01 (One) No. replacement & 01 (One) new Tube well 200 mm X 200 mm dia X 180m. deep tube wells by Rotary Rig including connecting DI rising main along with allied civil works for Augmentation of Mollarpur Zone-I (Part-A) PWSS under Rampurhat Sub-Division within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000208/2025-2026 | 737/RSD | 20/08/2025 | 60 | RAJ ASSOCIATES | 40.56 | 0 | 0
1065 | Birbhum Division | Rampurhat Sub-Division | Sinking of 02 (Two) Nos. new Tube well 200 mm X 200 mm dia X 180m. deep tube wells by Rotary Rig including connecting DI rising main along with allied civil works for Augmentation of Mollarpur Zone-I (Part-B) PWSS under Rampurhat Sub-Division within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000236/2025-2026 | 2206/BHM | 26/08/2025 | 90 | RADHARANI ENTERPRISE | 51.13 | 0 | 0
1066 | Birbhum Division | Rampurhat Sub-Division | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Mollarpur Zone-I W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing)¿ (Sl. No.5) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000238/2022-2023 | 2247/BHM | 17/10/2022 | 273 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 185.79 | 0 | 85
1067 | Birbhum Division | Rampurhat Sub-Division | Construction of 750cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Bishnupur W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing)¿ (Sl. No.7) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000240/2022-2023 | 2727/BHM | 08/12/2022 | 274 | S K CONSTRUCTION | 165.71 | 0 | 100
1068 | Birbhum Division | Rampurhat Sub-Division | Different works such as Pump House, Boundary wall, Rising main, LDS, repairing works and allied works related to Augmentation of Bishnupur PWSS within Birbhum RWS Sub-Division, under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000257/2025-2026 | 2197/BHM | 22/08/2025 | 90 | SUBHANKAR ROY | 109.95 | 0 | 0
1069 | Birbhum Division | Rampurhat Sub-Division | Laying distribution system for proposed augmentation scheme for Md. Bazar Piped Water Supply Scheme under Md. Bazar Block, under Birbhum Division, PHE Dte (Sl. No.7) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000264/2022-2023 | 859/BHM | 20/04/2022 | 498 | M/S GOUTAM DAS | 319.7 | 0 | 95
1070 | Birbhum Division | Rampurhat Sub-Division | Additional Laying distribution system at Mayureswar, Kushtor and Adjoining Mouzas including Functional Household Tap Connection under Augmentation of Mayureswar Piped Water Supply Scheme under Rampurhat sub-Division, under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000264/2025-2026 | 2360/BHM | 11/09/2025 | 90 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 130.05 | 0 | 0
1071 | Birbhum Division | Rampurhat Sub-Division | Laying distribution system including FHTC for proposed augmentation scheme for Mollarpur Zone-I Piped Water Supply Scheme, Mayureswar-I Block, under Birbhum Division, PHE Dte. (2nd Call)¿ (SL.No.1) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000272/2022-2023 | 2246/BHM | 17/10/2022 | 951 | M/S GOUTAM DAS | 908.98 | 0 | 78
1072 | Birbhum Division | Rampurhat Sub-Division | Sinking of 01 (One) No. Tube well 200 mm X 200 mm dia X180m. deep tube wells by Rotary Rig including connecting main at Augmentation of Mollarpur Zone-II PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000298/2023-2024 | 3673/BHM | 29/08/2023 | 45 | HARUN AR RASHID | 13.71 | 0 | 100
1073 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development (PH No-3) for Augumentation of Mollarpur Zone-I Part -C Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000351/2023-2024 | 3948/BHM | 03/10/2023 | 183 | ABUL HASNATH | 11.59 | 0 | 100
1074 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development (PH No-1) for Augumentation of Mollarpur Zone-I Part -C Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000357/2023-2024 | 3955/BHM | 03/10/2023 | 183 | AINUL SHAIKH | 9.98 | 0 | 0
1075 | Birbhum Division | Rampurhat Sub-Division | Sinking of 03 (Three) nos. Rig Bored Tube well by DTH method of drilling (125 mm X 115 mm) dia for source Augmentation of Hatgacha PWSS under Rampurhat Sub-Division, Birbhum Division P.H.E Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000357/2024-2025 | 3156/BHM | 19/11/2024 | 45 | BHABATARAN SADHU | 9.87 | 0 | 0
1076 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development (PH No-2) for Augumentation of Mollarpur Zone-I Part -C Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000362/2023-2024 | 3994/BHM | 05/10/2023 | 60 | ABDUL MOTALIB | 11.13 | 0 | 0
1077 | Birbhum Division | Rampurhat Sub-Division | Sinking of 1 No. 200 mm dia 72 Metre deep tubewell fitted with 200 mm dia PVC pipe and fibre glass stainer etc under Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000368/2021-2022 | 176/BH | 03/11/2021 | 15 | AMIT KUMAR ROY | 3.5 | 0 | 82
1078 | Birbhum Division | Rampurhat Sub-Division | Additional work for connecting pipeline from ground bore tubewell 03 nos. existing distribution system of Bishnupur pipe water supply scheme under RWS, Birbhum Sub-Division within Birbhum Divsion, PHE Dte.(Sl.No.1) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000373/2024-2025 | 184/RWS | 21/11/2024 | 15 | BHASKAR MANDAL | 0.97 | 0 | 70
1079 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall,PCC approach Road,Land Development (PH No-2) for Augmentation of Mayureswar Piped Water Supply Scheme, Block -Mayureswar-II within Birbhum Division, PHE Dte. (Sl. No.6) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000382/2022-2023 | 2842/BHM | 21/12/2022 | 60 | NOBI SEIKH | 13.39 | 0 | 100
1080 | Birbhum Division | Rampurhat Sub-Division | Laying of bypass Connection line and Land Development at Khorasinpur Ohr site under Mollarpur Zone-II W/S Scheme under Rampurhat Sub- Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000390/2021-2022 | 371/RSD | 28/09/2021 | 30 | SHIB GANGA CONSTRUCTION | 4.24 | 0 | 100
1081 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall,PCC approach Road,Land Development (PH No-2) for Augumentation of Mollarpur Zone-I Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. (Sl. No.2) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000390/2022-2023 | 2915/BHM | 27/12/2022 | 60 | SAFIUDDIN SEKH | 11.31 | 0 | 100
1082 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall,PCC approach Road, Land Development (PH No-3) for Augmentation of Mollarpur Zone-I Piped Water Supply Scheme, Block-Mayureswar-I within Birbhum Division, PHE Dte. (Sl. No.3) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000391/2022-2023 | 2914/BHM | 27/12/2022 | 60 | SAFIUDDIN SEKH | 11.25 | 0 | 100
1083 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall, PCC approach Road, Land Development (PH No-3) for Augmentation of Mayureswar Piped Water Supply Scheme, Block-Mayureswar-II within Birbhum Division, PHE Dte. (Sl. No.7) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000407/2022-2023 | 39/BHM | 04/01/2023 | 60 | SK GOLAM MORTUJA | 11.37 | 0 | 100
1084 | Birbhum Division | Rampurhat Sub-Division | Sinking of 2 Nos. 200 mm dia X 66 mtr. deep Tubewell with UPVC pipe and strainer for Bishnupur W/S Scheme under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000450/2023-2024 | 09/BHM | 03/01/2024 | 240 | HARUN AR RASHID | 8.38 | 0 | 97
1085 | Birbhum Division | Rampurhat Sub-Division | Alided work of Connecting pipe line from Ground Bore Tube Well to Existing distribution system of Bishnupur Piped Water Supply Scheme, under RWS Birbhum Sub-Division within Birbhum Division, P.H.E. Dte. (Sl. No.2) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000476/2022-2023 | 226/BHM | 20/01/2023 | 15 | SEVAK CO - OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD | 2.42 | 0 | 100
1086 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall, PCC approach Road, Land Development (PH No-1) for Augmentation of Mayureswar Piped Water Supply Scheme, Block-Mayureswar-II within Birbhum Division, PHE Dte. (Sl. No.5) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000478/2022-2023 | 228/BHM | 20/01/2023 | 60 | CHOWDHURY ENTERPRISE | 11.39 | 0 | 100
1087 | Birbhum Division | Rampurhat Sub-Division | Painting of R.C.C. Over Head Reservoir for Md. Bazar Piped Water Supply Scheme, under RWS Birbhum Sub-Division within Birbhum Division, P.H.E. Dte. (Sl. No.8) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000479/2022-2023 | 229/BHM | 20/01/2023 | 15 | BHASKAR MANDAL | 1.76 | 0 | 100
1088 | Birbhum Division | Rampurhat Sub-Division | Laying distribution System including providing Functional Household Tap Connection(FHTC) within the command area Augmentation of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.14) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000493/2022-2023 | 285/BHM | 01/02/2023 | 45 | TAPAN KUMAR DATTA | 74.19 | 0 | 16
1089 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development (PH No-1) for Augumentation of Mollarpur Zone-I Piped Water Supply Scheme, Block-Mayureswar-I within Birbhum Division, PHE Dte. (Sl. No.1) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000502/2022-2023 | 334/BHM | 02/02/2023 | 60 | JAHIR HOSSAIN | 10.42 | 0 | 0
1090 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch room at Head work Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development for (PH No-1) for Augumentation of Mollarpur Zone-II Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. (Sl. No.4) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000512/2022-2023 | 518/BHM | 20/02/2023 | 60 | ANARUL HOQUE | 14.5 | 0 | 100
1091 | Birbhum Division | Rampurhat Sub-Division | Sinking of 03 (Three) Nos Tubewell 250 mm X 150 mm dia X 300 m. deep tubewells by Rotary Rig at Augumentation of Mollarpur Zone-I PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. (Sl. No.3) (2nd Call) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000539/2022-2023 | 713/BHM | 02/03/2023 | 45 | SUNIL RABI DAS | 56.14 | 0 | 100
1092 | Birbhum Division | Rampurhat Sub-Division | Sinking of 04 (Four) Nos Tubewell 250 mm X 150 mm dia X 300 m. deep tubewells by Rotary Rig at Augmentation of Mayureswar PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. (Sl. No.1) (2nd Call) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000551/2022-2023 | 810/BHM | 14/03/2023 | 60 | SATYAJIT GHOSH | 74.84 | 0 | 100
1093 | Birbhum Division | Rampurhat Sub-Division | Additional Laying distribution system at Kotasur and Adjoining Mouzas including Functional Household Tap Connection under Augmentation of Mayureswar Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000569/2024-2025 | 400/BHM | 06/02/2025 | 90 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 97.7 | 0 | 0
1094 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch room at Pump House Site with sanitary and water supply arrangement as per departmental drawing (Size 3.60 mtr. x 3.30 mtr. room with 1.2 mtr. wide verandah), Boundary Wall, PCC approach Road (PH No.-4) for Augmentation of Mayureswar Piped Water Supply Scheme, Block-Mayureswar-II within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000578/2023-2024 | 757/BHM | 01/03/2024 | 354 | M/S ZEBA | 10.17 | 0 | 65
1095 | Birbhum Division | Rampurhat Sub-Division | Laying of Balance Distribution Main pipeline through road crossing of SH 11 and Md Bazar-Kulkuri Road (Node R1-1, 4-47, 7-87, 9-108, 18-24, 28-29, 30-270 & 34-317) and NH-14 (Node 33-34) by adopting Jack Pushing method for Augmentation of Md Bazar Piped Water Supply Scheme under Md Bazar Block, under Birbhum Division P.H.E Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000602/2022-2023 | 1046/BHM | 31/03/2023 | 60 | M/S GOUTAM DAS | 57.55 | 0 | 0
1096 | Birbhum Division | Rampurhat Sub-Division | Annual Mtc. of pipeline (Distribution and rising main) for the water supply schemes related to the daily supply of water to the consumers under Birbhum Division, PHE Dte.¿ Bishnupur W/S Scheme (Sl. No.-49) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000635/2020-2021 | 1865/BHM | 31/12/2020 | 365 | TAPAN ENTERPRISE | 2.99 | 0 | 0
1097 | Birbhum Division | Rampurhat Sub-Division | Jack pushing & Augur boring along with extension of pipeline, restoration of Roads and all allied works for Mohammad Bazar piped Water Supply Scheme under Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000688/2024-2025 | 862/BHM | 26/03/2025 | 157 | M/S GOUTAM DAS | 69.84 | 0 | 100
1098 | Birbhum Division | Rampurhat Sub-Division | Rising Main with 200mm dia DI pipe and Delivery main with 200mm dia HDPE pipe for OHR under Bishnupur Piped Supply Scheme of Birbhum RWS Sub-Division, Block- Rampurhat-II, P.H.E. Dte. within Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000690/2024-2025 | 865/BHM | 26/03/2025 | 60 | TAPAN KUMAR DATTA | 40.58 | 0 | 0
1099 | Birbhum Division | Rampurhat Sub-Division | Sinking of one unmber 200mm dia 50m. deep tubewell fitted with 200mm dia. PVC pipe and Strainer etc. at Bishnupur W/S Scheme under RWS, Birbhum Sub-Division,PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000732/2021-2022 | 20/BH | 18/02/2022 | 20 | TAPAN ENTERPRISE | 2.65 | 0 | 100
1100 | Birbhum Division | Rampurhat Sub-Division | Laying of UPVC pipe line for supply of drinking water at Damra Namupara village under Md. Bazar Block within Birbhum Division, P.H. E Dte. (Sl. No. - 05) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000743/2020-2021 | 50/BSSD | 18/02/2021 | 15 | B.M.SARKAR | 4.86 | 0 | 100
1101 | Birbhum Division | Rampurhat Sub-Division | Repairing Renovation and up-gradation of Resting Room of Security Guard of Mayureswar Piped Water Supply Scheme under RWS Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000777/2021-2022 | 36/BH | 09/03/2022 | 30 | SUBHANKAR ROY | 3.61 | 0 | 100
1102 | Birbhum Division | Rampurhat Sub-Division | Connecting pipe line from ground bore tube well to existing distribution system of Bishnupur W/S Scheme under Bishnupur water supply scheme, Dist-Birbhum under Birbhum Division,PHE.Dte.(Part-II) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000829/2021-2022 | 22/BH | 18/02/2022 | 20 | BHASKAR MANDAL | 2.02 | 0 | 92
1103 | Birbhum Division | Rampurhat Sub-Division | Connecting pipe line from ground bore tube well to existing distribution system of Bishnupur W/S Scheme under Bishnupur W/S Scheme dist. birbhum division, PHE Dte.(Part-I) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000868/2021-2022 | 21/BH | 18/02/2022 | 20 | TAPAN ENTERPRISE | 4.83 | 0 | 100
1104 | Birbhum Division | Rampurhat Sub-Division | Laying of UPVC pipe line at Kharia village for Md. Bazar Piped Water supply scheme under RWS Birbhum Sub-Division within Birbhum Division, PHE Dte. (sl. no.) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000886/2021-2022 | 56/BH | 17/03/2022 | 20 | SAI BABA CONSTRUCTION | 1.07 | 0 | 100
1105 | Birbhum Division | Rampurhat Sub-Division | Repairing and Renovation of Bargachha Pump House and Boundary Wall under Md. Bazar Piped Water Supply Scheme under RWS, Birbhum Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000902/2021-2022 | 34/BH | 09/03/2022 | 30 | ARYAN CONSTRUCTION | 3.9 | 0 | 100
1106 | Birbhum Division | Rampurhat Sub-Division | Construction of Switch room cum chlorine room with sanitary and water supply arrangement 5.40mtr.x 3.65mtr. size Bishnupur W/S Scheme under Rumpurhat Sub- Division,P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/001087/2021-2022 | 23/BH | 18/02/2022 | 20 | TAPAN ENTERPRISE | 4.98 | 0 | 100
1107 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000022/2022-2023 | 2208/BHM | 12/10/2022 | 0 | Resource Division | 6.02 | 0 | 0
1108 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000029/2022-2023 | 2294/BHM | 20/10/2022 | 0 | Resource Division | 5.82 | 0 | 0
1109 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000069/2021-2022 | 596/BHM | 09/03/2022 | 0 | Resource Division | 525.88 | 0 | 0
1110 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000105/2022-2023 | 1123/BHM | 10/04/2023 | 0 | Resource Division | 32.67 | 0 | 0
1111 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000175/2023-2024 | 2071/BHM | 14/06/2023 | 0 | Resource Division | 30.8 | 0 | 0
1112 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000182/2023-2024 | 2277/BHM | 13/07/2023 | 0 | Resource Division | 54.13 | 0 | 0
1113 | Birbhum Division | Rampurhat Sub-Division | Materials Payment | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | VCH/001324/2021-2022 | BP-2021-22-355 | 14/03/2022 | 0 | RESOURCES DIVISION | 497.76 | 0 | 0
1114 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new connection at Augmentation Mollarpur PWSS (Malanchi), block- Mayureswar-I | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00079/2024-2025 | BP-2024-2025-36 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.85 | 0 | 0
1115 | Bolpur Mechanical | Rampurhat Sub-Division | quotation for Aug. of Bishnupur water supply scheme | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00091/2022-2023 | BP-2022-2023-79 | 20/12/2022 | 0 | WBSEDCL | 1.98 | 0 | 0
1116 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOATATION MONEY FOR MOLLARPUR ZONE-II WS SCHEME | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00114/2023-2024 | BP-2023-2024-33 | 18/05/2023 | 0 | WBSEDCL | 2.9 | 0 | 0
1117 | Bolpur Mechanical | Rampurhat Sub-Division | New Power Connection at Delora PWSS under Bolpur mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00414/2024-2025 | BP-24-25-130 | 29/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.84 | 0 | 0
1118 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOATAION FOR MUYURESWAR WS SCHEME | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00723/2023-2024 | BP-2023-2024-74 | 23/08/2023 | 0 | WBSEDCL | 2.64 | 0 | 0
1119 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR MAYURESWAR WS SCHEME | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00724/2023-2024 | BP-2023-2024-75 | 24/08/2023 | 0 | WBSEDCL | 4.48 | 0 | 0
1120 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR AUG OF MOLLARPUR | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00931/2023-2024 | BP-2023-2024-81 | 18/09/2023 | 0 | WBSEDCL | 4.98 | 0 | 0
1121 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR AUG OF MOLLARPUR | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00932/2023-2024 | BP-2023-2024-80 | 18/09/2023 | 0 | WBSEDCL | 2.99 | 0 | 0
1122 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR RAJCHANDRAPUR P.H.NO. 4 PWSS FOR AUG. OF MAYURESWAR WS SCHEME | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/01277/2023-2024 | BP-23-24-132 | 17/10/2023 | 0 | WBSEDCL | 5.26 | 0 | 0
1123 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Md. Bazar water supply scheme under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000010/2023-2024 | 718/Bol.MD | 19/04/2023 | 45 | HINDOL ROY | 35.27 | 0 | 100
1124 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electro mechanical equipments at Augmentation of Hatgacha Piped water supply scheme under MD Bazar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000041/2025-2026 | 736/BOL.MD | 29/04/2025 | 45 | TAPAN ENTERPRISE | 5.24 | 0 | 0
1125 | Bolpur Mechanical | Rampurhat Sub-Division | Supply delivery & Installation of Voltage correction device at Mollarpur Zone-II (Kamraghat) water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000049/2023-2024 | 1036/Bol.MD | 05/06/2023 | 45 | S.K.ELECTRICALS | 12.8 | 0 | 0
1126 | Bolpur Mechanical | Rampurhat Sub-Division | SUPPLY DELIVERY & INSTALLATION OF ELECTRO MECHANICAL ACCESSORIES AND OTHER ALLIED WORKS AT BISHNUPUR WATER SUPPLY SCHEME. UNDER BOLPUR MECHANICAL DIVISION PHE DTE. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000125/2022-2023 | 740/AE-III | 24/06/2022 | 20 | SUNIL RABIDAS | 4.85 | 0 | 0
1127 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electro mechanical equipments at Augmentation of Mollarpur Zone-I and Zone-II Piped water supply scheme under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000251/2023-2024 | 1436/Bol.MD | 11/07/2023 | 419 | SUNIL RABIDAS | 47.6 | 0 | 100
1128 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electro mechanical equipments at Augmentation of Hatgacha Piped water supply scheme under MD Bazar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000253/2023-2024 | 1437/Bol.MD | 11/07/2023 | 45 | TAPAN ENTERPRISE | 5.24 | 0 | 0
1129 | Bolpur Mechanical | Rampurhat Sub-Division | Supply delivery & Installation of Voltage correction device at Bishnapur Augmentation water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000328/2022-2023 | 1150/AE-III | 24/11/2022 | 45 | SUNIL RABIDAS | 3.37 | 0 | 0
1130 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and delivery of Submersible pump motor set, Slluice valve,NRV for Hatgacha Water Supply Scheme of Md. Bazar block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000424/2024-2025 | 659/BMSD/(D) | 02/09/2024 | 30 | B. P. TRADING CORPORATION | 1.52 | 0 | 100
1131 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and delivery of kit kat fuse, Main switch, change over switch, bushbar for Hatgacha Water Supply Scheme of Md. Bazar block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000425/2024-2025 | 650/BMSD(D) | 02/09/2024 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 2.51 | 0 | 100
1132 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & Delivery of power cable for Augmentation of Bishnupur (Block-Rampurhat-II) under Bolpur Mechanical Division, P.H.E Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000710/2023-2024 | 1362/AE-III | 17/10/2023 | 15 | M. S. ENTERPRISE | 4.32 | 0 | 100
1133 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of Column pipe & others at store for Augmentation of Bishnupur and other water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000801/2022-2023 | 515/AE-III | 28/03/2023 | 20 | S.K.ELECTRICALS | 2.46 | 0 | 0
1134 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of Cable at store for Augmentation of Bishnupur and other water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000802/2022-2023 | 519/AE-III | 28/03/2023 | 20 | SATYAJIT GHOSH | 3.21 | 0 | 0
1135 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of Chlorination System at store for Augmentation of Bishnupur and other water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000812/2022-2023 | 528/AE-III | 28/03/2023 | 20 | M/S S.R. ENTERPRISE | 2.7 | 0 | 0
1136 | Bolpur Mechanical | Rampurhat Sub-Division | Additional estimate for installation Augmentation Mollarpur water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/001170/2023-2024 | 299/AE-III | 22/02/2024 | 7 | SUNIL RABIDAS | 4.89 | 0 | 100
1137 | Bolpur Mechanical | Rampurhat Sub-Division | Replacement of voltage correction device at Mollarpur zone-I(Ph-III) (at Block compound) water supply scheme under under Bolpur Mechanical Division, PHE Dte.(Aug. of Mollarpur W/S Scehem) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/001179/2023-2024 | 309/AE-III | 23/02/2024 | 15 | BIRBHUM ELECTRIC WORKS | 2.97 | 0 | 100
1138 | Bolpur Mechanical | Rampurhat Sub-Division | PROVIDING ELECTRO MECHANICAL ACCESSORIES AND OTHERS FOR Augmentation of Hatgacha water supply scheme UNDER BOLPUR MECHANICAL DIVISION IN THE DISTRICT OF BIRBHUM. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/001303/2023-2024 | 667/Bol.MD | 22/03/2024 | 30 | HINDOL ROY | 22.96 | 0 | 100
1139 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at PASCHIM NAOPARA, PHULUR & PURBA SIUR its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000189/2023-2024 | 2262/BHM | 12/07/2023 | 993 | B RAI CONSTRUCTION COMPANY | 1402.44 | 0 | 45
1140 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000068/2022-2023 | 1422/BHM | 24/04/2023 | 0 | Resource Division | 40.92 | 0 | 0
1141 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Paschim Nowapara PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/02182/2023-2024 | BP-2023-24-319 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.69 | 0 | 0
1142 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR PASCHIM NOWAPARA PH NO-I | AE,Assistant Engineer | JE,Junior Engineer | BILL/02236/2023-2024 |  | 14/03/2024 | 0 | WBSEDCL | 5.62 | 0 | 0
1143 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Paschim Nowapara PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/02240/2023-2024 | BP-2023-24-320 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.62 | 0 | 0
1144 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Paschim Naopara & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000433/2023-2024 | 2095/Bol.MD | 22/08/2023 | 588 | BIRBHUM ELECTRIC WORKS | 27.94 | 0 | 50
1145 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
1146 | Birbhum Division | Nalhati Sub-Division | Restoration charges for laying of PHE pipeline from Chainage 5.80 KM (Hiytnagar) to 9.5 KM of Murarai Mitrapur Road under Rampurhat Highway Sub Division of Birbhum Highway Division-_ in the Dist of Birbhum during the year 2023-24 | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00736/2024-2025 | BP-2024-25-223 | 12/09/2024 | 0 | EXECUTIVE ENGINEER BIRBHUM HIGHWAY DIVISION-I P.W (ROADS) DIRECTORATE | 17.21 | 0 | 0
1147 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at KASHIMNAGAR, KAMARKHUL & GAGANPUR and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000288/2023-2024 | 3647/BHM | 25/08/2023 | 274 | BENGAL ENGINEERING | 1204.06 | 0 | 30
1148 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000059/2023-2024 | 1516/BHM | 26/04/2023 | 0 | Resource Division | 13.93 | 0 | 0
1149 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR KASHIMNAGAR P H NI.I WS SCHEME | AE,Assistant Engineer | JE1,Junior Engineer | BILL/01828/2023-2024 | BP-23-24-251 | 06/02/2024 | 0 | WBSEDCL | 3.1 | 0 | 0
1150 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR KASHIMNAGAR P H NO.Ii WS SCHEME | AE,Assistant Engineer | JE1,Junior Engineer | BILL/01829/2023-2024 | BP-23-24-252 | 06/02/2024 | 0 | WBSEDCL | 3.21 | 0 | 0
1151 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Kashimnagar PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000943/2023-2024 | 3304/BOL.MD | 29/09/2023 | 540 | CHAKRABORTY MINING & ENGINERING | 30.42 | 0 | 80
1152 | Birbhum Division | RWS Birbhum Sub-Division | Providing FHTC including laying of distribution system within the command area of villages Rajganja, Hajrapur, Chinpai & Balijuri , G.P - Parulia, Chinpai & Balijuri, Block - Dubrajpur for ensuing draught like situation within Birbhum Division, PHE Dte. (Phase-II) | AE | JE | ORD/000095/2023-2024 | 1647/BHM | 02/05/2023 | 45 | RICK CONSTRUCTION | 28.38 | 0 | 43
1153 | Birbhum Division | RWS Birbhum Sub-Division | Providing FHTC including laying of distribution system within the command area of villages Jethia, Haridaspur, Jinderpur, Kapista. Gagha & Debogram,G.P - Bharkata, Kapista, Ganpur & Rampur, Block - Md.Bazar for ensuing draught like situation within Birbhum Division, PHE Dte. (Phase-II) | AE | JE | ORD/000107/2023-2024 | 1732/BHM | 12/05/2023 | 60 | HIMANGSU SEKHAR SARKAR | 78.36 | 0 | 0
1154 | Birbhum Division | RWS Birbhum Sub-Division | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of village Muktipur & Kuralmetia under Rajnagar Block for ensuing draught like situation within Birbhum Division, PHE Dte. | AE | JE | ORD/000108/2023-2024 | 1725/BHM | 12/05/2023 | 45 | BHABANI ENTERPRISE | 16.76 | 0 | 100
1155 | Birbhum Division | RWS Birbhum Sub-Division | Extension work of HDPE pipeline for providing FHTC of Kanakpur Mini W/S Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000131/2024-2025 | 2160/BHM | 05/08/2024 | 45 | BROTHERS ENTERPIRSE | 5.74 | 0 | 100
1156 | Birbhum Division | RWS Birbhum Sub-Division | Restoration of distribution pipe line (HDPE), Construction of Sluice Valve Chamber & concreting including FHTC for augmentation of Khayrasole (Zone-II) Piped Water Supply Scheme, Khayrasole Block, under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000135/2024-2025 | 2154/BHM | 01/08/2024 | 45 | RANJIT GHOSH | 4.57 | 0 | 100
1157 | Birbhum Division | RWS Birbhum Sub-Division | Allied work of Laying Rising main including extension of pipeline with restoration of road for Paikar Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000139/2024-2025 | 2353/BHM | 22/08/2024 | 45 | SK ALIM | 94.64 | 0 | 100
1158 | Birbhum Division | RWS Birbhum Sub-Division | Allied work of Installation of Sluice Valve along with restoration of road and Land development at new OHR site under Augmentation of Murarai w/s Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000140/2024-2025 | 2354/BHM | 22/08/2024 | 163 | SK ALIM | 44.38 | 0 | 90
1159 | Birbhum Division | RWS Birbhum Sub-Division | Balance work of distribution pipeline including extension of pipeline for left out habitation (Purbo gopalpur)along with FHTC and restoration of roads for Bhadrapur Z-II w/s Scheme under Nalhati Sub-Division within Birbhum Division,P.H.E. Dte. | AE | JE | ORD/000141/2024-2025 | 2415/BHM | 28/08/2024 | 60 | SHIB GANGA CONSTRUCTION | 42.63 | 0 | 45
1160 | Birbhum Division | RWS Birbhum Sub-Division | Construction of 20 Nos Water Supply Overhead Structure at Different places under Draught Prone area at Dubrajpur Block (14 Nos.)and MD. Bazar (6 Nos) under RWS Birbhum Sub Division within Birbhum Division PHE Dte.. | AE | JE | ORD/000203/2023-2024 | 3163/BHM | 24/07/2023 | 585 | PREMANANDA ROY BISWAS | 93.11 | 0 | 95
1161 | Birbhum Division | RWS Birbhum Sub-Division | Allied work of Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of village Raotara J.L No 76 , G.P Parulia , Block Dubrajpur for ensuing draught like situation within Birbhum Division, PHE Dte. | AE | JE | ORD/000211/2023-2024 | 3260/BHM | 26/07/2023 | 45 | GOUTAM MONDAL | 3.02 | 0 | 100
1162 | Birbhum Division | RWS Birbhum Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of village Asanjola, Bamnigao under Block Rampurhat- I for ensuing draught like situation within Birbhum Division, PHE Dte. (Sl. No.3) | AE | JE | ORD/000244/2022-2023 | 2585/BHM | 22/11/2022 | 30 | INDRAJIT DUTTA. | 21.46 | 0 | 100
1163 | Birbhum Division | RWS Birbhum Sub-Division | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of village Rajganja, Hazrapur, Chinpai and Balijuri under Block Dubrajpur for ensuing draught like situation within Birbhum Division, PHE Dte. (Sl. No.2) | AE | JE | ORD/000334/2022-2023 | 2605/BHM | 24/11/2022 | 60 | RICK CONSTRUCTION | 78.18 | 0 | 100
1164 | Birbhum Division | RWS Birbhum Sub-Division | Allied Works related to FHTC for village Putka JL No 04 G.P Lokepur Block Khoirasole for ensuing draught line situation within Birbhum Division PHE Dte.( Sl. No.-05) | AE | JE | ORD/000377/2024-2025 | 188/RWS | 21/11/2024 | 30 | BHABANI ENTERPRISE | 0.95 | 0 | 90
1165 | Birbhum Division | RWS Birbhum Sub-Division | Allied work of Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of village Sagarbhanga, J.L No 63, G.P Nakraconda, Block -Khoyrasole for ensuing draught like situation within Birbhum Division, PHE Dte. | AE | JE | ORD/000412/2023-2024 | 4287/BHM | 10/11/2023 | 45 | DATA CONSTRUCTION | 7.41 | 0 | 100
1166 | Birbhum Division | RWS Birbhum Sub-Division | Additional work for providing Balance FHTC including laying of distribution system for village Geruapahari JL NO 74,G.P Babuijore, Block- Khoirasole for ensuing draught line situation within Birbhum Division PHE Dte. (Sl. No.8) | AE | JE | ORD/000472/2022-2023 | 222/BHM | 20/01/2023 | 45 | MA KANKALI ENTERPRISE | 7.51 | 0 | 84
1167 | Birbhum Division | RWS Birbhum Sub-Division | Allied Work of Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of village Gaisara, J.L No 46, G.P Tantipara, Block Rajnagar for ensuing draught like situation within Birbhum Division, PHE Dte. | AE | JE | ORD/000588/2023-2024 | 752/BHM | 29/02/2024 | 45 | AVIJIT CHANDA | 4.89 | 0 | 100
1168 | Birbhum Division | Birbhum Sadar Sub-Division | Sinking of 250 X 200 mm Dia, 125 m deep tubewell, 5.90 m X 4.10 m Pump room / Chlorine room with sanitary arrangements, 8.00 m X 8.00 m Pump room / Chlorine room with sanitary arrangements, 150 CuM capacity O.H.R., 100 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at DAKSHIN MADANPUR & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000317/2024-2025 | 3130/BHM | 18/11/2024 | 365 | MALLICK CONSTRUCTION | 288.15 | 0 | 20
1169 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000051/2024-2025 | 3260/BHM | 02/12/2024 | 0 | Resource Division | 6.91 | 0 | 0
1170 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000074/2022-2023 | 1391/BHM | 24/04/2023 | 0 | Resource Division | 32.83 | 0 | 0
1171 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply delivery of voltage correction device at head work site of Augmentation of Ahmadpur (At Dakshin Madanpur) PWSS of Sainthia Block in the district of Birbhum, under P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000530/2024-2025 | 3795/BOL.MD | 12/09/2024 | 247 | M/S SWAPAN BANERJEE | 15.07 | 0 | 80
1172 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply delivery of voltage correction device at head work site of Dakshin Madanpur PWSS in the district of Birbhum, under P.H.E. Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000532/2024-2025 | 3796/BOL.MD | 12/09/2024 | 30 | M/S A.D.ENTERPRISE | 5.88 | 0 | 0
1173 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Dakshin Madanpur & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000582/2023-2024 | 3385/Bol.MD | 16/10/2023 | 90 | R. N. S. TRADING | 54.02 | 0 | 0
1174 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at DEOASH, JASODA & JIUI and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000013/2023-2024 | 1194/BHM | 12/04/2023 | 792 | M/S. JAN MAHAMMAD | 1367.24 | 0 | 75
1175 | Birbhum Division | Birbhum Sadar Sub-Division | Repairing and renovation of existing Pump House, Chlorine room, Security guard room and Boundary wall for Deoash and Adjoining Mouzas PWSS Under Birbhum Division, P.H.E Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000064/2025-2026 | 1583/BHM | 02/06/2025 | 90 | SUBHRADIP SARKAR | 18.7 | 0 | 0
1176 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000048/2022-2023 | 1375/BHM | 24/04/2023 | 0 | Resource Division | 34.3 | 0 | 0
1177 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Dewas PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/01027/2024-2025 | BP-24-25-278 | 06/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.73 | 0 | 0
1178 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Dewas PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/02252/2023-2024 | BP-2023-24-316 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.41 | 0 | 0
1179 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Deoash & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000414/2023-2024 | 2086/Bol.MD | 22/08/2023 | 589 | SUNIL RABIDAS | 28.9 | 0 | 40
1180 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Name of Work: Supply delivery of voltage correction device & laying of cable through underground trench at head work site of Deoash PWSS in the district of Birbhum, under P.H.E. Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000542/2024-2025 | 3801/BOL.MD | 12/09/2024 | 30 | SATYAJIT GHOSH | 4.41 | 0 | 100
1181 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Dalima, Kahinagar & Dumurgram and its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000080/2023-2024 | 1423/BHM | 25/04/2023 | 1090 | AKASH CONSTRUCTION | 1377.29 | 0 | 16
1182 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000169/2023-2024 | 2176/BHM | 23/06/2023 | 0 | Resource Division | 13.65 | 0 | 0
1183 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Dumurgram P/H-I Scheme in Murarai CCC under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | BILL/00085/2024-2025 | BP-2024-25-20 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.55 | 0 | 0
1184 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for DURUMGRAM piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000898/2023-2024 | 3293/Bol.MD | 29/09/2023 | 580 | QUAZI NOZRUL ISLAM | 31.48 | 0 | 60
1185 | Birbhum Division | RWS Birbhum Sub-Division | Road restoration work at different villages under implementation of Mini Piped Water Supply Scheme within Labpur Block having less than 100 Households under Birbhum Division PHE Dte. | AE,Assistant Engineer (HQ) | JE,Junior Engineer | ORD/000177/2025-2026 | 2095/BHM | 14/08/2025 | 90 | ARABINDA GHOSH | 27.75 | 0 | 60
1186 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer (HQ) | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
1187 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
1188 | Birbhum Division | Rampurhat Sub-Division | Providing FHTC from existing distribution system at Beja,Taratari,Chuatari & Selahat mouzas within Beja w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-03) | AE | JE3 | ORD/000168/2022-2023 | 306/RSD | 08/09/2022 | 30 | GOURANGA MONDAL | 4.55 | 0 | 50
1189 | Birbhum Division | Rampurhat Sub-Division | Additional laying of distribution system at Beja and Chuatari Mouzas for providing FHTC for Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. (Sl.No.04) | AE | JE3 | ORD/000169/2022-2023 | 307/RSD | 08/09/2022 | 30 | GOURANGA MONDAL | 4.77 | 0 | 100
1190 | Birbhum Division | Rampurhat Sub-Division | Additional laying of distribution system At Beja Village for providing FHTC for Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. (Sl. No-05) | AE | JE3 | ORD/000170/2022-2023 | 308/RSD | 08/09/2022 | 30 | GOURANGA MONDAL | 4.95 | 0 | 50
1191 | Birbhum Division | Rampurhat Sub-Division | Additional Laying of distribution system at Terateri Mouza for providing FHTC for Beja Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. (Sl.No-06) | AE | JE3 | ORD/000172/2022-2023 | 309/RSD | 08/09/2022 | 30 | GOURANGA MONDAL | 4.98 | 0 | 50
1192 | Birbhum Division | Rampurhat Sub-Division | Certified that the total quantity of fuel supplied for the vehicle No. WB53B-8630 of Consumer for official purpose under Assistant Engineer (HQ) Birbhum Division for the month of Nov'23 and Dec'23 | AE | JE3 | BILL/00882/2023-2024 | BP-2023-24-422 | 07/03/2024 | 0 | JAYRAM FILLING STATION | 0.48 | 0 | 0
1193 | Birbhum Division | Rampurhat Sub-Division | Certified that entire quantity of HSD actually purchased and consumer for the purpose of office works as per context Log Book | AE | JE3 | BILL/01015/2023-2024 | BP-2023-24-483 | 27/03/2024 | 0 | JAYRAM FILLING STATION | 0.48 | 0 | 0
1194 | Birbhum Division | Rampurhat Sub-Division | Continution work for Supply of one no. Diesel driven Motor Cab / Maxi Cab (Air Condition) on hire Basis under the Assitant Engineer (H.Q) Birbhum Division P.H.E Dte. (Period from 01.05.2024 to 31.10.2024) | AE | JE3 | ORD/000090/2024-2025 | 1373/BHM | 26/04/2024 | 183 | JAMSED ALI KHAN | 0.96 | 0 | 0
1195 | Birbhum Division | Rampurhat Sub-Division | Allied Functional Household Tap Connection from existing distribution system at different mouzas under Puranagram Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000262/2023-2024 | 3453/BHM | 03/08/2023 | 466 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 80.63 | 0 | 65
1196 | Birbhum Division | Rampurhat Sub-Division | Continution work for Supply of one no. Diesel driven Motor Cab / Maxi Cab (Air Condition) on hire Basis under the Assitant Engineer (H.Q) Birbhum Division P.H.E Dte. (Period from 01.11.2023 to 30.04.2024) | AE | JE3 | ORD/000431/2023-2024 | 4180/BHM | 31/10/2023 | 182 | JAMSED ALI KHAN | 0.95 | 0 | 100
1197 | Birbhum Division | Rampurhat Sub-Division | Continuation work for Supply of one no. Diesel-driven Motor Cab / Maxi Cab (Air Condition) on hire Basis under the Assitant Engineer (H.Q) Birbhum Division P.H.E Dte. (Period from 01.11.2024 to 30.04.2025) | AE | JE3 | ORD/000436/2024-2025 | 2969/BHM | 30/10/2024 | 182 | JAMSED ALI KHAN | 0.96 | 0 | 100
1198 | Birbhum Division | Nalhati Sub-Division | Restoration of Roads, pucca drain including Jack pushing & Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Kanaipur piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000045/2025-2026 | 1507/BHM | 23/05/2025 | 90 | M/S GOUTAM DAS | 41.79 | 0 | 10
1199 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Majhkaltia, Sahira & KANAPIUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000075/2023-2024 | 1348/BHM | 20/04/2023 | 835 | M/S GOUTAM DAS | 1594.34 | 0 | 28
1200 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000013/2023-2024 | 1429/BHM | 25/04/2023 | 0 | Resource Division | 15.61 | 0 | 0
1201 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR KANAIPUR W S P H NO I WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01783/2023-2024 | BP-23-24-240 | 29/01/2024 | 0 | WBSEDCL | 5.09 | 0 | 0
1202 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR KANAIPUR P H NO.II WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01785/2023-2024 | BP-23-24-241 | 29/01/2024 | 0 | WBSEDCL | 0.23 | 0 | 0
1203 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for KANAIPUR piped water supply scheme, Nalhati - I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000931/2023-2024 | 3561/BOL.MD | 04/12/2023 | 60 | PRADIP KUMAR DHABAL | 27.77 | 0 | 90
1204 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Jijigram, Math Basori & Bilaspur and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000191/2023-2024 | 3019/BHM | 14/07/2023 | 961 | SUNIL RABI DAS | 1250.5 | 0 | 60
1205 | Birbhum Division | Nalhati Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
1206 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000088/2023-2024 | 1549/BHM | 26/04/2023 | 0 | Resource Division | 18.63 | 0 | 0
1207 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Math Basuri Water Supply Scheme P/H -I in Paikar CCC under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer | JE3,Junior Engineer | BILL/00115/2024-2025 | BP-2024-2025-46 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.03 | 0 | 0
1208 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Math Basuri Water Supply Scheme P/H -II in Paikar CCC under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer | JE3,Junior Engineer | BILL/00116/2024-2025 | BP-2024-2025-47 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.21 | 0 | 0
1209 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at DERPUR, KURUMSAHA & MATIARA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000056/2023-2024 | 1245/BHM | 17/04/2023 | 1074 | BRAHMA CONSTRUCTION COMPANY | 978.83 | 0 | 65
1210 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000051/2022-2023 | 1366/BHM | 24/04/2023 | 0 | Resource Division | 19.69 | 0 | 0
1211 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR KURUMSAHA P.H.NO.I | AE,Assistant Engineer | JE,Junior Engineer | BILL/00707/2023-2024 | BP-2023-2024-63 | 02/08/2023 | 0 | WBSEDCL | 3.85 | 0 | 0
1212 | Bolpur Mechanical | Birbhum Sadar Sub-Division | wbsedcl quotation for kurumsaha p.h.no.ii ws scheme | AE,Assistant Engineer | JE,Junior Engineer | BILL/00716/2023-2024 | BP-23-24-70 | 09/08/2023 | 0 | WBSEDCL | 3.91 | 0 | 0
1213 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Kurumsaha & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000418/2023-2024 | 2090/Bol.MD | 22/08/2023 | 679 | MITRA ENTERPRISE | 28.04 | 0 | 80
1214 | Central Drilling | Birbhum Sadar Sub-Division | PROVIDING DRLLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR Kurumsaha W/S SCHEME (TW-II), SAINTHIA BLOCK, UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000405/2022-2023 | 1428/CDD | 29/11/2022 | 30 | C.M. ENTERPRISE | 10.49 | 0 | 0
1215 | Central Drilling | Birbhum Sadar Sub-Division | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN KURUMSAHA PWSS (TW-I), SAINTHIA BLOCK, BIRBHUM DISTRICT UNDER CDD, PHE DTE. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000415/2022-2023 | 382/CMSD-I | 05/08/2022 | 15 | C.M. ENTERPRISE | 4.18 | 0 | 0
1216 | Central Drilling | Birbhum Sadar Sub-Division | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTTRUCTION OF TUBE WELL IN KURUMSAHA PWSS (TW-I), BLOCK-SAINTHIA, BIRBHUM DISTRICT UNDER CDD, PHE DTE. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000416/2022-2023 | 390/CMSD-I | 05/08/2022 | 15 | C.M. ENTERPRISE | 2.66 | 0 | 0
1217 | Central Drilling | Birbhum Sadar Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN KURUMSAHA PWSS (TW-I), BLOCK-SAINTHIA, BIRBHUM DISTRICT UNDER CDD, PHE DTE. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000417/2022-2023 | 398/CMSD-I | 05/08/2022 | 15 | C.M. ENTERPRISE | 3.77 | 0 | 0
1218 | Birbhum Division | Birbhum Division | Different works related to water supply scheme at RAUTARA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000567/2022-2023 | 900/BHM | 22/03/2023 | 710 | M/S.KHAN CHOWDHURY BROTHERS AND CO. | 216.16 | 0 | 80
1219 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | RTOR000029/2023-2024 | 1565/BHM | 26/04/2023 | 0 | Resource Division | 5.78 | 0 | 0
1220 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION BILL FOR RAUTARA WS SCHEME P.H.NO.I | AE(HQ),Assistant Engineer | JE,Junior Engineer | BILL/01151/2023-2024 | BP-23-24-95 | 26/09/2023 | 0 | WBSEDCL | 4.22 | 0 | 0
1221 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR RAUTARA WS SCHEME P H .NO.2 | AE(HQ),Assistant Engineer | JE,Junior Engineer | BILL/01486/2023-2024 | BP-23-24-197 | 19/12/2023 | 0 | WBSEDCL | 4.53 | 0 | 0
1222 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Rautara PWSS at Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000290/2023-2024 | 1496/Bol.MD | 17/07/2023 | 870 | M/S SWAPAN BANERJEE | 27.11 | 0 | 80
1223 | Birbhum Division | Rampurhat Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, Boundary wall related to water supply scheme at Chakpara Piped Water Supply Scheme within Rampurhat-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000063/2025-2026 | 1584/BHM | 02/06/2025 | 90 | ABUL HASNATH | 26.1 | 0 | 0
1224 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000138/2023-2024 | 1558/BHM | 26/04/2023 | 0 | Resource Division | 32.34 | 0 | 0
1225 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000220/2023-2024 | 228/BHM | 24/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
1226 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for Chakpara PWSS P/H no-2 ( block: Rampurhat I) | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/00076/2024-2025 | BP-2024-2025-22 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.83 | 0 | 0
1227 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Chakpara PWSS P/H -1 ( Block : Rampurhat -1) | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/00077/2024-2025 | BP-2024-2025-24 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.09 | 0 | 0
1228 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Chakpara & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000917/2023-2024 | 3525/Bol.MD | 29/11/2023 | 759 | M. S. ENTERPRISE | 39.06 | 0 | 60
1229 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at NABAGRAM, SAHAPUR & SHASPUR and its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000268/2023-2024 | 3522/BHM | 11/08/2023 | 821 | SUNIL RABI DAS | 1157.77 | 0 | 40
1230 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Nabagram) Water Supply Scheme under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000626/2022-2023 | 217/RSD | 21/06/2022 | 45 | ECO CARE | 4 | 0 | 100
1231 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000131/2023-2024 | 1554/BHM | 26/04/2023 | 0 | Resource Division | 26.05 | 0 | 0
1232 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000225/2023-2024 | 227/BHM | 24/01/2024 | 0 | Resource Division | 0.92 | 0 | 0
1233 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Nabagram TW No-II (Block-Rampurhat-II) | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02223/2023-2024 |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.49 | 0 | 0
1234 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Nabagram TW No-I (Block-Rampurhat-II) | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02224/2023-2024 |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.85 | 0 | 0
1235 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR NABAGRAM TW-II | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02246/2023-2024 | BP-2023-24-311 | 18/03/2024 | 0 | WBSEDCL | 3.49 | 0 | 0
1236 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR NABAGRAM TW-1 | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02249/2023-2024 | BP-2023-24-312 | 18/03/2024 | 0 | WBSEDCL | 2.85 | 0 | 0
1237 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Nabagram PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000481/2023-2024 | 2233/Bol.MD | 12/09/2023 | 658 | M. S. ENTERPRISE | 45.35 | 0 | 80
1238 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Nabagram PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/001250/2023-2024 | 526/BOL.MD | 14/03/2024 | 383 | MENAKA ENTERPRISE | 7.62 | 0 | 40
1239 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at MATIKONA, NOHONA, SHIRSHA & CHUNPALASHI Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 | ORD/000278/2023-2024 | 3598/BHM | 21/08/2023 | 949 | BIPIN KUMAR SINGH | 2395.67 | 0 | 4
1240 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for SHIRSHA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - A) | Assistant Engineer | JE1 | ORD/000776/2022-2023 | 284/BSD | 25/07/2022 | 90 | M/S R DUTTA & CO. | 4.93 | 0 | 100
1241 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for SHIRSHA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - B) | Assistant Engineer | JE1 | ORD/000777/2022-2023 | 311/BSD | 17/08/2022 | 90 | M/S R DUTTA & CO. | 1.43 | 0 | 100
1242 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE1 | RTOR000120/2023-2024 | 1527/BHM | 26/04/2023 | 0 | Resource Division | 19.61 | 0 | 0
1243 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer | JE1 | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1244 | Birbhum Division | Bolpur Sub-Division | Construction of 150 CUM capacity OHR including Soil Investigation, 5.09 m X 4.1 m Pump House/Chlorine Room with Sanitary, Laying of Rising Main and Distribution System and FHTC and Construction of Boundary Wall Approach Road and Land Development works at H/W site and 2 nd T/W site under Ulandi PIPED WATER SUPPLY SCHEME within Illambazar Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000092/2024-2025 | 2037/BHM | 19/07/2024 | 365 | SHIBU BISWAS, BADARTALA , BASIRHAT, PIN - 743292 | 413.14 | 0 | 5
1245 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for ULANDI Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte" | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000643/2022-2023 | 154/BSD | 18/04/2022 | 90 | M/S R DUTTA & CO. | 3.93 | 0 | 100
1246 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | RTOR000016/2024-2025 | 2381/BHM | 27/08/2024 | 0 | Resource Division | 9.66 | 0 | 0
1247 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | RTOR000143/2023-2024 | 1575/BHM | 26/04/2023 | 0 | Resource Division | 15.86 | 0 | 0
1248 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1249 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at PODDA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under Birbhum Division, PHE Dte | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000065/2023-2024 | 1310/BHM | 19/04/2023 | 973 | P. C. CONSTRUCTION | 210.99 | 0 | 80
1250 | Birbhum Division | Rampurhat Sub-Division | Preparation & Submission of DPR for (Podda) Water Supply Scheme under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000557/2022-2023 | 171/RSD | 29/04/2022 | 45 | ECO CARE | 2.91 | 0 | 100
1251 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000128/2023-2024 | 1542/BHM | 26/04/2023 | 0 | Resource Division | 12.98 | 0 | 0
1252 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000223/2023-2024 | 222/BHM | 24/01/2024 | 0 | Resource Division | 3.26 | 0 | 0
1253 | Bolpur Mechanical | Rampurhat Sub-Division | wbsedcl quotation money for podda pwss | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/01433/2023-2024 | BP-23-24-153 | 04/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0
1254 | Bolpur Mechanical | Rampurhat Sub-Division | wbsedcl quotation money for poddsa p.h.no.1 pwss | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/01434/2023-2024 | BP-23-24-154 | 04/12/2023 | 0 | WBSEDCL | 4.8 | 0 | 0
1255 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Podda PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000007/2024-2025 | 687/AE-III | 08/04/2024 | 14 | S.K.ELECTRICALS | 1.58 | 0 | 0
1256 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Podda PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000354/2023-2024 | 1749/Bol.MD | 27/07/2023 | 60 | S.K.ELECTRICALS | 44.24 | 0 | 90
1257 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Podda PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/001256/2023-2024 | 528/BOL.MD | 14/03/2024 | 60 | M/S. S.G ENTERPRISE | 7.62 | 0 | 0
1258 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at PURBA ANANTAPUR & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000030/2023-2024 | 1193/BHM | 12/04/2023 | 450 | MEHEBUB RAHAMAN | 257.78 | 0 | 80
1259 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Purba Anantapur) Water Supply Scheme under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000632/2022-2023 | 235/RSD | 04/07/2022 | 45 | ECO CARE | 3.63 | 0 | 100
1260 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000129/2023-2024 | 1539/BHM | 26/04/2023 | 0 | Resource Division | 56.84 | 0 | 0
1261 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000221/2023-2024 | 223/BHM | 24/01/2024 | 0 | Resource Division | 4.31 | 0 | 0
1262 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR PURBA ANANTAPUR WS SCHEME UNDER BOL MD | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/01554/2023-2024 | BP-23-24-200 | 28/12/2023 | 0 | WBSEDCL | 3.81 | 0 | 0
1263 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR PURBA ANANTAPUR W S P H NO I WS SCHEME | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/01779/2023-2024 | BP-23-24-255 | 06/02/2024 | 0 | WBSEDCL | 5.65 | 0 | 0
1264 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Purba Anantapur PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000479/2023-2024 | 2231/Bol.MD | 12/09/2023 | 293 | ORIENTAL ENGINEERING CO. | 44.37 | 0 | 40
1265 | Birbhum Division | Birbhum Division | Different works for KASHERHAT & Sehana and its adjoining mouzas water supply scheme within SURI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000383/2023-2024 | 4138/BHM | 18/10/2023 | 1079 | PASCON | 975.41 | 0 | 60
1266 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | RTOR000040/2022-2023 | 1387/BHM | 24/04/2023 | 0 | Resource Division | 20.85 | 0 | 0
1267 | Bolpur Mechanical | Birbhum Division | New service connection at Kasherhat PH-I W/S scheme Block-Suri II under Bolpur Mechanical Division,PHE Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | BILL/00130/2024-2025 | BP-2024-2025-63 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.72 | 0 | 0
1268 | Bolpur Mechanical | Birbhum Division | New service connection at Kasherhat PH-II W/S scheme Block-Suri II under Bolpur Mechanical Division,PHE Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | BILL/00132/2024-2025 | BP-2024-2025-64 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.21 | 0 | 0
1269 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Kasherhat PWSS at Suri - II Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000398/2023-2024 | 2076/BOL.MD. | 21/08/2023 | 667 | MITRA ENTERPRISE | 28.66 | 0 | 90
1270 | Birbhum Division | Bolpur Sub-Division | "Construction of 200CuM. capacity O.H.R. with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements.laying of Rising Main,Distribution System with FHTC and different works related to FEUGRAM PIPED WATER SUPPLY SCHEME (TSM/015471) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000099/2024-2025 | 2115/BHM | 29/07/2024 | 365 | BANI ENGINEERING CO. | 483.16 | 0 | 0
1271 | Birbhum Division | Bolpur Sub-Division | Preparation & Submission of Detail Project Report (DPR) for FEUGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/001139/2021-2022 | 89/BSD | 10/03/2022 | 90 | RADIANT | 4.87 | 0 | 100
1272 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | RTOR000018/2024-2025 | 2441/BHM | 30/08/2024 | 0 | Resource Division | 10.68 | 0 | 0
1273 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | RTOR000061/2023-2024 | 1449/BHM | 25/04/2023 | 0 | Resource Division | 24.16 | 0 | 0
1274 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Feugram Water supply Scheme (T/W-I & II), Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000956/2024-2025 | 4532/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.35 | 0 | 40
1275 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1276 | Birbhum Division | Bolpur Sub-Division | Construction of 250 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, laying of Rising Main, Distribution System with FHTC and different works related to RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME (TSM/016099) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000127/2024-2025 | 2239/BHM | 13/08/2024 | 594 | DILIP KUMAR MONDAL | 480.2 | 0 | 15
1277 | Birbhum Division | Bolpur Sub-Division | Restoration of Road, damaged during laying of pipe line under Ramkrishnapur PWSS of Bolpur Sub-Division within Birbhum Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000318/2025-2026 | 2763/BHM | 29/10/2025 | 90 | DILIP KUMAR MONDAL | 19.25 | 0 | 0
1278 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for RAMKRISHNAPUR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. ". | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000646/2022-2023 | 180/BSD | 05/05/2022 | 90 | RADIANT | 4.8 | 0 | 100
1279 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000032/2024-2025 | 2480/BHM | 03/09/2024 | 0 | Resource Division | 11.16 | 0 | 0
1280 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Benga Chatra & Ramkrishnapur Water supply Scheme, Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000969/2024-2025 | 4538/BOL.MD | 20/12/2024 | 120 | MENAKA ENTERPRISE | 73.34 | 0 | 50
1281 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1282 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at PANIARA & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000694/2023-2024 | 1040/BHM | 15/03/2024 | 60 | ANIRUDDHA FARUQUE | 65.65 | 0 | 0
1283 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000034/2023-2024 | 1585/BHM | 26/04/2023 | 0 | Resource Division | 8.69 | 0 | 0
1284 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for PANIARA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000904/2023-2024 | 3299/Bol.MD | 29/09/2023 | 550 | M/S. UTTAM KUMAR CHATTERJEE | 26 | 0 | 70
1285 | Birbhum Division | Bolpur Sub-Division | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000084/2024-2025 | 1948/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0
1286 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for KHAYERBANI Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000656/2022-2023 | 163/BSD | 25/04/2022 | 180 | APEX ENGINEERING | 3.16 | 0 | 100
1287 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000011/2024-2025 | 2387/BHM | 27/08/2024 | 0 | Resource Division | 7.2 | 0 | 0
1288 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000159/2023-2024 | 1599/BHM | 27/04/2023 | 0 | Resource Division | 19.67 | 0 | 0
1289 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Khayerbani PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001127/2024-2025 | 330/BOL.MD | 19/02/2025 | 120 | SARVATAH PROJECTS PRIVATE LIMITED | 74.48 | 0 | 0
1290 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1291 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000168/2023-2024 | 1624/BHM | 28/04/2023 | 0 | Resource Division | 18.95 | 0 | 0
1292 | Bolpur Mechanical | Nalhati Sub-Division | wbsedcl quotation for khanpur pump house no-i | AE,Assistant Engineer | JE3,Junior Engineer | BILL/02080/2023-2024 | BP-2023-24-288 | 04/03/2024 | 0 | WBSEDCL | 3.35 | 0 | 0
1293 | Bolpur Mechanical | Nalhati Sub-Division | New service connection at Khanpur PWSS under Dubrajpur Block, under Bolpur Mech. Division,PHE. Dte. | AE,Assistant Engineer | JE3,Junior Engineer | BILL/02190/2023-2024 |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.35 | 0 | 0
1294 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for KHANPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000981/2023-2024 | 3296/Bol.MD | 29/09/2023 | 60 | DEY ENTERPRISE | 27.42 | 0 | 0
1295 | Birbhum Division | Birbhum Division | Different works related to water supply scheme at LACHHIATOR, DAKSHINGRAM, SONJ & SHIBGRAM and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000385/2023-2024 | 4142/BHM | 19/10/2023 | 805 | B RAI CONSTRUCTION COMPANY | 2003.84 | 0 | 60
1296 | Birbhum Division | Birbhum Division | Continuation Work Order for Preparation & Submission of DPR for (Lachhiator) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000806/2022-2023 | 295/RSD | 07/09/2022 | 90 | ENVIROTECH SOLUTIONS | 3.22 | 0 | 100
1297 | Birbhum Division | Birbhum Division | Continuation Work Order for Preparation & Submission of DPR for (Lachhiator) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000807/2022-2023 | 403/RSD | 13/10/2022 | 90 | ENVIROTECH SOLUTIONS | 3.5 | 0 | 100
1298 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | RTOR000076/2023-2024 | 1460/BHM | 25/04/2023 | 0 | Resource Division | 103.64 | 0 | 0
1299 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | RTOR000206/2023-2024 | 204/BHM | 22/01/2024 | 0 | Resource Division | 8.19 | 0 | 0
1300 | Bolpur Mechanical | Birbhum Division | New service connection at Lachiatore PH-IV PWSS under Bol.MD, P.H.E Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | BILL/00824/2024-2025 | BP-24-25-185 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.14 | 0 | 0
1301 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR LOCHIATORE PIPED WS SCHEME PH NO.I | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | BILL/01880/2023-2024 | BP-23-24-284 | 22/02/2024 | 0 | WBSEDCL | 4.19 | 0 | 0
1302 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR LACHIATORE PIPED WS SCHEME PH NO.II | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | BILL/01881/2023-2024 | BP-23-24-282 | 22/02/2024 | 0 | WBSEDCL | 2.54 | 0 | 0
1303 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR LACHIATOR W/S SCHEME PH-3 | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | BILL/02464/2023-2024 | BP-24-25-03 | 09/04/2024 | 0 | WBSEDCL | 3.39 | 0 | 0
1304 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Lachhiator PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000738/2023-2024 | 3479/Bol.MD | 07/11/2023 | 60 | DEY ENTERPRISE | 65.96 | 0 | 80
1305 | Bolpur Mechanical | Birbhum Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Lachhiator PWSS under Rampurhat - I Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/001248/2023-2024 | 525/BOL.MD | 14/03/2024 | 60 | ABHISEK ENGTNEERING CONCERN | 7.61 | 0 | 0
1306 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
1307 | Birbhum Division | Rampurhat Sub-Division | Sinking of Tubewell, Construction of OHR, Construction of Boundary wall, pump house and laying distribution system along with FHTC works at Augmentation of Ground Water Based Dunigram Zone-I & Zone-II Piped Water Supply Scheme within Rampurhat-II Block under Birbhum Division, PHE Dte. (2nd Call) | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000393/2023-2024 | 4161/BHM | 30/10/2023 | 790 | M/S GOUTAM DAS | 509.85 | 0 | 50
1308 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000098/2022-2023 | 973/BHM | 27/03/2023 | 0 | Resource Division | 81.55 | 0 | 0
1309 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000107/2022-2023 | 1120/BHM | 10/04/2023 | 0 | Resource Division | 20.81 | 0 | 0
1310 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000231/2023-2024 | 234/BHM | 24/01/2024 | 0 | Resource Division | 1.85 | 0 | 0
1311 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Dunigram (Zone-I) TW No-III (Block-Rampurhat-II) | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/02237/2023-2024 | BP-23-24-307 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.64 | 0 | 0
1312 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Dunigram (Zone-II) TW No-I (Block-Rampurhat-II) | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/02238/2023-2024 | bp-23-24-566 | 20/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.83 | 0 | 0
1313 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping Machinaries at newly sunk Ground Water Based Tube Wells and allied works at Augmentation of Dunigram [( Zone-I, Pump House No - II ) and ( Zone-II, Pump House No - I & II )] Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division.. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000453/2023-2024 | 2130/Bol.MD | 25/08/2023 | 675 | M. S. ENTERPRISE | 76.88 | 0 | 65
1314 | Birbhum Division | Bolpur Sub-Division | Construction of 250 & 150 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main, Distribution System with FHTC including different works related to SANTOSHPUR / NAWADA PALANDI /PAPURI / SAJNOR / RAYEN PIPED WATER SUPPLY SCHEME (5 Nos Scheme) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division PHE DTE. | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000085/2024-2025 | 1951/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2322.64 | 0 | 5
1315 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for RAYEN Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000648/2022-2023 | 196/BSD | 19/05/2022 | 90 | RADIANT | 2.91 | 0 | 100
1316 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | RTOR000007/2024-2025 | 2385/BHM | 27/08/2024 | 0 | Resource Division | 4.3 | 0 | 0
1317 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | RTOR000070/2023-2024 | 1551/BHM | 26/04/2023 | 0 | Resource Division | 13.45 | 0 | 0
1318 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1319 | Birbhum Division | Birbhum Division | Different works related to water supply scheme at DHAMARA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000023/2023-2024 | 1244/BHM | 17/04/2023 | 807 | ASHIM KUMAR CHAKRABORTY | 341.34 | 0 | 65
1320 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | RTOR000167/2023-2024 | 1621/BHM | 28/04/2023 | 0 | Resource Division | 9.04 | 0 | 0
1321 | Bolpur Mechanical | Birbhum Division | Empowering for new connection at Chakraipur Pump House -II in Mollarpur CCC under Bolpur Mechanical Division, PHE,Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | BILL/00113/2024-2025 | BP-2024-2025-50 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.52 | 0 | 0
1322 | Bolpur Mechanical | Birbhum Division | WBSEDCL Quotation for Dhamara Piped Water Supply Scheme. | AE(HQ),Assistant Engineer | JE,Junior Engineer | BILL/01841/2023-2024 | BP-23-24-266 | 07/02/2024 | 0 | WBSEDCL | 3.01 | 0 | 0
1323 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for DHAMARA piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000293/2023-2024 | 1499/Bol.MD | 17/07/2023 | 624 | UTTAM KUMAR CHATTERJEE | 28.15 | 0 | 70
1324 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at BARSHAL & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000266/2023-2024 | 3506/BHM | 10/08/2023 | 767 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 1024.06 | 0 | 30
1325 | Birbhum Division | Rampurhat Sub-Division | Accetance cum Work Order For Supply and delivery of Sluice Valve for Barshal piped water supply scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000636/2023-2024 | 947/BHM | 14/03/2024 | 30 | SSPR VALVE MANUFACTURING PVT LTD | 9.32 | 0 | 100
1326 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000137/2023-2024 | 1557/BHM | 26/04/2023 | 0 | Resource Division | 407.86 | 0 | 0
1327 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000219/2023-2024 | 236/BHM | 24/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
1328 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & Installation of Low lift Pumping Mchinery and other allied work for BARSHAL & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000871/2023-2024 | 3388/BOL.MD | 16/10/2023 | 90 | UNIVERSAL ENTERPRISES | 50.94 | 0 | 30
1329 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & Installation of High lift Pumping Mchinery and other allied work for BARSHAL & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000873/2023-2024 | 3370/BOL.MD | 11/10/2023 | 659 | SUNIL RABIDAS | 87.29 | 0 | 0
1330 | Birbhum Division | Bolpur Sub-Division | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000084/2024-2025 | 1948/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0
1331 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for RANIPARA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000659/2022-2023 | 185/BSD | 11/05/2022 | 180 | APEX ENGINEERING | 3.52 | 0 | 100
1332 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000013/2024-2025 | 2396/BHM | 27/08/2024 | 0 | Resource Division | 5.4 | 0 | 0
1333 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Ranipara PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001129/2024-2025 | 335/BOL.MD | 19/02/2025 | 120 | SATYAJIT GHOSH | 76.45 | 0 | 7
1334 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1335 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at DHANASAHA, CHHATAR-BANDI, BHABANIPUR, BHUBANESWAR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000384/2023-2024 | 4141/BHM | 19/10/2023 | 709 | B RAI CONSTRUCTION COMPANY | 2996.46 | 0 | 5
1336 | Birbhum Division | Bolpur Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
1337 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for DHANASAHA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - A) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000772/2022-2023 | 216/BSD | 31/05/2022 | 90 | M/S R DUTTA & CO. | 4.93 | 0 | 100
1338 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for DHANASAHA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - B) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000773/2022-2023 | 299/BSD | 10/08/2022 | 90 | M/S R DUTTA & CO. | 2.5 | 0 | 100
1339 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | RTOR000123/2023-2024 | 1524/BHM | 26/04/2023 | 0 | Resource Division | 194.02 | 0 | 0
1340 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1341 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at DHANASAHA, CHHATAR-BANDI, BHABANIPUR, BHUBANESWAR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000384/2023-2024 | 4141/BHM | 19/10/2023 | 709 | B RAI CONSTRUCTION COMPANY | 2996.46 | 0 | 5
1342 | Birbhum Division | Bolpur Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
1343 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHHATAR BANDI Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - A) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000767/2022-2023 | 183/BSD | 05/05/2022 | 90 | M/S R DUTTA & CO. | 4.93 | 0 | 100
1344 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHHATAR BANDI Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - B) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000768/2022-2023 | 292/BSD | 29/07/2022 | 90 | M/S R DUTTA & CO. | 2.15 | 0 | 100
1345 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | RTOR000078/2023-2024 | 1545/BHM | 26/04/2023 | 0 | Resource Division | 51.45 | 0 | 0
1346 | Bolpur Mechanical | Bolpur Sub-Division | New Power Connection at Chhatarbandi PWSS under Bolpur Mechanical division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | BILL/00415/2024-2025 | BP-24-25-132 | 29/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.83 | 0 | 0
1347 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1348 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Uttarpur, Shinpur, Pariharpur, Jashahari of Hazarpur w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.8) | AE | JE1 | ORD/000049/2020-2021 | 1242 /BHM | 28/09/2020 | 60 | NANDANIK ENGINEERS C. OP. SOC. LTD. | 36.52 | 35.74 | 0
1349 | Birbhum Division | Rampurhat Sub-Division | Laying of Distribution System with UPVC Pipes and Providing Tap Connection for Existing School & AWC under Hazarpur PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000077/2021-2022 | 276/RSD | 16/07/2021 | 10 | ABUL HASNAT | 1 | 0 | 100
1350 | Birbhum Division | Rampurhat Sub-Division | Additional laying of UPVC Pipe line at Hazarpur, Kanakpur & Ekdala Mouzas along with other allied works for providing FHTC under Hazarpur Piped W/S Scheme under Rampurhat Sub- Division, P.H.E. Dte within Birbhum Division P.H.E. Dte. | AE | JE1 | ORD/000392/2021-2022 | 373/RSD | 28/09/2021 | 30 | UJJWAL DAS | 2.79 | 0 | 100
1351 | Birbhum Division | Bolpur Sub-Division | Providing functional household tap connection (FHTC) from existing distribution system in within the command area of village Nachansaha Water Supply Scheme. | Assistant Engineer | JE1 ,JE4 | ORD/000207/2020-2021 | 95/BHM | 29/01/2021 | 90 | PINTU KHAN | 4.66 | 4.66 | 0
1352 | Birbhum Division | Bolpur Sub-Division | Providing functional household tap connection (FHTC) from existing distribution system in within the command area of village Nachansaha Water Supply Scheme.(Sl No. 05) | Assistant Engineer | JE1 ,JE4 | ORD/000208/2020-2021 | 256/BHM | 26/02/2021 | 90 | SUBHRADIP SARKAR | 4.67 | 4.45 | 0
1353 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nachansa w/s Scheme (Leftout House Hold) in Bolpur Sub-Division under Birbhum Division, PHE Dte.(Sl. No.7) | Assistant Engineer | JE1 ,JE4 | ORD/000273/2021-2022 | 1526/BHM | 13/09/2021 | 60 | S R ENTERPRISE | 48.52 | 0 | 100
1354 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre and left out Household at Narayanpur and Daronda village existing distribution System within Nachansaha W/S Scheme and Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE4 | ORD/000348/2021-2022 | 402/BSD | 25/10/2021 | 10 | NAZIR HOSSAIN | 0.96 | 0 | 0
1355 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) in Purba Narayanpur Mouza from existing distribution system within the command area of Nachansaha & Adjoining Mouzas Water Supply Scheme under Bolpur Sub-Division of Birbhum Division, PHE Dte. (Sl. No.3) | Assistant Engineer | JE1 ,JE4 | ORD/000397/2020-2021 | 257/BHM | 26/02/2021 | 45 | NAZIR HOSSAIN | 4.66 | 3.02 | 100
1356 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre and left out Household at Narayanpur and Daronda village existing distribution System within Nachansaha W/S Scheme and Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE4 | ORD/000411/2021-2022 | 402/ BSD | 25/10/2021 | 10 | NAZIR HOSSAIN | 0.96 | 0 | 100
1357 | Birbhum Division | Bolpur Sub-Division | Extension of Pipeline from existing distribution System for providing FHTC at Jagdalpur village of Shibpur Mouza within the coverage area of Nachansaha & Adj. Moujas Water Supply Scheme at Bilati G.P. within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.10) | Assistant Engineer | JE1 ,JE4 | ORD/000434/2021-2022 | 2164/BHM | 24/12/2021 | 60 | M/S.CHANDRANATH MUKHERJEE | 18.6 | 0 | 100
1358 | Birbhum Division | Bolpur Sub-Division | Retrofitting of existing distribution Pipeline with Sluice Valve at different Locations of PURBA NARAYANPUR Mouza within the command area of Nachansaha and its Adjoining Mouzas W/S Scheme for providing FHTC under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No. -14) | Assistant Engineer | JE1 ,JE4 | ORD/000554/2021-2022 | 377/ BSD | 05/10/2021 | 30 | PINTU KHAN | 4.83 | 0 | 100
1359 | Birbhum Division | Bolpur Sub-Division | Retrofitting works to the existing distribution System for FHTC within the coverage area of Nachansaha & Adj. Moujas Water Supply Scheme at GOLTIKURI village (Part) and Nachansaha Mouja (Part) of Bilati G.P. within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 03) | Assistant Engineer | JE1 ,JE4 | ORD/000702/2021-2022 | 424/BSD | 18/11/2021 | 30 | S R ENTERPRISE | 4.84 | 0 | 100
1360 | Birbhum Division | Bolpur Sub-Division | Retrofitting works to the existing distribution System for providing FHTC within the coverage area of Nachansaha & its Adj. Moujas Water Supply Scheme at Shibpur Mouja and Jagdalpur village (Part) of Bilati G.P. under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 05) | Assistant Engineer | JE1 ,JE4 | ORD/000706/2021-2022 | 449/BSD | 10/12/2021 | 30 | S R ENTERPRISE | 4.81 | 0 | 100
1361 | Birbhum Division | Bolpur Sub-Division | Restoration of Cement concrete Road, damaged due to laying of Pipeline during FHTC work at NACHANSAHA and Purba-Narayanpur Moujas at Bilati G.P. within the coverage area of Nachansaha & Adj. Moujas Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 05). | Assistant Engineer | JE1 ,JE4 | ORD/000812/2021-2022 | 102/BSD | 16/03/2022 | 10 | S R ENTERPRISE | 0.93 | 0 | 100
1362 | Birbhum Division | Bolpur Sub-Division | Providing functional household tap connection (FHTC) from existing distribution system in within the command area of village Nachansaha Water Supply Scheme. | Assistant Engineer | JE1 ,JE4 | VCH/001029/2020-2021 |  | 17/03/2021 | 0 | PINTU KHAN | 4.28 | 0 | 0
1363 | Birbhum Division | Bolpur Sub-Division | Providing functional Household tap connection (FHTC) in village Nachansaha (part) from existing distribution system within the command area of Nachansaha & Adjoining mouzas water supply scheme under Bolpur Sub Division PHE (Sl.No.05) | Assistant Engineer | JE1 ,JE4 | VCH/001035/2020-2021 |  | 19/03/2021 | 0 | SUBHRADIP SARKAR | 4.45 | 0 | 0
1364 | Birbhum Division |  | Laying of HDPE Pipe line for Uska, Tentulia, Dubrajpur, Raghunathpur mouzas for providing FHTC under Raypur Zone II Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. |  |  | ORD/000029/2022-2023 | 178/RSD | 02/05/2022 | 30 | SK ABDUL HALIM | 4.99 | 0 | 100
1365 | Birbhum Division |  | Laying of HDPE Pipe line for Deucha, Dubrajpur mouzas for providing FHTC under Raypur Zone II Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. |  |  | ORD/000030/2022-2023 | 179/RSD | 02/05/2022 | 30 | SK ABDUL HALIM | 4.67 | 0 | 100
1366 | Birbhum Division |  | Laying of HDPE Pipe line for Deucha mouza for providing FHTC under Raypur Zone II Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. |  |  | ORD/000031/2022-2023 | 180/RSD | 02/05/2022 | 30 | SK ABDUL HALIM | 5 | 0 | 100
1367 | Birbhum Division |  | Construction of PCC approach Road at Head Work Site for Raypur Zone-I Piped Water Supply Scheme under under Rampurhat Sub-Division under Birbhum Division, PHE Dte. |  |  | ORD/000068/2022-2023 | 225/RSD | 23/06/2022 | 30 | GOURANGA MONDAL | 2.6 | 0 | 100
1368 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raipur Zone-II Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.13) |  |  | ORD/000433/2021-2022 | 24/BHM | 06/01/2022 | 60 | SK ALIM | 75.03 | 0 | 97
1369 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raipur Zone-I Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.12) |  |  | ORD/000480/2021-2022 | 279/BHM | 09/02/2022 | 60 | PRADIP KUMAR SHARMA | 76.52 | 0 | 50
1370 | Birbhum Division |  | Connection between New Tubewells to existing CWR by DI pipe near Dwarka River Bank site for Raypur Piped Water Supply Scheme under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. |  |  | ORD/000520/2021-2022 | 14/RSD | 04/01/2022 | 30 | ASIT GHOSH | 3.34 | 0 | 100
1371 | Birbhum Division |  | Sinking for 3 nos. 200 mm dia. Tubewell with horizontal strainer on the River Bed of Dwarka under Raypur Piped Water Supply Scheme under Birbhum Division P.H.E. Dte. |  |  | ORD/000544/2021-2022 | 31/RSD | 04/01/2022 | 30 | SUNIL RABI DAS | 4.91 | 0 | 100
1372 | Birbhum Division |  | Additional Laying & joining with UPVC pipes within distribution system From near OHR Site to Deucha Masjid of Raipur (Zone-II) piped W/S Scheme under Birbhum Division, PHE Dte. |  |  | ORD/000545/2021-2022 | 32/RSD | 04/01/2022 | 30 | GOURANGA MONDAL | 4.96 | 0 | 100
1373 | Birbhum Division |  | Additional Laying & joining with UPVC pipes within distribution system From near Deucha Masjid to Deucha Eid Gaha of Raipur (Zone-II) piped W/S Scheme under Birbhum Division, PHE Dte. |  |  | ORD/000546/2021-2022 | 33/RSD | 04/01/2022 | 30 | GOURANGA MONDAL | 4.96 | 0 | 100
1374 | Birbhum Division |  | Additional Laying & joining with UPVC pipes within distribution system From near Deucha Bus Stand to Deucha Bridge of Raipur (Zone-II) piped W/S Scheme under Birbhum Division, PHE Dte. |  |  | ORD/000547/2021-2022 | 34/RSD | 04/01/2022 | 30 | GOURANGA MONDAL | 4.95 | 0 | 100
1375 | Birbhum Division |  | Laying of UPVC pipes within distribution system from Deucha to Harinsingha Road at Sahapara of Raipur (Zone-II) piped W/S Scheme under Birbhum Division, PHE Dte. |  |  | ORD/000643/2021-2022 | 100/RSD | 07/03/2022 | 30 | GOURANGA MONDAL | 2.34 | 0 | 100
1376 | Birbhum Division |  | Supply & delivery of CI/DI Specials for Laying of Rising Main DI K9 from Deucha CWR site to Raypur Zone-I & II OHRs under Raypur Piped Water Supply Scheme under Rampurhat Sub Division, P.H.E Dte. under Birbhum Division, P.H.E. Dte. |  |  | ORD/000646/2021-2022 | 117/RSD | 10/03/2022 | 30 | ASIT GHOSH | 0.46 | 0 | 100
1377 | Birbhum Division |  | Supply & delivery of CIDF Sluice Valves for Laying of Rising Main DI K9 from Deucha CWR site to Raypur Zone-I & II OHRs under Raypur Piped Water Supply Scheme under Rampurhat Sub Division, P.H.E Dte. under Birbhum Division, P.H.E. Dte. |  |  | ORD/000667/2021-2022 | 119/RSD | 11/03/2022 | 30 | ASIT GHOSH | 0.55 | 0 | 50
1378 | Birbhum Division |  | Supply & delivery of CIDF Sluice Valves for Laying of Rising Main DI K9 from Deucha CWR site to Raypur Zone-I & II OHRs under Raypur Piped Water Supply Scheme under Rampurhat Sub Division, P.H.E Dte. under Birbhum Division, P.H.E. Dte |  |  | ORD/000698/2021-2022 | 119/RSD | 11/03/2022 | 30 | ASIT GHOSH | 0.55 | 0 | 50
1379 | Birbhum Division |  | Supply & delivery of sluice valve for Raipur W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex Dist.-Birbhum under Birbhum Division, PHE Dte. (Sl. No.-02) |  |  | ORD/000725/2021-2022 | 420/BHM | 24/02/2022 | 15 | UJJWAL DAS | 4.59 | 0 | 100
1380 | Birbhum Division |  | Laying of Rising Main DI K9 from Deucha CWR site to Raypur Zone-I and II OHRs under Raypur Piped Water Supply Scheme under Rampurhat Sub-Division, P.H.E Dte. under Birbhum Division, P.H.E. Dte. (Sl. No.1) |  |  | ORD/000861/2021-2022 | 1339/BHM | 18/08/2021 | 221 | ASIT GHOSH | 7.34 | 0 | 100
1381 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) at Churar Village (JL No.-137) of different locations from existing distribution system within the command area of Khoyrasole Piped Water Supply Scheme at Khoyrasole Block under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte. (Sl. No.-1) |  |  | ORD/000023/2021-2022 | 1096/BHM | 07/07/2021 | 60 | PRAVAT SARKAR | 35.23 | 0 | 100
1382 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) at Kendgara Village (JL No.-120) of different locations from existing distribution system within the command area of Khoyrasole Piped Water Supply Scheme at Khoyrasole Block under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte (Sl. No.-2) |  |  | ORD/000274/2021-2022 | 1476/BHM | 06/09/2021 | 60 | NUR MOBINUL ISLAM | 27.58 | 0 | 100
1383 | Birbhum Division |  | Supply and delivery of Sluice Valve for Augmentation of Khoyrasole Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-6) |  |  | ORD/000348/2023-2024 | 4625/BHM | 18/12/2023 | 30 | BAHIR CONSTRUCTION PRIVATE LIMITED | 9.3 | 0 | 100
1384 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) at Mahammadpur Village (JL No.-115) of different locations from existing distribution system within the command area of Khoyrasole Piped Water Supply Scheme at Khoyrasole Block under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte. (Sl. No.21) |  |  | ORD/000564/2020-2021 | 203/BHM | 18/02/2021 | 45 | BHAGYADHAR GHOSH | 14.28 | 0 | 100
1385 | Birbhum Division |  | Continuation Work Order for Supply and delivery of Sluice Valve for Augmentation of Khoyrasole Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-6) |  |  | ORD/000579/2023-2024 | 737/BHM | 28/02/2024 | 30 | BAHIR CONSTRUCTION PRIVATE LIMITED | 9.3 | 0 | 100
1386 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Gangmuri, of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. (Sl. No.2) |  |  | ORD/000065/2020-2021 | 1237 /BHM | 28/09/2020 | 45 | S R ENTERPRISE | 21.49 | 20.65 | 0
1387 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Madanpur, Jaypur, Talpur, Rahida, Ranigram, Hirapur, Marbuni, Laubani) of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. |  |  | ORD/000067/2020-2021 | 1167 /BHM | 21/09/2020 | 60 | M/S KRIPASINDHU GHOSH & CO. | 42.21 | 29.05 | 100
1388 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Sahabad, Azimnagar, Natangram, Gobra of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. (Sl. No.1) |  |  | ORD/000219/2020-2021 | 1236 /BHM | 28/09/2020 | 45 | RAJ KUMAR DAS | 25.65 | 0 | 40
1389 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Hazarpur of Hazarpur w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-A) |  |  | ORD/000055/2020-2021 | 1180 /BHM | 21/09/2020 | 60 | UJJWAL DAS | 41.06 | 42.13 | 0
1390 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kanakpur, Bholadanga, Ekdala of Hazarpur w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. |  |  | ORD/000056/2020-2021 | 1181 /BHM | 21/09/2020 | 60 | APORUPA CONSTRUCTION | 42.76 | 43.67 | 0
1391 | Birbhum Division | Bolpur Sub-Division | Payment for Supply of diesel | Assistant Engineer | JE2 | BILL/00270/2023-2024 | BP-2023-24-127 | 25/08/2023 | 0 | JAYRAM FILLING STATION | 0.72 | 0 | 0
1392 | Birbhum Division | Bolpur Sub-Division | Payment of Deisel Oil and fuel for the month of July23 to Sept'23 | Assistant Engineer | JE2 | BILL/00476/2023-2024 | BP-2023-24-235 | 01/11/2023 | 0 | JAYRAM FILLING STATION | 0.72 | 0 | 0
1393 | Birbhum Division | Bolpur Sub-Division | Certified that the total quantity of fuel supplied for the vehicle no. WB53B-8630 consumed for official purpose under Assistant Engineer (HQ), Birbhum Division PHE Dte. for the month of Oct'23. | Assistant Engineer | JE2 | BILL/00883/2023-2024 | BP-2023-24-407 | 01/03/2024 | 0 | JAYRAM FILLING STATION | 0.2 | 0 | 0
1394 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at Khujutipara Mouja (JL No.-127) at different locations from existing distribution system within the command area of Khujutipapara and Adjoining Mouzas W/S Scheme at Nanoor Block under Bolpur Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte | Assistant Engineer | JE2 | ORD/000084/2020-2021 | 1088 /BHM | 05/09/2020 | 30 | BHAGYADHAR GHOSH | 4.7 | 4.7 | 0
1395 | Birbhum Division | Bolpur Sub-Division | Continution work for Supply of one no. Diesel driven Motor Cab / Maxi Cab (Air Condition) on hire Basis under the Assitant Engineer (H.Q) Birbhum Division P.H.E Dte. (Period from 01.05.2023 to 31.10.2023) | Assistant Engineer | JE2 | ORD/000166/2023-2024 | 1607/BHM | 27/04/2023 | 184 | JAMSED ALI KHAN | 0.96 | 0 | 100
1396 | Birbhum Division | Bolpur Sub-Division | Continuation Work of Hiring of Ambassador Car (Diesel) registered Luxury Taxi for the office of the Assistant Engineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition for 364 days (from 02.07.2021 to 30.06.2022) for 364 days (from 02.07.2022 to 30.06.2023) for 31 Days (from 01.07.2023 to 31.07.2023). | Assistant Engineer | JE2 | ORD/000168/2023-2024 | 155/RSD | 28/06/2023 | 31 | SOUMITA PAL | 0.17 | 0 | 0
1397 | Birbhum Division | Bolpur Sub-Division | Preparation and broadcasting of 10 minutes programme (PHE Manusaher sathe) planned for Awarness generation through (Audio visual Documentation) TV and social media of covering the area of Birbhum Distric under Birbhum Division PHE Dte. (Sl.No.01) | Assistant Engineer | JE2 | ORD/000192/2020-2021 | 1570/BHM | 07/12/2020 | 60 | TARANGA ONLINE | 0.89 | 0.89 | 0
1398 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) and Retrofitting of pipe lines From Khujutipara Fishery Market to Petrol pump, Chatimgram on Basapara Nanoor Road for Providing sufficient water to Nanagar Kodda Village from existing distribution system within the command area of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED | Assistant Engineer | JE2 | ORD/000325/2022-2023 | 2586/BHM | 22/11/2022 | 30 | M/S.CHANDRANATH MUKHERJEE | 23.26 | 0 | 0
1399 | Birbhum Division | Bolpur Sub-Division | Supply of one no. diesel driven car(Diesel) on hire basis office uses for the official of the Assistant Engineer, RWS, Birbhum Sub-Division, PHE Dte.(Period from 06.07.2023 to 31.12.2023) | Assistant Engineer | JE2 | ORD/000340/2023-2024 | 337/RWS | 05/07/2023 | 179 | AADIL CONSTRUCTION | 0.85 | 0 | 15
1400 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Nabasta of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (2nd Call) (Sl. No.24) | Assistant Engineer | JE2 | ORD/000359/2020-2021 | 31/BHM | 13/01/2021 | 60 | MANAS KUMAR MONDAL | 28.93 | 13.59 | 45
1401 | Birbhum Division | Bolpur Sub-Division | Continuation order against "Hiring of 1(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, PHE Dte. under Birbhum Division, PHE Dte. For the period of 01.04.2023 to 30.09.2023". For another 06 (Six) months i.e. from 01.10.2023 to 31.03.2024. | Assistant Engineer | JE2 | ORD/000449/2023-2024 | 436/BSD | 29/09/2023 | 182 | SK AKRAM HOSSAIN | 0.86 | 0 | 100
1402 | Birbhum Division | Bolpur Sub-Division | Allied works of extension pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages BAITARA & KHUJUTIPARA of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No. - 08) | Assistant Engineer | JE2 | ORD/000518/2021-2022 | 375/BSD | 05/10/2021 | 30 | MANAS KUMAR MONDAL | 4.56 | 0 | 98
1403 | Birbhum Division | Bolpur Sub-Division | Supply of one no. Diesel driven Motor Cab/Maxi Cab(Air Condition) on hire basis under the Assistant Engineer (H.Q), Birbhum Division PHE Dte.(Period from 01.11.2022 to 30.04.2023) | Assistant Engineer | JE2 | ORD/000531/2022-2023 | 2320/BHM | 28/10/2022 | 184 | JAMSED ALI KHAN | 0.96 | 0 | 100
1404 | Birbhum Division | Bolpur Sub-Division | Supply of one no. diesel driven Car (Diesel) on hire basis office uses for the officials of the Assistant Engineer, RWS, Birbhum Sub-Division, P.H.E. Dte. [Period from (01.02.2023 to 05.07.2023) | Assistant Engineer | JE2 | ORD/000572/2022-2023 | 185/RWS | 31/01/2023 | 155 | AADIL CONSTRUCTION | 0.73 | 0 | 100
1405 | Birbhum Division | Bolpur Sub-Division | Hiring of 01(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, P.H.E. Dte under Birbhum Division, P.H.E Dte. for the period of 01.04.2023 to 30.09.2023 | Assistant Engineer | JE2 | ORD/000684/2022-2023 | 154/BSD | 30/03/2023 | 183 | SK AKRAM HOSSAIN | 0.86 | 0 | 87
1406 | Birbhum Division | Bolpur Sub-Division | Cleaning the Chokage of 150mm. DI pipe line, repairing of UPVC pipe, retrofitting of pipeline for Providing sufficient water to Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages of Baitara, Sehela and Nabsata of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, Public Health Engineering Department. | Assistant Engineer | JE2 | ORD/000822/2022-2023 | 309/BSD | 16/08/2022 | 30 | BHAGYADHAR GHOSH | 4.42 | 0 | 100
1407 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Jhaupara, Dattakaya, Shingdohari in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte (Sl. No.9) |  |  | ORD/000001/2021-2022 | 681/BHM | 01/06/2021 | 60 | BELAL SK | 43.79 | 38.61 | 92
1408 | Birbhum Division |  | Sinking and replacement of 200mm dia 60 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Haridaspur (near head work side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. |  |  | ORD/000002/2022-2023 | 208/AE/NSD | 05/04/2022 | 30 | SURJASISH DATTA | 3.74 | 0 | 100
1409 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Haridaspur in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.10) |  |  | ORD/000003/2021-2022 | 1006/BHM | 11/06/2021 | 60 | M/S KRIPASINDHU GHOSH & CO. | 36.62 | 36.61 | 100
1410 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Bhagabatipur in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.12) |  |  | ORD/000004/2021-2022 | 1015/BHM | 15/06/2021 | 60 | TAPAN KUMAR DATTA | 30.21 | 0 | 100
1411 | Birbhum Division |  | Construction of Boundary Wall at OHR site at Haridaspur Piped Water Supply Scheme (South side) under Nalhati Sub-Division within Birbhum Division, PHED. |  |  | ORD/000009/2022-2023 | 224/AE/NSD | 19/04/2022 | 60 | RAJA CONSTRUCTION | 4.84 | 0 | 45
1412 | Birbhum Division |  | Balance work for construction of High Lift Pump house including stainless steel railing at Haridaspur PWSS Under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. |  |  | ORD/000106/2022-2023 | 357/AE/NSD | 20/07/2022 | 45 | SUNIL RABI DAS | 5 | 0 | 0
1413 | Birbhum Division |  | Extention of pipeline by HDPE pipe at Gunia and Kalyanpur habitation for providing FHTC of Haridaspur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division PHED. |  |  | ORD/000112/2022-2023 | 200/AE/NSD | 01/04/2022 | 45 | M/S S.N CONSTRUCTION | 3.15 | 0 | 100
1414 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Sanakpur in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.8) |  |  | ORD/000130/2021-2022 | 910/BHM | 10/06/2021 | 60 | MS B N ENTERPRISES | 32.66 | 0 | 100
1415 | Birbhum Division |  | Extention of pipeline by HDPE pipe at Bhagabatipur and Chachka habitations for providing FHTC of Haridaspur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHED. |  |  | ORD/000152/2022-2023 | 211/AE/NSD | 07/04/2022 | 45 | HUMAYUN KABIR | 4.84 | 0 | 100
1416 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Chachka-Balarampur habitations under Haridaspur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000309/2021-2022 | 530/AE/NSD | 08/10/2021 | 45 | SUBHRANIL DAS | 4.74 | 0 | 100
1417 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Chachka habitations under Haridaspur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000310/2021-2022 | 531/AE/NSD | 08/10/2021 | 45 | HUMAYUN KABIR | 4.75 | 0 | 100
1418 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Jungul,Gunua in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.11) |  |  | ORD/000330/2020-2021 | 274 / BHM | 26/02/2021 | 45 | KAZI EMDADUL HAQUE | 23.6 | 21.04 | 95
1419 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Kalyanpur Habitation under Haridaspur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000360/2021-2022 | 593/AE/NSD | 23/11/2021 | 45 | M/S S.N CONSTRUCTION | 4.82 | 0 | 100
1420 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Gunia Habitation under Haridaspur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000361/2021-2022 | 594/AE/NSD | 23/11/2021 | 45 | AJIMUL ISLAM | 4.82 | 0 | 100
1421 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Dasturpur (South) Habitation under Haridaspur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000362/2021-2022 | 595/AE/NSD | 23/11/2021 | 45 | DATA CONSTRUCTION | 4.82 | 0 | 100
1422 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Dasturpur (North) Habitation under Haridaspur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000363/2021-2022 | 596/AE/NSD | 23/11/2021 | 45 | SURJASISH DATTA | 4.82 | 0 | 100
1423 | Birbhum Division |  | Sinking of 200mm 50 m. deep replacement (No.-1) Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at Haridaspur Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. |  |  | ORD/000611/2021-2022 | 122/AE/NSD | 04/03/2022 | 30 | SURJASISH DATTA | 3.3 | 0 | 100
1424 | Birbhum Division |  | Land development including strengthening of River side filling HARIDASPUR PWSS under Nalhati Sub-Division, PHE Dte. |  |  | ORD/000623/2021-2022 | 22/NSD | 17/01/2022 | 21 | SUNIL RABI DAS | 4.84 | 0 | 100
1425 | Birbhum Division | Nalhati Sub-Division | Replacement with Extension of 63 & 75 mm Dia. UPVC Pipe line in different habitations within Gopalpur (Zone-II) Piped Water Supply Scheme under Nalhati Sub-Division P.H.E Dte. | AE | JE3 | ORD/000010/2022-2023 | 206/AE/NSD | 05/04/2022 | 45 | SUPRABHAT RABIDAS | 4.22 | 0 | 50
1426 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply Scheme (Zone-II) under Nalhati Sub Division within Birbhum Division PHED. | AE | JE3 | ORD/000016/2022-2023 | 229/AE/NSD | 21/04/2022 | 45 | MD ZIAUL ISLAM | 3.34 | 0 | 0
1427 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in left out habitations , under Ramchandrapur & Kestara Village (J.L:-100) under Murarai - I Block, within the command area of Gopalpur Zone II W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000083/2021-2022 | 370/AE/NSD | 22/07/2021 | 45 | SUPRABHAT RABIDAS | 4.97 | 0 | 50
1428 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply Scheme (Zone-II) under Nalhati Sub Division within Birbhum Division PHED. | AE | JE3 | ORD/000141/2022-2023 | 383/AE/NSD | 10/08/2022 | 45 | MD ZIAUL ISLAM | 3.34 | 0 | 50
1429 | Birbhum Division | Nalhati Sub-Division | Replacement of UPVC pipe line & Inter connection of D.I. pipeline from new tube well to rising main at Guskira village of Gopalpur (Zone-II) Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000213/2022-2023 | 408/AE/NSD | 06/09/2022 | 30 | SUPRABHAT RABIDAS | 4.84 | 0 | 100
1430 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Ramchandrapur and Kestora under Murarai-I Block within the command area of Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000285/2021-2022 | 509/AE/NSD | 01/10/2021 | 45 | SUPRABHAT RABIDAS | 4.66 | 0 | 33
1431 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000294/2021-2022 | 508/AE/NSD | 01/10/2021 | 45 | SHIB GANGA CONSTRUCTION | 4.67 | 0 | 67
1432 | Birbhum Division | Nalhati Sub-Division | Extension of pipeline for left out habitations along with FHTC at Gopalpur PWSS (Zone-I) under Nalhati Sub Division P.H.E.D (Sl. No.12) | AE | JE3 | ORD/000398/2022-2023 | 28/BHM | 04/01/2023 | 45 | SUBHRANIL DAS | 11.64 | 0 | 100
1433 | Birbhum Division | Nalhati Sub-Division | Extension of pipeline for left out habitations along with FHTC at Gopalpur PWSS( Zone-II)under Nalhati Sub Division P.H.E.D. (Sl. No.11) | AE | JE3 | ORD/000401/2022-2023 | 31/BHM | 04/01/2023 | 45 | ISLAM CONSTRUCTION | 17.06 | 0 | 0
1434 | Birbhum Division | Nalhati Sub-Division | Approaching path to Pump House along with Land Development at OHR site of Gopalpur PWSS (Zone-II) under Nalhati Sub-Division, PHED. | AE | JE3 | ORD/000615/2022-2023 | 131/NSD | 31/03/2023 | 30 | SUPRABHAT RABIDAS | 0.97 | 0 | 100
1435 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 500cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Pachiara W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000015/2023-2024 | 1290/BHM | 18/04/2023 | 275 | M/S GOUTAM DAS | 128.83 | 0 | 0
1436 | Birbhum Division | Birbhum Sadar Sub-Division | Trial Bore and Sinking of 200 mm dia. tubewell (04 nos.) 30 m. Deep fitted with M.S.E.R.W. Housing pipe and Fibre Glass Strainer on the river bank of Sal for the Augmentation of Panchiara Piped Water Supply Scheme under Birbhum Sadar Sub-Division PHE Dte. with Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000114/2023-2024 | 1982/BHM | 05/06/2023 | 30 | AMIT KUMAR ROY | 5.7 | 0 | 100
1437 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of Boundary wall at Pump House River Bank site under Pachiara Piped Water Supply Scheme within Birbhum Sadar Sub-Division, P.H.E. Dte. under Birbhum Division, P.H.E. Dte. (Sl. No. -19) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000123/2021-2022 | 250/BSSD | 03/08/2021 | 45 | RANJIT GHOSH | 2.69 | 0 | 100
1438 | Birbhum Division | Birbhum Sadar Sub-Division | Laying distribution system including FHTC for proposed augmentation scheme for Pachiara Piped Water Supply Scheme, Dubrajpur Block, under Birbhum Division, PHE Dte.? (Sl. No.1) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000248/2022-2023 | 1161/BHM | 23/05/2022 | 1166 | M/S GOUTAM DAS | 467.38 | 0 | 92
1439 | Birbhum Division | Birbhum Sadar Sub-Division | Laying of Rising Main Pipe line for the Augmentation of Pachiara Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000523/2023-2024 | 768/BHM | 01/03/2024 | 45 | M/S JOY MAA BANAMALI | 6.37 | 0 | 0
1440 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of Drain and Valve Chamber Pachiara Water Supply Scheme at Rampur under RWS Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte.(Sl.No.5) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000543/2022-2023 | 134/BH | 15/06/2022 | 30 | UTPAL DEY | 3.03 | 0 | 0
1441 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000013/2022-2023 | 907/BHM | 26/04/2022 | 0 | Resource Division | 4.36 | 0 | 0
1442 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000096/2022-2023 | 946/BHM | 24/03/2023 | 0 | Resource Division | 68.5 | 0 | 0
1443 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000108/2022-2023 | 1119/BHM | 10/04/2023 | 0 | Resource Division | 10.48 | 0 | 0
1444 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000180/2023-2024 | 2245/BHM | 07/07/2023 | 0 | Resource Division | 2.85 | 0 | 0
1445 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000191/2023-2024 | 3282/BHM | 27/07/2023 | 0 | Resource Division | 1.37 | 0 | 0
1446 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR PACHAIARA WS SCHEME | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01364/2023-2024 | BP-23-24-146 | 28/11/2023 | 0 | WBSEDCL | 0.02 | 0 | 0
1447 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR PACHHIARA | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01577/2023-2024 | BP-23-24-203 | 04/01/2024 | 0 | WBSEDCL | 5.75 | 0 | 0
1448 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing and Installation of Electro-Mechanical equipments and other allied Works for Augmentation of PANCHIARA PWSS under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000451/2023-2024 | 2129/Bol.MD | 25/08/2023 | 90 | SATYAJIT GHOSH | 96.79 | 0 | 50
1449 | Birbhum Division | Nalhati Sub-Division | Lohapur Gumani setu with a link to lohapur railway station from 0.00 kmp and from 2.00 kmp to 6.40km under Birbhum Highway Division-I in the district of Birbhum Restoration of Widening. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00090/2023-2024 | BP-2023-24-61 | 07/06/2023 | 0 | NATIONAL CONSTRUCTION | 9.65 | 0 | 0
1450 | Birbhum Division | Nalhati Sub-Division | Sarda Bujung road from 0.00 km to 3.20 km under Birbhum Highway Division-I in the District of Birbhum Restoration work of hard shoulder portion with Jhama metal consolidation and moorum damaged by the PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00107/2023-2024 | BP-2023-24-64 | 08/06/2023 | 0 | SAMSHER HOSSAIN | 5.16 | 0 | 0
1451 | Birbhum Division | Nalhati Sub-Division | Laying distribution system including functional household for proposed augmentation scheme for Murarai Piped Water Supply Scheme under Murarai ¿ I Block, under Birbhum Division, PHE Dte.¿ (Sl. No.4) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000004/2022-2023 | 555/BHM | 08/04/2022 | 180 | SK ALIM | 392.31 | 0 | 72
1452 | Birbhum Division | Nalhati Sub-Division | Repairing & renovation of Boundary Wall with Land filling at Head Work site (Murarai-1 Dev. Block) at Murarai Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHED. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000013/2022-2023 | 199/AE/NSD | 01/04/2022 | 30 | M/S S.N CONSTRUCTION | 4.85 | 0 | 100
1453 | Birbhum Division | Nalhati Sub-Division | Construction of 550 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Kaytha W/S Scheme under Na Division hati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000017/2023-2024 | 1183/BHM | 12/04/2023 | 275 | S K CONSTRUCTION | 142.19 | 0 | 100
1454 | Birbhum Division | Nalhati Sub-Division | Construction of 400 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Pile foundation including pipe connection & allied works for augmentation of Bara Zone I W/S Scheme under Nalhati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000020/2023-2024 | 1184/BHM | 12/04/2023 | 275 | TAPAN KUMAR DATTA | 112 | 0 | 65
1455 | Birbhum Division | Nalhati Sub-Division | Allied works for Laying of 315 mm dia. HDPE pipe line instead of 350 mm dia. D.I. pipe line along with laying of 90 mm dia. HDPE pipe line to the left-out habitations along with restoration of road including Jack Pushing/augor boring of Rajgram (Zone-I) PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000024/2023-2024 | 1246/BHM | 17/04/2023 | 806 | MANASH GHOSH | 177.06 | 0 | 96
1456 | Birbhum Division | Nalhati Sub-Division | Construction of 900 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and Allied for balance work of distribution pipeline including 315mm dia HDPE pipeline instead of 350mm dia DI pipeline along with restoration of roads and providing FHTC for Paikar w/s Scheme under Nalhati Sub-Division within Birbhum Division,P.H.E. Dte | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000025/2023-2024 | 1100/BHM | 06/04/2023 | 636 | SK ALIM | 455.72 | 0 | 100
1457 | Birbhum Division | Nalhati Sub-Division | Construction of 600 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including raft foundation and Balance work of distribution pipeline including extension of pipeline along with FHTC and restoration of roads for Bhadrapur Z-II w/s Scheme under Nalhati Sub-Division within Birbhum Division,P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000029/2023-2024 | 1107/BHM | 10/04/2023 | 549 | SUNIL RABI DAS | 229.46 | 0 | 100
1458 | Birbhum Division | Nalhati Sub-Division | Allied work for Balance work of distribution Pipe line including FHTC Work along with restoration of PWD road Flank & Other Connecting road including dismantling work with jack pushing, Augur Boring for Augmentation of Bara Zone-II Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000033/2023-2024 | 1099/BHM | 06/04/2023 | 180 | MANASH GHOSH | 199.45 | 0 | 95
1459 | Birbhum Division | Nalhati Sub-Division | Sinking of 200 mm dia 51.0 m deep Tube wells, Construction of Pump-House with retaining wall & inspection path including Land development and Laying of 250 mm dia HDPE rising main with interconnection of Rajgram w/s Scheme, under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte.¿ (Sl. No.2) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000042/2022-2023 | 1072/BHM | 13/05/2022 | 161 | SUNIL RABI DAS | 108.04 | 0 | 100
1460 | Birbhum Division | Nalhati Sub-Division | Laying distribution system for proposed augmentation scheme for Bhadrapur Zone-II Piped Water Supply Scheme under Nalhati-II Block, under Birbhum Division, PHE Dte. (Sl. No.2) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000044/2022-2023 | 806/BHM | 12/04/2022 | 180 | SUNIL RABI DAS | 407.95 | 0 | 100
1461 | Birbhum Division | Nalhati Sub-Division | Construction of 700 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Pile foundation including pipe connection & allied works for augmentation of Chatra W/S Scheme under Nalhati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000046/2023-2024 | 1289/BHM | 18/04/2023 | 275 | RAJGRAM FAV CO OPT LAB CON AND CONST SO LTD | 152.19 | 0 | 82
1462 | Birbhum Division | Nalhati Sub-Division | Allied work for Balance work of distribution Pipe line including FHTC Work along with restoration of PMGSY road Flank & Other Connecting road including dismantling work with Augur Boring for Augmentation of Bara Zone-I Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000050/2023-2024 | 1243/BHM | 17/04/2023 | 562 | PASCON | 97.58 | 0 | 55
1463 | Birbhum Division | Nalhati Sub-Division | Repairng, Renovation of Pump house & repairing of CWR of Murarai Piped Water Supply Scheme at RWS,Birbhum Sub-Division under Birbhum Division, PHE Dte.(Sl. No.01) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000063/2022-2023 | 86/BH | 05/05/2022 | 20 | M/S S.N CONSTRUCTION | 4.77 | 0 | 0
1464 | Birbhum Division | Nalhati Sub-Division | Allied work for Balance work of distribution Pipe line including FHTC Work along with restoration of PWD road Flank & Other Connecting road including dismantling work with jack pushing, Augur Boring for Augmentation of Kaytha Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000079/2023-2024 | 1428/BHM | 25/04/2023 | 270 | PRANAB KUMAR GHOSH | 133.64 | 0 | 55
1465 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection(FHTC) from existing distribution system in Rudranagar Pathanpara (Chatra Zone-II) W/S Scheme (Rudranagar) under RWS Birbhum Sub-Divition within Birbhum Division PHE Dte. (Sl. No.10) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000090/2022-2023 | 139/BH | 15/06/2022 | 20 | ISLAM CONSTRUCTION | 4.75 | 0 | 0
1466 | Birbhum Division | Nalhati Sub-Division | Construction of Pump House of 5.40 mtr. x 3.6 mtr. size with sanitary and water supply arrangement at Bara (Zone-I) Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHED. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000098/2022-2023 | 351/AE/NSD | 19/07/2022 | 60 | NUR MOBINUL ISLAM | 4.99 | 0 | 100
1467 | Birbhum Division | Nalhati Sub-Division | Allied for balance work of distribution pipeline for Dhitora (Part) village including FHTC under Augmentation of Murarai W/S Scheme under Nalhati Sub-division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000101/2023-2024 | 1722/BHM | 12/05/2023 | 30 | M/S PROCHESTA ENTERPRISE | 35.04 | 0 | 100
1468 | Birbhum Division | Nalhati Sub-Division | Construction of Pump House of 5.40 mtr X 3.6 mtr. Size with sanitary and water supply arrangements at new Head work site of Murarai PWSS under Nalhati Sub-Division within Birbhum division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000102/2022-2023 | 353/AE/NSD | 20/07/2022 | 60 | M/S S.N CONSTRUCTION | 4.84 | 0 | 100
1469 | Birbhum Division | Nalhati Sub-Division | Emergent repair and replacement of Pipeline below the Railway culvert near Murarai Railway Station with allied works including extension of Pipe line of Murarai Aug. w/s Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000102/2023-2024 | 1723/BHM | 12/05/2023 | 45 | SK ALIM | 20.14 | 0 | 100
1470 | Birbhum Division | Nalhati Sub-Division | Construction of Pump House of 5.40 mtr X 3.6 mtr. Size with sanitary and water supply arrangements at new Head work site of Lohapur PWSS under Nalhati Sub-Division within Birbhum division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000103/2022-2023 | 354/AE/NSD | 20/07/2022 | 60 | GOLAM RASUL | 4.84 | 0 | 100
1471 | Birbhum Division | Nalhati Sub-Division | Sinking of 200 mm dia & 87mtr.deep Tube well fitted with PVC pipe and fibre glass Strainer for Augmentation of Lohapur Water Supply Scheme at New Head Work site under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000109/2022-2023 | 362/AE/NSD | 21/07/2022 | 45 | HARUN AR RASHID | 4.83 | 0 | 99
1472 | Birbhum Division | Nalhati Sub-Division | Allied work for Laying HDPE pipeline instead of DI Pipeline including Dismantling and restoration of Cement Concrete road for Augmentation of Bara Zone-I Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000124/2023-2024 | 1978/BHM | 05/06/2023 | 45 | PASCON | 27.73 | 0 | 100
1473 | Birbhum Division | Nalhati Sub-Division | Extension by HDPE Pipeline for the left out villages for proposed Augmentation of Bhadrapur Zone-I Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte.(Sl. No.2) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000126/2022-2023 | 1934/BHM | 06/09/2022 | 60 | M/S GOUTAM DAS | 160.74 | 0 | 100
1474 | Birbhum Division | Nalhati Sub-Division | Sinking of 1 no. new 200mm dia Tube Well of UPVC pipe 90m deep with fibre glass strainer including connecting main for Rajgram PWSS at Jagannathpur CWR site under Nalhati Sub- Division within Birbhum Division PHED. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000128/2023-2024 | 2073/BHM | 08/06/2023 | 30 | AJIMUL ISLAM | 6.7 | 0 | 100
1475 | Birbhum Division | Nalhati Sub-Division | Supply & delivery of Sluice Valve for augmentation of Bhadrapur W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, PHE Dte. (Sl. No.-02) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000129/2022-2023 | 1242/BHM | 03/06/2022 | 15 | APORUPA CONSTRUCTION | 4.99 | 0 | 100
1476 | Birbhum Division | Nalhati Sub-Division | Balance work for 160 mm dia HDPE Distribution main for Laksminarayanpur W/S Scheme, under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000130/2023-2024 | 1945/BHM | 01/06/2023 | 45 | HUMAYUN KABIR | 37.63 | 0 | 100
1477 | Birbhum Division | Nalhati Sub-Division | Supply & delivery of Sluice Valve for augmentation of Rajgram W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, PHE Dte (Sl. No.-01) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000131/2022-2023 | 1241/BHM | 03/06/2022 | 15 | SSPR VALVE MANUFACTURING PVT LTD | 4.99 | 0 | 100
1478 | Birbhum Division | Nalhati Sub-Division | Sinking replacement of 200mm dia Tube Well of UPVC pipe 90m deep with fibre glass strainer including connecting main for Lakshminaraynpur PWSS under Nalhati Sub- Division within Birbhum Division PHED. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000131/2023-2024 | 1947/BHM | 01/06/2023 | 45 | A R ENTERPRISE | 7.95 | 0 | 100
1479 | Birbhum Division | Nalhati Sub-Division | Laying distribution system for proposed augmentation scheme for Laxminarayanpur Piped Water Supply Scheme under Nalhati-I Block, under Birbhum Division, PHE Dte.(Sl. No.3) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000135/2022-2023 | 803/BHM | 12/04/2022 | 549 | PASCON | 297.86 | 0 | 100
1480 | Birbhum Division | Nalhati Sub-Division | Laying distribution system including functional household connection for proposed augmentation scheme for BARA Zone-I Piped Water Supply Scheme under Nalhati-II Block under Birbhum Division, PHE Dte.? (Sl. No.2) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000136/2022-2023 | 860/BHM | 20/04/2022 | 922 | PASCON | 392.49 | 0 | 80
1481 | Birbhum Division | Nalhati Sub-Division | Renovation of Boundary wall at Head Work Site (West Side) at Paikar Water Supply Scheme under Nalhati Sub Division within Birbhum Division Phe.Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000171/2022-2023 | 348/AE/NSD | 19/07/2022 | 45 | BISWAJIT RABIDAS | 3.09 | 0 | 0
1482 | Birbhum Division | Nalhati Sub-Division | Laying of Distribution pipeline through road crossing by adopting Jack Pushing method near Natun Bazar more to Augmentation of Murarai Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000181/2022-2023 | 405/AE/NSD | 05/09/2022 | 30 | M/S PROCHESTA ENTERPRISE | 4.97 | 0 | 100
1483 | Birbhum Division | Nalhati Sub-Division | Restoration of concrete road including dismantling of concrete at Node point 26,27,28,97 & 99 for Augmentation of Murarai and its adjoining mouzas Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000183/2022-2023 | 344/AE/NSD | 18/07/2022 | 30 | SK ABDUL HALIM | 4.97 | 0 | 100
1484 | Birbhum Division | Nalhati Sub-Division | Sinking of 200 mm dia. & 87 mtr. deep Tube well fitted with PVC pipe and fibre glass Strainer at new Head Work site (Tube well-2) Augmentation of Murarai Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000185/2022-2023 | 389/AE/NSD | 16/08/2022 | 60 | NUR MOBINUL ISLAM | 4.83 | 0 | 97
1485 | Birbhum Division | Nalhati Sub-Division | Renovation of Boundary Wall near Switch Room at Rajgram Water Supply Scheme under Nalhati Sub-Division, PHE Dte. (2nd Call) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000190/2022-2023 | 394/AE/NSD | 18/08/2022 | 60 | MD ASIF ALI | 4.85 | 0 | 0
1486 | Birbhum Division | Nalhati Sub-Division | Laying distribution system for proposed augmentation scheme for Bara Zone-II Piped Water Supply Scheme under Nalhati-II Block, under Birbhum Division, PHE Dte.(Sl. No.1) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000211/2022-2023 | 805/BHM | 12/04/2022 | 180 | MANASH GHOSH | 397.16 | 0 | 100
1487 | Birbhum Division | Nalhati Sub-Division | Re-Construction of damaged Boundary Wall at 1 no. Tube well site of Lohapur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000212/2022-2023 | 407/AE/NSD | 05/09/2022 | 45 | GOLAM RASUL | 4.99 | 0 | 100
1488 | Birbhum Division | Nalhati Sub-Division | Construction of RCC Retaining Wall including Land filling towards approach of Pump House at Head Work site of Bara Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000216/2022-2023 | 412/AE/NSD | 08/09/2022 | 45 | DATA CONSTRUCTION | 4.99 | 0 | 100
1489 | Birbhum Division | Nalhati Sub-Division | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Bhadrapur Zone-I W/S Scheme under Birbhum Division, PHE Dte. (As per Departmental Drawing)¿ (Sl. No.1) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000236/2022-2023 | 2467/BHM | 11/11/2022 | 273 | M/S. JAN MAHAMMAD | 185.25 | 0 | 100
1490 | Birbhum Division | Nalhati Sub-Division | Construction of 1000 Cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for Augmentation of Lohapur Water Supply Scheme under Birbhum Division, PHE Dte. (As per Departmental Drawing). | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000239/2022-2023 | 2203/BHM | 12/10/2022 | 9 | SUNIL RABI DAS | 200.79 | 0 | 40
1491 | Birbhum Division | Nalhati Sub-Division | Sinking of 200 mm dia. 87 mtr. deep Tube well by rotary rig method using UPVC deep well screen (RDS) pipes with Ribs 200 mm dia. At Chatra Zone-II Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000245/2021-2022 | 444/AE/NSD | 26/08/2021 | 60 | ISLAM CONSTRUCTION | 4.79 | 0 | 100
1492 | Birbhum Division | Nalhati Sub-Division | Laying of Rising main from existing OHR (Zone-I) to proposed OHR (Zone-II) of Rajgram for Augmentation of Rajgram (Zone-II) Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000255/2022-2023 | 457/NSD | 27/09/2022 | 210 | S P CONSTRUCTION | 4.98 | 0 | 100
1493 | Birbhum Division | Nalhati Sub-Division | Laying distribution system for proposed augmentation scheme for Chatra Piped Water Supply Scheme under Murarai ? I Block, under Birbhum Division, PHE Dte.?(Sl. No.3) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000263/2022-2023 | 957/BHM | 28/04/2022 | 180 | M/S GOUTAM DAS | 427.38 | 0 | 100
1494 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Paikar Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000283/2021-2022 | 507/AE/NSD | 01/10/2021 | 45 | SHIB GANGA CONSTRUCTION | 4.67 | 0 | 100
1495 | Birbhum Division | Nalhati Sub-Division | Construction of 1000 Cum Capacity and 20.0m Staging Height RCC Over Head Reservoir along with Soil Test and Laying of HDPE pipeline from node point 6 to 13 and node point 272 to 378 and cutting & restoration of concrete road for laying of extension pipeline including FHTC for Augmentation of Murarai w/s Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000284/2022-2023 | 2277/BHM | 19/10/2022 | 365 | SK ALIM | 720.71 | 0 | 100
1496 | Birbhum Division | Nalhati Sub-Division | Sinking of 200 mm dia. & 87 mtr. deep Tube well fitted with PVC pipe and fibre glass Strainer at new Head Work site (Tube well-2) Augmentation of Lohapur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000285/2022-2023 | 485/AE/NSD | 20/10/2022 | 60 | GOLAM RASUL | 4.84 | 0 | 100
1497 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Paikar W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000311/2021-2022 | 532/AE/NSD | 08/10/2021 | 45 | SHIB GANGA CONSTRUCTION | 4.74 | 0 | 100
1498 | Birbhum Division | Nalhati Sub-Division | Sinking of 200 mm dia & 87 mtr. deep Tube well fitted with PVC pipe and fibre glass Strainer for Augmentation of Bara (Zone-I) Water Supply Scheme at New Head Work site (Tube well-2) under Nalhati Sub-Division within Birbhum Division, PHE Dte.(Sl No - 06) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000320/2022-2023 | 440/NSD | 19/09/2022 | 45 | KAZI ZAKIR HOSSAIN | 4.82 | 0 | 0
1499 | Birbhum Division | Nalhati Sub-Division | Laying distribution system including FHTC for proposed augmentation scheme for Paikar Piped Water Supply Scheme Mararai-II Block under Birbhum Division PHE Dte (Sl.No. 2) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000343/2022-2023 | 1456/BHM | 07/07/2022 | 968 | SK ALIM | 663.22 | 0 | 80
1500 | Birbhum Division | Nalhati Sub-Division | Laying distribution system for proposed augmentation scheme for Kaytha piped water supply scheme nalhati-I Block under Birbhum Division PHE Dte. (2nd Call) (Sl.No1) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000344/2022-2023 | 1159/BHM | 23/05/2022 | 312 | PRANAB KUMAR GHOSH | 278.72 | 0 | 95
1501 | Birbhum Division | Nalhati Sub-Division | Allied works for replacement of MS pipe line in place of DI pipe,including restortion of road of Augmentation of Rjgram Water Supply Scheme (Zone-II) under Nalhati Sub-Division within Birbhum Division, PHE Dte. (Sl. No.4) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000354/2022-2023 | 2690/BHM | 06/12/2022 | 150 | S P CONSTRUCTION | 195.67 | 0 | 91
1502 | Birbhum Division | Nalhati Sub-Division | Sinking of 200mm dia 87 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Bhadrapur Zone-II PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000373/2021-2022 | 633/AE/NSD | 03/12/2021 | 45 | RAJA CONSTRUCTION | 4.79 | 0 | 100
1503 | Birbhum Division | Nalhati Sub-Division | Sinking of 200mm dia 87 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Bhadrapur Zone-I (near OHR side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000374/2021-2022 | 634/AE/NSD | 03/12/2021 | 45 | MD. SHAHA JAMAL | 4.79 | 0 | 50
1504 | Birbhum Division | Nalhati Sub-Division | Sinking of 200mm dia 87 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Bhadrapur Zone-I (near river side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000375/2021-2022 | 635/AE/NSD | 03/12/2021 | 45 | GOLAM RASUL | 4.79 | 0 | 100
1505 | Birbhum Division | Nalhati Sub-Division | Inter-connection between 2 nos. Tube wells to Pump House at Bara Zone-I Piped Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000378/2022-2023 | 569/NSD | 19/12/2022 | 135 | DATA CONSTRUCTION | 0.97 | 0 | 100
1506 | Birbhum Division | Nalhati Sub-Division | Inter-connection between 2 nos. Tube wells to Pump House at Lohapur Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000379/2022-2023 | 570/NSD | 19/12/2022 | 45 | GOLAM RASUL | 0.97 | 0 | 100
1507 | Birbhum Division | Nalhati Sub-Division | Inter-connection between 2 nos. Tube wells to Pump House near new Head Work site at Augmentation of Murarai Piped Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000381/2022-2023 | 572/NSD | 19/12/2022 | 45 | NUR MOBINUL ISLAM | 0.97 | 0 | 100
1508 | Birbhum Division | Nalhati Sub-Division | Allied work for Extension of Pipe line including FHTC Work along with restoration of PWD & Other Connecting roads for Augmentation of Chatra Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. (Sl. No.2) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000409/2022-2023 | 46/BHM | 04/01/2023 | 1050 | M/S GOUTAM DAS | 222.76 | 0 | 61
1509 | Birbhum Division | Nalhati Sub-Division | Allied work for Laying of Balance pipe line of different dia as per revised drawing including Jack pushing with restoration of road and pipe carrying stracture along with extension of pipe line and balance FHTC of Augmentation of Lohapur Water Supply Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte.(Sl. No.1) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000483/2022-2023 | 259/BHM | 30/01/2023 | 600 | SUNIL RABI DAS | 325.53 | 0 | 93
1510 | Birbhum Division | Nalhati Sub-Division | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Rajgram (Zone-II) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000490/2021-2022 | 65/AE/NSD | 11/02/2022 | 15 | MOYTEC | 0.99 | 0 | 100
1511 | Birbhum Division | Nalhati Sub-Division | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Chatra Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000491/2021-2022 | 66/AE/NSD | 11/02/2022 | 15 | MOYTEC | 0.99 | 0 | 100
1512 | Birbhum Division | Nalhati Sub-Division | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Kaytha Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000492/2021-2022 | 67/AE/NSD | 11/02/2022 | 15 | MOYTEC | 0.99 | 0 | 100
1513 | Birbhum Division | Nalhati Sub-Division | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Bara (Zone-I) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000493/2021-2022 | 68/AE/NSD | 11/02/2022 | 15 | G.MITRA & ASSOCIATE | 0.98 | 0 | 100
1514 | Birbhum Division | Nalhati Sub-Division | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Bara (Zone-II) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000494/2021-2022 | 69/AE/NSD | 11/02/2022 | 15 | GEOCON INDIA | 0.99 | 0 | 100
1515 | Birbhum Division | Nalhati Sub-Division | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Bhadrapur (Zone-II) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000496/2021-2022 | 71/AE/NSD | 11/02/2022 | 15 | GEOCON INDIA | 0.99 | 0 | 0
1516 | Birbhum Division | Nalhati Sub-Division | Supply and delivery of Sluice Valve for Augmentation of Rajgram W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. (2nd Call) (Sl No-1) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000533/2022-2023 | 666//BHM | 28/02/2023 | 30 | AMRT INDUSTRIES PRIVATE LIMITED | 8.42 | 0 | 100
1517 | Birbhum Division | Nalhati Sub-Division | Surging of 2 nos. existing Tube wells of Lohapur Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000555/2021-2022 | 695/AE/NSD | 31/12/2021 | 15 | GOLAM RASUL | 0.63 | 0 | 100
1518 | Birbhum Division | Nalhati Sub-Division | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Bhadrapur (Zone-I) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000574/2021-2022 | 691/AE/NSD | 30/12/2021 | 15 | G.MITRA & ASSOCIATE | 0.99 | 0 | 100
1519 | Birbhum Division | Nalhati Sub-Division | Allied works for extension of HDPE pipe line including FHTC of Bhadrapur (Zone-I) PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000603/2022-2023 | 1047/BHM | 31/03/2023 | 60 | M/S GOUTAM DAS | 96.04 | 0 | 0
1520 | Birbhum Division | Nalhati Sub-Division | Emergent repairing & relaying of 150 mm dia. DI Rising main of Laxminarayanpur PWSS under Nalhati Sub-Division within Birbhum Division, PHED. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000616/2022-2023 | 132/NSD | 31/03/2023 | 30 | HUMAYUN KABIR | 0.96 | 0 | 100
1521 | Birbhum Division | Nalhati Sub-Division | Laying of 160mm dia. HDPE pipe line from CWR site to Dhabuni village, of Laxshminarayan Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. (2nd Call)¿(Sl. No.9) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000617/2020-2021 | 1708/BHM | 07/10/2020 | 45 | HUMAYUN KABIR | 39.25 | 0 | 100
1522 | Birbhum Division | Nalhati Sub-Division | Distribution system relating to argumentation of Rajgram Zone-II Water Supply Scheme under Murarai-I Block, District- Birbhum, under Birbhum Division, PHE Dte. (Sl. No.-3) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000633/2021-2022 | 550/BHM | 07/03/2022 | 360 | S P CONSTRUCTION | 401.32 | 0 | 99
1523 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Bhatra, Abdullapur and adjacent area under Rajgram W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000634/2021-2022 | 592/AE/NSD | 23/11/2021 | 45 | MD ASIF ALI | 4.82 | 0 | 50
1524 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Laxminarayanpur Water Supply Scheme within Nalhati Sub-Division Birbhum Division, PHE Dte. (2nd Call). (Sl. No.14) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000635/2021-2022 | 562/BHM | 09/03/2022 | 60 | BELAL SK | 76.15 | 0 | 100
1525 | Birbhum Division | Nalhati Sub-Division | Distribution system Relating to argumentation of Bhadrapur Zone-I Water Supply Scheme under Nalhati - I Block, District- Birbhum, under Birbhum Division, PHE Dte. (Sl. No.-1) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000711/2021-2022 | 548/BHM | 07/03/2022 | 240 | M/S GOUTAM DAS | 505.15 | 0 | 100
1526 | Birbhum Division | Nalhati Sub-Division | Repairing of Pump House of Bara Water Supply Scheme under RWS Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000774/2021-2022 | 35/BH | 09/03/2022 | 30 | RANJIT GHOSH | 0.86 | 0 | 0
1527 | Birbhum Division | Nalhati Sub-Division | Repairing and renovation of boundary wall near OHR site at Paikar Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000794/2021-2022 | 447/AE/NSD | 26/08/2021 | 45 | SHIB GANGA CONSTRUCTION | 4.84 | 0 | 100
1528 | Birbhum Division | Nalhati Sub-Division | Supply & delivery of sluice valve for Augmentation of Rajgram W/S scheme under Birbhum Division, PHE Dte including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. (Sl. No.-01) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000806/2021-2022 | 561/BHM | 15/03/2022 | 15 | SSPR VALVE MANUFACTURING PVT LTD | 0.97 | 0 | 100
1529 | Birbhum Division | Nalhati Sub-Division | Sinking of 200mm dia 87 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Kaitha PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000847/2021-2022 | 636/AE/NSD | 03/12/2021 | 45 | ENAMUL ISLAM | 4.79 | 0 | 96
1530 | Birbhum Division | Nalhati Sub-Division | Sinking of 200mm 90 m. deep Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at New Head Work site of Bara (Zone-I) Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000849/2021-2022 | 120/AE/NSD | 03/03/2022 | 30 | DATA CONSTRUCTION | 4.8 | 0 | 100
1531 | Birbhum Division | Nalhati Sub-Division | Sinking of 200mm 90 m. deep Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at New Head Work site of Murarai Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000888/2021-2022 | 125/AE/NSD | 04/03/2022 | 30 | NUR MOBINUL ISLAM | 4.79 | 0 | 100
1532 | Birbhum Division | Nalhati Sub-Division | Sinking of 200mm 50 m. deep (Replacement No.-1) Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at Laxminarayanpur Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000892/2021-2022 | 124/AE/NSD | 04/03/2022 | 30 | BELAL SK | 3.3 | 0 | 98
1533 | Birbhum Division | Nalhati Sub-Division | Collection Household details including Geo reference in habitations named Jagannathpur, Sonarpur, Natun Abdullahapur, Puratan Abdullahapur & Vatra under Rajgram Water Supply Scheme under Nalhati Sub-Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000903/2021-2022 | 311/AE/NSD | 29/05/2021 | 15 | MD ASIF ALI | 0.32 | 0 | 72
1534 | Birbhum Division | Nalhati Sub-Division | Distribution system relating to argumentation of Rajgram Zone-I Piped Water Supply Scheme under Murarai-I Block, District - Birbhum, under Birbhum Division, PHE Dte. (Sl. No.-2) | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000960/2021-2022 | 647/BHM | 25/03/2022 | 180 | MANASH GHOSH | 309.72 | 0 | 100
1535 | Birbhum Division | Nalhati Sub-Division | Replacement of existing pipeline by UPVC in Chatra Zone-I Water Supply Scheme under Nalhati Sub-Division under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000980/2021-2022 | 371/AE/NSD | 23/07/2021 | 45 | ISLAM CONSTRUCTION | 4.84 | 0 | 100
1536 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000024/2022-2023 | 2207/BHM | 12/10/2022 | 0 | Resource Division | 251.49 | 0 | 0
1537 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000027/2022-2023 | 2295/BHM | 20/10/2022 | 0 | Resource Division | 15.26 | 0 | 0
1538 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000028/2022-2023 | 2289/BHM | 20/10/2022 | 0 | Resource Division | 115.36 | 0 | 0
1539 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000032/2022-2023 | 2291/BHM | 20/10/2022 | 0 | Resource Division | 187.32 | 0 | 0
1540 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000067/2021-2022 | 559/BHM | 08/03/2022 | 0 | Resource Division | 1638.42 | 0 | 0
1541 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000094/2022-2023 | 817/BHM | 15/03/2023 | 0 | Resource Division | 36.51 | 0 | 0
1542 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000095/2022-2023 | 945/BHM | 24/03/2023 | 0 | Resource Division | 157.64 | 0 | 0
1543 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000104/2022-2023 | 1121/BHM | 10/04/2023 | 0 | Resource Division | 32.67 | 0 | 0
1544 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000176/2023-2024 | 2070/BHM | 14/06/2023 | 0 | Resource Division | 36.96 | 0 | 0
1545 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000183/2023-2024 | 2278/BHM | 13/07/2023 | 0 | Resource Division | 118.06 | 0 | 0
1546 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | RTOR000196/2023-2024 | 3575/ BHM | 18/08/2023 | 0 | Resource Division | 1.91 | 0 | 0
1547 | Birbhum Division | Nalhati Sub-Division | Materials Payment | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | VCH/001322/2021-2022 | BP-2021-22-355 | 14/03/2022 | 0 | RESOURCES DIVISION | 1265.56 | 0 | 0
1548 | Bolpur Mechanical | Nalhati Sub-Division | ELECTRIC QUOTATION BILL FOR BARA WS SCHEME | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00009/2023-2024 | BP-2023-2024-07 | 13/04/2023 | 0 | WBSEDCL | 1.8 | 0 | 0
1549 | Bolpur Mechanical | Nalhati Sub-Division | Quotation for new service connection at Kaitha PWSS (Block-Nalhati - I), Lohapur CCC, WBSEDCL | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00218/2024-2025 | BP-24-25-100 | 02/07/2024 | 0 | WBSEDCL | 6.71 | 0 | 0
1550 | Bolpur Mechanical | Nalhati Sub-Division | Additional Quotation deposit for empowering Augmentation of Rajgram Water Supply Scheme in Murarai CCC under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00221/2024-2025 | BP-24-25-99 | 02/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.24 | 0 | 0
1551 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Sadashibpur Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00362/2024-2025 | BP-24-25-135 | 29/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.51 | 0 | 0
1552 | Bolpur Mechanical | Nalhati Sub-Division | wbsedcl quotation for amdol ws scheme | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/00710/2023-2024 |  | 28/07/2023 | 0 | WBSEDCL | 3.65 | 0 | 0
1553 | Bolpur Mechanical | Nalhati Sub-Division | wbsedcl quotation for lohapur ws scheme | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/01873/2023-2024 | BP-23-24-278 | 29/02/2024 | 0 | WBSEDCL | 3.4 | 0 | 0
1554 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR KARULIA MINI SCHEME UNDER RAJGRAM WS SCHEME | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/02255/2023-2024 | BP-23-24-321 | 18/03/2024 | 0 | WBSEDCL | 0.45 | 0 | 0
1555 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR LOKEPUR DAS PARA SCHEME UNDER RAJGRAM WS SCHEME | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/02256/2023-2024 | BP-23-24-322 | 18/03/2024 | 0 | WBSEDCL | 0.09 | 0 | 0
1556 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR ASENGA PH NO I UNDER RAJGRAM WS SCHEME | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | BILL/02257/2023-2024 | BP-23-24-323 | 18/03/2024 | 0 | WBSEDCL | 3.22 | 0 | 0
1557 | Bolpur Mechanical | Nalhati Sub-Division | Supply and installation of Voltage Correction device & other allied work for Augmentation of Laxminarayanpur water supply scheme under Bolpur Mechanical Division PHE Dte | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000004/2023-2024 | 713/Bol.MD | 19/04/2023 | 45 | QUAZI NOZRUL ISLAM | 14.45 | 0 | 0
1558 | Bolpur Mechanical | Nalhati Sub-Division | Supply and Delivery of Sub-Mersible Pump Controllers for Augmentation of Kaytha water supply scheme (Block- Nalhati - I) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000005/2024-2025 | 688./AE-III | 08/04/2024 | 21 | M/S. YOUTH ENGINEERS' ENTERPRISE | 2.98 | 0 | 100
1559 | Bolpur Mechanical | Nalhati Sub-Division | Withrawing, Lowering & Cable laying of Submersible Pumping machinery at Laxminarayanpur water supply scheme, under Bolpur Mechanical Division P.H.E. Dte. within Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000009/2023-2024 | 553/AE-III | 05/04/2023 | 20 | MONI ELECTRICAL WORKS | 2.83 | 0 | 100
1560 | Bolpur Mechanical | Nalhati Sub-Division | Supply and installation of Pumps and other electro-mechanical accessories for Augmentation of Rajgram water supply scheme under Bolpur Mechanical Division PHE Dte | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000022/2022-2023 | 421/Bol.M.D | 12/05/2022 | 45 | QUAZI NOZRUL ISLAM | 18.29 | 0 | 0
1561 | Bolpur Mechanical | Nalhati Sub-Division | OPERATION AND GUARDING OF PUMPING MACHINERY AND OTHERS AT AUGMENTATION OF BARA Zone-I WATER SUPPLY SCHEME UNDER CENTRAL MECHANICAL DIVISION P.H .E DTE. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000022/2023-2024 | 653/AE-III | 26/04/2023 | 61 | SINHA ELECTRICALS | 0.5 | 0 | 0
1562 | Bolpur Mechanical | Nalhati Sub-Division | OPERATION AND GUARDING OF PUMPING MACHINERY AND OTHERS AT AUGMENTATION OF MURARAI WATER SUPPLY SCHEME.UNDER CENTRAL MECHANICAL DIVISION P.H .E DTE. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000060/2023-2024 | 778/AE-III | 27/06/2023 | 92 | S. K. ENTERPRISE | 0.75 | 0 | 0
1563 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Bara Zone-I water supply scheme (T.W No.-I), under Bolpur Mechanical Division PHE Dte | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000226/2022-2023 | 856/Bol.MD | 15/09/2022 | 60 | SINHA ELECTRICALS | 21.35 | 0 | 100
1564 | Bolpur Mechanical | Nalhati Sub-Division | Supply & Installation of Submersible Pumping machinery at newly sunk Tubewell & others allied works at Kaitha Augmentation water supply scheme under Bolpur Mechanical Division P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000230/2022-2023 | 570/AE-III | 10/05/2022 | 20 | WEST BENGAL ENGINEERING CO. | 2.35 | 0 | 0
1565 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Murarai water supply scheme (T.W No.-I), under Bolpur Mechanical Division PHE Dte | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000301/2022-2023 | 964/Bol.MD | 13/10/2022 | 60 | S.K.ELECTRICALS | 20.95 | 0 | 60
1566 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Bhadrapur Zone-I water supply scheme (T.W No.-I), under Bolpur Mechanical Division PHE Dte | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000302/2022-2023 | 965/Bol.MD | 13/10/2022 | 60 | RAJIB COMPANY | 21.92 | 0 | 80
1567 | Bolpur Mechanical | Nalhati Sub-Division | Supply and Installation of open well submersible Pumping machinery at existing CWR for Augmentation of Lakshminarayanpur water supply scheme under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000358/2023-2024 | 1006/AE-III | 25/07/2023 | 15 | QUAZI NOZRUL ISLAM | 1.63 | 0 | 100
1568 | Bolpur Mechanical | Nalhati Sub-Division | Supply, delivery and installation of flow meter at for Augmentation of Laxminarayanpur water Supply under Bolpur Mechanical Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000403/2023-2024 | 1043/AE-III | 07/08/2023 | 15 | QUAZI NOZRUL ISLAM | 2.65 | 0 | 0
1569 | Bolpur Mechanical | Nalhati Sub-Division | Supply and delivery of Kit kat fuse, Main switch, change over, Busbar switch for Augmentation of Murarai Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000403/2024-2025 | 649/BMSD(D) | 02/09/2024 | 30 | BIRBHUM ELECTRIC WORKS | 2.42 | 0 | 100
1570 | Bolpur Mechanical | Nalhati Sub-Division | Supply and delivery of electro-mechanical accessories for Rajgram Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000426/2024-2025 | 651/BMSD(D) | 02/09/2024 | 30 | TAPAN ENTERPRISE | 1.89 | 0 | 100
1571 | Bolpur Mechanical | Nalhati Sub-Division | Supply and delivery of Submersible pump motor set and accesssories for Rajgram Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000427/2024-2025 | 662/BMSD(D) | 03/09/2024 | 30 | M/S. UTTAM KUMAR CHATTERJEE | 2.16 | 0 | 100
1572 | Bolpur Mechanical | Nalhati Sub-Division | Supply delivery ,installation of MCC Panel and allied works at High Lift Site of Murarai water supply scheme [within Augmentation of Murarai Water Supply Scheme] under Bolpur Mechanical Division PHE Dte.. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000490/2023-2024 | 2251/BOL.MD. | 13/09/2023 | 60 | M/S SAJAHAN CHOWDHURY | 11.4 | 0 | 100
1573 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories including other allied works for Augmentation of Paikar Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000491/2023-2024 | 2246/Bol.MD | 13/09/2023 | 571 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 32.14 | 0 | 70
1574 | Bolpur Mechanical | Nalhati Sub-Division | Providing electro-mechanical accessories and others for Augmentation of Murarai water supply scheme T.W. No.-II, under Bolpur Mechanical Division PHE Dte within Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000531/2022-2023 | 103/Bol.M.D | 07/02/2023 | 30 | M/S SANTI CONSTRUCTION | 12.93 | 0 | 95
1575 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Bhadrapur Zone-I water supply scheme (T.W. No.-II), under Bolpur Mechanical Division PHE Dte. within Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000532/2022-2023 | 104/Bol.MD | 07/02/2023 | 30 | M/S A.D.ENTERPRISE | 9.82 | 0 | 91
1576 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Augmentation of Lohapur water supply scheme (T.W No.-I), under Bolpur Mechanical Division PHE Dte within Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000533/2022-2023 | 105/Bol.M.D | 07/02/2023 | 60 | SHIVAM ENTERPRISE | 21.47 | 0 | 100
1577 | Bolpur Mechanical | Nalhati Sub-Division | Repairing of pump foundation and allied works at pump House under Augmentation of Bara piped water supply scheme.(Block Nalhati-II) under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000533/2023-2024 | 1076/AE-III | 21/08/2023 | 10 | SINHA ELECTRICALS | 0.28 | 0 | 0
1578 | Bolpur Mechanical | Nalhati Sub-Division | Supply, delivery and installation of servo motor operated copper wound line voltage corrector at P/H-II for Paikar water supply scheme of Murarai-II Block under Bolpur Mechanical Division, PHE | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000614/2024-2025 | 3878/BOL.MD | 20/09/2024 | 227 | RSA ENTERPRISE | 6.89 | 0 | 100
1579 | Bolpur Mechanical | Nalhati Sub-Division | Supply and installation of Pumps and other electro-mechanical accessories for Augmentation of Bara Zone-I water supply scheme (T.W. No.-II), under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000754/2022-2023 | 428/AE-III | 22/03/2023 | 20 | MASSK ENGINEERING WORKS | 3.48 | 0 | 0
1580 | Bolpur Mechanical | Nalhati Sub-Division | Supply and installation of Pumps and other electro-mechanical accessories for Augmentation of Lohapur water supply scheme (T.W. No.-II), under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000767/2022-2023 | 426/AE-III | 22/03/2023 | 20 | SUNIL RABIDAS | 4.34 | 0 | 100
1581 | Bolpur Mechanical | Nalhati Sub-Division | Supply, delivery and installation of servo motor operated copper wound line voltage corrector at Pump House No. I of Chatra (Zone-I) water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000849/2023-2024 | 553/BMSD(D) | 24/11/2023 | 30 | SINHA ELECTRICALS | 4.18 | 0 | 100
1582 | Bolpur Mechanical | Nalhati Sub-Division | Supply and installation of manual operated Motor control panel at Pump House No. II of Chatra (Zone-I) water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000860/2023-2024 | 551/BMSD(D) | 24/11/2023 | 30 | ABHISEK ENGTNEERING CONCERN | 2.05 | 0 | 100
1583 | Bolpur Mechanical | Nalhati Sub-Division | Supply and installation of manual operated Motor control panel at Pump House No. I of Chatra (Zone-II) water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000861/2023-2024 | 548/BMSD(D) | 24/11/2023 | 30 | SARKAR ELECTRICAL | 2.05 | 0 | 100
1584 | Bolpur Mechanical | Nalhati Sub-Division | Supply and installation of manual operated Motor control panel at Pump House No. II of Chatra (Zone-II) water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000862/2023-2024 | 549/BMSD(D) | 24/11/2023 | 30 | S.P. CONSTRUCTION | 2.97 | 0 | 100
1585 | Bolpur Mechanical | Nalhati Sub-Division | Supply and installation of manual operated Motor control panel at Pump House No. I of Chatra (Zone-I) water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000882/2023-2024 | 552/BMSD(D) | 24/11/2023 | 30 | UTTAM KUMAR CHATTERJEE | 2.33 | 0 | 100
1586 | Bolpur Mechanical | Nalhati Sub-Division | Operation and Guarding of Pumping Machinery and others at Augmentation of Bhadrapur Zone-I Water Supply Scheme under Bolpur Mechanical Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/000883/2022-2023 | 415/AE-III | 21/03/2023 | 91 | M/S A.D.ENTERPRISE | 0.74 | 0 | 0
1587 | Bolpur Mechanical | Nalhati Sub-Division | Supply and installation of manual operated Motor control panel and other allied works for Pump House No.III of Murarai Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/001090/2023-2024 | 018/BMSD(D) | 22/01/2024 | 30 | QUAZI NOZRUL ISLAM | 2.44 | 0 | 100
1588 | Bolpur Mechanical | Nalhati Sub-Division | Supply, delivery and installation of servo motor operated copper wound line voltage corrector and other allied works at Pump House No.III of Murarai water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/001098/2023-2024 | 019/BMSD(D) | 22/01/2024 | 30 | M/S. UTTAM KUMAR CHATTERJEE | 3.62 | 0 | 100
1589 | Bolpur Mechanical | Nalhati Sub-Division | Erection of Cable on O.H pole and other allied works at Augmentation of Lohapur water supply scheme (T.W No- II) (Block-Nalhati-II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/001114/2023-2024 | 1657/AE-III | 22/12/2023 | 7 | SUNIL RABIDAS | 0.68 | 0 | 100
1590 | Bolpur Mechanical | Nalhati Sub-Division | Replacement of power cable of distance pump of PH-I at Lohapur Water Supply Scheme (P.H.-I) (Block-Nalhati-II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | ORD/001229/2023-2024 | 510/BOL.MD | 13/03/2024 | 30 | SINHA ELECTRICALS | 9.13 | 0 | 100
1591 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL Quoation bill for Rajgram W/S Scheme | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | VCH/000445/2022-2023 | BP-2022-23-03 | 01/06/2022 | 0 | WBSEDCL | 1.58 | 0 | 0
1592 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL Quoation bill for Rajgram W/S Scheme | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | VCH/000446/2022-2023 | BP-2022-23-01 | 01/06/2022 | 0 | WBSEDCL | 10.48 | 0 | 0
1593 | Bolpur Mechanical | Nalhati Sub-Division | electric quotation bill for Aug of Bhadrapur | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | VCH/000453/2022-2023 | BP/2022-23-09 | 02/06/2022 | 0 | WBSEDCL | 1.39 | 0 | 0
1594 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL Quotation bill for Bara ws scheme | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | VCH/000573/2022-2023 | BP-2022-23-21 | 04/08/2022 | 0 | WBSEDCL | 4.02 | 0 | 0
1595 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION BILL FOR Bara WS SCHEME | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | VCH/000576/2022-2023 |  | 18/07/2022 | 0 | WBSEDCL | 4.02 | 0 | 0
1596 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR AUG.MURARAI WS SCHEME | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | VCH/000804/2022-2023 | BP-2022-23-53 | 20/09/2022 | 0 | WBSEDCL | 2.52 | 0 | 0
1597 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR AUG.MURARAI WS SCHEME | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | VCH/000805/2022-2023 | BP-2022-23-54 | 20/09/2022 | 0 | WBSEDCL | 1.35 | 0 | 0
1598 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL quotation for Lohapur PWSS WS SCHEME under BOL MD PHE DTE | AE,Assistant Engineer-III | JE1,JE2,JE3,Junior Engineer | VCH/001159/2022-2023 | BP-2022-23-63 | 03/11/2022 | 0 | WBSEDCL | 4.94 | 0 | 0
1599 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at KANIOR, KOGRAM & KUSHIPUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000596/2022-2023 | 1059/BHM | 31/03/2023 | 915 | SK ALIM | 1229.19 | 0 | 25
1600 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000049/2023-2024 | 1452/BHM | 25/04/2023 | 0 | Resource Division | 8.28 | 0 | 0
1601 | Bolpur Mechanical | Nalhati Sub-Division | QUOTATION FOR KUHSIPUR PH 2 NALHATI-I BLOCK | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00003/2024-2025 | BP-24-25-04 | 09/04/2024 | 0 | WBSEDCL | 5.3 | 0 | 0
1602 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR KUSHIPUR W/S SCHEME PH-2 (NALHATI-1) | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02465/2023-2024 |  | 27/03/2024 | 0 | WBSEDCL | 5.3 | 0 | 0
1603 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Kushipur PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000911/2023-2024 | 3540/BOL.MD | 30/11/2023 | 60 | S.G.TECHNICAL SERVICES | 27.3 | 0 | 40
1604 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000017/2023-2024 | 1436/BHM | 25/04/2023 | 0 | Resource Division | 40.75 | 0 | 0
1605 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Abdullapur Water Supply Scheme P/H-II in Paikar CCC under Bolpur Mechanical division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | BILL/00979/2024-2025 | BP-2024-25-268 | 27/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.97 | 0 | 0
1606 | Bolpur Mechanical | Nalhati Sub-Division | Supply and delivery of Submersible pump motor set for Abdullapur Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000405/2024-2025 | 653/BMSD(D) | 02/09/2024 | 30 | HINDOL ROY | 1.51 | 0 | 100
1607 | Bolpur Mechanical | Nalhati Sub-Division | Supply and delivery of Al. armoured cable, Sluice Valve, NRV for Abdullapur Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000406/2024-2025 | 654/BMSD(D) | 02/09/2024 | 30 | SATYAJIT GHOSH | 2.55 | 0 | 100
1608 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for ABDULLAPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000883/2023-2024 | 3287/Bol.MD | 29/09/2023 | 641 | MENAKA ENTERPRISE | 41.33 | 0 | 65
1609 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000085/2023-2024 | 1487/BHM | 25/04/2023 | 0 | Resource Division | 157.22 | 0 | 0
1610 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Chanchali P/H-I Water Supply Scheme, Nandigram Kalitala in Paikar CCC under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00152/2024-2025 | BP-2024-2025-79 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.5 | 0 | 0
1611 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for Chanchali Water Supply Scheme P/H-II in Paikar CCC under Bolpur Mechanical division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00826/2024-2025 | BP-24-25-180 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.04 | 0 | 0
1612 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for CHANCHALI piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000532/2023-2024 | 2173/Bol.MD | 01/09/2023 | 608 | M/S. SREEJIT ENTERPRISE | 30.68 | 0 | 70
1613 | Birbhum Division | Birbhum Division | Road restoration work at different villages under implementation of Mini Piped Water Supply Scheme within Bolpur Sriniketan Block having less than 100 Households under Birbhum Division PHE Dte. | AE,Assistant Engineer (HQ) | JE1,Junior Engineer | ORD/000246/2025-2026 | 2209/BHM | 26/08/2025 | 90 | SOURAV MONDAL | 21.17 | 0 | 0
1614 | Birbhum Division | Birbhum Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer (HQ) | JE1,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
1615 | Birbhum Division | Nalhati Sub-Division | Extension of pipeline of different left out habitations including FHTC along with 1 no. Pump House as boosting of water supply of Amdol water supply scheme under Nalhati Sub-Division, within Birbhum Division PHE Dte (Sl. No.7) | AE | JE3 | ORD/000367/2022-2023 | 2780/BHM | 14/12/2022 | 900 | KAMIRUL SK AND CO | 211.6 | 0 | 75
1616 | Birbhum Division | Birbhum Sadar Sub-Division | Road crossing, repairing & restoration of damage pipe lines & PCC roads, sluice valve chambers including all allied works for Paikpara Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000046/2025-2026 | 1510/BHM | 23/05/2025 | 90 | SHREE J.M. CONSTRUCTION | 8.94 | 0 | 0
1617 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at NETURI, PAIKPARA & PAKURIA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000256/2023-2024 | 3441/BHM | 03/08/2023 | 940 | SHREE J.M. CONSTRUCTION | 1236.08 | 0 | 54
1618 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000144/2023-2024 | 1587/BHM | 26/04/2023 | 0 | Resource Division | 8.06 | 0 | 0
1619 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Paikpara & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000441/2023-2024 | 2100/Bol.MD | 22/08/2023 | 588 | SATYAJIT GHOSH | 27.98 | 0 | 70
1620 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply & Installation of 20kVA Votage Correction Devices at Paikpara water supply scheme (P/H-1 & P/H-II) (Block- Nalhati - I) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000985/2024-2025 | 2029./AE-III | 19/12/2024 | 21 | BIRBHUM ELECTRIC WORKS | 4.97 | 0 | 100
1621 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at DERPUR, KURUMSAHA & MATIARA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000056/2023-2024 | 1245/BHM | 17/04/2023 | 1074 | BRAHMA CONSTRUCTION COMPANY | 978.83 | 0 | 65
1622 | Birbhum Division | Birbhum Sadar Sub-Division | Repairing of Pump House & construction of drain under Matiara Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000221/2025-2026 | 2141/BHM | 19/08/2025 | 90 | BRAHMA CONSTRUCTION COMPANY | 17.25 | 0 | 0
1623 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000052/2022-2023 | 1365/BHM | 24/04/2023 | 0 | Resource Division | 12.93 | 0 | 0
1624 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Matiara PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/00174/2024-2025 | BP-24-25-90 | 19/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.48 | 0 | 0
1625 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Matiara & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000420/2023-2024 | 2091/Bol.MD | 22/08/2023 | 754 | CINZANO | 27.89 | 0 | 50
1626 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply delivery of voltage correction device & laying of cable through underground trench at head work site of Matiara PWSS in the district of Birbhum, under P.H.E. Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000602/2024-2025 | 3872/BOL.MD | 19/09/2024 | 30 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 4.35 | 0 | 0
1627 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at ABHIRAMPUR, BEHIRA, SAMSA & UTTAR BANGAON and its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000082/2023-2024 | 1437/BHM | 25/04/2023 | 820 | ASHOK KUMAR GHOSH | 1446.74 | 0 | 55
1628 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE2,Junior Engineer | RTOR000054/2022-2023 | 1369/BHM | 24/04/2023 | 0 | Resource Division | 37.66 | 0 | 0
1629 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR UTTAR BANGAON P H NO.I WS SCHEME | AE,Assistant Engineer | JE2,Junior Engineer | BILL/01473/2023-2024 | BP-23-24-199 | 12/12/2023 | 0 | WBSEDCL | 7.29 | 0 | 0
1630 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR UTTAR BANGAOUN WS SCHEME | AE,Assistant Engineer | JE2,Junior Engineer | BILL/02140/2023-2024 | BP-23-24-303 | 15/03/2024 | 0 | WBSEDCL | 6.69 | 0 | 0
1631 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Uttar Bangaon & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000388/2023-2024 | 1927/Bol.MD | 11/08/2023 | 412 | P. K. ENGINEERING | 27.89 | 0 | 90
1632 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at BHALIAN, BANGJITA & BIRSINGHA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000047/2023-2024 | 1258/BHM | 17/04/2023 | 806 | NAUTANDAS AND CO | 1377.28 | 0 | 35
1633 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE2,Junior Engineer | RTOR000055/2022-2023 | 1379/BHM | 24/04/2023 | 0 | Resource Division | 41.06 | 0 | 0
1634 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUIOTATION FOR BHALIAN PH NO-I | AE,Assistant Engineer | JE2,Junior Engineer | BILL/01848/2023-2024 | BP-23-24-274 | 15/02/2024 | 0 | WBSEDCL | 0.96 | 0 | 0
1635 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR BHALIAN PWSS PUMP HOUSE NO-II | AE,Assistant Engineer | JE2,Junior Engineer | BILL/02131/2023-2024 | BP-2023-24-294 | 20/03/2024 | 0 | WBSEDCL | 4.72 | 0 | 0
1636 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Bhalian & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000416/2023-2024 | 2088/Bol.MD | 22/08/2023 | 679 | MENAKA ENTERPRISE | 28.76 | 0 | 80
1637 | Central Drilling | Birbhum Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X 200mm X 150Mtrs. depth) by utilising Departmental Machineries for Bhalian W/S Scheme (T/W-II) Sainthia Block under Birbum District, Central Drilling Division, PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000495/2022-2023 | 1131/CDD | 04/11/2022 | 30 | C.M. ENTERPRISE | 9.04 | 0 | 100
1638 | Birbhum Division | Rampurhat Sub-Division | Sinking of 250 X 150 mm Dia tubewell Drilling by Direct Rotary method (Two Nos ), Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 150 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Tilai & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000132/2024-2025 | 2316/BHM | 21/08/2024 | 365 | S D CONSTRUCTION | 349.88 | 0 | 15
1639 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000040/2024-2025 | 2483/BHM | 03/09/2024 | 0 | Resource Division | 7.68 | 0 | 0
1640 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000101/2023-2024 | 1531/BHM | 26/04/2023 | 0 | Resource Division | 13.56 | 0 | 0
1641 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Tilai & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000923/2023-2024 | 3529/Bol.MD | 29/11/2023 | 60 | MITRA ENTERPRISE | 26.05 | 0 | 30
1642 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at CHINPAI, LOBA & PARATPUR and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000265/2023-2024 | 3476/BHM | 08/08/2023 | 816 | B RAI CONSTRUCTION COMPANY | 2497.19 | 0 | 45
1643 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000073/2022-2023 | 1401/BHM | 24/04/2023 | 0 | Resource Division | 70.19 | 0 | 0
1644 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000187/2023-2024 | 3279/BHM | 27/07/2023 | 0 | Resource Division | 2.05 | 0 | 0
1645 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Paratpur & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000937/2023-2024 | 3394/Bol.MD | 17/10/2023 | 90 | EASTERN INDIA SALES & SERVICE | 79.72 | 0 | 0
1646 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000402/2023-2024 | 4139/BHM | 18/10/2023 | 896 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 0 | 60
1647 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | RTOR000088/2022-2023 | 1360/BHM | 24/04/2023 | 0 | Resource Division | 16.65 | 0 | 0
1648 | Bolpur Mechanical | Bolpur Sub-Division | NEW SERVICE CONNECTION AT KENDRADANGAL WATER SUPPLY SCHEME. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | BILL/00437/2024-2025 | BP-2024-25-140 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.31 | 0 | 0
1649 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1650 | Birbhum Division | Birbhum Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 300 CuM capacity O.H.R. Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to SRIKANTAPUR water supply scheme at & its adjoining mouzas water supply scheme within Md. Bazar Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000103/2024-2025 | 2112/BHM | 29/07/2024 | 365 | M/S R B ENTERPRISE | 571.1 | 0 | 0
1651 | Birbhum Division | Birbhum Division | Sinking of 3 nos. 200mm X 165mm dia x 300 mtr. deep Tube Well by Rig boring method including connecting pipeline and all other allied works under Srikantapur Piped Water Supply Scheme under Birbhum Division, P.H.E. Dte. (2nd Call) | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000577/2024-2025 | 437/BHM | 10/02/2025 | 60 | M/S R B ENTERPRISE | 20.14 | 0 | 0
1652 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | RTOR000025/2024-2025 | 2448/BHM | 30/08/2024 | 0 | Resource Division | 13.19 | 0 | 0
1653 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | RTOR000140/2023-2024 | 1578/BHM | 26/04/2023 | 0 | Resource Division | 26.45 | 0 | 0
1654 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for SRIKANTAPUR piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000583/2023-2024 | 3387/Bol.MD | 16/10/2023 | 60 | SARKAR ELECTRICAL | 28.28 | 0 | 20
1655 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Palsa & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000090/2023-2024 | 1639/BHM | 02/05/2023 | 1214 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 290.19 | 0 | 30
1656 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000044/2023-2024 | 1441/BHM | 25/04/2023 | 0 | Resource Division | 11.75 | 0 | 0
1657 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION MONEY FOR PALSA P H NO.II WS SCHEME | AE,Assistant Engineer | JE1,Junior Engineer | BILL/01823/2023-2024 | BP-2023-24-258 | 06/02/2024 | 0 | WBSEDCL | 3.04 | 0 | 0
1658 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR PALSA PUMP HOUSE NO I | AE,Assistant Engineer | JE1,Junior Engineer | BILL/01825/2023-2024 | BP-23-24-257 | 06/02/2024 | 0 | WBSEDCL | 3.06 | 0 | 0
1659 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for PALSA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000903/2023-2024 | 3298/Bol.MD | 29/09/2023 | 338 | CINZANO | 27.21 | 0 | 75
1660 | Birbhum Division | Bolpur Sub-Division | Construction of 200 Cum capacity O.H.R. with soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, laying of Rising Main, Distribution System with FHTC and different works related to BENGA CHATRA PIPED WATER SUPPLY SCHEME (TSM/015476) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000147/2024-2025 | 2576/BHM | 09/09/2024 | 365 | M/S R B ENTERPRISE | 367.97 | 0 | 0
1661 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BENGACHATRA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000641/2022-2023 | 156/BSD | 20/04/2022 | 90 | RADIANT | 4.36 | 0 | 100
1662 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000052/2024-2025 | 3258/BHM | 02/12/2024 | 0 | Resource Division | 9.4 | 0 | 0
1663 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000066/2023-2024 | 1523/BHM | 26/04/2023 | 0 | Resource Division | 33.24 | 0 | 0
1664 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Benga Chatra & Ramkrishnapur Water supply Scheme, Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000969/2024-2025 | 4538/BOL.MD | 20/12/2024 | 120 | MENAKA ENTERPRISE | 73.34 | 0 | 50
1665 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1666 | Birbhum Division | Nalhati Sub-Division | Extension of pipeline (DI & HDPE) with FHTC, Restoration of Roads including Augur boring along with supply of sluice valve with construction of valve chamber for Prasadpur piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000194/2025-2026 | 2144/BHM | 19/08/2025 | 90 | APORUPA CONSTRUCTION | 46.38 | 0 | 0
1667 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at NAWAPARA & PRASADPUR and its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000207/2023-2024 | 3257/BHM | 26/07/2023 | 275 | MANASH GHOSH | 866.09 | 0 | 5
1668 | Birbhum Division | Nalhati Sub-Division | Preparation and submission of DPR for (Prasadpur) Water Supply Scheme under Nalhati-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000759/2022-2023 | 232/AE/NSD | 21/04/2022 | 45 | MS SOBHA AND CO | 4.81 | 0 | 100
1669 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000110/2023-2024 | 1509/BHM | 26/04/2023 | 0 | Resource Division | 9.92 | 0 | 0
1670 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Prasadpur PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000464/2023-2024 | 2138/Bol.MD | 25/08/2023 | 615 | QUAZI NOZRUL ISLAM | 44.39 | 0 | 40
1671 | Bolpur Mechanical | Nalhati Sub-Division | Supply and Delivery of Open well Submersible Pumping Machineries and allied accessories for Prasadpur PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000524/2024-2025 | 3783/BOL.MD | 12/09/2024 | 30 | M/S. UTTAM KUMAR CHATTERJEE | 28.98 | 0 | 100
1672 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at SHANKARPUR & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte.150 | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000021/2023-2024 | 1094/BHM | 06/04/2023 | 909 | SYED GOLAM ZILANI | 353.43 | 0 | 30
1673 | Birbhum Division | Birbhum Sadar Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
1674 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000069/2023-2024 | 1586/BHM | 26/04/2023 | 0 | Resource Division | 111.93 | 0 | 0
1675 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR SHANKARPUR WATER SUPPLY SCHEME | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/01832/2023-2024 | BP-23-24-259 | 06/02/2024 | 0 | WBSEDCL | 21.4 | 0 | 0
1676 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Shankarpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000907/2023-2024 | 3551/Bol.MD | 01/12/2023 | 90 | QUAZI NOZRUL ISLAM | 85.3 | 0 | 20
1677 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Modification works on Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Shankarpur PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/001238/2023-2024 | 536/BOL.MD | 14/03/2024 | 60 | DEY ENTERPRISE | 5.77 | 0 | 0
1678 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Modification works on Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Shankarpur PWSS under Rajnagar Block in the Dist of Birbhum under Bolpur Mechanical Division,PHEDte | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/001239/2023-2024 | 535/BOL.MD | 14/03/2024 | 60 | TULIP ENTERPRISE | 5.41 | 0 | 30
1679 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Sankarpur PWSS under Rajnagar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/001240/2023-2024 | 534/BOL.MD | 14/03/2024 | 449 | SINHA ELECTRICALS | 7.8 | 0 | 100
1680 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at ALBANDHA, BERGRAM & BIDYADHARPUR Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000387/2023-2024 | 4146/BHM | 19/10/2023 | 805 | AMAL DUTTA ROY | 1648.21 | 0 | 12
1681 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | RTOR000084/2022-2023 | 1356/BHM | 24/04/2023 | 0 | Resource Division | 16.74 | 0 | 0
1682 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | RTOR000127/2023-2024 | 1538/BHM | 26/04/2023 | 0 | Resource Division | 16.74 | 0 | 0
1683 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1684 | Birbhum Division | Nalhati Sub-Division | Jack pushing including Augur boring for extension of pipeline (DI & HDPE ) including supply of sluice valve with construction of valve chamber and restoration of Roads, pucca drain for KANIOR piped Water Supply Scheme (Nalhati-I Block) under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000447/2024-2025 | 3536/BHM | 23/12/2024 | 58 | SK ALIM | 73.24 | 0 | 95
1685 | Birbhum Division | Nalhati Sub-Division | Hiring of SWIFT DZIRE (diesel) registered luxury car for the office of the Assistant Engineer, Nalhati Sub-Division P.H.E. Dte. for 24 hours service including Driver and the cost of fuel & lubricants as per terms & condition with effect from 01.10.2024 to 31.12.2024.Hiring charges of Ambassador Car (Diesel) Fuel :- Diesel : 1 liter for every 12 KM. Lubricants : Mobil: 1 liter for every 500 KM. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000497/2024-2025 | 312/NSD | 30/09/2024 | 92 | JOY CHAND MAL | 0.43 | 0 | 0
1686 | Birbhum Division | Nalhati Sub-Division | Hiring of SWIFT DZIRE (diesel) registered luxury car for the office of the Assistant Engineer, Nalhati Sub-Division P.H.E. Dte. for 24 hours service including Driver and the cost of fuel & lubricants as per terms & condition with effect from 01.01.2025 to 31.01.2025.Hiring charges of Ambassador Car (Diesel) Fuel :- Diesel : 1 liter for every 12 KM. Lubricants : Mobil: 1 liter for every 500 KM. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000536/2024-2025 | 429/NSD | 31/12/2024 | 31 | JOY CHAND MAL | 0.15 | 0 | 0
1687 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at KANIOR, KOGRAM & KUSHIPUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000596/2022-2023 | 1059/BHM | 31/03/2023 | 915 | SK ALIM | 1229.19 | 0 | 25
1688 | Birbhum Division | Nalhati Sub-Division | Hiring of Swift Dizer (Diesel) or equivalent luxury car for office of the Assistant Engineer, Nalhati Sub-Division under Birbhum Division, PHE Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & with effect from 01.02.2025 to 31.07.2025 | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000598/2024-2025 | 40/NSD | 31/01/2025 | 181 | JOY CHAND MAL | 0.85 | 0 | 0
1689 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000014/2023-2024 | 1430/BHM | 25/04/2023 | 0 | Resource Division | 14.24 | 0 | 0
1690 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR KANIOR | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01574/2023-2024 | BP-23-24-209 | 04/01/2024 | 0 | WBSEDCL | 3.26 | 0 | 0
1691 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR KANIOR | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01575/2023-2024 | BP-23-24-208 | 04/01/2024 | 0 | WBSEDCL | 0.44 | 0 | 0
1692 | Bolpur Mechanical | Nalhati Sub-Division | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Kanior PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000002/2024-2025 | 685./AE-III | 08/04/2024 | 14 | GOENKA ENTERPRISE | 1.58 | 0 | 100
1693 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Kanior PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000915/2023-2024 | 3542/BOL.MD | 30/11/2023 | 60 | GOENKA ENTERPRISE | 30.69 | 0 | 60
1694 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at PATALPUR & its adjoining mouzas water supply scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000350/2023-2024 | 3949/BHM | 03/10/2023 | 270 | RAJKUMAR DAS | 89.99 | 0 | 30
1695 | Birbhum Division | Birbhum Sadar Sub-Division | Sinking of 2 nos. (Two) 200 mm dia x 30 mtr deep Tubewell for Patalpur & its adjoining mouzas water supply scheme within Rajnagar Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000416/2023-2024 | 4339/BHM | 23/11/2023 | 30 | RAJKUMAR DAS | 2.74 | 0 | 100
1696 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at patalpur water supply scheme under Bolpur Mechanical Division, P.H.E Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | BILL/01017/2024-2025 | BP-2024-25-274 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.68 | 0 | 0
1697 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Patalpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000908/2023-2024 | 3552/Bol.MD | 01/12/2023 | 90 | A. G. ENTERPRISE | 55.59 | 0 | 0
1698 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
1699 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
1700 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Bhadulia & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000675/2022-2023 | 99/BSSD | 14/06/2022 | 45 | RADIANT | 2.71 | 0 | 100
1701 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000237/2023-2024 | 438/BHM | 01/02/2024 | 0 | Resource Division | 131.6 | 0 | 0
1702 | Birbhum Division | Bolpur Sub-Division | Construction of 250 & 150 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main, Distribution System with FHTC including different works related to SANTOSHPUR / NAWADA PALANDI /PAPURI / SAJNOR / RAYEN PIPED WATER SUPPLY SCHEME (5 Nos Scheme) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division PHE DTE. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000085/2024-2025 | 1951/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2322.64 | 0 | 5
1703 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for SAJNOR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000740/2022-2023 | 279/BSD | 21/07/2022 | 90 | RADIANT | 4.94 | 0 | 100
1704 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000006/2024-2025 | 2394/BHM | 27/08/2024 | 0 | Resource Division | 12.08 | 0 | 0
1705 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000053/2023-2024 | 1456/BHM | 25/04/2023 | 0 | Resource Division | 16.14 | 0 | 0
1706 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1707 | Birbhum Division | Rampurhat Sub-Division | Different works related to Water Supply Scheme at PRAYAGPUR & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000276/2023-2024 | 3596/BHM | 21/08/2023 | 813 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 516.3 | 0 | 55
1708 | Birbhum Division | Rampurhat Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
1709 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (PRAYAGPUR) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000842/2022-2023 | 333/RSD | 08/09/2022 | 45 | ENVIROTECH SOLUTIONS | 3.22 | 0 | 100
1710 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (PRAYAGPUR) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000843/2022-2023 | 437/RSD | 25/11/2022 | 45 | ENVIROTECH SOLUTIONS | 2.5 | 0 | 100
1711 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000024/2023-2024 | 1444/BHM | 25/04/2023 | 0 | Resource Division | 36.79 | 0 | 0
1712 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000215/2023-2024 | 231/BHM | 24/01/2024 | 0 | Resource Division | 5.61 | 0 | 0
1713 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation money for new service connection at Prayagpur PWSS P/H- III under Mayureswar CCC | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00822/2024-2025 | BP-24-25-183 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0
1714 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Prayagpur Piped Water Supply Scheme, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000509/2024-2025 | 3756/Bol.MD | 12/09/2024 | 30 | M/S P.P ELECTRICALS | 25.25 | 0 | 0
1715 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Prayagpur PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000839/2023-2024 | 3278/Bol.MD | 29/09/2023 | 825 | ORIENTAL ENGINEERING CO. | 55.59 | 0 | 50
1716 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Prayagpur PWSS under Mayureswar - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/001244/2023-2024 | 529/BOL.MD | 14/03/2024 | 60 | SWAPAN ENTERPRISE | 7.62 | 0 | 0
1717 | Birbhum Division | Rampurhat Sub-Division | Sinking of 250 X 150 mm Dia (through) and 180 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Ninga & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUMDivision, PHE Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000320/2024-2025 | 3116/BHM | 13/11/2024 | 365 | M/S DATTA ENTERPRISE | 375.28 | 0 | 20
1718 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (NINGA) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000786/2022-2023 | 289/RSD | 31/08/2022 | 45 | ECO CARE | 2.4 | 0 | 100
1719 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (NINGA) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000797/2022-2023 | 373/RSD | 22/09/2022 | 45 | ECO CARE | 2.91 | 0 | 100
1720 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000047/2024-2025 | 3261/BHM | 02/12/2024 | 0 | Resource Division | 12.4 | 0 | 0
1721 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000082/2023-2024 | 1550/BHM | 26/04/2023 | 0 | Resource Division | 58.2 | 0 | 0
1722 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Ninga PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000477/2023-2024 | 2230/Bol.MD | 12/09/2023 | 60 | DEY ENTERPRISE | 44.43 | 0 | 0
1723 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Ninga PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/001252/2023-2024 | 527/BOL.MD | 14/03/2024 | 60 | DIPALI CONSTRUCTION | 7.61 | 0 | 0
1724 | Birbhum Division | Nalhati Sub-Division | Sinking of 200 X 200 mm Dia (through) and 125 m deep tubewell, 02 nos, 5.90 m X 4.10 m Chlorine room with sanitary arrangements, 300 CuM OHR & 150 cum OHR, 200 Cum CWR, Boundary wall with Gate, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Bautia & its adjoining mouzas water supply scheme within Nalhati-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000191/2024-2025 | 2772/BHM | 30/09/2024 | 365 | M/S GHOSH AND CO. | 887.39 | 0 | 2
1725 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000048/2024-2025 | 3262/BHM | 02/12/2024 | 0 | Resource Division | 21.17 | 0 | 0
1726 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000115/2023-2024 | 1505/BHM | 25/04/2023 | 0 | Resource Division | 433.77 | 0 | 0
1727 | Bolpur Mechanical | Nalhati Sub-Division | Supply & Installation of High lift pumping machineries and other allied works for Bautia piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000925/2023-2024 | 3558/BOL.MD | 04/12/2023 | 90 | R. N. S. TRADING | 91.5 | 0 | 0
1728 | Bolpur Mechanical | Nalhati Sub-Division | Supply & Installation of Low lift pumping machineries and other allied works for Bautia piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000927/2023-2024 | 3559/BOL.MD | 04/12/2023 | 484 | M/S. UTTAM KUMAR CHATTERJEE | 24.37 | 0 | 40
1729 | Birbhum Division | Bolpur Sub-Division | Construction 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements.Laying of Rising Main,Distribution system,including FHTC and different works related to water supply scheme at GOPINATHPUR PIPED WATER SUPPLY SCHEME (TSM/015544) within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 | ORD/000111/2024-2025 | 2165/BHM | 05/08/2024 | 365 | KINGS & CO. | 396.77 | 0 | 10
1730 | Birbhum Division | Bolpur Sub-Division | Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Superstructure part as per Departmental Drawing), pipe connection and cost of pipes & specials with necessary soil investigation with foundation design as per soil test report for GOPINATHPUR PIPED WATER SUPPLY SCHEMEwithin ILLAMBAZAR Block under BIRBHUM Division, PHE Dte. | Assistant Engineer | JE1 | ORD/000262/2025-2026 | 2350/BHM | 10/09/2025 | 365 | SYED KHORSED ALAM | 85.64 | 0 | 0
1731 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for GOPINATHPUR Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer | JE1 | ORD/000642/2022-2023 | 137/BSD | 07/04/2022 | 90 | M/S R DUTTA & CO. | 3.93 | 0 | 100
1732 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE1 | RTOR000022/2024-2025 | 2445/BHM | 30/08/2024 | 0 | Resource Division | 10.06 | 0 | 0
1733 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE1 | RTOR000119/2023-2024 | 1528/BHM | 26/04/2023 | 0 | Resource Division | 30.37 | 0 | 0
1734 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer | JE1 | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1735 | Birbhum Division | Bolpur Sub-Division | "Construction of 200CuM. capacity O.H.R. with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main ,Distribution Systemwith FHTC including different works related to MADDA PIPED WATER SUPPLY SCHEME (TSM/016100) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte." | Assistant Engineer | JE2 | ORD/000093/2024-2025 | 2106/BHM | 29/07/2024 | 365 | M/S NIBHAS SINHA | 434.39 | 0 | 0
1736 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for MADDA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer | JE2 | ORD/001141/2021-2022 | 122/BSD | 31/03/2022 | 90 | RADIANT | 4 | 0 | 100
1737 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE2 | RTOR000017/2024-2025 | 2391/BHM | 27/08/2024 | 0 | Resource Division | 8.56 | 0 | 0
1738 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Madda WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer | JE2 | ORD/000972/2024-2025 | 4525/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.08 | 0 | 0
1739 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer | JE2 | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1740 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at AHAMADPUR & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte. 150 | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000112/2023-2024 | 1877/BHM | 31/05/2023 | 840 | B.B.C ENTERPRISE | 411.79 | 0 | 75
1741 | Birbhum Division | Birbhum Sadar Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
1742 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000151/2023-2024 | 1591/BHM | 26/04/2023 | 0 | Resource Division | 182.11 | 0 | 0
1743 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR AHAMADPUR WATER SUPPLY SCHEME | AE,Assistant Engineer-III | JE,Junior Engineer | BILL/01831/2023-2024 | BP-23-24-261 | 06/02/2024 | 0 | WBSEDCL | 15.58 | 0 | 0
1744 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR AHMADPUR WS SCHEME | AE,Assistant Engineer-III | JE,Junior Engineer | BILL/01834/2023-2024 | BP-23-24-250 | 06/02/2024 | 0 | WBSEDCL | 0.26 | 0 | 0
1745 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Ahamadpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000527/2023-2024 | 2157/Bol.MD | 29/08/2023 | 828 | SINHA ELECTRICALS | 92.12 | 0 | 70
1746 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply and delivery of outdoor type pump controller unit for Ahamedpur and others PWSS under Rajnagar block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/001221/2023-2024 | 406/Bol.MD | 07/03/2024 | 45 | M/S. UTTAM KUMAR CHATTERJEE | 20.06 | 0 | 100
1747 | Birbhum Division | Birbhum Division | Different works for SIUR & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000083/2023-2024 | 1440/BHM | 25/04/2023 | 1131 | MUKHERJEE CONSTRUCTION | 777.14 | 0 | 15
1748 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | RTOR000039/2022-2023 | 1384/BHM | 24/04/2023 | 0 | Resource Division | 193.96 | 0 | 0
1749 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | RTOR000188/2023-2024 | 3280/BHM | 27/07/2023 | 0 | Resource Division | 2.56 | 0 | 0
1750 | Bolpur Mechanical | Birbhum Division | Providing electro-mechanical accessories and others for Siur & Adjoining Moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000771/2022-2023 | 306/Bol.MD | 23/03/2023 | 366 | M. S. ENTERPRISE | 90.15 | 0 | 0
1751 | Bolpur Mechanical | Birbhum Division | Providing electro mechanical accessories and others for Siur and Adjoining Mouzas Water Supply Scheme under Bolpur Mechanical Division, PHE Dte | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000783/2022-2023 | 318/BOL.M.D | 27/03/2023 | 366 | M. S. ENTERPRISE | 90.15 | 0 | 60
1752 | Birbhum Division | Rampurhat Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at HANSAN & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000114/2024-2025 | 2179/BHM | 06/08/2024 | 365 | RADIANT | 490.17 | 0 | 30
1753 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (HANSAN) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000790/2022-2023 | 326/RSD | 08/09/2022 | 45 | ECO CARE | 3.05 | 0 | 100
1754 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (HANSAN) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000799/2022-2023 | 426/RSD | 04/11/2022 | 45 | ECO CARE | 2.91 | 0 | 100
1755 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000028/2023-2024 | 1520/BHM | 26/04/2023 | 0 | Resource Division | 25.75 | 0 | 0
1756 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000042/2024-2025 | 2485/BHM | 03/09/2024 | 0 | Resource Division | 11.9 | 0 | 0
1757 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of Sub-Mersible Pump Controllers for Hasan water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000402/2024-2025 | 1295./AE-III | 27/08/2024 | 65 | SWAPAN BANERJEE | 2.84 | 0 | 100
1758 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Hansan PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000476/2023-2024 | 2229/Bol.MD | 12/09/2023 | 60 | P. K. ENGINEERING | 44.33 | 0 | 0
1759 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of Main Swich, Change over switch,Busbar for Hasan water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. " | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000529/2024-2025 | 1454./AE-III | 09/09/2024 | 7 | SATYAJIT GHOSH | 0 | 0 | 0
1760 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of Main Swich, Change over switch,Busbar for Hasan water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. " | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000548/2024-2025 | 1454./AE-III | 09/09/2024 | 7 | SATYAJIT GHOSH | 2.83 | 0 | 100
1761 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Hansan PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/001243/2023-2024 | 522/BOL.MD | 14/03/2024 | 60 | KAMAKHYA ENTERPRISE | 7.62 | 0 | 0
1762 | Birbhum Division | Bolpur Sub-Division | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000084/2024-2025 | 1948/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0
1763 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for FARIDPUR Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000654/2022-2023 | 146/BSD | 12/04/2022 | 180 | APEX ENGINEERING | 4.22 | 0 | 100
1764 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000009/2024-2025 | 2397/BHM | 27/08/2024 | 0 | Resource Division | 8.9 | 0 | 0
1765 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000152/2023-2024 | 1590/BHM | 26/04/2023 | 0 | Resource Division | 65.61 | 0 | 0
1766 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Faridpur PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001120/2024-2025 | 327/BOL.MD | 19/02/2025 | 120 | OSMAN SEKH | 76.33 | 0 | 0
1767 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1768 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at RAGHABPUR PIPED WATER SUPPLY SCHEME (TSM/016570) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000566/2022-2023 | 899/BHM | 22/03/2023 | 275 | M/S.KHAN CHOWDHURY BROTHERS AND CO. | 210.82 | 0 | 0
1769 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for RAGHABPUR Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001143/2021-2022 | 123/BSD | 31/03/2022 | 180 | APEX ENGINEERING | 2.11 | 0 | 100
1770 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000153/2023-2024 | 1594/BHM | 26/04/2023 | 0 | Resource Division | 20.44 | 0 | 0
1771 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000160/2023-2024 | 1628/BHM | 28/04/2023 | 0 | Resource Division | 20.44 | 0 | 0
1772 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1773 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
1774 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
1775 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Penchalia & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000679/2022-2023 | 126/BSSD | 12/07/2022 | 45 | RADIANT | 2.43 | 0 | 100
1776 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000248/2023-2024 | 429/BHM | 01/02/2024 | 0 | Resource Division | 87.68 | 0 | 0
1777 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
1778 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
1779 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Sagarbanga & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000680/2022-2023 | 131/BSSD | 14/07/2022 | 45 | RADIANT | 1.23 | 0 | 100
1780 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000250/2023-2024 | 422/BHM | 01/02/2024 | 0 | Resource Division | 15.47 | 0 | 0
1781 | Birbhum Division | Rampurhat Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 200 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at CHHORA & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000098/2024-2025 | 2116/BHM | 29/07/2024 | 611 | ASIM KUMAR MONDAL | 400.06 | 0 | 30
1782 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000028/2024-2025 | 2451/BHM | 30/08/2024 | 0 | Resource Division | 11.19 | 0 | 0
1783 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000146/2023-2024 | 1593/BHM | 26/04/2023 | 0 | Resource Division | 13.6 | 0 | 0
1784 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Chhora & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000924/2023-2024 | 3530/Bol.MD | 29/11/2023 | 623 | S.K.ELECTRICALS | 27.63 | 0 | 70
1785 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
1786 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
1787 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Aliat & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000683/2022-2023 | 142/BSSD | 21/07/2022 | 45 | RADIANT | 2.37 | 0 | 100
1788 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000232/2023-2024 | 440/BHM | 01/02/2024 | 0 | Resource Division | 109.46 | 0 | 0
1789 | Birbhum Division | Central Mechanical Sub-DivisionIII | Sinking of 200 mm dia all through and 150 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements,, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I and II and Providing functional household tap connection related to water supply scheme at Kashtagara and Adjoining Moujas Piped Water Supply Scheme within RAMPURHAT-I Block underBIRBHUM Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000365/2024-2025 | 3141/BHM | 19/11/2024 | 365 | M/S DIPAK ENTERPRISE | 895.59 | 0 | 0
1790 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000046/2024-2025 | 3263/BHM | 02/12/2024 | 0 | Resource Division | 26.95 | 0 | 0
1791 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000145/2023-2024 | 1589/BHM | 26/04/2023 | 0 | Resource Division | 13.11 | 0 | 0
1792 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing Electro-mechanical accessories and others for Kashtagara Zone - II PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000914/2023-2024 | 3523/Bol.MD | 29/11/2023 | 60 | M/S. DILIP MITRA | 27.61 | 0 | 0
1793 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing Electro-mechanical accessories and others for Kashtagara Zone - I PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000916/2023-2024 | 3524/Bol.MD | 29/11/2023 | 60 | WEST BENGAL ENGINEERING CO. | 27.68 | 0 | 0
1794 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Kastagara PWSS under Rampurhat - I Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001247/2023-2024 | 524/BOL.MD | 14/03/2024 | 60 | S.G.TECHNICAL SERVICES | 7.61 | 0 | 40
1795 | Birbhum Division | Rampurhat Sub-Division | Construction of 200 CuM OHR (ZONE-I) & 350 CuM OHR (ZONE-II) with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, Rising main, Laying distribution( Z-I & II), Boundary wall,Land development,road restoration and Providing functional household tap connection and different works related to KUSUMBA & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. |  | JE2 | ORD/000122/2024-2025 | 2225/BHM | 12/08/2024 | 729 | SUNIL RABI DAS | 800.42 | 0 | 20
1796 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division |  | JE2 | RTOR000035/2024-2025 | 2481/BHM | 03/09/2024 | 0 | Resource Division | 24.98 | 0 | 0
1797 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division |  | JE2 | RTOR000071/2023-2024 | 1466/BHM | 25/04/2023 | 0 | Resource Division | 13.68 | 0 | 0
1798 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Kusumba Zone - II PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. |  | JE2 | ORD/000410/2023-2024 | 2101/Bol.MD | 22/08/2023 | 598 | MENAKA ENTERPRISE | 28.5 | 0 | 41
1799 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Kusumba Zone - I PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. |  | JE2 | ORD/000912/2023-2024 | 3522/Bol.MD | 29/11/2023 | 60 | PRADIP KUMAR DHABAL | 27.77 | 0 | 30
1800 | Birbhum Division | Rampurhat Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, Boundary wall, Land development, Laying distribution, road restoration and Providing functional household tap connection related to AUGMENTATION OF MARGRAM & Its adjoining Mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000091/2024-2025 | 2006/BHM | 12/07/2024 | 546 | PROJECT INDIA , 38/A, KHELAT BABU LANE, KOLKATA - 700037. | 692.88 | 0 | 35
1801 | Birbhum Division | Rampurhat Sub-Division | Balance Laying of rising main along with road restoration other allied works for AUGMENTATION of MARGRAM & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000105/2025-2026 | 1750/BHM | 02/07/2025 | 90 | PROJECT INDIA | 391.67 | 0 | 35
1802 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order For Supply and delivery of Sluice Valve for Augmentation of Margram W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000110/2023-2024 | 1632/BHM | 28/04/2023 | 30 | MAKALI ENGINEERING CORPORATION | 9.57 | 0 | 100
1803 | Birbhum Division | Rampurhat Sub-Division | Renovation of Existing Switch Room (Old head work site) size 5.40 mtr. X 3.65 mtr with Sanitary and water supply arrangement at Margram Piped Water Supply Scheme under Rampurhat Sub-Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000230/2023-2024 | 201/RSD | 28/07/2023 | 15 | TAPAN ENTERPRISE | 0.97 | 0 | 100
1804 | Birbhum Division | Rampurhat Sub-Division | Restoration works of concrete Road along with culverts (4nos) for Augmentation MARGRAM Water Supply Scheme under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000403/2023-2024 | 3516/BHM | 10/08/2023 | 60 | PULAK KUMAR PAL | 16.34 | 0 | 100
1805 | Birbhum Division | Rampurhat Sub-Division | Hiring of Ambassador Car (Diesel/Petrol/Electric) registered Luxury Taxi for the office of the Assistant Engineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition with effect from 01.02.2025 to 31.01.2026 i.e. (365 Days) (For JJM Works) (SL. No. 01) | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000565/2024-2025 | 133/RSD | 31/01/2025 | 365 | PULAK KUMAR PAL | 1.72 | 0 | 0
1806 | Birbhum Division | Rampurhat Sub-Division | Laying of Rising main with DI pipe line for MARGRAM water supply scheme under Rampurhat Sub-Division under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000642/2021-2022 | 99/RSD | 07/03/2022 | 30 | TAPAS KUMAR SARKHEL | 2.41 | 0 | 100
1807 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of Sluice Valve & Non-Return Valve for Augmentation of Margram water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000440/2024-2025 | 1299./AE-III | 27/08/2024 | 7 | SUNIL RABIDAS | 2.87 | 0 | 0
1808 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Wells and allieds works at Augmentation of Margram ( Pump House No - I, II & III ) Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000455/2023-2024 | 2132/Bol.MD | 25/08/2023 | 707 | SUNIL RABIDAS | 90.64 | 0 | 50
1809 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Starter Feeder Panel at existing Pump House Beside OHR and allied works at Margram ( Pump House No - IV ) Piped Water Supply Scheme, Block-Rampurhat-II [within Augmentation of Margram] under Bolpur Mechanical Division. PHE Dte | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000456/2023-2024 | 2133/Bol.MD | 25/08/2023 | 60 | GOENKA ENTERPRISE | 6.55 | 0 | 100
1810 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of Electrical accessories ie Main switch change over switch etc for Augmentation of Margram water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000547/2024-2025 | 1456./AE-III | 09/09/2024 | 7 | BIRBHUM ELECTRIC WORKS | 2.88 | 0 | 100
1811 | Birbhum Division | Nalhati Sub-Division | Sinking of 300 X 200 mm Dia (through) and 180 m deep tubewell , 02 nos, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Dhananjaypur & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000101/2024-2025 | 2114/BHM | 29/07/2024 | 730 | QUAZI SIRAJUL ISLAM | 435.37 | 0 | 1
1812 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE2,Junior Engineer | RTOR000019/2024-2025 | 2442/BHM | 30/08/2024 | 0 | Resource Division | 10.92 | 0 | 0
1813 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE2,Junior Engineer | RTOR000031/2023-2024 | 1443/BHM | 25/04/2023 | 0 | Resource Division | 20.68 | 0 | 0
1814 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for DHANANJAYPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000897/2023-2024 | 3292/Bol.MD | 29/09/2023 | 60 | ABHISEK ENGTNEERING CONCERN | 27.4 | 0 | 0
1815 | Birbhum Division | Rampurhat Sub-Division | Sinking of 250 X 150 mm Dia, 150 m deep Tube Well Drilling by Direct Rotary method, Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing FHTC, related to water supply scheme at Mahesha & its adjoining mouzas water supply scheme within Mayureswar-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000086/2024-2025 | 1952/BHM | 04/07/2024 | 850 | S K CONSTRUCTION VILL& POST - DEBKUNDA, P.S - BELDANGA, DIST - MURSHIDABAD | 609.18 | 0 | 60
1816 | Birbhum Division | Rampurhat Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
1817 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (MAHESHA) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000840/2022-2023 | 324/RSD | 08/09/2022 | 45 | ENVIROTECH SOLUTIONS | 3.54 | 0 | 100
1818 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (MAHESHA) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000841/2022-2023 | 435/RSD | 21/11/2022 | 45 | ENVIROTECH SOLUTIONS | 3.54 | 0 | 100
1819 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000015/2024-2025 | 2390/BHM | 27/08/2024 | 0 | Resource Division | 16.84 | 0 | 0
1820 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000022/2023-2024 | 1446/BHM | 25/04/2023 | 0 | Resource Division | 50.7 | 0 | 0
1821 | Bolpur Mechanical | Rampurhat Sub-Division | Supply, delivery and storage of different Electro-Mechanical accessories at Mahesha PWSS under Bolpur Mmechanical Dsivision, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000512/2024-2025 | 3759/Bol.MD | 12/09/2024 | 30 | P. K. ENGINEERING | 16.05 | 0 | 0
1822 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Mahesha Piped Water Supply Scheme, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000516/2024-2025 | 3762/Bol.MD | 12/09/2024 | 30 | QUAZI NOZRUL ISLAM | 25.33 | 0 | 0
1823 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Mahesha PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000840/2023-2024 | 3279/Bol.MD | 29/09/2023 | 60 | WEST BENGAL ENGINEERING CO. | 66.12 | 0 | 0
1824 | Bolpur Mechanical | Rampurhat Sub-Division | Supply, delivery and Installation of Centrifugal pumping machinery at Mahesha PWSS under Bolpur Mechanical Division, P.H.E. Dte. of Mayureswar - II Block | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/001191/2023-2024 | 376/Bol.MD | 06/03/2024 | 45 | MITRA ENTERPRISE | 7.69 | 0 | 100
1825 | Bolpur Mechanical | Rampurhat Sub-Division | Replacement of PDB cum MCC Panel including other allieds works at Mahesha PWSS under Bolpur Mechanical Division, P.H.E. Dte. Of Mayureswar - II block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/001194/2023-2024 | 378/Bol.MD | 06/03/2024 | 45 | J.K.ENGINEERING CO | 7.25 | 0 | 100
1826 | Birbhum Division | Central Mechanical Sub-DivisionIII | Different works related to water supply scheme at GULALGACHI & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000389/2023-2024 | 4145/BHM | 19/10/2023 | 744 | M/S SAHA AND MONDAL CONSTRUCTION | 635.78 | 0 | 10
1827 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000040/2023-2024 | 1453/BHM | 25/04/2023 | 0 | Resource Division | 435.57 | 0 | 0
1828 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | QUOTATION FOR GULALGACHI PWSS RAJNAGAR BLOCK | Assistant Engineer-III | Junior Engineer | BILL/00009/2024-2025 | BP-24-25-07 | 09/04/2024 | 0 | WBSEDCL | 6.1 | 0 | 0
1829 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing electro-mechanical accessories and others for Gulalgachi water supply scheme in Rajnagar Block under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000386/2023-2024 | 1917/Bol.MD | 10/08/2023 | 756 | DEY ENTERPRISE | 105.62 | 0 | 84
1830 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Hiring of Luxury Car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/001077/2024-2025 | 4229/Bol.MD | 24/10/2024 | 121 | RAJIB GHOSH | 0.57 | 0 | 100
1831 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001232/2024-2025 | 1662/BOL.MD | 28/06/2024 | 200 | SATYAJIT GHOSH | 0.57 | 0 | 100
1832 | Birbhum Division | Birbhum Sadar Sub-Division | Survey, Planning, Design, Supply, Delivery, Erection, Construction, Commissioning and Completion in all respect all Civil and E&M Works including all allied, related and Enabling Works for 5.0 MGD capacity Radial Collector Well, Access Bridge, Substation Building, 1000 Cum capacity UGR with high lift Pump House and Raw Water Rising Main from Collector Well to River Bank UGR including 03(Three) months Trial Run and subsequent Operation & Maintenance for 1(One) year for Sub-Surface Water Based Piped Water Supply Scheme in Khairasole Block, District Birbhum on Turnkey basis under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000580/2023-2024 | 445/BHM | 01/02/2024 | 547 | G B CONSTRUCTION | 2150.9 | 0 | 70
1833 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000197/2023-2024 | 3810/BHM | 12/09/2023 | 0 | Resource Division | 1630.08 | 0 | 0
1834 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000262/2023-2024 | 623/BHM | 15/02/2024 | 0 | Resource Division | 301.46 | 0 | 0
1835 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Intake site for sub-surface based piped water supply scheme at Khoyrasole . | AE,Assistant Engineer-III | JE,Junior Engineer | BILL/00084/2024-2025 | BP-2024-2025-21 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.9 | 0 | 0
1836 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at 20 nos. OHR site Piped water supply scheme of Khoyrasole project under Khoyrasole Block in the Dist. of Birbhum under Bolpur Mechanical Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000579/2024-2025 | 3892/Bol.MD | 23/09/2024 | 365 | SATYAJIT GHOSH | 145.74 | 0 | 68
1837 | Birbhum Division | Rampurhat Sub-Division | Sinking of 250 X 150 mm Dia (through) and 25 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM, 300 CuM, 150 CuM capacity O.H.R. for Zone-I, II and III respectively, 300 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I, II and III and Providing functional household tap connection related to water supply scheme at AYAS & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000088/2024-2025 | 1949/BHM | 04/07/2024 | 635 | PRADIP KUMAR DEB, 103/4 NAINAN PARA LANE , KOLKATA-700036 | 1332.94 | 0 | 55
1838 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000014/2024-2025 | 2389/BHM | 27/08/2024 | 0 | Resource Division | 42.26 | 0 | 0
1839 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000093/2023-2024 | 1495/BHM | 25/04/2023 | 0 | Resource Division | 249.36 | 0 | 0
1840 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & Installation of Low lift Pumping Mchinery and other allied work for AYAS & Adjoining moujas water supply scheme under within Rampurhat - I Block Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000869/2023-2024 | 3389/BOL.MD | 16/10/2023 | 533 | S.K.ELECTRICALS | 59.94 | 0 | 50
1841 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of High lift Pumping Machinery and other allied work for AYAS and Adjoining moujas water supply scheme under within Rampurhat - I Block Bolpur Mechanical Division PHE Dte | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000872/2023-2024 | 3372/Bol.MD | 12/10/2023 | 628 | SINHA ELECTRICALS | 95.35 | 0 | 30
1842 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
1843 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
1844 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Tamra & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000678/2022-2023 | 122/BSSD | 05/07/2022 | 45 | RADIANT | 1.62 | 0 | 100
1845 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000233/2023-2024 | 436/BHM | 01/02/2024 | 0 | Resource Division | 54.82 | 0 | 0
1846 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Bahadurpur & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. Sl No 01 | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000527/2022-2023 | 884/BHM | 21/03/2023 | 1229 | ABUL KALAM | 380.11 | 0 | 70
1847 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000041/2023-2024 | 1529/BHM | 26/04/2023 | 0 | Resource Division | 23.48 | 0 | 0
1848 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Bahadurpur Water Supply Scheme P/H -I in Murarai CCC under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | BILL/00224/2024-2025 | BP-24-25-113 | 02/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.61 | 0 | 0
1849 | Bolpur Mechanical | Nalhati Sub-Division | Name of Work: Supply, delivery and installation of servo motor operated copper wound line voltage corrector at T/W-I&II for Bahadurpur water supply scheme of Murarai-I Block under Bolpur Mechanical Division, PHE Dte.. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000543/2024-2025 | 3802/BOL.MD | 12/09/2024 | 111 | SUNIL RABIDAS | 5.02 | 0 | 100
1850 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for BAHADURPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000888/2023-2024 | 3291/Bol.M.D | 29/09/2023 | 550 | SUNIL RABIDAS | 27.54 | 0 | 60
1851 | Birbhum Division | Central Mechanical Sub-DivisionIII | Construction of 100 Cum Capacity CWR as per departmental drawing nearer to Kochujore for collection of water from Chinpai Head work site under Chinpai Piped Water Supply Scheme under Birbhum Sadar Sub- Division within Birbhum Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000056/2025-2026 | 308/BSSD | 22/05/2025 | 120 | HIRANMAY GHOSH | 17.82 | 0 | 100
1852 | Birbhum Division | Central Mechanical Sub-DivisionIII | Laying of rising main pipe line, Jack Pushing of Railway & NH-14 for Chinpai Piped Water Supply Scheme in Rajnagar Block under Birbhum Sadar Sub-Division, PHE Dte. within Birbhum Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000219/2025-2026 | 2164/BHM | 20/08/2025 | 90 | B RAI CONSTRUCTION COMPANY | 73.46 | 0 | 0
1853 | Birbhum Division | Central Mechanical Sub-DivisionIII | Different works related to water supply scheme at CHINPAI, LOBA & PARATPUR and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000265/2023-2024 | 3476/BHM | 08/08/2023 | 816 | B RAI CONSTRUCTION COMPANY | 2497.19 | 0 | 45
1854 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000070/2022-2023 | 1390/BHM | 24/04/2023 | 0 | Resource Division | 179.71 | 0 | 0
1855 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000186/2023-2024 | 3281/BHM | 27/07/2023 | 0 | Resource Division | 1.02 | 0 | 0
1856 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing electro-mechanical accessories and others for Chinpai & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000383/2023-2024 | 1914/Bol.MD | 10/08/2023 | 366 | M/S P.P ELECTRICALS | 106.93 | 0 | 50
1857 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply and Delivery of Pump Starter, Diaphragm type Chlorinator dosing pump and Colum pipes at Chinpai and Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/001314/2023-2024 | 707/Bol.MD | 27/03/2024 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 7.99 | 0 | 100
1858 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
1859 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
1860 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Ekura & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000677/2022-2023 | 115/BSSD | 28/06/2022 | 45 | RADIANT | 2.64 | 0 | 100
1861 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000240/2023-2024 | 426/BHM | 01/02/2024 | 0 | Resource Division | 109.46 | 0 | 0
1862 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000402/2023-2024 | 4139/BHM | 18/10/2023 | 896 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 0 | 60
1863 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | RTOR000112/2023-2024 | 1546/BHM | 26/04/2023 | 0 | Resource Division | 214.47 | 0 | 0
1864 | Bolpur Mechanical | Bolpur Sub-Division | WBSEDCL QUOTATION FOR KANKALITALA PWSS | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | BILL/01590/2023-2024 | BP-23-24-222 | 15/01/2024 | 0 | WBSEDCL | 10.64 | 0 | 0
1865 | Bolpur Mechanical | Bolpur Sub-Division | Supply and delivery of chlorinator dosing pump for kankalitala Water Supply Project under Bolpur Mechanical Divn. P.H.E. Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000551/2024-2025 | 3819/BOL.MD | 18/09/2024 | 20 | SINHA ELECTRICALS | 3.24 | 0 | 100
1866 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1867 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-5) |  |  | ORD/000005/2021-2022 | 1019/BHM | 17/06/2021 | 60 | SUNIL RABI DAS | 50.07 | 49.78 | 100
1868 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Bishnupur Konaipara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. |  |  | ORD/000162/2020-2021 | 34/BH | 26/02/2021 | 20 | MUKADDUMUL MOULA | 4.84 | 4.84 | 0
1869 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Bishnupur Panchayatpara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. |  |  | ORD/000163/2020-2021 | 35/BH | 26/02/2021 | 20 | M/S S.N CONSTRUCTION | 4.84 | 4.84 | 0
1870 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Sashtitalapara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. |  |  | ORD/000165/2020-2021 | 37/BH | 26/02/2021 | 20 | M/S K.S. GHOSH | 4.84 | 4.84 | 0
1871 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Baroipara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. |  |  | ORD/000166/2020-2021 | 38/BH | 26/02/2021 | 20 | TAPAN ENTERPRISE | 4.84 | 4.84 | 0
1872 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Talipara within the command area of Bishnupur Water Supply Scheme of Rampurhat - II Block under Brbhum Division, PHE Dte. (Sl. No.04) |  |  | ORD/000331/2020-2021 | 36 / BH | 26/02/2021 | 20 | BIJOY KUMAR CHOWDHURY | 4.84 | 4.84 | 100
1873 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Baroipara and its adjoining area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. |  |  | ORD/000364/2021-2022 | 177/BH | 03/11/2021 | 15 | TAPAN ENTERPRISE | 4.83 | 0 | 50
1874 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Talipara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. |  |  | ORD/000366/2021-2022 | 179/BH | 03/11/2021 | 15 | BIJOY KUMAR CHOUDHURY | 3.73 | 0 | 100
1875 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Sashtitalapara and its adjoining area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. |  |  | ORD/000367/2021-2022 | 178/BH | 03/11/2021 | 15 | M/S K.S. GHOSH | 3.64 | 0 | 100
1876 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Bishnupur Panchayatpara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. |  |  | ORD/000370/2021-2022 | 180/BH | 03/11/2021 | 15 | MUKADDUMUL MOULA | 3.86 | 0 | 100
1877 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿ (Sl. No.2) |  |  | ORD/000425/2021-2022 | 2033/BHM | 09/12/2021 | 60 | TAPAN KUMAR DATTA | 94.18 | 0 | 0
1878 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿ (Sl. No.2) |  |  | ORD/000664/2021-2022 | 2033/ BHM | 09/12/2021 | 60 | TAPAN KUMAR DATTA | 94.18 | 0 | 40
1879 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Hiring of Ambassador Car (Diesel) registered Luxury Taxi for the office of the Assistant Engineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition with effect from 01.02.2024 to 31.07.2024 i.e. (182 Days) "from 01.08.2024 to 31.01.2025 i.e. (184 Days)" | AE | JE3 | ORD/000155/2024-2025 | 354/RSD | 31/07/2024 | 184 | SOUMITA PAL | 0.86 | 0 | 0
1880 | Birbhum Division | Rampurhat Sub-Division | Hiring of Ambassador Car (Diesel) registered Luxury Taxi for the office of the Assistant Engineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition with effect from 01.08.2023 to 31.01.2024 i.e. (184 Days). | AE | JE3 | ORD/000228/2023-2024 | 199/RSD | 28/07/2023 | 184 | SOUMITA PAL | 0.86 | 0 | 100
1881 | Birbhum Division | Rampurhat Sub-Division | Hiring of Ambassador Car (Diesel) registered Luxury Taxi for the office of the Assistant Engineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition with effect from 01.02.2024 to 31.07.2024 i.e. (182 Days). | AE | JE3 | ORD/000459/2023-2024 | 27/RSD | 22/01/2024 | 182 | SOUMITA PAL | 0.86 | 0 | 0
1882 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Batikar Gram Panchayet under Batikar Water Supply Scheme in Batikar Jagpalla and Batikar Bus Stand and Repairing of pipeline due to leakage of house connection in distributions pipeline in different area (i.e. Kustikuri, Nabagram and Charakdanga) under Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 02). | Assistant Engineer | JE1 ,JE4 | ORD/000055/2022-2023 | 201/BSD | 20/05/2022 | 30 | M/S SARADA CONSTRUCTION. | 3.98 | 0 | 75
1883 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at habitation Batikor, village-Batikor (JL No.02) at different locations from existing distribution system within the command area of Batikor piped water supply scheme at Illambazar Block under Bolpur Sub Division within Birbhum Division, PHE Dte. (Phase-1) | Assistant Engineer | JE1 ,JE4 | ORD/000079/2020-2021 | 1089/BHM | 05/09/2020 | 30 | PRANAB KUMAR GHOSH | 4.71 | 4.71 | 0
1884 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Narasonda, Ikshusara, Anaipur of Batikar w/s Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 ,JE4 | ORD/000080/2020-2021 | 1171 /BHM | 21/09/2020 | 60 | MS B N ENTERPRISES | 39.49 | 22.6 | 0
1885 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Batikor of Batikar w/s Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 ,JE4 | ORD/000081/2020-2021 | 1170 /BHM | 21/09/2020 | 60 | HIMANGSU SEKHAR SARKAR | 31.27 | 23.66 | 0
1886 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Khushtikuri of Batikar w/s Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. (6a) | Assistant Engineer | JE1 ,JE4 | ORD/000082/2020-2021 | 1172 /BHM | 21/09/2020 | 45 | INDRAJIT DAS | 24.28 | 16.83 | 89
1887 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Narasonda, Ikshusara, Anaipur of Batikar w/s Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer | JE1 ,JE4 | ORD/000211/2020-2021 | 1563/BHM | 17/12/2020 | 60 | MS B N ENTERPRISES | 4.91 | 0 | 0
1888 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Karchadihi Mouza within the command area of for Batikar Water Supply Scheme under Bolpur Sub Division of Birbhum Division, PHE Dte.(Sl. No.2) | Assistant Engineer | JE1 ,JE4 | ORD/000280/2020-2021 | 255/BHM | 26/02/2021 | 45 | MS KAZIMEHERUDDIN | 4.67 | 4.67 | 100
1889 | Birbhum Division | Bolpur Sub-Division | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) within the Command area of Batikar Water Supply Scheme in Anaipur (Purbo Para) village for Swajal Gram under Illambazar Block of Bolpur Sub-Division within Birbhum Division P.H.E. Deptt. | Assistant Engineer | JE1 ,JE4 | ORD/000299/2022-2023 | 381/BSD | 29/09/2022 | 10 | M/S SARADA CONSTRUCTION. | 0.96 | 0 | 91
1890 | Birbhum Division | Bolpur Sub-Division | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) within the Command area of Batikar Water Supply Scheme in Karchadihi, Ikshusara and Anaipur (Paschim Para) village for Swajal Gram under Illambazar Block of Bolpur Sub-Division within Birbhum Division P.H.E. Deptt. | Assistant Engineer | JE1 ,JE4 | ORD/000300/2022-2023 | 382/BSD | 29/09/2022 | 10 | M/S SARADA CONSTRUCTION. | 0.97 | 0 | 91
1891 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) for remaining household at UTTAR SULTANPUR Mouza from existing distribution System within the command area of Batikar Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE4 | ORD/000349/2021-2022 | 403/BSD | 25/10/2021 | 10 | INDRAJIT DAS | 0.96 | 0 | 100
1892 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Balta Mouza (Part) within the command area of Batikar Water Supply Scheme under Bolpur Sub Division of Birbhum Division, PHE Dte. (Sl. No.1) | Assistant Engineer | JE1 ,JE4 | ORD/000492/2020-2021 | 280/BHM | 26/02/2021 | 45 | HIMANGSU SEKHAR SARKAR | 4.67 | 4.5 | 100
1893 | Birbhum Division | Bolpur Sub-Division | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) in Batikar (02) under BATIKAR Gram Panchayat within the Command area of Batikar Water Supply, Scheme for Swajal Gram under Illambazar Block of Bolpur Sub-Division within BIRBHUM DIVISION P.H.E. Deptt.(Sl. No.12) | Assistant Engineer | JE1 ,JE4 | ORD/000500/2022-2023 | 332/BHM | 02/02/2023 | 45 | KAUSHIK RAY | 18.74 | 0 | 100
1894 | Birbhum Division | Bolpur Sub-Division | Construction of remaining Boundary Wall at Head Work site of BATIKAR Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Length: 123 Mtr.). (Sl. 04) | Assistant Engineer | JE1 ,JE4 | ORD/000736/2021-2022 | 425/BSD | 18/11/2021 | 60 | GANAPATI ENGINEERING CORP. | 4.85 | 0 | 0
1895 | Birbhum Division | Bolpur Sub-Division | Balance work of Laying Rising main with inter connection pipe line from Tube Well No. - 2 to Tube Well No. - 1 including OHR with Distribution main of BATIKAR Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No. -10) | Assistant Engineer | JE1 ,JE4 | ORD/000803/2021-2022 | 320/BSD | 31/08/2021 | 15 | PRANAB KUMAR GHOSH | 0.93 | 0 | 0
1896 | Birbhum Division | Bolpur Sub-Division | Allied works of extension boosting pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system in various node point (From 03 to 11,110 to 120, 144 to 158, 9 to 168 174 to 175), of Batikar village within the command area in the villages Batikar (JL No.- 02.) Water Supply Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. - 03) | Assistant Engineer | JE1 ,JE4 | ORD/000830/2021-2022 | 11/BSD | 11/01/2022 | 30 | HIMANGSU SEKHAR SARKAR | 4.38 | 0 | 100
1897 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing Distribution System within the command area of Batikar Water Supply Scheme at Mouja: KHUSTIKURI & UTTAR SULTANPUR under Bolpur Sub Division within Birbhum Division, PHED. (Sl. - 01) | Assistant Engineer | JE1 ,JE4 | ORD/000844/2021-2022 | 379/ BSD | 07/10/2021 | 30 | MS KAZIMEHERUDDIN | 4.77 | 0 | 100
1898 | Birbhum Division | Bolpur Sub-Division | Retrofitting works to the existing distribution system within the command area of Batikar Water Supply Scheme at Khustikuri and Narasonda Moujas under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 ,JE4 | ORD/001074/2021-2022 | 324/BSD | 01/09/2021 | 30 | INDRAJIT DAS | 4.85 | 0 | 74
1899 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bansjore W/S Scheme in Suri Sadar Sub-Division under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000053/2023-2024 | 1248/BHM | 17/04/2023 | 45 | PRANAB KUMAR GHOSH | 33.15 | 0 | 100
1900 | Birbhum Division | Birbhum Sadar Sub-Division | Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bansjore W/S Scheme in Suri Sadar Sub-Division under Birbhum Division, P.H.E. Dte. (Sl. No.- 2) | AE | JE3 | ORD/000355/2021-2022 | 1865/BHM | 16/11/2021 | 60 | PRANAB KUMAR GHOSH | 65.87 | 0 | 45
1901 | Birbhum Division | Birbhum Sadar Sub-Division | Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bansjore w/s Scheme in Suri Sadar Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.2) | AE | JE3 | ORD/000570/2021-2022 | 1865/ BHM | 16/11/2021 | 60 | PRANAB KUMAR GHOSH | 65.87 | 0 | 85
1902 | Birbhum Division | Bolpur Sub-Division | Withdrawing of existing pipe for previous Head Work Site and relaying of 250mm. dia. DI pipes From OHR to Node point 192A due to Change of Head Work Site at Tilutia Zone - I Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 07). | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000059/2022-2023 | 204/BSD | 23/05/2022 | 192 | ARABINDA GHOSH | 3.65 | 0 | 100
1903 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from the existing distribution system within the command area of "Tilutia Zone - II under Tilutia Zone - II Water Supply Scheme within Birbhum Division PHE Dte." (Sl. No. - 8) | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000096/2022-2023 | 1476/BHM | 12/07/2022 | 60 | RAJKUMAR DAS | 66.75 | 0 | 100
1904 | Birbhum Division | Bolpur Sub-Division | Adopting Jack Pushing of Hume Pipe (NP3/ NP4) as Cashing to Cross Water carrier Pipe in front of OHR at TILUTIA ZONE - II Water Supply Scheme under Bolpur Sub-Division, P.H.E. Deptt. (Sl. No.: 10). | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000110/2022-2023 | 242/BSD | 22/06/2022 | 20 | S. S. CONSTRUCTION | 3.1 | 0 | 100
1905 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tilutia Zone-I under Tilutia Zone-I Water Supply Scheme within Birbhum Division, PHE Dte. | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000277/2022-2023 | 2245/BHM | 17/10/2022 | 60 | MANAS KUMAR MONDAL | 66.75 | 0 | 100
1906 | Birbhum Division | Bolpur Sub-Division | Balance FHTC works at different Villages within coverage area of Tilutia Water Supply Scheme (Zone-II) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No.10) | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000534/2022-2023 | 665/BHM | 28/02/2023 | 135 | INDRAJIT DAS | 25.54 | 0 | 100
1907 | Birbhum Division | Bolpur Sub-Division | Laying of Rising Main from Tube Well - I & Tube Well - II to O.H.R. for Tilutia Zone - II Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 04). | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000644/2021-2022 | 87/BSD | 10/03/2022 | 20 | SYED HASMAT ALI | 2.65 | 0 | 100
1908 | Birbhum Division | Bolpur Sub-Division | Laying of Rising Main pipeline from Tube-well No. - I & II to O.H.R at Mahanpur of Tilutia Zone - I Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED.. (Sl. No.: 15). | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000645/2021-2022 | 86/BSD | 10/03/2022 | 15 | INDRAJIT DAS | 2.52 | 0 | 100
1909 | Birbhum Division | Bolpur Sub-Division | Sinking of 02(Two) nos. 300mm X 200mm dia. X 300m deep Tube Wells by Rotary Rig for Tilutia-II Piped Water Supply Scheme in Nanoor Block under Bolpur Sub-Division within Birbhum Division, P.H.E Dte.(2nd Call) (Sl. No.5) | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000670/2020-2021 | 1503/BHM | 26/11/2020 | 60 | PASCON | 32.45 | 0 | 100
1910 | Birbhum Division | Bolpur Sub-Division | Dismantling & Restoration of cement concrete road for laying of distribution pipeline of Tilutia Zone - I Piped Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 01) | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000688/2021-2022 | 446/BSD | 10/12/2021 | 30 | M/S KRIPASINDHU GHOSH & CO. | 4.82 | 0 | 100
1911 | Birbhum Division | Bolpur Sub-Division | Construction of Pump House (Size - 5.40 Mtr. x 3.60 Mtr.) at Tilutia Zone -I Head work site of Tilutia water supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (2nd Call). (Sl. 04) | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000741/2021-2022 | 12/BSD | 11/01/2022 | 60 | SANTU SEKH | 4.84 | 0 | 100
1912 | Birbhum Division | Bolpur Sub-Division | Construction of Pump House (Size - 5.40 Mtr. x 3.60 Mtr.) at Tilutia Zone - II Head Works site of Tilutia Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (2nd Call). (Sl. - 02) | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000825/2021-2022 | 17/BSD | 11/01/2022 | 60 | MD SAFIUL HASSAN | 4.82 | 0 | 100
1913 | Birbhum Division | Bolpur Sub-Division | Supply and delivery of 300mm dia., 3.0 Mtr. long UPVC slotted pipe (Strainer) (CD) for sinking of 02 nos deep Tube-wells of Tilutia Zone - II Piped Water Supply Scheme in Nanoor Block under Bolpur Sub-Division within Birbhum Division PHED. (Sl. No.: 01). | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000840/2021-2022 | 479/BSD | 27/12/2021 | 15 | PASCON | 2.05 | 0 | 100
1914 | Birbhum Division | Bolpur Sub-Division | Supply and delivery of 150mm and 100mm. dia. Sluice Valves including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Tilutia Zone - I & II Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 02). | Assistant Engineer | JE2 ,JE4 ,JE_BLK_NANOOR | ORD/000854/2021-2022 | 93/BSD | 11/03/2022 | 15 | MAKALI ENGINEERING CORPORATION | 1.81 | 0 | 100
1915 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Margram Water Supply Scheme within Birbhum Rampurhat Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.4) | AE | JE1 | ORD/000006/2022-2023 | 739/BHM | 04/04/2022 | 60 | PULAK KUMAR PAL | 52.82 | 0 | 100
1916 | Birbhum Division | Rampurhat Sub-Division | Additional Laying distribution system at Margram mouza including FHTC under Augmentation of Margram Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000070/2023-2024 | 1343/BHM | 20/04/2023 | 90 | PULAK KUMAR PAL | 145.64 | 0 | 50
1917 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Margram in Rampurhat Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.7) | AE | JE1 | ORD/000121/2022-2023 | 1567/BHM | 26/07/2022 | 60 | PULAK KUMAR PAL | 44.05 | 0 | 100
1918 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Margram in Rampurhat Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.7) | AE | JE1 | ORD/000142/2022-2023 | .1567/BHM | 26/07/2022 | 60 | PULAK KUMAR PAL | 44.05 | 0 | 0
1919 | Birbhum Division | Rampurhat Sub-Division | DI Relaying & Concrete Road Restoration work at Benegram Mouza under MARGRAM Water Supply Scheme within Rampurhat Sub-Division Birbhum Division PHE Dte. | AE | JE1 | ORD/000149/2025-2026 | 691/RSD | 31/07/2025 | 90 | RUBAL CONSTRACTION | 2.03 | 0 | 0
1920 | Birbhum Division | Rampurhat Sub-Division | Providing FHTC from existing distribution system with Allied works at Benegram & Mazarpara within Margram w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-12) | AE | JE1 | ORD/000186/2022-2023 | 315/RSD | 08/09/2022 | 30 | RUBAL CONSTRACTION | 4.97 | 0 | 100
1921 | Birbhum Division | Rampurhat Sub-Division | Providing FHTC from existing distribution system with Allied works at Hospital para, Chot dangal within Margram w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-13) | AE | JE1 | ORD/000187/2022-2023 | 316/RSD | 08/09/2022 | 30 | M/S TAPAN ENTERPRISE | 4.98 | 0 | 100
1922 | Birbhum Division | Rampurhat Sub-Division | Providing FHTC from existing distribution system with Allied works at Khanpur within Margram w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-14) | AE | JE1 | ORD/000188/2022-2023 | 317/RSD | 08/09/2022 | 30 | RUBAL CONSTRACTION | 4.97 | 0 | 100
1923 | Birbhum Division | Rampurhat Sub-Division | Laying UPVC Pipe line in place of AC line due to strengthenig of Rampurhat--Parulia PWD Road at Margram Mouza of existing MARGRAM Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. (Sl. No.3) | AE | JE1 | ORD/000495/2022-2023 | 231/BHM | 20/01/2023 | 30 | MAINUL ISLAM | 3.72 | 0 | 100
1924 | Birbhum Division | Rampurhat Sub-Division | Sinking of o1 (one) No 200mm dia.X 66.0 mtr deep Tube Well with UPVC pipe & strainer for Margram W/s scheme under Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000542/2021-2022 | 29/RSD | 04/01/2022 | 30 | TAPAN ENTERPRISE | 4.29 | 0 | 100
1925 | Birbhum Division | Rampurhat Sub-Division | Additional concreting works (Fulmali para, Baganpara(Part) for LDS of Margram pipe water supply scheme under Rampurhat Sub-Division under Birbhum Division PHE Dte. | AE | JE1 | ORD/000671/2021-2022 | 101/RSD | 07/03/2022 | 30 | PULAK KUMAR PAL | 4.96 | 0 | 100
1926 | Birbhum Division | Rampurhat Sub-Division | Laying of Distribution Main pipeline through crossing of PWD road at Margram Hospital More by adopting Jack Pushing method for Margram PWSS under Rampurhat Sub-Division, PHE Dte. | AE | JE1 | ORD/000672/2021-2022 | 112/RSD | 07/03/2022 | 15 | PULAK KUMAR PAL | 4.33 | 0 | 100
1927 | Birbhum Division | Rampurhat Sub-Division | Laying of HDPE (110mm and 90mm dia) distribution line and concreting works etc at Hospital para, khanpara, Benegram of Margram water supply scheme under Rampurhat sub division under Birbhum Division PHE Dte. | AE | JE1 | ORD/000677/2021-2022 | 102/RSD | 07/03/2022 | 30 | RUBAL CONSTRACTION | 4.99 | 0 | 100
1928 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE | JE1 | RTOR000026/2022-2023 | 2205/BHM | 12/10/2022 | 0 | Resource Division | 0.05 | 0 | 0
1929 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE | JE1 | RTOR000041/2021-2022 | 219/BHM | 02/02/2022 | 0 | Resource Division | 16.47 | 0 | 0
1930 | Birbhum Division | Rampurhat Sub-Division | Payment for Supply of diesel | AE | JE1 | BILL/00270/2023-2024 | BP-2023-24-127 | 25/08/2023 | 0 | JAYRAM FILLING STATION | 0.72 | 0 | 0
1931 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Narayanpur of Narayanpur w/s Scheme at Rampurhat-I Block under Birbhum Division, PHE Dte. (Sl. No.12) | AE | JE1 | ORD/000042/2020-2021 | 1426 / BHM | 04/11/2020 | 60 | SUNIL RABI DAS | 35.91 | 35.58 | 0
1932 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Balia Mrityunjoypur of Narayanpur w/s Scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl. No.3) | AE | JE1 | ORD/000226/2020-2021 | 1706/BHM | 23/12/2020 | 60 | SANJUKTA ENGINEERS | 36.44 | 0 | 27
1933 | Birbhum Division | Rampurhat Sub-Division | Sinking of o1 (one) No 200mm dia.X 42.0 mtr deep Tube Well with UPVC pipe & strainer for Narayanpur W/s scheme under Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000543/2021-2022 | 30/RSD | 04/01/2022 | 30 | ISLAM CONSTRUCTION | 2.92 | 0 | 50
1934 | Birbhum Division | Rampurhat Sub-Division | PCC Work for road restoration at Hattala due to laying of 160mm dia HDPE Bypass Pipe line from CWR to Suripara more for providing drinking water at Hattala surrounding Area of Narayanpur W/S Scheme under Rampurhat Sub- Division, P.H.E. Dte within Birbhum Division P.H.E. Dte | AE | JE1 | ORD/000585/2022-2023 | 1012/BHM | 30/03/2023 | 45 | ISLAM CONSTRUCTION | 4.17 | 0 | 0
1935 | Birbhum Division | Rampurhat Sub-Division | Laying Bypass UPVC Pipe line from CWR to Suripara more for providing drinking water Hattala surrounding Area of Narayanpur W/S Scheme under Rampurhat Sub-Division, P.H.E. Dte within Birbhum Division, P.H.E. Dte. (Sl. No.2) | AE | JE1 | ORD/000815/2021-2022 | 2069/BHM | 13/12/2021 | 60 | ISLAM CONSTRUCTION | 13.26 | 0 | 50
1936 | Birbhum Division | Rampurhat Sub-Division | Laying of Distribution System by HDPE pipe below heavy duty PWD concrete Road at Narayanpur for Narayanpur Water Supply Scheme Form Bhawani Padmabati Pry School to Narayanpur High School under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. (Sl. No.4) | AE | JE1 | ORD/000842/2021-2022 | 622/BHM | 11/03/2022 | 60 | SANJUKTA ENGINEERS | 6.96 | 0 | 0
1937 | Central Drilling | Rampurhat Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR NARAYANPUR W/S SCH, SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | AE | JE1 | ORD/000278/2022-2023 | 1133/CDD | 04/11/2022 | 30 | MENAKA ENTERPRISE | 8.09 | 0 | 100
1938 | Central Drilling | Rampurhat Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR NARAYANPUR W/S SCHEME, SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | AE | JE1 | ORD/000279/2022-2023 | 1132/CDD | 04/11/2022 | 30 | MENAKA ENTERPRISE | 11.09 | 0 | 92
1939 | Birbhum Division | Nalhati Sub-Division | Construction of 300 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Tejhati W/S Scheme under Nalhati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000085/2023-2024 | 1636/BHM | 02/05/2023 | 276 | GOLAM RASUL | 86.89 | 0 | 40
1940 | Birbhum Division | Nalhati Sub-Division | Sinking replacement of 200mm dia Tube Well of UPVC pipe 90m deep with fibre glass strainer including connecting main for Tejhati PWSS under Nalhati Sub- Division within Birbhum Division PHED | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000135/2023-2024 | 2017/BHM | 06/06/2023 | 45 | BHARAT CONSTRUCTION | 6.85 | 0 | 80
1941 | Birbhum Division | Nalhati Sub-Division | Allied work of distribution Pipe line including FHTC Work along with restoration of road including dismantling work with jack pushing & Augur Boring for Augmentation of Tejhati Water Supply Scheme under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000291/2023-2024 | 3653/BHM | 25/08/2023 | 60 | QUAZI SIRAJUL ISLAM. | 67.81 | 0 | 70
1942 | Birbhum Division | Nalhati Sub-Division | Laying distribution system including FHTC for proposed augmentation scheme for Tezhati Piped Water Supply Scheme, Nalhati-I Block, under Birbhum Division, PHE Dte.¿ (Sl. No.7) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000507/2022-2023 | 1150/BHM | 23/05/2022 | 1012 | QUAZI SIRAJUL ISLAM. | 168.84 | 0 | 62
1943 | Birbhum Division | Nalhati Sub-Division | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for 1 no OHR site at Tejhati Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000685/2021-2022 | 167/AE/NSD | 22/03/2022 | 15 | MOYTEC | 0.99 | 0 | 100
1944 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000008/2023-2024 | 1111/BHM | 10/04/2023 | 0 | Resource Division | 14.64 | 0 | 0
1945 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000065/2021-2022 | 486/BHM | 02/03/2022 | 0 | Resource Division | 4.21 | 0 | 0
1946 | Bolpur Mechanical | Nalhati Sub-Division | Supply and installation of Voltage Correction device & other allied work at Augmentation of Tejhati water supply scheme under Bolpur Mechanical Division PHE Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000005/2023-2024 | 714/Bol.MD | 19/04/2023 | 45 | STANDARD ELECTRICALS | 14.18 | 0 | 0
1947 | Bolpur Mechanical | Nalhati Sub-Division | Supply Delivery and Installation of automatically Voltage Correction Device at Augmentation of Tejhati water supply scheme (Block- Nalhati - I) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000865/2023-2024 | 1363/AE-III | 17/10/2023 | 15 | SINHA ELECTRICALS | 3.38 | 0 | 100
1948 | Bolpur Mechanical | Nalhati Sub-Division | Supply and Delivery of automatically controlled Chlorinator for Augmentation of Tejhati water supply scheme (Block- Nalhati - I) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000975/2023-2024 | 1449/AE-III | 17/11/2023 | 10 | CINZANO | 3.27 | 0 | 100
1949 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at KULARA & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000034/2023-2024 | 1098/BHM | 06/04/2023 | 275 | M/S H. R. CONSTRUCTION | 263.91 | 0 | 45
1950 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000102/2023-2024 | 1504/BHM | 25/04/2023 | 0 | Resource Division | 8.75 | 0 | 0
1951 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Kulora Water Supply Scheme P/H -II in Paikar CCC under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00090/2024-2025 | BP-2024-2025-43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.48 | 0 | 0
1952 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR KULARA P H NO.I WS SCHEME | AE,Assistant Engineer | JE1,Junior Engineer | BILL/01595/2023-2024 | BP-23-24-227 | 15/01/2024 | 0 | WBSEDCL | 2.99 | 0 | 0
1953 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for KULARA piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000546/2023-2024 | 2142/Bol.MD | 25/08/2023 | 585 | KAMAKHYA ENTERPRISE | 27.21 | 0 | 70
1954 | Bolpur Mechanical | Nalhati Sub-Division | Supply and installation of manual operated Motor control panel for Kulara water supply scheme (Amdol Pump House-III) of Murarai-II Block under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/001281/2023-2024 | 178/BMSD(D) | 18/03/2024 | 30 | M/S M3 SOLUTION | 2.6 | 0 | 100
1955 | Bolpur Mechanical | Nalhati Sub-Division | Supply, delivery and installation of servo motor operated copper wound line voltage corrector for Kulara water supply scheme (Amdol Pump House-III) of Murarai-II Block under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/001282/2023-2024 | 179/BMSD(D) | 18/03/2024 | 30 | SUNIL RABIDAS | 3.18 | 0 | 100
1956 | Birbhum Division | Birbhum Sadar Sub-Division | Balance work for laying of pipe line including FHTC within the command area of Aligarh (Phase III) Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000127/2023-2024 | 2272/BHM | 13/07/2023 | 45 | PARTHA PRATIM ACHARYYA | 32.89 | 0 | 40
1957 | Birbhum Division | Nalhati Sub-Division | Restoration of Roads, pucca drain including Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Jogai Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000071/2025-2026 | 1593/BHM | 03/06/2025 | 90 | QUAZI SIRAJUL ISLAM | 95.37 | 0 | 0
1958 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE2,Junior Engineer | RTOR000048/2023-2024 | 1458/BHM | 25/04/2023 | 0 | Resource Division | 10.24 | 0 | 0
1959 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR JOGAI P H NO. I WS SCHEME | AE,Assistant Engineer | JE2,Junior Engineer | BILL/01598/2023-2024 | BP-23-24-229 | 15/01/2024 | 0 | WBSEDCL | 3.25 | 0 | 0
1960 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR JOGAI P H NO .II WS SCHEME | AE,Assistant Engineer | JE2,Junior Engineer | BILL/01599/2023-2024 | BP-23-24-230 | 15/01/2024 | 0 | WBSEDCL | 3.16 | 0 | 0
1961 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Jagoi PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000942/2023-2024 | 3303/BOL.MD | 29/09/2023 | 550 | SUNRISE ENGINEERING CORPORATION | 28.91 | 0 | 100
1962 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at METEGAON & its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000006/2023-2024 | 1085/BHM | 06/04/2023 | 1121 | M/S S.S. ENTERPRISE | 432.4 | 0 | 42
1963 | Birbhum Division | Birbhum Sadar Sub-Division | Acceptance cum Work Order for Supply and delivery of Sluice Valve for Metegaon and Adjoining Mouzas PWSS under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000638/2023-2024 | 949/BHM | 14/03/2024 | 30 | SSPR VALVE MANUFACTURING PVT LTD | 9.2 | 0 | 100
1964 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000079/2022-2023 | 1398/BHM | 24/04/2023 | 0 | Resource Division | 114.57 | 0 | 0
1965 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Metegaon & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000580/2023-2024 | 3384/Bol.MD | 16/10/2023 | 90 | SATYAJIT GHOSH | 52.86 | 0 | 0
1966 | Birbhum Division | Rampurhat Sub-Division | Allied works for Providing FHTC from existing distribution system under Kot Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000105/2023-2024 | 2059/BHM | 08/06/2023 | 405 | SAPTADIP CONSTRUCTION | 54.29 | 0 | 91
1967 | Birbhum Division | Nalhati Sub-Division | Extention of pipeline by HDPE pipe at Gunia and Kalyanpur habitation for providing FHTC of Haridaspur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division PHED. | AE | JE1 | ORD/000112/2022-2023 | 200/AE/NSD | 01/04/2022 | 45 | M/S S.N CONSTRUCTION | 3.15 | 0 | 100
1968 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 250 CuM capacity O.H.R., Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at NARAYANPUR & its adjoining mouzas wate supply scheme within Sainthia Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000125/2024-2025 | 2238/BHM | 13/08/2024 | 565 | DILIP KUMAR MONDAL | 383.91 | 0 | 80
1969 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE2,Junior Engineer | RTOR000033/2024-2025 | 2488/BHM | 03/09/2024 | 0 | Resource Division | 9.52 | 0 | 0
1970 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE2,Junior Engineer | RTOR000062/2022-2023 | 1421/BHM | 24/04/2023 | 0 | Resource Division | 68.68 | 0 | 0
1971 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR NARAYANPUR WS SCHEME | AE,Assistant Engineer | JE2,Junior Engineer | BILL/00701/2023-2024 | BP-2023-2024-57 | 02/08/2023 | 0 | WBSEDCL | 4.31 | 0 | 0
1972 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR NARAYAN PUR WS SCHEME | AE,Assistant Engineer | JE2,Junior Engineer | BILL/00702/2023-2024 | BP-2023-2024-58 | 02/08/2023 | 0 | WBSEDCL | 10.03 | 0 | 0
1973 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Narayanpur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000777/2022-2023 | 314/Bol.MD | 24/03/2023 | 889 | RAJIB COMPANY | 28.9 | 0 | 90
1974 | Birbhum Division | Birbhum Division | Different works related to water supply scheme at BHEJENA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | ORD/000098/2023-2024 | 1980/BHM | 05/06/2023 | 274 | APURBA MONDAL | 205.69 | 0 | 50
1975 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | RTOR000020/2023-2024 | 1439/BHM | 25/04/2023 | 0 | Resource Division | 23.01 | 0 | 0
1976 | Bolpur Mechanical | Birbhum Division | Quotation deposit for Bhejena Water Supply Scheme P/H-I in Md Bazar CCC under Bolpur Mechanical division, PHE Dte | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | BILL/00900/2024-2025 | BP-24-25-236 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.66 | 0 | 0
1977 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Bhejena PWSS at Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | ORD/000584/2023-2024 | 3386/Bol.MD | 16/10/2023 | 60 | INDTECH ASSOCIATES | 28.01 | 0 | 60
1978 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at Madhupur, Khamedda & Bara-Karttikchungri and its adjoining mouzas water supply scheme within Rampurhat-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000395/2023-2024 | 4163/BHM | 30/10/2023 | 560 | M/S ASHA CONSTRUCTION | 1089.94 | 0 | 40
1979 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Madhupur) Water Supply Scheme under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000565/2022-2023 | 188/RSD | 12/05/2022 | 45 | ECO CARE | 4.36 | 0 | 100
1980 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000135/2023-2024 | 1552/BHM | 26/04/2023 | 0 | Resource Division | 66.54 | 0 | 0
1981 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000228/2023-2024 | 218/BHM | 24/01/2024 | 0 | Resource Division | 2.46 | 0 | 0
1982 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Madhupur PWSS P.H No-I (Block-Rampurhat - II), Margram CCC, WBSEDCL | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/00122/2024-2025 | BP-2024-2025-62 | 05/06/2024 | 0 | WBSEDCL | 3.44 | 0 | 0
1983 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Madhupur PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000987/2023-2024 | 3596/BOL.MD | 08/12/2023 | 60 | DAS ENTERPRISE | 44.5 | 0 | 0
1984 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | RTOR000091/2023-2024 | 1548/BHM | 26/04/2023 | 0 | Resource Division | 9.67 | 0 | 0
1985 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR SADANANDAPUR PH NO-1 | AE(HQ),Assistant Engineer | JE,Junior Engineer | BILL/01570/2023-2024 | BP-23-24-224 | 15/01/2024 | 0 | WBSEDCL | 0.31 | 0 | 0
1986 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for SADANANDAPUR piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000295/2023-2024 | 1500/Bol.MD | 17/07/2023 | 60 | SATYAJIT GHOSH | 27.88 | 0 | 85
1987 | Bolpur Mechanical | Birbhum Division | Supply, delivery and installation of servo motor operated copper wound line voltage corrector at sadanandapur W/S scheme (Asenga I & II) of Md. Bazar block under Bolpur Mechanical Division, P.H.E.Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000759/2024-2025 | 769/BMSD(D) | 26/09/2024 | 30 | DEY ENTERPRISE | 4.33 | 0 | 100
1988 | Birbhum Division | Birbhum Division | Different works for KASHERHAT & Sehana and its adjoining mouzas water supply scheme within SURI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000383/2023-2024 | 4138/BHM | 18/10/2023 | 1079 | PASCON | 975.41 | 0 | 60
1989 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | RTOR000041/2022-2023 | 1388/BHM | 24/04/2023 | 0 | Resource Division | 27.21 | 0 | 0
1990 | Bolpur Mechanical | Birbhum Division | New service connection at Sehana PH-I PWSS, under Suri-II Block. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | BILL/00124/2024-2025 | BP-2024-2025-65 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.87 | 0 | 0
1991 | Bolpur Mechanical | Birbhum Division | New service connection at Sehana PH-II, Suri-II Block | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | BILL/00125/2024-2025 | BP-2024-2025-66 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.59 | 0 | 0
1992 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Sehana PWSS at Suri - II Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000434/2023-2024 | 2106/BOL.MD. | 22/08/2023 | 678 | STANDARD ELECTRICALS | 28.52 | 0 | 100
1993 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at DEOASH, JASODA & JIUI and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000013/2023-2024 | 1194/BHM | 12/04/2023 | 792 | M/S. JAN MAHAMMAD | 1367.24 | 0 | 75
1994 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000049/2022-2023 | 1378/BHM | 24/04/2023 | 0 | Resource Division | 47.2 | 0 | 0
1995 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR UTTAR JASHODA P H NO.I WS SCHEME | AE,Assistant Engineer | JE,Junior Engineer | BILL/01469/2023-2024 | BP-23-24-195 | 14/12/2023 | 0 | WBSEDCL | 7.21 | 0 | 0
1996 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Jashoda & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000050/2023-2024 | 1057/Bol.MD | 08/06/2023 | 663 | SATYAJIT GHOSH | 29 | 0 | 70
1997 | Central Drilling | Birbhum Sadar Sub-Division | Providing Tube Well materials, conforming to IS: 12818 2010 with other works at site for construction of Tube Well in Jashoda W/S Scheme, TW-I, Sainthia Block, Birbhum District under CDD, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000463/2022-2023 | 385/CMSD-I | 05/08/2022 | 15 | C.M. ENTERPRISE | 4.18 | 0 | 100
1998 | Central Drilling | Birbhum Sadar Sub-Division | Supply & Delivery of Consumables with other works at site for construction of Tube Well in Jashoda PWSS , TW-I, Sainthia Block, Birbhum District under CDD, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000464/2022-2023 | 391/CMSD-I | 05/08/2022 | 15 | C.M. ENTERPRISE | 2.66 | 0 | 100
1999 | Central Drilling | Birbhum Sadar Sub-Division | Providing drilling crews for construction of Tube Well by departmental Rig machine in Jashoda W/S Scheme, TW-I, Sainthia Block, Birbhum District under CDD, PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000465/2022-2023 | 397/CMSD-I | 05/08/2022 | 15 | C.M. ENTERPRISE | 3.77 | 0 | 100
2000 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at BARUA GOPALPUR & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000397/2023-2024 | 4162/BHM | 30/10/2023 | 274 | SUNIL RABI DAS | 781.48 | 0 | 0
2001 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000141/2023-2024 | 1579/BHM | 26/04/2023 | 0 | Resource Division | 155.49 | 0 | 0
2002 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for BARUA GOPALPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000884/2023-2024 | 3288/Bol.MD | 29/09/2023 | 60 | PADMA ENGINEERING CO. | 45.96 | 0 | 0
2003 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at BIRCHANDRAPUR, ASURLAYA, BARATURIGRAM & KANAIPUR and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000471/2023-2024 | 505/BHM | 05/02/2024 | 603 | B RAI CONSTRUCTION COMPANY | 2071.77 | 0 | 20
2004 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Bara Turigram) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000829/2022-2023 | 310/RSD | 08/09/2022 | 90 | ENVIROTECH SOLUTIONS | 3.58 | 0 | 100
2005 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Bara Turigram) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000830/2022-2023 | 422/RSD | 03/11/2022 | 90 | ENVIROTECH SOLUTIONS | 3.29 | 0 | 100
2006 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Bara Turigram) Water Supply Scheme (Part-C) under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000831/2022-2023 | 443/RSD | 02/12/2022 | 90 | ENVIROTECH SOLUTIONS | 2.22 | 0 | 100
2007 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000126/2023-2024 | 1543/BHM | 26/04/2023 | 0 | Resource Division | 222.46 | 0 | 0
2008 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Baraturigram PWSS P/H -III under Mayureswar ccc (Block-Mayureswar -I) | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/00952/2024-2025 | BP-2024-25-260 | 18/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0
2009 | Bolpur Mechanical | Rampurhat Sub-Division | New service connection for Baraturigram PH-I Water supply scheme under Bolpur Mechanical Division, P.H.E Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/01089/2024-2025 | BP-24-25-282 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.29 | 0 | 0
2010 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Baraturigram PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000735/2023-2024 | 3478/Bol.MD | 07/11/2023 | 60 | R. N. S. TRADING | 66.79 | 0 | 0
2011 | Bolpur Mechanical | Rampurhat Sub-Division | Supply, delivery & Installation of Submersible Pumping Machinery and other allied work for newly sunk T/W at Baraturigram water supply scheme(Block-Mayureswar-I) under Bolpur Mechanical Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001202/2023-2024 | 369/BOL.MD | 06/03/2024 | 30 | RAJIB GHOSH | 8.79 | 0 | 100
2012 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Baraturigram Piped water supply scheme(PH-III) under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/001204/2023-2024 | 370/BOL.MD | 06/03/2024 | 30 | MASSK ENGINEERING WORKS | 7.19 | 0 | 100
2013 | Birbhum Division | Rampurhat Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 200 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to KANDURI & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000097/2024-2025 | 2110/BHM | 29/07/2024 | 611 | PULAK KUMAR PAL | 409.54 | 0 | 35
2014 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000029/2024-2025 | 2452/BHM | 30/08/2024 | 0 | Resource Division | 12.18 | 0 | 0
2015 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000142/2023-2024 | 1577/BHM | 26/04/2023 | 0 | Resource Division | 9.64 | 0 | 0
2016 | Birbhum Division | Bolpur Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 150 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to Piped Water supply scheme at Bheter & its adjoining mouzas within NANOOR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000112/2024-2025 | 2164/BHM | 05/08/2024 | 365 | PALCON | 301.86 | 0 | 0
2017 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHETER Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000620/2022-2023 | 132/BSD | 05/04/2022 | 90 | RADIANT | 3.27 | 0 | 100
2018 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | RTOR000023/2024-2025 | 2446/BHM | 30/08/2024 | 0 | Resource Division | 6.97 | 0 | 0
2019 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | RTOR000136/2023-2024 | 1553/BHM | 26/04/2023 | 0 | Resource Division | 27.28 | 0 | 0
2020 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Bheter WSS (TW No. I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000955/2024-2025 | 4522/BOL.MD | 20/12/2024 | 377 | SATYAJIT GHOSH | 75.08 | 0 | 50
2021 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE2 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2022 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
2023 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
2024 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Palashbuni & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000681/2022-2023 | 134/BSSD | 18/07/2022 | 45 | RADIANT | 2.72 | 0 | 100
2025 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000245/2023-2024 | 425/BHM | 01/02/2024 | 0 | Resource Division | 131.6 | 0 | 0
2026 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
2027 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
2028 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for laying distribution of Haripur & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000858/2022-2023 | 88/BSSD | 20/05/2022 | 45 | RADIANT | 3.18 | 0 | 100
2029 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Pump House cum Chlorine Room, Boundary Wall, Soil Investigation Report, Construction Over Head Reservoir (OHR), Construction of Pipe carrying structure, Service Road at Head Work Site & Land Development, FHTC Connection of Haripur & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000859/2022-2023 | 93/BSSD | 27/05/2022 | 45 | RADIANT | 2.22 | 0 | 100
2030 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000241/2023-2024 | 427/BHM | 01/02/2024 | 0 | Resource Division | 328.76 | 0 | 0
2031 | Birbhum Division | Birbhum Division | Different works related to water supply scheme at SEKEDDAHA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000109/2024-2025 | 2139/BHM | 31/07/2024 | 730 | M/S GOUTAM DAS | 1425.93 | 0 | 25
2032 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | RTOR000090/2023-2024 | 1497/BHM | 25/04/2023 | 0 | Resource Division | 484.43 | 0 | 0
2033 | Bolpur Mechanical | Birbhum Division | Supply & Installation of Low lift Pumping Mchinery and other allied work for SEKADDAHA & Adjoining moujas water supply scheme within Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000549/2023-2024 | 2145/Bol.MD | 25/08/2023 | 90 | WEST BENGAL ENGINEERING CO. | 75.81 | 0 | 0
2034 | Bolpur Mechanical | Birbhum Division | Supply & Installation of High lift Pumping Mchinery and other allied work for SEKADDAHA & Adjoining moujas water supply scheme within Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000552/2023-2024 | 2148/Bol.MD | 25/08/2023 | 90 | ORIENTAL ENGINEERING CO. | 92.33 | 0 | 10
2035 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Sekedda PWSS (New Tube Well) at Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/001192/2023-2024 | 367/BOL.MD | 06/03/2024 | 30 | HINDOL ROY | 13.96 | 0 | 100
2036 | Birbhum Division | Rampurhat Sub-Division | Additional FHTC works from existing distribution system at Kalikapur,Kajipara,& Narayanghati habitations under Narayanghati mouza within Narayanghati w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte.(Sl.No-27) | AE | JE1 | ORD/000201/2022-2023 | 330/RSD | 08/09/2022 | 30 | TAPAN KUMAR DATTA | 4.98 | 0 | 100
2037 | Birbhum Division | Rampurhat Sub-Division | Additional FHTC works from existing distribution system at different mouzas ie Bhabaghati, Hatinagar, Mahalas, Bandha, Balur & Akna within Narayanghati w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte.(Sl.No-28) | AE | JE1 | ORD/000202/2022-2023 | 331/RSD | 08/09/2022 | 30 | TAPAN KUMAR DATTA | 4.95 | 0 | 100
2038 | Birbhum Division | Rampurhat Sub-Division | Additional FHTC works from existing distribution system at Narayanghati & Bidyadhari habitation under Narayanghati mouzas within Narayanghati w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-29) | AE | JE1 | ORD/000203/2022-2023 | 332/RSD | 08/09/2022 | 30 | TAPAN KUMAR DATTA | 4.97 | 0 | 100
2039 | Birbhum Division | Rampurhat Sub-Division | Providing 01 No. additional FHTC along with allied works from existing distribution system at Narayanghati (Konai Para) Jl. No. 92 under Kundala G.P. within Narayanghati W/S Scheme under Rampurhat Sub- Division, P.H.E. Dte. | AE | JE1 | ORD/000229/2023-2024 | 200/RSD | 28/07/2023 | 7 | ASHUTOSH BISWAS | 0.29 | 0 | 100
2040 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Narayanghati w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-2) | AE | JE1 | ORD/000365/2021-2022 | 1915/BHM | 24/11/2021 | 60 | TAPAN KUMAR DATTA | 82.11 | 0 | 53
2041 | Birbhum Division | Central Mechanical Sub-DivisionIII | Different works related to water supply scheme at PARULIA, KHANPUR & PADUMA and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000076/2023-2024 | 1425/BHM | 25/04/2023 | 982 | BIPIN KUMAR SINGH | 2248.63 | 0 | 55
2042 | Birbhum Division | Central Mechanical Sub-DivisionIII | Laying of distribution system and road restoration at Parulia Piped Water Supply Scheme, Dubrajpur Block, under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000271/2025-2026 | 2417/BHM | 18/09/2025 | 90 | BIPIN KUMAR SINGH | 68.09 | 0 | 0
2043 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000069/2022-2023 | 1402/BHM | 24/04/2023 | 0 | Resource Division | 193.54 | 0 | 0
2044 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing electro-mechanical accessories and others for Parulia & adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000053/2023-2024 | 1060/Bol.MD | 08/06/2023 | 366 | CINZANO | 69.83 | 0 | 0
2045 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at PARULIA, KHANPUR & PADUMA and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000076/2023-2024 | 1425/BHM | 25/04/2023 | 982 | BIPIN KUMAR SINGH | 2248.63 | 0 | 55
2046 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Paduma PWSS at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000397/2023-2024 | 2075/BOL.MD. | 21/08/2023 | 90 | S.P. CONSTRUCTION | 80.24 | 0 | 40
2047 | Birbhum Division | Bolpur Sub-Division | Road restoration work for Punna Piped Water Supply Scheme, Labpur Block, under Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000190/2025-2026 | 2132/BHM | 18/08/2025 | 90 | TEKNO ENTERPRISE | 29.63 | 0 | 0
2048 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at PUNNA PIPED WATER SUPPLY SCHEME(TSM/016169) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000295/2023-2024 | 3668/BHM | 28/08/2023 | 794 | TEKNO ENTERPRISE | 729.3 | 0 | 20
2049 | Birbhum Division | Bolpur Sub-Division | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for PUNNA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.¿. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000950/2022-2023 | 266/BSD | 11/07/2022 | 180 | APEX ENGINEERING | 4.92 | 0 | 100
2050 | Birbhum Division | Bolpur Sub-Division | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for PUNNA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000955/2022-2023 | 305/BSD | 12/08/2022 | 90 | APEX ENGINEERING | 1.41 | 0 | 100
2051 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000161/2023-2024 | 1627/BHM | 28/04/2023 | 0 | Resource Division | 35.82 | 0 | 0
2052 | Bolpur Mechanical | Bolpur Sub-Division | Quotation for new service connection at Punna PWSS P/H- I under Ahmedpur CCC | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | BILL/01091/2024-2025 | BP-24-25-281 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0
2053 | Bolpur Mechanical | Bolpur Sub-Division | Supply Delivery and Installation of automatically Voltage Correction Device at Augmentation for Bolpur SD Hospital & Bolpur water supply scheme under Bolpur Mechanical Divn. PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000582/2024-2025 | 3794/BOL.MD | 12/09/2024 | 30 | EVEREST INFRATECH INC | 6.77 | 0 | 0
2054 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2055 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at DULA SAHAPUR PIPED WATER SUPPLY SCHEME (TSM017017) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000303/2024-2025 | 3022/BHM | 30/10/2024 | 365 | M/S S. CHOUDHURY | 597.84 | 0 | 0
2056 | Birbhum Division | Bolpur Sub-Division | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for DULASAHAPARA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000947/2022-2023 | 232/BSD | 10/06/2022 | 180 | APEX ENGINEERING | 4.92 | 0 | 100
2057 | Birbhum Division | Bolpur Sub-Division | Continuation work for "Preparation & Submission of additional Detail Project Report (DPR) for DULASAHAPARA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000952/2022-2023 | 293/BSD | 29/07/2022 | 90 | APEX ENGINEERING | 1.41 | 0 | 100
2058 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000147/2023-2024 | 1598/BHM | 26/04/2023 | 0 | Resource Division | 23.88 | 0 | 0
2059 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Dula Sahapur PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001118/2024-2025 | 326/BOL.MD | 19/02/2025 | 120 | SUNRISE ENGINEERING CORPORATION | 74.48 | 0 | 0
2060 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2061 | Birbhum Division |  | Construction of Temporary road including removing of bushes & vegetation for Beja W/S Scheme under Rampurhat Sub-Division, P.H.E. Dte. |  |  | ORD/000028/2022-2023 | 177/RSD | 29/04/2022 | 30 | NEEL ENTERPRISE | 1.84 | 0 | 100
2062 | Birbhum Division |  | Additional laying of distribution system at Beja and Chuatari Mouzas for providing FHTC for Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. (Sl.No.04) |  |  | ORD/000169/2022-2023 | 307/RSD | 08/09/2022 | 30 | GOURANGA MONDAL | 4.77 | 0 | 100
2063 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Beja W/S Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. |  |  | ORD/000173/2021-2022 | 1325/BHM | 16/08/2021 | 60 | PRADIP KUMAR SHARMA | 38.54 | 0 | 92
2064 | Birbhum Division |  | Allied works for Additional Laying of UPVC Pipe line for providing FHTC at Dheka and Hapina Mouzas under Beja Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. |  |  | ORD/000521/2021-2022 | 15/RSD | 04/01/2022 | 30 | PRADIP KUMAR SHARMA | 4.27 | 0 | 100
2065 | Birbhum Division |  | Allied works for Additional Laying of UPVC Pipe line for Chuatari,Bandihat and Selhat mouzas under Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. |  |  | ORD/000528/2021-2022 | 16/RSD | 04/01/2022 | 30 | PRADIP KUMAR SHARMA | 4.15 | 0 | 100
2066 | Birbhum Division |  | Allied works for Additional Laying of UPVC Pipe line for Chuatari and Kumarpur Mouzas under Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. |  |  | ORD/000529/2021-2022 | 17/RSD | 04/01/2022 | 30 | PRADIP KUMAR SHARMA | 4.06 | 0 | 100
2067 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at MASTALI Piped Water Supply Scheme (TSM/017207) within Labpur Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000473/2023-2024 | 523/BHM | 05/02/2024 | 517 | PREMANANDA ROY BISWAS | 302.55 | 0 | 20
2068 | Birbhum Division | Bolpur Sub-Division | Continuation work Order for "Preparation & Submission of Detail Project Report (DPR) for MASTALI Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000657/2022-2023 | 172/BSD | 29/04/2022 | 360 | APEX ENGINEERING | 3.16 | 0 | 100
2069 | Bolpur Mechanical | Bolpur Sub-Division | New power connection at Mastali PWSS(P/H-I) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | BILL/00565/2024-2025 | BP-24-25-162 | 27/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.35 | 0 | 0
2070 | Bolpur Mechanical | Bolpur Sub-Division | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000210/2024-2025 | 748./AE-III | 29/04/2024 | 59 | RAJIB GHOSH | 0.28 | 0 | 100
2071 | Bolpur Mechanical | Bolpur Sub-Division | -Hiring of Luxury Car (B-S-IV)Diesel-53-C 3045. for the office of the Assistant Engineer-III/Central Mechanical Division, PHE Dte Suri,Birbhum. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000863/2024-2025 | 1286./AE-III | 23/08/2024 | 31 | RAJIB GHOSH | 0.15 | 0 | 0
2072 | Bolpur Mechanical | Bolpur Sub-Division | Hiring of Luxury Car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division. PHE. Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001382/2023-2024 | 3397/BOL.MD | 31/10/2023 | 121 | RAJIB GHOSH | 0.57 | 0 | 100
2073 | Bolpur Mechanical | Bolpur Sub-Division | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001419/2023-2024 | 119/AE-III | 22/01/2024 | 92 | RAJIB GHOSH | 0.44 | 0 | 100
2074 | Bolpur Mechanical | Bolpur Sub-Division | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001420/2023-2024 | 1132./AE-III | 12/09/2023 | 92 | RAJIB GHOSH | 0.44 | 0 | 100
2075 | Bolpur Mechanical | Bolpur Sub-Division | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001421/2023-2024 | 760/AE-III | 27/06/2023 | 92 | RAJIB GHOSH | 0.44 | 0 | 100
2076 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2077 | Birbhum Division | Birbhum Mechanical (Drill.) Sub-Division | Different works related to water supply scheme at CHARICHA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000396/2023-2024 | 4164/BHM | 30/10/2023 | 609 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 970.91 | 0 | 35
2078 | Birbhum Division | Birbhum Mechanical (Drill.) Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000166/2023-2024 | 1622/BHM | 28/04/2023 | 0 | Resource Division | 248.27 | 0 | 0
2079 | Bolpur Mechanical | Birbhum Mechanical (Drill.) Sub-Division | Supply & Installation of Low lift Pumping Mchinery and other allied work for CHARICHA & Adjoining moujas water supply scheme within Md. Bazar Block under Bolpur Mechanical Division PHE | Assistant Engineer | Junior Engineer | ORD/000550/2023-2024 | 2146/Bol.MD | 25/08/2023 | 90 | KAMAKHYA ENTERPRISE | 31.63 | 0 | 0
2080 | Bolpur Mechanical | Birbhum Mechanical (Drill.) Sub-Division | Supply & Installation of High lift Pumping Mchinery and other allied work for CHARICHA & Adjoining moujas water supply scheme within Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000551/2023-2024 | 2147/Bol.MD | 25/08/2023 | 90 | DEY ENTERPRISE | 90.92 | 0 | 0
2081 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area of Rasa W/S Scheme in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte. | AE | JE2, Birbhum Sadar Sub-Division | ORD/000338/2023-2024 | 3895/BHM | 21/09/2023 | 60 | HIRANMAY GHOSH | 74.96 | 0 | 72
2082 | Birbhum Division | Birbhum Sadar Sub-Division | Allied work for Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area of Rasa W/S Scheme in Suri Sadar Sub-Division under Birbhum Division, PHE Dte. | AE | JE2, Birbhum Sadar Sub-Division | ORD/000369/2023-2024 | 3750/BHM | 05/09/2023 | 45 | RICK CONSTRUCTION | 9.92 | 0 | 100
2083 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasa in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.(Sl. No.9) | AE | JE2, Birbhum Sadar Sub-Division | ORD/000410/2022-2023 | 2587/BHM | 22/11/2022 | 60 | HIRANMAY GHOSH | 58.98 | 0 | 49
2084 | Birbhum Division | Central Mechanical Sub-DivisionIII | Sinking of Tubewell, Construction of OHR, Construction of Boundary wall, pump house and laying distribution system along with FHTC works at Augmentation of Dubrajpur (Rural) & its adjoining mouzas water supply scheme within Dubrajpur under Birbhum Division, PHE Dte. (2nd Call) | Assistant Engineer-III | Junior Engineer | ORD/000472/2023-2024 | 524/BHM | 05/02/2024 | 574 | KOUSIK DAS | 457.67 | 0 | 64
2085 | Birbhum Division | Central Mechanical Sub-DivisionIII | Allied work for Construction of Boundary wall near Mama Bhagne Pahar & Shifting of Rising main pipe line near Sal River Bridge due to pipe line beneath the NH Road under the Augmentation of Dubrajpur Rural Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. Within Birbhum Division, P.H.E. Dte | Assistant Engineer-III | Junior Engineer | ORD/000514/2023-2024 | 662/BHM | 20/02/2024 | 45 | RICK CONSTRUCTION | 4.04 | 0 | 100
2086 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing and installation of High Lift Pumping Machineries including others at Augmentation of Dubrajpur (Rural) Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. Block : Dubrajpur, Dist : Birbhum. | Assistant Engineer-III | Junior Engineer | ORD/001045/2023-2024 | 05/BOL.MD | 03/01/2024 | 90 | SATYAJIT GHOSH | 78.65 | 0 | 40
2087 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing and installation of Low Lift Pumping Machineries including other works for Augmentation of Dubrajpur (Rural) Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. Block : Dubrajpur, Dist : Birbhum | Assistant Engineer-III | Junior Engineer | ORD/001046/2023-2024 | 06/BOL.MD | 03/01/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 41.18 | 0 | 40
2088 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Replacement of PDB cum MCC Panel including other allieds works at Augmentation of Dubrajpur Water Supply Scheme under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/001212/2023-2024 | 374/BOL.MD | 06/03/2024 | 30 | BIRBHUM ELECTRIC WORKS | 8.61 | 0 | 100
2089 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Repairing of Gasious Chlorination system and others at Dubrajpur Aug. water supply scheme under Bolpur Mechanical Division PHE, Dte | Assistant Engineer-III | Junior Engineer | ORD/001313/2023-2024 | 604./AE-III | 27/03/2024 | 21 | ORIENTAL ENGINEERING CO. | 3.84 | 0 | 100
2090 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply and Delivery of 100 KG , baby chlorine cylinder for different water supply scheme under Bolpur Mechanical Division PHE. Dte | Assistant Engineer-III | Junior Engineer | ORD/001322/2023-2024 | 613./AE-III | 27/03/2024 | 21 | UNIVERSAL ENTERPRISES | 4.77 | 0 | 100
2091 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Supply & Delivery at site of 10 H.P Submersible Pumping Machinery for Beluti PWSS at Mayureswar-II Block under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001343/2023-2024 | 612./AE-III | 27/03/2024 | 7 | DEY ENTERPRISE | 1.82 | 0 | 100
2092 | Birbhum Division | Bolpur Sub-Division | Work order for the work of construction of 300 Cum capacity O.H.R with soil investigation, 5.90 X 4.10 m pump room/ Chlorine room with sanitary arrangements. Laying of rising main, Distribution system with FHTC and different works related to DASKALGRAM PIPED WATER SUPPLY SCHEME (TSM/015491) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE4 | ORD/000081/2024-2025 | 1784/BHM | 14/06/2024 | 365 | NEW APOLLO HARDWARE | 663.67 | 0 | 0
2093 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for DASKALGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - B) | Assistant Engineer | JE4 | ORD/000736/2022-2023 | 341/BSD | 05/09/2022 | 90 | RADIANT | 2.54 | 0 | 100
2094 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for DASKALGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | Assistant Engineer | JE4 | ORD/000778/2022-2023 | 255/BSD | 05/07/2022 | 90 | RADIANT | 4.73 | 0 | 100
2095 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE4 | RTOR000002/2024-2025 | 2392/BHM | 27/08/2024 | 0 | Resource Division | 15.79 | 0 | 0
2096 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE4 | RTOR000099/2023-2024 | 1488/BHM | 25/04/2023 | 0 | Resource Division | 74.7 | 0 | 0
2097 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer | JE4 | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2098 | Birbhum Division | Bolpur Sub-Division | Construction of 400 Cum. OHR with Soil Investigation,Pump Room/Chlorine Room with sanitary arrangement,Laying of Rising Main Distribution System with FHTC and different works related to LAYEKPUR PIPED WATER SUPPLY SCHEME (TSM/016003) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000186/2024-2025 | 2771/BHM | 30/09/2024 | 365 | SS ENTERPRISE | 663.03 | 0 | 0
2099 | Birbhum Division | Bolpur Sub-Division | Road restoration work for Layekpur Piped Water Supply Scheme, Labpur Block, under Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000250/2025-2026 | 2242/BHM | 29/08/2025 | 90 | ARUP HAZRA | 27.91 | 0 | 0
2100 | Birbhum Division | Bolpur Sub-Division | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for LAYEKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000948/2022-2023 | 237/BSD | 17/06/2022 | 180 | APEX ENGINEERING | 4.92 | 0 | 100
2101 | Birbhum Division | Bolpur Sub-Division | Continuation work for "Preparation & Submission of additional Detail Project Report (DPR) for LAYEKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000953/2022-2023 | 300/BSD | 10/08/2022 | 90 | APEX ENGINEERING | 2.46 | 0 | 100
2102 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Layekpur PWSS (TW No III), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001134/2024-2025 | 334/BOL.MD | 19/02/2025 | 327 | M/S. UTTAM KUMAR CHATTERJEE | 37.24 | 0 | 0
2103 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2104 | Birbhum Division | Bolpur Sub-Division | Providing Household Tap Connection (FHTC) at Daronda Mouja ( J.L No 129) at different Location from existing distribution system within the command area of Daronda and adjoining Mouza W/S Scheme at Illambazar Block under Bolpur Sub-Division P.H.E Dte within Birbhum Division P.H.E Dte. | Assistant Engineer | JE1 | ORD/000083/2020-2021 | 1087/BHM | 05/09/2020 | 30 | S.S. BHATTACHARJEE. | 4.71 | 4.69 | 0
2105 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chella, Ramnagar, Bonovilla, Lakshipur, Daronda, Dhalla, Saldanga, Usurdihi, Ushahar etc. in different locations under Daronda Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.1) | Assistant Engineer | JE1 | ORD/000122/2022-2023 | 1569/BHM | 26/07/2022 | 60 | HOQUEDAR ALI | 43.32 | 0 | 100
2106 | Birbhum Division | Bolpur Sub-Division | Continution work for Supply of one no. Diesel Motor Cab/Maxi Cub (Air Condition) on hire basis under the Executive Engineer Birbhum Division P.H.E Dte (Period From 01.05.2023 to 31.10.2023) | Assistant Engineer | JE1 | ORD/000165/2023-2024 | 1618/BHM | 27/04/2023 | 183 | PREMANANDA ROY BISWAS | 0.96 | 0 | 60
2107 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre and left out Household at Narayanpur and Daronda village existing distribution System within Nachansaha W/S Scheme and Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 | ORD/000348/2021-2022 | 402/BSD | 25/10/2021 | 10 | NAZIR HOSSAIN | 0.96 | 0 | 0
2108 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre and left out Household at Narayanpur and Daronda village existing distribution System within Nachansaha W/S Scheme and Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 | ORD/000411/2021-2022 | 402/ BSD | 25/10/2021 | 10 | NAZIR HOSSAIN | 0.96 | 0 | 100
2109 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Illambazar (Illambazar & Daronda) within Ruppur & Illambazar G.P.under Bolpur Sub-Division within Birbhum Division, PHED | Assistant Engineer | JE1 | ORD/000459/2021-2022 | 16/BSD | 11/01/2022 | 15 | GANAPATI ENGINEERING CORP. | 1.97 | 0 | 48
2110 | Birbhum Division | Bolpur Sub-Division | Hiring of SWIFT DIZER (Diesel) or equivalent luxury car for office of the Assistant Engineer, Nalhati Sub - Division under Birbhum Division, PHE Dte. (Period from 01.04.2023 to 30.09.2023) 183-Days. | Assistant Engineer | JE1 | ORD/000607/2022-2023 | 130/AE/NSD | 31/03/2023 | 183 | JOY CHAND MAL | 0.86 | 0 | 85
2111 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Saldanga, Dhalla, Lakshmipur, Daranda & Ramnagar of Daranda w/s Scheme at Illambazar Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No.10) | Assistant Engineer | JE1 | ORD/000609/2020-2021 | 1024/BHM | 04/11/2020 | 45 | S.S. BHATTACHARJEE. | 13.82 | 0 | 35
2112 | Birbhum Division | Bolpur Sub-Division | Replacement of UPVC pipe line damaged due to widening of road from Bubahat More towards Chella road along with extension of UPVC pipe line for habitation of Daranda Palpara, Chasapara, Malpara, Bauripara, Darjipara, Suripara, High School Para etc. for Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. 01) | Assistant Engineer | JE1 | ORD/000619/2021-2022 | 241/BSD | 16/07/2021 | 30 | S.S. BHATTACHARJEE. | 4.99 | 0 | 100
2113 | Birbhum Division | Bolpur Sub-Division | Replacement of damaged UPVC pipe line due to widening of road from Bubahat More towards Chella along with extension of UPVC pipe line for the habitation of Halsidanga, Chella, etc. of Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 | ORD/000819/2021-2022 | 457/BSD | 13/12/2021 | 30 | S.S. BHATTACHARJEE. | 4.34 | 0 | 50
2114 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Khujutipara of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (Sl. No.07) | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000044/2020-2021 | 1460/BHM | 12/11/2020 | 45 | MS BUILDWELL | 21.21 | 18.87 | 0
2115 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Sakadda of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (Sl. No.05) | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000046/2020-2021 | 1459/BHM | 12/11/2020 | 60 | MS B N ENTERPRISES | 27.38 | 20.07 | 0
2116 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Chhatingram of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (Sl. No.6) | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000075/2020-2021 | 1422/BHM | 04/11/2020 | 45 | INDRAJIT DAS | 15.08 | 11.18 | 0
2117 | Birbhum Division | Bolpur Sub-Division | Allied works of extension of pipe line for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages of Baitara (in the habitation Suchpur & Baitara) of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000333/2021-2022 | 376/BSD | 05/10/2021 | 30 | M/S KRIPASINDHU GHOSH & CO. | 4.85 | 0 | 100
2118 | Birbhum Division | Bolpur Sub-Division | Allied works of extension pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Nabasta (in the habitation NABASTA) Khujutipara W/S Scheme at Nanoor Block within Bolpur Sub-Division under Birbhum Division P.H.E. Dte. (Mouja: Nabastha Node point 01 to 02) | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000350/2021-2022 | 327/BSD | 01/09/2021 | 30 | MANAS KUMAR MONDAL | 4.84 | 4.61 | 0
2119 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Nabasta of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (2nd Call) (Sl. No.24) | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000359/2020-2021 | 31/BHM | 13/01/2021 | 60 | MANAS KUMAR MONDAL | 28.93 | 0 | 45
2120 | Birbhum Division | Bolpur Sub-Division | Allied works of extension pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Sakadda (in the habitation SERPUR AND SAKADDA) of Khujutipara W/S Scheme at Nanoor Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000417/2021-2022 | 306/BSD | 19/08/2021 | 30 | MS B N ENTERPRISES | 4.9 | 3.54 | 100
2121 | Birbhum Division | Bolpur Sub-Division | Retrofitting of pipe lines From OHR to Khujutipara Fishary Market, Khujutipara for Providing suficient water to Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages SAKKADA of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Part -A). | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000475/2021-2022 | 426/BSD | 22/11/2021 | 30 | MANAS KUMAR MONDAL | 4.85 | 0 | 100
2122 | Birbhum Division | Bolpur Sub-Division | Allied works of extension pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages KHUJUTIPARA of Khujutipara W/S Scheme at Nanoor Block under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000477/2021-2022 | 373/ BSD | 05/10/2021 | 30 | M/S BUILDWELL | 3.82 | 0 | 100
2123 | Birbhum Division | Bolpur Sub-Division | Survey for Functional Household Tap Connection (FHTC) at different School and Anganwadi Centre in Nanoor Block, Bolpur-Sriniketan Block (Part) under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000499/2021-2022 | 312/ BSD | 25/08/2021 | 15 | NAZIR HOSSAIN | 0.1 | 0 | 100
2124 | Birbhum Division | Bolpur Sub-Division | Survey for Functional Household Tap (FHTC) at different School and Anganwadi Centre in Labpur Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000500/2021-2022 | 335/ BSD | 06/09/2021 | 15 | NAZIR HOSSAIN | 0.1 | 0 | 50
2125 | Birbhum Division | Bolpur Sub-Division | Survey for Functional Household Tap Connection (FHTC) at different School and Anganwadi Centre in Labpur Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000501/2021-2022 | 335/ BSD | 06/09/2021 | 15 | NAZIR HOSSAIN | 0.1 | 0 | 50
2126 | Birbhum Division | Bolpur Sub-Division | Retrofitting of pipe lines from Khujutipara Fishary Market to Smashan Kali Mandir, Khujutipar on Basapara-Nanoor Road for Providing Functional Household Tap Connection (FHTC) from existing distribution system at the village Sakadda within the command area of Khujutipara Water Supply Scheme (Part -B) of Bolpur Sub-Division under Birbhum Division, PHED. (Sl. - 08) | Assistant Engineer | JE2 ,JE_BLK_NANOOR | ORD/000523/2021-2022 | 452/BSD | 13/12/2021 | 30 | MANAS KUMAR MONDAL | 3.96 | 0 | 100
2127 | Birbhum Division |  | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chatra-Koma Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. (Sl. No. - 05) |  |  | ORD/000047/2022-2023 | 91/BSSD | 27/05/2022 | 20 | INDRAJIT MONDAL | 4.05 | 0 | 92
2128 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area (Januri, Uttar Metegram, Rajnagar, Shibpur) of Chatra-Koma w/s Scheme at Suri-II Block under Birbhum Division, PHE Dte. (Sl. No.3) |  |  | ORD/000061/2020-2021 | 1282/BHM | 01/10/2020 | 45 | ISLAM CONSTRUCTION | 12.08 | 8.51 | 100
2129 | Birbhum Division |  | Laying Distribution pipeline from MSK school towards main road under Charta- Coma Piped Water Suply Scheme under Birbhum Sadar Sub Division, P.H.E Dte. within Birbhum Division PHE Dte. |  |  | ORD/000084/2023-2024 | 1637/BHM | 02/05/2023 | 30 | SUBHANKAR ROY | 5.3 | 0 | 100
2130 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area (Moldihi, Koma, Kanslpai, Muradpur) of Chatra-Koma w/s Scheme at Suri-II Block under Birbhum Division, PHE Dte. |  |  | ORD/000186/2020-2021 | 1174/BHM | 21/09/2020 | 60 | SYED KHORSID ALAM | 32.84 | 17.04 | 100
2131 | Birbhum Division |  | Extension of pipe line for Providing Functional Household Tap Connection (FHTC) at Kanspai (JL No.82) Muradpur Adibasipara (Jl. No.83), Maldihi Adibashipara (Sl. No.80) & Khanna (Jl. No.) Villages of different locations from existing distribution system within the command area of Chatra-Koma Piped Water Supply Scheme at Suri-II Block under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.09) |  |  | ORD/000381/2020-2021 | 71/ BSSD | 26/02/2021 | 15 | SYED KHORSID ALAM | 3.82 | 0 | 100
2132 | Birbhum Division |  | Extension of pipe line for Providing Functional Household Tap Connection (FHTC) at Kanspai( JL No. - 82) Muradpur Adibasipara (JL No. 83), Maldihi Adibasipara (JL No.-80) & Khanna (JL No.-) Villages of different locations from existing distribution system within the command area of Chatra-Koma Piped Water Supply Scheme at Suri-II Block under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte. (Sl. No. - 09) |  |  | ORD/000608/2020-2021 | 71/BSSD. | 26/02/2021 | 15 | SYED KHORSID ALAM | 3.82 | 0 | 0
2133 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area (Moldihi, Koma, Kanslpai, Muradpur) of Chatra-Koma w/s Scheme at Suri-II Block under Birbhum Division, PHE Dte. |  |  | ORD/000620/2020-2021 | 1174/BHM | 21/09/2020 | 60 | SYED KHORSID ALAM | 32.84 | 0 | 0
2134 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area (Januri, Uttar Metegram, Rajnagar, Shibpur) of Chatra-Koma w/s Scheme at Suri-II Block under Birbhum Division, PHE Dte. (Sl. No.3) |  |  | ORD/000744/2020-2021 | 1281/BHM | 07/10/2020 | 45 | NUR MOBINUL ISLAM | 12.08 | 0 | 75
2135 | Birbhum Division |  | Providing Tap Connection for Existing School & AWC in Naryanpur PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000079/2021-2022 | 278/RSD | 16/07/2021 | 10 | SHIB GANGA CONSTRUCTION | 0.5 | 0 | 0
2136 | Birbhum Division |  | Additional FHTC works from existing distribution system at Narayanpur mouza within Narayanpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-30) |  |  | ORD/000179/2022-2023 | 273/RSD | 16/08/2022 | 30 | SUNIL RABI DAS | 4.85 | 0 | 100
2137 | Birbhum Division |  | Additional FHTC works from existing distribution system at Narayanpur habitation within Narayanpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-31) |  |  | ORD/000180/2022-2023 | 277/RSD | 18/08/2022 | 30 | SUNIL RABI DAS | 4.89 | 0 | 100
2138 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Balia Mrityunjoypur of Narayanpur w/s Scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl. No.3) |  |  | ORD/000226/2020-2021 | 1706/BHM | 23/12/2020 | 60 | SANJUKTA ENGINEERS | 36.44 | 25.01 | 27
2139 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Narayanghati w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-2) |  |  | ORD/000365/2021-2022 | 1915/BHM | 24/11/2021 | 60 | TAPAN KUMAR DATTA | 82.11 | 0 | 53
2140 | Birbhum Division |  | Sinking of o1 (one) No 200mm dia.X 42.0 mtr deep Tube Well with UPVC pipe & strainer for Narayanpur W/s scheme under Birbhum Division, P.H.E. Dte. |  |  | ORD/000543/2021-2022 | 30/RSD | 04/01/2022 | 30 | ISLAM CONSTRUCTION | 2.92 | 0 | 50
2141 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Balia Mrityunjoypur of Narayanpur w/s Scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl. No.3) |  |  | ORD/000607/2020-2021 | 1706 /BHM | 23/12/2020 | 60 | SANJUKTA ENGINEERS | 36.44 | 0 | 100
2142 | Birbhum Division |  | Laying Bypass UPVC Pipe line from CWR to Suripara more for providing drinking water Hattala surrounding Area of Narayanpur W/S Scheme under Rampurhat Sub-Division, P.H.E. Dte within Birbhum Division, P.H.E. Dte. (Sl. No.2) |  |  | ORD/000815/2021-2022 | 2069/BHM | 13/12/2021 | 60 | ISLAM CONSTRUCTION | 13.26 | 0 | 50
2143 | Birbhum Division | RWS Birbhum Sub-Division | Distribution System including providing Functional Household Tap Connection(FHTC) at Lalitakundu Paschim Par within the command area of Bishnupur Water Supply Scheme Under RWS Birbhum Sub-Division,within Birbhum Division,PHE Dte.(Sl. No.07) | AE | JE | ORD/000081/2022-2023 | 136/BH | 15/06/2022 | 30 | BIJOY KUMAR CHOUDHURY | 4.71 | 0 | 50
2144 | Birbhum Division | RWS Birbhum Sub-Division | Providing Functional Household Tap Connection(FHTC) at Lalitakundu Purba Par within the command area of Bishnupur Water Supply Scheme under RWS Birbhum Sub-Division within Birbhum Division, PHE Dte. (Sl. No.08) | AE | JE | ORD/000087/2022-2023 | 137/BH | 15/06/2022 | 20 | BIJOY KUMAR CHOUDHURY | 3.56 | 0 | 100
2145 | Birbhum Division | RWS Birbhum Sub-Division | Providing Functional Household Tap Connection(FHTC) at Baswa Lat Para within the command area of Bishnupur Water Supply Scheme under RWS Birbhum Sub-Divition within Birbhum Division PHE Dte.(Sl. No.09) | AE | JE | ORD/000088/2022-2023 | 138/BH | 15/06/2022 | 20 | BIJOY KUMAR CHOUDHURY | 3.6 | 0 | 50
2146 | Birbhum Division | RWS Birbhum Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Baroipara and its adjoining area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000364/2021-2022 | 177/BH | 03/11/2021 | 15 | TAPAN ENTERPRISE | 4.83 | 0 | 50
2147 | Birbhum Division | RWS Birbhum Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿ (Sl. No.2) | AE | JE | ORD/000664/2021-2022 | 2033/ BHM | 09/12/2021 | 60 | TAPAN KUMAR DATTA | 94.18 | 0 | 40
2148 | Birbhum Division | RWS Birbhum Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000040/2021-2022 | 218/BHM | 02/02/2022 | 0 | Resource Division | 26.49 | 0 | 0
2149 | Birbhum Division | Rampurhat Sub-Division | Providing FHTC from existing distribution system with Allied works at Karkaria mouza within Improvement of Tarapith w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-23) | AE | JE2 | ORD/000182/2022-2023 | 278/RSD | 18/08/2022 | 30 | SHIB GANGA CONSTRUCTION | 4.99 | 0 | 100
2150 | Birbhum Division | Rampurhat Sub-Division | Providing FHTC from existing distribution system with Allied works at Tarapur mouza within Improvement of Tarapith w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-24) | AE | JE2 | ORD/000184/2022-2023 | 280/RSD | 22/08/2022 | 30 | SHIB GANGA CONSTRUCTION | 4.98 | 0 | 100
2151 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tarapit Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte. (Sl. No.11) | AE | JE2 | ORD/000336/2021-2022 | 1770/BHM | 29/10/2021 | 60 | SUNIL RABI DAS | 80.28 | 0 | 100
2152 | Birbhum Division | Rampurhat Sub-Division | Laying of Distribution Main pipeline through crossing of PWD road at Karkaria more East side by adopting Jack Pushing method for Improvement of Tarapith PWSS under Rampurhat Sub-Division, PHE Dte. | AE | JE2 | ORD/000510/2021-2022 | 08/RSD | 04/01/2022 | 15 | SUNIL RABI DAS | 4.14 | 0 | 100
2153 | Birbhum Division | Rampurhat Sub-Division | Laying, joining and interconnecting the tubewells (5 nos.) to OHR with HDPE pipes and Specials including Bypass arrangement for Improvement of Tarapith piped W/S Scheme under Birbhum Division, PHE Dte. (Sl. No.2) | AE | JE2 | ORD/000709/2021-2022 | 1333/BHM | 18/08/2021 | 45 | SACHIN KUMAR SARKAR | 16.23 | 0 | 100
2154 | Birbhum Division | Rampurhat Sub-Division | Rising main with DI pipe line for SHEKPUR Piped Water Supply Scheme under Rampurhat Sub-Division under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000035/2022-2023 | 183/RSD | 02/05/2022 | 30 | AJIMUL ISLAM | 3.98 | 0 | 100
2155 | Birbhum Division | Rampurhat Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sekhpur under Sekhpur Water Supply Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.6) | AE | JE1 | ORD/000123/2022-2023 | 1611/BHM | 28/07/2022 | 60 | M/S KRIPASINDHU GHOSH & CO. | 95.28 | 0 | 100
2156 | Birbhum Division | Rampurhat Sub-Division | Retrofitting works for Providing Balance Functional Household Tap Connection (FHTC) by Sinking of 2 nos. additional Tubewells at Rukumpur & Dumra mouza (200mm dia all through & 150 Mtr Deep) along with Connecting Line, Boundary wall & related works for Sekhpur Piped Water Supply Scheme under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000657/2023-2024 | 1027/BHM | 15/03/2024 | 451 | GOLAM RASUL | 86.37 | 0 | 0
2157 | Birbhum Division | Rampurhat Sub-Division | Sinking of 01 Nos (3 rd ) Tubewell 200mm dia 96 m. deep tube well fitted with PVC pipe and fiber glass Strainer at Sekhpur PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000676/2021-2022 | 106/RSD | 07/03/2022 | 30 | ISLAM CONSTRUCTION | 4.98 | 0 | 100
2158 | Birbhum Division | Nalhati Sub-Division | Sinking of 200 mm dia & 87mtr.deep Tube well fitted with PVC pipe and fibre glass Strainer of Head Work site of Kurumgram Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000108/2022-2023 | 361/AE/NSD | 21/07/2022 | 45 | MD SURAJ ALI | 4.84 | 0 | 100
2159 | Birbhum Division | Nalhati Sub-Division | Replacement including extension of pipe line with FHTC to different habitations of kurumgram village including 200 mm PVC tube well & restoration of roads at Kurumgram Water Supply Scheme under Nalhati Sub-Division within Birbhum Division PHE Dte. | AE | JE1 | ORD/000370/2022-2023 | 1429/BHM | 05/07/2022 | 60 | MD SURAJ ALI | 40.52 | 0 | 95
2160 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kurumgram Water Supply Scheme within Nalhati Sub-Division Birbhum Division, PHE Dte. (2nd Call) (Sl. No.13) | AE | JE1 | ORD/000420/2021-2022 | 2109/BHM | 17/12/2021 | 60 | M/S MD AMINUL ISLAM | 76.13 | 0 | 100
2161 | Birbhum Division | Nalhati Sub-Division | Surging of 2 nos. existing Tube wells and other ancillary works at Kurumgram Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | AE | JE1 | ORD/000639/2021-2022 | 694/AE/NSD | 30/12/2021 | 15 | MD SURAJ ALI | 0.94 | 0 | 100
2162 | Birbhum Division | Bolpur Sub-Division | Survey for Functional Household Tap Connection (FHTC) at various places within coverage area of Bolpur Externally Aidded Project Water Supply Scheme (Zone-VI) under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000024/2021-2022 | 231/BSD | 07/07/2021 | 15 | M/S HORIZEN | 0.1 | 0 | 100
2163 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at NURPUR (Part) & Gheropara (Part) with extension of pipeline from existing distribution system within (Zone-VII) of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, P.H.E. Deptt. (Sl. No.: 03). | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000082/2022-2023 | 252/BSD | 04/07/2022 | 30 | CHAYAN KUMAR MONDAL | 4.81 | 0 | 100
2164 | Birbhum Division | Bolpur Sub-Division | Retrofitting of pipe lines at Laichili Pukurpara, Mirdhapara, Mosjidpara and Korapara of GAYESHPUR Mouja for Providing sufficient water to Functional Household Tap Connection (FHTC) from existing distribution system for Augmentation of Bolpur Water Supply, Sanitation & Health Education Project (Indo-German), under Bolpur Sub-Division within Birbhum Division, P.H.E. Deptt. (Sl. No.: 04). | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000084/2022-2023 | 258/BSD | 07/07/2022 | 30 | PRATICK KUMAR GHOSH | 4.82 | 0 | 100
2165 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from the existing distribution system within the command area of Mouja Durgapur (143), Gitgram (144), Bara Simulia (145), Chota Simulia (145), Dakshin Gobindapur (151), Ramganja (152) & Panchshoa (142) etc. of Zone - X under Augmentation of Bolpur Water Supply, Sanitation & Health Education Project (Indo - German) in Bolpur Sub-Division within Birbhum Division PHE Dte. (Sl. No. - 3) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000097/2022-2023 | 1469/BHM | 11/07/2022 | 60 | SACHIN KUMAR SARKAR | 38.19 | 0 | 100
2166 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at Habitation- Kankutia, village -KANKUTIA, G.P. - Raipur-Supur from existing Distribution System within the command area of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) (Zone-VI) under Bolpur Sub-Division within Birbhum Division, Public Health Engineering Department. (Sl. No.: 05). | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000154/2022-2023 | 308/BSD | 16/08/2022 | 30 | SEKH MAMTAZ HOSSAIN | 4.81 | 0 | 100
2167 | Birbhum Division | Bolpur Sub-Division | Retrofitting works for providing functional household tap connection (FHTC) at Mahidapur village of Zone-VIII by Surging of existing 01 no tube well (Indo-German) along with connecting pipe line & Construction of Switch Room Cum Chlorine Room 2.25 mtr.X 3.00 mtr. Size near BITM (Gopalnagar mouzas) of Bolpur water supply scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000154/2024-2025 | 2614/BHM | 11/09/2024 | 90 | INDRANIL DUTTA | 5.23 | 0 | 100
2168 | Birbhum Division | Bolpur Sub-Division | Survey for Functional Household Tap Connection (FHTC) at Gayeshpur and Bergram under Sian-Muluk Gram Panchayet within coverage area of Bolpur Externally Aided Project Water Supply Scheme (Zone - XI) under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000255/2021-2022 | 310/BSD | 24/08/2021 | 20 | IMAGIN | 0.38 | 0 | 100
2169 | Birbhum Division | Bolpur Sub-Division | Providing Functional Tap Connection (FHTC) from existing distribution System in in Sian MULUK G.P. (Vill. Baidyanathpur, Dwarkanathpur, Purba Islampur, Sahajpur, Sian) within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) (Zone - XI) under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000314/2021-2022 | 382/BSD | 07/10/2021 | 30 | ARABINDA GHOSH | 4.83 | 0 | 100
2170 | Birbhum Division | Bolpur Sub-Division | Providing Functional Tap Connection (FHTC) from existing distribution System in KANKALITALA G.P. Vill.: Layek Bazar, Adityapur, Uttar Narayanpur, Khosh Kadampur (Purbapara) within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) (Zone -XII) under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000315/2021-2022 | 381/BSD | 07/10/2021 | 30 | ARNAB CHANDRA | 4.83 | 0 | 100
2171 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system at MULUK (121) village and Arazi Muluk (125) Village (Part) within the command area of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) (Zone- XIII) under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000317/2021-2022 | 385/BSD | 07/10/2021 | 30 | SYED HASMAT ALI | 4.85 | 0 | 100
2172 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Surul Mouza, JL : 104 (Habitation - MOLDANGA) within the command area of for Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) Zone - VIII under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000319/2021-2022 | 380/BSD | 07/10/2021 | 30 | PRATICK KUMAR GHOSH | 4.22 | 0 | 100
2173 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Augmentation of Bolpur Water Supply, Sanitation & health education project (Indo-German) Zone-XII in Bolpur Sub-Division under Birbhum Division, PHE Dte. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000328/2022-2023 | 2271/BHM | 18/10/2022 | 30 | SUPRIYA RAY | 25.56 | 0 | 100
2174 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) at Zone - XI of Sian Muluk G.P.under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000329/2021-2022 | 399/BSD | 25/10/2021 | 10 | SK.RUHUL AMIN | 0.97 | 0 | 100
2175 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mouja Haripur,(146), Rasulpur (147) and Upparkhara etc. Zone-X under Augmentation of Bolpur W/S Sanitation & Health Education Project (Indo-German) in Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000330/2022-2023 | 2244/BHM | 17/10/2022 | 30 | SUPRIYA RAY | 26.69 | 0 | 100
2176 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system in SHYAMBATI Mouza JL : 67 (Habitation - Shyambati, Subhaspally, Munnapara etc.) within the command area of for Augmentation of Bolpur Water Supply Sanitation & Health Education Project ( Indo- German ) Zone - IX under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000334/2021-2022 | 383/BSD | 07/10/2021 | 30 | B. B. CONSTRUCTION | 4.69 | 0 | 100
2177 | Birbhum Division | Bolpur Sub-Division | Providing Functional Tap Connection (FHTC) at School & Anganwadi Centre from existing distribution System within (Zone ¿ VII) of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000345/2021-2022 | 397/BSD | 25/10/2021 | 10 | MS AD ENTERPRISE | 0.97 | 0 | 100
2178 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health Centre, Govt. institution & Household of Habitation-Damonpur, Mouja Ramkantapur (139) from existing distribution system within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) Zone - X & Zone - XIII within Sian Muluk G.P. of Bolpur Sub -Division under Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000413/2021-2022 | 447 /BSD | 10/12/2021 | 30 | SUBHRADIP SARKAR | 4.85 | 0 | 100
2179 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone- XI Indo -German Water Supply Scheme in Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000471/2021-2022 | 2165/BHM | 24/12/2021 | 60 | SYED HASMAT ALI | 26.72 | 0 | 80
2180 | Birbhum Division | Bolpur Sub-Division | Providing Functional Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone-XIII (Indo-German) Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte (Sl. No. 09) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000474/2021-2022 | 2163/BHM | 24/12/2021 | 60 | BISWARUP GHOSH | 30.65 | 0 | 99
2181 | Birbhum Division | Bolpur Sub-Division | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) in Mehidipur (105) village under Raipur-Supur Gram Panchayat within the Command area of Bolpur Water Supply, Sanitation & Health Education Project (Indo-German), Zone - VIII for Swajal Gram under Bolpur-Sriniketan Block of Bolpur Sub-Division within Birbhum Division P.H.E. Deptt. (Sl. No.7) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000474/2022-2023 | 224/BHM | 20/01/2023 | 45 | B RAI CONSTRUCTION COMPANY | 57.78 | 0 | 100
2182 | Birbhum Division | Bolpur Sub-Division | Extension of 90 Mtr. dia. HDPE pipeline near Udyanpally OHR at Ward no. 6 (Six) under Zone - I for Augmentation of Bolpur Water Supply, Sanitation & Health Education Project (Indo-German), within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No. - 01) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000488/2021-2022 | 301/BSD | 19/08/2021 | 30 | INDRAJIT DAS | 4.97 | 0 | 100
2183 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre from existing distribution System of (Zone ¿ VIII & Zone ¿ IX) under Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHED | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000515/2021-2022 | 398/BSD | 25/10/2021 | 10 | GANAPATI ENGINEERING CORP. | 0.97 | 0 | 100
2184 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) at Zone - XII of Sian Muluk G.P. under Bolpur Sub-Division within Birbhum Division, PHED | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000516/2021-2022 | 400/BSD | 25/10/2021 | 10 | JAYANTA BARAL | 0.96 | 0 | 100
2185 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone - XII Indo German Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No. 08) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000605/2021-2022 | 78/BHM | 18/01/2022 | 60 | SOUMEN CHATTERJEE | 26.72 | 0 | 100
2186 | Birbhum Division | Bolpur Sub-Division | Additional remaining work of C.W.R .and development of land of C.W.R. site at Rasulpur (Near Ajoy River Bank) for Augmentation of Bolpur Water Supply, Sanitation & Health Education Project (Indo-German). Zone - X under Bolpur Sub-Division within Birbhum Division PHED. (Sl. No. - 12) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000607/2021-2022 | 456/BSD | 13/12/2021 | 30 | MS B N ENTERPRISES | 4.14 | 0 | 100
2187 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone -X Indo-German Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No. 13) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000620/2021-2022 | 280/BHM | 09/02/2022 | 162 | PINTU KHAN | 33.49 | 0 | 92
2188 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) at Zone - X and Zone - XIII of Sian Muluk G.P. under Bolpur Sub-Division within Birbhum Division, PHED. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000624/2021-2022 | 401/BSD | 25/10/2021 | 10 | SUBHRADIP SARKAR | 0.97 | 0 | 0
2189 | Birbhum Division | Bolpur Sub-Division | Survey for Functional Household Tap Connection (FHTC) at various places within coverage area of Bolpur Externally Aided Project Water Supply Scheme (Zone-VII) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No. - 02) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000627/2021-2022 | 239/BSD | 16/07/2021 | 30 | M/S HORIZEN | 0.97 | 0 | 0
2190 | Birbhum Division | Bolpur Sub-Division | Survey for Functional Household Tap Connection (FHTC) at various places within coverage area of Bolpur Externally Aided Project Water Supply Scheme (Zone-VI) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No. - 01) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000630/2021-2022 | 237/BSD | 16/07/2021 | 30 | M/S HORIZEN | 0.97 | 0 | 100
2191 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone - IX Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No. - 06) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000632/2021-2022 | 380/BHM | 21/02/2022 | 120 | INDRAJIT DAS | 36.29 | 0 | 100
2192 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone-IX (Indo German) water supply w/s Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.11) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000636/2021-2022 | 1659 / BHM | 30/09/2021 | 60 | HIMANGSU SEKHAR SARKAR | 37.25 | 0 | 100
2193 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at Leftout School & Aganwadi Centre with extension of pipeline from existing distribution system within (Zone-VII) of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 07). | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000647/2021-2022 | 70/BSD | 03/03/2022 | 15 | MS AD ENTERPRISE | 2.53 | 0 | 100
2194 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone-VII Indo German Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.14) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000669/2021-2022 | 578/bhm | 17/03/2022 | 45 | ASHA ENTERPRISE | 25.13 | 0 | 100
2195 | Birbhum Division | Bolpur Sub-Division | Construction of Boundary Wall at CWR site (Goalpara) of Zone-IX of Augmentation of Bolpur Water Supply, Sanitation and Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (155.00m long). (Sl.no. 08) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000699/2021-2022 | 2013/BHM | 31/12/2021 | 30 | ABDUL SALEK MALLIK | 10.35 | 0 | 100
2196 | Birbhum Division | Bolpur Sub-Division | Construction of Boundary Wall at CWR site Head Work site of Zone-III of Augmentation of Bolpur Water Supply, Sanitation and Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (124.00m long). (Sl.no. 07) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000700/2021-2022 | 2016/BHM | 31/12/2021 | 30 | ABDUL SALEK MALLIK | 8 | 0 | 100
2197 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone - VIII Indo German Water Supply Scheme in Bolpur Sub-Division undr Birbhum Division PHED. (Sl. 15) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000713/2021-2022 | 597/BHM | 21/03/2022 | 45 | RADHARANI ENTERPRISE | 25.23 | 0 | 100
2198 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at habitation - Ramchandrapur, Village -Raipur, G.P. - Raipur-Supur from existing distribution system within the command area of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) (Zone-VI) under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 05). | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000716/2021-2022 | 75/BSD | 03/03/2022 | 30 | MAA KANKALI ENTERPRISE | 4.83 | 0 | 100
2199 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) at habitation - Raipur Village -Raipur, G.P. - Raipur-Supur from existing distribution system within the command area of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) (Zone-VI) under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 06). | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000721/2021-2022 | 76/BSD | 03/03/2022 | 30 | SEKH MAMTAZ HOSSAIN | 4.77 | 0 | 100
2200 | Birbhum Division | Bolpur Sub-Division | Retrofitting work of columns bracings shell wall top Dom etc and overall painting of overhead reservoir situated at boipur sub division phe campus of surul WS Scheme under Bolpur Sub Division within Birbhum Division PHE Dte. | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000751/2020-2021 | 1682/BHM | 21/12/2020 | 60 | M/S KRIPASINDHU GHOSH & CO. | 14.59 | 0 | 100
2201 | Birbhum Division | Bolpur Sub-Division | Survey for Functional Household Tap Connection (FHTC) at various places within coverage area of Bolpur Externally Aided Project Water Supply Scheme (Zone - X) (2nd Phase : - Jay Krishnapur, Ramakantapur, Ramganj, Gulandi, Gahara etc.) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (2nd Call). (Sl. No.: 09) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000813/2021-2022 | 347/BSD | 15/09/2021 | 30 | IMAGIN | 0.97 | 0 | 100
2202 | Birbhum Division | Bolpur Sub-Division | Restoration of Cement Concrete road damage due to providing Functional Household Tap Connection (FHTC) from existing distribution system within Kankalitala Gram Panchayet (Vill. - Layek Bazar, Nildanga, Adityapur etc.) within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) Zone-XII under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 09). | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000866/2021-2022 | 58/BSD | 22/02/2022 | 7 | ARNAB CHANDRA | 0.8 | 0 | 92
2203 | Birbhum Division | Bolpur Sub-Division | Laying of Rising Main pipeline from Tube-well no. - II to new O.H.R. of Layekbazar with D.I. (K-9) pipe including inter-connection and extension of pipe line at Paruldanga, Choto Canalpar, Paruldanga Nishapati Colony, Nildanga Adibasipara, Rintoladanga (Dangapara), Jharnadanga etc. for providing FHTC within the command area for Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) Zone - XII under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. noo. - 11) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000950/2021-2022 | 455/BSD | 13/12/2021 | 30 | GANAPATI ENGINEERING CORP. | 4.55 | 0 | 100
2204 | Birbhum Division | Bolpur Sub-Division | Extension of pipeline to Madhakhara, Rasulpur & Haripur mouzas and Supplying & Laying of Rising Main & Distribution main with ERWMS pipe at Golamighat Bridge under ZONE-X for Augmentation of BOLPUR WATER SUPPLY, Sanitation & Health Education Project (INDO-GERMAN), within Bolpur Sub-Division under Birbhum Division, PHED.?(Sl. No.1) | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | ORD/000952/2021-2022 | 1590/BHM | 22/09/2021 | 60 | PRABHAT KUMAR MONDAL. | 43.05 | 0 | 100
2205 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | RTOR000023/2022-2023 | 2209/BHM | 12/10/2022 | 0 | Resource Division | 0.02 | 0 | 0
2206 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE1 ,JE2 ,JE3 ,JE4 | RTOR000042/2021-2022 | 220/BHM | 02/02/2022 | 0 | Resource Division | 54.98 | 0 | 0
2207 | Birbhum Division | Birbhum Division | Different works related to water supply scheme at EKPARA & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000157/2023-2024 | 2067/BHM | 08/06/2023 | 452 | CHOWDHURY ENTERPRISE | 237.87 | 0 | 0
2208 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | RTOR000124/2023-2024 | 1541/BHM | 26/04/2023 | 0 | Resource Division | 9.27 | 0 | 0
2209 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | RTOR000217/2023-2024 | 229/BHM | 24/01/2024 | 0 | Resource Division | 0.62 | 0 | 0
2210 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Ekpara & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer-III | JE1,Junior Engineer | ORD/000926/2023-2024 | 3531/Bol.MD | 29/11/2023 | 60 | BIRBHUM ELECTRIC WORKS | 22.77 | 0 | 30
2211 | Birbhum Division | Birbhum Sadar Sub-Division | Road crossing, Repairing & restoration of damaged pipe lines & PCC roads, sluice valve chambers including all allied works for Monai Piped Water Supply Scheme under Birbhum Division, P.H.E Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000049/2025-2026 | 1512/BHM | 23/05/2025 | 90 | GHOSH ENTERPRISE | 54.1 | 0 | 0
2212 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at MONAI & its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000078/2023-2024 | 1427/BHM | 25/04/2023 | 845 | GHOSH ENTERPRISE | 316.44 | 0 | 80
2213 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE2,Junior Engineer | RTOR000058/2022-2023 | 1419/BHM | 24/04/2023 | 0 | Resource Division | 20.44 | 0 | 0
2214 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUIOTATION FOR MONAI PH NO-I | AE,Assistant Engineer | JE2,Junior Engineer | BILL/01847/2023-2024 | BP-23-24-273 | 15/02/2024 | 0 | WBSEDCL | 3.97 | 0 | 0
2215 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR MONAI PH II WS SCHEME | AE,Assistant Engineer | JE2,Junior Engineer | BILL/02135/2023-2024 | BP-2023-24-296 | 12/03/2024 | 0 | WBSEDCL | 3.45 | 0 | 0
2216 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Monai & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000985/2023-2024 | 3308/BOL.MD | 29/09/2023 | 641 | H.K.DAS & CO. | 28.74 | 0 | 75
2217 | Birbhum Division | Birbhum Division | Different works related to water supply scheme at ASENGA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | ORD/000069/2023-2024 | 1342/BHM | 20/04/2023 | 275 | M/S GOUTAM DAS | 409.61 | 0 | 65
2218 | Birbhum Division | Birbhum Division | Jack pushing for crossing PWD Road at different locations including all other allied works for Asenga piped Water Supply Scheme (Md.Bazar Development Block) under Birbhum Division P.H.E. Dte. | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | ORD/000687/2024-2025 | 863/BHM | 26/03/2025 | 75 | M/S GOUTAM DAS | 65.5 | 0 | 40
2219 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | RTOR000011/2023-2024 | 1433/BHM | 25/04/2023 | 0 | Resource Division | 95.69 | 0 | 0
2220 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR ASENGA P H NO.I WS SCHEME | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | BILL/01449/2023-2024 | BP-23-24-172 | 07/12/2023 | 0 | WBSEDCL | 6.71 | 0 | 0
2221 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR ASENGA PH NO.2 WS SCHEME | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | BILL/01452/2023-2024 | BP-23-24-171 | 07/12/2023 | 0 | WBSEDCL | 3.82 | 0 | 0
2222 | Bolpur Mechanical | Birbhum Division | New Service connection at Asenga WSS, Block- Khoyrasole under Bolpur Mechanical Division, PHE Dte | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | BILL/02146/2023-2024 |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.22 | 0 | 0
2223 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR ASENGA TW-I (OHR SITE) | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | BILL/02251/2023-2024 |  | 14/03/2024 | 0 | WBSEDCL | 3.22 | 0 | 0
2224 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for ASENGA and Adjoining moujas water supply scheme in Md Bazar Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer | Estimator,Junior Engineer | ORD/000399/2023-2024 | 2078/BOL.MD. | 21/08/2023 | 60 | UNIVERSAL ENTERPRISES | 28.8 | 0 | 70
2225 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at LAKSHMI NARAYANPUR & its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000400/2023-2024 | 4176/BHM | 31/10/2023 | 274 | APURBA MONDAL | 472.43 | 0 | 0
2226 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000077/2022-2023 | 1395/BHM | 24/04/2023 | 0 | Resource Division | 168.11 | 0 | 0
2227 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing electro-mechanical accessories and others for Lakshmi Narayanpur & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000385/2023-2024 | 1916/Bol.MD | 10/08/2023 | 366 | S.P. CONSTRUCTION | 72.38 | 0 | 0
2228 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply Delivery & Installation of open well Sub-Mersable Pumping Machinery and allied electro-mechanical works at CWR under Lakshminarayanpur water supply scheme (Block-Nalhati-I) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/001171/2023-2024 | 298/AE-III | 22/02/2024 | 21 | QUAZI NOZRUL ISLAM | 3.32 | 0 | 100
2229 | Birbhum Division | RWS Birbhum Sub-Division | Supply of one no. diesel driven car(Diesel) on hire basis office uses for the officials of the Assistant Engineer, RWS, Birbhum Sub-Division, PHE Dte.(Period from 28.06.2024 to 26.12.2024) | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000089/2024-2025 | 96/RWS | 27/06/2024 | 179 | ADIL CONSTRUCTION | 0.85 | 0 | 0
2230 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
2231 | Birbhum Division | RWS Birbhum Sub-Division | Supply of one no. diesel driven car(diesel) on hire basis office uses for the officials of the Assistant Engineer, RWS,Birbhum Sub-Division, PHE Dte.(Period from 27/12/2024 to 24/07/2025) | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000453/2024-2025 | 204/RWS | 27/12/2024 | 210 | ADIL CONSTRUCTION | 1 | 0 | 0
2232 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
2233 | Birbhum Division | Rampurhat Sub-Division | Allied works for Laying of distribution Pipe line for providing FHTC at Pukurpara, Gopinathpur, Narayanpur,Uchpur, Gragara and Hatin mouza within Basudebpur PWSS under Birbhum Division, P.H.E. Dte. | AE | JE2 | ORD/000087/2023-2024 | 1640/BHM | 02/05/2023 | 45 | M/S BUILDWELL | 7.58 | 0 | 0
2234 | Birbhum Division | Rampurhat Sub-Division | Additional laying of UPVC Pipe line for Maharapur, Routara, Mirpur diff mouzas for providing FHTC under JHIKADDA Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte | AE | JE1 | ORD/000007/2023-2024 | 1086/BHM | 06/04/2023 | 60 | KAZI ZAKIR HOSSAIN | 6.72 | 0 | 100
2235 | Birbhum Division | Rampurhat Sub-Division | Additional FHTC works along with Laying pipelines at different mouzas within Jhikadda W/S under Rampurhat Sub Division, Birbhum, Division, P.H.E Dte. | AE | JE1 | ORD/000314/2022-2023 | 2507/BHM | 17/11/2022 | 45 | KAZI EMDADUL HAQUE | 12.78 | 0 | 100
2236 | Birbhum Division | Rampurhat Sub-Division | Different works related to Water Supply Scheme at CHHAMNA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000190/2023-2024 | 3020/BHM | 14/07/2023 | 718 | S K CONSTRUCTION | 557.28 | 0 | 40
2237 | Birbhum Division | Rampurhat Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
2238 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (CHHAMNA) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000834/2022-2023 | 287/RSD | 31/08/2022 | 45 | ENVIROTECH SOLUTIONS | 3.43 | 0 | 100
2239 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (CHHAMNA) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000835/2022-2023 | 371/RSD | 21/09/2022 | 45 | ENVIROTECH SOLUTIONS | 2.5 | 0 | 100
2240 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000096/2023-2024 | 1493/BHM | 25/04/2023 | 0 | Resource Division | 17.09 | 0 | 0
2241 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000213/2023-2024 | 233/BHM | 24/01/2024 | 0 | Resource Division | 8.62 | 0 | 0
2242 | Bolpur Mechanical | Rampurhat Sub-Division | NEW SERVICE CONNECTION AT CHHAMNA PWSS PH-II UNDER BOLPUR MECHANICAL DIVISION PHE Dte... | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00023/2024-2025 | BP-24-25-10 | 25/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.41 | 0 | 0
2243 | Bolpur Mechanical | Rampurhat Sub-Division | NEW SERVICE CONNECTION AT CHHAMNA PWSS PH-I UNDER BOLPUR MECHANICAL DIVISION, PHE Dte... | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00024/2024-2025 | BP-24-25-11 | 25/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.1 | 0 | 0
2244 | Bolpur Mechanical | Rampurhat Sub-Division | New service connection at Chhamna Pump House-3, under Bolpur Mech. Division, P.H.e. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00074/2024-2025 | BP-2024-2025-28 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.13 | 0 | 0
2245 | Bolpur Mechanical | Rampurhat Sub-Division | Operation and Guarding of pumping machinery and others at Chhamna PWSS, Block: Mayureswar- II (Pump House No. I), under Bolpur MechanicalDivision, P.H.E Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000836/2024-2025 | 1636./AE-III | 21/10/2024 | 92 | SUNIL RABIDAS | 0.89 | 0 | 0
2246 | Bolpur Mechanical | Rampurhat Sub-Division | Operation and Guarding of pumping machinery and others at Chhamna PWSS,Block: Mayureswar- II (Pump House No. II), under Bolpur MechanicalDivision, P.H.E Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000837/2024-2025 | 1637./AE-III | 21/10/2024 | 92 | SUNIL RABIDAS | 0.89 | 0 | 0
2247 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Chhamna PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000844/2023-2024 | 3283/BOL.MD | 29/09/2023 | 60 | SUNIL RABIDAS | 55.68 | 0 | 40
2248 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Chamna PWSS, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/001216/2023-2024 | 401/Bol.MD | 07/03/2024 | 45 | M/S SWAPAN BANERJEE | 25.28 | 0 | 90
2249 | Birbhum Division | RWS Birbhum Sub-Division | Road restoration work at different villages under implementation of Mini Piped Water Supply Scheme within Suri-II,Nanoor,Md Bazar Block having less than 100 Households under Birbhum Division PHE Dte. | AE,Assistant Engineer (HQ) | JE1,Junior Engineer | ORD/000175/2025-2026 | 2094/BHM | 14/08/2025 | 90 | BHASKAR MANDAL | 29.4 | 0 | 35
2250 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer (HQ) | JE1,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
2251 | Birbhum Division | Rampurhat Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, Boundary wall, High Lift Pump house (11 m x 6 m) and Sinking of 200 mm Dia all Through Tube Well related to water supply scheme at Kanaipur Piped Water Supply Scheme within Rampurhat-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000066/2025-2026 | 1581/BHM | 02/06/2025 | 90 | BENGAL ENGINEERING | 69.7 | 0 | 0
2252 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at KANAIPUR & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000206/2023-2024 | 3251/BHM | 26/07/2023 | 705 | BENGAL ENGINEERING | 564.7 | 0 | 30
2253 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Kanaipur) Water Supply Scheme under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000628/2022-2023 | 220/RSD | 21/06/2022 | 90 | ENVIROTECH SOLUTIONS | 4.93 | 0 | 100
2254 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000105/2023-2024 | 1513/BHM | 26/04/2023 | 0 | Resource Division | 57.41 | 0 | 0
2255 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000218/2023-2024 | 235/BHM | 24/01/2024 | 0 | Resource Division | 9.27 | 0 | 0
2256 | Bolpur Mechanical | Rampurhat Sub-Division | New service connection at Kanaipur PH-II PWSS ,Mayureswar- I , under Bolpur mechanical Division, P.H.E Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/00109/2024-2025 | BP-2024-2025-48 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.27 | 0 | 0
2257 | Bolpur Mechanical | Rampurhat Sub-Division | New service connection at Kanaipur PH-I PWSS , Mayureswar-I Block under Bolpur Mechanical Division,P.H.E Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/00110/2024-2025 | BP-2024-2025-49 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.8 | 0 | 0
2258 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories (H/L and L/L) and others for Kanaipur & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000526/2023-2024 | 2168/Bol.MD | 31/08/2023 | 578 | SATYAJIT GHOSH | 77.69 | 0 | 48
2259 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at KAYERA Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000019/2023-2024 | 1214/BHM | 12/04/2023 | 275 | USHA ENTERPRISE | 334.74 | 0 | 5
2260 | Birbhum Division | Bolpur Sub-Division | Hiring of 01 (One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, P.H.E Dte. under Birbhum Division, P.H.E Dte. For the period of 01.04.2024 to 30.09.2024. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000704/2023-2024 | 269/BSD | 15/03/2024 | 184 | SK AKRAM HOSSAIN | 0.86 | 0 | 100
2261 | Birbhum Division | Bolpur Sub-Division | Preparation & Submission of Detail Project Report (DPR) for KAYERA Water Supply Scheme & SHRICHANDRAPUR Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/001118/2021-2022 | 99/BSD | 15/03/2022 | 90 | M/S R DUTTA & CO. | 4.65 | 0 | 100
2262 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | RTOR000081/2023-2024 | 1489/BHM | 25/04/2023 | 0 | Resource Division | 11.95 | 0 | 0
2263 | Bolpur Mechanical | Bolpur Sub-Division | New Service connection of Kayera PWSS P/H- I (Block- Illambazar) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | BILL/00135/2024-2025 | BP-2024-2025-54 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.83 | 0 | 0
2264 | Bolpur Mechanical | Bolpur Sub-Division | Additional Quotation for extra involvement of materials against consumer ID 503652443 at Koyra site under Illambazar ccc | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | BILL/00970/2024-2025 | BP-2024-25-266 | 25/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.54 | 0 | 0
2265 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2266 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at TALWAN & its adjoining mouzas water supply scheme within Mayureswar-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (3rd Call) | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000476/2023-2024 | 601/BHM | 09/02/2024 | 733 | PRALAY ROY | 309.43 | 0 | 35
2267 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Talowan) Water Supply Scheme under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000637/2022-2023 | 264/RSD | 29/07/2022 | 90 | ENVIROTECH SOLUTIONS | 3.58 | 0 | 100
2268 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation money for new service connection at Talowan PWSS P/H- I under Mollarpur CCC | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/00823/2024-2025 | BP-24-25-184 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.75 | 0 | 0
2269 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Taloan PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000722/2023-2024 | 3471/Bol.MD | 07/11/2023 | 60 | QUAZI NOZRUL ISLAM | 43.81 | 0 | 40
2270 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at SIMGRAM & its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000100/2023-2024 | 1719/BHM | 12/05/2023 | 615 | M/S MD AMINUL ISLAM | 69.99 | 0 | 65
2271 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000103/2023-2024 | 1530/BHM | 26/04/2023 | 0 | Resource Division | 10.16 | 0 | 0
2272 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Simgram Water Supply Scheme P/H -I in Paikar CCC under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00091/2024-2025 | BP-2024-2025-42 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.97 | 0 | 0
2273 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Simgram Water Supply Scheme P/H -II in Paikar CCC under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00114/2024-2025 | BP-2024-2025-53 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.08 | 0 | 0
2274 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for SIMGRAM piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000548/2023-2024 | 2144/Bol.MD | 25/08/2023 | 60 | S.G.TECHNICAL SERVICES | 25.67 | 0 | 60
2275 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at NAOADANGAL & its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000579/2022-2023 | 935/BHM | 23/03/2023 | 275 | SYED KHORSED ALAM | 434.91 | 0 | 15
2276 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000083/2022-2023 | 1400/BHM | 24/04/2023 | 0 | Resource Division | 240.3 | 0 | 0
2277 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000178/2023-2024 | 2171/BHM | 23/06/2023 | 0 | Resource Division | 3.42 | 0 | 0
2278 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000189/2023-2024 | 3278/BHM | 27/07/2023 | 0 | Resource Division | 5.69 | 0 | 0
2279 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR NAOADANGAL | AE,Assistant Engineer-III | JE,Junior Engineer | BILL/01576/2023-2024 | BP-23-24-204 | 04/01/2024 | 0 | WBSEDCL | 8.4 | 0 | 0
2280 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Naoadangal & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000365/2023-2024 | 1842/Bol.MD | 01/08/2023 | 90 | ORIENTAL ENGINEERING CO. | 54.58 | 0 | 50
2281 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/001048/2023-2024 | ..1299/Bol.MD | 28/06/2023 | 123 | SATYAJIT GHOSH | 1.58 | 0 | 100
2282 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply, Delivery and Installation of 1 M.T. HOT crane at High Lift Pump House of Noadangal water supply scheme under Bolpur Mechanical Division, PHE. Dte | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/001237/2023-2024 | 537/BOL.MD | 14/03/2024 | 383 | ORIENTAL ENGINEERING CO. | 8.48 | 0 | 100
2283 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at CHARKALGRAM PIPED WATER SUPPLY SCHEME(TSM/016091) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE_BLK_NANOOR | ORD/000151/2024-2025 | 2608/BHM | 11/09/2024 | 365 | GARGO TRADERS | 432.8 | 0 | 0
2284 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHARKALGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | Assistant Engineer | JE_BLK_NANOOR | ORD/000734/2022-2023 | 235/BSD | 15/06/2022 | 180 | RADIANT | 4.94 | 0 | 100
2285 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHARKALGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - B). | Assistant Engineer | JE_BLK_NANOOR | ORD/000735/2022-2023 | 310/BSD | 16/08/2022 | 180 | RADIANT | 2.18 | 0 | 100
2286 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE_BLK_NANOOR | RTOR000064/2023-2024 | 1470/BHM | 25/04/2023 | 0 | Resource Division | 26.63 | 0 | 0
2287 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Angora & Charkalgram Water supply Scheme, Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer | JE_BLK_NANOOR | ORD/000968/2024-2025 | 4537/BOL.MD | 20/12/2024 | 285 | MENAKA ENTERPRISE | 73.34 | 0 | 100
2288 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer | JE_BLK_NANOOR | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2289 | Birbhum Division | Nalhati Sub-Division | Restoration of Roads, pucca drain including Jack pushing & Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Sariha piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000048/2025-2026 | 1509/BHM | 23/05/2025 | 90 | M/S GOUTAM DAS | 83.28 | 0 | 10
2290 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Majhkaltia, Sahira & KANAPIUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000075/2023-2024 | 1348/BHM | 20/04/2023 | 835 | M/S GOUTAM DAS | 1594.34 | 0 | 28
2291 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000170/2023-2024 | 2177/BHM | 23/06/2023 | 0 | Resource Division | 14.08 | 0 | 0
2292 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Sariha PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000881/2023-2024 | 3366/BOL.MD | 11/10/2023 | 627 | T.D.K. ENTERPRISE | 27.35 | 0 | 40
2293 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
2294 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
2295 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Demurtita & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000674/2022-2023 | 96/BSSD | 06/06/2022 | 45 | RADIANT | 1.59 | 0 | 100
2296 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000239/2023-2024 | 441/BHM | 01/02/2024 | 0 | Resource Division | 54.82 | 0 | 0
2297 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at MONACHITURA PIPED WATER SUPPLY SCHEME (TSM/017000) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000366/2024-2025 | 3155/BHM | 19/11/2024 | 365 | M/S TAPAS KUMAR CHAKRABORTY | 574 | 0 | 0
2298 | Birbhum Division | Bolpur Sub-Division | Preparation & Submission of Detail Project Report (DPR) for MONACHITURA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001135/2021-2022 | 100/BSD | 15/03/2022 | 180 | APEX ENGINEERING | 4.92 | 0 | 100
2299 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Mona Chaitura PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001130/2024-2025 | 332/BOL.MD | 19/02/2025 | 120 | OSMAN SEKH | 76.25 | 0 | 50
2300 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2301 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at BALIARA & its adjoining mouzas water supply scheme within NANOOR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000077/2023-2024 | 1426/BHM | 25/04/2023 | 275 | M/S REBATI SANKAR SINHA | 378.55 | 0 | 0
2302 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BALIARA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/001134/2021-2022 | 103/BSD | 16/03/2022 | 90 | RADIANT | 4.36 | 0 | 100
2303 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | RTOR000133/2023-2024 | 1559/BHM | 26/04/2023 | 0 | Resource Division | 22.71 | 0 | 0
2304 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Baliara WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000962/2024-2025 | 4531/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.08 | 0 | 0
2305 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,JE_BLK_NANOOR,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2306 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
2307 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
2308 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Noapara & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000672/2022-2023 | 86/BSSD | 19/05/2022 | 45 | RADIANT | 3.33 | 0 | 100
2309 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000244/2023-2024 | 432/BHM | 01/02/2024 | 0 | Resource Division | 142.08 | 0 | 0
2310 | Birbhum Division | RWS Birbhum Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Baliharpur Water Supply Scheme within Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.5) | AE |  | ORD/000020/2022-2023 | 820/BHM | 13/04/2022 | 60 | S S ENTERPRISE | 93.73 | 0 | 100
2311 | Birbhum Division | RWS Birbhum Sub-Division | Balance work for Providing Functional Household tap connections (FHTC) from existing distribution system within the command area of Baliharpur piped water supply scheme (Palan and rest of Baliharpur , Muralpur, Kusumkandar, Salchatra , Kendsarail, Dhatrabandhi,Hosaipur & bhagabandha ) under Birbhum Sadar sub division P.H.E Dte. | AE |  | ORD/000096/2023-2024 | 1645/BHM | 02/05/2023 | 712 | BIJOY KUMAR CHOUDHURY | 57.82 | 0 | 96
2312 | Birbhum Division | RWS Birbhum Sub-Division | Dressing and levelling of over undulated existing land of CWR & pump house site by earth cutting at plot no.295 mouza-Hinglo, JL No.40 for Baliharpur Piped Water Supply Scheme of Block-Md. Bazar under Birbhum Division, PHE Dte, (Sl. No.7) | AE |  | ORD/000111/2022-2023 | 762/BHM | 06/04/2022 | 10 | GOUTAM DAS | 0.96 | 0 | 100
2313 | Birbhum Division | RWS Birbhum Sub-Division | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Baliharpur Piped Water Supply Scheme within Birbhum Sadar Sub-Division under Birbhum Division, P.H.E Dte. | AE |  | ORD/000604/2022-2023 | 1048/BHM | 31/03/2023 | 647 | M/S GOUTAM DAS | 15.07 | 0 | 100
2314 | Birbhum Division | RWS Birbhum Sub-Division | Work Order for Sinking of 2 (Two) nos. 200 mm dia. Tubewell of 6m depth with horizontal strainer on the river Bed of Dwarka River and Connecting Pipe line from Tubewells to C.W.R under Baliharpur Piped Water Supply Scheme in Mahammad Bazar Block, Dist: Birbhum under Birbhum Division, P.H.E. Dte. (Sl. No.-01) | AE |  | ORD/000809/2021-2022 | 418/BHM | 24/02/2022 | 30 | BHABATARAN SADHU | 4.29 | 0 | 100
2315 | Birbhum Division | RWS Birbhum Sub-Division | Laying remaining portion DI(K9) clear water rising main Pipe Line from CWR towards OHR under Baliharpur Piped Water Supply Scheme in Mahammad Bazar Block, Dist: Birbhum under Birbhum Division P.H.E. Dte. (Sl. No.-02) | AE |  | ORD/000811/2021-2022 | 417/BHM | 24/02/2022 | 30 | LAXMI NARAYAN ENGINEERS CO-OP SOCIETY LTD | 1.78 | 0 | 100
2316 | Birbhum Division | RWS Birbhum Sub-Division | Trial Bore for Sinking of 200mm dia. Tubewell on the river Bank & Bed of Dwaraka under Baliharpur Piped Water Supply Scheme under Birbhum Division P.H.E. Dte. (Sl. No.-01) | AE |  | ORD/000836/2021-2022 | 2025 /BHM | 04/01/2022 | 30 | BHABATARAN SADHU | 0.45 | 0 | 100
2317 | Birbhum Division | Nalhati Sub-Division | Extension of pipe line including FHTC for left out habitations along with FHTC at Raghunathpur PWSS under Nalhati Sub Division P.H.ED.. (Sl.No.05) | AE | JE2 | ORD/000560/2022-2023 | 875/BHM | 21/03/2023 | 75 | DUBE ENTERPRISE | 60.43 | 0 | 85
2318 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at DHANASAHA, CHHATAR-BANDI, BHABANIPUR, BHUBANESWAR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer | JE1 | ORD/000384/2023-2024 | 4141/BHM | 19/10/2023 | 709 | B RAI CONSTRUCTION COMPANY | 2996.46 | 0 | 5
2319 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHUBANESWAR Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - A) | Assistant Engineer | JE1 | ORD/000763/2022-2023 | 162/BSD | 25/04/2022 | 90 | M/S R DUTTA & CO. | 4.93 | 0 | 100
2320 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHUBANESWAR Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - B) | Assistant Engineer | JE1 | ORD/000764/2022-2023 | 267/BSD | 14/07/2022 | 90 | M/S R DUTTA & CO. | 1.07 | 0 | 100
2321 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE1 | RTOR000058/2023-2024 | 1450/BHM | 25/04/2023 | 0 | Resource Division | 129.25 | 0 | 0
2322 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer | JE1 | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2323 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
2324 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE2 | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
2325 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Baghasola & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE2 | ORD/000669/2022-2023 | 77/BSSD | 05/05/2022 | 45 | RADIANT | 2.22 | 0 | 100
2326 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE2 | RTOR000234/2023-2024 | 434/BHM | 01/02/2024 | 0 | Resource Division | 109.46 | 0 | 0
2327 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at CHANDRAPUR & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000026/2023-2024 | 1093/BHM | 06/04/2023 | 720 | SADANANDA CHATTARAJ | 377 | 0 | 100
2328 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000035/2023-2024 | 1455/BHM | 25/04/2023 | 0 | Resource Division | 110.67 | 0 | 0
2329 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR CHANDRAPUR WATER SUPPLY SCHEME | AE,Assistant Engineer-III | JE,Junior Engineer | BILL/01833/2023-2024 | BP-23-24-260 | 06/02/2024 | 0 | WBSEDCL | 15.71 | 0 | 0
2330 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing electro-mechanical accessories and others for Chanddrapur water supply scheme in Rajnagar block under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000387/2023-2024 | 1918/Bol.MD | 10/08/2023 | 662 | A.K. INDUSTRIES | 90.43 | 0 | 80
2331 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply & delivery of different electrical accessories at Chandrapur Piped water supply scheme under Bolpur Mechanical Division, PHE Dte.(Rajnagar Block) | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000584/2024-2025 | 1478./AE-III | 11/09/2024 | 7 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 2.11 | 0 | 100
2332 | Birbhum Division | Rampurhat Sub-Division | Sinking of 200 mm dia Alll through and 150 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements,, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I & Zone- II and Providing functional household tap connection related to water supply scheme at Augmentation Of Ground Water Based Hazarpur Zone-I & Zone-II Piped Water Supply Scheme within RAMPURHAT-II Block underBIRBHUM Division, PHE Dte | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000435/2024-2025 | 3432/BHM | 16/12/2024 | 365 | MONDAL& CO | 434.56 | 0 | 25
2333 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000099/2022-2023 | 974/BHM | 27/03/2023 | 0 | Resource Division | 183.82 | 0 | 0
2334 | Bolpur Mechanical | Rampurhat Sub-Division | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Wells and allieds works at Augmentation of Hazarpur [( Zone-I, Pump House No - II ) and ( Zone-II, Pump House No - I & II )] Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000454/2023-2024 | 2131/Bol.MD | 25/08/2023 | 646 | QUAZI NOZRUL ISLAM | 68.76 | 0 | 30
2335 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at RAUTGARA & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000569/2022-2023 | 902/BHM | 22/03/2023 | 651 | PULAK KUMAR PAL | 173.47 | 0 | 100
2336 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Rautgara) Water Supply Scheme under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000633/2022-2023 | 236/RSD | 05/07/2022 | 90 | ENVIROTECH SOLUTIONS | 2.15 | 0 | 100
2337 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000027/2023-2024 | 1567/BHM | 26/04/2023 | 0 | Resource Division | 4.49 | 0 | 0
2338 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE1,Junior Engineer | RTOR000200/2023-2024 | 196/BHM | 22/01/2024 | 0 | Resource Division | 0.12 | 0 | 0
2339 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR RAUTGARA PUMP HOUSE NO-I& II | AE,Assistant Engineer-III | JE1,Junior Engineer | BILL/02119/2023-2024 | BP-2023-24-291 | 06/03/2024 | 0 | WBSEDCL | 2.78 | 0 | 0
2340 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Delivery of Pumping Machinery for Routgara water supply scheme Block Mayureswar ¿ I under Bolpur Mechanical Division PHE. Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000196/2024-2025 | 946./AE-III | 27/06/2024 | 7 | M. S. ENTERPRISE | 1.49 | 0 | 100
2341 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Rautgara PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000351/2023-2024 | 1748/Bol.MD | 27/07/2023 | 891 | M. S. ENTERPRISE | 45.04 | 0 | 90
2342 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of Submersible Cable acceessories for Routgara Piped water supply scheme. under Bolpur Mechanical Division, PHE. Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000352/2024-2025 | 1183./AE-III | 09/08/2024 | 10 | RAJIB GHOSH | 0.99 | 0 | 100
2343 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of submersible cable accessories at Routgara Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000430/2024-2025 | 1296./AE-III | 27/08/2024 | 7 | RAJIB GHOSH | 2.52 | 0 | 100
2344 | Bolpur Mechanical | Rampurhat Sub-Division | Supply & delivery of different electrical accessories at Routgara Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000460/2024-2025 | 1308./AE-III | 28/08/2024 | 7 | TAPAN ENTERPRISE | 2.95 | 0 | 100
2345 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Delivery of Sub-Mersible Pump Controllers for Routgara water supply scheme under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE1,Junior Engineer | ORD/000528/2024-2025 | 1453./AE-III | 09/09/2024 | 7 | M/S. YOUTH ENGINEERS' ENTERPRISE | 2.86 | 0 | 100
2346 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at GOPINATHPUR PIPED WATER SUPPLY SCHEME (TSM/016258) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000010/2023-2024 | 1091/BHM | 06/04/2023 | 275 | M/S R B ENTERPRISE | 495.22 | 0 | 0
2347 | Birbhum Division | Bolpur Sub-Division | Continuation work Order for "Preparation & Submission of Detail Project Report (DPR) for GOPINATHPUR Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000662/2022-2023 | 214/BSD | 31/05/2022 | 180 | APEX ENGINEERING | 4.22 | 0 | 100
2348 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000158/2023-2024 | 1601/BHM | 27/04/2023 | 0 | Resource Division | 19.19 | 0 | 0
2349 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Gopinathpur PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001122/2024-2025 | 328/BOL.MD | 19/02/2025 | 120 | M/S. UTTAM KUMAR CHATTERJEE | 74.48 | 0 | 0
2350 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2351 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at THIBA PIPEED WATER SUPPLY SCHEME (TSM/017115) within Labpur Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000161/2024-2025 | 2662/BHM | 13/09/2024 | 365 | PATHIK PABAN NANDI | 243.95 | 0 | 0
2352 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for THIBA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000661/2022-2023 | 208/BSD | 25/05/2022 | 180 | APEX ENGINEERING | 3.16 | 0 | 100
2353 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000155/2023-2024 | 1603/BHM | 27/04/2023 | 0 | Resource Division | 20 | 0 | 0
2354 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Thiba PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001133/2024-2025 | 337/BOL.MD | 19/02/2025 | 239 | PADMA ENGINEERING CO. | 75.59 | 0 | 40
2355 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2356 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
2357 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
2358 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Chora & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000673/2022-2023 | 92/BSSD | 27/05/2022 | 45 | RADIANT | 1.41 | 0 | 100
2359 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000117/2023-2024 | 1500/BHM | 25/04/2023 | 0 | Resource Division | 0.22 | 0 | 0
2360 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE,Junior Engineer | RTOR000238/2023-2024 | 439/BHM | 01/02/2024 | 0 | Resource Division | 54.82 | 0 | 0
2361 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at AMLACHATURI & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000401/2023-2024 | 4136/BHM | 18/10/2023 | 806 | M/S KRIPASINDHU GHOSH & CO. | 531.73 | 0 | 20
2362 | Birbhum Division | Birbhum Sadar Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
2363 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000037/2023-2024 | 1574/BHM | 26/04/2023 | 0 | Resource Division | 20.07 | 0 | 0
2364 | Bolpur Mechanical | Birbhum Sadar Sub-Division | QUOTATION FOR AMLACHATURI PWSS | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/00011/2024-2025 | BP-24-25-05 | 09/04/2024 | 0 | WBSEDCL | 5.03 | 0 | 0
2365 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Amlachaturi & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000525/2023-2024 | 2167/Bol.MD | 31/08/2023 | 584 | SATYAJIT GHOSH | 88.42 | 0 | 85
2366 | Birbhum Division | Rampurhat Sub-Division | Sinking of 250 X 150 mm Dia (through) and 180 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Budhigram & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000413/2024-2025 | 3315/BHM | 04/12/2024 | 730 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 346.49 | 0 | 30
2367 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Budhigram) Water Supply Scheme under Rampurhat-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000638/2022-2023 | 276/RSD | 18/08/2022 | 45 | ECO CARE | 4.73 | 0 | 100
2368 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000084/2023-2024 | 1490/BHM | 25/04/2023 | 0 | Resource Division | 17.6 | 0 | 0
2369 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Budhigram PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000474/2023-2024 | 2227/Bol.MD | 12/09/2023 | 688 | SUNIL RABIDAS | 44.41 | 0 | 30
2370 | Bolpur Mechanical | Rampurhat Sub-Division | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Budhigram PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/001233/2023-2024 | 519/BOL.MD | 14/03/2024 | 349 | TAPAN ENTERPRISE | 7.61 | 0 | 60
2371 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at NABAGRAM, SAHAPUR & SHASPUR and its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000268/2023-2024 | 3522/BHM | 11/08/2023 | 821 | SUNIL RABI DAS | 1157.77 | 0 | 40
2372 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000134/2023-2024 | 1556/BHM | 26/04/2023 | 0 | Resource Division | 138.02 | 0 | 0
2373 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000227/2023-2024 | 219/BHM | 24/01/2024 | 0 | Resource Division | 5.24 | 0 | 0
2374 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation for new service connection at Sahapur TW No-I (Block-Rampurhat-II) | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02222/2023-2024 |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.89 | 0 | 0
2375 | Bolpur Mechanical | Rampurhat Sub-Division | WBSEDCL QUOTATION FOR SAHAPUR TW-II | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/02248/2023-2024 |  | 14/03/2024 | 0 | WBSEDCL | 3.21 | 0 | 0
2376 | Bolpur Mechanical | Rampurhat Sub-Division | Providing electro-mechanical accessories and others for Shapaur & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000772/2022-2023 | 307/Bol.MD | 23/03/2023 | 366 | A. G. ENTERPRISE | 93.34 | 0 | 0
2377 | Bolpur Mechanical | Rampurhat Sub-Division | Providing electro mechanical accessories and others for Sahapur and Adjoining Mouzas Water Supply Scheme under Bolpur Mechanical Division, PHE Dte | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000784/2022-2023 | 319/Bol.MD | 27/03/2023 | 366 | A. G. ENTERPRISE | 93.34 | 0 | 50
2378 | Birbhum Division | Central Mechanical Sub-DivisionIII | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuMOHR (ZONE-I) & 350 CuM (ZONE-II) ,Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at MASHRA & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000145/2024-2025 | 2514/BHM | 04/09/2024 | 365 | GARGO TRADERS | 915.63 | 0 | 0
2379 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000044/2024-2025 | 3264/BHM | 02/12/2024 | 0 | Resource Division | 24.27 | 0 | 0
2380 | Birbhum Division | Central Mechanical Sub-DivisionIII | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer | RTOR000079/2023-2024 | 1571/BHM | 26/04/2023 | 0 | Resource Division | 14.85 | 0 | 0
2381 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing Electro-mechanical accessories and others for Masra Zone - II PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000877/2023-2024 | 3520/BOL.MD | 29/11/2023 | 60 | CINZANO | 28.82 | 0 | 0
2382 | Bolpur Mechanical | Central Mechanical Sub-DivisionIII | Providing Electro-mechanical accessories and others for Masra Zone - I PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000910/2023-2024 | 3521/Bol.MD | 29/11/2023 | 60 | DEY ENTERPRISE | 27.71 | 0 | 0
2383 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at DADPUR & its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000555/2022-2023 | 839/BHM | 16/03/2023 | 1234 | NABIN DEBNATH | 315.84 | 0 | 80
2384 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000043/2023-2024 | 1537/BHM | 26/04/2023 | 0 | Resource Division | 31.16 | 0 | 0
2385 | Bolpur Mechanical | Nalhati Sub-Division | Additional Quotation charges for Modification of Dadpur, Murarai CCC under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | BILL/00088/2024-2025 | BP-2024-2025-17 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.69 | 0 | 0
2386 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for empowering Dadpur Water Supply Scheme P/H -III in Murarai CCC under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | BILL/00222/2024-2025 | BP-24-25-106 | 02/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.7 | 0 | 0
2387 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION MONEY FOR DADPUR P H NO.I WS SCHEME | AE,Assistant Engineer | JE3,Junior Engineer | BILL/01822/2023-2024 | BP-23-24-253 | 06/02/2024 | 0 | WBSEDCL | 2.72 | 0 | 0
2388 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION MONEY FOR DADPUR P H NO.II WS SCHEME | AE,Assistant Engineer | JE3,Junior Engineer | BILL/01824/2023-2024 | BP-23-24-254 | 06/02/2024 | 0 | WBSEDCL | 2.7 | 0 | 0
2389 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for DADPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000886/2023-2024 | 3289/Bol.MD | 29/09/2023 | 784 | QUAZI NOZRUL ISLAM | 27.77 | 0 | 60
2390 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply Scheme (Zone-II) under Nalhati Sub Division within Birbhum Division PHED. |  |  | ORD/000016/2022-2023 | 229/AE/NSD | 21/04/2022 | 45 | MD ZIAUL ISLAM | 3.34 | 0 | 0
2391 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Ramchandrapur in Gopalpur w/s Scheme at under Nalhat Sub Division, PHE Dte. (Sl. No.13) |  |  | ORD/000117/2020-2021 | 1711/BHM | 23/12/2020 | 60 | UMWELT ENGINEER PVT. LTD | 31.5 | 31.3 | 100
2392 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Gopalpur in Gopalpur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.15) |  |  | ORD/000135/2020-2021 | 1710/BHM | 23/12/2020 | 60 | SUNIL RABI DAS | 29.13 | 29.13 | 100
2393 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply Scheme (Zone-II) under Nalhati Sub Division within Birbhum Division PHED. |  |  | ORD/000141/2022-2023 | 383/AE/NSD | 10/08/2022 | 45 | MD ZIAUL ISLAM | 3.34 | 0 | 50
2394 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Ramchandrapur, Kestara in Gopalpur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.14) |  |  | ORD/000224/2020-2021 | 1712/BHM | 23/12/2020 | 60 | MLG CONSTRUCTION | 37.12 | 37.48 | 100
2395 | Birbhum Division |  | Work order for collection of Household Data through Mobile App/Hard copy including Geo-reference and submission of the same in soft copy against completed FHTC works at the command area of Murarai W/S Scheme under Birbhum Division |  |  | ORD/000254/2021-2022 | 145/BH | 07/09/2021 | 10 | M/S S.N CONSTRUCTION | 0.1 | 0 | 0
2396 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000284/2021-2022 | 508/AE/NSD | 01/10/2021 | 45 | SHIB GANGA CONSTRUCTION | 4.67 | 0 | 67
2397 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Ramchandrapur and Kestora under Murarai-I Block within the command area of Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000285/2021-2022 | 509/AE/NSD | 01/10/2021 | 45 | SUPRABHAT RABIDAS | 4.66 | 0 | 33
2398 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000294/2021-2022 | 508/AE/NSD | 01/10/2021 | 45 | SHIB GANGA CONSTRUCTION | 4.67 | 0 | 67
2399 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Ramchandrapur and Kestora under Murarai-I Block within the command area of Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000295/2021-2022 | 509/AE/NSD | 01/10/2021 | 45 | SUPRABHAT RABIDAS | 4.66 | 0 | 33
2400 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Narayanghati w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-2) |  |  | ORD/000548/2021-2022 | 1915 /BHM | 24/11/2021 | 60 | TAPAN KUMAR DATTA | 82.11 | 0 | 100
2401 | Birbhum Division |  | Laying of HDPE Pipe line for Induripara at Balur mouza for providing FHTC under Narayanghati Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. |  |  | ORD/000680/2021-2022 | 122/RSD | 11/03/2022 | 30 | TAPAN KUMAR DATTA | 4.94 | 0 | 100
2402 | Birbhum Division |  | Laying of HDPE Pipe line for Akna, Balur, Nima dangal at diff mouzas for providing FHTC under Narayanghati Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. |  |  | ORD/000681/2021-2022 | 123/RSD | 11/03/2022 | 30 | TAPAN KUMAR DATTA | 4.93 | 0 | 0
2403 | Birbhum Division |  | Laying of HDPE Pipe line for Kalikapur, Mahalas at Kalikapur mouza for providing FHTC under Narayanghati Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. |  |  | ORD/000682/2021-2022 | 124/RSD | 11/03/2022 | 30 | TAPAN KUMAR DATTA | 4.96 | 0 | 100
2404 | Birbhum Division |  | Laying of HDPE Pipe line for Narayanghati mouza for providing FHTC under Narayanghati Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. |  |  | ORD/000683/2021-2022 | 125/RSD | 11/03/2022 | 30 | TAPAN KUMAR DATTA | 4.98 | 0 | 100
2405 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Harisara w/s Scheme in Nalhati Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-6) | AE | JE1 | ORD/000241/2021-2022 | 1334/BHM | 18/08/2021 | 60 | PRAVAT SARKAR | 55.76 | 0 | 100
2406 | Birbhum Division | Nalhati Sub-Division | Extention of UPVC pipe line to the Harisara habitation within Harisara PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000656/2021-2022 | 524/AE/NSD | 08/10/2021 | 30 | B.M.SARKAR | 4.82 | 0 | 0
2407 | Birbhum Division |  | Sinking of replacement the tubewell 200mm dia & 87 m. deep with PVC pipe and fibre glass Strainer at Bhabanandapur (near head work side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. |  |  | ORD/000003/2022-2023 | 207/AE/NSD | 05/04/2022 | 30 | A R ENTERPRISE | 4.79 | 0 | 100
2408 | Birbhum Division |  | Extention of UPVC pipeline for providing FHTC in different habitation under Bhabanandapur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division PHED. |  |  | ORD/000036/2022-2023 | 264/AE/NSD | 11/05/2022 | 45 | ASGAR SK | 4.84 | 0 | 100
2409 | Birbhum Division |  | Extension of UPVC pipe line for providing FHTC at Bhabanandapur habitation under Bhabanandapur PWSS under Nalhati Sub-Division, within Birbhum Division P.H.E Dte. |  |  | ORD/000054/2022-2023 | 281/NSD | 20/05/2022 | 30 | SURJASISH DATTA | 1.45 | 0 | 100
2410 | Birbhum Division |  | Continuation Work of Hiring of Ambassador Car (Diesel) registered Luxury Taxi for the office of the Assistant Egineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition for 364 days (from 02.07.2021 to 30.06.2022) for 364 days (from 02.07.2022 to 30.06.2023). |  |  | ORD/000066/2022-2023 | 223/RSD | 23/06/2022 | 364 | SOUMITA PAL | 2.04 | 0 | 50
2411 | Birbhum Division |  | Extention of pipeline by HDPE pipe at Nasipur habitation for providing FHTC of Bhabanandapur W/S Scheme, under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. |  |  | ORD/000094/2022-2023 | 279/NSD | 20/05/2022 | 30 | MD ASIF ALI | 2.16 | 0 | 100
2412 | Birbhum Division |  | Providing functional household tap connection (FHTC) from existing distribution system in Bhabanandapur Uttarpara and Its adjoining areas of Bhabanandapur Habitation under Bhabanandapur Mouza (JL.24) under Nalhati -I Block. of Bhabanandapur Water Supply Scheme (Sl.No.01) |  |  | ORD/000204/2020-2021 | 1648/BHM | 18/12/2020 | 90 | A R ENTERPRISE | 4.74 | 4.74 | 0
2413 | Birbhum Division |  | Laying distribution system for proposed augmentation scheme for Bara Zone-II Piped Water Supply Scheme under Nalhati-II Block, under Birbhum Division, PHE Dte.(Sl. No.1) |  |  | ORD/000211/2022-2023 | 805/BHM | 12/04/2022 | 180 | MANASH GHOSH | 397.16 | 0 | 100
2414 | Birbhum Division |  | Providing functional household tap connection (FHTC) from existing distribution system in Bhabanandapur purbapara and its adjoining areas of Bhabanandapur Habitation under Bhabanandapur Mouzas (Jl.24) under Nalhati -I of Bhabanandapur Wsater Supply scheme (Sl.no.03) |  |  | ORD/000213/2020-2021 | 1650/BHM | 18/12/2020 | 120 | SURJASISH DATTA | 4.67 | 4.67 | 0
2415 | Birbhum Division |  | Providing functional house hold tap connection (FHTC) form existing distribution system in Bhabanandapur Dakshinpara and its adjoining areas of Bhabanandapur Habitation under Bhabanandapur Mouza (J.L.24) under Nalhati-I Block within the command area of Bhabanandapur WS Scheme.(Sl.No.02) |  |  | ORD/000217/2020-2021 | 1649/BHM | 18/12/2020 | 90 | ASGAR SK | 4.7 | 4.7 | 0
2416 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Bhabanandapur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000286/2021-2022 | 510/AE/NSD | 01/10/2021 | 45 | SURJASISH DATTA | 4.67 | 0 | 50
2417 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Bhabanandapur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000296/2021-2022 | 510/AE/NSD | 01/10/2021 | 45 | SURJASISH DATTA | 4.67 | 0 | 50
2418 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Jerapara, Nachpahari, Sialdanga & Tarapur habitation & its adj. areas under Bhabanandapur Village (JL No.24) under Nalhati-I Block, within the command area of Bhabanandapur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.03) |  |  | ORD/000306/2020-2021 | 51/NSD | 08/02/2021 | 30 | KAZI ZAKIR HOSSAIN | 4.97 | 4.97 | 0
2419 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Nasipur Uttarpara and its and adjoining areas under Nasipur Habitaiton within Bhabanandapur villages (JL no 24)under Nalhati I Block within the command area of Bhabandaapur water supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (SL no. 03) |  |  | ORD/000360/2020-2021 | 52/NSD | 08/02/2021 | 60 | NUR MOBINUL ISLAM | 4.98 | 4.98 | 100
2420 | Birbhum Division |  | Hiring of SWIFT DIZER (Diesel) or equivalent luxury car for office of the Assistant Engineer, Nalhati Sub - Division under Birbhum Division, PHE Dte. (Period from 01.10.2023 to 31.03.2024) 182-Days. |  |  | ORD/000375/2023-2024 | 353/NSD | 29/09/2023 | 182 | JOY CHAND MAL | 0.86 | 0 | 100
2421 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Nasipur Dakshinpara and its adjoining areas, under Nasipur Habitation within Bhabanandapur village (J.L.-24) under Nalhati-1 Block within the command area of Bhabanandapur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. |  |  | ORD/000436/2020-2021 | 53/AE/NSD | 08/02/2021 | 60 | MD SHAHAJAMAL | 4.98 | 0 | 100
2422 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Bhabanandapur Paschimpara and it's adjoining areas, under Bhabanandapur Habitation under Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000454/2020-2021 | 50/AE/NSD | 08/02/2021 | 60 | SURJASISH DATTA | 4.59 | 4.59 | 50
2423 | Birbhum Division |  | Extention of Pipeline along with FHTC at left out habitations of BHABANANDAPUR PWSS under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. (Sl. No.11) |  |  | ORD/000490/2022-2023 | 289/BHM | 01/02/2023 | 225 | M/S SARADA CONSTRUCTION. | 16.48 | 0 | 100
2424 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Bhabanandapur Paschimpara and it's adjoining areas, under Bhabanandapur Habitation under Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000503/2020-2021 | 50/AE/NSD | 08/02/2021 | 60 | SURJASISH DATTA | 4.59 | 0 | 50
2425 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Jerapara, Nachpahari,Sialdanga, Tarapur Hbitations and it's adjoining areas, under Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000504/2020-2021 | 51/AE/NSD | 08/02/2021 | 60 | KAZI ZAKIR HOSSAIN | 4.97 | 0 | 100
2426 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Nasihapur uttarpara and adjoining areas under Nasihapur Habitation, within Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000505/2020-2021 | 52/AE/NSD | 08/02/2021 | 60 | NUR MOBINUL ISLAM | 4.98 | 0 | 0
2427 | Birbhum Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Nasihapur Purba para and it's adjoining areas, under Nasihapur Habitation under Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. |  |  | ORD/000506/2020-2021 | 54/AE/NSD | 08/02/2021 | 60 | GOLAM RASUL | 4.98 | 4.98 | 100
2428 | Birbhum Division |  | Supply of one No. Diesel driven Motor Cab/Maxi Car (Air Condition) on hire basis under the Executive Engineer, Birbhum Division, P.H.E Dte. (Period from 01.11.2022 to 30.04.2023) |  |  | ORD/000694/2022-2023 | 2322/BHM | 28/10/2022 | 184 | PREMANANDA ROY BISWAS | 0.96 | 0 | 84
2429 | Birbhum Division |  | Continuation Work Order for Supply of one no. diesel driven Motor Cab (Non Air-conditioned) on hire basis for official uses of the Assistant Engineer, Birbhum Sadar Sub-Division, P.H.E Dte. (Period from 01.09.2021 to 28.02.2022) |  |  | ORD/001171/2021-2022 | 305/BSSD | 31/05/2021 | 183 | RITA RABIDAS | 0.71 | 0 | 60
2430 | Birbhum Division | Bolpur Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of "INDUS W/S Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte. " (Sl. No. 05) | Assistant Engineer | JE1 | ORD/000414/2021-2022 | 2065/BHM | 13/12/2021 | 60 | QUAZI SIRAJUL ISLAM. | 61.02 | 0 | 100
2431 | Birbhum Division | Bolpur Sub-Division | Rising Main Pipe line from TW1, TW2 to OHR including of CI specials for proposed INDUS piped Water Supply Scheme, under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No.: 1) | Assistant Engineer | JE1 | ORD/000596/2020-2021 | 21/BSD | 29/01/2021 | 30 | SYED HASMAT ALI | 1.45 | 0 | 100
2432 | Birbhum Division | Bolpur Sub-Division | Supply and delivery of 80mm dia. Sluice Valves, including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Indas Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 03). | Assistant Engineer | JE1 | ORD/000657/2021-2022 | 27/BSD | 21/01/2022 | 15 | MAKALI ENGINEERING CORPORATION | 0.65 | 0 | 100
2433 | Birbhum Division | Nalhati Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sadashibpur (Bisor) Water Supply Scheme within Nalhati Sub-Division Birbhum Division, PHE Dte. (Sl. No.1) | AE | JE1 | ORD/000018/2022-2023 | 822/BHM | 13/04/2022 | 60 | QUAZI SIRAJUL ISLAM. | 94.04 | 0 | 100
2434 | Birbhum Division | Nalhati Sub-Division | Restoration of concrete road including dismantling of Water Supply Scheme For Sadashibpur and it's adjoining Mouzas under Nalhati Sub-Division, within Birbhum Division P.H.E Dte. | AE | JE1 | ORD/000105/2022-2023 | 356/AE/NSD | 20/07/2022 | 60 | SUPER SKILL | 4.83 | 0 | 100
2435 | Birbhum Division | Nalhati Sub-Division | Supply & delivery of Sluice Valve for Sadashibpur (Bishor) W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, PHE Dte (Sl. No.-03) | AE | JE1 | ORD/000132/2022-2023 | 1243/BHM | 03/06/2022 | 15 | MAKALI ENGINEERING CORPORATION | 4.99 | 0 | 100
2436 | Birbhum Division | Nalhati Sub-Division | Balance work of distribution pipeline including extention of pipeline along with FHTC and restoration of roads alongwith Construction of 500 M³ capacity 20.00 Mtr. staging height RCC Over Head Reservoir at Sadasibhpur W/S Scheme within Nalhati Sub-Division under Birbhum Division, P.H.E. Dte.(Sl. No.3) | AE | JE1 | ORD/000385/2022-2023 | 2857/BHM | 22/12/2022 | 557 | SUPER SKILL | 175.35 | 0 | 100
2437 | Birbhum Division | Nalhati Sub-Division | Balance work for Pump House at Head Work site of Sadashibpur PWSS under Nalhati Sub-Division within Birbhum Division, PHED. | AE | JE1 | ORD/000686/2021-2022 | 168/AE/NSD | 22/03/2022 | 15 | SUBHRANIL DAS | 0.83 | 0 | 100
2438 | Birbhum Division | Nalhati Sub-Division | Supply & delivery of Sluice Valve for augmentation of Sadashibpur (Bisor) W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, PHE Dte. (Sl. No.-03) | AE | JE1 | ORD/000805/2021-2022 | 715/BHM | 31/03/2022 | 15 | MAKALI ENGINEERING CORPORATION | 4.99 | 0 | 100
2439 | Birbhum Division | Nalhati Sub-Division | Balance works of Laying Distribution system at Sadasibpur, Kendishta, Chhatina and Amudda habitations under Sadashibpur W/S Scheme under Nalhati Sub-Division, within Birbhum Division P.H.E Dte.. (SL.No.5) | AE | JE1 | ORD/000826/2021-2022 | 498/BHM | 02/03/2022 | 45 | SUPER SKILL | 47 | 0 | 100
2440 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE | JE1 | RTOR000037/2021-2022 | 213/BHM | 02/02/2022 | 0 | Resource Division | 15.63 | 0 | 0
2441 | Birbhum Division | Birbhum Sadar Sub-Division | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Bandirban Zone-VI Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte | AE | JE2 | ORD/000169/2024-2025 | 2709/BHM | 24/09/2024 | 90 | BISWARUP GHOSH | 95 | 0 | 0
2442 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of village Kuralmita, Muktipur under Block Rajnagar for ensuing draught like situation within Birbhum Division, PHE Dte. (Sl. No. - 02) | AE | JE2 | ORD/000268/2022-2023 | 000079 | 28/09/2022 | 30 | ROY BISWAS CONSTRUCTION | 0 | 0 | 0
2443 | Birbhum Division | Birbhum Sadar Sub-Division | Laying of distribution system including FHTC at Karidhya, Kalipur, Amaipur, Laksmindarpur, Baramahula Chhora & Brojergram Mouza for Bandirban (Kanmara) Zone IV Piped Water Supply Scheme, Suri-I Block under Birbhum Sadar Sub-Division, P.H.E. Dte. Within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000572/2024-2025 | 431/BHM | 10/02/2025 | 203 | PREMANANDA ROY BISWAS | 189.3 | 0 | 75
2444 | Birbhum Division | Birbhum Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV under Bandirban Water Supply Water Supply Scheme within Birbhum Division, PHE Dte | AE | JE2 | ORD/000576/2023-2024 | 729/BHM | 28/02/2024 | 361 | S R ENTERPRISE | 83.89 | 0 | 95
2445 | Birbhum Division | Birbhum Sadar Sub-Division | Laying of distribution system including FHTC at Bandirban (Kanmara) Zone I, II, III Tasarkata, Ranpur & Lambodarpur Zone IV, Zone- V, VI Piped Water Supply Scheme, Suri-I Block under Birbhum Sadar Sub-Division, P.H.E. Dte. Within Birbhum Division P.H.E. Dte. | AE | JE2 | ORD/000619/2024-2025 | 611/BHM | 03/03/2025 | 90 | SYED KHORSED ALAM | 183.69 | 0 | 0
2446 | Birbhum Division | Birbhum Sadar Sub-Division | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Choto Alaunda in Suri I covered under Bandirban Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000652/2023-2024 | 1025/BHM | 15/03/2024 | 123 | BHABANI ENTERPRISE | 30.93 | 0 | 35
2447 | Birbhum Division | Birbhum Sadar Sub-Division | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Junedpur in Suri I, II & Sainthia covered under Bhandirbon Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000653/2023-2024 | 1023/BHM | 15/03/2024 | 60 | ARKA JYOTI GHOSH | 31.99 | 0 | 25
2448 | Birbhum Division | Birbhum Sadar Sub-Division | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Itagoria in Suri I covered under Bandirban Water Supply Scheme under Suri Sadar-Sub Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000656/2023-2024 | 1021/BHM | 15/03/2024 | 60 | RANJIT GHOSH | 29.38 | 0 | 40
2449 | Birbhum Division | Birbhum Sadar Sub-Division | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Bandirban Zone-V Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000676/2023-2024 | 1038/BHM | 15/03/2024 | 487 | SOUMEN CHATTERJEE | 48.94 | 0 | 35
2450 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 300 Cum capacity and 20.0m staging height RCC Over Head Reservoir & Laying distribution system including all allied works as per departmental drawing (DRG. No. PC-I/OHR/07/2012) at Zone-V under the Piped Water Supply Scheme for Bandirban (Kanmara) Suri-I & Rajnagar Block under Birbhum Division, PHE Dte (Sl. No.5) | AE | JE2 | ORD/000714/2021-2022 | 1994/BHM | 07/12/2021 | 1093 | APURBA MONDAL | 180.84 | 0 | 87
2451 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 150 Cum Capacity and 20.0m Staging Height RCC Over Head Reservoir along with Soil Test and Laying pipeline for Augmentation of Nagari w/s Scheme under Birbhum Sadar Sub-Division within Birbhum Division,P.H.E. Dte. (Sl. No.6) | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000432/2022-2023 | 105/BHM | 11/01/2023 | 180 | M/S KRIPASINDHU GHOSH & CO. | 189.64 | 0 | 75
2452 | Birbhum Division | Birbhum Sadar Sub-Division | Trial Bore and Sinking for 03 nos. working 200mm dia. Tubewell of 6m depth each with horizontal strainer on the river Bed of Kuskurini and connecting pipe line etc. complete under Augmentation of Nagari Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000509/2023-2024 | 652/BHM | 20/02/2024 | 45 | INDRANIL DUTTA | 7.99 | 0 | 100
2453 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000003/2023-2024 | 1114/BHM | 10/04/2023 | 0 | Resource Division | 2.73 | 0 | 0
2454 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000100/2022-2023 | 970/BHM | 27/03/2023 | 0 | Resource Division | 11.88 | 0 | 0
2455 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000194/2023-2024 | 3275/BHM | 27/07/2023 | 0 | Resource Division | 0.34 | 0 | 0
2456 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Quotation for new service connection at Augmentation of Nagari PWSS at SURI-I Block | AE,Assistant Engineer-III | JE3,Junior Engineer | BILL/00995/2024-2025 | BP-24-25-270 | 04/12/2024 | 0 | WBSEDCL | 6.24 | 0 | 0
2457 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply & delivery of Electrical accessories for Augmentation of Nagari water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000453/2024-2025 | 1301./AE-III | 27/08/2024 | 111 | HINDOL ROY | 2.8 | 0 | 100
2458 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Wells and allied works at Augmentation of Nagari Piped Water Supply Scheme, Block-Suri-I under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000470/2023-2024 | 2223/Bol.MD | 12/09/2023 | 60 | HINDOL ROY | 23.52 | 0 | 50
2459 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply & delivery of 80mm dia Column Pipe for Augmentation of Nagari water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. " | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000499/2024-2025 | 1450./AE-III | 09/09/2024 | 7 | VIBGYOR INFOTECH | 2.96 | 0 | 100
2460 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Replacement of Centrifugal Pumping Machinery and allide works at Karidhya water supply scheme (Suri-I) under Bolpur Mechanical Division, P.H.E. Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000540/2024-2025 | 3799/BOL.MD | 12/09/2024 | 30 | WEST BENGAL ENGINEERING CO. | 10.68 | 0 | 0
2461 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 200 CuM capacity O.H.R, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at MEHERPUR & its adjoining mouzas water supply scheme within Sainthia Block including supply of all labour & materials under BIRBHUM Division, PHE Dte" | AE,Assistant Engineer | JE,Junior Engineer | ORD/000130/2024-2025 | 2264/BHM | 14/08/2024 | 715 | PRANAB KUMAR GHOSH | 327.36 | 0 | 0
2462 | Birbhum Division | Birbhum Sadar Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer | JE,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
2463 | Birbhum Division | Birbhum Sadar Sub-Division | Sinking of 02(Two) nos. 200mm X 200 mm X 174m deep Tube Wells Fitted With M.S Housing & Well Pipe by Direct Rotary Rig for Meharpur and Adjacent areas Piped Water Supply Scheme, Block: Sainthia under Birbhum Division, P.H.E Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000525/2024-2025 | 259/BHM | 21/01/2025 | 60 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 24.15 | 0 | 0
2464 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000037/2024-2025 | 2491/BHM | 03/09/2024 | 0 | Resource Division | 9.36 | 0 | 0
2465 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000060/2022-2023 | 1417/BHM | 24/04/2023 | 0 | Resource Division | 21.84 | 0 | 0
2466 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Meherpur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000422/2023-2024 | 2092/Bol.MD | 22/08/2023 | 647 | A.S.ENTERPRISE | 28.01 | 0 | 60
2467 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at KASHIMNAGAR, KAMARKHUL & GAGANPUR and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000288/2023-2024 | 3647/BHM | 25/08/2023 | 274 | BENGAL ENGINEERING | 1204.06 | 0 | 30
2468 | Birbhum Division | Nalhati Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
2469 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000056/2023-2024 | 1517/BHM | 26/04/2023 | 0 | Resource Division | 13.34 | 0 | 0
2470 | Bolpur Mechanical | Nalhati Sub-Division | Quotation deposit for Kamarkhur Water Supply Scheme P/H-I in Paikar CCC under Bolpur Mechanical division, PHE Dte | AE,Assistant Engineer | JE1,Junior Engineer | BILL/00828/2024-2025 | BP-24-25-182 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.97 | 0 | 0
2471 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for KAMARKHUL piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000545/2023-2024 | 2141/Bol.MD | 25/08/2023 | 950 | M. S. ENTERPRISE | 27.82 | 0 | 40
2472 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000086/2023-2024 | 1570/BHM | 26/04/2023 | 0 | Resource Division | 27.14 | 0 | 0
2473 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for HARINDUBA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000899/2023-2024 | 3294/Bol.MD | 29/09/2023 | 550 | M/S SWAPAN BANERJEE | 27.4 | 0 | 0
2474 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 300 CuM capacity O.H.R., 150 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at BALIJURI & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000159/2024-2025 | 2663/BHM | 13/09/2024 | 365 | PATHIK PABAN NANDI | 513.18 | 0 | 25
2475 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000050/2024-2025 | 3267/BHM | 02/12/2024 | 0 | Resource Division | 15.81 | 0 | 0
2476 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE3,Junior Engineer | RTOR000082/2022-2023 | 1389/BHM | 24/04/2023 | 0 | Resource Division | 137.77 | 0 | 0
2477 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Balijuri & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE3,Junior Engineer | ORD/000577/2023-2024 | 3381/Bol.MD | 16/10/2023 | 90 | SATYAJIT GHOSH | 80.85 | 0 | 100
2478 | Birbhum Division | Birbhum Sadar Sub-Division | Road crossing, repairing & restoration of damage pipe lines & PCC roads, sluice valve chambers including all allied works for Nanubazar Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000089/2025-2026 | 1646/BHM | 12/06/2025 | 90 | PRANAB KUMAR GHOSH | 49.37 | 0 | 0
2479 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house , 200 CuM, capacity O.H.R. , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at NANUBAZAR & its adjoining mouzas water supply scheme within Sainthia Blocki ncluding supply of all labour & materials under BIRBHUM Division, PHE Dte". | AE,Assistant Engineer | JE,Junior Engineer | ORD/000129/2024-2025 | 2263/BHM | 14/08/2024 | 715 | PRANAB KUMAR GHOSH | 366.36 | 0 | 20
2480 | Birbhum Division | Birbhum Sadar Sub-Division | Sinking of 02(Two) nos. 200mm X 200 mm X 174m deep Tube Wells Fitted With M.S Housing & Well Pipe by Direct Rotary Rig for Nanubazar and Adjacent areas Piped Water Supply Scheme, Block:Sainthia under Birbhum Division, P.H.E Dte | AE,Assistant Engineer | JE,Junior Engineer | ORD/000535/2024-2025 | 315/BHM | 28/01/2025 | 60 | WATER TECH | 25.26 | 0 | 0
2481 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000036/2024-2025 | 2490/BHM | 03/09/2024 | 0 | Resource Division | 9.46 | 0 | 0
2482 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE,Junior Engineer | RTOR000061/2022-2023 | 1420/BHM | 24/04/2023 | 0 | Resource Division | 115.81 | 0 | 0
2483 | Bolpur Mechanical | Birbhum Sadar Sub-Division | New service connection at Nanubazar PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | BILL/01026/2024-2025 | BP-24-25-277 | 06/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.13 | 0 | 0
2484 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Nanubazar & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000428/2023-2024 | 2093/Bol.MD | 22/08/2023 | 679 | ASHUTOSH DAS & CO. | 28.65 | 0 | 45
2485 | Birbhum Division | Birbhum Division | Different works for KAMAR DANGAL & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. Sl No 02 | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000529/2022-2023 | 885/BHM | 21/03/2023 | 275 | M/S.KHAN CHOWDHURY BROTHERS AND CO. | 208.71 | 0 | 80
2486 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | RTOR000037/2022-2023 | 1382/BHM | 24/04/2023 | 0 | Resource Division | 16.97 | 0 | 0
2487 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR PURBA KAMARDANGAL WS SCHEME | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | BILL/01788/2023-2024 | BP-23-24-242 | 29/01/2024 | 0 | WBSEDCL | 6.19 | 0 | 0
2488 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Kamardangal PWSS at Suri - I Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000429/2023-2024 | 2104/BOL.MD. | 22/08/2023 | 60 | M/S S.R. ENTERPRISE | 27.85 | 0 | 30
2489 | Birbhum Division | Birbhum Mechanical (Drill.) Sub-Division | Different works related to water supply scheme at ABHIRAMPUR, BEHIRA, SAMSA & UTTAR BANGAON and its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000082/2023-2024 | 1437/BHM | 25/04/2023 | 820 | ASHOK KUMAR GHOSH | 1446.74 | 0 | 55
2490 | Birbhum Division | Birbhum Mechanical (Drill.) Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000046/2022-2023 | 1376/BHM | 24/04/2023 | 0 | Resource Division | 22.58 | 0 | 0
2491 | Bolpur Mechanical | Birbhum Mechanical (Drill.) Sub-Division | Quotation deposit for Behira Water Supply Scheme P/H-II in Sainthia CCC under Bolpur Mechanical division, PHE Dte | Assistant Engineer | Junior Engineer | BILL/01088/2024-2025 | BP-24-25-285 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.44 | 0 | 0
2492 | Bolpur Mechanical | Birbhum Mechanical (Drill.) Sub-Division | Providing Electro-mechanical accessories and others for Behira & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000440/2023-2024 | 2099/Bol.MD | 22/08/2023 | 738 | C M ENTERPRISE | 24.27 | 0 | 50
2493 | Birbhum Division | Birbhum Division | Different works related to Water Supply Scheme at BELUTI & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000536/2022-2023 | 673/BHM | 01/03/2023 | 671 | ESCON INDIA | 208.6 | 0 | 100
2494 | Birbhum Division | Birbhum Division | Preparation & Submission of DPR for (Beluti) Water Supply Scheme under Mayureswar-II Development Block. | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000562/2022-2023 | 161/RSD | 20/04/2022 | 45 | ENVIROTECH SOLUTIONS | 2.15 | 0 | 100
2495 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | RTOR000094/2023-2024 | 1486/BHM | 25/04/2023 | 0 | Resource Division | 2.93 | 0 | 0
2496 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | RTOR000208/2023-2024 | 203/BHM | 22/01/2024 | 0 | Resource Division | 2.56 | 0 | 0
2497 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR RBELUTI P H NO.II WS SCHEME | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | BILL/01487/2023-2024 | BP-23-24-198 | 19/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0
2498 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOITATION FOR BELUTI PH NO-I | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | BILL/01837/2023-2024 | BP-23-24-267 | 07/02/2024 | 0 | WBSEDCL | 8.05 | 0 | 0
2499 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Beluti PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000845/2023-2024 | 3284/Bol.MD | 29/09/2023 | 550 | DEY ENTERPRISE | 43.64 | 0 | 90
2500 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Jijigram, Math Basori & Bilaspur and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000191/2023-2024 | 3019/BHM | 14/07/2023 | 961 | SUNIL RABI DAS | 1250.5 | 0 | 60
2501 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000083/2023-2024 | 1491/BHM | 25/04/2023 | 0 | Resource Division | 53.18 | 0 | 0
2502 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR UTTAR JIJIGRAM P H NO.II WS SCHEME | AE,Assistant Engineer | JE3,Junior Engineer | BILL/01470/2023-2024 | BP-23-24-194 | 14/12/2023 | 0 | WBSEDCL | 3.14 | 0 | 0
2503 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR UTTAR JIJIGRAM P H NO.I WS SCHEME | AE,Assistant Engineer | JE3,Junior Engineer | BILL/01471/2023-2024 | BP-23-24-193 | 14/12/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
2504 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Jijigram PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000389/2023-2024 | 1928/Bol.MD | 11/08/2023 | 60 | SUNIL RABIDAS | 27.41 | 0 | 100
2505 | Central Drilling | Nalhati Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm x 200mm x 150mtrs depth) by utilising Departmental Machineries for Jijigram PWSS,TW-II , Murarai-II Block under Birbhum District ,CDD,P.H.E. Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000448/2022-2023 | 1380/CDD | 24/11/2022 | 30 | OSMAN SEKH | 10.67 | 0 | 100
2506 | Central Drilling | Nalhati Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm x 200mm x 150mtrs depth) by utilising Departmental Machineries for Jijigram PWSS,TW-I , Murarai-II Block under Birbhum District ,CDD,P.H.E. Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000449/2022-2023 | 1379/CDD | 24/11/2022 | 30 | OSMAN SEKH | 10.67 | 0 | 100
2507 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
2508 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at MATIKONA, NOHONA, SHIRSHA & CHUNPALASHI Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000278/2023-2024 | 3598/BHM | 21/08/2023 | 949 | BIPIN KUMAR SINGH | 2395.67 | 0 | 4
2509 | Birbhum Division | Bolpur Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
2510 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for MATIKONA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000774/2022-2023 | 224/BSD | 08/06/2022 | 90 | M/S R DUTTA & CO. | 4.99 | 0 | 100
2511 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | RTOR000122/2023-2024 | 1525/BHM | 26/04/2023 | 0 | Resource Division | 14.35 | 0 | 0
2512 | Bolpur Mechanical | Bolpur Sub-Division | New power connection at Matikona PWSS under Bolpur Mechanical Division.PHE.Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | BILL/00416/2024-2025 | BP-24-25-131 | 29/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.04 | 0 | 0
2513 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE1 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2514 | Birbhum Division | Birbhum Division | Different Works for KACHUJOR & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000005/2023-2024 | 1084/BHM | 06/04/2023 | 1033 | HIRANMAY GHOSH | 149.6 | 0 | 35
2515 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | RTOR000036/2022-2023 | 1381/BHM | 24/04/2023 | 0 | Resource Division | 9.47 | 0 | 0
2516 | Bolpur Mechanical | Birbhum Division | Quotation for new service connection at Kachujore Water Supply Scheme (TW No-II) under Suri-I Block. | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | BILL/00070/2024-2025 | BP-2024-2025-31 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.09 | 0 | 0
2517 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR KACHUJORE PWSS | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | BILL/01787/2023-2024 | BP-23-24-247 | 29/01/2024 | 0 | WBSEDCL | 4.01 | 0 | 0
2518 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for Kachujor PWSS at Suri -I Block under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer-III | JE3,Junior Engineer | ORD/000424/2023-2024 | 2102/BOL.MD. | 22/08/2023 | 588 | UNITED TRADERS | 27.62 | 0 | 50
2519 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer-III | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
2520 | Birbhum Division | Rampurhat Sub-Division | Different works related to water supply scheme at LACHHIATOR, DAKSHINGRAM, SONJ & SHIBGRAM and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000385/2023-2024 | 4142/BHM | 19/10/2023 | 805 | B RAI CONSTRUCTION COMPANY | 2003.84 | 0 | 60
2521 | Birbhum Division | Rampurhat Sub-Division | Continuation Work Order for Preparation & Submission of DPR for (Shibgram) Water Supply Scheme under Mayureswar-I Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000635/2022-2023 | 244/RSD | 14/07/2022 | 90 | ENVIROTECH SOLUTIONS | 4.65 | 0 | 100
2522 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000075/2023-2024 | 1522/BHM | 26/04/2023 | 0 | Resource Division | 10.37 | 0 | 0
2523 | Birbhum Division | Rampurhat Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000205/2023-2024 | 198/BHM | 22/01/2024 | 0 | Resource Division | 4 | 0 | 0
2524 | Bolpur Mechanical | Rampurhat Sub-Division | New service connection at Shibgram PH-II under Mayureswar -I block. | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00073/2024-2025 | BP-2024-2025-29 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.84 | 0 | 0
2525 | Bolpur Mechanical | Rampurhat Sub-Division | Quotation For new connection at Shibgram PWSS P/H-1 (block -Mayureswar -I) | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/00080/2024-2025 | BP-2024-2025-30 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.21 | 0 | 0
2526 | Bolpur Mechanical | Rampurhat Sub-Division | Providing Electro-mechanical accessories and others for Shibgram PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000726/2023-2024 | 3473/Bol.MD | 07/11/2023 | 60 | R. N. S. TRADING | 44.5 | 0 | 0
2527 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at BHALIAN, BANGJITA & BIRSINGHA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000047/2023-2024 | 1258/BHM | 17/04/2023 | 806 | NAUTANDAS AND CO | 1377.28 | 0 | 35
2528 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE2,Junior Engineer | RTOR000047/2022-2023 | 1377/BHM | 24/04/2023 | 0 | Resource Division | 9.12 | 0 | 0
2529 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR BIRSINGA PAHARPUR WS SCHEME | AE,Assistant Engineer | JE2,Junior Engineer | BILL/00705/2023-2024 | BP-2023-2024-62 | 02/08/2023 | 0 | WBSEDCL | 2.3 | 0 | 0
2530 | Bolpur Mechanical | Birbhum Sadar Sub-Division | WBSEDCL QUOTATION FOR BIRSINGHA PAHARPUR P.H.NO.II | AE,Assistant Engineer | JE2,Junior Engineer | BILL/00706/2023-2024 | BP-2023-2024-61 | 02/08/2023 | 0 | WBSEDCL | 2.3 | 0 | 0
2531 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Birsingha & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000051/2023-2024 | 1058 | 08/06/2023 | 60 | S.G.TECHNICAL SERVICES | 28.79 | 0 | 85
2532 | Central Drilling | Birbhum Sadar Sub-Division | PROVIDING DRILLIG CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BIRSINGHA W/S SCH (TW-II), SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000377/2022-2023 | 1431/CDD | 29/11/2022 | 30 | C.M. ENTERPRISE | 10.49 | 0 | 0
2533 | Central Drilling | Birbhum Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BIRSINGHA W/S SCHEME (TW-I), SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | AE,Assistant Engineer | JE2,Junior Engineer | ORD/000390/2022-2023 | 1430/CDD | 29/11/2022 | 30 | C.M. ENTERPRISE | 10.49 | 0 | 0
2534 | Birbhum Division | Birbhum Sadar Sub-Division | Different works related to water supply scheme at PARULIA, KHANPUR & PADUMA and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000076/2023-2024 | 1425/BHM | 25/04/2023 | 982 | BIPIN KUMAR SINGH | 2248.63 | 0 | 55
2535 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000071/2022-2023 | 1393/BHM | 24/04/2023 | 0 | Resource Division | 113.77 | 0 | 0
2536 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Khanpur & Adjoining moujas water supply scheme under Bolpur Mechanical Division PHE Dte., Block : Dubrajpur, Dist : Birbhum. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000517/2024-2025 | 3763/Bol.MD | 12/09/2024 | 30 | AHALYA ENGINEERING WORKS | 19.44 | 0 | 100
2537 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply, delivery and storage of different Electro-Mechanical accessories at Khanpur PWSS under Bolpur Mmechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000578/2024-2025 | 3849/BOL.MD | 18/09/2024 | 30 | CINZANO | 31.2 | 0 | 0
2538 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Supply Delivery & Installation of Electro-mechanical accessories at Khanpur & Adjoining moujas water supply scheme under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000899/2024-2025 | 4408/Bol.MD | 28/11/2024 | 45 | AHALYA ENGINEERING WORKS | 16.93 | 0 | 100
2539 | Bolpur Mechanical | Birbhum Sadar Sub-Division | Providing Electro-mechanical accessories and others for Khanpur and Adjoining moujas water supply scheme under Bolpur Mechanical Division PHE Dte., Block : Dubrajpur, Dist : Birbhum | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/001047/2023-2024 | 07/BOL.MD | 03/01/2024 | 90 | AHALYA ENGINEERING WORKS | 21.75 | 0 | 100
2540 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
2541 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE3 | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
2542 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Baraban & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE3 | ORD/000668/2022-2023 | 76/BSSD | 05/05/2022 | 45 | RADIANT | 3.35 | 0 | 100
2543 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE3 | RTOR000235/2023-2024 | 435/BHM | 01/02/2024 | 0 | Resource Division | 164.74 | 0 | 0
2544 | Birbhum Division | Bolpur Sub-Division | Construction of 250 & 150 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main, Distribution System with FHTC including different works related to SANTOSHPUR / NAWADA PALANDI /PAPURI / SAJNOR / RAYEN PIPED WATER SUPPLY SCHEME (5 Nos Scheme) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division PHE DTE. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000085/2024-2025 | 1951/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2322.64 | 0 | 5
2545 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for NAWDA PALANDI Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000737/2022-2023 | 263/BSD | 11/07/2022 | 90 | RADIANT | 4.94 | 0 | 100
2546 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for NAWDA PALUNDI Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - B) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000738/2022-2023 | 344/BSD | 12/09/2022 | 90 | RADIANT | 1.82 | 0 | 100
2547 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000004/2024-2025 | 2384/BHM | 27/08/2024 | 0 | Resource Division | 13.57 | 0 | 0
2548 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000067/2023-2024 | 1468/BHM | 25/04/2023 | 0 | Resource Division | 23.68 | 0 | 0
2549 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Nawada Palandi WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000960/2024-2025 | 4529/BOL.MD | 20/12/2024 | 377 | SATYAJIT GHOSH | 75.08 | 0 | 40
2550 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2551 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | RTOR000092/2022-2023 | 1363/BHM | 24/04/2023 | 0 | Resource Division | 263.55 | 0 | 0
2552 | Bolpur Mechanical | Bolpur Sub-Division | Providing Electro-mechanical accessories and others for Ruppur & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000876/2023-2024 | 3514/Bol.MD | 24/11/2023 | 90 | M. S. ENTERPRISE | 88.27 | 0 | 85
2553 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2554 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
2555 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE2 | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
2556 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Rupaspur & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE2 | ORD/000666/2022-2023 | 72/BSSD | 28/04/2022 | 45 | RADIANT | 2.49 | 0 | 100
2557 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE2 | RTOR000249/2023-2024 | 428/BHM | 01/02/2024 | 0 | Resource Division | 109.46 | 0 | 0
2558 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | AE | JE | ORD/000083/2024-2025 | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 100
2559 | Birbhum Division | Birbhum Sadar Sub-Division | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | AE | JE | ORD/000392/2023-2024 | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 81
2560 | Birbhum Division | Birbhum Sadar Sub-Division | Preparation & Submission of DPR for Bhaddi & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | AE | JE | ORD/000670/2022-2023 | 80/BSSD | 10/05/2022 | 45 | RADIANT | 2.42 | 0 | 100
2561 | Birbhum Division | Birbhum Sadar Sub-Division | Material Requisition To Resource Division | AE | JE | RTOR000236/2023-2024 | 437/BHM | 01/02/2024 | 0 | Resource Division | 109.46 | 0 | 0
2562 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at HATKALUA PIPED WATER SUPPLY SCHEME (TSM/016242) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer | JE3 | ORD/000011/2023-2024 | 1096/BHM | 06/04/2023 | 545 | M/S R B ENTERPRISE | 446.12 | 0 | 5
2563 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for HATKALUA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer | JE3 | ORD/001142/2021-2022 | 105/BSD | 21/03/2022 | 180 | APEX ENGINEERING | 3.87 | 0 | 100
2564 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JE3 | RTOR000050/2023-2024 | 1457/BHM | 25/04/2023 | 0 | Resource Division | 20.15 | 0 | 0
2565 | Bolpur Mechanical | Bolpur Sub-Division | Quotation for new service connection at Hatkaluha PWSS(P/H-I) | Assistant Engineer | JE3 | BILL/01023/2024-2025 | BP-24-25-275 | 06/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.62 | 0 | 0
2566 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer | JE3 | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2567 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
2568 | Birbhum Division | Bolpur Sub-Division | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000084/2024-2025 | 1948/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0
2569 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for SHEKHAMPUR Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000660/2022-2023 | 193/BSD | 17/05/2022 | 180 | APEX ENGINEERING | 4.29 | 0 | 100
2570 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000010/2024-2025 | 2386/BHM | 27/08/2024 | 0 | Resource Division | 10.3 | 0 | 0
2571 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000156/2023-2024 | 1602/BHM | 27/04/2023 | 0 | Resource Division | 22.21 | 0 | 0
2572 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Sekhampur PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001131/2024-2025 | 336/BOL.MD | 19/02/2025 | 120 | SATYAJIT GHOSH | 76.45 | 0 | 0
2573 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2574 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at BHATRA PIPED WATER SUPPLY SCHEME (TSM017151) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000305/2024-2025 | 3020/BHM | 30/10/2024 | 365 | DIPAYAN DEY | 441.62 | 0 | 0
2575 | Birbhum Division | Bolpur Sub-Division | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for BHATRA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000653/2022-2023 | 141/BSD | 07/04/2022 | 180 | APEX ENGINEERING | 4.57 | 0 | 100
2576 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | RTOR000150/2023-2024 | 1596/BHM | 26/04/2023 | 0 | Resource Division | 69.42 | 0 | 0
2577 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Bhatra PWSS (TW No I and II), Block- Labpur in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/001117/2024-2025 | 325/BOL.MD | 19/02/2025 | 120 | OSMAN SEKH | 76.34 | 0 | 0
2578 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE3 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2579 | Birbhum Division | Birbhum Division | Different works related to water supply scheme at MOUBELIA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000009/2023-2024 | 1182/BHM | 12/04/2023 | 537 | M/S R B ENTERPRISE | 304.55 | 0 | 100
2580 | Birbhum Division | Birbhum Division | Sinking of additional T.W, Road crossing, Repairing & restoration of damaged pipe lines, sluice valve chambers, including all allied works for Moubelia PWSS of Md.Bazar Development Block Under Birbhum Division, P.H.E Dte | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000076/2025-2026 | 1639/BHM | 11/06/2025 | 90 | M/S R B ENTERPRISE | 46.39 | 0 | 0
2581 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | RTOR000164/2023-2024 | 1620/BHM | 28/04/2023 | 0 | Resource Division | 13.88 | 0 | 0
2582 | Birbhum Division | Birbhum Division | Material Requisition To Resource Division | AE(HQ),Assistant Engineer | JE,Junior Engineer | RTOR000185/2023-2024 | 3075/BHM | 19/07/2023 | 0 | Resource Division | 4.35 | 0 | 0
2583 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR MOUBELIA WS SCHEME | AE(HQ),Assistant Engineer | JE,Junior Engineer | BILL/01448/2023-2024 | BP-23-24-176 | 07/12/2023 | 0 | WBSEDCL | 0.39 | 0 | 0
2584 | Bolpur Mechanical | Birbhum Division | WBSEDCL QUOTATION FOR MOUBELIA WS SCHEME | AE(HQ),Assistant Engineer | JE,Junior Engineer | BILL/01451/2023-2024 | BP-23-24-175 | 07/12/2023 | 0 | WBSEDCL | 4.48 | 0 | 0
2585 | Bolpur Mechanical | Birbhum Division | Providing Electro-mechanical accessories and others for MOUBELIA piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | AE(HQ),Assistant Engineer | JE,Junior Engineer | ORD/000401/2023-2024 | 2077/BOL.MD. | 21/08/2023 | 60 | DIPALI CONSTRUCTION | 27.4 | 0 | 80
2586 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | RTOR000093/2022-2023 | 1364/BHM | 24/04/2023 | 0 | Resource Division | 19.72 | 0 | 0
2587 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE4 ,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2588 | Birbhum Division | Bolpur Sub-Division | Different works related to water supply scheme at BRAHMANKHANDA PIPED WATER SUPPLY SCHEME (TSM/015460) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000150/2024-2025 | 2598/BHM | 10/09/2024 | 365 | ASHOK MITRA | 463.91 | 0 | 20
2589 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BRAHAMAKHANDA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000732/2022-2023 | 221/BSD | 07/06/2022 | 180 | RADIANT | 4.94 | 0 | 100
2590 | Birbhum Division | Bolpur Sub-Division | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BRAHAMAKHANDA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - B) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000733/2022-2023 | 298/BSD | 10/08/2022 | 90 | RADIANT | 1.82 | 0 | 100
2591 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000054/2024-2025 | 3265/BHM | 02/12/2024 | 0 | Resource Division | 14.05 | 0 | 0
2592 | Birbhum Division | Bolpur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | RTOR000062/2023-2024 | 1494/BHM | 25/04/2023 | 0 | Resource Division | 41.61 | 0 | 0
2593 | Bolpur Mechanical | Bolpur Sub-Division | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Brahmankhnda Water supply Scheme (T/W-I & II), Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000966/2024-2025 | 4535/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.35 | 0 | 50
2594 | Central Drilling | Bolpur Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer (HQ) | JE_BLK_NANOOR,Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
2595 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at DHITORA & its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000036/2023-2024 | 1108/BHM | 10/04/2023 | 691 | M/S PROCHESTA ENTERPRISE | 215.75 | 0 | 100
2596 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE1,Junior Engineer | RTOR000116/2023-2024 | 1501/BHM | 25/04/2023 | 0 | Resource Division | 10.63 | 0 | 0
2597 | Bolpur Mechanical | Nalhati Sub-Division | QUOTATION BILL FOR DHITORA WS SCHEME P H NO.I | AE,Assistant Engineer | JE1,Junior Engineer | BILL/01355/2023-2024 | BP-23-24-147 | 28/11/2023 | 0 | WBSEDCL | 3.81 | 0 | 0
2598 | Bolpur Mechanical | Nalhati Sub-Division | QUOTATION BILL FOR DHITORA WS SCHEME P H NO.II | AE,Assistant Engineer | JE1,Junior Engineer | BILL/01356/2023-2024 | BP-23-24-148 | 28/11/2023 | 0 | WBSEDCL | 2.61 | 0 | 0
2599 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOITATION FOR DHITORA PH NO-I | AE,Assistant Engineer | JE1,Junior Engineer | BILL/01838/2023-2024 | BP-23-24-268 | 08/02/2024 | 0 | WBSEDCL | 1.3 | 0 | 0
2600 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for DHITORA RIGHT SIDE piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE1,Junior Engineer | ORD/000390/2023-2024 | 1929/Bol.MD | 11/08/2023 | 325 | ORIENTAL ENGINEERING CO. | 27.2 | 0 | 80
2601 | Birbhum Division | Nalhati Sub-Division | Jack pushing along with extension of pipeline (DI & HDPE), Restoration of Roads etc for Atkulia piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000670/2024-2025 | 799/BHM | 24/03/2025 | 360 | M/S S. CHOUDHURY | 76.4 | 0 | 0
2602 | Birbhum Division | Nalhati Sub-Division | Preparation and submission of DPR for (Atkulia) Water Supply Scheme under Nalhati-II Development Block. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000755/2022-2023 | 218/AE/NSD | 18/04/2022 | 45 | MS SOBHA AND CO | 4.89 | 0 | 100
2603 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer-III | JE2,Junior Engineer | RTOR000109/2023-2024 | 1510/BHM | 26/04/2023 | 0 | Resource Division | 62.89 | 0 | 0
2604 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR Atkulia Piped Water Supply Scheme | AE,Assistant Engineer-III | JE2,Junior Engineer | BILL/01604/2023-2024 | BP-23-24-237 | 29/01/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
2605 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Atkulia PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000459/2023-2024 | 2134/Bol.MD | 25/08/2023 | 582 | SINHA ELECTRICALS | 57.83 | 0 | 30
2606 | Bolpur Mechanical | Nalhati Sub-Division | Supply and Delivery of Open well Submersible Pumping Machineries and allied accessories for Atkulia PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | AE,Assistant Engineer-III | JE2,Junior Engineer | ORD/000526/2024-2025 | 3784/BOL.MD | 12/09/2024 | 30 | EASTERN INDIA SALES & SERVICE | 37.46 | 0 | 0
2607 | Birbhum Division | Nalhati Sub-Division | Different works related to water supply scheme at Jijigram, Math Basori & Bilaspur and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000191/2023-2024 | 3019/BHM | 14/07/2023 | 961 | SUNIL RABI DAS | 1250.5 | 0 | 60
2608 | Birbhum Division | Nalhati Sub-Division | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000492/2024-2025 | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 100
2609 | Birbhum Division | Nalhati Sub-Division | Material Requisition To Resource Division | AE,Assistant Engineer | JE3,Junior Engineer | RTOR000089/2023-2024 | 1569/BHM | 26/04/2023 | 0 | Resource Division | 24.53 | 0 | 0
2610 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOTATION FOR BILASPUR PIPED WATER SUPPLY SCHEME.P H NO.I WS SCHEME | AE,Assistant Engineer | JE3,Junior Engineer | BILL/01596/2023-2024 | BP-23-24-225 | 15/01/2024 | 0 | WBSEDCL | 4.45 | 0 | 0
2611 | Bolpur Mechanical | Nalhati Sub-Division | WBSEDCL QUOATION FOR BILASPUR P H NO.II WS SCHEME | AE,Assistant Engineer | JE3,Junior Engineer | BILL/01597/2023-2024 | BP-23-24-226 | 15/01/2024 | 0 | WBSEDCL | 3.45 | 0 | 0
2612 | Bolpur Mechanical | Nalhati Sub-Division | Providing Electro-mechanical accessories and others for Bilaspur PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | AE,Assistant Engineer | JE3,Junior Engineer | ORD/000939/2023-2024 | 3300/BOL.MD | 29/09/2023 | 550 | SUNIL RABIDAS | 28.71 | 0 | 100
2613 | Birbhum Division | RWS Birbhum Sub-Division | Road restoration work at different villages under implementation of Mini Piped Water Supply Scheme within Illambazar Block having less than 100 Households under Birbhum Division PHE Dte. | AE,Assistant Engineer (HQ) | JE,Junior Engineer | ORD/000220/2025-2026 | 2152/BHM | 19/08/2025 | 90 | SOURAV MONDAL | 17.41 | 0 | 0
2614 | Birbhum Division | RWS Birbhum Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | AE,Assistant Engineer (HQ) | JE,Junior Engineer | ORD/000333/2022-2023 | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 92
Total | [10 empty] | 2031263.44 | 1256.13