## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amra village of Natungram piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-332/BWD/2020-21) |  |  | ORD/000079/2020-2021 | 2732/BWD | 10/08/2020 | 30 | BAMDEB CONSTRUCTION & CO | 4.92 | 4.92 | 1
2 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Natungram Piped Water Supply Scheme at Amar (6 Nos Habitation Part), Natungram (4 Nos Habitation Part) & Bohar Village (Mouza), Bardhaman-I Block under Burdwan Division, PHE Dte.(Agreement No. 73/2020-2021 OF SE/CC/PHE. DTE.) |  |  | ORD/000140/2020-2021 | 7052/BWD | 22/12/2020 | 90 | HAMID SK | 48.2 | 41.4 | 1
3 | Burdwan Division |  | Providing Functional House hold Tap connection (FHTC) from existing distribution system within the command area of NATUNGRAM piped water supply scheme at Natungram village under Bardhaman-I Block under Burdwan Division, PHE Dte.[Gr.-C] |  |  | ORD/000152/2021-2022 | 687/BSD | 09/06/2021 | 30 | HAMID SK | 2.95 | 2.91 | 1
4 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amar village of Natungram piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-579/BWD/2020-21) |  |  | ORD/000263/2020-2021 | 4465/BWD | 11/11/2020 | 30 | BAMDEB CONSTRUCTION & CO | 4.92 | 4.92 | 1
5 | Burdwan Division |  | Providing 45 Nos.FHTC at SIJEPARA village for declearation of SWAJALGRAM under NATUNGRAM Piped Water Supply Scheme , Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte |  |  | ORD/000298/2024-2025 | 1280/BSD | 12/07/2024 | 45 | SHANKHA GHOSH | 1.76 | 0 | 0
6 | Burdwan Division |  | Providing 50 Nos.FHTC at BIRPUR village for declearation of SWAJALGRAM under NATUNGRAM Piped Water Supply Scheme , Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. |  |  | ORD/000299/2024-2025 | 1281/BSD | 12/07/2024 | 45 | I.S. ENTERPRISE | 2.28 | 0 | 100
7 | Burdwan Division |  | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ I Block under Burdwan Division, PHE. Dte. |  |  | ORD/000342/2021-2022 | 32/BWD | 04/01/2022 | 30 | ROY BISWAS CONSTRUCTION | 9.89 | 0 | 1
8 | Burdwan Division |  | Publication charges bill for the office of the Executive Engineer, Burdwan Division, PHE Dte.[Invoice No.-BCWB20RV-0001293, dt.-19/05/20, BCWB20RV-0001770, dt.-31/05/20, BCWB20RV-0001920, dt.-05/06/20, BCWB20RV-0001860, dt.-03/06/20, BCWB20RV-0001861, dt.-03/06/20, BCWB20RV-0001928, dt.-05/06/20, BCWB20RV-0001820, dt.-03/06/20, BCWB19RV-0059455, dt.-20/03/20, BCWB19RV-0059454. dt.-20/03/20, BCWB19RV-0057682, dt.-12/03/20, BCWB20RV-0003210, dt.-26/06/20, BCWB20RV-0000918, dt.-07/05/20, BCWB20RV-0001352, dt.-22/05/20, BCWB19RV-0050592, dt.-30/01/20] |  |  | VCH/000411/2022-2023 | 240/DW/22-23 | 04/07/2022 | 0 | BENNETT COLEMAN & COMPANY LIMITED | 1.89 | 0 | 0
9 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Deriapur village of Deriapur piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-158/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000086/2020-2021 | 2691/BWD | 07/08/2020 | 30 | ASHOK KUMAR GHOSH | 4.92 | 4.92 | 1
10 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Deriapur village of Deriapur piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-351/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000108/2020-2021 | 3898/BWD | 12/10/2020 | 30 | ASHOK KUMAR GHOSH | 3.59 | 3.59 | 1
11 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of DERIAPUR Piped Water Supply Scheme at Astikur, Balagar & Bora Village (Mouza), Raina-I Block under Burdwan Division, PHE Dte.(Agreement No. 474/BWD OF 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000129/2020-2021 | 4916/BWD | 08/12/2020 | 90 | ASHOK KUMAR GHOSH | 39.84 | 29.82 | 1
12 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000344/2021-2022 | 39/BWD | 05/01/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 15.62 | 0 | 1
13 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
14 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nandra village of Nandra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-176/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000102/2020-2021 | 2735/BWD | 10/08/2020 | 30 | BHARAT CONSTRUCTION | 4.92 | 4.92 | 1
15 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur & Dangachha village of Nandra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-177/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000103/2020-2021 | 2736/BWD | 10/08/2020 | 30 | BHARAT CONSTRUCTION | 4.92 | 4.92 | 1
16 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC (130 nos.) and Extension of UPVC dist. Pipeline at Noapara, Pirtala ,Nandra village of NANDRA water supply scheme at Burdwan-II Block under Burdwan Division PHE Dte..Gr. I | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000213/2021-2022 | 1479/BSD | 09/11/2021 | 30 | BHARAT CONSTRUCTION | 4.81 | 0 | 1
17 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC in Nandra & Naopara village for 100% coverage in Sajal Gram from existing distribution system within NANDRA PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Gr.F. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000339/2022-2023 | 1360/BSD | 03/08/2022 | 5 | BHARAT CONSTRUCTION | 0.97 | 0 | 1
18 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000416/2021-2022 | 385/BWD | 20/01/2022 | 30 | BISWAS ENTERPRISE | 11.97 | 0 | 100
19 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
20 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur & Dangachha village of Nandra Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿10B¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000463/2020-2021 | 4085/BWD | 16/10/2020 | 30 | BHARAT CONSTRUCTION | 1.65 | 1.65 | 0
21 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC in Nandra & Naopara village for 100% coverage in Sajal Gram from existing distribution system within Nandra PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000654/2022-2023 | 1360-A/BSD | 03/08/2022 | 5 | BHARAT CONSTRUCTION | 0.97 | 0 | 1
22 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nandra village of Nandra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000714/2020-2021 | 4087/BWD | 16/10/2020 | 30 | BHARAT CONSTRUCTION | 2 | 2 | 1
23 | Burdwan Division | Burdwan Sadar Sub-Division | Additional Extension of UPVC distribution pipeline in connection with FHTC for NANDRA & adjoining mouzas water supply scheme at Bardhaman-I Block under Burdwan division, PHE Dte.[Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000743/2020-2021 | 73/BSD | 19/01/2021 | 30 | BHARAT CONSTRUCTION | 4.22 | 4.18 | 1
24 | Burdwan Division | Burdwan Sadar Sub-Division | Repairing of Pipeline of DVC 11 No. Canal towards Amila Bazar and DVC 11B No. Conal Towards Sehara Bazar at TARAPOSH Pipes Water Supply Scheme at Khandaghosh Block under Burdwan Division,PHE Dte. Group : F | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000093/2022-2023 | 833/BSD | 23/05/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 1.56 | 0 | 1
25 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Khandaghosh Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000405/2021-2022 | 283/BWD | 17/01/2022 | 30 | J. K. CORPORATION | 11.88 | 0 | 1
26 | Burdwan Division | Burdwan Sadar Sub-Division | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Taraposh piped water supply scheme at Alladipur, Chintamonipur, Jarul, Kamdebpur, Punia, Sunia & Taraposh, Khandaghosh Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000584/2020-2021 | 4766/BWD | 01/12/2020 | 90 | SINGHA ROY AND CO. | 70.55 | 0 | 1
27 | Burdwan Division | Burdwan Sadar Sub-Division | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of TARAPOSE Piped Water Supply Scheme within KHANDAGHOSH Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000759/2022-2023 | 1289/BWD | 20/03/2023 | 30 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 21.86 | 0 | 100
28 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of 250 cum capacity 20 Mtr staging height RCC Over Head Reservoir including pipe connection and cost of pipes specials including soil investigation for TARAPOSH & its adjoining mouzas water supply scheme under Burdwan Sub-Division, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000973/2020-2021 | 4594/BWD | 24/11/2020 | 180 | MITRA CONSTRUCTION | 57 | 0 | 100
29 | Burdwan Division | Burdwan Sadar Sub-Division | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Head Quarters, Burdwan Division, PHE Dte. for the month of June & July'22. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | VCH/000493/2022-2023 | 460/VEH/22-23 | 29/08/2022 | 0 | SK. ASRAFUDDIN | 0.76 | 0 | 0
30 | Burdwan Division | Burdwan Sadar Sub-Division | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Engineer, Headquarters, Burdwan Division, PHE Dte. for the month of September & October'2022. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | VCH/000839/2022-2023 | 766/VEH/22-23 | 22/11/2022 | 0 | SK. ASRAFUDDIN | 0.7 | 0 | 0
31 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ I Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000342/2021-2022 | 32/BWD | 04/01/2022 | 30 | ROY BISWAS CONSTRUCTION | 9.89 | 0 | 1
32 | Burdwan Division | Burdwan Sadar Sub-Division | Providing 22 Nos.FHTC at IDILPUR & FAKIRPUR village for declearation of SWAJALGRAM under FAKIRPUR Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000166/2024-2025 | 1035/BSD | 10/06/2024 | 30 | IMPULSE INTERNATIONAL | 0.75 | 0 | 0
33 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Balance Functional Household Tap Connection (FHTC)for Swajal Gram from existing distribution system within the command area of Idilpur & Fakirpur village under Fakirpur Piped W/S.Scheme under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr. I | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000346/2022-2023 | 1380/BSD | 05/08/2022 | 5 | BAMDEB CONSTRUCTION & CO | 0.96 | 0 | 100
34 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall at Head works site of Fakirpur water supply scheme under Bardhaman-I Block under Burdwan Division, PHE Dte.[Length-50.20 Mtr][Part-B][South & West Side][Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000558/2021-2022 | 1026/BSD | 05/08/2021 | 45 | AYSAN KHAN | 3.77 | 0 | 1
35 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of FAKIRPUR Piped Water Supply Scheme at Fakirpur & Bongpur village (Mouza), Burdwan - I Block under Burdwan Division, PHE Dte._2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000641/2020-2021 | 355/BWD | 15/01/2021 | 45 | AYSAN KHAN | 36.69 | 8.64 | 1
36 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Balance Functional Household Tap Connection(FHTC)for Swajal Gram from existing distribution system within the command area of Idilpur & Fakirpur Village under of FAKIRPUR W.S.Scheme of Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000847/2022-2023 | 1380-A/BSD | 05/08/2022 | 5 | BAMDEB CONSTRUCTION & CO | 0.96 | 0 | 0
37 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000345/2021-2022 | 40/BWD | 05/01/2022 | 30 | PREMANANDA ROY BISWAS | 22.68 | 0 | 1
38 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Balarampur Piped Water Supply Scheme at Balarampur (3 Nos Habitation), Berugram (3 Nos Habitation), Krishnapur (2 Nos Habitation) & Sadipur (3 Nos Habitation Part) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 66/2020-2021 OF SE/CC/PHE. DTE.] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000431/2020-2021 | 5009/BWD | 10/12/2020 | 90 | M/S ASHA CONSTRUCTION | 100.79 | 25.68 | 0
39 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of BALARAMPUR & its adjoining mouzas Piped Water Supply Scheme, Block - Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000524/2022-2023 | 4887/BWD | 02/11/2022 | 30 | BIBHUTI SHAW | 10.07 | 0 | 100
40 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000592/2021-2022 | 1454/BWD | 11/03/2022 | 30 | PREMANANDA ROY BISWAS | 18.83 | 0 | 1
41 | Burdwan Division | Burdwan Sadar Sub-Division | Laying pipeline with FHTC for BALARAMPUR Water Supply Scheme at Matnasipur village (600 Nos) (from near rail gate to matnasipur) and rest portion FHTC work of Berugram village (46 Nos), Balarampur village (40 Nos), Nasipur village (45 Nos), Salimdanga village (15 Nos) within Jamalpur Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000639/2021-2022 | 1620/BWD | 21/03/2022 | 1217 | M/S ASHA CONSTRUCTION | 47.32 | 0 | 100
42 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of temporary approach road for Boring machine and its accessories at 4th Tube Well site (due to low land) of Balarampur PWSS, Jamalpur Dev. Block Burdwan Sub-Division under Burdwan Division,PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/001089/2023-2024 | 519/BSD | 13/03/2024 | 15 | BIBHUTI SHAW | 0.92 | 0 | 100
43 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | RTOR000023/2021-2022 | 423/BWD | 20/01/2022 | 0 | Resource Division | 5.5 | 0 | 0
44 | Burdwan Division |  | Replacement and extension of pipe line from the existing Distribution System within scheme jurisdiction at Sahebnagar village under AGRADWIP PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.(Sl No-4) |  |  | ORD/000143/2021-2022 | 592/KTS | 06/09/2021 | 30 | TAPAS KUMAR ROY | 4.84 | 0 | 1
45 | Burdwan Division |  | Replacement and extension of pipe line from the existing Distribution System within scheme jurisdiction at Agradwip Gopinath para and Majherpara village under AGRADWIP PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.(Sl No-5) |  |  | ORD/000144/2021-2022 | 593/KTS | 06/09/2021 | 30 | CHANCHAL PAL | 3.47 | 0 | 1
46 | Burdwan Division |  | Replacement and extension of pipe line from the existing Distribution System within scheme jurisdiction at Agradwip Ghosh para village under AGRADWIP PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.(Sl No-6) |  |  | ORD/000145/2021-2022 | 594/KTS | 06/09/2021 | 30 | SHUBHRA KANTI GHOSH | 3.56 | 0 | 1
47 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Agradwip Piped Water Supply Scheme at Agradwip (P) village & Kharpur (P) village, Katwa - II Block under Burdwan Division, PHE Dte._Part-B.[Agreement No. 685/BWD OF 2020-2021.] |  |  | ORD/000305/2020-2021 | 1511/BWD | 19/02/2021 | 45 | SHUBHRA KANTI GHOSH | 44.47 | 43.51 | 0
48 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Agradwip Piped Water Supply Scheme at Agradwip (P) village & Kharpur (P) village, Katwa - II Block under Burdwan Division, PHE Dte._Part-A. [Agreement No. 704/BWD OF 2020-2021] |  |  | ORD/000323/2020-2021 | 1567/BWD | 22/02/2021 | 45 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 44.39 | 43.48 | 0
49 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AGRADWIP Piped Water Supply Scheme at Agradwip, Babla danga, Gonsaidhowra, Saheb Nagar & Sarawaridhowra (Mouza), Katwa - II Block under Burdwan Division, PHE Dte. |  |  | ORD/000445/2021-2022 | 6253/BWD | 01/11/2021 | 60 | SHUBHRA KANTI GHOSH | 53.67 | 0 | 1
50 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for the work of " Sinking of 300 x 200mm x 150 mtr depth by DR Rig, Repairing & Renovation of existing OHR, Construction of 01 (One) 5.25 x 3.25m No Pump House cum Chlorine Room including laying UPVC distribution system (LDS) and interconnection of PWSS & construction of Boundary wall & other allied works at Golgram under GOLGRAM PWSS, Block- Galsi-I, Dist- Purba Bardhman under Durgapur W/S Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000045/2024-2025 | 771/DWSD | 06/06/2024 | 476 | ARISH CONSTRUCTION | 83.56 | 0 | 90
51 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for the work of Balance work for Distribution System (CI/DI/UPVC), Earth Work & Concrete Work for GOLGRAM PWSS Schemes of GALSI-I Block under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000050/2024-2025 | 767/DWSD | 06/06/2024 | 25 | SHUBHRA KANTI GHOSH | 1.12 | 0 | 100
52 | Burdwan Division | Durgapur Sub-DIvision | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of February'23. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00117/2023-2024 | 13/JJM | 17/04/2023 | 0 | SUJAUDDIN SEKH | 0.36 | 0 | 0
53 | Burdwan Division | Durgapur Sub-DIvision | Construction of approach road from entrance to OHR, Pump House and filling of low land around Over Head Reservoir with carried earth at 1st Tube well site of Golgram & its adjoining mouzas water supply scheme, Block-Galsi-I, under Burdwan Division, PHE Dte. [SL-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000122/2022-2023 | 335/DSD | 27/06/2022 | 30 | CHOUDHURY INFRA | 1.86 | 0 | 1
54 | Burdwan Division | Durgapur Sub-DIvision | Making Connection with Rising Main And Over Head Reservoir of Golgram W/S Scheme within Durgapur Sub-Division in Galsi-I Block under Burdwan Division, P.H.E. Dte. [Gr.-G] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000135/2022-2023 | 348/DSD | 30/06/2022 | 15 | RANADHIR SINHA | 0.33 | 0 | 1
55 | Burdwan Division | Durgapur Sub-DIvision | Formal Work Order for providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Golgram Piped Water Supply Scheme at Golgram Village (Mouza), Galsi-I Block under Burdwan Division, PHE Dte. [Agreement No. 100/SE/CC/PHE/Dte of 2020-2021.] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000425/2020-2021 | 638/BWD | 25/01/2021 | 60 | SHUBHRA KANTI GHOSH | 63.87 | 0 | 1
56 | Burdwan Division | Durgapur Sub-DIvision | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Galsi ¿ I Block under Burdwan Division, PHE. Dte._2ND CALL. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000673/2021-2022 | 1738/BWD | 28/03/2022 | 1101 | JYOTI ENTERPRISE | 5.72 | 0 | 100
57 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline at Pratappur DANDA PARA, BATHAN PARA, BANGAL PARA, HINDU PARA & ADIBASI PARA of PRATAPPUR (ZONE-I) and its adjoining mouza's Piped W/S Scheme including water tap connection (FHTC) at Babuisol Vill (Goswamibandh Adibashipara Hab.), Kuldiha Vill (Adibashipara Hab.) Lachminnarayanpur Vill (2 Nos. Hab.), Pratappur Vill (2 Nos. Habs.), Radhaballabhpur Vill (1 No. Hab), Ramharipur Vill (2 Nos. Hab.) Radhamohanpur Vill. (1 No. Hab.) at Ausgram-II Block under Burdwan Division, PHE Dte._2ND CALL | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000206/2021-2022 | 6393/BWD | 16/11/2021 | 60 | SAIKAT RAY | 44.09 | 0 | 1
58 | Burdwan Division | Durgapur Sub-DIvision | Connection from newly constructed Over Head Reservoir to Distribution System & Rising main Pipe Line of PRATAPPUR ( ZONE - I & II ) and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block, within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte._2nd Call [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000262/2021-2022 | 689/DSD | 08/12/2021 | 21 | S.S. ENTERPRISE | 1.66 | 0 | 1
59 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline for providing FHTC at Pratappur CHITIM DANGA, RAMHARIPUR , MUSLIMPARA & DHANDAGHA of PRATAPPUR (ZONE-I) and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur (Burdwan North)Sub Division under Burdwan Division, P.H.E. Dte. [Sl-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000566/2021-2022 | 134/DSD | 02/03/2022 | 30 | SAIKAT RAY | 4.64 | 0 | 1
60 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline at Babuisole & Gosaibandh village of PRATAPPUR (ZONE-II) and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000842/2020-2021 | 173/DSD | 19/02/2021 | 21 | RALLY CO-OP LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.67 | 0 | 1
61 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline at Kuldiha & Raniganj village of PRATAPPUR (ZONE-II) and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000843/2020-2021 | 172/DSD | 19/02/2021 | 21 | RELIABLE ENGINEERS CO.-OPERATIVE CONSTRUCTION SOCIETY LTD. | 4.73 | 0 | 1
62 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PRATAPPUR Piped Water Supply Scheme at Raniganj (Part), Babuisol (Part), Pratappur (Part), village, habitation, Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000920/2023-2024 | 5482/BWD | 13/12/2023 | 30 | N.S. ENTERPRISE | 10.92 | 0 | 100
63 | Durgapur W/S Division | Durgapur Sub-DIvision | Quotation for new service connection at URA PWSS TW-I under CMD/PHED | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00215/2024-2025 | BP-2024-25-104 | 03/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.65 | 0 | 0
64 | Burdwan Division | Durgapur Sub-DIvision | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of URA Piped Water Supply Scheme at Ura (1 No Part & 1 No Habitation), Sarul (2 Nos Habitation) & Adrahati Village (Mouza), Gaisi-II Block under Burdwan Division, PHE Dte..(Agreement No. 95/SE/CC/PHE/Dte of 2020-2021) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000445/2020-2021 | 1087/BWD | 08/02/2021 | 60 | M/S PURBASHA | 66.7 | 7.15 | 1
65 | Burdwan Division | Durgapur Sub-DIvision | Construction of drain and pathway at Head work site of URA piped water supply scheme, Block-Galsi-II within Durgapur (Bardhaman North) Sub-Division, under Burdwan Division, PHE Dte. SL-03 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000529/2022-2023 | 648/DSD | 03/11/2022 | 30 | M/S PURBASHA | 3.66 | 0 | 1
66 | Burdwan Division | Katwa Sub-Division | Augmentation of BAHRAN BIRAHIMPUR Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation with repairing of Pump house -I & II under Ketugram-II Block, District:- Purba-Burdwan. | Assistant Engineer |  | ORD/000060/2022-2023 | 2252/BWD | 02/05/2022 | 365 | ASHOK MITRA | 290.62 | 0 | 100
67 | Burdwan Division | Katwa Sub-Division | Route Survey and preparation of DPR for BAHARAN BIRHIMPUR PWSS under Ketugram-II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-01] | Assistant Engineer |  | ORD/000537/2021-2022 | 43/KTS | 24/01/2022 | 21 | RADIANT | 2.6 | 0 | 1
68 | Burdwan Division | Katwa Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000051/2021-2022 | 534/BWD | 27/01/2022 | 0 | Resource Division | 11.25 | 0 | 0
69 | Burdwan Division | Katwa Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000085/2021-2022 | 882/BWD | 11/02/2022 | 0 | Resource Division | 7.08 | 0 | 0
70 | Burdwan Division | Katwa Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000202/2021-2022 | 1525/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
71 | Burdwan Division | Katwa Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
72 | Burdwan Division | Kalna Sub-division | Quotation for new service connection charges of Monteswar PWSS.[PH No.-3] | Assistant Engineer |  | BILL/01126/2023-2024 | 1085/JJM | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.99 | 0 | 0
73 | Burdwan Division | Kalna Sub-division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Jahannagar, Ganganandapur, Nowapara & Monteswar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, P.H.E. Dte.[Part ¿ A] | Assistant Engineer |  | ORD/000323/2022-2023 | 3632/BWD | 22/08/2022 | 20 | RAMASISH ENTERPRISE | 12.8 | 0 | 1
74 | Burdwan Division | Kalna Sub-division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Jahannagar, Ganganandapur, Nowapara & Monteswar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, P.H.E. Dte.[Part B] | Assistant Engineer |  | ORD/000357/2022-2023 | 3728/BWD | 30/08/2022 | 20 | NANDY UDYOG | 2.88 | 0 | 1
75 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 1ST TW Site of Aug. of MONTESWAR & its adjoining mouzas Piped Water Supply Scheme, Block ? Monteswar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000550/2022-2023 | 5178/BWD | 23/11/2022 | 30 | ANIRUDDHA FARUQUE | 8.73 | 0 | 100
76 | Burdwan Division | Kalna Sub-division | Work Order for "Surging of existing 300 x 200 mm dia Tube Well depth 123 mtr & lowering of part tube well 200 x 150 mm dia depth , existing 300 x 200 mm dia tube well at Manteswar zone-I under Kalna Sub-Division , PHE Dte." | Assistant Engineer |  | ORD/000551/2023-2024 | 1306/KSD | 23/08/2023 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 4.2 | 0 | 100
77 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Monteswar W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-F) | Assistant Engineer |  | ORD/000572/2021-2022 | 208/KSD | 23/02/2022 | 21 | INDRANIL DUTTA & ASSOCIATES | 2.75 | 0 | 1
78 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000049/2021-2022 | 563/BWD | 27/01/2022 | 0 | Resource Division | 14.37 | 0 | 0
79 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
80 | Durgapur W/S Division | Durgapur Sub-DIvision | Quotation for new service connection at Chaktetul Ausgram -I PWSS under CMD/PHED | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00197/2024-2025 | BP-2024-25-99 | 27/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.38 | 0 | 0
81 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for the work of "Sinking of 300 x 200 mm x 150 mtr deapth by DR, Repairing & Renovation of existing OHR, Construction of 01 (One) no 5.25 x 3.25 m Pump House cum Chlorine Room including laying UPVC distribution system (LDS) and interconnection & other allied works at CHAKTETUL PWSS, Block- Galsi-I, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000043/2024-2025 | 759/DWSD | 06/06/2024 | 270 | M/S JAYDEEP DASGUPTA | 77.42 | 0 | 90
82 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of CHAKTENTUL Piped Water Supply Scheme at Chaktentul (1 No Part, 2 Nos Habitation), Bharatpur (2 Nos Habitation) Village (Mouza), Galsi-I Block under Burdwan Division, PHE Dte.(Agreement No. 71/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000128/2020-2021 | 5005/BWD | 10/12/2020 | 90 | SUPRIYA RAY | 75.14 | 0 | 1
83 | Burdwan Division | Durgapur Sub-DIvision | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Galsi ¿ I Block under Burdwan Division, PHE. Dte._2ND CALL. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000673/2021-2022 | 1738/BWD | 28/03/2022 | 1101 | JYOTI ENTERPRISE | 5.72 | 0 | 100
84 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000115/2021-2022 | 1103/BWD | 26/02/2022 | 0 | Resource Division | 12.3 | 0 | 0
85 | Burdwan Division | Kalna Sub-division | Construction of concrete path way at Head Work Site & 2nd & 3rd Tube Well site along with plinth protection of Pump House No-I & laying of 200 mm dia DI Pipe for wash out and over flow drain of existing OHR of Putsuri W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000038/2022-2023 | 2218/BWD | 28/04/2022 | 30 | BISHWAJIT DAS | 4.07 | 0 | 0
86 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Putsuri Piped Water Supply Scheme at Denur (6 Nos Habitation Part) & Putsuri (11 Nos Habitation Part) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte.(Agreement No. 55/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer |  | ORD/000125/2020-2021 | 4887/BWD | 07/12/2020 | 90 | M/S S. CHOUDHURY | 77.12 | 0 | 1
87 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PUTSURI Piped Water Supply Scheme at Kasa (6 Nos. Habs.), Purba Balarampur, Bhurkunda (7 Nos. Habs.), Patun (5 Nos. Habs.) & Bigha (3 Nos. Habs.) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000302/2021-2022 | 7020/BWD | 17/12/2021 | 60 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 53.94 | 0 | 1
88 | Burdwan Division | Kalna Sub-division | Sinking of Tube Well, Construction of Pump House, Boundary wall & interconnection work of Kasa village of PUTSURI Water Supply Scheme within Kalna Sub-Division under Burdwan division, PHE Dte. | Assistant Engineer |  | ORD/000721/2023-2024 | 4532/BWD | 13/10/2023 | 60 | B.S. ENTERPRISE | 27.32 | 0 | 40
89 | Burdwan Division | Kalna Sub-division | Laying of different dia.UPVC pipeline at the damaged portion from Denur to Mousa Daukadanga under Putsuri & its adjoining mouzas water supply scheme within Kalna Sub-Division, under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000778/2021-2022 | 6013/BWD | 05/10/2021 | 30 | D.M. ENTERPRISE | 23.17 | 0 | 1
90 | Burdwan Division | Kalna Sub-division | Construction of Pump House cum switch room (5.40m x 3.60m) with sanitary arrangement (As per drawing no-PHE/SE/CC/PH/ DWG-01/2022-2023) at Aug. of MANTESWAR Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. 1 No Pump House. | Assistant Engineer |  | ORD/001013/2023-2024 | 467/BWD | 05/02/2024 | 60 | BISHWAJIT DAS | 5.86 | 0 | 100
91 | Burdwan Division | Burdwan Sadar Sub-Division | Quotation for new service connection of Augmentation of Raina water supply scheme.[REF ID-503550762][TW-3] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01691/2023-2024 | 1367/JJM | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.08 | 0 | 0
92 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration work at various location at Thanar Danga to Nandipara Kalitala via.Ranapara and Raina Co-Operative Society of Augmentation of Raina Water Supply Scheme at Raina-I Block within under Burdwan Division,PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000180/2023-2024 | 1004/BSD | 06/06/2023 | 15 | SOUMYAVASH DAS | 0.95 | 0 | 100
93 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of RAINA W/S Scheme (H.W SITE) under Raina-I Block within Burdwan Sub-Division, PHE Dte. [For 01 No. Tube well]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000190/2023-2024 | 2697/BWD | 08/06/2023 | 30 | RANADHIR SINHA | 13.2 | 0 | 100
94 | Burdwan Division | Burdwan Sadar Sub-Division | Laying Distribution of 160 mm dia HDPE pipeline for Augmentation of RAINA Piped Water Supply Scheme AT NODE 138 to 135, 135 to 119, 119 to 114, 114 to 110 to 105, 105 to 93 within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.B. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000365/2022-2023 | 1404/BSD | 10/08/2022 | 45 | RANADHIR SINHA | 4.77 | 0 | 0
95 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Raina W/S Scheme under Raina-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.12. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000501/2021-2022 | 187/BSD | 31/01/2022 | 30 | RADIANT | 2.72 | 0 | 1
96 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of 100 mm dia C.I. Sluice valve (P.N.-I) of Augmentation of Raina water supply scheme of Raina-I under Burdwan sub division, PHE Dte. Gr.C. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000572/2022-2023 | 1851/BSD | 21/10/2022 | 15 | SINHA BROTHERS | 0.47 | 0 | 1
97 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of RAINA Piped Water Supply Scheme with LDS, FHTC, Rising Main & Construction of 300 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test under Raina ¿ I Block, District - Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000600/2021-2022 | 1475/BWD | 14/03/2022 | 365 | RANADHIR SINHA | 319.21 | 0 | 100
98 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000060/2021-2022 | 559/BWD | 27/01/2022 | 0 | Resource Division | 12.84 | 0 | 0
99 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000095/2021-2022 | 932/BWD | 16/02/2022 | 0 | Resource Division | 23.01 | 0 | 0
100 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000217/2021-2022 | 1540/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
101 | Burdwan Division | Burdwan Sadar Sub-Division | Quotation for shifting of 11 KV Raina Local Feeder at Raina PHE under Burdwan South Division, WBSEDCL.[Ref ID-860249099, App ID-100000061079, dt.-22/09/2022] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | VCH/000558/2022-2023 | 675/DW/22-23 | 29/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.94 | 0 | 0
102 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
103 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of augmentation BHALKI Piped Water Supply Scheme at Bhalki (Part), Chandipur (Part), Samantapara (Part), Telota (Part) & Abhirampuri (Part) village, habitation, Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000006/2022-2023 | 1907/BWD | 07/04/2022 | 30 | ROY CONSTRUCTION | 49.52 | 0 | 1
104 | Burdwan Division | Durgapur Sub-DIvision | Restoration of Pipeline by Re-Laying of Pipe Line for Rejuvenation of BHALKI and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000104/2021-2022 | 3877/BWD | 27/07/2021 | 60 | ASHOK KUMAR GHOSH | 279.81 | 0 | 1
105 | Burdwan Division | Durgapur Sub-DIvision | Construction of Drain and restoration of connection for Augmentation of BHALKI W/S Scheme , Block- Ausgram-II, under Durgapur (Burdwan North)Sub Division Burdwan Division, P.H.E. Dte. [SL-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000121/2022-2023 | 334/DSD | 27/06/2022 | 30 | TAUSIF HOSSAIN MONDAL | 1.88 | 0 | 1
106 | Burdwan Division | Durgapur Sub-DIvision | Making structure with GI pipe for provision of joining and laying of pipeline near Abhirampur branch Canal for Bhalki and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-H] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000134/2022-2023 | 349/DSD | 30/06/2022 | 45 | PARTHA RAY | 1.9 | 0 | 1
107 | Burdwan Division | Kalna Sub-division | Load enhancement charges of Aug of Patuli water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | BILL/00563/2023-2024 | 665/JJM | 21/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.03 | 0 | 0
108 | Burdwan Division | Kalna Sub-division | Quotation from WBSEDCL for new service connection of Augmentation of Patuli TW-3 Water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | BILL/00666/2024-2025 | 826/JJM | 18/09/2024 | 0 | WBSEDCL | 7.53 | 0 | 0
109 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of JHAUDANGA (SM/16293), KASHIPUR (SM/16297), PATULI (SM/09718) & PARULIA (SM/09719) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000163/2024-2025 | 2202/BWD | 13/06/2024 | 631 | MONDAL PRECISION PVT LTD | 570 | 0 | 2
110 | Burdwan Division | Kalna Sub-division | Augmentation of PATULI Water Supply Scheme (Zone-I & II) with LDS, Rising Main, FHTC work, Pump House & Boundary Wall of Purbasthali - II Block in Kalna Sub-Division, District - Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000384/2021-2022 | 256/BWD | 13/01/2022 | 180 | IJABUL SEKH | 407.57 | 0 | 80
111 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Patuli W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | Assistant Engineer |  | ORD/000513/2021-2022 | 181/KSD | 21/02/2022 | 21 | M/S R. DUTTA & CO. | 3.75 | 0 | 1
112 | Burdwan Division | Kalna Sub-division | Work Order for "Replacement of Valve and Restoration of Concrete Roads at Patuli Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer |  | ORD/000549/2023-2024 | 1304/KSD | 23/08/2023 | 30 | IYASIN DAFADAR | 4.09 | 0 | 100
113 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at H.W & 2nd Tubewell site for PATULI (Zone-I & II) Piped Water Supply Scheme, Block - Purbasthali - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 + 2 = 4 Nos. GTW]. | Assistant Engineer |  | ORD/000640/2021-2022 | 1621/BWD | 21/03/2022 | 1025 | AUXILIARY TUBE WELL DRILLERS | 31.66 | 0 | 50
114 | Burdwan Division | Kalna Sub-division | Work Order for " Restoration of Pipeline and Other Allied Works i.c.w. Augmentation of PATULI(SM/09718) Piped Water Supply Scheme under PURBASTHALI-II Block,Kalna Sub-Division, District:- Purba Bardhaman." | Assistant Engineer |  | ORD/001187/2023-2024 | 2191/KSD | 15/03/2024 | 10 | IYASIN DAFADAR | 4.52 | 0 | 2
115 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000018/2021-2022 | 7348/BWD | 30/12/2021 | 0 | Resource Division | 13.73 | 0 | 0
116 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000033/2021-2022 | 557/BWD | 27/01/2022 | 0 | Resource Division | 22.05 | 0 | 0
117 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000097/2021-2022 | 769/BWD | 07/02/2022 | 0 | Resource Division | 51.93 | 0 | 0
118 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000165/2021-2022 | 1325/BWD | 08/03/2022 | 0 | Resource Division | 74.18 | 0 | 0
119 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000183/2021-2022 | 1378/BWD | 09/03/2022 | 0 | Resource Division | 4.45 | 0 | 0
120 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000233/2021-2022 | 1557/BWD | 15/03/2022 | 0 | Resource Division | 0 | 0 | 0
121 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001555/2021-2022 | 1194/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0
122 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
123 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of Patuli (Zone - II) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer |  | ORD/000065/2023-2024 | 2566/CMD | 06/06/2023 | 30 | M/S. S.R. ENTERPRISE | 21.77 | 0 | 0
124 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of JHAUDANGA (SM/16293), KASHIPUR (SM/16297), PATULI (SM/09718) & PARULIA (SM/09719) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000163/2024-2025 | 2202/BWD | 13/06/2024 | 631 | MONDAL PRECISION PVT LTD | 570 | 0 | 2
125 | Burdwan Division | Kalna Sub-division | Augmentation of PARULIA Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction 300 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Construction of Boundary wall under Kalna Sub-Division, Block ¿ Purbasthali ¿ II, Dist. - Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000437/2021-2022 | 699/BWD | 02/02/2022 | 365 | M/S ASHA CONSTRUCTION | 407.54 | 0 | 100
126 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 2nd TW Site of Aug. of PARULIA & its adjoining mouzas Piped Water Supply Scheme, Block ? Purbasthali ? II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000549/2022-2023 | 5126/BWD | 21/11/2022 | 30 | M/S SYCHROTECH INDUSTRY | 8.72 | 0 | 0
127 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Parulia W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-D) | Assistant Engineer |  | ORD/000582/2021-2022 | 216/KSD | 24/02/2022 | 21 | M/S R. DUTTA & CO. | 2.84 | 0 | 1
128 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000034/2021-2022 | 535/BWD | 27/01/2022 | 0 | Resource Division | 14.55 | 0 | 0
129 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000039/2022-2023 | 4632/BWD | 17/10/2022 | 0 | Resource Division | 12.32 | 0 | 0
130 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000080/2021-2022 | 604/BWD | 28/01/2022 | 0 | Resource Division | 24.12 | 0 | 0
131 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000108/2021-2022 | 906/BWD | 15/02/2022 | 0 | Resource Division | 6.93 | 0 | 0
132 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000240/2021-2022 | 1564/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
133 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
134 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Parhati W/S Scheme under Memari-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.13. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000502/2021-2022 | 188/BSD | 31/01/2022 | 30 | RADIANT | 2.72 | 0 | 1
135 | Burdwan Division | Burdwan Sadar Sub-Division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Paharhati, Nababhat, Shyamsundar & Dewandighi-Mirzapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000519/2022-2023 | 4703/BWD | 19/10/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 0 | 1
136 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PARHATI Piped Water Supply Scheme (Mouza- Akalia, Chandipur, Ganti, Kabastigiri, Kanpur, Kasipur, Madhupur, Parhati, Tajpur) of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000551/2022-2023 | 5193/BWD | 24/11/2022 | 45 | ANWESHA CONSTRUCTION | 39.72 | 0 | 1
137 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of PARHATI Piped Water Supply Scheme with LDS, Construction of 350 Cum capacity OHR with 20.0 Mtgr. Staging height inclusive of soil test & FHTC under Memari - II Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000597/2021-2022 | 1472/BWD | 14/03/2022 | 365 | ASHOK KUMAR GHOSH | 361.27 | 0 | 100
138 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Balance Functional Household Tap Connection (848 nos FHTC) from existing distribution system within the command area of PARHATI Piped Water Supply Scheme at (Akalia, Chandipur, Ganti, Kabastigiri, Kanpur, Kasipur, Madhupur, Parhati, Tajpur) Mouza, Construction of boundary wall at head work site & 2nd T/W site under MEMARI-II Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000776/2022-2023 | 1363/BWD | 22/03/2023 | 60 | ASHOK KUMAR GHOSH | 53.71 | 0 | 100
139 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000052/2021-2022 | 549/BWD | 27/01/2022 | 0 | Resource Division | 16.9 | 0 | 0
140 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000094/2021-2022 | 904/BWD | 15/02/2022 | 0 | Resource Division | 11.38 | 0 | 0
141 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000198/2021-2022 | 1521/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
142 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
143 | Burdwan Division | Kalna Sub-division | Restoration of existing concrete road and HDD Boring for laying distribution system of augmentation of Dhatrigram Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000079/2023-2024 | 2055/BWD | 04/05/2023 | 60 | PUSPA ENTERPRISE | 38.67 | 0 | 100
144 | Burdwan Division | Kalna Sub-division | Augmentation of Dhatrigram Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of new 500 cum capacity OHR with 20.0 mtr. Staging height with soil investigation including construction of 5(five) nos. switch-room(5.40mx3.6m), construction of five nos. new boundary wall for new TW sites & repairing of existing OHR, switch room & boundary wall under Kalna-I Block, District:- Purba-Burdwan. | Assistant Engineer | JUNIOR ENGINEER | ORD/000145/2022-2023 | 3046/BWD | 08/07/2022 | 1029 | PUSPA ENTERPRISE | 697.5 | 0 | 70
145 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of DHATRIGRAM Piped Water Supply Scheme, Block - Kalna - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | Assistant Engineer | JUNIOR ENGINEER | ORD/000219/2023-2024 | 2710/BWD | 08/06/2023 | 45 | AUXILIARY TUBE WELL DRILLERS | 19.76 | 0 | 100
146 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Dhatrigram W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-C) | Assistant Engineer | JUNIOR ENGINEER | ORD/000515/2021-2022 | 183/KSD | 21/02/2022 | 21 | LEMNISCATE | 3.17 | 0 | 1
147 | Burdwan Division | Kalna Sub-division | Shifting of pipe line of DHATRIGRAM Piped Water Supply Scheme for widening of road from Nabadwip more to Dhatrigram rail gate along the Dhatrigram-Burdwan road within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000685/2023-2024 | 4281/BWD | 29/09/2023 | 60 | IYASIN DAFADAR | 11.99 | 0 | 100
148 | Burdwan Division | Kalna Sub-division | Additional pipe laying and other allied works of distribution system for construction of New OHR Site within the command area of Aug. of DHATRIGRAM Piped Water Supply Scheme of KALNA Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000967/2023-2024 | 004/BWD | 02/01/2024 | 243 | PUSPA ENTERPRISE | 55.13 | 0 | 33
149 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000047/2022-2023 | 4850/BWD | 20/10/2022 | 0 | Resource Division | 15.4 | 0 | 0
150 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000178/2021-2022 | 1336/BWD | 08/03/2022 | 0 | Resource Division | 70.03 | 0 | 0
151 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000187/2021-2022 | 1382/BWD | 09/03/2022 | 0 | Resource Division | 3.88 | 0 | 0
152 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000230/2021-2022 | 1552/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
153 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
154 | Central Mechanical | Kalna Sub-division | Additional Quotation for new service connection for Dhatrigram Daspara PWSS . | Assistant Engineer | JUNIOR ENGINEER | BILL/00310/2024-2025 | BP-2024-25-151 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.45 | 0 | 0
155 | Central Mechanical | Kalna Sub-division | New service connection charges for Dhatrigram PWSS TW 4 | Assistant Engineer | JUNIOR ENGINEER | BILL/01485/2023-2024 | BP-2023-24-181 | 04/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.35 | 0 | 0
156 | Central Mechanical | Kalna Sub-division | New service connection charges for Dhatrigram PWSS TW-7 | Assistant Engineer | JUNIOR ENGINEER | BILL/01487/2023-2024 | BP-2023-24-182 | 04/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.36 | 0 | 0
157 | Central Mechanical | Kalna Sub-division | Supply and Installation of Submersible Pumping Machinery for breakdown maintenance along with allied accessories for Tube Well no- 3A & Lowering of pumping machinery at T.W-3B at DHATRIGRAM and some other works at jot raghab & Deriapur Water Supply Scheme, under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000109/2023-2024 | 387/CMSD-I | 19/04/2023 | 21 | CHOUDHURY ENTERPRISE | 0.69 | 0 | 0
158 | Central Mechanical | Kalna Sub-division | Installation of a Voltage correcting device along with allied accessories at DHATRIGRAM Water Supply Scheme, Pump house-2 under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000122/2023-2024 | 497/CMSD-I | 13/06/2023 | 21 | SUDIKSHA CONSTRUCTION | 3.48 | 0 | 0
159 | Central Mechanical | Kalna Sub-division | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000590/2024-2025 | 3105/CMD | 11/12/2024 | 60 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0
160 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 4 & 5 at Augumentation of DHATRIGRAM Water Supply Scheme [BLOCK- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001612/2023-2024 | 1543/CMD | 05/03/2024 | 60 | M/S. SWAPAN BANERJEE | 24.62 | 0 | 90
161 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration work of hard shoulder at Badulia Khandaghosh Road from 12.00 to 13.00 km (L/S) due to laying of water supply pipeline by PHE Dte. under Sadarghat Highway Sub-Division No.-I of Burdwan South Highway Division, P.W. Roads Dte. in the district of Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00362/2024-2025 | 565/JJM | 23/07/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 8.12 | 0 | 0
162 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of KHANDAGHOSH Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 600 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation & construction of boundary wall at Head works, 2nd TW & 3rd TW site under Khandaghosh Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000017/2022-2023 | 1967/BWD | 12/04/2022 | 365 | M/S JAN MAHAMMAD | 666.04 | 0 | 100
163 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Balance Functional Household Tap Connection (372 nos FHTC) from existing distribution system within the command area of KHANDAGHOSH Piped Water Supply Scheme at (Khandaghosh, Lodna, Metedanga, Nabagram, Kapsit, Barsiali) Mouza under KHANDAGHOSH Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000195/2023-2024 | 2689/BWD | 08/06/2023 | 30 | KAUSHIK RAY | 16.73 | 0 | 100
164 | Burdwan Division | Burdwan Sadar Sub-Division | Dismantling of concrete road for Augmentation of KHANDAGHOSH Pipe water supply scheme (Mouza: Khandaghosh, Lodna, Barisiali, Kapshit, Nabagram, Metedanga) at Khandaghosh Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000440/2022-2023 | 1466/BSD | 25/08/2022 | 45 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.84 | 0 | 1
165 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Khandaghosh W/S Scheme under Khandaghosh Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.15. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000504/2021-2022 | 190/BSD | 31/01/2022 | 30 | RADIANT | 3.01 | 0 | 1
166 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall at Head Works Site of Aug. of KHANDAGHOSH Water Supply Scheme under KHANDAGHOSH Block of Burdwan Division, PHE Dte. (Length -210.00 Mtr, Col-80 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000534/2023-2024 | 3631/BWD | 21/08/2023 | 60 | ROY ASSOCIATE | 28.73 | 0 | 100
167 | Burdwan Division | Burdwan Sadar Sub-Division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of KHANDAGHOSH Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte._SL. No. 07 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000618/2021-2022 | 141/AE/HQ | 16/03/2022 | 10 | MAKALI ENGINEERING CORPORATION | 4.52 | 0 | 0
168 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000015/2022-2023 | 3278/BWD | 29/07/2022 | 0 | Resource Division | 34.57 | 0 | 0
169 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000047/2021-2022 | 565/BWD | 27/01/2022 | 0 | Resource Division | 25.72 | 0 | 0
170 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000096/2021-2022 | 951/BWD | 17/02/2022 | 0 | Resource Division | 59.29 | 0 | 0
171 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000205/2021-2022 | 1528/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
172 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
173 | Burdwan Division | Central Mechanical Sub-Division | RAJAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under PURBASTHALI-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000656/2022-2023 | 359/BWD | 30/01/2023 | 519 | PABITRA KUMAR SAMANTA | 116.35 | 0 | 90
174 | Burdwan Division | Central Mechanical Sub-Division | Work order for ' Laying of Pipeline and providing FHTC under Rajapur(SM/16308) and Sadhpukharia PWSS (SM/14021) under Kalna Sub-Division under Burdwan Division, PHE Dte. '. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000804/2024-2025 | 1775/KSD | 20/11/2024 | 39 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 3.33 | 0 | 100
175 | Burdwan Division | Central Mechanical Sub-Division | Additional work for Increasing height of boundary wall & land development work and construction of retaining wall at 2nd TW site and construction of approach road at 1st TW Site of RAJAPUR Water Supply Scheme at Purbasthali-I Block within Kalna Sub- Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001039/2023-2024 | 782/BWD | 27/02/2024 | 30 | THE BENGAL HARDWARE | 11.55 | 0 | 100
176 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000086/2022-2023 | 1241/BWD | 17/03/2023 | 0 | Resource Division | 3.55 | 0 | 0
177 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000477/2023-2024 | 4001/BWD | 08/09/2023 | 0 | Resource Division | 1.09 | 0 | 0
178 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000807/2023-2024 | 298/BWD | 24/01/2024 | 0 | Resource Division | 8.86 | 0 | 0
179 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Rajapur PWSS TW-1 | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/01090/2023-2024 | BP-2023-24-120 | 17/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.97 | 0 | 0
180 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Rajapur PWSS TW-2 | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/01091/2023-2024 | BP-2023-24-121 | 17/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.51 | 0 | 0
181 | Central Mechanical | Central Mechanical Sub-Division | Damage restoration charges in connection with WBSEDCL electrification under Rajapur PWSS | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/01477/2023-2024 | BP-2023-24-176 | 29/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.1 | 0 | 0
182 | Central Mechanical | Central Mechanical Sub-Division | Addl. New service connection charges for Rajapur PWSS TW-1 | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/01730/2023-2024 | BP-2023-24-245 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.76 | 0 | 0
183 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at RAJAPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000053/2023-2024 | 2516/CMD | 02/06/2023 | 30 | M/S GHOSH ENTERPRISE | 20.8 | 0 | 90
184 | Burdwan Division | Kalna Sub-division | Laying of additional pipeline and providing FHTC at SUTRA water supply scheme under Kalna Sub-Division, Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000157/2024-2025 | 2175/BWD | 12/06/2024 | 120 | DUBE ENTERPRISE | 42.09 | 0 | 40
185 | Burdwan Division | Kalna Sub-division | Balance work for laying of pipeline, providing FHTC & other allied works in connection with Augmentation of MONTESWAR PWSS & SUTRA PWSS (SM/13280) under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000980/2024-2025 | 3572/BWD | 27/09/2024 | 181 | BAKSHI ENTERPRISE | 51.14 | 0 | 30
186 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000090/2022-2023 | 1243/BWD | 17/03/2023 | 0 | Resource Division | 10.3 | 0 | 0
187 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000101/2022-2023 | 1632/BWD | 06/04/2023 | 0 | Resource Division | 11.55 | 0 | 0
188 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000618/2023-2024 | 4885/BWD | 10/11/2023 | 0 | Resource Division | 33.21 | 0 | 0
189 | Central Mechanical | Kalna Sub-division | New service connection charges for Sutra PWSS TW-1 | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | BILL/00792/2023-2024 | BP-2023-24-80 | 25/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.89 | 0 | 0
190 | Central Mechanical | Kalna Sub-division | New service connection charges for Sutra PWSS TW-2 | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | BILL/00793/2023-2024 | BP-2023-24-81 | 25/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.84 | 0 | 0
191 | Central Mechanical | Kalna Sub-division | SUPPLY & INSTALLATION WORKS FOR SUTRA PWSS | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | BILL/02623/2023-2024 | BP-2023-24-558 | 21/02/2024 | 0 | M.S. ENTERPRISE | 21.99 | 0 | 0
192 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
193 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sutra Water Supply Scheme [ Block- Monteswar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000185/2023-2024 | 2967/CMD | 17/07/2023 | 30 | M.S. ENTERPRISE | 27.67 | 0 | 100
194 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to UCHALAN, CHAK CHANDAN, SERPUR & KATNABIL Piped Water Supply Scheme under Raina II Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000367/2023-2024 | 3076/BWD | 18/07/2023 | 988 | SK ALIM | 1307.56 | 0 | 75
195 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for Supply of one No.Diesel Driven Ambassador Car No. WB:41H-4009 on hire basis for the office of the Assistant Engineer,Burdwan Sub-Division,PHE Dte(Period from 01-03-2025 to 31.05.2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001407/2024-2025 | 457/BSD | 28/02/2025 | 90 | SK. ASFIA | 1.2 | 0 | 100
196 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000267/2023-2024 | 1898/BWD | 12/05/2023 | 0 | Resource Division | 11.69 | 0 | 0
197 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000504/2023-2024 | 4028/BWD | 08/09/2023 | 0 | Resource Division | 8.29 | 0 | 0
198 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000660/2023-2024 | 5118/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
199 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Chak Chandan PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01667/2023-2024 | BP-2023-24-220 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.07 | 0 | 0
200 | Central Mechanical | Burdwan Sadar Sub-Division | New electric connection for Chakchandan PWSS, PH-2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01874/2023-2024 | BP-2023-24-340 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.49 | 0 | 0
201 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
202 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chak Chandan Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000726/2023-2024 | 4037/CMD | 29/08/2023 | 30 | M/S. S.R. ENTERPRISE | 28.98 | 0 | 96
203 | Central Mechanical | Burdwan Sadar Sub-Division | Delivery of different Electro-mechanical items (for urgent FHTC) for Chak Chandan Water Supply Scheme PH 1 (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001669/2023-2024 | 08/CMSD | 02/01/2024 | 40 | CHOUDHURY ENTERPRISE | 0.92 | 0 | 100
204 | Central Mechanical | Burdwan Sadar Sub-Division | Supply and delivery of submersible pumping machinery (for urgent FHTC) for Chak Chandan Water Supply Scheme PH 1 (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001671/2023-2024 | 65/CMSD | 11/01/2024 | 12 | CHOUDHURY ENTERPRISE | 0.86 | 0 | 100
205 | Central Mechanical | Burdwan Sadar Sub-Division | Emergency installation (for urgent FHTC) at Chak Chandan Water Supply Scheme PH 1 (part-3) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001675/2023-2024 | 82/CMSD | 15/01/2024 | 12 | CHOUDHURY ENTERPRISE | 0.88 | 0 | 100
206 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KALIGRAM & PALITPUR Piped Water Supply Scheme under Burdwan I Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000499/2023-2024 | 3532/BWD | 10/08/2023 | 722 | SUPRITI ENTERPRISE | 704.5 | 0 | 50
207 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000096/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.64 | 0 | 0
208 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000300/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.63 | 0 | 0
209 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000719/2023-2024 | 5272/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
210 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Kaligram PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01676/2023-2024 | BP-2023-24-225 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.91 | 0 | 0
211 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new service connection at KALIGRAM W/S Scheme PH-II. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01815/2023-2024 | BP-2023-24-305 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.57 | 0 | 0
212 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
213 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kaligram Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000655/2023-2024 | 3998/CMD | 29/08/2023 | 30 | MITRA ENTERPRISE | 28.83 | 0 | 0
214 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAGRAM & KHEJURHATI Piped Water Supply Scheme under Khandaghosh Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000083/2023-2024 | 2080/BWD | 04/05/2023 | 698 | KHAN ENTERPRISE | 688.15 | 0 | 58
215 | Burdwan Division | Durgapur Sub-DIvision | Balance work for providing Functional Household Tap Connection (FHTC) within command area GOPALBERA & CHAGRAM W/S. Scheme of Khandaghosh Block under Burdwan Divn., PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000959/2024-2025 | 4438/BWD | 18/12/2024 | 253 | DUBE ENTERPRISE | 143.33 | 0 | 70
216 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000104/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 18.8 | 0 | 0
217 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000190/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 10.42 | 0 | 0
218 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000712/2023-2024 | 5043/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
219 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Chagram PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00819/2023-2024 | BP-2023-24-95 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.24 | 0 | 0
220 | Central Mechanical | Durgapur Sub-DIvision | New Electric connection Chagram W/S PH-II | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01791/2023-2024 | BP-2023-24-306 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.27 | 0 | 0
221 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 10
222 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chagram Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000213/2023-2024 | 3068/CMD | 21/07/2023 | 30 | PADMA ENGINEERING CO. | 28.96 | 0 | 100
223 | Burdwan Division | Central Mechanical Sub-Division | KOTALGHOSH Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000498/2023-2024 | 3528/BWD | 10/08/2023 | 965 | BRINDABAN KONAR | 325.17 | 0 | 5
224 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000113/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 1.92 | 0 | 0
225 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000387/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 1.48 | 0 | 0
226 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000812/2023-2024 | 306/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0
227 | Central Mechanical | Central Mechanical Sub-Division | Additional quotation in second time against additional works at Kotalghosh PWSS TW-2. | Assistant Engineer | Junior Engineer | BILL/00699/2024-2025 | BP-2024-25-269 | 23/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.87 | 0 | 0
228 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Kotalghosh PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01482/2023-2024 | BP-2023-24-183 | 04/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.28 | 0 | 0
229 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR KOTALGHOSH PWSS TW 2. | Assistant Engineer | Junior Engineer | BILL/02487/2023-2024 | BP-2023-24-540 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.46 | 0 | 0
230 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
231 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KOTALGHOSH Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000925/2023-2024 | 4188/CMD | 29/08/2023 | 610 | MITRA ASSOCIATE | 26.74 | 0 | 48
232 | Burdwan Division | Durgapur Sub-DIvision | Shifting of pipeline for Strengthening work of Anandabazar-Galsi via Sar Road under Asansol Highway Division P.W. (Roads) [Node No- 6-7-8-9-10] and restore damage pipeline at Askaran village due to construction of drain by the Kurkuba GP of BAHIRGHANNYA and its adjoining mouza's Piped W/S Scheme at Galsi-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000002/2023-2024 | 1604/BWD | 05/04/2023 | 84 | SUPRIYA RAY | 16.6 | 0 | 100
233 | Burdwan Division | Durgapur Sub-DIvision | Laying parallel pipeline to increase the water supply towards Kalyanpur [ Node No-146 t0 100 ] of BAHIRGHANNYA and its adjoining mouza's Piped W/S Scheme at Galsi-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000130/2022-2023 | 343/DSD | 30/06/2022 | 30 | SUPRIYA RAY | 4.89 | 0 | 1
234 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bahirgannya piped water supply scheme at Bahirgannya (04 Nos. habitation Part), Askaran (02 Nos. habitation), Brindabanpur (02 Nos. Habitation), Kurkuba (03 Nos Habitation) & Srirampur (02 Nos. Habitation) village, Galsi-II Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000564/2020-2021 | 5006/BWD | 10/12/2020 | 90 | SUPRIYA RAY | 99.82 | 0 | 1
235 | Burdwan Division | Burdwan Sadar Sub-Division | HARIGRAM Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Burdwan-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000684/2022-2023 | 481/BWD | 08/02/2023 | 693 | SAKTI ENTERPRISE | 262.46 | 0 | 81
236 | Burdwan Division | Burdwan Sadar Sub-Division | Allied works (OHR, FHTC, internal pathway, approach road and road restoration) for HARIGRAM PWSS under Bardhaman II Block within Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000722/2025-2026 | 1405/BWD | 16/05/2025 | 90 | S.R. ENTERPRISE | 14.32 | 0 | 0
237 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 183 | SK.ASFIA | 2.4 | 0 | 70
238 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000071/2022-2023 | 1252/BWD | 17/03/2023 | 0 | Resource Division | 7.5 | 0 | 0
239 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000108/2022-2023 | 1643/BWD | 06/04/2023 | 0 | Resource Division | 1.79 | 0 | 0
240 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000717/2023-2024 | 5267/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
241 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Harigram PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01471/2023-2024 | BP-2023-24-169 | 27/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.5 | 0 | 0
242 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Harigram PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01707/2023-2024 | BP-2023-24-236 | 06/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.69 | 0 | 0
243 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 12
244 | Central Mechanical | Burdwan Sadar Sub-Division | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000564/2024-2025 | 3103/CMD | 11/12/2024 | 60 | S DUTTA | 15.06 | 0 | 0
245 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Harigram Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000590/2023-2024 | 3940/CMD | 23/08/2023 | 30 | CHOUDHURY ENTERPRISE | 28.9 | 0 | 100
246 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000845/2023-2024 | 1759/BSD | 28/07/2023 | 66 | MD HASIN | 0.85 | 0 | 0
247 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000257/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.5 | 0 | 0
248 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000514/2023-2024 | 4038/BWD | 08/09/2023 | 0 | Resource Division | 0.41 | 0 | 0
249 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000667/2023-2024 | 5088/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
250 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Gangua W/S scheme TW No-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02274/2023-2024 | BP-2023-24-409 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.34 | 0 | 0
251 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Gangua PWSS TW 2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02414/2023-2024 | BP-2023-24-512 | 08/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.61 | 0 | 0
252 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 12
253 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gangua Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000649/2023-2024 | 3992/CMD | 29/08/2023 | 30 | C.M. ENTERPRISE | 28.85 | 0 | 90
254 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEARA, PATHARDANGA & SHIKARPUR Piped Water Supply Scheme under KALNA-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000734/2022-2023 | 1004/BWD | 06/03/2023 | 641 | M/S TAPAS KUMAR CHAKRABORTY | 1584.09 | 0 | 75
255 | Burdwan Division | Kalna Sub-division | Work Order For "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR NANDAI PWSS & SHIKARPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001144/2023-2024 | 1980/KSD | 09/02/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0 | 100
256 | Burdwan Division | Kalna Sub-division | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 51
257 | Burdwan Division | Kalna Sub-division | Temporary approach road from Shikarpur Graveyard to OHr site and Shikarpur Bus stand to 2nd tube well site in order to carry building materials for Shikarpur Piped W/S. Scheme (SM/14437) within Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001229/2024-2025 | 767/BWD | 27/02/2025 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 5.75 | 0 | 0
258 | Burdwan Division | Kalna Sub-division | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0
259 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000037/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 41.55 | 0 | 0
260 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000089/2022-2023 | 1249/BWD | 17/03/2023 | 0 | Resource Division | 15.17 | 0 | 0
261 | Central Mechanical | Kalna Sub-division | Quotation for new electric service connection at Shikarpur PH NO.-2 | Assistant Engineer | JUNIOR ENGINEER | BILL/01736/2023-2024 | BP-2023-24-247 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.73 | 0 | 0
262 | Central Mechanical | Kalna Sub-division | Electric quotation for New Service Connection at Shikarpur W/S Scehem PH-I. | Assistant Engineer | JUNIOR ENGINEER | BILL/01774/2023-2024 | BP-2023-24-287 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.57 | 0 | 0
263 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0
264 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SHIKARPUR Water Supply Scheme [ Block- KALNA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000836/2023-2024 | 4110/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 30.14 | 0 | 50
265 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEARA, PATHARDANGA & SHIKARPUR Piped Water Supply Scheme under KALNA-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000734/2022-2023 | 1004/BWD | 06/03/2023 | 641 | M/S TAPAS KUMAR CHAKRABORTY | 1584.09 | 0 | 75
266 | Burdwan Division | Kalna Sub-division | Work order for "Restoration of pipeline with other allied works at different places of Ghanashyampur mouja under Pathardanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | JUNIOR ENGINEER | ORD/000861/2024-2025 | 1846/KSD | 27/11/2024 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 4.22 | 0 | 100
267 | Burdwan Division | Kalna Sub-division | Work order for " Restoration of pipeline with other allied works at different places of Pathardanga mouja under Pathardanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | JUNIOR ENGINEER | ORD/000862/2024-2025 | 1847/KSD | 27/11/2024 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 4.14 | 0 | 100
268 | Burdwan Division | Kalna Sub-division | Work order for "Restoration of pipeline with other allied works at different places of Rampur mouja under Pathardanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER | ORD/000864/2024-2025 | 1849/KSD | 27/11/2024 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 3.66 | 0 | 100
269 | Burdwan Division | Kalna Sub-division | Work order for "Restoration of pipeline with other allied works at different places of Beshbati mouja of Pathardanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | JUNIOR ENGINEER | ORD/000867/2024-2025 | 1852/KSD | 27/11/2024 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 3.58 | 0 | 100
270 | Burdwan Division | Kalna Sub-division | Work Order for Supply of 1 (one) No. Diesel driven Motor cab on hire basis for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.07.2023 to 31.12.2023] | Assistant Engineer | JUNIOR ENGINEER | ORD/000898/2023-2024 | 825/KSD | 28/06/2023 | 184 | PARTHA PRATIM ACHARYA | 0 | 0 | 0
271 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL UNDER PATHARDANGA PWSS AND TAIPARA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE. (2 UNITS:- 1 NO FOR PATHARDANGA PWSS & 1 NO FOR TAIPARA PWSS)" | Assistant Engineer | JUNIOR ENGINEER | ORD/001141/2023-2024 | 1977/KSD | 09/02/2024 | 10 | BISWAS ENTERPRISE | 0.66 | 0 | 100
272 | Burdwan Division | Kalna Sub-division | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 51
273 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000088/2022-2023 | 1242/BWD | 17/03/2023 | 0 | Resource Division | 17.57 | 0 | 0
274 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000103/2022-2023 | 1636/BWD | 06/04/2023 | 0 | Resource Division | 4.2 | 0 | 0
275 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000498/2023-2024 | 4022/BWD | 08/09/2023 | 0 | Resource Division | 34.67 | 0 | 0
276 | Central Mechanical | Kalna Sub-division | New service connection charges for Pathardanga PWSS TW-2 | Assistant Engineer | JUNIOR ENGINEER | BILL/01530/2023-2024 | BP-2023-24-198 | 13/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.06 | 0 | 0
277 | Central Mechanical | Kalna Sub-division | New Service connection for Pathardanga W/S Scheme PH No.-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01803/2023-2024 | BP-2023-24-307 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.44 | 0 | 0
278 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0
279 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PATHARDANGA Water Supply Scheme [ Block- KALNA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000690/2023-2024 | 4016/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 29.61 | 0 | 60
280 | Burdwan Division | Central Mechanical Sub-Division | Constn. of pump house, Plinth Protection for Pump House & OHR, extension of pipeline for providing FHTC at MURULIA village, Adivasi para, approach road for 2nd Pump house of PURBA GOPALPUR PWSS Under Katwa Sub Division, Block- Mongolkote, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001124/2024-2025 | 496/BWD | 28/01/2025 | 397 | MONDAL ENTERPRISE | 26.97 | 0 | 67
281 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000109/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 35.89 | 0 | 0
282 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000181/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 17.8 | 0 | 0
283 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000729/2023-2024 | 5263/BWD | 30/11/2023 | 0 | Resource Division | 20.78 | 0 | 0
284 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Purba Gopalpur PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01416/2023-2024 | BP-2023-24-144 | 31/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.2 | 0 | 0
285 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Purba Gopalpur PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01769/2023-2024 | BP-2023-24-274 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.51 | 0 | 0
286 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
287 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PURBA GOPALPUR Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000560/2023-2024 | 3873/CMD | 17/08/2023 | 363 | UNIVERSAL ENTERPRISES | 29.94 | 0 | 90
288 | Burdwan Division | Burdwan Sadar Sub-Division | KURMUN Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000659/2023-2024 | 4124/BWD | 14/09/2023 | 818 | GHOSH CONCERN | 550.63 | 0 | 65
289 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-02-2024 to 30-04-2024) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001181/2023-2024 | 188/BSD | 31/01/2024 | 66 | PARVIN BEGAM | 0.85 | 0 | 97
290 | Burdwan Division | Burdwan Sadar Sub-Division | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001212/2023-2024 | 907/BWD | 04/03/2024 | 30 | MANASH GHOSH | 23.87 | 0 | 100
291 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work [ i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, with allied work of KURMUN Piped Water Supply Scheme, Block-Burdwan- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001220/2024-2025 | 727/BWD | 24/02/2025 | 120 | SHIVAM UN-EMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 95.65 | 0 | 0
292 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000102/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 9.02 | 0 | 0
293 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000391/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.67 | 0 | 0
294 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000725/2023-2024 | 5271/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
295 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Kurmun PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01675/2023-2024 | BP-2023-24-226 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0
296 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Kurmun PWSS | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02857/2023-2024 | BP-2023-24-603 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.63 | 0 | 0
297 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
298 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kurmun Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000658/2023-2024 | 4001/CMD | 29/08/2023 | 30 | S.P. CONSTRUCTION | 28.96 | 0 | 100
299 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch room, boundary walls with gates, land development, surface drains and internal pathways at different TW site for BAKALSA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000573/2023-2024 | 3723/BWD | 25/08/2023 | 727 | M/S GHOSH & CO. | 534.23 | 0 | 25
300 | Burdwan Division | Burdwan Sadar Sub-Division | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001212/2023-2024 | 907/BWD | 04/03/2024 | 30 | MANASH GHOSH | 23.87 | 0 | 100
301 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000090/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.25 | 0 | 0
302 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000222/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 21.15 | 0 | 0
303 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000575/2023-2024 | 4893/BWD | 10/11/2023 | 0 | Resource Division | 6.5 | 0 | 0
304 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000708/2023-2024 | 5041/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
305 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Bakalsa PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01828/2023-2024 | BP-2023-24-336 | 06/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.04 | 0 | 0
306 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Bakalsa PWSS. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02248/2023-2024 | BP-2023-24-395 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.99 | 0 | 0
307 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
308 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
309 | Burdwan Division | Burdwan Sadar Sub-Division | NANDIARA Piped Water Supply Scheme with sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of 200 cum capacity RCC OHRs with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site under Memari-II Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000487/2023-2024 | 3502/BWD | 10/08/2023 | 690 | S.S.S. ENTERPRISES | 451.06 | 0 | 45
310 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-12-2024 to 28-02-2025 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/001043/2024-2025 | 2636/BSD | 29/11/2024 | 90 | SK. ASFIA | 1.2 | 0 | 60
311 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-02-2024 to 30-04-2024) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/001181/2023-2024 | 188/BSD | 31/01/2024 | 66 | PARVIN BEGAM | 0.85 | 0 | 97
312 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000351/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.72 | 0 | 0
313 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000428/2023-2024 | 3836/BWD | 01/09/2023 | 0 | Resource Division | 2.35 | 0 | 0
314 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000680/2023-2024 | 5064/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
315 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for NANDIARA PWSS TW 1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | BILL/02442/2023-2024 | BP-2023-24-521 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.76 | 0 | 0
316 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for NANDIARA PWSS TW 2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | BILL/02443/2023-2024 | BP-2023-24-520 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.33 | 0 | 0
317 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0
318 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nandiara Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000715/2023-2024 | 4026/CMD | 29/08/2023 | 642 | JAGANNATH ENTERPRISE | 29.39 | 0 | 50
319 | Burdwan Division | Burdwan Sadar Sub-Division | KANDARSONA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Burdwan-II Block, District:- Purba-Bardhaman. [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000655/2022-2023 | 358/BWD | 30/01/2023 | 701 | M/S S.S. ENTERPRISE | 284.66 | 0 | 90
320 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000068/2022-2023 | 1256/BWD | 17/03/2023 | 0 | Resource Division | 6.23 | 0 | 0
321 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000113/2022-2023 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.3 | 0 | 0
322 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000721/2023-2024 | 5262/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
323 | Central Mechanical | Burdwan Sadar Sub-Division | New Service Connection charges for Kandarsona W/S Scheme TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00604/2023-2024 | BP-2023-24-11 | 17/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0
324 | Central Mechanical | Burdwan Sadar Sub-Division | New Service Connection charges for Kandarsona W/S Scheme TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00605/2023-2024 | BP-2023-24-12 | 17/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.4 | 0 | 0
325 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kandarsona Water Supply Scheme [Block- Burdwan-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000033/2023-2024 | 2471/CMD | 30/05/2023 | 30 | DUTTA ENTERPRISE | 28.92 | 0 | 80
326 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 12
327 | Central Mechanical | Burdwan Sadar Sub-Division | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000564/2024-2025 | 3103/CMD | 11/12/2024 | 60 | S DUTTA | 15.06 | 0 | 0
328 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & delivery of standby Submersible pumping machinery for Kandarsona & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001638/2023-2024 | 823/CMSD | 05/10/2023 | 21 | DUTTA ENTERPRISE | 0.84 | 0 | 98
329 | Central Mechanical | Burdwan Sadar Sub-Division | Re-orientation of delivery pipe line by supply & fitting fixing different CIDF materials, pressure gauge etc. at Kandarsona water supply scheme, T.W. No.- I & II under CMD, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001707/2023-2024 | 843/CMSD | 18/10/2023 | 10 | DUTTA ENTERPRISE | 0.79 | 0 | 99
330 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of hard shoulder from 0.00 km to 2.918 km of Sagrai Raina Road (MDR) for laying of water supply pipeline of Gopalpur PWSS under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01127/2023-2024 | 1084/JJM | 20/12/2023 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 4.72 | 0 | 0
331 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOPALPUR & RASUIKHANDA Piped Water Supply Scheme under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000006/2023-2024 | 1691/BWD | 12/04/2023 | 719 | SK ALIM | 1081.52 | 0 | 92
332 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 366 | SK ALIM | 1353.91 | 0 | 25
333 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000197/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 12.69 | 0 | 0
334 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000482/2023-2024 | 4006/BWD | 08/09/2023 | 0 | Resource Division | 5.14 | 0 | 0
335 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000669/2023-2024 | 5083/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
336 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Gopalpur PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01528/2023-2024 | BP-2023-24-193 | 11/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.82 | 0 | 0
337 | Central Mechanical | Burdwan Sadar Sub-Division | New electric connection for Gopalpur PWSS. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01869/2023-2024 | BP-2023-24-344 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.66 | 0 | 0
338 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
339 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gopalpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000720/2023-2024 | 4031/CMD | 29/08/2023 | 30 | M/S. SWAPAN BANERJEE | 28.98 | 0 | 100
340 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENRIA, MAHATA, DEBPUR Piped Water Supply Scheme under BHATAR Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000019/2023-2024 | 1737/BWD | 13/04/2023 | 993 | M/S B. RAI CONSTRUCTION COMPANY | 1643.39 | 0 | 81
341 | Burdwan Division | Durgapur Sub-DIvision | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period AUG.'2024 to OCT.'2024] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000845/2024-2025 | 575/DSD | 19/07/2024 | 78 | MD HASIN | 1 | 0 | 0
342 | Burdwan Division | Durgapur Sub-DIvision | FOR FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING SCHEME DESCRIPTION AT KHEJURHATI PWSS AND OTHER SCHEMES ( 16 Nos) WITHIN BHATAR BLOCK UNDER BURDWAN DIVISION , PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001422/2024-2025 | 298/DSD | 20/02/2025 | 21 | SHUBHRA KANTI GHOSH | 1.39 | 0 | 0
343 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000068/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 45.74 | 0 | 0
344 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000169/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 5.19 | 0 | 0
345 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000578/2023-2024 | 4926/BWD | 10/11/2023 | 0 | Resource Division | 37.58 | 0 | 0
346 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Mahata PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01830/2023-2024 | BP-2023-24-338 | 06/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.54 | 0 | 0
347 | Central Mechanical | Durgapur Sub-DIvision | New Service connection at Mahata PWSS PH-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02318/2023-2024 | BP-2023-24-538 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.24 | 0 | 0
348 | Central Mechanical | Durgapur Sub-DIvision | ADDITIONAL CONNECTION FOR MAHATA PWSS PH-1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02875/2023-2024 | BP-2023-24-599 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.1 | 0 | 0
349 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
350 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MAHATA Water Supply Scheme [ Block- BHATAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000822/2023-2024 | 4099/CMD | 29/08/2023 | 30 | BENGAL CONSTRUCTION. | 27.79 | 0 | 90
351 | Burdwan Division | Durgapur Sub-DIvision | Way leave / Track crossing proposal with Application ID: SER-ADRA-2024-WL-114 in IR-RBCS laying of 200 mm dia Carrier pipe with 600 mm dia Casing pipe for water supply on (Jal Jeevan Mission) at KM 317/03 to 317/04 in between Seharabazar (SRBZ) to Kaiyar (KYB) by PHE Dte.,Burdwan Division. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01098/2024-2025 | 1184/JJM | 20/12/2024 | 0 | INDIAN RAILWAY | 5.32 | 0 | 0
352 | Burdwan Division | Durgapur Sub-DIvision | AMILIA Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000737/2022-2023 | 1067/BWD | 13/03/2023 | 300 | SHUBHRA KANTI GHOSH | 247.76 | 0 | 40
353 | Burdwan Division | Durgapur Sub-DIvision | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period AUG.'2024 to OCT.'2024] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000845/2024-2025 | 575/DSD | 19/07/2024 | 78 | MD HASIN | 1 | 0 | 0
354 | Burdwan Division | Durgapur Sub-DIvision | Survey, planning, design of pipe crossing system by adopting trenchless technologies (e.g. Jack Pushing Method etc.) for crossing Railway, as per relevant I.S. Code with latest amendment, guidelines, specification and requirement of the authorities owning the railway track, submission of design report and drawing obtaining permission on behalf of the PHE Dte. across the railway track between Seharabazar (SRBZ) and Kaiyar (KYB) Station & connecting with existing 160mm dia HDPE distribution main line of AMILIA Water Supply Scheme of Khandaghosh Block under Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001308/2024-2025 | 938/BWD | 11/03/2025 | 30 | MANASH GHOSH | 30.33 | 0 | 0
355 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000084/2022-2023 | 1239/BWD | 17/03/2023 | 0 | Resource Division | 5.51 | 0 | 0
356 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000102/2022-2023 | 1637/BWD | 06/04/2023 | 0 | Resource Division | 1.93 | 0 | 0
357 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000789/2023-2024 | 319/BWD | 24/01/2024 | 0 | Resource Division | 21.17 | 0 | 0
358 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges of Amilia W/S Scheme TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00678/2023-2024 | BP-2023-24-23 | 21/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.9 | 0 | 0
359 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges of Amilia W/S Scheme TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00679/2023-2024 | BP-2023-24-24 | 21/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.81 | 0 | 0
360 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Amilia Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000051/2023-2024 | 2515/CMD | 02/06/2023 | 30 | MS MANABESH ROY | 28.91 | 0 | 90
361 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 10
362 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Balance works related sinking of Tube-wells at ARJURI village,PH,BW, LDS , Rising Mains, FHTCs,Road Restoration ,Land Development Etc. Construction of CHOTORAMCHANDRAPUR Piped Water Supply Scheme under Aushgram-II Block, of Durgapur Water supply Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000188/2024-2025 | 1610/DWSD | 26/11/2024 | 270 | KALPANA BUILDERS | 78.66 | 0 | 0
363 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000012/2024-2025 | 1724/G/DWSD | 10/12/2024 | 0 | Resource Division | 3.99 | 0 | 0
364 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000051/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.33 | 0 | 0
365 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000308/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 5.69 | 0 | 0
366 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000755/2023-2024 | 5244/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0
367 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Chhoto Ramchandrapur PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01486/2023-2024 | BP-2023-24-180 | 04/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.92 | 0 | 0
368 | Central Mechanical | Durgapur Sub-DIvision | New service connection for Choto Ramchandrapur W/S scheme TW No-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02276/2023-2024 | BP-2023-24-413 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.94 | 0 | 0
369 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chhoto Ramchandrapur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000688/2023-2024 | 4015/CMD | 29/08/2023 | 580 | JAL PRAVAHIKA PVT LTD | 27.77 | 0 | 48
370 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000366/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.26 | 0 | 0
371 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000499/2023-2024 | 4023/BWD | 08/09/2023 | 0 | Resource Division | 5.83 | 0 | 0
372 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000686/2023-2024 | 5079/BWD | 23/11/2023 | 0 | Resource Division | 19.78 | 0 | 0
373 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR PASCHIM NABAGRAM PWSS PH-2 | Assistant Engineer | Junior Engineer | BILL/00189/2024-2025 | BP-2024-25-86 | 15/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.13 | 0 | 0
374 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR PASCHIM NABAGRAM PWSS PH-1 | Assistant Engineer | Junior Engineer | BILL/00190/2024-2025 | BP-2024-25-85 | 15/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.06 | 0 | 0
375 | Central Mechanical | Central Mechanical Sub-Division | Additional Quotation for service connection at Paschim Nabagram PWSS PH-2. | Assistant Engineer | Junior Engineer | BILL/00419/2024-2025 | BP-2024-25-220 | 26/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12 | 0 | 0
376 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
377 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PASCHIM NABAGRAM Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000926/2023-2024 | 4189/CMD | 29/08/2023 | 30 | M/S. S.R. ENTERPRISE | 29.91 | 0 | 43
378 | Burdwan Division | Burdwan Sadar Sub-Division | BAHIRSARBAMANGALA-A Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000106/2023-2024 | 2297/BWD | 19/05/2023 | 365 | MLG CONSTRUCTION | 371.05 | 0 | 30
379 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000203/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.5 | 0 | 0
380 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000507/2023-2024 | 4031/BWD | 08/09/2023 | 0 | Resource Division | 3.08 | 0 | 0
381 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000645/2023-2024 | 5094/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
382 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Bahir Sarbamangala (Part-A) PWSS TW-1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02895/2023-2024 | BP-2023-24-624 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.85 | 0 | 0
383 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Bahir Sarbamangala (Part-A) PWSS TW-2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02896/2023-2024 | BP-2023-24-625 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.52 | 0 | 0
384 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
385 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bahir Sarbamangala-A Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001050/2023-2024 | 4045/CMD | 29/08/2023 | 672 | P.K. ENGINEERING | 29.35 | 0 | 45
386 | Durgapur W/S Division | Durgapur Sub-DIvision | Formal Work Order for Additional work for laying 200 mm dia HDPE pipe line and other necessary allied works Amarpur & Bhedia Piped W/S Scheme, Block- Aushgram-2, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000141/2024-2025 | 1291/DWSD | 06/09/2024 | 210 | SAIKAT RAY | 196.61 | 0 | 60
387 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Sinking of 300X200 mm dia TW,Pump House,Boundary wall concrete road & bituminous road restoration ,Jack pushing with laying of MS Pipe FHTC and land development of H/W Site drain & Internal pathway laying of MS pipe under Bhedia PWSS (JJM),Block-Aushgram-II,Dist-Purba Bardhaman under Durgapur W/S Division,PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000170/2024-2025 | 1611/DWSD | 26/11/2024 | 90 | SUPRIYA RAY | 87.54 | 0 | 0
388 | Burdwan Division | Durgapur Sub-DIvision | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways for BHEDIA Piped Water Supply Scheme under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000807/2023-2024 | 4847/BWD | 09/11/2023 | 730 | SUPRIYA RAY | 397.54 | 0 | 50
389 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000047/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.03 | 0 | 0
390 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000254/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 14.27 | 0 | 0
391 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000603/2023-2024 | 4909/BWD | 10/11/2023 | 0 | Resource Division | 33.07 | 0 | 0
392 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Bhedia PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00822/2024-2025 | BP-2024-25-319 | 30/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.48 | 0 | 0
393 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR BHEDIA PWSS PH-1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/03139/2023-2024 | BP-2023-24-649 | 20/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.26 | 0 | 0
394 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BHEDIA Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000826/2023-2024 | 4103/CMD | 29/08/2023 | 611 | WEST BENGAL ENGINEERING CO. | 27.76 | 0 | 80
395 | Burdwan Division | Central Mechanical Sub-Division | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | Assistant Engineer | Junior Engineer | ORD/000107/2024-2025 | 485/KTS | 16/04/2024 | 72 | AJIT SAMANTA | 0.92 | 0 | 10
396 | Burdwan Division | Central Mechanical Sub-Division | LAKHURIA Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000526/2023-2024 | 3619/BWD | 18/08/2023 | 867 | SK ABDUL LALAN | 317.51 | 0 | 53
397 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000114/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 1.64 | 0 | 0
398 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000393/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 5.83 | 0 | 0
399 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000814/2023-2024 | 295/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0
400 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Lakhuria PWSS PH-I. | Assistant Engineer | Junior Engineer | BILL/00342/2024-2025 | BP-2024-25-165 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0
401 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Lakhuria PWSS PH-2. | Assistant Engineer | Junior Engineer | BILL/00345/2024-2025 | BP-2024-25-166 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.69 | 0 | 0
402 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
403 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Lakhuria Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000769/2023-2024 | 4067/CMD | 29/08/2023 | 640 | GLACIER ENGINEERING CO | 26.98 | 0 | 43
404 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAJITPUR, SHUKUR & HARISHNAPUR Piped Water Supply Scheme under RAINA-I Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000388/2023-2024 | 3197/BWD | 24/07/2023 | 907 | MRITYUNJOY MUKHERJEE & CO. | 1242.03 | 0 | 55
405 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000275/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.85 | 0 | 0
406 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000481/2023-2024 | 4005/BWD | 08/09/2023 | 0 | Resource Division | 10.43 | 0 | 0
407 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000670/2023-2024 | 5084/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
408 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection at HARISHNAPUR, PWSS. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/02358/2023-2024 | BP-2023-24-483 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0
409 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Harishnapur PWSS TW-01 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/02411/2023-2024 | BP-2023-24-495 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.92 | 0 | 0
410 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
411 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Harishnapur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000721/2023-2024 | 4032/CMD | 29/08/2023 | 30 | SUBRATA BHADRA | 28.96 | 0 | 0
412 | Burdwan Division | Central Mechanical Sub-Division | MAKHALTOR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000733/2022-2023 | 1050/BWD | 10/03/2023 | 663 | HAMID SK | 195.79 | 0 | 99
413 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000064/2022-2023 | 1260/BWD | 17/03/2023 | 0 | Resource Division | 6.59 | 0 | 0
414 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges of Makhaltor W/S Scheme TW-1 | Assistant Engineer | Junior Engineer | BILL/00687/2023-2024 | BP-2023-24-35 | 26/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.3 | 0 | 0
415 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Makhaltor W/S Scheme TW-2 | Assistant Engineer | Junior Engineer | BILL/00697/2023-2024 | BP-2023-24-38 | 27/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.11 | 0 | 0
416 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0
417 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MAKHALTOR Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000108/2023-2024 | 2612/CMD | 08/06/2023 | 280 | SOUNAK ENTERPRISE | 27.65 | 0 | 30
418 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALGANA & GANGPUR Piped Water Supply Scheme under Burdwan ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000538/2023-2024 | 3699/BWD | 24/08/2023 | 769 | SUPRITI ENTERPRISE | 1345.79 | 0 | 20
419 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000012/2024-2025 | 4112/BWD | 25/11/2024 | 0 | Resource Division | 15.69 | 0 | 0
420 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000023/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 6.43 | 0 | 0
421 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000255/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.55 | 0 | 0
422 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000401/2023-2024 | 3873/BWD | 01/09/2023 | 0 | Resource Division | 5.75 | 0 | 0
423 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000566/2023-2024 | 4920/BWD | 10/11/2023 | 0 | Resource Division | 42.46 | 0 | 0
424 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new service connection Gangpur PWSS TW-2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00322/2024-2025 | BP-2024-25-163 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.72 | 0 | 0
425 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR GANGPUR TW 1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02953/2023-2024 | BP-2023-24-636 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.74 | 0 | 0
426 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 12
427 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gangpur Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000670/2023-2024 | 4008/CMD | 29/08/2023 | 30 | CHATTERJEE ENTERPRISE | 28.95 | 0 | 0
428 | Burdwan Division | Central Mechanical Sub-Division | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Ankhona, Pandugram, Sripur PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000286/2024-2025 | 2738/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 128.29 | 0 | 75
429 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ANKHONA, PANDUGRAM & SRIPUR Piped Water Supply Scheme under KETUGRAM¿I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000436/2023-2024 | 3388/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 989.13 | 0 | 50
430 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000014/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.55 | 0 | 0
431 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000325/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.91 | 0 | 0
432 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000614/2023-2024 | 4916/BWD | 10/11/2023 | 0 | Resource Division | 19.75 | 0 | 0
433 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR SRIPUR PWSS PH-2. | Assistant Engineer | Junior Engineer | BILL/00104/2024-2025 | BP-2024-25-45 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.76 | 0 | 0
434 | Central Mechanical | Central Mechanical Sub-Division | New Service connection at Sripur PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/02371/2023-2024 | BP-2023-24-489 | 01/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.49 | 0 | 0
435 | Central Mechanical | Central Mechanical Sub-Division | New service connection at Sripur PWSS TW No.2 | Assistant Engineer | Junior Engineer | BILL/02373/2023-2024 | BP-2023-24-490 | 01/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.54 | 0 | 0
436 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
437 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SRIPUR Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000862/2023-2024 | 4129/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 27.65 | 0 | 88
438 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Sripur Scheme (T/W-I & II) , Ketugram-I Block under Purba Bardhaman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000159/2023-2024 | 860/CDD | 10/07/2023 | 30 | OSMAN SEKH | 16.62 | 0 | 0
439 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 3rd Tube well site at Bagila village to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for BAGILA its Adjoining Mouza W/S scheme, block -MEMARI-I within Burdwan Sub-Division ,PHE Dte._2ND CALL | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000096/2023-2024 | 809/BSD | 03/05/2023 | 45 | A R TRADERS | 3.6 | 0 | 100
440 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of BAGILA Piped Water Supply Scheme with sinking of Tube-well, LDS & FHTC For Songoti Pally, LDS & FHTC For Station Para & LDS & FHTC For Taktipur, Baharampur, Krishnapur, Talchina & Kiskinda Habitation under Memari-I Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000172/2023-2024 | 3036/BWD | 14/07/2023 | 537 | H SAMANTA | 149.26 | 0 | 85
441 | Burdwan Division | Burdwan Sadar Sub-Division | Interconnection between Head Work site T/W to 2nd T/W site for BAGILA Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000182/2023-2024 | 1006/BSD | 06/06/2023 | 30 | A R TRADERS | 0.96 | 0 | 100
442 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of 150mm DI pipeline between Bagila health centre to Bagila Baroaritala for BAGILA Piped Water Supply Scheme to provide house connection under memari-I block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000336/2023-2024 | 1473/BSD | 12/07/2023 | 15 | A R TRADERS | 0.97 | 0 | 100
443 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Bagila PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000396/2023-2024 | 1584/BSD | 24/07/2023 | 15 | MEASURE LAND | 0.78 | 0 | 100
444 | Burdwan Division | Burdwan Sadar Sub-Division | Designing,making and erection of Sign Board for SWAJAL GRAM in Krishnapur village of Memari-I Block under Bagila Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000506/2025-2026 | 2350/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0
445 | Burdwan Division | Burdwan Sadar Sub-Division | Providing balance FHTC work on distribution system for FHTC work for BAGILA Piped Water Supply Scheme at various mouza within Memari I Block under Burdwan Divn., PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000687/2025-2026 | 1407/BWD | 16/05/2025 | 45 | H SAMANTA | 10.2 | 0 | 0
446 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC work on distribution system for FHTC work for BAGILA Piped W/S. Scheme at berhampur, Krishnapur, Kiskinda, Taktipur mouza within Memari I Block under Burdwan Divn., PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000713/2025-2026 | 2289/BWD | 06/08/2025 | 45 | H SAMANTA | 9.73 | 0 | 0
447 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration Rising main line for FHTC work and Construction of boundary wall at Head work site with gate and land development, drain and internal pathway and for BAGILA PWSS under Memari-I Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000904/2023-2024 | 5381/BWD | 08/12/2023 | 60 | SK RAJU | 35.42 | 0 | 100
448 | Burdwan Division | Burdwan Sadar Sub-Division | Replacement of Tube-well & Rising main at HEAD TW SITE for Aug. of BAGILA, SASINARA ZONE-I, SASINARA ZONE-II, Piped Water Supply Scheme within MEMARI-I Block under Burdwan Division, PHE. Dte. District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000974/2023-2024 | 027/BWD | 03/01/2024 | 60 | KOUSIK MALLICK | 38.87 | 0 | 90
449 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Aug. Bagila PWSS TW-3 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00769/2023-2024 | BP-2023-24-67 | 20/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.18 | 0 | 0
450 | Central Mechanical | Burdwan Sadar Sub-Division | Electric quotation for New Service Connection at Bagila W/S (Aug.) Scehem PH-IV. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01783/2023-2024 | BP-2023-24-291 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0
451 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Bagila Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000085/2023-2024 | 2591/CMD | 07/06/2023 | 30 | SUBRATA BHADRA | 11.09 | 0 | 50
452 | Central Mechanical | Burdwan Sadar Sub-Division | Illumination arrangement & different electro-mechanical works at BAGILA water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000414/2024-2025 | 2795/CMD | 01/10/2024 | 60 | GOENKA ENTERPRISE | 14.16 | 0 | 0
453 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & delivery of standby Submersible pumping machinery & automatic Chlorinator for Bagila & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001416/2023-2024 | 152/CMSD | 22/01/2024 | 15 | BEHERA ENTERPRISE | 1.74 | 0 | 100
454 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 4 at Augmentation of BAGILA Water Supply Scheme [ BLOCK- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001608/2023-2024 | 1537/CMD | 05/03/2024 | 240 | SUDIKSHA CONSTRUCTION | 12.32 | 0 | 100
455 | Burdwan Division | Burdwan Sadar Sub-Division | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Astikpur, Dakhinkul & Balagar of DERIAPUR Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000762/2022-2023 | 1296/BWD | 21/03/2023 | 651 | T.K. BANERJEE & CO. | 68.81 | 0 | 100
456 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAKULIA, KULSANA & HALIMPUR Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000461/2023-2024 | 3443/BWD | 08/08/2023 | 836 | ASHOK KUMAR GHOSH | 1588.1 | 0 | 15
457 | Burdwan Division | Central Mechanical Sub-Division | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | Assistant Engineer | Junior Engineer | ORD/001212/2023-2024 | 907/BWD | 04/03/2024 | 30 | MANASH GHOSH | 23.87 | 0 | 100
458 | Burdwan Division | Central Mechanical Sub-Division | Balance work of CHAKULIA Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman | Assistant Engineer | Junior Engineer | ORD/001263/2024-2025 | 846/BWD | 05/03/2025 | 120 | M/S M.M. ENTERPRISE | 214.08 | 0 | 0
459 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000014/2024-2025 | 4110/BWD | 25/11/2024 | 0 | Resource Division | 9.28 | 0 | 0
460 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000032/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
461 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000288/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.8 | 0 | 0
462 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000713/2023-2024 | 5047/BWD | 23/11/2023 | 0 | Resource Division | 19.78 | 0 | 0
463 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection for Chakulia PWSS TW-2. | Assistant Engineer | Junior Engineer | BILL/00253/2024-2025 | BP-2024-25-133 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.1 | 0 | 0
464 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection for Chakulia PWSS TW-1. | Assistant Engineer | Junior Engineer | BILL/00255/2024-2025 | BP-2024-25-134 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.57 | 0 | 0
465 | Central Mechanical | Central Mechanical Sub-Division | Additional quotation in second time against additional work at Chakulia PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/00683/2024-2025 | BP-2024-25-268 | 21/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.31 | 0 | 0
466 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
467 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and Compound lighting arrangement for Tube well No.- 1 & 2 at CHAKULIA Water Supply Scheme [BLOCK- MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman | Assistant Engineer | Junior Engineer | ORD/001604/2023-2024 | 1534/CMD | 05/03/2024 | 626 | CHATTERJEE ENTERPRISE | 28.81 | 0 | 70
468 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for Chakulia W/S Scheme (T/W-I & II), Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000198/2023-2024 | 1339/CDD | 13/09/2023 | 210 | M/S SAIKAT ENTERPRISE | 23.35 | 0 | 100
469 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of NATU W/S Scheme under Raina - I Block within Burdwan Sub-Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000204/2023-2024 | 2707/BWD | 08/06/2023 | 30 | M/S D. PALIT & CO. | 13.25 | 0 | 100
470 | Burdwan Division | Burdwan Sadar Sub-Division | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at Head Work Site and providing leftout FHTC, Road Restoration with allied work for NATU Piped Water Supply Scheme, Block-Raina-I within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000373/2024-2025 | 2994/BWD | 01/08/2024 | 487 | ANWESHA CONSTRUCTION | 55.19 | 0 | 75
471 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Natu PWSS under Raina-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000398/2023-2024 | 1586/BSD | 24/07/2023 | 15 | GEO-SOLUTION | 0.78 | 0 | 100
472 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch rooms & Rising main at different TW site for NATU Piped Water Supply Scheme under Raina - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000667/2023-2024 | 4164/BWD | 20/09/2023 | 300 | M/S MA TARA ENTERPRISE | 8.01 | 0 | 100
473 | Burdwan Division | Burdwan Sadar Sub-Division | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Birupur & Siyali of NATU Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000813/2022-2023 | 1576/BWD | 31/03/2023 | 761 | KALYAN CHOWDHURY | 30.88 | 0 | 100
474 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of Pipeline for providing Functional Household Tap Connection (FHTC) at Birupur & Sudarshanpur village under NATU Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001035/2023-2024 | 675/BWD | 19/02/2024 | 424 | KALYAN CHOWDHURY | 7.49 | 0 | 100
475 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR NATU (AUGMENTATION) PWSS TW 03 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/00118/2024-2025 | BP-2024-25-58 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.49 | 0 | 0
476 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Natu Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000097/2023-2024 | 2598/CMD | 07/06/2023 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 11.15 | 0 | 96
477 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of Pump House at Head Work site of Satgachia Zone-I Piped water supply scheme at Memari-II BlockUnder Burdwan Division, Dist.-Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000179/2024-2025 | 998/BSD | 06/06/2024 | 30 | INDRAJIT MONDAL | 0.96 | 0 | 90
478 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-I W/S Scheme at DEBIPUR Mouza under Memari-I Block and SATGACHIA Z-I W/S Scheme at BEGUNIA Mouza under Memari-II Block within Burdwan Sub-Division, PHE Dte. [For 02 Nos. Tube well]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000192/2023-2024 | 2687/BWD | 08/06/2023 | 60 | ANIRUDDHA FARUQUE | 26.48 | 0 | 50
479 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of Conc. road, Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for MAGRA, SANUI, SATGACHIA Zone-I & NARAGOHALIA PIPED WATER SUPPLY SCHEME, Block-Memari-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001192/2024-2025 | 611/BWD | 11/02/2025 | 180 | M/S ASHA CONSTRUCTION | 354.13 | 0 | 25
480 | Burdwan Division | Burdwan Sadar Sub-Division | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001269/2024-2025 | 848/BWD | 05/03/2025 | 120 | PROJECT INDIA | 394.29 | 0 | 0
481 | Burdwan Division | Burdwan Sadar Sub-Division | 150MM DI bypass pipeline at DVC Canel side for smooth water supply for FHTC from Patra mouza to Katna, Shrirampur & Begunia mouza under satgachia zone- I pwss within Memari- II block under Burdwan Division PHE DTE. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001335/2024-2025 | 633/BSD | 19/03/2025 | 30 | M/S ANAND CONSTRUCTION | 4.94 | 0 | 0
482 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR AUGMENTATION OF SATGACHIA PWSS | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/02825/2023-2024 | BP-2023-24-593 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.58 | 0 | 0
483 | Central Mechanical | Burdwan Sadar Sub-Division | Illumination arrangement & different electro-mechanical works at SATGACHIA (Zone-I, Part-B) water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000417/2024-2025 | 2801/CMD | 01/10/2024 | 60 | S.K. ELECTRICALS | 12.53 | 0 | 0
484 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of SATGACHIA(Z-I, Part-B)[MEMARI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000934/2023-2024 | 4197/CMD | 29/08/2023 | 30 | DAS TRADING CO. | 24.41 | 0 | 0
485 | Burdwan Division | Burdwan Sadar Sub-Division | UCHITPUR Single Village Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000789/2022-2023 | 1422/BWD | 24/03/2023 | 90 | ANWESHA CONSTRUCTION | 77.19 | 0 | 100
486 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC at leftour part of Malik Para of Uchitpur Village under UCHITPUR Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001037/2023-2024 | 281/BSD | 09/02/2024 | 30 | ANWESHA CONSTRUCTION | 0.95 | 0 | 100
487 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC at leftour part of Dhara Para of Uchitpur Village under UCHITPUR Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001094/2023-2024 | 518/BSD | 13/03/2024 | 30 | ANWESHA CONSTRUCTION | 0.95 | 0 | 100
488 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline & installation of Air Valve for providing FHTC at Dharapara & Malick para of Uchitpur village for UCHITPUR Piped Water Supply Scheme[New Scheme], Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001171/2023-2024 | 530/BSD | 14/03/2024 | 30 | ANWESHA CONSTRUCTION | 0.96 | 0 | 0
489 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000422/2023-2024 | 3839/BWD | 01/09/2023 | 0 | Resource Division | 1.31 | 0 | 0
490 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000698/2023-2024 | 5068/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
491 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Uchitpur PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/00776/2023-2024 | BP-2023-24-79 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.26 | 0 | 0
492 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
493 | Central Mechanical | Burdwan Sadar Sub-Division | Supply and Delivery of standby pump motor set for Sipta, Uchitpur, Haripur & others Water Supply Scheme under CMD, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000142/2024-2025 | 2596/CMD | 27/08/2024 | 30 | JOYGURU ENTERPRISE | 4.72 | 0 | 100
494 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Uchitpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000146/2023-2024 | 2881/CMD | 07/07/2023 | 331 | WEST BENGAL ENGINEERING CO. | 28.96 | 0 | 100
495 | Burdwan Division | Central Mechanical Sub-Division | Augmentation of SAHAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & renovation of switch-rooms & boundary walls at different TW site under Katwa-II Block, District:- Purba-Bardhaman. | Assistant Engineer | Junior Engineer,JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000132/2023-2024 | 2343/BWD | 22/05/2023 | 120 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 137.76 | 0 | 95
496 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Sahapur PWSS TW-1 | Assistant Engineer | Junior Engineer,JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | BILL/01521/2023-2024 | BP-2023-24-187 | 09/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.16 | 0 | 0
497 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Sahapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer,JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000096/2023-2024 | 2586/CMD | 07/06/2023 | 30 | M/S, S.S. ENTERPRISE. | 22.6 | 0 | 46
498 | Burdwan Division | Central Mechanical Sub-Division | MAHULA Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ketugram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000431/2023-2024 | 3665/BWD | 22/08/2023 | 300 | SUJATA CONSTRUCTION | 262.37 | 0 | 3
499 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000052/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.27 | 0 | 0
500 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000337/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.89 | 0 | 0
501 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000626/2023-2024 | 4872/BWD | 10/11/2023 | 0 | Resource Division | 29.6 | 0 | 0
502 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Mahula PWSS PH-I. | Assistant Engineer | Junior Engineer | BILL/00344/2024-2025 | BP-2024-25-173 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.02 | 0 | 0
503 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Mahula PWSS PH-2. | Assistant Engineer | Junior Engineer | BILL/00350/2024-2025 | BP-2024-25-172 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.31 | 0 | 0
504 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
505 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at MAHULA [KETUGRAM-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000882/2023-2024 | 4145/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 21.4 | 0 | 70
506 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilizing Departmental Machineries for Mahula W/S Scheme (T/W-I & II) , Ketugram-I Block under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 1057/CDD | 16/08/2023 | 30 | C.M. ENTERPRISE | 16.2 | 0 | 0
507 | Burdwan Division | Central Mechanical Sub-Division | NAYAPARA Piped Water Supply Scheme (Mini Scheme) with sinking of Tube-well, LDS, Rising Main, drain and internal pathway at different TW site under Mongolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000840/2023-2024 | 5121/BWD | 23/11/2023 | 464 | HAMID SK | 104.6 | 0 | 100
508 | Burdwan Division | Central Mechanical Sub-Division | Sinking of additional tube well, Construction of pump house, Boundary wall, Land development under NAYAPARA PWSS, Katwa Sub-Division, Block- Mongolkote, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001102/2024-2025 | 456/BWD | 21/01/2025 | 224 | HI-LIGHT ELECTRONICS | 34.04 | 0 | 20
509 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000036/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.66 | 0 | 0
510 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000353/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.93 | 0 | 0
511 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000816/2023-2024 | 297/BWD | 24/01/2024 | 0 | Resource Division | 14.5 | 0 | 0
512 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR NAYAPARA PWSS. | Assistant Engineer | Junior Engineer | BILL/02476/2023-2024 | BP-2023-24-532 | 13/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.03 | 0 | 0
513 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
514 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at NAYAPARA [MANGOLKOTE] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000892/2023-2024 | 4155/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 21.36 | 0 | 46
515 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PALISGRAM, PURBA NAYAPARA & SITAHATI Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000695/2023-2024 | 4364/BWD | 04/10/2023 | 910 | M/S S. CHOUDHURY | 1505.07 | 0 | 77
516 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000039/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.93 | 0 | 0
517 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000266/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 15.26 | 0 | 0
518 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000730/2023-2024 | 5231/BWD | 30/11/2023 | 0 | Resource Division | 20.37 | 0 | 0
519 | Central Mechanical | Central Mechanical Sub-Division | New service connection for Purba Nayapara PWSS TW 1. | Assistant Engineer | Junior Engineer | BILL/02911/2023-2024 | BP-2023-24-621 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.46 | 0 | 0
520 | Central Mechanical | Central Mechanical Sub-Division | New service connection for Purba Nayapara PWSS TW 2. | Assistant Engineer | Junior Engineer | BILL/02912/2023-2024 | BP-2023-24-622 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.56 | 0 | 0
521 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
522 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PURBA NAYAPARA Water Supply Scheme [ Block- MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000874/2023-2024 | 4137/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 29.6 | 0 | 88
523 | Burdwan Division | Central Mechanical Sub-Division | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | Assistant Engineer | Junior Engineer | ORD/000107/2024-2025 | 485/KTS | 16/04/2024 | 72 | AJIT SAMANTA | 0.92 | 0 | 10
524 | Burdwan Division | Central Mechanical Sub-Division | BANKAPASI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongolkote Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer | Junior Engineer | ORD/000501/2023-2024 | 3534/BWD | 10/08/2023 | 783 | DESTINATION SOLUTIONS & SERVICES PRIVATE LIMITED | 490.18 | 0 | 20
525 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000029/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 4.03 | 0 | 0
526 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000229/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.91 | 0 | 0
527 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000559/2023-2024 | 4892/BWD | 10/11/2023 | 0 | Resource Division | 27.17 | 0 | 0
528 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR BANKAPASI PWSS. | Assistant Engineer | Junior Engineer | BILL/02862/2023-2024 | BP-2023-24-613 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.89 | 0 | 0
529 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR BANKAPASI PWSS TW- 2. | Assistant Engineer | Junior Engineer | BILL/02864/2023-2024 | BP-2023-24-614 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.23 | 0 | 0
530 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
531 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BANKAPASI Water Supply Scheme [ Block- MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000877/2023-2024 | 4140/CMD | 29/08/2023 | 640 | CHOUDHURY ENTERPRISE | 28.62 | 0 | 43
532 | Burdwan Division | Central Mechanical Sub-Division | JHAMATPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000134/2023-2024 | 2384/BWD | 23/05/2023 | 300 | M/S M.M. ENTERPRISE | 228.72 | 0 | 80
533 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000059/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.42 | 0 | 0
534 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000293/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 2.35 | 0 | 0
535 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000594/2023-2024 | 4902/BWD | 10/11/2023 | 0 | Resource Division | 10 | 0 | 0
536 | Central Mechanical | Central Mechanical Sub-Division | Supplimentary Quotation for ROW at Jhamatpur PWSS TW-2. | Assistant Engineer | Junior Engineer | BILL/00254/2024-2025 | BP-2024-25-132 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.71 | 0 | 0
537 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Jhamatpur PWSS Tw-1 | Assistant Engineer | Junior Engineer | BILL/00761/2023-2024 | BP-2023-24-63 | 18/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.3 | 0 | 0
538 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Jhamatpur PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01899/2023-2024 | BP-2023-24-369 | 15/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.3 | 0 | 0
539 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0
540 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at JHAMATPUR Water Supply Scheme [Block - KETUGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 2887/CMD | 10/07/2023 | 730 | A.S. ENTERPRISE | 20.76 | 0 | 40
541 | Burdwan Division | RWS Burdwan Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AKALPAUSH & BIRUHA Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | ORD/000542/2023-2024 | 3698/BWD | 24/08/2023 | 365 | SUPRITI ENTERPRISE | 1010.87 | 0 | 37
542 | Burdwan Division | RWS Burdwan Sub-Division | Work order for "Restoration of pipeline with other allied works at different places of Bardalia,Masidpur,Biruha,Mainagari mouja under Birhua Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-II panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | ORD/000860/2024-2025 | 1845/KSD | 27/11/2024 | 15 | SUPRITI ENTERPRISE | 2.89 | 0 | 100
543 | Burdwan Division | RWS Burdwan Sub-Division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR BIRUHA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | ORD/001147/2023-2024 | 2096/KSD | 04/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0 | 2
544 | Burdwan Division | RWS Burdwan Sub-Division | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0
545 | Burdwan Division | RWS Burdwan Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | RTOR000070/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 12.79 | 0 | 0
546 | Burdwan Division | RWS Burdwan Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | RTOR000263/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.53 | 0 | 0
547 | Burdwan Division | RWS Burdwan Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | RTOR000608/2023-2024 | 4913/BWD | 10/11/2023 | 0 | Resource Division | 35.77 | 0 | 0
548 | Central Mechanical | RWS Burdwan Sub-Division | New electric connection for Biruha PWSS, PH-1. | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | BILL/01870/2023-2024 | BP-2023-24-354 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0
549 | Central Mechanical | RWS Burdwan Sub-Division | New electric connection for Biruha PWSS, PH-2. | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | BILL/01871/2023-2024 | BP-2023-24-355 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.94 | 0 | 0
550 | Central Mechanical | RWS Burdwan Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 20
551 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of JHAUDANGA (SM/16293), KASHIPUR (SM/16297), PATULI (SM/09718) & PARULIA (SM/09719) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000163/2024-2025 | 2202/BWD | 13/06/2024 | 631 | MONDAL PRECISION PVT LTD | 570 | 0 | 2
552 | Burdwan Division | Kalna Sub-division | Augmentation of KASHIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Purbasthali - II Block, Purba Burdwan District under Burdwan Division, PHE.Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000176/2023-2024 | 2588/BWD | 01/06/2023 | 60 | BAKSHI ENTERPRISE | 19.74 | 0 | 100
553 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 09 Nos. Piped W/S. Schemes under Purbasthali II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000338/2024-2025 | 3018/BWD | 05/08/2024 | 50 | HORIZEN | 23.7 | 0 | 10
554 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR KASHIPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001166/2023-2024 | 2022/KSD | 06/03/2024 | 10 | DEL DELTA CONSTRUCTION | 0.66 | 0 | 100
555 | Central Mechanical | Kalna Sub-division | New service connection charges for Kashipur PWSS TW-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01866/2023-2024 | BP-2023-24-356 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.77 | 0 | 0
556 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of KASHIPUR[PURBASTHALI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001080/2023-2024 | 4437/CMD | 01/11/2023 | 30 | DUTTA ENTERPRISE | 24.4 | 0 | 100
557 | Burdwan Division | Kalna Sub-division | Augmentation of BUNDEBAJ PWSS to accommodate FHTC Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Kalna - II Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000728/2023-2024 | 4615/BWD | 17/10/2023 | 60 | M/S CHANDRANATH MUKHERJEE | 39.76 | 0 | 100
558 | Burdwan Division | Kalna Sub-division | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0
559 | Central Mechanical | Kalna Sub-division | Quotation for load enhancement of Bundebaj PWSS TW-2 | Assistant Engineer |  | BILL/00812/2024-2025 | BP-2024-25-303 | 24/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.51 | 0 | 0
560 | Central Mechanical | Kalna Sub-division | Quotation for load enhancement of Bundebaj PH-2 | Assistant Engineer |  | BILL/00813/2024-2025 | BP-2024-25-304 | 24/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.51 | 0 | 0
561 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of BUNDEBAJ[KALNA-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer |  | ORD/001078/2023-2024 | 4202/CMD | 29/08/2023 | 30 | C.M. ENTERPRISE | 24.42 | 0 | 0
562 | Burdwan Division | Central Mechanical Sub-Division | MASARU Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 100 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mangalkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000495/2023-2024 | 3522/BWD | 10/08/2023 | 754 | M/S B.N. GUPTA | 262.74 | 0 | 100
563 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000341/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.25 | 0 | 0
564 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000451/2023-2024 | 3975/BWD | 08/09/2023 | 0 | Resource Division | 0.98 | 0 | 0
565 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000582/2023-2024 | 4896/BWD | 10/11/2023 | 0 | Resource Division | 13.36 | 0 | 0
566 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Mosharu PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/02194/2023-2024 | BP-2023-24-375 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.85 | 0 | 0
567 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Mosharu PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/02195/2023-2024 | BP-2023-24-374 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.41 | 0 | 0
568 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
569 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at MASARU [MONGOLKOTE] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000884/2023-2024 | 4147/CMD | 29/08/2023 | 640 | CHOUDHURY ENTERPRISE | 21.27 | 0 | 46
570 | Burdwan Division | Burdwan Sadar Sub-Division | Pipeline with FHTC for KEUNTA Water Supply Scheme at Kalui village (30 Nos.), Keunta village (30 Nos.), Mandarpur village (30 Nos.), Rampur village (30 Nos.), Nandanpur village (60 Nos.), within Raina-II Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000712/2022-2023 | 855/BWD | 28/02/2023 | 45 | DUBE ENTERPRISE | 60.1 | 0 | 100
571 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of SAJIARA (SM/09716), NAMA BHANDARTIKURI (SM/14917) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000394/2024-2025 | 3010/BWD | 02/08/2024 | 240 | PRATIMA CONSTRUCTION | 79.16 | 0 | 2
572 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NAMA BHANDARITURI, SAHAPUR & MOUDANGA Piped Water Supply Scheme under PURBASTHALI-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000511/2023-2024 | 3689/BWD | 23/08/2023 | 770 | THE MAHADEV CONSTRUCTION | 734.18 | 0 | 50
573 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000349/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.77 | 0 | 0
574 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000509/2023-2024 | 4033/BWD | 08/09/2023 | 0 | Resource Division | 0.33 | 0 | 0
575 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000805/2023-2024 | 304/BWD | 24/01/2024 | 0 | Resource Division | 3.84 | 0 | 0
576 | Central Mechanical | Kalna Sub-division | New service connection for Nama Bhandartikuri W/S Scheme. | Assistant Engineer | JUNIOR ENGINEER | BILL/02190/2023-2024 | BP-2023-24-385 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.19 | 0 | 0
577 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0
578 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at NAMA BHANDARITURI Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000830/2023-2024 | 4107/CMD | 29/08/2023 | 30 | B.P. TRADING CORPORATION | 20.79 | 0 | 60
579 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for the work of Trial bore with necessary allied work and supply and delivery of office furnitures for the new office setup of the EE/DWSD/PHE Dte. at Nababhat,Purba bardhaman.in connection with Taherpur W/S Scheme under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000038/2024-2025 | 750/DWSD | 05/06/2024 | 90 | K.M. ENTERPRISE | 3.83 | 0 | 100
580 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for the work of " Construction of Additional Store Room at Nababhat Office Building under Galsi-II Pipe Water Supply Scheme (JJM) under Durgapur W/S Division, PHE Dte |  |  | ORD/000046/2024-2025 | 764/DWSD | 06/06/2024 | 90 | KIRON ENTERPRISE | 17.08 | 0 | 30
581 | Durgapur W/S Division |  | Formal Work Order for the work of Sinking of 3 nos 300 x 200mm dia Tube Well-150 mtr and 7 Nos 200 x 200 mm dia River Bank Tube Well- 51 mtr with Construction of Pump House Cum Switch Room Chlorine Room under TAHERPUR PWSS (JJM) Block- Galsi-II, Distric- Purba Bardhaman under Durgapur W/S Division, PHE Dte |  |  | ORD/000093/2024-2025 | 1000/DWSD | 11/07/2024 | 520 | S & P ENTERPRISE | 102.54 | 0 | 60
582 | Durgapur W/S Division |  | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe Carring Bridge with Pipe supporting structure under TAHERPUR and KHANO Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte. |  |  | ORD/000158/2024-2025 | 1506/DWSD | 05/11/2024 | 236 | MANASH GHOSH | 1114.23 | 0 | 60
583 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for Preparation and Submission of Structural Design Calculation (Civil) & Structural drawing of Proposed CWR with M.S Structural Pump House over cwr, WBSEDCL Mettering Room and - PDB Room -2 Nos, Transformer yeard -2 nos, Chlorin Room -1 No with General Arrangement Drawing of Internal Road - Drain & necessary Soil investigation at Intake Site of "THERPUR (Zone-I, II, III) and KHANO (Zone I & II) PWSS (6 Copy) under Durgapur W/s Division, PHE Dte. |  |  | ORD/000192/2024-2025 | 1608/DWSD | 26/11/2024 | 45 | DAFFODIL | 9.48 | 0 | 90
584 | Durgapur W/S Division |  | Formal Work Order for the work of " Sinking of 3 nos. 300 x 200 mm dia T/W- 150 mtr and 7 nos 200 x 200 mm dia River Bank T/W- 51 mtr with Construction of P/H cum switch room under Taherpur PWSS (JJM) Block- Galsi-II, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. |  |  | ORD/000317/2023-2024 | 377/DWSD | 15/03/2024 | 90 | S & P ENTERPRISE | 0 | 0 | 0
585 | Burdwan Division |  | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. |  |  | ORD/000872/2023-2024 | 5324/BWD | 01/12/2023 | 120 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 0 | 100
586 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000329/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 55.9 | 0 | 0
587 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000400/2023-2024 | 3831/BWD | 01/09/2023 | 0 | Resource Division | 269.94 | 0 | 0
588 | Central Mechanical |  | Quotation for new service connection for Taherpur PWSS TW - 2 (Z-I) |  |  | BILL/00296/2024-2025 | BP-2024-25-146 | 19/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0
589 | Central Mechanical |  | Quotation for new service connection at Taherpur PWSS TW-3 |  |  | BILL/01092/2024-2025 | BP-2024-25-404 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.08 | 0 | 0
590 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for OHR SITE of Zone-1, 2, & 3 at TAHERPUR Water Supply Scheme [ BLOCK- Galsi-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000560/2024-2025 | 3102/CMD | 11/12/2024 | 60 | M/S, S.S. ENTERPRISE. | 38.16 | 0 | 28
591 | Central Mechanical |  | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Taherpur-khano sub surface water supply scheme under Central Mechanical Division PHE Dte. |  |  | ORD/000784/2024-2025 | 480/CMD | 06/02/2025 | 75 | GLACIER ENGINEERING CO | 105.71 | 0 | 0
592 | Burdwan Division |  | Different types of works in connection with implementation of MIRGAHAR Piped Water Supply Scheme (SM/18365) & BAGPUR PWSS (SM/13323) under Kalna Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000186/2024-2025 | 2400/BWD | 26/06/2024 | 120 | M/S S. CHOUDHURY | 301.24 | 0 | 60
593 | Burdwan Division |  | MIRGAHAR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 700 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls and land development, drain and internal pathway at different TW site under Monteswar Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000374/2023-2024 | 3104/BWD | 19/07/2023 | 365 | M/S S. CHOUDHURY | 929.46 | 0 | 60
594 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000357/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 19.8 | 0 | 0
595 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000461/2023-2024 | 3985/BWD | 08/09/2023 | 0 | Resource Division | 262.83 | 0 | 0
596 | Central Mechanical |  | New service connection charges for Mirghar PWSS TW-2 |  |  | BILL/01368/2023-2024 | BP-2023-24-134 | 24/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.42 | 0 | 0
597 | Central Mechanical |  | New service connection charges for Mirghar PWSS TW-3 |  |  | BILL/01369/2023-2024 | BP-2023-24-135 | 24/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.29 | 0 | 0
598 | Central Mechanical |  | NEW SERVICE CONNECTION FOR MIRGHAR PWSS |  |  | BILL/02591/2023-2024 | BP-2023-24-552 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.8 | 0 | 0
599 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
600 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1,2, 3 & 4 at MIRGHAR Water Supply Scheme [ Block- MONTESWAER] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000467/2023-2024 | 3724/CMD | 08/08/2023 | 30 | P.K. ENGINEERING | 59.87 | 0 | 75
601 | Central Mechanical |  | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000590/2024-2025 | 3105/CMD | 11/12/2024 | 60 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0
602 | Central Mechanical |  | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000602/2024-2025 | 3106/CMD | 11/12/2024 | 60 | S.K. ELECTRICALS | 13.6 | 0 | 0
603 | Central Mechanical |  | Supply and delivery of Stationary items for the official works related with Mirghar and differents water supply scheme under JJM Programme for Central Mechanical Division and its subordinate offices of P.H.E. Dte. |  |  | ORD/001033/2023-2024 | 702/CMSD | 17/08/2023 | 10 | BURDWAN DISTRICT CENTRAL SERVICE CUM MARKETING INDUSTRIAL CO-OPARETIVE UNION LTD | 0.74 | 0 | 100
604 | Central Mechanical |  | continuation order Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of Assistant Engineer, under C.M.D. P.H.E. Dte. w.e.f.- 01/01/2024 to 29/02/2024. [Under JJM Works] |  |  | ORD/001636/2023-2024 | 1240/CMSD | 31/12/2023 | 60 | SUBRATA BHADRA | 0.79 | 0 | 100
605 | Burdwan Division |  | Restoration work of Sankarpur - Nibhuji bazar Road from 13.80 km to 15.75km. damaged due to laying of underground water pipe line by PHE with box cutting and Jhama with moorum consolidation under Kalna Highway sub Division of Burdwan south Highway Division P.W(Roads) Dte . During the year 2023-24 |  |  | BILL/00644/2024-2025 | 825/JJM | 13/09/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 3.34 | 0 | 0
606 | Burdwan Division |  | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. |  |  | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 366 | SK ALIM | 1353.91 | 0 | 25
607 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000280/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 6.97 | 0 | 0
608 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000427/2023-2024 | 3858/BWD | 01/09/2023 | 0 | Resource Division | 2.13 | 0 | 0
609 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000691/2023-2024 | 5066/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
610 | Central Mechanical |  | New service connection for Shankarpur PWSS TW-1. |  |  | BILL/02279/2023-2024 | BP-2023-24-436 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.32 | 0 | 0
611 | Central Mechanical |  | NEW SERVICE CONNECTION FOR SANKARPUR PWSS TW 2. |  |  | BILL/03181/2023-2024 | BP-2023-24-665 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.26 | 0 | 0
612 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
613 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sankarpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000723/2023-2024 | 4034/CMD | 29/08/2023 | 30 | GOENKA ENTERPRISE | 29.4 | 0 | 95
614 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of TALIT-SIMDAL Piped Water Supply Scheme with LDS, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test, Construction of boundary wall construction at Head work site & FHTC under Burdwan ¿ I Block, District - Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000004/2022-2023 | 1876/BWD | 05/04/2022 | 1122 | M/S S.S. ENTERPRISE | 576.42 | 0 | 85
615 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Talit-Simdal W/S Scheme under Burdwan-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.8. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000496/2021-2022 | 183/BSD | 31/01/2022 | 30 | RADIANT | 2.96 | 0 | 1
616 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of TALIT-SIMDAL & its adjoining mouzas Piped Water Supply Scheme, Block - Burdwan - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000553/2022-2023 | 5195/BWD | 24/11/2022 | 30 | ANIRUDDHA FARUQUE | 11.35 | 0 | 0
617 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000042/2021-2022 | 538/BWD | 27/01/2022 | 0 | Resource Division | 20.19 | 0 | 0
618 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000088/2021-2022 | 880/BWD | 11/02/2022 | 0 | Resource Division | 9.9 | 0 | 0
619 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000232/2021-2022 | 1556/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
620 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
621 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for Additional work of Construction of CWR cum Pump House with MS Structural work, Substation, Chlorine Room etc, Laying of MS pipe and necessary allied works of Surface Based Purangan and 11 Nos Mouzas Sub Surface based Pipe W/S Scheme (JJM) under Galsi-I Block, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. |  |  | ORD/000124/2024-2025 | 1112/DWSD | 02/08/2024 | 120 | MANASH GHOSH | 98.87 | 0 | 0
622 | Durgapur W/S Division |  | Formal Work Order for Road Restoration work of PWD Road for laying of Rising Main of 11 Nos Mouzas and Purangan PWSS under Sub Surface Based 11 Nos Mouzas Pipe W/S Scheme (JJM), Galsi-I Block, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. |  |  | ORD/000140/2024-2025 | 1290/DWSD | 06/09/2024 | 275 | MANASH GHOSH | 216.51 | 0 | 80
623 | Durgapur W/S Division |  | Formal Work Order for Additional work of Soil investigation & construction of CWR/Pump House etc, Land development of H/W Site,drain & internal Path Way, Concrete Road Restoration,FHTC with Platform with necessary allied Works of Sub Surface Based PURANGAN Pipe W/S Scheme (JJM) under Galsi - I Block, Dist - Purba- Bardhaman ,under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000163/2024-2025 | 1521/DWSD | 11/11/2024 | 360 | MANASH GHOSH | 789.87 | 0 | 75
624 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for Preparation and Submission of Structural Design Calculation (Civil) & Structural drawing of Proposed CWR with M.S Structural Pump House over cwr, WBSEDCL Mettering Room and - PDB Room -2 Nos, Transformer yeard -2 nos, Chlorin Room -1 No with General Arrangement Drawing of Internal Road - Drain & necessary Soil investigation at Intake Site of "PURANGAN (Zone-I, II, III) and 11 Nos. Mouzas PWSS under Durgapur W/s Division, PHE Dte. |  |  | ORD/000190/2024-2025 | 1607/DWSD | 26/11/2024 | 45 | MANASH GHOSH | 9.46 | 0 | 100
625 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for the work of Sinking of 3 Nos 300 x 200 mm dia T/W 150 mtr and 5 nos 200 x 200 mm dia River Bank T/W 51 mtr with Construction of 3 nos P/H cum switch room under chlorine room under PURANGAN PWSS (JJM), Block:- Galsi-I , Dist- Purba Bardhaman. |  |  | ORD/000309/2023-2024 | 372/DWSD | 15/03/2024 | 90 | MANASH GHOSH | 90.55 | 0 | 53
626 | Burdwan Division |  | Sub Surface Based Piped Water Supply Scheme with LDS, FHTC, Construction of different capacity RCC OHRs with 20.0 mtr. with Staging height including soil investigation, Construction of CWR, Chlorine Room, Guard Room, Sub Station Building, High Lift Pump House Boundary walls with gates, land development, drain and internal pathway of PURANGAN Piped Water Supply Scheme under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME]_ 2ND CALL |  |  | ORD/000459/2023-2024 | 3441/BWD | 08/08/2023 | 730 | MANASH GHOSH | 1312.95 | 0 | 65
627 | Burdwan Division |  | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. |  |  | ORD/000872/2023-2024 | 5324/BWD | 01/12/2023 | 120 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 0 | 100
628 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000373/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.26 | 0 | 0
629 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000436/2023-2024 | 3835/BWD | 01/09/2023 | 0 | Resource Division | 24.5 | 0 | 0
630 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000766/2023-2024 | 192/BWD | 10/01/2024 | 0 | Resource Division | 24.5 | 0 | 0
631 | Central Mechanical |  | Quotation for new service connection at Purangan. |  |  | BILL/01083/2024-2025 | BP-2024-25-403 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.32 | 0 | 0
632 | Central Mechanical |  | Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries including intake (Low lift) pumping machineries, High Lift pumping machineries, 0-1 kg/hour gaseous chlorination system and illumination arrangement of Purangan & 11 nos. mouza Sub-Surface Based Piped Water Supply Scheme under Purba Bardhaman District PHE Dte. |  |  | ORD/000003/2025-2026 | 905/CMD | 04/04/2025 | 75 | WEST BENGAL ENGINEERING CO. | 317.99 | 0 | 0
633 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for OHR SITE of Zone-1, 2, & 3 at PURANGAN Water Supply Scheme [ BLOCK- Galsi-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000562/2024-2025 | 3099/CMD | 11/12/2024 | 373 | CHOUDHURY ENTERPRISE | 38.16 | 0 | 32
634 | Central Mechanical |  | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Purangan & 11 nos. Mouza water supply scheme under Central Mechanical Division PHE Dte. |  |  | ORD/000774/2024-2025 | 479/CMD | 06/02/2025 | 75 | S.P. CONSTRUCTION | 135.24 | 0 | 0
635 | Burdwan Division | Durgapur Sub-DIvision | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period NOV.'2024 to JAN.'2025] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000847/2024-2025 | 886/DSD | 21/10/2024 | 78 | MD HASIN | 1 | 0 | 0
636 | Burdwan Division | Durgapur Sub-DIvision | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day. [PeriodFebruary.'2025 to April'2025] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001180/2024-2025 | 129/DSD | 29/01/2025 | 78 | MD HASIN | 1 | 0 | 0
637 | Burdwan Division | Durgapur Sub-DIvision | FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING SCHEME DESCRIPTION AT NASIGRAM PWSS AND OTHER SCHEMES (16 Nos) WITHIN BHATAR BLOCK UNDER BURDWAN DIVISION , PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001423/2024-2025 | 311/DSD | 21/02/2025 | 21 | SHUBHRA KANTI GHOSH | 1.39 | 0 | 0
638 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000283/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 22.79 | 0 | 0
639 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000554/2023-2024 | 4949/BWD | 10/11/2023 | 0 | Resource Division | 123.19 | 0 | 0
640 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Santoshpur PWSS TW-1 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01732/2023-2024 | BP-2023-24-261 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.42 | 0 | 0
641 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new electric service connection at Santoshpur PH NO.-2 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01741/2023-2024 | BP-2023-24-260 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.91 | 0 | 0
642 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
643 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SANTOSHPUR Water Supply Scheme [ Block- BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000783/2023-2024 | 4076/CMD | 29/08/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 41.68 | 0 | 60
644 | Burdwan Division |  | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000003/2025-2026 | 1116/BWD | 03/04/2025 | 120 | SOFIQUL ISLAM | 176.89 | 0 | 0
645 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000273/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.98 | 0 | 0
646 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000426/2023-2024 | 3859/BWD | 01/09/2023 | 0 | Resource Division | 13.03 | 0 | 0
647 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000689/2023-2024 | 5077/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
648 | Central Mechanical |  | New service connection for Rean W/S scheme TW No-1 |  |  | BILL/02272/2023-2024 | BP-2023-24-421 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4 | 0 | 0
649 | Central Mechanical |  | New service connection at Rean PWSS TW -2 |  |  | BILL/02329/2023-2024 | BP-2023-24-453 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0
650 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and compound lighting arrangement for Tube well No.- 1 & 2 at REAN Water Supply Scheme [ BLOCK- MEMARI- II] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001602/2023-2024 | 1532/CMD | 05/03/2024 | 60 | SUBRATA BHADRA | 28.81 | 0 | 70
651 | Burdwan Division | Burdwan Sadar Sub-Division | Hire & fuel charges of vehicle Car No.-wb-41H-9788 for the month of August'2023 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | BILL/01037/2023-2024 | 747/JJM | 11/10/2023 | 0 | SK. ASRAFUDDIN | 0.4 | 0 | 0
652 | Burdwan Division | Burdwan Sadar Sub-Division | Hire & fuel charges of vehicle Car No.-WB-41G-8280 for the month of January to July'2023. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | BILL/01042/2023-2024 | 852/JJM | 30/10/2023 | 0 | MD HASIN | 2.5 | 0 | 0
653 | Burdwan Division | Burdwan Sadar Sub-Division | Vehicle Bill (Car No.-WB-41H-9788) for the month of October'2023. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | BILL/01677/2023-2024 | 1033/JJM | 11/12/2023 | 0 | SK. ASRAFUDDIN | 0.37 | 0 | 0
654 | Burdwan Division | Burdwan Sadar Sub-Division | Vehicle bill for the month of October'2023. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | BILL/01678/2023-2024 | 1040/JJM | 11/12/2023 | 0 | SK.ASFIA | 0.38 | 0 | 0
655 | Burdwan Division | Burdwan Sadar Sub-Division | Vehicle Bill [Car No.-WB-41H-9788] for the month of December'23. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | BILL/02062/2023-2024 | 1322/JJM | 01/02/2024 | 0 | SK. ASRAFUDDIN | 0.4 | 0 | 0
656 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall including land development at 3rd Tube Well site of Sahhosenpur water supply scheme under Jamalpur Block of Burdwan Division, PHE Dte. (Length -58.00 Mtr, Col-21 Nos). GROUP : D | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000083/2022-2023 | 817/BSD | 20/05/2022 | 45 | SARKAR CONSTRUCTION | 3.47 | 0 | 1
657 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for Providing FHTC at Srikrishnapur village under SAHAHOSENPUR Piped Water Supply Scheme at Srikrishnapur village within Jamalpur Block , under Burdwan Division, PHE Dte. Group : B | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000089/2022-2023 | 829/BSD | 23/05/2022 | 30 | MMS CONSTRUCTIONS PVT LTD | 4.62 | 0 | 1
658 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of different slab of damage valve chamber due to widening of PMGSY ROAD and sand filling of PMGSY ROAD of Sahahossenpur water supply scheme under Jamalpur Block of Burdwan Division, PHE Dte. Gr.E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000092/2022-2023 | 832/BSD | 23/05/2022 | 30 | ROY BISWAS CONSTRUCTION | 2.68 | 0 | 1
659 | Burdwan Division | Burdwan Sadar Sub-Division | Replace Damaged & deface FHTC(By WBSRDA)with all with accessories within the command area of SAHHOSENPUR Piped W/S Scheme at SahhosenpurSaikh Para and Rajarampur village,Jamalpur Development Block under Burdwan Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000156/2024-2025 | 1045/BSD | 10/06/2024 | 30 | SARKAR CONSTRUCTION | 0.83 | 0 | 100
660 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for Sahhosenpur water supply scheme at Sahhosenpur village (Near Masjid) within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000281/2021-2022 | 1212/BSD | 09/09/2021 | 30 | ROY BISWAS CONSTRUCTION | 4.96 | 0 | 1
661 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for Sahhosenpur water supply scheme at Jotsrirram village within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000320/2021-2022 | 1333/BSD | 30/09/2021 | 30 | PREMANANDA ROY BISWAS | 4.52 | 0 | 1
662 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline including providing FHTC for SAHHOSENPUR Piped Water Supply Scheme at Jotdakshin (6 Nos), Jotshiram (20 Nos) Habitation for Sajal Gram (As per field verification report duly signed by Pradhan for Har Ghar Jal Certification) within Jamalpur Block under Burdwan Division, PHE Dte. Gr.T. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000356/2022-2023 | 1341/BSD | 02/08/2022 | 5 | ROY BISWAS CONSTRUCTION | 0.95 | 0 | 1
663 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahahosenpur (Part) village (Sahahosenpur (Part) habitation) of Sahahosenpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [Sl. No. : ¿17¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000539/2020-2021 | 816/BWD | 01/02/2021 | 15 | ROY BISWAS CONSTRUCTION | 4.86 | 0 | 1
664 | Burdwan Division | Burdwan Sadar Sub-Division | Pipeline laying at different culvert crossing for damage of PMGSY Road of Sahhosenpur water supply scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Gr.-F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000552/2021-2022 | 1481/BSD | 09/11/2021 | 30 | ROY BISWAS CONSTRUCTION | 3.53 | 0 | 1
665 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for Sahhosenpur water supply scheme at Srikrishnapur and Rajarampur village within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-H] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000553/2021-2022 | 1483/BSD | 09/11/2021 | 30 | DIPAK ROY | 4.7 | 0 | 1
666 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for Sahhosenpur water supply scheme at Jotdakshin village within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000555/2021-2022 | 1524/BSD | 18/11/2021 | 30 | THREE MAA ENTERPRISE | 4.81 | 0 | 1
667 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sahahosenpur Piped Water Supply Scheme at Srikrishnapur Village, Rajarampur Village (2 Nos. habitations), Paikpara Village, Jotdakshin Village & Jotsriram Village, Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000646/2020-2021 | 1690/BWD | 24/02/2021 | 60 | DIPAK ROY | 70.56 | 9.56 | 1
668 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of interconnection of the Pump No.-1, 2 & 3 with OHR and distribution main of 350 mm dia for Sahhosenpur water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000720/2021-2022 | 1482/BSD | 09/11/2021 | 30 | THREE MAA ENTERPRISE | 4.83 | 0 | 1
669 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 40
670 | Burdwan Division | Durgapur Sub-DIvision | Quotation of new connection charges for Bhatar (Zone-I) water supply scheme. P.H. No.-4 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00132/2022-2023 | 942/JJM/22-23 | 09/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.67 | 0 | 0
671 | Burdwan Division | Durgapur Sub-DIvision | Quotation from WBSEDCL for load enhancement of Augmentation of Bhatar Zone-II (Kulnagar) w/s scheme for P.H.-6. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00173/2024-2025 | 1036/JJM | 25/10/2024 | 0 | WBSEDCL | 3.57 | 0 | 0
672 | Burdwan Division | Durgapur Sub-DIvision | Quotation of Bhatar water supply scheme, Zone-II, PHE Dte. [Quotation No.-5003600235/Quot/03, dt.-10/02/2023] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00375/2022-2023 | 1168/JJM | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.37 | 0 | 0
673 | Burdwan Division | Durgapur Sub-DIvision | Quotation of new service connection charges of Aug. of Bhatar (Zone-II) TW-6 water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/01338/2023-2024 | 1275/JJM | 18/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.53 | 0 | 0
674 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bhatar Piped Water Supply Scheme at Kapshar, Bamsor & Belenda (3nos) Village (Mouza) under Burwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000017/2021-2022 | 3301/BWD | 15/06/2021 | 60 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 141.14 | 0 | 1
675 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bhatar Piped Water Supply Scheme at Bhatar, Kantar, Kulchanda, Kulnagar, Palar, Satkhali & Chandipur (7nos) Village (Mouza) under Burwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000018/2021-2022 | 3300/BWD | 15/06/2021 | 60 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 143.17 | 87.73 | 1
676 | Burdwan Division | Durgapur Sub-DIvision | Sinking of additional 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell Site for Augmentation of BHATAR (Zone-I) Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000059/2022-2023 | 2240/BWD | 02/05/2022 | 45 | AUXILIARY TUBE WELL DRILLERS | 28.54 | 0 | 1
677 | Burdwan Division | Durgapur Sub-DIvision | Sinking of 200 mm dia River Bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Norja village Block -Bhatar, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000271/2022-2023 | 496/DSD | 12/08/2022 | 21 | DHIRENDRANATH SOM | 4.35 | 0 | 100
678 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Vivekanandapally for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000291/2021-2022 | 720/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 2.24 | 0 | 1
679 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Bhatar Alinagar for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte.[Gr.-G] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000292/2021-2022 | 721/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 4.69 | 0 | 1
680 | Burdwan Division | Durgapur Sub-DIvision | Extension of uPVC pipe line of LDS at Kalpukur Dakshin Para to Palar Lal para for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-H] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000293/2021-2022 | 722/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 1.99 | 0 | 1
681 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Bhatar Maldanga road to Kalpukur Purbapar for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-I] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000295/2021-2022 | 723/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 4.26 | 0 | 1
682 | Burdwan Division | Durgapur Sub-DIvision | Providing Left-Out FHTC to Pallar Habitation within Bhatar Zone-I PWSS, within Durgapur (Burdwan North) Sub-Division, PHE Dte, under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000380/2023-2024 | 555/DSD | 20/07/2023 | 30 | TARAMA AGENCY | 4.22 | 0 | 100
683 | Burdwan Division | Durgapur Sub-DIvision | Providing Left-Out FHTC to Katari Habitation within Bhatar Zone-II PWSS, within Durgapur (Burdwan North) Sub-Division, PHE Dte, under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000381/2023-2024 | 556/DSD | 20/07/2023 | 30 | BIPLAB SAMANTA | 3.98 | 0 | 100
684 | Burdwan Division | Durgapur Sub-DIvision | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design and drawings of overall LDS for Bhatar Piped Water Supply Scheme Zone I & Zone II under Bhatar Block. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000617/2024-2025 | 3350/BWD | 11/09/2024 | 15 | HORIZEN | 5.23 | 0 | 100
685 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Kapshor village for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-2] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000875/2022-2023 | 728/DSD | 30/12/2022 | 21 | DHIRENDRANATH SOM | 0.95 | 0 | 100
686 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Belenda Purbapara for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-03] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000876/2022-2023 | 729/DSD | 30/12/2022 | 21 | DHIRENDRANATH SOM | 0.95 | 0 | 100
687 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Bamshor and Belenda Purbapara for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-04] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000877/2022-2023 | 730/DSD | 30/12/2022 | 21 | DHIRENDRANATH SOM | 0.96 | 0 | 100
688 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Balsidanga village for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-05] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000878/2022-2023 | 731/DSD | 30/12/2022 | 21 | DHIRENDRANATH SOM | 0.89 | 0 | 100
689 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS near rail crossing at Balsidanga for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-8] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000881/2022-2023 | 734/DSD | 30/12/2022 | 21 | DHIRENDRANATH SOM | 0.96 | 0 | 100
690 | Burdwan Division | Durgapur Sub-DIvision | Laying of UPVC pipeline in Pallar habitation (Palar Asram Para North side) with Bhatar Zone-I PWSS within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000934/2023-2024 | 907/DSD | 15/12/2023 | 45 | PAPRI HAZRA | 0.8 | 0 | 100
691 | Burdwan Division | Durgapur Sub-DIvision | Laying of UPVC pipeline in Bardanga Adibasipara ,Vill-Satkhali within Bhatar Zone-II PWSS within Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000934/2024-2025 | 1074/DSD | 10/12/2024 | 45 | BIPLAB SAMANTA | 2.53 | 0 | 0
692 | Burdwan Division | Durgapur Sub-DIvision | Laying of UPVC pipeline in Pallar habitation (Palar Asram Para South side) with Bhatar Zone-I PWSS within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000936/2023-2024 | 908/DSD | 15/12/2023 | 45 | TARAMA AGENCY | 0.39 | 0 | 100
693 | Burdwan Division | Durgapur Sub-DIvision | Retrofitting of RCC Elevated Reservoir (Capacity 300 cum) by shortcreting, Guniting etc. in connection with Augmentation of Bhatar w/s scheme (Zone-I) under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000963/2020-2021 | 1793./BWD | 26/02/2021 | 45 | LAGNAJITA & CO. | 20.57 | 0 | 1
694 | Burdwan Division | Durgapur Sub-DIvision | Laying of UPVC pipeline in Katari Habitation within Bhatar Zone- II PWSS WITHIN Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001104/2023-2024 | 239/DSD | 12/03/2024 | 30 | BIPLAB SAMANTA | 0.56 | 0 | 100
695 | Burdwan Division | Durgapur Sub-DIvision | Providing Left Out FHTC to Sansotosh Sayar Par within Bhatar Zone-II PWSS WITHIN Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001105/2023-2024 | 240/DSD | 12/03/2024 | 30 | BIPLAB SAMANTA | 0.94 | 0 | 100
696 | Burdwan Division | Durgapur Sub-DIvision | Providing Left Out FHTC to Area Adjacent to Railway Station within Bhatar Zone-II PWSS WITHIN Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001106/2023-2024 | 241/DSD | 12/03/2024 | 30 | BIPLAB SAMANTA | 0.95 | 0 | 100
697 | Burdwan Division | Durgapur Sub-DIvision | Providing Left Out FHTC to Ashram Paschimpara within Bhatar Zone-I PWSS WITHIN Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001165/2023-2024 | 270/DSD | 15/03/2024 | 30 | PAPRI HAZRA | 0.92 | 0 | 100
698 | Burdwan Division | Durgapur Sub-DIvision | Land demarcation and preparation of sketch map including legal charges for different PWSS under JJM of Bhatar Block under Duragapur (Burdwan North) Sub-Division, P.H.E. DTE. [Part-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001509/2024-2025 | 157/DSD | 27/01/2025 | 180 | SHUBHRA KANTI GHOSH | 0.81 | 0 | 70
699 | Burdwan Division | Durgapur Sub-DIvision | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | VCH/001013/2021-2022 |  | 21/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0
700 | Burdwan Division | Durgapur Sub-DIvision | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | VCH/001045/2021-2022 | 934/DW | 31/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0
701 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 4 at Augmentation of Bhatar (Zone - I) (Bamsor) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000934/2022-2023 | 1311/CMD | 22/03/2023 | 30 | SRI KRISHNA NIRMAN | 11.88 | 0 | 99
702 | Central Drilling | Durgapur Sub-DIvision | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 120 mtrs. depth) by utilising Departmental machineries for Bhatar W/S Scheme (Z-II) Bhatar block under Purba bardhaman district, CDD, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000002/2023-2024 | 64/CDD | 06/04/2023 | 30 | C.M. ENTERPRISE | 9.91 | 0 | 0
703 | Durgapur W/S Division | Durgapur Sub-DIvision | QUOTATION FOR NEW SERVICE CONNECTION AT MANKAR PWSS ZONE-2 T.W-1 UNDER C.M.D, P.H.E Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00263/2024-2025 |  | 31/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.72 | 0 | 0
704 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum formal Work Order for the work of Sinking of 300 x 200mm x 150mtr depth by DR Rig Tube Well , Construction of 01 (One) no 5.25 x 3.25m Pump House cum Chlorine room with sanitary arrangement, Boundary Wall including laying UPVC distribution system (LDS) and Providing FHTC and other allied works at MANKAR under Retrofitting of Mankar PWSS (Zone-II, Part-B) under Galsi-I Block within Durgapur Water Supply Division P.H.E Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000029/2024-2025 | 757/DWSD | 06/06/2024 | 399 | RAMKRISHNA CHAKRABORTY | 66.25 | 0 | 60
705 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for the work of "Sinking of 300 X 200mm x 150mtr depth by DR Rig Tube Wells, Construction of 01 (One) no 5.25 x 3.25m Pump House cum Chlorine Room with sanitary arrangement, Boundary Wall including laying UPVC distribution system (LDS) and providing FHTC and allied works at Mankar under Retrofitting of Mankar PWSS (Zone-II, Part-A), under Galsi-I Block, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000044/2024-2025 | 760/DWSD | 06/06/2024 | 360 | G.S CONSTRUCTION AND CO | 92.69 | 0 | 10
706 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for the work of Balance Work for Distribution System and Rising Main Pipeline (CV/DVAC/UPVC), Construction of different dia Sluice valve /Air valve/Washout chamber in different sizes, Concrete Road renovation, Mechanical joints for MANKAR (ZONE-II) Water Supply Schemes of GALSI-I Block under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000048/2024-2025 | 769/DWSD | 06/06/2024 | 25 | SHANKHA GHOSH | 2.06 | 0 | 100
707 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for the work of Balance work for Distribution System and Rising Main Pipeline (UPVC/HDPE), Construction of different dia Sluice valve /Air valve/Washout chamber in different sizes,Concrete road renovation for MANKAR (ZONE-I) Water Supply Schemes of GALSI-I Block under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000051/2024-2025 | 766/DWSD | 06/06/2024 | 25 | SOUMYAVASH DAS | 1.4 | 0 | 100
708 | Durgapur W/S Division | Durgapur Sub-DIvision | Formal Work Order for Sinking of 300 x 200 mm x 150mtr depth by DR Rig, Construction of 01 (One) no 5.25 x 3.25 m Pump House cum Chlorine room with sanitary arrangement, Boundary wall, including laying UPVC distribution system (LDS) and Providing FHTC and other allied works at Mankar under Retrofitting of Mankar PWSS, Block- Galsi-I, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. (Zone-I/Part-B) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000122/2024-2025 | 1114/DWSD | 02/08/2024 | 120 | MANASH GHOSH | 163.89 | 0 | 0
709 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Drain Constriction & Repairing works For Mankar Water Supply Scheme (Zone-II) at Nayak Para, Dist:- Purba Bardhaman under DWSD, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000129/2024-2025 | 1211/DWSD | 23/08/2024 | 10 | SOUMYAVASH DAS | 0.66 | 0 | 100
710 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR Sinking of 300 x 200 mm x 150 mtr deapth by DR Rig, Construction of 1 (One) no 5.25 x 3.25 m Pump House cum Chlorine room with sanitary arrangement, Boundary wall including laying UPVC distribution system (LDS) and providing FHTC and other allied works at Mankar under Retrofitting of Mankar PWSS, Block- Galsi-I under DURGAPUR W/S DIVISION, PHE DTE. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000266/2024-2025 | 260/DWSD | 11/02/2025 | 418 | M/S. GOUTAM ROY | 105.88 | 0 | 5
711 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Augmentation of MANKAR Piped Water Supply Scheme at Mankar Palpara, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-05] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000025/2023-2024 | 153/DSD | 13/04/2023 | 21 | SOUMYAVASH DAS | 0.95 | 0 | 100
712 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of Augmentation of MANKAR Piped Water Supply Scheme at backside of Mankar Girls School, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-01] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000052/2023-2024 | 176/DSD | 18/04/2023 | 21 | SHUBHRA KANTI GHOSH | 0.95 | 0 | 95
713 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of Augmentation of MANKAR Piped Water Supply Scheme at Mankar Nayekpara, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-02] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000053/2023-2024 | 177/DSD | 18/04/2023 | 21 | SOUMYAVASH DAS | 0.96 | 0 | 100
714 | Burdwan Division | Durgapur Sub-DIvision | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) within the command area of Augmentation of MANKAR Piped Water Supply Scheme Near Mankar Masjitala, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-03] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000055/2023-2024 | 178/DSD | 18/04/2023 | 21 | SOUMYAVASH DAS | 0.96 | 0 | 100
715 | Burdwan Division | Durgapur Sub-DIvision | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) within the command area of Augmentation of MANKAR Piped Water Supply Scheme at back side of Mankar Girls School, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-04] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000056/2023-2024 | 179/DSD | 18/04/2023 | 21 | SHUBHRA KANTI GHOSH | 0.96 | 0 | 100
716 | Burdwan Division | Durgapur Sub-DIvision | Replacement of damaged AC pipeline at Raipur under Mankar (Zone-II) piped water supply scheme within Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-06] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000060/2023-2024 | 182/DSD | 18/04/2023 | 21 | MONDAL CONSTRUCTION | 0.97 | 0 | 0
717 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline in connection with FHTC for MANKAR Piped W/S Scheme under Galsi-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. (Gr.-B) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000085/2021-2022 | 446/DSD | 14/07/2021 | 30 | N.B. CONSTRUCTION | 1.81 | 0 | 1
718 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mankar Piped Water Supply Scheme at Mankar (Part) Village (Mouza) under Burwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000097/2021-2022 | 3591/BWD | 13/07/2021 | 60 | SAMRAT REALPROJECTS PRIVATE LIMITED | 140.03 | 0 | 1
719 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mankar Piped Water Supply Scheme at Bagabanpur (Part), Budbud (Part) & Mallikpur (Part) Village (Mouza) under Burwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000098/2021-2022 | 3372/BWD | 23/06/2021 | 60 | SAMRAT REALPROJECTS PRIVATE LIMITED | 79.3 | 0 | 1
720 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mankar Piped Water Supply Scheme at Sukdal Village (Mouza) 5 nos Habitation under Burwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000110/2021-2022 | 3878/BWD | 27/07/2021 | 60 | SUJAY KUMAR RAY | 151.77 | 0 | 1
721 | Burdwan Division | Durgapur Sub-DIvision | Modification to Rising main and D.I. distribution to ensure more controll of water supply of MANKAR water Supply Scheme under Durgapur (Burdwan North) Sub-Division in Galsi-I Block under Burdwan Division, P.H.E. Dte. [SL-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000118/2022-2023 | 336/DSD | 27/06/2022 | 21 | SHUBHRA KANTI GHOSH | 2.82 | 0 | 1
722 | Burdwan Division | Durgapur Sub-DIvision | Replacement of damage A.C. Pipeline from Mankar Dani Pukur to Purbasa colony via Post Office & Annapurnatala to Panchakalitala under Mankar (Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte._2ND CALL. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000242/2021-2022 | 6633/BWD | 29/11/2021 | 30 | PREMANANDA ROY BISWAS | 11.43 | 0 | 1
723 | Burdwan Division | Durgapur Sub-DIvision | Replacement of damage UPVC Pipeline at Mankar Masjit Tala under Mankar (Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000266/2021-2022 | 693/DSD | 08/12/2021 | 21 | SURATH DEY | 1.47 | 0 | 1
724 | Burdwan Division | Durgapur Sub-DIvision | Connection from newly Retrofitted Over Head Reservoir to Distribution System & Rising main Pipe Line of MANKAR (Zone-I) Water Supply Scheme under Galsi-I Block under within Durgapur Sub Division PHE Dte. Under Burdwan Division PHE Dte. [Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000272/2022-2023 | 497/DSD | 12/08/2022 | 30 | SHUBHRA KANTI GHOSH | 4.77 | 0 | 1
725 | Burdwan Division | Durgapur Sub-DIvision | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Mankar piped water supply scheme at Budbud (Part), Budbud habitation, Malikpara village (Malikpara habitation) & Bagabanpur village (Bagabanpur habitation), Galsi-I Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000518/2020-2021 | 308/BWD | 14/01/2021 | 30 | RELIABLE ENGINEERS CO.-OPERATIVE CONSTRUCTION SOCIETY LTD. | 21.83 | 0 | 1
726 | Burdwan Division | Durgapur Sub-DIvision | Restoration of village Road dismantled by laying pipeline for providing FHTC near north side of Budbub Canal par colony under Mankar (Zone-I) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. SL-01 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000527/2022-2023 | 646/DSD | 03/11/2022 | 21 | ROY CONSTRUCTION | 4.79 | 0 | 1
727 | Burdwan Division | Durgapur Sub-DIvision | Restoration of village Road dismantled by laying pipeline for providing FHTC Budbud Village, Girls School Para, Sukanta Nagar etc. under Mankar (Zone-I) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. SL-02 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000528/2022-2023 | 647/DSD | 03/11/2022 | 21 | DEY NIRMAN | 4.8 | 0 | 1
728 | Burdwan Division | Durgapur Sub-DIvision | Restoration of village Road dismantled by laying pipeline for providing FHTC at SUKDAL Village, near Sukdal Petrol and near Hindi School under Mankar (Zone-I) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte._2nd call SL-04 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000530/2022-2023 | 649/DSD | 03/11/2022 | 21 | PRATIVA CONSTRUCTION | 4.72 | 0 | 1
729 | Burdwan Division | Durgapur Sub-DIvision | Ground development, vertical extension of valve chamber, construction of pathway, drain etc. at Head work site of Mankar (Z-II) water supply scheme, Block-Galsi-I under Durgapur (Bardhaman North)Sub-Division under Burdwan Division, PHE Dte. SL-05 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000531/2022-2023 | 650/DSD | 03/11/2022 | 30 | SAIKAT RAY | 3.42 | 0 | 100
730 | Burdwan Division | Durgapur Sub-DIvision | Replacement of damage A.C. Pipeline at Mankar Bhattacharya Para & New royel club to Battala under Mankar(Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. SL-06 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000532/2022-2023 | 651/DSD | 03/11/2022 | 30 | OM ENTERPRISE | 4.72 | 0 | 1
731 | Burdwan Division | Durgapur Sub-DIvision | Replacement of damage A.C. Pipeline Mankar Pal Para & Nayakpara under Mankar(Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. SL-07 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000533/2022-2023 | 652/DSD | 03/11/2022 | 30 | SOUMYAVASH DAS | 4.55 | 0 | 1
732 | Burdwan Division | Durgapur Sub-DIvision | Dismantling of encroachments within Head work site of Mankar (Zone-II) Pipe Water Supply Scheme, at Galsi-I Block within Durgapur(Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [SL-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000545/2021-2022 | 130/DSD | 02/03/2022 | 3 | PARTHA RAY | 0.19 | 0 | 1
733 | Burdwan Division | Durgapur Sub-DIvision | Laying of new 300 & 200 mm dia sluice valve with valve chamber and replacement of 200 & 150 mm dia sluice valve with valve chamber at Budbud bazar and near NH2 and sukdal within Durgapur Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000568/2023-2024 | 657/DSD | 24/08/2023 | 15 | SOUMYAVASH DAS | 0.96 | 0 | 100
734 | Burdwan Division | Durgapur Sub-DIvision | Shifting of 300 MM dia D.I. pipe and laying of 12 mtr 150 mm dia D.I.pipe for widening of NH2 at Budbud more and supply of 80 mm dia Sluice valve and construction of valve chamber of Mankar Water supply scheme within Galsi -I Block,under Durgapur Sub Division,PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000578/2023-2024 | 658/DSD | 24/08/2023 | 15 | SHANKHA GHOSH | 0.96 | 0 | 100
735 | Burdwan Division | Durgapur Sub-DIvision | Laying of pipe line at North side Canal Bank for construction of diversion road by PWD Dept. under Mankar(Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000627/2021-2022 | 167/DSD | 16/03/2022 | 30 | N.B. CONSTRUCTION | 0.65 | 0 | 1
736 | Burdwan Division | Durgapur Sub-DIvision | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Galsi ¿ I Block under Burdwan Division, PHE. Dte._2ND CALL. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000673/2021-2022 | 1738/BWD | 28/03/2022 | 1101 | JYOTI ENTERPRISE | 5.72 | 0 | 100
737 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional House Hold Tap connection (FHTC) from existing distribution system within the command area of MANKAR piped water supply scheme at Budbud (Part) village Budbud (Part) habitation (Mouza), Galsi-I Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000707/2020-2021 | 547/BWD | 22/01/2021 | 30 | SAIKAT RAY | 22.24 | 22.23 | 1
738 | Burdwan Division | Durgapur Sub-DIvision | Laying Parallel pipeline from Mankar Hattala to Bhattacharya para & restore to damage pipeline at difference location of Mallickpara for water supply smoothly of MANKAR (Z-II) and its adjoining mouza's Piped W/S Scheme at Galsi-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000804/2023-2024 | 4819/BWD | 08/11/2023 | 60 | SHUBHRA KANTI GHOSH | 24.08 | 0 | 100
739 | Burdwan Division | Durgapur Sub-DIvision | Retrofitting of RCC Elevated Reservoir (Capacity 450 Cum) by Shortcreting, Guniting etc. in connection with Augmentation of Mankar W/S. Scheme (Zone - I) under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000835/2021-2022 | 6043/BWD | 07/10/2021 | 45 | SUDIPTO GORAIN | 19.85 | 0 | 1
740 | Burdwan Division | Durgapur Sub-DIvision | Crossing of Mankar-Guskara Bolgona Road at Head works site of Mankar (Z-I) W/S Scheme for laying distribution and rising main through pushing of 750mm.dia. RCC casing pipe by hydraulic jacking method for Mankar (Z-I) W/S Scheme under Durgapur (Bardhaman North) Sub Division, Burdwan Division, PHE Dte.[SL-12] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000855/2022-2023 | 712/DSD | 30/12/2022 | 30 | SHUBHRA KANTI GHOSH | 4.74 | 0 | 100
741 | Burdwan Division | Durgapur Sub-DIvision | Laying of hume pipe 600 MM dia and laying of 48 mtr 315 mm dia HDPE pipe for widening of NH2 crossing at Budbud more fly over of Mankar Water supply scheme within Galsi -I Block,under Durgapur Sub Division,PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000987/2023-2024 | 43/DSD | 17/01/2024 | 60 | SOUMYAVASH DAS | 4.77 | 0 | 100
742 | Burdwan Division | Durgapur Sub-DIvision | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | VCH/001013/2021-2022 |  | 21/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0
743 | Burdwan Division | Durgapur Sub-DIvision | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | VCH/001045/2021-2022 | 934/DW | 31/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0
744 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1&2 (ZONE:-1&2) at Augmentation MANKAR Water Supply Scheme [ BLOCK- GALSI-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000007/2025-2026 | 1003/CMD | 17/04/2025 | 60 | DAS CONSTRUCTION | 51.38 | 0 | 30
745 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amra Piped Water Supply Scheme at Amra (2 Nos Habitation Part) & Dogachia Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte._3rd CALL. |  |  | ORD/000008/2021-2022 | 3138/BWD | 03/06/2021 | 45 | D.M. ENTERPRISE | 57.42 | 20.77 | 1
746 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-C) [SL. No. : 11] |  |  | ORD/000031/2021-2022 | 3408/BWD | 25/06/2021 | 15 | N.S. ENTERPRISE | 4.86 | 4.27 | 1
747 | Burdwan Division |  | Providing FHTC for Dogachia Mouza [(Habitation (Village)] for AMRA piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. |  |  | ORD/000068/2023-2024 | 2019/BWD | 28/04/2023 | 30 | DEY NIRMAN | 20.61 | 0 | 100
748 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amra village of Amra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-208/BWD/2020-21) |  |  | ORD/000083/2020-2021 | 2734/BWD | 10/08/2020 | 30 | DEBASHISH ENTERPRISE | 4.92 | 4.92 | 1
749 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Teli Nuri village of Amra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-427/BWD/2020-21) |  |  | ORD/000085/2020-2021 | 3530/BWD | 25/09/2020 | 30 | KALYAN CHOWDHURY | 4.92 | 4.92 | 1
750 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amra village of Amra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-404/BWD/2020-21) |  |  | ORD/000092/2020-2021 | 3531/BWD | 25/09/2020 | 30 | DEBASHISH ENTERPRISE | 4.92 | 4.92 | 1
751 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dogachia village of Amra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-232/BWD/2020-21) |  |  | ORD/000093/2020-2021 | 2737/BWD | 10/08/2020 | 30 | KALYAN CHOWDHURY | 4.92 | 4.92 | 1
752 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AMRA Piped Water Supply Scheme (Vill-Dogechia, Habitation- Dogechia ) at Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte.Gr.A. |  |  | ORD/000386/2021-2022 | 57/BSD | 13/01/2022 | 30 | DEY NIRMAN | 4.81 | 0 | 1
753 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-B) [SL. No. : 13] |  |  | ORD/000427/2020-2021 | 592/BWD | 25/01/2021 | 15 | DEY NIRMAN | 4.84 | 4.84 | 0
754 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dattapur village (Adampur habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 11] |  |  | ORD/000428/2020-2021 | 590/BWD | 25/01/2021 | 15 | N.S. ENTERPRISE | 4.86 | 3.29 | 0
755 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-A) [SL. No. : 12] (Agreement No. 671/BWD of 2020-21) |  |  | ORD/000429/2020-2021 | 591/BWD | 25/01/2021 | 15 | MUKHERJEE ENTERPRISE | 4.86 | 4.86 | 0
756 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-A) [SL. No. : 12] (Agreement no. 839/BWD of 2020-21) |  |  | ORD/000430/2020-2021 | 1397/BWD | 15/02/2021 | 15 | MUKHERJEE ENTERPRISE | 4.86 | 4.86 | 0
757 | Burdwan Division |  | Construction of Boundary wall at 3rd Tube well site of Dogachia Mouza of Amra water supply scheme under Jamalpur block under Burdwan Division, PHE Dte. [Length-59 Mtr][Gr.-F] |  |  | ORD/000557/2021-2022 | 1028/BSD | 05/08/2021 | 45 | MUKHERJEE ENTERPRISE | 4.45 | 0 | 1
758 | Burdwan Division |  | Extension of pipeline at AMRA water supply scheme at different villages (Tengaberia, Badpur & Kolupukur) FHTC of Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-F] |  |  | ORD/000561/2021-2022 | 1374/BSD | 05/10/2021 | 30 | D.M. ENTERPRISE | 4.74 | 0 | 1
759 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jajanpur village and Jajanpur-Tangaberia habitation of JAUGRAM piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Gr.-6B] |  |  | ORD/000740/2020-2021 | 3331/BWD | 18/09/2020 | 30 | DEY NIRMAN | 4.86 | 4.86 | 0
760 | Burdwan Division |  | Supply of SS316 grade flow control valve for FHTC at different water supply schemes within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional store.[Part-2] |  |  | ORD/001307/2020-2021 | 1792 /BWD | 26/02/2021 | 10 | INDIA PIPE FITTING CO | 9.7 | 0 | 1
761 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mugura village of Mugura piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-163/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000088/2020-2021 | 2690/BWD | 07/08/2020 | 30 | LAKSHMIKANTA DAS | 4.92 | 4.92 | 1
762 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jagarpur & Mugura village of Mugura piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-238/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000095/2020-2021 | 2689/BWD | 07/08/2020 | 30 | HAFIJUR RAHAMAN MIDYA | 4.92 | 4.92 | 1
763 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mugura village of Mugura Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿3A¿] (Agreement no. 163/BWD,2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000135/2020-2021 | 3535/BWD | 25/09/2020 | 30 | LAKSHMIKANTA DAS | 2.69 | 0 | 1
764 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jagarpur & Mugura village of Mugura Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿3B¿] (Agreement no.238/BWD of 2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000136/2020-2021 | 4118/BWD | 16/10/2020 | 30 | HAFIJUR RAHAMAN MIDYA | 4.92 | 0 | 1
765 | Burdwan Division | Burdwan Sadar Sub-Division | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at Head Work Site & 2nd TW Site and providing leftout FHTC, Road Restoration with allied work for MUGRA Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000279/2024-2025 | 2711/BWD | 11/07/2024 | 2720 | M/S PURBASHA | 40.24 | 0 | 90
766 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sultanpur village of Sultanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-373/BWD/2020-21) |  |  | ORD/000084/2020-2021 | 2602/BWD | 04/08/2020 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.91 | 4.91 | 1
767 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gopalpur village of Sultanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-338/BWD/2020-21) |  |  | ORD/000087/2020-2021 | 2609/BWD | 04/08/2020 | 30 | BISWAS ENTERPRISE | 4.91 | 4.91 | 1
768 | Burdwan Division |  | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-5]. |  |  | ORD/000090/2021-2022 | 3590/BWD | 13/07/2021 | 30 | PREMANANDA ROY BISWAS | 127.5 | 0.24 | 1
769 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sultanpur village of Sultanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-374/BWD/2020-21) |  |  | ORD/000116/2020-2021 | 3701/BWD | 05/10/2020 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.19 | 4.19 | 1
770 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sultanpur Piped Water Supply Scheme at Halbele, Hridaypur, Isabpur, Nowapara & Uplati Village (Mouza), Kalna ¿ I Block under Burdwan Division, PHE Dte.(Agreement No. 56/2020-2021 OF SE/CC/PHE. DTE.) |  |  | ORD/000124/2020-2021 | 4901/BWD | 07/12/2020 | 90 | MAJILA ENTERPRISE | 94.67 | 70.51 | 1
771 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gopalpur village of Sultanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-339/BWD/2020-21) |  |  | ORD/000356/2020-2021 | 3700/BWD | 05/10/2020 | 30 | BISWAS ENTERPRISE | 4.91 | 4.91 | 1
772 | Burdwan Division |  | Providing FHTC in each household from dist. System within Scheme jurisdiction in Hridaypur, Upalati, Belerhat, Gopalpur, Sultanpur, Isabpur & Naopara Village of SULTANPUR W/S. Scheme under Burdwan Division, PHE Dte. |  |  | ORD/000584/2021-2022 | 1357/BWD | 09/03/2022 | 30 | TAPAS KUMAR ROY | 16.69 | 0 | 1
773 | Burdwan Division |  | Protection work of distribution system (200 mm dia) of 35 Mtr length near the head work site (Right Side) of Sultanpur & its adjoining mouzas water supply scheme by UC Bullah including Drum Sheet within Kalna Sub-Division under Burdwan Division, PHE Dte.[Gr.-E] |  |  | ORD/000845/2020-2021 | 20/KSD | 07/01/2021 | 30 | DEBASHISH ENTERPRISE | 0.75 | 0 | 1
774 | Burdwan Division |  | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Engineer, Head Quarters, Burdwan Division, PHE Dte. for the month of March'23. |  |  | BILL/00296/2023-2024 | 201/JJM | 01/06/2023 | 0 | SK. ASRAFUDDIN | 0.39 | 0 | 0
775 | Burdwan Division |  | Vehicle bill for the office of the Assistant Engineer, Head Quarters Burdwan Division, PHE Dte. for the month of June'23. |  |  | BILL/00616/2023-2024 | 482/JJM | 09/08/2023 | 0 | SK. ASRAFUDDIN | 0.4 | 0 | 0
776 | Burdwan Division |  | MAINTENANCE OF ROAD (WHISH IS DAMAGED FOR LAYING PIPELINE BY PHE DEPTT) NAMELY NARUGRAM H.C TO BADSHI ROAD VIDE- PACKAGE NO- WB 22 12 UNDER PMGSY-III UNDER NARUGRAM GP. & RAINA-I BLOCK, IN PURBA BARDHAMAN DISTRICT |  |  | BILL/00740/2024-2025 | 894/JJM | 25/09/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 3.86 | 0 | 0
777 | Burdwan Division |  | Vehicle bill for the month of October & November'2023. |  |  | BILL/01671/2023-2024 | 1145/JJM | 29/12/2023 | 0 | SOURAV JANA | 0.79 | 0 | 0
778 | Burdwan Division |  | Vehicle bill for the month of november'2023. |  |  | BILL/01672/2023-2024 | 1141/JJM | 29/12/2023 | 0 | SK.ASFIA | 0.4 | 0 | 0
779 | Burdwan Division |  | Vehicle bill for the month of november'2023. |  |  | BILL/01673/2023-2024 | 1140/JJM | 29/12/2023 | 0 | SK. ASRAFUDDIN | 0.4 | 0 | 0
780 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Anguna village of Anguna piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-302/BWD/2020-21) |  |  | ORD/000090/2020-2021 | 3355/BWD | 21/09/2020 | 30 | ANWESHA CONSTRUCTION | 4.59 | 4.59 | 1
781 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gunar village of Anguna piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-203/BWD/2020-21) |  |  | ORD/000096/2020-2021 | 2693/BWD | 07/08/2020 | 30 | M/S ANAND CONSTRUCTION | 4.92 | 4.92 | 1
782 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Anguna village of Anguna piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-171/BWD/2020-21) |  |  | ORD/000097/2020-2021 | 2684/BWD | 07/08/2020 | 30 | ANWESHA CONSTRUCTION | 4.91 | 4.91 | 1
783 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gunar village of Anguna piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-369/BWD/2020-21) |  |  | ORD/000101/2020-2021 | 3515/BWD | 25/09/2020 | 30 | M/S ANAND CONSTRUCTION | 2.17 | 2.17 | 1
784 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Anguna village of Anguna Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿1A¿] |  |  | ORD/000133/2020-2021 | 2694/BWD | 10/07/2020 | 30 | ANWESHA CONSTRUCTION | 4.91 | 0 | 1
785 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Anguna village of Anguna Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿1A¿] (Agreement no. 171/BWD of 2020-21) |  |  | ORD/000134/2020-2021 | 2698/BWD | 07/08/2020 | 30 | ANWESHA CONSTRUCTION | 4.91 | 0 | 1
786 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Anguna Piped Water Supply Scheme at Anguna (Part), Gunar (Part) & Sakita Village (Mouza), Raina-I Block under Burdwan Division, PHE Dte. |  |  | ORD/000291/2020-2021 | 517/BWD | 21/01/2021 | 45 | SK ALIM | 33.4 | 19.46 | 1
787 | Burdwan Division |  | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. |  |  | ORD/000344/2021-2022 | 39/BWD | 05/01/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 15.62 | 0 | 1
788 | Burdwan Division |  | Extension of pipe line of existing distribution system within the command area of Anguna Piped Water Supply Scheme, Anguna village within Raina-1 Block of Burdwan Sub Division under Burdwan Division,PHE Dte".Gr.A. |  |  | ORD/000439/2022-2023 | 1465/BSD | 25/08/2022 | 45 | ANWESHA CONSTRUCTION | 4.97 | 0 | 1
789 | Burdwan Division |  | Extension of pipeline of Anguna water supply scheme at Anguna, Sanktia and Gunar village within Raina-I Block under Burdwan division, PHE Dte.[Gr.-A] |  |  | ORD/000711/2021-2022 | 1480/BSD | 09/11/2021 | 30 | SK ABDUL HALIM | 4.44 | 0 | 1
790 | Burdwan Division |  | Extension of pipeline for Anguna water supply scheme at Anguna, Sanktia and Gunar village within Raina-I Block under Burdwan Division, PHE Dte.[Gr.-B] |  |  | ORD/000715/2021-2022 | 1429/BSD | 28/10/2021 | 30 | SK ABDUL HALIM | 4.38 | 0 | 1
791 | Burdwan Division |  | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Anguna, Sanktia, Gunar village of ANGUNA Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000811/2022-2023 | 1575/BWD | 31/03/2023 | 60 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 33.16 | 0 | 100
792 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000123/2021-2022 | 1108/BWD | 26/02/2022 | 0 | Resource Division | 25.78 | 0 | 0
793 | Burdwan Division |  | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0
794 | Burdwan Division | Kalna Sub-division | Hire & fuel charges of vehicle (Car No.-WB-04G-6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of March'23. | Assistant Engineer |  | BILL/00290/2023-2024 | 204/JJM | 01/06/2023 | 0 | M/S MUNMUN DEY | 0.28 | 0 | 0
795 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Dharmadanga Piped Water Supply Scheme at Dharmadanga (P) Village (Mouza), Kalna-I Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000255/2021-2022 | 6641/BWD | 29/11/2021 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 14.94 | 0 | 1
796 | Burdwan Division | Kalna Sub-division | Water tap connection in each household from existing distribution system within scheme jurisdiction in Koldanga-Mirpur village (35 Nos) & Rameswarpur village (50 Nos) (Total-85 Nos) of Dharmadanga water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL NO.-C] | Assistant Engineer |  | ORD/000321/2021-2022 | 1026/KSD | 01/10/2021 | 15 | SETH ENTERPRISE | 2.95 | 0 | 1
797 | Burdwan Division | Kalna Sub-division | Work Order for "Providing Functional house hold tap connections within command ares of Dharmadanga water supply scheme within Kalna-I Block under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer |  | ORD/000550/2023-2024 | 1305/KSD | 23/08/2023 | 15 | BISWAS ENTERPRISE | 2.81 | 0 | 100
798 | Burdwan Division | Kalna Sub-division | Work order for "Providing Functional house hold tap connections for Sajal Gram Village within Kalna-I Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Dharmadanga Water Supply Scheme) Sl No- 5 | Assistant Engineer |  | ORD/000689/2022-2023 | 101/KSD | 08/02/2023 | 28 | BUILD-TECH | 0.88 | 0 | 100
799 | Burdwan Division | Kalna Sub-division | Continuation order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Rameswarpur village and Rameswarpur habitation of Dharmadanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Group-1B] | Assistant Engineer |  | ORD/000732/2020-2021 | 4743/BWD | 01/12/2020 | 30 | TAPAS KUMAR ROY | 3.2 | 0 | 1
800 | Burdwan Division | Kalna Sub-division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Rameswarpur (P) Village, Kalna - I Block within Dharma Danga PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer |  | ORD/000741/2023-2024 | 836/AE/HQ | 31/10/2023 | 30 | MUNSHI JAVEDUR JAMAN | 0.76 | 0 | 100
801 | Burdwan Division | Kalna Sub-division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Madhuban (P) Village, Kalna - I Block within Dharma Danga PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer |  | ORD/000794/2023-2024 | 873/AE/HQ | 07/11/2023 | 30 | PAPRI HAZRA | 0.76 | 0 | 100
802 | Burdwan Division | Kalna Sub-division | Work Order for 'Laying distribution system including providing FHTC in the left out portion of Dharmadanga piped water supply scheme under Kalna Sub-Division under Burdwan Division, PHE Dte.'. | Assistant Engineer |  | ORD/000806/2024-2025 | 1770/KSD | 20/11/2024 | 30 | BISWAS ENTERPRISE | 1.67 | 0 | 100
803 | Burdwan Division | Kalna Sub-division | Extension of different dia UPVC pipeline at Rameswarpur village of Dharmadanga water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Sl No.-A] | Assistant Engineer |  | ORD/000829/2020-2021 | 167/KSD | 19/02/2021 | 30 | BISHWAJIT DAS | 3.97 | 0 | 1
804 | Burdwan Division | Kalna Sub-division | Work Order for "Laying distribution system including providing FHTC in the leftout portion of Dharmadanga (SM/07545) water supply scheme under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer |  | ORD/000953/2024-2025 | 1921/KSD | 02/12/2024 | 30 | H SAMANTA | 2.02 | 0 | 0
805 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhuban village of Dharmadanga Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 6B] | Assistant Engineer |  | ORD/000972/2020-2021 | 4745/BWD | 01/12/2020 | 30 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 2.66 | 0 | 1
806 | Burdwan Division | Kalna Sub-division | Rest portion of OHR work (Plastering, Priming & Painting and interconnection of Rising Main with Specials) & Construction of Boundary wall with Smriti Saudha at Aug. of DHARMADANGA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Length - 81.01 Mtr, No of Columns=28 Nos. Centre to Centre- 3.0 Mtr.). | Assistant Engineer |  | ORD/000995/2023-2024 | 267/BWD | 15/01/2024 | 60 | S.K. CONSTRUCTION | 27.45 | 0 | 100
807 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur (Part) village (Kashipur habitation) of Kashipur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 18] [Agr. No. 720/BWD of 2020-2021] |  |  | ORD/000375/2020-2021 | 1441/BWD | 18/02/2021 | 15 | PREMANANDA ROY BISWAS | 4.48 | 0 | 1
808 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur village (Kashipur habitation) of Kashipur Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 20] |  |  | ORD/000466/2020-2021 | 596/BWD | 25/01/2021 | 15 | IYASIN DAFADAR | 4.86 | 1.7 | 1
809 | Burdwan Division |  | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001013/2021-2022 |  | 21/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0
810 | Burdwan Division |  | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001045/2021-2022 | 934/DW | 31/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0
811 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jargram (Part) village (Jargram (P) habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 05] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000027/2022-2023 | 2058/BWD | 19/04/2022 | 15 | LAKSHMIKANTA DAS | 4.86 | 0 | 1
812 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of uPVC pipeline regarding FHTC for Gureghar, Dumo, Basantabati habitation under Madhabpur (Zone-II) W/S. Scheme at Jamalpur Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000160/2022-2023 | 3139/BWD | 19/07/2022 | 30 | PRATIMA CONSTRUCTION | 5.64 | 0 | 1
813 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gureghar village and Gureghar habitation of Madhabpur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-440/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000165/2020-2021 | 3332/BWD | 18/09/2020 | 30 | KAUSHIK RAY | 4.87 | 4.87 | 1
814 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jarogram village and Jaragram habitation of Madhabpur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-441/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000173/2020-2021 | 3333/BWD | 18/09/2020 | 30 | SUPRIYA RAY | 4.87 | 4.87 | 1
815 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mirzapur village (Mirzapur habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 10] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000194/2021-2022 | 6189/BWD | 28/10/2021 | 15 | JAI MAA DURGA & CO. | 2.19 | 0 | 1
816 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of MADHABPUR (Z-I) W/S Scheme under Jamalpur Block within Burdwan Sub-Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000201/2023-2024 | 2704/BWD | 08/06/2023 | 30 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.26 | 0 | 100
817 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for providing functional household tap connection at Gureghar village of MADHABPUR Zone-II piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000234/2021-2022 | 1128/BSD | 26/08/2021 | 45 | SAIKAT RAY | 1.4 | 0 | 0
818 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jarogram village and Jarogram habitation of Madhabpur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-662/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000259/2020-2021 | 4911/BWD | 08/12/2020 | 30 | SUPRIYA RAY | 4.87 | 4.87 | 1
819 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gureghar village and Gureghar habitation of Madhabpur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-557/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000260/2020-2021 | 4910/BWD | 08/12/2020 | 30 | KAUSHIK RAY | 4.87 | 4.87 | 1
820 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of MADHABPUR PWSS under Jamalpur Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000363/2023-2024 | 1525/BSD | 17/07/2023 | 15 | CARTO | 0.78 | 0 | 100
821 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dumo village (Dumo habitation) & Satgoria village (Satgoria habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 07] [Agr. No.721/BWD of 2020-2021] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000376/2020-2021 | 1418/BWD | 18/02/2021 | 15 | BRINDABAN KONAR | 4.86 | 4.86 | 1
822 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jargram (Part) village (Jargram (P) habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 05] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000421/2020-2021 | 1416/BWD | 18/02/2021 | 15 | LAKSHMIKANTA DAS | 4.86 | 0 | 1
823 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhabpur (Part) village (Madhabpur (P) habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 06] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000458/2020-2021 | 1417/BWD | 18/02/2021 | 15 | KAJAL MUKHERJEE | 4.86 | 0 | 1
824 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gureghar village (Gureghar habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B). [SL. No. : 09] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000460/2020-2021 | 1420/BWD | 18/02/2021 | 15 | SAIKAT RAY | 4.87 | 0 | 0
825 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch rooms & Rising main at different TW site for MADHABPUR (Zone-I) Piped Water Supply Scheme under Jamalpur Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000532/2023-2024 | 3629/BWD | 21/08/2023 | 60 | DEBJYOTI GOSWAMI | 9.11 | 0 | 80
826 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of damaged UPVC pipeline with HDPE pipes at Madhabpur village for Madhabpur Zone-I water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-G] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000534/2021-2022 | 1478/BSD | 09/11/2021 | 30 | KOUSIK MALLICK | 3.57 | 0 | 1
827 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mirzapur village (Mirzapur habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 10] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000536/2020-2021 | 1421/BWD | 18/02/2021 | 15 | JAI MAA DURGA & CO. | 4.86 | 4.86 | 0
828 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gureghar village (Gureghar habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A). [SL. No. : 08] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000543/2020-2021 | 1419/BWD | 18/02/2021 | 15 | KAUSHIK RAY | 4.87 | 4.87 | 0
829 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of uPVC pipeline for providing FHTC from existing distribution pipe line system within command area of MADHABPUR (Zone-II) W/S Scheme at Khalerpar under Gureghar village, Jamalpur Development Block under Burdwan Division, PHE Dte". Gr,B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000562/2022-2023 | 2099/BSD | 28/11/2022 | 30 | PRATIMA CONSTRUCTION | 0.9 | 0 | 1
830 | Burdwan Division | Burdwan Sadar Sub-Division | Repairing of damaged 180 mm dia UPVC pipeline at Madhabpur village for Madhabpur water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000844/2020-2021 | 79/BSD | 19/01/2021 | 30 | KOUSIK MALLICK | 4.82 | 0 | 1
831 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhabpur village and Madhabpur habitation of MADHABPUR Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿7C¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000846/2020-2021 | 7050/BWD | 22/12/2020 | 30 | KAJAL MUKHERJEE | 4.86 | 0 | 1
832 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhabpur village and Madhabpur habitation of MADHABPUR Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿7C¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000847/2020-2021 | 3334/BWD | 18/09/2020 | 30 | KAJAL MUKHERJEE | 4.86 | 0 | 1
833 | Burdwan Division | Durgapur Sub-DIvision | Hire & fuel charges of vehicle (Car No.-WB-41D-4561) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of September & October'2022. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00142/2022-2023 | 823/VEH | 02/12/2022 | 0 | SUJAUDDIN SEKH | 0.73 | 0 | 0
834 | Burdwan Division | Durgapur Sub-DIvision | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of November'2022. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00286/2022-2023 | 954/JJM/22-23 | 13/01/2023 | 0 | SUJAUDDIN SEKH | 0.38 | 0 | 0
835 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline at "Sansad No. 10, 11 and 24" of Eruar and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur (Bardhaman North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-N] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000173/2021-2022 | 607/DSD | 07/10/2021 | 30 | DUBE ENTERPRISE | 3.15 | 0 | 1
836 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ERUAR Piped Water Supply Scheme at Eruar (Part-A) (Eruar (Part-A) Habitation) village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. (Agreement no. 569/BWD of 2020-2021) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000290/2020-2021 | 356/BWD | 15/01/2021 | 30 | HAFIJUR RAHAMAN MIDYA | 19.95 | 6.07 | 1
837 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ERUAR Piped Water Supply Scheme at Eruar (Part-D) (Eruar (Part-D) Habitation) village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. ._2ND CALL (Agreement No.703/BWD of 2020-2021) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000296/2020-2021 | 1569/15/BWD | 22/02/2021 | 30 | DUBE ENTERPRISE | 18.61 | 7.01 | 1
838 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) & Restoration of pipeline at Sixteen Nos. samsad of Eruar Gram Panchayat from ERUAR Piped Water Supply Scheme at Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000296/2021-2022 | 7033/BWD | 17/12/2021 | 60 | IJABUL SEKH | 92.08 | 0 | 1
839 | Burdwan Division | Durgapur Sub-DIvision | Providing Left-Out FHTC to Eruar Habitation within ERUAR PWSS, within Durgapur (Burdwan North) Sub-Division, PHE Dte, under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000382/2023-2024 | 557/DSD | 20/07/2023 | 30 | SANDIPAN SENGUPTA | 4.44 | 0 | 0
840 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of ERUAR piped water supply scheme at Eruar (Part-B) (Eruar (Part-B) Habitation) village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. [Tr No.-678/BWD/20-21] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000386/2020-2021 | 1264/BWD | 11/02/2021 | 30 | S.T. ENTERPRISE | 22.24 | 0 | 100
841 | Burdwan Division | Durgapur Sub-DIvision | Laying of pipeline for ERUAR Piped Water Supply Scheme in Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000443/2024-2025 | 3079/BWD | 09/08/2024 | 90 | SOUMYAVASH DAS | 5.01 | 0 | 0
842 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Muratipur village and Muratipur habitation of ERUAR Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿11B¿] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000457/2020-2021 | 4748/BWD | 01/12/2020 | 30 | S. MONDAL | 4.86 | 4.86 | 0
843 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional House hold Tap connection (FHTC) from existing distribution system within the command area of ERUAR piped water supply scheme at Erusr (Part-C) (Eruar Part-C Habitation) village (Mouza) within Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000763/2020-2021 | 1265 /BWD | 11/02/2021 | 30 | S.T. ENTERPRISE | 18.05 | 12.4 | 1
844 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of ERUAR piped water supply scheme at Muratipur (Part) (Muratipur Part Habitation) village (Mouza) within Bhatar Block under Burdwan Division, PHE Dte._2nd Call. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000765/2020-2021 | 1266/BWD | 11/02/2021 | 30 | S.N. ENTERPRISE | 18.71 | 4.37 | 1
845 | Burdwan Division | Durgapur Sub-DIvision | Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site(ERRUAR4 TH Pump House),Kaluttak under ERUAR PWSS, Bhatar Dev. Block, within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. DTE. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000936/2024-2025 | 1082/DSD | 11/12/2024 | 60 | SWAPAN KUMAR ROY | 3.72 | 0 | 0
846 | Burdwan Division | Durgapur Sub-DIvision | Replacing of existing damaged pipe line at KALUTAK and repairing of 4th Pump house and changing of 2 nos. valve at ERUAR village of ERAUR PWSS of Bhatar Block within Durgapur (Burdwan North) Sub- Division under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000937/2023-2024 | 909/DSD | 15/12/2023 | 45 | SWAPAN KUMAR ROY | 0.93 | 0 | 100
847 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SUDPUR Piped Water Supply Scheme (PART-A) at Katwa-I Block under Burdwan Division, PHE Dte. [Agreement No. 44/2020-2021 OF SE/CC/PHE. DTE.] |  |  | ORD/000058/2020-2021 | 4290/BWD | 03/11/2020 | 90 | MD HASIN | 86.85 | 68.84 | 1
848 | Burdwan Division |  | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Sudpur, Lokpur & Narayanpur village under SUDPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte [Sl - 4 ] |  |  | ORD/000120/2021-2022 | 564/KTS | 31/08/2021 | 15 | BABUL SK | 2.42 | 0 | 1
849 | Burdwan Division |  | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Rayerpara, Purba and Paschim Bijoynagar village under SUDPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte [Sl - 5 ] |  |  | ORD/000125/2021-2022 | 565/KTS | 31/08/2021 | 15 | HAMID SK | 3.6 | 0 | 1
850 | Burdwan Division |  | Balance work of OHR at Head Work site, construction of HUME Pipe culvert , Road restoration work and boundary wall at 2nd TW site with Gate, land development at Head work site and 2nd TW site under KAITHAN, SUDPUR & PANUHAT Piped Water Supply Scheme under KATWA -I Block, under Katwa Sub-Division within Burdwan Division, PHE Dte. |  |  | ORD/000486/2024-2025 | 3141/BWD | 20/08/2024 | 120 | VISHAL CONSTRUCTION CO. | 126.29 | 0 | 50
851 | Burdwan Division |  | Urgent repairing work at Sudpur piped water supply scheme to ensuring FHTC work under Katwa-I Block under Katwa Sub-Division, under Burdwan Division, PHE Dte.[Tr No.-875/BWD/20-21] |  |  | ORD/000614/2020-2021 | 91/KTS | 12/02/2021 | 3 | HAMID SK | 0.92 | 0.92 | 1
852 | Burdwan Division | Burdwan Sadar Sub-Division | Providing left out FHTC for Putunda village within SUHARI PWSS , Bardhhaman-II Development Block under Burdwan Division, PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000144/2024-2025 | 1032/BSD | 10/06/2024 | 30 | ISHAN CONSTRUCTION | 0.96 | 0 | 100
853 | Burdwan Division | Burdwan Sadar Sub-Division | Allied work for inter connection between 3rd tube well site and laying distribution system for Suhari PWSS within Bardhaman-II Block , under Burdwan Division, PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000292/2024-2025 | 1274/BSD | 12/07/2024 | 7 | ISHAN CONSTRUCTION | 2.34 | 0 | 100
854 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC (650 Nos.) from dist. System within the command area of SUHARI piped water supply scheme at Masjidpara, Allahadipara, Varpally, Saktigarh Utttar Bazar Habitation (Putunda & Saktigarh Mouza) at Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000294/2021-2022 | 7027/BWD | 17/12/2021 | 30 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 19.58 | 0 | 1
855 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC in Jarul village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte.(Part-A). Gr.K. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000347/2022-2023 | 1381/BWD | 05/08/2022 | 5 | SAMANTA CONSTRUCTION | 0.96 | 0 | 0
856 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC in Jarul village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte.(Part-B).Gr.L. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000348/2022-2023 | 1382/BSD | 05/08/2022 | 5 | SAMANTA CONSTRUCTION | 0.96 | 0 | 0
857 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC in Shuhari village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte.(Part-A).Gr.M. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000349/2022-2023 | 1383/BSD | 05/08/2022 | 5 | SAMANTA CONSTRUCTION | 0.97 | 0 | 0
858 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC in Shuhari village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS Bardhhaman-II Development Block under Burdwan Division, PHE Dte.(Part-B). Gr.N. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000350/2022-2023 | 1384/BSD | 05/08/2022 | 5 | SAMANTA CONSTRUCTION | 0.96 | 0 | 0
859 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC in Atagar village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Gr.O. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000351/2022-2023 | 1390/BSD | 08/08/2022 | 5 | SAMANTA CONSTRUCTION | 0.56 | 0 | 0
860 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000416/2021-2022 | 385/BWD | 20/01/2022 | 30 | BISWAS ENTERPRISE | 11.97 | 0 | 100
861 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
862 | Burdwan Division | Burdwan Sadar Sub-Division | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Suhari piped water supply scheme at Putunda, Atagarh (08 Nos. Habitation), Ghatshila (04 Nos. Habitation), Jarur (02 Nos. Habitation), Saiadpur Chak, Tajpur (04 Nos. Habitation) village, Bardhaman-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000529/2020-2021 | 5004/BWD | 10/12/2020 | 90 | NATIONAL CONSTRUCTION | 80.78 | 0 | 0
863 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC for 100% coverage in different village (SUHARI, JARUL, ATTAGAR & GHATSHILA) from existing distribution system within SUHARI PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte._2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000572/2023-2024 | 3722/BWD | 25/08/2023 | 30 | BIPLAB SAMANTA | 18.91 | 0 | 100
864 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Purba Krishnapur village of Suhari piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Phase-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000677/2020-2021 | 1326/BWD | 12/02/2021 | 30 | SAMANTA CONSTRUCTION | 4.92 | 0 | 1
865 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for SUHARI its Adjoining Mouza W/S Scheme, Block -Bardhaman-II within Burdwan Sub-Division, PHE Dte. (Mouza- PURBA KRISHNAPUR) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000767/2022-2023 | 502/BSD | 21/03/2023 | 45 | M/S PALASH BISWAS | 3.45 | 0 | 100
866 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Tajpur Village, Burdwan - II Block within Suhari PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000773/2023-2024 | 853/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0 | 100
867 | Burdwan Division | Burdwan Sadar Sub-Division | Providing laying distribution pipe line due to shal balla pileing at Sontoshpur village by P.Samiti for SUHARI PWSS at Bardhhaman-II Development Block under Burdwan Division,PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001178/2023-2024 | 537/BSD | 14/03/2024 | 30 | M/S PALASH BISWAS | 0.89 | 0 | 100
868 | Burdwan Division | Kalna Sub-division | Hire & fuel charges of vehicle (Car No.-WB-41J-6795) for the office of the Deputy Superintending Engineer, Central Circle, PHE Dte. for the month of November & December'22. | Assistant Engineer |  | BILL/00464/2022-2023 | 1131/JJM | 28/02/2023 | 0 | MD HASIN | 0.72 | 0 | 0
869 | Burdwan Division | Kalna Sub-division | Restoration of Nepakuli -Baghnapara road from 1.50 km to 2.50 km damaged due to laying of underground water pipe line by PHE with box cutting and Jhama moorum consolidation under Kalna Highway Sub-Division of Burdwan South Highway Division , P.W (Roads) Dte. during the year 2023-2024 | Assistant Engineer |  | BILL/00892/2024-2025 | 1025/JJM | 05/10/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 1.74 | 0 | 0
870 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sihigram village and Adibashipara, Hindupara (Sihigram), Kamarpara & Makarpara habitation of Majhergram piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-605/BWD/2020-21) | Assistant Engineer |  | ORD/000249/2020-2021 | 4125/BWD | 16/10/2020 | 30 | N.S. ENTERPRISE | 4.86 | 1.35 | 1
871 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dhanya Kherur village and Deleypara, Malpara, Mandalpara, Paschimpara & Purba Daspara habitation of Majhergram piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-385/BWD/2020-21) | Assistant Engineer |  | ORD/000257/2020-2021 | 4124/BWD | 16/10/2020 | 30 | SUBRATA GUPTA | 4.86 | 4.86 | 1
872 | Burdwan Division | Kalna Sub-division | Construction of sanitary Latrine and water supply arrangement at Head Work Site of Majhigram Singot piped water supply schemes under Mongalkote Block under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No-01] | Assistant Engineer |  | ORD/000593/2021-2022 | 159/KTS | 24/02/2022 | 21 | BABUL SK | 1.76 | 0 | 1
873 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dhanya Kherur village and Duleypara, Malpara, Mandalpara, Paschimpara & Purba Daspara Habitation of Majhergram piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer |  | ORD/000607/2020-2021 | 260/BWD | 13/01/2021 | 30 | SUBRATA GUPTA | 4.86 | 4.86 | 1
874 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Majhergram Piped Water Supply Scheme at Sihigram (P) (Paschimpara habs.), Sonagachi (3 Nos. habs.), Majhergram (8 Nos. habs.) & Ganguria (3 Nos. habs), Monteswar Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000639/2020-2021 | 1497/BWD | 18/02/2021 | 60 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 57.97 | 17.09 | 1
875 | Burdwan Division | Kalna Sub-division | Continuation work for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sihigram village and Adibasipara, Hindupara (Sihigram), Kamarpara & Makarpara habitation of Majhergram Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿11B¿] | Assistant Engineer |  | ORD/000658/2021-2022 | 1667/BWD | 23/03/2022 | 30 | N.S. ENTERPRISE | 4.16 | 0 | 1
876 | Burdwan Division | Kalna Sub-division | Extension of 63 mm dia UPVC pipeline to provide house connection to the beneficiaries of Sihigram village of Majhergram water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Sl No.-D] | Assistant Engineer |  | ORD/000859/2020-2021 | 141/KSD | 12/02/2021 | 30 | GOUTAM DEY | 3.14 | 0 | 1
877 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000125/2021-2022 | 1106/BWD | 26/02/2022 | 0 | Resource Division | 44.82 | 0 | 0
878 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0
879 | Burdwan Division | Durgapur Sub-DIvision | Trial boring at Kumarun for Serua and its Adjoining Mouza Water Supply Scheme within Bhatar Block under Burdwan Division PHE Dte. [Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000314/2022-2023 | 526/DSD | 22/08/2022 | 7 | BABA ADHIRA CONSTRUCTION | 0.6 | 0 | 1
880 | Burdwan Division | Durgapur Sub-DIvision | Trial boring at Serua for Serua and its Adjoining Mouza Water Supply Scheme within Bhatar Block under Burdwan Division PHE Dte. [Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000315/2022-2023 | 527/DSD | 22/08/2022 | 7 | BABA ADHIRA CONSTRUCTION | 0.6 | 0 | 1
881 | Burdwan Division | Durgapur Sub-DIvision | Extension of 180 mm dia pipeline at "Serua" villages of Serua and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000331/2021-2022 | 01/DSD | 03/01/2022 | 30 | DHIRENDRANATH SOM | 4.82 | 0 | 1
882 | Burdwan Division | Durgapur Sub-DIvision | Extension of 50 mm dia. pipeline at "Serua-Basuda-Jhujkadanga" villages of Serua and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte.[Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000332/2021-2022 | 02/DSD | 03/01/2022 | 30 | DHIRENDRANATH SOM | 1.84 | 0 | 1
883 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline at "Panua, Ratanpur & Rajipur" villages of Serua and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000334/2021-2022 | 04/DSD | 03/01/2022 | 30 | DHIRENDRANATH SOM | 4.68 | 0 | 1
884 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline at "Bamunara & Kumarun & Sakraw" villages of Serua and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000335/2021-2022 | 05/DSD | 03/01/2022 | 30 | DHIRENDRANATH SOM | 2.98 | 0 | 0
885 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Serua Piped Water Supply Scheme at Rajipur, Ratanpur, Serua & Basuda (P) village, Bhatar Block under Burdwan Division, PHE Dte.[Agreement No. 708/BWD OF 2020-2021] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000340/2020-2021 | 1580/BWD | 22/02/2021 | 60 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 74.3 | 24.39 | 1
886 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Serua Piped Water Supply Scheme at Bamunara village (Bamunara habs), Jhujkadanga village, Kumarun village & Panua (P) village (Panua (P) & Sakra habs), Bhatar Block under Burdwan Division, PHE Dte.[ | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000344/2020-2021 | 1579/BWD | 22/02/2021 | 60 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 54.03 | 22.16 | 1
887 | Burdwan Division | Durgapur Sub-DIvision | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000389/2021-2022 | 268/BWD | 14/01/2022 | 30 | BHARAT CONSTRUCTION | 14.17 | 0 | 1
888 | Burdwan Division | Durgapur Sub-DIvision | Relaying of distribution main in alternate route for improvement of water supply at Basudha (South Panoa) village within Serua water supply scheme in Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000698/2021-2022 | 6119/BWD | 25/10/2021 | 30 | KOUSIK MALLICK | 26.54 | 0 | 1
889 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Basuda village and Basuda Habitation of Serua piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I][Gr.-9A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000791/2020-2021 | 4086/BWD | 16/10/2020 | 30 | DHIRENDRANATH SOM | 4.87 | 0 | 1
890 | Burdwan Division | Durgapur Sub-DIvision | Construction of Boundary wall, Land Development work at Head work site, Construction of approach road from main road to OHR of SERUA Piped water supply Scheme, P.H.E Dte. Block:-Bhatar Dist: Purba Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001341/2024-2025 | 1024/BWD | 21/03/2025 | 90 | KALYAN CHOWDHURY | 18.74 | 0 | 50
891 | Burdwan Division | Durgapur Sub-DIvision | Restoration and shifting of pipeline, providing sluice valve, Painting and minor repairing of Switch room, Clearing compound premises, making temporary earthen road and repairing of old Valve chamber, Septic tank etc of Serua Piped water supply Scheme , P.H.E Dte. Block:-Bhatar Dist: Purba Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001417/2024-2025 | 236/DSD | 07/02/2025 | 45 | DHIRENDRANATH SOM | 10.43 | 0 | 100
892 | Burdwan Division | Durgapur Sub-DIvision | Laying parallel pipeline to increase the water supply towards Kaldanda of PUBER and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000132/2022-2023 | 344/DSD | 30/06/2022 | 30 | ANWESHA CONSTRUCTION | 4.81 | 0 | 1
893 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline including water tap connection (FHTC) at Pubar Vill [Kamalpur & Pubar (Part) Hab.] of PUBAR and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte._2ND CALL. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000175/2021-2022 | 6105/BWD | 08/10/2021 | 30 | ANWESHA CONSTRUCTION | 29.76 | 0 | 1
894 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline including water tap connection (FHTC) at Pubar Vill [Kamalpur & Pubar (Part) Hab.] of PUBAR and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte._2ND CALL | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000193/2021-2022 | 6104/BWD | 08/10/2021 | 30 | ANWESHA CONSTRUCTION | 29.76 | 0 | 1
895 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Pubar (Part) village (Pubar (Part) habitation) of Pubar Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [Sl. No. : ¿16¿] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000420/2020-2021 | 66/BWD | 05/01/2021 | 15 | SUBRATA GUPTA | 4.86 | 0 | 1
896 | Burdwan Division | Durgapur Sub-DIvision | Extension of Pipeline with Providing Functional Household Tap Connection (FHTC) within the command area of PUBER Piped Water Supply Scheme , Block- Ausgram-II within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000457/2021-2022 | 77/DSD | 11/02/2022 | 30 | ANWESHA CONSTRUCTION | 4.75 | 0 | 1
897 | Burdwan Division | Durgapur Sub-DIvision | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Ausgram-II Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000472/2021-2022 | 940/BWD | 17/02/2022 | 30 | NANDY UDYOG | 11.82 | 0 | 0
898 | Burdwan Division | Durgapur Sub-DIvision | Relaying of pipeline damaged by construction of Road/Drain etc. at different location of Pubar and its adjoining mouzas water supply scheme at Ausgram-II Block within Durgapur Sub-Division, under Burdwan Division, PHE Dte. [SL-20] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000862/2022-2023 | 719/DSD | 30/12/2022 | 30 | ASRUL HAQUE MONDAL | 0.88 | 0 | 100
899 | Burdwan Division |  | Relaying of pipe line damaged by Construction of Community Centre & construction of road / drain etc. at different location of TAKIPUR and its adjoining mouza's Piped W/S Scheme at Ausgram-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte.[SL-08] |  |  | ORD/000046/2023-2024 | 174/DSD | 18/04/2023 | 21 | TARAMA AGENCY | 0.91 | 0 | 100
900 | Burdwan Division |  | Relaying of pipe line damaged by Construction of Health Centre & construction of road / drain etc. at different location of TAKIPUR and its adjoining mouza's Piped W/S Scheme at Ausgram-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte.[SL-9] |  |  | ORD/000047/2023-2024 | 175/DSD | 18/04/2023 | 21 | TARAMA AGENCY | 0.77 | 0 | 100
901 | Burdwan Division |  | Construction of Path way, Drain, Vertical Extension of valve chamber & repairing of OHR connection etc. including shifting of damage pipeline at Head work site of TAKIPUR water supply scheme, Block-Ausgram-II within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Gr.-H] |  |  | ORD/000230/2021-2022 | 662/DSD | 22/11/2021 | 30 | PAL CONSTRUCTION | 4.02 | 0 | 1
902 | Burdwan Division |  | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of TAKIPUR Piped Water Supply Scheme at Takipur (Part), Asinda (part) & Chanwari (Part) habitation, Ausgram-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. |  |  | ORD/000259/2021-2022 | 6693/BWD | 01/12/2021 | 30 | HAMID SK | 20.08 | 0 | 1
903 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Takipur Piped Water Supply Scheme at Asinda, Chonari & Takipur Village (Mouza), Ausgram-I Block under Burdwan Division, PHE Dte. (Agreement No. 575/BWD of 2020-2021) |  |  | ORD/000274/2020-2021 | 440/BWD | 19/01/2021 | 45 | KOUSIK MALLICK | 36.91 | 33.1 | 1
904 | Burdwan Division |  | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of TAKIPUR Piped Water Supply Scheme at Takipur (Part), Asinda (part) & Chanwari (Part) habitation, Ausgram-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Sl-A] |  |  | ORD/000565/2021-2022 | 135/DSD | 02/03/2022 | 30 | HAMID SK | 4.78 | 0 | 1
905 | Burdwan Division |  | Installation of Sluice Valve, Air Valve and inter connection of Pipeline and allied works to regulate the water supply towards Ashinda & Takipur Village of TAKIPUR and its adjoining mouza's Piped W/S Scheme at Ausgram-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [SL-09] |  |  | ORD/000852/2022-2023 | 709/DSD | 30/12/2022 | 30 | HAMID SK | 4.71 | 0 | 0
906 | Burdwan Division | Kalna Sub-division | Hire & fuel charges of vehicle Car No.-WB-04G-7127 for the month of July & August'2023. | Assistant Engineer |  | BILL/01047/2023-2024 | 767/JJM | 12/10/2023 | 0 | PARTHA PRATIM ACHARYA | 0.78 | 0 | 0
907 | Burdwan Division | Kalna Sub-division | Vehicle bill for the month of August & September'2023. | Assistant Engineer |  | BILL/01675/2023-2024 | 1139/JJM | 29/12/2023 | 0 | MD HASIN | 0.77 | 0 | 0
908 | Burdwan Division | Kalna Sub-division | Vehicle bill [car No.-WB-04G-7127] for the month of October & November'2023. | Assistant Engineer |  | BILL/02061/2023-2024 | 1321/JJM | 01/02/2024 | 0 | PARTHA PRATIM ACHARYA | 0.73 | 0 | 0
909 | Burdwan Division | Kalna Sub-division | Work order for " Providing Functional house hold tap connections for Sajal Gram Village within Kalna-II Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Tehata Water Supply Scheme)" | Assistant Engineer |  | ORD/000037/2023-2024 | 345/KSD | 17/04/2023 | 30 | ARINDAM BHATTACHARYA | 0.88 | 0 | 100
910 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Baitipara village (Baitipara habitation) of Tehata Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Sl. No. : ¿01¿] | Assistant Engineer |  | ORD/000123/2021-2022 | 4020/BWD | 05/08/2021 | 15 | SUKANTA DEY | 3.23 | 0 | 1
911 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of TEHATA Zone-I & II (SM/16301) Water Supply Scheme, CHAKSIMLA (SM/15586) Water Supply Scheme & DWARIATON (SM/16285) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000162/2024-2025 | 2201/BWD | 13/06/2024 | 752 | M/S ASHA CONSTRUCTION | 449.98 | 0 | 25
912 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tehata Piped Water Supply Scheme at Bajitpur (P), Jhiekra (P), Habibpur (P), Narenga Kutubpur (P) & Saipara (P) Village (Mouza), Kalna-II Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000254/2021-2022 | 6640/BWD | 29/11/2021 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 26.96 | 0 | 1
913 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Tehata (Part) village Tehata (Part) habitation of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-05] | Assistant Engineer |  | ORD/000689/2020-2021 | 1223/BWD | 11/02/2021 | 15 | ROY & ROY CONSTRUCTION | 3.16 | 3.16 | 1
914 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Tehata (Part) village, Tehata (Part) habitation of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-05] | Assistant Engineer |  | ORD/000690/2020-2021 | 55/BWD | 05/01/2021 | 15 | ROY & ROY CONSTRUCTION | 4.86 | 4.86 | 1
915 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bajitpur village, Bajit habitation & Jhikra village (Jhikra habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-02] | Assistant Engineer |  | ORD/000692/2020-2021 | 52/BWD | 05/01/2021 | 15 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.86 | 4.86 | 1
916 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Tehata (Part) village (Bajitpur & Sarpukur habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-06] | Assistant Engineer |  | ORD/000693/2020-2021 | 56/BWD | 05/01/2021 | 15 | M/S UNIQUE | 4.86 | 4.86 | 1
917 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Baitipara village (Baitipara Habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Sl No.-01] | Assistant Engineer |  | ORD/000709/2020-2021 | 51/BWD | 05/01/2021 | 15 | SUKANTA DEY | 4.87 | 0 | 1
918 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kutubpur (Part) village (Habibpur Habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-03] | Assistant Engineer |  | ORD/000713/2020-2021 | 53/BWD | 05/01/2021 | 15 | TAPAS KUMAR ROY | 4.86 | 4.86 | 0
919 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kutubpur (Part) village (Kutub Habitation) & Suipara village (Suipara Habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Sl No.-04] | Assistant Engineer |  | ORD/000723/2020-2021 | 54/BWD | 05/01/2021 | 15 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.84 | 4.84 | 1
920 | Burdwan Division | Kalna Sub-division | Providing FHTC work at Suipara village (13 Nos), Tehata village (52 Nos), Bajitpur village (18 Nos) Narenga village (282 nos) & Baitipara village (52 Nos) under TEHATA Zone-I Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000883/2023-2024 | 5516/BWD | 14/12/2023 | 30 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 19.32 | 0 | 0
921 | Burdwan Division | Kalna Sub-division | Providing FHTC work at Agradaha village (25 Nos), Jhikra village (20 Nos), Kutubpur village (122 Nos) Habibpur village (232 Nos) & Bajitpur village (16 Nos) under Tehata Zone-II Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000884/2023-2024 | 5515/BWD | 14/12/2023 | 30 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 23.96 | 0 | 0
922 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal work order for the work of " Supplying and Laying of different dia UPVC pipe (LDS) including providing FHTC and Repairing and renovation of existing RCC OHR at Amrargarh under Amarargarh PWSS, Block- Aushgram-II, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000041/2024-2025 | 751/DWSD | 05/06/2024 | 300 | SAIKAT RAY | 36.37 | 0 | 100
923 | Burdwan Division | Durgapur Sub-DIvision | Restoration of village Road dismantled by laying pipeline for providing FHTC at Amarargarh Ankurepara, Bonpara & Sahapara of AMARARGARH Piped Water Supply Scheme [Rectrofitting] under Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-06] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000030/2023-2024 | 154/DSD | 13/04/2023 | 637 | SAIKAT RAY | 0.97 | 0 | 100
924 | Burdwan Division | Durgapur Sub-DIvision | Restoration of village Road dismantled by laying pipeline for providing FHTC at Amarargarh Dakshinpara of AMARARGARH Piped Water Supply Scheme [Retrofitting] under Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-07] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000031/2023-2024 | 155/DSD | 13/04/2023 | 21 | RAM MOHAN MUKHERJEE | 0.97 | 0 | 100
925 | Burdwan Division | Durgapur Sub-DIvision | Restoration of village Road dismantled by laying pipeline for providing FHTC at Amarargarh Mandalpara of AMARARGARH Piped Water Supply Scheme [Retrofitting] under Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-08] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000032/2023-2024 | 156/DSD | 13/04/2023 | 21 | PARTHA RAY | 0.96 | 0 | 100
926 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amrargarh Piped Water Supply Scheme at Amrargarh (10 Nos Habitation), Dombandi (2 Nos Habitation), Jamtara (2 Nos Habitation) & Panch Mahali Village (Mouza), Ausgram-II Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000103/2021-2022 | 3875/BWD | 27/07/2021 | 60 | B.B.C. ENTERPRISE | 91.55 | 0 | 100
927 | Burdwan Division | Kalna Sub-division | Quotation from WBSEDCL for load enhancement charges of Aug Naopara w/s scheme under Burdwan Division, PHE Dte. (Application No.-5004355150)(Ref. ID-500374861) | Assistant Engineer |  | BILL/00903/2024-2025 | 1047/JJM | 30/10/2024 | 0 | WBSEDCL | 1.34 | 0 | 0
928 | Burdwan Division | Kalna Sub-division | Laying Rising main and distribution pipeline including Providing Functional Household Tap Connection (FHTC) within the command are of Augmentation of NAOPARA Piped W/S. Scheme under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000003/2022-2023 | 1870/BWD | 05/04/2022 | 45 | KOUSIK MALLICK | 66.6 | 0 | 1
929 | Burdwan Division | Kalna Sub-division | Work Order for Repairing and laying of UPVC pipeline & providing FHTC work from the house of Habu Sk to the house of Asadul Kha at Naopara Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000127/2023-2024 | 421/KSD | 11/05/2023 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.97 | 0 | 100
930 | Burdwan Division | Kalna Sub-division | Work order for Repairing and laying of UPVC pipeline & providing FHTC work from wood shop to the house of Patal Das at Naopara Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000147/2023-2024 | 396/KSD | 02/05/2023 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.99 | 0 | 100
931 | Burdwan Division | Kalna Sub-division | Work order for Repairing and laying of UPVC pipeline & providing FHTC work from Mallick oil mil to the house of Khalil Sk at Naopara Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000148/2023-2024 | 397/KSD | 02/05/2023 | 30 | ARINDAM BHATTACHARYA | 0.99 | 0 | 0
932 | Burdwan Division | Kalna Sub-division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Jahannagar, Ganganandapur, Nowapara & Monteswar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, P.H.E. Dte.[Part ¿ A] | Assistant Engineer |  | ORD/000323/2022-2023 | 3632/BWD | 22/08/2022 | 20 | RAMASISH ENTERPRISE | 12.8 | 0 | 1
933 | Burdwan Division | Kalna Sub-division | Work Order for "Repairing and laying of UPVC pipeline & providing FHTC work from the shop of Bhoton Sk to the petrol pump at Naopara Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer |  | ORD/000553/2023-2024 | 1308/KSD | 23/08/2023 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 3.59 | 0 | 100
934 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Naopara W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-I) | Assistant Engineer |  | ORD/000576/2021-2022 | 211/KSD | 23/02/2022 | 21 | ROY CHOWDHURY ASSOCIATES | 2.43 | 0 | 1
935 | Burdwan Division | Kalna Sub-division | Work Order for "Restoration of Pipeline of Naopara Piped Water Supply Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl-1) | Assistant Engineer |  | ORD/001131/2023-2024 | 2060/KSD | 23/02/2024 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 2.98 | 0 | 50
936 | Burdwan Division | Kalna Sub-division | Work Order for "Ancillary work of Rising Main including Construction of Sluice Valve Chamber & other allied work of Naopara Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-2) | Assistant Engineer |  | ORD/001132/2023-2024 | 2061/KSD | 23/02/2024 | 20 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 1.69 | 0 | 5
937 | Burdwan Division | Kalna Sub-division | Work Order for "Road Restoration and other ancilliary works under NAOPARA(SM/09407) water supply scheme under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer |  | ORD/001191/2023-2024 | 2198/KSD | 15/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 1.34 | 0 | 50
938 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000040/2021-2022 | 542/BWD | 27/01/2022 | 0 | Resource Division | 9.97 | 0 | 0
939 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000152/2021-2022 | 1240/BWD | 07/03/2022 | 0 | Resource Division | 4.19 | 0 | 0
940 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000203/2021-2022 | 1526/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
941 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
942 | Burdwan Division | Katwa Sub-Division | Augmentation of Laying Distribution and Rising main Network and Construction of 250 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir including Soil Investigation and pipe connection with cost of pipes, specials and Providing Functional Household Tap Connection (FHTC) from distribution system within the command area of SINGHI Piped Water Supply Scheme under JAL SWAPNA MISSION under Katwa II Block in Purba Bardhaman District under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000020/2022-2023 | 2014/BWD | 18/04/2022 | 683 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 465.17 | 0 | 95
943 | Burdwan Division | Katwa Sub-Division | Route Survey and preparation of DPR for SINGHI PWSS under Katwa -II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-03] | Assistant Engineer |  | ORD/000539/2021-2022 | 54/KTS | 25/01/2022 | 21 | RADIANT | 2.81 | 0 | 1
944 | Burdwan Division | Katwa Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000050/2021-2022 | 566/BWD | 27/01/2022 | 0 | Resource Division | 22.48 | 0 | 0
945 | Burdwan Division | Katwa Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000150/2021-2022 | 1239/BWD | 07/03/2022 | 0 | Resource Division | 4.33 | 0 | 0
946 | Burdwan Division | Katwa Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000158/2021-2022 | 1318/BWD | 08/03/2022 | 0 | Resource Division | 23.18 | 0 | 0
947 | Burdwan Division | Katwa Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000200/2021-2022 | 1523/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
948 | Burdwan Division | Katwa Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
949 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of pipeline for providing FHTC 100% coverage and also construction & installation of Sluice Valve & Valve Chamber to control the flow of water, road restoration work etc. of different Piped W/S Schemes, Block Jamalpur under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000194/2024-2025 | 2488/BWD | 01/07/2024 | 550 | M/S NATIONAL CONSTRUCTION | 480.97 | 0 | 80
950 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
951 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional House Hold Tap Connection (FHTC) at Ajhapur village (Habitation,near Head Work Site)under AJHAPUR PWSS at Jamalpur Dev. Block of Burdwan Sub-Division under Burdwan Division,PHE Dte. Gr.D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000442/2022-2023 | 1480/BSD | 25/08/2022 | 30 | T.K. BANERJEE & CO. | 3.33 | 0 | 1
952 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 46/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000452/2020-2021 | 4753/BWD | 01/12/2020 | 90 | SK ALIM | 93.16 | 22.74 | 0
953 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection(FHTC)from existing distribution pipe line system within command area of AJHAPUR Piped W/S Scheme at Ajhapur Habitation (Near Head Works Site), Jamalpur Development Block under Burdwan Division,PHE Dte. Gr.E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000478/2022-2023 | 1602/BSD | 14/09/2022 | 30 | DEY NIRMAN | 4.03 | 0 | 1
954 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) of AJHAPUR & its adjoining mouzas Piped Water Supply Scheme, Block - Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000545/2022-2023 | 5124/BWD | 21/11/2022 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 11.24 | 0 | 1
955 | Burdwan Division | Burdwan Sadar Sub-Division | Beautification of PWSS with Arboriculture, Recharge Pit including shaft and anciliary works at AJHAPUR (Jamalpur Block) P.W.S.S under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000545/2024-2025 | 276/RWS | 03/09/2024 | 10 | DEY NIRMAN | 0.91 | 0 | 0
956 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AJHAPUR Piped Water Supply Scheme and its adjoining mouzas (Vill- Ajhapur, Habitation- Purba Sadipur, Musunda) at Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000578/2021-2022 | 1352/BWD | 09/03/2022 | 45 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 41.37 | 0 | 1
957 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline of AJHAPUR Piped Water Supply scheme of Jamalpur Block under Burdwan Sub-Division,under Burdwan Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000581/2022-2023 | 1978/BSD | 17/11/2022 | 15 | DEY NIRMAN | 0.51 | 0 | 1
958 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for AJHAPUR its Adjoining Mouza W/S Scheme, Block -Jamalpur within Burdwan Sub-Division, PHE Dte. (Mouza- SALMULA) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000841/2022-2023 | 507/BSD | 21/03/2023 | 45 | M/S MA TARA ENTERPRISE | 3.29 | 0 | 100
959 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall at 4th Tubewell site with Inter Connection and providing FHTC at Mirepara, Adampur, Shalmula Village (Habitation) of AJHAPUR Water Supply Scheme under JAMALPUR Block of Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/001040/2023-2024 | 783/BWD | 27/02/2024 | 30 | MUNSHI JAVEDUR JAMAN | 14.96 | 0 | 100
960 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 40
961 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of overhead structure for placing 2 Nos 5000 lit PVC tank including interconnection, Installation of Solar pump, FHTC, LDS & Sinking of 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe at Mohanpur village for AJHAPUR Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/001251/2024-2025 | 817/BWD | 04/03/2025 | 90 | UJJWAL MUKHERJEE | 23.02 | 0 | 0
962 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | RTOR000024/2021-2022 | 422/BWD | 20/01/2022 | 0 | Resource Division | 5.49 | 0 | 0
963 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | VCH/001555/2021-2022 | 1194/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0
964 | Burdwan Division | Burdwan Division | Re-Laying of U-PVC (Damaged by Irrigation Department) pipeline near Uttar Mahanpur to Dakhin Mahanpur under ANTPARA PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000027/2025-2026 | 1299/BWD | 28/04/2025 | 90 | GOUTAM KUMAR MITRA | 9.64 | 0 | 0
965 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) at Antpara village within the command area of ANTPARA Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : A] | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000034/2022-2023 | 240/AE/HQ | 20/04/2022 | 30 | N.S. ENTERPRISE | 4.77 | 0 | 1
966 | Burdwan Division | Burdwan Division | Laying of uPVC pipe for providing FHTC at Baratikra Village within ANTPARA Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte. [Group : C] | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000036/2022-2023 | 242/AE/HQ | 20/04/2022 | 30 | J. K. CORPORATION | 4.58 | 0 | 1
967 | Burdwan Division | Burdwan Division | Laying of distribution system of different damaged section at Chakundi & Saligram village regarding smooth running FHTC work within Nabastha PWSS, Bardhhaman II Development Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000138/2023-2024 | 787/BSD | 28/04/2023 | 30 | D.M. ENTERPRISE | 0.97 | 0 | 100
968 | Burdwan Division | Burdwan Division | Functional Household Tap Connection (FHTC) at Baratikra village within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. (Part-A). | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000167/2021-2022 | 1858/AE/HQ | 05/10/2021 | 30 | J. K. CORPORATION | 4.83 | 0 | 1
969 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) at Baratikra village within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. (Part-B). | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000168/2021-2022 | 1859/AE/HQ | 05/10/2021 | 30 | INDRAJIT MONDAL | 4.83 | 0 | 1
970 | Burdwan Division | Burdwan Division | Construction of sluice valve chamber and extension of pipeline for making functional of Household Tap at Daspur village within Antpara piped water supply scheme under Burdwan Division, PHE Dte.[Gr.-A] | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000325/2021-2022 | 1728/AE/HQ | 25/08/2021 | 30 | J. K. CORPORATION | 1.64 | 0 | 1
971 | Burdwan Division | Burdwan Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000345/2021-2022 | 40/BWD | 05/01/2022 | 30 | PREMANANDA ROY BISWAS | 22.68 | 0 | 1
972 | Burdwan Division | Burdwan Division | Re-Laying of UPVC Pipeline (Damaged by Irrigation Department) at Dakshin Mohanpur Habitation under ANTPARA Piped Water Supply Scheme, Jamalpur Development Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000407/2023-2024 | 400/AE/HQ | 28/07/2023 | 30 | J K CORPORATION | 0.96 | 0 | 100
973 | Burdwan Division | Burdwan Division | Laying of UPVC Pipeline at Daspur Habitation under ANTPARA Piped Water Supply Scheme, Jamalpur Development Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000409/2023-2024 | 416/AE/HQ | 01/08/2023 | 30 | J K CORPORATION | 0.96 | 0 | 100
974 | Burdwan Division | Burdwan Division | Laying of HDPE pipeline at Antpara village for dedicated water supply at Dakshinmohonpur village within Antpara PWSS, Block-Jamalpur under Burdwan Division, PHE Dte. [Group : A] | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000455/2021-2022 | 65/AE/HQ | 11/02/2022 | 30 | SUPER SKILL | 4.68 | 0 | 1
975 | Burdwan Division | Burdwan Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) of ANTPARA & its adjoining mouzas Piped Water Supply Scheme, [Nandanpur Vill.] Block ? Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. _2ND CALL. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000566/2022-2023 | 5275/BWD | 30/11/2022 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 9.45 | 0 | 0
976 | Burdwan Division | Burdwan Division | Extension of pipeline for providing functional house hold tap connection at Antpara habitation within the command area of Antpara water supply scheme under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000567/2020-2021 | 1258/AE/HQ | 15/02/2021 | 30 | WESTERN WATER SUPPLY AGENCY | 4.8 | 0 | 1
977 | Burdwan Division | Burdwan Division | Extension of pipeline for providing functional house hold tap connection at Dakshin Mohonpur & Uttar Mohanpur habitation under Antpara water supply scheme under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000586/2020-2021 | 1244/AE/HQ | 12/02/2021 | 30 | DIBAKAR SHAW | 4.81 | 0 | 1
978 | Burdwan Division | Burdwan Division | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near RAMKRISHNAPUR MONDAL PARA under ANTPARA PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000588/2024-2025 | 740/AE/HQ | 13/09/2024 | 30 | J.K. CORPORATION | 0.96 | 0 | 100
979 | Burdwan Division | Burdwan Division | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near RAMKRISHNAPUR MUSLIM PARA under ANTPARA PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000589/2024-2025 | 741/AE/HQ | 13/09/2024 | 30 | J.K. CORPORATION | 0.95 | 0 | 100
980 | Burdwan Division | Burdwan Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000592/2021-2022 | 1454/BWD | 11/03/2022 | 30 | PREMANANDA ROY BISWAS | 18.83 | 0 | 1
981 | Burdwan Division | Burdwan Division | Construction of different dia. Sluice Valve chamber to operate water flow for supplying water in zonal demand basis within command area of Antpara PWSS under Burdwan Division, PHE Dte._Gr-C | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000628/2021-2022 | 125/AE/HQ | 04/03/2022 | 15 | SUPER SKILL | 4.81 | 0 | 1
982 | Burdwan Division | Burdwan Division | Repairing and restoration of pipeline besides river bank of Damodar damaged due to construction of retaining wall at Antpara to Dakshinmohanpur within command area of ANTPARA PWSS under Burdwan Division, PHE Dte._Gr-B | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000661/2021-2022 | 134/AE/HQ | 11/03/2022 | 20 | SUPER SKILL | 4.18 | 0 | 1
983 | Burdwan Division | Burdwan Division | Laying of uPVC pipe for providing FHTC at Dakshinmohanpur habitation within ANTPARA Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-C | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000664/2021-2022 | 145/AE/HQ | 16/03/2022 | 20 | MUKHERJEE ENTERPRISE | 4.75 | 0 | 1
984 | Burdwan Division | Burdwan Division | Laying of uPVC pipe for providing FHTC at Nandanpur Village within ANTPARA Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-D | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000666/2021-2022 | 146/AE/HQ | 16/03/2022 | 1111 | MUNSHI JAVEDUR JAMAN | 4.75 | 0 | 100
985 | Burdwan Division | Burdwan Division | Continuation work order for functional household tap connection (FHTC) at Baratikra village within the command area of Antpara piped water supply scheme at Jamalpur Block under Burdwan Division, PHE Dte.[Part-A][Gr.-D] | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000790/2021-2022 | 1950/AE/HQ | 22/12/2021 | 30 | J. K. CORPORATION | 4.73 | 0 | 1
986 | Burdwan Division | Burdwan Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ramkrishnapur village (Ramkrishnapur Habitation) of Antpara piped water supply scheme within Head Quarters under Burdwan Division, PHE Dte.[Part-A] | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000950/2020-2021 | 1083/BWD | 08/02/2021 | 15 | DIBAKAR SHAW | 4.78 | 0 | 1
987 | Burdwan Division | Burdwan Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dakshin Mohanpur village (Dakshin Mohanpur Habitation) of Antpara piped water supply scheme within Head Quarters under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/000951/2020-2021 | 4691/BWD | 20/01/2021 | 809 | DIBAKAR SHAW | 4.86 | 0 | 100
988 | Burdwan Division | Burdwan Division | Laying of UPVC (Damaged By Irrigation Department) pipeline at Daspur & Uttar Mohanpur habitation, ANTPARA Piped W/S. Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/001071/2023-2024 | 167/AE/HQ | 07/03/2024 | 30 | J.K. CORPORATION | 0.82 | 0 | 100
989 | Burdwan Division | Burdwan Division | Laying UPVC (Damaged By Irrigation Department) pipeline at Uttar Mohanpur habitation, ANTPARA Piped W/S. Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/001072/2023-2024 | 168/AE/HQ | 07/03/2024 | 30 | J.K. CORPORATION | 0.92 | 0 | 100
990 | Burdwan Division | Burdwan Division | Laying of UPVC (Damaged By Irrigation Department) pipeline near Baratikra Bridge including construction of new valve chamber under ANTPARA Piped W/S. Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/001073/2023-2024 | 169/AE/HQ | 07/03/2024 | 30 | J.K. CORPORATION | 0.84 | 0 | 100
991 | Burdwan Division | Burdwan Division | Arrangement of drinking water supply by installation of solar submersible pump including sinking of 200 mm. dia. Tube well 150 Mtr. Deep by direct rotary rig method, Laying dist. System, FHTC and 2 Nos. 5000 Ltr. PVC tank installation with construction of RCC structure for ANTPARA Piped W/S. Scheme, Block Jamalpur under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/001082/2023-2024 | 1085/BWD | 12/03/2024 | 259 | HI-LIGHT ELECTRONICS | 16.31 | 0 | 40
992 | Burdwan Division | Burdwan Division | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 40
993 | Burdwan Division | Burdwan Division | Hire & fuel charges of vehicle (Car No.-WB-41H-3668) for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. for the month of May & June'22. | AE(HQs), Burdwan Division, PHE Dte. | JE/RWS/JAMALPUR | VCH/000494/2022-2023 | 462/VEH/22-23 | 29/08/2022 | 0 | MD HASIN | 0.51 | 0 | 0
994 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC from dist. System within the command area of GOBINDAPUR Piped Water Supply Scheme at Gobindapur (Part), Ichabacha, Taherpur, Dangapara, Purba Kashiara (Part), Matdanga, Chilinda, Sitarampur Village at Memari-I Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000373/2021-2022 | 210/BWD | 11/01/2022 | 30 | A R TRADERS | 28.37 | 0 | 1
995 | Burdwan Division | Burdwan Sadar Sub-Division | Beautification of PWSS with Land filling and arboriculture of Head Works site & 2nd pump house Gobindapur Pwss under memari-i Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000547/2024-2025 | 278/RWS | 03/09/2024 | 10 | MUNSHI JAVEDUR JAMAN | 0.97 | 0 | 0
996 | Burdwan Division | Burdwan Sadar Sub-Division | Emergent 56 Nos. Street Stand Post closed for FHTC Work under Gobindapur Piped Water Supply Scheme (Retro Fittings) under Burdwan Sub-Divn.within Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000582/2022-2023 | 1974/BSD | 16/11/2022 | 15 | A R TRADERS | 0.24 | 0 | 1
997 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at Kamarhati village (Purba para,Pal para,Kana para,Pandit para, pashim para)within Raina-II Block, under Burdwan Division, PHE Dte. Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000031/2022-2023 | 678/BSD | 22/04/2022 | 30 | BAMDEB CONSTRUCTION & CO | 2.84 | 0 | 1
998 | Burdwan Division | Burdwan Sadar Sub-Division | Land Development(at entrance)of Head Works Site of of KAMARHATI ZONE-II PIPED Water Supply Scheme at RAINA-II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. Group : F. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000108/2022-2023 | 988/BSD | 16/06/2022 | 15 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 1.85 | 0 | 1
999 | Burdwan Division | Burdwan Sadar Sub-Division | Pipeline with FHTC for KAMARHATI ZONE -II Water Supply Scheme at Kamarhati village(70 NOS) of Raina-II Block,under Burdwan Division, PHE Dte. Group : B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000110/2022-2023 | 1015/BSD | 20/06/2022 | 30 | KONAR ENTERPRISE | 4.95 | 0 | 1
1000 | Burdwan Division | Burdwan Sadar Sub-Division | Pipeline with FHTC for KAMARHATI ZONE -II Water Supply Scheme at Kamarhati village(80 NOS) of Raina-II Block,under Burdwan Division, PHE Dte. Group : C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000111/2022-2023 | 1016/BSD | 20/06/2022 | 30 | D.M. ENTERPRISE | 4.94 | 0 | 1
1001 | Burdwan Division | Burdwan Sadar Sub-Division | Pipeline with FHTC for KAMARHATI ZONE -II Water Supply Scheme at Kamarhati village (52 Nos.) of Raina-II Block,under Burdwan Division, PHE Dte. Group : A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000113/2022-2023 | 1035/BSD | 20/06/2022 | 30 | KOUSIK MALLICK | 4.96 | 0 | 1
1002 | Burdwan Division | Burdwan Sadar Sub-Division | Laying pipeline with FHTC for KAMARHATI Zone -II Water Supply Scheme at Kamarhati village (95 Nos.), Barati village (155 Nos.), Baidyapur village (110 Nos.), Jashapur village (125 Nos.) of Raina-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000164/2022-2023 | 3166/BWD | 21/07/2022 | 45 | ANWESHA CONSTRUCTION | 31.48 | 0 | 1
1003 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing dist. System within Scheme jurisdiction in Katshimul village (Part) of Kamarhati (Zone-II) piped water supply scheme within Burdwan Sub-Division PHE Dte Part-A.Gr. D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000214/2021-2022 | 1476/BSD | 09/11/2021 | 30 | MUNSHI JAVEDUR JAMAN | 4.83 | 0 | 1
1004 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing dist. System within Scheme jurisdiction in Katshimul village (Part) of Kamarhati (Zone-II) piped water supply scheme within Burdwan Sub-Division PHE Dte Part-B..Gr. E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000215/2021-2022 | 1477/BSD | 09/11/2021 | 30 | DUBE ENTERPRISE | 4.83 | 0 | 1
1005 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamarhati Z-II Piped Water Supply Scheme at Gotan, Kamarhati & Jashapur Village (Mouza), Raina-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000235/2021-2022 | 6535/BWD | 24/11/2021 | 60 | KOUSIK MALLICK | 71.1 | 0 | 1
1006 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing dist. System within Scheme jurisdiction in Katshimul village (Part) of Kamarhati (Zone-II) piped water supply scheme within Burdwan Sub-Division PHE Dte Part-A.Gr. D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000307/2021-2022 | 1686/BSD | 17/12/2021 | 30 | MUNSHI JAVEDUR JAMAN | 4.83 | 0 | 1
1007 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing dist. System within Scheme jurisdiction in Katshimul village (Part) of Kamarhati (Zone-II) piped water supply scheme within Burdwan Sub-Division PHE Dte Part-B..Gr. E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000308/2021-2022 | 1685/BSD | 17/12/2021 | 30 | DUBE ENTERPRISE | 4.83 | 0 | 1
1008 | Burdwan Division | Burdwan Sadar Sub-Division | FHTC for Kamarhati (Zone-II) Water Supply Scheme at Kamarhati Village (36 Nos) of Raina II Block under Burdwan Division, PHE Dte [For 100% FHTC at Kamarhati Village (Harghar Jal). Gr.J | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000342/2022-2023 | 1367/BSD | 04/08/2022 | 5 | ANWESHA CONSTRUCTION | 0.98 | 0 | 1
1009 | Burdwan Division | Burdwan Sadar Sub-Division | 225mm.Dia UPVC Pipeline at Node 11A to 11B of KAMARHATI(Zone-I)Water Supply Scheme within Raina-II Block , under Burdwan Division, PHE Dte. Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000387/2021-2022 | 58/BSD | 13/01/2022 | 30 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 2.99 | 0 | 1
1010 | Burdwan Division | Burdwan Sadar Sub-Division | 225mm.Dia UPVC Pipeline at Node 86C-92,86-B-86C,86-A-86B,10-11-53-53A of KAMARHATI(Zone-I)Water Supply Scheme within Raina-II Block , under Burdwan Division, PHE Dte. Gr.C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000388/2021-2022 | 59/BSD | 13/01/2022 | 30 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 3.96 | 0 | 1
1011 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at Barati and Badyapur village within Raina-II Block , under Burdwan Division, PHE Dte(Zone-II). Gr.D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000442/2021-2022 | 200/BSD | 01/02/2022 | 30 | ARISTOCON ENGINEERS CO-OP SOCIETY LTD | 4.8 | 0 | 1
1012 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at Jashapur village within Raina-II Block , under Burdwan Division, PHE Dte.Gr.C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000465/2021-2022 | 276/BSD | 15/02/2022 | 30 | KOUSIK MALLICK | 4.99 | 0 | 1
1013 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at Kamarhati village within Raina-II Block , under Burdwan Division, PHE Dte. (Zone-II). Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000549/2021-2022 | 369/BSD | 02/03/2022 | 30 | DUBE ENTERPRISE | 4.98 | 0 | 1
1014 | Burdwan Division | Burdwan Sadar Sub-Division | Bullah pilling (92.0 mtr) at HD Works Site(North,East & South) for protection of Boundary wall beside irrigation canel of KAMARHATI ZONE-II W/S Scheme of RAINA-II Block at Burdwan Sub -Division within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman.Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000644/2021-2022 | 468/BSD | 21/03/2022 | 15 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.61 | 0 | 1
1015 | Burdwan Division | Burdwan Sadar Sub-Division | FHTC for KAMARHATI (Zone-II] Water Supply Scheme at Kamarhati village (36 Nos) of Raina-II Block under Burdwan Division, PHE Dte. [for 100% FHTC at Kamarhati village (Harghar Jal)] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000653/2022-2023 | 1367-A/BSD | 04/08/2022 | 5 | ANWESHA CONSTRUCTION | 0.98 | 0 | 1
1016 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at GOTAN village within Raina II Block, under Burdwan Division, PHE Dte. Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000674/2021-2022 | 534/BSD | 28/03/2022 | 30 | KOUSIK MALLICK | 4.96 | 0 | 1
1017 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of interconnection of the Pump No.-1 & 2 with OHR and distribution main of 300 mm dia for Kamarhati (Zone-II) piped water supply scheme within Raina-II Block under Burdwan Division, PHE Dte.[Gr.-H] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000690/2021-2022 | 959/BSD | 23/07/2021 | 30 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.8 | 0 | 1
1018 | Burdwan Division | Burdwan Sadar Sub-Division | Formal Work Order for Laying distribution system including providing house connection at Nizampur, Daminya village (Mouza) of KAMARHATI Piped W/S. Scheme (Zone-I) at Raina - II Block under Burdwan Division, PHE. Dte.(Part-B) _2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000934/2020-2021 | 1601/BWD | 22/02/2021 | 90 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 184.73 | 0 | 100
1019 | Burdwan Division | Kalna Sub-division | NAME OF THE WORK -RESTORATION WORK OF BIDYANAGAR TO VIA DAMODAR PARA TO BOGPUR ROAD,PACKAGE NO-WB-22-27,BLOCK-PURBASTHALI-1,GP-SRIRAMPUR & JAHANNAGAR. | Assistant Engineer |  | BILL/00739/2024-2025 | 893/JJM | 25/09/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 5.21 | 0 | 0
1020 | Burdwan Division | Kalna Sub-division | Quotation from WBSEDCL for new service connection charges of Krishnabati w/s scheme under Burdwan Division, PHE Dte. (Application No.-5004422952)(Ref. ID-503758136) | Assistant Engineer |  | BILL/00902/2024-2025 | 1048/JJM | 30/10/2024 | 0 | WBSEDCL | 7.08 | 0 | 0
1021 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Krishnabati Piped Water Supply Scheme at Bahara (3 Nos Habitation), Chak Bahara (Natungram Habitation), Chandanpur Simuldanga & Krishnabati (2 Nos Habitation) Village (Mouza), Mangalkot Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000088/2021-2022 | 3592/BWD | 13/07/2021 | 60 | H SAMANTA | 84.33 | 0 | 100
1022 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000181/2024-2025 | 2296/BWD | 20/06/2024 | 616 | M/S DATTA ENTERPRISE | 579.85 | 0 | 2
1023 | Burdwan Division | Kalna Sub-division | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0
1024 | Burdwan Division | Durgapur Sub-DIvision | Augmentation of BANNABAGRAM Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 400 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including construction of switch room without sanitary arrangements Block-Ausgram-I, District:- Purba-Burdwan. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000074/2022-2023 | 2497/BWD | 13/05/2022 | 1051 | GHOSH CONCERN | 454.28 | 0 | 70
1025 | Burdwan Division | Durgapur Sub-DIvision | Laying of pipeline for road crossing due to construction of culvert along PWD Road near Bannabagram Hospital of Bannabagram Piped Water Supply Scheme under Ausgram-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr,-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000133/2022-2023 | 345/DSD | 30/06/2022 | 30 | DUBE ENTERPRISE | 1.07 | 0 | 1
1026 | Burdwan Division | Durgapur Sub-DIvision | Sinking of additional 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Augmentation of BANANABAGRAM Piped Water Supply Scheme, Block - Ausgram - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]_3RD CALL | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000208/2022-2023 | 3297/BWD | 29/07/2022 | 45 | ANIRUDDHA FARUQUE | 27.54 | 0 | 1
1027 | Burdwan Division | Durgapur Sub-DIvision | Shifting of UPVC Pipeline due to construction of culvert along PWD Road near Bannabagram Hospital of Bannabagram Piped Water Supply Scheme under Ausgram-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-G] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000463/2021-2022 | 79/DSD | 11/02/2022 | 30 | M/S UNIQUE | 2.13 | 0 | 1
1028 | Burdwan Division | Durgapur Sub-DIvision | Route Survey & Preparation of DPR for BANNABAGRAM PWSS under Durgapur(Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000654/2021-2022 | 101/DSD | 18/02/2022 | 15 | SIRCON ENGINEERING SERVICES | 3.09 | 0 | 1
1029 | Burdwan Division | Durgapur Sub-DIvision | Left out part of Laying Distribution system for Augmentation of BANNABAGRAM and its adjoining mouza's Piped W/S Scheme at Ausgram-I Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000686/2023-2024 | 4283/BWD | 29/09/2023 | 94 | GHOSH CONCERN | 93.7 | 0 | 100
1030 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000029/2021-2022 | 550/BWD | 27/01/2022 | 0 | Resource Division | 13.66 | 0 | 0
1031 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000036/2022-2023 | 4628/BWD | 17/10/2022 | 0 | Resource Division | 12.32 | 0 | 0
1032 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000144/2021-2022 | 1203/BWD | 04/03/2022 | 0 | Resource Division | 22.68 | 0 | 0
1033 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000170/2021-2022 | 1330/BWD | 08/03/2022 | 0 | Resource Division | 39.95 | 0 | 0
1034 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000191/2021-2022 | 1373/BWD | 09/03/2022 | 0 | Resource Division | 3.83 | 0 | 0
1035 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000238/2021-2022 | 1562/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
1036 | Burdwan Division | Durgapur Sub-DIvision | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
1037 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Bononabagram Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000075/2023-2024 | 2561/CMD | 06/06/2023 | 30 | SOUVIK HALDER | 10.98 | 0 | 0
1038 | Burdwan Division | Durgapur Sub-DIvision | Quotation for new connection charges for Augmentation of Kotachandipur w/s scheme under Burdwan Division, PHE Dte. T.W. No.-3 [Application No.-5003543454, dt.-05/12/2022, Ref. ID-503235377] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00117/2022-2023 | 916/DW | 30/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.02 | 0 | 0
1039 | Burdwan Division | Durgapur Sub-DIvision | Sinking of additional 250 X 150mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for KOTACHANDIPUR Piped Water Supply Scheme, Block - Ausgram - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000033/2022-2023 | 2202/BWD | 28/04/2022 | 30 | ANIRUDDHA FARUQUE | 10.15 | 0 | 1
1040 | Burdwan Division | Durgapur Sub-DIvision | Construction of drain at new 3rd Tube well site of Augmentation of Kota Chandipur water supply scheme, Block-Ausgram-II within Durgapur (Bardhaman North) Sub-Division, under Burdwan Division, Phe Dte.[SL-03] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000041/2023-2024 | 169/DSD | 18/04/2023 | 21 | PARTHA RAY | 0.96 | 0 | 100
1041 | Burdwan Division | Durgapur Sub-DIvision | Ground development at new 3rd Tube well site of Augmentation of Kota Chandipur water supply scheme, Block-Ausgram-II within Durgapur (Bardhaman North) Sub-Division, under Burdwan Division, Phe. Dte.[SL-04] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000042/2023-2024 | 170/DSD | 18/04/2023 | 21 | M/S MUKHERJEE CONSTRUCTION | 0.91 | 0 | 100
1042 | Burdwan Division | Durgapur Sub-DIvision | Construction of pathway at new 3rd Tube well site of Augmentation of Kota Chandipur water supply scheme, Block-Ausgram-II within Durgapur (Bardhaman North) Sub-Division, under Burdwan Division, Phe. Dte.[SL-05] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000043/2023-2024 | 171/DSD | 18/04/2023 | 21 | M/S MUKHERJEE CONSTRUCTION | 0.96 | 0 | 100
1043 | Burdwan Division | Durgapur Sub-DIvision | Restoration of village Road dismantled by laying pipeline for providing FHTC at Kota Ankure para, Bauripara & Loharpara under Augmentation of KOTA-CHANDIPUR Piped Water Supply Scheme under Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-07] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000058/2023-2024 | 181/DSD | 18/04/2023 | 21 | PARTHA RAY | 0.96 | 0 | 100
1044 | Burdwan Division | Durgapur Sub-DIvision | Repairing and painting of 2 Nos existing Pump House for Kota Chnadipur Pipe Water Supply Scheme, Block- Ausgram-II, under Durgapur Sub-Division, P.H.E Dte. within Burdwan Division P.H.E. Dte. Dist:Purba Bardhaman. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000137/2022-2023 | 346/DSD | 30/06/2022 | 45 | SUNNY CONSTRUCTION | 2.13 | 0 | 0
1045 | Burdwan Division | Durgapur Sub-DIvision | Work Order for Augmentation of Kota-Chandipur Water Supply Scheme with LDS, Rising Main, FHTC work, Pump House & Boundary Wall of Ausgram ¿ II Block in Burdwan (North) Sub-Division, District ¿ Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000310/2021-2022 | 7088/BWD | 22/12/2021 | 150 | TIRUPATI ENTERPRISES | 218.89 | 0 | 1
1046 | Burdwan Division | Durgapur Sub-DIvision | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Dignagar, Galsi, Barabelun & Kotachandipur Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. Dte. _2ND CALL | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000311/2022-2023 | 3624/BWD | 22/08/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.76 | 0 | 1
1047 | Burdwan Division | Durgapur Sub-DIvision | Route Survey & Preparation of DPR for KOTA-CHANDIPUR PWSS under Ausgram-II under Durgapur (Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000645/2021-2022 | 99/DSD | 18/02/2022 | 15 | SIRCON ENGINEERING SERVICES | 2.74 | 0 | 1
1048 | Burdwan Division | Durgapur Sub-DIvision | Colour washing, lettering, earthling and other allied works of RCC elevated reservoir (Capacity-200 cum) in connection with Augmentation of Kota-Chandipur water supply scheme within Durgapur (Bardhaman North) Sub-Division, PHE Dte, Block-Ausgram-II under Burdwan Division, PHE Dte. [SL-21] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000865/2022-2023 | 720/DSD | 30/12/2022 | 30 | TIRUPATI ENTERPRISES | 1.85 | 0 | 100
1049 | Burdwan Division | Durgapur Sub-DIvision | Retrofitting of RCC elevated reservoir (Capacity-200 cum) by shotcreting, guinting etc. connection with Augmentation of Kota-Chandipur water supply scheme within Durgapur (Bardhaman North) Sub-Division, PHE Dte, Block-Ausgram-II under Burdwan Division, PHE Dte. [SL-22] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000872/2022-2023 | 721/DSD | 30/12/2022 | 30 | P. ENTERPRISE | 2.98 | 0 | 100
1050 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of Augmentation of KOTA-CHANDIPUR Piped Water Supply Scheme [Retrofitting] at Kota (Part), village, habitation, Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000878/2023-2024 | 5358/BWD | 06/12/2023 | 30 | DEBJYOTI GOSWAMI | 9.29 | 0 | 100
1051 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000017/2021-2022 | 7347/BWD | 30/12/2021 | 0 | Resource Division | 6.59 | 0 | 0
1052 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000025/2021-2022 | 558/BWD | 27/01/2022 | 0 | Resource Division | 6.51 | 0 | 0
1053 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000099/2021-2022 | 771/BWD | 07/02/2022 | 0 | Resource Division | 18.27 | 0 | 0
1054 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000169/2021-2022 | 1329/BWD | 08/03/2022 | 0 | Resource Division | 18.37 | 0 | 0
1055 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000188/2021-2022 | 1384/BWD | 09/03/2022 | 0 | Resource Division | 3.83 | 0 | 0
1056 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000237/2021-2022 | 1561/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
1057 | Burdwan Division | Durgapur Sub-DIvision | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | VCH/001555/2021-2022 | 1194/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0
1058 | Burdwan Division | Durgapur Sub-DIvision | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
1059 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation-1 of Kotachandipur Water Supply Scheme [ Block- Ausgram-I ] at Tube well No.-3 under CMD, PHE Dte., Dist.- Purba-Bardhaman | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000622/2022-2023 | 2100/CMD | 08/09/2022 | 30 | DELTA ENGINEERING ENTERPRISE | 11.65 | 0 | 0
1060 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of pipeline for providing FHTC 100% coverage and also construction & installation of Sluice Valve & Valve Chamber to control the flow of water, road restoration work etc. of different Piped W/S Schemes, Block Jamalpur under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000194/2024-2025 | 2488/BWD | 01/07/2024 | 550 | M/S NATIONAL CONSTRUCTION | 480.97 | 0 | 80
1061 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nabagram Piped Water Supply Scheme at Ajhapur (Part) (Masagram Habitation), Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 115/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000440/2020-2021 | 1402/BWD | 15/02/2021 | 60 | M/S ASHA CONSTRUCTION | 67.11 | 36.94 | 1
1062 | Burdwan Division | Burdwan Sadar Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nabagram Piped Water Supply Scheme at Ajhapur (Part) (Ajhapur Habitation), Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement no. 116/SE/CC/PHE/Dte of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000470/2020-2021 | 1515/BWD | 19/02/2021 | 60 | S.S. CONSTRUCTION | 75.65 | 75.24 | 0
1063 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC for 100% coverage at Nabagram, Basishta Pur, Keliri, Ajhapur & Dattapur Mouza (Village) for NABAGRAM Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000570/2023-2024 | 3716/BWD | 24/08/2023 | 30 | M/S UNIQUE | 23.77 | 0 | 50
1064 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall (Back side of OHR) including land development & Pumping out of water at Pump house no - 1 Site of Nabagram Water Supply Scheme under Jamalpur Dev. Block of Burdwan Division, PHE Dte. (Length -50.00 Mtr, Col-20 Nos). Gr.G. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000659/2021-2022 | 472/BSD | 21/03/2022 | 45 | MOHAMMAD ISSA | 3.77 | 0 | 1
1065 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 mm X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) with construction of Pump House, Boundary wall, Land Development and Rising main connection of NABAGRAM Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. [FOR 3rd. TUBE WELL SITE]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/001041/2023-2024 | 784/BWD | 27/02/2024 | 490 | ANIRUDDHA FARUQUE | 29.04 | 0 | 35
1066 | Burdwan Division | Burdwan Sadar Sub-Division | 02 Nos. Quotation for new connection of WBSEDCL of Augmentation of Kaity water supply scheme. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/00195/2023-2024 | 302/JJM/23-24 | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 12.21 | 0 | 0
1067 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of KAITY Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 700 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under RAINA- II Block, District:- Purba-Burdwan. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000124/2022-2023 | 2930/BWD | 28/06/2022 | 365 | SK ALIM | 689.36 | 0 | 100
1068 | Burdwan Division | Burdwan Sadar Sub-Division | Allied works for Augmentation of KAITY W/S Scheme under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000345/2023-2024 | 3034/BWD | 14/07/2023 | 90 | SK ALIM | 122.65 | 0 | 100
1069 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
1070 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Kaity W/S Scheme under Raina-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.16. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000505/2021-2022 | 191/BSD | 31/01/2022 | 30 | RADIANT | 3.43 | 0 | 1
1071 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of KAITY & its adjoining mouzas Piped Water Supply Scheme, Block - Raina - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000538/2022-2023 | 5026/BWD | 10/11/2022 | 30 | M/S D. PALIT & CO. | 10.06 | 0 | 1
1072 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 3rd TW Site of Aug. KAITY & its adjoining mouzas Piped Water Supply Scheme, Block ¿ Raina ¿ II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000569/2022-2023 | 5281/BWD | 01/12/2022 | 30 | MUNSHI ENTERPRISE | 11.34 | 0 | 0
1073 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for KAITY its Adjoining Mouza W/S Scheme, Block -Raina-II within Burdwan Sub-Division, PHE Dte. (Mouza- DURGABATI) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000768/2022-2023 | 503/BSD | 21/03/2023 | 45 | DEBJYOTI GOSWAMI | 3.61 | 0 | 100
1074 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000190/2021-2022 | 1385/BWD | 09/03/2022 | 0 | Resource Division | 4.26 | 0 | 0
1075 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000228/2021-2022 | 1550/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
1076 | Burdwan Division | Burdwan Sadar Sub-Division | Quotation for shifting of 25 KVA DTR along with 11 KV HTOH Kaity Feeder at Kaity PHE campus under Madhabdihi-CCC. [Ref Id-860252403] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | VCH/000627/2022-2023 | 726/DW/22-23 | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.71 | 0 | 0
1077 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
1078 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring of Tube Well No- 01 & 02 at Augmentation Kaity [Block ¿Raina-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000918/2022-2023 | 1082/CMD | 03/03/2023 | 30 | JOYGURU ENTERPRISE | 12.31 | 0 | 100
1079 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of Electro-mechanical accessories at Kaity PH-1 (replacement T.W) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000993/2023-2024 | 4352/CMD | 20/09/2023 | 30 | MITRA ENTERPRISE | 3.28 | 0 | 100
1080 | Burdwan Division | Katwa Sub-Division | Quotation from WBSEDCL for additional T/W at Jaggeswardihi w/s scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | BILL/00895/2024-2025 | 1035/JJM | 25/10/2024 | 0 | WBSEDCL | 3.22 | 0 | 0
1081 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection from existing distribution system within the command area of JAGGESWARDIHI PWSS under Sitalgram village under Mongalkote Block within Katwa Sub-Division under Burdwan Division PHE Dte. | Assistant Engineer |  | ORD/000163/2022-2023 | 3150/BWD | 20/07/2022 | 30 | BAMDEB CONSTRUCTION & CO | 15.4 | 0 | 1
1082 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jageswardihi Piped Water Supply Scheme at Kaichar & Sitalgram Village (Mouza), Mongolkot Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000258/2021-2022 | 6694/BWD | 01/12/2021 | 60 | HAMID SK | 58.77 | 0 | 1
1083 | Burdwan Division | Katwa Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Mongalkote Block under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000407/2021-2022 | 284/BWD | 17/01/2022 | 30 | BABUL SK | 6.81 | 0 | 1
1084 | Burdwan Division | Katwa Sub-Division | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of JAGGESWARDIHI and its adjoining mouzas Piped Water Supply Scheme, Block Mongalkote, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000535/2022-2023 | 4959/BWD | 09/11/2022 | 30 | ANIRUDDHA FARUQUE | 13.08 | 0 | 1
1085 | Burdwan Division | Katwa Sub-Division | Surging of existing tube well at 1st , 2nd and 3rd Tube Well Site at Jaggeswardihi under Jaggeswardihi Piped Water Supply Scheme under Mongalkote Block under Katwa Sub-Division within Burdwan Division, P.H.E.Dte [Sl No-02] | Assistant Engineer |  | ORD/000594/2021-2022 | 149/KTS | 23/02/2022 | 15 | PARTHA PRATIM ACHARYA | 1.03 | 0 | 1
1086 | Burdwan Division | Katwa Sub-Division | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Jaggeswardihi village under Jaggeswardihi PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.. [Sl No-03] | Assistant Engineer |  | ORD/000606/2021-2022 | 170/KTS | 25/02/2022 | 7 | BABUL SK | 2.05 | 0 | 1
1087 | Burdwan Division | Katwa Sub-Division | Extension of pipe line at Kaichar Khane Para from the existing Distribution System within scheme jurisdiction under Jaggeswardihi PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-04] | Assistant Engineer |  | ORD/000607/2021-2022 | 171/KTS | 25/02/2022 | 15 | BABUL SK | 4.64 | 0 | 1
1088 | Burdwan Division | Katwa Sub-Division | Extension of pipe line at Kaichar Paschim Para from the existing Distribution System within scheme jurisdiction under Jaggeswardihi PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-06] | Assistant Engineer |  | ORD/000609/2021-2022 | 173/KTS | 25/02/2022 | 15 | BABUL SK | 4.67 | 0 | 1
1089 | Burdwan Division | Katwa Sub-Division | Extension of pipeline from the existing distribution system within scheme jurisdiction at Kanaidanga under Jaggeswardihi piped water supply scheme under Mongalkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-2] | Assistant Engineer |  | ORD/000830/2020-2021 | 82/KTS | 09/02/2021 | 15 | HAMID SK | 1.25 | 0 | 1
1090 | Burdwan Division | Katwa Sub-Division | Construction of Pump House, Boundary walls and Raising Main for Aug. of JAGGESWARDIHI Piped Water Supply Scheme under Mongalkote Block, District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/000922/2023-2024 | 5494/BWD | 13/12/2023 | 385 | PAPRI HAZRA | 10.13 | 0 | 75
1091 | Burdwan Division | Katwa Sub-Division | Providing FHTC (151 Nos.) of the left out house hold at Ichak habitation including Laying of pipe line from the existing Distribution System within the command area of JAGGESWARDIHI Piped Water Supply Scheme at Mangalkote Block under Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001121/2024-2025 | 495/BWD | 28/01/2025 | 30 | ABDUL HAI | 8.3 | 0 | 0
1092 | Burdwan Division | Katwa Sub-Division | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Chanak village under Kashiara PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. _2nd Call [Sl No-01] | Assistant Engineer |  | ORD/000076/2022-2023 | 319/KTS | 25/04/2022 | 21 | ASMA ENTERPRISE | 0.95 | 0 | 1
1093 | Burdwan Division | Katwa Sub-Division | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Gopalbera village under KASIYARA PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl - 1] | Assistant Engineer |  | ORD/000158/2021-2022 | 661/KTS | 28/09/2021 | 15 | MAJUMDER ENTERPRISE | 1.26 | 0 | 1
1094 | Burdwan Division | Katwa Sub-Division | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Kasiyara and Dirghyasoya village under KASIYARA PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl - 2] | Assistant Engineer |  | ORD/000159/2021-2022 | 662/KTS | 28/09/2021 | 15 | MAJUMDER ENTERPRISE | 4.56 | 0 | 1
1095 | Burdwan Division | Katwa Sub-Division | Extention of pipe line for providing FHTC from existing Distribuation System within scheme jurisdiction in Kashiara Piped Water Supply Scheme at Gotishta Village within Katwa Sub-Division under Burdwan Division PHE Dte. (Sl -3) | Assistant Engineer |  | ORD/000160/2021-2022 | 663/KTS | 28/09/2021 | 15 | MAJUMDER ENTERPRISE | 4.84 | 0 | 1
1096 | Burdwan Division | Katwa Sub-Division | Connection of CGWB Tube well Raising Main Line of Head Work Site of Kashiyara Piped Water Supply Scheme within Katwa Sub-Division under Burdwan Division, P.H.E. Dte. (Sl No-1) | Assistant Engineer |  | ORD/000162/2021-2022 | 635/KTS | 20/09/2021 | 15 | ASMA ENTERPRISE | 0.92 | 0 | 1
1097 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection at Gopalbera , Gotistha, dirghesoa habitation of Gopalbera , Gotistha, Kashiara village of Chanak and Gotistha G.P. from existing distribution system within the command area of Kashiara PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-01) | Assistant Engineer |  | ORD/000590/2021-2022 | 127/KTS | 21/02/2022 | 30 | TAPAS KUMAR ROY | 4.83 | 0 | 1
1098 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 1
1099 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/06/2024 to 31/07/2024) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000184/2024-2025 | 411/DSD | 28/05/2024 | 61 | SUJAUDDIN SEKH | 0.8 | 0 | 0
1100 | Burdwan Division | Durgapur Sub-DIvision | KARATIA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000368/2023-2024 | 3082/BWD | 18/07/2023 | 898 | BANSBERIA CONSTRUCTION CO. | 578.76 | 0 | 95
1101 | Burdwan Division | Durgapur Sub-DIvision | Continuation work for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-II) on hire basis for the office of the assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE.Govt. of West Bengal (for the period of December'2023 to May'2024) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000971/2023-2024 | 877/DSD | 30/11/2023 | 183 | SUJAUDDIN SEKH | 0.87 | 0 | 50
1102 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000030/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 4.22 | 0 | 0
1103 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000315/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.44 | 0 | 0
1104 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000633/2023-2024 | 4875/BWD | 10/11/2023 | 0 | Resource Division | 25.7 | 0 | 0
1105 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Karatia PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00961/2023-2024 | BP-2023-24-117 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.9 | 0 | 0
1106 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Karatia PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01465/2023-2024 | BP-2023-24-161 | 18/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.19 | 0 | 0
1107 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Karatia Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000233/2023-2024 | 3172/CMD | 26/07/2023 | 30 | C.M. ENTERPRISE | 27.12 | 0 | 96
1108 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0
1109 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA, BALABATI, UKHRID & RUPSA Piped Water Supply Scheme under KHANDAGHOSH Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000008/2023-2024 | 1726/BWD | 13/04/2023 | 902 | S.P. CONSTRUCTION | 1710.27 | 0 | 45
1110 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000082/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 31.25 | 0 | 0
1111 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000165/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 12.6 | 0 | 0
1112 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000736/2023-2024 | 5234/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
1113 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Ukhrid W/S Scheme PH-II. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01810/2023-2024 | BP-2023-24-304 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.29 | 0 | 0
1114 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at UKHRID W/S Scheme PH-I. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01816/2023-2024 | BP-2023-24-303 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.54 | 0 | 0
1115 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0
1116 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Ukhrid Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000708/2023-2024 | 4019/CMD | 29/08/2023 | 30 | C.M. ENTERPRISE | 28.88 | 0 | 100
1117 | Burdwan Division | Kalna Sub-division | Alt&ment of Fund due to damaged causes by PHED pipe tine work in connection with the work namely Construction of road from Jamna Samabay Samiti on PWD (Roads) to Moynampur more on Memari- Monteswar PWD Road via Dheuchanda, Katsihi Village under Monteswar Block in the District Purba Bardhaman under RIDF-XXVI¦I | Assistant Engineer | JUNIOR ENGINEER | BILL/00950/2024-2025 | 1051/JJM | 05/11/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 10.97 | 0 | 0
1118 | Burdwan Division | Kalna Sub-division | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/08/2024 to 30/09/2024) | Assistant Engineer | JUNIOR ENGINEER | ORD/000552/2024-2025 | 602/DSD | 30/07/2024 | 61 | SUJAUDDIN SEKH | 0.8 | 0 | 100
1119 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BELENDA, JAMNA, PIPLON & PARGUNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000689/2023-2024 | 4388/BWD | 05/10/2023 | 667 | AKASH CONSTRUCTION | 2296.4 | 0 | 50
1120 | Burdwan Division | Kalna Sub-division | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/10/2024 to 30/11/2024) | Assistant Engineer | JUNIOR ENGINEER | ORD/000839/2024-2025 | 772/DSD | 18/09/2024 | 61 | SUJAUDDIN SEKH | 0.8 | 0 | 0
1121 | Burdwan Division | Kalna Sub-division | Balance work for laying of pipeline, providing FHTC & other allied works in connection with Augmentation of MONTESWAR PWSS & SUTRA PWSS (SM/13280) under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000980/2024-2025 | 3572/BWD | 27/09/2024 | 181 | BAKSHI ENTERPRISE | 51.14 | 0 | 30
1122 | Burdwan Division | Kalna Sub-division | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/12/2024 to 31/12/2024) | Assistant Engineer | JUNIOR ENGINEER | ORD/000994/2024-2025 | 992/DSD | 25/11/2024 | 61 | SUJAUDDIN SEKH | 0.4 | 0 | 0
1123 | Burdwan Division | Kalna Sub-division | Supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/02/2025 to 31/03/2025) | Assistant Engineer | JUNIOR ENGINEER | ORD/001508/2024-2025 | 142/DSD | 24/01/2025 | 59 | SK ALACK JANDER | 0.8 | 0 | 0
1124 | Burdwan Division | Kalna Sub-division | Continuation for Supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/04/2025 to 31/05/2025) | Assistant Engineer | JUNIOR ENGINEER | ORD/001513/2024-2025 | 483/DSD | 21/03/2025 | 61 | SK ALACK JANDER | 0.8 | 0 | 0
1125 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000290/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 5.72 | 0 | 0
1126 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000542/2023-2024 | 4307/BWD | 29/09/2023 | 0 | Resource Division | 78.8 | 0 | 0
1127 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000784/2023-2024 | 329/BWD | 24/01/2024 | 0 | Resource Division | 36.64 | 0 | 0
1128 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR JAMNA PWSS. | Assistant Engineer | JUNIOR ENGINEER | BILL/02691/2023-2024 | BP-2023-24-572 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.32 | 0 | 0
1129 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR JAMNA PWSS TW -2. | Assistant Engineer | JUNIOR ENGINEER | BILL/03106/2023-2024 | BP-2023-24-646 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.48 | 0 | 0
1130 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
1131 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Jamna Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000738/2023-2024 | 4048/CMD | 29/08/2023 | 703 | MS DAS ELECTRIC CO | 29.95 | 0 | 50
1132 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for SATINANDI Piped Water Supply Scheme with INSTALLATION OF BARBED WIRE, FHTC ,Road restoration ,DEMOLITION WORK & land development with road at TW site under Galsi-II Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000183/2024-2025 | 1620/DWSD | 26/11/2024 | 326 | A K SIKDAR | 79.05 | 0 | 70
1133 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Sinking of 300 x 200 mm dia tube well 150 mtr depth by DR Rig method for trial bore at Tetulmari & Golgram under Satinandi PWSS (JJM), Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000185/2024-2025 | 1596/DWSD | 25/11/2024 | 20 | S & P ENTERPRISE | 7.5 | 0 | 60
1134 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000018/2024-2025 | 1724/A/DWSD | 10/12/2024 | 0 | Resource Division | 0.31 | 0 | 0
1135 | Burdwan Division | Durgapur Sub-DIvision | SATINANDI Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Burdwan-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000584/2022-2023 | 5520/BWD | 23/12/2022 | 365 | MD HASIN | 389.47 | 0 | 40
1136 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000075/2022-2023 | 1264/BWD | 17/03/2023 | 0 | Resource Division | 8.15 | 0 | 0
1137 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000497/2023-2024 | 4021/BWD | 08/09/2023 | 0 | Resource Division | 1.24 | 0 | 0
1138 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000600/2023-2024 | 4906/BWD | 10/11/2023 | 0 | Resource Division | 33.07 | 0 | 0
1139 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges of Satinandi Water Supply Scheme TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00674/2023-2024 | BP-2023-24-25 | 21/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.08 | 0 | 0
1140 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges of Satinandi Water Supply Scheme TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00675/2023-2024 | BP-2023-24-26 | 21/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.05 | 0 | 0
1141 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Satinandi Water Supply Scheme [ Block- Galsi-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000044/2023-2024 | 2496/CMD | 01/06/2023 | 30 | DEY ENTERPRISE | 27.74 | 0 | 50
1142 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
1143 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-09-2024 to 30-11-2024 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000682/2024-2025 | 1957/BSD | 30/08/2024 | 91 | SK. ASFIA | 1.2 | 0 | 60
1144 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 183 | SK.ASFIA | 2.4 | 0 | 70
1145 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of concrete road by Cement concrete (mix 1:1.5:3),Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for DURGADANGA SVS & DEHA PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001039/2024-2025 | 141/BWD | 08/01/2025 | 90 | MUKHERJEE ENTERPRISE | 64.37 | 0 | 0
1146 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for Supply of one No.Diesel Driven Ambassador Car No. WB:41H-4009 on hire basis for the office of the Assistant Engineer,Burdwan Sub-Division,PHE Dte(Period from 01-03-2025 to 31.05.2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001407/2024-2025 | 457/BSD | 28/02/2025 | 90 | SK. ASFIA | 1.2 | 0 | 100
1147 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000238/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.9 | 0 | 0
1148 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000463/2023-2024 | 3987/BWD | 08/09/2023 | 0 | Resource Division | 4.94 | 0 | 0
1149 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000664/2023-2024 | 5103/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1150 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new electric service connection at Deha PH NO.-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01737/2023-2024 | BP-2023-24-241 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.48 | 0 | 0
1151 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new electric service connection at Deha PH NO.-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01738/2023-2024 | BP-2023-24-242 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0
1152 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DEHA Water Supply Scheme [ Block- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000807/2023-2024 | 4092/CMD | 29/08/2023 | 491 | ORIENTAL ENGINEERING CO. | 29.39 | 0 | 100
1153 | Burdwan Division | Kalna Sub-division | HARIPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000774/2022-2023 | 1340/BWD | 22/03/2023 | 373 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 94.46 | 0 | 100
1154 | Burdwan Division | Kalna Sub-division | Refitting & Re-fixing of Existing FHTC along with laying of damaged portion Pipeline Due to construction of Concrete Drain by PRI body at Haripur (SM/13315) Piped Water Supply Scheme water supply scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000999/2024-2025 | 4619/BWD | 31/12/2024 | 30 | MONDAL & CO. | 9.67 | 0 | 100
1155 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000152/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 10.75 | 0 | 0
1156 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000521/2023-2024 | 4284/BWD | 29/09/2023 | 0 | Resource Division | 0.55 | 0 | 0
1157 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000599/2023-2024 | 4905/BWD | 10/11/2023 | 0 | Resource Division | 4.86 | 0 | 0
1158 | Central Mechanical | Kalna Sub-division | New service connection charges for Haripur PWSS TW-1 | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | BILL/00820/2023-2024 | BP-2023-24-97 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.02 | 0 | 0
1159 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 30
1160 | Central Mechanical | Kalna Sub-division | Supply and Delivery of standby pump motor set for Sipta, Uchitpur, Haripur & others Water Supply Scheme under CMD, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000142/2024-2025 | 2596/CMD | 27/08/2024 | 30 | JOYGURU ENTERPRISE | 4.72 | 0 | 100
1161 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at HARIPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000164/2023-2024 | 2931/CMD | 12/07/2023 | 30 | ASHIM UDYOG | 20.77 | 0 | 30
1162 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000042/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 37.35 | 0 | 0
1163 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000178/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 20.14 | 0 | 0
1164 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR NIRALGACHI PWSS TW-I | Assistant Engineer | JUNIOR ENGINEER | BILL/00106/2024-2025 | BP-2024-25-42 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.14 | 0 | 0
1165 | Central Mechanical | Kalna Sub-division | Quotation for new service connection at Niralgachi PWSS TW-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/00663/2024-2025 | BP-2024-25-265 | 20/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.28 | 0 | 0
1166 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0
1167 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Niralgachhi Water Supply Scheme [ Block- KALNA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000759/2023-2024 | 4061/CMD | 29/08/2023 | 644 | M/S, S.S. ENTERPRISE. | 27.79 | 0 | 90
1168 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PASCHIM KHARAMPUR, SHUSHNA & SIGHNALI Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000482/2023-2024 | 3494/BWD | 09/08/2023 | 783 | S.P. CONSTRUCTION | 1925.07 | 0 | 80
1169 | Burdwan Division | Durgapur Sub-DIvision | Providing FHTC with laying of 90 mm dia HDPE Pipe of Susunia PWSS under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001161/2023-2024 | 266/DSD | 15/03/2024 | 30 | PRONAB KUMAR DEY | 0.95 | 0 | 0
1170 | Burdwan Division | Durgapur Sub-DIvision | Providing FHTC with laying of 90 mm dia HDPE Pipe of Susunia PWSS of kalsar village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001162/2023-2024 | 267./DSD | 15/03/2024 | 382 | PRONAB KUMAR DEY | 0.97 | 0 | 100
1171 | Burdwan Division | Durgapur Sub-DIvision | Providing FHTC with laying of 90 mm dia HDPE Pipe of Susunia PWSS of Kuli village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001163/2023-2024 | 269/DSD | 15/03/2024 | 30 | SOUMYAVASH DAS | 0.94 | 0 | 0
1172 | Burdwan Division | Durgapur Sub-DIvision | Construction of valve chamber HD works site and installation of sluice valve at Budpur village of Susunia PWSS under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001164/2023-2024 | 268./DSD | 15/03/2024 | 30 | PRONAB KUMAR DEY | 0.94 | 0 | 0
1173 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000319/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.94 | 0 | 0
1174 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000455/2023-2024 | 3979/BWD | 08/09/2023 | 0 | Resource Division | 32.04 | 0 | 0
1175 | Central Mechanical | Durgapur Sub-DIvision | New service at Shushna PWSS TW-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02291/2023-2024 | BP-2023-24-440 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.03 | 0 | 0
1176 | Central Mechanical | Durgapur Sub-DIvision | New Service connection at SHUSHNA PWSS TW-1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02359/2023-2024 | BP-2023-24-481 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.48 | 0 | 0
1177 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
1178 | Central Mechanical | Durgapur Sub-DIvision | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000590/2024-2025 | 3105/CMD | 11/12/2024 | 60 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0
1179 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Shushna Water Supply Scheme [ Block- MONTESWAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000761/2023-2024 | 4062/CMD | 29/08/2023 | 30 | ORIENTAL ENGINEERING CO. | 28.97 | 0 | 80
1180 | Burdwan Division | Burdwan Sadar Sub-Division | BAHIRSARBAMANGALA-B Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000107/2023-2024 | 2298/BWD | 19/05/2023 | 365 | MLG CONSTRUCTION | 308.66 | 0 | 0
1181 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000202/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.95 | 0 | 0
1182 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000508/2023-2024 | 4032/BWD | 08/09/2023 | 0 | Resource Division | 6.34 | 0 | 0
1183 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000646/2023-2024 | 5095/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1184 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bahir Sarbamangala-B Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001049/2023-2024 | 4046/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 29.34 | 0 | 0
1185 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENUA, IBRAMBAD & UJNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000462/2023-2024 | 3456/BWD | 08/08/2023 | 855 | M/S S. CHOUDHURY | 2123.7 | 0 | 20
1186 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000278/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 3.02 | 0 | 0
1187 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000454/2023-2024 | 3978/BWD | 08/09/2023 | 0 | Resource Division | 32.08 | 0 | 0
1188 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000520/2023-2024 | 4052/BWD | 11/09/2023 | 0 | Resource Division | 3.03 | 0 | 0
1189 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000780/2023-2024 | 323/BWD | 24/01/2024 | 0 | Resource Division | 34.15 | 0 | 0
1190 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new electric service connection at Ibrambad PH NO.-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01749/2023-2024 | BP-2023-24-249 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.13 | 0 | 0
1191 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR IBRAMBAD PWSS. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02690/2023-2024 | BP-2023-24-573 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.51 | 0 | 0
1192 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
1193 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Ibrambad Water Supply Scheme [ Block- Monteswar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000765/2023-2024 | 4064/CMD | 29/08/2023 | 30 | M/S. S.R. ENTERPRISE | 28.96 | 0 | 90
1194 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Balance work for NIRSINHAPUR Piped Water Supply Scheme i.e , Construction work LDS, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway etc. at 3rd Pump house site under AUSGRAM-II Block, District:- Purba-Bardhaman, under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000184/2024-2025 | 1594/DWSD | 25/11/2024 | 367 | KIRON ENTERPRISE | 59.79 | 0 | 65
1195 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000019/2024-2025 | 1724/D/DWSD | 10/12/2024 | 0 | Resource Division | 2 | 0 | 0
1196 | Burdwan Division | Durgapur Sub-DIvision | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways for NRISINHAPUR Piped Water Supply Scheme under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000353/2023-2024 | 3066/BWD | 17/07/2023 | 624 | M/S H.R. CONSTRUCTION | 401.37 | 0 | 50
1197 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000206/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.86 | 0 | 0
1198 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000450/2023-2024 | 3974/BWD | 08/09/2023 | 0 | Resource Division | 1.93 | 0 | 0
1199 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000598/2023-2024 | 4904/BWD | 10/11/2023 | 0 | Resource Division | 33.07 | 0 | 0
1200 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Nrisinhapur PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00823/2024-2025 | BP-2024-25-318 | 30/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.63 | 0 | 0
1201 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Nrisinhapur PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01826/2023-2024 | BP-2023-24-328 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.56 | 0 | 0
1202 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at NRISINHAPUR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000820/2023-2024 | 4097/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 28.96 | 0 | 48
1203 | Durgapur W/S Division | Durgapur Sub-DIvision | ACCEPTANCE CUM FORMAL WORK ORDER FOR Supplying, delivery, Installation of 13 (Thirteen) Nos new PC and upgradation 6 (Six) Nos existing PC including providing other asseries as per office requirement for JJM works under Durgapur W/s Division, PHE Dte under Jaykrishnapur PWSS,Aligram PWSS,Jadabganj PWSS and Kalyanpur PWSS. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000237/2024-2025 | 59/DWSD | 10/01/2025 | 45 | DIGITEK SOLUTIONS | 17.56 | 0 | 85
1204 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000727/2023-2024 | 4581/BWD | 16/10/2023 | 965 | SAFECO ENTERPRISES | 1551.98 | 0 | 60
1205 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000024/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 39.22 | 0 | 0
1206 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000292/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 6.23 | 0 | 0
1207 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000776/2023-2024 | 200/BWD | 10/01/2024 | 0 | Resource Division | 7.26 | 0 | 0
1208 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0
1209 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0
1210 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JAYKRISHNAPUR Water Supply Scheme [ Block- AUSGRAM-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000810/2023-2024 | 4094/CMD | 29/08/2023 | 588 | MS S G ENTERPRISE | 27.68 | 0 | 96
1211 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to UCHALAN, CHAK CHANDAN, SERPUR & KATNABIL Piped Water Supply Scheme under Raina II Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000367/2023-2024 | 3076/BWD | 18/07/2023 | 988 | SK ALIM | 1307.56 | 0 | 75
1212 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related(schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-02-2025 to 30-04-2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001402/2024-2025 | 240/BSD | 31/01/2025 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
1213 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000301/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.9 | 0 | 0
1214 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000483/2023-2024 | 4007/BWD | 08/09/2023 | 0 | Resource Division | 2.05 | 0 | 0
1215 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000692/2023-2024 | 5073/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1216 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR SERPUR PWSS PH-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/00107/2024-2025 | BP-2024-25-43 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.23 | 0 | 0
1217 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Serpur W/S Scheme PH No.-I | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01797/2023-2024 | BP-2023-24-301 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0
1218 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
1219 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Serpur Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000651/2023-2024 | 3994/CMD | 29/08/2023 | 549 | S.P. CONSTRUCTION | 28.92 | 0 | 80
1220 | Burdwan Division | Durgapur Sub-DIvision | Restoration of damaged flanks due to laying of HDPE pipe line along the flank of Burdwan Katwa Road from 14.70 kmp to 16.20 kmp in the district of Purba Bardhaman under Bardhaman Division,P.W.D. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00711/2024-2025 | 867/JJM | 23/09/2024 | 0 | EXECUTIVE ENGINEER PWD BURDWAN DIVISION | 7.9 | 0 | 0
1221 | Burdwan Division | Durgapur Sub-DIvision | Vehicle bill (Car No.-WB-41H-3668) for the month of July to September'2023. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/01679/2023-2024 | 1142/JJM | 29/12/2023 | 0 | MD HASIN | 0.86 | 0 | 0
1222 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ORGRAM Piped Water Supply Scheme & Sibda Colony habitation, Bhatar Block under Burdwan Division, PHE Dte.(Agreement No. 59/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000123/2020-2021 | 4886/BWD | 07/12/2020 | 90 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 97.01 | 0 | 1
1223 | Burdwan Division | Durgapur Sub-DIvision | Extension of distribution main for providing FHTC at Shalkuni village within Orgram W/S Scheme (Zone-II) in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000288/2021-2022 | 717/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 3.62 | 0 | 1
1224 | Burdwan Division | Durgapur Sub-DIvision | Extension of distribution main for providing FHTC at Shilakot village within Orgram W/S Scheme (Zone-II) in Bhatar Block under Burdwan Division, P.H.E. Dte.[Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000289/2021-2022 | 718/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 3.15 | 0 | 1
1225 | Burdwan Division | Durgapur Sub-DIvision | Extension of distribution main for providing FHTC at Shikarpur village within Orgram W/S Scheme (Zone-II) in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000290/2021-2022 | 719/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 3.28 | 0 | 1
1226 | Burdwan Division | Durgapur Sub-DIvision | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ORGRAM Piped Water Supply Scheme at Salkuni, Orgram (10 Nos Habitation), & Silakote Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte._2ND CALL.(Agreement no. 102/SE/CC/PHE/Dte of 2020-2021) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000424/2020-2021 | 1086/BWD | 08/02/2021 | 90 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 81.92 | 0 | 1
1227 | Burdwan Division | Durgapur Sub-DIvision | Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for Orgram (Zone-I) & it's adjoining mouzas W/S. scheme under Burdwan Division, P.H.E. Dte.Ref. Drawing No.PC-I/OHR/7/2012 Dated 07.06.2012. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000448/2021-2022 | 764/BWD | 07/02/2022 | 180 | S.N. ENTERPRISE | 67.98 | 0 | 0
1228 | Burdwan Division | Durgapur Sub-DIvision | Shifting and relaying of Distribution system and Rising main at OHR site of Orgram Piped W/S Scheme (Zone-II) at Bhatar Block under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000566/2023-2024 | 655/DSD | 24/08/2023 | 30 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0
1229 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline at Bagmara village of Orgram (Z-II) and its adjoining mouzas piped water supply scheme at Bhatar Block within Burdwan Sadar Sub-Division, under Burdwan Division, PHE Dte.[Gr.-G] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000781/2021-2022 | 952/BSD | 23/07/2021 | 30 | M/S S. CHOUDHURY | 2.01 | 0 | 1
1230 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PASCHIM KHARAMPUR, SHUSHNA & SIGHNALI Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000482/2023-2024 | 3494/BWD | 09/08/2023 | 783 | S.P. CONSTRUCTION | 1925.07 | 0 | 80
1231 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000365/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 14.14 | 0 | 0
1232 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000452/2023-2024 | 3976/BWD | 08/09/2023 | 0 | Resource Division | 103.5 | 0 | 0
1233 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000781/2023-2024 | 324/BWD | 24/01/2024 | 0 | Resource Division | 92.56 | 0 | 0
1234 | Central Mechanical | Durgapur Sub-DIvision | New service Paschim Kharapur PWSS TW-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02290/2023-2024 | BP-2023-24-441 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.93 | 0 | 0
1235 | Central Mechanical | Durgapur Sub-DIvision | New Service connection at PASCHIM KHARAMPUR PWSS TW-1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02360/2023-2024 | BP-2023-24-479 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.89 | 0 | 0
1236 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
1237 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Paschim Kharampur Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000739/2023-2024 | 4049/CMD | 29/08/2023 | 609 | MITRA ENTERPRISE | 29.57 | 0 | 85
1238 | Burdwan Division | Central Mechanical Sub-Division | Different types of works involve in connection with Augmentation of DIRGHAPARA (SM/07804) Water Supply Scheme, MOUDANGA (SM/ 14020) Water supply Scheme & BHANDARTIKURI (SM/14925) Water Supply Scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000357/2024-2025 | 2912/BWD | 25/07/2024 | 431 | BANSBERIA CONSTRUCTION CO. | 293.38 | 0 | 22
1239 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NAMA BHANDARITURI, SAHAPUR & MOUDANGA Piped Water Supply Scheme under PURBASTHALI-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000511/2023-2024 | 3689/BWD | 23/08/2023 | 770 | THE MAHADEV CONSTRUCTION | 734.18 | 0 | 50
1240 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000346/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 14.15 | 0 | 0
1241 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000511/2023-2024 | 4035/BWD | 08/09/2023 | 0 | Resource Division | 1.38 | 0 | 0
1242 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000804/2023-2024 | 305/BWD | 24/01/2024 | 0 | Resource Division | 17.52 | 0 | 0
1243 | Central Mechanical | Central Mechanical Sub-Division | New service connection for Moudanga PH-1 PWSS. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00089/2024-2025 | BP-2024-25-28 | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.45 | 0 | 0
1244 | Central Mechanical | Central Mechanical Sub-Division | New service connection for MOUDANGA PWSS | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/02562/2023-2024 | BP-2023-24-546 | 19/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.78 | 0 | 0
1245 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 30
1246 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MOUDANGA Water Supply Scheme [ Block- PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000829/2023-2024 | 4106/CMD | 29/08/2023 | 581 | WEST BENGAL ENGINEERING CO. | 26.95 | 0 | 50
1247 | Burdwan Division | Burdwan Sadar Sub-Division | DURGADANGA Single Village Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000010/2023-2024 | 1714/BWD | 12/04/2023 | 90 | A R TRADERS | 57.63 | 0 | 100
1248 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall at HEAD WORK Site & 2nd TW site & Culvert at Head work site & Interconnection between Head work site distribution line 2nd Tw site of DURGADANGA Piped Water Supply Scheme under MEMARI-I Block of Burdwan Division, PHE Dte. (Length -164.00 Mtr, Col-66 Nos). | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000321/2024-2025 | 2857/BWD | 22/07/2024 | 468 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 29.26 | 0 | 50
1249 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of Tube-well, construction of switch rooms & Rising main at 2ND TW site for DURGADANGA Piped Water Supply Scheme under MEMARI-I Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000868/2023-2024 | 5307/BWD | 01/12/2023 | 60 | A R TRADERS | 21.69 | 0 | 100
1250 | Burdwan Division | Burdwan Sadar Sub-Division | Allied work of Laying distribution system for FHTC work for DURGADANGA Piped Water Supply Scheme at Durgadanga mouza within MEMARI - I Block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001017/2023-2024 | 521/BWD | 06/02/2024 | 30 | A R TRADERS | 13.36 | 0 | 100
1251 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of concrete road by Cement concrete (mix 1:1.5:3),Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for DURGADANGA SVS & DEHA PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001039/2024-2025 | 141/BWD | 08/01/2025 | 90 | MUKHERJEE ENTERPRISE | 64.37 | 0 | 0
1252 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000186/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 10.35 | 0 | 0
1253 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000411/2023-2024 | 3869/BWD | 01/09/2023 | 0 | Resource Division | 8.83 | 0 | 0
1254 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000749/2023-2024 | 5250/BWD | 30/11/2023 | 0 | Resource Division | 20.21 | 0 | 0
1255 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Durgadanga PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01262/2023-2024 | BP-2023-24-122 | 17/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.07 | 0 | 0
1256 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR DURGADANGA PWSS | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/02838/2023-2024 | BP-2023-24-587 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.12 | 0 | 0
1257 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0
1258 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Durgadanga Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000139/2023-2024 | 2820/CMD | 04/07/2023 | 30 | C.M. ENTERPRISE | 29.33 | 0 | 95
1259 | Burdwan Division | Durgapur Sub-DIvision | MARO Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000175/2023-2024 | 2569/BWD | 01/06/2023 | 120 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 113.32 | 0 | 90
1260 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells at Maro Dakshin Para, LDSs, Interconnections, FHTCs, Construction of MARO Piped Water Supply Scheme for obstruction of Railway under Galsi-I Block, of Durgapur Sub Division, under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000334/2024-2025 | 2895/BWD | 23/07/2024 | 371 | PREMANANDA ROY BISWAS | 42.93 | 0 | 90
1261 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000027/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.65 | 0 | 0
1262 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000340/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7 | 0 | 0
1263 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000605/2023-2024 | 4910/BWD | 10/11/2023 | 0 | Resource Division | 12.78 | 0 | 0
1264 | Central Mechanical | Durgapur Sub-DIvision | New service connection for MARO PWSS, PG-1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02485/2023-2024 | BP-2023-24-537 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.06 | 0 | 0
1265 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
1266 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MARO Water Supply Scheme [ Block- GALSI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000903/2023-2024 | 4167/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 28.54 | 0 | 48
1267 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHARKHI & SHIBNUL Piped Water Supply Scheme under KETUGRAM-II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000049/2023-2024 | 1823/BWD | 18/04/2023 | 1293 | PASCON | 723.75 | 0 | 35
1268 | Burdwan Division | Central Mechanical Sub-Division | Balance work for OHR, extension of pipeline to provide FHTC with land development, plinth protection for pump house & OHR under Charkhi PWSS, Block-Ketugram-II under Katwa Sub Division within Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000312/2024-2025 | 2836/BWD | 19/07/2024 | 835 | PASCON | 74.08 | 0 | 90
1269 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000488/2023-2024 | 4012/BWD | 08/09/2023 | 0 | Resource Division | 0.69 | 0 | 0
1270 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000622/2023-2024 | 4880/BWD | 10/11/2023 | 0 | Resource Division | 29.6 | 0 | 0
1271 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000770/2023-2024 | 194/BWD | 10/01/2024 | 0 | Resource Division | 9.75 | 0 | 0
1272 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Charkhi PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/00880/2023-2024 | BP-2023-24-110 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.25 | 0 | 0
1273 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new electric service connection at Charki PWSS TW No-1 | Assistant Engineer | Junior Engineer | BILL/01744/2023-2024 | BP-2023-24-251 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0
1274 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0
1275 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHARKHI Water Supply Scheme [ Block- KETUGRAM-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000391/2023-2024 | 3663/CMD | 01/08/2023 | 670 | AHALYA ENGINEERING WORKS | 27.78 | 0 | 48
1276 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-C) [SL. No. : 11] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000031/2021-2022 | 3408/BWD | 25/06/2021 | 15 | N.S. ENTERPRISE | 4.86 | 0 | 1
1277 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC for Dogachia Mouza [(Habitation (Village)] for AMRA piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000068/2023-2024 | 2019/BWD | 28/04/2023 | 30 | DEY NIRMAN | 20.61 | 0 | 100
1278 | Burdwan Division | Burdwan Sadar Sub-Division | BALANCE PORTION Boundary wall at 3RD Tubewell site Of Jaugram Water Supply scheme under JAMALPUR Block of Burdwan Division, PHE Dte. (LENGTH- 34.0M , COL- 14 NOS) GROUP : G | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000086/2022-2023 | 820/BSD | 20/05/2022 | 45 | MUKHERJEE ENTERPRISE | 3.3 | 0 | 1
1279 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of 100 mm dia D.I Pipe for Road widening from 4 lane to 6 lane of NH2 at chainage 599+654 & 599+154 at Jougram Water supply within Jamalpur Block,under Burdwan Division,PHE Dte". Group : B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000109/2022-2023 | 981/BSD | 16/06/2022 | 30 | PRATIVA CONSTRUCTION | 2.97 | 0 | 0
1280 | Burdwan Division | Burdwan Sadar Sub-Division | Repairing and Restoration of damaged and chokaged various Dia UPVC Pipeline and Construction of Valve Chambers to conrrol flow of waer for providing FHTC in JOUGRAM PWSS at Jamalpur Dev.block under Burdwan Division,PHE Dte.Group : D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000112/2022-2023 | 1017/BSD | 20/06/2022 | 30 | MUKHERJEE ENTERPRISE | 1.43 | 0 | 1
1281 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of pipeline for providing FHTC 100% coverage and also construction & installation of Sluice Valve & Valve Chamber to control the flow of water, road restoration work etc. of different Piped W/S Schemes, Block Jamalpur under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000194/2024-2025 | 2488/BWD | 01/07/2024 | 550 | M/S NATIONAL CONSTRUCTION | 480.97 | 0 | 80
1282 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jaugram Piped Water Supply Scheme at Jaugram Village (P) (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000278/2021-2022 | 6952/BWD | 14/12/2021 | 30 | SAIKAT RAY | 33.69 | 0 | 1
1283 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for providing functional house hold tap connection at Jougram village of Jougram piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte..Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000311/2021-2022 | 1033/BSD | 05/08/2021 | 30 | N.S. ENTERPRISE | 0.69 | 0 | 1
1284 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000345/2021-2022 | 40/BWD | 05/01/2022 | 30 | PREMANANDA ROY BISWAS | 22.68 | 0 | 1
1285 | Burdwan Division | Burdwan Sadar Sub-Division | Replacement of 775 meter AC pipeline by using UPVC pipeline in Jaugram piped water supply scheme at Jamalpur Block under Burdwan Division PHE Dte.Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000400/2021-2022 | 69/BSD | 14/01/2022 | 30 | MUKHERJEE ENTERPRISE | 4.83 | 0 | 1
1286 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-B) [SL. No. : 13] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000444/2020-2021 | 1398/BWD | 15/02/2021 | 15 | DEY NIRMAN | 4.84 | 0 | 0
1287 | Burdwan Division | Burdwan Sadar Sub-Division | Land Development at Jougram 4th T/W Site at Jamalpur Block under Burdwan Sub Division in Burdwan Division,PHE Dte. Gr.G. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000445/2022-2023 | 1487/BSD | 26/08/2022 | 30 | PANCHANAN CHAKROBORTY | 1.17 | 0 | 1
1288 | Burdwan Division | Burdwan Sadar Sub-Division | Replace damaged and chokaged various dia. A.C. Pipeline with UPVC pipes, construction of valve chambers and providing FHTC at mouza (Habitation) under JOUGRAM PWSS, Jamalpur Development Block of Burdwan Sub-Division under Burdwan Division, PHE Dte". Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000475/2022-2023 | 1599/BSD | 14/09/2022 | 30 | MUKHERJEE ENTERPRISE | 3.38 | 0 | 1
1289 | Burdwan Division | Burdwan Sadar Sub-Division | Concrete road at Head Work site Tubewell site of Jaugram Water Supply Scheme under JAMALPUR Block of Burdwan Division, PHE Dte. Gr.L | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000484/2022-2023 | 1608/BSD | 14/09/2022 | 15 | DUBE ENTERPRISE | 1.7 | 0 | 1
1290 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000592/2021-2022 | 1454/BWD | 11/03/2022 | 30 | PREMANANDA ROY BISWAS | 18.83 | 0 | 1
1291 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall at 3RD Tubewell site Of Jaugram Water Supply scheme under JAMALPUR Block of Burdwan Division, PHE Dte. (LENGTH- 70.0M , COL- 28 NOS ) Gr.E | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000649/2021-2022 | 470/BSD | 21/03/2022 | 45 | MUKHERJEE ENTERPRISE | 3.83 | 0 | 1
1292 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall at 4th Tubewell site Of Jaugram Water Supply scheme under JAMALPUR Block of Burdwan Division, PHE Dte. (LENGTH- 71.0M, COL.- 28 NOS )Gr.F. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000650/2021-2022 | 471/BSD | 21/03/2022 | 45 | PANCHANAN CHAKROBORTY | 3.77 | 0 | 1
1293 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ilsora village and Ilsora habitation of JAUGRAM Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿6A¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000779/2020-2021 | 3330/BWD | 18/09/2020 | 30 | MUKHERJEE ENTERPRISE | 4.86 | 0 | 1
1294 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Moyna Habitation of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [GROUP - 'B'] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/001346/2020-2021 | 2401/BWD | 20/07/2020 | 30 | DEY NIRMAN | 4.92 | 0 | 100
1295 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ilsora village and Ilsora habitation of JAUGRAM Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿6A¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/001347/2020-2021 | 4513/BWD | 12/11/2020 | 30 | MUKHERJEE ENTERPRISE | 4.86 | 0 | 100
1296 | Burdwan Division | Central Mechanical Sub-Division | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Ankhona, Pandugram, Sripur PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000286/2024-2025 | 2738/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 128.29 | 0 | 75
1297 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ANKHONA, PANDUGRAM & SRIPUR Piped Water Supply Scheme under KETUGRAM¿I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000436/2023-2024 | 3388/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 989.13 | 0 | 50
1298 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000093/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.29 | 0 | 0
1299 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000211/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 21.5 | 0 | 0
1300 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000643/2023-2024 | 5109/BWD | 23/11/2023 | 0 | Resource Division | 20.84 | 0 | 0
1301 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection Ankhona PWSS TW No. 2. | Assistant Engineer | Junior Engineer | BILL/00778/2024-2025 | BP-2024-25-294 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.38 | 0 | 0
1302 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection Ankhona PWSS TW No.1. | Assistant Engineer | Junior Engineer | BILL/00779/2024-2025 | BP-2024-25-293 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.99 | 0 | 0
1303 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
1304 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at ANKHONA Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000859/2023-2024 | 4127/CMD | 29/08/2023 | 30 | M/S, N.G. ENTERPRISES. | 27.75 | 0 | 0
1305 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Ankhona W/S Scheme (T/W-I & II) ,Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000167/2023-2024 | 1350/CDD | 13/09/2023 | 30 | ASHUTOSH DAS & CO | 16.59 | 0 | 0
1306 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout FHTC, Const. of Boundary Wall (HW Site & 2nd TW Site), Drain, Pathway and land development at Head Work site & 2nd TW Site (Replacement), Rising main connection of 2nd TW (Replacement) with necessary repairing work for SEHERA Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001017/2024-2025 | 63/BWD | 06/01/2025 | 90 | H SAMANTA | 41.78 | 0 | 0
1307 | Burdwan Division | Burdwan Sadar Sub-Division | Functional Household Tap Connection (FHTC) for Sehera, Mogolmari, Kona Krishnapur village for Augmentation of SEHERA Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001086/2023-2024 | 1112/BWD | 13/03/2024 | 60 | PAL CONSTRUCTION | 35.49 | 0 | 0
1308 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of Interconnection of Head work site New Tube well of Sehera Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001276/2023-2024 | 738/BSD | 20/04/2023 | 15 | M/S UNIT CONSTRUCTION | 0.95 | 0 | 100
1309 | Central Mechanical | Burdwan Sadar Sub-Division | Making illumination arrangement and mise works at Aug. of Sheherabazar water supply scheme RAINA-I BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000481/2024-2025 | 2952/CMD | 20/11/2024 | 233 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 17.51 | 0 | 30
1310 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of SEHERA( Part-B)[RAINA-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001076/2023-2024 | 4200/CMD | 29/08/2023 | 30 | AMUSAR IMPEX PVT. LTD. | 24.39 | 0 | 0
1311 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 09 Nos. Piped W/S. Schemes under Purbasthali II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000338/2024-2025 | 3018/BWD | 05/08/2024 | 50 | HORIZEN | 23.7 | 0 | 10
1312 | Burdwan Division | Kalna Sub-division | Augmentation of PURBASTHALI Surface Water Supply Scheme (ZONE-4B) with LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-II Block, District:- Purba-Bardhaman._2ND CALL | Assistant Engineer |  | ORD/000895/2023-2024 | 5371/BWD | 07/12/2023 | 570 | TAPAS KUMAR CHAKRABORTY & CO. | 819.09 | 0 | 5
1313 | Burdwan Division | Kalna Sub-division | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 51
1314 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000762/2023-2024 | 196/BWD | 10/01/2024 | 0 | Resource Division | 6.16 | 0 | 0
1315 | Burdwan Division | Central Mechanical Sub-Division | Augmentation of EKAIHAT Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & Construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-I Block, District:- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000174/2023-2024 | 3031/BWD | 14/07/2023 | 627 | HAMID SK | 130.08 | 0 | 100
1316 | Central Mechanical | Central Mechanical Sub-Division | QUOTATION FOR AUGMENTATION OF EKAIHAT PWSS TW-4 | Assistant Engineer | Junior Engineer | BILL/00664/2024-2025 | BP-2024-25-266 | 20/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.65 | 0 | 0
1317 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Ekaihat Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000090/2023-2024 | 2583/CMD | 07/06/2023 | 30 | M/S. S.R. ENTERPRISE | 22.38 | 0 | 0
1318 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMEGERIA, ARGUN, CHINISPUR & KULUTIA Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000533/2023-2024 | 3630/BWD | 21/08/2023 | 1107 | M/S GOUTAM DAS | 1421.7 | 0 | 75
1319 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000091/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.01 | 0 | 0
1320 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000741/2023-2024 | 5252/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0
1321 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000772/2023-2024 | 199/BWD | 10/01/2024 | 0 | Resource Division | 11.48 | 0 | 0
1322 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Amegeria PWSS PH-I. | Assistant Engineer | Junior Engineer | BILL/00343/2024-2025 | BP-2024-25-167 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.43 | 0 | 0
1323 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Amgoria PWSS TW 2. | Assistant Engineer | Junior Engineer | BILL/00445/2024-2025 | BP-2024-25-232 | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.65 | 0 | 0
1324 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
1325 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at AMEGERIA Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000902/2023-2024 | 4166/CMD | 29/08/2023 | 640 | M/S, S.DAS AND ENTERPRISE. | 28.48 | 0 | 88
1326 | Burdwan Division | Kalna Sub-division | Continual work order for " Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01/06/2025 to 31/08/2025] [Vehicle No-WB 04G 7127]". | Assistant Engineer | JUNIOR ENGINEER | ORD/000329/2025-2026 | 734/KSD | 30/05/2025 | 92 | PARTHA PRATIM ACHARYA | 1.2 | 0 | 0
1327 | Burdwan Division | Kalna Sub-division | Continuation work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection Vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.06.2024 to 30.11.2024]" (Vehicle No-WB 04G 7127) | Assistant Engineer | JUNIOR ENGINEER | ORD/000465/2024-2025 | 272/KSD | 30/05/2024 | 183 | PARTHA PRATIM ACHARYA | 2.4 | 0 | 0
1328 | Burdwan Division | Kalna Sub-division | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.12.2023 to 31.05.2024]" (Vehicle No-WB 04G 7127) | Assistant Engineer | JUNIOR ENGINEER | ORD/000983/2023-2024 | 1681/KSD | 22/11/2023 | 183 | PARTHA PRATIM ACHARYA | 0.87 | 0 | 51
1329 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DAFARPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001148/2023-2024 | 2104/KSD | 04/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0 | 2
1330 | Burdwan Division | Kalna Sub-division | Continuation work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.12.2024 to 28.02.2025] [Vehicle No-WB 04G 7127]". | Assistant Engineer | JUNIOR ENGINEER | ORD/001207/2024-2025 | 1877/KSD | 28/11/2024 | 90 | PARTHA PRATIM ACHARYA | 1.2 | 0 | 0
1331 | Burdwan Division | Kalna Sub-division | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.12.2023 to 31.05.2024]" (Vehicle No-WB 04G 7127) | Assistant Engineer | JUNIOR ENGINEER | ORD/001248/2023-2024 | 1681/KSD | 22/11/2023 | 183 | PARTHA PRATIM ACHARYA | 2.4 | 0 | 0
1332 | Burdwan Division | Kalna Sub-division | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0
1333 | Burdwan Division | Kalna Sub-division | Continual work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.03.2025 to 31.05.2025] [Vehicle No-WB 04G 7127]". | Assistant Engineer | JUNIOR ENGINEER | ORD/001450/2024-2025 | 335/KSD | 28/02/2025 | 92 | PARTHA PRATIM ACHARYA | 1.2 | 0 | 0
1334 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000075/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 28.1 | 0 | 0
1335 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000237/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.02 | 0 | 0
1336 | Central Mechanical | Kalna Sub-division | Additional quotation for Dafarpur PWSS PH-2 | Assistant Engineer | JUNIOR ENGINEER | BILL/00426/2024-2025 | BP-2024-25-224 | 26/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.51 | 0 | 0
1337 | Central Mechanical | Kalna Sub-division | New service at Dafarpur PWSS TW-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/02292/2023-2024 | BP-2023-24-438 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.7 | 0 | 0
1338 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR DAFARPUR PWSS TW -1. | Assistant Engineer | JUNIOR ENGINEER | BILL/03103/2023-2024 | BP-2023-24-643 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 20.65 | 0 | 0
1339 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at DAFARPUR Water Supply Scheme [Block - KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000895/2023-2024 | 4158/CMD | 29/08/2023 | 733 | GOENKA ENTERPRISE | 20.81 | 0 | 90
1340 | Burdwan Division | Central Mechanical Sub-Division | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Murgram, Moregram, Malgram, Khanji, PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000289/2024-2025 | 2739/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 185.75 | 0 | 72
1341 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MALGRAM, MURGRAM, MORGRAM & KHANJI Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 3387/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 1333.98 | 0 | 40
1342 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000099/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 5.23 | 0 | 0
1343 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000379/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.94 | 0 | 0
1344 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000748/2023-2024 | 5261/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0
1345 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Khanji PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01665/2023-2024 | BP-2023-24-223 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.96 | 0 | 0
1346 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new electric service connection at Khanji PWSS TW No-1 | Assistant Engineer | Junior Engineer | BILL/01731/2023-2024 | BP-2023-24-270 | 11/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.48 | 0 | 0
1347 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
1348 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHANJI Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000842/2023-2024 | 4114/CMD | 29/08/2023 | 30 | M/S. S.R. ENTERPRISE | 29.41 | 0 | 97
1349 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Khanji Water Supply Scheme [ BLOCK- Ketugram-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/001389/2024-2025 | 882/CMD | 26/03/2025 | 60 | KAMAKHYA ENTERPRISE | 11.62 | 0 | 0
1350 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works or construction of Tube Well (250mm x 200mm x 114 Mtrs. Depth) by utilising Departmental machineries for Khanji Scheme (T/W-i & II) ketugram-I Block under Purba Bardhaman District, CDD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000055/2023-2024 | 861/CDD | 10/07/2023 | 30 | OSMAN SEKH | 16.66 | 0 | 100
1351 | Burdwan Division | Kalna Sub-division | Augmentation of BAMANGARIA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Purbasthali - I Block, Purba Burdwan District under Burdwan Division, PHE.Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000076/2023-2024 | 2044/BWD | 03/05/2023 | 60 | TAPAS KUMAR ROY | 38.28 | 0 | 100
1352 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of BAMUNGARIA[PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001077/2023-2024 | 4201/CMD | 29/08/2023 | 30 | DAS TRADING CO. | 24.41 | 0 | 0
1353 | Burdwan Division | Kalna Sub-division | KHARGAKUR PWSS Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna-II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer | JUNIOR ENGINEER | ORD/000556/2023-2024 | 3751/BWD | 28/08/2023 | 365 | MITRA CONSTRUCTION | 310.02 | 0 | 15
1354 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR KHAGRAKUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001155/2023-2024 | 2171/KSD | 11/03/2024 | 10 | MITRA CONSTRUCTION | 0.66 | 0 | 100
1355 | Burdwan Division | Kalna Sub-division | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0
1356 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000382/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 14.2 | 0 | 0
1357 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000399/2023-2024 | 3842/BWD | 01/09/2023 | 0 | Resource Division | 6.91 | 0 | 0
1358 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000538/2023-2024 | 4305/BWD | 29/09/2023 | 0 | Resource Division | 25.37 | 0 | 0
1359 | Central Mechanical | Kalna Sub-division | Quotation for new electric service connection at Khargakur PH NO.-2 | Assistant Engineer | JUNIOR ENGINEER | BILL/01745/2023-2024 | BP-2023-24-256 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.28 | 0 | 0
1360 | Central Mechanical | Kalna Sub-division | Quotation for new electric service connection at Khargakur PH NO.-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01746/2023-2024 | BP-2023-24-257 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.35 | 0 | 0
1361 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 20
1362 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHARGAKUR Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000893/2023-2024 | 4156/CMD | 29/08/2023 | 30 | S.K. ELECTRICALS | 26.96 | 0 | 0
1363 | Burdwan Division | Kalna Sub-division | KUSDANGA PWSS Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000706/2023-2024 | 4523/BWD | 12/10/2023 | 813 | SYED KHORSED ALAM | 258.8 | 0 | 25
1364 | Burdwan Division | Kalna Sub-division | Restoration of Masonary drain due laying of 90 mm. dia. HDPE pipe along with increasing height of boundary wall and other ancillary work under the command area of Kusdanga PWSS (SM/16036) under Kalna Sub Division under Burdwan Divn., PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000885/2024-2025 | 4240/BWD | 03/12/2024 | 21 | RUBAL CONSTRUCTION | 13.62 | 0 | 100
1365 | Burdwan Division | Kalna Sub-division | Road Restoration work under the command area of Kusdanga PWSS (SM/16036) under Kalna Sub Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000886/2024-2025 | 4170/BWD | 29/11/2024 | 21 | RUBAL CONSTRUCTION | 15.12 | 0 | 100
1366 | Burdwan Division | Kalna Sub-division | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0
1367 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000084/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 22.36 | 0 | 0
1368 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000392/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.79 | 0 | 0
1369 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000632/2023-2024 | 4874/BWD | 10/11/2023 | 0 | Resource Division | 28.85 | 0 | 0
1370 | Central Mechanical | Kalna Sub-division | New Service connection for Kushodanga W/S Scheme. | Assistant Engineer | JUNIOR ENGINEER | BILL/02278/2023-2024 | BP-2023-24-437 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.25 | 0 | 0
1371 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR KUSDANGA PWSS TW -2. | Assistant Engineer | JUNIOR ENGINEER | BILL/03107/2023-2024 | BP-2023-24-647 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.03 | 0 | 0
1372 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and Compound lighting arrangement for Tube well No.- 1 & 2 at KUSDANGA Water Supply Scheme [BLOCK- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001607/2023-2024 | 1536/CMD | 05/03/2024 | 60 | MITRA ENTERPRISE | 28.81 | 0 | 50
1373 | Burdwan Division | Burdwan Sadar Sub-Division | Installation of air valve with valve Chamber and installation of pressure gauge for improvement of valve pressure at dist.line,repairing valve chamber with RCC cover slab and interconnection of valve chamber with upvc pipe for draining out waste water at Head work site of RASULPUR PWSS under Memari-I Dev.Block under Bardhaman Sadar south sub-Divn,PHE Dte | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000118/2024-2025 | 997/BSD | 06/06/2024 | 30 | DEBASHISH ENTERPRISE | 0.83 | 0 | 0
1374 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-II W/S Scheme at Kalsi Mouza, RASULPUR W/S Scheme at 4th TW site & ALIPUR W/S Scheme at 4th TW site under Memari-I Block under within Burdwan Sub-Division, PHE Dte. [For 3 Nos. Tube well]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000159/2023-2024 | 2455/BWD | 31/05/2023 | 60 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 39.76 | 0 | 100
1375 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of height of Boundary Wall by Angle Rolled Section and Barbed Wire and Roof treatment of Pump house for Rasulpur and its Adjoining Mouza W/S Scheme, block -Memari-I within Burdwan Sub-Division ,PHE Dte | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000300/2024-2025 | 1282/BSD | 12/07/2024 | 60 | GHOSH CONSTRUCTION | 1.27 | 0 | 98
1376 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Rasulpur PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000395/2023-2024 | 1583/BSD | 24/07/2023 | 15 | GEO-SOLUTION | 0.78 | 0 | 100
1377 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch rooms & Rising main at different TW site for RASULPUR Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000881/2023-2024 | 5356/BWD | 06/12/2023 | 60 | SANDIP SARKAR | 7.43 | 0 | 95
1378 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for RASULPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000982/2024-2025 | 4474/BWD | 19/12/2024 | 90 | SARKAR AGENCY | 91.74 | 0 | 51
1379 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for New Electric Connection for Rasulpur Augmentation W/S Scheme TW No. - 4 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01735/2023-2024 | BP-2023-24-254 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.09 | 0 | 0
1380 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Rasulpur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000089/2023-2024 | 2594/CMD | 07/06/2023 | 30 | CHOUDHURY ENTERPRISE | 22.76 | 0 | 50
1381 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & installation of Automatic Chlorinator at Rasulpur water supply scheme, P.H. No.- II under CMD, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001750/2023-2024 | 18/CMSD | 04/01/2024 | 12 | MS S M ELECTRICAL | 0.96 | 0 | 100
1382 | Burdwan Division |  | JIUDHARA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000719/2023-2024 | 4534/BWD | 13/10/2023 | 780 | SOMNATH ROY CHOWDHURY | 625.16 | 0 | 45
1383 | Burdwan Division |  | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0
1384 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000295/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.12 | 0 | 0
1385 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000525/2023-2024 | 4291/BWD | 29/09/2023 | 0 | Resource Division | 50.47 | 0 | 0
1386 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000629/2023-2024 | 4877/BWD | 10/11/2023 | 0 | Resource Division | 26.94 | 0 | 0
1387 | Central Mechanical |  | New service connection for Jewdhara PWSS PH-1 |  |  | BILL/02314/2023-2024 | BP-2023-24-458 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.55 | 0 | 0
1388 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 20
1389 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at JIUDHARA Water Supply Scheme [ Block- KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000900/2023-2024 | 4164/CMD | 29/08/2023 | 30 | DUTTA ENTERPRISE | 44.4 | 0 | 0
1390 | Burdwan Division |  | Continuation for Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day for the month of May'2025 |  |  | ORD/000142/2025-2026 | 660/DSD | 30/04/2025 | 31 | MD HASIN | 0.4 | 0 | 0
1391 | Burdwan Division |  | Land demarcation and preparation of sketch map for Haldi, Sultanpur, Berugram & Karail Piped W/S. Scheme (New Scheme) at different Blocks under JJM under Burdwan Division, PHE Dte. |  |  | ORD/000756/2023-2024 | 842/AE/HQ | 01/11/2023 | 15 | M/S S. CHOUDHURY | 0.33 | 0 | 100
1392 | Burdwan Division |  | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period AUG.'2024 to OCT.'2024] |  |  | ORD/000845/2024-2025 | 575/DSD | 19/07/2024 | 78 | MD HASIN | 1 | 0 | 0
1393 | Burdwan Division |  | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period NOV.'2024 to JAN.'2025] |  |  | ORD/000847/2024-2025 | 886/DSD | 21/10/2024 | 78 | MD HASIN | 1 | 0 | 0
1394 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BERUGRAM & SULTANPUR Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000979/2023-2024 | 092/BWD | 05/01/2024 | 604 | SK ALIM | 1368.51 | 0 | 55
1395 | Burdwan Division |  | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day. [PeriodFebruary.'2025 to April'2025] |  |  | ORD/001180/2024-2025 | 129/DSD | 29/01/2025 | 78 | MD HASIN | 1 | 0 | 0
1396 | Burdwan Division |  | Balance work of BERUGRAM & SULTANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman. |  |  | ORD/001214/2024-2025 | 723/BWD | 24/02/2025 | 180 | MD HASIN | 438.83 | 0 | 0
1397 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000249/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.09 | 0 | 0
1398 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000523/2023-2024 | 4289/BWD | 29/09/2023 | 0 | Resource Division | 16.32 | 0 | 0
1399 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000655/2023-2024 | 5114/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1400 | Central Mechanical |  | Quotation for new service connection at Berugram W/S Scheme PH-I. |  |  | BILL/01804/2023-2024 | BP-2023-24-323 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.94 | 0 | 0
1401 | Central Mechanical |  | New Service connection for Berugram PWSS TW-2. |  |  | BILL/02333/2023-2024 | BP-2023-24-475 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.69 | 0 | 0
1402 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 10
1403 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Berugram Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] |  |  | ORD/000932/2023-2024 | 4195/CMD | 29/08/2023 | 30 | M/S, S.DAS AND ENTERPRISE. | 29.71 | 0 | 0
1404 | Burdwan Division |  | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. |  |  | ORD/000288/2024-2025 | 2741/BWD | 12/07/2024 | 538 | M/S M.M. ENTERPRISE | 205.15 | 0 | 65
1405 | Burdwan Division |  | EHIAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000456/2023-2024 | 3438/BWD | 08/08/2023 | 365 | M/S S.S. ENTERPRISE | 732.05 | 0 | 75
1406 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 4111/BWD | 25/11/2024 | 0 | Resource Division | 9.24 | 0 | 0
1407 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000250/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.15 | 0 | 0
1408 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000398/2023-2024 | 3874/BWD | 01/09/2023 | 0 | Resource Division | 64.94 | 0 | 0
1409 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000576/2023-2024 | 4924/BWD | 10/11/2023 | 0 | Resource Division | 40.35 | 0 | 0
1410 | Central Mechanical |  | New service connection charges for Ehiapur PWSS TW-1 |  |  | BILL/01470/2023-2024 | BP-2023-24-168 | 27/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.42 | 0 | 0
1411 | Central Mechanical |  | New service connection charges for Ehiapur PWSS TW-3 |  |  | BILL/01726/2023-2024 | BP-2023-24-258 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.52 | 0 | 0
1412 | Central Mechanical |  | New service connection charges for Ehiapur PWSS TW-2 |  |  | BILL/01727/2023-2024 | BP-2023-24-259 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.82 | 0 | 0
1413 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
1414 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at EHIAPUR Water Supply Scheme [ Block- KETUGRAM-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000843/2023-2024 | 4115/CMD | 29/08/2023 | 615 | ASHIM UDYOG | 44.39 | 0 | 61
1415 | Central Drilling |  | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Ehiapur W/S Scheme (T/W-I & II) ,Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000163/2023-2024 | 1348/CDD | 13/09/2023 | 30 | CHANDA ENTERPRISE | 16.67 | 0 | 0
1416 | Burdwan Division |  | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day |  |  | ORD/000107/2024-2025 | 485/KTS | 16/04/2024 | 72 | AJIT SAMANTA | 0.92 | 0 | 10
1417 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAKULIA, KULSANA & HALIMPUR Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000461/2023-2024 | 3443/BWD | 08/08/2023 | 836 | ASHOK KUMAR GHOSH | 1588.1 | 0 | 15
1418 | Burdwan Division |  | Balance work of HALIMPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman |  |  | ORD/001261/2024-2025 | 845/BWD | 05/03/2025 | 120 | M/S H.R. CONSTRUCTION | 248.04 | 0 | 0
1419 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000015/2024-2025 | 4109/BWD | 25/11/2024 | 0 | Resource Division | 6.9 | 0 | 0
1420 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000274/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.69 | 0 | 0
1421 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000408/2023-2024 | 3872/BWD | 01/09/2023 | 0 | Resource Division | 1.27 | 0 | 0
1422 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000571/2023-2024 | 4921/BWD | 10/11/2023 | 0 | Resource Division | 27.49 | 0 | 0
1423 | Central Mechanical |  | Quotation for new service connection at Halimpur PWSS TW-1 |  |  | BILL/01086/2024-2025 | BP-2024-25-396 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.11 | 0 | 0
1424 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
1425 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at HALIMPUR Water Supply Scheme [ Block- MANGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000871/2023-2024 | 4134/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 45.29 | 0 | 0
1426 | Central Drilling |  | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for Halimpur W/S Scheme (T/W-I & II), Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000153/2023-2024 | 1340/CDD | 13/09/2023 | 583 | M/S SAIKAT ENTERPRISE | 23.35 | 0 | 100
1427 | Burdwan Division |  | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day |  |  | ORD/000107/2024-2025 | 485/KTS | 16/04/2024 | 72 | AJIT SAMANTA | 0.92 | 0 | 10
1428 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAKULIA, KULSANA & HALIMPUR Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000461/2023-2024 | 3443/BWD | 08/08/2023 | 836 | ASHOK KUMAR GHOSH | 1588.1 | 0 | 15
1429 | Burdwan Division |  | Balance work of KULSANA Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman. |  |  | ORD/001303/2024-2025 | 935/BWD | 11/03/2025 | 120 | M/S GHOSH CONSTRUCTION | 249.53 | 0 | 0
1430 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 4099/BWD | 25/11/2024 | 0 | Resource Division | 20.51 | 0 | 0
1431 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000389/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 1.75 | 0 | 0
1432 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000406/2023-2024 | 3826/BWD | 01/09/2023 | 0 | Resource Division | 4.47 | 0 | 0
1433 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000801/2023-2024 | 308/BWD | 24/01/2024 | 0 | Resource Division | 32.08 | 0 | 0
1434 | Central Mechanical |  | QUOTATION FOR NEW SERVICE CONNECTION AT KULSANA PWSS TW-1 |  |  | BILL/00367/2024-2025 | BP-2024-25-187 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.91 | 0 | 0
1435 | Central Mechanical |  | Quotation for new service connection at Kulsana PWSS TW-2 |  |  | BILL/00376/2024-2025 | BP-2024-25-186 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.43 | 0 | 0
1436 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
1437 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KULSANA Water Supply Scheme [ Block-MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000876/2023-2024 | 4139/CMD | 29/08/2023 | 640 | M/S, S.S. ENTERPRISE. | 44.56 | 0 | 43
1438 | Central Drilling |  | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for Kulsana W/S Scheme (T/W-I & II), Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000154/2023-2024 | 1341/CDD | 13/09/2023 | 322 | SUNRISE ENGINEERING CORPORATION | 23.34 | 0 | 100
1439 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for Sinking of 300X200 mm dia TW,Pump House,Boundary wall concrete road & bituminous road restoration ,Jack pushing with laying of MS Pipe FHTC and land development of H/W Site drain & Internal pathway laying of MS pipe under Bhedia PWSS (JJM),Block-Aushgram-II,Dist-Purba Bardhaman under Durgapur W/S Division,PHE Dte. |  |  | ORD/000170/2024-2025 | 1611/DWSD | 26/11/2024 | 90 | SUPRIYA RAY | 87.54 | 0 | 0
1440 | Burdwan Division |  | PANDUK Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL |  |  | ORD/000483/2023-2024 | 3505/BWD | 10/08/2023 | 875 | M/S PIONEER CONSTRUCTION | 722.29 | 0 | 80
1441 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000363/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.25 | 0 | 0
1442 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000415/2023-2024 | 3840/BWD | 01/09/2023 | 0 | Resource Division | 55.98 | 0 | 0
1443 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000565/2023-2024 | 4919/BWD | 10/11/2023 | 0 | Resource Division | 53.67 | 0 | 0
1444 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000768/2023-2024 | 204/BWD | 10/01/2024 | 0 | Resource Division | 12.89 | 0 | 0
1445 | Central Mechanical |  | Quotation for new service connection for Panduk PWSS PH 1. |  |  | BILL/00221/2024-2025 | BP-2024-25-112 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.47 | 0 | 0
1446 | Central Mechanical |  | Quotation for new service connection for Panduk PWSS PH 2. |  |  | BILL/00222/2024-2025 | BP-2024-25-113 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.92 | 0 | 0
1447 | Central Mechanical |  | Quotation for new service connection for Panduk PWSS PH 3. |  |  | BILL/00223/2024-2025 | BP-2024-25-114 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.39 | 0 | 0
1448 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at PANDUK Water Supply Scheme [ Block- AUSGRAM-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000794/2023-2024 | 4082/CMD | 29/08/2023 | 611 | PADMA ENGINEERING CO. | 41.68 | 0 | 67
1449 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMUL & AURIA Piped Water Supply Scheme under Katwa ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000389/2023-2024 | 3198/BWD | 24/07/2023 | 1257 | MANASH GHOSH | 1418.89 | 0 | 48
1450 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000213/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 17.33 | 0 | 0
1451 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000433/2023-2024 | 3853/BWD | 01/09/2023 | 0 | Resource Division | 64.75 | 0 | 0
1452 | Central Mechanical |  | New service connection charges for Auria PWSS TW-1 |  |  | BILL/01518/2023-2024 | BP-2023-24-188 | 09/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.89 | 0 | 0
1453 | Central Mechanical |  | New service connection charges for Auria PWSS TW-2 |  |  | BILL/01519/2023-2024 | BP-2023-24-189 | 09/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.77 | 0 | 0
1454 | Central Mechanical |  | New service connection charges for Auria PWSS TW-3 |  |  | BILL/01520/2023-2024 | BP-2023-24-190 | 09/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7 | 0 | 0
1455 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0
1456 | Central Mechanical |  | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000602/2024-2025 | 3106/CMD | 11/12/2024 | 60 | S.K. ELECTRICALS | 13.6 | 0 | 0
1457 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at AURIA Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000802/2023-2024 | 4088/CMD | 29/08/2023 | 30 | ORIENTAL ENGINEERING CO. | 44.4 | 0 | 64
1458 | Durgapur W/S Division |  | FORMAL WORK ORDER FOR Balance work for construction of boundary wall, dismantling concrete road including mending work, construction of approach road by fillup stone dust, bolders on low load at OHR site and etc allied works under Bakshibad PWSS, Ausgram-II Block under DURGAPUR W/S DIVISION,PHE DTE. |  |  | ORD/000264/2024-2025 | 256/DWSD | 11/02/2025 | 324 | M/S. UNIT CONSTRUCTION | 122.59 | 0 | 95
1459 | Burdwan Division |  | BAKSIBAD POGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL |  |  | ORD/000484/2023-2024 | 3504/BWD | 10/08/2023 | 813 | M/S PIONEER CONSTRUCTION | 691.24 | 0 | 40
1460 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000223/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 20.29 | 0 | 0
1461 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000418/2023-2024 | 3864/BWD | 01/09/2023 | 0 | Resource Division | 128.72 | 0 | 0
1462 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000644/2023-2024 | 5110/BWD | 23/11/2023 | 0 | Resource Division | 22.15 | 0 | 0
1463 | Central Mechanical |  | Quotation for new service connection at Baksibad PWSS TW-2. |  |  | BILL/01191/2024-2025 | BP-2024-25-412 | 11/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.75 | 0 | 0
1464 | Central Mechanical |  | NEW SERVICE CONNECTION FOR BAKSIBAD PWSS PH-1. |  |  | BILL/03140/2023-2024 | BP-2023-24-652 | 20/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.55 | 0 | 0
1465 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Baksibad Pogram Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000742/2023-2024 | 4052/CMD | 29/08/2023 | 553 | JAGANNATH ENTERPRISE | 29.61 | 0 | 80
1466 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ICHALABAD & HATSIMUL Piped Water Supply Scheme under Burdwan ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000423/2023-2024 | 3292/BWD | 31/07/2023 | 885 | M/S NATIONAL CONSTRUCTION | 1617.18 | 0 | 60
1467 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000277/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 2.25 | 0 | 0
1468 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000441/2023-2024 | 3846/BWD | 01/09/2023 | 0 | Resource Division | 17.48 | 0 | 0
1469 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000671/2023-2024 | 5076/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1470 | Central Mechanical |  | Electric quotation for New Service Connection at Hatsimul W/S Scehem PH-I. |  |  | BILL/01771/2023-2024 | BP-2023-24-29 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.13 | 0 | 0
1471 | Central Mechanical |  | Electric quotation for New Service Connection at Hatsimul W/S Scehem PH-II. |  |  | BILL/01772/2023-2024 | BP-2023-24-293 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.12 | 0 | 0
1472 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 12
1473 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Hatsimul Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000671/2023-2024 | 4009?CMD | 29/08/2023 | 30 | WEST BENGAL ENGINEERING CO. | 28.96 | 0 | 100
1474 | Burdwan Division | Burdwan Sadar Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Barwa Piped Water Supply Scheme at Berwa (2 Nos Habitation Part), Mutra (2 Nos Habitation Part), Baneswarpur & Senpur (4 Nos Habitation) Village (Mouza), Memari-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000038/2021-2022 | 3442/BWD | 28/06/2021 | 90 | KALYAN CHOWDHURY | 45.14 | 17.46 | 100
1475 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of Pump House at Head Work site of BARWA Piped water supply scheme at Memari-II Block under Burdwan Division, Dist.-Purba Bardhaman | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000133/2024-2025 | 1007/BSD | 06/06/2024 | 30 | I.S. ENTERPRISE | 0.97 | 0 | 100
1476 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of 75 mm dia pipeline at Miya Para, Modhya Bohar & Bhagar Para Purba Bohar regarding FHTC under Satgachia (Zone-I) water supply scheme under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000350/2021-2022 | 703/BSD | 11/06/2021 | 5 | M/S SAYAN CHAKRABORTY | 0.88 | 0 | 1
1477 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Barwa village of Barwa piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-573/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000471/2020-2021 | 4627/BWD | 25/11/2020 | 30 | M/S SAYAN CHAKRABORTY | 4.92 | 4.92 | 1
1478 | Burdwan Division | Burdwan Sadar Sub-Division | Emergency repaired cleaning of chokage AC Pipeline for BARWA Piped Water Supply Scheme (Retrrofittings)at Mutra, senpur, Mohanpur & Barwa village distribution line smooth drinking (FHTC) water supply within Memari-II Block under Burdwan Division, PHE Dte. Gr.C | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000563/2022-2023 | 1919/BSD | 11/11/2022 | 15 | A R TRADERS | 0.79 | 0 | 1
1479 | Burdwan Division | Burdwan Sadar Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Barwa Piped Water Supply Scheme at Berwa (2 Nos Habitation Part), Mutra (2 Nos Habitation Part), Baneswarpur & Senpur (4 Nos Habitation) Village (Mouza), Memari-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000647/2020-2021 | 916/BWD | 02/02/2021 | 90 | KALYAN CHOWDHURY | 45.14 | 0 | 1
1480 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bohar (Part) village (Bohar (Part) habitation) of Satgachia Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Sl. No. : ¿20¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000667/2020-2021 | 70/BWD | 05/01/2021 | 15 | M/S SAYAN CHAKRABORTY | 4.86 | 0 | 0
1481 | Burdwan Division | Burdwan Sadar Sub-Division | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001269/2024-2025 | 848/BWD | 05/03/2025 | 120 | PROJECT INDIA | 394.29 | 0 | 0
1482 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Saktigarh (Pt-A) village of Saktigarh piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-172/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000098/2020-2021 | 2747/BWD | 10/08/2020 | 30 | SARKAR AGENCY | 4.92 | 4.92 | 1
1483 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Saktigarh (Pt-A) village of Shaktigarh Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿8A¿] (T.R. No. 428/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000150/2020-2021 | 3801/BWD | 08/10/2020 | 30 | SARKAR AGENCY | 4.92 | 4.92 | 1
1484 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Saktigarh (Pt-B) village of Shaktigarh Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿8B¿] (T.R. No.-380/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000151/2020-2021 | 2742/BWD | 10/08/2020 | 30 | T.K. BANERJEE & CO. | 4.91 | 4.91 | 1
1485 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Shaktigarh (Part-B) village of Shaktigarh piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-649/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000253/2020-2021 | 4271/BWD | 03/11/2020 | 30 | T.K. BANERJEE & CO. | 4.91 | 4.91 | 1
1486 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Saktigarh Piped water supply scheme at Shaktigarh village, Burdwan-II Block under Burdwan Division, PHE Dte. [Tr No.-101/SE/CC/2020-21] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000403/2020-2021 | 715/BWD | 28/01/2021 | 60 | SARKAR AGENCY | 62.17 | 17.35 | 1
1487 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 2nd tube well site for Shaktigarh & its adjoining mouzas water supply scheme , Block-Bardhaman-II under Burdwan Division, PHE Dte.[Gr.-G] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000754/2021-2022 | 1391/BSD | 07/10/2021 | 60 | DEBJYOTI GOSWAMI | 2.77 | 0 | 1
1488 | Burdwan Division | Burdwan Sadar Sub-Division | Providing bib cock,stop cock & PVC Pipe for existing FHTC of Shaktigar PWSS under Burdwan Sub Division ,Block:BWN-II under Burdwan Divn,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001281/2024-2025 | 504/BSD | 06/03/2025 | 30 | SARKAR AGENCY | 0.94 | 0 | 100
1489 | Burdwan Division |  | Supply of 10 mm NB Gun-Metal Ferrule conforming to IS:2692-1989 for water tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-4] |  |  | ORD/000108/2021-2022 | 3186/BWD | 08/06/2021 | 30 | R.K. INDUSTRIES | 76.05 | 20.36 | 0
1490 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of GANGATIKURI Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, PHE Dte. |  |  | ORD/000706/2020-2021 | 1007/BWD | 05/02/2021 | 90 | M/S ASOKE GHOSH & BROTHERS | 47.52 | 0 | 1
1491 | Burdwan Division | Katwa Sub-Division | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Enayatpur and Sankhai village under UDDHARANPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-1) | Assistant Engineer |  | ORD/000140/2021-2022 | 589/KTS | 06/09/2021 | 30 | M/S S. CHOUDHURY | 4.85 | 0 | 1
1492 | Burdwan Division | Katwa Sub-Division | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Uddharanpur village under UDDHARANPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.(Sl No-2) | Assistant Engineer |  | ORD/000141/2021-2022 | 590/KTS | 06/09/2021 | 30 | M/S S. CHOUDHURY | 4.83 | 0 | 1
1493 | Burdwan Division | Katwa Sub-Division | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Naihati village under UDDHARANPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-3) | Assistant Engineer |  | ORD/000142/2021-2022 | 591/KTS | 06/09/2021 | 30 | M/S S. CHOUDHURY | 4.83 | 0 | 1
1494 | Burdwan Division | Katwa Sub-Division | Special maintenance and construction of sluice Valve chamber at Uddharanpur Piped water Supply Scheme at Ketugram-II Block, under Katwa Sub-Division within Burdwan Division PHE Dte.[Sl No-2] | Assistant Engineer |  | ORD/000370/2023-2024 | 611/KTS | 19/06/2023 | 30 | BABUL SK | 0.97 | 0 | 100
1495 | Burdwan Division | Katwa Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Uddharanpur Piped Water Supply Scheme at Enayetpur, Naihati, Sankhai, Sitahati & Uddharanpur (1 No Habitation) Village (Mouza), Ketugram-II Block under Burdwan Division, PHE Dte. (Agreement No. 97/SE/CC/PHE/Dte of 2020-2021) | Assistant Engineer |  | ORD/000416/2020-2021 | 913/BWD | 02/02/2021 | 60 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 86.77 | 0 | 1
1496 | Burdwan Division | Katwa Sub-Division | Drinking water supply to 10 Nos ICDS for Uddharanpur water supply scheme Ketugram-II Block under Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000961/2020-2021 | 36/KTS | 18/01/2021 | 30 | MAA KHEPIMAYER CHARANE | 4.79 | 0 | 1
1497 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) at Parbatpur village within the command area of MAHINDAR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : A] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000040/2022-2023 | 227/AE/HQ | 19/04/2022 | 30 | M/S S. CHOUDHURY | 4.78 | 0 | 1
1498 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) at Sahapur and Faimpur village within the command area of MAHINDAR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : D] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000048/2022-2023 | 202/AE/HQ | 06/04/2022 | 30 | DEBJYOTI GOSWAMI | 4.84 | 0 | 1
1499 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) at Mahindar village within the command area of MAHINDAR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : E] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000049/2022-2023 | 203/AE/HQ | 06/04/2022 | 30 | M/S ASHA CONSTRUCTION | 4.85 | 0 | 1
1500 | Burdwan Division | Burdwan Division | Construction of approach road to get to the Head works site of MAHINDAR Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._2ND CALL [Group : G] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000051/2022-2023 | 205/AE/HQ | 06/04/2022 | 30 | APORUPA CONSTRUCTION | 4.84 | 0 | 100
1501 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mahindar Piped Water Supply Scheme at Mahindar Village (2 Nos habitations), Faimpur Village, Shitalpur Village, Sahapur Village (2 Nos. habitations & Parbatpur Village (2 Nos. habitations), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 684/BWD OF 2020-2021.] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000301/2020-2021 | 1456/BWD | 18/02/2021 | 60 | S.S. CONSTRUCTION | 73.07 | 0 | 1
1502 | Burdwan Division | Burdwan Division | Repairing of concrete road damaged due to laying of pipeline within command area of MAHINDER PWSS under Burdwan Division PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000560/2023-2024 | 760/AE/HQ | 23/08/2023 | 30 | GHOSH CONSTRUCTION | 2.68 | 0 | 100
1503 | Burdwan Division | Burdwan Division | Laying of uPVC pipe for providing FHTC at Faimpur, Parbatpur, Sahapur, Silatpur and Mahindar Village within Mahindar Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr. F | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000631/2021-2022 | 128/AE/HQ | 04/03/2022 | 15 | M/S S. CHOUDHURY | 4.82 | 0 | 1
1504 | Burdwan Division | Burdwan Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhabpur village and Madhabpur habitation of MADHABPUR Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿7C¿] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000846/2020-2021 | 7050/BWD | 22/12/2020 | 30 | KAJAL MUKHERJEE | 4.86 | 0 | 1
1505 | Burdwan Division | Burdwan Division | Laying of rising main for interconnection of Pump House No 1 & 2 and distribution main alongwith bypass arrangement for Over Head Reservoir for Mahindar Piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte. [Gr.-D] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000957/2020-2021 | 1229/AE/HQ | 10/02/2021 | 30 | APORUPA CONSTRUCTION | 4.97 | 0 | 1
1506 | Burdwan Division | Burdwan Division | Material Requisition To Resource Division | AE(HQs), Burdwan Division, PHE Dte. |  | RTOR000055/2022-2023 | 5523/BWD | 23/12/2022 | 0 | Resource Division | 0.62 | 0 | 0
1507 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Siptai Piped Water Supply Scheme at Shrimanpur Village, Siptai Village, Ilampur Village, Prijpur Village & Gohaldaha Village, Jamalpur Block under Burdwan Division, PHE Dte. |  |  | ORD/000024/2021-2022 | 3342/BWD | 21/06/2021 | 45 | ASHOK KUMAR GHOSH | 41.9 | 40.42 | 1
1508 | Burdwan Division |  | Extension of pipeline including providing FHTC for SIPTAI Piped Water Supply Scheme at Pirijpur 40 No¿s Habitation for Sajal Gram (As per FIELD VERIFICATION REPORT FOR HAR GHAR JAL CERTIFICATION within Jamalpur under Burdwan Division, PHE Dte. Gr.Q. |  |  | ORD/000353/2022-2023 | 1392/BSD | 08/08/2022 | 5 | ROY CONSTRUCTION | 0.95 | 0 | 1
1509 | Burdwan Division |  | Extension of pipeline including providing FHTC for SIPTAI Piped Water Supply Scheme at Siptai (42 Nos) Habitation for Sajal Gram (As per FIELD VERIFICATION REPORT DULY SIGNED BY PRADHAN FOR HAR GHAR JAL CERTIFICATION) within Jamalpur Block under Burdwan Division, PHE Dte. Gr.R |  |  | ORD/000354/2022-2023 | 1393/BSD | 08/08/2022 | 5 | ROY CONSTRUCTION | 0.97 | 0 | 100
1510 | Burdwan Division |  | Extension of pipeline including FHTC for Siptai Piped Water Supply Scheme at Ilampur (30 Nos) habitation for Sajal Gram (As per FIELD VERIFICATION REPORT DULY SIGNED BY PRADHAN FOR HAR GHAR JAL CERTIFICATION) within Jamalpur Block under Burdwan Division, PHE Dte. Gr.S. |  |  | ORD/000355/2022-2023 | 1394/BSD | 08/08/2022 | 5 | ROY CONSTRUCTION | 0.96 | 0 | 1
1511 | Burdwan Division |  | Extension of pipeline including FHTC for SIPTAI Piped Water Supply Scheme at Pirijpur (40 Nos) Habitation for Sajal Gram (As per field verification report duly signed by Pradhan for Har Ghar Jal Certification) within Jamalpur Block under Burdwan Division, PHE Dte. |  |  | ORD/000849/2022-2023 | 1392-A/BSD | 08/08/2022 | 5 | ROY CONSTRUCTION | 0.95 | 0 | 0
1512 | Burdwan Division |  | Extension of pipeline including FHTC for SIPTAI Piped Water Supply Scheme at Siptai (42 Nos) Habitation for Sajal Gram (As per field verification report duly signed by Pradhan for Har Ghar Jal Certification) within Jamalpur Block under Burdwan Division, PHE Dte. |  |  | ORD/000850/2022-2023 | 1393-A/BSD | 08/08/2022 | 5 | ROY CONSTRUCTION | 0.97 | 0 | 100
1513 | Burdwan Division |  | Extension of pipeline including providing FHTC for Siptai Piped Water Supply Scheme at Ilampur[30 No's],Habitation for Sajal Gram (As per Sajal Gram(As per Field Verification Report duly signed by Pradhan for Har Ghar Jal Certification)within Jamalpur Block under Burdwan Division, PHE Dte. |  |  | ORD/000851/2022-2023 | 1394-A/BSD | 08/08/2022 | 5 | ROY CONSTRUCTION | 0.96 | 0 | 100
1514 | Burdwan Division |  | Providing FHTC for 100% coverage at Srimanpur (Village) (Habitation) for SIPTAI Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. |  |  | ORD/000921/2023-2024 | 5487/BWD | 13/12/2023 | 30 | GOUTAM KUMAR MITRA | 4.34 | 0 | 100
1515 | Burdwan Division |  | Additional work for laying of UPVC pipeline for providing FHTC at Srimanpur (Village) (Habitation) under SIPTAI Piped W/S. Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. |  |  | ORD/001030/2023-2024 | 99/AE/HQ | 15/02/2024 | 30 | GOUTAM KUMAR MITRA | 0.72 | 0 | 100
1516 | Burdwan Division | Kalna Sub-division | Laying of UPVC pipeline for smooth running of FHTC work of SHUSHUNIA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000115/2023-2024 | 2342/BWD | 22/05/2023 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 22.26 | 0 | 100
1517 | Burdwan Division | Kalna Sub-division | Work order for Restoration of road and base concreting in FHTC for retrofitting of Shushunia water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000131/2023-2024 | 427/KSD | 11/05/2023 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 0.6 | 0 | 100
1518 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Shushuni Piped Water Supply Scheme at Shushuni (Part) (Ghoshpara & Sethpur habitation) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte. [Agreement No.661/BWD OF 2020-2021] | Assistant Engineer |  | ORD/000300/2020-2021 | 1152/BWD | 09/02/2021 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 19.79 | 0 | 1
1519 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Shushuni Piped Water Supply Scheme at Shushuni (Part) (Tentulia Bogpara habitation), Budhpur & Kalswar Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte.[Agreement No. 660/BWD OF 2020-2021] | Assistant Engineer |  | ORD/000333/2020-2021 | 1151/BWD | 09/02/2021 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 22.8 | 0 | 1
1520 | Burdwan Division | Kalna Sub-division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Kuli Village, Monteswar Block within Susunia PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer |  | ORD/000734/2023-2024 | 827/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0 | 100
1521 | Burdwan Division | Kalna Sub-division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Budhpur Village, Monteswar Block within Susunia PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer |  | ORD/000735/2023-2024 | 828/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0 | 100
1522 | Burdwan Division | Kalna Sub-division | Continuation work order for water tap connection in each household from existing distribution system within scheme jurisdiction in Kuli habitation of Shushunia piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Gr.-H] | Assistant Engineer |  | ORD/000910/2020-2021 | 4787./BWD | 02/12/2020 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 2.92 | 0 | 1
1523 | Burdwan Division | Katwa Sub-Division | Laying of uPVC pipeline due to obstruction arise for PWD roads within Gopikantapur W/S Scheme under Burdwan Division, PHE Dte. [Group: ¿F¿] | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | ORD/000222/2021-2022 | 1817/AE/HQ | 21/09/2021 | 30 | M/S S. CHOUDHURY | 3.55 | 0 | 1
1524 | Burdwan Division | Katwa Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Gopikantapur Piped Water Supply Scheme at Kubajpur, Pranballabhpur (2 Nos Habitation) & Ramchandrapur Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 98/SE/CC/PHE/Dte of 2020-2021.] | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | ORD/000417/2020-2021 | 914/BWD | 02/02/2021 | 60 | S.S. CONSTRUCTION | 62.95 | 0 | 1
1525 | Burdwan Division | Katwa Sub-Division | Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for Gopikantapur & it's adjoining mouzas W/S. scheme under Burdwan Division, P.H.E. Dte.Ref. Drawing No.PC-I/OHR/11/2012 (Sheet No.1&2)(R-I) Dated 20.06.2012. [Revision - 1 dt. 20.12.2012] | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | ORD/000438/2021-2022 | 696/BWD | 02/02/2022 | 180 | M/S JAN MAHAMMAD | 76.26 | 0 | 0
1526 | Burdwan Division | Katwa Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Gopikantapur Piped Water Supply Scheme at Bishnubati, Chakdighi & Dhapdhara Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 96/SE/CC/PHE/Dte of 2020-2021.] | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | ORD/000439/2020-2021 | 716/BWD | 28/01/2021 | 45 | BHARAT CONSTRUCTION | 47 | 0 | 1
1527 | Burdwan Division | Katwa Sub-Division | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhairabpur Habitation of Gopikantapur piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | ORD/000562/2021-2022 | 4818/BWD | 22/09/2021 | 30 | D.M. ENTERPRISE | 3.76 | 0 | 1
1528 | Burdwan Division | Katwa Sub-Division | Laying of uPVC pipe for providing FHTC at Gopikantapur, Ramchandrapur and Bishnubati Village within Gopikantapur Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-G | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | ORD/000632/2021-2022 | 129/AE/HQ | 04/03/2022 | 15 | S.S. CONSTRUCTION | 3.71 | 0 | 1
1529 | Burdwan Division | Katwa Sub-Division | Extension of pipeline (Branch & Sub Branch) for Functional House Hold Tap Connection from existing distribution system within the command area of GOPIKANTAPUR Piped Water Supply Scheme, at Bhairabpur village, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-H | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | ORD/000633/2021-2022 | 130/AE/HQ | 04/03/2022 | 15 | D.M. ENTERPRISE | 2.37 | 0 | 1
1530 | Burdwan Division | Katwa Sub-Division | Laying of HDPE and UPVC pipe for providing FHTC at Pranballabhpur Village within GOPIKANTAPUR Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-G | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | ORD/000662/2021-2022 | 148/AE/HQ | 16/03/2022 | 20 | OM ENTERPRISE | 4.8 | 0 | 1
1531 | Burdwan Division | Katwa Sub-Division | Laying of UPVC pipe for providing FHTC in different habitaion of Ramchandrapur, Pranballabpur Mouza within Gopikantapur piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte. [Gr.-B] | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | ORD/000768/2021-2022 | 1856/AE/HQ | 05/10/2021 | 30 | M/S S. CHOUDHURY | 4.82 | 0 | 1
1532 | Burdwan Division | Katwa Sub-Division | Preparation and Submission of DPR for Augmentation of Ground Water Based Piped Water Supply Scheme for GOPIKANTAPUR, Block:Jamalpur under Burdwan Division, P.H.E Dte. | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | ORD/000989/2024-2025 | 1911/BSD | 28/08/2024 | 15 | MEASURE LAND | 0.78 | 0 | 0
1533 | Burdwan Division | Katwa Sub-Division | Sinking of 300 mm X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) with construction of Pump House & Boundary wall of GOPIKANTAPUR Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. [FOR 3rd. TUBE WELL SITE]. | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | ORD/001043/2023-2024 | 786/BWD | 27/02/2024 | 440 | BIBHUTI SHAW | 23.9 | 0 | 40
1534 | Burdwan Division | Katwa Sub-Division | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 40
1535 | Burdwan Division | Katwa Sub-Division | Material Requisition To Resource Division | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | RTOR000117/2021-2022 | 1102/BWD | 26/02/2022 | 0 | Resource Division | 8.61 | 0 | 0
1536 | Burdwan Division | Katwa Sub-Division | Hire & fuel charges of vehicle (Car No.-WB-41H-3668) for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. for the month of May & June'22. | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | VCH/000494/2022-2023 | 462/VEH/22-23 | 29/08/2022 | 0 | MD HASIN | 0.51 | 0 | 0
1537 | Burdwan Division | Katwa Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte.,Assistant Engineer |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0
1538 | Burdwan Division | Durgapur Sub-DIvision | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of April'23. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00293/2023-2024 | 203/JJM | 01/06/2023 | 0 | SUJAUDDIN SEKH | 0.4 | 0 | 0
1539 | Burdwan Division | Durgapur Sub-DIvision | Vehicle bill for the month of September & October'2023. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/01676/2023-2024 | 961/JJM | 01/12/2023 | 0 | SUJAUDDIN SEKH | 0.65 | 0 | 0
1540 | Burdwan Division | Durgapur Sub-DIvision | Sinking of 200mm dia River bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Taranagar village under Joykrishnapur water supply scheme,Block -Galsi-II, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000330/2022-2023 | 533/DSD | 22/08/2022 | 21 | ANIRUDDHA FARUQUE | 4.35 | 0 | 1
1541 | Burdwan Division | Durgapur Sub-DIvision | Sinking of 200mm dia River bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Simuliya village under Joykrishnapur water supply scheme,Block -Galsi-II, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000331/2022-2023 | 534/DSD | 22/08/2022 | 21 | SANDIPAN SENGUPTA | 4.35 | 0 | 1
1542 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Joykrishnapur Piped Water Supply Scheme at Joykrishnapur (4 Nos Habitation), Pilgram & Taranagar (2 Nos Habitation) Village (Mouza), Galsi-II Block under Burdwan Divn., PHE Dte.[Agreement No. 609/BWD OF 2020-2021] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000380/2020-2021 | 752/BWD | 29/01/2021 | 45 | SUDHAMAY MAJUMDAR | 43.97 | 30.35 | 1
1543 | Burdwan Division | Durgapur Sub-DIvision | Laying of parallel line with 90 mm dia uPVC pipe within Node 86-88 and providing air valve for improvement of water supply to FHTC at Pilgram village within Jaykrishnapur and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-I) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000464/2021-2022 | 81/DSD | 11/02/2022 | 30 | TARAMA AGENCY | 3.12 | 0 | 1
1544 | Burdwan Division | Durgapur Sub-DIvision | Restoration of damaged pipeline of distribution main for construction of drain, concrete road etc. at various point at Jaykrishnapur, Taranagar and Pilgram village for providing FHTC within Jaykrishnapur W/S Scheme in Galsi-II Block under Burdwan Division, P.H.E. Dte.[SL-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000622/2021-2022 | 162/DSD | 16/03/2022 | 30 | SUDHAMAY MAJUMDAR | 4.81 | 0 | 1
1545 | Burdwan Division | Durgapur Sub-DIvision | Making Connection with 90 mm dia uPVC pipe within Node 162-168 for improvement of water supply to FHTC at Taranagar village within Jaykrishnapur and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-24] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000866/2022-2023 | 722/DSD | 30/12/2022 | 30 | TARAMA AGENCY | 2.07 | 0 | 100
1546 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline at Parhat & Patuna village of Mahachanda and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur (Bardhaman North) Sub Division under Burdwan Division, P.H.E. Dte. (Gr.-C) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000107/2021-2022 | 418/DSD | 02/07/2021 | 30 | PAPRI HAZRA | 4.18 | 0 | 0
1547 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda village and Mahachanda habitation of MAHACHANDA piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-527/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000163/2020-2021 | 3343/BWD | 18/09/2020 | 30 | BIPLAB SAMANTA | 4.86 | 4.86 | 1
1548 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda village and Mahachanda habitation of MAHACHANDA piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. (Tr No.-528/BWD/20-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000164/2020-2021 | 4270/BWD | 03/11/2020 | 30 | BIPLAB SAMANTA | 4.86 | 4.86 | 1
1549 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village and Bandh-O-Tawra & Nunari habitation of MAHACHANDA piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-529/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000166/2020-2021 | 3344/BWD | 18/09/2020 | 30 | PAPRI HAZRA | 4.86 | 4.86 | 1
1550 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village and Bandh-O-Tawra & Nunari habitation of MAHACHANDA piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-530/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000170/2020-2021 | 4006/BWD | 14/10/2020 | 30 | PAPRI HAZRA | 4.79 | 4.79 | 1
1551 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village (Patuna habitation) & Parhat village (Parhat habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [SL. No. : 04] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000202/2021-2022 | 6266/BWD | 02/11/2021 | 15 | PAPRI HAZRA | 4.86 | 0 | 1
1552 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village (Patuna habitation) & Parhat village (Parhat habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 03] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000203/2021-2022 | 6265/BWD | 02/11/2021 | 15 | BIPLAB SAMANTA | 4.86 | 0 | 1
1553 | Burdwan Division | Durgapur Sub-DIvision | Arrangement of drinking water supply by installation of solar submersible pump including sinking of 200 mm. dia. Tube well 150 Mtr. Deep by direct rotary rig method, Laying dist. System, FHTC for Nunari Village under MAHACHANDA Piped W/S. Scheme, Block Bhatar under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000225/2024-2025 | 2525/BWD | 03/07/2024 | 120 | THE BUSINESS ENGINEERS INDIA | 28 | 0 | 25
1554 | Burdwan Division | Durgapur Sub-DIvision | Restoration of pipeline at 6-Mile_Shibpur-Dharampur along & across Bardhaman-Katwa Road (SH-7) & providing FHTC at Aimapara (Part), Mahachanda (Part), Shibpur, Dharampur, Nunari (Part) Village (Mouza) under MAHACHANDA Piped W/S. Scheme under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000277/2021-2022 | 6934/BWD | 13/12/2021 | 45 | PREMANANDA ROY BISWAS | 43.33 | 0 | 1
1555 | Burdwan Division | Durgapur Sub-DIvision | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000389/2021-2022 | 268/BWD | 14/01/2022 | 30 | BHARAT CONSTRUCTION | 14.17 | 0 | 1
1556 | Burdwan Division | Durgapur Sub-DIvision | Laying of UPVC pipeline in TAWRA Habitation within Mahachanda PWSS WITHIN Durgapur(Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000397/2024-2025 | 622/DSD | 05/08/2024 | 30 | MAA MAHAMAYA CONSTRUCTION | 4.54 | 0 | 100
1557 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda village (Iymapara & Mahachanda (Part) habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 01] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000411/2020-2021 | 577/BWD | 25/01/2021 | 15 | S. MONDAL | 4.86 | 0 | 1
1558 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda village (Shibpur-Dharampur habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 02] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000453/2020-2021 | 578/BWD | 25/01/2021 | 15 | PRONAB KUMAR DEY | 4.86 | 0 | 1
1559 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village (Patuna habitation) & Parhat village (Parhat habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 03] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000454/2020-2021 | 582/BWD | 25/01/2021 | 15 | BIPLAB SAMANTA | 4.86 | 4.86 | 0
1560 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village (Patuna habitation) & Parhat village (Parhat habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [SL. No. : 04] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000459/2020-2021 | 583/BWD | 25/01/2021 | 15 | PAPRI HAZRA | 4.86 | 4.84 | 0
1561 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda (Part) village (Aymapara & Mahachanda (P) habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte [SL. No. : 15] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000461/2020-2021 | 1466/BWD | 18/02/2021 | 15 | BARABELUN NO.-II G.P. UNEMPLOYED CO-OP LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.86 | 0 | 1
1562 | Burdwan Division | Durgapur Sub-DIvision | Laying of parallel line with 90 mm dia uPVC pipe within Node J8-J-48 and providing air valve for improvement of water supply to FHTC at Twara village within MAHACHANDA and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000467/2022-2023 | 3967/BWD | 13/09/2022 | 30 | PAPRI HAZRA | 5.26 | 0 | 1
1563 | Burdwan Division | Durgapur Sub-DIvision | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mahachanda Piped Water Supply Scheme , Block- Bhatar within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000478/2021-2022 | 97/DSD | 18/02/2022 | 30 | BIPLAB SAMANTA | 3.54 | 0 | 1
1564 | Burdwan Division | Durgapur Sub-DIvision | Restoration of damaged flanks during laying of distribution pipe with jhama metal and moorum of Bardhaman Katwa road from Shibpur towards 6th Mile ( From Node 89 -64) of Mahachanda Water Supply Scheme within Durgapur Sub Division Under Burdwan Division, PHE Dte.[SL-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000624/2021-2022 | 165/DSD | 16/03/2022 | 30 | PREMANANDA ROY BISWAS | 3.89 | 0 | 1
1565 | Burdwan Division | Durgapur Sub-DIvision | Restoration of damaged flanks during laying of distribution pipe with jhama metal and moorum of Bardhaman Katwa road from Shibpur towards 6th Mile ( From Node 89 -64) of Mahachanda Water Supply Scheme within Durgapur Sub Division Under Burdwan Division, PHE Dte.[SL-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000638/2021-2022 | 165/DSD | 16/03/2022 | 30 | OM ENTERPRISE | 3.88 | 0 | 1
1566 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in Parhat (Part-B) village of MAHACHANDA piped W/S Scheme within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000938/2023-2024 | 910/DSD | 15/12/2023 | 434 | OM ENTERPRISE | 0.96 | 0 | 100
1567 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in Parhat (Part-A) village of MAHACHANDA piped W/S Scheme within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000939/2023-2024 | 911/DSD | 15/12/2023 | 434 | OM ENTERPRISE | 0.95 | 0 | 100
1568 | Burdwan Division |  | Providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Ramkrishnapur piped water supply scheme at Jamui, Fakirpur, Khemta, Ramkrishnapur & Chandipur village (Mouza), Raina-I Block under Burdwan Division, PHE Dte. |  |  | ORD/000147/2021-2022 | 4217/BWD | 16/08/2021 | 45 | GHOSH CONCERN | 36.49 | 0 | 1
1569 | Burdwan Division |  | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. |  |  | ORD/000344/2021-2022 | 39/BWD | 05/01/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 15.62 | 0 | 1
1570 | Burdwan Division |  | Extension of pipeline for Ramkrishnapur Water Supply Scheme at Ramkrishnapur and chandipur village within Raina-I Block , under Burdwan Division, PHE Dte. Gr.B. |  |  | ORD/000375/2021-2022 | 43/BSD | 10/01/2022 | 30 | SUPRIYA RAY | 4.79 | 0 | 1
1571 | Burdwan Division |  | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-5]. |  |  | ORD/000090/2021-2022 | 3590/BWD | 13/07/2021 | 30 | PREMANANDA ROY BISWAS | 127.5 | 42.32 | 1
1572 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SONARUDRA Piped Water Supply Scheme at Purbasthali-I Block under Burdwan Division, PHE Dte.(Agreement No. 51/2020-2021 OF SE/CC/PHE. DTE.) |  |  | ORD/000120/2020-2021 | 4900/BWD | 07/12/2020 | 90 | J.D.J. ENTERPRISE | 88.29 | 22.1 | 0
1573 | Burdwan Division |  | Construction of pathway & plinth protection of Pump House and Surface Drain at the Head Work Site of Sonarudra water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) |  |  | ORD/000356/2021-2022 | 1218/KSD Dt-10.12.2021 | 10/12/2021 | 31 | BABUL SK | 1.77 | 0 | 1
1574 | Burdwan Division |  | Providing FHTC from the existing distribution line and special repair of existing different dia UPVC pipeline including supply of Sluice Valve for proper functioning the existing line of Sonarudra W/S Scheme of Purbasthali-I block within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) |  |  | ORD/000394/2021-2022 | 1260/KSD Dt-22.12.2021 | 22/12/2021 | 31 | BABUL SK | 4.14 | 0 | 1
1575 | Burdwan Division |  | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kashira Piped Water Supply Scheme at Chanak (Part), Gopalbera, Krishnapur, Gatistha & Kashira (Part) Village (Mouza), Mongolkot Block under Burdwan Division, PHE Dte. (Agreement No. 99/SE/CC/PHE/Dte of 2020-2021) |  |  | ORD/000418/2020-2021 | 915/BWD | 02/02/2021 | 60 | MAJUMDER ENTERPRISE | 53.52 | 7.18 | 0
1576 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Paranpur village and Paranpur habitation of Jahannagar piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-814/BWD/2020-21) |  |  | ORD/000548/2020-2021 | 4110/BWD | 16/10/2020 | 30 | J. K. CORPORATION | 4.86 | 2.74 | 0
1577 | Burdwan Division |  | Interconnection of tube well no.-1 & Tube well No.-2 along with connection of existing OHR by 100 mm dia DI (K9) pipe and construction of sluice valve chamber of Sonarudra water supply scheme within Kalna Sub-Division, under Burdwan Division, PHE Dte. |  |  | ORD/000549/2020-2021 | 8/KSD | 05/01/2021 | 30 | BISWAS ENTERPRISE | 2.54 | 2.28 | 1
1578 | Burdwan Division |  | Providing FHTC from the existing distribution line and special repair of existing different dia UPVC pipeline including supply of Sluice Valve for proper functioning the existing line of Sonarudra W/S Scheme of Purbasthali-I block within Kalna Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000672/2021-2022 | 29/KSD | 07/01/2022 | 30 | BABUL SK | 4.14 | 0 | 1
1579 | Burdwan Division |  | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] |  |  | ORD/000867/2020-2021 | 4318/BWD | 04/11/2020 | 10 | MD HASIN | 4.93 | 0 | 1
1580 | Burdwan Division | Katwa Sub-Division | Augmentation of PALITA Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 350 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation, Construction of boundarywall at HW and 2nd TW site with repairing of Pump house -I & II under Ketugram-I Block, District:- Purba-Burdwan. | Assistant Engineer |  | ORD/000029/2022-2023 | 2139/BWD | 25/04/2022 | 1347 | M/S GUPTA ENTERPRISE | 472.81 | 0 | 98
1581 | Burdwan Division | Katwa Sub-Division | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day.(Sl No-1) | Assistant Engineer |  | ORD/000510/2023-2024 | 499/KTS | 22/05/2023 | 70 | M/S MUNMUN DEY | 0.9 | 0 | 100
1582 | Burdwan Division | Katwa Sub-Division | Route Survey and preparation of DPR for PALITA PWSS under Ketugram-I Block under Katwa Sub-Division under Burdwan Division PHE Dte.[Sl No-04] | Assistant Engineer |  | ORD/000540/2021-2022 | 55/KTS | 25/01/2022 | 21 | RADIANT | 2.78 | 0 | 1
1583 | Burdwan Division | Katwa Sub-Division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of PALITA Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte._Sl. No. 09 | Assistant Engineer |  | ORD/000620/2021-2022 | 143/AE/HQ | 16/03/2022 | 10 | MAKALI ENGINEERING CORPORATION | 4.52 | 0 | 0
1584 | Burdwan Division | Katwa Sub-Division | Continuation order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. (Sl No-1) | Assistant Engineer |  | ORD/000930/2023-2024 | 1016/KTS | 20/09/2023 | 23 | M/S MUNMUN DEY | 0.3 | 0 | 0
1585 | Burdwan Division | Katwa Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000044/2021-2022 | 543/BWD | 27/01/2022 | 0 | Resource Division | 15.49 | 0 | 0
1586 | Burdwan Division | Katwa Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000107/2021-2022 | 929/BWD | 16/02/2022 | 0 | Resource Division | 26.89 | 0 | 0
1587 | Burdwan Division | Katwa Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000207/2021-2022 | 1530/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
1588 | Burdwan Division | Katwa Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
1589 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for Kulingram Water Supply Scheme (Rewra village, Gokul Village, Kulingram uttar Village, Chak Village, Ranapara Village, Kantagaria Village, Mirjapur Village, Duttapara Village, Kolsara Village, Gopalpur Village) within Jamalpur Block including water tap connection (FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000007/2021-2022 | 3116/BWD | 02/06/2021 | 60 | SK ALIM | 151.26 | 145.73 | 0
1590 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of additional 250 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for KULINGRAM Piped Water Supply Scheme, Block - Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000073/2022-2023 | 2473/BWD | 12/05/2022 | 30 | NADIA TUBEWELLS | 10.32 | 0 | 1
1591 | Burdwan Division | Burdwan Sadar Sub-Division | Relaying of damage of pipeline due to irrigation cannel and 75 mm dia HDPE pipeline with FHTC for KULINGRAM Water Supply Scheme within Jamalpur Block,under Burdwan Division, PHE Dte. Group : A | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000088/2022-2023 | 828/BSD | 23/05/2022 | 30 | BISWAKARMA CONSTRUCTION | 4.96 | 0 | 1
1592 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) for the balance household in (Kolsara, Kulingram Uttar, Kulingram Dakshin, Ranapara Uttar, Ranapara Dakshin, Dutta Para, Kantagoria, Gokul, Gopalpur, Reora & Chack) Part Habitations from existing distribution system within the command area of KULINGRAM Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000126/2021-2022 | 4536/BWD | 06/09/2021 | 30 | SK ALIM | 31.2 | 0 | 1
1593 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for KULINGRAM Water Supply Scheme FOR FHTC work within Jamalpur Block , under Burdwan Division, PHE Dte. Gr.B | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000440/2021-2022 | 198/BSD | 01/02/2022 | 30 | SK ALIM | 4.34 | 0 | 1
1594 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of Interconnection of 4th Tube well site and Laying of 90 mm dia HDPE pipeline for KULINGRAM Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000622/2023-2024 | 3917/BWD | 05/09/2023 | 30 | BARABELUN NO.-II G.P. UNEMPLOYED CO-OP LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 8.28 | 0 | 100
1595 | Burdwan Division | Burdwan Sadar Sub-Division | HDPE pipeline of 75 mm dia of Kulingram water supply scheme for FHTC (Gopalpur, Ranapara, Koisara, Gokul Katagoria)of Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000703/2021-2022 | 1424/BSD | 25/10/2021 | 30 | SK ALIM | 4.52 | 0 | 1
1596 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Gopalpur Village, Jamalpur Block within Kulingram PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000796/2023-2024 | 875/AE/HQ | 07/11/2023 | 30 | PAPRI HAZRA | 0.76 | 0 | 100
1597 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Gangarambati Village, Jamalpur Block within Kulingram PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000797/2023-2024 | 876/AE/HQ | 07/11/2023 | 30 | PAPRI HAZRA | 0.76 | 0 | 100
1598 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC for Declaration of Sajal Gram at Duttapara (25 Nos), Kamalpur (04 Nos) and Chak Mujaffarpur (07) Mouzas (Habitation) for KULINGRAM Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte._2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000838/2024-2025 | 967/AE/HQ | 22/11/2024 | 30 | SOUMYAVASH DAS | 2.47 | 0 | 100
1599 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 40
1600 | Burdwan Division |  | Regarding release of fund for restoration of road under PMGSY scheme under Ketugram-II Block Katwa Sub-Division PHE Dte. Khatundi to Chitahati (Package No-WB-22-47) |  |  | BILL/00772/2024-2025 | 896/JJM | 26/09/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 2.45 | 0 | 0
1601 | Burdwan Division |  | Construction of sanitary system and drinking water supply arrangement for Head Work Site of Natungram Water Supply Scheme under Katwa Sub-Division within Burdwan Division P.H.E Dte. (Sl No-3) |  |  | ORD/000275/2021-2022 | 800/KTS | 10/12/2021 | 45 | JAHAR GHOSH | 1 | 0 | 1
1602 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Natungram Piped Water Supply Scheme at Natungram (Part) & Charnarayanpur Village (Mouza), Ketugram-II Block under Burdwan Division, PHE Dte. (Agreement no. 567/BWD of 2020-2021) |  |  | ORD/000294/2020-2021 | 357/BWD | 15/01/2021 | 30 | JAHAR GHOSH | 22.73 | 0 | 1
1603 | Burdwan Division |  | Construction of Boundary wall including land development, Pathway and plantation at Head works site of Natungram water supply scheme, Block-Ketugram-II under Katwa Sub-Division under Burdwan Division, PHE Dte. [Tr No.-347/BWD/20-21] |  |  | ORD/000482/2020-2021 | 4282/BWD | 03/11/2020 | 60 | MOJAI SK | 31.33 | 0 | 1
1604 | Burdwan Division |  | Connection of CWR & IEP with the existing distribution system under Natungram Piped Water Supply Scheme under Katwa Sub-Division under Burdwan Division, P.H.E. Dte. [Sl No-01] |  |  | ORD/000596/2021-2022 | 160/KTS | 24/02/2022 | 30 | JAHAR GHOSH | 1.5 | 0 | 1
1605 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SRIKHANDA Piped Water Supply Scheme at Katwa - I Block under Burdwan Division, PHE Dte.(Agreement No. 53/2020-2021 OF SE/CC/PHE. DTE.) |  |  | ORD/000121/2020-2021 | 4880/BWD | 07/12/2020 | 90 | ASHOK KUMAR GHOSH | 96.84 | 0 | 1
1606 | Burdwan Division |  | Supplying, laying and commissioning of Rising main at pump no. - 2 of Srikhanda PWSS under Katwa Sub-Division under Burdwan Division, PHE Dte. [Sl No-07] |  |  | ORD/000161/2022-2023 | 444/KTS | 27/06/2022 | 30 | ASHOK KUMAR GHOSH | 1.84 | 0 | 1
1607 | Burdwan Division |  | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of SRIKHANDA and its adjoining mouzas Piped Water Supply Scheme, Block Katwa I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. |  |  | ORD/000669/2022-2023 | 388/BWD | 31/01/2023 | 30 | SUBODH KUMAR MONDAL | 11.81 | 0 | 100
1608 | Burdwan Division | Burdwan Sadar Sub-Division | Concrete cutting of khalina, shibrampur, shyamsundar uttar para,shyamsundar dakshin para ,natungram village for Augmentation of Shyamsundar Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.D. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000367/2022-2023 | 1406/BSD | 10/08/2022 | 30 | SK ALIM | 4.68 | 0 | 1
1609 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of Pipeline for Natungram and Shyamsundar village of Augmentation of Shyamsundar Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.C | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000441/2022-2023 | 1479/BSD | 25/08/2022 | 45 | SK ABDUL HALIM | 4.84 | 0 | 1
1610 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of 100 mm dia C.I. Sluice valve(P.N.-I) of Augmentation of Shyamsundar Water Supply Scheme of Raina-I under Burdwan Sub Division, PHE Dte. Gr.F. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000479/2022-2023 | 1603/BSD | 14/09/2022 | 15 | SK ALIM | 1.73 | 0 | 1
1611 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of Pipeline for Shyamsundar village Uttar para of Augmentation of Shyamsundar Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.G. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000480/2022-2023 | 1604/BSD | 14/09/2022 | 30 | M/S PROCHESTA ENTERPRISE | 4.78 | 0 | 1
1612 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of Pipeline for Shyamsundar village Dakshin para of Augmentation of Shyamsundar Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.I. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000482/2022-2023 | 1606/BSD | 14/09/2022 | 30 | SK ABDUL HALIM | 4.77 | 0 | 1
1613 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Shyamsundar W/S Scheme under Raina-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.7. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000495/2021-2022 | 182/BSD | 31/01/2022 | 30 | RADIANT | 2.9 | 0 | 1
1614 | Burdwan Division | Burdwan Sadar Sub-Division | Sand filling at PWD road side near bazar to thana more(Drawing NOD 15 to 16,16 to 17,6 to 89,11 to 12,12 to 13,12 to 156,10 to 11,13 to 14,14 to 15,1 to 2 to 267,2 to 3 ,7 to 8,7 to 82,4 to 5 ,5 to 6,6 to 82,3 to 4. at Shyamsundar Water supply scheme of Raina Block within Burdwan Division, PHE Dte. Gr.A. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000501/2022-2023 | 1224/BSD | 08/07/2022 | 7 | SK ALIM | 4.16 | 0 | 1
1615 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of SHYAMSUNDAR & its adjoining mouzas Piped Water Supply Scheme [Shyamsundar Mouza], Block ¿ Raina ¿ I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000509/2022-2023 | 4446/BWD | 27/09/2022 | 30 | SK ALIM | 9.87 | 0 | 1
1616 | Burdwan Division | Burdwan Sadar Sub-Division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Paharhati, Nababhat, Shyamsundar & Dewandighi-Mirzapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000519/2022-2023 | 4703/BWD | 19/10/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 0 | 1
1617 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of SHYAMSUNDAR Piped Water Supply Scheme with LDS, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test, Construction of boundary wall at Head works & 2nd TW site & FHTC under Raina ¿ I Block, District - Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000598/2021-2022 | 1474/BWD | 14/03/2022 | 365 | SK ALIM | 474.78 | 0 | 100
1618 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000053/2021-2022 | 532/BWD | 27/01/2022 | 0 | Resource Division | 15.09 | 0 | 0
1619 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000089/2021-2022 | 901/BWD | 15/02/2022 | 0 | Resource Division | 23.47 | 0 | 0
1620 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000216/2021-2022 | 1539/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
1621 | Burdwan Division | Burdwan Sadar Sub-Division | Conversion of ACSR Cond to AB CABL of 11KV Shyamsundar Feeder Emanating from Raina S/STN at Shyamsundar PWSS under Burdwan Division, PHE Dte. [Ref ID-860250397, Application ID-100000060727, dt.-16/09/2022] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | VCH/000551/2022-2023 | 653/DW/22-23 | 28/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.08 | 0 | 0
1622 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
1623 | Burdwan Division | Kalna Sub-division | Quotation from WBSEDCL for load enhancement of Kaigram water supply scheme for P.H.-1 & 2 under Burdwan Division, PHE Dte. | Assistant Engineer |  | BILL/00549/2024-2025 | 732/JJM | 27/08/2024 | 0 | WBSEDCL | 5.01 | 0 | 0
1624 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell site for KAIGRAM Piped Water Supply Scheme, Block - Monteswar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | Assistant Engineer |  | ORD/000011/2022-2023 | 1959/BWD | 12/04/2022 | 45 | ACME CONSTRUCTION | 14.81 | 0 | 100
1625 | Burdwan Division | Kalna Sub-division | Augmentation of KAIGRAM Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction 250 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Construction of Boundary wall under Kalna Sub-Division, Block - Monteswar, Dist. - Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000436/2021-2022 | 697/BWD | 02/02/2022 | 365 | B.B.C. ENTERPRISE | 291.4 | 0 | 80
1626 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Kaigram W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No- E) | Assistant Engineer |  | ORD/000517/2021-2022 | 185/KSD | 21/02/2022 | 21 | LEMNISCATE | 2.66 | 0 | 1
1627 | Burdwan Division | Kalna Sub-division | Work Order for "Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site for Augmentation of Kaigram Piped Water Supply Scheme (SM/09717) within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer |  | ORD/001186/2023-2024 | 2190/KSD | 15/03/2024 | 10 | PARTHA PRATIM ACHARYA | 4.56 | 0 | 100
1628 | Burdwan Division | Kalna Sub-division | Work Order for " Renovation of Pump House for Augmentation of Kaigram Piped Water Supply Scheme (SM/09717) under Kalna Sub-Division under Burdwan Division, PHE Dte. (1 no Pump House Repairing)" | Assistant Engineer |  | ORD/001193/2023-2024 | 2203/KSD | 18/03/2024 | 10 | PARTHA PRATIM ACHARYA | 1.28 | 0 | 100
1629 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000032/2021-2022 | 533/BWD | 27/01/2022 | 0 | Resource Division | 16.17 | 0 | 0
1630 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000079/2021-2022 | 605/BWD | 28/01/2022 | 0 | Resource Division | 24.12 | 0 | 0
1631 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000106/2021-2022 | 905/BWD | 15/02/2022 | 0 | Resource Division | 12.41 | 0 | 0
1632 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000239/2021-2022 | 1563/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
1633 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
1634 | Central Mechanical | Kalna Sub-division | Quotation for new service connection (Load enhancement) at Kaigram PWSS PH-2. | Assistant Engineer |  | BILL/00461/2024-2025 |  | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.48 | 0 | 0
1635 | Central Mechanical | Kalna Sub-division | Quotation for new service connection (Load enhancement) at Kaigram PWSS PH-1. | Assistant Engineer |  | BILL/00462/2024-2025 |  | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.53 | 0 | 0
1636 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of Kaigram Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer |  | ORD/000067/2023-2024 | 2564/CMD | 06/06/2023 | 30 | CHOUDHURY ENTERPRISE | 20.45 | 0 | 98
1637 | Burdwan Division | Central Mechanical Sub-Division | Quotation from WBSEDCL for new service connection of Augmentation of ground water based Ketugram Zone-I PWSS. | Assistant Engineer | Junior Engineer | BILL/00516/2024-2025 | 688/JJM | 14/08/2024 | 0 | WBSEDCL | 9.28 | 0 | 0
1638 | Burdwan Division | Central Mechanical Sub-Division | Sinking of additional 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Augmentation of KETUGRAM (ZONE-I) Piped Water Supply Scheme, Block - Ketugram - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | Assistant Engineer | Junior Engineer | ORD/000067/2022-2023 | 2420/BWD | 11/05/2022 | 45 | AUXILIARY TUBE WELL DRILLERS | 23.9 | 0 | 100
1639 | Burdwan Division | Central Mechanical Sub-Division | Sinking of additional 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Augmentation of KETUGRAM (ZONE-II) Piped Water Supply Scheme, Block - Ketugram - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [3 Nos. GTW]. | Assistant Engineer | Junior Engineer | ORD/000068/2022-2023 | 2421/BWD | 11/05/2022 | 965 | AUXILIARY TUBE WELL DRILLERS | 35.85 | 0 | 80
1640 | Burdwan Division | Central Mechanical Sub-Division | Augmentation of KETUGRAM ZONE-II Piped Water Supply Scheme with LDS, FHTC, & Construction of 1250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under Ketugram-II Block, District:- Purba-Burdwan. | Assistant Engineer | Junior Engineer | ORD/000125/2022-2023 | 2996/BWD | 05/07/2022 | 880 | S & P ENTERPRISE | 1064.91 | 0 | 90
1641 | Burdwan Division | Central Mechanical Sub-Division | Augmentation of KETUGRAM ZONE-I (PART-A & PART-B) Piped Water Supply Scheme with LDS, FHTC, & Construction of 700 cum & 200 Cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation respectively under Ketugram-I Block, District:- Purba-Burdwan. | Assistant Engineer | Junior Engineer | ORD/000149/2022-2023 | 3075/BWD | 11/07/2022 | 1135 | M/S S.S. ENTERPRISE | 930.6 | 0 | 70
1642 | Burdwan Division | Central Mechanical Sub-Division | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000288/2024-2025 | 2741/BWD | 12/07/2024 | 538 | M/S M.M. ENTERPRISE | 205.15 | 0 | 65
1643 | Burdwan Division | Central Mechanical Sub-Division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Baharan-Birampur, Kaithan, Majhigram-Sigot & Ketugram (Zone-I & II) Piped Water Supply Scheme within Katwa Sub-Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 4702/BWD | 19/10/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 0 | 1
1644 | Burdwan Division | Central Mechanical Sub-Division | Route Survey and Preparation of DPR for KETUGRAM (ZONE-I & II ) PWSS under Ketugram-I & II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-06] | Assistant Engineer | Junior Engineer | ORD/000547/2021-2022 | 66/KTS | 27/01/2022 | 21 | RADIANT | 4.81 | 0 | 1
1645 | Burdwan Division | Central Mechanical Sub-Division | Inter connection work with MS pipe from OHR to Distribution system and restoration of village road and drains for Augmentation of KETUGRAM Z-II Piped Water Supply Scheme under Ketugram-II Block, Dist-Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000909/2023-2024 | 5481/BWD | 13/12/2023 | 354 | S & P ENTERPRISE | 181.31 | 0 | 40
1646 | Burdwan Division | Central Mechanical Sub-Division | Continuation work order for Supply of 1 (one) No. Diesel driven Ambassador Car (Luxury Taxi) / Motor Cab on hire basis for the Office of the Assistant Engineer, under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.01.2025 to 30.06.2025]. | Assistant Engineer | Junior Engineer | ORD/001026/2024-2025 | 1810/KTS | 31/12/2024 | 181 | KRISHNA MONDAL | 2.4 | 0 | 20
1647 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000012/2022-2023 | 3271/BWD | 29/07/2022 | 0 | Resource Division | 50.19 | 0 | 0
1648 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000035/2022-2023 | 4631/BWD | 17/10/2022 | 0 | Resource Division | 0.06 | 0 | 0
1649 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000156/2021-2022 | 1248/BWD | 07/03/2022 | 0 | Resource Division | 4.32 | 0 | 0
1650 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000176/2021-2022 | 1334/BWD | 08/03/2022 | 0 | Resource Division | 114.05 | 0 | 0
1651 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000227/2021-2022 | 1549/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
1652 | Burdwan Division | Central Mechanical Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
1653 | Central Mechanical | Central Mechanical Sub-Division | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 3 of Kandra [ Ketugram ] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [ Block - Ketugram-I ] | Assistant Engineer | Junior Engineer | ORD/000007/2022-2023 | 1170/CMD | 27/06/2022 | 365 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.38 | 0 | 1
1654 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Ketugram (Zone - I) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000062/2023-2024 | 2569/CMD | 06/06/2023 | 30 | M/S, MONDAL ASSOCIATES. | 10.98 | 0 | 0
1655 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 3 at Augumentation of Ketugram (Zone - II) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000077/2023-2024 | 2573/CMD | 06/06/2023 | 30 | SOUNAK ENTERPRISE | 21.96 | 0 | 40
1656 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Augmentation of Ketugram Water Supply Scheme [Zone-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | Assistant Engineer | Junior Engineer | ORD/000624/2022-2023 | 2098/CMD | 08/09/2022 | 30 | STANDARD ELECTRICALS | 11.51 | 0 | 1
1657 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of Borshul (Zone-II) (Mouzas :- Belna, Manikhati, Jafrabad, Kalinagar, Baje Salepur, Totopara) Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under BARDHAMAN- II Block, District:- Purba-Burdwan. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000151/2022-2023 | 3101/BWD | 14/07/2022 | 898 | ASHOK KUMAR GHOSH | 342.55 | 0 | 80
1658 | Burdwan Division | Burdwan Sadar Sub-Division | Improvement works of Borshul Godown & other allied works under Augmentation of BORSHUL (Zone-II) PWSS in Bardhaman-II Block. (SM/10481) within Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000187/2024-2025 | 2418/BWD | 27/06/2024 | 90 | ANWESHA CONSTRUCTION | 20.86 | 0 | 0
1659 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BELNA Mouza & Head Works Site for BORSHUL (Zone-II) Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000206/2023-2024 | 2709/BWD | 08/06/2023 | 45 | M/S D. PALIT & CO. | 19.82 | 0 | 100
1660 | Burdwan Division | Burdwan Sadar Sub-Division | Improvement works including repairing & remodelling of Borshul Inspection Banglow under Augmentation of BORSHUL (Zone-II) PWSS in Bardhaman-II Block. (SM/10481) within Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000285/2024-2025 | 2971/BWD | 31/07/2024 | 90 | ESCON INDIA | 15.27 | 0 | 100
1661 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
1662 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall at 2nd T/W Site (Belna-Mouza) of BARSUL Zone II Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. (Length =100.00 Mtr, Col-36 Nos). | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000487/2024-2025 | 3142/BWD | 20/08/2024 | 134 | PANCHANAN CHAKROBORTY | 6.77 | 0 | 100
1663 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Borsul (Zone-I) & (Zone-II) W/S Scheme under Burdwan-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000510/2021-2022 | 176/BSD | 31/01/2022 | 30 | APEX ENGINEERING | 4.18 | 0 | 1
1664 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of 3.6mtr.x3.0mtr.Size pump house including plinth protection with surface drain at Head Work TW site for Borshul (Zone-II) Water Supply Scheme, Block: Burdwan-II within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000589/2023-2024 | 2042/BSD | 24/08/2023 | 45 | RAHAMAN ENTERPRISE | 4.84 | 0 | 100
1665 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for BARSUL ZONE-II its Adjoining Mouza W/S Scheme, Block -BURDWAN-II within Burdwan Sub-Division, PHE Dte. (Mouza- Belna) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000772/2022-2023 | 509/BSD | 21/03/2023 | 45 | MOHAMMAD ISSA | 3.49 | 0 | 100
1666 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch room, rising main & Sinking of Tube-well at 3rd TW SITE for BARSHUL Zone-II Piped Water Supply Scheme under BARDHAMAN-II Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001101/2023-2024 | 1128/BWD | 14/03/2024 | 292 | M/S R.K. SAMANTA & CO. | 19.02 | 0 | 100
1667 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000045/2022-2023 | 4852/BWD | 20/10/2022 | 0 | Resource Division | 12.32 | 0 | 0
1668 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new service connection at Borsul W/S Scheme Zone-II, PH-III. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/00862/2024-2025 | BP-2024-25-334 | 04/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.86 | 0 | 0
1669 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Borshul PWSS Z-II TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/01414/2023-2024 | BP-2023-24-140 | 28/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.99 | 0 | 0
1670 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Borshul PWSS ZONE-II, TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/01827/2023-2024 | BP-2023-24-335 | 06/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.11 | 0 | 0
1671 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring of Tube Well No- 01, 02 & 03 at Augmentation Borsul (Zone-II) [Block ¿Burdwan -2] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000914/2023-2024 | 4178/CMD | 29/08/2023 | 491 | M/S, S.S. ENTERPRISE. | 35.95 | 0 | 100
1672 | Burdwan Division | Burdwan Sadar Sub-Division | Quotation of New connection charges at Augmentation of Mondalgram water supply scheme. [Application No.-5003701437] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/00065/2023-2024 | 152/JJM | 26/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.64 | 0 | 0
1673 | Burdwan Division | Burdwan Sadar Sub-Division | Additional quotation for Untia PHE of Augmentation of Mondalgram water supply scheme.[Memo No.-SGA/ADDL/QUOTI, Dated-21/06/23] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/00239/2023-2024 | 358/JJM | 14/07/2023 | 0 | WEST BENGAL BUILDING AND OTHER CONSTRUCTION WORKERS WELFARE FUND | 2.16 | 0 | 0
1674 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mondalgram Piped Water Supply Scheme at Mondalgram (10 Nos Habitation) Village (Mouza), Memari-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000111/2021-2022 | 3879/BWD | 27/07/2021 | 60 | SUPRIYA RAY | 102.04 | 0 | 1
1675 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MONDALGRAM Piped Water Supply Scheme at Bamunia (Part) (4 Nos. Habs.), Bhigobanpur, Halaodharpur (Part) (2 Nos. Habs.), Mondalgram (Part) (10 Nos. Habs.), Saragachi & Malamba Village (Mouza), Memari - II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000479/2021-2022 | 994/BWD | 21/02/2022 | 60 | SUPRIYA RAY | 61.24 | 0 | 70
1676 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) of MONDALGRAM & its adjoining mouzas Piped Water Supply Scheme, Block ? Memari ? II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000554/2022-2023 | 5196/BWD | 24/11/2022 | 30 | ANIRUDDHA FARUQUE | 11.24 | 0 | 1
1677 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of UPVC water supply line for Mondalgram and its adjoining mouzas W/S. Scheme within Memari- II Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000614/2021-2022 | 1576/BWD | 16/03/2022 | 30 | PAPRI HAZRA | 10.41 | 0 | 1
1678 | Burdwan Division | Burdwan Sadar Sub-Division | Left out Functional House hold Tap Connection (FHTC) for MONDALGRAM and its adjoining Mouza W/S Scheme, block ¿Memari II within Burdwan Sub-Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000773/2022-2023 | 1326/BWD | 22/03/2023 | 60 | DEBASHISH ENTERPRISE | 30.33 | 0 | 35
1679 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for MONDALGRAM its Adjoining Mouza W/S Scheme, Block -Memari-II within Burdwan Sub-Division, PHE Dte. (Mouza- Untia) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000840/2022-2023 | 508/BSD | 21/03/2023 | 45 | NARSAD SAIKH | 3.12 | 0 | 100
1680 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KACHUA & KAMALPUR Piped Water Supply Scheme under Purbasthali ¿ I Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000133/2023-2024 | 2344/BWD | 22/05/2023 | 863 | CONCORD ENGINEERING | 470.92 | 0 | 40
1681 | Burdwan Division | Durgapur Sub-DIvision | Different types of works involve in connection with Augmentation of SRIRAMPUR (Zone I & II) (SM/08103), MANGANPUR (SM/13327), KAMALPUR (SM/13453) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000190/2024-2025 | 2429/BWD | 27/06/2024 | 480 | S.P. CONSTRUCTION | 500.89 | 0 | 2
1682 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000502/2023-2024 | 4026/BWD | 08/09/2023 | 0 | Resource Division | 0.98 | 0 | 0
1683 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Kamalpur PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02215/2023-2024 | BP-2023-24-388 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.38 | 0 | 0
1684 | Central Mechanical | Durgapur Sub-DIvision | New service connection for KAMALPUR PWSS TW-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02399/2023-2024 | BP-2023-24-501 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.24 | 0 | 0
1685 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at KAMALPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000813/2023-2024 | 4095/CMD | 29/08/2023 | 519 | MUKHERJEE ART CENTRE | 21.4 | 0 | 100
1686 | Burdwan Division | Burdwan Sadar Sub-Division | Rest portion of OHR (Plaster, Painting and interconnection of Rising Main with Specials) at SAHAPUR Piped Water Supply Scheme under Memari-I Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000188/2024-2025 | 2419/BWD | 27/06/2024 | 90 | S.K. CONSTRUCTION | 20.6 | 0 | 100
1687 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
1688 | Burdwan Division | Burdwan Sadar Sub-Division | Designing,making and erection of Sign Board for SWAJAL GRAM in Nagarkona village of Memari-I Block under Sahapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte (5 Nos. Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000441/2025-2026 | 2306/BSD | 19/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0
1689 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, making and erection of Sign Board for SWAJAL GRAM in Sahapur village of Memari-I Block under Sahapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000471/2025-2026 | 2337/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0
1690 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, making and erection of Sign Board for SWAJAL GRAM in Sekhpur village of Memari-I Block under Sahapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000614/2025-2026 | 2370/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0
1691 | Burdwan Division | Burdwan Sadar Sub-Division | SAHAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000636/2022-2023 | 82/BWD | 09/01/2023 | 365 | S.K. CONSTRUCTION | 256.31 | 0 | 100
1692 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000067/2022-2023 | 1262/BWD | 17/03/2023 | 0 | Resource Division | 7.32 | 0 | 0
1693 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000500/2023-2024 | 4024/BWD | 08/09/2023 | 0 | Resource Division | 2.93 | 0 | 0
1694 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000690/2023-2024 | 5074/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1695 | Central Mechanical | Burdwan Sadar Sub-Division | New Service Connection charges for Sahapur W/S Scheme TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00602/2023-2024 | BP-2023-24-13 | 17/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.9 | 0 | 0
1696 | Central Mechanical | Burdwan Sadar Sub-Division | New Service Connection charges for Sahapur W/S Scheme TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00603/2023-2024 | BP-2023-24-14 | 17/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.08 | 0 | 0
1697 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sahapur Water Supply Scheme [Block- Memari-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000037/2023-2024 | 2480/CMD | 31/05/2023 | 30 | P.K. ENGINEERING | 29.29 | 0 | 98
1698 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0
1699 | Burdwan Division | Burdwan Sadar Sub-Division | Shifting of pole for laying of water supply pipeline of Baikunthapur pwss under Burdwan Division, PHE Dte. [Ref ID-860315315, Application ID-100000120685, dt.-01/10/2024] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01091/2024-2025 | 1173/JJM | 17/12/2024 | 0 | WBSEDCL | 0.89 | 0 | 0
1700 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA & BAIKUNTHAPUR Piped Water Supply Scheme under Burdwan II Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000089/2023-2024 | 2214/BWD | 15/05/2023 | 839 | CONCORD ENGINEERING | 750.87 | 0 | 55
1701 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000020/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 4.39 | 0 | 0
1702 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000218/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 1.97 | 0 | 0
1703 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000707/2023-2024 | 5044/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1704 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection at BAIAKUNTHAPUR PWSS Ph-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02325/2023-2024 | BP-2023-24-442 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.45 | 0 | 0
1705 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection at BAIAKUNTHAPUR PWSS Ph-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02326/2023-2024 | BP-2023-24-443 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.73 | 0 | 0
1706 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Baikunthapur PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02940/2023-2024 | BP-2023-24-517 | 08/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.48 | 0 | 0
1707 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 12
1708 | Central Mechanical | Burdwan Sadar Sub-Division | Hiring of inspection vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of the Assistant Engineer,under CMD PHE Dte. w.e.f -01/08/2024 to 30/09/2024 .[Under JJM Works] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000418/2024-2025 | 834/CMSD | 07/06/2024 | 61 | PRODYUT GHOSH | 0.8 | 0 | 0
1709 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Baikunthapur Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000663/2023-2024 | 4006/CMD | 29/08/2023 | 30 | A.S. ENTERPRISE | 28.95 | 0 | 100
1710 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA & BAIKUNTHAPUR Piped Water Supply Scheme under Burdwan II Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000089/2023-2024 | 2214/BWD | 15/05/2023 | 839 | CONCORD ENGINEERING | 750.87 | 0 | 55
1711 | Burdwan Division | Durgapur Sub-DIvision | Continuation Work for the supply of one no. Diesel driven Motor Cab/Maxi Cab (Air Conditioner) on hire basis for the office of the Assistant Engineer, to be used by the Assistant Engineer, RWS Burdwan Sub-Divn., PHE. Dte. (Period from 01/05/2024 to 30/06/2024) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000151/2024-2025 | 154/RWS | 29/04/2024 | 61 | MD HASIN | 0.8 | 0 | 0
1712 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000018/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.95 | 0 | 0
1713 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000701/2023-2024 | 5060/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1714 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000771/2023-2024 | 195/BWD | 10/01/2024 | 0 | Resource Division | 5.52 | 0 | 0
1715 | Central Mechanical | Durgapur Sub-DIvision | New Service connection forAmra PWSS TW-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02336/2023-2024 | BP-2023-24-473 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 16.94 | 0 | 0
1716 | Central Mechanical | Durgapur Sub-DIvision | New Service connection for Amra PWSS TW-1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02337/2023-2024 | BP-2023-24-472 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.51 | 0 | 0
1717 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 12
1718 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Amra Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000672/2023-2024 | 4005/CMD | 29/08/2023 | 642 | S.K. ENTERPRISE | 28.98 | 0 | 85
1719 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA, BALABATI, UKHRID & RUPSA Piped Water Supply Scheme under KHANDAGHOSH Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000008/2023-2024 | 1726/BWD | 13/04/2023 | 902 | S.P. CONSTRUCTION | 1710.27 | 0 | 45
1720 | Burdwan Division | Durgapur Sub-DIvision | FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING LAND DESCRIPTION AT RUPSA PWSS AND OTHER SCHEMES (49 Nos.) WITHIN KHANDOGHOSH BLOCK UNDER BURDWAN DIVISION , PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000947/2024-2025 | 1086/DSD | 11/12/2024 | 15 | SOUMYAVASH DAS | 3.18 | 0 | 100
1721 | Burdwan Division | Durgapur Sub-DIvision | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001180/2023-2024 | 995/DSD | 29/12/2023 | 183 | SUJAUDDIN SEKH | 2 | 0 | 60
1722 | Burdwan Division | Durgapur Sub-DIvision | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BALABATI, AMRA & RUPSA W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001189/2024-2025 | 609/BWD | 11/02/2025 | 120 | M/S S.S. ENTERPRISE | 194.58 | 0 | 0
1723 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000079/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 8.1 | 0 | 0
1724 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000199/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 20.06 | 0 | 0
1725 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000731/2023-2024 | 5238/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
1726 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at RUPSA PWSS PH-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00384/2024-2025 | BP-2024-25-201 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0
1727 | Central Mechanical | Durgapur Sub-DIvision | New service connection for Rupsa W/S scheme TW No-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02275/2023-2024 | BP-2023-24-410 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0
1728 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0
1729 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Rupsa Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000706/2023-2024 | 4013/CMD | 29/08/2023 | 30 | SAIKAT ENTERPRISE | 28.98 | 0 | 85
1730 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Demarcation of new land of PHE site under various places (Jadabganj PWSS) under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000133/2024-2025 | 1243/DWSD | 29/08/2024 | 30 | SAIKAT RAY | 28.57 | 0 | 80
1731 | Durgapur W/S Division | Durgapur Sub-DIvision | Continution Work Order for Demarcation of new land of PHE site under various places (Jadabganj PWSS) under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000143/2024-2025 | 1312/DWSD | 12/09/2024 | 15 | SAIKAT RAY | 28.57 | 0 | 70
1732 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000727/2023-2024 | 4581/BWD | 16/10/2023 | 965 | SAFECO ENTERPRISES | 1551.98 | 0 | 60
1733 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000285/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.54 | 0 | 0
1734 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000552/2023-2024 | 4285/BWD | 29/09/2023 | 0 | Resource Division | 47.1 | 0 | 0
1735 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000579/2023-2024 | 4927/BWD | 10/11/2023 | 0 | Resource Division | 36.98 | 0 | 0
1736 | Central Mechanical | Durgapur Sub-DIvision | QUOTATION FOR NEW SERVICE CONNECTION AT JADABGANJ PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00370/2024-2025 | BP-2024-25-191 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0
1737 | Central Mechanical | Durgapur Sub-DIvision | New service connection at Jadabganj PWSS PH-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02313/2023-2024 | BP-2023-24-432 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.24 | 0 | 0
1738 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0
1739 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Jadabganj Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000767/2023-2024 | 4065/CMD | 29/08/2023 | 620 | M/S. SWAPAN BANERJEE | 27.78 | 0 | 96
1740 | Burdwan Division | Durgapur Sub-DIvision | EORA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000062/2023-2024 | 1936/BWD | 24/04/2023 | 865 | TUSHAR KANTI GHOSH | 79.02 | 0 | 100
1741 | Burdwan Division | Durgapur Sub-DIvision | Road Restoration for Eora PWSS in Bhatar Block under Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000429/2024-2025 | 624/DSD | 05/08/2024 | 30 | KOHINOOR CONSTRUCTION CO. | 5.38 | 0 | 0
1742 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000187/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 23.59 | 0 | 0
1743 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000443/2023-2024 | 3833/BWD | 01/09/2023 | 0 | Resource Division | 3.71 | 0 | 0
1744 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000750/2023-2024 | 5249/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0
1745 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR EORA PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02596/2023-2024 | BP-2023-24-548 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.64 | 0 | 0
1746 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR EORA PWSS TW -1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/03102/2023-2024 | BP-2023-24-642 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.54 | 0 | 0
1747 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
1748 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Eora Water Supply Scheme [ Block- Bhatar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000746/2023-2024 | 4056/CMD | 29/08/2023 | 990 | SUNRISE ENGINEERING CORPORATION | 26.98 | 0 | 90
1749 | Burdwan Division | Central Mechanical Sub-Division | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | Assistant Engineer | Junior Engineer | ORD/000683/2024-2025 | 1009/KTS | 19/07/2024 | 60 | AJIT SAMANTA | 0.77 | 0 | 100
1750 | Burdwan Division | Central Mechanical Sub-Division | KALIKAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | Junior Engineer | ORD/000732/2022-2023 | 1047/BWD | 09/03/2023 | 968 | PASCON | 629.59 | 0 | 67
1751 | Burdwan Division | Central Mechanical Sub-Division | Balance work of OHR, Functional Household Tap Connection, Road restoration etc. for Kalikapur PWSS under KATWA -II Block under Katwa Sub-Division under Burdwan Division, PHED, District:- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/001040/2024-2025 | 192/BWD | 08/01/2025 | 662 | PASCON | 57.78 | 0 | 90
1752 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000063/2022-2023 | 1259/BWD | 17/03/2023 | 0 | Resource Division | 17.21 | 0 | 0
1753 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000111/2022-2023 | 1645/BWD | 06/04/2023 | 0 | Resource Division | 14.26 | 0 | 0
1754 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Kalikapur PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01444/2023-2024 | BP-2023-24-155 | 07/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.07 | 0 | 0
1755 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Kalikapur PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01469/2023-2024 | BP-2023-24-170 | 27/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0
1756 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0
1757 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kalikapur Water Supply Scheme [ Block- Katwa-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000596/2023-2024 | 3953/CMD | 24/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 29.61 | 0 | 90
1758 | Burdwan Division | Central Mechanical Sub-Division | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day.(Sl No-1) | Assistant Engineer | Junior Engineer | ORD/000510/2023-2024 | 499/KTS | 22/05/2023 | 70 | M/S MUNMUN DEY | 0.9 | 0 | 100
1759 | Burdwan Division | Central Mechanical Sub-Division | SRIBATI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000710/2022-2023 | 776/BWD | 24/02/2023 | 1253 | MANASH GHOSH | 629.32 | 0 | 80
1760 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000061/2022-2023 | 1258/BWD | 17/03/2023 | 0 | Resource Division | 17.24 | 0 | 0
1761 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000110/2022-2023 | 1633/BWD | 06/04/2023 | 0 | Resource Division | 9.14 | 0 | 0
1762 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000787/2023-2024 | 321/BWD | 24/01/2024 | 0 | Resource Division | 26.68 | 0 | 0
1763 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Sribati PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/00755/2023-2024 | BP-2023-24-61 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.58 | 0 | 0
1764 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for SribatiPWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/00881/2023-2024 | BP-2023-24-111 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.83 | 0 | 0
1765 | Central Mechanical | Central Mechanical Sub-Division | SUPPLY AND INSTALLATION WORKS FOR SRIBATI PWSS | Assistant Engineer | Junior Engineer | BILL/02622/2023-2024 | BP-2023-24-559 | 21/02/2024 | 0 | S.K. ELECTRICALS | 23.73 | 0 | 0
1766 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sribati Water Supply Scheme [ Block- Katwa-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000059/2023-2024 | 2520/CMD | 02/06/2023 | 30 | S.K. ELECTRICALS | 29.6 | 0 | 48
1767 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0
1768 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOHAGRAM, KHERUA & JABAGRAM Piped Water Supply Scheme under Mangalkote Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000697/2022-2023 | 582/BWD | 17/02/2023 | 1049 | PUSPA ENTERPRISE | 1185.88 | 0 | 75
1769 | Burdwan Division | Central Mechanical Sub-Division | Continuation order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. (Sl No-1) | Assistant Engineer | Junior Engineer | ORD/000930/2023-2024 | 1016/KTS | 20/09/2023 | 23 | M/S MUNMUN DEY | 0.3 | 0 | 0
1770 | Burdwan Division | Central Mechanical Sub-Division | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001301/2024-2025 | 936/BWD | 11/03/2025 | 180 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0
1771 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000060/2022-2023 | 1257/BWD | 17/03/2023 | 0 | Resource Division | 13.53 | 0 | 0
1772 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000112/2022-2023 | 1646/BWD | 06/04/2023 | 0 | Resource Division | 1.65 | 0 | 0
1773 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000703/2023-2024 | 5061/BWD | 23/11/2023 | 0 | Resource Division | 19.78 | 0 | 0
1774 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR JABAGRAM PWSS TW-2. | Assistant Engineer | Junior Engineer | BILL/00008/2024-2025 | BP-2024-25-1 | 04/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.75 | 0 | 0
1775 | Central Mechanical | Central Mechanical Sub-Division | New Service connection charges for Jabagram W/S Scheme TW-I | Assistant Engineer | Junior Engineer | BILL/00572/2023-2024 | BP-2023-24-8 | 12/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.81 | 0 | 0
1776 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JABAGRAM Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000035/2023-2024 | 2472/CMD | 30/05/2023 | 570 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 28.96 | 0 | 88
1777 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
1778 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch room, boundary walls with gates, land development, surface drains and internal pathways at different TW site for KASHIARA Piped Water Supply Scheme under BURDWAN I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000480/2023-2024 | 256/BWD | 09/08/2023 | 836 | PUSPA ENTERPRISE | 597.52 | 0 | 70
1779 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000098/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.83 | 0 | 0
1780 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000317/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.97 | 0 | 0
1781 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000722/2023-2024 | 5265/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
1782 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Kashiara W/S Scheme. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02189/2023-2024 | BP-2023-24-384 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.91 | 0 | 0
1783 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Kashiara PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02207/2023-2024 | BP-2023-24-398 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.22 | 0 | 0
1784 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
1785 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kashiara Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000656/2023-2024 | 3999/CMD | 29/08/2023 | 30 | MENAKA ENTERPRISE. | 28.98 | 0 | 90
1786 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARASAT, JAGADABAD & KHAIDYA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000465/2023-2024 | 3460/BWD | 08/08/2023 | 783 | CONCORD EMC ENCLAVE LLP | 1526.24 | 0 | 5
1787 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation for the work of Supply of one No. Diesel Driven Car (other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub- Division, PHE Dte. (Period from 01-11-2025 to 31-12-2025). | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000751/2025-2026 | 239/RWS | 31/10/2025 | 61 | MD HASIN | 0.8 | 0 | 0
1788 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000094/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 8.29 | 0 | 0
1789 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000286/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.21 | 0 | 0
1790 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000718/2023-2024 | 5274/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
1791 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR JAGDABAD PWSS PH-1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02872/2023-2024 | BP-2023-24-609 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.65 | 0 | 0
1792 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR JAGDABAD PWSS PH-2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02873/2023-2024 | BP-2023-24-608 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.21 | 0 | 0
1793 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
1794 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Jagadbad Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000654/2023-2024 | 3997/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 28.93 | 0 | 0
1795 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 1
1796 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000009/2024-2025 | 1724/J/DWSD | 10/12/2024 | 0 | Resource Division | 11.03 | 0 | 0
1797 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KHANDARI & CHHORA Piped Water Supply Scheme under Ausgram II Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000735/2022-2023 | 1005/BWD | 06/03/2023 | 696 | M/S NATIONAL CONSTRUCTION | 1331.54 | 0 | 100
1798 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000038/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 65.98 | 0 | 0
1799 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000082/2022-2023 | 1267/BWD | 17/03/2023 | 0 | Resource Division | 13.39 | 0 | 0
1800 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000378/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.58 | 0 | 0
1801 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000636/2023-2024 | 5104/BWD | 23/11/2023 | 0 | Resource Division | 21.42 | 0 | 0
1802 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Khandari PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00721/2023-2024 | BP-2023-24-49 | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.71 | 0 | 0
1803 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Khandari PWSS TW 2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00816/2023-2024 | BP-2023-24-98 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.97 | 0 | 0
1804 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khandari Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000045/2023-2024 | 2508/CMD | 02/06/2023 | 30 | CHOUDHURY ENTERPRISE | 27.79 | 0 | 98
1805 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KALIGRAM & PALITPUR Piped Water Supply Scheme under Burdwan I Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000499/2023-2024 | 3532/BWD | 10/08/2023 | 722 | SUPRITI ENTERPRISE | 704.5 | 0 | 50
1806 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000009/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 5.23 | 0 | 0
1807 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000361/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.42 | 0 | 0
1808 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000728/2023-2024 | 5275/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
1809 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Palitpur PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01671/2023-2024 | BP-2023-24-228 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.84 | 0 | 0
1810 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Palitpur PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01672/2023-2024 | BP-2023-24-229 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.84 | 0 | 0
1811 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
1812 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Palitpur Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000661/2023-2024 | 4004/CMD | 29/08/2023 | 703 | SUBRATA BHADRA | 28.96 | 0 | 90
1813 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA, BALABATI, UKHRID & RUPSA Piped Water Supply Scheme under KHANDAGHOSH Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000008/2023-2024 | 1726/BWD | 13/04/2023 | 902 | S.P. CONSTRUCTION | 1710.27 | 0 | 45
1814 | Burdwan Division | Burdwan Sadar Sub-Division | Surveying, planning, design, drawing and construction of pipe carrying structural bridge for carrying 200 mm. dia. D.I. Pipe line at AMRA Piped W/S. Scheme, Khandaghosh Dev. Block under Durgapur (Burdwan North) Sub-Division, PHE. Dte. within Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000831/2024-2025 | 4085/BWD | 22/11/2024 | 361 | S.P. CONSTRUCTION | 149.75 | 0 | 25
1815 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BALABATI, AMRA & RUPSA W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001189/2024-2025 | 609/BWD | 11/02/2025 | 120 | M/S S.S. ENTERPRISE | 194.58 | 0 | 0
1816 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000194/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 15.41 | 0 | 0
1817 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000702/2023-2024 | 5049/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1818 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Amra PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01474/2023-2024 | BP-2023-24-172 | 29/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.84 | 0 | 0
1819 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Amra PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01475/2023-2024 | BP-2023-24-173 | 29/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.42 | 0 | 0
1820 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 10
1821 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & fitting fixing of FASD motor starter (for urgent FHTC) for Tube well no.-I & II at Amra water supply scheme, (Block- Khandaghosh) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000268/2024-2025 | 743/CMSD | 13/05/2024 | 10 | M/S. SWAPAN BANERJEE | 0.6 | 0 | 100
1822 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Amra Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000678/2023-2024 | 4010/CMD | 29/08/2023 | 30 | M/S. SWAPAN BANERJEE | 28.98 | 0 | 100
1823 | Burdwan Division | Central Mechanical Sub-Division | Balance work of OHR, construction Concrete Road, Drum Sheet Pilling, Functional Household Tap Connection, construction of HUME Pipe culvert, land development, Road restoration etc. under Billeswar PWSS, Purulia PWSS & Gurpara PWSS under KATWA -II Block under Katwa Sub-Divn. under Burdwan Division, PHED. District:- Purba-Bardhaman | Assistant Engineer | Junior Engineer | ORD/000310/2024-2025 | 2834/BWD | 19/07/2024 | 835 | PASCON | 190.06 | 0 | 90
1824 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000162/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 15.02 | 0 | 0
1825 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000490/2023-2024 | 4014/BWD | 08/09/2023 | 0 | Resource Division | 8.73 | 0 | 0
1826 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000597/2023-2024 | 4891/BWD | 10/11/2023 | 0 | Resource Division | 10 | 0 | 0
1827 | Central Mechanical | Central Mechanical Sub-Division | New service connection at Purulia PWSS TW No.1 | Assistant Engineer | Junior Engineer | BILL/02377/2023-2024 | BP-2023-24-492 | 01/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.09 | 0 | 0
1828 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR PURULIA PWSS TW 2. | Assistant Engineer | Junior Engineer | BILL/03136/2023-2024 | BP-2023-24-650 | 20/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.36 | 0 | 0
1829 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0
1830 | Central Mechanical | Central Mechanical Sub-Division | Supply and delivery of 7.5 HP pump motor set at T.W. No - 2 of PURULIA (Block- Ketugram-II) water supply scheme under CMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000733/2024-2025 | 821/DIC/BMSD(D) | 05/12/2024 | 33 | BARMAN ROY TRADERS | 0.67 | 0 | 100
1831 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at PURULIA Water Supply Scheme [Block - KETUGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000823/2023-2024 | 4100/CMD | 29/08/2023 | 665 | BARMAN ROY TRADERS | 21.01 | 0 | 43
1832 | Central Mechanical | Central Mechanical Sub-Division | Increasing of tube well casing and other works at PURULIA PWSS under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/001580/2024-2025 | 151/DIC/BMSD(D) | 04/03/2025 | 7 | BARMAN ROY TRADERS | 0.29 | 0 | 100
1833 | Central Mechanical | Central Mechanical Sub-Division | Supply and delivery of 7.5 HP pump motor set at T.W. No - 1 of PURULIA (Block-Ketugram-II) water supply scheme under CMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001583/2024-2025 | 159/DIC/BMSD(D) | 06/03/2025 | 7 | BARMAN ROY TRADERS | 0.67 | 0 | 100
1834 | Burdwan Division | Central Mechanical Sub-Division | Balance work of OHR, construction Concrete Road, Drum Sheet Pilling, Functional Household Tap Connection, construction of HUME Pipe culvert, land development, Road restoration etc. under Billeswar PWSS, Purulia PWSS & Gurpara PWSS under KATWA -II Block under Katwa Sub-Divn. under Burdwan Division, PHED. District:- Purba-Bardhaman | Assistant Engineer | Junior Engineer | ORD/000310/2024-2025 | 2834/BWD | 19/07/2024 | 835 | PASCON | 190.06 | 0 | 90
1835 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000062/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.83 | 0 | 0
1836 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000153/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.05 | 0 | 0
1837 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000624/2023-2024 | 4870/BWD | 10/11/2023 | 0 | Resource Division | 29.6 | 0 | 0
1838 | Central Mechanical | Central Mechanical Sub-Division | New Service connection for Billwswar PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/02350/2023-2024 | BP-2023-24-466 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.04 | 0 | 0
1839 | Central Mechanical | Central Mechanical Sub-Division | New service connection at Billeswar PWSS TW No.1 | Assistant Engineer | Junior Engineer | BILL/02374/2023-2024 | BP-2023-24-493 | 01/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.28 | 0 | 0
1840 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0
1841 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BILLESWAR Water Supply Scheme [ Block- KETUGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000779/2023-2024 | 4073/CMD | 29/08/2023 | 30 | KAMAKHYA ENTERPRISE | 26.97 | 0 | 88
1842 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related (schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-05-2025 to 31-07-2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000181/2025-2026 | 960/BSD | 30/04/2025 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
1843 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHAGABATIPUR, MACHKHARA & UDGARA Piped Water Supply Scheme under Raina ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000690/2023-2024 | 4386/BWD | 05/10/2023 | 365 | SK ALIM | 1378.97 | 0 | 55
1844 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2024 to 31-01-2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000896/2024-2025 | 2438/BSD | 29/10/2024 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
1845 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 366 | SK ALIM | 1353.91 | 0 | 25
1846 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000207/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 9.24 | 0 | 0
1847 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000535/2023-2024 | 4287/BWD | 29/09/2023 | 0 | Resource Division | 4.57 | 0 | 0
1848 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000699/2023-2024 | 5069/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1849 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Udgram W/S Scheme PH No.-II | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01798/2023-2024 | BP-2023-24-311 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.73 | 0 | 0
1850 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Udgra W/S Scheme PH No.-I | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01799/2023-2024 | BP-2023-24-310 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.13 | 0 | 0
1851 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
1852 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Udgara Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000712/2023-2024 | 4023/CMD | 29/08/2023 | 30 | CHATTERJEE ENTERPRISE | 28.95 | 0 | 0
1853 | Burdwan Division | Durgapur Sub-DIvision | BAZAR MAHAMMADPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000801/2022-2023 | 1529/BWD | 29/03/2023 | 659 | ASHOK MITRA | 537.95 | 0 | 100
1854 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000064/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 32.63 | 0 | 0
1855 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000172/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 4.84 | 0 | 0
1856 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000601/2023-2024 | 4907/BWD | 10/11/2023 | 0 | Resource Division | 33.07 | 0 | 0
1857 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Bazar Mahammadpur PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00883/2023-2024 | BP-2023-24-109 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.85 | 0 | 0
1858 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Bazar Mohammadpur PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01734/2023-2024 | BP-2023-24-250 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.98 | 0 | 0
1859 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
1860 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAZAR MAHAMMADPUR Water Supply Scheme [ Block- BHATAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000235/2023-2024 | 3171/CMD | 26/07/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 27.78 | 0 | 95
1861 | Central Mechanical | Durgapur Sub-DIvision | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000590/2024-2025 | 3105/CMD | 11/12/2024 | 60 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0
1862 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of DIRGHAPARA (SM/07804) Water Supply Scheme, MOUDANGA (SM/ 14020) Water supply Scheme & BHANDARTIKURI (SM/14925) Water Supply Scheme under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000357/2024-2025 | 2912/BWD | 25/07/2024 | 431 | BANSBERIA CONSTRUCTION CO. | 293.38 | 0 | 22
1863 | Burdwan Division | Kalna Sub-division | BHANDARTIKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000758/2022-2023 | 1280/BWD | 20/03/2023 | 90 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. | 65.35 | 0 | 100
1864 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000142/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 15.82 | 0 | 0
1865 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000416/2023-2024 | 3866/BWD | 01/09/2023 | 0 | Resource Division | 0.23 | 0 | 0
1866 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000797/2023-2024 | 312/BWD | 24/01/2024 | 0 | Resource Division | 7.05 | 0 | 0
1867 | Central Mechanical | Kalna Sub-division | New service connection charges for Bhandarituri PWSS TW-1 | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | BILL/01535/2023-2024 | BP-2023-24-202 | 18/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.82 | 0 | 0
1868 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 30
1869 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at BHANDARITURI Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000816/2023-2024 | 4096/CMD | 29/08/2023 | 30 | KAMAKHYA ENTERPRISE | 20.75 | 0 | 60
1870 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000226/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 4.92 | 0 | 0
1871 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000496/2023-2024 | 4020/BWD | 08/09/2023 | 0 | Resource Division | 0.41 | 0 | 0
1872 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000651/2023-2024 | 5113/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1873 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Bamchandrapur PWSS TW-2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02893/2023-2024 | BP-2023-24-626 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.71 | 0 | 0
1874 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Bamchandrapur PWSS TW-1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02894/2023-2024 | BP-2023-24-627 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.75 | 0 | 0
1875 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 12
1876 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bamchandrapur Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000734/2023-2024 | 4044/CMD | 29/08/2023 | 30 | S.K. ENTERPRISE | 30.08 | 0 | 90
1877 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHAGABATIPUR, MACHKHARA & UDGARA Piped Water Supply Scheme under Raina ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000690/2023-2024 | 4386/BWD | 05/10/2023 | 365 | SK ALIM | 1378.97 | 0 | 55
1878 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 366 | SK ALIM | 1353.91 | 0 | 25
1879 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000335/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.92 | 0 | 0
1880 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000536/2023-2024 | 4296/BWD | 29/09/2023 | 0 | Resource Division | 5.11 | 0 | 0
1881 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000675/2023-2024 | 5063/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1882 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Machkhanda PWSS. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/02247/2023-2024 | BP-2023-24-399 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.37 | 0 | 0
1883 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Mackhara PWSS TW-2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/02280/2023-2024 | BP-2023-24-434 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.5 | 0 | 0
1884 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
1885 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Machkhara Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000709/2023-2024 | 4020/CMD | 29/08/2023 | 598 | CHOUDHURY ENTERPRISE | 28.98 | 0 | 85
1886 | Burdwan Division | Central Mechanical Sub-Division | Continuation work order for Supply of 1 (one) No. Diesel driven Ambassador Car (Luxury Taxi) / Motor Cab on hire basis for the Office of the Assistant Engineer, under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.07.2025 to 31.12.2025]. | Assistant Engineer | Junior Engineer | ORD/000319/2025-2026 | 1595/KTS | 30/06/2025 | 184 | KRISHNA MONDAL | 2.4 | 0 | 33
1887 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEULIA, GOBARDHANPUR, KHARIJA-KASHIGRAM & UNIATATARPUR Piped Water Supply Scheme under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000477/2023-2024 | 3491/BWD | 09/08/2023 | 815 | POWER TOOLS & ENGINEERING | 1741.05 | 0 | 10
1888 | Burdwan Division | Central Mechanical Sub-Division | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. | Assistant Engineer | Junior Engineer | ORD/001080/2023-2024 | 22/KTS | 05/01/2024 | 70 | AJIT SAMANTA | 0.9 | 0 | 100
1889 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000111/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 2.74 | 0 | 0
1890 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000383/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 22.26 | 0 | 0
1891 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000811/2023-2024 | 301/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0
1892 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR KHARIJA KASHIGRAM PWSS PH-2 | Assistant Engineer | Junior Engineer | BILL/00192/2024-2025 | BP-2024-25-91 | 17/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.45 | 0 | 0
1893 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Kharija Kashigram PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01770/2023-2024 | BP-2023-24-275 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.81 | 0 | 0
1894 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
1895 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHARIJA KASHIGRAM Water Supply Scheme [ Block-MONGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000778/2023-2024 | 4072/CMD | 29/08/2023 | 640 | SOUNAK ENTERPRISE | 27.79 | 0 | 48
1896 | Burdwan Division | Kalna Sub-division | Quotation from WBSEDCL for new service connection of Ganganandapur w/s scheme. T.W.-3 | Assistant Engineer |  | BILL/00401/2023-2024 | 537/JJM | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.6 | 0 | 0
1897 | Burdwan Division | Kalna Sub-division | Augmentation of GANGANANDAPUR Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 300 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation & construction of pump house ( 3.60mx 3.0m) & boundary wall at new TW site under Purbasthali ¿ I Block, District - Purba Bardhaman. | Assistant Engineer |  | ORD/000019/2022-2023 | 2013/BWD | 18/04/2022 | 1020 | MANASH GHOSH | 421.4 | 0 | 70
1898 | Burdwan Division | Kalna Sub-division | Sinking of additional 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for GANGANANDAPUR Piped Water Supply Scheme, Block - Purbasthali - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000070/2022-2023 | 2424/BWD | 11/05/2022 | 30 | M/S SYCHROTECH INDUSTRY | 9.01 | 0 | 0
1899 | Burdwan Division | Kalna Sub-division | Work Order for " Renovation of Pump house along with laboratory building of Ganganandapur piped water supply scheme in connection with Augmentation of Ganganandapur Piped Water Supply Scheme under Burdwan Division, PHE Dte." | Assistant Engineer |  | ORD/000135/2024-2025 | 318/KSD | 07/06/2024 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 4.31 | 0 | 100
1900 | Burdwan Division | Kalna Sub-division | Work Order for "Additional work in connection with renovation of Pump house and laboratory building of Ganganandapur piped water supply scheme in connection with Augmentation of Ganganandapur Piped Water Supply Scheme under Burdwan Division, PHE Dte." | Assistant Engineer |  | ORD/000136/2024-2025 | 319/KSD | 07/06/2024 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 3.83 | 0 | 100
1901 | Burdwan Division | Kalna Sub-division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Jahannagar, Ganganandapur, Nowapara & Monteswar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, P.H.E. Dte.[Part ¿ A] | Assistant Engineer |  | ORD/000323/2022-2023 | 3632/BWD | 22/08/2022 | 20 | RAMASISH ENTERPRISE | 12.8 | 0 | 1
1902 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 14 Nos. Piped W/S. Schemes under Purbasthali I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000337/2024-2025 | 3017/BWD | 05/08/2024 | 75 | HORIZEN | 38 | 0 | 100
1903 | Burdwan Division | Kalna Sub-division | Interconnection of rising main from 2nd Tube Well site and renovation of boundary wall and pump house at 2nd Tube Well Site of Ganganandapur W/S Scheme within Kalna Sub-Division under Burdwan Division , PHE Dte. (Sl No-C) | Assistant Engineer |  | ORD/000449/2021-2022 | 88/KSD | 21/01/2022 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 1.2 | 0 | 1
1904 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Ganganandapur W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-E) | Assistant Engineer |  | ORD/000571/2021-2022 | 207/KSD | 23/02/2022 | 21 | ROY CHOWDHURY ASSOCIATES | 2.84 | 0 | 1
1905 | Burdwan Division | Kalna Sub-division | Work Order for "Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory under The Assistant Engineer, Kalna Sub- Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation,Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL : Ganganandapur Sub District Water Testing Laboratory under Kalna Sub Division)". | Assistant Engineer |  | ORD/000671/2023-2024 | 1334/KSD | 28/08/2023 | 30 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.51 | 0 | 1
1906 | Burdwan Division | Kalna Sub-division | Additional works to implement the GANGANANDAPUR Piped Water Supply Scheme under Purbasthali-I Block, Dist :- Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000707/2022-2023 | 754/BWD | 23/02/2023 | 60 | MANASH GHOSH | 76.57 | 0 | 85
1907 | Burdwan Division | Kalna Sub-division | Construction of Pump House cum switch room (5.40 mtr x 3.60 mtr) with sanitary arrangement (as per drawing no. PHE/SE/CC/PH/DWG-01/2022-2023) at GANGANANDAPUR Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | Assistant Engineer |  | ORD/000708/2023-2024 | 4481/BWD | 11/10/2023 | 60 | LOKNATH ENTERPRISE | 6.31 | 0 | 0
1908 | Burdwan Division | Kalna Sub-division | Work Order for " Renovation of boundary wall in connection with Augmentation of Ganganandapur Water Supply Scheme (SM/09411) within Kalna Sub-Division under Burdwan Division, PHE Dte. (Length - 170 Mtr). - 2 Nos". | Assistant Engineer |  | ORD/000801/2024-2025 | 1778/KSD | 20/11/2024 | 30 | UNIQUE CONSTRUCTION | 4.55 | 0 | 100
1909 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000036/2021-2022 | 553/BWD | 27/01/2022 | 0 | Resource Division | 18.08 | 0 | 0
1910 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000042/2022-2023 | 4626/BWD | 17/10/2022 | 0 | Resource Division | 18.48 | 0 | 0
1911 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000081/2021-2022 | 603/BWD | 28/01/2022 | 0 | Resource Division | 24.12 | 0 | 0
1912 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000105/2021-2022 | 952/BWD | 17/02/2022 | 0 | Resource Division | 74.99 | 0 | 0
1913 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000201/2021-2022 | 1524/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
1914 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
1915 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Ganganandapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer |  | ORD/000073/2023-2024 | 2562/CMD | 06/06/2023 | 30 | SUDIPTA GHOSH | 10.98 | 0 | 95
1916 | Burdwan Division | Burdwan Sadar Sub-Division | NAROTTAMBATI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000488/2023-2024 | 3501/BWD | 10/08/2023 | 875 | S.S.S. ENTERPRISES | 585.33 | 0 | 75
1917 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000845/2023-2024 | 1759/BSD | 28/07/2023 | 66 | MD HASIN | 0.85 | 0 | 0
1918 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-12-2024 to 28-02-2025 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001043/2024-2025 | 2636/BSD | 29/11/2024 | 90 | SK. ASFIA | 1.2 | 0 | 60
1919 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000352/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.94 | 0 | 0
1920 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000425/2023-2024 | 3837/BWD | 01/09/2023 | 0 | Resource Division | 6.91 | 0 | 0
1921 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000681/2023-2024 | 5081/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1922 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Narottambati PWSS. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/02404/2023-2024 | BP-2023-24-496 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.09 | 0 | 0
1923 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR NAROTTAMBATI PWSS TW 2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/03180/2023-2024 | BP-2023-24-664 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.31 | 0 | 0
1924 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
1925 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Narottombati Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000909/2023-2024 | 4173/CMD | 29/08/2023 | 30 | J.S. CONSTRUCTION. | 29.71 | 0 | 90
1926 | Burdwan Division | Central Mechanical Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme MONGALKOTE PWSS (Sl No-06) | Assistant Engineer | Junior Engineer | ORD/000074/2023-2024 | 399/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 2.93 | 0 | 100
1927 | Burdwan Division | Central Mechanical Sub-Division | Extension and replacement of pipe line from the existing Distribution System within scheme jurisdiction at Mongalkote village under Mongalkote PWSS under Mongalkote Block within Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-01] | Assistant Engineer | Junior Engineer | ORD/000153/2022-2023 | 437/KTS | 27/06/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.84 | 0 | 0
1928 | Burdwan Division | Central Mechanical Sub-Division | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of Mongalkote & Natunhat and its adjoining mouzas Piped Water Supply Scheme, Block - Mongalkote, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000517/2022-2023 | 4658/BWD | 18/10/2022 | 30 | ANIRUDDHA FARUQUE | 13.24 | 0 | 1
1929 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augmentation of Mongolkot Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000120/2023-2024 | 2631/CMD | 13/06/2023 | 30 | S.K. ELECTRICALS | 22.05 | 0 | 0
1930 | Central Mechanical | Central Mechanical Sub-Division | Yard lighting arrangement & allied works at Mangalkote water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000410/2024-2025 | 2790/CMD | 01/10/2024 | 60 | JAGANNATH ENTERPRISE | 13.47 | 0 | 0
1931 | Burdwan Division | Central Mechanical Sub-Division | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Murgram, Moregram, Malgram, Khanji, PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000289/2024-2025 | 2739/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 185.75 | 0 | 72
1932 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MALGRAM, MURGRAM, MORGRAM & KHANJI Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 3387/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 1333.98 | 0 | 40
1933 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000008/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.83 | 0 | 0
1934 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000016/2024-2025 | 4108/BWD | 25/11/2024 | 0 | Resource Division | 4.93 | 0 | 0
1935 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000338/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.73 | 0 | 0
1936 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000743/2023-2024 | 5259/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0
1937 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Malgram PWSS PH-I. | Assistant Engineer | Junior Engineer | BILL/00346/2024-2025 | BP-2024-25-168 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.14 | 0 | 0
1938 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Malgram PWSS PH-2. | Assistant Engineer | Junior Engineer | BILL/00418/2024-2025 | BP-2024-25-225 | 26/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.27 | 0 | 0
1939 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
1940 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MALGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000865/2023-2024 | 4120/CMD | 29/08/2023 | 550 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 27.75 | 0 | 82
1941 | Burdwan Division | Central Mechanical Sub-Division | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000288/2024-2025 | 2741/BWD | 12/07/2024 | 538 | M/S M.M. ENTERPRISE | 205.15 | 0 | 65
1942 | Burdwan Division | Central Mechanical Sub-Division | KHATUNDI Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ketugram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000413/2023-2024 | 3258/BWD | 27/07/2023 | 767 | SUJAN KUMAR MISTRY | 260.06 | 0 | 60
1943 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000384/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.05 | 0 | 0
1944 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000456/2023-2024 | 3980/BWD | 08/09/2023 | 0 | Resource Division | 0.66 | 0 | 0
1945 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000739/2023-2024 | 5251/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0
1946 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Khatundi PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01725/2023-2024 | BP-2023-24-252 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.23 | 0 | 0
1947 | Central Mechanical | Central Mechanical Sub-Division | New Service connection for Khatundi PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/02346/2023-2024 | BP-2023-24-463 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.33 | 0 | 0
1948 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
1949 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at KHATUNDI Water Supply Scheme [Block - KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000848/2023-2024 | 4121/CMD | 29/08/2023 | 30 | A.K SIKDAR | 20.81 | 0 | 91
1950 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Khatundi W/S Scheme (T/W-I & II) , Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000172/2023-2024 | 1055/CDD | 16/08/2023 | 30 | OSMAN SEKH | 16.61 | 0 | 0
1951 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARABAINAN & CHAUDANGA Piped Water Supply Scheme under Raina ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000412/2023-2024 | 3257/BWD | 27/07/2023 | 807 | SK ALIM | 1144.16 | 0 | 90
1952 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-09-2024 to 30-11-2024 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000682/2024-2025 | 1957/BSD | 30/08/2024 | 91 | SK. ASFIA | 1.2 | 0 | 60
1953 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000303/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.3 | 0 | 0
1954 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000419/2023-2024 | 3863/BWD | 01/09/2023 | 0 | Resource Division | 3.95 | 0 | 0
1955 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000662/2023-2024 | 5082/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
1956 | Central Mechanical | Burdwan Sadar Sub-Division | New electric connection for Chaudanga PWSS, PH-1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01884/2023-2024 | BP-2023-24-347 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.67 | 0 | 0
1957 | Central Mechanical | Burdwan Sadar Sub-Division | New electric connection for Chuadanga PWSS, PH-2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01885/2023-2024 | BP-2023-24-348 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.13 | 0 | 0
1958 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
1959 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAUDANGA Water Supply Scheme [ Block-RAINA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000805/2023-2024 | 4090/CMD | 29/08/2023 | 610 | MS DAS ELECTRIC CO | 28.98 | 0 | 50
1960 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for RAYAN PART-(IV) DURGA DANGA W/S Scheme under Burdwan-I Block under Burdwan Sub- Division under Burdwan Division PHE Dte | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000851/2024-2025 | 2587/BSD | 26/11/2024 | 45 | APEX ENGINEERING | 2.43 | 0 | 0
1961 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation RAYAN (Part-IV) (Durgadanga) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of switch rooms & boundary walls with gates at different TW site under Burdwan - I Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000994/2023-2024 | 245/BWD | 15/01/2024 | 442 | DHIRENDRANATH SOM | 93.34 | 0 | 100
1962 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000003/2024-2025 | 4102/BWD | 25/11/2024 | 0 | Resource Division | 10.19 | 0 | 0
1963 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new service connection of Rayan (Aug) Part-4 (Durgadanga) PWSS TW 1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00443/2024-2025 | BP-2024-25-236 | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.91 | 0 | 0
1964 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Rayan. Part -4 Durgadanga Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000095/2023-2024 | 2597/CMD | 07/06/2023 | 693 | M/S, S.S. ENTERPRISE. | 24.11 | 0 | 50
1965 | Burdwan Division | Central Mechanical Sub-Division | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Murgram, Moregram, Malgram, Khanji, PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000289/2024-2025 | 2739/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 185.75 | 0 | 72
1966 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MALGRAM, MURGRAM, MORGRAM & KHANJI Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 3387/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 1333.98 | 0 | 40
1967 | Burdwan Division | Central Mechanical Sub-Division | Extension work of pipe line MORGRAM Piped W/S. Scheme under Ketugram-I Block under Katwa Sub-Division within Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001067/2023-2024 | 990/BWD | 06/03/2024 | 482 | PUSPA ENTERPRISE | 133.47 | 0 | 82
1968 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000010/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.97 | 0 | 0
1969 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000344/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.45 | 0 | 0
1970 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000745/2023-2024 | 5257/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0
1971 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Morgram W/S Scheme PH-I. | Assistant Engineer | Junior Engineer | BILL/01805/2023-2024 | BP-2023-24-315 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.76 | 0 | 0
1972 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Morgram W/S Scheme PH-II. | Assistant Engineer | Junior Engineer | BILL/01806/2023-2024 | BP-2023-24-316 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0
1973 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
1974 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MORGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000857/2023-2024 | 4125/CMD | 29/08/2023 | 30 | JAGANNATH ENTERPRISE | 27.79 | 0 | 88
1975 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Morgram W/S Scheme (T/W-I & II) , Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000170/2023-2024 | 1346/CDD | 13/09/2023 | 30 | S B S ENTERPRISE | 16.67 | 0 | 0
1976 | Burdwan Division | Central Mechanical Sub-Division | CHATKA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | Assistant Engineer | Junior Engineer | ORD/000352/2023-2024 | 3065/BWD | 17/07/2023 | 534 | M/S H.R. CONSTRUCTION | 402.79 | 0 | 86
1977 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000304/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 2.18 | 0 | 0
1978 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000430/2023-2024 | 3856/BWD | 01/09/2023 | 0 | Resource Division | 0.69 | 0 | 0
1979 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000738/2023-2024 | 5232/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0
1980 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Chatka PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01767/2023-2024 | BP-2023-24-276 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.85 | 0 | 0
1981 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Chatka PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01768/2023-2024 | BP-2023-24-277 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.06 | 0 | 0
1982 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
1983 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHATKA Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000867/2023-2024 | 4117/CMD | 29/08/2023 | 740 | SOUNAK ENTERPRISE | 28.48 | 0 | 90
1984 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Chatka W/S Scheme (T/W-I & II), Ketugram-I Block under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000174/2023-2024 | 1344/CDD | 13/09/2023 | 30 | OSMAN SEKH | 16.61 | 0 | 0
1985 | Durgapur W/S Division | Kalna Sub-division | Acceptance cum Formal Work order for Laying of interconnection for PH NO-3 (At Taranagar) Pipe Line for under JOYKRISHNAPUR PWSS, Galsi-II Block, under Durgapur W/S Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000162/2024-2025 | 1410/DWSD | 01/10/2024 | 60 | MUNSHI JAVEDUR JAMAN | 0.63 | 0 | 100
1986 | Burdwan Division | Kalna Sub-division | Laying of Rising main in between Tube Well and Distribution Line for Shimulia Village in Galsi -II Block under Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.. | Assistant Engineer | JUNIOR ENGINEER | ORD/000396/2024-2025 | 621/DSD | 05/08/2024 | 30 | MAA MAHAMAYA CONSTRUCTION | 2.15 | 0 | 100
1987 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GHUNI & JOYKRISHNAPUR Piped Water Supply Scheme under Purbasthali II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000492/2023-2024 | 3510/BWD | 10/08/2023 | 808 | BKB INFRA PROJECTS PRIVATE LIMITED | 551.42 | 0 | 20
1988 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR JOYKRISHNAPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE.". | Assistant Engineer | JUNIOR ENGINEER | ORD/000569/2024-2025 | 1015/KSD | 07/08/2024 | 15 | DEL DELTA CONSTRUCTION | 0.66 | 0 | 100
1989 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000297/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.33 | 0 | 0
1990 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000513/2023-2024 | 4037/BWD | 08/09/2023 | 0 | Resource Division | 37.2 | 0 | 0
1991 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000540/2023-2024 | 4288/BWD | 29/09/2023 | 0 | Resource Division | 0.55 | 0 | 0
1992 | Central Mechanical | Kalna Sub-division | Quotation for new service connection at Joykrishnapur PWSS PH-2 | Assistant Engineer | JUNIOR ENGINEER | BILL/01817/2023-2024 | BP-2023-24-333 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.33 | 0 | 0
1993 | Central Mechanical | Kalna Sub-division | Quotation for new service connection at Joykrishnapur W/S Scheme for PH No-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01820/2023-2024 | BP-2023-24-332 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.57 | 0 | 0
1994 | Central Mechanical | Kalna Sub-division | New service connection charges for Joykrishnapur PWSS TW-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/02191/2023-2024 | BP-2023-24-390 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.39 | 0 | 0
1995 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME. | Assistant Engineer | JUNIOR ENGINEER | BILL/02828/2023-2024 | BP-2023-24-592 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0
1996 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 3 at Joykrishnapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000762/2022-2023 | 838/CMD | 20/02/2023 | 30 | C.M. ENTERPRISE | 10.43 | 0 | 100
1997 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 4 at Joykrishnapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000763/2022-2023 | 839/CMD | 20/02/2023 | 30 | MS MANABESH ROY | 10.14 | 0 | 100
1998 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JOYKRISHNAPUR Water Supply Scheme [ Block- PURBASTHALI-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000880/2023-2024 | 4143/CMD | 29/08/2023 | 646 | JYOTY SOLAR POWER. | 26.98 | 0 | 45
1999 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEULIA, GOBARDHANPUR, KHARIJA-KASHIGRAM & UNIATATARPUR Piped Water Supply Scheme under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000477/2023-2024 | 3491/BWD | 09/08/2023 | 815 | POWER TOOLS & ENGINEERING | 1741.05 | 0 | 10
2000 | Burdwan Division | Central Mechanical Sub-Division | Balance work for OHR, extension of pipeline to provide FHTC in Barulia & Narayanpur mouza with Sinking of Tube well, Construction of Pump house, Boundary Wall, Land Development, Plinth Protection for pump house & OHR under, approach road to 2nd pump house UNIATATARPUR PWSS, Katwa Sub Division, Block- Mongolkote, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000504/2024-2025 | 3162/BWD | 22/08/2024 | 120 | POWER TOOLS & ENGINEERING | 152.52 | 0 | 0
2001 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000332/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.34 | 0 | 0
2002 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000458/2023-2024 | 3982/BWD | 08/09/2023 | 0 | Resource Division | 2.76 | 0 | 0
2003 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000700/2023-2024 | 5070/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
2004 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection for Unitatarpur PWSS PH-1 | Assistant Engineer | Junior Engineer | BILL/00247/2024-2025 | BP-2024-25-127 | 31/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.22 | 0 | 0
2005 | Central Mechanical | Central Mechanical Sub-Division | Quotation for New service connection for Unitatarpur PWSS PH 2 | Assistant Engineer | Junior Engineer | BILL/00248/2024-2025 | BP-2024-25-126 | 31/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.78 | 0 | 0
2006 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
2007 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at UNIATATARPUR Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000824/2023-2024 | 4101/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 26.93 | 0 | 48
2008 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC for 100% coverage at Napara, Astai, Panch Shimul, Dastanpur, Keotara, Siromani, Abujhati & Ajhapur Habitation (Village) for ABUJHATI Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000098/2023-2024 | 2236/BWD | 16/05/2023 | 688 | PAL CONSTRUCTION | 36.63 | 0 | 50
2009 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of CIDF/D.I Pipes with specials for providing FHTC at Siromoni mouza within command area of Abujhati Piped W/S Scheme Jamalpur Development Block under Burdwan Division,PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000181/2023-2024 | 1005/BSD | 06/06/2023 | 15 | DEBASHISH ENTERPRISE | 0.94 | 0 | 100
2010 | Burdwan Division | Burdwan Sadar Sub-Division | Improvement of 300 CuM OHR (Concreting, Plastering, Primer and Painting) for Abujhati PWSS under Jamalpur Block under Burdwan Divn., PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000344/2024-2025 | 450/AE/HQ | 24/07/2024 | 45 | DEBASHISH ENTERPRISE | 2.01 | 0 | 100
2011 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of ABUJHATI PWSS under Jamalpur Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000364/2023-2024 | 1526/BSD | 17/07/2023 | 15 | MEASURE LAND | 0.78 | 0 | 100
2012 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of HDPE Pipeline from 4th Number Pump House to main distribution system for ABUJHATI Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000722/2023-2024 | 3925/BWD | 05/09/2023 | 30 | MAA BHABANI CONSTRUCTION | 21.04 | 0 | 100
2013 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of overflow chamber with u-PVC pipe line for removal of excess water at Head work Site Under ABUJHATI PWSS Jamalpur Dev. Block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/001037/2024-2025 | 88/AE/HQ | 08/01/2025 | 30 | SOUMYAVASH DAS | 0.97 | 0 | 100
2014 | Burdwan Division | Burdwan Sadar Sub-Division | Laying different dia UPVC Pipeline for inter connection of existing FHTC near Raypara of Abujhati Flyover i.c.w. Road widening from 4 lane to 6 lane of NH-2 at chane 601+9521+960 under ABUIHATI PWSS in jamalpur Block within Burdwan Sub Divn. under Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/001173/2023-2024 | 532/BSD | 14/03/2024 | 30 | SOUMYAVASH DAS | 0.89 | 0 | 100
2015 | Burdwan Division | Burdwan Sadar Sub-Division | Construction & Installation of Sluice valve & valve Chamber to control the flow of water with laying of u-PVC Pipe under Abujhati PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/001293/2024-2025 | 351/AE/HQ | 10/03/2025 | 30 | DEBASHISH ENTERPRISE | 5.47 | 0 | 100
2016 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Abujhati PWSS TW-4 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | BILL/00765/2023-2024 | BP-2023-24-66 | 20/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0
2017 | Central Mechanical | Burdwan Sadar Sub-Division | Illumination arrangement and miscelleneous works at Abujhati water supply scheme under Jamalpur Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000404/2024-2025 | 2783/CMD | 01/10/2024 | 60 | M/S. S.R. ENTERPRISE | 19.25 | 0 | 20
2018 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augmentation of ABUJHATI[JAMALPUR] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000568/2023-2024 | 3902/CMD | 18/08/2023 | 30 | KUNDU CONSTRUCTION. | 12.25 | 0 | 95
2019 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of RAYAN (Part-III) (KOPIBAGAN) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan -I Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000120/2023-2024 | 2304/BWD | 19/05/2023 | 927 | IJABUL SEKH | 166.98 | 0 | 100
2020 | Burdwan Division | Burdwan Sadar Sub-Division | Re-Connection of existing FHTC from newly laid distribution pipe At SUKANTA PALLY for Augmentation of RAYAN (PART-III) [ KOPIBAGAN] PIPED WATER SUPPLY SCHEME , Block- Burdwan-I , within Burdwan Sub Division under Burdwan Division PHE Dte | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000128/2024-2025 | 1009/BSD | 06/06/2024 | 30 | SK RAJU | 0.96 | 0 | 0
2021 | Burdwan Division | Burdwan Sadar Sub-Division | Re-Connection of existing FHTC from newly laid distribution pipe At KHA PUKUR ADIBASIPARA for Augmentation of RAYAN (PART-III) [ KOPIBAGAN] PIPED WATER SUPPLY SCHEME , Block- Burdwan-I , within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000142/2024-2025 | 1030/BSD | 10/06/2024 | 30 | SK RAJU | 0.96 | 0 | 0
2022 | Burdwan Division | Burdwan Sadar Sub-Division | Allied work for Road restoration work due to FHTC & Extension pipe line for different village and inside road of OHR side for Rayan pwss at Bardhhaman-I Development Block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000301/2024-2025 | 1273/BSD | 12/07/2024 | 217 | MAA KALI CONSTRUCTION | 3.89 | 0 | 100
2023 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for RAYAN PART-III KOPIBAGAN W/S Scheme under Burdwan-I Block under Burdwan Sub- Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000849/2024-2025 | 2586/BSD | 26/11/2024 | 45 | APEX ENGINEERING | 2.57 | 0 | 0
2024 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000004/2024-2025 | 4100/BWD | 25/11/2024 | 0 | Resource Division | 11.09 | 0 | 0
2025 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Rayan. Part -3 Kopibagan Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000092/2023-2024 | 2596/CMD | 07/06/2023 | 694 | CHOUDHURY ENTERPRISE | 24.13 | 0 | 50
2026 | Central Mechanical | Burdwan Sadar Sub-Division | Illumination arrangement & different electro-mechanical works at RAYAN water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000442/2024-2025 | 2799/CMD | 01/10/2024 | 60 | JOYGURU ENTERPRISE | 6.04 | 0 | 40
2027 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMEGERIA, ARGUN, CHINISPUR & KULUTIA Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000533/2023-2024 | 3630/BWD | 21/08/2023 | 1107 | M/S GOUTAM DAS | 1421.7 | 0 | 75
2028 | Burdwan Division | Central Mechanical Sub-Division | Hiring of one no Diesel Motor Cab (BS-VI) including the cost of fuel . mobile & other charges for the inspection of the different projects of JJM for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. (Period:- 01/03/2025 to 31/08/2025) [Sl No-02] | Assistant Engineer | Junior Engineer | ORD/001324/2024-2025 | 321/KTS | 28/02/2025 | 184 | HAMID SK | 1.84 | 0 | 0
2029 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000095/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.38 | 0 | 0
2030 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000212/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 16.15 | 0 | 0
2031 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000742/2023-2024 | 5253/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0
2032 | Central Mechanical | Central Mechanical Sub-Division | New Service connection at Argun PWSS PH-2 | Assistant Engineer | Junior Engineer | BILL/02344/2023-2024 | BP-2023-24-461 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.63 | 0 | 0
2033 | Central Mechanical | Central Mechanical Sub-Division | New Service connection for Argun PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/02349/2023-2024 | BP-2023-24-460 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.91 | 0 | 0
2034 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
2035 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at ARGUN Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000845/2023-2024 | 4119/CMD | 29/08/2023 | 30 | DUTTA ENTERPRISE | 26.95 | 0 | 88
2036 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Argun W/S Scheme (T/W-I & II) , Ketugram-I Block under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000171/2023-2024 | 1056/CDD | 16/08/2023 | 30 | C.M. ENTERPRISE | 16.2 | 0 | 0
2037 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Balance work for distribution system HDPE earth work & concrete work for Kayrapur PWSS, Block- Ausgram-I under Durgapur W/S Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000131/2024-2025 | 1240/DWSD | 29/08/2024 | 15 | TARA MA AGENCY | 1 | 0 | 100
2038 | Burdwan Division | Durgapur Sub-DIvision | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of November'2022. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00286/2022-2023 | 954/JJM/22-23 | 13/01/2023 | 0 | SUJAUDDIN SEKH | 0.38 | 0 | 0
2039 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhada village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte.. [SL. No. : 20] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000028/2021-2022 | 3399/BWD | 24/06/2021 | 15 | M/S S. CHOUDHURY | 4.86 | 0 | 1
2040 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kayrapur village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 19] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000029/2021-2022 | 3398/BWD | 24/06/2021 | 15 | M/S S. CHOUDHURY | 4.86 | 0 | 1
2041 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Koranji village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 21] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000030/2021-2022 | 3397/BWD | 24/06/2021 | 15 | M/S S. CHOUDHURY | 3.44 | 0 | 1
2042 | Burdwan Division | Durgapur Sub-DIvision | Restoration of damaged pipeline of distribution main for construction of drain at Billwagram village within Kayrapur W/S Scheme (Part-B) in Ausgram-I Block under Burdwan Division, P.H.E. Dte.[SL-11] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000035/2023-2024 | 159/DSD | 13/04/2023 | 21 | SANDIPAN SENGUPTA | 0.52 | 0 | 100
2043 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Belari village of Kayrapur Piped W/S Scheme (Part-A) within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte.[Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000286/2021-2022 | 715/DSD | 17/12/2021 | 15 | M/S S. CHOUDHURY | 4.83 | 0 | 1
2044 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kayrapur vilage of Kayrapur Piped W/S Scheme (Part-A) within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000287/2021-2022 | 716/DSD | 17/12/2021 | 15 | M/S S. CHOUDHURY | 4.83 | 0 | 1
2045 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from distribution system within the command area of KAYRAPUR Water Supply Scheme (Part-A) at Belari, Bara, Bhada & Kayrapur (Part) village under JAL SAPNO MISSION under Ausgram-I Block in Purba Bardhanan District under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000341/2021-2022 | 26/BWD | 04/01/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 42.23 | 0 | 1
2046 | Burdwan Division | Durgapur Sub-DIvision | Land development and Construction of connecting road from PH to OHR at 1st tube well site of KAYRAPUR Water Supply Scheme (Part-B) within Durgapur Sub Division Under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000383/2023-2024 | 558/DSD | 20/07/2023 | 30 | SAMANTA CONSTRUCTION | 4.84 | 0 | 0
2047 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from distribution system within the command area of KAYRAPUR Water Supply Scheme (Part-B) at Billogram, Brajapur, Asinda and Noada village under JAL SAPNO MISSION under Ausgram-I Block in Purba Bardhanan District under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000450/2021-2022 | 860/BWD | 11/02/2022 | 60 | ASHOK KUMAR GHOSH | 95.9 | 0 | 1
2048 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Belari village of Kayrapur Piped W/S Scheme (Part-A) within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000480/2021-2022 | 736/DSD | 28/12/2021 | 15 | M/S S. CHOUDHURY | 4.83 | 0 | 1
2049 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kayrapur vilage of Kayrapur Piped W/S Scheme (Part-A) within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000481/2021-2022 | 737/DSD | 28/12/2021 | 15 | M/S S. CHOUDHURY | 4.83 | 0 | 1
2050 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhada village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte.. [SL. No. : 20] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000532/2020-2021 | 1458/BWD | 18/02/2021 | 15 | M/S S. CHOUDHURY | 4.86 | 4.86 | 0
2051 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kayrapur village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 19] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000534/2020-2021 | 1459/BWD | 18/02/2021 | 15 | M/S S. CHOUDHURY | 4.86 | 4.86 | 0
2052 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Koranji village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 21] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000537/2020-2021 | 1457/BWD | 18/02/2021 | 15 | M/S S. CHOUDHURY | 4.86 | 4.86 | 0
2053 | Burdwan Division | Durgapur Sub-DIvision | Relaying and restoration of damaged pipeline of distribution main for construction of drain at Brajapur, Chonary and Asinda village to keep on FHTC within Kayrapur W/S Scheme (Part-B) in Ausgram-I Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000562/2023-2024 | 651/DSD | 24/08/2023 | 30 | TARAMA AGENCY | 0.95 | 0 | 100
2054 | Burdwan Division | Durgapur Sub-DIvision | Designing, Making and Erection of Sign Board for SAJAL GRAM in Kayrapur Village, Ausgram-I Block within Kayrapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000730/2023-2024 | 823/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0 | 0
2055 | Burdwan Division | Durgapur Sub-DIvision | Additional cutting of existing concrete pavement between Node J4 to J51 for laying of 300 mm dia D.I distribution in connection with Laying distribution system of Kayrapur Piped Water Supply Scheme at Ausgram-I Block within Durgapur Sub-Division under Burdwan Division, PHE Dte. (Gr.-C) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000965/2020-2021 | 109/DSD | 29/01/2021 | 15 | M/S S. CHOUDHURY | 4.05 | 0 | 1
2056 | Burdwan Division | Durgapur Sub-DIvision | Laying of rising main in between two number of Tube wells to Over Head Reservoir for Kayrapur water supply scheme (Part-A) within Durgapur Sub-Division in Ausgram-I Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000967/2020-2021 | 991/BWD | 04/02/2021 | 30 | M/S S. CHOUDHURY | 7.12 | 0 | 1
2057 | Burdwan Division | Durgapur Sub-DIvision | Construction of boundary wall at 2nd Tube well site of KAYRAPUR Water Supply Scheme (Part-B) and its adjoining mouzas, Block-Ausgram-I, under Burdwan Division P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000988/2023-2024 | 44/DSD | 17/01/2024 | 30 | SK BADIUZZAMAL | 3.83 | 0 | 100
2058 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000121/2021-2022 | 1110/BWD | 26/02/2022 | 0 | Resource Division | 25.78 | 0 | 0
2059 | Burdwan Division | Durgapur Sub-DIvision | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0
2060 | Burdwan Division | Kalna Sub-division | KHANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Monteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000803/2023-2024 | 4808/BWD | 08/11/2023 | 723 | NATIONAL CONSTRUCTION | 707.7 | 0 | 60
2061 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000381/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.22 | 0 | 0
2062 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000531/2023-2024 | 4293/BWD | 29/09/2023 | 0 | Resource Division | 2.89 | 0 | 0
2063 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000558/2023-2024 | 4934/BWD | 10/11/2023 | 0 | Resource Division | 67.03 | 0 | 0
2064 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR KHANPUR PWSS. | Assistant Engineer | JUNIOR ENGINEER | BILL/02687/2023-2024 | BP-2023-24-562 | 23/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.01 | 0 | 0
2065 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
2066 | Central Mechanical | Kalna Sub-division | CONTINUATION OREDER- Hiring of inspection vehicle no. [ WB41H5741] (Diesel/CNG/LPG Driven) for supervision of the site for the office of the Assistant Engineer ,CMD PHE Dte. [W.E.F- 01.08.2025 to 30.09.2025] | Assistant Engineer | JUNIOR ENGINEER | ORD/000131/2025-2026 | 1035/CMSD | 30/07/2025 | 61 | PRODYUT GHOSH | 0.8 | 0 | 0
2067 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KHANPUR Water Supply Scheme [ Block-MONTESWAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000799/2023-2024 | 4086/CMD | 29/08/2023 | 30 | S DUTTA | 43.47 | 0 | 65
2068 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of KALYANPUR (SM/16299) Water Supply Scheme & BHABANANDAPUR (SM/16024) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000189/2024-2025 | 2433/BWD | 27/06/2024 | 247 | BALAJEE ENTERPRISES | 225.16 | 0 | 2
2069 | Burdwan Division | Kalna Sub-division | Providing FHTC work at Kalyanpur village under KALYANPUR Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000885/2023-2024 | 5514/BWD | 14/12/2023 | 151 | SETH ENTERPRISE | 13.89 | 0 | 100
2070 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR AUGMENTATION FOR KALYANPUR PWSS PH-2 | Assistant Engineer | JUNIOR ENGINEER | BILL/00186/2024-2025 | BP-2024-25-87 | 15/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.96 | 0 | 0
2071 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of KALYANPUR[KALNA-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001079/2023-2024 | 4438/CMD | 01/11/2023 | 760 | SOUNAK ENTERPRISE | 24.41 | 0 | 50
2072 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR GAHAK PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/000571/2024-2025 | 1017/KSD | 07/08/2024 | 15 | DEL DELTA CONSTRUCTION | 0.66 | 0 | 100
2073 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMPUR, GAHAK & SHANKRA Piped Water Supply Scheme under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000639/2023-2024 | 3957/BWD | 07/09/2023 | 1051 | M/S B. NANDI | 758.52 | 0 | 20
2074 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000252/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.5 | 0 | 0
2075 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000548/2023-2024 | 4308/BWD | 29/09/2023 | 0 | Resource Division | 0.81 | 0 | 0
2076 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000591/2023-2024 | 4899/BWD | 10/11/2023 | 0 | Resource Division | 15.99 | 0 | 0
2077 | Central Mechanical | Kalna Sub-division | New service connection for Gahak PWSS TW-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/02392/2023-2024 | BP-2023-24-498 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.7 | 0 | 0
2078 | Central Mechanical | Kalna Sub-division | New service connection for Gahak PWSS TW-1. | Assistant Engineer | JUNIOR ENGINEER | BILL/02393/2023-2024 | BP-2023-24-497 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0
2079 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0
2080 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GAHAK Water Supply Scheme [ Block- PURBASTHALI -1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | Assistant Engineer | JUNIOR ENGINEER | ORD/000929/2023-2024 | 4192/CMD | 29/08/2023 | 30 | SOUNAK ENTERPRISE | 21.33 | 0 | 50
2081 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of KULTI (SM/16301) Water Supply Scheme, Block Kalna II under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000235/2024-2025 | 2553/BWD | 04/07/2024 | 240 | HAMID SK | 222.11 | 0 | 80
2082 | Burdwan Division | Kalna Sub-division | Augmentation of KULTI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Kalna - II Block, Purba Burdwan District under Burdwan Division, PHE.Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000588/2023-2024 | 3747/BWD | 28/08/2023 | 60 | MAHALAXMI CONSTRUCTION | 21.92 | 0 | 0
2083 | Central Mechanical | Kalna Sub-division | New service connection for augmentation of Kulti PH-3 PWSS. | Assistant Engineer | JUNIOR ENGINEER | BILL/00086/2024-2025 | BP-2024-25-29 | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.7 | 0 | 0
2084 | Central Mechanical | Kalna Sub-division | Additional Quotation for augmentation of Kulti PWSS PH 3 | Assistant Engineer | JUNIOR ENGINEER | BILL/00938/2024-2025 | BP-2024-25-407 | 11/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.79 | 0 | 0
2085 | Central Mechanical | Kalna Sub-division | Illumination arrangement at Kulti water supply scheme under Kalna 2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000407/2024-2025 | 2787/CMD | 01/10/2024 | 334 | DELTA ENGINEERING ENTERPRISE | 10.7 | 0 | 30
2086 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1, 2 & 3 at Augmentation of KULTI[KALNA-II]] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001081/2023-2024 | 4439/CMD | 04/10/2023 | 698 | CHOUDHURY ENTERPRISE | 36.64 | 0 | 33
2087 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of PALLA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Memari - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000099/2023-2024 | 2415/BWD | 29/05/2023 | 701 | LAKSHMIKANTA DAS | 11.03 | 0 | 100
2088 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of PALLA W/S Scheme under Memari - I Block within Burdwan Sub-Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000203/2023-2024 | 2706/BWD | 08/06/2023 | 30 | DAS CONSTRUCTION | 13.26 | 0 | 100
2089 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Palla PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000397/2023-2024 | 1585/BSD | 24/07/2023 | 15 | MEASURE LAND | 0.78 | 0 | 100
2090 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch rooms & Rising main at different TW site for PALLA Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000592/2023-2024 | 3765/BWD | 29/08/2023 | 60 | SANDIP SARKAR | 7.52 | 0 | 98
2091 | Burdwan Division | Burdwan Sadar Sub-Division | Laying distribution pipe line, FHTC, 3rd tube well installation, Construction of switch room and boundary wall for PALLA village under Augmentation of PALLA Piped Water Supply Scheme, Block - Memari - I, under Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000876/2023-2024 | 5329/BWD | 04/12/2023 | 502 | SARKAR AGENCY | 136.31 | 0 | 95
2092 | Central Mechanical | Burdwan Sadar Sub-Division | Additional quotation for installation of DTR 25KVA at Palla PWSS PH-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00441/2024-2025 | BP-2024-25-235 | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.51 | 0 | 0
2093 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR PALLA PWSS | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/02597/2023-2024 | BP-2023-24-553 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.35 | 0 | 0
2094 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & installation of Automatic Chlorinator at Palla water supply scheme, P.H. No.- II under CMD, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000243/2024-2025 | 726/CMSD | 10/05/2024 | 10 | MITRA ENTERPRISE | 0.96 | 0 | 100
2095 | Central Mechanical | Burdwan Sadar Sub-Division | Illumination arrangement & different electro-mechanical works at PALLA and others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000441/2024-2025 | 2798/CMD | 01/10/2024 | 60 | SUBRATA BHADRA | 15.45 | 0 | 0
2096 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augmentation of PALLA[MEMARI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000573/2023-2024 | 3903/CMD | 18/08/2023 | 30 | SIMARR | 11.88 | 0 | 100
2097 | Burdwan Division | Burdwan Sadar Sub-Division | NETRAKHANDA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000660/2023-2024 | 4121/BWD | 14/09/2023 | 365 | SUJAY KUMAR RAY | 345.67 | 0 | 50
2098 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000355/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.53 | 0 | 0
2099 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000524/2023-2024 | 4290/BWD | 29/09/2023 | 0 | Resource Division | 2.08 | 0 | 0
2100 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000682/2023-2024 | 5055/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
2101 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Netrakhanda W/S Scheme PH No.-II | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01801/2023-2024 | BP-2023-24-320 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.85 | 0 | 0
2102 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Netrakahanda W/S Scheme PH No.-I | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01802/2023-2024 | BP-2023-24-319 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0
2103 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
2104 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Netrakhanda Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000722/2023-2024 | 4033/CMD | 29/08/2023 | 30 | GLACIER ENGINEERING CO | 28.97 | 0 | 96
2105 | Burdwan Division | Burdwan Sadar Sub-Division | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PALASHAN Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000001/2023-2024 | 1601/BWD | 04/04/2023 | 60 | BHOWMICK ENTERPRISE | 50.14 | 0 | 100
2106 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
2107 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, making and erection of Sign Board for SWAJAL GRAM in Paschimpara village of Raina-I Block under Palashan Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte(5 nos Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000514/2025-2026 | 2355/BSD | 21/08/2025 | 10 | S.M. ENGOCON | 0.72 | 0 | 0
2108 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of PALASON & its adjoining mouzas Piped Water Supply Scheme, Block - Raina - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000515/2022-2023 | 4612/BWD | 17/10/2022 | 30 | M/S SYCHROTECH INDUSTRY | 10.12 | 0 | 0
2109 | Burdwan Division | Burdwan Sadar Sub-Division | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at 3rd TW Site and providing leftout FHTC, Road Restoration with allied work for PALASON Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000688/2024-2025 | 3671/BWD | 22/10/2024 | 90 | A.K. SIKDAR | 42.74 | 0 | 0
2110 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for PALASON its Adjoining Mouza W/S Scheme, Block - Raina-I within Burdwan Sub-Division, PHE Dte. (Mouza- PASCHIM PARA) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000765/2022-2023 | 497/BSD | 21/03/2023 | 45 | MAA MAHAMAYA CONSTRUCTION | 3.63 | 0 | 100
2111 | Burdwan Division | Burdwan Sadar Sub-Division | Left out FHTC & distribution Networks at Palasan Paschim para under PALASAN Piped Water Supply Scheme, Block- RAINA-I within Burdwan Sub-Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000781/2025-2026 | 1471/BSD | 25/06/2025 | 30 | SK ABDUL HALIM | 1.97 | 0 | 0
2112 | Burdwan Division | Burdwan Sadar Sub-Division | Improvement work of PALASON Piped Water Supply Scheme for smooth running of FHTC within Raina-I block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001195/2023-2024 | 2739/BSD | 28/11/2023 | 30 | ANWESHA CONSTRUCTION | 0.95 | 0 | 100
2113 | Central Mechanical | Burdwan Sadar Sub-Division | New Service Connection Charges Bill for TW-3 of Aug. Palasan W/S Scheme | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/00571/2023-2024 | BP-2023-24-7 | 08/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.39 | 0 | 0
2114 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Palasan Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000206/2023-2024 | 3047/CMD | 20/07/2023 | 30 | S.K. ELECTRICALS | 11.09 | 0 | 80
2115 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of a voltage Correcting device along with allied accessories at PALASAN Water Supply Scheme, Pump House-1, under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000948/2022-2023 | 1160/CMD | 13/03/2023 | 30 | P.K. ENGINEERING | 2.98 | 0 | 0
2116 | Burdwan Division | Central Mechanical Sub-Division | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000288/2024-2025 | 2741/BWD | 12/07/2024 | 538 | M/S M.M. ENTERPRISE | 205.15 | 0 | 65
2117 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000221/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 12.89 | 0 | 0
2118 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Bakalsa PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/00829/2024-2025 | BP-2024-25-322 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.62 | 0 | 0
2119 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bakalsa Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000905/2023-2024 | 4169/CMD | 29/08/2023 | 580 | M/S, S.DAS AND ENTERPRISE. | 29.71 | 0 | 50
2120 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAKALSA Water Supply Scheme [ Block- KETUGRAM-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | Assistant Engineer | Junior Engineer | ORD/000928/2023-2024 | 4191/CMD | 29/08/2023 | 485 | MITRA ASSOCIATE | 20.63 | 0 | 44
2121 | Burdwan Division | Central Mechanical Sub-Division | KANKURHATI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at KANKURHATI Mouza (J.L. - 120) under KETUGRAM -II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | Junior Engineer | ORD/000791/2022-2023 | 1428/BWD | 24/03/2023 | 648 | HAMID SK | 77.54 | 0 | 100
2122 | Burdwan Division | Central Mechanical Sub-Division | KANKURHATI Piped Water Supply Scheme (Balance Portion) with sinking of Tube-well, LDS, Rising Main, FHTC, & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at BEGUNKHOLA Mouza (J.L. - 121) under KETUGRAM -II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL. | Assistant Engineer | Junior Engineer | ORD/001016/2023-2024 | 517/BWD | 06/02/2024 | 604 | OM ENTERPRISE | 60.2 | 0 | 80
2123 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000007/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.87 | 0 | 0
2124 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000164/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 21.7 | 0 | 0
2125 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000564/2023-2024 | 4938/BWD | 10/11/2023 | 0 | Resource Division | 0.73 | 0 | 0
2126 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Kankurhati W/S Scheme TW-1 | Assistant Engineer | Junior Engineer | BILL/00682/2023-2024 | BP-2023-24-28 | 22/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.49 | 0 | 0
2127 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Kankurhati PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01129/2024-2025 | BP-2023-24-406 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.45 | 0 | 0
2128 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at KANKURHATI [KETUGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000058/2023-2024 | 2519/CMD | 02/06/2023 | 30 | P.K. ENGINEERING | 21.26 | 0 | 40
2129 | Burdwan Division | Burdwan Sadar Sub-Division | Shifting of pipeline of 160mm & 90mm HDPE pipeline for Irrigation canel crossing and special maintenance for FHTC work for Sagrai & Khandaghosh Piped Water Supply Scheme within Khandaghosh block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000127/2024-2025 | 1008/BSD | 06/06/2024 | 30 | SHUBHRA KANTI GHOSH | 0.86 | 0 | 100
2130 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of SAGRAI W/S Scheme (2ND TW SITE) under Khandaghosh Block within Burdwan Sub-Division, PHE Dte. [For 01 No. Tube well]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000191/2023-2024 | 2688/BWD | 08/06/2023 | 30 | NATIONAL CONSTRUCTION | 13.23 | 0 | 100
2131 | Burdwan Division | Burdwan Sadar Sub-Division | Beautification of PWSS with Arboriculture, Recharge Pit including shaft and anciliary works at SAGRAI (Khandaghosh Block) P.W.S.S under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000551/2024-2025 | 282/RWS | 03/09/2024 | 120 | ALOKA CONSTRUCTION | 0.97 | 0 | 100
2132 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Sagrai Village, Khandaghosh Block within Sagrai PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000737/2023-2024 | 830/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0 | 100
2133 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for SAGRAI its Adjoining Mouza W/S Scheme, Block -Khandaghosh within Burdwan Sub-Division, PHE Dte. (Mouza- Jubila) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000769/2022-2023 | 504/BSD | 21/03/2023 | 45 | JYOTI ENTERPRISE | 3.5 | 0 | 100
2134 | Burdwan Division | Burdwan Sadar Sub-Division | Restore of Pipeline damaded by construction of drain by Zilla Parishad near Jobila Muslimpara under SAGRAI Piped Water Supply Scheme, Block- Khandaghosh within Burdwan Sub Division under Burdwan Division PHE Dte | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001027/2023-2024 | 278/BSD | 09/02/2024 | 30 | SHUBHRA KANTI GHOSH | 0.96 | 0 | 100
2135 | Burdwan Division | Burdwan Sadar Sub-Division | Repairing damaged concrete road by cement concrete (mix 1:1.5:3) for FHTC work for SAGRAI Piped W/S. Scheme and its adj. mouzas within Khandaghosh Block under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001056/2023-2024 | 895/BWD | 01/03/2024 | 30 | SK KHAIRUL ISLAM | 8.78 | 0 | 100
2136 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of Rising main in between 3rd Tube Wells to 125 mm dia distribution pipe line at Chatimpur village for SAGRAI Pipe Water Supply scheme in Khandaghosh Block under Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001091/2023-2024 | 516/BSD | 13/03/2024 | 30 | SHANKHA GHOSH | 0.97 | 0 | 100
2137 | Burdwan Division | Burdwan Sadar Sub-Division | Restore of Pipeline damaged by construction of drain by Zilla Parishad near Jobila Sarkarpara under SAGRAI Piped Water Supply Scheme, Block- Khandaghosh within Burdwan Sub Division under Burdwan Division PHE Dte | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001172/2023-2024 | 531/BSD | 14/03/2024 | 30 | SHUBHRA KANTI GHOSH | 0.96 | 0 | 100
2138 | Burdwan Division | Burdwan Sadar Sub-Division | Restore of Pipeline damaded by construction of drain by Zilla Parishad near Jobila F.P.School & Peer Tala & Chatimpur under SAGRAI Piped Water Supply Scheme, Block- Khandaghosh within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001177/2023-2024 | 534/BSD | 14/03/2024 | 30 | SHUBHRA KANTI GHOSH | 0.94 | 0 | 100
2139 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new service connection for Sagrai PWSS TW-4. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00256/2024-2025 | BP-2024-25-135 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.68 | 0 | 0
2140 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Sagrai W/S Scheme TW-3 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00685/2023-2024 | BP-2023-24-27 | 22/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.31 | 0 | 0
2141 | Central Mechanical | Burdwan Sadar Sub-Division | Illumination arrangement & different electro-mechanical works at SAGRAI water supply scheme under KHANDAGHOSH Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000416/2024-2025 | 2800/CMD | 01/10/2024 | 60 | CHOUDHURY ENTERPRISE | 14.29 | 0 | 0
2142 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of SAGRAI(Part-B)[KHANDAGHOSH] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000572/2023-2024 | 3898/CMD | 18/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 24.41 | 0 | 40
2143 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Amadpur W/S Scheme. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/02187/2023-2024 | BP-2023-24-383 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.47 | 0 | 0
2144 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Amadpur W/S Scheme. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/02188/2023-2024 | BP-2023-24-382 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.69 | 0 | 0
2145 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0
2146 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for new Tube well no.- 1 & 2 of AMADPUR[MEMARI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001089/2023-2024 | 4511/CMD | 06/10/2023 | 30 | AMUSAR IMPEX PVT. LTD. | 25.2 | 0 | 0
2147 | Durgapur W/S Division |  | Execution and payment of wayleave permission with railway services for crossing of portable water supply PWSSat Khano under Khano PWSS under DWSD,PHE Dte |  |  | ORD/000011/2025-2026 | 657/DWSD | 21/04/2025 | 195 | MANASH GHOSH | 7.09 | 0 | 71
2148 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for Design Engineering Services of Survey, General arrangement drawing, Pile foundation design and drawings, Pipe Pedestal and BOM, Structural design design and drawing, Fabrication drawings for 26 Numbers different dia meter pipe crossing Pipe Bridge at "PURANGAN (Zone-I, II, III), 11 Nos. Mouzas under PURSHA and UCHCHGRAM, SHILLA (Zone-I, II, III, IV), TAHER PUR (Zone-I, II, III) and KHANO (Zone-I and II) sites under Durgapur W/S Division,PHE Dte. |  |  | ORD/000105/2024-2025 | 1058/DWSD | 25/07/2024 | 270 | ASTER CONSULTANCY | 47.43 | 0 | 70
2149 | Durgapur W/S Division |  | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe Carring Bridge with Pipe supporting structure under TAHERPUR and KHANO Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte. |  |  | ORD/000158/2024-2025 | 1506/DWSD | 05/11/2024 | 236 | MANASH GHOSH | 1114.23 | 0 | 60
2150 | Burdwan Division |  | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. |  |  | ORD/000872/2023-2024 | 5324/BWD | 01/12/2023 | 120 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 0 | 100
2151 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000380/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.77 | 0 | 0
2152 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000537/2023-2024 | 4297/BWD | 29/09/2023 | 0 | Resource Division | 1.83 | 0 | 0
2153 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000553/2023-2024 | 4445/BWD | 09/10/2023 | 0 | Resource Division | 14.51 | 0 | 0
2154 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000765/2023-2024 | 198/BWD | 10/01/2024 | 0 | Resource Division | 16.34 | 0 | 0
2155 | Central Mechanical |  | Quotation for new service connection for Khano PWSS PH 3. |  |  | BILL/00220/2024-2025 | BP-2024-25-110 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.74 | 0 | 0
2156 | Central Mechanical |  | New service connection charges for Khano PWSS Z-I TW-2 |  |  | BILL/00821/2024-2025 | BP-2024-25-323 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.9 | 0 | 0
2157 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone-1 & 2, T.W. No.- 1 & 2 at KHANO Water Supply Scheme [ BLOCK- Galsi-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000559/2024-2025 | 3089/CMD | 10/12/2024 | 236 | M.S. ENTERPRISE | 50.29 | 0 | 24
2158 | Central Mechanical |  | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Taherpur-khano sub surface water supply scheme under Central Mechanical Division PHE Dte. |  |  | ORD/000784/2024-2025 | 480/CMD | 06/02/2025 | 75 | GLACIER ENGINEERING CO | 105.71 | 0 | 0
2159 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NABASTA, PASHALA & POALKURA Piped Water Supply Scheme under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000739/2023-2024 | 4652/BWD | 31/10/2023 | 898 | STARCO CONSTRUCTIONS | 900.17 | 0 | 2
2160 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000080/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.33 | 0 | 0
2161 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000367/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.8 | 0 | 0
2162 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000757/2023-2024 | 5242/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0
2163 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR PASHALA PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02594/2023-2024 | BP-2023-24-550 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.16 | 0 | 0
2164 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR PASHALA PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02595/2023-2024 | BP-2023-24-549 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 14.97 | 0 | 0
2165 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
2166 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PASHALA Water Supply Scheme [ Block-BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000777/2023-2024 | 4071/CMD | 29/08/2023 | 30 | SOUNAK ENTERPRISE | 27.79 | 0 | 0
2167 | Burdwan Division |  | GUSUMBA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000427/2023-2024 | 3325/BWD | 02/08/2023 | 791 | NATIONAL CONSTRUCTION | 766.99 | 0 | 48
2168 | Burdwan Division |  | Balance work of OHR, construction concrete Road, Functional Household Tap Connection, Construction of drain, Road restoration etc. for GOSUMBA PWSS, under KATWA-I Block under Katwa Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000678/2024-2025 | 3622/BWD | 03/10/2024 | 90 | MA KANKALI ENTERPRISE | 67.86 | 0 | 0
2169 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000271/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.48 | 0 | 0
2170 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000539/2023-2024 | 4306/BWD | 29/09/2023 | 0 | Resource Division | 72.67 | 0 | 0
2171 | Central Mechanical |  | NEW SERVICE CONNECTION FOR GUSUMBA PWSS TW-3 |  |  | BILL/00129/2024-2025 | BP-2024-25-60 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.93 | 0 | 0
2172 | Central Mechanical |  | Quotation for new service connection at Gusumba PWSS, PH-2. |  |  | BILL/00463/2024-2025 | BP-2024-25-251 | 01/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.55 | 0 | 0
2173 | Central Mechanical |  | NEW SERVICE CONNECTION FOR GUSUMBA PWSS TW -1. |  |  | BILL/03098/2023-2024 | BP-2023-24-638 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.88 | 0 | 0
2174 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0
2175 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at GUSUMBA Water Supply Scheme [ Block- KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000863/2023-2024 | 4130/CMD | 29/08/2023 | 30 | S.P. CONSTRUCTION | 44.39 | 0 | 31
2176 | Burdwan Division |  | Continuation work order for Supply of 1 (one) No. Diesel driven Ambassador Car (Luxury Taxi) / Motor Cab on hire basis for the Office of the Assistant Engineer, under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.07.2025 to 31.12.2025]. |  |  | ORD/000319/2025-2026 | 1595/KTS | 30/06/2025 | 184 | KRISHNA MONDAL | 2.4 | 0 | 33
2177 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAGHTONA, & KASIGRAM Piped Water Supply Scheme under Katwa ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000390/2023-2024 | 3199/BWD | 24/07/2023 | 1257 | MANASH GHOSH | 1161.82 | 0 | 95
2178 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 4105/BWD | 25/11/2024 | 0 | Resource Division | 11.5 | 0 | 0
2179 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000215/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 1.33 | 0 | 0
2180 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000432/2023-2024 | 3854/BWD | 01/09/2023 | 0 | Resource Division | 39.78 | 0 | 0
2181 | Central Mechanical |  | NEW SERVICE CONNECTION FOR BAGHTONA PWSS TW-2 |  |  | BILL/00127/2024-2025 | BP-2024-25-61 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.01 | 0 | 0
2182 | Central Mechanical |  | Additional Quotation for new service connection charges for Baghtona PWSS TW-1 |  |  | BILL/01421/2023-2024 | BP-2023-24-145 | 31/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.9 | 0 | 0
2183 | Central Mechanical |  | New service connection charges for Baghtona PWSS TW-1 |  |  | BILL/01422/2023-2024 | BP-2023-24-149 | 01/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.36 | 0 | 0
2184 | Central Mechanical |  | Additional quotation for Baghtona PWSS TW-1 |  |  | BILL/01543/2023-2024 | BP-2023-24-210 | 01/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0 | 0 | 0
2185 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0
2186 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAGHTONA Water Supply Scheme [ Block- KATWA-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000597/2023-2024 | 3954/CMD | 24/08/2023 | 615 | SOUNAK ENTERPRISE | 28.48 | 0 | 44
2187 | Burdwan Division |  | BAINCHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000486/2023-2024 | 3503/BWD | 10/08/2023 | 783 | MAA ENGINEERS CO. OPERATIVE & CONSTRUCTION SOCIETY LTD. | 521.7 | 0 | 75
2188 | Burdwan Division |  | Emmergent LDS work for continuation of pipe line between Chandrapur and Kamal by laying of 200 mm dia. Di pipe and other ancillary work under BAINCHI PWSS (SM/18335) under Katwa-I Block, District:- Purba-Bardhaman |  |  | ORD/001318/2024-2025 | 984/BWD | 13/03/2025 | 62 | BABLU KUMAR MONDAL | 9.24 | 0 | 97
2189 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000219/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.1 | 0 | 0
2190 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000506/2023-2024 | 4030/BWD | 08/09/2023 | 0 | Resource Division | 46.22 | 0 | 0
2191 | Central Mechanical |  | New service connection charges for Bainchi PWSS TW-1 |  |  | BILL/00826/2024-2025 | BP-2024-25-325 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.89 | 0 | 0
2192 | Central Mechanical |  | New service connection charges for Bainchi PWSS TW-2 |  |  | BILL/00827/2024-2025 | BP-2024-25-324 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.75 | 0 | 0
2193 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0
2194 | Central Mechanical |  | CONTINUATION ORDER-Hiring of inspection vehicle bearing no. WB41H5698 (Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Assistant Engineer, CMSD,P.H.E. Dte. [W.E.F-01/09/2025 TO 31/10/2025 ] |  |  | ORD/000280/2025-2026 | 1166/CMSD | 25/08/2025 | 61 | SUBRATA BHADRA | 0.81 | 0 | 0
2195 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAINCHI Water Supply Scheme [ Block- KATWA-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000885/2023-2024 | 4148/CMD | 29/08/2023 | 740 | M/S, S.S. ENTERPRISE. | 30.35 | 0 | 88
2196 | Burdwan Division | Durgapur Sub-DIvision | BAHADURPUR Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000464/2023-2024 | 3455/BWD | 08/08/2023 | 180 | KOUSIK MALLICK | 190.29 | 0 | 95
2197 | Burdwan Division | Durgapur Sub-DIvision | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001180/2023-2024 | 995/DSD | 29/12/2023 | 183 | SUJAUDDIN SEKH | 2 | 0 | 60
2198 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000045/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.44 | 0 | 0
2199 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000217/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.54 | 0 | 0
2200 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000613/2023-2024 | 4916/BWD | 10/11/2023 | 0 | Resource Division | 30.36 | 0 | 0
2201 | Central Mechanical | Durgapur Sub-DIvision | New service connection for Bahadurpur PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02466/2023-2024 | BP-2023-24-529 | 13/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.96 | 0 | 0
2202 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR BAHADURPUR PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02471/2023-2024 | BP-2023-24-533 | 13/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.83 | 0 | 0
2203 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bahadurpur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000912/2023-2024 | 4176/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 28.59 | 0 | 96
2204 | Burdwan Division |  | Balance work OHR Connection, Platform, Laying Parallel Pipeline, providing FHTC, Construction of Boundary Wall, Drain & Pathway at Head Work site & Repairing of Pump House at Head Work site & 2nd Tube Well Site for AUGMENTATION OF RAINA PIPED WATER SUPPLY SCHEME, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. |  |  | ORD/000173/2024-2025 | 2268/BWD | 18/06/2024 | 378 | RANADHIR SINHA | 96.75 | 0 | 65
2205 | Burdwan Division |  | Construction of boundary wall (128.40 Mtr.) including switch room at 3rd tube well site (New) of Aug. of RAINA and its adj. mouzas Piped W/S. Scheme under Budwan Division, PHE. Dte. |  |  | ORD/000185/2024-2025 | 2398/BWD | 26/06/2024 | 370 | RANADHIR SINHA | 19.41 | 0 | 82
2206 | Burdwan Division |  | Restoration of village road damaged by laying pipeline at Nandipara Kalitala,Ranapara and Raina Co-Operative Society of Augmentation of Raina Water Supply Scheme at Raina-I Block within under Burdwan Division,PHE Dte |  |  | ORD/000999/2023-2024 | 117/BSD | 18/01/2024 | 15 | SOUMYAVASH DAS | 0.92 | 0 | 100
2207 | Burdwan Division |  | Repairing and restore pipe line dammaged by laying of pipeline at different location of Augmentation of RAINA and its adjoining mouza's Piped W/S Scheme at Raina-I Block within Burdwan Sub Division under Burdwan Division, P.H.E. Dte |  |  | ORD/001001/2023-2024 | 118/BSD | 18/01/2024 | 30 | POMPA CONSTRUCTION CO. | 0.94 | 0 | 100
2208 | Durgapur W/S Division |  | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.06.2025 to 31.08.2025. |  |  | ORD/000041/2025-2026 | 852/DWSD | 29/05/2025 | 90 | BIPLAB BANERJEE | 0.41 | 0 | 35
2209 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for Design Engineering Services of Survey, General arrangement drawing, Pile foundation design and drawings, Pipe Pedestal and BOM, Structural design design and drawing, Fabrication drawings for 26 Numbers different dia meter pipe crossing Pipe Bridge at "PURANGAN (Zone-I, II, III), 11 Nos. Mouzas under PURSHA and UCHCHGRAM, SHILLA (Zone-I, II, III, IV), TAHER PUR (Zone-I, II, III) and KHANO (Zone-I and II) sites under Durgapur W/S Division,PHE Dte. |  |  | ORD/000105/2024-2025 | 1058/DWSD | 25/07/2024 | 270 | ASTER CONSULTANCY | 47.43 | 0 | 70
2210 | Durgapur W/S Division |  | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhhaman on daily basis (as and when required including Govt. holidays) period of 01.09.2025 to 28.02.2026 (181 days) (Sl-02) |  |  | ORD/000127/2025-2026 | 1380/DWSD | 26/08/2025 | 181 | PRAMIT CHATTERJEE | 0.86 | 0 | 0
2211 | Durgapur W/S Division |  | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.09.2024 to 28.02.2025 (6 Months)(Sl-03) |  |  | ORD/000137/2024-2025 | 1250/DWSD | 30/08/2024 | 182 | BIPLAB BANERJEE | 0.82 | 0 | 0
2212 | Durgapur W/S Division |  | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe carring Bridge with Pipe supporting structure under PURANGRAM and 11 nos Mouzas Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte. |  |  | ORD/000157/2024-2025 | 1503/DWSD | 05/11/2024 | 120 | MANASH GHOSH | 1075.24 | 0 | 50
2213 | Durgapur W/S Division |  | Formal Work Order for Additional work of Soil investigation & construction of CWR/Pump House etc, Land development of H/W Site,drain & internal Path Way, Concrete Road Restoration,FHTC with Platform with necessary allied Works of Sub Surface Based PURANGAN Pipe W/S Scheme (JJM) under Galsi - I Block, Dist - Purba- Bardhaman ,under Durgapur Water Supply Division, PHE Dte. |  |  | ORD/000163/2024-2025 | 1521/DWSD | 11/11/2024 | 360 | MANASH GHOSH | 789.87 | 0 | 75
2214 | Durgapur W/S Division |  | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.03.2025 to 31.05.2025. |  |  | ORD/000273/2024-2025 | 334/DWSD | 27/02/2025 | 89 | BIPLAB BANERJEE | 0.41 | 0 | 35
2215 | Durgapur W/S Division |  | Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.03.2024 to 31.08.2024 (6 Months)(Sl-03) |  |  | ORD/000296/2023-2024 | 269/DWSD | 29/02/2024 | 184 | BIPLAB BANERJEE | 0.82 | 0 | 0
2216 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for the work of Sinking of 3 nos 300 x 200 mm dia T/W 150 mtr and 20Nos 200 x 200 mm dia Riverbank T/W 51 mtr with Construction of P/H cum switch room chlorine room at Uchagram under 11 nos mouzas PWSS (JJM), Block:- Galsi-I, Dist- Purba Bardhaman. |  |  | ORD/000310/2023-2024 | 373/DWSD | 15/03/2024 | 785 | S & P ENTERPRISE | 72.51 | 0 | 50
2217 | Burdwan Division |  | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. |  |  | ORD/000872/2023-2024 | 5324/BWD | 01/12/2023 | 120 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 0 | 100
2218 | Central Mechanical |  | Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries including intake (Low lift) pumping machineries, High Lift pumping machineries, 0-1 kg/hour gaseous chlorination system and illumination arrangement of Purangan & 11 nos. mouza Sub-Surface Based Piped Water Supply Scheme under Purba Bardhaman District PHE Dte. |  |  | ORD/000003/2025-2026 | 905/CMD | 04/04/2025 | 75 | WEST BENGAL ENGINEERING CO. | 317.99 | 0 | 0
2219 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone- Pursa, Uchchagram &, Rampur at 11 nos. Mouja Water Supply Scheme [ BLOCK- Galsi-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000605/2024-2025 | 3100/CMD | 11/12/2024 | 60 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 37.78 | 0 | 0
2220 | Central Mechanical |  | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Purangan & 11 nos. Mouza water supply scheme under Central Mechanical Division PHE Dte. |  |  | ORD/000774/2024-2025 | 479/CMD | 06/02/2025 | 75 | S.P. CONSTRUCTION | 135.24 | 0 | 0
2221 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000530/2023-2024 | 4292/BWD | 29/09/2023 | 0 | Resource Division | 68.65 | 0 | 0
2222 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000580/2023-2024 | 4894/BWD | 10/11/2023 | 0 | Resource Division | 36.98 | 0 | 0
2223 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000769/2023-2024 | 205/BWD | 10/01/2024 | 0 | Resource Division | 19.71 | 0 | 0
2224 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000779/2023-2024 | 322/BWD | 24/01/2024 | 0 | Resource Division | 42.03 | 0 | 0
2225 | Central Mechanical |  | New service connection for Khandra PH-3 PWSS. |  |  | BILL/00087/2024-2025 | BP-2024-25-26 | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.24 | 0 | 0
2226 | Central Mechanical |  | New Service connection at KHANDRA PWSS TW-1. |  |  | BILL/02366/2023-2024 | BP-2023-24-486 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0
2227 | Central Mechanical |  | New Service connection at KHANDRA PWSS TW-2. |  |  | BILL/02367/2023-2024 | BP-2023-24-487 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.6 | 0 | 0
2228 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
2229 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KHANDRA Water Supply Scheme [ Block-MONTESWAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000920/2023-2024 | 4184/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 44.74 | 0 | 33
2230 | Burdwan Division | Katwa Sub-Division | Hire & fuel charges of vehicle (Car No.-WB-04G-6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of January'23. | Assistant Engineer |  | BILL/00468/2022-2023 | 1118/JJM | 27/02/2023 | 0 | M/S MUNMUN DEY | 0.26 | 0 | 0
2231 | Burdwan Division | Katwa Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme AGRADWIP, KHETPUR PALASHI, SAHAPUR PWSS (Sl No-1) | Assistant Engineer |  | ORD/000069/2023-2024 | 393/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 3.71 | 0 | 100
2232 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur (Pt.-A) village of Khetpur Palasi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-183/BWD/2020-21) | Assistant Engineer |  | ORD/000104/2020-2021 | 2601/BWD | 04/08/2020 | 30 | CHANCHAL PAL | 4.92 | 4.92 | 1
2233 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur (Pt-B) village of Khetpur Palasi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-165/BWD/2020-21) | Assistant Engineer |  | ORD/000105/2020-2021 | 2605/BWD | 04/08/2020 | 30 | SANTANU BHATTACHARYAY | 4.92 | 4.92 | 1
2234 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur Palashi (Pt-B) village of Khetpur Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-463/BWD/2020-21) | Assistant Engineer |  | ORD/000284/2020-2021 | 242/KTS | 01/10/2020 | 4 | SANTANU BHATTACHARYAY | 1.21 | 1.2 | 1
2235 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur Palashi (Part-A) village of Khetpur Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. (Tr No.-471/BWD/2020-21) | Assistant Engineer |  | ORD/000350/2020-2021 | 241/KTS | 01/10/2020 | 4 | CHANCHAL PAL | 1.19 | 1.17 | 1
2236 | Burdwan Division | Katwa Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur (Pt-A) village of Khetpur-Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-257/BWD/2020-21) | Assistant Engineer |  | ORD/000473/2020-2021 | 3528-A/BWD | 25/09/2020 | 30 | CHANCHAL PAL | 2.81 | 2.81 | 1
2237 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection from existing distribution system within the command area of Kshetpur Palashi PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-1] | Assistant Engineer |  | ORD/000589/2021-2022 | 126/KTS | 21/02/2022 | 30 | SANTANU BHATTACHARYAY | 3.19 | 0 | 1
2238 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur village of Khetpur Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000626/2020-2021 | 366/KTS | 15/12/2020 | 7 | TAPAS KUMAR ROY | 2.82 | 2.8 | 1
2239 | Burdwan Division | Katwa Sub-Division | Construction of sluice valve chamber (80 mm dia S/V) of Khetpur Palashi piped water supply scheme under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No.-01] | Assistant Engineer |  | ORD/000731/2020-2021 | 14/KTS | 08/01/2021 | 3 | CHANCHAL PAL | 0.41 | 0.41 | 1
2240 | Burdwan Division | Katwa Sub-Division | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | Assistant Engineer |  | ORD/000867/2020-2021 | 4318/BWD | 04/11/2020 | 10 | MD HASIN | 4.93 | 0 | 1
2241 | Burdwan Division | Katwa Sub-Division | Hire & fuel charges of vehicle (Car No.-WB-41H/3668) for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. for the month of July & August'2022. | Assistant Engineer |  | VCH/000645/2022-2023 | 612/VEH/22-23 | 23/09/2022 | 0 | MD HASIN | 0.56 | 0 | 0
2242 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for Providing Functional Household tap connection at Siali Habitation of SIALI Piped Water Supply Scheme under Burdwan Division, P.H.E.Dte. [Group : D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000037/2022-2023 | 243/AE/HQ | 20/04/2022 | 30 | BOSE ENTERPRISE | 3.1 | 0 | 1
2243 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of HDPE pipeline for Providing Functional Household Tap Connection at Amarpur Habitation of SIALI Piped Water Supply Scheme under Burdwan Division,P.H.E.Dte. [Group : E] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000039/2022-2023 | 244/AE/HQ | 20/04/2022 | 30 | BOSE ENTERPRISE | 4.11 | 0 | 1
2244 | Burdwan Division | Burdwan Sadar Sub-Division | Re-alignment of damaged distribution pipeline at different section due to road widening (PWD Deptt.) of SIALI piped water supply scheme at Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-G] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000261/2021-2022 | 667/BSD | 08/06/2021 | 30 | RAINBOW CONSTRUCTION | 4.7 | 0 | 1
2245 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Amarpur (Amarpur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 572/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000298/2020-2021 | 439/BWD | 19/01/2021 | 60 | M/S ANAND CONSTRUCTION | 16.46 | 0 | 1
2246 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for providing functional house hold tap connection at Kora (Part) village of Siali piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000309/2021-2022 | 1643/BSD | 14/12/2021 | 30 | MUKHERJEE ENTERPRISE | 1.73 | 0 | 1
2247 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC for 100% coverage at Muidipur, Ujirpur, Reshalatpur, Kora, Siali & Amarpur Habitation (Village) for SIALI piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000344/2023-2024 | 3033/BWD | 14/07/2023 | 264 | ANWESHA CONSTRUCTION | 31.38 | 0 | 100
2248 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Mudipur (Part), Rasalatpur (Part) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000346/2021-2022 | 58/BWD | 05/01/2022 | 30 | BOSE ENTERPRISE | 18.34 | 0 | 1
2249 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of uPVC distribution pipe line (Node-128 & 136) in regarding FHTC at Par-Ujirpur village from Sura (Zone-II) water supply scheme within Siali W/S scheme at Jamalpur Development Block. under Burdwan Division, PHE Dte. Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000550/2021-2022 | 370/BSD | 02/03/2022 | 30 | BHARAT CONSTRUCTION | 3.36 | 0 | 1
2250 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline from existing distribution system within the command area of Siali piped water supply scheme at Siali (Math Siali & Siali Habitation) village mouza under Jamalpur Block under Burdwan Division, PHE Dte. [Gr.-E] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000559/2021-2022 | 957/BSD | 23/07/2021 | 30 | ELECTRONIC SURVILLANCE | 3.22 | 0 | 1
2251 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline from existing distribution system within the command area of Siali piped water supply scheme for FHTC at Ujirpur (Par Ujirpur & Ujirpur Habitation) village mouza under Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000560/2021-2022 | 958/BSD | 23/07/2021 | 30 | ELECTRONIC SURVILLANCE | 4.3 | 0 | 1
2252 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for providing functional household tap connection at Reshalatpur (Part) of Siali piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000577/2021-2022 | 1142/BSD | 26/08/2021 | 30 | DHIRENDRANATH SOM | 2.49 | 0 | 1
2253 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Kora (Kora Habitation), Mudipur (Part) (Mudipur (Part) Habitation) & Reshalatpur (Part) (Reshalatpur (Part) Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000642/2020-2021 | 649/BWD | 27/01/2021 | 60 | DHIRENDRANATH SOM | 19.53 | 0 | 1
2254 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Reshalatpur village and Reshalatpur habitation of SIALI piped water supply scheme within Burdwan Sub-Division, under Burdwan Division, PHE Dte.[Phase-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000694/2020-2021 | 3321/BWD | 18/09/2020 | 30 | MUKHERJEE ENTERPRISE | 4.84 | 0 | 1
2255 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Reshalatpur village and Reslatpur habitation of Siali piped water supply scheme under Burdwan Division, PHE Dte.[Phase-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000718/2021-2022 | 7089/BWD | 22/12/2021 | 30 | MUKHERJEE ENTERPRISE | 3.45 | 0 | 1
2256 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline (Branch & Sub Branch) from existing distribution system within the command area of Siali piped water supply scheme for FHTC at Mudipur village and Mudipur habitation within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-I] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000774/2021-2022 | 1030/BSD | 05/08/2021 | 30 | ELECTRONIC SURVILLANCE | 2.16 | 0 | 1
2257 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Ujirpur (Par Ujirpur & Ujirpur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte._2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000922/2020-2021 | 1546/BWD | 22/02/2021 | 30 | SKILLS AND FACILITY TRAINING INSTITUTE | 18.87 | 0 | 1
2258 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Siali (Math Siali & Siali Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte._2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000923/2020-2021 | 1709/BWD | 25/02/2021 | 30 | SKILLS AND FACILITY TRAINING INSTITUTE | 18.33 | 0 | 1
2259 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Rahatpur village and Rahatpur Habitation of Rahatpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-491/BWD/2020-21) |  |  | ORD/000200/2020-2021 | 4116/BWD | 16/10/2020 | 30 | DUBE ENTERPRISE | 4.87 | 4.87 | 1
2260 | Burdwan Division |  | Extension of 63 mm dia UPVC pipeline to provide house connection to the beneficiaries of Rahatpur water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Sl No.-B] |  |  | ORD/000828/2020-2021 | 139/KSD | 12/02/2021 | 30 | DUBE ENTERPRISE | 4.49 | 0 | 1
2261 | Burdwan Division |  | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Rahatpur village and Rahatpur habitation of Rahatpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Gr.-7A] |  |  | ORD/000837/2020-2021 | 4913./BWD | 08/12/2020 | 30 | DUBE ENTERPRISE | 4.31 | 0 | 1
2262 | Burdwan Division | Kalna Sub-division | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of March to September'2022. | Assistant Engineer |  | BILL/00145/2022-2023 | 866/VEH | 09/12/2022 | 0 | PARTHA PRATIM ACHARYA | 2.79 | 0 | 0
2263 | Burdwan Division | Kalna Sub-division | Hire & fuel charges of vehicle (Car No.-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of October & November'2022. | Assistant Engineer |  | BILL/00288/2022-2023 | 956/JJM/22-23 | 13/01/2023 | 0 | PARTHA PRATIM ACHARYA | 0.77 | 0 | 0
2264 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Banki village and Banki habitation of Bamungoria Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿10B¿] | Assistant Engineer |  | ORD/000137/2021-2022 | 4543/BWD | 06/09/2021 | 30 | GOUTAM KUMAR MITRA | 0.97 | 0 | 1
2265 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bamangaria village and Bamangaria habitation of Bamangaria piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-536/BWD/2020-21) | Assistant Engineer |  | ORD/000169/2020-2021 | 4122/BWD | 16/10/2020 | 30 | PAL CONSTRUCTION | 4.86 | 4.86 | 1
2266 | Burdwan Division | Kalna Sub-division | Different Types of work involved in connection with Augmentation of SONARUDRA (SM/16349) & KACHUA (SM/13497) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000192/2024-2025 | 2430/BWD | 27/06/2024 | 480 | R.G. INFRASTRUCTURE | 240.7 | 0 | 2
2267 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 14 Nos. Piped W/S. Schemes under Purbasthali I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000337/2024-2025 | 3017/BWD | 05/08/2024 | 75 | HORIZEN | 38 | 0 | 100
2268 | Burdwan Division | Kalna Sub-division | Extension of different dia UPVC pipeline to provide house connections to the different leftout areas in the command area of Bamungaria W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer |  | ORD/000392/2021-2022 | 07/KSD Dt-04.01.2022 | 04/01/2022 | 31 | PAL CONSTRUCTION | 2.52 | 0 | 1
2269 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhaturia village (Bhaturia habitation) of Bamungoria Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part-A). [SL. No. : 22] | Assistant Engineer |  | ORD/000467/2020-2021 | 1461/BWD | 18/02/2021 | 15 | ABDUL HAI | 4.86 | 4.86 | 0
2270 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhaturia village (Bhaturia habitation) of Bamungoria Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part-B). [SL. No. : 23] | Assistant Engineer |  | ORD/000530/2020-2021 | 1460/BWD | 18/02/2021 | 15 | SANTANU BHATTACHARYAY | 4.86 | 4.86 | 0
2271 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Banki village and Banki Habitation of Bamangaria piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer |  | ORD/000606/2020-2021 | 4123/BWD | 16/10/2020 | 30 | GOUTAM KUMAR MITRA | 4.86 | 4.52 | 1
2272 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bamangaria village and Bamungoria habitation of Bamungoria Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿10A¿] | Assistant Engineer |  | ORD/000920/2020-2021 | 151/BWD | 08/01/2021 | 30 | PAL CONSTRUCTION | 1.73 | 0 | 1
2273 | Burdwan Division | Burdwan Division | Providing FHTC for 100% coverage at Baidyabatipur, Tilkuria, Mahishgaria, Narayanpur & Mathurapur village (Mouza) for MAHISHGARIA Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000101/2023-2024 | 2259/BWD | 18/05/2023 | 30 | MUKHERJEE ENTERPRISE | 11.92 | 0 | 100
2274 | Burdwan Division | Burdwan Division | Extension of pipeline including leftout Functional Household Tap Connection (FHTC) for Mahishgoria Piped Water Supply Scheme at Mahishgoria, Bidyabatipur, Narayanpur village in Jamalpur Block under Burdwan Division, PHE Dte. GROUP : D | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000230/2022-2023 | 427/AE/HQ | 03/08/2022 | 30 | A R TRADERS | 4.91 | 0 | 1
2275 | Burdwan Division | Burdwan Division | Land development and Construction of valve chamber by raising of height at 2nd Pumphouse, MAHISHGORIA piped W/S Scheme at Jamalpur Development Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/001033/2024-2025 | 85/AE/HQ | 08/01/2025 | 30 | A.R. TRADERS | 0.72 | 0 | 0
2276 | Burdwan Division | Burdwan Division | Land development and Construction of valve chamber by raising of height for control of water flow within command area of MAHISHGORIA H/W Pump house, MAHISHGORIA piped W/S Scheme at Jamalpur Development Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/001034/2024-2025 | 86/AE/HQ | 08/01/2025 | 30 | A.R. TRADERS | 0.93 | 0 | 0
2277 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jhaudanga & Sarisha village and North Jhaudwnga (Part) & Sarisha habitation of Jhaudanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-554/BWD/2020-21) | Assistant Engineer |  | ORD/000256/2020-2021 | 4114/BWD | 16/10/2020 | 30 | BARABELUN NO.-II G.P. UNEMPLOYED CO-OP LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.86 | 4.86 | 1
2278 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 09 Nos. Piped W/S. Schemes under Purbasthali II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000338/2024-2025 | 3018/BWD | 05/08/2024 | 50 | HORIZEN | 23.7 | 0 | 10
2279 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jhaudanga village and North Jhaudanga (Part) habitation of Jhaudanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-761/BWD/2020-21) | Assistant Engineer |  | ORD/000372/2020-2021 | 4113/BWD | 16/10/2020 | 30 | BARDHAMAN AQUA ENGINEERING | 4.86 | 4.86 | 1
2280 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jhaudanga village and North Jhaudanga (Part) habitation of Jhaudanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-762/BWD/2020-21) | Assistant Engineer |  | ORD/000373/2020-2021 | 4795/BWD | 03/12/2020 | 30 | BARDHAMAN AQUA ENGINEERING | 3.51 | 3.51 | 1
2281 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jhaudanga village (Jhaudanga south habitation) of Jhaudanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-868/BWD/2020-21) | Assistant Engineer |  | ORD/000612/2020-2021 | 597/BWD | 25/01/2021 | 15 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.86 | 4.86 | 1
2282 | Burdwan Division | Kalna Sub-division | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 51
2283 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for UTTAR RADHAKANTAPUR Piped water Supply Scheme at Harirambati[7 Nos],Kamalpur[4 Nos],Kole[5 Nos],Mallikapur[2 Nos],Sahanagar[5 Nos]Total 23 Nos FHTC Work for Sajal Gram(As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout household water tap connection(FHTC)under Burdwan Division,PHE Dte.Gr.D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000336/2022-2023 | 1359/BSD | 03/08/2022 | 5 | D.M. ENTERPRISE | 0.96 | 0 | 1
2284 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Radhakantapur High School Kantagorer Par [23 Nos],Total 23 Nos FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification) within Memari-I Block including leftout household water tap connection(FHTC)under Burdwan Division,PHE Dte. Gr.U | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000337/2022-2023 | 1365/BSD | 04/08/2022 | 5 | D.M. ENTERPRISE | 0.97 | 0 | 1
2285 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Radhakantapur Purbo Sansad Dule Para(23 Nos)Total 23 Nos FHTC Work for Sajal Gram(As per Field Verification Report for Har Ghar Jal Certification and praved for Prodhan of Gop Ganter-II G.P. within Memari-I Block including leftout household water tap connection(FHTC)under Burdwan Division,PHE Dte. Gr.V | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000338/2022-2023 | 1366/BSD | 04/08/2022 | 5 | D.M. ENTERPRISE | 0.97 | 0 | 1
2286 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Memari-I Block (Daluibazar-II, Gopegantar-I & II G.P.) under Burdwan Division, PHE. Dte. Dte._Part-A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000371/2021-2022 | 209/BWD | 11/01/2022 | 30 | M/S ANAND CONSTRUCTION | 21.11 | 0 | 1
2287 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Uttar Radhakantapur, Patra, Katna etc village mouza, Memari-I Block under BURDWAN Division, P.H.E Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000590/2023-2024 | 3763/BWD | 29/08/2023 | 760 | DEY NIRMAN | 13.95 | 0 | 100
2288 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Harirambati [7 No's], Kamalpur [4 No's], Kole [5 No's] Mallikapur [2 No's], Sahanagar [5 No's]Total 23 No's FHTC Work for Sajal Gram (As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000647/2022-2023 | 1359-A/BSD | 03/08/2022 | 5 | D.M. ENTERPRISE | 0.96 | 0 | 1
2289 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Radhakantapur High School Kantagorer Par [23 Nos] Total 23 No's FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000651/2022-2023 | 1365-A/BSD | 04/08/2022 | 5 | D.M. ENTERPRISE | 0.97 | 0 | 1
2290 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Radhakantapur Purbo Sansad Dule Para[23 No's] Total 23 No's FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000652/2022-2023 | 1366-A/BSD | 04/08/2022 | 5 | D.M. ENTERPRISE | 0.97 | 0 | 1
2291 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Purba Shrirampur Village, Memari - II Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000742/2023-2024 | 837/AE/HQ | 31/10/2023 | 30 | MUNSHI JAVEDUR JAMAN | 0.76 | 0 | 100
2292 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Mallikpur Village, Memari - I Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000781/2023-2024 | 859/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0 | 100
2293 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Sahanagar Village, Memari - I Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000782/2023-2024 | 860/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0 | 100
2294 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Kamalpur Village, Memari - I Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000785/2023-2024 | 862/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0 | 100
2295 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Balidanga Village, Memari - I Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000786/2023-2024 | 863/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0 | 100
2296 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of PVC Water supply line at Koley village for UTTAR RADHAKANTAPUR and its adjoining mouza W/S Scheme Block:Memari-I within Burdwan Sub-Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001012/2023-2024 | 120/BSD | 18/01/2024 | 30 | A R TRADERS | 0.92 | 0 | 98
2297 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of 200mm.dia. HDPE Distribution pipe line (Node No.118 to 119) for Masagram (Zone-I) & adjoining mouzas Water Supply Scheme at Jamalpur Development block under Burdwan Division,PHE Dte. Group : C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000090/2022-2023 | 830/BSD | 23/05/2022 | 30 | M/S ASHA CONSTRUCTION | 4.6 | 0 | 1
2298 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipe linefor providing functional house hold tap connection at Sanchra habitation(Part)of MOSAGRAM ZONE-II Piped Water Supply Schemewithin Burdwan Sub-Divn under Burdwan Division,PHE Dte". Group : E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000104/2022-2023 | 987/BSD | 16/06/2022 | 30 | MD HASIN | 2.51 | 0 | 1
2299 | Burdwan Division | Burdwan Sadar Sub-Division | Re-laying of UPVC Pipeline(Damaged by Irrigation Department)and repairing damaged FHTC at Masagram Mouza (Habitation) under Masagram Zone-I Piped Water Supply Scheme Jamalpur Development under Burdwan Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000183/2023-2024 | 1007/BSD | 06/06/2023 | 15 | DEBASHISH ENTERPRISE | 0.85 | 0 | 100
2300 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Masagram Piped Water Supply Scheme at Habaspur Village, Chouberia Village, Ballabhbati Village & Masagram (4 Nos. habitations), Jamalpur Block under Burdwan Division, PHE Dte. (Agr. No. 710/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000342/2020-2021 | 1578/BWD | 22/02/2021 | 60 | MD HASIN | 60.21 | 14.7 | 1
2301 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of UPVC distribution pipeline in connection with FHTC for Masagram (Zone-I) & adjoining mouzas water supply scheme at Jamalpur Development Block under Burdwan Division, PHE Dte.[Gr.-B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000419/2021-2022 | 1112/BSD | 23/08/2021 | 45 | M/S ASHA CONSTRUCTION | 4.71 | 0 | 1
2302 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Masagram Piped Water Supply Scheme at Dadpur Village, Sarangpur Village (2Nos. habitations) & Sanchra Village, Jamalpur Block under Burdwan Division, PHE Dte.(Agreement No. 753/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000437/2020-2021 | 1599/BWD | 22/02/2021 | 60 | M/S ASHA CONSTRUCTION | 65 | 34.96 | 1
2303 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary Wall at 2nd T/W Site of Masagram Zone-I Water Supply Scheme under Jamalpur Block of Burdwan Division, PHE Dte (Length-50.0 Mtr,Col-17 Nos). Gr.E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000443/2021-2022 | 201/BSD | 01/02/2022 | 45 | SANDIPAN SENGUPTA | 3.12 | 0 | 1
2304 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of UPVC distribution pipeline in connection with FHTC for Masagram (Zone-II) and its adjoining mouzas water supply scheme at Jamalpur Development Block under Burdwan Division, PHE Dte. (Habaspur Habitation) [Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000535/2021-2022 | 1206/BSD | 09/09/2021 | 30 | MD HASIN | 4.85 | 0 | 1
2305 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Approach P.C.C Road & Circular Soak Well At Head works site of MASAGRAM Zone-II Piped W/S. Scheme at Jamalpur Dev. Block under Burdwan Division, PHE Dte._2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000837/2024-2025 | 966/AE/HQ | 22/11/2024 | 30 | SOUMYAVASH DAS | 0.93 | 0 | 0
2306 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 mm X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) with construction of Pump House, Boundary wall, Land Development and Rising main connection of MASAGRAM (Zone-II) Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. [FOR 3rd. TUBE WELL SITE]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001042/2023-2024 | 785/BWD | 27/02/2024 | 187 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 25.8 | 0 | 40
2307 | Burdwan Division | Burdwan Sadar Sub-Division | Re-laying of u-PVC Pipeline damaged by Irrigation department at Sanchra village of Masagram Zone-II Piped W/S Scheme at Jamalpur Development Block under Burdwan Division,PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001130/2023-2024 | 127/BSD | 18/01/2024 | 30 | DHIRENDRANATH SOM | 0.85 | 0 | 0
2308 | Burdwan Division | Kalna Sub-division | Quotation charges of WBSEDCL of Aug. of Samudragarh PWSS. [Ref. ID-503495985] | Assistant Engineer |  | BILL/01124/2023-2024 | 1087/JJM | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.42 | 0 | 0
2309 | Burdwan Division | Kalna Sub-division | Quotation charges of WBSEDCL of Aug. of Samudragarh PWSS. [Ref. ID-503564676][TW-4] | Assistant Engineer |  | BILL/01690/2023-2024 | 1366/JJM | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.35 | 0 | 0
2310 | Burdwan Division | Kalna Sub-division | Quotation from WBSEDCL for load enhancement of Augmentation of Samudragarh w/s scheme for P.H.-3 under Burdwan Division, PHE Dte. | Assistant Engineer |  | BILL/01928/2023-2024 | 1825/JJM | 27/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.39 | 0 | 0
2311 | Burdwan Division | Kalna Sub-division | Augmentation of SAMUDRAGARH Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 450 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation including with construction of boundary wall at Head works site under Purbasthali I Block, District - Purba Bardhaman. | Assistant Engineer |  | ORD/000015/2022-2023 | 1963/BWD | 12/04/2022 | 365 | AZAD ENTERPRISE | 426.18 | 0 | 80
2312 | Burdwan Division | Kalna Sub-division | Additional works to implement the augmentation of SAMUDRAGARH Piped Water Supply Scheme under Purbasthali-I Block, Dist :- Purba Burdwan under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000016/2023-2024 | 1731/BWD | 13/04/2023 | 30 | AZAD CONSTRUCTION | 18.67 | 0 | 100
2313 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Samudragarh W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-E) | Assistant Engineer |  | ORD/000583/2021-2022 | 217/KSD | 24/02/2022 | 21 | M/S R. DUTTA & CO. | 2.8 | 0 | 1
2314 | Burdwan Division | Kalna Sub-division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of SAMUDRAGARH Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte.SL. No. 10 | Assistant Engineer |  | ORD/000636/2021-2022 | 144/AE/HQ | 16/03/2022 | 10 | MA SARADA ENTERPRISE | 4.52 | 0 | 1
2315 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000041/2021-2022 | 540/BWD | 27/01/2022 | 0 | Resource Division | 20.81 | 0 | 0
2316 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000109/2021-2022 | 930/BWD | 16/02/2022 | 0 | Resource Division | 22 | 0 | 0
2317 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000208/2021-2022 | 1531/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
2318 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
2319 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall including land development at 2nd Pump house of PALSIT within command area of PALSIT Piped W/S. Scheme under Burdwan Division, PHE. Dte. [Group : F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000057/2022-2023 | 238/AE/HQ | 19/04/2022 | 30 | M/S F.S. ENTERPRISE | 0.96 | 0 | 1
2320 | Burdwan Division | Burdwan Sadar Sub-Division | Providing left out FHTC for 100% covarage in different village within PALSIT PWSS , Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000116/2024-2025 | 995/BSD | 06/06/2024 | 30 | M/S PALASH BISWAS | 0.96 | 0 | 100
2321 | Burdwan Division | Burdwan Sadar Sub-Division | Providing left out FHTC for 100% coverage in different village within PALSIT PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000153/2024-2025 | 1038/BSD | 10/06/2024 | 30 | M/S PALASH BISWAS | 0.95 | 0 | 100
2322 | Burdwan Division | Burdwan Sadar Sub-Division | Additional extension UPVC distribution Pipeline in connection with FHTC work for Palsit Piped Water Supply Scheme at Khargram, Karanda, Palsit & Bhaita under Bardhaman- II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000172/2021-2022 | 6065/BWD | 07/10/2021 | 30 | BRINDABAN KONAR | 14.22 | 0 | 1
2323 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of PALSIT & its adjoining mouzas Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000523/2022-2023 | 4886/BWD | 02/11/2022 | 30 | WESTERN WATER SUPPLY AGENCY | 10.04 | 0 | 100
2324 | Burdwan Division | Burdwan Sadar Sub-Division | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Palsit piped water supply scheme at Bhaita (11 Nos Habitation), Khargram (17 Nos. Habitation), Palsit (19 Nos. Habitation), Karanda (17 Nos. Habitation) & Paschim Chandipur village, Bardhaman-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000528/2020-2021 | 5000/BWD | 10/12/2020 | 90 | BRINDABAN KONAR | 96.95 | 27.91 | 0
2325 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for PALSIT its Adjoining Mouza W/S Scheme, Block -Bardhaman-II within Burdwan Sub-Division, PHE Dte. (Mouza- KARANA) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000766/2022-2023 | 498/BSD | 21/03/2023 | 45 | M/S PALASH BISWAS | 3.32 | 0 | 100
2326 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC for 100% coverage in different village from existing distribution system within PALSIT PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000790/2022-2023 | 1423/BWD | 24/03/2023 | 30 | BABUL SK | 28.53 | 0 | 100
2327 | Burdwan Division | Burdwan Sadar Sub-Division | Providing parallel distribution system from Khargram more to Bhaita High School within PALSIT PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000968/2023-2024 | 005/BWD | 02/01/2024 | 30 | TARAMA AGENCY | 20.68 | 0 | 100
2328 | Burdwan Division | Burdwan Sadar Sub-Division | Hire & fuel charges of vehicle (Car No.-WB-41H/3668) for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. for the month of July & August'2022. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | VCH/000645/2022-2023 | 612/VEH/22-23 | 23/09/2022 | 0 | MD HASIN | 0.56 | 0 | 0
2329 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of SRIDHARPUR Piped Water Supply Scheme with LDS, FHTC, Rising Main with necessary interconnection, Construction of 200 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation under Memari II Block, District Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000007/2022-2023 | 1937/BWD | 11/04/2022 | 365 | SUJAY KUMAR RAY | 251.3 | 0 | 60
2330 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Sridharpur W/S Scheme under Memari-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.6. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000494/2021-2022 | 181/BSD | 31/01/2022 | 30 | RADIANT | 2.59 | 0 | 1
2331 | Burdwan Division | Burdwan Sadar Sub-Division | Replacement of Tube-well & Rising main at HEAD TW site for Aug. of PARHATI, SRIDHARPUR, SATGACHIA ZONE-I, SATGACHIA ZONE-II, Piped Water Supply Scheme within MEMARI-II Block under Burdwan Divn., PHE. Dte. District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000973/2023-2024 | 24/BWD | 03/01/2024 | 637 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 54.2 | 0 | 90
2332 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000062/2021-2022 | 562/BWD | 27/01/2022 | 0 | Resource Division | 11 | 0 | 0
2333 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000110/2021-2022 | 1069/BWD | 24/02/2022 | 0 | Resource Division | 37.52 | 0 | 0
2334 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000197/2021-2022 | 1520/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
2335 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
2336 | Burdwan Division | Burdwan Sadar Sub-Division | Repairing of dismantling concrete road by Cement Concrete (1:3:6) for Augmentation of KHANDAGHOSH Pipe Water Supply Scheme (Mouza Khandaghosh, Iodna, Barisiali, Kapshit, Nabagram, Metedanga) at Khandaghosh Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000364/2022-2023 | 1403/BSD | 10/08/2022 | 60 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.81 | 0 | 100
2337 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Sagrai W/S Scheme under Khandaghosh Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.11. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000500/2021-2022 | 186/BSD | 31/01/2022 | 30 | RADIANT | 2.92 | 0 | 1
2338 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of SAGRAI & its adjoining mouzas Piped Water Supply Scheme, Block - Khandaghosh, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000516/2022-2023 | 4613/BWD | 17/10/2022 | 30 | M/S SYCHROTECH INDUSTRY | 10.22 | 0 | 0
2339 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of SAGRAI Piped Water Supply Scheme with LDS, FHTC, Rising Main with necessary interconnections & Construction of 400 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test under Khandaghosh Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000642/2021-2022 | 1624/BWD | 21/03/2022 | 12 | NATIONAL CONSTRUCTION | 472.26 | 0 | 1
2340 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000058/2021-2022 | 561/BWD | 27/01/2022 | 0 | Resource Division | 16.61 | 0 | 0
2341 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000092/2021-2022 | 931/BWD | 16/02/2022 | 0 | Resource Division | 25.87 | 0 | 0
2342 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000218/2021-2022 | 1541/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
2343 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
2344 | Burdwan Division | Burdwan Sadar Sub-Division | Laying distribution and rising main pipeline including Providing Functional Household Tap Connection (FHTC) for augmentation of SASINARA ZONE III Piped Water Supply Scheme under MEMARI I Block, District: Purba Bardhaman under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000001/2022-2023 | 1839/BWD | 04/04/2022 | 30 | THREE MAA ENTERPRISE | 49.71 | 0 | 1
2345 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of 90mm dia pipeline for SASINARA ZONE-III Piped Water Supply Scheme from Pump house to Nishraghar dharmatala via Annapurnatala under MEMARI- I Block under Burdwan Sub-Division under Burdwan Division, PHE Dte. Group.A. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000099/2022-2023 | 965/BSD | 14/06/2022 | 30 | THREE MAA ENTERPRISE | 4.78 | 0 | 1
2346 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Sasinara (Zone-II) & (Zone-III) W/S Scheme under Burdwan-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000491/2021-2022 | 177/BSD | 31/01/2022 | 30 | RADIANT | 3.76 | 0 | 1
2347 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SASINARA ZONE-III Piped Water Supply Scheme and under NISHRAGHAR Mouza under MEMARI-I Block of Burdwan Sub-Division under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000764/2022-2023 | 510/BSD | 21/03/2023 | 45 | A R TRADERS | 3.51 | 0 | 100
2348 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000151/2021-2022 | 1245/BWD | 07/03/2022 | 0 | Resource Division | 3.92 | 0 | 0
2349 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000180/2021-2022 | 1337/BWD | 08/03/2022 | 0 | Resource Division | 2.81 | 0 | 0
2350 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000225/2021-2022 | 1548/BWD | 15/03/2022 | 0 | Resource Division | 1.32 | 0 | 0
2351 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of SASINARA ZONE-I Piped Water Supply Scheme with LDS, FHTC, Rising main & Construction of 400 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under Memari-I Block, District:- Purba-Burdwan. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000127/2022-2023 | 2971/BWD | 30/06/2022 | 1371 | MRITYUNJOY MUKHERJEE & CO. | 658.71 | 0 | 70
2352 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of Pump House at Head Work site of SASINARA ZONE-I Piped water supply scheme at Memari-I Block under Burdwan Division, Dist.-Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000182/2024-2025 | 1004/BSD | 06/06/2024 | 30 | MS MOLLA CONSTRUCTION | 0.96 | 0 | 0
2353 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-I W/S Scheme at DEBIPUR Mouza under Memari-I Block and SATGACHIA Z-I W/S Scheme at BEGUNIA Mouza under Memari-II Block within Burdwan Sub-Division, PHE Dte. [For 02 Nos. Tube well]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000192/2023-2024 | 2687/BWD | 08/06/2023 | 60 | ANIRUDDHA FARUQUE | 26.48 | 0 | 50
2354 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
2355 | Burdwan Division | Burdwan Sadar Sub-Division | Designing,making and erection of Sign Board for SWAJAL GRAM in Dharmma Simla village of Memari-I Block under Sasinara(Zone-I) Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte (5 Nos. Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000443/2025-2026 | 2307/BSD | 19/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0
2356 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, making and erection of Sign Board for SWAJAL GRAM in Chaupira village of Memari-I Block under Sasinara (Zone-I) Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. (5 nos Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000495/2025-2026 | 2364/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0
2357 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Sasinara (Zone-I) W/S Scheme under Memari-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.3 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000511/2021-2022 | 178/BSD | 31/01/2022 | 30 | APEX ENGINEERING | 3.01 | 0 | 1
2358 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch rooms & Rising main at different TW site for SASINARA (Zone-I) Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000577/2023-2024 | 3725/BWD | 25/08/2023 | 615 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 9.03 | 0 | 90
2359 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, making and erection of Sign Board for SWAJAL GRAM in Jot Chaitanya village of Memari-I Block under Sasinara(Z-I) Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000616/2025-2026 | 2368/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0
2360 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall at 1st Tube well site for SASINARA ZONE- III PWSS under MEMARI - I Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000709/2024-2025 | 3706/BWD | 28/10/2024 | 90 | S.M. ENTERPRISE | 10.59 | 0 | 100
2361 | Burdwan Division | Burdwan Sadar Sub-Division | Replacement of Tube-well & Rising main at HEAD TW SITE for Aug. of BAGILA, SASINARA ZONE-I, SASINARA ZONE-II, Piped Water Supply Scheme within MEMARI-I Block under Burdwan Division, PHE. Dte. District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000974/2023-2024 | 027/BWD | 03/01/2024 | 60 | KOUSIK MALLICK | 38.87 | 0 | 90
2362 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000043/2022-2023 | 4853/BWD | 20/10/2022 | 0 | Resource Division | 13.55 | 0 | 0
2363 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000154/2021-2022 | 1246/BWD | 07/03/2022 | 0 | Resource Division | 4.36 | 0 | 0
2364 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000174/2021-2022 | 1333/BWD | 08/03/2022 | 0 | Resource Division | 51.36 | 0 | 0
2365 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000226/2021-2022 | 1554/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
2366 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
2367 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new service connection at Sasinara W/S (Aug) Z-1, TW-3. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00931/2024-2025 | BP-2024-25-350 | 05/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.88 | 0 | 0
2368 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone- 1 & 2, Tube well No.-3 at Augumentation of SASINARA Water Supply Scheme [BLOCK- MEMARI-I] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000035/2024-2025 | 2138/CMD | 05/07/2024 | 60 | C.M. ENTERPRISE | 24.63 | 0 | 100
2369 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) at Basantaput and Paratal village within the command area of HIRANYAGRAM Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : B] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000041/2022-2023 | 228/AE/HQ | 19/04/2022 | 30 | M/S UNIQUE | 4.77 | 0 | 1
2370 | Burdwan Division | Burdwan Division | Construction of boundary wall (North-East Side) at Headworks site of HIRANYAGRAM W/S Scheme under Jamalpur Block of Burdwan Division, PHE Dte. (Length-63Mtr., Column-26Nos.) [Group : E] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000044/2022-2023 | 237/AE/HQ | 19/04/2022 | 30 | APORUPA CONSTRUCTION | 4.83 | 0 | 1
2371 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) at Basantapur and Ruda village within the command area of HIRANYAGRAM Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : B] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000046/2022-2023 | 200/AE/HQ | 06/04/2022 | 30 | DEY NIRMAN | 4.85 | 0 | 1
2372 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) at Paratal village within the command area of HIRANYAGRAM Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : C] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000047/2022-2023 | 201/AE/HQ | 06/04/2022 | 30 | M/S SAYAN CHAKRABORTY | 4.85 | 0 | 1
2373 | Burdwan Division | Burdwan Division | Laying of 75mm and 50mm dia. uPVC pipe for providing FHTC at different habitation of Paratal and Ruda Mouza within Hiranyagram Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E DTE. [Group: ¿B¿] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000223/2021-2022 | 1818/AE/HQ | 21/09/2021 | 30 | APORUPA CONSTRUCTION | 4.74 | 0 | 1
2374 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Hiranyagram Piped Water Supply Scheme at Ruda Village (2 Nos. habitations), Hiranyagram Village (2 Nos. habitations), Sajipur Village, Basantapur Village (2 Nos. habitations), Parutal Village (2 Nos. habitations), Betragarh Village, Jamalpur Block under Burdwan Division, PHE Dte.[Agreement No. 711/BWD OF 2020-2021.] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000336/2020-2021 | 1597/BWD | 22/02/2021 | 60 | MANASH GHOSH | 93.36 | 45.05 | 1
2375 | Burdwan Division | Burdwan Division | Construction of balance portion of boundary wall at H/W SITE of HIRANYAGRAM Piped W/S. Scheme under Burdwan Division PHE Dte. [Group : C] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000360/2022-2023 | 447/AE/HQ | 16/08/2022 | 30 | APORUPA CONSTRUCTION | 2.98 | 0 | 1
2376 | Burdwan Division | Burdwan Division | Construction of valve chamber and necessary repairing work of pipeline for smooth running of HIRANYAGRAM Piped Water Supply Scheme, Jamalpur Dev. Block under Burdwan Division, P.H.E Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000402/2023-2024 | 387/AE/HQ | 26/07/2023 | 30 | SANDIPAN SENGUPTA | 0.74 | 0 | 100
2377 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) at Hiranyagram village within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : B] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000459/2021-2022 | 67/AE/HQ | 11/02/2022 | 30 | APORUPA CONSTRUCTION | 4.83 | 0 | 1
2378 | Burdwan Division | Burdwan Division | Laying of uPVC pipe for providing FHTC at Ruda, Sajipur, Paratal, Betragar Village within Hiranyagram Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-D | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000629/2021-2022 | 126/AE/HQ | 04/03/2022 | 15 | APORUPA CONSTRUCTION | 4.64 | 0 | 100
2379 | Burdwan Division | Burdwan Division | Continuation order for supply & delivery of different dia CIDF pipes, sluice valve & fittings for construction of RCC OHR (450 cum capacity) for Hiranyagram w/s scheme under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000692/2021-2022 | 388/BWD | 20/01/2022 | 20 | ASHOKE ENGINEERING WORKS | 15.17 | 0 | 1
2380 | Burdwan Division | Burdwan Division | Material Requisition To Resource Division | AE(HQs), Burdwan Division, PHE Dte. |  | RTOR000054/2022-2023 | 5525/BWD | 23/12/2022 | 0 | Resource Division | 0.62 | 0 | 0
2381 | Burdwan Division | Burdwan Division | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Head Quarters, Burdwan Division, PHE Dte. for the month of June & July'22. | AE(HQs), Burdwan Division, PHE Dte. |  | VCH/000493/2022-2023 | 460/VEH/22-23 | 29/08/2022 | 0 | SK. ASRAFUDDIN | 0.76 | 0 | 0
2382 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bhatkunda Piped Water Supply Scheme at Bhatkunda (Part) Village (Adibasi Para, Bhatkunda (P), Boldanga Adibashipara habitation), Moukota (Part) Village (Adibashipara, Moukota (P) habitation), Parisha Village, Chaktilong Village, Ranngakhila Village (4Nos. habitations), Balarambati Village & Jijira Village (2 Nos. habitations) Ausgram - II Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000015/2021-2022 | 3205/BWD | 09/06/2021 | 618 | ASHOK KUMAR GHOSH | 55.74 | 0 | 100
2383 | Burdwan Division | Durgapur Sub-DIvision | Land development and Construction of culvert and approach road at 2nd tubewell site of Bhatkunda Water Supply Scheme within Durgapur Sub Division Under Burdwan Division, PHE Dte.[SL-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000119/2022-2023 | 337/DSD | 27/06/2022 | 30 | RAM MOHAN MUKHERJEE | 3.33 | 0 | 1
2384 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipeline of laying distribution system at Moukata village at Bhatkunda and its adjoining mouzas water supply scheme within Ausgram-II Block under Durgapur Sub-Division under Burdwan Division, PHE Dte. [Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000835/2020-2021 | 171/DSD | 19/02/2021 | 21 | SHUBHRA KANTI GHOSH | 4.62 | 0 | 1
2385 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SUDPUR Piped Water Supply Scheme (PART-A) at Katwa-I Block under Burdwan Division, PHE Dte. [Agreement No. 44/2020-2021 OF SE/CC/PHE. DTE.] | Assistant Engineer |  | ORD/000058/2020-2021 | 4290/BWD | 03/11/2020 | 90 | MD HASIN | 86.85 | 0 | 1
2386 | Burdwan Division | Katwa Sub-Division | Laying of pipe line parallel to the main line of the existing Distribution System including providing FHTC at Kalyanbati, Narayanpur, Bijoynagar, Purba Bijnagar & Ramkrishnapur village (Mouza) within scheme jurisdiction of SUDPUR Piped W/S. Scheme under Burdwan Division PHE Dte. | Assistant Engineer |  | ORD/000279/2021-2022 | 6972/BWD | 15/12/2021 | 60 | MD HASIN | 63.4 | 0 | 1
2387 | Burdwan Division | Katwa Sub-Division | Construction of valve Chamber and supply of sluice valve at Sudpur PWSS under Katwa-I Block under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No-4] | Assistant Engineer |  | ORD/000372/2023-2024 | 671/KTS | 22/06/2023 | 30 | HAMID SK | 0.93 | 0 | 100
2388 | Burdwan Division | Katwa Sub-Division | Balance work of OHR at Head Work site, construction of HUME Pipe culvert , Road restoration work and boundary wall at 2nd TW site with Gate, land development at Head work site and 2nd TW site under KAITHAN, SUDPUR & PANUHAT Piped Water Supply Scheme under KATWA -I Block, under Katwa Sub-Division within Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000486/2024-2025 | 3141/BWD | 20/08/2024 | 120 | VISHAL CONSTRUCTION CO. | 126.29 | 0 | 50
2389 | Burdwan Division | Katwa Sub-Division | Supply, delivery & installation of submersible pumping machinery, voltage stabiliser, chlorinator and internal house wiring for Tube well No.-3 of Sudpur water supply scheme under CMD PHE Dte. | Assistant Engineer |  | VCH/000758/2022-2023 | 788/DW/22-23 | 23/11/2022 | 0 | M.S. ENTERPRISE | 9.43 | 0 | 0
2390 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENRIA, MAHATA, DEBPUR Piped Water Supply Scheme under BHATAR Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000019/2023-2024 | 1737/BWD | 13/04/2023 | 993 | M/S B. RAI CONSTRUCTION COMPANY | 1643.39 | 0 | 81
2391 | Burdwan Division | Durgapur Sub-DIvision | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | Assistant Engineer,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001180/2023-2024 | 995/DSD | 29/12/2023 | 183 | SUJAUDDIN SEKH | 2 | 0 | 60
2392 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000087/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 21.04 | 0 | 0
2393 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000173/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 20.38 | 0 | 0
2394 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000640/2023-2024 | 5106/BWD | 23/11/2023 | 0 | Resource Division | 20.32 | 0 | 0
2395 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Debpur PWSS TW-1 | Assistant Engineer,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01419/2023-2024 | BP-2023-24-146 | 31/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.73 | 0 | 0
2396 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Debpur PWSS TW-2 | Assistant Engineer,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01673/2023-2024 | BP-2023-24-224 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.53 | 0 | 0
2397 | Central Mechanical | Durgapur Sub-DIvision | SUPPLY AND INSTALLATION WORKS FOR DEBPUR PWSS | Assistant Engineer,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02624/2023-2024 | BP-2023-24-557 | 21/02/2024 | 0 | P.K. ENGINEERING | 11.09 | 0 | 0
2398 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
2399 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Debpur Water Supply Scheme [ Block- Bhatar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000232/2023-2024 | 3174/CMD | 26/07/2023 | 30 | P.K. ENGINEERING | 27.69 | 0 | 95
2400 | Central Mechanical | Durgapur Sub-DIvision | Continuation order-Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven ) for supervision of site for the office of the Assistant Engineer,under CMD,PHE,Dte. [W.e.f-29/06/2024 to 31/07/2024] | Assistant Engineer,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000424/2024-2025 | 897/CMSD | 28/06/2024 | 33 | SUBRATA BHADRA | 0.4 | 0 | 0
2401 | Burdwan Division | Durgapur Sub-DIvision | Land Development work , Remaining FHTC at Balsidanga Piped Water Supply Scheme , P.H.E Dte. Block:-Bhatar Dist: Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000315/2025-2026 | 1064/DSD | 24/07/2025 | 116 | KALYAN CHOWDHURY | 1.93 | 0 | 100
2402 | Burdwan Division | Durgapur Sub-DIvision | Additional work for BALSIDANGA Piped Water Supply Scheme with FHTC & approach road with bullah pilling under Bhatar Block, District:- Purba Bardhaman [New SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000573/2024-2025 | 3314/BWD | 06/09/2024 | 90 | KALYAN CHOWDHURY | 14.81 | 0 | 100
2403 | Burdwan Division | Durgapur Sub-DIvision | BALSIDANGA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under BHATAR Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000793/2022-2023 | 1443/BWD | 24/03/2023 | 90 | G.S. CONSTRUCTION & CO. | 60.82 | 0 | 100
2404 | Burdwan Division | Durgapur Sub-DIvision | Sinking of 250 X 150 mm dia Tubewell, Construction of pump House, Connection with pump house and Modification to distribution network by making a loop and extension with uPVC pipe to augment the water supply to FHTC at Beldanga and Kanchgoria village of BALSHIDANGA W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001220/2023-2024 | 1017/BWD | 07/03/2024 | 60 | BAMDEB CONSTRUCTION & CO | 40.65 | 0 | 100
2405 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000006/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 14.19 | 0 | 0
2406 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000158/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 9.5 | 0 | 0
2407 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000754/2023-2024 | 5256/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0
2408 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Balsidanga PWSS PH-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00388/2024-2025 | BP-2024-25-203 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.09 | 0 | 0
2409 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Balsidanga PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00774/2023-2024 | BP-2023-24-71 | 21/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.28 | 0 | 0
2410 | Central Mechanical | Durgapur Sub-DIvision | ADDITIONAL QUOTATION NEW SERVICE CONNECTION FOR BALSIDNAGA PWSS TW -1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/03105/2023-2024 | BP-2023-24-645 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.04 | 0 | 0
2411 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
2412 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Balsidanga Water Supply Scheme [ Block- Bhatar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000137/2023-2024 | 2818/CMD | 04/07/2023 | 640 | M/S. SWAPAN BANERJEE | 26.97 | 0 | 60
2413 | Burdwan Division | Durgapur Sub-DIvision | GOPALBERA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000081/2023-2024 | 2079/BWD | 04/05/2023 | 698 | KHAN ENTERPRISE | 588.35 | 0 | 50
2414 | Burdwan Division | Durgapur Sub-DIvision | Balance work for providing Functional Household Tap Connection (FHTC) within command area GOPALBERA & CHAGRAM W/S. Scheme of Khandaghosh Block under Burdwan Divn., PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000959/2024-2025 | 4438/BWD | 18/12/2024 | 253 | DUBE ENTERPRISE | 143.33 | 0 | 70
2415 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000105/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 9.42 | 0 | 0
2416 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000192/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.22 | 0 | 0
2417 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000715/2023-2024 | 5269/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
2418 | Central Mechanical | Durgapur Sub-DIvision | New service connection for Gopalbera PWSS TW -1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02415/2023-2024 | BP-2023-24-513 | 08/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.42 | 0 | 0
2419 | Central Mechanical | Durgapur Sub-DIvision | New service connection for Gopalbera PWSS TW -2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02416/2023-2024 | BP-2023-24-514 | 08/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.28 | 0 | 0
2420 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 10
2421 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gopalbera Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000732/2023-2024 | 4042/CMD | 29/08/2023 | 30 | ASHIM UDYOG | 28.95 | 0 | 100
2422 | Burdwan Division | Burdwan Sadar Sub-Division | CHOTKHANDA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000123/2023-2024 | 2306/BWD | 19/05/2023 | 683 | ASHOK KUMAR GHOSH | 513.64 | 0 | 85
2423 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, land development, Sluice valve chamber for smooth water supply of FHTC work for CHOTKHANDA PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000930/2024-2025 | 4280/BWD | 09/12/2024 | 90 | TARAMA AGENCY | 21.09 | 0 | 0
2424 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000236/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.93 | 0 | 0
2425 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000467/2023-2024 | 3991/BWD | 08/09/2023 | 0 | Resource Division | 9.08 | 0 | 0
2426 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000663/2023-2024 | 5085/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
2427 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Chotkhanda PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01728/2023-2024 | BP-2023-24-244 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.02 | 0 | 0
2428 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new electric service connection at Chotkhanda TW NO.-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01740/2023-2024 | BP-2023-24-243 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.61 | 0 | 0
2429 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0
2430 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chotkhanda Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000731/2023-2024 | 4041/CMD | 29/08/2023 | 369 | S.K. ENTERPRISE | 29.59 | 0 | 100
2431 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & delivery of different electro-mechanical accessories (for urgent FHTC) for Tube well no.-I & II at Chotkhanda w/s scheme, (Block- Memari-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001902/2023-2024 | 540/CMSD | 28/03/2024 | 7 | S.K. ENTERPRISE | 0.53 | 0 | 100
2432 | Burdwan Division | Katwa Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme AGRADWIP, KHETPUR PALASHI, SAHAPUR PWSS (Sl No-1) | Assistant Engineer |  | ORD/000069/2023-2024 | 393/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 3.71 | 0 | 100
2433 | Burdwan Division | Katwa Sub-Division | Supplying and laying of valves along with construction of valve chamber at the existing distribution pipe line of Agradwip PWSS under Katwa Sub-Division under Burdwan Division, PHE Dte [Sl No-04] | Assistant Engineer |  | ORD/000157/2022-2023 | 440/KTS | 27/06/2022 | 30 | TAPAS KUMAR ROY | 0.78 | 0 | 1
2434 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection from existing distribution system within the command area of AGRADWIP PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-1) | Assistant Engineer |  | ORD/000237/2021-2022 | 688/KTS | 08/10/2021 | 7 | CHANCHAL PAL | 1.21 | 0 | 1
2435 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AGRADWIP Piped Water Supply Scheme at Agradwip, Babla danga, Gonsaidhowra, Saheb Nagar & Sarawaridhowra (Mouza), Katwa - II Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000445/2021-2022 | 6253/BWD | 01/11/2021 | 60 | SHUBHRA KANTI GHOSH | 53.67 | 0 | 1
2436 | Burdwan Division | Katwa Sub-Division | Extension of pipe line of Providing Functional Household Tap Connection (FHTC) from existing distribution system within command area of Agradwip Water Supply Schame under Agradwip PWSS at Babla danga and Saheb Nagar Habitation Katwa-II Block Katwa Sub-Division under Burdwan Division PHE Dte.. [Sl No-02] | Assistant Engineer |  | ORD/000605/2021-2022 | 161/KTS | 24/02/2022 | 7 | SHUBHRA KANTI GHOSH | 2.1 | 0 | 1
2437 | Burdwan Division | Katwa Sub-Division | Extension of pipe line of Providing Functional Household Tap Connection (FHTC) from existing distribution system within command area of Agradwip Water Supply Schame under Agradwip PWSS at Gonsaishowra, & Sarawaridhowar Habitation Katwa-II Block Katwa Sub-Division under Burdwan Division PHE Dte.. [Sl No-05] | Assistant Engineer |  | ORD/000608/2021-2022 | 172/KTS | 25/02/2022 | 7 | SHUBHRA KANTI GHOSH | 1.32 | 0 | 1
2438 | Durgapur W/S Division | Durgapur Sub-DIvision | Formal Work Order for Additional work for laying 200 mm dia HDPE pipe line and other necessary allied works Amarpur & Bhedia Piped W/S Scheme, Block- Aushgram-2, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000141/2024-2025 | 1291/DWSD | 06/09/2024 | 210 | SAIKAT RAY | 196.61 | 0 | 60
2439 | Burdwan Division | Durgapur Sub-DIvision | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways for AMARPUR Piped Water Supply Scheme under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000820/2023-2024 | 4952/BWD | 17/11/2023 | 365 | SUJAY KUMAR RAY | 344.32 | 0 | 50
2440 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000043/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 9.35 | 0 | 0
2441 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000208/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 20.19 | 0 | 0
2442 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000611/2023-2024 | 4932/BWD | 10/11/2023 | 0 | Resource Division | 30.36 | 0 | 0
2443 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR AMARPUR PWSS PH 1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02866/2023-2024 | BP-2023-24-604 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0
2444 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR AMARPUR PWSS PH 2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02867/2023-2024 | BP-2023-24-605 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.88 | 0 | 0
2445 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Amarpur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000913/2023-2024 | 4177/CMD | 29/08/2023 | 611 | AMUSAR IMPEX PVT. LTD. | 28.55 | 0 | 96
2446 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of SRIRAMPUR (Zone I & II) (SM/08103), MANGANPUR (SM/13327), KAMALPUR (SM/13453) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000190/2024-2025 | 2429/BWD | 27/06/2024 | 480 | S.P. CONSTRUCTION | 500.89 | 0 | 2
2447 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MANGANPUR & BAGPUR Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000391/2023-2024 | 3200/BWD | 24/07/2023 | 1100 | M/S GHOSH & CO. | 711.81 | 0 | 10
2448 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000339/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.02 | 0 | 0
2449 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000475/2023-2024 | 3999/BWD | 08/09/2023 | 0 | Resource Division | 3.31 | 0 | 0
2450 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000802/2023-2024 | 315/BWD | 24/01/2024 | 0 | Resource Division | 17.52 | 0 | 0
2451 | Central Mechanical | Kalna Sub-division | New service connection charges for Manganpur PWSS TW-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01670/2023-2024 | BP-2023-24-227 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.63 | 0 | 0
2452 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 30
2453 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0
2454 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at MANGANPUR Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000730/2023-2024 | 4040/CMD | 29/08/2023 | 30 | SOUNAK ENTERPRISE | 22.1 | 0 | 50
2455 | Central Mechanical | Kalna Sub-division | Supply and delivery of portable generator set for emergency internal installation work at Manganpur and other Water Supply Scheme under CMD., PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001419/2023-2024 | 153/CMSD | 22/01/2024 | 15 | M/S, MONDAL ASSOCIATES. | 2.11 | 0 | 100
2456 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENUA, IBRAMBAD & UJNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000462/2023-2024 | 3456/BWD | 08/08/2023 | 855 | M/S S. CHOUDHURY | 2123.7 | 0 | 20
2457 | Burdwan Division | Durgapur Sub-DIvision | Arrangement of drinking water supply by installation of solar submersible pump including sinking of 200 mm. dia. Tube well 150 Mtr. Deep by direct rotary rig method, Laying dist. System, FHTC and 2 Nos. 5000 Ltr. PVC tank installation with construction of RCC structure for RUIGORIA Habitation which is uncovered of DHENUA Piped W/S. Scheme, Block Manteswar under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000686/2024-2025 | 3667/BWD | 22/10/2024 | 90 | UJJWAL MUKHERJEE | 31.83 | 0 | 0
2458 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000244/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.24 | 0 | 0
2459 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000448/2023-2024 | 3972/BWD | 08/09/2023 | 0 | Resource Division | 108.75 | 0 | 0
2460 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR DHENUA PWSS. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02689/2023-2024 | BP-2023-24-564 | 23/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.21 | 0 | 0
2461 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR DHENUA PWSS TW -1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/03101/2023-2024 | BP-2023-24-641 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.52 | 0 | 0
2462 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
2463 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Dhenua Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000740/2023-2024 | 4050/CMD | 29/08/2023 | 640 | SUBRATA BHADRA | 29.91 | 0 | 100
2464 | Central Mechanical | Durgapur Sub-DIvision | CONTINUATION ORDER-Hiring of inspection vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of the Assistant Engineer ,under CMD,PHE,Dte.[W.E.F-31/01/2025 TO 31/03/2025][UNDER JJM WORKS] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000778/2024-2025 | 110/CMSD | 30/01/2025 | 60 | PRODYUT GHOSH | 0.79 | 0 | 0
2465 | Burdwan Division | Durgapur Sub-DIvision | MANDARDIHI (PART:-B) Piped Water Supply Scheme with LDS & FHTC [NODE POINT 49 TO 77] under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000717/2022-2023 | 919/BWD | 02/03/2023 | 30 | PAPRI HAZRA | 18.89 | 0 | 100
2466 | Burdwan Division | Durgapur Sub-DIvision | MANDARDIHI (PART:-A) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000719/2022-2023 | 928/BWD | 02/03/2023 | 60 | DUBE ENTERPRISE | 63.01 | 0 | 30
2467 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000080/2022-2023 | 1238/BWD | 17/03/2023 | 0 | Resource Division | 2.16 | 0 | 0
2468 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000752/2023-2024 | 5247/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0
2469 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Mandardihi PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01050/2023-2024 | BP-2023-24-119 | 17/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.61 | 0 | 0
2470 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Mandardihi PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01420/2023-2024 | BP-2023-24-148 | 31/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.15 | 0 | 0
2471 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
2472 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MANDARDIHI Water Supply Scheme [ Block- BHATAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000359/2023-2024 | 3504/CMD | 31/07/2023 | 668 | S.K. ELECTRICALS | 26.96 | 0 | 90
2473 | Central Mechanical | Durgapur Sub-DIvision | Supply and delivery of submersible pumping machinery (for urgent FHTC) for mandardihi Water Supply Scheme PH 2 (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001672/2023-2024 | 66/CMSD | 11/01/2024 | 12 | CHOUDHURY ENTERPRISE | 0.81 | 0 | 100
2474 | Central Mechanical | Durgapur Sub-DIvision | Emergency installation (for urgent FHTC) at Mandardihi Water Supply Scheme PH 2 (part-3) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001676/2023-2024 | 83/CMSD | 15/01/2024 | 12 | CHOUDHURY ENTERPRISE | 0.92 | 0 | 100
2475 | Central Mechanical | Durgapur Sub-DIvision | Supply and delivery of different Electro-mechanical items (for urgent FHTC) for Mandardihi Water Supply Scheme PH 2 (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001748/2023-2024 | 19/CMSD | 04/01/2024 | 10 | CHOUDHURY ENTERPRISE | 0.91 | 0 | 100
2476 | Burdwan Division | Central Mechanical Sub-Division | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | Assistant Engineer | Junior Engineer | ORD/000683/2024-2025 | 1009/KTS | 19/07/2024 | 60 | AJIT SAMANTA | 0.77 | 0 | 100
2477 | Burdwan Division | Central Mechanical Sub-Division | JAGADANANDAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000711/2022-2023 | 777/BWD | 24/02/2023 | 1253 | MANASH GHOSH | 562.08 | 0 | 78
2478 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000062/2022-2023 | 1246/BWD | 17/03/2023 | 0 | Resource Division | 17.02 | 0 | 0
2479 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000096/2022-2023 | 1638/BWD | 06/04/2023 | 0 | Resource Division | 1.1 | 0 | 0
2480 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000786/2023-2024 | 327/BWD | 24/01/2024 | 0 | Resource Division | 22.74 | 0 | 0
2481 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Jagadanandapur W/S Scheme TW-1 | Assistant Engineer | Junior Engineer | BILL/00694/2023-2024 | BP-2023-24-36 | 27/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.38 | 0 | 0
2482 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Jagadanandapur PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/00797/2023-2024 | BP-2023-24-85 | 26/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.95 | 0 | 0
2483 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0
2484 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Jagadanandapur Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000126/2023-2024 | 2659/CMD | 16/06/2023 | 30 | PADMA ENGINEERING CO. | 28.97 | 0 | 60
2485 | Burdwan Division | Kalna Sub-division | Work Order for "Supply of 1 (one) No. Diesel driven Motor cab (Inspection vehicle) on hire basis for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period for 3 (Three) Months]". | Assistant Engineer | JUNIOR ENGINEER | ORD/000668/2023-2024 | 1333/KSD | 28/08/2023 | 72 | PARTHA PRATIM ACHARYA | 0.92 | 0 | 100
2486 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEARA, PATHARDANGA & SHIKARPUR Piped Water Supply Scheme under KALNA-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000734/2022-2023 | 1004/BWD | 06/03/2023 | 641 | M/S TAPAS KUMAR CHAKRABORTY | 1584.09 | 0 | 75
2487 | Burdwan Division | Kalna Sub-division | Work order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DEARA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001143/2023-2024 | 1979/KSD | 09/02/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0 | 100
2488 | Burdwan Division | Kalna Sub-division | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 51
2489 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000087/2022-2023 | 1237/BWD | 17/03/2023 | 0 | Resource Division | 10.42 | 0 | 0
2490 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000091/2022-2023 | 1640/BWD | 06/04/2023 | 0 | Resource Division | 4.7 | 0 | 0
2491 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000515/2023-2024 | 3967/BWD | 08/09/2023 | 0 | Resource Division | 19.84 | 0 | 0
2492 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000638/2023-2024 | 5093/BWD | 23/11/2023 | 0 | Resource Division | 21.42 | 0 | 0
2493 | Central Mechanical | Kalna Sub-division | New service connection charges for Deara PWSS TW-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01669/2023-2024 | BP-2023-24-222 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.46 | 0 | 0
2494 | Central Mechanical | Kalna Sub-division | New service connection for DEARA PWSS | Assistant Engineer | JUNIOR ENGINEER | BILL/02561/2023-2024 | BP-2023-24-544 | 19/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.53 | 0 | 0
2495 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0
2496 | Central Mechanical | Kalna Sub-division | Continuation Order-Providing Diesel generator set at DEARA Water supply scheme for Urgent FHTC connection under CMD PHE Dte. [W.E.F- 05.06.2024 TO 08.06.2024] | Assistant Engineer | JUNIOR ENGINEER | ORD/000461/2024-2025 | 827/CMSD | 04/06/2024 | 7 | S.K. ENTERPRISE | 0.85 | 0 | 100
2497 | Central Mechanical | Kalna Sub-division | Installation of Electrical items & allied works for Urgent FHTC for Deara PH 1 water supply scheme under CMD P.H.E. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000500/2024-2025 | 822/CMSD | 31/05/2024 | 30 | S.K. ENTERPRISE | 0.64 | 0 | 100
2498 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Deara Water Supply Scheme [ Block- KALNA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000757/2023-2024 | 4060/CMD | 29/08/2023 | 485 | S.K. ENTERPRISE | 28.6 | 0 | 100
2499 | Burdwan Division | Durgapur Sub-DIvision | NASIGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000050/2023-2024 | 1826/BWD | 19/04/2023 | 742 | MD HASIN | 742.95 | 0 | 50
2500 | Burdwan Division | Durgapur Sub-DIvision | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000420/2023-2024 | 593/DSD | 31/07/2023 | 66 | AFIBS ENTERPRISE | 0.85 | 0 | 100
2501 | Burdwan Division | Durgapur Sub-DIvision | Making connection with 4th tube well, Construction of Plinth protection of OHR, Restoration of road and FHTC (The rest portion) of Bara Belun Water Supply Scheme at Bara Belun village & Providing Functional Household Tap Connection (FHTC) within the command area of NASIGRAM Piped W/S. Scheme within Bhatar Block under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000690/2024-2025 | 3685/BWD | 23/10/2024 | 120 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 91.48 | 0 | 0
2502 | Burdwan Division | Durgapur Sub-DIvision | Continuation Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/11/2023 to 31/01/2024] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000755/2023-2024 | 825/DSD | 31/10/2023 | 66 | AFIBS ENTERPRISE | 0.85 | 0 | 100
2503 | Burdwan Division | Durgapur Sub-DIvision | Continuation Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/11/2023 to 31/01/2024] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001210/2023-2024 | 825/DSD | 31/10/2023 | 66 | AFIBS ENTERPRISE | 0.85 | 0 | 100
2504 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000071/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 27.18 | 0 | 0
2505 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000176/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 17.06 | 0 | 0
2506 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000583/2023-2024 | 4897/BWD | 10/11/2023 | 0 | Resource Division | 38.94 | 0 | 0
2507 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Nasigram PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00772/2023-2024 | BP-2023-24-72 | 21/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.83 | 0 | 0
2508 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Nasigram PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00773/2023-2024 | BP-2023-24-73 | 21/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.19 | 0 | 0
2509 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR NASIGRAM PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02592/2023-2024 | BP-2023-24-574 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.54 | 0 | 0
2510 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
2511 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at NASIGRAM Water Supply Scheme [ Block- BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000141/2023-2024 | 2856/CMD | 05/07/2023 | 30 | M/S. S.R. ENTERPRISE | 41.65 | 0 | 90
2512 | Burdwan Division | Central Mechanical Sub-Division | Balance work of OHR, construction Concrete Road, Drum Sheet Pilling, Functional Household Tap Connection, construction of HUME Pipe culvert, land development, Road restoration etc. under Billeswar PWSS, Purulia PWSS & Gurpara PWSS under KATWA -II Block under Katwa Sub-Divn. under Burdwan Division, PHED. District:- Purba-Bardhaman | Assistant Engineer | Junior Engineer | ORD/000310/2024-2025 | 2834/BWD | 19/07/2024 | 835 | PASCON | 190.06 | 0 | 90
2513 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000063/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 9.42 | 0 | 0
2514 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000150/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 17.31 | 0 | 0
2515 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000625/2023-2024 | 4871/BWD | 10/11/2023 | 0 | Resource Division | 29.6 | 0 | 0
2516 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Gurpara W/S Scheme PH-I. | Assistant Engineer | Junior Engineer | BILL/01809/2023-2024 | BP-2023-24-308 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.28 | 0 | 0
2517 | Central Mechanical | Central Mechanical Sub-Division | New service connection at Guyrpara PWSS TW No.2 | Assistant Engineer | Junior Engineer | BILL/02376/2023-2024 | BP-2023-24-488 | 01/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.9 | 0 | 0
2518 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0
2519 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gurpara Water Supply Scheme [ Block- Ketugram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000749/2023-2024 | 4059/CMD | 29/08/2023 | 30 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 26.93 | 0 | 91
2520 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NABASTA, PASHALA & POALKURA Piped Water Supply Scheme under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000739/2023-2024 | 4652/BWD | 31/10/2023 | 898 | STARCO CONSTRUCTIONS | 900.17 | 0 | 2
2521 | Burdwan Division | Durgapur Sub-DIvision | Providing Parallal LDS (Node- 30-43-42-41-49 to 36) & 4nos ICDS connection for at Palsa-Chandrasekharpara within Nabastha PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001068/2024-2025 | 358/BWD | 16/01/2025 | 60 | PRATIVA CONSTRUCTION | 7.61 | 0 | 0
2522 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000077/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 80.57 | 0 | 0
2523 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000348/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 3.49 | 0 | 0
2524 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000604/2023-2024 | 4931/BWD | 10/11/2023 | 0 | Resource Division | 33.07 | 0 | 0
2525 | Central Mechanical | Durgapur Sub-DIvision | New Service connection at Nabastha PWSS PH-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02316/2023-2024 | BP-2023-24-456 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.04 | 0 | 0
2526 | Central Mechanical | Durgapur Sub-DIvision | New Service connection at Nabastha PWSS PH-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02317/2023-2024 | BP-2023-24-457 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.95 | 0 | 0
2527 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
2528 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at NABASTA Water Supply Scheme [ Block-BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000776/2023-2024 | 4070/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 27.79 | 0 | 40
2529 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR Balance work for PHANRIJANGAL PWSS with sining of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block under DURGAPUR W/S DIVISION, PHE DTE. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000267/2024-2025 | 281/DWSD | 17/02/2025 | 120 | SUJAY KUMAR RAY | 101.85 | 0 | 0
2530 | Burdwan Division | Durgapur Sub-DIvision | PHANRIJANGAL Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000173/2023-2024 | 3030/BWD | 14/07/2023 | 180 | SUPRIYA RAY | 271.24 | 0 | 35
2531 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000002/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 32.65 | 0 | 0
2532 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000369/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.24 | 0 | 0
2533 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000634/2023-2024 | 5090/BWD | 23/11/2023 | 0 | Resource Division | 21.84 | 0 | 0
2534 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Phanrijangal PWSS TW 1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01484/2023-2024 | BP-2023-24-184 | 04/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.21 | 0 | 0
2535 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Phanrijangal PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01544/2023-2024 | BP-2023-24-213 | 03/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.42 | 0 | 0
2536 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PHANRIJANGAL Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000692/2023-2024 | 4017/CMD | 29/08/2023 | 30 | SOUNAK ENTERPRISE | 28.48 | 0 | 98
2537 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NABASTA, PASHALA & POALKURA Piped Water Supply Scheme under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000739/2023-2024 | 4652/BWD | 31/10/2023 | 898 | STARCO CONSTRUCTIONS | 900.17 | 0 | 2
2538 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000372/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 15.26 | 0 | 0
2539 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000555/2023-2024 | 4948/BWD | 10/11/2023 | 0 | Resource Division | 1.3 | 0 | 0
2540 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000753/2023-2024 | 5239/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0
2541 | Central Mechanical | Durgapur Sub-DIvision | Additional quotation for new service connection for POALKURA PWSS PH1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01221/2024-2025 | BP-2024-25-418 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.5 | 0 | 0
2542 | Central Mechanical | Durgapur Sub-DIvision | New Service connection at Poalkura PWSS PH-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02319/2023-2024 | BP-2023-24-455 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.32 | 0 | 0
2543 | Central Mechanical | Durgapur Sub-DIvision | New service connection for Poalkora PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02560/2023-2024 | BP-2023-24-545 | 19/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.14 | 0 | 0
2544 | Central Mechanical | Durgapur Sub-DIvision | New service connection for Poalkura PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02842/2023-2024 | BP-2023-24-590 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.85 | 0 | 0
2545 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
2546 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at POALKURA Water Supply Scheme [ Block- BHATAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000917/2023-2024 | 4181/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 27.65 | 0 | 40
2547 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
2548 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, making and erection of Sign Board for SWAJAL GRAM in Jamaipota village of Raina-I Block under Mini Piped Water Supply Scheme (100 Household) within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos. Board) | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000477/2025-2026 | 2341/BSD | 21/08/2025 | 10 | S.M. ENGOCON | 0.72 | 0 | 0
2549 | Burdwan Division | Burdwan Sadar Sub-Division | Implementation of Ground Water Based Mini Piped Water supply Scheme in 129 Nos. villages in Aushgram I & II, Burdwan I & II, Galsi I & II, Katwa I & II, Ketugream I & II, Raina I & II, Bhatar, Khandaghosh, Mongalkote and Memari II Block maximum 100 households in Purba Bardhaman district under Burdwan Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000703/2022-2023 | 641/BWD | 20/02/2023 | 1042 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4231.72 | 0 | 42
2550 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new service connection at Nabagram PWSS TW-3 | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00960/2024-2025 | BP-2024-25-381 | 14/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 19.77 | 0 | 0
2551 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new service connection at Jahannagar Augmentation PWSS TW-3 | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/01036/2024-2025 | BP-2024-25-382 | 14/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.54 | 0 | 0
2552 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 6 at Augmentation of Bhatar (Zone - II) (Bhumsor) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000933/2022-2023 | 1310/CMD | 22/03/2023 | 30 | SUDIPTA GHOSH | 12.05 | 0 | 95
2553 | Burdwan Division | Kalna Sub-division | ARJUNPUKUR Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000003/2023-2024 | 1617/BWD | 05/04/2023 | 365 | AZAD ENTERPRISE | 397.64 | 0 | 85
2554 | Burdwan Division | Kalna Sub-division | Laying of additional pipeline and providing FHTC at ARJUNPUKUR Water Supply Scheme under Kalna Sub-Division, Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000175/2024-2025 | 2252/BWD | 18/06/2024 | 90 | IYASIN DAFADAR | 16.6 | 0 | 2
2555 | Burdwan Division | Kalna Sub-division | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0
2556 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000177/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 17.1 | 0 | 0
2557 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000476/2023-2024 | 4000/BWD | 08/09/2023 | 0 | Resource Division | 1.54 | 0 | 0
2558 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000795/2023-2024 | 314/BWD | 24/01/2024 | 0 | Resource Division | 14.63 | 0 | 0
2559 | Central Mechanical | Kalna Sub-division | New service connection charges for Arjunpukur PWSS Tw-1 | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | BILL/00698/2023-2024 | BP-2023-24-50 | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0
2560 | Central Mechanical | Kalna Sub-division | New service connection charges for Arjunpukur PWSS Tw-2 | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | BILL/00699/2023-2024 | BP-2023-24-51 | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.05 | 0 | 0
2561 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at ARJUNPUKUR Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000125/2023-2024 | 2638/CMD | 14/06/2023 | 444 | ANJAN ENTERPRISE | 21.51 | 0 | 90
2562 | Central Mechanical | Kalna Sub-division | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000590/2024-2025 | 3105/CMD | 11/12/2024 | 60 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0
2563 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0
2564 | Burdwan Division | Durgapur Sub-DIvision | TELUN Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KHANDAGHOSH Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000803/2022-2023 | 1535/BWD | 29/03/2023 | 952 | G.B. CONSTRUCTION & CO. | 449.21 | 0 | 30
2565 | Burdwan Division | Durgapur Sub-DIvision | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BICHKHARA & TELUN W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001096/2024-2025 | 434/BWD | 20/01/2025 | 182 | KOUSIK MALLICK | 108.55 | 0 | 50
2566 | Burdwan Division | Durgapur Sub-DIvision | Land demarcation and preparation of sketch map including legal charges for different PWSS under JJM of Khandaghosh Block under Duragapur (Burdwan North) Sub-Division, P.H.E. DTE. [Part-A] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001510/2024-2025 | 158/DSD | 27/01/2025 | 180 | SHUBHRA KANTI GHOSH | 0.81 | 0 | 90
2567 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000061/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 7.19 | 0 | 0
2568 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000168/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.11 | 0 | 0
2569 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000735/2023-2024 | 5258/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
2570 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at TELUN W/S Scheme PH-II. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01811/2023-2024 | BP-2023-24-302 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.25 | 0 | 0
2571 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Telun PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02208/2023-2024 | BP-2023-24-392 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.9 | 0 | 0
2572 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0
2573 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Telun Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000907/2023-2024 | 4171/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 29.82 | 0 | 0
2574 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA, BALABATI, UKHRID & RUPSA Piped Water Supply Scheme under KHANDAGHOSH Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000008/2023-2024 | 1726/BWD | 13/04/2023 | 902 | S.P. CONSTRUCTION | 1710.27 | 0 | 45
2575 | Burdwan Division | Durgapur Sub-DIvision | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BALABATI, AMRA & RUPSA W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001189/2024-2025 | 609/BWD | 11/02/2025 | 120 | M/S S.S. ENTERPRISE | 194.58 | 0 | 0
2576 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000076/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.2 | 0 | 0
2577 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000167/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 9.06 | 0 | 0
2578 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000709/2023-2024 | 5048/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
2579 | Central Mechanical | Durgapur Sub-DIvision | Electric quotation for New Service Connection at Balabati W/S Scehem PH-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01773/2023-2024 | BP-2023-24-284 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.71 | 0 | 0
2580 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Balabati PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01777/2023-2024 | BP-2023-24-283 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.89 | 0 | 0
2581 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 10
2582 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Balabati Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000679/2023-2024 | 4011/CMD | 29/08/2023 | 369 | UNIVERSAL ENTERPRISES | 28.95 | 0 | 100
2583 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | Assistant Engineer | Junior Engineer | ORD/000442/2024-2025 | 306/AE/HQ | 31/05/2024 | 61 | MD HASIN | 0.8 | 0 | 0
2584 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | Assistant Engineer | Junior Engineer | ORD/000507/2024-2025 | 547/AE/HQ | 01/08/2024 | 61 | MD HASIN | 0.8 | 0 | 0
2585 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.10.2025 to 30.11.2025] | Assistant Engineer | Junior Engineer | ORD/000701/2025-2026 | 1195/AE/HQ | 24/09/2025 | 61 | MD HASIN | 0.8 | 0 | 0
2586 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.10.2024 to 30.11.2024] | Assistant Engineer | Junior Engineer | ORD/000707/2024-2025 | 802/AE/HQ | 30/09/2024 | 61 | MD HASIN | 0.8 | 0 | 0
2587 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.12.2024 to 31.01.2025] | Assistant Engineer | Junior Engineer | ORD/000897/2024-2025 | 1010/AE/HQ | 29/11/2024 | 61 | MD HASIN | 0.8 | 0 | 0
2588 | Burdwan Division | Central Mechanical Sub-Division | Different work for MERA PWSS (Mustafapur, Arangabad and Mera mouza) plinth protection for pump house & OHR under MERA PWSS, at Katwa -I Block under Katwa Sub-Division under Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000964/2024-2025 | 4374/BWD | 13/12/2024 | 90 | J.K. CORPORATION | 51.3 | 0 | 0
2589 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.02.2025 to 31.03.2025] | Assistant Engineer | Junior Engineer | ORD/001154/2024-2025 | 186/AE/HQ | 31/01/2025 | 59 | MD HASIN | 0.8 | 0 | 0
2590 | Burdwan Division | Central Mechanical Sub-Division | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | Assistant Engineer | Junior Engineer | ORD/001205/2023-2024 | 43/AE/HQ | 29/01/2024 | 60 | MD HASIN | 0.8 | 0 | 0
2591 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | Assistant Engineer | Junior Engineer | ORD/001231/2023-2024 | 236/AE/HQ | 28/03/2024 | 61 | MD HASIN | 0.8 | 0 | 0
2592 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000066/2022-2023 | 1261/BWD | 17/03/2023 | 0 | Resource Division | 7.73 | 0 | 0
2593 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000109/2022-2023 | 1642/BWD | 06/04/2023 | 0 | Resource Division | 1.83 | 0 | 0
2594 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000621/2023-2024 | 4879/BWD | 10/11/2023 | 0 | Resource Division | 31.56 | 0 | 0
2595 | Central Mechanical | Central Mechanical Sub-Division | New Service connection for Mera PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/02351/2023-2024 | BP-2023-24-462 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.98 | 0 | 0
2596 | Central Mechanical | Central Mechanical Sub-Division | New service connection for MERA PWSS TW 2. | Assistant Engineer | Junior Engineer | BILL/02446/2023-2024 | BP-2023-24-525 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.08 | 0 | 0
2597 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0
2598 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MERA Water Supply Scheme [ Block- KATWA-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000886/2023-2024 | 4149/CMD | 29/08/2023 | 30 | GOENKA ENTERPRISE | 26.98 | 0 | 91
2599 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENRIA, MAHATA, DEBPUR Piped Water Supply Scheme under BHATAR Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000019/2023-2024 | 1737/BWD | 13/04/2023 | 993 | M/S B. RAI CONSTRUCTION COMPANY | 1643.39 | 0 | 81
2600 | Burdwan Division | Durgapur Sub-DIvision | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period NOV.'2024 to JAN.'2025] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000847/2024-2025 | 886/DSD | 21/10/2024 | 78 | MD HASIN | 1 | 0 | 0
2601 | Burdwan Division | Durgapur Sub-DIvision | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day. [PeriodFebruary.'2025 to April'2025] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001180/2024-2025 | 129/DSD | 29/01/2025 | 78 | MD HASIN | 1 | 0 | 0
2602 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000067/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 31.52 | 0 | 0
2603 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000171/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 8.61 | 0 | 0
2604 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000586/2023-2024 | 4930/BWD | 10/11/2023 | 0 | Resource Division | 34.57 | 0 | 0
2605 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000782/2023-2024 | 325/BWD | 24/01/2024 | 0 | Resource Division | 6.44 | 0 | 0
2606 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Dhenria PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01418/2023-2024 | BP-2023-24-147 | 31/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0
2607 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Dhenria PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01473/2023-2024 | BP-2023-24-167 | 27/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.71 | 0 | 0
2608 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
2609 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DHENRIA Water Supply Scheme [ Block-BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000559/2023-2024 | 3872/CMD | 17/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 27.79 | 0 | 90
2610 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NAMA BHANDARITURI, SAHAPUR & MOUDANGA Piped Water Supply Scheme under PURBASTHALI-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000511/2023-2024 | 3689/BWD | 23/08/2023 | 770 | THE MAHADEV CONSTRUCTION | 734.18 | 0 | 50
2611 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000279/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.45 | 0 | 0
2612 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000510/2023-2024 | 4034/BWD | 08/09/2023 | 0 | Resource Division | 3.06 | 0 | 0
2613 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000808/2023-2024 | 299/BWD | 24/01/2024 | 0 | Resource Division | 14.63 | 0 | 0
2614 | Central Mechanical | Kalna Sub-division | Additional Quotation for new service connection for Sahapur PWSS, PH-1. | Assistant Engineer | JUNIOR ENGINEER | BILL/00311/2024-2025 | BP-2024-25-152 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.86 | 0 | 0
2615 | Central Mechanical | Kalna Sub-division | New service connection charges for Sahapur PWSS TW-2 | Assistant Engineer | JUNIOR ENGINEER | BILL/01831/2023-2024 | BP-2023-24-337 | 06/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.21 | 0 | 0
2616 | Central Mechanical | Kalna Sub-division | New service connection for Sahapur PWSS. | Assistant Engineer | JUNIOR ENGINEER | BILL/02249/2023-2024 | BP-2023-24-389 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.86 | 0 | 0
2617 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at SAHAPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000036/2023-2024 | 2473/CMD | 30/05/2023 | 30 | MAA KALI ENTERPRISE | 20.8 | 0 | 90
2618 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 30
2619 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHARKHI & SHIBNUL Piped Water Supply Scheme under KETUGRAM-II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000049/2023-2024 | 1823/BWD | 18/04/2023 | 1293 | PASCON | 723.75 | 0 | 35
2620 | Burdwan Division | Central Mechanical Sub-Division | Balance work for OHR, extension of pipeline to provide FHTC with land development, plinth protection for pump house & OHR under SIBLUN PWSS, Block-Ketugram-II under Katwa Sub Division within Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000311/2024-2025 | 2835/BWD | 19/07/2024 | 835 | PASCON | 84.02 | 0 | 80
2621 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000065/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.1 | 0 | 0
2622 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000163/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 75.98 | 0 | 0
2623 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000487/2023-2024 | 4011/BWD | 08/09/2023 | 0 | Resource Division | 1.1 | 0 | 0
2624 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000759/2023-2024 | 5246/BWD | 30/11/2023 | 0 | Resource Division | 18.9 | 0 | 0
2625 | Central Mechanical | Central Mechanical Sub-Division | REVISED QUOTATION FOR NEW SERVICE CONNECTION AT SHIBLUN PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/00369/2024-2025 | BP-2024-25-190 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.19 | 0 | 0
2626 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Shiblun PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01355/2023-2024 | BP-2023-24-133 | 22/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.04 | 0 | 0
2627 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Shiblun PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01898/2023-2024 | BP-2023-24-368 | 15/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.19 | 0 | 0
2628 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0
2629 | Burdwan Division | Burdwan Sadar Sub-Division | GOPALPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Jamalpur Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000121/2023-2024 | 2305/BWD | 19/05/2023 | 757 | IJABUL SEKH | 266.75 | 0 | 100
2630 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for GOPALPUR W/S Scheme under Burdwan-I Block under Burdwan Sub- Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000846/2024-2025 | 2584/BSD | 26/11/2024 | 45 | APEX ENGINEERING | 2.71 | 0 | 0
2631 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | RTOR000268/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.02 | 0 | 0
2632 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Gopalpur PWSS TW-1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | BILL/02282/2023-2024 | BP-2023-24-433 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4 | 0 | 0
2633 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection at GOPALPUR PWSS TW-2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | BILL/02363/2023-2024 | BP-2023-24-483 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.65 | 0 | 0
2634 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at GOPALPUR Water Supply Scheme [Block-JAMALPUR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000904/2023-2024 | 4168/CMD | 29/08/2023 | 546 | SOUNAK ENTERPRISE | 22.1 | 0 | 100
2635 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of TEHATA Zone-I & II (SM/16301) Water Supply Scheme, CHAKSIMLA (SM/15586) Water Supply Scheme & DWARIATON (SM/16285) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000162/2024-2025 | 2201/BWD | 13/06/2024 | 752 | M/S ASHA CONSTRUCTION | 449.98 | 0 | 25
2636 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALINDAR, CHAK SHIMLA & DWARIATAN Piped Water Supply Scheme under Kalna II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000539/2023-2024 | 3700/BWD | 24/08/2023 | 770 | SUPRITI ENTERPRISE | 1424.22 | 0 | 30
2637 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR CHAKSIMLA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001151/2023-2024 | 2020/KSD | 06/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0 | 2
2638 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000072/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 8.53 | 0 | 0
2639 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000287/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.27 | 0 | 0
2640 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000793/2023-2024 | 318/BWD | 24/01/2024 | 0 | Resource Division | 30.81 | 0 | 0
2641 | Central Mechanical | Kalna Sub-division | New service connection at Chak Shimla PWSS Ph-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/02323/2023-2024 | BP-2023-24-449 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.74 | 0 | 0
2642 | Central Mechanical | Kalna Sub-division | New service connection at Chak Shimla PWSS Ph-2 | Assistant Engineer | JUNIOR ENGINEER | BILL/02324/2023-2024 | BP-2023-24-450 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.35 | 0 | 0
2643 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 20
2644 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAK SIMLA Water Supply Scheme [ Block-KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | Assistant Engineer | JUNIOR ENGINEER | ORD/000931/2023-2024 | 4194/CMD | 29/08/2023 | 735 | J.S. CONSTRUCTION. | 28.48 | 0 | 40
2645 | Burdwan Division | Burdwan Sadar Sub-Division | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at Head Work Site & 2nd TW Site and providing leftout FHTC, Road Restoration with allied work for MUGRA Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000279/2024-2025 | 2711/BWD | 11/07/2024 | 2720 | M/S PURBASHA | 40.24 | 0 | 90
2646 | Burdwan Division | Burdwan Sadar Sub-Division | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MUGURA Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000792/2022-2023 | 1429/BWD | 24/03/2023 | 30 | J K CORPORATION | 18.57 | 0 | 100
2647 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Retrofitting of Mugura PWSS under Raina-I Development Block under Burdwan Division, P.H.E Dte(2nd Call) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000913/2023-2024 | 2831/BSD | 07/12/2023 | 15 | MEASURE LAND | 0.78 | 0 | 100
2648 | Burdwan Division | Central Mechanical Sub-Division | JAJIGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000742/2022-2023 | 1135/BWD | 13/03/2023 | 749 | POWER TOOLS & ENGINEERING | 368.83 | 0 | 75
2649 | Burdwan Division | Central Mechanical Sub-Division | Construction of Office Cum Godown at Head work site of JAJIGRAM PWSS under Katwa Sub Division, within Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000854/2023-2024 | 5201/BWD | 29/11/2023 | 180 | SUBODH KUMAR MONDAL | 37.69 | 0 | 10
2650 | Burdwan Division | Central Mechanical Sub-Division | Balance work for the construction of office cum Go-Down at ground floor at the head work site of JAJIGRAM PWSS under Katwa I Block under Katwa Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001025/2024-2025 | 106/BWD | 07/01/2025 | 60 | SUBODH KUMAR MONDAL | 9.11 | 0 | 0
2651 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000149/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.59 | 0 | 0
2652 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000492/2023-2024 | 4016/BWD | 08/09/2023 | 0 | Resource Division | 0.97 | 0 | 0
2653 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000631/2023-2024 | 4883/BWD | 10/11/2023 | 0 | Resource Division | 28.85 | 0 | 0
2654 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Jajigram PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01476/2023-2024 | BP-2023-24-174 | 29/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.42 | 0 | 0
2655 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Jajigram PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01539/2023-2024 | BP-2023-24-206 | 30/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.31 | 0 | 0
2656 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0
2657 | Central Mechanical | Central Mechanical Sub-Division | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000602/2024-2025 | 3106/CMD | 11/12/2024 | 60 | S.K. ELECTRICALS | 13.6 | 0 | 0
2658 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JAJIGRAM Water Supply Scheme [ Block- KATWA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000853/2023-2024 | 4123/CMD | 29/08/2023 | 415 | M/S, N.G. ENTERPRISES. | 26.94 | 0 | 100
2659 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of Interconnection of 3rd Tube well Site of Chotobainan Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000090/2023-2024 | 737/BSD | 20/04/2023 | 15 | BRINDABAN KONAR | 0.93 | 0 | 100
2660 | Burdwan Division | Burdwan Sadar Sub-Division | Improvement/ Strenthenning of RCC Elevated Reservoir (Capacity 700 Cum) & pipe line of CHOTOBAINAN PWSS for smooth running of FHTC work under RAINA-II Block, District:- Purba- Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000295/2024-2025 | 1277/BSD | 12/07/2024 | 60 | ANWESHA CONSTRUCTION | 3.34 | 0 | 100
2661 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of CHHOTOBAINAN (NILEDIGHIR PAR) W/S Scheme under Raina-II Block within Burdwan Sub-Division, PHE Dte. [For 01 No. Tube well]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000595/2023-2024 | 3768/BWD | 29/08/2023 | 30 | B.S. ENTERPRISE | 13.13 | 0 | 100
2662 | Burdwan Division | Burdwan Sadar Sub-Division | Pipeline with FHTC for CHOTOBAINAN Water Supply Scheme at Gopalpur village (400 Nos), Akhina village (250 Nos) within Raina-II Block, under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000795/2022-2023 | 1498/BWD | 28/03/2023 | 614 | BRINDABAN KONAR | 59.24 | 0 | 100
2663 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Switch room cum chlorine room with sanitary and water supply arrangement (P.H-4) at New Tube Well Site of CHOTOBAINAN and its adjoining Mouzas Pipe Water Supply Scheme of cracky nature of soil according to departmental drawing no.-PHE/BD/P.H/DRG-01/DCE-2017, Block:- Raina-II, under Burdwan Sub-Division, P.H.E Dte. within Burdwan Division P.H.E. Dte. Dist:Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000972/2023-2024 | 001/BWD | 02/01/2024 | 60 | CHOWDHURY CONSTRUCTION | 5.83 | 0 | 99
2664 | Burdwan Division | Burdwan Sadar Sub-Division | Balance Work for extension of pipe lines to provide FHTC With Sinking of Tubwell (Replacement TW), Repairing of pump house with Boundary wall at head worksite & other related works for CHOTOBAINAN PWSS under Burdwan Sub-Div., Block -Raina-II, under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001099/2024-2025 | 435/BWD | 20/01/2025 | 120 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 106.18 | 0 | 0
2665 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Chhotobainan PWSS under Raina-II Development Block under Burdwan Division, P.H.E Dte (2nd Call) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001226/2023-2024 | 2974/BSD | 20/12/2023 | 15 | MEASURE LAND | 0.78 | 0 | 100
2666 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Augmentation of Chotoboinan PWSS TW-4. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/02281/2023-2024 | BP-2023-24-435 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.66 | 0 | 0
2667 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Chotoboinan Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000083/2023-2024 | 2590/CMD | 07/06/2023 | 30 | CHOUDHURY ENTERPRISE | 22.51 | 0 | 48
2668 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Augmentation of Chhotoboinan Water Supply Scheme [ Block- Raina-II ] ( Tube Well no 4 ) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000618/2022-2023 | 3142/CMD | 29/11/2022 | 30 | CHATTERJEE ENTERPRISE | 10.99 | 0 | 0
2669 | Central Mechanical | Burdwan Sadar Sub-Division | Providing Electrical accessories for Tube well No. 2 of Chotobainan & others Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000991/2023-2024 | 4347/CMD | 19/09/2023 | 30 | DUTTA ENTERPRISE | 3.09 | 0 | 100
2670 | Central Mechanical | Burdwan Sadar Sub-Division | Procurement of electro-mechanical accessories for Chotoboinan Water Supply Scheme under JJM under CMD, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001017/2023-2024 | 529/CMSD | 07/07/2023 | 30 | JOYGURU ENTERPRISE | 0.84 | 0 | 99
2671 | Burdwan Division | Central Mechanical Sub-Division | Construction of Pump House, Boundary walls and Raising Main for Aug. of PANUHAT Piped W/S. Scheme under Katwa-I Block, District:- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000923/2023-2024 | 5484/BWD | 13/12/2023 | 60 | SUBODH KUMAR MONDAL | 9.73 | 0 | 26
2672 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR ADDITIONAL TUBE WELL AT PANUHAT | Assistant Engineer | Junior Engineer | BILL/00128/2024-2025 | BP-2024-25-62 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.52 | 0 | 0
2673 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Augmentation of Panuhat PWSS TW - 01. | Assistant Engineer | Junior Engineer | BILL/00749/2024-2025 | BP-2024-25-283 | 10/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.98 | 0 | 0
2674 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Panuhat Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000084/2023-2024 | 2581/CMD | 07/06/2023 | 760 | DUTTA ENTERPRISE | 11.02 | 0 | 0
2675 | Central Mechanical | Central Mechanical Sub-Division | Yard lighting arrangement & allied works at Panuhat water supply scheme under Katwa-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000464/2024-2025 | 2791/CMD | 01/10/2024 | 60 | BEHERA ENTERPRISE | 7.11 | 0 | 0
2676 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMEGERIA, ARGUN, CHINISPUR & KULUTIA Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000533/2023-2024 | 3630/BWD | 21/08/2023 | 1107 | M/S GOUTAM DAS | 1421.7 | 0 | 75
2677 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000390/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.23 | 0 | 0
2678 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000407/2023-2024 | 3825/BWD | 01/09/2023 | 0 | Resource Division | 2.16 | 0 | 0
2679 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000740/2023-2024 | 5240/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0
2680 | Central Mechanical | Central Mechanical Sub-Division | New Service connection at Kulutia PWSS TW NO. 1 | Assistant Engineer | Junior Engineer | BILL/02370/2023-2024 | BP-2023-24-491 | 01/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.01 | 0 | 0
2681 | Central Mechanical | Central Mechanical Sub-Division | New service connection for Kulitia PWSS PH-2. | Assistant Engineer | Junior Engineer | BILL/02910/2023-2024 | BP-2023-24-623 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.19 | 0 | 0
2682 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
2683 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KULUTIA Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000856/2023-2024 | 4124/CMD | 29/08/2023 | 610 | KAMAKHYA ENTERPRISE | 26.93 | 0 | 46
2684 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Kulutia W/S Scheme (T/W-I & II) ,Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000165/2023-2024 | 1349/CDD | 13/09/2023 | 30 | UNIVERSAL ENTERPRISES | 16.66 | 0 | 0
2685 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of CIDF/DI Pipes with specials within command area of Balarampur piped W/S Scheme at Shalim Danga Sabgi Bazar,,Jamalpur Development Block under Burdwan Division,PHE Dte. [2nd Call]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000140/2023-2024 | 789/BSD | 28/04/2023 | 15 | GHOSH ENTERPRISE | 0.32 | 0 | 100
2686 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of BALARAMPUR W/S Scheme under Jamalpur Block within Burdwan Sub-Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000202/2023-2024 | 2705/BWD | 08/06/2023 | 30 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.26 | 0 | 100
2687 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Balarampur PWSS under Jamalpur Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000393/2023-2024 | 1528/BSD | 17/07/2023 | 15 | GEO-SOLUTION | 0.78 | 0 | 100
2688 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch rooms & Rising main at different TW site for BALARAMPUR Piped Water Supply Scheme under Jamalpur Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000594/2023-2024 | 3769/BWD | 29/08/2023 | 60 | SOUMYAVASH DAS | 8.94 | 0 | 100
2689 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall at 4Th Tubewell of BALARAMPUR PWSS at Jamalpur Block under Burdwan Division, PHE Dte. (Length -110 Mtr, Col-42 Nos). | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000932/2024-2025 | 4300/BWD | 10/12/2024 | 30 | MOFIZ UDDIN MOLLICK | 9.09 | 0 | 100
2690 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of (i) Pump House cum chlorine room without sanitary and water supply arrangement at 5th Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/ DEC-17 (Size 3.60 mtr x 3.00 mtr room), (CD) and UPVC Deep Well Screen (RDS), (ii) Interconnection between pump house & delivery line for BALARAMPUR W/S Scheme under Jamalpur Block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/001054/2023-2024 | 832/BWD | 29/02/2024 | 30 | SK KHAIRUL ISLAM | 4.79 | 0 | 100
2691 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 40
2692 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Balarampur PWSS TW-4 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | BILL/02213/2023-2024 | BP-2023-24-386 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.6 | 0 | 0
2693 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection at BALARAMPUR PWSS TW-5. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | BILL/02364/2023-2024 | BP-2023-24-482 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 16.19 | 0 | 0
2694 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Balarampur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000082/2023-2024 | 2589/CMD | 07/06/2023 | 697 | P.K. ENGINEERING | 22.61 | 0 | 90
2695 | Central Mechanical | Burdwan Sadar Sub-Division | Illumination arrangement and miscellaneous works at Balarampur water supply scheme under Jamalpur Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000444/2024-2025 | 2786/CMD | 01/10/2024 | 60 | A.K. ENTERPRISE | 15.91 | 0 | 30
2696 | Central Mechanical | Burdwan Sadar Sub-Division | Procurement of electro-mechanical accessories for Balarampur Water Supply Scheme under JJM under CMD, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/001020/2023-2024 | 531/CMSD | 07/07/2023 | 30 | M/S. S.D. CONSTRUCTION | 0.58 | 0 | 100
2697 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Drain at Head Work site for SHYAMSUNDAR PIPED WATER SUPPLY SCHEME , Block- Raina-I , within Burdwan Sub Division under Burdwan Division PHE Dte | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000148/2024-2025 | 1041/BSD | 10/06/2024 | 30 | LAKSHMIKANTA DAS | 0.93 | 0 | 100
2698 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pathway at Head Work site for SHYAMSUNDAR PIPED WATER SUPPLY SCHEME , Block- Raina-I , within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000154/2024-2025 | 1040/BSD | 10/06/2024 | 30 | POMPA CONSTRUCTION CO. | 0.93 | 0 | 0
2699 | Burdwan Division | Burdwan Sadar Sub-Division | Laying Parallel Pipeline, providing FHTC and Repairing of Pump House at 2nd Tube Well Site for Aug. of SHYAMSUNDAR Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000224/2024-2025 | 2524/BWD | 03/07/2024 | 90 | DEBASHISH ENTERPRISE | 22.66 | 0 | 0
2700 | Burdwan Division | Burdwan Sadar Sub-Division | Allied works for Augmentation of SHYAMSUNDAR W/S Scheme under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000346/2023-2024 | 3035/BWD | 14/07/2023 | 90 | SK ALIM | 113.11 | 0 | 100
2701 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
2702 | Burdwan Division | Burdwan Sadar Sub-Division | Restore of pipeline damaged by construction of Pathashree Road near Muktipur Village for SHYAMSUNDAR PIPED WATER SUPPLY SCHEME , Block- Raina-I , within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000518/2024-2025 | 1865/BSD | 22/08/2024 | 30 | MAA MAHAMAYA CONSTRUCTION | 0.97 | 0 | 100
2703 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of SHYAMSUNDAR Piped Water Supply Scheme with LDS, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test, Construction of boundary wall at Head works & 2nd TW site & FHTC under Raina ¿ I Block, District - Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000598/2021-2022 | 1474/BWD | 14/03/2022 | 365 | SK ALIM | 474.78 | 0 | 100
2704 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, making and erection of Sign Board for SWAJAL GRAM in Muktipur village of Raina-I Block under Shyamsundar Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000617/2025-2026 | 2369/BSD | 21/08/2025 | 10 | S.M. ENGOCON | 0.72 | 0 | 0
2705 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for SHYAMSUNDAR its Adjoining Mouza W/S Scheme, Block -Raina-I within Burdwan Sub-Division, PHE Dte. (Mouza- Gopinathpur) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000770/2022-2023 | 505/BSD | 21/03/2023 | 45 | JYOTI ENTERPRISE | 3.5 | 0 | 100
2706 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Aug. of Shyamsundar PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/00855/2023-2024 | BP-2023-24-104 | 07/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.18 | 0 | 0
2707 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Aug. Shyamsundar PWSS TW-4 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/01425/2023-2024 | BP-2023-24-150 | 05/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.25 | 0 | 0
2708 | Central Mechanical | Burdwan Sadar Sub-Division | Making illumination arrangement and mise works at SHYAMSUNDAR water supply scheme RAINA-I BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000474/2024-2025 | 2954/CMD | 20/11/2024 | 60 | CHATTERJEE ENTERPRISE | 14.87 | 0 | 30
2709 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of SHYAMSUNDAR(Part-B)[RAINA-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000569/2023-2024 | 3901/CMD | 18/08/2023 | 286 | SOUNAK ENTERPRISE | 24.41 | 0 | 90
2710 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC for 100% coverage at RUPPUR & Dhuluk Habitation (Village) for RUPPUR Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000125/2023-2024 | 2315/BWD | 19/05/2023 | 60 | MAJILA ENTERPRISE | 62.34 | 0 | 100
2711 | Burdwan Division | Burdwan Sadar Sub-Division | Relaying and replace of damaged HDPE pipeline with repairing of valve for control of water flow within command area of RUPPUR Piped W/S Scheme at Ruppur Habitation,Jamalpur Development Block under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000155/2024-2025 | 1044/BSD | 10/06/2024 | 30 | SANDIPAN SENGUPTA | 0.65 | 0 | 100
2712 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Ruppur PWSS under Jamalpur Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000351/2023-2024 | 1478/BSD | 12/07/2023 | 15 | CARTO | 0.78 | 0 | 100
2713 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 mm X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) with construction of Pump House, Boundary wall, Land Development and Rising main connection of RUPPUR Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. [FOR 3rd. TUBE WELL SITE] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000996/2024-2025 | 4593/BWD | 31/12/2024 | 120 | HI-LIGHT ELECTRONICS | 26.2 | 0 | 30
2714 | Central Mechanical | Burdwan Sadar Sub-Division | Illumination arrangement and miscellaneous works at Ruppur water supply scheme under Jamalpur Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/000473/2024-2025 | 2947/CMD | 20/11/2024 | 60 | M/S. SWAPAN BANERJEE | 19.64 | 0 | 30
2715 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 3 at Augumentation of RUPPUR Water Supply Scheme [BLOCK- JAMALPUR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,RWS_JAMALPUR | ORD/001609/2023-2024 | 1540/CMD | 05/03/2024 | 60 | KAMAKHYA ENTERPRISE | 12.33 | 0 | 0
2716 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOPALPUR & RASUIKHANDA Piped Water Supply Scheme under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000006/2023-2024 | 1691/BWD | 12/04/2023 | 719 | SK ALIM | 1081.52 | 0 | 92
2717 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 183 | SK.ASFIA | 2.4 | 0 | 70
2718 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 366 | SK ALIM | 1353.91 | 0 | 25
2719 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000184/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 7.15 | 0 | 0
2720 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000484/2023-2024 | 4008/BWD | 08/09/2023 | 0 | Resource Division | 2.23 | 0 | 0
2721 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000688/2023-2024 | 5065/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
2722 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Rasuikhanda PWSS TW 1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01371/2023-2024 | BP-2023-24-139 | 25/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.04 | 0 | 0
2723 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Rasuikhanda PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01426/2023-2024 | BP-2023-24-153 | 05/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.7 | 0 | 0
2724 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
2725 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Rasuikhanda Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000184/2023-2024 | 2968/CMD | 17/07/2023 | 351 | ORIENTAL ENGINEERING CO. | 28.96 | 0 | 90
2726 | Burdwan Division | Katwa Sub-Division | Augmentation of KSHETPUR PALASHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & Renovation of switch-rooms & boundary walls at different TW site under Katwa-II Block, District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/000117/2023-2024 | 2303/BWD | 19/05/2023 | 448 | SHUBHRA KANTI GHOSH | 121.71 | 0 | 95
2727 | Central Mechanical | Katwa Sub-Division | New service connection charges for Kshetpur Palashi PWSS TW-1 | Assistant Engineer |  | BILL/01764/2023-2024 | BP-2023-24-280 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4 | 0 | 0
2728 | Central Mechanical | Katwa Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Kshetpur Plasi Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer |  | ORD/000094/2023-2024 | 2585/CMD | 07/06/2023 | 820 | SOUNAK ENTERPRISE | 22.6 | 0 | 48
2729 | Burdwan Division | Central Mechanical Sub-Division | SIPTA Single Village Scheme with sinking of LDS, Rising Main and FHTC under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000100/2023-2024 | 2258/BWD | 18/05/2023 | 90 | ROY CONSTRUCTION | 115.09 | 0 | 100
2730 | Burdwan Division | Central Mechanical Sub-Division | Providing 20 Nos.FHTC at SIPTA village for declearation of SWAJALGRAM under SIPTA Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000514/2024-2025 | 1861/BSD | 22/08/2024 | 30 | ROY CONSTRUCTION | 0.96 | 0 | 0
2731 | Burdwan Division | Central Mechanical Sub-Division | SIPTA Single Village Scheme with sinking of Tube-well & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000794/2022-2023 | 1444/BWD | 24/03/2023 | 90 | S.B. ASSOCIATES | 49.61 | 0 | 100
2732 | Burdwan Division | Central Mechanical Sub-Division | Construction of approach road near 2nd. Tube well site of SIPTA Water Supply Scheme [New Scheme], Raina-I, under Burdwan Sub Division PHE Dte. under Burdwan Division PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001046/2024-2025 | 211/BWD | 09/01/2025 | 30 | SAIKAT RAY | 7.2 | 0 | 0
2733 | Burdwan Division | Central Mechanical Sub-Division | Restore of village Road dismalted by laying pipe line at for providing FHTC at Kukre village under SIPTA PIPED WATER SUPPLY SCHEME [new scheme],Block-Raina-I,within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001174/2024-2025 | 261/BSD | 05/02/2025 | 15 | ROY CONSTRUCTION | 0.96 | 0 | 100
2734 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000155/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 8.72 | 0 | 0
2735 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000694/2023-2024 | 5058/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
2736 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Sipta PWSS TW-1 | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00795/2023-2024 | BP-2023-24-88 | 26/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.76 | 0 | 0
2737 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Sipta PWSS TW-2 | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00796/2023-2024 | BP-2023-24-89 | 26/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.07 | 0 | 0
2738 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
2739 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sipta Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000147/2023-2024 | 2880/CMD | 07/07/2023 | 30 | S.G. ENTERPRISE | 28.95 | 0 | 95
2740 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ONARI & SASANGA Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL |  |  | ORD/000452/2023-2024 | 3430/BWD | 07/08/2023 | 786 | M/S JAN MAHAMMAD | 1398.82 | 0 | 50
2741 | Burdwan Division |  | Supply of flow control devices and CIDF Pipes for ONARI PWSS (SM/18246) under Burdwan Division, PHE Dte._2ND CALL |  |  | ORD/001024/2024-2025 | 81/AE/HQ | 07/01/2025 | 127 | MAKALI ENGINEERING CORPORATION | 9.95 | 0 | 100
2742 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000359/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 14.41 | 0 | 0
2743 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000403/2023-2024 | 3829/BWD | 01/09/2023 | 0 | Resource Division | 24.57 | 0 | 0
2744 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000685/2023-2024 | 5075/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
2745 | Central Mechanical |  | New service connection for Onari PWSS TW-1. |  |  | BILL/02892/2023-2024 | BP-2023-24-619 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.68 | 0 | 0
2746 | Central Mechanical |  | New Service connection for Onari PWSS TW-2. |  |  | BILL/02897/2023-2024 | BP-2023-24-620 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.68 | 0 | 0
2747 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0
2748 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Onari Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000680/2023-2024 | 4012/CMD | 29/08/2023 | 30 | M/S. S.R. ENTERPRISE | 28.09 | 0 | 95
2749 | Burdwan Division | Kalna Sub-division | Restoration work of Singerkone to Pandua Kulti road via badla from 0.00 km to 2.90 km, (in stretches) damaged due to laying of underground water pipe line by PHE with box cutting and Jhama with moorum consolidation under-Kalna Highvway Sub Division of Burdwan South Highway Division, P.W(Roads)Dte. during the year 2023-24. | Assistant Engineer |  | BILL/00648/2024-2025 | 825/JJM | 13/09/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 5.36 | 0 | 0
2750 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of KULTI (SM/16301) Water Supply Scheme, Block Kalna II under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000235/2024-2025 | 2553/BWD | 04/07/2024 | 240 | HAMID SK | 222.11 | 0 | 80
2751 | Burdwan Division | Kalna Sub-division | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of Kulti piped water supply scheme at Chagram village (Chagram habitation), Dakshin Krishnapur village (Krishnapur habitation), Kala village (Anandanagar, Baganpara, Kala & Saklompur habitation), Kulti village (Dhapaspara & Kulti habitation), Dampara village (Dampara habitation) & Kashipur village (Kashipur habitation), Kalna-II Block under Burdwan Division, PHE Dte.[Tr No.-108/SE/CC/20-21] | Assistant Engineer |  | ORD/000405/2020-2021 | 1130/BWD | 09/02/2021 | 60 | UMWELT ENGINEER PVT LTD | 103.15 | 31.07 | 1
2752 | Burdwan Division | Kalna Sub-division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Kalna ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000476/2021-2022 | 943/BWD | 17/02/2022 | 30 | UDYOG CONSTRUCTION | 5.27 | 0 | 100
2753 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR MOHANPUR Piped Water Supply Scheme with Inter-connection, LDS, FHTC ,Road restoration & construction of switch rooms & boundary walls with gates, land development with road at TW site under Galsi-II Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000220/2024-2025 | 41/DWSD | 08/01/2025 | 334 | MD.HASIN | 148.94 | 0 | 70
2754 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000002/2024-2025 | 1724/N/DWSD | 10/12/2024 | 0 | Resource Division | 11.33 | 0 | 0
2755 | Burdwan Division | Durgapur Sub-DIvision | Shifting of 11KV Line of Mohanpur PWSS under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01080/2023-2024 | 1055/JJM | 13/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.33 | 0 | 0
2756 | Burdwan Division | Durgapur Sub-DIvision | MOHANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000386/2023-2024 | 3149/BWD | 20/07/2023 | 774 | MD HASIN | 963.53 | 0 | 80
2757 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000343/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 2.41 | 0 | 0
2758 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000446/2023-2024 | 3844/BWD | 01/09/2023 | 0 | Resource Division | 251.04 | 0 | 0
2759 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000563/2023-2024 | 4937/BWD | 10/11/2023 | 0 | Resource Division | 54.72 | 0 | 0
2760 | Central Mechanical | Durgapur Sub-DIvision | New service connection for Mohanpur PWSS . | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02408/2023-2024 | BP-2023-24-506 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.86 | 0 | 0
2761 | Central Mechanical | Durgapur Sub-DIvision | New service connection for Mohanpur PWSS . | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02410/2023-2024 | BP-2023-24-507 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.83 | 0 | 0
2762 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
2763 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-4 at MOHANPUR Water Supply Scheme [ BLOCK- GALSI-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001388/2024-2025 | 881/CMD | 26/03/2025 | 60 | CHOUDHURY ENTERPRISE | 12.88 | 0 | 0
2764 | Burdwan Division |  | BANDMURA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000830/2023-2024 | 5007/BWD | 22/11/2023 | 1136 | MANASH GHOSH | 883.19 | 0 | 35
2765 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000549/2023-2024 | 4312/BWD | 29/09/2023 | 0 | Resource Division | 73.01 | 0 | 0
2766 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000767/2023-2024 | 208/BWD | 10/01/2024 | 0 | Resource Division | 21.5 | 0 | 0
2767 | Central Mechanical |  | Quotation for new service connection for Bandmura PWSS TW-2. |  |  | BILL/00776/2024-2025 | BP-2024-25-292 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.03 | 0 | 0
2768 | Central Mechanical |  | NEW SERVICE CONNECTION FOR BANDMURA PWSS TW 1. |  |  | BILL/02490/2023-2024 | BP-2023-24-536 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.36 | 0 | 0
2769 | Central Mechanical |  | New service connection for Bandhmura PWSS PH-3. |  |  | BILL/02906/2023-2024 | BP-2023-24-615 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.32 | 0 | 0
2770 | Central Mechanical |  | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte , w.e.f : 01/05/2025 to 30/06/2025. |  |  | ORD/000009/2025-2026 | 248/DIC/BMSD(D) | 23/04/2025 | 61 | SUBRATA BHADRA | 0.81 | 0 | 0
2771 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0
2772 | Central Mechanical |  | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte , w.e.f : 01/07/2025 to 30/08/2025. |  |  | ORD/000077/2025-2026 | 476/DIC/BMSD(D) | 26/06/2025 | 61 | SUBRATA BHADRA | 0.81 | 0 | 0
2773 | Central Mechanical |  | continuation order for Hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte ,wef : 01/ 11/ 20 24 to 31/12/2024. |  |  | ORD/000526/2024-2025 | 739/DIC/BMSD(D) | 25/10/2024 | 61 | SUBRATA BHADRA | 0.81 | 0 | 0
2774 | Central Mechanical |  | Hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte , w.e.f : 01/ 01/ 2025 to 28/02/2025 |  |  | ORD/000657/2024-2025 | 922/DIC/BMSD(D) | 26/12/2024 | 59 | SUBRATA BHADRA | 0.8 | 0 | 0
2775 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at BANDMURA Water Supply Scheme [ Block- KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000869/2023-2024 | 4132/CMD | 29/08/2023 | 590 | GLACIER ENGINEERING CO | 44.42 | 0 | 31
2776 | Central Mechanical |  | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte , w.e.f : 01/03/2025 to 30/04/2025. |  |  | ORD/000917/2024-2025 | 134/DIC/BMSD(D) | 24/02/2025 | 61 | SUBRATA BHADRA | 0.81 | 0 | 0
2777 | Burdwan Division |  | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. |  |  | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 366 | SK ALIM | 1353.91 | 0 | 25
2778 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 4115/BWD | 25/11/2024 | 0 | Resource Division | 21.15 | 0 | 0
2779 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000247/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 1.8 | 0 | 0
2780 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000423/2023-2024 | 3860/BWD | 01/09/2023 | 0 | Resource Division | 3.41 | 0 | 0
2781 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000654/2023-2024 | 5100/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
2782 | Central Mechanical |  | New electric connection for Belswar PWSS, PH-1. |  |  | BILL/01872/2023-2024 | BP-2023-24-360 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.01 | 0 | 0
2783 | Central Mechanical |  | NEW SERVICE CONNECTION FOR BELSHAR PWSS TW 2. |  |  | BILL/03182/2023-2024 | BP-2023-24-666 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.39 | 0 | 0
2784 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
2785 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Belshar Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000719/2023-2024 | 4030/CMD | 29/08/2023 | 474 | SINHA ELECTRICALS | 28.97 | 0 | 96
2786 | Burdwan Division |  | NALA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000425/2023-2024 | 3327/BWD | 02/08/2023 | 669 | MD HASIN | 752.05 | 0 | 75
2787 | Burdwan Division |  | Balance work i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, Solar System with structure, inter Connection of Additional Tube Well, & allied work for NALA Piped Water Supply Scheme under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. |  |  | ORD/001266/2024-2025 | 847/BWD | 05/03/2025 | 120 | DIAMOND ENGINEERS CO-OP SOCIETY LTD. | 184.95 | 0 | 0
2788 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000396/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.83 | 0 | 0
2789 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000412/2023-2024 | 3868/BWD | 01/09/2023 | 0 | Resource Division | 3.83 | 0 | 0
2790 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000679/2023-2024 | 5054/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
2791 | Central Mechanical |  | New service connection at NALA PWSS Ph-1 |  |  | BILL/02327/2023-2024 | BP-2023-24-444 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.2 | 0 | 0
2792 | Central Mechanical |  | New service connection at NALA PWSS Ph-2 |  |  | BILL/02328/2023-2024 | BP-2023-24-445 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0
2793 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
2794 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nala Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000659/2023-2024 | 4002/CMD | 29/08/2023 | 528 | P.K. ENGINEERING | 28.89 | 0 | 95
2795 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SIMULIA & LAKSHIMPUR Piped Water Supply Scheme under Mongalkote Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000694/2023-2024 | 4363/BWD | 04/10/2023 | 727 | PUSPA ENTERPRISE | 1090.95 | 0 | 37
2796 | Burdwan Division |  | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/001301/2024-2025 | 936/BWD | 11/03/2025 | 180 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0
2797 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000527/2023-2024 | 4302/BWD | 29/09/2023 | 0 | Resource Division | 10.51 | 0 | 0
2798 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000569/2023-2024 | 4941/BWD | 10/11/2023 | 0 | Resource Division | 27.49 | 0 | 0
2799 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000773/2023-2024 | 206/BWD | 10/01/2024 | 0 | Resource Division | 17.75 | 0 | 0
2800 | Central Mechanical |  | NEW SERVICE CONNECTION FOR LAKSHIMPUR PWSS TW-1 |  |  | BILL/00188/2024-2025 | BP-2024-25-89 | 15/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.14 | 0 | 0
2801 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
2802 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at LAKSHIMPUR Water Supply Scheme [ Block- MONGALKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000801/2023-2024 | 4087/CMD | 29/08/2023 | 640 | ORIENTAL ENGINEERING CO. | 44.4 | 0 | 31
2803 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MEJHIARY & KARUI Piped Water Supply Scheme under Katwa ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000421/2023-2024 | 3291/BWD | 31/07/2023 | 701 | M/S S. CHOUDHURY | 1294.79 | 0 | 100
2804 | Burdwan Division |  | Construction of Toilet (1.8 m x 1.8 m) with sanitary arrangement under KARUI PWSS (SM/18460) 2nd Tube Well Site under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-3) |  |  | ORD/001264/2024-2025 | 344/KTS | 05/03/2025 | 30 | JAMALUDDIN SK | 2.46 | 0 | 0
2805 | Burdwan Division |  | Construction of Toilet (1.8 m x 1.8 m) with sanitary arrangement under KARUI PWSS (SM/18460) 3rd Tube Well Site under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-04) |  |  | ORD/001265/2024-2025 | 345/KTS | 05/03/2025 | 30 | JAMALUDDIN SK | 2.46 | 0 | 0
2806 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000316/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 20.46 | 0 | 0
2807 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000437/2023-2024 | 3850/BWD | 01/09/2023 | 0 | Resource Division | 63.64 | 0 | 0
2808 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000556/2023-2024 | 4889/BWD | 10/11/2023 | 0 | Resource Division | 75.91 | 0 | 0
2809 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000778/2023-2024 | 326/BWD | 24/01/2024 | 0 | Resource Division | 8.78 | 0 | 0
2810 | Central Mechanical |  | New service connection charges for Karui PWSS TW-2 |  |  | BILL/00798/2023-2024 | BP-2023-24-86 | 26/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.67 | 0 | 0
2811 | Central Mechanical |  | New service connection charges for Karui PWSS TW-1 |  |  | BILL/00821/2023-2024 | BP-2023-24-101 | 03/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.19 | 0 | 0
2812 | Central Mechanical |  | New service connection charges for Karui PWSS TW-3 |  |  | BILL/01354/2023-2024 | BP-2023-24-132 | 22/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.65 | 0 | 0
2813 | Central Mechanical |  | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of site for the office of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte, [w.e.f.-01/05/2024 to 30/06/2024] |  |  | ORD/000002/2024-2025 | 259/DIC/BMSD(D) | 26/04/2024 | 61 | SUBRATA BHADRA | 0.79 | 0 | 0
2814 | Central Mechanical |  | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of site for the office of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte, [w.e.f: 01.07.2024 to 31.08.2024] |  |  | ORD/000053/2024-2025 | 350/DIC/BMSD(D) | 27/06/2024 | 62 | SUBRATA BHADRA | 0.79 | 0 | 0
2815 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0
2816 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KARUI Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000215/2023-2024 | 3099/CMD | 24/07/2023 | 550 | JAL PRAVAHIKA PVT LTD | 44.4 | 0 | 91
2817 | Central Mechanical |  | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000602/2024-2025 | 3106/CMD | 11/12/2024 | 60 | S.K. ELECTRICALS | 13.6 | 0 | 0
2818 | Central Mechanical |  | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of The Driller In Charge, Bardhaman Mech, Sub Division ( Drilling) under C.M.D. P.H.E. Dte. w.e.f.-01/09/2023 to 31/10/2023. |  |  | ORD/001162/2023-2024 | 70/DIC/BMSD(D) | 28/08/2023 | 61 | SUBRATA BHADRA | 0.79 | 0 | 100
2819 | Central Mechanical |  | Continuation order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of The Driller In Charge, Bardhaman Mech, Sub Division ( Drilling) under C.M.D. P.H.E. Dte. w.e.f.-01/11/2023 to 31/12/2023. |  |  | ORD/001198/2023-2024 | 159/DIC/BMSD(D) | 31/10/2023 | 61 | SUBRATA BHADRA | 0.79 | 0 | 100
2820 | Central Mechanical |  | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of site for the office of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte, Dte. [w.e.f: 01.01.2024 to 29.02.2024] |  |  | ORD/001697/2023-2024 | 365/DIC/BMSD(D) | 29/12/2023 | 60 | SUBRATA BHADRA | 0.78 | 0 | 100
2821 | Central Mechanical |  | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of site for the office of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte, [w.e.f: 01.03.2024 to 30.04.2024] |  |  | ORD/001726/2023-2024 | 141/DIC/BMSD(D) | 29/02/2024 | 61 | SUBRATA BHADRA | 0.79 | 0 | 100
2822 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kashipur Piped Water Supply Scheme at Sripur, (Sripur Habitation), Kashipur (Part) (Kashipur & Sahabganj Part Habitation) Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000003/2021-2022 | 3118/BWD | 02/06/2021 | 30 | PREMANANDA ROY BISWAS | 35.02 | 29.66 | 1
2823 | Burdwan Division | Durgapur Sub-DIvision | Extension of distribution main for providing FHTC at Kashipur Ramgere Adibasipara within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000176/2021-2022 | 602/DSD | 07/10/2021 | 30 | THREE MAA ENTERPRISE | 4.82 | 0 | 1
2824 | Burdwan Division | Durgapur Sub-DIvision | Extension of distribution main for providing FHTC at Kashipur Ramgere Adibasipara within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000182/2021-2022 | 619/DSD | 25/10/2021 | 30 | THREE MAA ENTERPRISE | 4.82 | 0 | 1
2825 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur village in Sahebganj habitation of Kashipur piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-361/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000266/2020-2021 | 3973/BWD | 14/10/2020 | 30 | PREMANANDA ROY BISWAS | 4.84 | 0 | 0
2826 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nurpur village and Nurpur habitation of Kashipur piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-359/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000267/2020-2021 | 3340/BWD | 18/09/2020 | 30 | THREE MAA ENTERPRISE | 4.84 | 0 | 0
2827 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur village and Sahebganj habitation of Kashipur piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-360/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000312/2020-2021 | 3339/BWD | 18/09/2020 | 30 | PREMANANDA ROY BISWAS | 4.84 | 0 | 0
2828 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur (Part) village (Sahebganj (P) habitation) of Kashipur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 16] [Agree Ment No.719/BWD of 2020-21] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000368/2020-2021 | 1440/BWD | 18/02/2021 | 15 | THREE MAA ENTERPRISE | 4.52 | 0 | 1
2829 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur (Part) village (Kashipur habitation) of Kashipur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 18] [Agr. No. 720/BWD of 2020-2021] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000375/2020-2021 | 1441/BWD | 18/02/2021 | 15 | PREMANANDA ROY BISWAS | 4.48 | 0 | 1
2830 | Burdwan Division | Durgapur Sub-DIvision | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000389/2021-2022 | 268/BWD | 14/01/2022 | 30 | BHARAT CONSTRUCTION | 14.17 | 0 | 1
2831 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC)from distribution system within the command area of Kashipur water supply scheme at Kashipur Nurpur and Sahebganj village to make its Swajalgram under JAL JIBAN MISSION within Bhatar Block in Purba Bardhanan District undrer Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000398/2024-2025 | 623/DSD | 05/08/2024 | 90 | RAM MOHAN MUKHERJEE | 3.15 | 0 | 0
2832 | Burdwan Division | Durgapur Sub-DIvision | Restoration of damaged pipeline of distribution main for construction of drain, concrete road etc at various point at Majhipara village for providing FHTC within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000563/2023-2024 | 652/DSD | 24/08/2023 | 30 | ANWESHA CONSTRUCTION | 0.96 | 0 | 100
2833 | Burdwan Division | Durgapur Sub-DIvision | Relaying and restoration of damaged pipeline of distribution main for widening of PWD road and Bridge at Sahebganj Bazar for providing FHTC within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000564/2023-2024 | 653/DSD | 24/08/2023 | 30 | ANWESHA CONSTRUCTION | 0.95 | 0 | 100
2834 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sripur village (Sripur Habitation) of Kashipur piped water supply scheme within Durgapur Sub-Division under Burdwan Division, PHE Dte.(Tr No.-718/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000613/2020-2021 | 1439/BWD | 18/02/2021 | 15 | ROY BISWAS CONSTRUCTION | 4.5 | 4.5 | 1
2835 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nurpur village and Nurpur Habitation of KASHIPUR piped water supply scheme within Durgapur Sub-Division (Bardhaman North) under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000659/2020-2021 | 3971/BWD | 14/10/2020 | 30 | THREE MAA ENTERPRISE | 1.21 | 0 | 1
2836 | Burdwan Division | Durgapur Sub-DIvision | Restoration of damaged pipeline during construction of drain, concrete road etc and making valve chamber at various point at Kashipur village within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. [SL-14] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000886/2022-2023 | 739/DSD | 30/12/2022 | 21 | PAPRI HAZRA | 0.87 | 0 | 100
2837 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ICHALABAD & HATSIMUL Piped Water Supply Scheme under Burdwan ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000423/2023-2024 | 3292/BWD | 31/07/2023 | 885 | M/S NATIONAL CONSTRUCTION | 1617.18 | 0 | 60
2838 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000281/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.88 | 0 | 0
2839 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000439/2023-2024 | 3848/BWD | 01/09/2023 | 0 | Resource Division | 15.12 | 0 | 0
2840 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000672/2023-2024 | 5062/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
2841 | Central Mechanical |  | Quotation for new service connection for Ichalabad PWSS PH 1. |  |  | BILL/00230/2024-2025 | BP-2024-25-121 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 36.6 | 0 | 0
2842 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 12
2843 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Balance portion of Boundary wall at Head Works Site of RASULPUR Water Supply scheme under MEMARI-I Block of Burdwan Division, PHE Dte. (Length -15.00 Mtr, Col-7 Nos). Gr.E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000443/2022-2023 | 1481/BSD | 25/08/2022 | 30 | DEBASHISH ENTERPRISE | 1.95 | 0 | 100
2844 | Burdwan Division | Burdwan Sadar Sub-Division | Emergency repair and provided (4 nos.100 dia S.V) No's Sluice Valve at Rasulpur Natun Rasta,Nichu Bazar of RASULPUR Piped Water Supply Scheme (Retrofittings) for smooth drinking water supply within within Memari-I Block under Burdwan Division, PHE Dte. Gr.D | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000564/2022-2023 | 1920/BSD | 11/11/2022 | 15 | SUPRIYA RAY | 0.73 | 0 | 100
2845 | Burdwan Division | Burdwan Sadar Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasulpur Piped Water Supply Scheme at Jitkanu, Genraghata, Paschim Tazpur, Ulara (2 Nos Habitation) & Baidyadanga Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte.(Agreement No. 104/SE/CC/PHE/DTE of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000578/2020-2021 | 996/BWD | 04/02/2021 | 60 | MITRA CONSTRUCTION | 93.49 | 94.11 | 0
2846 | Burdwan Division | Burdwan Sadar Sub-Division | Emergency repair and provide 5 (5 nos 100 dia. S.V) No's Sluice Valve at Chaknara & Ullara village under Rasulpur piped water supply scheme (Retro Fittings) for smooth drinking water supply within Memari-I Block under Burdwan Division, PHE Dte (Part-B). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000578/2022-2023 | 1972/BSD | 16/11/2022 | 15 | SUPRIYA RAY | 0.9 | 0 | 0
2847 | Burdwan Division | Burdwan Sadar Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasulpur Piped Water Supply Scheme at Chaknara, Rasulpur (4 Nos Habitation Part) Daluibazar (Part) Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte..[Agreement No. 103/SE/CC/PHE/Dte of 2020-2021.] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000600/2020-2021 | 997/BWD | 04/02/2021 | 60 | MITRA CONSTRUCTION | 95.96 | 94.67 | 0
2848 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC from dist. System within the command area of RASULPUR Piped Water Supply Scheme at Genraghata, Paschim Tazpur, Ulara, Daluibazar of Daluibazar - I G.P. and different samsad such as Samsad No. 05, 13, 08, 12, 09, 10, 11, 15 & 14 within Nimo-I G.P. at Memari-I Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000612/2021-2022 | 1572/BWD | 16/03/2022 | 60 | SUJAY KUMAR RAY | 55.17 | 0 | 1
2849 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of damaged portion of 75 mm dia & 125 mm dia UPVC pipeline due to widening of GT Road by from Palla Road more to Mahamaya Store at RASULPUR water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Gr.-C] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000783/2020-2021 | 19/BSD | 06/01/2021 | 30 | PAL CONSTRUCTION | 4.79 | 0 | 0
2850 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for RASULPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000982/2024-2025 | 4474/BWD | 19/12/2024 | 90 | SARKAR AGENCY | 91.74 | 0 | 51
2851 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000021/2021-2022 | 425/BWD | 20/01/2022 | 0 | Resource Division | 5.5 | 0 | 0
2852 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC of distribution pipe line at Nari village(Habitation-Sutradharpara,Adibasipara & Suriyapally)for RAYAN Water Supply Scheme at Bardhhaman-I Development Block under Burdwan Division,PHE Dte.Gr.A | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000030/2022-2023 | 677/BSD | 22/04/2022 | 30 | BRINDABAN KONAR | 2.68 | 0 | 1
2853 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of RAYAN Piped Water Supply Scheme at Naridaspara and balance portion of Sukantapally, Suryapally, Nari Purbapara & Nasakali (Nari Mouza), Burdwan - I Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000080/2022-2023 | 2558/BWD | 19/05/2022 | 30 | SARKAR AGENCY | 41.42 | 0 | 1
2854 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rayan Piped Water Supply Scheme at Rayan (Part) (Baisnabpara, Bayanpara, Bhotargra, Bhtarpur, DVC Canal, Dakhinpara, Dangapara, Daspara, Dulapara, Durgamandir, Ghatimgore, Gopaldighi & Hatu Dewan (N)) Village (Mouza), Bardhaman-I Block under Burdwan Division, PHE Dte.._2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000099/2021-2022 | 3202/BWD | 09/06/2021 | 60 | SUNNY ELECTRIC CO. | 53.1 | 0 | 1
2855 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rayan Piped Water Supply Scheme at Rayan (Part) (Hatu Dewan(S), Kantai Krishnapur, Katwa Road, KhanPukur, Krishnapur, MadanSayar, Makumpara, Malikpara, Malir Bagan, Muchipara, Muslimpara & Narupara) Village (Mouza), Bardhaman-I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000191/2021-2022 | 3143/BWD | 04/06/2021 | 45 | S.R. ENTERPRISE | 49.27 | 0 | 1
2856 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of RAYAN Piped Water Supply Scheme at Narayandighi & Sadhanpur (Part) Village (Mouza), Burdwan - I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000340/2021-2022 | 27/BWD | 04/01/2022 | 30 | DUBE ENTERPRISE | 30.24 | 0 | 1
2857 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of upvc distribution pipe line, s/valve chamber & conc. Work (Habitation-Belbagan,sutradharpara, Khanpukur & Adibasipara under Nari village) in regarding FHTC for Rayan water supply scheme at Bardhhaman-I Development Block under Burdwan Division, PHE Dte.Gr.B. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000401/2021-2022 | 70/BSD | 14/01/2022 | 30 | BRINDABAN KONAR | 4.64 | 0 | 1
2858 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of interconnection between tube well No 1 to 6 & OHR and OHR to distribution system for RAYAN & Its Adjoing Mouzas Water Supply Scheme within Bardhaman I Dev. Block , under Burdwan Division, PHE Dte.Gr.C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000402/2021-2022 | 71/BSD | 14/01/2022 | 30 | BRINDABAN KONAR | 4.81 | 0 | 1
2859 | Burdwan Division | Burdwan Sadar Sub-Division | Road restoration work due to FHTC & extension pipeline for different village (Rayan, Naryandighi, Nari Das Para, Krishnapur, Nari & Sukantapally) under RAYAN Piped W/S. Scheme at Burdwan - I Dev. Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000593/2023-2024 | 3771/BWD | 29/08/2023 | 30 | DURGAPADA MONDAL | 5.97 | 0 | 100
2860 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of UPVC distribution pipeline sluice valve chamber & concrete work in regarding FHTC for Rayan water supply scheme of Bardhaman-I Development Block under Burdwan Division, PHE Dte.[Gr.-E] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000767/2021-2022 | 1428/BSD | 28/10/2021 | 30 | S.R. ENTERPRISE | 4.01 | 0 | 1
2861 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000001/2024-2025 | 4103/BWD | 25/11/2024 | 0 | Resource Division | 54.42 | 0 | 0
2862 | Burdwan Division | Katwa Sub-Division | Vehicle bill [Car No.-WB-04G-6018] for the month of November & December'2023. | Assistant Engineer |  | BILL/02053/2023-2024 | 1894/JJM | 28/03/2024 | 0 | M/S MUNMUN DEY | 0.45 | 0 | 0
2863 | Burdwan Division | Katwa Sub-Division | Vehicle bill [Car No.-WB-04G-6018] for the month of September & October'2023. | Assistant Engineer |  | BILL/02056/2023-2024 | 1269/JJM | 16/01/2024 | 0 | M/S MUNMUN DEY | 0.49 | 0 | 0
2864 | Burdwan Division | Katwa Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme EKAIHAT, PANUHAT PWSS (Sl No-2) | Assistant Engineer |  | ORD/000070/2023-2024 | 394/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 2.48 | 0 | 100
2865 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bikaihat & Akaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-169/BWD/2020-21) | Assistant Engineer |  | ORD/000106/2020-2021 | 2598/BWD | 04/08/2020 | 30 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 4.92 | 4.92 | 1
2866 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Akaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-196/BWD/2020-21) | Assistant Engineer |  | ORD/000107/2020-2021 | 2597/BWD | 04/08/2020 | 30 | JAI MAA DURGA & CO. | 4.92 | 4.92 | 1
2867 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection from existing distribution system within the command area of Akaihat and Bikihat PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-1) | Assistant Engineer |  | ORD/000238/2021-2022 | 750/KTS | 24/11/2021 | 15 | JAI MAA DURGA & CO. | 2.54 | 0 | 1
2868 | Burdwan Division | Katwa Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ekaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-329/BWD/2020-21) | Assistant Engineer |  | ORD/000261/2020-2021 | 3739/BWD | 07/10/2020 | 30 | JAI MAA DURGA & CO. | 1.74 | 1.74 | 1
2869 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ekaihat & Bikaihat (Pt-A) village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-486/BWD/2020-21) | Assistant Engineer |  | ORD/000265/2020-2021 | 236/KTS | 30/09/2020 | 4 | JAI MAA DURGA & CO. | 1.29 | 1.28 | 1
2870 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ekaihat & Bikaihat (Part-B) village of Ekaihat & Bikaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. (Tr No.-539/BWD/2020-21) | Assistant Engineer |  | ORD/000357/2020-2021 | 237/KTS | 30/09/2020 | 4 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 1.32 | 1.32 | 1
2871 | Burdwan Division | Katwa Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bikaihat & Ekaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-538/BWD/2020-21) | Assistant Engineer |  | ORD/000474/2020-2021 | 3697/BWD | 05/10/2020 | 30 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 1.79 | 1.79 | 1
2872 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ekaihat & Bikaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000625/2020-2021 | 364/KTS | 15/12/2020 | 7 | BISHWAJIT DAS | 1.18 | 1.18 | 1
2873 | Burdwan Division | Katwa Sub-Division | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | Assistant Engineer |  | ORD/000867/2020-2021 | 4318/BWD | 04/11/2020 | 10 | MD HASIN | 4.93 | 0 | 1
2874 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Chhotobainan village of Chhotobainan piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-173/BWD/2020-21) |  |  | ORD/000118/2020-2021 | 2740/BWD | 10/08/2020 | 30 | BOSE ENTERPRISE | 4.9 | 4.9 | 1
2875 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Momrejpur village of Chhotobainan piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-174/BWD/2020-21) |  |  | ORD/000119/2020-2021 | 2741/BWD | 10/08/2020 | 30 | TIRUPATI ENTERPRISES | 4.92 | 4.92 | 1
2876 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chhotobainan Piped Water Supply Scheme at Chhotobainan (3 Nos Part Habitation), Akhina, Dakhin Mohanour, Pahalanpur & Rupsara Village (Mouza), Raina-II Block under Burdwan Division, PHE Dte.(Agreement No. 62/2020-2021 OF SE/CC/PHE. DTE.) |  |  | ORD/000127/2020-2021 | 4852/BWD | 04/12/2020 | 90 | TIRUPATI ENTERPRISES | 100.4 | 82.44 | 1
2877 | Burdwan Division |  | Extension of pipeline for CHHOTOBAINAN water supply scheme at Chhotobainan village within Raina-II Block under Burdwan Division, PHE Dte. (Gr.-D) |  |  | ORD/000208/2021-2022 | 956/BSD | 23/07/2021 | 30 | BOSE ENTERPRISE | 4.92 | 4.28 | 0
2878 | Burdwan Division |  | Extension of pipeline for CHHOTOBAINAN water supply scheme at Pahalanpur and Rupsara and Dakshin Mohonpur village within Raina-II Block under Burdwan Division, PHE Dte. [Gr.-E] |  |  | ORD/000212/2021-2022 | 988/BSD | 30/07/2021 | 30 | TIRUPATI ENTERPRISES | 4.82 | 3.35 | 1
2879 | Burdwan Division |  | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001246/2021-2022 | 900/DW | 03/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 34.54 | 0 | 0
2880 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bundebaj (Pt-A) village of Bundebaj Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 8A] (T.R. No. 320/BWD/2020-21) | Assistant Engineer |  | ORD/000137/2020-2021 | 2586/BWD | 04/08/2020 | 30 | MOMINUL ISLAM MONDAL | 4.92 | 4.92 | 1
2881 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bundebaj (Pt-B) village of Bundebaj Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 8B] (T.R. no. 377/BWD/2020-21) | Assistant Engineer |  | ORD/000138/2020-2021 | 2591/BWD | 04/08/2020 | 30 | MAA LAXMI ENTERPRISE | 4.92 | 4.92 | 1
2882 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bohar village and Minapur & Khortikpara habitation of SATGACHIA piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Gr.-4A] | Assistant Engineer |  | ORD/000739/2020-2021 | 3326/BWD | 18/09/2020 | 30 | SUBRATA GUPTA | 4.87 | 4.84 | 0
2883 | Burdwan Division | Kalna Sub-division | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | Assistant Engineer |  | ORD/000867/2020-2021 | 4318/BWD | 04/11/2020 | 10 | MD HASIN | 4.93 | 0 | 1
2884 | Burdwan Division | Burdwan Sadar Sub-Division | Vehicle bill for the office of the Assistant Engineer, Burdwan Division, PHE Dte. for the month of July'23. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/00613/2023-2024 | 560/JJM | 24/08/2023 | 0 | SK.ASFIA | 0.4 | 0 | 0
2885 | Burdwan Division | Burdwan Sadar Sub-Division | Hire & fuel charges of vehicle Car No.-WB-41J-6795 for the month of June & July2023. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/01035/2023-2024 | 745/JJM | 11/10/2023 | 0 | MD HASIN | 0.79 | 0 | 0
2886 | Burdwan Division | Burdwan Sadar Sub-Division | Realignment and culvert crossing of D.I. pipeline at damaged section and repairing of uPVC pipeline at Nandanpur, Keunta and Rampur village within Keunta Piped Water Supply Scheme, Raina ¿ II Block under Burdwan Division, PHE. Dte. [Group : D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000043/2022-2023 | 236/AE/HQ | 19/04/2022 | 30 | SUPER SKILL | 4.61 | 0 | 1
2887 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000390/2021-2022 | 269/BWD | 14/01/2022 | 30 | PRONAB KUMAR DEY | 6.99 | 0 | 1
2888 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KEUNTA Piped Water Supply Scheme at Kalui, Keunta, Kulpukur, Rathtala, Mandarpur, Rampur & Nandanpur habitation, Raina - I Block under Burdwan Division, PHE Dte. (Agreement No. 57/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000443/2020-2021 | 4853/BWD | 04/12/2020 | 90 | SUPER SKILL | 95.71 | 0 | 1
2889 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) at Nandanpur and Rampur village within the command area of Keunta Piped Water Supply Scheme at Raina-II Block under Burdwan Division, PHE Dte. [Group : D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000461/2021-2022 | 69/AE/HQ | 11/02/2022 | 30 | SUPER SKILL | 4.16 | 0 | 1
2890 | Burdwan Division | Burdwan Sadar Sub-Division | Repairing of damage concrete work due to laying of pipeline at Keunta within Keunta water supply scheme under Burdwan Division, PHE Dte. [Gr.-G] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000556/2021-2022 | 1895/AE/HQ | 16/11/2021 | 30 | DUBE ENTERPRISE | 2.39 | 0 | 1
2891 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipe line for providing Functional Household Tap Connection (FHTC) and construction of sluice valve chamber within the command area of KEUNTA Piped Water Supply scheme, Raina-II Block under Burdwan Division, PHE Dte._Gr-H | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000663/2021-2022 | 138/AE/HQ | 15/03/2022 | 20 | SUPER SKILL | 4.81 | 0 | 1
2892 | Burdwan Division | Burdwan Sadar Sub-Division | Pipeline with FHTC for KEUNTA Water Supply Scheme at Kalui village (30 Nos.), Keunta village (30 Nos.), Mandarpur village (30 Nos.), Rampur village (30 Nos.), Nandanpur village (60 Nos.), within Raina-II Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000712/2022-2023 | 855/BWD | 28/02/2023 | 45 | DUBE ENTERPRISE | 60.1 | 0 | 100
2893 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000005/2021-2022 | 3692/BWD | 16/07/2021 | 0 | Resource Division | 12.43 | 0 | 0
2894 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | VCH/001013/2021-2022 |  | 21/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0
2895 | Burdwan Division | Burdwan Sadar Sub-Division | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | VCH/001045/2021-2022 | 934/DW | 31/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0
2896 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of additional 250 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for MAHESHDANGA Piped Water Supply Scheme, Block - Memari - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000072/2022-2023 | 2472/BWD | 12/05/2022 | 30 | NADIA TUBEWELLS | 10.32 | 0 | 1
2897 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of 200 mm dia HDPE distribution pipe line (Node No-402 To 401B) for Mahesdanga & ADJOINING MOUZAS WATER SUPPLY SCHEME at Memari-I Development Block under Burdwan Division, PHE Dte. Group : C | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000082/2022-2023 | 816/BSD | 20/05/2022 | 30 | M/S ASHA CONSTRUCTION | 4.79 | 0 | 1
2898 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of 200mm.dia. HDPE Distribution pipe line(Node No.401B to 401)for MAHESHDANGA & adjoining mouzas Water Supply Scheme at Memari-I Development block under Burdwan Division,PHE Dte. Group - D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000091/2022-2023 | 831/BSD | 23/05/2022 | 30 | M/S ASHA CONSTRUCTION | 4.49 | 0 | 1
2899 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall including land development at 2nd Tube Well site of MAHESHDANGA water supply scheme under Memari-I Block of Burdwan Division, PHE Dte. (Length -52.00 Mtr, Col-20 Nos). " Group : C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000106/2022-2023 | 985/BSD | 16/06/2022 | 45 | MAA MAHAMAYA CONSTRUCTION | 3.46 | 0 | 1
2900 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maheshdanga Piped Water Supply Scheme at Salda Village (2 Nos. habitations) & Bahara Village (5 Nos. habitations), Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000156/2021-2022 | 4634/BWD | 09/09/2021 | 60 | CREATION CONSTRUCTION | 52.73 | 0 | 1
2901 | Burdwan Division | Burdwan Sadar Sub-Division | Canal crossing of Mahesdanga water supply scheme(Node point 192 to 193) under Memari-I Block under Burdwan Division, PHE Dte.[Gr.-D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000313/2021-2022 | 1158/BSD | 31/08/2021 | 30 | RANADHIR SINHA | 4.85 | 0 | 1
2902 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maheshdanga Piped Water Supply Scheme at Maheshdanga Village (5 Nos. habitations) & Kathalgachhi Village (3 Nos. habitations), Memari ¿ I Block under Burdwan Division, PHE Dte.(Agreement No. 722/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000324/2020-2021 | 1687/BWD | 24/02/2021 | 60 | PABITRA KUMAR SAMANTA | 54.78 | 52.52 | 1
2903 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall (SOUTH side) at Pump house no - I Site of Maheshdanga Water Supply Scheme under Memari-I Dev. Block of Burdwan Division, PHE Dte. (Length -58.00 Mtr, Col-21 Nos). Gr. G | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000475/2021-2022 | 280/BSD | 15/02/2022 | 45 | SK ABDUL HALIM | 4.19 | 0 | 1
2904 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of 168 Mtr long P.C.C Approach road from Main Road to OHR site and inside boundary of OHR Site of MAHESHDANGA PWSS under Memari-I Development Block under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000530/2023-2024 | 3627/BWD | 21/08/2023 | 30 | MANAS BHATTACHARYA | 5.95 | 0 | 100
2905 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC from dist. System within the command area of MAHESDANGA Piped Water Supply Scheme at Bahera (Part) and Mahesdanga (Part) Village (Mahesdanga, Aymadeulepara, Kamarpara & Jangalpara Habs.) at Memari-I Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000611/2021-2022 | 1571/BWD | 16/03/2022 | 30 | SUPRIYA RAY | 22.42 | 0 | 1
2906 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC from dist. System within the command area of MAHESDANGA Piped Water Supply Scheme at Deule Village, Salda Village, Bhara Village, Kathalgachi Village & Koleypara Village at Memari-I Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000613/2021-2022 | 1573/BWD | 16/03/2022 | 60 | SUPRIYA RAY | 70.5 | 0 | 0
2907 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maheshdanga Piped Water Supply Scheme at Deule Village (4 Nos. habitations), Memari ¿ I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000638/2020-2021 | 1796/A/BWD | 26/02/2021 | 45 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 27.66 | 27.65 | 0
2908 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall (North side) including Front Gate at Pump house no - I Site of Maheshdanga Water Supply Scheme under Memari-I Dev. Block of Burdwan Division, PHE Dte. (Length -55.00 Mtr, Col-20 Nos). Gr.D. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000647/2021-2022 | 469/BSD | 21/03/2022 | 45 | SK ABDUL HALIM | 4.37 | 0 | 1
2909 | Burdwan Division | Burdwan Sadar Sub-Division | Earth work in excavation including shoring work of 700 cum capacity 20 Mtr staging height RCC Over Head Reservoir of Mahesdanga water supply scheme of Memari-I Block under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000770/2021-2022 | 1365/BSD | 05/10/2021 | 5 | SK ALIM | 4.73 | 0 | 1
2910 | Burdwan Division | Burdwan Sadar Sub-Division | Earth filling and sand filling in excavated portion and land development at Head work site of 700 cum capacity 20 Mtr staging height RCC Over Head Reservoir of Mahesdanga water supply scheme of Memari-I Block under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000773/2021-2022 | 1408/BSD | 08/10/2021 | 5 | M/S PROCHESTA ENTERPRISE | 4.14 | 0 | 1
2911 | Burdwan Division | Burdwan Sadar Sub-Division | Replacement of fully damaged PVC water supply line at Dulepara along National Highway for MAHESDANGA and its adj.mouza W/S Scheme,Block:Memari-I within Burdwan Sub-Division,PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000870/2023-2024 | 2746/BSD | 28/11/2023 | 30 | SUPRIYA RAY | 0.96 | 0 | 100
2912 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000020/2021-2022 | 421/BWD | 20/01/2022 | 0 | Resource Division | 5.49 | 0 | 0
2913 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | VCH/001555/2021-2022 | 1194/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0
2914 | Burdwan Division | Burdwan Division | Laying of HDPE pipeline at Sonargoria and Kubajur village for providing FHTC within Shura PWSS (Zone-II), Block-Jamalpur under Burdwan Division, PHE Dte._2ND CALL [Group : F] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000050/2022-2023 | 204/AE/HQ | 06/04/2022 | 30 | M/S UNIT CONSTRUCTION | 4.81 | 0 | 1
2915 | Burdwan Division | Burdwan Division | Laying of HDPE pipe for providing FHTC in different habitation of Shura Mouza within Shura Piped Water Supply Scheme (Zone-I), Jamalpur Block under Burdwan Division, P.H.E DTE. [Group: ¿A¿] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000225/2021-2022 | 1815/AE/HQ | 21/09/2021 | 30 | SUKALPA NIRMAN | 4.79 | 0 | 1
2916 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system at leftout area of Chakdighi Gram Panchayat within the command area of SHURA ZONE-I Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. GROUP : C | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000229/2022-2023 | 426/AE/HQ | 03/08/2022 | 30 | D.M. ENTERPRISE | 3.25 | 0 | 1
2917 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Shura (Zone-II) Piped Water Supply Scheme at Haragobindapur Village, Kubajpur Village, Dhapdhara Village, Sonargoria Village, Sahahosenpur Village & Paikpara Village Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 687/BWD of 2020-2021) | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000338/2020-2021 | 1324/BWD | 12/02/2021 | 60 | M/S PIONEER CONSTRUCTION | 73.63 | 0 | 1
2918 | Burdwan Division | Burdwan Division | Laying of HDPE pipe for underground crossing of river embankment at different section of Shura piped water supply scheme (Zone-II) under Burdwan Division, PHE Dte. [Gr.-A] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000414/2021-2022 | 1855/AE/HQ | 05/10/2021 | 30 | M/S PIONEER CONSTRUCTION | 4.67 | 0 | 1
2919 | Burdwan Division | Burdwan Division | Beautification work at Head work, 2nd Pump house site of Surah Zone-I PWSS with Arboriculture, Recharge Pit including shaft and anciliary works at (Jamalpur Block) P.W.S.S under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000549/2024-2025 | 280/RWS | 03/09/2024 | 10 | D.M. ENTERPRISE | 0.97 | 0 | 0
2920 | Burdwan Division | Burdwan Division | Beautification work at Head work, 2nd Pump house site of Surah Zone-II PWSS with Arboriculture, Recharge Pit including shaft and anciliary works at (Jamalpur Block) P.W.S.S under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000550/2024-2025 | 281/RWS | 27/08/2024 | 10 | J.K. CORPORATION | 0.97 | 0 | 0
2921 | Burdwan Division | Burdwan Division | Extension of pipeline & providing Functional House Tap Connection at leftout portion of SHURA Zone-II W/S Scheme within Jamalpur Block under Burdwan Division, P.H.E Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000571/2023-2024 | 764/AE/HQ | 25/08/2023 | 30 | SANDIPAN SENGUPTA | 3.93 | 0 | 100
2922 | Burdwan Division | Burdwan Division | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near Dhapdhara Uttor Pal Para under SHURA Z-II PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000590/2024-2025 | 742/AE/HQ | 13/09/2024 | 30 | J.K. CORPORATION | 0.96 | 0 | 100
2923 | Burdwan Division | Burdwan Division | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near Dhapdhara Bostom Para under SHURA Z-II PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000591/2024-2025 | 743/AE/HQ | 13/09/2024 | 30 | J.K. CORPORATION | 0.94 | 0 | 100
2924 | Burdwan Division | Burdwan Division | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near Dhapdhara Purba Pal Para under SHURA Z-II PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000592/2024-2025 | 744/AE/HQ | 13/09/2024 | 30 | J.K. CORPORATION | 0.96 | 0 | 100
2925 | Burdwan Division | Burdwan Division | Relaying of UPVC pipe damaged due to construction of guard wall to maintain water supply at different location within command area of SURAH ZONE II PWSS Block Jamalpur under Burdwan Division P.H.E Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000625/2022-2023 | 523/AE/HQ | 29/09/2022 | 30 | J. K. CORPORATION | 0.41 | 0 | 0
2926 | Burdwan Division | Burdwan Division | Laying of HDPE pipeline at Shura, Chakdighi and Shukpur village for providing FHTC within Shura PWSS (Zone-I), Block-Jamalpur under Burdwan Division, PHE Dte._Gr-A | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000626/2021-2022 | 124/AE/HQ | 04/03/2022 | 15 | BANGA NIRMAN | 4.71 | 0 | 1
2927 | Burdwan Division | Burdwan Division | Supplying, laying, fitting, fixing of Sluice valve including construction of valve chamber within command area of SURAH ZONE I PWSS Block Jamalpur under Burdwan Division P.H.E Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000626/2022-2023 | 524/AE/HQ | 29/09/2022 | 30 | D.M. ENTERPRISE | 0.41 | 0 | 100
2928 | Burdwan Division | Burdwan Division | Shifting & Relaying of Damaged UPVC Pipeline at Chakdighi for Construction of Road under "PATHASHREE", SHURA ZONE-I PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000627/2024-2025 | 745/AE/HQ | 13/09/2024 | 30 | D.M. ENTERPRISE | 0.95 | 0 | 100
2929 | Burdwan Division | Burdwan Division | Shifting & Relaying of Damaged UPVC Pipeline at Chakdighi Baganbari for Construction of Road under "PATHASHREE", SHURA ZONE-I PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000628/2024-2025 | 746/AE/HQ | 13/09/2024 | 30 | D.M. ENTERPRISE | 0.72 | 0 | 100
2930 | Burdwan Division | Burdwan Division | Laying of HDPE pipeline at Dhapdhara village for providing FHTC within SHURA PWSS (Zone-II), Block-Jamalpur under Burdwan Division, PHE Dte._Gr-A | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000665/2021-2022 | 133/AE/HQ | 11/03/2022 | 20 | M/S UNIT CONSTRUCTION | 2.79 | 0 | 1
2931 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Shura (Zone-I) Piped Water Supply Scheme at Shura Village (3 Nos. habitations), Chakdihi Village & Shukpur Village, Jamalpur Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000675/2020-2021 | 1763/BWD | 26/02/2021 | 60 | SUKALPA NIRMAN | 83.4 | 26.66 | 1
2932 | Burdwan Division | Burdwan Division | Extension of pipeline for SHURA (Zone-II) Piped W/S. Scheme Total 129 Nos. FHTC work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Jamalpur Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000723/2022-2023 | 970/BWD | 03/03/2023 | 30 | SANDIPAN SENGUPTA | 4.08 | 0 | 1
2933 | Burdwan Division | Burdwan Division | Supply & delivery of different dia. CIDF Pipes, Sluice valve & fittings for construction of RCC OHR (350 cum capacity) for SHURA (ZONE-I) W/S. Scheme under Burdwan Division, P.H.E. Dte. [Group: B] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000742/2021-2022 | 165/AE/HQ | 24/03/2022 | 10 | BENGAL BUILDERS | 3.08 | 0 | 1
2934 | Burdwan Division | Burdwan Division | Extension of pipeline for SHURA (Zone-I) Piped W/S. Scheme Total 115 Nos. FHTC work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Jamalpur Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000751/2022-2023 | 1185/BWD | 15/03/2023 | 30 | SK NUR ALAM | 3.52 | 0 | 100
2935 | Burdwan Division | Burdwan Division | Laying of rising main for interconnection of Pump House 1 & 2 and distribution main along with bye pass arrangement for Over Head Reservoir for Shura piped water supply scheme (Zone-II) within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-B] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000924/2020-2021 | 1226/AE/HQ | 10/02/2021 | 30 | M/S UNIT CONSTRUCTION | 4.29 | 0 | 1
2936 | Burdwan Division | Burdwan Division | Laying of rising main for interconnection of Pump House -1 &2 and distribution main alongwith bye-pass arrangement for Over Head Reservoir for Shura piped water supply scheme (Zone-I) within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-A] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000929/2020-2021 | 1228/AE/HQ | 10/02/2021 | 30 | BENGAL BUILDERS | 4.71 | 0 | 1
2937 | Burdwan Division | Burdwan Division | Laying of different dia UPVC pipeline for providing FHTC work at various places under SHURA ZONE- I PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/001028/2023-2024 | 97/AE/HQ | 15/02/2024 | 30 | D.M. ENTERPRISE | 0.93 | 0 | 100
2938 | Burdwan Division | Burdwan Division | Construction & Installation of Sluice valve & valve Chamber to control the flow of water under SHURA ZONE-I PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/001029/2023-2024 | 98/AE/HQ | 15/02/2024 | 30 | D.M. ENTERPRISE | 0.76 | 0 | 100
2939 | Burdwan Division | Burdwan Division | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Engineer, Headquarters, Burdwan Division, PHE Dte. for the month of September & October'2022. | AE(HQs), Burdwan Division, PHE Dte. |  | VCH/000839/2022-2023 | 766/VEH/22-23 | 22/11/2022 | 0 | SK. ASRAFUDDIN | 0.7 | 0 | 0
2940 | Burdwan Division | Burdwan Sadar Sub-Division | Providing 19 Nos. FHTC at ISHUFABAD & GRAMGORIA village for declaration of SWAJALGRAM under ISHUFABAD Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000152/2024-2025 | 1037/BSD | 10/06/2024 | 30 | DEBASHISH ENTERPRISE | 0.91 | 0 | 0
2941 | Burdwan Division | Burdwan Sadar Sub-Division | Providing 19 Nos. FHTC at DHOLAN & FAGUPUR village for declaration of SWAJALGRAM under ISHUFABAD Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000178/2024-2025 | 1036/BSD | 10/06/2024 | 30 | MUKHERJEE ENTERPRISES | 0.91 | 0 | 100
2942 | Burdwan Division | Burdwan Sadar Sub-Division | Providing 35 Nos.FHTC at KASHIMPUR village for declearation of SWAJALGRAM under ISHUFABAD Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000296/2024-2025 | 1278/BSD | 12/07/2024 | 45 | DUBE ENTERPRISE | 1.64 | 0 | 0
2943 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
2944 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for ISUFABAD Water Supply Scheme at KASIMPUR village within BURDWAN-I Block , under Burdwan Division, PHE Dte.Gr.A | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000473/2021-2022 | 274/BSD | 15/02/2022 | 30 | SUPRIYA RAY | 4.98 | 0 | 1
2945 | Burdwan Division | Burdwan Sadar Sub-Division | Pipeline with FHTC for Isufabad Water Supply Scheme at Fagupur village (15 Nos) of Burdwan-I Block, under Burdwan Division, PHE Dte. Gr.C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000476/2022-2023 | 1600/BSD | 14/09/2022 | 30 | DUBE ENTERPRISE | 3.08 | 0 | 1
2946 | Burdwan Division | Burdwan Sadar Sub-Division | Pipeline with FHTC for Isufabad Water Supply Scheme at ISUFABAD village (15 Nos) of Burdwan-I Block, under Burdwan Division, PHE Dte. Gr.J. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000483/2022-2023 | 1607/BSD | 14/09/2022 | 30 | DUBE ENTERPRISE | 1.89 | 0 | 1
2947 | Burdwan Division | Kalna Sub-division | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of December22 to February'23. | Assistant Engineer |  | BILL/00118/2023-2024 | 30/JJM | 19/04/2023 | 0 | PARTHA PRATIM ACHARYA | 1.19 | 0 | 0
2948 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dhamai village and Dhamai habitation of Nadanghat piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-558/BWD/2020-21) | Assistant Engineer |  | ORD/000255/2020-2021 | 4120/BWD | 16/10/2020 | 30 | NANDY UDYOG | 4.85 | 4.85 | 1
2949 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dhamai village and Nimar habitation of Nadanghat piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-389/BWD/2020-21) | Assistant Engineer |  | ORD/000258/2020-2021 | 4121/BWD | 16/10/2020 | 30 | RUPALI ENTERPRISE | 4.86 | 4.86 | 1
2950 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nadanghat Piped Water Supply Scheme at Kundapara village & Nadanghat village, Purbasthali - I Block under Burdwan Division, PHE Dte. (Agreement No. 700/BWD of 2020-2021) | Assistant Engineer |  | ORD/000334/2020-2021 | 1543/BWD | 22/02/2021 | 60 | MAA LAXMI ENTERPRISE | 51.66 | 0 | 1
2951 | Burdwan Division | Kalna Sub-division | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Nadanghat piped water supply scheme at Kundapara village (37 nos FHTC) & Nadanghat village (75 nos FHTC), Purbasthali-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer |  | ORD/000470/2021-2022 | 153/KSD | 15/02/2022 | 15 | MAA LAXMI ENTERPRISE | 4.51 | 0 | 1
2952 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC in Purba Kashiara village for 100% coverage in Sajal Gram from existing distribution system within RAIPUR PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Gr.E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000345/2022-2023 | 1368/BSD | 04/08/2022 | 5 | ASHOK KUMAR GHOSH | 0.68 | 0 | 0
2953 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC and extension of UPVC distribution pipeline at Raipur, Gumri, Namalpur & Mahipal habitation for RAIPUR Piped Water Supply Scheme at Burdwan - II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000358/2021-2022 | 104/BWD | 06/01/2022 | 30 | ROY CONSTRUCTION | 23.65 | 0 | 1
2954 | Burdwan Division | Burdwan Sadar Sub-Division | Different type of works related (Internal pathways and approach road 2nd pump, Land-Development, FHTC, repair of boundary wall & pump houses and road restoration) under RAIPUR PWSS under Burdwan-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000374/2024-2025 | 2995/BWD | 01/08/2024 | 184 | PRATIVA CONSTRUCTION | 11.79 | 0 | 80
2955 | Burdwan Division | Burdwan Sadar Sub-Division | Shifting & Relaying of 2nd T.Well Raising main and providing 5 nos (100mm dia) S/Valve at existing dist. Line for Raipur water supply scheme at Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Group: H | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000481/2022-2023 | 1605/BSD | 14/09/2022 | 30 | ASHOK KUMAR GHOSH | 1.72 | 0 | 0
2956 | Burdwan Division | Burdwan Sadar Sub-Division | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Raipur piped water supply scheme at Mahipal (05 Nos Habitation), Purba Kashiara (08 Nos. Habitation), Sahara (04 Nos. Habitation), Sonakur (07 Nos. Habitation), Baratpur (16 Nos, Habitation) & Raipur (10 Nos. Habitation) village, Bardhaman-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000533/2020-2021 | 5007/BWD | 10/12/2020 | 90 | ASHOK KUMAR GHOSH | 43.99 | 0 | 1
2957 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC (12 Nos.) and extension of UPVC distribution pipeline at Basatpur Habitation for Raipur water supply scheme at Burdwan-II Development Block under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000543/2021-2022 | 1461/BSD | 01/11/2021 | 30 | ASHOK KUMAR GHOSH | 2.14 | 0 | 1
2958 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) of RAIPUR & its adjoining mouzas Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. _2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000568/2022-2023 | 5273/BWD | 30/11/2022 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 9.45 | 0 | 1
2959 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of inter connection between 3rd tube well site and distribution system for Raipur PWSS within Bardhaman-II Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000574/2023-2024 | 2039/BSD | 24/08/2023 | 45 | ISHAN CONSTRUCTION | 1.57 | 0 | 100
2960 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Basatpur village of Raipur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿1A¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000679/2020-2021 | 2726/BWD | 10/08/2020 | 30 | ASHOK KUMAR GHOSH | 4.92 | 0 | 1
2961 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Mahipal Village, Burdwan - II Block within Raipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000775/2023-2024 | 854/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0 | 100
2962 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Basatpur Village, Burdwan - II Block within Raipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000776/2023-2024 | 856/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0 | 100
2963 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Purba Kashiara Village, Burdwan - II Block within Raipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000778/2023-2024 | 857/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0 | 100
2964 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for RAIPUR its Adjoining Mouza W/S Scheme, Block -Bardhaman-II within Burdwan Sub-Division, PHE Dte. (Mouza- PURBA KASHIARA) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000839/2022-2023 | 501/BSD | 21/03/2023 | 45 | IRIN CONSTRUCTION CO. | 3.3 | 0 | 100
2965 | Burdwan Division | Burdwan Sadar Sub-Division | MAINTENANCE OF ROAD (WHISH IS DAMAGED FOR LAYING PIPELINE BY PHE DEPTT) NAMELY NARUGRAM H.C TO BADSHI ROAD VIDE- PACKAGE NO- WB 22 12 UNDER PMGSY-III UNDER NARUGRAM GP. & RAINA-I BLOCK, IN PURBA BARDHAMAN DISTRICT | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/00740/2024-2025 | 894/JJM | 25/09/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 3.86 | 0 | 0
2966 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of LOHAI Piped Water Supply Scheme at Madhabdihi, Bhanjanpur, Akhina & Dakhin Gopalpur Village (Mouza), Raina-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000157/2021-2022 | 4635/BWD | 09/09/2021 | 60 | CREATION CONSTRUCTION | 61.85 | 0 | 1
2967 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Barakalmi & Sirajpur village of Lohana Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 22] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000195/2021-2022 | 6188/BWD | 28/10/2021 | 15 | PARTHA PRATIM ACHARYA | 4.86 | 0 | 1
2968 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of uPVC pipe for providing FHTC in different habitation of Lohai, Akhina and Dakshin Gopalpur Mouza within Lohai Piped Water Supply Scheme, Raina-II Block under Burdwan Division P.H.E DTE. [Group: ¿E¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000221/2021-2022 | 1816/AE/HQ | 21/09/2021 | 30 | M/S S. CHOUDHURY | 4.76 | 0 | 1
2969 | Burdwan Division | Burdwan Sadar Sub-Division | Plinth protection and uplift of inner side of base floor of OHR and construction of sluice valve chamber at LOHAI PWSS at Raina-II Block under Burdwan Division PHE Dte. [Group : B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000359/2022-2023 | 446/AE/HQ | 16/08/2022 | 30 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 1.91 | 0 | 1
2970 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Natungram village and Natungram, Daspara, Palpara habitation of Lohana piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-475/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000370/2020-2021 | 4781/BWD | 02/12/2020 | 30 | PARTHA PRATIM ACHARYA | 2.95 | 0 | 1
2971 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Lohai Piped Water Supply Scheme at Arui, Dighra, Jotragob, Konerpur & Lohai Village (Mouza), Raina-II Block under Burdwan Division, PHE Dte. [Agreement No. 54/2020-2021 OF SE/CC/PHE. DTE.] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000419/2020-2021 | 4888/BWD | 07/12/2020 | 90 | M/S S. CHOUDHURY | 75.66 | 0 | 1
2972 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of dedicated HDPE pipeline for supply of sufficient water at Bhanjapur village of Lohai piped water supply scheme, Raina-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000575/2021-2022 | 6741/BWD | 03/12/2021 | 30 | THREE MAA ENTERPRISE | 20.11 | 0 | 1
2973 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of uPVC pipe for providing FHTC at Bhanjapur, Alampur and Akhina Village within Lohai Piped Water Supply Scheme, Raina-II Block under Burdwan Division P.H.E Dte.Gr. E | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000630/2021-2022 | 127/AE/HQ | 04/03/2022 | 15 | M/S S. CHOUDHURY | 4.79 | 0 | 1
2974 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of uPVC pipe for providing FHTC at Madhabdihi, Lohai and Akhina Village within LOHAI Piped Water Supply Scheme, Raina-II Block under Burdwan Division P.H.E Dte._Gr-E | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000668/2021-2022 | 137/AE/HQ | 15/03/2022 | 20 | M/S S. CHOUDHURY | 4.8 | 0 | 1
2975 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for providing functional house hold tap connection at Bhanjapur Mouza within Lohai water supply scheme under Burdwan Division, PHE Dte.[Gr.-D] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000969/2020-2021 | 1259/AE/HQ | 15/02/2021 | 30 | M/S S. CHOUDHURY | 4.14 | 0 | 1
2976 | Burdwan Division | Burdwan Sadar Sub-Division | Balance Work for extension of pipe lines to provide FHTC with Sinking of Tubwell, Construction of pump house with Boundary wall & other related work for LOHAI PWSS under Burdwan Sub-Div., Block -Raina-II, under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001014/2024-2025 | 61/BWD | 06/01/2025 | 120 | B.S. ENTERPRISE | 62.48 | 0 | 0
2977 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Ghosh Piped Water Supply Scheme at Mondaljana Part (Bajamondaljana, Kashirampur & Mondaljana Habitation), Horirampur & Ghosh Part Village (Mouza) Memari-I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000102/2021-2022 | 3781/BWD | 22/07/2021 | 30 | KAUSHIK RAY | 20.09 | 20.09 | 1
2978 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of GHOSH Piped Water Supply Scheme at Andur & Bahapur village (Mouza), Memari ¿ I Block under Burdwan Division, PHE Dte.(Agreement No. 577/BWD of 2020-2021) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000328/2020-2021 | 437/BWD | 24/02/2021 | 30 | MAJILA ENTERPRISE | 22.76 | 0 | 1
2979 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for GHOSH Piped Water Supply Scheme at Mondaljone (6 Nos), Kashirampur (8 Nos),Total 14 Nos FHTC Work for Sajal Gram(As per Field verification report for Har Ghar Jal Certification within Memari-I Block including leftout household water connection (FHTC) under Burdwan Division,PHE Dte. Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000333/2022-2023 | 1350/BSD | 02/08/2022 | 5 | MAJILA ENTERPRISE | 0.97 | 0 | 1
2980 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC from dist. System within the command area of GHOSH Piped Water Supply Scheme at Kashirampur, Joyampur, Sajina, Ichapur, Purba-Gantar, Andur, Bahabpur & Ghosh (Part) village (Mouza) at Memari-I Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000338/2021-2022 | 25/BWD | 04/01/2022 | 30 | MAJILA ENTERPRISE | 36.17 | 0 | 1
2981 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Memari-I Block (Daluibazar-II, Gopegantar-I & II G.P.) under Burdwan Division, PHE. Dte. Dte._Part-A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000371/2021-2022 | 209/BWD | 11/01/2022 | 30 | M/S ANAND CONSTRUCTION | 21.11 | 0 | 1
2982 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for GHOSH Piped Water Supply Scheme at Mondaljona [6 No's], Kashirampur [8 No's],Total 14 No's FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Memari-I Block including leftout husehold water tap connection(FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000644/2022-2023 | 1350-A/BSD | 02/08/2022 | 5 | MAJILA ENTERPRISE | 0.97 | 0 | 0
2983 | Burdwan Division | Burdwan Sadar Sub-Division | Re-Laying of damaged pipeline on distribution system for FHTC work for GHOSH Piped Water Supply Scheme at JOY RAMPUR mouza within MEMARI - I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001070/2024-2025 | 104/BSD | 16/01/2025 | 30 | N.S. ENTERPRISE | 4.81 | 0 | 0
2984 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashiara village of Kasiara piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-260/BWD/2020-21) |  |  | ORD/000245/2020-2021 | 341/BWD | 22/09/2020 | 30 | HAMID SK | 4.92 | 4.92 | 1
2985 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Chanak village of Kashiara piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-259/BWD/2020-21) |  |  | ORD/000246/2020-2021 | 3412/BWD | 22/09/2020 | 30 | BABUL SK | 4.92 | 4.92 | 1
2986 | Burdwan Division |  | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kashira Piped Water Supply Scheme at Chanak (Part), Gopalbera, Krishnapur, Gatistha & Kashira (Part) Village (Mouza), Mongolkot Block under Burdwan Division, PHE Dte. (Agreement No. 99/SE/CC/PHE/Dte of 2020-2021) |  |  | ORD/000418/2020-2021 | 915/BWD | 02/02/2021 | 60 | MAJUMDER ENTERPRISE | 53.52 | 45.56 | 0
2987 | Burdwan Division | Kalna Sub-division | Quotation from WBSEDCL for Augmentation of Dogachia water supply scheme for Pump House No.-4 under Burdwan Division, PHE Dte. | Assistant Engineer |  | BILL/00365/2024-2025 | 566/JJM | 23/07/2024 | 0 | WBSEDCL | 8.89 | 0 | 0
2988 | Burdwan Division | Kalna Sub-division | Quotation from WBSEDCL for Augmentation of Dogachia water supply scheme for Pump House No.-3 under Burdwan Division, PHE Dte. | Assistant Engineer |  | BILL/00366/2024-2025 | 567/JJM | 23/07/2024 | 0 | WBSEDCL | 7.63 | 0 | 0
2989 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 2nd TW Site of Aug. of DOGACHHIA & its adjoining mouzas Piped Water Supply Scheme, Block ? Purbasthali ? I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000547/2022-2023 | 5129/BWD | 21/11/2022 | 30 | MUNSHI ENTERPRISE | 8.72 | 0 | 0
2990 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Dogachia W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-H) | Assistant Engineer |  | ORD/000574/2021-2022 | 210/KSD | 23/02/2022 | 21 | ROY CHOWDHURY ASSOCIATES | 2.62 | 0 | 1
2991 | Burdwan Division | Kalna Sub-division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of DOGACHIA Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte._SL.No-08 | Assistant Engineer |  | ORD/000619/2021-2022 | 142/AE/HQ | 16/03/2022 | 10 | MAKALI ENGINEERING CORPORATION | 4.52 | 0 | 0
2992 | Burdwan Division | Kalna Sub-division | Augmentation of DOGACHIA Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 200 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation & boundary wall construction at 2nd TW site under Purbasthali ¿ I Block, District - Purba Bardhaman. | Assistant Engineer |  | ORD/000678/2021-2022 | 1809/BWD | 31/03/2022 | 365 | MITRA CONSTRUCTION | 226.14 | 0 | 60
2993 | Burdwan Division | Kalna Sub-division | Sinking of tube well, laying dist. system, construction of pump house and laying rising main of DOGACHIA Piped Water Supply Scheme with Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000877/2023-2024 | 5337/BWD | 04/12/2023 | 120 | MITRA CONSTRUCTION | 78.72 | 0 | 20
2994 | Burdwan Division | Kalna Sub-division | Additional work to implement augmentation of DOGACHHIA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000929/2023-2024 | 5512/BWD | 14/12/2023 | 30 | PARTHA PRATIM ACHARYA | 9.39 | 0 | 100
2995 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000043/2021-2022 | 541/BWD | 27/01/2022 | 0 | Resource Division | 9.17 | 0 | 0
2996 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000104/2021-2022 | 949/BWD | 17/02/2022 | 0 | Resource Division | 14.44 | 0 | 0
2997 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000149/2021-2022 | 1247/BWD | 07/03/2022 | 0 | Resource Division | 4.19 | 0 | 0
2998 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000206/2021-2022 | 1529/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
2999 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
3000 | Burdwan Division | Kalna Sub-division | Additional works for construction of OHR having capacity 250 cum in connection with Augmentation of CHAMPAHATI PWSS (SM/09416) under Purbasthali-I Block under Kalna Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000359/2024-2025 | 2924/BWD | 26/07/2024 | 90 | MONDAL ENTERPRISE | 27.44 | 0 | 2
3001 | Burdwan Division | Kalna Sub-division | Relaying of HDPE pipeline at damaged portion at Kutirpara village within Champahati W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | Assistant Engineer |  | ORD/000469/2021-2022 | 152/KSD | 15/02/2022 | 30 | P.C. CONSTRUCTION | 4.84 | 0 | 1
3002 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Champahati W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-G) | Assistant Engineer |  | ORD/000573/2021-2022 | 209/KSD | 23/02/2022 | 21 | INDRANIL DUTTA & ASSOCIATES | 2.7 | 0 | 1
3003 | Burdwan Division | Kalna Sub-division | Augmentation of CHAMPAHATI Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 250 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test with construction of boundary wall at Head works site under Kalna ¿ II Block, District - Purba Bardhaman. | Assistant Engineer |  | ORD/000653/2021-2022 | 1655/BWD | 22/03/2022 | 365 | MONDAL ENTERPRISE | 265.13 | 0 | 80
3004 | Burdwan Division | Kalna Sub-division | Additional works to implement the CHAMPAHATI Piped Water Supply Scheme under Purbasthali-I Block, Dist :- Purba Burdwan under Burdwan Divn., PHE. Dte. | Assistant Engineer |  | ORD/000757/2022-2023 | 1270/BWD | 17/03/2023 | 30 | MONDAL ENTERPRISE | 24.02 | 0 | 50
3005 | Burdwan Division | Kalna Sub-division | Additional Work of CHAMPAHATI Piped Water Supply Scheme with sinking of Tube-wells, LDSs, FHTCs, construction of switch rooms & boundary wall with gate under PURBASTHALI-I Block, District:- Purba Bardhaman._2ND CALL. | Assistant Engineer |  | ORD/001011/2023-2024 | 370/BWD | 29/01/2024 | 245 | ANWESHA CONSTRUCTION | 59.07 | 0 | 20
3006 | Burdwan Division | Kalna Sub-division | Work Order for "Laying of Rising Main for CHAMPAHATI(SM/09416) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer |  | ORD/001184/2023-2024 | 2187/KSD | 15/03/2024 | 10 | DEL DELTA CONSTRUCTION | 4.82 | 0 | 2
3007 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000040/2022-2023 | 4633/BWD | 17/10/2022 | 0 | Resource Division | 12.32 | 0 | 0
3008 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000048/2021-2022 | 564/BWD | 27/01/2022 | 0 | Resource Division | 10.64 | 0 | 0
3009 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000084/2021-2022 | 606/BWD | 28/01/2022 | 0 | Resource Division | 24.12 | 0 | 0
3010 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000103/2021-2022 | 950/BWD | 17/02/2022 | 0 | Resource Division | 35.32 | 0 | 0
3011 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000211/2021-2022 | 1534/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
3012 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
3013 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MANIKHAR Piped Water Supply Scheme at Kalna-I Block under Burdwan Division, PHE Dte. (Agreement No. 47/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer |  | ORD/000113/2020-2021 | 4787/BWD | 02/12/2020 | 90 | H SAMANTA | 96.04 | 0 | 1
3014 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 11 Nos. Piped W/S. Schemes under Kalna I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000335/2024-2025 | 3015/BWD | 05/08/2024 | 60 | HORIZEN | 29.6 | 0 | 10
3015 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 2nd TW Site of MANIKHAR & its adjoining mouzas Piped Water Supply Scheme, Block Kalna I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000704/2022-2023 | 658/BWD | 21/02/2023 | 30 | DAS CONSTRUCTION | 8.72 | 0 | 1
3016 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000119/2021-2022 | 1112/BWD | 26/02/2022 | 0 | Resource Division | 28.05 | 0 | 0
3017 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0
3018 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of NABABHAT Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 450 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation & repairing of Pump House at Head works & 2nd TW site under Burdwan I Block, District - Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000016/2022-2023 | 1964/BWD | 12/04/2022 | 1085 | S.P. CONSTRUCTION | 514.15 | 0 | 100
3019 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall at East side of Nababhat PHE Complex Burdwan Division, PHE Dte. (Length-106.0Mtr, Col-37 Nos.) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000431/2021-2022 | 4664/BWD | 10/09/2021 | 30 | MANAS KUMAR CHATTERJEE | 7.89 | 0 | 1
3020 | Burdwan Division | Burdwan Sadar Sub-Division | Land Development at East Side of Office Building under Nababhat PHE Complex under Burdwan Sub-Division in Burdwan Division,PHE Dte. Gr.D. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000466/2021-2022 | 277/BSD | 15/02/2022 | 30 | MANAS KUMAR CHATTERJEE | 3.17 | 0 | 1
3021 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Nababhat W/S Scheme under Burdwan-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl. No.14. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000503/2021-2022 | 189/BSD | 31/01/2022 | 30 | RADIANT | 2.87 | 0 | 1
3022 | Burdwan Division | Burdwan Sadar Sub-Division | Wall Painting at East Side Boundary Wall of Nababhat PHE Complex for IEC Programme for FHTC WORK under Burdwan Sub-Division, PHE Dte. Gr. A. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000507/2022-2023 | 1067/BSD | 27/06/2022 | 7 | FIVE HURDS ENGINEERING FARM | 0.4 | 0 | 1
3023 | Burdwan Division | Burdwan Sadar Sub-Division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Paharhati, Nababhat, Shyamsundar & Dewandighi-Mirzapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000519/2022-2023 | 4703/BWD | 19/10/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 0 | 1
3024 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of NABABHAT & its adjoining mouzas Piped Water Supply Scheme, Block - Burdwan - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000552/2022-2023 | 5194/BWD | 24/11/2022 | 30 | ANIRUDDHA FARUQUE | 11.24 | 0 | 1
3025 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall (with main gate) at west side of Nababhat PHE complex of Augmentation of Nababhat under Burdwan Division, PHE Dte. (Length-110 Mtr, Col-45 Nos.) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000935/2021-2022 | 6254/BWD | 01/11/2021 | 30 | SUROVI CONSTRUCTION AND GENERAL ORDER SUPPLIERS | 7.05 | 0 | 0
3026 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000061/2021-2022 | 544/BWD | 27/01/2022 | 0 | Resource Division | 25.82 | 0 | 0
3027 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000155/2021-2022 | 1238/BWD | 07/03/2022 | 0 | Resource Division | 4.19 | 0 | 0
3028 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000162/2021-2022 | 1322/BWD | 08/03/2022 | 0 | Resource Division | 12.13 | 0 | 0
3029 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000214/2021-2022 | 1537/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
3030 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
3031 | Burdwan Division | Central Mechanical Sub-Division | Augmentation of KAITHAN Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation including repairing of pump house at Head Works & 2nd TW site under Katwa ¿ I Block, District - Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000018/2022-2023 | 2007/BWD | 13/04/2022 | 365 | VISHAL CONSTRUCTION CO. | 365.96 | 0 | 95
3032 | Burdwan Division | Central Mechanical Sub-Division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Baharan-Birampur, Kaithan, Majhigram-Sigot & Ketugram (Zone-I & II) Piped Water Supply Scheme within Katwa Sub-Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 4702/BWD | 19/10/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 0 | 1
3033 | Burdwan Division | Central Mechanical Sub-Division | Route Survey and preparation of DPR for KAITHAN PWSS under Katwa-I & II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-02] | Assistant Engineer | Junior Engineer | ORD/000538/2021-2022 | 45/KTS | 24/01/2022 | 21 | RADIANT | 2.59 | 0 | 1
3034 | Burdwan Division | Central Mechanical Sub-Division | Construction of Boundary Wall at Head Work site of KAITHAN PWSS under Katwa-I Block under Katwa Sub-Division within Burdwan Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000856/2023-2024 | 5200/BWD | 29/11/2023 | 30 | SUBODH KUMAR MONDAL | 22.82 | 0 | 75
3035 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000057/2021-2022 | 547/BWD | 27/01/2022 | 0 | Resource Division | 17.27 | 0 | 0
3036 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000112/2021-2022 | 1089/BWD | 25/02/2022 | 0 | Resource Division | 32.22 | 0 | 0
3037 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000164/2021-2022 | 1324/BWD | 08/03/2022 | 0 | Resource Division | 17.01 | 0 | 0
3038 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000182/2021-2022 | 1377/BWD | 09/03/2022 | 0 | Resource Division | 4.13 | 0 | 0
3039 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000231/2021-2022 | 1542/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
3040 | Burdwan Division | Central Mechanical Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
3041 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum formal work order for the work of " Supplying & Laying of different dia UPVC pipe at Dignagar under Dignagar PWSS, Block- Aushgram-I, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000037/2024-2025 | 761/DWSD | 06/06/2024 | 260 | SAFTI PRIVATE LIMITED | 53.8 | 0 | 35
3042 | Burdwan Division | Durgapur Sub-DIvision | Quotation for Dignagar water supply scheme. P.H. No.-03 [Quotation Memo No.-5003612925/Quot/03, dt.-17/02/2023] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00374/2022-2023 | 1169/JJM | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.06 | 0 | 0
3043 | Burdwan Division | Durgapur Sub-DIvision | Sinking of additional 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Augmentation of DIGNAGAR Piped Water Supply Scheme, Block - Ausgram I, Dist Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000056/2022-2023 | 2234/BWD | 29/04/2022 | 30 | J. K. CORPORATION | 14.12 | 0 | 1
3044 | Burdwan Division | Durgapur Sub-DIvision | Laying of UPVC pipe line by replacement of AC pipe, installation new SSP and Sluice valve, restoration of existing Street Stand Posts, Valve chamber, and allied work of DIGNAGAR W/S Scheme under Durgapur (Burdwan North)Sub Division under Burdwan Division, P.H.E. Dte.[Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000187/2021-2022 | 624/DSD | 25/10/2021 | 45 | ANWESHA CONSTRUCTION | 2.08 | 0 | 1
3045 | Burdwan Division | Durgapur Sub-DIvision | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Dignagar, Galsi, Barabelun & Kotachandipur Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. Dte. _2ND CALL | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000311/2022-2023 | 3624/BWD | 22/08/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.76 | 0 | 1
3046 | Burdwan Division | Durgapur Sub-DIvision | Augmentation of DIGNAGAR Piped Water Supply Scheme with LDS, FHTC Work, Rising Main, Switch room (with water supply & sanitary arrangements), 400 cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Boundary wall construction (New TW Site) with repairing of existing switch room cum chlorine room, Block ¿ Ausgram ¿ I, District - Purba Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000410/2021-2022 | 289/BWD | 17/01/2022 | 365 | S.S. ENTERPRISE | 390.11 | 0 | 1
3047 | Burdwan Division | Durgapur Sub-DIvision | Route Survey & Preparation of DPR for DIGNAGAR PWSS under Durgapur (Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000648/2021-2022 | 100/DSD | 18/02/2022 | 15 | SIRCON ENGINEERING SERVICES | 2.81 | 0 | 1
3048 | Burdwan Division | Durgapur Sub-DIvision | Installation of AIR valve with MS pipe Connection near both side of Dignagar irrigation Canal under Augmentation of DIGNAGAR and its adjoining mouza¿s piped W/S Scheme at Ausgram-I Block within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000940/2023-2024 | 912/DSD | 15/12/2023 | 30 | S.S. ENTERPRISE | 0.96 | 0 | 100
3049 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000028/2021-2022 | 552/BWD | 27/01/2022 | 0 | Resource Division | 12.66 | 0 | 0
3050 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000064/2021-2022 | 618/BWD | 28/01/2022 | 0 | Resource Division | 22.71 | 0 | 0
3051 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000166/2021-2022 | 1326/BWD | 08/03/2022 | 0 | Resource Division | 36.24 | 0 | 0
3052 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000184/2021-2022 | 1379/BWD | 09/03/2022 | 0 | Resource Division | 4.45 | 0 | 0
3053 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000234/2021-2022 | 1558/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
3054 | Burdwan Division | Durgapur Sub-DIvision | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
3055 | Burdwan Division | Durgapur Sub-DIvision | Quotation from WBSEDCL for Augmentation of Bhatakul Zone-2 water supply scheme for P.H.-2 under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00390/2024-2025 | 536/JJM | 18/07/2024 | 0 | WBSEDCL | 11.79 | 0 | 0
3056 | Burdwan Division | Durgapur Sub-DIvision | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell site for Augmentation of BHATAKUL (Zone-I & II) Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000014/2022-2023 | 1962/BWD | 12/04/2022 | 45 | ACME CONSTRUCTION | 22.05 | 0 | 100
3057 | Burdwan Division | Durgapur Sub-DIvision | Augmentation of BHATAKUL Piped Water Supply Scheme (Zone - I & II) including Laying Distribution System, Functional Household Tap Connection, Pumping Main, 350 Cum capacity Over Head Reservoir with 20 Mtr. staging height (including Soil Testing), Switch Room with sanitary arrangement, construction of Boundary wall in Head work site and repairing of pump house at Bhatar Block in under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000398/2021-2022 | 277/BWD | 14/01/2022 | 657 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 351.08 | 0 | 100
3058 | Burdwan Division | Durgapur Sub-DIvision | Construction of Drum Sheet Walling and Approach road to HW site for Augmentation of Bhatakul (Zone-I ) Piped water supply Scheme , P.H.E Dte. Block:-Bhatar, Dist: Purba Bardhaman. SL-13 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000534/2022-2023 | 653/DSD | 03/11/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 2.99 | 0 | 100
3059 | Burdwan Division | Durgapur Sub-DIvision | Route Survey & Preparation of DPR for BHATAKUL PWSS under Durgapur(Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-F] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000657/2021-2022 | 106/DSD | 18/02/2022 | 15 | SIRCON ENGINEERING SERVICES | 2.63 | 0 | 1
3060 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000020/2022-2023 | 3276/BWD | 29/07/2022 | 0 | Resource Division | 69.15 | 0 | 0
3061 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000030/2021-2022 | 548/BWD | 27/01/2022 | 0 | Resource Division | 9.39 | 0 | 0
3062 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000100/2021-2022 | 768/BWD | 07/02/2022 | 0 | Resource Division | 38.41 | 0 | 0
3063 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000172/2021-2022 | 1338/BWD | 08/03/2022 | 0 | Resource Division | 56.67 | 0 | 0
3064 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000192/2021-2022 | 1374/BWD | 09/03/2022 | 0 | Resource Division | 3.83 | 0 | 0
3065 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000220/2021-2022 | 1543/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
3066 | Burdwan Division | Durgapur Sub-DIvision | Shifting of 25 KVA S/STN with Selenda 11KV HTOH Line from the premises of Bhatakul PWSS under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | VCH/000653/2022-2023 | 550/DW/22-23 | 13/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.43 | 0 | 0
3067 | Burdwan Division | Durgapur Sub-DIvision | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | VCH/001555/2021-2022 | 1194/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0
3068 | Burdwan Division | Durgapur Sub-DIvision | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
3069 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection for Bhatakul PWSS Zone-2, PH-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00309/2024-2025 |  | 19/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 11.79 | 0 | 0
3070 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augmentation of Bhatakul (Zone-I) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000620/2022-2023 | 2093/CMD | 08/09/2022 | 30 | CHOUDHURY ENTERPRISE | 10.82 | 0 | 1
3071 | Central Mechanical | Durgapur Sub-DIvision | Restoration of power line for New Well No. 1 at Bhatakul (Zone - I) Water Supply Scheme, under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000781/2022-2023 | 1370/CMSD - I | 30/12/2022 | 15 | CHOUDHURY ENTERPRISE | 1.66 | 0 | 1
3072 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for the work of Sinking of 250 x 150 mtr deapth by DR Rig and supplying and laying of UPVC pipe line (LDS) and construction of temporary KIOSK for arrangement of electrification of Tube well at BHALKI under BHALKI PWSS , Block- Ausgram-II, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000055/2024-2025 | 772/DWSD | 06/06/2024 | 360 | EVEREST INFRATECH INC | 64.56 | 0 | 5
3073 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of augmentation BHALKI Piped Water Supply Scheme at Bhalki (Part), Chandipur (Part), Samantapara (Part), Telota (Part) & Abhirampuri (Part) village, habitation, Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000006/2022-2023 | 1907/BWD | 07/04/2022 | 30 | ROY CONSTRUCTION | 49.52 | 0 | 1
3074 | Burdwan Division | Durgapur Sub-DIvision | Construction of Drain and restoration of connection for Augmentation of BHALKI W/S Scheme , Block- Ausgram-II, under Durgapur (Burdwan North)Sub Division Burdwan Division, P.H.E. Dte. [SL-B] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000121/2022-2023 | 334/DSD | 27/06/2022 | 30 | TAUSIF HOSSAIN MONDAL | 1.88 | 0 | 1
3075 | Burdwan Division | Durgapur Sub-DIvision | Making structure with GI pipe for provision of joining and laying of pipeline near Abhirampur branch Canal for Bhalki and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-H] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000134/2022-2023 | 349/DSD | 30/06/2022 | 45 | PARTHA RAY | 1.9 | 0 | 1
3076 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration work due to laying of 160 mm, 140 mm dia HDPE pipe along with Bardhaman Kalna Road from 31.00kmp to 32.00 kmp with sand filling, GSB, WBM & BM and shoulder portion jhama with moorum consolidation of Augmentation of Satgachia Zone-II water supply scheme "JAL JEEVAN MISSION" under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00097/2023-2024 | 195/JJM | 31/05/2023 | 0 | EXECUTIVE ENGINEER PWD BURDWAN DIVISION | 27.42 | 0 | 0
3077 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of SATGACHIA (Zone-II) Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 400 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation under Memari ¿ II Block, District - Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000005/2022-2023 | 1900/BWD | 07/04/2022 | 1031 | G.B. CONSTRUCTION & CO. | 391.54 | 0 | 100
3078 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline & providing Functional Household Tap Connection (350 Nos. FHTC) from existing distribution system within the command are of SATGACHIA Zone - II Piped W/S. Scheme at (Bohar, Jakra, Raibati) Mouza (14 Nos. Habitation) under Memari - II Block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000005/2023-2024 | 1681/BWD | 10/04/2023 | 45 | G.B. CONSTRUCTION & CO. | 39.5 | 0 | 100
3079 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Satgachia (Zone-I) & (Zone-II) W/S Scheme under Memari-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.4. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000492/2021-2022 | 179/BSD | 31/01/2022 | 30 | RADIANT | 4.21 | 0 | 1
3080 | Burdwan Division | Burdwan Sadar Sub-Division | Relaying of damaged pipeline of 90mm HDPE pipeline for FHTC work & shifiting of sluice valve chamber for Road culvert work from Zilla parisad at Satgachia zone-II Piped Water Supply Scheme within Memari-II block under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000510/2024-2025 | 1857/BSD | 22/08/2024 | 30 | D.M. ENTERPRISE | 0.93 | 0 | 100
3081 | Burdwan Division | Burdwan Sadar Sub-Division | Replacement of Tube-well & Rising main at HEAD TW site for Aug. of PARHATI, SRIDHARPUR, SATGACHIA ZONE-I, SATGACHIA ZONE-II, Piped Water Supply Scheme within MEMARI-II Block under Burdwan Divn., PHE. Dte. District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000973/2023-2024 | 24/BWD | 03/01/2024 | 637 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 54.2 | 0 | 90
3082 | Burdwan Division | Burdwan Sadar Sub-Division | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001269/2024-2025 | 848/BWD | 05/03/2025 | 120 | PROJECT INDIA | 394.29 | 0 | 0
3083 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration work of Debipur-Bulbulitala Road from 15.00 km to 17.10 km (in stretches) damage due to laying of underground water pipeline by PHE with box cutting and jhama with moorum consolidation under Kalna Highway Sub-Division of Burdwan South Highway Division, P.W. Roads Dte. during the Year 2023-2024. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01173/2023-2024 | 1079/JJM | 20/12/2023 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 5.51 | 0 | 0
3084 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Satgachia (Zone-I) & (Zone-II) W/S Scheme under Memari-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.4. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000492/2021-2022 | 179/BSD | 31/01/2022 | 30 | RADIANT | 4.21 | 0 | 1
3085 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch rooms & Rising main at different TW site for SATGACHIA (Zone-I) Piped Water Supply Scheme under Memari - II Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000535/2023-2024 | 3632/BWD | 21/08/2023 | 60 | ROY ASSOCIATE | 9.08 | 0 | 100
3086 | Burdwan Division | Burdwan Sadar Sub-Division | Replacement of Tube-well & Rising main at HEAD TW site for Aug. of PARHATI, SRIDHARPUR, SATGACHIA ZONE-I, SATGACHIA ZONE-II, Piped Water Supply Scheme within MEMARI-II Block under Burdwan Divn., PHE. Dte. District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000973/2023-2024 | 24/BWD | 03/01/2024 | 637 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 54.2 | 0 | 90
3087 | Burdwan Division | Burdwan Sadar Sub-Division | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001269/2024-2025 | 848/BWD | 05/03/2025 | 120 | PROJECT INDIA | 394.29 | 0 | 0
3088 | Burdwan Division | Burdwan Sadar Sub-Division | Interconnection between Raising Main to OHR & OHR to distribution System with bypass arrangement for Palason Water Supply Scheme within Raina-I Block under Burdwan Division, PHE Dte._2ND CALL Gr.E. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000467/2021-2022 | 278/BSD | 15/02/2022 | 30 | S.S. ENTERPRISE | 3.23 | 0 | 1
3089 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of concrete road and rest portion of Boundary Wall at Head Works Site of PALASON Water Supply Scheme under Raina-I Block of Burdwan Division,PHE Dte(Length-48.00 Mtr,Col-16 Nos)[Front Side]Gr.F. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000490/2021-2022 | 279/BSD | 15/02/2022 | 45 | NEW MANGES INDUSTRIAL CORPORATION | 4.12 | 0 | 1
3090 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of PALASON piped water supply scheme at Raina-I Block under Burdwan Division, PHE Dte._2nd call. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000678/2020-2021 | 1409/BWD | 18/02/2021 | 60 | S.S. ENTERPRISE | 72.41 | 19.3 | 1
3091 | Burdwan Division | Burdwan Sadar Sub-Division | Hire & fuel charges of vehicle (Car No.-WB-41J-6795) for the office of the Deputy Superintending Engineer, Central Circle, PHE Dte. for the month of March to May'23. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/00461/2023-2024 | 430/JJM | 25/07/2023 | 0 | MD HASIN | 1.04 | 0 | 0
3092 | Burdwan Division | Burdwan Sadar Sub-Division | Hire & fuel charges of vehicle (Car No.-WB-04H-9111) for the office of the Superintending Engineer, Central Circle, PHE Dte. for the month of December'22 & January'23. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/00469/2022-2023 | 1116/JJM | 27/02/2023 | 0 | SOURAV JANA | 0.8 | 0 | 0
3093 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC in Chakundi, Nabastha & Saligram village for 100% coverage in Sajal Gram from existing distribution system within NABASTHA PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000013/2023-2024 | 1728/BWD | 13/04/2023 | 30 | KAUSHIK RAY | 23.96 | 0 | 100
3094 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nabastha Piped Water Supply Scheme at Saligram (9 Nos Habitation) Village (Mouza), Burdwan-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000040/2021-2022 | 3447/BWD | 29/06/2021 | 30 | PAL CONSTRUCTION | 19.73 | 0 | 1
3095 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall at Head works site of NABASTHA Piped Water Supply Scheme in Burdwan-II Block under Burdwan Division, PHE Dte. (Length - 154 Mtr., 69 Nos Column). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000097/2022-2023 | 2742/BWD | 08/06/2022 | 30 | MOYAZZEM CONSTRUCTION | 10.54 | 0 | 1
3096 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of distribution system of different damaged section at Begut, Nabastha & Palsha village regarding smooth running FHTC work within Nabastha PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000136/2023-2024 | 784/BSD | 28/04/2023 | 30 | D.M. ENTERPRISE | 0.95 | 0 | 100
3097 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC from existing distribution pipe line system within command area of Nabastha Piped W/S. Scheme at Chakundi- Mouza, Bardhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000162/2022-2023 | 3138/BWD | 19/07/2022 | 30 | BABUL SK | 11.86 | 0 | 1
3098 | Burdwan Division | Burdwan Sadar Sub-Division | Different type of works releted at head work side (Internal pathways , Land-Development, repair of pump house and drain) under Nabastha PWSS under Burdwan-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000291/2024-2025 | 1272/BSD | 12/07/2024 | 173 | M/S PALASH BISWAS | 4.77 | 0 | 100
3099 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC for 100% coverage at Palsha (30 nos) & Begut (13nos) and special repairing of Nabastha, Begut & Palsha village for Nabastha Piped W/S scheme , Bardhhaman-II Dev. Block under Burdwan Division, PHE Dte" Gr.C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000366/2022-2023 | 1405/BSD | 10/08/2022 | 212 | M/S ASHA CONSTRUCTION | 4.71 | 0 | 100
3100 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of NABASTHA piped water supply scheme at Begut, Bodhpur, Chakundi, Nabastha & Palsha village, Burdwan-II Block under Burdwan Division, PHE Dte.[Tr No.-65/BWD/20-21] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000385/2020-2021 | 5003/BWD | 10/12/2020 | 90 | M/S ASHA CONSTRUCTION | 88.6 | 18.24 | 1
3101 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000416/2021-2022 | 385/BWD | 20/01/2022 | 30 | BISWAS ENTERPRISE | 11.97 | 0 | 100
3102 | Burdwan Division | Burdwan Sadar Sub-Division | Speacial repairing and replace damaged pipe line from Nabastha bus stand to saligram & chakundi village of Nabastha piped water supply scheme at Bardhhaman-II Block under Burdwan Div., PHE Dte.Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000643/2021-2022 | 467/BSD | 21/03/2022 | 30 | SETH ENTERPRISE | 4.82 | 0 | 1
3103 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of interconnection between 4th tube well to OHR for Nabastha Water Supply Scheme within Burdhaman-II Block , under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000807/2022-2023 | 430/BSD | 15/03/2023 | 30 | D.M. ENTERPRISE | 0.91 | 0 | 100
3104 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Ground Water Based Piped Water Supply Scheme for NABASTHA, Block:Burdwan-II under Burdwan Division, P.H.E Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000987/2024-2025 | 1908/BSD | 28/08/2024 | 15 | MEASURE LAND | 0.78 | 0 | 0
3105 | Burdwan Division | Central Mechanical Sub-Division | Augmentation of KALERA Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 350 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including construction of switch-rooms(5.40mx3.6m) & Boundary walls for new TW site under Jamalpur Block, District:- Purba-Burdwan. [Treated as "New Scheme in place of Augmentation" vide Corrigendum Notice No. 1544/CC, dated 02.08.2022.] | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000256/2022-2023 | 3855/BWD | 07/09/2022 | 846 | M/S MAA TARA CONSTRUCTION | 302.71 | 0 | 100
3106 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000053/2022-2023 | 5522/BWDQ | 23/12/2022 | 0 | Resource Division | 8.88 | 0 | 0
3107 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000118/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 12.9 | 0 | 0
3108 | Central Mechanical | Central Mechanical Sub-Division | New Service Connection Charges for Kalera W/S Scheme PH-1 | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00002/2022-2023 | 25 | 02/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.51 | 0 | 0
3109 | Central Mechanical | Central Mechanical Sub-Division | New Service Connection Charges for Kalera W/S Scheme PH-2 | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00003/2022-2023 | 26 | 02/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.9 | 0 | 0
3110 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Kalera Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000609/2022-2023 | 3115/CMD | 23/11/2022 | 30 | P.K. ENGINEERING | 11.07 | 0 | 80
3111 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Kalera Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000610/2022-2023 | 3116/CMD | 23/11/2022 | 30 | DUTTA ENTERPRISE | 11.08 | 0 | 80
3112 | Central Drilling | Central Mechanical Sub-Division | Hiring of Diesel driven motor cab (BS-III & above) having contract carriage permit along with driver for the office of the Executive Engineer, CDD, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000004/2023-2024 | 45/S&WSD | 26/04/2023 | 7 | ASHUTOSH DAS & CO | 0.87 | 0 | 83
3113 | Central Drilling | Central Mechanical Sub-Division | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT KELERA W/S (TW-I) SCHEME, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000287/2022-2023 | 320/CMSD-I | 21/07/2022 | 15 | C.M. ENTERPRISE | 1.88 | 0 | 1
3114 | Central Drilling | Central Mechanical Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR KALERA W/S (TW-I) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000288/2022-2023 | 319/CMSD-I | 21/07/2022 | 15 | C.M. ENTERPRISE | 1.74 | 0 | 1
3115 | Central Drilling | Central Mechanical Sub-Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KALERA W/S (TW-I) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000289/2022-2023 | 316/CMSD-I | 22/07/2022 | 15 | C.M. ENTERPRISE | 3.28 | 0 | 1
3116 | Central Drilling | Central Mechanical Sub-Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KALERA W/S SCH (TW-II) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000290/2022-2023 | 317/CMSD-I | 22/07/2022 | 15 | C.M. ENTERPRISE | 3.28 | 0 | 1
3117 | Central Drilling | Central Mechanical Sub-Division | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT KALERA W/S SCH (TW-II) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000292/2022-2023 | 331/CMSD-I | 15/07/2022 | 15 | C.M. ENTERPRISE | 1.88 | 0 | 1
3118 | Central Drilling | Central Mechanical Sub-Division | Additional Transportation of Departmental rig unit no. Super RR with compressor and pump unit from Kalera PWSS under CDD, PHE dte. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000307/2022-2023 | 532/CMSD-II(D) | 01/12/2022 | 7 | PADMA ENGINEERING & CO. | 0.75 | 0 | 1
3119 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crews for construction of TW (250mm x 150mm) by Departmental rig machine for kalera WS (TW-II), Jamalpur block purba Burdwan, CDD, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000308/2022-2023 | 330/CMSD-I(D) | 15/07/2022 | 15 | C.M. ENTERPRISE | 1.74 | 0 | 1
3120 | Burdwan Division | Durgapur Sub-DIvision | Augmentation of BANPAS KAMARPARA Piped Water Supply Scheme (Ambana Mouza) with LDS, FHTC and Construction of Pump House at 4th TW site under Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-B]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000102/2023-2024 | 2261/BWD | 18/05/2023 | 60 | M/S K.P. CONSTRUCTION | 91.92 | 0 | 100
3121 | Burdwan Division | Durgapur Sub-DIvision | Augmentation of BANPAS KAMARPARA Piped Water Supply Scheme (Haribati & Chandai Mouza) with LDS & FHTC within Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-E]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000103/2023-2024 | 2262/BWD | 18/05/2023 | 60 | M/S K.P. CONSTRUCTION | 80.02 | 0 | 80
3122 | Burdwan Division | Durgapur Sub-DIvision | Sinking of additional 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 4th & 5th Tube well Site for Augmentation of BONPAS-KAMARPARA Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000141/2022-2023 | 3031/BWD | 07/07/2022 | 45 | B.K. ENTERPRISE | 28.13 | 0 | 1
3123 | Burdwan Division | Durgapur Sub-DIvision | Repairing of Switch room cum chlorine room with sanitary and water supply arrangement (P.H-2) at 2nd Tubewell Site for Bonpas-Kamarpara and its adjoining mouza's water supply scheme under Durgapur Sub-Division, P.H.E Dte. Block:-Bhatar, Dist:Purba Bardhaman. [Gr.-F] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000274/2022-2023 | 499/DSD | 12/08/2022 | 30 | SUPRIYA RAY | 2.03 | 0 | 100
3124 | Burdwan Division | Durgapur Sub-DIvision | Augmentation of BONPAS KAMARPARA Piped Water Supply Scheme (Banpas Mouza) with LDS, Rising main, FHTC and construction of Boundary wall for existing TW site under Bhatar Block, District:- Purba-Burdwan. (PART - A) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000376/2023-2024 | 3110/BWD | 19/07/2023 | 120 | R.G. INFRASTRUCTURE | 389.91 | 0 | 80
3125 | Burdwan Division | Durgapur Sub-DIvision | Augmentation of BANPAS Piped Water Supply Scheme (Mohanpur Mouza) with LDS & FHTC under Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-C]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000713/2022-2023 | 888/BWD | 01/03/2023 | 60 | KOUSIK MALLICK | 104.59 | 0 | 100
3126 | Burdwan Division | Durgapur Sub-DIvision | Augmentation of BANPAS Piped Water Supply Scheme (Dhandalsa Mouza) with LDS & FHTC and construction of Pump House at 4th TW site under Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-F]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000716/2022-2023 | 891/BWD | 01/03/2023 | 60 | DEY NIRMAN | 71.08 | 0 | 100
3127 | Burdwan Division | Durgapur Sub-DIvision | Construction of 600 cum capacity 20 mtr staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for Bonpass-Kamarpara & its adjoining mouzas water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000727/2021-2022 | 3655/BWD | 14/07/2021 | 180 | ASHOK MITRA | 107 | 0 | 1
3128 | Burdwan Division | Durgapur Sub-DIvision | Augmentation of BANPAS Piped Water Supply Scheme (Narayanpur Mouza) with LDS, FHTC and Construction of Pump House at 4th TW site under Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-D]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000728/2022-2023 | 1029/BWD | 09/03/2023 | 60 | SARKAR AGENCY | 111.93 | 0 | 100
3129 | Central Mechanical | Durgapur Sub-DIvision | Illumination arrangement and miscelleneous works at Bonpas Kamarpara water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000406/2024-2025 | 2785/CMD | 01/10/2024 | 60 | CINZANO | 14.08 | 0 | 50
3130 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 4 at BonpassKamarpara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000764/2022-2023 | 3328/CMD | 12/12/2022 | 30 | P.K. ENGINEERING | 10.06 | 0 | 80
3131 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 5 at BonpassKamarpara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000765/2022-2023 | 3329/CMD | 12/12/2022 | 30 | CHOUDHURY ENTERPRISE | 10.09 | 0 | 100
3132 | Burdwan Division | Burdwan Sadar Sub-Division | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000003/2025-2026 | 1116/BWD | 03/04/2025 | 120 | SOFIQUL ISLAM | 176.89 | 0 | 0
3133 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000440/2024-2025 | 305/AE/HQ | 31/05/2024 | 61 | SOURAV JANA | 0.8 | 0 | 0
3134 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000505/2024-2025 | 546/AE/HQ | 01/08/2024 | 61 | SOURAV JANA | 0.8 | 0 | 0
3135 | Burdwan Division | Burdwan Sadar Sub-Division | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000653/2023-2024 | 4076/BWD | 13/09/2023 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 0 | 100
3136 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.10.2024 to 30.11.2024] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000706/2024-2025 | 822/AE/HQ | 01/10/2024 | 61 | SOURAV JANA | 0.8 | 0 | 0
3137 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KUCHUT & NOAHATI Piped Water Supply Scheme under Memari - II Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000750/2022-2023 | 1172/BWD | 14/03/2023 | 1113 | NATIONAL CONSTRUCTION | 831.75 | 0 | 99
3138 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000845/2023-2024 | 1759/BSD | 28/07/2023 | 66 | MD HASIN | 0.85 | 0 | 0
3139 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.12.2024 to 31.01.2025] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000898/2024-2025 | 1011/AE/HQ | 29/11/2024 | 61 | SOURAV JANA | 0.8 | 0 | 0
3140 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2025 to 31.03.2025] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001156/2024-2025 | 184/AE/HQ | 31/01/2025 | 59 | SOURAV JANA | 0.8 | 0 | 0
3141 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001203/2023-2024 | 41/AE/HQ | 29/01/2024 | 60 | SOURAV JANA | 0.8 | 0 | 50
3142 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001229/2023-2024 | 232/AE/HQ | 28/03/2024 | 61 | SOURAV JANA | 0.8 | 0 | 0
3143 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2025 to 31.05.2025] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001403/2024-2025 | 454/AE/HQ | 28/03/2025 | 61 | SOURAV JANA | 0.8 | 0 | 0
3144 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000072/2022-2023 | 1269/BWD | 17/03/2023 | 0 | Resource Division | 14.2 | 0 | 0
3145 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000466/2023-2024 | 3990/BWD | 08/09/2023 | 0 | Resource Division | 1.7 | 0 | 0
3146 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000674/2023-2024 | 5051/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3147 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Kuchut PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00778/2023-2024 | BP-2023-24-77 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.87 | 0 | 0
3148 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Kuchut PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00779/2023-2024 | BP-2023-24-78 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.83 | 0 | 0
3149 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kuchut Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000050/2023-2024 | 2512/CMD | 02/06/2023 | 30 | CHOUDHURY ENTERPRISE | 29.4 | 0 | 50
3150 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0
3151 | Central Mechanical | Burdwan Sadar Sub-Division | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000564/2024-2025 | 3103/CMD | 11/12/2024 | 60 | S DUTTA | 15.06 | 0 | 0
3152 | Burdwan Division | Burdwan Sadar Sub-Division | BICHKHARA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch-rooms & boundary walls at different TW site under KHANDOGHOSH Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000638/2022-2023 | 253/BWD | 16/01/2023 | 180 | KOUSIK MALLICK | 121.67 | 0 | 90
3153 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BICHKHARA & TELUN W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001096/2024-2025 | 434/BWD | 20/01/2025 | 182 | KOUSIK MALLICK | 108.55 | 0 | 50
3154 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000077/2022-2023 | 1265/BWD | 17/03/2023 | 0 | Resource Division | 2.71 | 0 | 0
3155 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000098/2022-2023 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.14 | 0 | 0
3156 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000711/2023-2024 | 5042/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3157 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Bichkhara W/S Scheme TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00683/2023-2024 | BP-2023-24-29 | 22/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.61 | 0 | 0
3158 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Bichkhara W/S Scheme TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00684/2023-2024 | BP-2023-24-30 | 22/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.64 | 0 | 0
3159 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bichkhara Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000042/2023-2024 | 2494/CMD | 01/06/2023 | 30 | CONCORD ENGINEERING | 28.89 | 0 | 98
3160 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0
3161 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & delivery of standby Submersible pumping machinery & automatic Chlorinator for Bichkhara & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001408/2023-2024 | 149/CMSD | 22/01/2024 | 15 | CHOUDHURY ENTERPRISE | 1.76 | 0 | 100
3162 | Burdwan Division | Durgapur Sub-DIvision | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period May'2024 to July'2024] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000255/2024-2025 | 369/DSD | 30/04/2024 | 78 | MD HASIN | 1 | 0 | 0
3163 | Burdwan Division | Durgapur Sub-DIvision | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
3164 | Burdwan Division | Durgapur Sub-DIvision | PUNSUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANDOGOSH Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000637/2022-2023 | 162/BWD | 11/01/2023 | 365 | TIRUPATI ENTERPRISES | 278.54 | 0 | 75
3165 | Burdwan Division | Durgapur Sub-DIvision | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day [Period February'2024 to April'2024] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001233/2023-2024 | 91/DSD | 31/01/2024 | 78 | MD HASIN | 1 | 0 | 0
3166 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000076/2022-2023 | 1254/BWD | 17/03/2023 | 0 | Resource Division | 4.93 | 0 | 0
3167 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000104/2022-2023 | 1634/BWD | 06/04/2023 | 0 | Resource Division | 0.76 | 0 | 0
3168 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000704/2023-2024 | 5039/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3169 | Central Mechanical | Durgapur Sub-DIvision | Shifting of 25KVA DTR at Punshur Water Supply Scheme | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00608/2023-2024 | BP-2023-24-17 | 02/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.88 | 0 | 0
3170 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges of Punshur W/S Scheme TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00676/2023-2024 | BP-2023-24-21 | 21/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.29 | 0 | 0
3171 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges of Punshur W/S Scheme TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00677/2023-2024 | BP-2023-24-22 | 21/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.8 | 0 | 0
3172 | Central Mechanical | Durgapur Sub-DIvision | Supply & installation works for Punsur PWSS. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02564/2023-2024 | BP-2023-24-547 | 20/02/2024 | 0 | M/S. SWAPAN BANERJEE | 11.87 | 0 | 0
3173 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Punsur Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000043/2023-2024 | 2495/CMD | 01/06/2023 | 30 | M/S. SWAPAN BANERJEE | 28.94 | 0 | 100
3174 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0
3175 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 1
3176 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000049/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.34 | 0 | 0
3177 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000258/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.16 | 0 | 0
3178 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000619/2023-2024 | 4886/BWD | 10/11/2023 | 0 | Resource Division | 30.36 | 0 | 0
3179 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Bhuyera PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01780/2023-2024 | BP-2023-24-285 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.3 | 0 | 0
3180 | Central Mechanical | Durgapur Sub-DIvision | New service connection for Bhuyera W/S scheme TW No-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02277/2023-2024 | BP-2023-24-312 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.52 | 0 | 0
3181 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BHUYERA Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000837/2023-2024 | 4111/CMD | 29/08/2023 | 30 | SOUNAK ENTERPRISE | 29.61 | 0 | 48
3182 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000441/2024-2025 | 307/AE/HQ | 31/05/2024 | 61 | MD HASIN | 0.8 | 0 | 0
3183 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000508/2024-2025 | 548/AE/HQ | 01/08/2024 | 61 | MD HASIN | 0.8 | 0 | 0
3184 | Burdwan Division | Burdwan Sadar Sub-Division | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000653/2023-2024 | 4076/BWD | 13/09/2023 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 0 | 100
3185 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.10.2024 to 30.11.2024] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000708/2024-2025 | 803/AE/HQ | 30/09/2024 | 61 | MD HASIN | 0.8 | 0 | 0
3186 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000845/2023-2024 | 1759/BSD | 28/07/2023 | 66 | MD HASIN | 0.85 | 0 | 0
3187 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.12.2024 to 31.01.2025] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000895/2024-2025 | 1009/AE/HQ | 29/11/2024 | 61 | MD HASIN | 0.8 | 0 | 0
3188 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2025 to 31.03.2025] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001153/2024-2025 | 185/AE/HQ | 31/01/2025 | 59 | MD HASIN | 0.8 | 0 | 0
3189 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of Conc. road, Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for MAGRA, SANUI, SATGACHIA Zone-I & NARAGOHALIA PIPED WATER SUPPLY SCHEME, Block-Memari-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001192/2024-2025 | 611/BWD | 11/02/2025 | 180 | M/S ASHA CONSTRUCTION | 354.13 | 0 | 25
3190 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001204/2023-2024 | 42/AE/HQ | 29/01/2024 | 60 | MD HASIN | 0.8 | 0 | 50
3191 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001230/2023-2024 | 233/AE/HQ | 28/03/2024 | 61 | MD HASIN | 0.8 | 0 | 0
3192 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2025 to 31.05.2025] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001404/2024-2025 | 455/AE/HQ | 28/03/2025 | 61 | MD HASIN | 0.8 | 0 | 0
3193 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000070/2022-2023 | 1251/BWD | 17/03/2023 | 0 | Resource Division | 12.34 | 0 | 0
3194 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000462/2023-2024 | 3986/BWD | 08/09/2023 | 0 | Resource Division | 8.96 | 0 | 0
3195 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000676/2023-2024 | 5080/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3196 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Magra W/S Sechem. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/02184/2023-2024 | BP-2023-24-379 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.1 | 0 | 0
3197 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Magra PWSS TW-2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/02338/2023-2024 | BP-2023-24-474 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0
3198 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0
3199 | Central Mechanical | Burdwan Sadar Sub-Division | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000564/2024-2025 | 3103/CMD | 11/12/2024 | 60 | S DUTTA | 15.06 | 0 | 0
3200 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Magra Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000650/2023-2024 | 3993/CMD | 29/08/2023 | 611 | ORIENTAL ENGINEERING CO. | 29.35 | 0 | 100
3201 | Burdwan Division | Kalna Sub-division | Different Types of work involved in connection with Augmentation of RAHATPUR (SM/16306) & LAKSHMANPUR (SM/13493) Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000176/2024-2025 | 2069/BWD | 07/06/2024 | 240 | SAIKAT RAY | 213.73 | 0 | 2
3202 | Burdwan Division | Kalna Sub-division | LAKSHAMPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER | ORD/000799/2022-2023 | 1518/BWD | 28/03/2023 | 90 | JAHAR GHOSH | 42.34 | 0 | 40
3203 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000166/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 6.59 | 0 | 0
3204 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000394/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.66 | 0 | 0
3205 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000413/2023-2024 | 3867/BWD | 01/09/2023 | 0 | Resource Division | 0.14 | 0 | 0
3206 | Central Mechanical | Kalna Sub-division | New service connection charges for Lakshampur PWSS TW-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/00752/2023-2024 | BP-2023-24-55 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.74 | 0 | 0
3207 | Central Mechanical | Kalna Sub-division | Addl. quotation for new service connection charges for Laxmanpur PWSS | Assistant Engineer | JUNIOR ENGINEER | BILL/01459/2023-2024 | BP-2023-24-157 | 11/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.54 | 0 | 0
3208 | Central Mechanical | Kalna Sub-division | New service connection for Laxmanpur PWSS PH-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/02315/2023-2024 | BP-2023-24-454 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.01 | 0 | 0
3209 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at LAKSHAMPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000124/2023-2024 | 2639/CMD | 14/06/2023 | 30 | C.M. ENTERPRISE | 20.81 | 0 | 60
3210 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0
3211 | Central Mechanical | Kalna Sub-division | Withdrawing of pump motor set due to low discharge and installation of new pump motor set at Lakshampur PH 1 water supply scheme under CMD P.H.E. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001891/2023-2024 | 363/CMSD | 28/02/2024 | 15 | C.M. ENTERPRISE | 0.67 | 0 | 0
3212 | Durgapur W/S Division | Central Mechanical Sub-Division | FOMAL WORK ORDER FOR Balance works related (Sinking of Tube Wells at Bilaspur Village, LDS, Rising Mains, FHTCs, Road restoration of Sonaiaima PWSS under Ausgram-II Block under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000221/2024-2025 | 128/DWSD | 22/01/2025 | 120 | RANADHIR SINHA | 131.08 | 0 | 30
3213 | Durgapur W/S Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000017/2024-2025 | 1724/B/DWSD | 10/12/2024 | 0 | Resource Division | 7.42 | 0 | 0
3214 | Burdwan Division | Central Mechanical Sub-Division | SONAIAIMA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under AUSGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000639/2022-2023 | 254/BWD | 16/01/2023 | 806 | RANADHIR SINHA | 360.13 | 0 | 100
3215 | Burdwan Division | Central Mechanical Sub-Division | Repairing and restore pipe line damaged by newly laying of pipeline at different location of Somai village ( East Part) SONAIAIMA and its adjoining mouza's Piped W/S Scheme (NEW) at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000673/2023-2024 | 721/DSD | 21/09/2023 | 15 | RANADHIR SINHA | 0.86 | 0 | 100
3216 | Burdwan Division | Central Mechanical Sub-Division | Repairing and restore pipe line damaged by newly laying of pipeline at different location of Somai village (West Part) SONAIAIMA and its adjoining mouza's Piped W/S Scheme (NEW) at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000675/2023-2024 | 722/DSD | 21/09/2023 | 15 | RANADHIR SINHA | 0.87 | 0 | 100
3217 | Burdwan Division | Central Mechanical Sub-Division | Ground development at Head Work site of SONAIAIMA Piped water supply Scheme, block ¿ Ausgram - I within Durgapur Sub Division under Burdwan Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000676/2023-2024 | 723/DSD | 21/09/2023 | 30 | SINHA BROTHERS | 0.94 | 0 | 100
3218 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000078/2022-2023 | 1255/BWD | 17/03/2023 | 0 | Resource Division | 8.72 | 0 | 0
3219 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000093/2022-2023 | 1629/BWD | 06/04/2023 | 0 | Resource Division | 0.41 | 0 | 0
3220 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000635/2023-2024 | 5091/BWD | 23/11/2023 | 0 | Resource Division | 21.7 | 0 | 0
3221 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Sonaiaima PWSS TW-1 | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00720/2023-2024 | BP-2023-24-46 | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.13 | 0 | 0
3222 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Sonaiaima PWSS TW-2 | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00775/2023-2024 | BP-2023-24-99 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.06 | 0 | 0
3223 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sonaiaima Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000041/2023-2024 | 2493/CMD | 01/06/2023 | 30 | CHATTERJEE ENTERPRISE | 27.71 | 0 | 40
3224 | Burdwan Division | Central Mechanical Sub-Division | AKHARA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000011/2023-2024 | 1725/BWD | 13/04/2023 | 1205 | MANASH GHOSH | 455.23 | 0 | 78
3225 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000179/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 14.84 | 0 | 0
3226 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000493/2023-2024 | 4017/BWD | 08/09/2023 | 0 | Resource Division | 23.3 | 0 | 0
3227 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000630/2023-2024 | 4882/BWD | 10/11/2023 | 0 | Resource Division | 26 | 0 | 0
3228 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Akhra PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/00756/2023-2024 | BP-2023-24-56 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.96 | 0 | 0
3229 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Akhra PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/00757/2023-2024 | BP-2023-24-57 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.39 | 0 | 0
3230 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0
3231 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Akhra Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000135/2023-2024 | 2760/CMD | 28/06/2023 | 275 | CHOUDHURY ENTERPRISE | 27.73 | 0 | 40
3232 | Central Mechanical | Central Mechanical Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of Assistant Engineer, under C.M.D. P.H.E. Dte. w.e.f.- 01/11/2023 to 31/12/2023. [Under JJM Works]. | Assistant Engineer | Junior Engineer | ORD/001302/2023-2024 | 859/CMSD | 30/10/2023 | 61 | SUBRATA BHADRA | 0.8 | 0 | 100
3233 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAGRAM & KHEJURHATI Piped Water Supply Scheme under Khandaghosh Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000083/2023-2024 | 2080/BWD | 04/05/2023 | 698 | KHAN ENTERPRISE | 688.15 | 0 | 58
3234 | Burdwan Division | Durgapur Sub-DIvision | Balance work for providing Functional Household Tap Connection (FHTC) within the command area KHEJURHATI & GUIR W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001217/2024-2025 | 724/BWD | 24/02/2025 | 120 | ROY CONSTRUCTION | 153.99 | 0 | 0
3235 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000107/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 2.84 | 0 | 0
3236 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000195/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 2.96 | 0 | 0
3237 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000724/2023-2024 | 5276/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
3238 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Khejurhati PWSS TW 2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01532/2023-2024 | BP-2023-24-200 | 17/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.02 | 0 | 0
3239 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Khejurhati PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01540/2023-2024 | BP-2023-24-207 | 30/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.78 | 0 | 0
3240 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 10
3241 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khejurhati Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000390/2023-2024 | 3662/CMD | 01/08/2023 | 30 | SINHA ELECTRICALS | 28.98 | 0 | 98
3242 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 1
3243 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000054/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 73.04 | 0 | 0
3244 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000289/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.34 | 0 | 0
3245 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000615/2023-2024 | 4878/BWD | 10/11/2023 | 0 | Resource Division | 30.36 | 0 | 0
3246 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Jalkandar PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01781/2023-2024 | BP-2023-24-290 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.59 | 0 | 0
3247 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Jalikandar W/S Scheme for PH No-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01824/2023-2024 | BP-2023-24-330 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.52 | 0 | 0
3248 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JALKANDAR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000916/2023-2024 | 4180/CMD | 29/08/2023 | 30 | SOUNAK ENTERPRISE | 28.48 | 0 | 96
3249 | Central Mechanical | Durgapur Sub-DIvision | Supply & Delivery of Submersible Pumping Machinery for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [Block- AUSGRAM -2] under CMD, PHE Dte.,Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001623/2023-2024 | 349/DIC/BMSD(D) | 22/12/2023 | 7 | H.K. DAS & CO. | 0.8 | 0 | 0
3250 | Central Mechanical | Durgapur Sub-DIvision | Supply & delivery of the following Electrical & Mechanical accessories for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [ Block- AUSGRAM-2) under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001625/2023-2024 | 23/DIC/BMSD(D) | 05/01/2024 | 7 | H.K. DAS & CO. | 0.93 | 0 | 0
3251 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, and piping works for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001628/2023-2024 | 40/DIC/BMSD(D) | 15/01/2024 | 15 | H.K. DAS & CO. | 0.38 | 0 | 0
3252 | Central Mechanical | Durgapur Sub-DIvision | Supply & delivery of Electrical & Mechanical accessories for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.· Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001631/2023-2024 | 45/DIC/BMSD(D) | 19/01/2024 | 7 | H.K. DAS & CO. | 0.63 | 0 | 0
3253 | Central Mechanical | Durgapur Sub-DIvision | Supply & Delivery of actuator valve for Tube Well No: 02 at JALKHANDAR Water Supply Scheme [Block- AUSGRAM -2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001634/2023-2024 | 100/DIC/BMSD(D) | 12/02/2024 | 7 | H.K. DAS & CO. | 0.97 | 0 | 0
3254 | Burdwan Division | Burdwan Sadar Sub-Division | BARA PALASHAN Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000111/2023-2024 | 2300/BWD | 19/05/2023 | 867 | MLG CONSTRUCTION | 358.59 | 0 | 65
3255 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-06-2024 to 31-08-2024" | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000228/2024-2025 | 918/BSD | 28/05/2024 | 92 | SK. ASFIA | 1.2 | 0 | 60
3256 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for Supply of one No.Diesel Driven Ambassador Car No. WB:41H-4009 on hire basis for the office of the Assistant Engineer,Burdwan Sub-Division,PHE Dte(Period from 01-03-2025 to 31.05.2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/001407/2024-2025 | 457/BSD | 28/02/2025 | 90 | SK. ASFIA | 1.2 | 0 | 100
3257 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000234/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 23.4 | 0 | 0
3258 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000501/2023-2024 | 4025/BWD | 08/09/2023 | 0 | Resource Division | 6.08 | 0 | 0
3259 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000653/2023-2024 | 5099/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3260 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection at Barapalasan PWSS TW -2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | BILL/02331/2023-2024 | BP-2023-24-448 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.18 | 0 | 0
3261 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection at Barapalasan PWSS TW -1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | BILL/02332/2023-2024 | BP-2023-24-447 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.9 | 0 | 0
3262 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0
3263 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Barapalashan Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000711/2023-2024 | 4022/CMD | 29/08/2023 | 30 | MITRA ENTERPRISE | 29.26 | 0 | 100
3264 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMSUNDARPUR & BELGRAM Piped Water Supply Scheme under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000086/2023-2024 | 2147/BWD | 10/05/2023 | 730 | MAHMOOD ASSOCIATES PVT. LTD. | 1172.24 | 0 | 78
3265 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000034/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 53 | 0 | 0
3266 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000328/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.76 | 0 | 0
3267 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new electric service connection at Shyamsundarpur PH NO.-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01743/2023-2024 | BP-2023-24-246 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.34 | 0 | 0
3268 | Central Mechanical | Durgapur Sub-DIvision | New service connection for SHYAMSUNDARPUR PWSS TW 2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02447/2023-2024 | BP-2023-24-522 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4 | 0 | 0
3269 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
3270 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SHYAMSUNDARPUR Water Supply Scheme [ Block- GALSI-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000838/2023-2024 | 4112/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 27.73 | 0 | 48
3271 | Burdwan Division | Burdwan Sadar Sub-Division | Additional laying distribution system work for KUSHA W/S. Scheme under Burdwan - II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000434/2023-2024 | 3386/BWD | 03/08/2023 | 60 | RICK CONSTRUCTION | 39.84 | 0 | 100
3272 | Burdwan Division | Burdwan Sadar Sub-Division | KUSHA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Bardhaman-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000671/2022-2023 | 389/BWD. | 31/01/2023 | 791 | SYED KHORSED ALAM | 250.51 | 0 | 75
3273 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000013/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.48 | 0 | 0
3274 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000069/2022-2023 | 1250/BWD | 17/03/2023 | 0 | Resource Division | 6.52 | 0 | 0
3275 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000726/2023-2024 | 5270/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
3276 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection charges for Kusha W/S Scheme TW-I | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00573/2023-2024 | BP-2023-24-9 | 12/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.07 | 0 | 0
3277 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection charges for Kusha W/S Scheme TW-II | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00574/2023-2024 | BP-2023-24-10 | 12/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.41 | 0 | 0
3278 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kusha Water Supply Scheme [Block- Burdwan-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000034/2023-2024 | 2470/CMD | 30/05/2023 | 30 | SUBRATA BHADRA | 28.71 | 0 | 60
3279 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 12
3280 | Central Mechanical | Burdwan Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of Assistant Engineer, under C.M.D. P.H.E. Dte. w.e.f.-01/07/2023 to 31/08/2023. [Under JJM Works]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000321/2023-2024 | 523/A/CMSD-I | 28/06/2023 | 62 | SUBRATA BHADRA | 0.79 | 0 | 50
3281 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & delivery of standby Submersible pumping machinery & automatic Chlorinator for Kusha & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001412/2023-2024 | 150/CMSD | 22/01/2024 | 15 | SUBRATA BHADRA | 1.76 | 0 | 100
3282 | Burdwan Division | Burdwan Sadar Sub-Division | MALKITA Single Village Scheme with sinking of Tube-well & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000054/2023-2024 | 1933/BWD | 24/04/2023 | 90 | GHOSH CONSTRUCTION | 49.99 | 0 | 100
3283 | Burdwan Division | Burdwan Sadar Sub-Division | MALKITA Single Village Scheme with LDS, Rising Main and FHTC under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000158/2023-2024 | 2454/BWD | 31/05/2023 | 90 | M/S PURBASHA | 71.78 | 0 | 72
3284 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
3285 | Burdwan Division | Burdwan Sadar Sub-Division | Installation of Sluice Valve, Washout Valve to regulate water supply with Road Restoration work, Extension pipeline and providing FHTC for MALKITA Piped Water Supply Scheme, Block- Burdwan-I, under Burdwan sub Division within Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001163/2024-2025 | 552/BWD | 04/02/2025 | 90 | M/S PURBASHA | 9.62 | 0 | 0
3286 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000442/2023-2024 | 3834/BWD | 01/09/2023 | 0 | Resource Division | 5.48 | 0 | 0
3287 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000677/2023-2024 | 5052/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3288 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Malkita PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00837/2023-2024 | BP-2023-24-102 | 04/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0
3289 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Malkita PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00838/2023-2024 | BP-2023-24-103 | 04/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.25 | 0 | 0
3290 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
3291 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Malkita Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000211/2023-2024 | 3067/CMD | 21/07/2023 | 30 | S.P. CONSTRUCTION | 28.96 | 0 | 100
3292 | Durgapur W/S Division | Durgapur Sub-DIvision | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.06.2025 to 31.08.2025 (3 Months). | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000042/2025-2026 | 854/DWSD | 29/05/2025 | 90 | PRAMIT CHATTERJEE | 0.41 | 0 | 0
3293 | Durgapur W/S Division | Durgapur Sub-DIvision | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-II under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.09.2024 to 28.02.2025 (6 Months)(Sl-02) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000139/2024-2025 | 1249/DWSD | 30/08/2024 | 182 | PRAMIT CHATTERJEE | 0.82 | 0 | 20
3294 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Sinking of 300 X 200mm dia Tube Well- 300 mtr.& 2 nos Trial Bore of 200 X 200mm dia Tube Well- 300 mtr at Pubar village under Chhora PWSS (JJM) Block - Ausgram -II, District:- Purba-Bardhaman, under Durgapur W/S Division , PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000169/2024-2025 | 1612/DWSD | 26/11/2024 | 60 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 34.01 | 0 | 0
3295 | Durgapur W/S Division | Durgapur Sub-DIvision | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2025 to 31.05.2025 (3 Months). | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000281/2024-2025 | 341/DWSD | 27/02/2025 | 89 | PRAMIT CHATTERJEE | 0.41 | 0 | 0
3296 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 1
3297 | Durgapur W/S Division | Durgapur Sub-DIvision | Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-II under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.03.2024 to 31.08.2024 (6 Months)(Sl-02) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000295/2023-2024 | 268/DWSD | 29/02/2024 | 6 | PRAMIT CHATTERJEE | 0.82 | 0 | 0
3298 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order work of Balance work for renovation and modification of administrative office building at PHE Complex 2nd Floor, Nababhat, P.O- Fagupur, Dist- Purba Bardhaman inconnection with Augmentation of Chhora PWSS under Aushgram-II Block. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000301/2023-2024 | 364/DWSD | 15/03/2024 | 30 | SANDIPAN SENGUPTA | 9.6 | 0 | 100
3299 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000011/2024-2025 | 1724/H/DWSD | 10/12/2024 | 0 | Resource Division | 7.83 | 0 | 0
3300 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KHANDARI & CHHORA Piped Water Supply Scheme under Ausgram II Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000735/2022-2023 | 1005/BWD | 06/03/2023 | 696 | M/S NATIONAL CONSTRUCTION | 1331.54 | 0 | 100
3301 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000083/2022-2023 | 1268/BWD | 17/03/2023 | 0 | Resource Division | 16.43 | 0 | 0
3302 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000095/2022-2023 | 1644/BWD | 06/04/2023 | 0 | Resource Division | 43.68 | 0 | 0
3303 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000639/2023-2024 | 5105/BWD | 23/11/2023 | 0 | Resource Division | 24.22 | 0 | 0
3304 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges of Chhora PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00746/2023-2024 | BP-2023-24-48 | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.21 | 0 | 0
3305 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges of Chhora PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00747/2023-2024 | BP-2023-24-47 | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.44 | 0 | 0
3306 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHHORA Water Supply Scheme [ Block- AUSGRAM-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000054/2023-2024 | 2514/CMD | 02/06/2023 | 30 | MITRA ENTERPRISE | 29.43 | 0 | 45
3307 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 03 Nos. Piped W/S. Schemes under Kalna II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000336/2024-2025 | 3016/BWD | 05/08/2024 | 20 | HORIZEN | 7.55 | 0 | 100
3308 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 2nd TW Site of KALYANPUR & its adjoining mouzas Piped Water Supply Scheme, Block ? Kalna ? II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000546/2022-2023 | 5128/BWD | 21/11/2022 | 30 | MUNSHI ENTERPRISE | 8.72 | 0 | 100
3309 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur (Part) village, Kalyan (Part) habitation of Kalyanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Part-A)[SL NO.-07] | Assistant Engineer |  | ORD/000691/2020-2021 | 57/BWD | 05/01/2021 | 15 | SETH ENTERPRISE | 4.86 | 4.86 | 1
3310 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur (Part) village (Kalyanpur Part habitation) of Kalyanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.(Part-B)[SL NO.-08] | Assistant Engineer |  | ORD/000744/2020-2021 | 58/BWD | 05/01/2021 | 15 | BISHWAJIT DAS | 4.86 | 4.86 | 1
3311 | Burdwan Division | Durgapur Sub-DIvision | KARJJANA [PART :-A] Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000721/2022-2023 | 955/BWD | 03/03/2023 | 60 | DHIRENDRANATH SOM | 44.51 | 0 | 100
3312 | Burdwan Division | Durgapur Sub-DIvision | KARJJANA [PART :-B] Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000722/2022-2023 | 956/BWD | 03/03/2023 | 60 | DHIRENDRANATH SOM | 45.79 | 0 | 95
3313 | Burdwan Division | Durgapur Sub-DIvision | Additional Distribution Pipeline work at KARJJANA Piped Water Supply Scheme with Rising Main, LDS & FHTC work under Bhatar Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001045/2023-2024 | 789/BWD | 27/02/2024 | 30 | DHIRENDRANATH SOM | 6.2 | 0 | 100
3314 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000081/2022-2023 | 1248/BWD | 17/03/2023 | 0 | Resource Division | 1.91 | 0 | 0
3315 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000751/2023-2024 | 5248/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0
3316 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Karjjana PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00753/2023-2024 | BP-2023-24-53 | 18/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.66 | 0 | 0
3317 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Karjjana PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00754/2023-2024 | BP-2023-24-54 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.43 | 0 | 0
3318 | Central Mechanical | Durgapur Sub-DIvision | New service connection for KARJANA PWSS, PH-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02486/2023-2024 | BP-2023-24-535 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.06 | 0 | 0
3319 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KARJJANA Water Supply Scheme [ Block-BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000061/2023-2024 | 2521/CMD | 02/06/2023 | 1031 | MITRA ASSOCIATES | 27.66 | 0 | 95
3320 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
3321 | Burdwan Division | RWS Burdwan Sub-Division | Restoration Work of damage portion of the RIDF road from Bilbari to Farakpur for PHE pipe laying work within MEMARI-II BLOCK IN THE DISTRICT OF PURBABARDHAMAN | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | BILL/00978/2024-2025 | 1052/JJM | 13/11/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 23.03 | 0 | 0
3322 | Burdwan Division | RWS Burdwan Sub-Division | BAMUNPUKUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000112/2023-2024 | 2301/BWD | 19/05/2023 | 866 | MLG CONSTRUCTION | 447.89 | 0 | 62
3323 | Burdwan Division | RWS Burdwan Sub-Division | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 183 | SK.ASFIA | 2.4 | 0 | 70
3324 | Burdwan Division | RWS Burdwan Sub-Division | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related(schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-02-2025 to 30-04-2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/001402/2024-2025 | 240/BSD | 31/01/2025 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
3325 | Burdwan Division | RWS Burdwan Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000227/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 8.19 | 0 | 0
3326 | Burdwan Division | RWS Burdwan Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000545/2023-2024 | 4299/BWD | 29/09/2023 | 0 | Resource Division | 9.65 | 0 | 0
3327 | Burdwan Division | RWS Burdwan Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000650/2023-2024 | 5112/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3328 | Central Mechanical | RWS Burdwan Sub-Division | Quotation for new service connection at Bamunpukur PWSS TW-2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | BILL/00932/2024-2025 | BP-2024-25-349 | 05/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.45 | 0 | 0
3329 | Central Mechanical | RWS Burdwan Sub-Division | New service connection for Bamunpukur PWSS of PH-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | BILL/02352/2023-2024 | BP-2023-24-471 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.81 | 0 | 0
3330 | Central Mechanical | RWS Burdwan Sub-Division | New service connection for Bamunpukur PWSS TW 1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | BILL/02439/2023-2024 | BP-2023-24-524 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.99 | 0 | 0
3331 | Central Mechanical | RWS Burdwan Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0
3332 | Central Mechanical | RWS Burdwan Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bamunpukur Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000710/2023-2024 | 4021/CMD | 29/08/2023 | 703 | DUTTA ENTERPRISE | 29.38 | 0 | 50
3333 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-05-2024 to 31-07-2024) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000108/2024-2025 | 807/BSD | 29/04/2024 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
3334 | Burdwan Division | Burdwan Sadar Sub-Division | CHAK PUROHIT Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000197/2023-2024 | 2702/BWD | 08/06/2023 | 300 | M/S PROCHESTA ENTERPRISE | 263.18 | 0 | 80
3335 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 366 | SK ALIM | 1353.91 | 0 | 25
3336 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000269/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.34 | 0 | 0
3337 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000485/2023-2024 | 4009/BWD | 08/09/2023 | 0 | Resource Division | 1.37 | 0 | 0
3338 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000661/2023-2024 | 5102/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3339 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Chakpurohit PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01527/2023-2024 | BP-2023-24-192 | 11/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.9 | 0 | 0
3340 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Chakpurohit PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01666/2023-2024 | BP-2023-24-221 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.93 | 0 | 0
3341 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
3342 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chak Purohit Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000576/2023-2024 | 3916/CMD | 21/08/2023 | 345 | P.K. ENGINEERING | 28.9 | 0 | 96
3343 | Burdwan Division | Central Mechanical Sub-Division | SHRIGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM -I Block, District:- Purba- Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000141/2023-2024 | 2385/BWD | 23/05/2023 | 365 | S.D. CONSTRUCTION | 351.47 | 0 | 43
3344 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000312/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.32 | 0 | 0
3345 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000486/2023-2024 | 4010/BWD | 08/09/2023 | 0 | Resource Division | 0.28 | 0 | 0
3346 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000760/2023-2024 | 5245/BWD | 30/11/2023 | 0 | Resource Division | 18.9 | 0 | 0
3347 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Shrigram PWSS PH-2. | Assistant Engineer | Junior Engineer | BILL/00416/2024-2025 | BP-2024-25-222 | 26/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.77 | 0 | 0
3348 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Shrigram PWSS PH-1. | Assistant Engineer | Junior Engineer | BILL/00417/2024-2025 | BP-2024-25-221 | 26/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.4 | 0 | 0
3349 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
3350 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SHRIGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000832/2023-2024 | 4109/CMD | 29/08/2023 | 30 | DUTTA ENTERPRISE | 26.96 | 0 | 100
3351 | Burdwan Division | Kalna Sub-division | Augmentation of PURBASTHALI Surface Water Supply Scheme (ZONE-3A) with LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-II Block, District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/000537/2023-2024 | 3701/BWD | 24/08/2023 | 860 | SUPRITI ENTERPRISE | 560.35 | 0 | 1
3352 | Burdwan Division | Kalna Sub-division | Work Order for "Route Survey & Prepatration of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-III (Zone-III A) (SM/15588) under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-4) | Assistant Engineer |  | ORD/001137/2023-2024 | 2079/KSD | 29/02/2024 | 45 | APEX ENGINEERING | 2.27 | 0 | 100
3353 | Burdwan Division | Kalna Sub-division | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 51
3354 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000517/2023-2024 | 3969/BWD | 08/09/2023 | 0 | Resource Division | 28.36 | 0 | 0
3355 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000763/2023-2024 | 197/BWD | 10/01/2024 | 0 | Resource Division | 6.16 | 0 | 0
3356 | Burdwan Division | Central Mechanical Sub-Division | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Ankhona, Pandugram, Sripur PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000286/2024-2025 | 2738/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 128.29 | 0 | 75
3357 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ANKHONA, PANDUGRAM & SRIPUR Piped Water Supply Scheme under KETUGRAM¿I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000436/2023-2024 | 3388/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 989.13 | 0 | 50
3358 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000012/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.69 | 0 | 0
3359 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000362/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.57 | 0 | 0
3360 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000627/2023-2024 | 4873/BWD | 10/11/2023 | 0 | Resource Division | 29.6 | 0 | 0
3361 | Central Mechanical | Central Mechanical Sub-Division | Quotation for burnt meter problem at Pandugram PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/00937/2024-2025 | BP-2024-25-408 | 11/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.07 | 0 | 0
3362 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Pandugram PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01724/2023-2024 | BP-2023-24-253 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.61 | 0 | 0
3363 | Central Mechanical | Central Mechanical Sub-Division | New electric connection for Pandugram PWSS, PH-1. | Assistant Engineer | Junior Engineer | BILL/01875/2023-2024 | BP-2023-24-378 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.98 | 0 | 0
3364 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
3365 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PANDUGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 4128/CMD | 29/08/2023 | 30 | MENAKA ENTERPRISE. | 26.95 | 0 | 48
3366 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Pandugram W/S Scheme (T/W-I & II) , Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000169/2023-2024 | 1347/CDD | 13/09/2023 | 30 | M/S S.K.GHOSH & CO. | 16.67 | 0 | 0
3367 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation under HATGOBINDAPUR Piped W/S. Scheme within Burdwan - II Block under Burdwan Division, P.H.E Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000014/2023-2024 | 1729/BWD | 13/04/2023 | 537 | GUPTA ENTERPRISE | 89.36 | 0 | 100
3368 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Hatgobindapur PWSS under Burdwan-II Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000350/2023-2024 | 1477/BSD | 12/07/2023 | 15 | MEASURE LAND | 0.78 | 0 | 100
3369 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of interconnection between 1st & 2nd tube well to OHR for Hatgobindapur PWSS within Burdhaman-II Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001065/2024-2025 | 103/BSD | 16/01/2025 | 46 | I.S. ENTERPRISE | 3.6 | 0 | 100
3370 | Burdwan Division | Burdwan Sadar Sub-Division | Crossing of Bardhaman-Kalna Road near Hatgobindapur College More with 150 mm dia. pipeline through pushing of 600 mm. dia. RCC casing pipe by hydraulic jacking method for Hatgobindapur W/S. Scheme under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001199/2024-2025 | 644/BWD | 17/02/2025 | 10 | I.S. ENTERPRISE | 5.57 | 0 | 100
3371 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Amragarah PWSS TW-2 (Aug). | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00899/2024-2025 | BP-2024-25-338 | 04/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.59 | 0 | 0
3372 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Amragarh PWSS TW-3 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01091/2024-2025 | BP-2024-25-401 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.49 | 0 | 0
3373 | Central Mechanical | Durgapur Sub-DIvision | Making illumination arrangement and mise works at AMRARGARH and adjacent water supply scheme ausgram-II BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000477/2024-2025 | 2955/CMD | 20/11/2024 | 60 | A.S. ENTERPRISE | 22.81 | 0 | 50
3374 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of AMRARGARH[AUSGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001086/2023-2024 | 4509/CMD | 06/10/2023 | 605 | S.K. ENTERPRISE | 24.39 | 0 | 80
3375 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of Pump House at Head Work site of SATGACHIA ZONE-II Piped water supply scheme at Memari-II Block under Burdwan Division, Dist.-Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000137/2024-2025 | 1002/BSD | 06/06/2024 | 30 | SAANVI ENTERPRISE | 0.96 | 0 | 10
3376 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of Tube-well, construction of switch rooms & Rising main at 3RD TW site for SATGACHIA ZONE-II Piped Water Supply Scheme under MEMARI-II Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000899/2023-2024 | 5357/BWD | 06/12/2023 | 60 | J K CORPORATION | 20.1 | 0 | 0
3377 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall and Land development with approach road including internal drain at 2ND TW site for SATGACHIA ZONE-II PWSS under Memari-II Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000948/2023-2024 | 5595/BWD | 20/12/2023 | 30 | GOUTAM KUMAR MITRA | 5.09 | 0 | 100
3378 | Burdwan Division | Burdwan Sadar Sub-Division | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001269/2024-2025 | 848/BWD | 05/03/2025 | 120 | PROJECT INDIA | 394.29 | 0 | 0
3379 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone- I & II, Tube well No.- I (Replacement tube well) at Satgachia Water Supply Scheme [ BLOCK- Memari-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000531/2024-2025 | 3071/CMD | 03/12/2024 | 60 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 25.34 | 0 | 95
3380 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of SATGACHIA(Z-II, Part-B)[MEMARI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001075/2023-2024 | 4199/CMD | 29/08/2023 | 30 | DAS TRADING CO. | 24.41 | 0 | 0
3381 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KASIPUR, PATHAR GHATA & SABIDPUR Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000541/2023-2024 | 3697/BWD | 24/08/2023 | 770 | SUPRITI ENTERPRISE | 1185.67 | 0 | 42
3382 | Burdwan Division | Kalna Sub-division | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0
3383 | Burdwan Division | Kalna Sub-division | Road restoration work for implementation of KASIPUR PWSS (SM/16019) within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001167/2024-2025 | 559/BWD | 06/02/2025 | 90 | SUPRITI ENTERPRISE | 9.43 | 0 | 100
3384 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000081/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 31.64 | 0 | 0
3385 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000374/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 6.85 | 0 | 0
3386 | Central Mechanical | Kalna Sub-division | New service at Kasipur PWSS TW-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/02293/2023-2024 | BP-2023-24-439 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.72 | 0 | 0
3387 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 20
3388 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KASIPUR Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000899/2023-2024 | 4163/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 28.59 | 0 | 0
3389 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KASIPUR, PATHAR GHATA & SABIDPUR Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000541/2023-2024 | 3697/BWD | 24/08/2023 | 770 | SUPRITI ENTERPRISE | 1185.67 | 0 | 42
3390 | Burdwan Division | Kalna Sub-division | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0
3391 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR SABIDPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001154/2023-2024 | 2150/KSD | 07/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0 | 2
3392 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000088/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 36.67 | 0 | 0
3393 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000276/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 22.3 | 0 | 0
3394 | Central Mechanical | Kalna Sub-division | Quotation for new electric service connection at Sabidpur PH NO.-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01748/2023-2024 | BP-2023-24-255 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.37 | 0 | 0
3395 | Central Mechanical | Kalna Sub-division | New service connection for SABIDPUR PWSS TW-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/02400/2023-2024 | BP-2023-24-502 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.96 | 0 | 0
3396 | Central Mechanical | Kalna Sub-division | CONTINUATION ORDER-Hiring of inspection vehicle (Diesel/CNG/LPG Driven) [bearing no. WB41H5741] for supervision of the site for the office of the Assistant Engineer,CMD,PHE,Dte.[w.e.f-01.06.2025 to 31.07.2025][JJM WORKS] | Assistant Engineer | JUNIOR ENGINEER | ORD/000010/2025-2026 | 646/CMSD | 26/05/2025 | 61 | PRODYUT GHOSH | 0.8 | 0 | 0
3397 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 20
3398 | Burdwan Division | RWS Burdwan Sub-Division | RESTORATION WORK OF KALNA BAIDYAPUR ROAD TO AKALPOUSH HC ROAD FROM 0.00 KM TO 1.50 KM (IN STRETCHES )DAMAGED DUE TO LAYING OF UNDERGROUND WATER PIPELINEBY PHE WITH BOX CUTTING AND JHAMA WITH MOORUM CONSOLIDATION UNDR KALNA HIGHWAY SUB DIVISION OF BURDWAN SOUTH HIGHWAY DIVISION P.W.(ROADS) DTE.. DURING YEAR 2023-2024. | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | BILL/00646/2024-2025 | 825/JJM | 13/09/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 1.85 | 0 | 0
3399 | Burdwan Division | RWS Burdwan Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AKALPAUSH & BIRUHA Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | ORD/000542/2023-2024 | 3698/BWD | 24/08/2023 | 365 | SUPRITI ENTERPRISE | 1010.87 | 0 | 37
3400 | Burdwan Division | RWS Burdwan Sub-Division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR AKALPOUSH PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | ORD/001146/2023-2024 | 2095/KSD | 04/03/2024 | 10 | BISWAS ENTERPRISE | 0.66 | 0 | 2
3401 | Burdwan Division | RWS Burdwan Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | RTOR000053/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 34.71 | 0 | 0
3402 | Burdwan Division | RWS Burdwan Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | RTOR000201/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 20.78 | 0 | 0
3403 | Burdwan Division | RWS Burdwan Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | RTOR000609/2023-2024 | 4914/BWD | 10/11/2023 | 0 | Resource Division | 31.31 | 0 | 0
3404 | Burdwan Division | RWS Burdwan Sub-Division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | RTOR000783/2023-2024 | 330/BWD | 24/01/2024 | 0 | Resource Division | 13.92 | 0 | 0
3405 | Central Mechanical | RWS Burdwan Sub-Division | New Service connection at Akalpoush PWSS PH-1 | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | BILL/02321/2023-2024 | BP-2023-24-451 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.42 | 0 | 0
3406 | Central Mechanical | RWS Burdwan Sub-Division | New Service connection at Akalpoush PWSS PH-2 | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | BILL/02322/2023-2024 | BP-2023-24-452 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.25 | 0 | 0
3407 | Central Mechanical | RWS Burdwan Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 20
3408 | Central Mechanical | RWS Burdwan Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at AKALPAUSH Water Supply Scheme [ Block-KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | Assistant Engineer | JUNIOR ENGINEER,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dte | ORD/001055/2023-2024 | 4190/CMD | 29/08/2023 | 30 | AMUSAR IMPEX PVT. LTD. | 28.57 | 0 | 100
3409 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials for JOUGRAM & It's Adjoining Mouzas W/S. scheme under Burdwan Sub-Division, Burdwan Division, P.H.E. Dte. Ref. Drawing No.PC-I/OHR/11/2012 (Sheet No.1&2)(R-I) Dated 20.06.2012. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000020/2021-2022 | 3114/BWD | 02/06/2021 | 180 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 90.26 | 0 | 100
3410 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of JAUGRAM Piped Water Supply Scheme LDS, FHTC, land development, drain at different TW site under JAMALPUR Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000171/2023-2024 | 3059/BWD | 17/07/2023 | 682 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 406.76 | 0 | 50
3411 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of HDPE pipes with installation & construction of new valve chambers to control the flow of water within command area of JOUGRAM Piped W/S. Scheme at Jougram habitation, Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000761/2022-2023 | 1292/BWD | 20/03/2023 | 30 | DIPAK SARKAR | 18.24 | 0 | 1
3412 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of Rising Main with interconnection of OHR and distribution line for JAUGRAM Piped Water Supply Scheme and its adjoining mouzas within Jamalpur Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000763/2022-2023 | 1297/BWD | 21/03/2023 | 30 | GOUTAM DEY | 5.55 | 0 | 100
3413 | Burdwan Division | Kalna Sub-division | Augmentation of NADANGHAT PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Purbasthali - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000077/2023-2024 | 2043/BWD | 03/05/2023 | 60 | HAFIJUR RAHAMAN MIDYA | 26.28 | 0 | 100
3414 | Burdwan Division | Kalna Sub-division | Laying of Rising Main and distribution system with FHTC work, sinking of tube wells with other allied works in connection with Augmentation of NADANGHAT Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000130/2024-2025 | 2066/BWD | 07/06/2024 | 120 | TIRUPATI ENTERPRISES | 272.43 | 0 | 0
3415 | Burdwan Division | Kalna Sub-division | Work Order for "Restoration and laying of HDPE Pipeline at 2nd Pump House adjacent to Parulia village of PARULIA PWSS & Nadanghat PWSS (SM/16298) under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER | ORD/000553/2024-2025 | 773/KSD | 12/07/2024 | 15 | HAMID SK | 0.96 | 0 | 100
3416 | Burdwan Division | Kalna Sub-division | Work Order for "Restoration and laying of HDPE Pipeline at 2nd Pump House adjacent to Dogachhia village of DOGACHHIA PWSS & Nadanghat PWSS (SM/16298) under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | JUNIOR ENGINEER | ORD/000554/2024-2025 | 774/KSD | 12/07/2024 | 15 | HAMID SK | 0.96 | 0 | 100
3417 | Burdwan Division | Kalna Sub-division | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 51
3418 | Central Mechanical | Kalna Sub-division | Quotation for load enhancement at Nadanghat PWSS PH 2. | Assistant Engineer | JUNIOR ENGINEER | BILL/00225/2024-2025 | BP-2024-25-116 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.89 | 0 | 0
3419 | Central Mechanical | Kalna Sub-division | Illumination arrangement at Nadanghat water supply scheme under Purbasthali-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000403/2024-2025 | 2782/CMD | 01/10/2024 | 60 | SUBRATA BHADRA | 16.18 | 0 | 0
3420 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of NADANGHAT[PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001082/2023-2024 | 4440/CMD | 04/10/2023 | 30 | S.K. ENTERPRISE | 24.39 | 0 | 0
3421 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Nandra PWSS under Burdwan-II Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000349/2023-2024 | 1476/BSD | 12/07/2023 | 15 | CARTO | 0.78 | 0 | 100
3422 | Burdwan Division | Burdwan Sadar Sub-Division | Different type of works related internal pathways and approach road, land development, repair of boundary wall & pump houses and road restoration under NANDRA PWSS under Burdwan II Block under Burdwan Divn., PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000721/2025-2026 | 1404/BWD | 16/05/2025 | 45 | POMPA CONSTRUCTION CO. | 5.89 | 0 | 0
3423 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of NADRA Piped Water Supply Scheme Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & Rising Main under BARDHAMAN-II Block, District:- Purba-Bardhaman. _2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000965/2023-2024 | 002/BWD | 02/01/2024 | 180 | R.G. INFRASTRUCTURE | 72.79 | 0 | 0
3424 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work for the supply of one no. Diesel driven Motor Cab/Maxi Cab (Air Conditioner) on hire basis for the office of the Assistant Engineer, to be used by the Assistant Engineer, RWS Burdwan Sub-Divn., PHE. Dte. (Period from 01/03/2024 to 30/04/2024) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001222/2023-2024 | 62/RWS | 27/02/2024 | 60 | MD HASIN | 0.8 | 0 | 0
3425 | Burdwan Division | Central Mechanical Sub-Division | Balance work for extension of pipeline to provide FHTC with land development, plinth protection for pump house under LOHARUNDI PWSS, Block-Ketugram-II under Katwa Sub Division within Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000572/2024-2025 | 3313/BWD | 06/09/2024 | 60 | LAKSHMIKANTA DAS | 9.88 | 0 | 0
3426 | Burdwan Division | Central Mechanical Sub-Division | LOHARUNDI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM -II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000875/2023-2024 | 5328/BWD | 04/12/2023 | 484 | OM ENTERPRISE | 96.34 | 0 | 90
3427 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000017/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.47 | 0 | 0
3428 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000334/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 1.95 | 0 | 0
3429 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000562/2023-2024 | 4936/BWD | 10/11/2023 | 0 | Resource Division | 0.46 | 0 | 0
3430 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Loharudni PWSS PH-2. | Assistant Engineer | Junior Engineer | BILL/00347/2024-2025 | BP-2024-25-169 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0
3431 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0
3432 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at LOHARUNDI [KETUGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000891/2023-2024 | 4154/CMD | 29/08/2023 | 640 | AMUSAR IMPEX PVT. LTD. | 21.26 | 0 | 46
3433 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GHUNI & JOYKRISHNAPUR Piped Water Supply Scheme under Purbasthali II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000492/2023-2024 | 3510/BWD | 10/08/2023 | 808 | BKB INFRA PROJECTS PRIVATE LIMITED | 551.42 | 0 | 20
3434 | Burdwan Division | Kalna Sub-division | work Order "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR GHUNI PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE.". | Assistant Engineer | JUNIOR ENGINEER | ORD/000565/2024-2025 | 1014/KSD | 07/08/2024 | 15 | DEL DELTA CONSTRUCTION | 0.66 | 0 | 100
3435 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000262/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.84 | 0 | 0
3436 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000503/2023-2024 | 4027/BWD | 08/09/2023 | 0 | Resource Division | 1.09 | 0 | 0
3437 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000585/2023-2024 | 4929/BWD | 10/11/2023 | 0 | Resource Division | 39.66 | 0 | 0
3438 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR | Assistant Engineer | JUNIOR ENGINEER | BILL/02826/2023-2024 | BP-2023-24-595 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.93 | 0 | 0
3439 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR GHUNI PIPED WATER SUPPLY SCHEME. | Assistant Engineer | JUNIOR ENGINEER | BILL/02829/2023-2024 | BP-2023-24-596 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.04 | 0 | 0
3440 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0
3441 | Central Mechanical | Kalna Sub-division | CONTINUATION ORDER -Hiring of inspection vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of the Assistant engineer ,under CMD,PHE,Dte. [W.E.F-01/12/2024 to 30/01/2025] [Under JJM Works] | Assistant Engineer | JUNIOR ENGINEER | ORD/000563/2024-2025 | 1377/CMSD | 28/11/2024 | 61 | PRODYUT GHOSH | 0.8 | 0 | 0
3442 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at GHUNI [PURBASTHALI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000889/2023-2024 | 4152/CMD | 29/08/2023 | 30 | S.K. ELECTRICALS | 20.78 | 0 | 90
3443 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALGANA & GANGPUR Piped Water Supply Scheme under Burdwan ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000538/2023-2024 | 3699/BWD | 24/08/2023 | 769 | SUPRITI ENTERPRISE | 1345.79 | 0 | 20
3444 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000224/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 3.74 | 0 | 0
3445 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000402/2023-2024 | 3830/BWD | 01/09/2023 | 0 | Resource Division | 19.8 | 0 | 0
3446 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000648/2023-2024 | 5111/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3447 | Central Mechanical |  | Quotation for new service connection at Augmentation of Balgona PWSS PH-4 |  |  | BILL/00391/2024-2025 | BP-2024-25-208 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.22 | 0 | 0
3448 | Central Mechanical |  | New service connection charges for Balgona PWSS TW-1 |  |  | BILL/01829/2023-2024 | BP-2023-24-339 | 06/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.44 | 0 | 0
3449 | Central Mechanical |  | New service connection charges for Balgana PWSS TW-2 |  |  | BILL/02206/2023-2024 | BP-2023-24-403 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.86 | 0 | 0
3450 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 12
3451 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Replacement T.W of Bolgona Water Supply Scheme(H.W site) [ BLOCK- Bhatar] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000529/2024-2025 | 3069/CMD | 03/12/2024 | 60 | CHOUDHURY ENTERPRISE | 18.41 | 0 | 0
3452 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Balgana Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000669/2023-2024 | 4007/CMD | 29/08/2023 | 581 | GLACIER ENGINEERING CO | 28.96 | 0 | 95
3453 | Burdwan Division |  | Supply of various D.I. Mechanical joints & specials for KATNABIL & BANTIR Piped W/S. Scheme within Burdwan Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. |  |  | ORD/000302/2024-2025 | 2825/BWD | 19/07/2024 | 216 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 100
3454 | Burdwan Division |  | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-08-2024 to 31-10-2024) |  |  | ORD/000557/2024-2025 | 1500/BSD | 30/07/2024 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
3455 | Burdwan Division |  | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. |  |  | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 366 | SK ALIM | 1353.91 | 0 | 25
3456 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000230/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 16.06 | 0 | 0
3457 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000420/2023-2024 | 3862/BWD | 01/09/2023 | 0 | Resource Division | 3.19 | 0 | 0
3458 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000652/2023-2024 | 5098/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3459 | Central Mechanical |  | New electric connection for Bantir PWSS, PH-1. |  |  | BILL/01873/2023-2024 | BP-2023-24-359 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.18 | 0 | 0
3460 | Central Mechanical |  | New service connection charges for Bantir PWSS TW-2 |  |  | BILL/02198/2023-2024 | BP-2023-24-402 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.33 | 0 | 0
3461 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
3462 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bantir Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000718/2023-2024 | 4029/CMD | 29/08/2023 | 520 | M.S. ENTERPRISE | 28.98 | 0 | 96
3463 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARASAT, JAGADABAD & KHAIDYA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000465/2023-2024 | 3460/BWD | 08/08/2023 | 783 | CONCORD EMC ENCLAVE LLP | 1526.24 | 0 | 5
3464 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000092/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 7.63 | 0 | 0
3465 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000239/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.22 | 0 | 0
3466 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000710/2023-2024 | 5040/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3467 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Barasat PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02203/2023-2024 | BP-2023-24-393 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.59 | 0 | 0
3468 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Barasat PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02204/2023-2024 | BP-2023-24-394 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.63 | 0 | 0
3469 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
3470 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Barasat Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000652/2023-2024 | 3995/CMD | 29/08/2023 | 30 | JAGANNATH ENTERPRISE | 28.95 | 0 | 0
3471 | Burdwan Division |  | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000003/2025-2026 | 1116/BWD | 03/04/2025 | 120 | SOFIQUL ISLAM | 176.89 | 0 | 0
3472 | Burdwan Division |  | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-05-2024 to 31-07-2024) |  |  | ORD/000108/2024-2025 | 807/BSD | 29/04/2024 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
3473 | Burdwan Division |  | BISHNUPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000451/2023-2024 | 3426/BWD | 07/08/2023 | 967 | NATIONAL CONSTRUCTION | 870.64 | 0 | 70
3474 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 4117/BWD | 25/11/2024 | 0 | Resource Division | 18.97 | 0 | 0
3475 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000264/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.44 | 0 | 0
3476 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000429/2023-2024 | 3857/BWD | 01/09/2023 | 0 | Resource Division | 4.47 | 0 | 0
3477 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000570/2023-2024 | 4942/BWD | 10/11/2023 | 0 | Resource Division | 41.11 | 0 | 0
3478 | Central Mechanical |  | New electric connection for Bishnupur PWSS, PH-1. |  |  | BILL/01877/2023-2024 | BP-2023-24-361 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 15.08 | 0 | 0
3479 | Central Mechanical |  | New electric connection for Bishnupur PWSS, PH-3. |  |  | BILL/01878/2023-2024 | BP-2023-24-362 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.87 | 0 | 0
3480 | Central Mechanical |  | New service connection charges for Bishnupur PWSS TW-2 |  |  | BILL/02211/2023-2024 | BP-2023-24-404 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.36 | 0 | 0
3481 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0
3482 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at BISHNUPUR Water Supply Scheme [ Block- MEMARI-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000791/2023-2024 | 4079/CMD | 29/08/2023 | 30 | C.M. ENTERPRISE | 44.08 | 0 | 95
3483 | Burdwan Division |  | KARAJGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000428/2023-2024 | 3326/BWD | 02/08/2023 | 1247 | MANASH GHOSH | 533.47 | 0 | 60
3484 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000313/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.39 | 0 | 0
3485 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000505/2023-2024 | 4029/BWD | 08/09/2023 | 0 | Resource Division | 72.54 | 0 | 0
3486 | Central Mechanical |  | Quotation for new service connection for Kharajgram PWSS TW-3 |  |  | BILL/00341/2024-2025 | BP-2024-25-164 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.61 | 0 | 0
3487 | Central Mechanical |  | New service connection charges for Karajgram PWSS TW-2 |  |  | BILL/01098/2024-2025 | BP-2024-25-405 | 25/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.19 | 0 | 0
3488 | Central Mechanical |  | New service connection for Karajgram PWSS PH-1. |  |  | BILL/02287/2023-2024 | BP-2023-24-417 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 11.35 | 0 | 0
3489 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0
3490 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KARAJGRAM Water Supply Scheme [ Block-KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000872/2023-2024 | 4135/CMD | 29/08/2023 | 610 | SOUNAK ENTERPRISE | 45.53 | 0 | 66
3491 | Burdwan Division |  | KHAJURDIHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL |  |  | ORD/000497/2023-2024 | 3527/BWD | 10/08/2023 | 965 | MONDAL ENTERPRISE | 570.77 | 0 | 75
3492 | Burdwan Division |  | Necessary restoration work of Khajurdihi PWSS under Katwa-I Block under Katwa Sub-Division Burdwan Division PHE Dte. (Sl no -06) |  |  | ORD/001053/2024-2025 | 1609-A/KTS | 14/11/2024 | 45 | D.M. ENTERPRISE | 0.97 | 0 | 100
3493 | Burdwan Division |  | Different work for Khajurdihi PWSS Khajurdihi and Bera mouza with boundary wall, land development, plinth protection for pump house & OHR under KHAJURDIHI PWSS, at Katwa -I Block under Katwa Sub Division under Burdwan Division PHE Dte. |  |  | ORD/001190/2024-2025 | 610/BWD | 11/02/2025 | 120 | MONDAL ENTERPRISE | 196.33 | 0 | 0
3494 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000377/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.74 | 0 | 0
3495 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000404/2023-2024 | 3828/BWD | 01/09/2023 | 0 | Resource Division | 96.08 | 0 | 0
3496 | Central Mechanical |  | Addl. quotation for Khajurdihi PWSS TW-2 |  |  | BILL/00830/2024-2025 | BP-2024-25-326 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.99 | 0 | 0
3497 | Central Mechanical |  | New Service Connection for KHAJURDIHI PWSS PH-1. |  |  | BILL/02284/2023-2024 | BP-2023-24-418 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.8 | 0 | 0
3498 | Central Mechanical |  | New service connection for Khajurdhi, PWSS PH-2. |  |  | BILL/02286/2023-2024 | BP-2023-24-419 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.81 | 0 | 0
3499 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0
3500 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Balance work of dismantling concrete road including mending work, construction of approach road by fill up stone dust , bolders etc. and allied works under LOAPUR Water Supply Scheme, Galsi-I Block, District:- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000166/2024-2025 | 1595/DWSD | 25/11/2024 | 120 | M/S ASHA CONSTRUCTION | 95.37 | 0 | 0
3501 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000007/2024-2025 | 1724/S/DWSD | 10/12/2024 | 0 | Resource Division | 17.89 | 0 | 0
3502 | Burdwan Division | Durgapur Sub-DIvision | LOAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000419/2023-2024 | 3290/BWD | 31/07/2023 | 365 | M/S ASHA CONSTRUCTION | 824.72 | 0 | 15
3503 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000395/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 3.72 | 0 | 0
3504 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000444/2023-2024 | 3845/BWD | 01/09/2023 | 0 | Resource Division | 164.37 | 0 | 0
3505 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000560/2023-2024 | 4918/BWD | 10/11/2023 | 0 | Resource Division | 60.13 | 0 | 0
3506 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR LOHAPUR PWSS PH-1. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | BILL/03137/2023-2024 | BP-2023-24-651 | 20/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.92 | 0 | 0
3507 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
3508 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MEJHIARY & KARUI Piped Water Supply Scheme under Katwa ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000421/2023-2024 | 3291/BWD | 31/07/2023 | 701 | M/S S. CHOUDHURY | 1294.79 | 0 | 100
3509 | Burdwan Division |  | Construction of Toilet (1.8 m x 1.8 m) with sanitary arrangement under MAJHIARI PWSS(SM/18456) 2nd Tube Well Site under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-05) |  |  | ORD/001267/2024-2025 | 346/KTS | 05/03/2025 | 30 | GHOSH CONSTRUCTION | 2.45 | 0 | 100
3510 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000342/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.86 | 0 | 0
3511 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000410/2023-2024 | 3870/BWD | 01/09/2023 | 0 | Resource Division | 6.49 | 0 | 0
3512 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000641/2023-2024 | 5107/BWD | 23/11/2023 | 0 | Resource Division | 20.32 | 0 | 0
3513 | Central Mechanical |  | New service connection charges for Mejhiari PWSS TW-2 |  |  | BILL/01538/2023-2024 | BP-2023-24-208 | 30/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.87 | 0 | 0
3514 | Central Mechanical |  | New service connection charges for Mejhiari PWSS TW-1 |  |  | BILL/01541/2023-2024 | BP-2023-24-211 | 01/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.05 | 0 | 0
3515 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0
3516 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MEJHIARI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000509/2023-2024 | 3854/CMD | 14/08/2023 | 30 | S.K. ELECTRICALS | 28.96 | 0 | 90
3517 | Central Mechanical |  | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000602/2024-2025 | 3106/CMD | 11/12/2024 | 60 | S.K. ELECTRICALS | 13.6 | 0 | 0
3518 | Central Mechanical |  | Supply & Delivery of Submersible Pumping Machinery, suspension clamp and tube well cover etc. for Tube well No.-2 at MEJHIARI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte.,Dist.- Purba-Bardhaman. |  |  | ORD/001624/2023-2024 | 352/DIC/BMSD(D) | 22/12/2023 | 7 | SUBRATA BHADRA | 0.89 | 0 | 0
3519 | Central Mechanical |  | Supply & Delivery of 3 Phase actuator operated wafer type butterfly valve for Tube well No.- 2 at MEJHIARI Water Supply Scheme [Block- KATWA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001626/2023-2024 | 24/DIC/BMSD(D) | 05/01/2024 | 7 | SUBRATA BHADRA | 0.98 | 0 | 99
3520 | Central Mechanical |  | Supply & Delivery of Submersible cable and column pipes for Tube Well No No:-2 at MEJHIARI water supply scheme[ Block - KATWA -2] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. |  |  | ORD/001630/2023-2024 | 42/DIC/BMSD(D) | 15/01/2024 | 7 | SUBRATA BHADRA | 0.82 | 0 | 100
3521 | Central Mechanical |  | Supply & delivery of valves, starter and Installation of Submersible Pumping Machinery for Tube well No. - 2 at MEJHIARI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte., Dist.· Purba Bardhaman. |  |  | ORD/001632/2023-2024 | 46/DIC/BMSD(D) | 19/01/2024 | 15 | SUBRATA BHADRA | 0.68 | 0 | 100
3522 | Central Mechanical |  | Supply & Delivery of Submersible Pumping Machinery, suspension clamp and tube well cover etc. for Tube well No.-2 at MEJHIARI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte.,Dist.- Purba-Bardhaman. |  |  | ORD/001690/2023-2024 | 351/DIC/BMSD(D) | 22/12/2023 | 7 | SUBRATA BHADRA | 0.89 | 0 | 100
3523 | Burdwan Division |  | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-08-2024 to 31-10-2024) |  |  | ORD/000557/2024-2025 | 1500/BSD | 30/07/2024 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
3524 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHANCHAL & NUDIPUR Piped Water Supply Scheme under Memari I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000692/2023-2024 | 4389/BWD | 05/10/2023 | 730 | MANASH GHOSH | 1343.97 | 0 | 45
3525 | Burdwan Division |  | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-12-2024 to 28-02-2025 |  |  | ORD/001043/2024-2025 | 2636/BSD | 29/11/2024 | 90 | SK. ASFIA | 1.2 | 0 | 60
3526 | Burdwan Division |  | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for NUDIPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. |  |  | ORD/001115/2024-2025 | 477/BWD | 24/01/2025 | 250 | SHIVAM UN-EMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 64.73 | 0 | 25
3527 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000358/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 19.77 | 0 | 0
3528 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000533/2023-2024 | 4295/BWD | 29/09/2023 | 0 | Resource Division | 3.92 | 0 | 0
3529 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000684/2023-2024 | 5057/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3530 | Central Mechanical |  | New service connection at Nudipur PWSS PH-2 |  |  | BILL/02354/2023-2024 | BP-2023-24-468 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.43 | 0 | 0
3531 | Central Mechanical |  | New service connection at Nudipur PWSS PH-1 |  |  | BILL/02356/2023-2024 | BP-2023-24-467 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.67 | 0 | 0
3532 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0
3533 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nudipur Water Supply Scheme [ Block- Memari-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001092/2023-2024 | 4512/CMD | 06/10/2023 | 30 | JAL PRAVAHIKA PVT LTD | 28.96 | 0 | 100
3534 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARABAINAN & CHAUDANGA Piped Water Supply Scheme under Raina ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000412/2023-2024 | 3257/BWD | 27/07/2023 | 807 | SK ALIM | 1144.16 | 0 | 90
3535 | Burdwan Division |  | Continuation Work Order supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2023 to 31-01-2024) |  |  | ORD/000985/2023-2024 | 2561/BSD | 30/10/2023 | 66 | MD HASIN | 0.85 | 0 | 0
3536 | Burdwan Division |  | Supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-02-2024 to 30-04-2024) |  |  | ORD/001181/2023-2024 | 188/BSD | 31/01/2024 | 66 | PARVIN BEGAM | 0.85 | 0 | 97
3537 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000231/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 10.15 | 0 | 0
3538 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000232/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.15 | 0 | 0
3539 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000424/2023-2024 | 3838/BWD | 01/09/2023 | 0 | Resource Division | 8.01 | 0 | 0
3540 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000788/2023-2024 | 320/BWD | 24/01/2024 | 0 | Resource Division | 21.17 | 0 | 0
3541 | Central Mechanical |  | Quotation for new electric service connection at Bara Bainan PH NO.-1 |  |  | BILL/01742/2023-2024 | BP-2023-24-262 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.49 | 0 | 0
3542 | Central Mechanical |  | New service connection charges for Bara Bainan PWSS TW-2 |  |  | BILL/02212/2023-2024 | BP-2023-24-387 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.11 | 0 | 0
3543 | Central Mechanical |  | New Service connection at BARA BAINAN PWSS TW-1. |  |  | BILL/02361/2023-2024 | BP-2023-24-485 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.68 | 0 | 0
3544 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
3545 | Central Mechanical |  | Installation of starter in the temporary Kisok and allied works for urgent FHTC at BOROBOINAN PUMP HOUSE NO. 2 (RAINA-02 BLOCK) W/s scheme under CMD PHE Dte. |  |  | ORD/000651/2024-2025 | 770/CMSD | 21/05/2024 | 10 | S.K. ENTERPRISE | 1 | 0 | 100
3546 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Barabainan Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000725/2023-2024 | 4036/CMD | 29/08/2023 | 30 | S.K. ENTERPRISE | 28.98 | 0 | 96
3547 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000001/2024-2025 | 1724/M/DWSD | 10/12/2024 | 0 | Resource Division | 16.63 | 0 | 0
3548 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000282/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.07 | 0 | 0
3549 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000445/2023-2024 | 3832/BWD | 01/09/2023 | 0 | Resource Division | 191.84 | 0 | 0
3550 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Sanko PWSS TW 3 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01228/2024-2025 | BP-2024-25-417 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.83 | 0 | 0
3551 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Sanko PWSS TW-1 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02193/2023-2024 | BP-2023-24-373 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.63 | 0 | 0
3552 | Central Mechanical | Durgapur Sub-DIvision | New service connection for Sanko PWSS . | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02409/2023-2024 | BP-2023-24-508 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.1 | 0 | 0
3553 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
3554 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SANKO Water Supply Scheme [ Block- GALSI-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000782/2023-2024 | 4075/CMD | 29/08/2023 | 615 | BENGAL CONSTRUCTION. | 41.68 | 0 | 96
3555 | Burdwan Division | Durgapur Sub-DIvision | Construction of Temporary Approach road to HW site for Augmentation of Amarun (Zone-II ) Piped water supply Scheme , P.H.E Dte. Block:-Bhatar, Dist: Purba Bardhaman. [Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000136/2022-2023 | 347/DSD | 30/06/2022 | 21 | M/S S. CHOUDHURY | 1.04 | 0 | 100
3556 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Arrah village and arrah habitation of AMARUN piped water supply scheme within Durgapur (bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-542/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000252/2020-2021 | 3346/BWD | 18/09/2020 | 30 | M.R. CONSTRUCTION CO. | 4.86 | 4.86 | 1
3557 | Burdwan Division | Durgapur Sub-DIvision | Relaying for shifting of distribution line at Eora village for construction of Box culvert by PWD Department within Amarun and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000313/2022-2023 | 525/DSD | 22/08/2022 | 15 | BHARAT CONSTRUCTION | 0.73 | 0 | 0
3558 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AMARUN (Z-I & II) Piped Water Supply Scheme at Arra, Amarun, Nawada, Sunur (Part), Eora, Palsona & Bijyapur Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000317/2021-2022 | 7086/BWD | 22/12/2021 | 60 | NATIONAL CONSTRUCTION | 85.05 | 0 | 1
3559 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AMARUN (Z-II) Piped Water Supply Scheme at Hanrgram (4 Nos. Habs.), Erachya (6 Nos. Habs.) Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000363/2021-2022 | 7157/BWD | 24/12/2021 | 60 | S.S. CONSTRUCTION | 76.46 | 0 | 1
3560 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amarun village and Amarun habitation of Amarun piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-805/BWD/2020-21) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000382/2020-2021 | 3345/BWD | 18/09/2020 | 30 | BHARAT CONSTRUCTION | 4.87 | 4.87 | 1
3561 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amarun village and Amarun habitation of Amarun piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I][Tr No.-508/BWD/20-21] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000383/2020-2021 | 4793/BWD | 03/12/2020 | 30 | BHARAT CONSTRUCTION | 4.87 | 4.8 | 1
3562 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Arra village and Arrah habitation of Amarun piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000624/2020-2021 | 4989/BWD | 10/12/2020 | 30 | M.R. CONSTRUCTION CO. | 4.86 | 4.86 | 1
3563 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Hanrgram Khaspara, Chhatipara and Daspara for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte.[SL-29] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000846/2022-2023 | 708/DSD | 31/12/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.61 | 0 | 100
3564 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Palsona Mouza for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Phase-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-15] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000857/2022-2023 | 714/DSD | 30/12/2022 | 30 | SANDIPAN SENGUPTA | 4.81 | 0 | 100
3565 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Bijyapur Mouza for providing FHTC of Amarun and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-16] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000858/2022-2023 | 715/DSD | 30/12/2022 | 30 | SAMANTA CONSTRUCTION | 4.83 | 0 | 100
3566 | Burdwan Division | Durgapur Sub-DIvision | Restoration of damaged pipeline of distribution main for construction of drain, concrete road etc at various point at Sunur, and Amarun village for providing FHTC within Amarun W/S Scheme (Zone-I &II) in Bhatar Block under Burdwan Division, P.H.E. Dte. [SL-17] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000859/2022-2023 | 716/DSD | 30/12/2022 | 30 | SAMANTA CONSTRUCTION | 1.93 | 0 | 100
3567 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Kubajpur Adibasipara and Erachya for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-26] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000868/2022-2023 | 724/DSD | 30/12/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.58 | 0 | 100
3568 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Nandanarayanpur and Paschimpara for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-27] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000869/2022-2023 | 725/DSD | 30/12/2022 | 30 | BABA ADHIRA CONSTRUCTION | 4.83 | 0 | 100
3569 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Ramnagar Mouza for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-28] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000870/2022-2023 | 726/DSD | 30/12/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.16 | 0 | 100
3570 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Hanrgram Uttarpara, Majhipukur par and Dulepara for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte.[SL-30] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000871/2022-2023 | 727/DSD | 30/12/2022 | 30 | RAM MOHAN MUKHERJEE | 4.78 | 0 | 100
3571 | Burdwan Division | Durgapur Sub-DIvision | Sinking of 250 X 150 mm dia Tubewell and Modification to distribution network by making a loop and extension with uPVC pipe to augment the water supply to FHTC at Sunur and Arra village of AMARUN and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001069/2023-2024 | 1016/BWD | 07/03/2024 | 60 | BAMDEB CONSTRUCTION & CO | 34.03 | 0 | 80
3572 | Burdwan Division |  | Construction of Boundary wall at 3rd TW site for Chakshanjadi W/S Scheme with in Jamalpur block under Burdwan Div. PHED.(Lenth-48.0mtr & Col.-19nos.) GROUP : E |  |  | ORD/000084/2022-2023 | 818/BSD | 20/05/2022 | 45 | M/S PURBASHA | 4.06 | 0 | 1
3573 | Burdwan Division |  | Construction of Boundary wall at 2nd TW site for Chakshanjadi W/S Scheme with in Jamalpur block under Burdwan Div. PHED.(Lenth-78.0mtr & Col.-28nos.) GROUP : F |  |  | ORD/000085/2022-2023 | 819/BSD | 20/05/2022 | 45 | SOUMYAVASH DAS | 4.06 | 0 | 1
3574 | Burdwan Division |  | Construction of boundary wall at Head works site of CHAKSHANJADI Piped Water Supply Scheme in Jamalpur Block under Burdwan Division, PHE Dte. (Length - 123 Mtr., 46 Nos Column). |  |  | ORD/000098/2022-2023 | 2743/BWD | 08/06/2022 | 30 | MOYAZZEM CONSTRUCTION | 8.12 | 0 | 1
3575 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chaksanjadi Piped Water Supply Scheme at Chaksanjadi & Shambhupur Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 680/BWD OF 2020-2021] |  |  | ORD/000313/2020-2021 | 1399/BWD | 15/02/2021 | 45 | B.B.C. ENTERPRISE | 43.5 | 42.3 | 0
3576 | Burdwan Division |  | Extension of pipeline including providing FHTC for CHAKSHANJADI Piped Water Supply Scheme at Chalbalpur Habitation for Sajal Gram (As per Field Verification Report duly signed by Pradhan for Har Ghar Jal Certification) within Jamalpur Block under Burdwan Divn.PHE Dte.Gr.G. |  |  | ORD/000340/2022-2023 | 1361/BSD | 03/08/2022 | 5 | M/S ANAND CONSTRUCTION | 0.95 | 0 | 1
3577 | Burdwan Division |  | Extension of pipeline providing FHTC for CHAKSHANJADI Piped Water Supply Scheme at Chalbalpur Habitation for Sajal Gram(As per Field Verification Report duly signed by Pradhan for Har Ghar Jal Certification)within Jamalpur Block under Burdwan Divn.PHE Dte.Gr.H. |  |  | ORD/000341/2022-2023 | 1364/BSD | 04/08/2022 | 5 | M/S ANAND CONSTRUCTION | 0.96 | 0 | 1
3578 | Burdwan Division |  | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). |  |  | ORD/000345/2021-2022 | 40/BWD | 05/01/2022 | 30 | PREMANANDA ROY BISWAS | 22.68 | 0 | 1
3579 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chaksanjadi Piped Water Supply Scheme at Jamdaha, Haibatpur, Chalbalpur & Kanakpur Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement no. 791/BWD of 2020-2021) |  |  | ORD/000432/2020-2021 | 1795/BWD | 26/02/2021 | 45 | M/S GUPTA ENTERPRISE | 40.21 | 0 | 1
3580 | Burdwan Division |  | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. |  |  | ORD/000592/2021-2022 | 1454/BWD | 11/03/2022 | 30 | PREMANANDA ROY BISWAS | 18.83 | 0 | 1
3581 | Burdwan Division |  | Continuation order for supply & delivery of different dia CIDF pipes, sluice valve & fittings for construction of RCC OHR (400 cum capacity) for Chakshanjadi w/s scheme under Burdwan Division, PHE Dte. |  |  | ORD/000693/2021-2022 | 387/BWD | 20/01/2022 | 20 | B.B.C. ENTERPRISE | 15.17 | 0 | 1
3582 | Burdwan Division |  | Laying of interconnection of both the Pump No.1,2 & 3 and distribution main of 250 mm dia along with Byw-Pass arrangement from Over Head Reservoir for Chak Shanjadi piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte. |  |  | ORD/000925/2020-2021 | 4970/BWD | 10/12/2020 | 30 | TIRUPATI ENTERPRISES | 8.98 | 0 | 1
3583 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000124/2021-2022 | 1107/BWD | 26/02/2022 | 0 | Resource Division | 44.82 | 0 | 0
3584 | Burdwan Division |  | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0
3585 | Burdwan Division | Katwa Sub-Division | Hire & fuel charges of vehicle (Car No.-WB-04G-6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of November & December'22. | Assistant Engineer |  | BILL/00467/2022-2023 | 1048/JJM | 07/02/2023 | 0 | M/S MUNMUN DEY | 0.59 | 0 | 0
3586 | Burdwan Division | Katwa Sub-Division | Hire & fuel charges of vehicle (Car No.-WB-04G-6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of January'23. | Assistant Engineer |  | BILL/00468/2022-2023 | 1118/JJM | 27/02/2023 | 0 | M/S MUNMUN DEY | 0.26 | 0 | 0
3587 | Burdwan Division | Katwa Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme EKAIHAT, PANUHAT PWSS (Sl No-2) | Assistant Engineer |  | ORD/000070/2023-2024 | 394/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 2.48 | 0 | 100
3588 | Burdwan Division | Katwa Sub-Division | Supplying, laying and commissioning of Rising main at pump no. - 1 of Panuhat Piped Water Supply Scheme under Katwa Sub-Division under Burdwan Division, PHE Dte. [Sl No-06] | Assistant Engineer |  | ORD/000159/2022-2023 | 443/KTS | 27/06/2022 | 30 | HAMID SK | 2.27 | 0 | 1
3589 | Burdwan Division | Katwa Sub-Division | Extension of pipe line for FHTC work from the existing Distribution System within scheme jurisdiction at Panuhat village under Panuhat PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Phase-1] (Sl No-1) | Assistant Engineer |  | ORD/000298/2021-2022 | 728/KTS | 16/11/2021 | 7 | HAMID SK | 1.96 | 0 | 1
3590 | Burdwan Division | Katwa Sub-Division | Extension of pipe line for FHTC work from the existing Distribution System within scheme jurisdiction at Panuhat village under Panuhat PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Phase-2] (Sl No-2) | Assistant Engineer |  | ORD/000299/2021-2022 | 729/KTS | 16/11/2021 | 7 | HAMID SK | 1.93 | 0 | 1
3591 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PANUHAT Piped Water Supply Scheme at different villages, Katwa-I Block under Burdwan Division, PHE Dte. (Part-B).[Agreement No. 728/BWD OF 2020-2021.] | Assistant Engineer |  | ORD/000325/2020-2021 | 1689/BWD | 24/02/2021 | 45 | HAMID SK | 35.28 | 0 | 0
3592 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PANUHAT Piped Water Supply Scheme at different villages, Katwa-I Block under Burdwan Division, PHE Dte. (Part-A).[Agreement No. 727/BWD OF 2020-2021.] | Assistant Engineer |  | ORD/000326/2020-2021 | 1688/BWD | 24/02/2021 | 45 | HAMID SK | 35.66 | 19 | 0
3593 | Burdwan Division | Katwa Sub-Division | Balance work of OHR at Head Work site, construction of HUME Pipe culvert , Road restoration work and boundary wall at 2nd TW site with Gate, land development at Head work site and 2nd TW site under KAITHAN, SUDPUR & PANUHAT Piped Water Supply Scheme under KATWA -I Block, under Katwa Sub-Division within Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000486/2024-2025 | 3141/BWD | 20/08/2024 | 120 | VISHAL CONSTRUCTION CO. | 126.29 | 0 | 50
3594 | Burdwan Division | Katwa Sub-Division | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of PANUHAT and its adjoining mouzas Piped Water Supply Scheme, Block Katwa I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000668/2022-2023 | 387/BWD | 31/01/2023 | 30 | SUBODH KUMAR MONDAL | 11.7 | 0 | 100
3595 | Burdwan Division | Katwa Sub-Division | Vehicle bill (Car No.-WB-04G-7127) for the month of September'2023. | Assistant Engineer |  | BILL/01680/2023-2024 | 1041/JJM | 11/12/2023 | 0 | PARTHA PRATIM ACHARYA | 0.39 | 0 | 0
3596 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mongalkot Piped Water Supply Scheme at Mongalkot (3 Nos Habitation) Village (Mouza), Mongalkot Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000087/2021-2022 | 3598/BWD | 13/07/2021 | 60 | S.S. CONSTRUCTION | 115.84 | 0 | 1
3597 | Burdwan Division | Katwa Sub-Division | Extension and replacement of pipe line from the existing Distribution System within scheme jurisdiction at Mongalkote village under Mongalkote PWSS under Mongalkote Block within Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-02] | Assistant Engineer |  | ORD/000154/2022-2023 | 438/KTS | 27/06/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.75 | 0 | 1
3598 | Burdwan Division | Katwa Sub-Division | Extension and replacement of pipe line from the existing Distribution System within scheme jurisdiction at Mongalkote village under Mongalkote PWSS under Mongalkote Block within Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-03] | Assistant Engineer |  | ORD/000155/2022-2023 | 439/KTS | 27/06/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 1.38 | 0 | 1
3599 | Burdwan Division | Katwa Sub-Division | Laying of 150 mm dia. D.I distribution pipe line and restoration of drainage system at Mojlish Dighir Par at Mongalkote under MONGALKOTE Piped Water Supply Scheme under Mongalkote Block under Katwa Sub-Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000615/2021-2022 | 1577/BWD | 16/03/2022 | 30 | ASMA ENTERPRISE | 7.93 | 0 | 1
3600 | Burdwan Division | Katwa Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000116/2021-2022 | 1101/BWD | 26/02/2022 | 0 | Resource Division | 9.23 | 0 | 0
3601 | Burdwan Division | Katwa Sub-Division | Hire & fuel charges of vehicle (Car No.-WB-04G/6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of May & June'2022. | Assistant Engineer |  | VCH/000646/2022-2023 | 546/VEH/22-23 | 13/09/2022 | 0 | M/S MUNMUN DEY | 0.56 | 0 | 0
3602 | Burdwan Division | Katwa Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0
3603 | Burdwan Division | Katwa Sub-Division | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Paschim Gopalpur & Mirapur village under Paschim Gopalpur PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-1) | Assistant Engineer |  | ORD/000236/2021-2022 | 698/KTS | 27/10/2021 | 15 | ASMA ENTERPRISE | 1.06 | 0 | 1
3604 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection from existing distribution system at Sukhpukuria village under Gotistha Gram Panchayet under Mongalkote Block under Paschim Gopalpur PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-2) | Assistant Engineer |  | ORD/000274/2021-2022 | 799/KTS | 10/12/2021 | 15 | JAMALUDDIN SK | 3.69 | 0 | 1
3605 | Burdwan Division | Katwa Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Mongalkote Block under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000407/2021-2022 | 284/BWD | 17/01/2022 | 30 | BABUL SK | 6.81 | 0 | 1
3606 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection at Jadabbati,Sukhpukuria and Pilsona habitation of Paschim Gopalpur, Sukhpukuria and Pilsona village of Gotistha G.P. from existing distribution system within the command area of Paschim Gopalpur PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. | Assistant Engineer |  | ORD/000591/2021-2022 | 1439/BWD | 11/03/2022 | 30 | PARTHA PRATIM ACHARYA | 10.47 | 0 | 1
3607 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Paschim Gopalpur (Part) village (Jadabbati, Mirapur & Paschim Gopalpur (Part) habitation) & Radhanagar village (Radhanagar habitation) of Paschim Gopalpur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Sl. No. : ¿14¿] | Assistant Engineer |  | ORD/000711/2020-2021 | 64/BWD | 05/01/2021 | 15 | ASMA ENTERPRISE | 4.86 | 0 | 1
3608 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jalahati village of Jalahati piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-768/BWD/2020-21) | Assistant Engineer |  | ORD/000387/2020-2021 | 4793/1/BWD | 03/12/2020 | 30 | SETH ENTERPRISE | 4.92 | 4.92 | 1
3609 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jalahati (P) village (Jalahati (P) habitation) of Jalahati Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 26] | Assistant Engineer |  | ORD/000413/2020-2021 | 1462/BWD | 18/02/2021 | 15 | BARDHAMAN AQUA ENGINEERING | 4.86 | 4.86 | 1
3610 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jalahati (P) village (Beltalapara habitation) of Jalahati Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part-B). [SL. No. : 25] | Assistant Engineer |  | ORD/000414/2020-2021 | 1464/BWD | 18/02/2021 | 15 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.86 | 4.86 | 1
3611 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jalahati (P)village (Beltalapara habitation) of Jalahati Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part-A). [SL. No. : 24] | Assistant Engineer |  | ORD/000415/2020-2021 | 1465/BWD | 18/02/2021 | 15 | SETH ENTERPRISE | 4.82 | 4.86 | 1
3612 | Burdwan Division | Kalna Sub-division | Providing 350 Nos. FHTC work at JALAHATI W/S scheme for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification) within Purbasthali-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000800/2022-2023 | 1520/BWD | 28/03/2023 | 30 | IYASIN DAFADAR | 14.47 | 0 | 0
3613 | Burdwan Division | Kalna Sub-division | Hire & fuel charges of vehicle Car No.-WB-41J-6795 for the month of June & July2023. | Assistant Engineer |  | BILL/01035/2023-2024 | 745/JJM | 11/10/2023 | 0 | MD HASIN | 0.79 | 0 | 0
3614 | Burdwan Division | Kalna Sub-division | Extension of different dia UPVC Pipeline (suggested) as per survey of Horizon of Zone-III portion of Surface Based W/S Scheme in Arsenic Affected Areas of Purbasthali - II Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000009/2021-2022 | 3136/BWD | 03/06/2021 | 60 | ASHOK KUMAR GHOSH | 34.74 | 0 | 1
3615 | Burdwan Division | Kalna Sub-division | Work Order for "Providing Functional house hold tap connections for Sajal Gram Village within Purbasthali-II Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Purbasthali Aug & Kamalnagar water supply scheme)" | Assistant Engineer |  | ORD/000027/2023-2024 | 346/KSD | 17/04/2023 | 30 | RAJESH DAFADAR | 0.88 | 0 | 100
3616 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) at balance portion from existing distribution system within the command area of Aug. of PURBASTHALI Piped Water Supply Scheme at Chupi village (Mouza), Purbasthali - II Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000028/2022-2023 | 2079/BWD | 20/04/2022 | 30 | M/S K.P. CONSTRUCTION | 39.64 | 0 | 100
3617 | Burdwan Division | Kalna Sub-division | Construction of Pump House cum chlorine room (3.6 mtr x 3.0 mtr room) without sanitary and water supply arrangement at old Head Work Site of Purbasthali & it's adj. mouzas water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.^ (Sl No-C) | Assistant Engineer |  | ORD/000323/2021-2022 | 986/KSD Dt- 24.09.2021 | 24/09/2021 | 60 | SURATH DEY | 2.84 | 0 | 1
3618 | Burdwan Division | Kalna Sub-division | Hire and labour charges for staging and scaffolding bamboo barricading and removal of rubbish for dismantling capacity 136 Cum of RCC Over Head Reservoir at Purbasthali & it's adj. mouzas water Supply Scheme within Kalna Sub Divison under Burdwan Division , PHE Dte. (Sl No-A) | Assistant Engineer |  | ORD/000327/2021-2022 | 967/KSD Dt-20.09.2021 | 20/09/2021 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.47 | 0 | 1
3619 | Burdwan Division | Kalna Sub-division | Work Order for "Repairing and laying of UPVC pipeline of Majida, Nimdaha, Lakshmipur and Ukhura village for smooth running of FHTC work of Surface Based Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer |  | ORD/000548/2023-2024 | 1303/KSD | 23/08/2023 | 15 | PARTHA PRATIM ACHARYA | 1 | 0 | 100
3620 | Burdwan Division | Kalna Sub-division | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Augmentation of Purbasthali piped water supply scheme at Palaspuli village (Mouza), Purbasthali-II Block under burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000587/2020-2021 | 993/BWD | 04/02/2021 | 45 | IJABUL SEKH | 51.07 | 31.5 | 0
3621 | Burdwan Division | Kalna Sub-division | Providing Functional Household tap connection from existing distribution system within the command area of Augmentation of Purbasthali piped water supply scheme at Palaspuli village (Mouza), Purbasthali-II Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000680/2020-2021 | 993./BWD | 04/02/2021 | 45 | IJABUL SEKH | 51.07 | 0 | 1
3622 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Augmentation of Purbasthali Piped Water Supply Scheme at Chupi Village (Mouza), Purbasthali-II Block under Burdwan Division, PHE Dte._2ND CALL | Assistant Engineer |  | ORD/000681/2020-2021 | 1589/BWD | 22/02/2021 | 45 | DHIRENDRA ENGINEERING & CONSTRUCTION | 70.28 | 17.82 | 1
3623 | Burdwan Division | Kalna Sub-division | Extension of different dia UPVC pipeline (suggested) as per survey of Horizon of Zone-I portion of surface based water supply scheme in Arsenic affected areas of Purbasthali-II Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000810/2020-2021 | 826/BWD | 01/02/2021 | 60 | DEY NIRMAN | 24.83 | 0 | 1
3624 | Burdwan Division | Kalna Sub-division | Extension of different dia UPVC pipeline (suggested) as per survey of Horizon of Zone-IV portion of surface Based Water supply scheme in Arsenic affected areas of Purbasthali-II Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000865/2020-2021 | 754/BWD | 29/01/2021 | 60 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 20.95 | 0 | 1
3625 | Burdwan Division | Kalna Sub-division | Laying of different dia UPVC pipe at the balance portion of different section for Augmentation of Purbasthali & its adjoining mouzas water supply scheme within Kalna Sub-Division, under Burdwan Division, PHE Dte.[Part-C][Gr.-C] | Assistant Engineer |  | ORD/000868/2020-2021 | 31/KSD | 11/01/2021 | 45 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.68 | 0 | 1
3626 | Burdwan Division | Kalna Sub-division | Relaying of different dia UPVC pipeline at damaged portion as shown by Horizon of Zone-III of surface based water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL-B] | Assistant Engineer |  | ORD/000959/2020-2021 | 148/KSD | 12/02/2021 | 30 | CHANCHAL PAL | 4.82 | 0 | 1
3627 | Burdwan Division | Kalna Sub-division | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0
3628 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000120/2021-2022 | 1111/BWD | 26/02/2022 | 0 | Resource Division | 37.62 | 0 | 0
3629 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0
3630 | Burdwan Division |  | Hire & fuel charges of vehicle (Car No.-WB-41G-2149) for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. for the month of February'23. |  |  | BILL/00565/2022-2023 | 1226/JJM | 20/03/2023 | 0 | SK.ASFIA | 0.4 | 0 | 0
3631 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kailaspur Habitation of Kenna Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [GROUP : ¿L¿] (T.R. No. 201/BWD of 2020-2021) |  |  | ORD/000161/2020-2021 | 2399/BWD | 20/07/2020 | 30 | BRINDABAN KONAR | 4.92 | 0 | 1
3632 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kailaspur Habitation of Kenna Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [GROUP : ¿L¿] (T.R. No. 248/BWD of 2020-2021) |  |  | ORD/000162/2020-2021 | 3517/BWD | 25/09/2020 | 30 | BRINDABAN KONAR | 4.92 | 0 | 1
3633 | Burdwan Division |  | Extension of pipeline for Kenna Water Supply Scheme (Kenna, Dahura, Kailashpur, Dadur, Baral Village) within Memari - I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. |  |  | ORD/000207/2021-2022 | 6307/BWD | 09/11/2021 | 60 | T.K. BANERJEE & CO. | 41.46 | 0 | 1
3634 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KENNA Piped Water Supply Scheme at Dandur, Kailashpur (2 Nos. Habitation) village (Mouza), Memari - I Block under Burdwan Division, PHE Dte.[Agreement No. 570/BWD OF 2020-2021.] |  |  | ORD/000329/2020-2021 | 438/BWD | 19/01/2021 | 30 | BRINDABAN KONAR | 22.09 | 21.79 | 0
3635 | Burdwan Division |  | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Memari-I Block (Daluibazar-II, Gopegantar-I & II G.P.) under Burdwan Division, PHE. Dte. Dte._Part-A. |  |  | ORD/000371/2021-2022 | 209/BWD | 11/01/2022 | 30 | M/S ANAND CONSTRUCTION | 21.11 | 0 | 1
3636 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kenna village of Kenna piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000604/2020-2021 | 1225/BWD | 11/02/2021 | 30 | BRINDABAN KONAR | 4.92 | 4.92 | 1
3637 | Burdwan Division |  | Extension of pipeline for KENNA Piped Water Supply Scheme at Kaliashpur 25 Nos FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. |  |  | ORD/000848/2022-2023 | 1391-A/BSD | 08/08/2022 | 5 | BRINDABAN KONAR | 0.97 | 0 | 0
3638 | Burdwan Division | Katwa Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SRIKHANDA Piped Water Supply Scheme at Katwa - I Block under Burdwan Division, PHE Dte.(Agreement No. 53/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer |  | ORD/000121/2020-2021 | 4880/BWD | 07/12/2020 | 90 | ASHOK KUMAR GHOSH | 96.84 | 37.54 | 1
3639 | Burdwan Division | Katwa Sub-Division | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-7] | Assistant Engineer |  | ORD/000348/2021-2022 | 2942/BWD | 04/05/2021 | 10 | KISHORE GHOSH | 3.94 | 0 | 1
3640 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bohar village and Bohar habitation of Satgachia piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-435/BWD/2020-21) | Assistant Engineer |  | ORD/000507/2020-2021 | 3327/BWD | 18/09/2020 | 30 | TARAMA AGENCY | 4.86 | 4.83 | 0
3641 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jakra village and Jakra Paschimpara habitation of Satgachhia piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-383/BWD/2020-21) | Assistant Engineer |  | ORD/000511/2020-2021 | 3328/BWD | 18/09/2020 | 30 | A R TRADERS | 4.86 | 4.86 | 0
3642 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jakra (Part) village (Innathgore Habitation) & Bohat (Part) village (Hamunpur Habitation) of Satgachia piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Sl No.-21] | Assistant Engineer |  | ORD/000793/2020-2021 | 71/BWD | 05/01/2021 | 15 | A R TRADERS | 4.86 | 4.86 | 0
3643 | Burdwan Division | Katwa Sub-Division | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bohar village and Bohar habitation of Satgachia piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Gr.-4B] | Assistant Engineer |  | ORD/000794/2020-2021 | 4990/BWD | 10/12/2020 | 30 | TARAMA AGENCY | 4.86 | 4.69 | 0
3644 | Burdwan Division | Burdwan Sadar Sub-Division | MAINTENANCE OF ROAD (WHISH IS DAMAGED FOR LAYING PIPELINE BY PHE DEPTT) NAMELY NARUGRAM H.C TO BADSHI ROAD VIDE- PACKAGE NO- WB 22 12 UNDER PMGSY-III UNDER NARUGRAM GP. & RAINA-I BLOCK, IN PURBA BARDHAMAN DISTRICT | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00740/2024-2025 | 894/JJM | 25/09/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 3.86 | 0 | 0
3645 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila habitation) of Bagila Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 08] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000034/2021-2022 | 3406/BWD | 25/06/2021 | 15 | PAL CONSTRUCTION | 4.86 | 4.86 | 0
3646 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila habitation) of Bagila Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [SL. No. : 09] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000042/2021-2022 | 3465/BWD | 29/06/2021 | 15 | HAMID SK | 4.87 | 4.87 | 0
3647 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch room cum chlorine room without toilet room at 4th Tube well site according to departmental drawing no.- PHE/BD/P.H/DRG-01/DCE-2017 for Bagila piped water supply scheme at Sanghatipally under Memari-I Block under Burdwan Sub-Division, PHE Dte within Burdwan Division PHE Dte. Dist- Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000043/2025-2026 | 1025/BSD | 08/05/2025 | 90 | H SAMANTA | 4.16 | 0 | 100
3648 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipe line for BAGILA Piped Water Supply Scheme at Krishnapur,Baharampur,Kiskindha,Taktipur in Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte.Group : A | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000102/2022-2023 | 983/BSD | 16/06/2022 | 30 | A R TRADERS | 4.83 | 0 | 1
3649 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of Pump House at Head Work site of BAGILA Piped water supply scheme at Memari-I Block under Burdwan Division, Dist.-Purba Bardhaman | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000126/2024-2025 | 1006/BSD | 06/06/2024 | 30 | A.R. TRADERS | 0.96 | 0 | 100
3650 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of BAGILA Piped Water Supply Scheme at Kiskinda (2 nos Hab), Krishnapur, Talchini & Bagila (Part) Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000149/2021-2022 | 4659/BWD | 10/09/2021 | 60 | HAMID SK | 60.69 | 0 | 1
3651 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of additional 250 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for BAGILA Piped Water Supply Scheme, Block - Memari - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte._ 2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000257/2022-2023 | 3503/BWD | 10/08/2022 | 30 | MUNSHI ENTERPRISE | 10.18 | 0 | 1
3652 | Burdwan Division | Burdwan Sadar Sub-Division | Emergency repaired cleaning of chokage AC Pipeline for (Retrofittins) for BAGILA Piped water supply scheme at Baharampur, Takipur & Kiskinda village for smooth drinking water supply (FHTC) within Memari-I Block under Burdwan Division, PHE Dte. Gr.A | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000561/2022-2023 | 1918/BSD | 11/11/2022 | 15 | A R TRADERS | 0.93 | 0 | 1
3653 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for BAGILA Water Supply Scheme at (Baharampur, Taktipur, Krishnapur & Kiskinda North East) village within Memari I Block, under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000669/2021-2022 | 1708/BWD | 25/03/2022 | 30 | A R TRADERS | 27.27 | 0 | 1
3654 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila Habitation) of Bagila piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Part-A)[SL NO.-08] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000745/2020-2021 | 587./BWD | 25/01/2021 | 15 | PAL CONSTRUCTION | 4.86 | 4.86 | 1
3655 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila Habitation) of Bagila piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Part-B)[SL NO.-09] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000746/2020-2021 | 585./BWD | 25/01/2021 | 15 | HAMID SK | 4.87 | 4.87 | 1
3656 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Ground Water Based Piped Water Supply Scheme for MAHESHDANGA, Block:Memari-I under Burdwan Division, P.H.E Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000988/2024-2025 | 1909/BSD | 28/08/2024 | 15 | CARTO | 0 | 0 | 0
3657 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of 150mm DI pipeline for interconnection of 4no tw to distribution line & Kalsi mouza 3rd tw to distribution line for Bagila Piped Water Supply Scheme under memari-I Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001071/2024-2025 | 105/BSD | 16/01/2025 | 30 | A.R. TRADERS | 1.88 | 0 | 0
3658 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of additional tube well 250 x 200 mm dia Tube well 150 mtr depth by D.R. Rig method using upvc pipe (CD) and fibre glass strainer for Bagila piped water supply scheme (2nd tube well site), Block-Memari-I under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001312/2020-2021 | 1494/BWD | 18/02/2021 | 30 | C.M. ENTERPRISE | 8.68 | 0 | 0
3659 | Burdwan Division | Central Mechanical Sub-Division | Quotation from WBSEDCL for new connection charges of Selimabad w/s scheme of T.W.-3 under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/01932/2023-2024 | 1824/JJM | 27/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.47 | 0 | 0
3660 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.06.2025 to 31.07.2025] | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000170/2025-2026 | 685/AE/HQ | 30/05/2025 | 61 | SK. ASRAFUDDIN | 0.8 | 0 | 0
3661 | Burdwan Division | Central Mechanical Sub-Division | Augmentation of SELIMABAD Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 350 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including construction of switch-rooms (5.40mx3.6m) & Boundary walls for new TW site under Jamalpur Block, District:- Purba-Burdwan. [Treated as "New Scheme in place of Augmentation" vide Corrigendum Notice No. 1545/CC, dated 02.08.2022.] | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000234/2022-2023 | 3386/BWD | 04/08/2022 | 1184 | S. DUTTA | 435.08 | 0 | 70
3662 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000439/2024-2025 | 304/AE/HQ | 31/05/2024 | 61 | SK. ASRAFUDDIN | 0.8 | 0 | 0
3663 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000506/2024-2025 | 545/AE/HQ | 01/08/2024 | 61 | SK. ASRAFUDDIN | 0.8 | 0 | 0
3664 | Burdwan Division | Central Mechanical Sub-Division | Laying of additional pipeline (HDPE) with interconnection from Selimabad 3rd Pump House to BDO Office under Selimabad PWSS, Jamalpur Dev. Block under PHE. Dte. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000697/2025-2026 | 1037/AE/HQ | 01/08/2025 | 30 | A.R. TRADERS | 0.97 | 0 | 0
3665 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.10.2024 to 30.11.2024] | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000705/2024-2025 | 821/AE/HQ | 01/10/2024 | 61 | SK. ASRAFUDDIN | 0.8 | 0 | 0
3666 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.12.2024 to 31.01.2025] | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000899/2024-2025 | 1012/AE/HQ | 29/11/2024 | 61 | SK. ASRAFUDDIN | 0.8 | 0 | 0
3667 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.02.2025 to 31.03.2025] | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001155/2024-2025 | 187/AE/HQ | 31/01/2025 | 59 | SK. ASRAFUDDIN | 0.8 | 0 | 0
3668 | Burdwan Division | Central Mechanical Sub-Division | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001206/2023-2024 | 44/AE/HQ | 29/01/2024 | 60 | SK. ASRAFUDDIN | 0.8 | 0 | 50
3669 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001232/2023-2024 | 226/AE/HQ | 27/03/2024 | 61 | SK. ASRAFUDDIN | 0.8 | 0 | 0
3670 | Burdwan Division | Central Mechanical Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.04.2025 to 31.05.2025] | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001406/2024-2025 | 453/AE/HQ | 28/03/2025 | 61 | SK. ASRAFUDDIN | 0.8 | 0 | 0
3671 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000052/2022-2023 | 5524/BWD | 23/12/2022 | 0 | Resource Division | 12.41 | 0 | 0
3672 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000117/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 5.49 | 0 | 0
3673 | Central Mechanical | Central Mechanical Sub-Division | Additional Quotation for new service connection at Selimabad PWSS PH-3. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00460/2024-2025 | BP-2024-25-248 | 01/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.95 | 0 | 0
3674 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Selimabad W/S Scheme TW-1 | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00607/2023-2024 | BP-2023-24-16 | 22/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.37 | 0 | 0
3675 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Selimabad PWSS TW-2 | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/01523/2023-2024 | BP-2023-24-191 | 09/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.82 | 0 | 0
3676 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR SELIMABAD PWSS. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/02698/2023-2024 | BP-2023-24-565 | 23/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.66 | 0 | 0
3677 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Selimabad Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000611/2022-2023 | 3117/CMD | 23/11/2022 | 30 | M/S. DAS ELECTRIC CO. | 11.08 | 0 | 80
3678 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Selimabad Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000612/2022-2023 | 3118/CMD | 23/11/2022 | 30 | SUBRATA BHADRA | 11.07 | 0 | 95
3679 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Selimabad Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000615/2022-2023 | 3119/CMD | 23/11/2022 | 740 | MITRA ENTERPRISE | 10.73 | 0 | 98
3680 | Central Drilling | Central Mechanical Sub-Division | Providing pea size Gravels and Bentonite Powder sodium based at site with other works for construction of tube well at Selimabad PWSS( TW-III),Jamalpur Block under Purba Bardhaman ,Central Drilling Division, P.H.E Dte | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000064/2023-2024 | 269/CMSD-I(D) | 04/12/2023 | 15 | C.M. ENTERPRISE | 1.88 | 0 | 100
3681 | Central Drilling | Central Mechanical Sub-Division | Providing Tube well materials Conforming to IS: 12818:2010 with other Works at site for construction of Tube Well at Selimabad PWSS (TW-III),Jamalpur Block under Purba Bardhaman , Central Drilling Division, P.H.E Dte. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000065/2023-2024 | 271/CMSD-I(D) | 04/12/2023 | 15 | C.M. ENTERPRISE | 3.28 | 0 | 100
3682 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crews for construction of TW (250mm x 150mm) by Departmental Rig machine for Selimabad PWSS (TW-III), Jamalpur block under Purba Midnapur, CDD, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000146/2023-2024 | 270/CMSD-I(D) | 04/12/2023 | 15 | C.M. ENTERPRISE | 1.73 | 0 | 100
3683 | Central Drilling | Central Mechanical Sub-Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR SELIMABAD PWSS (TW-I), JAMALPUR BLOCK UNDER PURBA BARDAMAN, CDD, PHE DTE. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000285/2022-2023 | 312/CMSD-I | 22/07/2022 | 15 | UTTAM KUMAR CHATTERJEE | 1.74 | 0 | 1
3684 | Central Drilling | Central Mechanical Sub-Division | PROVIDING TUBE WELLMATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT SELIMABAD PWSS (TW-I), JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000286/2022-2023 | 313/CMSD-I | 22/07/2022 | 15 | UTTAM KUMAR CHATTERJEE | 3.29 | 0 | 1
3685 | Central Drilling | Central Mechanical Sub-Division | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT SELIMABAD PWSS (TW-I), JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000291/2022-2023 | 315/CMSD-I | 12/07/2022 | 15 | UTTAM KUMAR CHATTERJEE | 1.88 | 0 | 1
3686 | Central Drilling | Central Mechanical Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm) by utilising Departmental machineries for Selimabad PWSS(TW-I), Jamalpur block under Purba Bardhaman District, CDD PHE Dte. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000450/2022-2023 | 322/CMSD-I(D) | 12/07/2022 | 15 | M/S SREEJIT ENTERPRISE | 1.73 | 0 | 100
3687 | Central Drilling | Central Mechanical Sub-Division | Providing pea size Gravels and Bentonite Powder sodium based at site with other works for construction of Tube well at Selimabad PWSS(TW-II), Jamalpur block under Purba Bardhaman District, CDD PHE Dte. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000451/2022-2023 | 324/CMSD-I(D) | 12/07/2022 | 15 | M/S SREEJIT ENTERPRISE | 1.88 | 0 | 100
3688 | Central Drilling | Central Mechanical Sub-Division | Providing Tube well materials conforming to IS: 12818:2010 with other works at site for construction of Tube well at Selimabad PWSS(TW-II), Jamalpur block under Purba Bardhaman District, CDD PHE Dte. | AE(HQs), Burdwan Division, PHE Dte.,ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000452/2022-2023 | 321/CMSD-I(D) | 12/07/2022 | 15 | M/S SREEJIT ENTERPRISE | 3.28 | 0 | 100
3689 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of DEWANDIGHI Piped Water Supply Scheme with LDS, FHTC, Rising main with necessary interconnection, Construction of 200 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under Burdwan-I Block, District:- Purba-Burdwan. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000026/2022-2023 | 2055/BWD | 19/04/2022 | 365 | SHREE J.M. CONSTRUCTION | 213.62 | 0 | 100
3690 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Dewandighi-Mirzapur W/S Scheme under Burdwan-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.5. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000493/2021-2022 | 180/BSD | 31/01/2022 | 30 | RADIANT | 2.51 | 0 | 1
3691 | Burdwan Division | Burdwan Sadar Sub-Division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Paharhati, Nababhat, Shyamsundar & Dewandighi-Mirzapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000519/2022-2023 | 4703/BWD | 19/10/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 0 | 1
3692 | Burdwan Division | Burdwan Sadar Sub-Division | Allied work for Augmentation of DEWANDIGHI PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000744/2022-2023 | 1168/BWD | 14/03/2023 | 45 | BOSE ENTERPRISE | 50.01 | 0 | 100
3693 | Burdwan Division | Burdwan Sadar Sub-Division | Balance Work for extension of pipe lines to provide FHTC With Sinking of Tub well , Construction of pump house with Boundary wall & other related work for TALIT-SIMDAL (SM/18112), NABABHAT (SM-15166) and DEWANDIGHI-MIRJAPUR (SM/09494) PWSS under Burdwan Sub-Div., Block -Bwn-1, under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001248/2024-2025 | 793/BWD | 03/03/2025 | 120 | M/S S.S. ENTERPRISE | 227.66 | 0 | 0
3694 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000056/2021-2022 | 560/BWD | 27/01/2022 | 0 | Resource Division | 11.04 | 0 | 0
3695 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000087/2021-2022 | 881/BWD | 11/02/2022 | 0 | Resource Division | 13.26 | 0 | 0
3696 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000215/2021-2022 | 1538/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
3697 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
3698 | Burdwan Division | Durgapur Sub-DIvision | KHURUL Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000926/2023-2024 | 5480/BWD | 13/12/2023 | 476 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 182.02 | 0 | 65
3699 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000003/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 23.91 | 0 | 0
3700 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000386/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 6.52 | 0 | 0
3701 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000606/2023-2024 | 4911/BWD | 10/11/2023 | 0 | Resource Division | 32.92 | 0 | 0
3702 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR KHURUL PIPED WATER SUPPLY SCHEME. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02831/2023-2024 | BP-2023-24-588 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.72 | 0 | 0
3703 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR KHURUL PIPED WATER SUPPLY SCHEME. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02832/2023-2024 | BP-2023-24-589 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.45 | 0 | 0
3704 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
3705 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHURUL Water Supply Scheme [ Block- BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000803/2023-2024 | 4089/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 27.79 | 0 | 60
3706 | Burdwan Division | Durgapur Sub-DIvision | GUIR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000018/2023-2024 | 1732/BWD | 13/04/2023 | 629 | UNIQUE AGENCY | 531.21 | 0 | 40
3707 | Burdwan Division | Durgapur Sub-DIvision | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period May'2024 to July'2024] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000255/2024-2025 | 369/DSD | 30/04/2024 | 78 | MD HASIN | 1 | 0 | 0
3708 | Burdwan Division | Durgapur Sub-DIvision | Balance work for providing Functional Household Tap Connection (FHTC) within the command area KHEJURHATI & GUIR W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001217/2024-2025 | 724/BWD | 24/02/2025 | 120 | ROY CONSTRUCTION | 153.99 | 0 | 0
3709 | Burdwan Division | Durgapur Sub-DIvision | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day [Period February'2024 to April'2024] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001233/2023-2024 | 91/DSD | 31/01/2024 | 78 | MD HASIN | 1 | 0 | 0
3710 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000073/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.93 | 0 | 0
3711 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000175/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.07 | 0 | 0
3712 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000716/2023-2024 | 5268/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
3713 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Guir PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00799/2023-2024 | BP-2023-24-84 | 26/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.96 | 0 | 0
3714 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Guir PWSS TW 1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/00817/2023-2024 | BP-2023-24-96 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.97 | 0 | 0
3715 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0
3716 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Guir Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000142/2023-2024 | 2855/CMD | 05/07/2023 | 30 | M/S GHOSH ENTERPRISE | 28.95 | 0 | 90
3717 | Burdwan Division | Burdwan Sadar Sub-Division | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000003/2025-2026 | 1116/BWD | 03/04/2025 | 120 | SOFIQUL ISLAM | 176.89 | 0 | 0
3718 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KUCHUT & NOAHATI Piped Water Supply Scheme under Memari - II Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000750/2022-2023 | 1172/BWD | 14/03/2023 | 1113 | NATIONAL CONSTRUCTION | 831.75 | 0 | 99
3719 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000073/2022-2023 | 1247/BWD | 17/03/2023 | 0 | Resource Division | 11.94 | 0 | 0
3720 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000465/2023-2024 | 3989/BWD | 08/09/2023 | 0 | Resource Division | 2.9 | 0 | 0
3721 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000683/2023-2024 | 5056/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3722 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Noahati PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00770/2023-2024 | BP-2023-24-74 | 21/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.87 | 0 | 0
3723 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Noahati PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00771/2023-2024 | BP-2023-24-75 | 21/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.17 | 0 | 0
3724 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0
3725 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Noahati Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000138/2023-2024 | 2819/CMD | 04/07/2023 | 30 | M/S. S.R. ENTERPRISE | 29.4 | 0 | 100
3726 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BELENDA, JAMNA, PIPLON & PARGUNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000689/2023-2024 | 4388/BWD | 05/10/2023 | 667 | AKASH CONSTRUCTION | 2296.4 | 0 | 50
3727 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000370/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 6.18 | 0 | 0
3728 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000543/2023-2024 | 4310/BWD | 29/09/2023 | 0 | Resource Division | 85.2 | 0 | 0
3729 | Central Mechanical | Kalna Sub-division | Quotation for new service connection for Piplon PWSS PH-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/00283/2024-2025 | BP-2024-25-143 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.73 | 0 | 0
3730 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR PIPLON PWSS. | Assistant Engineer | JUNIOR ENGINEER | BILL/02688/2023-2024 | BP-2023-24-563 | 23/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.15 | 0 | 0
3731 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR PIPLON PWSS TW -3. | Assistant Engineer | JUNIOR ENGINEER | BILL/03100/2023-2024 | BP-2023-24-640 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.25 | 0 | 0
3732 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
3733 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at PIPLON Water Supply Scheme [ Block- MONTESWAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000793/2023-2024 | 4081/CMD | 29/08/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 44.42 | 0 | 94
3734 | Burdwan Division | Burdwan Sadar Sub-Division | CHAK BATASPUR Single Village Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000085/2023-2024 | 2115/BWD | 10/05/2023 | 90 | ANWESHA CONSTRUCTION | 63.63 | 0 | 100
3735 | Burdwan Division | Burdwan Sadar Sub-Division | Beautification of PWSS with Arboriculture, Recharge Pit including shaft and approach footway to Pump-House. Facelifting of masonary works at ANGUNA-BATASPUR (Raina-I Block) P.W.S.S under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000361/2024-2025 | 230/RWS | 25/07/2024 | 10 | DAS ENTERPRISE | 0.97 | 0 | 0
3736 | Burdwan Division | Burdwan Sadar Sub-Division | Beautification of PWSS with Arboriculture at Chak Bataspur and Recharge Pit including shaft & anciliary works at Head Works site and Repair and colour at 2nd Tubewell site of Kaity (Raina-II Block) P.W.S.S under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000366/2024-2025 | 236/RWS | 30/07/2024 | 10 | ANWESHA CONSTRUCTION | 0.97 | 0 | 0
3737 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000240/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7 | 0 | 0
3738 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000526/2023-2024 | 4315/BWD | 29/09/2023 | 0 | Resource Division | 0.83 | 0 | 0
3739 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000659/2023-2024 | 5117/BWD | 23/11/2023 | 0 | Resource Division | 18.94 | 0 | 0
3740 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Chak Baraspur PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/00884/2023-2024 | BP-2023-24-107 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.19 | 0 | 0
3741 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAK BATASPUR Water Supply Scheme [ Block-RAINA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000165/2023-2024 | 2930/CMD | 12/07/2023 | 232 | CONCORD ENGINEERING | 28.98 | 0 | 40
3742 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
3743 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PASCHIM KHARAMPUR, SHUSHNA & SIGHNALI Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000482/2023-2024 | 3494/BWD | 09/08/2023 | 783 | S.P. CONSTRUCTION | 1925.07 | 0 | 80
3744 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000321/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 15.55 | 0 | 0
3745 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000453/2023-2024 | 3977/BWD | 08/09/2023 | 0 | Resource Division | 38.31 | 0 | 0
3746 | Central Mechanical | Durgapur Sub-DIvision | New service connection for SIGHNALI PWSS TW 1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02445/2023-2024 | BP-2023-24-519 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.24 | 0 | 0
3747 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR SIGHNALI PWSS. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02692/2023-2024 | BP-2023-24-571 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.01 | 0 | 0
3748 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
3749 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sighnali Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000743/2023-2024 | 4053/CMD | 29/08/2023 | 611 | ASHIM UDYOG | 27.76 | 0 | 100
3750 | Burdwan Division | Durgapur Sub-DIvision | Land demarcation and preparation of sketch map for Haldi, Sultanpur, Berugram & Karail Piped W/S. Scheme (New Scheme) at different Blocks under JJM under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000756/2023-2024 | 842/AE/HQ | 01/11/2023 | 15 | M/S S. CHOUDHURY | 0.33 | 0 | 100
3751 | Burdwan Division | Durgapur Sub-DIvision | KARAIL Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001010/2023-2024 | 345/BWD | 25/01/2024 | 120 | T.K. BANERJEE & CO. | 59.45 | 0 | 30
3752 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000310/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 19.71 | 0 | 0
3753 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Karail PH-1 PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00811/2024-2025 | BP-2024-25-307 | 24/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.51 | 0 | 0
3754 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 30
3755 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at KARAIL Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000827/2023-2024 | 4104/CMD | 29/08/2023 | 30 | PADMA ENGINEERING CO. | 20.8 | 0 | 60
3756 | Burdwan Division | Kalna Sub-division | Different types of works in connection with implementation of MIRGAHAR Piped Water Supply Scheme (SM/18365) & BAGPUR PWSS (SM/13323) under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000186/2024-2025 | 2400/BWD | 26/06/2024 | 120 | M/S S. CHOUDHURY | 301.24 | 0 | 60
3757 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MANGANPUR & BAGPUR Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000391/2023-2024 | 3200/BWD | 24/07/2023 | 1100 | M/S GHOSH & CO. | 711.81 | 0 | 10
3758 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000216/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.24 | 0 | 0
3759 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000474/2023-2024 | 3998/BWD | 08/09/2023 | 0 | Resource Division | 0.83 | 0 | 0
3760 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000796/2023-2024 | 313/BWD | 24/01/2024 | 0 | Resource Division | 17.19 | 0 | 0
3761 | Central Mechanical | Kalna Sub-division | Quotation for new service connection at Bogpur PWSS PH-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/00389/2024-2025 | BP-2024-25-202 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.2 | 0 | 0
3762 | Central Mechanical | Kalna Sub-division | New service connection for BAGPUR PWSS TW-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/02398/2023-2024 | BP-2023-24-499 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.09 | 0 | 0
3763 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 30
3764 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at BAGPUR Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001273/2023-2024 | 16/CMD | 03/01/2024 | 30 | BARMAN ROY TRADERS | 21.77 | 0 | 45
3765 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to UCHALAN, CHAK CHANDAN, SERPUR & KATNABIL Piped Water Supply Scheme under Raina II Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000367/2023-2024 | 3076/BWD | 18/07/2023 | 988 | SK ALIM | 1307.56 | 0 | 75
3766 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-08-2024 to 31-10-2024) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000557/2024-2025 | 1500/BSD | 30/07/2024 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
3767 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2023 to 31-01-2024) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000985/2023-2024 | 2561/BSD | 30/10/2023 | 66 | MD HASIN | 0.85 | 0 | 0
3768 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000160/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 2.75 | 0 | 0
3769 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000331/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.85 | 0 | 0
3770 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000478/2023-2024 | 4002/BWD | 08/09/2023 | 0 | Resource Division | 11.88 | 0 | 0
3771 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000697/2023-2024 | 5067/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3772 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Uchalan W/S Scheme PH No.-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01794/2023-2024 | BP-2023-24-299 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.13 | 0 | 0
3773 | Central Mechanical | Burdwan Sadar Sub-Division | New electric connection for Uchalan PWSS, PH-2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01882/2023-2024 | BP-2023-24-341 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.5 | 0 | 0
3774 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
3775 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Uchalan Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000910/2023-2024 | 4174/CMD | 29/08/2023 | 30 | M/S, S.DAS AND ENTERPRISE. | 29.71 | 0 | 50
3776 | Durgapur W/S Division | Durgapur Sub-DIvision | Formal Work Order for Balance works related sinking of tubewells at GANGARAMPUR village, LDS with Jack Pushing, Rising Main Construction Switchroom and FHTC of DIGHA PWSS of Ausgram-I Block, under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000179/2024-2025 | 1573/DWSD | 21/11/2024 | 120 | MANASH GHOSH | 189.93 | 0 | 95
3777 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000003/2024-2025 | 1724/O/DWSD | 10/12/2024 | 0 | Resource Division | 4.05 | 0 | 0
3778 | Burdwan Division | Durgapur Sub-DIvision | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways at different TW sites for DIGHA Piped Water Supply Scheme under Ausgram-I Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000463/2023-2024 | 3454/BWD | 08/08/2023 | 730 | APORUPA CONSTRUCTION | 423.95 | 0 | 75
3779 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000022/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 55.76 | 0 | 0
3780 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000245/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.65 | 0 | 0
3781 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000449/2023-2024 | 3973/BWD | 08/09/2023 | 0 | Resource Division | 29.28 | 0 | 0
3782 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000587/2023-2024 | 4944/BWD | 10/11/2023 | 0 | Resource Division | 34.27 | 0 | 0
3783 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR DIGHA PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02588/2023-2024 | BP-2023-24-554 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.08 | 0 | 0
3784 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR DIGHA PWSS PH-1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/03138/2023-2024 | BP-2023-24-648 | 20/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.12 | 0 | 0
3785 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0
3786 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEULIA, GOBARDHANPUR, KHARIJA-KASHIGRAM & UNIATATARPUR Piped Water Supply Scheme under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000477/2023-2024 | 3491/BWD | 09/08/2023 | 815 | POWER TOOLS & ENGINEERING | 1741.05 | 0 | 10
3787 | Burdwan Division | Central Mechanical Sub-Division | Designing, making and erection of Sign Board for SWAJAL GRAM in Taharpur village of Memari-I Block under Gobindapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte(5 nos Board) | Assistant Engineer | Junior Engineer | ORD/000508/2025-2026 | 2352/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0
3788 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000112/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 17.79 | 0 | 0
3789 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000385/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.53 | 0 | 0
3790 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000714/2023-2024 | 5277/BWD | 30/11/2023 | 0 | Resource Division | 20.37 | 0 | 0
3791 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection for Gobardhanpur PWSS TW-2. | Assistant Engineer | Junior Engineer | BILL/00252/2024-2025 | BP-2024-25-131 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.11 | 0 | 0
3792 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Gobardhanpur PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01087/2024-2025 | BP-2024-25-397 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.93 | 0 | 0
3793 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
3794 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GOBARDHANPUR Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | Assistant Engineer | Junior Engineer | ORD/000933/2023-2024 | 4196/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 29.71 | 0 | 0
3795 | Burdwan Division | Durgapur Sub-DIvision | CHHATINI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000093/2023-2024 | 2216/BWD | 15/05/2023 | 687 | SHWET BARANI | 539.35 | 0 | 55
3796 | Burdwan Division | Durgapur Sub-DIvision | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period May'2024 to July'2024] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000255/2024-2025 | 369/DSD | 30/04/2024 | 78 | MD HASIN | 1 | 0 | 0
3797 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) by sinking of tube well 250 x 150 mm. dia., Constn. of Pump House & Boundary Wall within command area of CHHATINI W/S. Scheme, Bhatar Block under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000401/2024-2025 | 3033/BWD | 06/08/2024 | 120 | SAHA CONSTRUCTION & CO. | 129.06 | 0 | 50
3798 | Burdwan Division | Durgapur Sub-DIvision | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day [Period February'2024 to April'2024] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001233/2023-2024 | 91/DSD | 31/01/2024 | 78 | MD HASIN | 1 | 0 | 0
3799 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000074/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 56.53 | 0 | 0
3800 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000311/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 19.47 | 0 | 0
3801 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000584/2023-2024 | 4928/BWD | 10/11/2023 | 0 | Resource Division | 34.57 | 0 | 0
3802 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Chhatini PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/01049/2023-2024 | BP-2023-24-118 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.96 | 0 | 0
3803 | Central Mechanical | Durgapur Sub-DIvision | New Service connection at CHHATINI PWSS TW-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02368/2023-2024 | BP-2023-24-480 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.24 | 0 | 0
3804 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
3805 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chhatini Water Supply Scheme [ Block- Bhatar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000212/2023-2024 | 3069/CMD | 21/07/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 27.79 | 0 | 60
3806 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000057/2022-2023 | 1236/BWD | 17/03/2023 | 0 | Resource Division | 13.55 | 0 | 0
3807 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000092/2022-2023 | 1630/BWD | 06/04/2023 | 0 | Resource Division | 1.65 | 0 | 0
3808 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000637/2023-2024 | 5092/BWD | 23/11/2023 | 0 | Resource Division | 24.47 | 0 | 0
3809 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Mulgram W/S Scheme TW-1 | Assistant Engineer | Junior Engineer | BILL/00695/2023-2024 | BP-2023-24-37 | 27/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.76 | 0 | 0
3810 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Mulgram PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01763/2023-2024 | BP-2023-24-273 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0
3811 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Mulgram Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000049/2023-2024 | 2511/CMD | 02/06/2023 | 30 | M/S. S.R. ENTERPRISE | 28.96 | 0 | 40
3812 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0
3813 | Central Mechanical | Central Mechanical Sub-Division | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000602/2024-2025 | 3106/CMD | 11/12/2024 | 60 | S.K. ELECTRICALS | 13.6 | 0 | 0
3814 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SARANGA & KAMALPUR Piped Water Supply Scheme under Khandaghosh Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000082/2023-2024 | 2078/BWD | 04/05/2023 | 698 | KHAN ENTERPRISE | 820.73 | 0 | 42
3815 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work for providing Functional Household Tap Connection (FHTC) within command area SARANGA W/S. Scheme of Khandaghosh Block under Burdwan Divn., PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001097/2024-2025 | 431/BWD | 20/01/2025 | 120 | ANWESHA CONSTRUCTION | 98.39 | 0 | 0
3816 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000108/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 7.15 | 0 | 0
3817 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000196/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 5.01 | 0 | 0
3818 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000733/2023-2024 | 5235/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
3819 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Saranga PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00800/2023-2024 | BP-2023-24-87 | 26/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.97 | 0 | 0
3820 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Saranga PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00818/2023-2024 | BP-2023-24-94 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.5 | 0 | 0
3821 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 10
3822 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Saranga Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000144/2023-2024 | 2854/CMD | 05/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 28.97 | 0 | 100
3823 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & delivery of submersible pumping machinery (for urgent FHTC) for Tube well no.-1 at Saranga w/s scheme, (Block -Khandaghosh) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001663/2023-2024 | 1075/CMSD | 15/12/2023 | 12 | SUBHRA ENTERPRISE | 0.67 | 0 | 100
3824 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & delivery of different electro-mechanical accessories (for urgent FHTC) for Tube well no.-1 at Saranga w/s scheme, ( Block -Khandaghosh) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001664/2023-2024 | 1073/CMSD | 15/12/2023 | 10 | SUBHRA ENTERPRISE | 0.8 | 0 | 100
3825 | Central Mechanical | Burdwan Sadar Sub-Division | Emergency Installation (for urgent FHTC) of departmental supply submersible pumping machinery with supply main switch, cable, starter etc. for Tube well no.-1 at Saranga w/s scheme, ( Block -Khandaghosh) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001666/2023-2024 | 06/CMSD | 02/01/2024 | 10 | SUBHRA ENTERPRISE | 0.72 | 0 | 100
3826 | Central Mechanical | Burdwan Sadar Sub-Division | Continuation order-Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven ) for supervision of site for the office of the Assistant Engineer,under CMD,PHE,Dte. [W.e.f-01/03/2024 to 29/04/2024) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001914/2023-2024 | 359/CMSD | 27/02/2024 | 60 | SUBRATA BHADRA | 0.79 | 0 | 100
3827 | Burdwan Division | Central Mechanical Sub-Division | BARA KULGACHHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000709/2022-2023 | 775/BWD | 24/02/2023 | 1253 | MANASH GHOSH | 557.58 | 0 | 73
3828 | Burdwan Division | Central Mechanical Sub-Division | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | Assistant Engineer | Junior Engineer | ORD/001212/2023-2024 | 907/BWD | 04/03/2024 | 30 | MANASH GHOSH | 23.87 | 0 | 100
3829 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000089/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 20.38 | 0 | 0
3830 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000134/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 9.61 | 0 | 0
3831 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000792/2023-2024 | 331/BWD | 24/01/2024 | 0 | Resource Division | 16.79 | 0 | 0
3832 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Barakulgachi PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/00882/2023-2024 | BP-2023-24-108 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.73 | 0 | 0
3833 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Bara Kulgachi PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01353/2023-2024 | BP-2023-24-131 | 22/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.92 | 0 | 0
3834 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0
3835 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BARAKULGACHHI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 3173/CMD | 26/07/2023 | 30 | GOENKA ENTERPRISE | 28.98 | 0 | 90
3836 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 1
3837 | Burdwan Division | Durgapur Sub-DIvision | PICHKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000064/2023-2024 | 1985/BWD | 27/04/2023 | 980 | BANSBERIA CONSTRUCTION CO. | 445.01 | 0 | 95
3838 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/06/2024 to 31/07/2024) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000184/2024-2025 | 411/DSD | 28/05/2024 | 61 | SUJAUDDIN SEKH | 0.8 | 0 | 0
3839 | Burdwan Division | Durgapur Sub-DIvision | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001180/2023-2024 | 995/DSD | 29/12/2023 | 183 | SUJAUDDIN SEKH | 2 | 0 | 60
3840 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000031/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 25.71 | 0 | 0
3841 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000189/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.16 | 0 | 0
3842 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000602/2023-2024 | 4908/BWD | 10/11/2023 | 0 | Resource Division | 12.03 | 0 | 0
3843 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Pichkuri PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00762/2023-2024 | BP-2023-24-64 | 18/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.96 | 0 | 0
3844 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Pichkuri PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00763/2023-2024 | BP-2023-24-65 | 18/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.26 | 0 | 0
3845 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Pichkuri Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000150/2023-2024 | 2886/CMD | 10/07/2023 | 30 | CHATTERJEE ENTERPRISE | 27.75 | 0 | 98
3846 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0
3847 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of hard shouldering and flank damaged during laying of PHE pipeline at Samanti village road from 0.00 Kmp to 3.00 Kmp within Samanti PWSS. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00138/2024-2025 | 226/JJM | 14/05/2024 | 0 | EXECUTIVE ENGINEER-I, BURDWAN DIVISION, P.W.D. | 5.08 | 0 | 0
3848 | Burdwan Division | Burdwan Sadar Sub-Division | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000653/2023-2024 | 4076/BWD | 13/09/2023 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 0 | 100
3849 | Burdwan Division | Burdwan Sadar Sub-Division | SAMANTI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under BARDHAMAN-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000802/2022-2023 | 1536/BWD | 29/03/2023 | 1008 | G.B. CONSTRUCTION & CO. | 504.69 | 0 | 36
3850 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000015/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 10.45 | 0 | 0
3851 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000170/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 23.19 | 0 | 0
3852 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000732/2023-2024 | 5237/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
3853 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Samanti PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00886/2023-2024 | BP-2023-24-112 | 10/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.1 | 0 | 0
3854 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for Samanti W/S scheme TW No-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02273/2023-2024 | BP-2023-24-411 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.6 | 0 | 0
3855 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 12
3856 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Samanti Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000194/2023-2024 | 2979/CMD | 18/07/2023 | 30 | MS DAS ELECTRIC CO | 28.98 | 0 | 95
3857 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Road Restoration ,Land development with access road & allied works for Augmentation of SAR PWSS , Ausgram-II Block under Durgapur Water Supply Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000175/2024-2025 | 1616/DWSD | 26/11/2024 | 90 | SAIKAT RAY | 10.77 | 0 | 0
3858 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for SATINANDI Piped Water Supply Scheme with INSTALLATION OF BARBED WIRE, FHTC ,Road restoration ,DEMOLITION WORK & land development with road at TW site under Galsi-II Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000183/2024-2025 | 1620/DWSD | 26/11/2024 | 326 | A K SIKDAR | 79.05 | 0 | 70
3859 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000015/2024-2025 | 1724/K/DWSD | 10/12/2024 | 0 | Resource Division | 0.55 | 0 | 0
3860 | Burdwan Division | Durgapur Sub-DIvision | SAR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000094/2023-2024 | 2231/BWD | 16/05/2023 | 365 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 193.73 | 0 | 100
3861 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000055/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 11.55 | 0 | 0
3862 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000294/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.41 | 0 | 0
3863 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000758/2023-2024 | 5241/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0
3864 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Sar PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01463/2023-2024 | BP-2023-24-162 | 18/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.45 | 0 | 0
3865 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Sar PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01464/2023-2024 | BP-2023-24-163 | 18/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.8 | 0 | 0
3866 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sar Water Supply Scheme [ Block-Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000588/2023-2024 | 3924/CMD | 22/08/2023 | 30 | D.K. ELECTRIC | 27.75 | 0 | 98
3867 | Burdwan Division | Durgapur Sub-DIvision | RAMCHANDRAPUR (ZONE-I & II ) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000536/2023-2024 | 3703/BWD | 24/08/2023 | 677 | SUPRITI ENTERPRISE | 582.13 | 0 | 60
3868 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000085/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 6.74 | 0 | 0
3869 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000270/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.32 | 0 | 0
3870 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000557/2023-2024 | 4890/BWD | 10/11/2023 | 0 | Resource Division | 10.17 | 0 | 0
3871 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection for Ramchandrapur Zone-2 PWSS PH 1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00226/2024-2025 | BP-2024-25-117 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.39 | 0 | 0
3872 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection for Ramchandarapur Zone-2 PWSS PH 2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00227/2024-2025 | BP-2024-25-118 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.35 | 0 | 0
3873 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Ramchandrapur Zone-1 PWSS PH-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00392/2024-2025 | BP-2024-25-205 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.44 | 0 | 0
3874 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR RAMCHANDRAPUR ZONE - I PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02593/2023-2024 | BP-2023-24-551 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.15 | 0 | 0
3875 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0
3876 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2, 3 & 4 at RAMCHANDRAPUR Water Supply Scheme [ Block- BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000919/2023-2024 | 4183/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 56.97 | 0 | 40
3877 | Burdwan Division | Kalna Sub-division | CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR SHYAMPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE. | Assistant Engineer | JUNIOR ENGINEER | ORD/000570/2024-2025 | 1016/KSD | 07/08/2024 | 15 | DEL DELTA CONSTRUCTION | 0.66 | 0 | 100
3878 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMPUR, GAHAK & SHANKRA Piped Water Supply Scheme under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000639/2023-2024 | 3957/BWD | 07/09/2023 | 1051 | M/S B. NANDI | 758.52 | 0 | 20
3879 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000320/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 14.98 | 0 | 0
3880 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000547/2023-2024 | 4300/BWD | 29/09/2023 | 0 | Resource Division | 0.58 | 0 | 0
3881 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000589/2023-2024 | 4946/BWD | 10/11/2023 | 0 | Resource Division | 9.76 | 0 | 0
3882 | Central Mechanical | Kalna Sub-division | Quotation for new service connection at Shyampur PWSS PH-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/00458/2024-2025 | BP-2024-25-250 | 01/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.61 | 0 | 0
3883 | Central Mechanical | Kalna Sub-division | Quotation for new service connection at Shyampur PWSS PH 1. | Assistant Engineer | JUNIOR ENGINEER | BILL/00934/2024-2025 | BP-2024-25-352 | 05/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.57 | 0 | 0
3884 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0
3885 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at SHYAMPUR [PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000888/2023-2024 | 4151/CMD | 29/08/2023 | 581 | DUTTA ENTERPRISE | 20.8 | 0 | 100
3886 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR ANGERSON PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001149/2023-2024 | 2105/KSD | 04/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0 | 2
3887 | Burdwan Division | Kalna Sub-division | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0
3888 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000060/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 42.44 | 0 | 0
3889 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000210/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.32 | 0 | 0
3890 | Central Mechanical | Kalna Sub-division | New service connection charges for Angarson PWSS TW-2 | Assistant Engineer | JUNIOR ENGINEER | BILL/01865/2023-2024 | BP-2023-24-350 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.07 | 0 | 0
3891 | Central Mechanical | Kalna Sub-division | New electric connection for Angarson PWSS, PH-1. | Assistant Engineer | JUNIOR ENGINEER | BILL/01888/2023-2024 | BP-2023-24-349 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.47 | 0 | 0
3892 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 20
3893 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at ANGARSON Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000894/2023-2024 | 4157/CMD | 29/08/2023 | 640 | S.K. ELECTRICALS | 27.77 | 0 | 95
3894 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall at Head Works Site of TEANDUL Water Supply Scheme under RAINA I Block of Burdwan Division, PHE Dte. (Length -151.00 Mtr, Col - 48 Nos). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000012/2023-2024 | 1727/BWD | 13/04/2023 | 60 | HI-LIGHT ELECTRONICS | 21.94 | 0 | 100
3895 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Path Way, Drain, Repairing of Pump House at 2nd TW Site and Providing leftout FHTC, Road Restoration with allied work for TENDUL Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000965/2024-2025 | 4375/BWD | 13/12/2024 | 90 | DEY NIRMAN | 12.69 | 0 | 0
3896 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of Parallel Pipeline from Distribution line near Head Work site to Sonadanga to improve water demand at Madubon, Sultanbad & Dhomas village by direct water supply of TENDUL Piped Water Supply Scheme, Raina-I Block under Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001110/2023-2024 | 1117/BWD | 14/03/2024 | 124 | ANWESHA CONSTRUCTION | 11.7 | 0 | 100
3897 | Burdwan Division | Central Mechanical Sub-Division | Augmentation of AGRADWIP Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-II Block, District:- Purba-Bardhaman._2ND CALL | Assistant Engineer | Junior Engineer | ORD/000558/2023-2024 | 3778/BWD | 29/08/2023 | 856 | MOTHER INFRASTRUCTURE | 420.6 | 0 | 86
3898 | Burdwan Division | Central Mechanical Sub-Division | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of AGRADWIP and its adjoining mouzas Piped Water Supply Scheme, Block Katwa II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000698/2022-2023 | 604/BWD | 17/02/2023 | 30 | AUXILIARY TUBE WELL DRILLERS | 12.77 | 0 | 100
3899 | Burdwan Division | Central Mechanical Sub-Division | Construction of Pump House, Boundary walls and Raising Main for Aug. of AGRADWIP Piped W/S. Scheme under Katwa-II Block, District:- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000925/2023-2024 | 5485/BWD | 13/12/2023 | 391 | JAMALUDDIN SK | 9.75 | 0 | 80
3900 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR AGRADIP KASHIPUR PWSS PH 1 | Assistant Engineer | Junior Engineer | BILL/02954/2023-2024 | BP-2023-24-637 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.92 | 0 | 0
3901 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Agradip Kashipur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000079/2023-2024 | 2579/CMD | 07/06/2023 | 486 | MITRA ENTERPRISE | 10.99 | 0 | 100
3902 | Central Mechanical | Central Mechanical Sub-Division | Installation of deptt.supplied Pump·motor set and other allied works at PH-1 of Aug. of Agradip Kashipur water supply scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000486/2024-2025 | 513/DIC/BMSD(D) | 20/08/2024 | 7 | MITRA ENTERPRISE | 0.33 | 0 | 100
3903 | Burdwan Division | Central Mechanical Sub-Division | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Murgram, Moregram, Malgram, Khanji, PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000289/2024-2025 | 2739/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 185.75 | 0 | 72
3904 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MALGRAM, MURGRAM, MORGRAM & KHANJI Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 3387/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 1333.98 | 0 | 40
3905 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000011/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
3906 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000347/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.01 | 0 | 0
3907 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000744/2023-2024 | 5260/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0
3908 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR MURGRAM PWSS PH-I. | Assistant Engineer | Junior Engineer | BILL/00103/2024-2025 | BP-2024-25-44 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.64 | 0 | 0
3909 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Murgram W/S Scheme PH-II. | Assistant Engineer | Junior Engineer | BILL/01807/2023-2024 | BP-2023-24-314 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.25 | 0 | 0
3910 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Murgram W/S Scheme PH-I. | Assistant Engineer | Junior Engineer | BILL/01808/2023-2024 | BP-2023-24-313 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.21 | 0 | 0
3911 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
3912 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MURGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000850/2023-2024 | 4122/CMD | 29/08/2023 | 30 | S.K. ELECTRICALS | 27.77 | 0 | 46
3913 | Central Mechanical | Central Mechanical Sub-Division | Supply & Delivery of 3 Phase actuator operated wafer type butterfly valve for Tube well No.- 1 at MURGRAM Water Supply Scheme [Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/001622/2023-2024 | 348/DIC/BMSD(D) | 22/12/2023 | 7 | SUBRATA BHADRA | 0.98 | 0 | 0
3914 | Central Mechanical | Central Mechanical Sub-Division | Supply & delivery of Submersible Pumping Machinery, Suspension clamp and tube well cover etc. Tube well No.- 1 at MURGRAM Water Supply Scheme [ Block· KETUGRAM -1] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/001627/2023-2024 | 25/DIC/BMSD(D) | 05/01/2024 | 7 | SUBRATA BHADRA | 0.86 | 0 | 100
3915 | Central Mechanical | Central Mechanical Sub-Division | Supply & Delivery of Submersible cable and column pipes for Tube Well No No:-1 at MURGRAM water supply scheme[ Block - KETUGRAM -1] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/001629/2023-2024 | 41/DIC/BMSD(D) | 15/01/2024 | 7 | SUBRATA BHADRA | 0.87 | 0 | 100
3916 | Central Mechanical | Central Mechanical Sub-Division | Supply & delivery of valves, starter and Installation of Submersible Pumping Machinery for Tube well No. - 1 at MURGRAM Water Supply Scheme [ Block- KETUGRAM -1] under CMD, PHE Dte., Dist.· Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/001633/2023-2024 | 48/DIC/BMSD(D) | 19/01/2024 | 15 | SUBRATA BHADRA | 0.69 | 0 | 100
3917 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Murgram W/S Scheme (T/W-I & II) , Ketugram-I Block under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000173/2023-2024 | 1345/CDD | 13/09/2023 | 30 | OSMAN SEKH | 16.61 | 0 | 0
3918 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-06-2024 to 31-08-2024" | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000228/2024-2025 | 918/BSD | 28/05/2024 | 92 | SK. ASFIA | 1.2 | 0 | 60
3919 | Burdwan Division | Burdwan Sadar Sub-Division | PIPULDAHA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000458/2023-2024 | 3440/BWD | 08/08/2023 | 1058 | SK ABDUL HALIM | 644.77 | 0 | 97
3920 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2024 to 31-01-2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000896/2024-2025 | 2438/BSD | 29/10/2024 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
3921 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000371/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 3.55 | 0 | 0
3922 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000417/2023-2024 | 3865/BWD | 01/09/2023 | 0 | Resource Division | 20.78 | 0 | 0
3923 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000687/2023-2024 | 5078/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
3924 | Central Mechanical | Burdwan Sadar Sub-Division | New electric connection for Pipuldaha PWSS. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01868/2023-2024 | BP-2023-24-346 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.54 | 0 | 0
3925 | Central Mechanical | Burdwan Sadar Sub-Division | New electric connection for Pipuldaha PWSS, PH-1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01883/2023-2024 | BP-2023-24-345 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.76 | 0 | 0
3926 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
3927 | Central Mechanical | Burdwan Sadar Sub-Division | Continuation Order- Hiring of inspection vehicle (Diesel /CNG/LPG Driven) for supervision of site for the office of Assistant Engineer under CMD,PHE,Dte. [W.E.F-30.04.2024 to 28.06.2024 ] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000423/2024-2025 | 703/CMSD | 29/04/2024 | 60 | SUBRATA BHADRA | 0.79 | 0 | 0
3928 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Pipuldaha Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000728/2023-2024 | 4039/CMD | 29/08/2023 | 30 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 28.94 | 0 | 50
3929 | Burdwan Division | Burdwan Sadar Sub-Division | Laying parallel 200 mm dia pipeline at Shyamnagar of Alipur pwss under Memari-I Development Block under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000044/2025-2026 | 1026/BSD | 08/05/2025 | 30 | ROHAN MONDAL | 4.92 | 0 | 0
3930 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-II W/S Scheme at Kalsi Mouza, RASULPUR W/S Scheme at 4th TW site & ALIPUR W/S Scheme at 4th TW site under Memari-I Block under within Burdwan Sub-Division, PHE Dte. [For 3 Nos. Tube well]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000159/2023-2024 | 2455/BWD | 31/05/2023 | 60 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 39.76 | 0 | 100
3931 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall and Soak Well at Head Works Site, Extension of Pipe Line at Alipur Adibasipara and Installation of water level indicator of ALIPUR Water Supply Scheme under MEMARI-I Block of Burdwan Division, PHE Dte. (Length -230.00 Mtr, Col-85 Nos). | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000180/2024-2025 | 2300/BWD | 20/06/2024 | 120 | ROHAN MONDAL | 31.47 | 0 | 17
3932 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Alipore PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000394/2023-2024 | 1582/BSD | 24/07/2023 | 15 | MEASURE LAND | 0.78 | 0 | 100
3933 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch rooms & Rising main at different TW site for ALIPUR Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000666/2023-2024 | 4162/BWD | 20/09/2023 | 60 | M/S PALASH BISWAS | 8.12 | 0 | 100
3934 | Burdwan Division | Burdwan Sadar Sub-Division | Replacing damaged PVC water supply line and re installation of FHTC at Shyamnagar for Alipur and its Adjoining Mouza W/S Scheme, block -Memari-I within Burdwan Sub-Division ,PHE Dte | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001085/2024-2025 | 114/BSD | 16/01/2025 | 30 | MUKHERJEE ENTERPRISE | 2.44 | 0 | 80
3935 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for ALIPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001095/2024-2025 | 430/BWD | 20/01/2025 | 287 | DULAL MAJUMDER | 117.26 | 0 | 30
3936 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new electric service connection at Alipur PH NO.-3 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01756/2023-2024 | BP-2023-24-266 | 11/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.78 | 0 | 0
3937 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Alipur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000088/2023-2024 | 2593/CMD | 07/06/2023 | 30 | SOUNAK ENTERPRISE | 22.73 | 0 | 50
3938 | Central Mechanical | Burdwan Sadar Sub-Division | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000564/2024-2025 | 3103/CMD | 11/12/2024 | 60 | S DUTTA | 15.06 | 0 | 0
3939 | Burdwan Division | Katwa Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme KASHIARA PWSS (Sl No-5) | Assistant Engineer |  | ORD/000073/2023-2024 | 397/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 2.62 | 0 | 100
3940 | Burdwan Division | Katwa Sub-Division | Augmentation of KASHIARA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under MONGALKOTE Block, District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/000753/2023-2024 | 4666/BWD | 01/11/2023 | 427 | M/S B. RAI CONSTRUCTION COMPANY | 372.35 | 0 | 30
3941 | Central Mechanical | Katwa Sub-Division | Quotation for new service connection at Augmentation of Kashiara PWSS TW-1 | Assistant Engineer |  | BILL/01088/2024-2025 | BP-2024-25-398 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.75 | 0 | 0
3942 | Central Mechanical | Katwa Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Kashiara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer |  | ORD/000080/2023-2024 | 2580/CMD | 07/06/2023 | 710 | GLACIER ENGINEERING CO | 11.03 | 0 | 100
3943 | Central Mechanical | Katwa Sub-Division | Yard lighting arrangement & allied works at Kasiara water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer |  | ORD/000409/2024-2025 | 2789/CMD | 01/10/2024 | 60 | BABA MALLESHWAR ENTERPRISE. | 5.55 | 0 | 0
3944 | Burdwan Division | Central Mechanical Sub-Division | CHAR SUJAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM -II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000179/2023-2024 | 3032/BWD | 14/07/2023 | 365 | M/S H.R. CONSTRUCTION | 471.47 | 0 | 91
3945 | Burdwan Division | Central Mechanical Sub-Division | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house & OHR under Charsujapur PWSS, Block-Ketugram-II under Katwa Sub Division within Burdwan division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000360/2024-2025 | 2923/BWD | 26/07/2024 | 90 | M/S H.R. CONSTRUCTION | 81.31 | 0 | 2
3946 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000016/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.28 | 0 | 0
3947 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000299/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.58 | 0 | 0
3948 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000746/2023-2024 | 5254/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0
3949 | Central Mechanical | Central Mechanical Sub-Division | New service connection for Char Sujapur PWSS PH-1. | Assistant Engineer | Junior Engineer | BILL/02288/2023-2024 | BP-2023-24-414 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.99 | 0 | 0
3950 | Central Mechanical | Central Mechanical Sub-Division | New service connection for Char Sujapur PWSS PH-2. | Assistant Engineer | Junior Engineer | BILL/02289/2023-2024 | BP-2023-24-415 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.27 | 0 | 0
3951 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0
3952 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAR SUJAPUR Water Supply Scheme [ Block- KETUGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000866/2023-2024 | 4118/CMD | 29/08/2023 | 550 | M/S. S.R. ENTERPRISE | 29.41 | 0 | 46
3953 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Char Sujapur Water Supply Scheme [ BLOCK- Ketugram-II] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/001394/2024-2025 | 883/CMD | 26/03/2025 | 60 | CHATTERJEE ENTERPRISE | 12.31 | 0 | 0
3954 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMEGERIA, ARGUN, CHINISPUR & KULUTIA Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000533/2023-2024 | 3630/BWD | 21/08/2023 | 1107 | M/S GOUTAM DAS | 1421.7 | 0 | 75
3955 | Burdwan Division | Central Mechanical Sub-Division | Hiring of one no Diesel Motor Cab (BS-VI) including the cost of fuel . mobile & other charges for the inspection of the different projects of JJM for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. (Period:- 01/03/2025 to 31/08/2025) [Sl No-02] | Assistant Engineer | Junior Engineer | ORD/001324/2024-2025 | 321/KTS | 28/02/2025 | 184 | HAMID SK | 1.84 | 0 | 0
3956 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000097/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.34 | 0 | 0
3957 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000235/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 20.24 | 0 | 0
3958 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000747/2023-2024 | 5255/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0
3959 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection CHINISPUR PWSS TW No. 2. | Assistant Engineer | Junior Engineer | BILL/00777/2024-2025 | BP-2024-25-296 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.51 | 0 | 0
3960 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection Chinispur PWSS TW No. 1. | Assistant Engineer | Junior Engineer | BILL/00780/2024-2025 | BP-2024-25-295 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.07 | 0 | 0
3961 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
3962 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHINISPUR Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000868/2023-2024 | 4116/CMD | 29/08/2023 | 640 | M/S, S.S. ENTERPRISE. | 28.48 | 0 | 88
3963 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Chinispur W/S Scheme (T/W-I & II) , Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000162/2023-2024 | 1054 | 16/08/2023 | 30 | OSMAN SEKH | 16.61 | 0 | 0
3964 | Burdwan Division | Burdwan Sadar Sub-Division | Replacement of Tube-well & Rising main at Head work TW site for BARWA Piped Water Supply Scheme under MEMARI-II Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000226/2024-2025 | 2523/BWD | 03/07/2024 | 90 | ROY ENTERPRISE | 15.27 | 0 | 80
3965 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of BERWA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000587/2023-2024 | 3743/BWD | 28/08/2023 | 942 | ROY ENTERPRISE | 334.82 | 0 | 65
3966 | Burdwan Division | Burdwan Sadar Sub-Division | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/001269/2024-2025 | 848/BWD | 05/03/2025 | 120 | PROJECT INDIA | 394.29 | 0 | 0
3967 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | BILL/02827/2023-2024 | BP-2023-24-594 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.25 | 0 | 0
3968 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Berawa Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000101/2023-2024 | 2600/CMD | 07/06/2023 | 755 | SOUNAK ENTERPRISE | 22.6 | 0 | 50
3969 | Central Mechanical | Burdwan Sadar Sub-Division | Illumination arrangement & different electro-mechanical works at BARWA water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000443/2024-2025 | 2796/CMD | 01/10/2024 | 60 | A.K. ENTERPRISE | 11.65 | 0 | 60
3970 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of GHOSH W/S Scheme under Memari-I Block within Burdwan Sub-Division, PHE Dte. [For Bahabpur village]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000200/2023-2024 | 2703/BWD | 08/06/2023 | 30 | DAS CONSTRUCTION | 13.25 | 0 | 0
3971 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of GHOSH PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000365/2023-2024 | 1527/BSD | 17/07/2023 | 15 | MEASURE LAND | 0.78 | 0 | 0
3972 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, making and erection of Sign Board for SWAJAL GRAM in Mandaljana village of Memari-I Block under Ghosh Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. (5 nos Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000496/2025-2026 | 2365/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0
3973 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch rooms & Rising main at different TW site for GHOSH Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000865/2023-2024 | 5296/BWD | 01/12/2023 | 60 | TRIYA CONSTRUCTION | 8.94 | 0 | 0
3974 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline & Left out FHTC Connection work for GHOSH Piped Water Supply Scheme at Bahabpur village [200 Nos], Andur [40 Nos], Tanti Gantar [80 Nos], Kabirpur [48 Nos], Total 368 Nos FHTC Work for Sajal Gram within Memari-I Block including leftout household water tap connection (FHTC) under BURDWAN Division, P.H.E Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001075/2023-2024 | 1021/BWD | 07/03/2024 | 336 | SKILLS AND FACILITY TRAINING INSTITUTE | 21.53 | 0 | 99
3975 | Burdwan Division | Burdwan Sadar Sub-Division | Allied work of Laying distribution system for FHTC work for GHOSH Piped Water Supply Scheme at Bahabpur mouza within MEMARI - I BLOCK under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001083/2024-2025 | 113/BSD | 16/01/2025 | 45 | A.R. TRADERS | 4.7 | 0 | 100
3976 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for GHOSH PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001193/2024-2025 | 612/BWD | 11/02/2025 | 90 | PAL CONSTRUCTION | 29.22 | 0 | 0
3977 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Ghosh Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000100/2023-2024 | 2588/CMD | 07/06/2023 | 30 | SUDIPTA GHOSH | 11.26 | 0 | 0
3978 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of voltage correcting device. LED fixture set & allied works at GHOSH Water Supply Scheme PH-II under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000148/2024-2025 | 1037/CMSD | 26/07/2024 | 30 | BENGAL ELECTRICAL CONSTRUCTION | 3.28 | 0 | 100
3979 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of KALYANPUR (SM/16299) Water Supply Scheme & BHABANANDAPUR (SM/16024) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000189/2024-2025 | 2433/BWD | 27/06/2024 | 247 | BALAJEE ENTERPRISES | 225.16 | 0 | 2
3980 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000069/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 44.37 | 0 | 0
3981 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000251/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.56 | 0 | 0
3982 | Central Mechanical | Kalna Sub-division | Quotation for new service connection for Bhabanandapur PWSS PH-2. | Assistant Engineer |  | BILL/00284/2024-2025 | BP-2024-25-144 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.78 | 0 | 0
3983 | Central Mechanical | Kalna Sub-division | Additional quotation for Bhavanandapur PWSS PH-1 | Assistant Engineer |  | BILL/00427/2024-2025 | BP-2024-25-223 | 26/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.67 | 0 | 0
3984 | Central Mechanical | Kalna Sub-division | New service connection for BHABANANDAPUR PWSS TW-1. | Assistant Engineer |  | BILL/02394/2023-2024 | BP-2023-24-500 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.85 | 0 | 0
3985 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer |  | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 20
3986 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BHABANANDAPUR Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer |  | ORD/000922/2023-2024 | 4161/CMD | 29/08/2023 | 521 | SOUNAK ENTERPRISE | 28.48 | 0 | 95
3987 | Burdwan Division | Kalna Sub-division | Construction of Pipe carrying Truss Bridge for carrying 200 mm dia MS Pipe at PWD Bridge under Hatgachha Mouza under the command area of Balindar PWSS (SM/16478) within Kalna -II block of Kalna Sub-Division, PHE Dte under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000017/2025-2026 | 1244/BWD | 23/04/2025 | 60 | M/S DATTA ENTERPRISE | 29.3 | 0 | 1
3988 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALINDAR, CHAK SHIMLA & DWARIATAN Piped Water Supply Scheme under Kalna II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000539/2023-2024 | 3700/BWD | 24/08/2023 | 770 | SUPRITI ENTERPRISE | 1424.22 | 0 | 30
3989 | Burdwan Division | Kalna Sub-division | Work order for "Restoration of pipeline with other allied works at different places of Bharkunda,potna,Bara dhamash,Balindar,Tola mouja under Balindar Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-II panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | JUNIOR ENGINEER | ORD/000858/2024-2025 | 1844/KSD | 27/11/2024 | 15 | SUPRITI ENTERPRISE | 2.86 | 0 | 0
3990 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR BALINDAR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001150/2023-2024 | 2106/KSD | 04/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0 | 2
3991 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000056/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 45.18 | 0 | 0
3992 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000204/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.21 | 0 | 0
3993 | Central Mechanical | Kalna Sub-division | New service connection charges for Balindar PWSS TW-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01867/2023-2024 | BP-2023-24-357 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.2 | 0 | 0
3994 | Central Mechanical | Kalna Sub-division | New service connection for BALINDAR PWSS TW-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/02401/2023-2024 | BP-2023-24-503 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.97 | 0 | 0
3995 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 20
3996 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BALINDAR Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000858/2023-2024 | 4126/CMD | 29/08/2023 | 756 | ASIA CONSTRUCTION. | 28.98 | 0 | 90
3997 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation for the work of Supply of one No. Diesel Driven Car (other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. (Period from 01-05-2025 to 30-06-2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000045/2025-2026 | 113/RWS | 30/04/2025 | 61 | MD HASIN | 0.8 | 0 | 0
3998 | Burdwan Division | Burdwan Sadar Sub-Division | Upgradation of Boundary wall, Drain & land development at Head work site for SHAKTIGAR PWSS under Burdwan-Sub Div, Block-Burdwan II under Burdwan Div. PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000051/2025-2026 | 1425/BWD | 20/05/2025 | 30 | SARKAR AGENCY | 5.39 | 0 | 0
3999 | Burdwan Division | Burdwan Sadar Sub-Division | Crossing of Old G.T Road near Head Works with 250 mm dia pipeline through pushing of 750mm.dia RCC casing pipe by hydraulic jacking method for Saktigarh W/S Scheme (Augmentation) under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000083/2024-2025 | 153/RWS | 29/04/2024 | 25 | IJABUL SEKH | 6.55 | 0 | 100
4000 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of one No. Diesel Driven Car ( other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. (Period from 01-07-2024 to 31-08-2024). | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000364/2024-2025 | 207/RWS | 28/06/2024 | 61 | MD HASIN | 0.8 | 0 | 0
4001 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of SAKTIGARH Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & Construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under BARDHAMAN-II Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000896/2023-2024 | 5376/BWD | 07/12/2023 | 390 | IJABUL SEKH | 203.46 | 0 | 50
4002 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation for the work of Supply of one No. Diesel Driven Car (other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. (Period from 01-01-2025 to 28-02-2025). | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000995/2024-2025 | 413/RWS | 31/12/2024 | 59 | MD HASIN | 0.79 | 0 | 0
4003 | Burdwan Division | Burdwan Sadar Sub-Division | Protection of LDS of Saktigarh PWSS Augmentation at the node point of 36-44-64 under Burdwan Division, PHE Dte. [SM-16479] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001168/2023-2024 | 92/RWS | 13/03/2024 | 20 | KHUSI BHAKAT | 0.78 | 0 | 100
4004 | Burdwan Division | Burdwan Sadar Sub-Division | Protection of LDS of Saktigarh PWSS Augmentation at the node point of 75-123 under Burdwan Division, PHE Dte. [SM-16479] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001169/2023-2024 | 93/RWS | 13/03/2024 | 20 | GHOSH ENTERPRISE | 0.79 | 0 | 100
4005 | Burdwan Division | Burdwan Sadar Sub-Division | Protection work of LDS and approach road to 2nd Pump-House of Saktigarh PWSS Augmentation at the node point of 161-166 under Burdwan Division, PHE Dte. [SM-16479] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001170/2023-2024 | 94/RWS | 13/03/2024 | 20 | JAYANTA CHAKRABORTY | 0.95 | 0 | 100
4006 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work for the supply of one no. Diesel driven Motor Cab/Maxi Cab (Air Conditioner) on hire basis for the office of the Assistant Engineer, to be used by the Assistant Engineer, RWS Burdwan Sub-Divn., PHE. Dte. (Period from 01/01/2024 to 29/02/2024) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001221/2023-2024 | 403/RWS | 29/12/2023 | 62 | MD HASIN | 0.8 | 0 | 0
4007 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new service connection for Shaktigarh PWSS PH-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00294/2024-2025 | BP-2024-25-183 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.48 | 0 | 0
4008 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new service connection at Augmentation of Shaktigarh W/S Scheme TW-3. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00372/2024-2025 | BP-2024-25-184 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.01 | 0 | 0
4009 | Central Mechanical | Burdwan Sadar Sub-Division | Additional quotation for conversion of HTOH line from HT at Saktigarh (Aug) PWSS. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00442/2024-2025 | BP-2024-25-231 | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.08 | 0 | 0
4010 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Saktigrah Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000098/2023-2024 | 2587/CMD | 07/06/2023 | 755 | P.K. ENGINEERING | 22.69 | 0 | 100
4011 | Central Mechanical | Burdwan Sadar Sub-Division | Illumination arrangement & different electro-mechanical works at SAKTIGARH water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000479/2024-2025 | 2956/CMD | 20/11/2024 | 60 | CHOUDHURY ENTERPRISE | 14.34 | 0 | 0
4012 | Burdwan Division | Kalna Sub-division | SADHPUKHARIA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER | ORD/000061/2023-2024 | 1934/BWD | 24/04/2023 | 313 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 72 | 0 | 30
4013 | Burdwan Division | Kalna Sub-division | Continuation work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) for the Office of the Assistant Engineer, Kalna Sub-Division, Burdwan Division, P.H.E. Dte. [Period - 01.06.2024 to 30.11.2024]" (Vehicle No-WB 25K 4575) | Assistant Engineer | JUNIOR ENGINEER | ORD/000461/2024-2025 | 273/KSD | 30/05/2024 | 183 | SUSMITA MANDAL | 2.4 | 0 | 0
4014 | Burdwan Division | Kalna Sub-division | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) for the Office of the Assistant Engineer, Kalna Sub-Division, Burdwan Division, P.H.E. Dte. [Period from 01.12.2023 to 31.05.2024] (Vehicle No-WB 25K 4575). | Assistant Engineer | JUNIOR ENGINEER | ORD/000982/2023-2024 | 1680/KSD | 22/11/2023 | 183 | SUSMITA MANDAL | 0.87 | 0 | 23
4015 | Burdwan Division | Kalna Sub-division | Continuation work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) for the Office of the Assistant Engineer, Kalna Sub-Division, Burdwan Division, P.H.E. Dte. [Period from 01.12.2024 to 28.02.2025]". [Vehicle No- WB 25K 4575]. | Assistant Engineer | JUNIOR ENGINEER | ORD/001066/2024-2025 | 1896/KSD | 29/11/2024 | 91 | SUSMITA MANDAL | 1.2 | 0 | 0
4016 | Burdwan Division | Kalna Sub-division | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) for the Office of the Assistant Engineer, Kalna Sub-Division, Burdwan Division, P.H.E. Dte. [Period from 01.03.2025 to 31.05.2025]". [Vehicle No- 25 K 4575]. | Assistant Engineer | JUNIOR ENGINEER | ORD/001243/2024-2025 | 316/KSD | 28/02/2025 | 92 | SUSMITA MANDAL | 1.2 | 0 | 1
4017 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000048/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
4018 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000185/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 15.09 | 0 | 0
4019 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000617/2023-2024 | 4884/BWD | 10/11/2023 | 0 | Resource Division | 33.21 | 0 | 0
4020 | Central Mechanical | Kalna Sub-division | New service connection charges for Sadhpukuria PWSS TW-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01488/2023-2024 | BP-2023-24-185 | 04/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0
4021 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SADHPUKHRIA Water Supply Scheme [ Block- KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | Assistant Engineer | JUNIOR ENGINEER | ORD/000864/2023-2024 | 4131/CMD | 29/08/2023 | 30 | SIMARR | 20.64 | 0 | 71
4022 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAJITPUR, SHUKUR & HARISHNAPUR Piped Water Supply Scheme under RAINA-I Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000388/2023-2024 | 3197/BWD | 24/07/2023 | 907 | MRITYUNJOY MUKHERJEE & CO. | 1242.03 | 0 | 55
4023 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-09-2024 to 30-11-2024 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000682/2024-2025 | 1957/BSD | 30/08/2024 | 91 | SK. ASFIA | 1.2 | 0 | 60
4024 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000220/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.46 | 0 | 0
4025 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000479/2023-2024 | 4003/BWD | 08/09/2023 | 0 | Resource Division | 9.08 | 0 | 0
4026 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000647/2023-2024 | 5096/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
4027 | Central Mechanical | Burdwan Sadar Sub-Division | New electric connection for Bajitpur PWSS, PH-1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01887/2023-2024 | BP-2023-24-358 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.31 | 0 | 0
4028 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bajitpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000717/2023-2024 | 4028/CMD | 29/08/2023 | 30 | SAIKAT ENTERPRISE | 28.98 | 0 | 0
4029 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Natungram PWSS under Burdwan-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000347/2023-2024 | 1474/BSD | 12/07/2023 | 15 | MEASURE LAND | 0.78 | 0 | 100
4030 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
4031 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of NATUNGRAM Piped Water Supply Scheme Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & Rising Main under BARDHAMAN-I Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000579/2023-2024 | 3726/BWD | 25/08/2023 | 915 | BASU ENTERPRISE | 72.82 | 0 | 90
4032 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for NATUNGRAM and KHETIA Piped Water Supply Scheme, Block-Burdwan-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001003/2024-2025 | 007/BWD | 02/01/2025 | 211 | M/S UNIQUE | 33.59 | 0 | 80
4033 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ONARI & SASANGA Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL |  |  | ORD/000452/2023-2024 | 3430/BWD | 07/08/2023 | 786 | M/S JAN MAHAMMAD | 1398.82 | 0 | 50
4034 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 4116/BWD | 25/11/2024 | 0 | Resource Division | 22.79 | 0 | 0
4035 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000296/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 6.45 | 0 | 0
4036 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000405/2023-2024 | 3827/BWD | 01/09/2023 | 0 | Resource Division | 17.67 | 0 | 0
4037 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000574/2023-2024 | 4923/BWD | 10/11/2023 | 0 | Resource Division | 41.11 | 0 | 0
4038 | Central Mechanical |  | Quotation for new service connection for Sasanga PWSS PH 2. |  |  | BILL/00229/2024-2025 | BP-2024-25-120 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.09 | 0 | 0
4039 | Central Mechanical |  | New service connection charges for Sasanga PWSS TW-1 |  |  | BILL/02209/2023-2024 | BP-2023-24-400 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.46 | 0 | 0
4040 | Central Mechanical |  | New service connection charges for Sasanga PWSS TW-2 |  |  | BILL/02210/2023-2024 | BP-2023-24-401 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.5 | 0 | 0
4041 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0
4042 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SASANGA Water Supply Scheme [ Block-KHONDOGHOSH ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000921/2023-2024 | 4185/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 45.37 | 0 | 90
4043 | Burdwan Division |  | Land demarcation and preparation of sketch map for Haldi, Sultanpur, Berugram & Karail Piped W/S. Scheme (New Scheme) at different Blocks under JJM under Burdwan Division, PHE Dte. |  |  | ORD/000756/2023-2024 | 842/AE/HQ | 01/11/2023 | 15 | M/S S. CHOUDHURY | 0.33 | 0 | 100
4044 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BERUGRAM & SULTANPUR Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000979/2023-2024 | 092/BWD | 05/01/2024 | 604 | SK ALIM | 1368.51 | 0 | 55
4045 | Burdwan Division |  | Balance work of BERUGRAM & SULTANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman. |  |  | ORD/001214/2024-2025 | 723/BWD | 24/02/2025 | 180 | MD HASIN | 438.83 | 0 | 0
4046 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000327/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.55 | 0 | 0
4047 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000522/2023-2024 | 4301/BWD | 29/09/2023 | 0 | Resource Division | 6.53 | 0 | 0
4048 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000695/2023-2024 | 5071/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
4049 | Central Mechanical |  | Quotation for new service connection at SULTANPUR W/S Scheme PH-I. |  |  | BILL/01812/2023-2024 | BP-2023-24-324 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.49 | 0 | 0
4050 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0
4051 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sultanpur Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000707/2023-2024 | 4018/CMD | 29/08/2023 | 30 | SUBRATA BHADRA | 28.96 | 0 | 0
4052 | Burdwan Division |  | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-06-2024 to 31-08-2024" |  |  | ORD/000228/2024-2025 | 918/BSD | 28/05/2024 | 92 | SK. ASFIA | 1.2 | 0 | 60
4053 | Burdwan Division |  | SANUI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000503/2023-2024 | 3536/BWD | 10/08/2023 | 783 | M/S ASHA CONSTRUCTION | 825.12 | 0 | 35
4054 | Burdwan Division |  | Restoration of Conc. road, Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for MAGRA, SANUI, SATGACHIA Zone-I & NARAGOHALIA PIPED WATER SUPPLY SCHEME, Block-Memari-I, within Burdwan Sub Division under Burdwan Division PHE Dte. |  |  | ORD/001192/2024-2025 | 611/BWD | 11/02/2025 | 180 | M/S ASHA CONSTRUCTION | 354.13 | 0 | 25
4055 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000017/2024-2025 | 4107/BWD | 25/11/2024 | 0 | Resource Division | 15.04 | 0 | 0
4056 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000284/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.15 | 0 | 0
4057 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000434/2023-2024 | 3852/BWD | 01/09/2023 | 0 | Resource Division | 13.05 | 0 | 0
4058 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000573/2023-2024 | 4943/BWD | 10/11/2023 | 0 | Resource Division | 41.11 | 0 | 0
4059 | Central Mechanical |  | New service connection for Sanui W/S Scheme. |  |  | BILL/02185/2023-2024 | BP-2023-24-381 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.95 | 0 | 0
4060 | Central Mechanical |  | New service connection for Sanui W/S Scheme. |  |  | BILL/02186/2023-2024 | BP-2023-24-380 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 15.93 | 0 | 0
4061 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0
4062 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SANUI Water Supply Scheme [ Block- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000785/2023-2024 | 4077/CMD | 29/08/2023 | 672 | JAL PRAVAHIKA PVT LTD | 44.08 | 0 | 70
4063 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PALISGRAM, PURBA NAYAPARA & SITAHATI Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000695/2023-2024 | 4364/BWD | 04/10/2023 | 910 | M/S S. CHOUDHURY | 1505.07 | 0 | 77
4064 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 4114/BWD | 25/11/2024 | 0 | Resource Division | 17.51 | 0 | 0
4065 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000360/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 2.93 | 0 | 0
4066 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000529/2023-2024 | 4304/BWD | 29/09/2023 | 0 | Resource Division | 1.53 | 0 | 0
4067 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000567/2023-2024 | 4939/BWD | 10/11/2023 | 0 | Resource Division | 27.8 | 0 | 0
4068 | Central Mechanical |  | NEW SERVICE CONNECTION FOR PALISHGRAM PWSS. |  |  | BILL/00006/2024-2025 | BP-2024-25-2 | 04/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.96 | 0 | 0
4069 | Central Mechanical |  | NEW SERVICE CONNECTION FOR PALISHGRAM PH -2 PWSS. |  |  | BILL/00007/2024-2025 | BP-2024-25-3 | 04/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.87 | 0 | 0
4070 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
4071 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at PALISGRAM Water Supply Scheme [ Block-MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000870/2023-2024 | 4133/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 44.62 | 0 | 63
4072 | Burdwan Division |  | GIDHGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000453/2023-2024 | 3431/BWD | 07/08/2023 | 786 | POWER TOOLS & ENGINEERING | 671.42 | 0 | 31
4073 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000265/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.31 | 0 | 0
4074 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000491/2023-2024 | 4015/BWD | 08/09/2023 | 0 | Resource Division | 74.64 | 0 | 0
4075 | Central Mechanical |  | Quotation for new service connection at Gidhgram PWSS TW 3. |  |  | BILL/01223/2024-2025 | BP-2024-25-413 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.54 | 0 | 0
4076 | Central Mechanical |  | New service connection for Gidhagram PWSS PH-3 |  |  | BILL/02283/2023-2024 | BP-2023-24-420 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.9 | 0 | 0
4077 | Central Mechanical |  | NEW SERVICE CONNECTION FOR GIDHGRAM PWSS TW 2. |  |  | BILL/02488/2023-2024 | BP-2023-24-534 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.91 | 0 | 0
4078 | Central Mechanical |  | NEW SERVICE CONNECTION FOR GIDHGRAM PWSS TW 1 |  |  | BILL/02955/2023-2024 | BP-2023-24-635 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.48 | 0 | 0
4079 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0
4080 | Central Mechanical |  | CONTINUATION ORDER-Hiring of inspection vehicle bearing no WB41H5698 (Disel/CNG/LPG driven) for supervision of JJM works under jurisdiction of the Assistant Engineer CMSD PHE Dte .[W.E.F- 01/11/2025 TO 31/12/2025] |  |  | ORD/000393/2025-2026 | 1436/CMSD | 29/10/2025 | 61 | SUBRATA BHADRA | 0.81 | 0 | 0
4081 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at GIDHGRAM Water Supply Scheme [ Block-KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000873/2023-2024 | 4136/CMD | 29/08/2023 | 605 | M/S, S.S. ENTERPRISE. | 45.53 | 0 | 64
4082 | Burdwan Division |  | Restoration work of Kalna baidyapur road from 7.90 km to 13.75 km (in stretches) damaged due to laying of underground water pipe line by PHE with box cutting and Jhama with moorum consolidation under Kalna Highway Sub-Division of Burdwan South Highway Division, P.W (Roads) Dte. during the year 2023-2024. |  |  | BILL/00890/2024-2025 | 1025/JJM | 05/10/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 8.1 | 0 | 0
4083 | Burdwan Division |  | Restoration work of Kulti Haritala to Jamna Bus stand via Krishnapur, Baharkuli,Sargoria road from 3.15 km to 5.70 km, damaged due to laying of underground water pipe line by PHE with box cutting and Jhama with moorum consolidation under Kalna Highway Sub Division of Burdwan South Highway Division, P.W(Roads) Dte. during the year 2023-24. |  |  | BILL/00891/2024-2025 | 1025/JJM | 05/10/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 5.36 | 0 | 0
4084 | Burdwan Division |  | Work order for Repairing of leakage of existing pipe line of Nasaratpur habitation of Purbasthali-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000124/2023-2024 | 419/KSD | 11/05/2023 | 30 | PARTHA PRATIM ACHARYA | 0.97 | 0 | 50
4085 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of NASARATPUR Piped Water Supply Scheme at Purbasthali-I Block under Burdwan Division, PHE Dte._2ND CALL. |  |  | ORD/000174/2021-2022 | 6079/BWD | 08/10/2021 | 60 | BRINDABAN KONAR | 54.89 | 0 | 1
4086 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of NASARATPUR Piped Water Supply Scheme at Gopinathpur (Part), Nasaratput (Part) & Paruldanga (Part) Village (Mouza), Purbasthali - I Block under Burdwan Division, PHE Dte |  |  | ORD/000372/2021-2022 | 211/BWD | 11/01/2022 | 60 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 76.77 | 0 | 1
4087 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SIMULIA & LAKSHIMPUR Piped Water Supply Scheme under Mongalkote Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000694/2023-2024 | 4363/BWD | 04/10/2023 | 727 | PUSPA ENTERPRISE | 1090.95 | 0 | 37
4088 | Burdwan Division |  | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/001301/2024-2025 | 936/BWD | 11/03/2025 | 180 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0
4089 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000323/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.62 | 0 | 0
4090 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000528/2023-2024 | 4303/BWD | 29/09/2023 | 0 | Resource Division | 4.13 | 0 | 0
4091 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000809/2023-2024 | 307/BWD | 24/01/2024 | 0 | Resource Division | 32.21 | 0 | 0
4092 | Central Mechanical |  | New service connection charges for Simulia PWSS TW-2 |  |  | BILL/02196/2023-2024 | BP-2023-24-377 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.22 | 0 | 0
4093 | Central Mechanical |  | New service connection charges for Shimulia PWSS TW-1 |  |  | BILL/02197/2023-2024 | BP-2023-24-376 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.42 | 0 | 0
4094 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
4095 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SIMULIA Water Supply Scheme [ Block- MONGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000796/2023-2024 | 4084/CMD | 29/08/2023 | 610 | P.K. ENGINEERING | 41.62 | 0 | 31
4096 | Burdwan Division | Kalna Sub-division | NAME OF THE WORK -RESTORATION WORK OF BIDYANAGAR TO VIA DAMODAR PARA TO BOGPUR ROAD,PACKAGE NO-WB-22-27,BLOCK-PURBASTHALI-1,GP-SRIRAMPUR & JAHANNAGAR. | Assistant Engineer |  | BILL/00739/2024-2025 | 893/JJM | 25/09/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 5.21 | 0 | 0
4097 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Srirampur Piped Water Supply Scheme at Srirampur (Srirampur & Srirampur East Para Habitation) Village (Mouza), Purbasthali-I Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000091/2021-2022 | 3654/BWD | 14/07/2021 | 60 | ASHOK KUMAR GHOSH | 102.42 | 0 | 1
4098 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of SRIRAMPUR (Zone I & II) (SM/08103), MANGANPUR (SM/13327), KAMALPUR (SM/13453) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000190/2024-2025 | 2429/BWD | 27/06/2024 | 480 | S.P. CONSTRUCTION | 500.89 | 0 | 2
4099 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Srirampur Piped Water Supply Scheme at Srirampur Northpara, Srirampur Southpara & Srirampur Westpara within Srirampur (P) Village (Mouza), Purbasthali-I Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000283/2021-2022 | 7002/BWD | 16/12/2021 | 60 | HAMID SK | 71.23 | 0 | 1
4100 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 1ST TW Site of SRIRAMPUR & its adjoining mouzas Piped Water Supply Scheme, Block ? Purbasthali ? I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000548/2022-2023 | 5127/BWD | 21/11/2022 | 30 | M/S SYCHROTECH INDUSTRY | 8.73 | 0 | 0
4101 | Burdwan Division | Kalna Sub-division | Work order for " Providing Functional house hold tap connections for Sajal Gram Village within Purbasthali-I Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Nadanghat & others scheme) Sl No-7" | Assistant Engineer |  | ORD/000690/2022-2023 | 103/KSD | 08/02/2023 | 28 | MOMINUL ISLAM MONDAL | 0.88 | 0 | 0
4102 | Burdwan Division | Kalna Sub-division | Laying of additional UPVC pipeline for interconnection with main line to branch line of SRIRAMPUR Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000710/2023-2024 | 4522/BWD | 12/10/2023 | 30 | JAMALUDDIN SK | 6.16 | 0 | 100
4103 | Burdwan Division | Kalna Sub-division | Bypass arrangement of rising main and providing Functional house hold tap connections at Srirampur GP within Purbasthali-I Block under SRIRAMPUR PWSS under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000715/2022-2023 | 889/BWD | 01/03/2023 | 30 | JAMALUDDIN SK | 13.01 | 0 | 0
4104 | Burdwan Division | Katwa Sub-Division | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the month of May & June'23. | Assistant Engineer |  | BILL/00791/2023-2024 | 632/JJM | 13/09/2023 | 0 | PARTHA PRATIM ACHARYA | 0.77 | 0 | 0
4105 | Burdwan Division | Katwa Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme AGRADWIP, KHETPUR PALASHI, SAHAPUR PWSS (Sl No-1) | Assistant Engineer |  | ORD/000069/2023-2024 | 393/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 3.71 | 0 | 100
4106 | Burdwan Division | Katwa Sub-Division | Augmentation of SAHAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & renovation of switch-rooms & boundary walls at different TW site under Katwa-II Block, District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/000132/2023-2024 | 2343/BWD | 22/05/2023 | 120 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 137.76 | 0 | 95
4107 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Pt-A) village of Sahapur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL.No : 11A] (Agreement no. 500/BWD of 2020-21) | Assistant Engineer |  | ORD/000143/2020-2021 | 2608/BWD | 04/08/2020 | 30 | RAINBOW CONSTRUCTION | 4.92 | 4.92 | 1
4108 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Pt-A) village of Sahapur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL.No : 11A] (Agreement no.505/BWD of 2020-21) | Assistant Engineer |  | ORD/000144/2020-2021 | 2607/BWD | 04/08/2020 | 30 | DUBE ENTERPRISE | 4.92 | 4.92 | 1
4109 | Burdwan Division | Katwa Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Pt-B) village of Sahapur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL.No : ¿11B¿](Agreement no.-497/BWD of 2020-21) | Assistant Engineer |  | ORD/000146/2020-2021 | 4913/BWD | 08/12/2020 | 30 | DUBE ENTERPRISE | 2.84 | 0 | 1
4110 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in SAHAPUR (Part-B) village of Sahapur piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-494/BWD/2020-21) | Assistant Engineer |  | ORD/000174/2020-2021 | 239/KTS | 30/09/2020 | 4 | DUBE ENTERPRISE | 1.42 | 1.41 | 1
4111 | Burdwan Division | Katwa Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Part-A) village of Sahapur piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-503/BWD/20-21) | Assistant Engineer |  | ORD/000176/2020-2021 | 238/KTS | 30/09/2020 | 4 | RAINBOW CONSTRUCTION | 1.45 | 1.45 | 1
4112 | Burdwan Division | Katwa Sub-Division | Continuation work order for Supply of 1 (one) No. Diesel driven Ambassador Car (Luxury Taxi) / Motor Cab on hire basis for the Office of the Assistant Engineer, under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.07.2024 to 31.12.2024]. | Assistant Engineer |  | ORD/000562/2024-2025 | 788/KTS | 28/06/2024 | 183 | KRISHNA MONDAL | 2.4 | 0 | 80
4113 | Burdwan Division | Katwa Sub-Division | Publication charges bill for the office of the Executive Engineer, Burdwan Division, PHE Dte.[Invoice No.-BCWB20RV-0001293, dt.-19/05/20, BCWB20RV-0001770, dt.-31/05/20, BCWB20RV-0001920, dt.-05/06/20, BCWB20RV-0001860, dt.-03/06/20, BCWB20RV-0001861, dt.-03/06/20, BCWB20RV-0001928, dt.-05/06/20, BCWB20RV-0001820, dt.-03/06/20, BCWB19RV-0059455, dt.-20/03/20, BCWB19RV-0059454. dt.-20/03/20, BCWB19RV-0057682, dt.-12/03/20, BCWB20RV-0003210, dt.-26/06/20, BCWB20RV-0000918, dt.-07/05/20, BCWB20RV-0001352, dt.-22/05/20, BCWB19RV-0050592, dt.-30/01/20] | Assistant Engineer |  | VCH/000411/2022-2023 | 240/DW/22-23 | 04/07/2022 | 0 | BENNETT COLEMAN & COMPANY LIMITED | 1.89 | 0 | 0
4114 | Burdwan Division |  | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of March to September'2022. |  |  | BILL/00145/2022-2023 | 866/VEH | 09/12/2022 | 0 | PARTHA PRATIM ACHARYA | 2.79 | 0 | 0
4115 | Burdwan Division |  | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-4]. |  |  | ORD/000004/2021-2022 | 3117/BWD | 02/06/2021 | 30 | PREMANANDA ROY BISWAS | 76.65 | 13.53 | 0
4116 | Burdwan Division |  | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-5]. |  |  | ORD/000090/2021-2022 | 3590/BWD | 13/07/2021 | 30 | PREMANANDA ROY BISWAS | 127.5 | 41.14 | 1
4117 | Burdwan Division |  | Supply of 10 mm NB Gun-Metal Ferrule conforming to IS:2692-1989 for water tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-4] |  |  | ORD/000108/2021-2022 | 3186/BWD | 08/06/2021 | 30 | R.K. INDUSTRIES | 76.05 | 25.03 | 0
4118 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MANIKHAR Piped Water Supply Scheme at Kalna-I Block under Burdwan Division, PHE Dte. (Agreement No. 47/2020-2021 OF SE/CC/PHE. DTE.) |  |  | ORD/000113/2020-2021 | 4787/BWD | 02/12/2020 | 90 | H SAMANTA | 96.04 | 0 | 1
4119 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PANUHAT Piped Water Supply Scheme at different villages, Katwa-I Block under Burdwan Division, PHE Dte. (Part-A).[Agreement No. 727/BWD OF 2020-2021.] |  |  | ORD/000326/2020-2021 | 1688/BWD | 24/02/2021 | 45 | HAMID SK | 35.66 | 16.34 | 0
4120 | Burdwan Division | Burdwan Sadar Sub-Division | Improvement of 300cum. OHR (Concreting,Plastering,Primer and Painting) for Abujhati PWSS under Jamalpur Block under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000134/2024-2025 | 1015/BSD | 07/06/2024 | 45 | DEBASHISH ENTERPRISE | 2.01 | 0 | 0
4121 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for providing functional household tap connection at Dastanpur & Keotara village (Mouza) of ABUJHATI piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Gr.-D) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000154/2021-2022 | 1091/BSD | 18/08/2021 | 45 | BHARAT CONSTRUCTION | 3.36 | 3.34 | 0
4122 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Abujhati village of Abujhati piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-312/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000167/2020-2021 | 2739/BWD | 10/08/2020 | 30 | INDRAJIT MONDAL | 4.92 | 4.92 | 1
4123 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ajhapur village of Abujhati piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-331/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000168/2020-2021 | 2748/BWD | 10/08/2020 | 30 | E-WORLD | 4.92 | 4.92 | 1
4124 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Abujhati village of Abujhati piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-456/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000171/2020-2021 | 3740/BWD | 07/10/2020 | 30 | INDRAJIT MONDAL | 4.92 | 4.92 | 1
4125 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ajhapur village of Abujhati piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-429/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000172/2020-2021 | 3803/BWD | 08/10/2020 | 30 | E-WORLD | 4.92 | 4.92 | 1
4126 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000345/2021-2022 | 40/BWD | 05/01/2022 | 30 | PREMANANDA ROY BISWAS | 22.68 | 0 | 1
4127 | Burdwan Division | Burdwan Sadar Sub-Division | Providing functional household tap connection from existing distribution system within the command area of Abujhati piped water supply scheme at Napara, Panchshimul & Siromani village Jamalpur Block under Burdwan Division, PHE Dte. (Tr No.-627/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000371/2020-2021 | 954/BWD | 03/02/2021 | 45 | KOUSIK MALLICK | 38.9 | 38.58 | 1
4128 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of Abujhati piped water supply scheme at Astai, Dastanpur & Keotara village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Tr No.-624/BWD/20-21] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000404/2020-2021 | 955/BWD | 03/02/2021 | 45 | BHARAT CONSTRUCTION | 41.04 | 39.68 | 1
4129 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Abujhati Piped Water Supply Scheme at Abujhati (Part) (3 Nos Habitation Part) & Ajapur (Part) (Abujhati Part Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. _2ND CALL. [Agreement No. 754/BWD OF 2020-2021] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000412/2020-2021 | 1740/BWD | 25/02/2021 | 45 | T.K. BANERJEE & CO. | 34.87 | 35.11 | 0
4130 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) of ABUJHATI & its adjoining mouzas Piped Water Supply Scheme, Block - Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000544/2022-2023 | 5125/BWD | 21/11/2022 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 11.23 | 0 | 1
4131 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000592/2021-2022 | 1454/BWD | 11/03/2022 | 30 | PREMANANDA ROY BISWAS | 18.83 | 0 | 1
4132 | Burdwan Division | Burdwan Sadar Sub-Division | Withdrawing and Relaying of Rising main line and Bullah pilling (60.0 mtr) at HD Works Site (near pond) due to Road widening from 4lane to 6 lane of NH2 at chanage 601+951 and 601+650 of ABUJHATI PWSS to in Jamalpur Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000760/2022-2023 | 1290/BWD | 20/03/2023 | 30 | SOUMYAVASH DAS | 5.77 | 0 | 100
4133 | Burdwan Division | Burdwan Sadar Sub-Division | Laying different dia UPVC Pipeline for inter connection of existing FHTC near Kayastyaparan of Abujhati Flyover i.c.w. Road widening from 4 lane to 6 lane of NH-2 at chane 601+9521+960 under ABUIHATI PWSS in jamalpur Block within Burdwan Sub Divn. under Burdwan Division, P.H.E. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/001093/2023-2024 | 517/BSD | 13/03/2024 | 30 | SOUMYAVASH DAS | 0.89 | 0 | 100
4134 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 40
4135 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dirghapara village and Dirghapara (Part-A) habitation of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿8A¿] | Assistant Engineer |  | ORD/000121/2021-2022 | 4391/BWD | 31/08/2021 | 30 | HAFIJUR RAHAMAN MIDYA | 4.55 | 4.1 | 1
4136 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jagarpur & Mugura village of Mugura Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿3B¿] (Agreement no.238/BWD of 2020-21) | Assistant Engineer |  | ORD/000136/2020-2021 | 4118/BWD | 16/10/2020 | 30 | HAFIJUR RAHAMAN MIDYA | 4.92 | 4.86 | 1
4137 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dirghapara village and Dirghapara (Part-B) habitation of Dirghapara piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-484/BWD/2020-21) | Assistant Engineer |  | ORD/000175/2020-2021 | 4119/BWD | 16/10/2020 | 30 | SK NUR ALAM | 4.86 | 4.86 | 1
4138 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [Sl. No. : ¿10¿] | Assistant Engineer |  | ORD/000197/2021-2022 | 6231/BWD | 01/11/2021 | 15 | HAFIJUR RAHAMAN MIDYA | 4.86 | 0 | 1
4139 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [Sl. No. : ¿11¿] | Assistant Engineer |  | ORD/000198/2021-2022 | 6232/BWD | 01/11/2021 | 15 | SK NUR ALAM | 4.86 | 0 | 1
4140 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - C) [Sl. No. : ¿12¿] | Assistant Engineer |  | ORD/000205/2021-2022 | 6401/BWD | 16/11/2021 | 15 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.84 | 0 | 1
4141 | Burdwan Division | Kalna Sub-division | Extension of different dia UPVC pipeline at the leftout portion of Kharoshgram village of Dirghapara PWSS within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000243/2021-2022 | 6106/BWD | 08/10/2021 | 30 | M/S UNIQUE | 6.67 | 0 | 1
4142 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of DIRGHAPARA (SM/07804) Water Supply Scheme, MOUDANGA (SM/ 14020) Water supply Scheme & BHANDARTIKURI (SM/14925) Water Supply Scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000357/2024-2025 | 2912/BWD | 25/07/2024 | 431 | BANSBERIA CONSTRUCTION CO. | 293.38 | 0 | 22
4143 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [Sl. No. : ¿10¿] | Assistant Engineer |  | ORD/000648/2020-2021 | 60/BWD | 05/01/2021 | 15 | HAFIJUR RAHAMAN MIDYA | 4.86 | 4.86 | 1
4144 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [Sl. No. : ¿11¿] | Assistant Engineer |  | ORD/000649/2020-2021 | 61/BWD | 05/01/2021 | 15 | SK NUR ALAM | 4.86 | 4.86 | 1
4145 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village , Kharashgram (Part) habitation of Dirghapara piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Part-C][SL NO.-12] | Assistant Engineer |  | ORD/000705/2020-2021 | 62/BWD | 05/01/2021 | 15 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.84 | 4.84 | 1
4146 | Burdwan Division | Kalna Sub-division | Extension of 63 mm dia UPVC pipeline to provide house connection at different leftout portion of Dirghapara w/s scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Sl-E] | Assistant Engineer |  | ORD/000937/2020-2021 | 171/KSD | 19/02/2021 | 30 | SK RAJU | 1.78 | 0 | 1
4147 | Burdwan Division | Kalna Sub-division | Restoration of UPVC pipeline which damaged during construction of PCC road & providing FHTC work at DIRGHAPARA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000949/2023-2024 | 5594/BWD | 20/12/2023 | 30 | UTPAL NANDI | 8.31 | 0 | 0
4148 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Purba Sahapur (Pt-B) village of Purba Sahapur Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 7B] | Assistant Engineer |  | ORD/000131/2020-2021 | 2584/BWD | 09/07/2020 | 30 | SETH ENTERPRISE | 4.92 | 0 | 1
4149 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Purba Sahapur (Pt-A) village of Purba Sahapur Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 7A] | Assistant Engineer |  | ORD/000132/2020-2021 | 2585/BWD | 09/07/2020 | 30 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.92 | 0 | 1
4150 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Pt-A) village of Sahapur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL.No : ¿11A¿] (Agreement no.-501/BWD of 2020-21) | Assistant Engineer |  | ORD/000145/2020-2021 | 4083/BWD | 16/10/2020 | 30 | RAINBOW CONSTRUCTION | 2.23 | 2.23 | 1
4151 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 03 Nos. Piped W/S. Schemes under Kalna II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000336/2024-2025 | 3016/BWD | 05/08/2024 | 20 | HORIZEN | 7.55 | 0 | 100
4152 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur, Char Sahapur and Natungram village of Sahapur piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. (Tr No.-789/BWD/2020-21) | Assistant Engineer |  | ORD/000517/2020-2021 | 365/KTS | 15/12/2020 | 7 | DUBE ENTERPRISE | 2.46 | 2.46 | 0
4153 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Part-B) village of Sahapur piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-497/BWD/2020-21) | Assistant Engineer |  | ORD/000547/2020-2021 | 4007/BWD | 14/10/2020 | 30 | DUBE ENTERPRISE | 2.84 | 2.84 | 0
4154 | Burdwan Division | Kalna Sub-division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Purba Sahapur (Pt-B) village of Purba Sahapur Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 7B] | Assistant Engineer |  | ORD/000738/2020-2021 | 2587/BWD | 04/08/2020 | 30 | SETH ENTERPRISE | 4.92 | 0 | 1
4155 | Burdwan Division | Kalna Sub-division | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | Assistant Engineer |  | ORD/000867/2020-2021 | 4318/BWD | 04/11/2020 | 10 | MD HASIN | 4.93 | 0 | 1
4156 | Burdwan Division | Kalna Sub-division | Extension of pipeline at Purbasahapur mouza under Purbasahapur water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Sl-A] | Assistant Engineer |  | ORD/000930/2020-2021 | 29/KSD | 11/01/2021 | 45 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.84 | 0 | 1
4157 | Burdwan Division | Durgapur Sub-DIvision | Providing left out FHTC for making Swajal Gram at Khanhati village within Adra Water supply Scheme in Galsi-II Block under Burdwan Division, P.H.E. Dte.[SL-09] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000033/2023-2024 | 157/DSD | 13/04/2023 | 21 | SHUBHRA KANTI GHOSH | 0.97 | 0 | 100
4158 | Burdwan Division | Durgapur Sub-DIvision | Restoration and relaying of damaged pipeline of distribution main for construction of drain, concrete road etc at Ruidaspara (South end) of Adra village for providing left out FHTC at Ruidaspara (South end) within Adra W/S Scheme in Galsi-II Block under Burdwan Division, P.H.E. Dte.[SL-12] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000036/2023-2024 | 160/DSD | 13/04/2023 | 21 | SHUBHRA KANTI GHOSH | 0.96 | 0 | 100
4159 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mohara (Part), Kaitara (Part) and Khanhati (Part) Village of Adra Piped W/S Scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000129/2022-2023 | 342/DSD | 30/06/2022 | 21 | SHUBHRA KANTI GHOSH | 4.82 | 0 | 1
4160 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Adra village (Adrahati habitation) of ADRA Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 05] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000204/2021-2022 | 6264/BWD | 02/11/2021 | 15 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 4.86 | 0 | 1
4161 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Adra village (Adrahati habitation) of ADRA Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - C) [SL. No. : 07] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000216/2021-2022 | 6194/BWD | 28/10/2021 | 15 | LAKSHMIKANTA DAS | 4.86 | 0 | 1
4162 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mohara vilage (Mohara habitation) of ADRA Piped W/S Scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000241/2021-2022 | 673/DSD | 29/11/2021 | 21 | KOUSIK MALLICK | 4.83 | 0 | 1
4163 | Burdwan Division | Durgapur Sub-DIvision | Sinking of 200 mm dia. River Bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Gohogram village Block -Galsi-II, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000269/2022-2023 | 494/DSD | 12/08/2022 | 21 | KOUSIK MALLICK | 4.35 | 0 | 1
4164 | Burdwan Division | Durgapur Sub-DIvision | Sinking of 200 mm dia River Bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Simasimi village Block -Galsi-I, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000270/2022-2023 | 495/DSD | 12/08/2022 | 21 | MUNSHI JAVEDUR JAMAN | 4.35 | 0 | 1
4165 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Kaitara, Patrahati and Mahara Mouza for providing FHTC of Adra and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000273/2022-2023 | 498/DSD | 12/08/2022 | 30 | SHUBHRA KANTI GHOSH | 4.81 | 0 | 1
4166 | Burdwan Division | Durgapur Sub-DIvision | Relaying and repairing of distribution after widening of PWD road in between Chainage 8.40 km to 10.74 km of Galsi Gohogram road between Node 74 to Node 117 within Adra W/S Scheme at Durgapur Sub-Division in Galsi-II Block under Burdwan Division, P.H.E. Dte.[Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000333/2021-2022 | 03/DSD | 03/01/2022 | 30 | SHUBHRA KANTI GHOSH | 4.82 | 0 | 1
4167 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Adra village (Adrahati habitation) of ADRA Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 05] [Agr. No. 745/BWD of 2020-2021] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000379/2020-2021 | 584/BWD | 25/01/2021 | 15 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 4.86 | 0 | 1
4168 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from distribution system within the command area of ADRA Water Supply Scheme at Adra (Part), Mohara (Part), Kaitara and Patrahati village under JAL SAPNO MISSION under Galsi-II Block in Purba Bardhanan District under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000415/2021-2022 | 384/BWD | 20/01/2022 | 60 | SHUBHRA KANTI GHOSH | 69.37 | 0 | 1
4169 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Adra village (Adrahati habitation) of ADRA Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [SL. No. : 06] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000462/2020-2021 | 585/BWD | 25/01/2021 | 15 | BASUNDHARA SOLUTION | 4.86 | 0 | 1
4170 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila Habitation) of Bagila piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Part-B)[SL NO.-09] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000746/2020-2021 | 585./BWD | 25/01/2021 | 15 | HAMID SK | 4.87 | 0 | 1
4171 | Burdwan Division | Durgapur Sub-DIvision | Extension of UPVC pipe line of LDS at Khanhati and Patrahati Mouza for providing FHTC of Adra and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte.[SL-23] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000844/2022-2023 | 706/DSD | 31/12/2022 | 30 | UTPAL NANDI | 4.46 | 0 | 0
4172 | Burdwan Division | Durgapur Sub-DIvision | Carriage of withdrawal stacked DI pipes of rising main from Adrahati to Barsul Divisional store and restoration of damaged pipeline of distribution main for construction of drain, concrete road etc at various point at Khanhati village for providing FHTC within Adra W/S Scheme in Galsi-II Block under Durgapur Sub Division, P.H.E. Dte. [SL-06] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000879/2022-2023 | 732/DSD | 30/12/2022 | 21 | SHUBHRA KANTI GHOSH | 0.61 | 0 | 25
4173 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ADRA Piped Water Supply Scheme at Kaitara village, Galsi-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-9] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000882/2022-2023 | 735/DSD | 30/12/2022 | 21 | SHUBHRA KANTI GHOSH | 0.97 | 0 | 100
4174 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mohara (Part) Village of Adra Piped W/S Scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [SL-12] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000888/2022-2023 | 737/DSD | 30/12/2022 | 21 | SHUBHRA KANTI GHOSH | 0.94 | 0 | 100
4175 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kaitara (Part) Village of Adra Piped W/S Scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [SL-11] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000889/2022-2023 | 736/DSD | 30/12/2022 | 21 | SHUBHRA KANTI GHOSH | 0.96 | 0 | 100
4176 | Burdwan Division | Durgapur Sub-DIvision | Connecting, relaying and repairing of distribution main towards Irkona (Node 4 to Node 18) and Mohora village Node 157 to Node 163 with newly reoriented line (from Chainage 8.40 km to 10.74 km of Galsi Gohogram road and from Node 152 to Node 157 beside PMGSY road) within Adra W/S Scheme at Durgapur Sub-Division in Galsi-II Block under Burdwan Division, P.H.E. Dte. (Gr.-'E') | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000966/2020-2021 | 554/DSD | 22/12/2020 | 21 | PAL CONSTRUCTION | 2.1 | 0 | 1
4177 | Burdwan Division | Burdwan Sadar Sub-Division | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MADANAGAR Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000063/2023-2024 | 1935/BWD | 24/04/2023 | 30 | S.C. ENTERPRISE | 20.87 | 0 | 100
4178 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madanagar habitation of Madanagar piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Tr No.-531/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000199/2020-2021 | 3741/BWD | 07/10/2020 | 30 | PABITRA KUMAR SAMANTA | 4.92 | 4.92 | 1
4179 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000344/2021-2022 | 39/BWD | 05/01/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 15.62 | 0 | 1
4180 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madanagar (Part) village (Madanagar Mejhpur Habitation) of Madanagar piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000605/2020-2021 | 69/BWD | 05/01/2021 | 15 | PABITRA KUMAR SAMANTA | 4.86 | 4.05 | 1
4181 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madanagar village of Madanagar piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-716/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000651/2020-2021 | 1224/BWD | 11/02/2021 | 30 | PABITRA KUMAR SAMANTA | 3.76 | 3.76 | 1
4182 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Ground Water Based Piped Water Supply Scheme for MADHANAGAR, Block:Raina-I under Burdwan Division, P.H.E Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000990/2024-2025 | 1912/BSD | 28/08/2024 | 15 | MEASURE LAND | 0.78 | 0 | 0
4183 | Burdwan Division | Burdwan Sadar Sub-Division | Restore of damaged Pipeline at Madanagar Dakshin Para under MADANAGAR Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001051/2023-2024 | 823/BWD | 28/02/2024 | 424 | UTPAL NANDI | 6.18 | 0 | 100
4184 | Burdwan Division | Kalna Sub-division | Quotation from WBSEDCL for Augmentation of Anukhal w/s scheme under Burdwan Division, PHE Dte. P.H. No.-3 & 4. | Assistant Engineer |  | BILL/00907/2024-2025 | 1046/JJM | 30/10/2024 | 0 | WBSEDCL | 17.05 | 0 | 0
4185 | Burdwan Division | Kalna Sub-division | Augmentation of ANUKHAL Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation with construction of boundary wall at Headworks site under Kalna-II Block, District:- Purba-Burdwan. | Assistant Engineer |  | ORD/000096/2022-2023 | 2741/BWD | 08/06/2022 | 365 | SINGHA ROY AND CO. | 374.09 | 0 | 70
4186 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Anukhal W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-D) | Assistant Engineer |  | ORD/000570/2021-2022 | 206/KSD | 23/02/2022 | 21 | INDRANIL DUTTA & ASSOCIATES | 2.86 | 0 | 1
4187 | Burdwan Division | Kalna Sub-division | Work Order for Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory under The Assistant Engineer, Kalna Sub-Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation,Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL : Anukhal Sub District Water Testing Laboratory under Kalna Sub Division.) | Assistant Engineer |  | ORD/000672/2023-2024 | 1335/KSD | 28/08/2023 | 30 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.91 | 0 | 100
4188 | Burdwan Division | Kalna Sub-division | Additional work to implement augmentation of ANUKHAL Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000821/2023-2024 | 4998/BWD | 21/11/2023 | 30 | UDYOG CONSTRUCTION | 7.48 | 0 | 100
4189 | Burdwan Division | Kalna Sub-division | Sinking of tube well, Laying dist. system, Providing FHTC, construction of Pump House & Boundary and Laying rising main of ANUKHAL Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000857/2023-2024 | 5206/BWD | 29/11/2023 | 120 | SINGHA ROY AND CO. | 119.49 | 0 | 15
4190 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000041/2022-2023 | 4627/BWD | 17/10/2022 | 0 | Resource Division | 12.32 | 0 | 0
4191 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000055/2021-2022 | 531/BWD | 27/01/2022 | 0 | Resource Division | 14.56 | 0 | 0
4192 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000148/2021-2022 | 1242/BWD | 07/03/2022 | 0 | Resource Division | 4.93 | 0 | 0
4193 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000160/2021-2022 | 1320/BWD | 08/03/2022 | 0 | Resource Division | 32.89 | 0 | 0
4194 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000210/2021-2022 | 1533/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
4195 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
4196 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Sankari W/S Scheme under Khandaghosh Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.10. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000498/2021-2022 | 185/BSD | 31/01/2022 | 30 | RADIANT | 2.52 | 0 | 1
4197 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of SANKARI Piped Water Supply Scheme with LDS, Rising Main, Constn. of 250 cum capacity OHR with 20.0 Mtr. staging height inclusive of soil test & FHTC under Khandaghosh Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000527/2021-2022 | 1119/BWD | 28/02/2022 | 365 | UNIQUE AGENCY | 208.48 | 0 | 100
4198 | Burdwan Division | Burdwan Sadar Sub-Division | Supply and delivery of different dia. CIDF sluice valve for Augmentation of SANKARI Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte._SL No. 06 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000617/2021-2022 | 140/AE/HQ | 16/03/2022 | 10 | MAKALI ENGINEERING CORPORATION | 4.52 | 0 | 0
4199 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000054/2021-2022 | 529/BWD | 27/01/2022 | 0 | Resource Division | 6.82 | 0 | 0
4200 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000093/2021-2022 | 903/BWD | 15/02/2022 | 0 | Resource Division | 18.21 | 0 | 0
4201 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000204/2021-2022 | 1527/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
4202 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
4203 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Sehara W/S Scheme under Raina-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.9 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000497/2021-2022 | 184/BSD | 31/01/2022 | 30 | RADIANT | 2.85 | 0 | 1
4204 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of SEHARA & its adjoining mouzas Piped Water Supply Scheme, Block ¿ Raina ¿ I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000537/2022-2023 | 5025/BWD | 10/11/2022 | 30 | M/S D. PALIT & CO. | 10.06 | 0 | 1
4205 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at TubeWell Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17 (Size3.60mtr x 3.00mtr room) for SEHARA its Adjoining Mouza W/S Scheme, Block -Raina-I within Burdwan Sub-Division, PHE Dte. (Mouza- Sehara)_2ND CALL | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000576/2023-2024 | 2041/BSD | 24/08/2023 | 45 | ANWESHA CONSTRUCTION | 3.21 | 0 | 100
4206 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of SEHARA Piped Water Supply Scheme with LDS, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & FHTC under Raina ¿ I Block, District - Purba Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000599/2021-2022 | 1473/BWD | 14/03/2022 | 365 | M/S PIONEER CONSTRUCTION | 430.73 | 0 | 100
4207 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000045/2021-2022 | 536/BWD | 27/01/2022 | 0 | Resource Division | 15.56 | 0 | 0
4208 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000091/2021-2022 | 902/BWD | 15/02/2022 | 0 | Resource Division | 13.85 | 0 | 0
4209 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | RTOR000212/2021-2022 | 1535/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
4210 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
4211 | Burdwan Division |  | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme SRIKHANDA, SUDPUR PWSS (Sl No-3) |  |  | ORD/000071/2023-2024 | 395/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 2.48 | 0 | 100
4212 | Burdwan Division |  | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Sudpur, Lokpur & Narayanpur village under SUDPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte [Sl - 4 ] |  |  | ORD/000120/2021-2022 | 564/KTS | 31/08/2021 | 15 | BABUL SK | 2.42 | 0 | 1
4213 | Burdwan Division |  | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Rayerpara, Purba and Paschim Bijoynagar village under SUDPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte [Sl - 5 ] |  |  | ORD/000125/2021-2022 | 565/KTS | 31/08/2021 | 15 | HAMID SK | 3.6 | 0 | 1
4214 | Burdwan Division |  | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Head Work Site to departmental drawing (Size 3.60 mtr x 3.00 mtr room) for SUDPUR water supply schemes under Katwa Sub-Division within Burdwan Division, PHE Dte.(Sl No-7) |  |  | ORD/000146/2021-2022 | 595/KTS | 06/09/2021 | 45 | BABUL SK | 2.99 | 0 | 1
4215 | Burdwan Division |  | Supplying and laying of valves along with construction of valve chamber at the existing distribution pipe line of Sudpur PWSS under Katwa Sub-Division under Burdwan Division, PHE Dte [Sl No-05] |  |  | ORD/000158/2022-2023 | 441/KTS | 27/06/2022 | 30 | MD HASIN | 0.86 | 0 | 1
4216 | Burdwan Division |  | Supplying and laying inter-connection from Pump no.-3 to rising main of Sudpur PWSS under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No-5] |  |  | ORD/000373/2023-2024 | 672/KTS | 22/06/2023 | 30 | HAMID SK | 0.93 | 0 | 100
4217 | Burdwan Division | Kalna Sub-division | Augmentation of Kusumgram Zone-I & II Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 450 & 300 cum capacity OHR with 20.0 mtr. Staging height including construction of switch-room without sanitary & water supply arrangement, boundary wall including repairing of boundary wall under Monteswar Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000541/2022-2023 | 5079/BWD | 17/11/2022 | 866 | MANASH GHOSH | 778.07 | 0 | 66
4218 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Kusumgram W/S Scheme (Zone-I & II) within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer | JUNIOR ENGINEER | ORD/000569/2021-2022 | 204/KSD | 23/02/2022 | 21 | ROY CHOWDHURY ASSOCIATES | 3.93 | 0 | 1
4219 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 1ST TW Site of Aug. of KUSUMGRAM (Z-II) & its adjoining mouzas Piped Water Supply Scheme, Block ? Monteswar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. _2ND CALL. | Assistant Engineer | JUNIOR ENGINEER | ORD/000657/2022-2023 | 371/BWD | 31/01/2023 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 7.33 | 0 | 1
4220 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000056/2022-2023 | 5521/BWD | 23/12/2022 | 0 | Resource Division | 32.81 | 0 | 0
4221 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000224/2021-2022 | 1547/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
4222 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
4223 | Central Mechanical | Kalna Sub-division | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 3 of Kulut [ Kusumgram ] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000010/2022-2023 | 1172/CMD | 27/06/2022 | 30 | M/S. DAS ELECTRIC CO. | 9.33 | 0 | 1
4224 | Central Mechanical | Kalna Sub-division | Installation of Electro-mechanical accessories at Kusungram zone-1 PH-2 (replacement T.W) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000994/2023-2024 | 4361/CMD | 21/09/2023 | 30 | BENGAL ELECTRICAL CONSTRUCTION | 1.97 | 0 | 100
4225 | Burdwan Division | Durgapur Sub-DIvision | Quotation for new connection charges of Augmentation of Barbelun w/s scheme under Burdwan Division, PHE Dte. T.W. No.-4 [Memo No.-5003603611/Quot/03, dt.-10/02/2023][App No.-5003603611, Ref. ID-503282585] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00291/2022-2023 | 1115/JJM | 27/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.4 | 0 | 0
4226 | Burdwan Division | Durgapur Sub-DIvision | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell site for Augmentation of BAROBELUN Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000013/2022-2023 | 1961/BWD | 12/04/2022 | 45 | ACME CONSTRUCTION | 22.05 | 0 | 1
4227 | Burdwan Division | Durgapur Sub-DIvision | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Dignagar, Galsi, Barabelun & Kotachandipur Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. Dte. _2ND CALL | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000311/2022-2023 | 3624/BWD | 22/08/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.76 | 0 | 1
4228 | Burdwan Division | Durgapur Sub-DIvision | Beautification of PWSS with Arboriculture, Recharge Pit including shaft at Head Works site and anciliary works at 1st & 4th Tubewell site of BARABELUN (Bhatar Block) P.W.S.S under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000367/2024-2025 | 238/RWS | 30/07/2024 | 10 | GHOSH ENTERPRISE | 0.97 | 0 | 100
4229 | Burdwan Division | Durgapur Sub-DIvision | Augmentation of BARABELUN Piped Water Supply Scheme with LDS, FHTC work, Rising Main, Switch Room (with water supply & sanitary arrangements), 400 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Boundary wall construction (HW, 2nd TW & 4th TW Site) with repairing of switch room cum chlorine room, Block - Bhatar, Dist. - Purba Bardhaman under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000423/2021-2022 | 571/BWD | 27/01/2022 | 365 | MD HASIN | 406.41 | 0 | 100
4230 | Burdwan Division | Durgapur Sub-DIvision | Route Survey & Preparation of DPR for BARABELUN PWSS under Durgapur(Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-E] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000656/2021-2022 | 105/DSD | 18/02/2022 | 15 | RISHAN ENGINEERING CONSULTANCY | 2.72 | 0 | 1
4231 | Burdwan Division | Durgapur Sub-DIvision | Making connection with 4th tube well, Construction of Plinth protection of OHR, Restoration of road and FHTC (The rest portion) of Bara Belun Water Supply Scheme at Bara Belun village & Providing Functional Household Tap Connection (FHTC) within the command area of NASIGRAM Piped W/S. Scheme within Bhatar Block under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000690/2024-2025 | 3685/BWD | 23/10/2024 | 120 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 91.48 | 0 | 0
4232 | Burdwan Division | Durgapur Sub-DIvision | Land development and beautification with plant and Construction of connecting road from Gate to Pumphouse, OHR at 1st tubewell site of Barobelun Water Supply Scheme within Durgapur Sub Division Under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000986/2023-2024 | 42/DSD | 17/01/2024 | 366 | MUNSHI JAVEDUR JAMAN | 4.82 | 0 | 72
4233 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC)from distribution system within the command area of Barobelun water supply scheme at Baneswarpur village under JJM under Bhatar Block in Purba Bardhanan District undrer Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001019/2023-2024 | 130/DSD | 07/02/2024 | 45 | JAMALUDDIN SK | 3.02 | 0 | 100
4234 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC)from distribution system within the command area of Barobelun water supply scheme at Khulla village under JJM under Bhatar Block in Purba Bardhanan District undrer Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001020/2023-2024 | 131/DSD | 07/02/2024 | 45 | JAMALUDDIN SK | 1.81 | 0 | 100
4235 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000026/2021-2022 | 556/BWD | 27/01/2022 | 0 | Resource Division | 13.64 | 0 | 0
4236 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000046/2022-2023 | 4854/BWD | 20/10/2022 | 0 | Resource Division | 6.16 | 0 | 0
4237 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000101/2021-2022 | 770/BWD | 07/02/2022 | 0 | Resource Division | 26.55 | 0 | 0
4238 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000168/2021-2022 | 1328/BWD | 08/03/2022 | 0 | Resource Division | 39.89 | 0 | 0
4239 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000186/2021-2022 | 1381/BWD | 09/03/2022 | 0 | Resource Division | 4.35 | 0 | 0
4240 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000236/2021-2022 | 1560/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
4241 | Burdwan Division | Durgapur Sub-DIvision | New connection charges bill for Barabelun water supply scheme under Burdwan Division, PHE Dte.[Application No.-5003437581, Ref ID-503142125] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | VCH/000524/2022-2023 | 596/DW/22-23 | 21/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.9 | 0 | 0
4242 | Burdwan Division | Durgapur Sub-DIvision | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
4243 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation of Barabelun Water Supply Scheme [ Block- Bhatar ] at 1st Tube well Site( Tube well No.-3) at under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000619/2022-2023 | 2095/CMD | 08/09/2022 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.9 | 0 | 0
4244 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation of Barabelun Water Supply Scheme [ Block- Bhatar ] at 2nd Tube well Site( Tube well No.-4) at under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000621/2022-2023 | 2094/CMD | 08/09/2022 | 30 | M/S. SWAPAN BANERJEE | 11.4 | 0 | 100
4245 | Burdwan Division | Durgapur Sub-DIvision | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways at different TW sites for SILUT Piped Water Supply Scheme under Ausgram-I Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000424/2023-2024 | 3323/BWD | 02/08/2023 | 730 | TAAS ENTERPRISE | 474.73 | 0 | 50
4246 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000035/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 69.42 | 0 | 0
4247 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000322/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.36 | 0 | 0
4248 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000592/2023-2024 | 4900/BWD | 10/11/2023 | 0 | Resource Division | 34.27 | 0 | 0
4249 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Silut PWSS PH-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00433/2024-2025 | BP-2024-25-234 | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.65 | 0 | 0
4250 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Silut W/S Scheme for PH No-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01819/2023-2024 | BP-2023-24-327 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.07 | 0 | 0
4251 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0
4252 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Silut Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001039/2023-2024 | 4179/CMD | 29/08/2023 | 580 | SOUMEN ELECTRIC | 27.67 | 0 | 48
4253 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte." [Period from 01.12.2023 to 31.01.2024] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001207/2023-2024 | 921/AE/HQ | 30/11/2023 | 62 | SOURAV JANA | 0.8 | 0 | 50
4254 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000260/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.43 | 0 | 0
4255 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000464/2023-2024 | 3988/BWD | 08/09/2023 | 0 | Resource Division | 1.04 | 0 | 0
4256 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000657/2023-2024 | 5115/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
4257 | Central Mechanical | Burdwan Sadar Sub-Division | Additional quotation for new service connection at Bijra PWSS | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01027/2024-2025 | BP-2024-25-383 | 14/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.24 | 0 | 0
4258 | Central Mechanical | Burdwan Sadar Sub-Division | Electric quotation for New Service Connection at Bijra W/S Scehem PH-I. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01779/2023-2024 | BP-2023-24-282 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.34 | 0 | 0
4259 | Central Mechanical | Burdwan Sadar Sub-Division | New electric connection for Bijra PWSS, PH-2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01876/2023-2024 | BP-2023-24-342 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.97 | 0 | 0
4260 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0
4261 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BIJRA Water Supply Scheme [ Block- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000806/2023-2024 | 4091/CMD | 29/08/2023 | 491 | ORIENTAL ENGINEERING CO. | 29.39 | 0 | 100
4262 | Burdwan Division | Burdwan Sadar Sub-Division | GHOSHPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000110/2023-2024 | 2299/BWD | 19/05/2023 | 958 | MLG CONSTRUCTION | 441.87 | 0 | 52
4263 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2024 to 31-01-2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000896/2024-2025 | 2438/BSD | 29/10/2024 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
4264 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2023 to 31-01-2024) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000985/2023-2024 | 2561/BSD | 30/10/2023 | 66 | MD HASIN | 0.85 | 0 | 0
4265 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000259/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 15.58 | 0 | 0
4266 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000468/2023-2024 | 3992/BWD | 08/09/2023 | 0 | Resource Division | 12.78 | 0 | 0
4267 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | RTOR000668/2023-2024 | 5089/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
4268 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection at Ghoshpur PWSS TW -1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | BILL/02330/2023-2024 | BP-2023-24-446 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.28 | 0 | 0
4269 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR GHOSHPUR PWSS. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | BILL/02701/2023-2024 | BP-2023-24-566 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.97 | 0 | 0
4270 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and Compound lighting arrangement for Tube well No.- 1 & 2 at GHOSHPUR Water Supply Scheme [BLOCK- MEMARI- 2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/001603/2023-2024 | 1533/CMD | 05/03/2024 | 60 | CHOUDHURY ENTERPRISE | 28.82 | 0 | 75
4271 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for LDS,FHTC,Road Restoration,Develop Boundary Wall Hight & Land Developement making With necessary allied works at AUSGRAM-I Block of BHOTA PWSS under Durgapur Water Supply Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000180/2024-2025 | 1617/DWSD | 26/11/2024 | 90 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 55.22 | 0 | 40
4272 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000016/2024-2025 | 1724/C/DWSD | 10/12/2024 | 0 | Resource Division | 3.52 | 0 | 0
4273 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AUSGRAM & BHOTA Piped Water Supply Scheme under Ausgram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000430/2023-2024 | 3324/BWD | 02/08/2023 | 776 | DUTTA ENTERPRISE | 763.14 | 0 | 70
4274 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000021/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.99 | 0 | 0
4275 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000256/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.44 | 0 | 0
4276 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000495/2023-2024 | 4019/BWD | 08/09/2023 | 0 | Resource Division | 4.01 | 0 | 0
4277 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000642/2023-2024 | 5108/BWD | 23/11/2023 | 0 | Resource Division | 20.18 | 0 | 0
4278 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Bhota W/S Scheme for PH No-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01822/2023-2024 | BP-2023-24-326 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.81 | 0 | 0
4279 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Bhota W/S Scheme for PH No-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01823/2023-2024 | BP-2023-24-325 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.77 | 0 | 0
4280 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0
4281 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bhota Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000741/2023-2024 | 4051/CMD | 29/08/2023 | 615 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 29.56 | 0 | 48
4282 | Burdwan Division | Kalna Sub-division | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/08/2024 to 30/09/2024) | Assistant Engineer | JUNIOR ENGINEER | ORD/000552/2024-2025 | 602/DSD | 30/07/2024 | 61 | SUJAUDDIN SEKH | 0.8 | 0 | 100
4283 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BELENDA, JAMNA, PIPLON & PARGUNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000689/2023-2024 | 4388/BWD | 05/10/2023 | 667 | AKASH CONSTRUCTION | 2296.4 | 0 | 50
4284 | Burdwan Division | Kalna Sub-division | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/10/2024 to 30/11/2024) | Assistant Engineer | JUNIOR ENGINEER | ORD/000839/2024-2025 | 772/DSD | 18/09/2024 | 61 | SUJAUDDIN SEKH | 0.8 | 0 | 0
4285 | Burdwan Division | Kalna Sub-division | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/12/2024 to 31/12/2024) | Assistant Engineer | JUNIOR ENGINEER | ORD/000994/2024-2025 | 992/DSD | 25/11/2024 | 61 | SUJAUDDIN SEKH | 0.4 | 0 | 0
4286 | Burdwan Division | Kalna Sub-division | Work Order for "DESIGNING,MAKING AND ERECTION OF SIGN BOARD FOR SAJAL GRAM IN ¿¿1 No...VILLAGE, ¿MANTESWAR BLOCK UNDER KALNA SUB DIVISION WITHIN BURDWAN DIVISION PHE DTE. (3nos board)" | Assistant Engineer | JUNIOR ENGINEER | ORD/001424/2024-2025 | 1920/KSD | 02/12/2024 | 10 | OMKAR ENTERPRISE | 0.42 | 0 | 100
4287 | Burdwan Division | Kalna Sub-division | Supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/02/2025 to 31/03/2025) | Assistant Engineer | JUNIOR ENGINEER | ORD/001508/2024-2025 | 142/DSD | 24/01/2025 | 59 | SK ALACK JANDER | 0.8 | 0 | 0
4288 | Burdwan Division | Kalna Sub-division | Continuation for Supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/04/2025 to 31/05/2025) | Assistant Engineer | JUNIOR ENGINEER | ORD/001513/2024-2025 | 483/DSD | 21/03/2025 | 61 | SK ALACK JANDER | 0.8 | 0 | 0
4289 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000241/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 3.1 | 0 | 0
4290 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000541/2023-2024 | 4309/BWD | 29/09/2023 | 0 | Resource Division | 11.47 | 0 | 0
4291 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000596/2023-2024 | 4947/BWD | 10/11/2023 | 0 | Resource Division | 35.92 | 0 | 0
4292 | Central Mechanical | Kalna Sub-division | Quotation for new service connection for Belenda PWSS PH 1. | Assistant Engineer | JUNIOR ENGINEER | BILL/00228/2024-2025 | BP-2024-25-119 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.29 | 0 | 0
4293 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR BELENDA PWSS TW -2. | Assistant Engineer | JUNIOR ENGINEER | BILL/03099/2023-2024 | BP-2023-24-639 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.64 | 0 | 0
4294 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
4295 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Belenda Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000911/2023-2024 | 4175/CMD | 29/08/2023 | 703 | SOUNAK ENTERPRISE | 28.48 | 0 | 95
4296 | Central Mechanical | Kalna Sub-division | CONTINUATION ORDER- Hiring of inspection vehicle (Diesel/CNG/LPG Driven)for supervision of site for the office of the Assisatnt Engineer,under CMD,PHE,Dte.[W.E.F-01.04.2025 to 31.05.2025] | Assistant Engineer | JUNIOR ENGINEER | ORD/001173/2024-2025 | 367/CMSD | 26/03/2025 | 61 | PRODYUT GHOSH | 0.8 | 0 | 0
4297 | Burdwan Division | Kalna Sub-division | KHULE Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000004/2023-2024 | 1618/BWD | 05/04/2023 | 638 | AZAD ENTERPRISE | 598.72 | 0 | 55
4298 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR ANUKHAL PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000962/2024-2025 | 1236/KSD | 30/09/2024 | 15 | SINGHA ROY AND CO. | 0.66 | 0 | 0
4299 | Burdwan Division | Kalna Sub-division | Work order for " CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DOGACHHIA PWSS UNDER KALNA SUBDIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000963/2024-2025 | 1237/KSD | 30/09/2024 | 15 | MITRA CONSTRUCTION | 0.66 | 0 | 0
4300 | Burdwan Division | Kalna Sub-division | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0
4301 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR KHULE PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE.". | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001289/2024-2025 | 1232/KSD | 27/09/2024 | 15 | WESTON ENGINEERS | 0.66 | 0 | 100
4302 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000046/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 56.68 | 0 | 0
4303 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000180/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 18.09 | 0 | 0
4304 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR KHULE PWSS. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | BILL/02696/2023-2024 | BP-2023-24-569 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.69 | 0 | 0
4305 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR KHULE PWSS. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | BILL/02697/2023-2024 | BP-2023-24-570 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.79 | 0 | 0
4306 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
4307 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khule Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000923/2023-2024 | 4186/CMD | 29/08/2023 | 30 | CINZANO | 29.1 | 0 | 0
4308 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Additional work for laying of Extension or Laying of parallel pipeline,providing FHTC,Road Restoration work, Land development under Kalaijhuti PWSS in Ausgram -II Block under Durgapur Water Supply Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000176/2024-2025 | 1622/DWSD | 26/11/2024 | 95 | ROY CONSTRUCTION | 27.08 | 0 | 40
4309 | Burdwan Division | Durgapur Sub-DIvision | KALAIJHUTI [Kalaijhuti Village (Node Point 1 to 84)] Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under AUSGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000804/2022-2023 | 1565/BWD | 30/03/2023 | 90 | PABITRA KUMAR SAMANTA | 93 | 0 | 100
4310 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000005/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.78 | 0 | 0
4311 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000174/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 16.15 | 0 | 0
4312 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000616/2023-2024 | 4876/BWD | 10/11/2023 | 0 | Resource Division | 30.36 | 0 | 0
4313 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Kalaijhuti PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00760/2023-2024 | BP-2023-24-60 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.51 | 0 | 0
4314 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KALAIJHUTI Water Supply Scheme [ Block- AUSGRAM-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000046/2023-2024 | 2509/CMD | 02/06/2023 | 30 | SOUNAK ENTERPRISE | 27.79 | 0 | 30
4315 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KONRAPUR & MASGARIA Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000026/2023-2024 | 1765/BWD | 17/04/2023 | 365 | M/S ASHA CONSTRUCTION | 710.72 | 0 | 43
4316 | Burdwan Division | Kalna Sub-division | Different types of balance works involve in connection with KONRAPUR (SM/13419) & MASGORIA (SM/13318) Piped water supply scheme under Purbasthali-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001028/2024-2025 | 142/BWD | 08/01/2025 | 120 | M/S ASHA CONSTRUCTION | 65.74 | 0 | 0
4317 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000161/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 8.28 | 0 | 0
4318 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000471/2023-2024 | 3995/BWD | 08/09/2023 | 0 | Resource Division | 11.87 | 0 | 0
4319 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000800/2023-2024 | 309/BWD | 24/01/2024 | 0 | Resource Division | 16.1 | 0 | 0
4320 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR KONRAPUR PWSS | Assistant Engineer | JUNIOR ENGINEER | BILL/02694/2023-2024 | BP-2023-24-567 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.54 | 0 | 0
4321 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR KONRAPUR PWSS. | Assistant Engineer | JUNIOR ENGINEER | BILL/02695/2023-2024 | BP-2023-24-568 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.76 | 0 | 0
4322 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 30
4323 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at KONRAPUR Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001056/2023-2024 | 4198/CMD | 29/08/2023 | 30 | MITRA ASSOCIATES | 21.47 | 0 | 50
4324 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SARANGA & KAMALPUR Piped Water Supply Scheme under Khandaghosh Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000082/2023-2024 | 2078/BWD | 04/05/2023 | 698 | KHAN ENTERPRISE | 820.73 | 0 | 42
4325 | Burdwan Division | Durgapur Sub-DIvision | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001180/2023-2024 | 995/DSD | 29/12/2023 | 183 | SUJAUDDIN SEKH | 2 | 0 | 60
4326 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000106/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 5.64 | 0 | 0
4327 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000193/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 14.43 | 0 | 0
4328 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000306/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 19.29 | 0 | 0
4329 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | RTOR000720/2023-2024 | 5266/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
4330 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR KAMALPUR PWSS PH-1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02870/2023-2024 | BP-2023-24-601 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.95 | 0 | 0
4331 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR KAMALPUR PWSS PH-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | BILL/02874/2023-2024 | BP-2023-24-602 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.8 | 0 | 0
4332 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 10
4333 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0
4334 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kamalpur Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000733/2023-2024 | 4043/CMD | 29/08/2023 | 30 | M/S. SWAPAN BANERJEE | 28.97 | 0 | 100
4335 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of various D.I. Mechanical joints & specials for KATNABIL & BANTIR Piped W/S. Scheme within Burdwan Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000302/2024-2025 | 2825/BWD | 19/07/2024 | 216 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 100
4336 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to UCHALAN, CHAK CHANDAN, SERPUR & KATNABIL Piped Water Supply Scheme under Raina II Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000367/2023-2024 | 3076/BWD | 18/07/2023 | 988 | SK ALIM | 1307.56 | 0 | 75
4337 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000375/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.23 | 0 | 0
4338 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000512/2023-2024 | 4036/BWD | 08/09/2023 | 0 | Resource Division | 4.83 | 0 | 0
4339 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000673/2023-2024 | 5050/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
4340 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Katnabil PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01700/2023-2024 | BP-2023-24-231 | 20/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.27 | 0 | 0
4341 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Katnabil W/S Scheme PH No.-II | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01800/2023-2024 | BP-2023-24-300 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.15 | 0 | 0
4342 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
4343 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Katnabil Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000727/2023-2024 | 4038/CMD | 29/08/2023 | 581 | AHALYA ENGINEERING WORKS | 28.95 | 0 | 96
4344 | Burdwan Division | Central Mechanical Sub-Division | RAJUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000007/2023-2024 | 1701/BWD | 12/04/2023 | 365 | TEKNO ENTERPRISE | 471.14 | 0 | 77
4345 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000057/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 16.04 | 0 | 0
4346 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000182/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 10.9 | 0 | 0
4347 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000489/2023-2024 | 4013/BWD | 08/09/2023 | 0 | Resource Division | 15.19 | 0 | 0
4348 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000623/2023-2024 | 4881/BWD | 10/11/2023 | 0 | Resource Division | 29.6 | 0 | 0
4349 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Rajur PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01766/2023-2024 | BP-2023-24-278 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.15 | 0 | 0
4350 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at RAJUR W/S Scheme PH-II. | Assistant Engineer | Junior Engineer | BILL/01813/2023-2024 | BP-2023-24-317 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.22 | 0 | 0
4351 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
4352 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at RAJUR Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000825/2023-2024 | 4102/CMD | 29/08/2023 | 30 | S DUTTA | 28.98 | 0 | 90
4353 | Burdwan Division | Kalna Sub-division | Restoration work of Barabaharkuli to Badla village road with a bridge over river Behula road from 0.0 km to 1.3 km and 1.8 km to 2.2 km damadged due to laying of underground water pipeline by PHE with box cutting and jhama with moorum consolidation under kalna highway subdivision of Burdwan south highway division ,P.W(Roads)dte ,during the year 2023-2024 | Assistant Engineer | JUNIOR ENGINEER | BILL/00645/2024-2025 | 825/JJM | 13/09/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 5.36 | 0 | 0
4354 | Burdwan Division | Kalna Sub-division | BARA BAHARKULI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000178/2023-2024 | 2597/BWD | 02/06/2023 | 365 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 236.3 | 0 | 65
4355 | Burdwan Division | Kalna Sub-division | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0
4356 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000050/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 10.04 | 0 | 0
4357 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000200/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 10.94 | 0 | 0
4358 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000785/2023-2024 | 328/BWD | 24/01/2024 | 0 | Resource Division | 24.62 | 0 | 0
4359 | Central Mechanical | Kalna Sub-division | New service connection charges for Bara Baharkuli PWSS TW-2 | Assistant Engineer | JUNIOR ENGINEER | BILL/01668/2023-2024 | BP-2023-24-219 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.15 | 0 | 0
4360 | Central Mechanical | Kalna Sub-division | Quotation for new electric service connection at Bara Baharkhuli PH NO.-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01747/2023-2024 | BP-2023-24-268 | 11/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.87 | 0 | 0
4361 | Burdwan Division | Central Mechanical Sub-Division | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000288/2024-2025 | 2741/BWD | 12/07/2024 | 538 | M/S M.M. ENTERPRISE | 205.15 | 0 | 65
4362 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000191/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 4.39 | 0 | 0
4363 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000397/2023-2024 | 3843/BWD | 01/09/2023 | 0 | Resource Division | 1.09 | 0 | 0
4364 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000581/2023-2024 | 4895/BWD | 10/11/2023 | 0 | Resource Division | 4.76 | 0 | 0
4365 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Chakdaha PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01765/2023-2024 | BP-2023-24-279 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.1 | 0 | 0
4366 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0
4367 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at CHAKDAHA [KETUGRAM-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000890/2023-2024 | 4153/CMD | 29/08/2023 | 640 | AMUSAR IMPEX PVT. LTD. | 21.26 | 0 | 47
4368 | Burdwan Division |  | Construction of boundary wall at Pump house no - 3 Site of Hatgobindapur Water Supply Scheme under Bardhaman-II Dev. Block of Burdwan Division, PHE Dte. (Length -40.00 Mtr, Col-16 Nos). Group : B |  |  | ORD/000052/2022-2023 | 701/BSD | 27/04/2022 | 45 | ANIRUDDHA FARUQUE | 2.61 | 0 | 1
4369 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of HATGOBINDAPUR Piped Water Supply Scheme and its adjoining mouzas at Burdwan - II Block under Burdwan Division, PHE. Dte. |  |  | ORD/000054/2022-2023 | 2232/BWD | 29/04/2022 | 30 | M/S ASHA CONSTRUCTION | 19.32 | 0 | 1
4370 | Burdwan Division |  | Additional work for Construction of boundary wall at Pump house no - 3 Site of Hatgobindapur Water Supply Scheme under Bardhaman-II Dev. Block of Burdwan Division, PHE Dte. (Length -18.00 Mtr, Col-2 Nos). Group - A. |  |  | ORD/000061/2022-2023 | 722/BSD | 02/05/2022 | 30 | MOHAMMAD ISSA | 1.48 | 0 | 1
4371 | Burdwan Division |  | Left out FHTC (Hatgobindapur, Banagram, Ramnagar & Hatkanda village) of HATGOBINDAPUR PWSS under Burdwan-II Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000116/2023-2024 | 2302/BWD | 19/05/2023 | 30 | M/S SAYAN CHAKRABORTY | 9.6 | 0 | 100
4372 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Hatgobindapur village (Part) of Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 01] |  |  | ORD/000122/2021-2022 | 4390/BWD | 31/08/2021 | 15 | M/S ASHA CONSTRUCTION | 4.86 | 0 | 1
4373 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Hatgobindapur village of Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿6A¿] (T.R. No. 156/BWD/2020-21) |  |  | ORD/000152/2020-2021 | 2743/BWD | 10/08/2020 | 30 | M/S ASHA CONSTRUCTION | 4.92 | 4.92 | 1
4374 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Banagram village of Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿6B¿] (T.R. No.-155/BWD/2020-21) |  |  | ORD/000153/2020-2021 | 2744/BWD | 10/08/2020 | 30 | M/S ASHA CONSTRUCTION | 4.92 | 0 | 1
4375 | Burdwan Division |  | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 3rd tube well site (Size-3.60 mtr x 3.00 mtr) for HATGOBINDAPUR water supply scheme under Burdwan-II development Block under Burdwan Sub-Division, under Burdwan Division, PHE Dte.[Gr.-A] |  |  | ORD/000211/2021-2022 | 665/BSD | 07/06/2021 | 45 | KAJAL MUKHERJEE | 2.76 | 0 | 0
4376 | Burdwan Division |  | Providing left out FHTC for 100% covarage in different village within Hatgobindapur PWSS , Bardhhaman-II Development Block under Burdwan Division, PHE Dte |  |  | ORD/000293/2024-2025 | 1275/BSD | 12/07/2024 | 45 | PAL CONSTRUCTION | 4.78 | 0 | 0
4377 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Hatgobindapur village of Hatgobindapur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-317/BWD/2020-21) |  |  | ORD/000347/2020-2021 | 3702/BWD | 05/10/2020 | 30 | M/S ASHA CONSTRUCTION | 4.92 | 4.92 | 1
4378 | Burdwan Division |  | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. |  |  | ORD/000416/2021-2022 | 385/BWD | 20/01/2022 | 30 | BISWAS ENTERPRISE | 11.97 | 0 | 100
4379 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Hatgobindapur village (Part) of Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 01] |  |  | ORD/000465/2020-2021 | 1413/BWD | 18/02/2021 | 15 | M/S ASHA CONSTRUCTION | 4.86 | 4.86 | 0
4380 | Burdwan Division |  | Extension of UPVC distribution pipeline in connection with FHTC for Hatgobindapur and its adjoining mouzas water supply scheme at Bardhaman-II Development Block under Burdwan Division, PHE Dte.[Gr-A] |  |  | ORD/000688/2021-2022 | 989/BSD | 30/07/2021 | 30 | M/S ASHA CONSTRUCTION | 4.82 | 0 | 1
4381 | Burdwan Division |  | Laying of interconnection of the Pump No.-3 with distribution line 100 mm dia for Hatgobindapur piped water supply scheme of Burdwan-II Block under Burdwan Division, PHE Dte.[Gr.-B] |  |  | ORD/000702/2021-2022 | 1027/BSD | 05/08/2021 | 30 | ANWESHA CONSTRUCTION | 1.67 | 0 | 1
4382 | Burdwan Division |  | Sinking of additional Tube well 250 x 200 mm dia Tube well 150 mtr depth by D.R. Rig method using UPVC pipe (CD) and fibre glass strainer for Hatgobindapur piped water supply scheme (3rd tube well site), Block-Burdwan-II under Burdwan Division, PHE Dte. |  |  | ORD/000982/2020-2021 | 1493/BWD | 18/02/2021 | 30 | C.M. ENTERPRISE | 8.68 | 0 | 1
4383 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 6800/BWD | 07/12/2021 | 0 | Resource Division | 2.85 | 0 | 0
4384 | Burdwan Division |  | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001246/2021-2022 | 900/DW | 03/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 34.54 | 0 | 0
4385 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ITLA Piped Water Supply Scheme at Itla (Itla Adibasipara Habitation) & Sudipur (Sudipur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 583/BWD OF 2020-2021.) | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000275/2020-2021 | 545/BWD | 22/01/2021 | 60 | ANWESHA CONSTRUCTION | 17.35 | 0 | 1
4386 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ITLA Piped Water Supply Scheme at Bahadurpur (Bahadurpur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000276/2020-2021 | 617/BWD | 25/01/2021 | 60 | A R TRADERS | 19.81 | 0 | 1
4387 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ITLA Piped Water Supply Scheme at Itla (Itla Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 593/BWD OF 2020-2021] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000308/2020-2021 | 618/BWD | 25/01/2021 | 60 | JAYANTA CHAKRABORTY | 18.36 | 0 | 1
4388 | Burdwan Division | Burdwan Division | Laying of uPVC pipe for providing FHTC at Itla Village within Itla Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte. [Group : E] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000489/2021-2022 | 66/AE/HQ | 11/02/2022 | 30 | MAUVE ENGINEERING AND SERVICES PVT LTD | 4.73 | 0 | 100
4389 | Burdwan Division | Burdwan Division | Interconnection between OHR & Delivery line at Head Works site under ITLA PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000629/2024-2025 | 747/AE/HQ | 13/09/2024 | 30 | DEBJYOTI GOSWAMI | 0.8 | 0 | 100
4390 | Burdwan Division | Burdwan Division | Repairing and restoration of damaged and chokaged various dia UPVC pipeline and Construction of Valve chambers to control flow of water for providing FHTC in ITLA Piped W/S. Scheme at Jamalpur Dev Block under Burdwan Division ,P.H.E Dte._Gr-I | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000667/2021-2022 | 147/AE/HQ | 16/03/2022 | 20 | BHARAT CONSTRUCTION | 4.55 | 0 | 1
4391 | Burdwan Division | Burdwan Division | Interconnection between inlet & delivery pipe with main distribution pipeline within command area of ITLA Piped W/S. Scheme, Jamalpur Block under Burdwan Division, PHE. Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000825/2022-2023 | 213/AE/HQ | 31/03/2023 | 30 | BHARAT CONSTRUCTION | 0.87 | 0 | 0
4392 | Burdwan Division | Burdwan Division | Re-Laying of UPVC Pipeline (damaged by Local Irrigation Work) for providing FHTC at Bag Kalapahar Mouza (Habitation) under ITLA Piped Water Supply Scheme, Jamalpur Development Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000903/2023-2024 | 5513/BWD | 14/12/2023 | 30 | UTPAL NANDI | 8.61 | 0 | 100
4393 | Burdwan Division | Burdwan Division | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/001100/2024-2025 | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 40
4394 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Head Works & 2nd Tube well Site for BORSHUL (Zone-I) Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000193/2023-2024 | 2691/BWD | 08/06/2023 | 45 | J K CORPORATION | 19.84 | 0 | 100
4395 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of boundary wall at 1ST TUBE WALL (HEAD WORK) Site of BARSUL Zone-I Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. Length =100.00 Mtr, Col-35 Nos). | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000277/2024-2025 | 2692/BWD | 10/07/2024 | 172 | RAHAMAN ENTERPRISE | 6.8 | 0 | 100
4396 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
4397 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 2nd Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17 (Size3.60mtrx3.00mtr room) for Barsul Zone-1 its Adjoining Mouza W/S Scheme, Block -Burdwan-II within Burdwan Sub-Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000575/2023-2024 | 2040/BSD | 24/08/2023 | 45 | DEBJYOTI GOSWAMI | 3.19 | 0 | 100
4398 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of Borshul (Zone-I) Piped Water Supply Scheme (Mouzas:- Barshul, Tatkhanda & Dakshin Goplapur) with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under BARDHAMAN- II Block, District:- Purba-Burdwan. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000700/2022-2023 | 616/BWD | 17/02/2023 | 683 | ASHOK KUMAR GHOSH | 331.77 | 0 | 51
4399 | Burdwan Division | Burdwan Sadar Sub-Division | Allied work for construction of pump house including plinth protection with surface drain at head work TW site for Borshul Z-I PWSS under Bardhaman-II block within Burdwan Div.PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000779/2025-2026 | 1470/BSD | 23/06/2025 | 60 | DAWN ASSOCIATES | 2.57 | 0 | 0
4400 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of pump house including plinth protection with surface drain at Head Work TW site for (3.6 mtr. x 3.0 mtr. Size) Borshul Zone-I water supply schemes, Block-Burdwan-II within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000970/2023-2024 | 006/BWD | 02/01/2024 | 364 | DAWN ASSOCIATES | 4.53 | 0 | 100
4401 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Borshul PWSS Z-I TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/01412/2023-2024 | BP-2023-24-141 | 28/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0
4402 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Borshul PWSS Z-I TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | BILL/01413/2023-2024 | BP-2023-24-142 | 28/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.63 | 0 | 0
4403 | Burdwan Division | Central Mechanical Sub-Division | Augmentation of SRIKHANDA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-II Block, District:- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000489/2023-2024 | 3508/BWD | 10/08/2023 | 875 | GUPTA ENTERPRISE | 656.48 | 0 | 18
4404 | Burdwan Division | Central Mechanical Sub-Division | Balance work of OHR, construction Concrete Road, Functional Household Tap Connection, Road restoration etc. for Nanagar PWSS, Srikhanda PWSS, under KATWA -I Block under Katwa Sub-Divn under Burdwan Division, PHE Dte. District:- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000685/2024-2025 | 3655/BWD | 21/10/2024 | 120 | HAMID SK | 121.69 | 0 | 0
4405 | Burdwan Division | Central Mechanical Sub-Division | Construction of Pump House, Boundary walls and Raising Main for Aug. of SRIKHANDA Piped Water Supply Scheme under Katwa-I Block, District:- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000924/2023-2024 | 5486/BWD | 13/12/2023 | 391 | BABUL SK | 9.77 | 0 | 75
4406 | Central Mechanical | Central Mechanical Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT AUGMENTATION OF SRIKHANDA PWSS TW 2 | Assistant Engineer | Junior Engineer | BILL/00365/2024-2025 | BP-2024-25-188 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.98 | 0 | 0
4407 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Augmentation of Srikhanda PWSS, PH-1. | Assistant Engineer | Junior Engineer | BILL/00464/2024-2025 | BP-2024-25-249 | 01/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.73 | 0 | 0
4408 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Srikhanda Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000087/2023-2024 | 2582/CMD | 07/06/2023 | 580 | AMUSAR IMPEX PVT. LTD. | 11.25 | 0 | 95
4409 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 2 at Augumentation of Srikhanda Water Supply Scheme [ BLOCK- Katwa-I ]under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/001644/2023-2024 | 1626/CMD | 15/03/2024 | 30 | D.K. ELECTRIC | 11.62 | 0 | 88
4410 | Durgapur W/S Division | Durgapur Sub-DIvision | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.06.2025 to 31.08.2025 (3 Months). | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000043/2025-2026 | 853/DWSD | 29/05/2025 | 90 | PRAMIT CHATTERJEE | 0.41 | 0 | 0
4411 | Durgapur W/S Division | Durgapur Sub-DIvision | Continuation Order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.08.2024 to 31.01.2025).(Sl-01) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000127/2024-2025 | 1079/DWSD | 30/07/2024 | 184 | SUJIT ROY | 0.82 | 0 | 0
4412 | Durgapur W/S Division | Durgapur Sub-DIvision | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 01.09.2025 to 28.02.2026 (181 days) (Sl-04) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000128/2025-2026 | 1381/DWSD | 26/08/2025 | 181 | PRAMIT CHATTERJEE | 0.86 | 0 | 0
4413 | Durgapur W/S Division | Durgapur Sub-DIvision | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.09.2024 to 28.02.2025 (6 Months).(Sl-01) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000138/2024-2025 | 1244/DWSD | 30/08/2024 | 182 | PRAMIT CHATTERJEE | 0.82 | 0 | 0
4414 | Durgapur W/S Division | Durgapur Sub-DIvision | Name of Work:- Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 16.09.2025 to 31.10.2025 (46 days) (Sl-01) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000139/2025-2026 | 1532/DWSD | 16/09/2025 | 46 | TKB ENTERPRISE | 0.22 | 0 | 0
4415 | Durgapur W/S Division | Durgapur Sub-DIvision | Continuation Order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.02.2025 to 31.07.2025). | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000268/2024-2025 | 163/DWSD | 27/01/2025 | 181 | SUJIT ROY | 0.82 | 0 | 0
4416 | Durgapur W/S Division | Durgapur Sub-DIvision | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2025 to 31.05.2025 (3 Months). | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000280/2024-2025 | 340/DWSD | 27/02/2025 | 89 | PRAMIT CHATTERJEE | 0.41 | 0 | 0
4417 | Durgapur W/S Division | Durgapur Sub-DIvision | Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.02.2024 to 31.07.2024).(Sl-01) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000287/2023-2024 | 106/DWSD | 31/01/2024 | 182 | SUJIT ROY | 0.82 | 0 | 25
4418 | Durgapur W/S Division | Durgapur Sub-DIvision | Hiring of Luxury Diesel Ambassadar Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2024 to 31.08.2024 (6 Months).(Sl-01) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000294/2023-2024 | 267/DWSD | 29/02/2024 | 184 | PRAMIT CHATTERJEE | 0.82 | 0 | 0
4419 | Durgapur W/S Division | Durgapur Sub-DIvision | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex, Banskopa,DGP-12 (w.e.f 18.02.2024 to 29.02.2024). (SL-02) | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000314/2023-2024 | 186/DWSD | 15/02/2024 | 12 | PRAMIT CHATTERJEE | 0.05 | 0 | 100
4420 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000727/2023-2024 | 4581/BWD | 16/10/2023 | 965 | SAFECO ENTERPRISES | 1551.98 | 0 | 60
4421 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000551/2023-2024 | 4314/BWD | 29/09/2023 | 0 | Resource Division | 1.38 | 0 | 0
4422 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000607/2023-2024 | 4912/BWD | 10/11/2023 | 0 | Resource Division | 32.92 | 0 | 0
4423 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000777/2023-2024 | 193/BWD | 10/01/2024 | 0 | Resource Division | 6.7 | 0 | 0
4424 | Central Mechanical | Durgapur Sub-DIvision | QUOTATION FOR NEW SERVICE CONNECTION AT ALIGRAM PWSS TW 2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00371/2024-2025 | BP-2024-25-193 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.58 | 0 | 0
4425 | Central Mechanical | Durgapur Sub-DIvision | New service connection at Aligram W/S PWSS PH-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02312/2023-2024 | BP-2023-24-431 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.53 | 0 | 0
4426 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0
4427 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Aligram Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000747/2023-2024 | 4057/CMD | 29/08/2023 | 642 | EASTERN INDIA SALES & SERVICE | 27.78 | 0 | 48
4428 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related (schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-05-2025 to 31-07-2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000181/2025-2026 | 960/BSD | 30/04/2025 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
4429 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2023 to 31-01-2024) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000985/2023-2024 | 2561/BSD | 30/10/2023 | 66 | MD HASIN | 0.85 | 0 | 0
4430 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000345/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.91 | 0 | 0
4431 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000469/2023-2024 | 3993/BWD | 08/09/2023 | 0 | Resource Division | 7.17 | 0 | 0
4432 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000678/2023-2024 | 5053/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
4433 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new service connection for Mashra PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/00297/2024-2025 | BP-2024-25-147 | 19/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.84 | 0 | 0
4434 | Central Mechanical | Burdwan Sadar Sub-Division | Electric quotation for New Service Connection at Moshra W/S Scehem PH-I. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01782/2023-2024 | BP-2023-24-289 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.54 | 0 | 0
4435 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0
4436 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Moshra Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000714/2023-2024 | 4025/CMD | 29/08/2023 | 642 | MAA KALI ENTERPRISE | 29.37 | 0 | 100
4437 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHATPARA & MAHARUTBA Piped Water Supply Scheme under Mangolkote Block, District:-Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000429/2023-2024 | 3328/BWD | 02/08/2023 | 791 | KAMIRUL SK & CO. | 815.64 | 0 | 10
4438 | Burdwan Division | Central Mechanical Sub-Division | Balance work of MAHARTUTBA Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman | Assistant Engineer | Junior Engineer | ORD/001212/2024-2025 | 722/BWD | 24/02/2025 | 120 | KAMIRUL SK & CO. | 147.19 | 0 | 0
4439 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000115/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 2.48 | 0 | 0
4440 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000336/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 1.47 | 0 | 0
4441 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000815/2023-2024 | 296/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0
4442 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Mahartuba PWSS PH-1 | Assistant Engineer | Junior Engineer | BILL/00385/2024-2025 | BP-2024-25-206 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7 | 0 | 0
4443 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR MAHARTUBA PWSS. | Assistant Engineer | Junior Engineer | BILL/02860/2023-2024 | BP-2023-24-610 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.94 | 0 | 0
4444 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
4445 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Maharutba Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000775/2023-2024 | 4069/CMD | 29/08/2023 | 30 | GLACIER ENGINEERING CO | 26.98 | 0 | 44
4446 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilising Departmental Machineries for MAHARUTBA W/S Scheme (T/W-I), Mongalkote Block under Purba Bardhaman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000157/2023-2024 | 1819/CDD | 07/12/2023 | 30 | M/S PRACHI ENGINEERING | 13.67 | 0 | 100
4447 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for MAHARUTBA W/S Scheme (T/W-II) Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 1338/CDD | 13/09/2023 | 30 | C.M. ENTERPRISE | 11.46 | 0 | 100
4448 | Durgapur W/S Division | Durgapur Sub-DIvision | Sinking of(300X200X150 Mtr deapth) of TW by DR rig method construction of 1 No PH cum Cholorine Room and interconnection and other allied works at Ausgram under Ausgram PWSS ,Ausgram-I,Dist-Purba Bardhaman under DWSD,PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000119/2025-2026 | 1276/DWSD | 08/08/2025 | 90 | SUPRIYA RAY | 33.97 | 0 | 0
4449 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for LDS,FHTC,Road Restoration,Develop Boundary Wall Hight & Land Developement making With necessary allied works at AUSGRAM-I Block of BHOTA PWSS under Durgapur Water Supply Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000180/2024-2025 | 1617/DWSD | 26/11/2024 | 90 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 55.22 | 0 | 40
4450 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 1
4451 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000005/2024-2025 | 1724/P/DWSD | 10/12/2024 | 0 | Resource Division | 8.51 | 0 | 0
4452 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AUSGRAM & BHOTA Piped Water Supply Scheme under Ausgram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000430/2023-2024 | 3324/BWD | 02/08/2023 | 776 | DUTTA ENTERPRISE | 763.14 | 0 | 70
4453 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000019/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 29.49 | 0 | 0
4454 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000214/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 15.16 | 0 | 0
4455 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000494/2023-2024 | 4018/BWD | 08/09/2023 | 0 | Resource Division | 29.12 | 0 | 0
4456 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000595/2023-2024 | 4903/BWD | 10/11/2023 | 0 | Resource Division | 33.07 | 0 | 0
4457 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection for Ausgram PWSS PH 1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00224/2024-2025 | BP-2024-25-115 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.27 | 0 | 0
4458 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Ausgram PWSS PH-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00383/2024-2025 | BP-2024-25-204 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.87 | 0 | 0
4459 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Aushgram W/S Scheme for PH No-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01818/2023-2024 | BP-2023-24-329 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.96 | 0 | 0
4460 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0
4461 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Ausgram Water Supply Scheme [ Block-Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000744/2023-2024 | 4054/CMD | 29/08/2023 | 614 | MENAKA ENTERPRISE. | 27.75 | 0 | 48
4462 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for the work of " Balance work for sinking of 250 x 150mm dia T/W, P/H, Boundary wall, DI RM and LLDS for proposed 3rd T/W and other allied works under Sauta PWSS, Block- Aushgram-II, Dist-Purba Bardhaman under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000001/2024-2025 | 768/DWSD | 06/06/2024 | 45 | SAIKAT RAY | 94.93 | 0 | 70
4463 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Balance works of 160 mm dia HDPE rising main at JOYRAMPUR area and etc. allied works at SUATA of Ausgram -II Block of SUATA W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000099/2024-2025 | 1012/DWSD | 16/07/2024 | 90 | SAIKAT RAY | 67.88 | 0 | 100
4464 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Balance Work for Suata PWSS with LDS,FHTC Under Ausgram- II Block, Diastrict- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000181/2024-2025 | 1618/DWSD | 26/11/2024 | 90 | SAIKAT RAY | 28 | 0 | 100
4465 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000010/2024-2025 | 1724/I/DWSD | 10/12/2024 | 0 | Resource Division | 2.16 | 0 | 0
4466 | Burdwan Division | Durgapur Sub-DIvision | SUATA Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000494/2023-2024 | 3524/BWD | 10/08/2023 | 629 | SAIKAT RAY | 615.97 | 0 | 45
4467 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000058/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 46.65 | 0 | 0
4468 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000326/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.13 | 0 | 0
4469 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000620/2023-2024 | 4887/BWD | 10/11/2023 | 0 | Resource Division | 30.36 | 0 | 0
4470 | Central Mechanical | Durgapur Sub-DIvision | QUOTATION FOR NEW SERVICE CONNECTION FOR SUATA (ADDL TW)PWSS, TW 2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00328/2024-2025 | BP-2024-25-162 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.68 | 0 | 0
4471 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Suata PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01701/2023-2024 | BP-2023-24-233 | 20/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.29 | 0 | 0
4472 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Suata W/S Scheme for PH No-1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01821/2023-2024 | BP-2023-24-331 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0
4473 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Suata Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000748/2023-2024 | 4058/CMD | 29/08/2023 | 30 | DEY ENTERPRISE | 27.79 | 0 | 96
4474 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHATPARA & MAHARUTBA Piped Water Supply Scheme under Mangolkote Block, District:-Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000429/2023-2024 | 3328/BWD | 02/08/2023 | 791 | KAMIRUL SK & CO. | 815.64 | 0 | 10
4475 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000253/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.75 | 0 | 0
4476 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000460/2023-2024 | 3984/BWD | 08/09/2023 | 0 | Resource Division | 1.21 | 0 | 0
4477 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000798/2023-2024 | 311/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0
4478 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Bhatpara PWSS PH-2. | Assistant Engineer | Junior Engineer | BILL/00348/2024-2025 | BP-2024-25-170 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.38 | 0 | 0
4479 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Bhatpara PWSS PH-1. | Assistant Engineer | Junior Engineer | BILL/00349/2024-2025 | BP-2024-25-171 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.58 | 0 | 0
4480 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
4481 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BHATPARA Water Supply Scheme [ Block- MANGALKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000831/2023-2024 | 4108/CMD | 29/08/2023 | 580 | JAL PRAVAHIKA PVT LTD | 28.97 | 0 | 42
4482 | Central Drilling | Central Mechanical Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for Bhatpara W/S Scheme (T/W-I & II), Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2023-2024 | 1820/CDD | 07/12/2023 | 268 | UTTAM KUMAR CHATTERJEE | 23.35 | 0 | 100
4483 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOHAGRAM, KHERUA & JABAGRAM Piped Water Supply Scheme under Mangalkote Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000697/2022-2023 | 582/BWD | 17/02/2023 | 1049 | PUSPA ENTERPRISE | 1185.88 | 0 | 75
4484 | Burdwan Division | Central Mechanical Sub-Division | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001301/2024-2025 | 936/BWD | 11/03/2025 | 180 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0
4485 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000058/2022-2023 | 1244/BWD | 17/03/2023 | 0 | Resource Division | 7.44 | 0 | 0
4486 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000110/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 2.89 | 0 | 0
4487 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000810/2023-2024 | 300/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0
4488 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges of Gohagram W/S Scheme TW-2 | Assistant Engineer | Junior Engineer | BILL/00690/2023-2024 | BP-2023-24-32 | 26/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.55 | 0 | 0
4489 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR GOHAGRAM PWSS TW 1. | Assistant Engineer | Junior Engineer | BILL/02489/2023-2024 | BP-2023-24-539 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.94 | 0 | 0
4490 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
4491 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GOHAGRAM Water Supply Scheme [ Block- MANGALKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000123/2023-2024 | 2640/CMD | 14/06/2023 | 740 | CHOUDHURY ENTERPRISE | 27.48 | 0 | 82
4492 | Central Mechanical | Central Mechanical Sub-Division | Supply and delivery of 10 HP pump motor set at T.W. No - 1 of Gohagram water supply scheme under CMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000842/2024-2025 | 930/DIC/BMSD(D) | 27/12/2024 | 7 | CHOUDHURY ENTERPRISE | 0.81 | 0 | 100
4493 | Burdwan Division | Central Mechanical Sub-Division | NIGAN Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 250 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000142/2023-2024 | 2386/BWD | 23/05/2023 | 365 | AKASH CONSTRUCTION | 400.98 | 0 | 15
4494 | Burdwan Division | Central Mechanical Sub-Division | Continuation work order for Supply of 1 (one) No. Diesel driven Ambassador Car (Luxury Taxi) / Motor Cab on hire basis for the Office of the Assistant Engineer, under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.07.2025 to 31.12.2025]. | Assistant Engineer | Junior Engineer | ORD/000319/2025-2026 | 1595/KTS | 30/06/2025 | 184 | KRISHNA MONDAL | 2.4 | 0 | 33
4495 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000356/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.74 | 0 | 0
4496 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000459/2023-2024 | 3983/BWD | 08/09/2023 | 0 | Resource Division | 3.91 | 0 | 0
4497 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000806/2023-2024 | 303/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0
4498 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Nigan PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01084/2024-2025 | BP-2024-25-394 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.95 | 0 | 0
4499 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Nigan PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01085/2024-2025 | BP-2024-25-395 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.15 | 0 | 0
4500 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
4501 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nigan Water Supply Scheme [ Block- MONGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000770/2023-2024 | 4068/CMD | 29/08/2023 | 710 | AHALYA ENGINEERING WORKS | 27.78 | 0 | 44
4502 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR Additional work for laying of extension or laying of paralled pipeline construction of boundary wall providing left out FHTC road restoration work inter connection of tube well with allied work for Augmentation of Galsi PWSS Galsi-II Block, Dist- Purba Bardhaman under DURGAPUR W/S DIVISION, PHE DTE. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000262/2024-2025 | 533/DWSD | 25/03/2025 | 90 | J D CONSTRUCTION | 159.4 | 0 | 0
4503 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR Additional work for Laying of Extension or Laying of parallel Pipeline, Sinking of Tube Well (5th. TW], Pump House, Providing Leftout FHTC, Road Restoration work, Inter Connection of Tube Well, with allied work for Augmentation of GALSI Piped Water Supply Scheme , Galsi-II Block ,Dist - Purba Bardhaman under Durgapur Water Supply Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000289/2024-2025 | 584/DWSD | 26/03/2025 | 90 | GHOSH CONSTRUCTION | 107.93 | 0 | 0
4504 | Burdwan Division | Durgapur Sub-DIvision | Restoration of damages caused by PHE Dte. at Galsi Gohogram Road between 0.00 Km & 1.50 Km. (NH-2 Junction) from laying of underground pipeline under Asansol Highway Division, PW Roads Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00024/2023-2024 | 24/JJM | 18/04/2023 | 0 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, P.W.(ROADS) DTE. | 4.56 | 0 | 0
4505 | Burdwan Division | Durgapur Sub-DIvision | Quotation for new connection charges for Augmentation of Galsi w/s scheme under Burdwan Division, PHE Dte. T.W. No.-5 [Application No.-5003534483, dt.-28/11/2022, Ref. ID-503226320] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00116/2022-2023 | 915/DW | 30/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.67 | 0 | 0
4506 | Burdwan Division | Durgapur Sub-DIvision | Construction of Toilet (Female) at Durgapur (Burdwan North) Sub Division premises under Augmentation of Galsi piped water supply scheme under Burdwan Division PHE Dte. [SL-08] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000059/2023-2024 | 183/DSD | 18/04/2023 | 21 | ANWESHA CONSTRUCTION | 0.91 | 0 | 100
4507 | Burdwan Division | Durgapur Sub-DIvision | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Dignagar, Galsi, Barabelun & Kotachandipur Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. Dte. _2ND CALL | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000311/2022-2023 | 3624/BWD | 22/08/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.76 | 0 | 1
4508 | Burdwan Division | Durgapur Sub-DIvision | Augmentation of GALSI Water Supply Scheme with LDS, Rising Main, FHTC Work, Pump House & Boundary Wall of Galsi - II Block in Durgapur (Burdwan North) Sub-Division, District - Purba Bardhaman under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000385/2021-2022 | 257/BWD | 13/01/2022 | 725 | M/S EL-CON | 425.49 | 0 | 40
4509 | Burdwan Division | Durgapur Sub-DIvision | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at H.W, 2nd and 3rd Tubewell site for GALSI Piped Water Supply Scheme, Block - Galsi ¿ II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [3 Nos. GTW]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000641/2021-2022 | 1622/BWD | 21/03/2022 | 60 | AUXILIARY TUBE WELL DRILLERS | 35.56 | 0 | 1
4510 | Burdwan Division | Durgapur Sub-DIvision | Route Survey & Preparation of DPR for GALSI PWSS under Durgapur(Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-D] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000655/2021-2022 | 102/DSD | 18/02/2022 | 15 | SIRCON ENGINEERING SERVICES | 2.74 | 0 | 1
4511 | Burdwan Division | Durgapur Sub-DIvision | Dismantling of concrete road in connection of Laying Distribution Network of Ground Water based Piped Water Supply Scheme for Augmentation of GALSI Piped Water Supply Scheme under Galsi-II in Purba Bardhaman District under Burdwan Division, P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000740/2022-2023 | 1084/BWD | 13/03/2023 | 30 | M/S EL-CON | 13.75 | 0 | 0
4512 | Burdwan Division | Durgapur Sub-DIvision | Retrofitting of RCC Elevated Reservoir (Capacity 450 Cum) by Shortcreting, Guniting etc. in connection with Augmentation of Galsi W/S. Scheme under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000819/2021-2022 | 6042/BWD | 07/10/2021 | 45 | SUDIPTO GORAIN | 10 | 0 | 1
4513 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000019/2021-2022 | 7346/BWD | 30/12/2021 | 0 | Resource Division | 13.73 | 0 | 0
4514 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000027/2021-2022 | 554/BWD | 27/01/2022 | 0 | Resource Division | 23.26 | 0 | 0
4515 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000037/2022-2023 | 4629/BWD | 17/10/2022 | 0 | Resource Division | 12.32 | 0 | 0
4516 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000098/2021-2022 | 772/BWD | 07/02/2022 | 0 | Resource Division | 43.86 | 0 | 0
4517 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000167/2021-2022 | 1327/BWD | 08/03/2022 | 0 | Resource Division | 55.09 | 0 | 0
4518 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000185/2021-2022 | 1380/BWD | 09/03/2022 | 0 | Resource Division | 3.86 | 0 | 0
4519 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | RTOR000235/2021-2022 | 1559/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
4520 | Burdwan Division | Durgapur Sub-DIvision | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | VCH/001555/2021-2022 | 1194/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0
4521 | Burdwan Division | Durgapur Sub-DIvision | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
4522 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 3 (SL no.5) at Augumentation of Galsi Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000068/2023-2024 | 2563/CMD | 06/06/2023 | 30 | C.M. ENTERPRISE | 10.78 | 0 | 0
4523 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation of Galsi Water Supply Scheme [ Block- Galsi-ii ] at pwss-2/3 site, Tube well No.-4 under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000613/2022-2023 | 2097/CMD | 08/09/2022 | 30 | UNIVERSAL ENTERPRISES | 11.07 | 0 | 1
4524 | Burdwan Division | Central Mechanical Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme GANGATIKURI PWSS (Sl No-04) | Assistant Engineer | Junior Engineer | ORD/000072/2023-2024 | 396/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 2.49 | 0 | 100
4525 | Burdwan Division | Central Mechanical Sub-Division | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | Assistant Engineer | Junior Engineer | ORD/000683/2024-2025 | 1009/KTS | 19/07/2024 | 60 | AJIT SAMANTA | 0.77 | 0 | 100
4526 | Burdwan Division | Central Mechanical Sub-Division | Augmentation of GANGATIKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM-II Block, District:- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000897/2023-2024 | 5375/BWD | 07/12/2023 | 602 | S.S. ENTERPRISE | 194.38 | 0 | 56
4527 | Burdwan Division | Central Mechanical Sub-Division | Protection work for construction of concrete road along with other allied work in connection with Gangatikuri PWSs (SM/15159) under Ketugram II Block under Katwa Sub Division within Burdwan Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/001059/2024-2025 | 258/BWD | 14/01/2025 | 352 | S.S. ENTERPRISE | 34.25 | 0 | 0
4528 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Augmentation of Gangatikuri PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/01093/2024-2025 | BP-2024-25-402 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.88 | 0 | 0
4529 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Gangatikuri Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000093/2023-2024 | 2584/CMD | 07/06/2023 | 730 | M/S, S.S. ENTERPRISE. | 22.6 | 0 | 44
4530 | Central Mechanical | Central Mechanical Sub-Division | Yard lighting arrangement & allied works at Gangatikuri water supply scheme under Ketugram-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000408/2024-2025 | 2788/CMD | 01/10/2024 | 60 | DILIP MAHATO | 15.98 | 0 | 0
4531 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PALISGRAM, PURBA NAYAPARA & SITAHATI Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000695/2023-2024 | 4364/BWD | 04/10/2023 | 910 | M/S S. CHOUDHURY | 1505.07 | 0 | 77
4532 | Burdwan Division | Central Mechanical Sub-Division | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | Assistant Engineer | Junior Engineer | ORD/001212/2023-2024 | 907/BWD | 04/03/2024 | 30 | MANASH GHOSH | 23.87 | 0 | 100
4533 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000009/2024-2025 | 4118/BWD | 25/11/2024 | 0 | Resource Division | 18.62 | 0 | 0
4534 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000041/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.1 | 0 | 0
4535 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000324/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.24 | 0 | 0
4536 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000734/2023-2024 | 5233/BWD | 30/11/2023 | 0 | Resource Division | 20.37 | 0 | 0
4537 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR SITAHATI PWSS. | Assistant Engineer | Junior Engineer | BILL/02861/2023-2024 | BP-2023-24-612 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.43 | 0 | 0
4538 | Central Mechanical | Central Mechanical Sub-Division | NEW SERVICE CONNECTION FOR SITAHATI PWSS. | Assistant Engineer | Junior Engineer | BILL/02863/2023-2024 | BP-2023-24-611 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.68 | 0 | 0
4539 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
4540 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SITAHATI Water Supply Scheme [ Block- MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000875/2023-2024 | 4138/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 27.7 | 0 | 46
4541 | Burdwan Division | Burdwan Sadar Sub-Division | Providing laying distrfrrrrribution pipe line at Amtala-Sukantapally due to construction of Road by gp for Nababhat PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000143/2024-2025 | 1031/BSD | 10/06/2024 | 30 | SANDIPAN SENGUPTA | 0.96 | 0 | 100
4542 | Burdwan Division | Burdwan Sadar Sub-Division | Allied work for Augmentation of NABABHAT PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000432/2023-2024 | 3360/BWD | 02/08/2023 | 60 | M/S ANAND CONSTRUCTION | 40.09 | 0 | 100
4543 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work for Augmentation of Nababhat PWSS in connection with renovation and modification of administrative office complex building under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000450/2023-2024 | 3400/BWD | 03/08/2023 | 30 | SANDIPAN SENGUPTA | 7.78 | 0 | 100
4544 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for NABABHAT its Adjoining Mouza W/S Scheme, Block -Bardhaman-I within Burdwan Sub-Division, PHE Dte. (Mouza- KRISHNAPUR) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000830/2022-2023 | 499/BSD | 21/03/2023 | 45 | BHASKAR NANDY | 3.16 | 0 | 100
4545 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work for Augmentation of Nababhat PWSS in connection with renovation and modification of administrative office complex building under Burdwan Division PHE Dte. (Part - II). | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000849/2023-2024 | 5156/BWD | 24/11/2023 | 30 | SANDIPAN SENGUPTA | 9.63 | 0 | 100
4546 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of inter connection between 3rd tube well site (Mouza-Krishnapur) and distribution system for Nababhat PWSS within Bardhaman-I Block , under Burdwan Division, PHE Dte | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000942/2023-2024 | 2951/BSD | 19/12/2023 | 45 | I.S. ENTERPRISE | 2.91 | 0 | 100
4547 | Burdwan Division | Burdwan Sadar Sub-Division | Providing laying distribution pipe line due to Constructioon of road by GP for NABABHAT PWSS under Burdwan-I Block of within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001190/2023-2024 | 536/BSD | 14/03/2024 | 30 | NABAKUMAR DAS | 0.86 | 0 | 100
4548 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work for Augmentation of Nababhat PWSS in connection with upgradation of Approach Road, Land Development, etc for Head Works Site of Nababhat PWSS under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001208/2024-2025 | 661/BWD | 18/02/2025 | 30 | M/S S. CHOUDHURY | 19.92 | 0 | 100
4549 | Burdwan Division | Burdwan Sadar Sub-Division | Balance Work for extension of pipe lines to provide FHTC With Sinking of Tub well , Construction of pump house with Boundary wall & other related work for TALIT-SIMDAL (SM/18112), NABABHAT (SM-15166) and DEWANDIGHI-MIRJAPUR (SM/09494) PWSS under Burdwan Sub-Div., Block -Bwn-1, under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001248/2024-2025 | 793/BWD | 03/03/2025 | 120 | M/S S.S. ENTERPRISE | 227.66 | 0 | 0
4550 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges of Aug. Nababhat W/S Scheme TW-3 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00686/2023-2024 | BP-2023-24-31 | 23/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.58 | 0 | 0
4551 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of NABABHAT( Part-B)[BURDWAN-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000571/2023-2024 | 3899/CMD | 18/08/2023 | 30 | CINZANO | 22.41 | 0 | 50
4552 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Chandutia PWSS under Burdwan-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000348/2023-2024 | 1475/BSD | 12/07/2023 | 15 | MEASURE LAND | 0.78 | 0 | 100
4553 | Burdwan Division | Burdwan Sadar Sub-Division | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 507 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 85
4554 | Burdwan Division | Katwa Sub-Division | Balance work of OHR at Head Work site, construction of HUME Pipe culvert , Road restoration work and boundary wall at 2nd TW site with Gate, land development at Head work site and 2nd TW site under KAITHAN, SUDPUR & PANUHAT Piped Water Supply Scheme under KATWA -I Block, under Katwa Sub-Division within Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000486/2024-2025 | 3141/BWD | 20/08/2024 | 120 | VISHAL CONSTRUCTION CO. | 126.29 | 0 | 50
4555 | Burdwan Division | Katwa Sub-Division | Augmentation of SUDPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-II Block, District:- Purba-Bardhaman._2ND CALL | Assistant Engineer |  | ORD/000658/2023-2024 | 4122/BWD | 14/09/2023 | 840 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 442.27 | 0 | 63
4556 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAJITPUR, SHUKUR & HARISHNAPUR Piped Water Supply Scheme under RAINA-I Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000388/2023-2024 | 3197/BWD | 24/07/2023 | 907 | MRITYUNJOY MUKHERJEE & CO. | 1242.03 | 0 | 55
4557 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related(schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-02-2025 to 30-04-2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001402/2024-2025 | 240/BSD | 31/01/2025 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
4558 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000314/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 5.01 | 0 | 0
4559 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000480/2023-2024 | 4004/BWD | 08/09/2023 | 0 | Resource Division | 7.71 | 0 | 0
4560 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000693/2023-2024 | 5072/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
4561 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Shukur PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01762/2023-2024 | BP-2023-24-272 | 15/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.71 | 0 | 0
4562 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Sukur W/S Scheme PH No.-I | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01793/2023-2024 | BP-2023-24-318 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.06 | 0 | 0
4563 | Central Mechanical | Burdwan Sadar Sub-Division | Continuation order-Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven ) for supervision of site for the office of the Assistant Engineer,under CMD,PHE,Dte. [W.e.f-01/10/2024 to 30/11/2024) [UNDER JJM WORKS] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000425/2024-2025 | 1248/CMSD | 30/09/2024 | 61 | PRODYUT GHOSH | 0.8 | 0 | 0
4564 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Shukur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000724/2023-2024 | 4035/CMD | 29/08/2023 | 642 | S.P. CONSTRUCTION | 28.98 | 0 | 95
4565 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KASIPUR, PATHAR GHATA & SABIDPUR Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000541/2023-2024 | 3697/BWD | 24/08/2023 | 770 | SUPRITI ENTERPRISE | 1185.67 | 0 | 42
4566 | Burdwan Division | Kalna Sub-division | Work Order for "Restoration of pipeline with other allied works at different places of Akalposh, singa, kadiara, panchrakhi mouja under Patahrghata Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-II panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000857/2024-2025 | 1843/KSD | 27/11/2024 | 15 | SUPRITI ENTERPRISE | 2.86 | 0 | 0
4567 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR PATHARGHATA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001167/2023-2024 | 2149/KSD | 07/03/2024 | 10 | DEL DELTA CONSTRUCTION | 0.66 | 0 | 100
4568 | Burdwan Division | Kalna Sub-division | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0
4569 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000086/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 32.19 | 0 | 0
4570 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000368/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.93 | 0 | 0
4571 | Central Mechanical | Kalna Sub-division | New electric connection for Patharghata PWSS, PH-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/01879/2023-2024 | BP-2023-24-351 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.33 | 0 | 0
4572 | Central Mechanical | Kalna Sub-division | New electric connection for Patharghata PWSS, PH-1. | Assistant Engineer | JUNIOR ENGINEER | BILL/01880/2023-2024 | BP-2023-24-351 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.41 | 0 | 0
4573 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 20
4574 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PATHAR GHATA Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000901/2023-2024 | 4165/CMD | 29/08/2023 | 735 | J.S. CONSTRUCTION. | 28.48 | 0 | 45
4575 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMPUR, GAHAK & SHANKRA Piped Water Supply Scheme under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000639/2023-2024 | 3957/BWD | 07/09/2023 | 1051 | M/S B. NANDI | 758.52 | 0 | 20
4576 | Burdwan Division | Kalna Sub-division | Work order for "Service for land acquisition for different PWSS under JJM of Purbasthali-I block under Kalna Sub-Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER | ORD/000962/2023-2024 | 1721/KSD | 05/12/2023 | 91 | PARTHA PRATIM ACHARYA | 0.96 | 0 | 5
4577 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000305/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.59 | 0 | 0
4578 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000546/2023-2024 | 4311/BWD | 29/09/2023 | 0 | Resource Division | 8.44 | 0 | 0
4579 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000590/2023-2024 | 4898/BWD | 10/11/2023 | 0 | Resource Division | 13.06 | 0 | 0
4580 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0
4581 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at SHANKRA [PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000887/2023-2024 | 4150/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 21.22 | 0 | 0
4582 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of TEHATA Zone-I & II (SM/16301) Water Supply Scheme, CHAKSIMLA (SM/15586) Water Supply Scheme & DWARIATON (SM/16285) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000162/2024-2025 | 2201/BWD | 13/06/2024 | 752 | M/S ASHA CONSTRUCTION | 449.98 | 0 | 25
4583 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALINDAR, CHAK SHIMLA & DWARIATAN Piped Water Supply Scheme under Kalna II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000539/2023-2024 | 3700/BWD | 24/08/2023 | 770 | SUPRITI ENTERPRISE | 1424.22 | 0 | 30
4584 | Burdwan Division | Kalna Sub-division | Work Order "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DWARIATON PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001152/2023-2024 | 2021/KSD | 06/03/2024 | 10 | BISWAS ENTERPRISE | 0.66 | 0 | 2
4585 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000078/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 33.94 | 0 | 0
4586 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000246/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 21.09 | 0 | 0
4587 | Central Mechanical | Kalna Sub-division | New electric connection for Dwariatan PWSS, PH-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/01881/2023-2024 | BP-2023-24-353 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.95 | 0 | 0
4588 | Central Mechanical | Kalna Sub-division | New Service connection at Dwariatan PWSS PH-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/02320/2023-2024 | BP-2023-24-459 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.24 | 0 | 0
4589 | Burdwan Division | Kalna Sub-division | Arrangement of drinking water supply by installation of solar submersible pump including sinking of 200 mm. dia. Tube well 150 Mtr. Deep by direct rotary rig method, Laying dist. System, FHTC and 2 Nos. 5000 Ltr. PVC tank installation with construction of RCC structure for BHAGABATITALA Habitation which is uncovered of MANIKHAR Piped W/S. Scheme, Block KALNA-1 under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000018/2025-2026 | 1245/BWD | 23/04/2025 | 45 | A.R. TRADERS | 30.74 | 0 | 75
4590 | Burdwan Division | Kalna Sub-division | Augmentation of MANIKHAR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Kalna - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000157/2023-2024 | 2453/BWD | 31/05/2023 | 60 | SETH ENTERPRISE | 34.49 | 0 | 100
4591 | Burdwan Division | Kalna Sub-division | Work order for 'Restoration of Concrete work and land development at Head Work Site of Manikhar PWSS under Kalna Sub-Division under Burdwan Division, PHE Dte.'. | Assistant Engineer |  | ORD/000807/2024-2025 | 1771/KSD | 20/11/2024 | 30 | BISWAS ENTERPRISE | 3.26 | 0 | 100
4592 | Burdwan Division | Kalna Sub-division | Work Oder for "Laying of Rising Main and alied work such as brick work, P.C.C. work and dismantling work etc. for Manikhar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer |  | ORD/000978/2023-2024 | 1706/KSD | 01/12/2023 | 7 | BISWAS ENTERPRISE | 0.51 | 0 | 100
4593 | Burdwan Division | Kalna Sub-division | Interconnection in distribution system from OHR to in between 1st and 2nd Tube Well site for smooth functioning of FHTC work of MAJHERGRAM W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000160/2023-2024 | 2575/BWD | 01/06/2023 | 30 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.54 | 0 | 100
4594 | Burdwan Division | Kalna Sub-division | Laying of UPVC pipeline & providing FHTC work at Dhanyakherur, Majhergram bazar & Hattola village of MAJHERGRAM Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000161/2023-2024 | 2456/BWD | 31/05/2023 | 30 | PRONAB KUMAR DEY | 9.68 | 0 | 100
4595 | Burdwan Division | Kalna Sub-division | Providing FHTC & laying of HDPE pipe line for village of Madhyamgram, Dakshinpara, Binnerpar, Dhanyakherur of MAJHERGRAM PWSS of Manteswer Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000174/2024-2025 | 2251/BWD | 18/06/2024 | 120 | A.R. TRADERS | 40.92 | 0 | 100
4596 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 2nd TW Site of Aug. of MAJHERGRAM & its adjoining mouzas Piped Water Supply Scheme, Block Monteswar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000542/2022-2023 | 5094/BWD | 17/11/2022 | 30 | DAS CONSTRUCTION | 8.71 | 0 | 1
4597 | Burdwan Division | Kalna Sub-division | Laying of 75 mm dia HDPE Pipe of Majhergram PWSS of Madhyamgram uttarpara village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | Assistant Engineer |  | ORD/000762/2024-2025 | 908/DSD | 28/10/2024 | 30 | M/S GOSWAMI CONSTRUCTION | 0.96 | 0 | 100
4598 | Burdwan Division | Kalna Sub-division | Painting and others ancillary works related to OHR of MAJHERGRAM PWSS under Durgapur Sub Division of MANTESWER Block under Burdwan Division P.H.E.Dte. | Assistant Engineer |  | ORD/001221/2024-2025 | 728/BWD | 24/02/2025 | 45 | A.R. TRADERS | 7.02 | 0 | 0
4599 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of JHAUDANGA (SM/16293), KASHIPUR (SM/16297), PATULI (SM/09718) & PARULIA (SM/09719) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000163/2024-2025 | 2202/BWD | 13/06/2024 | 631 | MONDAL PRECISION PVT LTD | 570 | 0 | 2
4600 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 09 Nos. Piped W/S. Schemes under Purbasthali II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000338/2024-2025 | 3018/BWD | 05/08/2024 | 50 | HORIZEN | 23.7 | 0 | 10
4601 | Burdwan Division | Kalna Sub-division | Construction Pump house and construction (As per drawing no-PHE/SE/CC/PH/DWG-01/ 2022-2023) of new (In same place) Pump House No-2 of JHAUDANGA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000709/2023-2024 | 4521/BWD | 12/10/2023 | 60 | IYASIN DAFADAR | 6.76 | 0 | 15
4602 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 1ST TW Site of JHAUDANGA & its adjoining mouzas Piped Water Supply Scheme, Block Purbasthali II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000720/2023-2024 | 273/BWD | 16/01/2024 | 30 | AUXILIARY TUBE WELL DRILLERS | 8.64 | 0 | 1
4603 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of JHAUDANGA( Part-B)[ PURBASTHALI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001084/2023-2024 | 4475/CMD | 05/10/2023 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 24.19 | 0 | 100
4604 | Burdwan Division | Kalna Sub-division | Augmentation of PURBA SAHAPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Kalna - II Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000416/2023-2024 | 3273/BWD | 28/07/2023 | 60 | PARTHA PRATIM ACHARYA | 21.94 | 0 | 80
4605 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of PURBA SAHAPUR[KALNA-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001085/2023-2024 | 4477/CMD | 05/10/2023 | 30 | DUTTA ENTERPRISE | 24.4 | 0 | 0
4606 | Burdwan Division | Kalna Sub-division | Augmentation of SONARUDRA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jivan Mission of Purbasthali - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000152/2023-2024 | 2442/BWD | 30/05/2023 | 60 | ROHAN MONDAL | 43.32 | 0 | 20
4607 | Burdwan Division | Kalna Sub-division | Different Types of work involved in connection with Augmentation of SONARUDRA (SM/16349) & KACHUA (SM/13497) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000192/2024-2025 | 2430/BWD | 27/06/2024 | 480 | R.G. INFRASTRUCTURE | 240.7 | 0 | 2
4608 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 14 Nos. Piped W/S. Schemes under Purbasthali I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000337/2024-2025 | 3017/BWD | 05/08/2024 | 75 | HORIZEN | 38 | 0 | 100
4609 | Burdwan Division | Kalna Sub-division | Laying of 140 mm dia HDPE Pipeline from Sonarudra Head Work Site more to upto Shyambati & Baidyapur more (Sec 34-2-3-6-10-12-14-16-16A-16B) of SONARUDRA W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000601/2021-2022 | 1486/BWD | 14/03/2022 | 30 | HAMID SK | 18.85 | 0 | 100
4610 | Burdwan Division | Kalna Sub-division | Sinking of additional Tube Well, construction of pump house & boundary wall & laying interconnection of SONARUDRA Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (PP Site- Shyambati Baidyapur). | Assistant Engineer |  | ORD/000864/2023-2024 | 5295/BWD | 01/12/2023 | 60 | HI-LIGHT ELECTRONICS | 27.37 | 0 | 60
4611 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch room, boundary walls with gates, land development, surface drains and internal pathways at different TW site for NERAGOHALIA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000478/2023-2024 | 3493/BWD | 09/08/2023 | 365 | M/S ASHA CONSTRUCTION | 577.52 | 0 | 35
4612 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of Conc. road, Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for MAGRA, SANUI, SATGACHIA Zone-I & NARAGOHALIA PIPED WATER SUPPLY SCHEME, Block-Memari-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001192/2024-2025 | 611/BWD | 11/02/2025 | 180 | M/S ASHA CONSTRUCTION | 354.13 | 0 | 25
4613 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000103/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 18.38 | 0 | 0
4614 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000354/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 20.45 | 0 | 0
4615 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000727/2023-2024 | 5273/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
4616 | Central Mechanical | Burdwan Sadar Sub-Division | Quotation for new service connection at NARAGOHALIA W/S Scheme PH-I. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01814/2023-2024 | BP-2023-24-321 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.28 | 0 | 0
4617 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Neragohalia PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02205/2023-2024 | BP-2023-24-391 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.09 | 0 | 0
4618 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
4619 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Neragohalia Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000660/2023-2024 | 4003/CMD | 29/08/2023 | 30 | DUTTA ENTERPRISE | 28.98 | 0 | 60
4620 | Burdwan Division |  | BALIDANGA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongolkote Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL |  |  | ORD/000457/2023-2024 | 3439/BWD | 08/08/2023 | 967 | M/S S.S. ENTERPRISE | 567.39 | 0 | 27
4621 | Burdwan Division |  | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. |  |  | ORD/001080/2023-2024 | 22/KTS | 05/01/2024 | 70 | AJIT SAMANTA | 0.9 | 0 | 100
4622 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000225/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.45 | 0 | 0
4623 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000409/2023-2024 | 3871/BWD | 01/09/2023 | 0 | Resource Division | 88.34 | 0 | 0
4624 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000649/2023-2024 | 5097/BWD | 23/11/2023 | 0 | Resource Division | 19.96 | 0 | 0
4625 | Central Mechanical |  | NEW SERVICE CONNECTION FOR BALIDANGA PWSS. |  |  | BILL/02474/2023-2024 | BP-2023-24-530 | 13/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.7 | 0 | 0
4626 | Central Mechanical |  | NEW SERVICE CONNECTION FOR BALIDANGA PWSS. |  |  | BILL/02475/2023-2024 | BP-2023-24-531 | 13/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.76 | 0 | 0
4627 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 10
4628 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BALIDANGA Water Supply Scheme [ Block- MANGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000883/2023-2024 | 4146/CMD | 29/08/2023 | 563 | CHOUDHURY ENTERPRISE | 29.7 | 0 | 46
4629 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Balidanga Water Supply Scheme [ BLOCK- Mangalkote ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001395/2024-2025 | 884/CMD | 26/03/2025 | 60 | M/S, S.S. ENTERPRISE. | 12.3 | 0 | 0
4630 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-05-2024 to 31-07-2024) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000108/2024-2025 | 807/BSD | 29/04/2024 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
4631 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHAGABATIPUR, MACHKHARA & UDGARA Piped Water Supply Scheme under Raina ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000690/2023-2024 | 4386/BWD | 05/10/2023 | 365 | SK ALIM | 1378.97 | 0 | 55
4632 | Burdwan Division | Burdwan Sadar Sub-Division | Balance work [i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, Construction of M.S.Structural bridge, canal Crossing, MS casing with allied work of Bhagabatipur, Machkhara, Udgara, Bantir, Chakpurohit Rasuikhanda, Sankarpur, Gopalpur & Belshar PWSS Block-RAINA- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001103/2024-2025 | 469/BWD | 24/01/2025 | 366 | SK ALIM | 1353.91 | 0 | 25
4633 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000205/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 5.77 | 0 | 0
4634 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000534/2023-2024 | 4286/BWD | 29/09/2023 | 0 | Resource Division | 1.53 | 0 | 0
4635 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | RTOR000656/2023-2024 | 5101/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
4636 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for BHAGABATIPUR W/S Scheme PH No.-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01795/2023-2024 | BP-2023-24-312 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.93 | 0 | 0
4637 | Central Mechanical | Burdwan Sadar Sub-Division | New electric connection for Bhagabatipur PWSS, PH-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/01886/2023-2024 | BP-2023-24-343 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.15 | 0 | 0
4638 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 10
4639 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bhagabatipur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000908/2023-2024 | 4172/CMD | 29/08/2023 | 595 | SOUNAK ENTERPRISE | 29.71 | 0 | 90
4640 | Burdwan Division | Kalna Sub-division | Augmentation of Radhanagar Baghnapara Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 200 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation & repairing of existing 180 cum OHR with repairing of switch rooms, boundary walls at different TW site under Kalna-I Block, District:- Purba-Burdwan | Assistant Engineer | JUNIOR ENGINEER | ORD/000476/2023-2024 | 3511/BWD | 10/08/2023 | 598 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 458.55 | 0 | 70
4641 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Radhanagar-Baghnapara W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer | JUNIOR ENGINEER | ORD/000579/2021-2022 | 214/KSD | 24/02/2022 | 21 | ROY CHOUDHURI CONSTRUCTION | 2.96 | 0 | 1
4642 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Radhanagar-Baghnapara W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer | JUNIOR ENGINEER | ORD/000580/2021-2022 | 214/KSD | 24/02/2022 | 21 | ROY CHOWDHURY ASSOCIATES | 2.96 | 0 | 0
4643 | Burdwan Division | Kalna Sub-division | Sinking of additional Tube Well, construction of pump house & boundary wall & laying interconnection of RADHANAGAR BAGHNAPARA Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (PP Site- Khaspur Karim Gachhi). | Assistant Engineer | JUNIOR ENGINEER | ORD/000882/2023-2024 | 5483/BWD | 13/12/2023 | 416 | MUKHERJEE ENTERPRISE | 26.91 | 0 | 45
4644 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000018/2022-2023 | 3277/BWD | 29/07/2022 | 0 | Resource Division | 65.16 | 0 | 0
4645 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000037/2021-2022 | 537/BWD | 27/01/2022 | 0 | Resource Division | 17.54 | 0 | 0
4646 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000193/2021-2022 | 1375/BWD | 09/03/2022 | 0 | Resource Division | 4.85 | 0 | 0
4647 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000221/2021-2022 | 1544/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
4648 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
4649 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 3 at Augumentation of Radhanagar Baghnapara Water Supply Scheme [ BLOCK- Kalna-I ]under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001643/2023-2024 | 1625/CMD | 15/03/2024 | 30 | JOYGURU ENTERPRISE | 12.31 | 0 | 0
4650 | Burdwan Division |  | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000003/2025-2026 | 1116/BWD | 03/04/2025 | 120 | SOFIQUL ISLAM | 176.89 | 0 | 0
4651 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000261/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 3.36 | 0 | 0
4652 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000658/2023-2024 | 5116/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
4653 | Central Mechanical |  | New service connection at Bijur PWSS PH-2 |  |  | BILL/02353/2023-2024 | BP-2023-24-470 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.63 | 0 | 0
4654 | Central Mechanical |  | New service connection at Bijur PWSS PH-1 |  |  | BILL/02355/2023-2024 | BP-2023-24-469 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.66 | 0 | 0
4655 | Central Mechanical |  | New service connection for BIJUR PWSS TW 1. |  |  | BILL/02440/2023-2024 | BP-2023-24-527 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.7 | 0 | 0
4656 | Central Mechanical |  | New service connection for BIJUR PWSS TW 2. |  |  | BILL/02441/2023-2024 | BP-2023-24-526 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.86 | 0 | 0
4657 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0
4658 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bijur Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000713/2023-2024 | 4024/CMD | 29/08/2023 | 30 | MS DAS ELECTRIC CO | 29.4 | 0 | 95
4659 | Burdwan Division |  | Shifting of 11KV HTOH Line for construction of new OHR of Chanchal pwss under Burdwan Division, PHE Dte. [Ref ID-860319929, App ID-100000124989, dt.-10/12/2024] |  |  | BILL/01092/2024-2025 | 1172/JJM | 17/12/2024 | 0 | WBSEDCL | 7 | 0 | 0
4660 | Burdwan Division |  | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related (schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-05-2025 to 31-07-2025) |  |  | ORD/000181/2025-2026 | 960/BSD | 30/04/2025 | 66 | PARVIN BEGAM | 0.85 | 0 | 100
4661 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHANCHAL & NUDIPUR Piped Water Supply Scheme under Memari I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000692/2023-2024 | 4389/BWD | 05/10/2023 | 730 | MANASH GHOSH | 1343.97 | 0 | 45
4662 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000291/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.41 | 0 | 0
4663 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000532/2023-2024 | 4294/BWD | 29/09/2023 | 0 | Resource Division | 1.69 | 0 | 0
4664 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000572/2023-2024 | 4922/BWD | 10/11/2023 | 0 | Resource Division | 41.11 | 0 | 0
4665 | Central Mechanical |  | New Service connection for Chanchal PWSS TW-2. |  |  | BILL/02334/2023-2024 | BP-2023-24-477 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 14.29 | 0 | 0
4666 | Central Mechanical |  | New Service connection for Chanchal PWSS TW-1. |  |  | BILL/02335/2023-2024 | BP-2023-24-476 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.26 | 0 | 0
4667 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0
4668 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at CHANCHAL Water Supply Scheme [ Block- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000788/2023-2024 | 4078/CMD | 29/08/2023 | 30 | UNIVERSAL ENTERPRISES | 44.1 | 0 | 0
4669 | Burdwan Division |  | DIGHRA Piped Water Supply Scheme with sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of 350 cum capacity RCC OHRs with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site under RAINA-II Block, District:- Purba Bardhaman [NEW SCHEME] |  |  | ORD/000485/2023-2024 | 3506/BWD | 10/08/2023 | 875 | M/S PIONEER CONSTRUCTION | 661.73 | 0 | 75
4670 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 4113/BWD | 25/11/2024 | 0 | Resource Division | 17.04 | 0 | 0
4671 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000248/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 15 | 0 | 0
4672 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000421/2023-2024 | 3861/BWD | 01/09/2023 | 0 | Resource Division | 15.75 | 0 | 0
4673 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000666/2023-2024 | 5087/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
4674 | Central Mechanical |  | New Service connection for Dighra W/S Scheme PH No.-I |  |  | BILL/01796/2023-2024 | BP-2023-24-322 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.03 | 0 | 0
4675 | Central Mechanical |  | NEW SERVICE CONNECTION FOR DIGHRA PWSS |  |  | BILL/02590/2023-2024 | BP-2023-24-556 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.16 | 0 | 0
4676 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
4677 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DIGHRA Water Supply Scheme [ Block- RAINA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000841/2023-2024 | 4113/CMD | 29/08/2023 | 642 | GOENKA ENTERPRISE | 28.98 | 0 | 85
4678 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for Design Engineering Services of Survey, General arrangement drawing, Pile foundation design and drawings, Pipe Pedestal and BOM, Structural design design and drawing, Fabrication drawings for 26 Numbers different dia meter pipe crossing Pipe Bridge at "PURANGAN (Zone-I, II, III), 11 Nos. Mouzas under PURSHA and UCHCHGRAM, SHILLA (Zone-I, II, III, IV), TAHER PUR (Zone-I, II, III) and KHANO (Zone-I and II) sites under Durgapur W/S Division,PHE Dte. |  |  | ORD/000105/2024-2025 | 1058/DWSD | 25/07/2024 | 270 | ASTER CONSULTANCY | 47.43 | 0 | 70
4679 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for the work of Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Junior Engineers for the office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.08.2024 to 31.01.2025 (6 Months) |  |  | ORD/000121/2024-2025 | 1108/DWSD | 01/08/2024 | 184 | SIDDHARTH ENTERPRISE | 0.82 | 0 | 0
4680 | Durgapur W/S Division |  | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe Carring Bridge with Pipe supporting structure under SHILLA PIPED W/S SCHMEME under Durgapur W/S Division, PHE Dte. |  |  | ORD/000160/2024-2025 | 1500/DWSD | 05/11/2024 | 422 | M/S S. CHOUDHURY | 1099 | 0 | 45
4681 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for Preparation and Submission of Structural Design Calculation (Civil) & Structural drawing of Proposed CWR with M.S Structural Pump House over cwr, WBSEDCL Mettering Room and - PDB Room -2 Nos, Transformer yeard -2 nos, Chlorin Room -1 No with General Arrangement Drawing of InternalRoad - Drain & necessary Soil investigation at Intake Site of "SHILLA (Zone-I, II, III &IV ) PWSS under Durgapur W/s Division, PHE Dte. |  |  | ORD/000191/2024-2025 | 1606/DWSD | 26/11/2024 | 45 | M/S S. CHOUDHURY | 9.48 | 0 | 100
4682 | Durgapur W/S Division |  | CONTINUTION ORDER FOR Hiring of LUXURY Disel Ambassador Car (Inspection Vehicle) for using of the Junior Engineers for the Office of the EE, Durgapur W/S Division, PHE Dte at Nababhat, Fagupur, Purba Bardhaman for the period of 01.02.2025 to 30.04.2025. (VEHICLE NO WB/04H-5935) |  |  | ORD/000263/2024-2025 | 184/DWSD | 28/01/2025 | 90 | SIDDHARTH ENTERPRISE | 0.41 | 0 | 33
4683 | Burdwan Division |  | Sub Surface Based Piped Water Supply Scheme with LDS, FHTC, Construction of different capacity RCC OHRs with 20.0 mtr. with Staging height including soil investigation, Construction of CWR, Chlorine Room, Guard Room, Sub Station Building, High Lift Pump House Boundary walls with gates, land development, drain and internal pathway of SHILLA Piped Water Supply Scheme under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000455/2023-2024 | 3437/BWD | 08/08/2023 | 877 | M/S S. CHOUDHURY | 2687.54 | 0 | 60
4684 | Burdwan Division |  | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. |  |  | ORD/000872/2023-2024 | 5324/BWD | 01/12/2023 | 120 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 0 | 100
4685 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000309/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.39 | 0 | 0
4686 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000440/2023-2024 | 3847/BWD | 01/09/2023 | 0 | Resource Division | 460.56 | 0 | 0
4687 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000774/2023-2024 | 207/BWD | 10/01/2024 | 0 | Resource Division | 57.55 | 0 | 0
4688 | Central Mechanical |  | Quotation for new service connection Shilla PWSS TW No. 3. |  |  | BILL/00781/2024-2025 | BP-2024-25-291 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.32 | 0 | 0
4689 | Central Mechanical |  | Quotation for new service connection at Shilla PWSS (Naba Khanda) Zone-I. |  |  | BILL/00783/2024-2025 | BP-2024-25-290 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.26 | 0 | 0
4690 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for OHR SITE of Zone-1, 2, 3 & 4 at SHILLA Water Supply Scheme [ BLOCK- Galsi-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000561/2024-2025 | 3101/CMD | 11/12/2024 | 200 | S.K. ELECTRICALS | 50.24 | 0 | 46
4691 | Central Mechanical |  | Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries including intake (Low lift) pumping machineries, illumination arrangement of Shilla Sub-Surface Based Piped Water Supply Scheme under Purba Bardhaman District PHE Dte. |  |  | ORD/000781/2024-2025 | 481/CMD | 06/02/2025 | 75 | JAL PRAVAHIKA PVT LTD | 0 | 0 | 0
4692 | Central Drilling |  | Construction of Tube Well (300 MM x 200 MM x Depth 500 Mtr) for Shilla W/S Scheme(T/W -I) Zone-IV, Block- Galsi-I, Purba Bardhaman District by Central Drilling Division, P.H. Engineering Dte. |  |  | ORD/000216/2023-2024 | 2236/CDD | 11/03/2024 | 60 | SATYAJIT GHOSH | 39.72 | 0 | 0
4693 | Burdwan Division |  | Continuation work order for Supply of 1 (one) No. Diesel driven Ambassador Car (Luxury Taxi) / Motor Cab on hire basis for the Office of the Assistant Engineer, under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.07.2025 to 31.12.2025]. |  |  | ORD/000319/2025-2026 | 1595/KTS | 30/06/2025 | 184 | KRISHNA MONDAL | 2.4 | 0 | 33
4694 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAGHTONA, & KASIGRAM Piped Water Supply Scheme under Katwa ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000390/2023-2024 | 3199/BWD | 24/07/2023 | 1257 | MANASH GHOSH | 1161.82 | 0 | 95
4695 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000020/2024-2025 | 4104/BWD | 25/11/2024 | 0 | Resource Division | 6.95 | 0 | 0
4696 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000318/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.67 | 0 | 0
4697 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000431/2023-2024 | 3855/BWD | 01/09/2023 | 0 | Resource Division | 68.67 | 0 | 0
4698 | Central Mechanical |  | New service connection for Kasigram PWSS PH-3. |  |  | BILL/02907/2023-2024 | BP-2023-24-618 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.73 | 0 | 0
4699 | Central Mechanical |  | New service connection for Kashigram PWSS PH-2. |  |  | BILL/02908/2023-2024 | BP-2023-24-617 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.06 | 0 | 0
4700 | Central Mechanical |  | New service connection for Kasigram PWSS PH-1. |  |  | BILL/02909/2023-2024 | BP-2023-24-616 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.69 | 0 | 0
4701 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0
4702 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KASIGRAM Water Supply Scheme [ Block-KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000881/2023-2024 | 4144/CMD | 29/08/2023 | 492 | M/S. SWAPAN BANERJEE | 45.09 | 0 | 90
4703 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for BARADOBA Piped Water Supply Scheme with FHTC ,Road restoration under AUSGRAM-II Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000173/2024-2025 | 1619/DWSD | 26/11/2024 | 60 | SAIKAT RAY | 15.24 | 0 | 0
4704 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000008/2024-2025 | 1724/R/DWSD | 10/12/2024 | 0 | Resource Division | 0.77 | 0 | 0
4705 | Burdwan Division | Durgapur Sub-DIvision | BARADOBA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under AUSHGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000188/2023-2024 | 2677/BWD | 08/06/2023 | 446 | THREE MAA ENTERPRISE | 109.1 | 0 | 100
4706 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000233/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.17 | 0 | 0
4707 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000438/2023-2024 | 3849/BWD | 01/09/2023 | 0 | Resource Division | 1.22 | 0 | 0
4708 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000612/2023-2024 | 4933/BWD | 10/11/2023 | 0 | Resource Division | 16.68 | 0 | 0
4709 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Baradoba PWSS TW-1 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | BILL/01349/2023-2024 | BP-2023-24-129 | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.34 | 0 | 0
4710 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Baradoba PWSS TW-2 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | BILL/01825/2023-2024 | BP-2023-24-334 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.77 | 0 | 0
4711 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at BARADOBA Water Supply Scheme [Block - AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000449/2023-2024 | 3699/CMD | 07/08/2023 | 999 | M/S, S.DAS AND ENTERPRISE. | 21.33 | 0 | 90
4712 | Burdwan Division |  | Quotation from WBSEDCL for Shifting of 33 KV & LTOH line at Briddhapara village against 1st T.W. of Simlon w/s scheme. |  |  | BILL/00172/2024-2025 | 270/JJM | 21/05/2024 | 0 | WBSEDCL | 14.29 | 0 | 0
4713 | Burdwan Division |  | Laying of rising main along with crossing of pipe line by HDD/Jack pushing method due to widening of Bardhaman-Kalna Road via Simlon in connection with Augmentation of SIMLON Piped Water Supply Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000129/2024-2025 | 2070/BWD | 07/06/2024 | 120 | MANASH GHOSH | 199.36 | 0 | 100
4714 | Burdwan Division |  | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 11 Nos. Piped W/S. Schemes under Kalna I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. |  |  | ORD/000335/2024-2025 | 3015/BWD | 05/08/2024 | 60 | HORIZEN | 29.6 | 0 | 10
4715 | Burdwan Division |  | AUGMENTATION OF SIMLON Piped Water Supply Scheme with sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of 500 cum capacity RCC OHRs with 20.0 mtr. Staging height including soil investigation (2 Nos.) & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site OF ZONE-I & ZONE-II under KALNA-I Block, District:- Purba Bardhaman. |  |  | ORD/000460/2023-2024 | 3442/BWD | 08/08/2023 | 603 | MANASH GHOSH | 1406.99 | 0 | 60
4716 | Burdwan Division |  | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 51
4717 | Central Mechanical |  | Quotation for new service connection at Simlon Zone-2 PWSS TW-1. |  |  | BILL/01190/2024-2025 | BP-2024-25-411 | 11/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.61 | 0 | 0
4718 | Central Mechanical |  | Illumination arrangement and miscellaneous works at Simlon water supply scheme under Kalna-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000402/2024-2025 | 2781/CMD | 01/10/2024 | 60 | SUDIPTA GHOSH | 9.5 | 0 | 0
4719 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of SIMLON (ZONE-I & II) [KALNA-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001301/2023-2024 | 259/CMD | 19/01/2024 | 30 | DUTTA ENTERPRISE | 24.4 | 0 | 0
4720 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENUA, IBRAMBAD & UJNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000462/2023-2024 | 3456/BWD | 08/08/2023 | 855 | M/S S. CHOUDHURY | 2123.7 | 0 | 20
4721 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000333/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 19.69 | 0 | 0
4722 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000447/2023-2024 | 3971/BWD | 08/09/2023 | 0 | Resource Division | 129.95 | 0 | 0
4723 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000794/2023-2024 | 316/BWD | 24/01/2024 | 0 | Resource Division | 47.08 | 0 | 0
4724 | Central Mechanical | Durgapur Sub-DIvision | ADDITIONAL QUOTATION FOR NEW SERVICE CONNECTION FOR UJNA PWSS PH-3 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | BILL/00187/2024-2025 | BP-2024-25-88 | 15/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.3 | 0 | 0
4725 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Ujna PWSS TW-2 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | BILL/01708/2023-2024 | BP-2023-24-235 | 06/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.34 | 0 | 0
4726 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Ujna PWSS TW-1 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | BILL/02199/2023-2024 | BP-2023-24-406 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.99 | 0 | 0
4727 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Ujna PWSS TW-3 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | BILL/02200/2023-2024 | BP-2023-24-406 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0
4728 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
4729 | Central Mechanical | Durgapur Sub-DIvision | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000590/2024-2025 | 3105/CMD | 11/12/2024 | 60 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0
4730 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at UJNA Water Supply Scheme [ Block- MONTESWAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000781/2023-2024 | 4074/CMD | 29/08/2023 | 30 | CONCORD ENGINEERING | 44.42 | 0 | 90
4731 | Burdwan Division |  | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMUL & AURIA Piped Water Supply Scheme under Katwa ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000389/2023-2024 | 3198/BWD | 24/07/2023 | 1257 | MANASH GHOSH | 1418.89 | 0 | 48
4732 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 4106/BWD | 25/11/2024 | 0 | Resource Division | 14.47 | 0 | 0
4733 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000209/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 4.61 | 0 | 0
4734 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000435/2023-2024 | 3851/BWD | 01/09/2023 | 0 | Resource Division | 43.58 | 0 | 0
4735 | Central Mechanical |  | Quotation for new service connection at Amul PWSS PH-3 |  |  | BILL/00386/2024-2025 | BP-2024-25-207 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.67 | 0 | 0
4736 | Central Mechanical |  | New Service connection for Amul PWSS TW-1 |  |  | BILL/02347/2023-2024 | BP-2023-24-464 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.91 | 0 | 0
4737 | Central Mechanical |  | New Service connection for Amul PWSS TW-2 |  |  | BILL/02348/2023-2024 | BP-2023-24-465 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.77 | 0 | 0
4738 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. |  |  | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0
4739 | Central Mechanical |  | Hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte ,wef : 01/ 09/ 20 24 to 31/10/2024. |  |  | ORD/000488/2024-2025 | 528/DIC/BMSD(D) | 23/08/2024 | 61 | SUBRATA BHADRA | 0.81 | 0 | 0
4740 | Central Mechanical |  | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at AMUL Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000795/2023-2024 | 4083/CMD | 29/08/2023 | 615 | JAL PRAVAHIKA PVT LTD | 44.4 | 0 | 31
4741 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Biswarambha, Dhitpur, Doghori, Falea, Harishi & Moail, (6nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000005/2021-2022 | 3121/BWD | 02/06/2021 | 60 | IJABUL SEKH | 225.09 | 91.62 | 0
4742 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Ukhra, Dafarpota, Dampal, Mmudpur, Narayanpur, Nowapara, Patuli, Tegachhi & Gachha (9nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000006/2021-2022 | 3122/BWD | 02/06/2021 | 60 | SK ALIM | 212.45 | 53.87 | 1
4743 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Sajiara, Simla, Barapara, Bodhsah, Dubrajpur, Gobindapur, Isabpur, Kaibati, Khord Kaibati, Kubajpur, Kuksimla, Muksimpara, Sanghoshpara, Sumuria & Chhatni (15nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000016/2021-2022 | 3230/BWD | 10/06/2021 | 60 | UNICON INDIA | 223.63 | 42.56 | 1
4744 | Burdwan Division | Kalna Sub-division | Sheet piling and others ancillary works to protect errosion of river bank protection area at raw water intake point of Kamalnagar WTP under Burdwan Division PHE Dte. | Assistant Engineer |  | ORD/000021/2022-2023 | 2015/BWD | 18/04/2022 | 45 | CONCORD ENGINEERING | 122.2 | 0 | 1
4745 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Majida, Rukuspur, Uttar Lakshmipur, Candipur, Gopipur, Kuturia & Mertala (7nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000027/2021-2022 | 3393/BWD | 24/06/2021 | 60 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 219.81 | 88.33 | 1
4746 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Harispur, Hatsiuri, Jajneswarpur, Jamalpur, Madhupur, Nakadaha, Nimdaha, Palasberia & Sarangpur (9nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000032/2021-2022 | 3417/BWD | 25/06/2021 | 60 | ASHOK KUMAR GHOSH | 230.37 | 82.01 | 1
4747 | Burdwan Division | Kalna Sub-division | Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Hapania, Kankhal, Khar Dattapara, Pathangram, Sontoshpur Pila & Uttar Srirampur (6nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000033/2021-2022 | 3416/BWD | 25/06/2021 | 60 | M/S ASHA CONSTRUCTION | 146.22 | 0 | 1
4748 | Burdwan Division | Kalna Sub-division | Work Order for Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Muragachha, Sardanga, Sihipara, Bagachra, Baragachhi, Belgachhi, Kumirpara, Lohachur, Atpara, Barea, Dhamas, Kamalapur & Kamalnagar (13nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000037/2021-2022 | 3418/BWD | 25/06/2021 | 60 | MRITYUNJOY MUKHERJEE & CO. | 232.13 | 80.59 | 1
4749 | Burdwan Division | Kalna Sub-division | Supply of SS316 grade flow control valve for FHTC at Surface Water Based w/s scheme for Arsenic affected areas of Purbasthali-II block within Kalna Sub-Division under Burdwan Division, PHE Dte. (Part-A) and delivered to Barsul Divisional Store .[Part-3] | Assistant Engineer |  | ORD/000113/2021-2022 | 3836/BWD | 23/07/2021 | 15 | A.K. SIKDAR | 17.62 | 17.62 | 1
4750 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000181/2024-2025 | 2296/BWD | 20/06/2024 | 616 | M/S DATTA ENTERPRISE | 579.85 | 0 | 2
4751 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Augmentation of Purbasthali Piped Water Supply Scheme at Kasthashali Village (Kasthashali habitation) (Mouza) & Purbasthali village (Purbasthali habitation), Purbasthali-II Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000316/2020-2021 | 1328/BWD | 12/02/2021 | 60 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 91.41 | 0 | 1
4752 | Burdwan Division | Kalna Sub-division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purbasthali ¿ II Block under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000365/2021-2022 | 149/BWD | 07/01/2022 | 30 | G.S. CONSTRUCTION & CO. | 22.15 | 0 | 1
4753 | Burdwan Division | Kalna Sub-division | Laying of 140 mm dia HDPE Pipe from Bardangamore to Khardattapara more (Node No- 289A -289- 286) of Zone-III under Surface Based W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | Assistant Engineer |  | ORD/000433/2021-2022 | 84/KSD | 20/01/2022 | 30 | UNICON INDIA | 4.84 | 0 | 1
4754 | Burdwan Division | Kalna Sub-division | Withdrawing of 110 mm dia HDPE Pipeline and relaying of 140 mm dia HDPE Pipe from Naomatha more to Bordanga more (Node No- 291 to 289-289A) under Surface Based W/S Scheme (Zone-III) within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer |  | ORD/000434/2021-2022 | 87/KSD | 21/01/2022 | 30 | UNICON INDIA | 4.84 | 0 | 1
4755 | Burdwan Division | Kalna Sub-division | Supply of SS316 grade flow control valve for FHTC at surface water based water supply scheme for Arsenic affected areas of Purbasthali-II Block within Kalna Sub-Division under Burdwan Division, PHE Dte.[Part-B] and delivered at Barsul Divisional store. | Assistant Engineer |  | ORD/000776/2021-2022 | 4476/BWD | 03/09/2021 | 15 | INDIA PIPE FITTING CO | 17.62 | 0 | 1
4756 | Burdwan Division | Kalna Sub-division | Painting and renovation work of WTP Building, Boundary Wall, Truss Bridge etc. at Kamalnagar of Surface Water Based Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000886/2023-2024 | 5517/BWD | 14/12/2023 | 30 | SETH ENTERPRISE | 12.63 | 0 | 100
4757 | Burdwan Division | Kalna Sub-division | Repairing and Renovation of Filter Bed, Main Boundary Gate, resetting of Paver Block Pathway, replacement of different damaged portion of doors/windows or any other structures & other related works for Kamalnagar WTP within Kalna Sub Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000894/2023-2024 | 5510/BWD | 14/12/2023 | 120 | GHOSH BROTHERS | 47.97 | 0 | 5
4758 | Burdwan Division | Kalna Sub-division | Relaying of different dia UPVC pipeline at damaged portion as shown by Horizon of Zone-III of surface based water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL-B] | Assistant Engineer |  | ORD/000959/2020-2021 | 148/KSD | 12/02/2021 | 30 | CHANCHAL PAL | 4.82 | 0 | 1
4759 | Burdwan Division | Kalna Sub-division | Construction of wash out & over flow & drain for drain out of over flow water by 250 mm dia UPVC pipeline & soak well along with land development at Zone-I Head work site of surface based water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL-C] | Assistant Engineer |  | ORD/000960/2020-2021 | 160/KSD | 19/02/2021 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 2.1 | 0 | 1
4760 | Burdwan Division | Kalna Sub-division | Painting & renovation work at Purbasthali raw water pumping station within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001122/2023-2024 | 4560/BWD | 16/10/2023 | 30 | CONCORD ENGINEERING | 6.53 | 0 | 100
4761 | Burdwan Division | Kalna Sub-division | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 51
4762 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Natu village of Natu piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-162/BWD/2020-21) |  |  | ORD/000080/2020-2021 | 2687/BWD | 07/08/2020 | 30 | SINGHA ROY AND CO. | 4.92 | 4.92 | 1
4763 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Haripur village of Natu piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-161/BWD/2020-21) |  |  | ORD/000081/2020-2021 | 2688/BWD | 07/08/2020 | 30 | MITRA CONSTRUCTION | 4.92 | 4.92 | 1
4764 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Natu Piped Water Supply Scheme at Notu (2 Nos Habitation Part), Horipur (4 Nos Habitation Part), Uttar Mohanpur Village (Mouza), Raina-I Block under Burdwan Division, PHE Dte.(Agreement No. 49/2020-2021 OF SE/CC/PHE. DTE.) |  |  | ORD/000126/2020-2021 | 4767/BWD | 01/12/2020 | 90 | SINGHA ROY AND CO. | 57.87 | 24.77 | 1
4765 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Haripur village of Natu piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-278/BWD/2020-21) |  |  | ORD/000295/2020-2021 | 3365/BWD | 21/09/2020 | 30 | MITRA CONSTRUCTION | 4.92 | 4.92 | 1
4766 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Natu village of Natu piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-276/BWD/2020-21) |  |  | ORD/000297/2020-2021 | 3363/BWD | 21/09/2020 | 30 | SINGHA ROY AND CO. | 4.46 | 4.46 | 1
4767 | Burdwan Division |  | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. |  |  | ORD/000344/2021-2022 | 39/BWD | 05/01/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 15.62 | 0 | 1
4768 | Burdwan Division |  | Extension of 75 mm dia pipeline at Miya Para, Modhya Bohar & Bhagar Para Purba Bohar regarding FHTC under Satgachia (Zone-I) water supply scheme under Burdwan Division, PHE Dte.[Gr.-A] |  |  | ORD/000350/2021-2022 | 703/BSD | 11/06/2021 | 5 | M/S SAYAN CHAKRABORTY | 0.88 | 0 | 1
4769 | Burdwan Division |  | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at Head Work Site and providing leftout FHTC, Road Restoration with allied work for NATU Piped Water Supply Scheme, Block-Raina-I within Burdwan Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000373/2024-2025 | 2994/BWD | 01/08/2024 | 487 | ANWESHA CONSTRUCTION | 55.19 | 0 | 75
4770 | Burdwan Division |  | Supply of SS316 grade flow control valve for FHTC at different water supply schemes within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional store.[Part-2] |  |  | ORD/001307/2020-2021 | 1792 /BWD | 26/02/2021 | 10 | INDIA PIPE FITTING CO | 9.7 | 0 | 1
4771 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bamunpara Piped Water Supply Scheme at Bamunpara (7 Nos Habitation Part), Sahajadpur (5 Nos Habitation Part), Gulita Daspara & Purba Khanpur (4 Nos Habitation) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte.(Agreement No. 69/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer |  | ORD/000130/2020-2021 | 5002/BWD | 07/12/2020 | 90 | M/S S. CHOUDHURY | 50.71 | 38.98 | 1
4772 | Burdwan Division | Kalna Sub-division | Laying of UPVC pipeline & providing FHTC work at Bamunpara, Sahajadpur, Tentulia & Gulita village of BAMUNPARA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000150/2023-2024 | 2423/BWD | 30/05/2023 | 30 | GOUTAM KUMAR MITRA | 9.65 | 0 | 100
4773 | Burdwan Division | Kalna Sub-division | Providing FHTC - Sahajadpur (5 nos habitations)-170 nos & Bamunpara (7 nos habitation)-170 nos & Extension of pipeline to provide house connection at Tentulia village & Sahajadpur village for Drain out water of wash out & over flow line from existing OHR at Head Works Site of BAMUNPARA W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000588/2021-2022 | 1417/BWD | 10/03/2022 | 30 | M/S UNIQUE | 16.5 | 0 | 1
4774 | Burdwan Division | Kalna Sub-division | Supply of SS316 grade flow control valve for FHTC at different water supply schemes within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional store.[Part-2] | Assistant Engineer |  | ORD/001307/2020-2021 | 1792 /BWD | 26/02/2021 | 10 | INDIA PIPE FITTING CO | 9.7 | 0 | 1
4775 | Burdwan Division |  | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of March & April'23. |  |  | BILL/00457/2023-2024 | 367/JJM | 18/07/2023 | 0 | PARTHA PRATIM ACHARYA | 0.77 | 0 | 0
4776 | Burdwan Division |  | Hire & fuel charges of vehicle Car No.-WB-41H-3668 for the month of May & June'2023. |  |  | BILL/01039/2023-2024 | 744/JJM | 11/10/2023 | 0 | MD HASIN | 0.53 | 0 | 0
4777 | Burdwan Division |  | Work Order for "Providing Functional house hold tap connections for Sajal Gram Village within Monteswar Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Putsuri water supply scheme)" |  |  | ORD/000028/2023-2024 | 344/KSD | 17/04/2023 | 30 | HASAN CONSTRUCTION | 0.88 | 0 | 0
4778 | Burdwan Division |  | Work Order for "Providing Functional house hold tap connections for Sajal Gram villages within Monteswar Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Putsuri water supply Scheme) (Sl No-9) |  |  | ORD/000029/2023-2024 | 344/KSD | 17/04/2023 | 30 | HASAN CONSTRUCTION | 0.88 | 0 | 0
4779 | Burdwan Division |  | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-5]. |  |  | ORD/000090/2021-2022 | 3590/BWD | 13/07/2021 | 30 | PREMANANDA ROY BISWAS | 127.5 | 7.13 | 1
4780 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Putsuri Piped Water Supply Scheme at Denur (6 Nos Habitation Part) & Putsuri (11 Nos Habitation Part) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte.(Agreement No. 55/2020-2021 OF SE/CC/PHE. DTE.) |  |  | ORD/000125/2020-2021 | 4887/BWD | 07/12/2020 | 90 | M/S S. CHOUDHURY | 77.12 | 45.3 | 1
4781 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Putsuri village of Putsuri piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-546/BWD/2020-21) |  |  | ORD/000268/2020-2021 | 3532/BWD | 25/09/2020 | 30 | PRONAB KUMAR DEY | 4.92 | 4.92 | 1
4782 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PUTSURI Piped Water Supply Scheme at Kasa (6 Nos. Habs.), Purba Balarampur, Bhurkunda (7 Nos. Habs.), Patun (5 Nos. Habs.) & Bigha (3 Nos. Habs.) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte. |  |  | ORD/000302/2021-2022 | 7020/BWD | 17/12/2021 | 60 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 53.94 | 0 | 1
4783 | Burdwan Division |  | Relaying of different dia UPVC Pipeline at the different damage portion towards Mojaharnagar, Gulita, Denur & Putsuri of Putsuri PWSS within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) |  |  | ORD/000322/2021-2022 | 985/KSD Dt- 24.09.2021 | 24/09/2021 | 30 | M/S S. CHOUDHURY | 3.66 | 0 | 100
4784 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Denur village of Putsuri piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-562/BWD/2020-21) |  |  | ORD/000355/2020-2021 | 3804/BWD | 08/10/2020 | 30 | IJABUL SEKH | 4.92 | 4.92 | 1
4785 | Burdwan Division |  | Work order for "Interconnection of rising main from 4th Tube Well site to Over Head Reservoir for FHTC related water supply under Putsuri W/S Scheme within Kalna Sub-Division under Burdwan Division , PHE Dte." |  |  | ORD/000554/2023-2024 | 1309/KSD | 23/08/2023 | 15 | PRONAB KUMAR DEY | 2.1 | 0 | 100
4786 | Burdwan Division |  | Laying of different dia.UPVC pipeline at the damaged portion from Denur to Mousa Daukadanga under Putsuri & its adjoining mouzas water supply scheme within Kalna Sub-Division, under Burdwan Division, PHE Dte. |  |  | ORD/000778/2021-2022 | 6013/BWD | 05/10/2021 | 30 | D.M. ENTERPRISE | 23.17 | 0 | 1
4787 | Burdwan Division |  | Extension of 75 mm dia UPVC pipeline at different places of Denur village under Putsuri & its adjoining mouzas water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL NO.-C] |  |  | ORD/000839/2020-2021 | 169/KSD | 19/02/2021 | 30 | M/S S. CHOUDHURY | 2.37 | 0 | 1
4788 | Burdwan Division |  | Providing FHTC with laying of 75 mm dia HDPE Pipe of Putsuri PWSS of Ghosh para village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte |  |  | ORD/001182/2023-2024 | 271/DSD | 15/03/2024 | 30 | SAYAK DEY | 0.97 | 0 | 100
4789 | Burdwan Division |  | Providing FHTC with laying of 75 mm dia HDPE Pipe of Putsuri PWSS of near Health Centre under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte |  |  | ORD/001183/2023-2024 | 272/DSD | 15/03/2024 | 30 | SAYAK DEY | 0.97 | 0 | 0
4790 | Burdwan Division |  | Load Enhancement charges bill for Putsuri water supply scheme under Burdwan Division, PHE Dte.[Application No.-5003378053, Consumer Id-500684865] |  |  | VCH/000392/2022-2023 | 300/DW/22-23 | 05/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.56 | 0 | 0
4791 | Burdwan Division |  | Vehicle bill for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of May'23. |  |  | BILL/00614/2023-2024 | 562/JJM | 24/08/2023 | 0 | SUJAUDDIN SEKH | 0.4 | 0 | 0
4792 | Burdwan Division |  | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the month of June & July'23. |  |  | BILL/00792/2023-2024 | 633/JJM | 13/09/2023 | 0 | SUJAUDDIN SEKH | 0.78 | 0 | 0
4793 | Burdwan Division |  | Hire & fuel charges of vehicle Car No.-WB-37C-8293 for the month of August'2023. |  |  | BILL/01036/2023-2024 | 746/JJM | 11/10/2023 | 0 | SUJAUDDIN SEKH | 0.39 | 0 | 0
4794 | Burdwan Division |  | Vehicle bill for the month of November'23. |  |  | BILL/01674/2023-2024 | 1138/JJM | 29/12/2023 | 0 | SUJAUDDIN SEKH | 0.38 | 0 | 0
4795 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of CHAKTENTUL Piped Water Supply Scheme at Chaktentul (1 No Part, 2 Nos Habitation), Bharatpur (2 Nos Habitation) Village (Mouza), Galsi-I Block under Burdwan Division, PHE Dte.(Agreement No. 71/2020-2021 OF SE/CC/PHE. DTE.) |  |  | ORD/000128/2020-2021 | 5005/BWD | 10/12/2020 | 90 | SUPRIYA RAY | 75.14 | 33.71 | 1
4796 | Burdwan Division |  | Supply of 10 mm NB Gun-metal Ferrul conforming to IS:2692-1989 for water tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division PHE Dte. and delivered at Barsul Divisional Store. [Part-6] |  |  | ORD/000199/2021-2022 | 3402/BWD | 24/06/2021 | 30 | A.K. SIKDAR | 91.8 | 20 | 1
4797 | Burdwan Division |  | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-7] |  |  | ORD/000348/2021-2022 | 2942/BWD | 04/05/2021 | 10 | KISHORE GHOSH | 3.94 | 0 | 1
4798 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Chaktentul village and Chaktentul habitation of Chaktentul piped water supply scheme within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Phase-I] |  |  | ORD/000700/2020-2021 | 4455/BWD | 10/11/2020 | 30 | SAIKAT RAY | 4.92 | 4.92 | 1
4799 | Burdwan Division |  | Repairing of valve chamber & Construction of new valve chamber and supply of sluice valve at Head Works Site for CHAKTATUL PWSS within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. |  |  | ORD/000932/2023-2024 | 905/DSD | 15/12/2023 | 30 | SAIKAT RAY | 0.97 | 0 | 0
4800 | Burdwan Division |  | Laying of interconnection of Head Works Site to distribution main line for CHAKTATUL PWSS within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. |  |  | ORD/000933/2023-2024 | 906/DSD | 15/12/2023 | 45 | SAIKAT RAY | 0.95 | 0 | 100
4801 | Burdwan Division |  | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0
4802 | Burdwan Division | Kalna Sub-division | Hire & fuel charges of vehicle (Car No.-WB-41J-6795) for the office of the Superintending Engineer, Central Circle, PHE Dte. for the month of January & February'23. | Assistant Engineer |  | BILL/00292/2023-2024 | 218/JJM | 06/06/2023 | 0 | MD HASIN | 0.79 | 0 | 0
4803 | Burdwan Division | Kalna Sub-division | Quotation for new service connection charges at Nandai PWSS [PH No.-V][Ref ID-503434397] | Assistant Engineer |  | BILL/01125/2023-2024 | 1086/JJM | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.28 | 0 | 0
4804 | Burdwan Division | Kalna Sub-division | Vehicle bill (Car No.-WB-04G-7127) for the month of September'2023. | Assistant Engineer |  | BILL/01680/2023-2024 | 1041/JJM | 11/12/2023 | 0 | PARTHA PRATIM ACHARYA | 0.39 | 0 | 0
4805 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of NANDAI Piped Water Supply Scheme at opposite site of railway track at Malatipur, Nagargachhi, Mirjapur, Durgapur habitations, Kalna - I Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000002/2022-2023 | 1869/BWD | 05/04/2022 | 30 | KOUSIK MALLICK | 51.64 | 0 | 1
4806 | Burdwan Division | Kalna Sub-division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Uttar Rameswarpur village of Nandai Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 4B] | Assistant Engineer |  | ORD/000035/2021-2022 | 3409/BWD | 25/06/2021 | 30 | AURGHA BHATTACHARYA | 4.92 | 0 | 1
4807 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nandai Piped Water Supply Scheme at Nandai (Part) (7 Nos Habitation Part), Nagargachhi, Pardupra & Uttar Rameswarpur (Part) Village (Mouza), Kalna-I Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000089/2021-2022 | 3599/BWD | 13/07/2021 | 60 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 110.43 | 0 | 1
4808 | Burdwan Division | Kalna Sub-division | Providing FHTC in the left out portion of Natungram, Kutirdanga, Kharinan village along with other ancillary work in order to declare Sajal Gram under the command area of NANDAI PWSS (SM/08104) within Kalna Sub Division under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000135/2025-2026 | 1447/BWD | 22/05/2025 | 120 | MUKHERJEE ENTERPRISE | 42.77 | 0 | 0
4809 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of BAIDYAPUR (Z-I) PWSS, Block - Kalna - II and NANDAI PWSS, Block - Kalna - I Piped Water Supply Scheme, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | Assistant Engineer |  | ORD/000151/2023-2024 | 2424/BWD | 30/05/2023 | 45 | KOUSIK MALLICK | 19.84 | 0 | 100
4810 | Burdwan Division | Kalna Sub-division | Construction of Pump House cum switch room (5.40 mtr x 3.60 mtr) with sanitary arrangement (as per drawing no. PHE/SE/CC/PH/DWG-01/2022-2023) at NANDAI Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | Assistant Engineer |  | ORD/000806/2023-2024 | 4820/BWD | 08/11/2023 | 352 | SK BADIUZZAMAL | 5.69 | 0 | 100
4811 | Burdwan Division | Kalna Sub-division | Work Order for "Laying of pipeline at gap portion of old and new pipeline of Nandai Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division , PHE Dte. " | Assistant Engineer |  | ORD/000947/2023-2024 | 1714/KSD | 04/12/2023 | 7 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.64 | 0 | 100
4812 | Burdwan Division | Kalna Sub-division | Work Order For "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR NANDAI PWSS & SHIKARPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer |  | ORD/001144/2023-2024 | 1980/KSD | 09/02/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0 | 100
4813 | Burdwan Division | Kalna Sub-division | Work Order for "Restoration of 350 mm dia DI Rising Main with other allied works in connection with Augmentation of Nandai (SM/08104) Piped Water Supply Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer |  | ORD/001188/2023-2024 | 2192/KSD | 15/03/2024 | 15 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 3.3 | 0 | 100
4814 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000122/2021-2022 | 1109/BWD | 26/02/2022 | 0 | Resource Division | 67.99 | 0 | 0
4815 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0
4816 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Chaitynapur village of Jaggeswardihi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-204/BWD/2020-21) |  |  | ORD/000089/2020-2021 | 2604/BWD | 04/08/2020 | 30 | SUBRATA GUPTA | 4.92 | 4.92 | 1
4817 | Burdwan Division |  | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jaggeswardihi village of Jaggeswardihi Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL. No : 9A] (T.R. No.-219/BWD/2020-21) |  |  | ORD/000139/2020-2021 | 2630/BWD | 04/08/2020 | 30 | ABDUL HAI | 4.92 | 0 | 1
4818 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jaggeswardihi (Part) village of Jaggeswardihi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-251/BWD/2020-21) |  |  | ORD/000243/2020-2021 | 3383/BWD | 22/09/2020 | 30 | SUBRATA GUPTA | 4.92 | 4.92 | 1
4819 | Burdwan Division |  | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jaggeswardihi (Part) village of Jaggeswardihi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-250/BWD/2020-21) |  |  | ORD/000244/2020-2021 | 3413/BWD | 22/09/2020 | 30 | ABDUL HAI | 4.92 | 4.92 | 1
4820 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jageswardihi Piped Water Supply Scheme at Kaichar & Sitalgram Village (Mouza), Mongolkot Block under Burdwan Division, PHE Dte. |  |  | ORD/000258/2021-2022 | 6694/BWD | 01/12/2021 | 60 | HAMID SK | 58.77 | 0 | 1
4821 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jaggeswardihi Piped Water Supply Scheme at Kanaidanga & Jageswardihi (1 Part & 1 Habitation) Village (Mouza), Mangolkote Block under Burdwan Division, PHE Dte.[Agreement No. 578/BWD OF 2020-2021] |  |  | ORD/000331/2020-2021 | 436/BWD | 19/01/2021 | 45 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 38.09 | 37.75 | 0
4822 | Burdwan Division |  | Extension of pipeline from the existing distribution system within scheme jurisdiction at Kanaidanga under Jaggeswardihi piped water supply scheme under Mongalkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-2] |  |  | ORD/000830/2020-2021 | 82/KTS | 09/02/2021 | 15 | HAMID SK | 1.25 | 0 | 1
4823 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Palla Piped Water Supply Scheme at Palla (Part) (7 Nos Habitation Part) Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000023/2021-2022 | 3345/BWD | 21/06/2021 | 30 | M/S ASHA CONSTRUCTION | 27.79 | 13.13 | 0
4824 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Palla(Pt-B) village of Palla piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-246/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000082/2020-2021 | 2738/BWD | 10/08/2020 | 30 | S.C. ENTERPRISE | 4.92 | 4.92 | 1
4825 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Palla(Pt-A) village of Palla piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-245/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000094/2020-2021 | 2746/BWD | 10/08/2020 | 30 | JAYANTA CHAKRABORTY | 4.92 | 4.92 | 1
4826 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection(FHTC)from existing distribution system within the command area of PALLA Water supply scheme at Palla(Paschim palla Habitation part) village (Mouza) opposite side of navigation cannel, in Memari-I Block including leftout household water tap connection(FHTC) under Burdwan Division, PHE Dte. Group : B | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000103/2022-2023 | 984/BSD | 16/06/2022 | 30 | DUBE ENTERPRISE | 4.22 | 0 | 1
4827 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Palla(Pt-A) village of Palla piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-487/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000117/2020-2021 | 3972/BWD | 14/10/2020 | 30 | JAYANTA CHAKRABORTY | 4.92 | 4.92 | 1
4828 | Burdwan Division | Burdwan Sadar Sub-Division | Additional work providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Palla piped water supply scheme at Palla village (Mouza) Memari-I Block under Burdwan Division, PHE Dte. [Gr.-F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000153/2021-2022 | 685/BSD | 09/06/2021 | 30 | S.C. ENTERPRISE | 0.77 | 0.76 | 1
4829 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PALLA Piped Water Supply Scheme at Palla(Paschim Palla Habitation Part)village(Mouza)Memari-I Block under Burdwan Division, PHE Dte.Gr.C | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000441/2021-2022 | 199/BSD | 01/02/2022 | 30 | MUKHERJEE ENTERPRISE | 4.58 | 0 | 1
4830 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Palla (Pt-B) village of Palla Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿11B¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000674/2020-2021 | 4912/BWD | 08/12/2020 | 30 | S.C. ENTERPRISE | 4.92 | 4.88 | 1
4831 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Retaining wall for protection of soil erosion at Headwork site (Western Side) at TEANDUL Piped Water Supply Scheme under Burdwan Division, PHE Dte. [Group : B] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000035/2022-2023 | 241/AE/HQ | 20/04/2022 | 30 | ROY CONSTRUCTION | 4.82 | 0 | 1
4832 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of TEANDUL Piped Water Supply Scheme at Raina-I Block under Burdwan Division, PHE Dte.(Agreement No. 61/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000112/2020-2021 | 4881/BWD | 07/12/2020 | 90 | ASHOK KUMAR GHOSH | 70.51 | 26.97 | 1
4833 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Retaining wall for protection of soil erosion at Headwork site (southern side) at Teandul PWSS under Burdwan Division, PHE Dte. [Group: ¿H¿] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000224/2021-2022 | 1902/AE/HQ | 16/11/2021 | 30 | ASHOK KUMAR GHOSH | 4.5 | 0 | 1
4834 | Burdwan Division | Burdwan Sadar Sub-Division | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Madhuban, Sultanbad, Dhamas & Teyandul of TEANDUL Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000754/2022-2023 | 1228/BWD | 17/03/2023 | 60 | M/S UNIQUE | 31.31 | 0 | 0
4835 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of UPVC and HDPE Pipe Line, Providing Left Out FHTC at south part of Debipur rail gate, Land Development & construction of PCC approach Road inside proposed boundary of H/W Site of ALIPUR & its adjacent mouza Water Supply Scheme under MEMARI-I Block of Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000287/2024-2025 | 2740/BWD | 12/07/2024 | 171 | M/S K.P. CONSTRUCTION | 122.03 | 0 | 50
4836 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ALIPUR Piped Water Supply Scheme at Debipur, Alipur & Benapur (2 Nos Habitation) Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte. [Agreement No. 92/2020-2021 OF SE/CC/PHE. DTE.] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000423/2020-2021 | 812/BWD | 01/02/2021 | 90 | MD HASIN | 90.85 | 18.82 | 0
4837 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for ALIPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001095/2024-2025 | 430/BWD | 20/01/2025 | 287 | DULAL MAJUMDER | 117.26 | 0 | 30
4838 | Burdwan Division | Durgapur Sub-DIvision | Modification to the distribution network by making a loop to augment the water supply to FHTC at Gopinathbati village of Dwariyapur and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte._2nd call[SL-05] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000057/2023-2024 | 180/DSD | 18/04/2023 | 21 | ANIRUDDHA FARUQUE | 0.92 | 0 | 100
4839 | Burdwan Division | Durgapur Sub-DIvision | Restoration of damaged pipeline of distribution main at Laxmiganj village and laying of parallel line at Gonna village for providing FHTC within Dwariapur W/S Scheme in Ausgram-II Block under Burdwan Division, P.H.E. Dte. [Gr.-G] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000336/2021-2022 | 06/DSD | 03/01/2022 | 30 | RANADHIR SINHA | 2.11 | 0 | 1
4840 | Burdwan Division | Durgapur Sub-DIvision | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Ausgram-I Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000366/2021-2022 | 120/BWD | 07/01/2022 | 30 | ANIRUDDHA FARUQUE | 12.33 | 0 | 1
4841 | Burdwan Division | Durgapur Sub-DIvision | Restoration of damaged concrete road in connection with laying distribution system at Laxmiganj, Gonna and Gopinathbati village within Dwariapur Piped Water Supply Scheme at Ausgram-I Block within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Gr.-H] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000451/2021-2022 | 80/DSD | 11/02/2022 | 15 | RANADHIR SINHA | 4.73 | 0 | 1
4842 | Burdwan Division | Durgapur Sub-DIvision | Making Connection with Rising Main And Over Head Reservoir of Dwariapur W/S Scheme within Durgapur Sub-Division in Ausgram-I Block under Burdwan Division, P.H.E. Dte.[Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000551/2021-2022 | 133/DSD | 02/03/2022 | 15 | RANADHIR SINHA | 0.34 | 0 | 1
4843 | Burdwan Division | Durgapur Sub-DIvision | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Dwariapur Piped Water Supply Scheme at Gonna (1 No. Habitation), Alutia (Part), Dwariapur (7Nos Habitation) & Lakshmiganj (5 Nos Habitation) Village (Mouza), Ausgram-I Block under Burdwan Division, PHE Dte.[Agreement No. 109/2020-2021 OF SE/CC/PHE. DTE.] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000601/2020-2021 | 1600/BWD | 22/02/2021 | 60 | RANADHIR SINHA | 81.21 | 0 | 1
4844 | Burdwan Division | Durgapur Sub-DIvision | Restoration of damaged concrete road in connection with providing FHTC work at Laxmiganj, Gonna and Gopinathbati and Dwariapur village within Dwariapur Piped Water Supply Scheme at Ausgram-I Block within Durgapur Sub-Division under Burdwan Division, PHE Dte.[SL-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000621/2021-2022 | 163/DSD | 16/03/2022 | 15 | RANADHIR SINHA | 4.12 | 0 | 1
4845 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nabagram Piped Water Supply Scheme at Konar Village (2 Nos. habitations), Dadpur Village (4 Nos. habitations), Paschim Memari Village (2 Nos. habitations), Pingur Village & Nabagram Village (4 Nos. habitations), Memari - I Block under Burdwan Division, PHE Dte.[Agreement No. 681/BWD OF 2020-2021] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000311/2020-2021 | 1400/BWD | 15/02/2021 | 60 | UNIQUE AGENCY | 68.1 | 63.58 | 1
4846 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for NABAGRAM Piped Water Supply Scheme at Konarpara [24 No's]Total 24 No's FHTC Work for Sajal Gram (As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout husehold water tap connection (FHTC) under Burdwan Division, PHE Dte".Gr. B | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000334/2022-2023 | 1351/BSD | 02/08/2022 | 5 | BHARAT CONSTRUCTION | 0.97 | 0 | 1
4847 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for NABAGRAM Piped water Supply Scheme at Kalupukur[2 Nos]Kalanabagram[5 Nos]Dadpur[8 Nos],Paschim Memari[6 Nos]Pingur[3 Nos]Chuadanga:3 Nos Total 27 Nos FHTC Work for Sajal Gram(As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout household water tap connection(FHTC)under Burdwan Division,PHE Dte.Gr.C. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000335/2022-2023 | 1352/BSD | 02/08/2022 | 5 | BHARAT CONSTRUCTION | 0.97 | 0 | 1
4848 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Memari-I Block (Daluibazar-II, Gopegantar-I & II G.P.) under Burdwan Division, PHE. Dte. Dte._Part-A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000371/2021-2022 | 209/BWD | 11/01/2022 | 30 | M/S ANAND CONSTRUCTION | 21.11 | 0 | 1
4849 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for NABAGRAM Piped Water Supply Scheme at Konarpara [24 No's]Total 24 No's FHTC Work for Sajal Gram (As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout husehold water tap connection(FHTC) under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000645/2022-2023 | 1351-A/BSD | 02/08/2022 | 5 | BHARAT CONSTRUCTION | 0.97 | 0 | 1
4850 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline for NABAGRAM Piped Water Supply Scheme at Kalupukur [2 No's], Kalanabagram[5 No's] Dadpur [8 No's], Paschim Memari [6 No's], Pingur [3 No's] Chuadanga [3 No's] Total 27 No's FHTC Work for Sajal Gram (As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000646/2022-2023 | 1352-A/BSD | 02/08/2022 | 5 | BHARAT CONSTRUCTION | 0.97 | 0 | 1
4851 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 150mm. dia. 100 Mtr. Deep tube well & Laying Distribution pipeline including FHTC under Jal Swapna Scheme for SWASTI PALLY Mini Piped W/S. Scheme within NABAGRAM Piped W/S. Scheme under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000714/2022-2023 | 890/BWD | 01/03/2023 | 45 | BAMDEB CONSTRUCTION & CO | 30.68 | 0 | 100
4852 | Burdwan Division | Burdwan Sadar Sub-Division | Allied work of interconnection between 2nd TW to distribution line for FHTC work for KHETIA Piped Water Supply Scheme and its adjoining mouzas within BURDWAN-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000132/2024-2025 | 1016/BSD | 07/06/2024 | 45 | ROY CONSTRUCTION | 4.79 | 0 | 100
4853 | Burdwan Division | Burdwan Sadar Sub-Division | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur Palashi (Part-A) village of Khetpur Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. (Tr No.-471/BWD/2020-21) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000350/2020-2021 | 241/KTS | 01/10/2020 | 4 | CHANCHAL PAL | 1.19 | 0 | 1
4854 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Khetia Piped Water Supply Scheme at Simdali (P) village (09 Nos. (P) habs), Burdwan-I Block under Burdwan Division, PHE Dte. [Agreement No. 749/BWD OF 2020-2021] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000441/2020-2021 | 1496/BWD | 18/02/2021 | 60 | H SAMANTA | 52.6 | 0 | 1
4855 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Khetia Piped Water Supply Scheme at Gopalbati village, Khetia village (04 Nos. habs) & Tentral village Burdwan-I Block under Burdwan Division, PHE Dte. [Agreement No. 748/BWD OF 2020-2021.] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000442/2020-2021 | 1495/BWD | 18/02/2021 | 45 | H SAMANTA | 29.16 | 15.96 | 1
4856 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system at KHETIA Pipe Water Supply Scheme of Burdwan -I Block under Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000464/2022-2023 | 3963/BWD | 13/09/2022 | 30 | M/S UNIQUE | 6.23 | 0 | 1
4857 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection(FHTC)from existing distribution system at Khetia Water Supply Scheme(Habitation-Khetia,Gopalbati,Tentral)of Burdwan-I Block under Burdwan Sub-Division under Burdwan Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000635/2022-2023 | 11/BSD | 06/01/2023 | 15 | M/S UNIQUE | 0.92 | 0 | 0
4858 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Gopalbati Village, Burdwan - I Block within Khetia PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000732/2023-2024 | 825/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0 | 100
4859 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Tentral Village, Burdwan - I Block within Khetia PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000733/2023-2024 | 826/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0 | 100
4860 | Burdwan Division | Burdwan Sadar Sub-Division | KHETIA Piped Water Supply Scheme with Rising Main & Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation at different TW site under BARDHAMAN-I Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000874/2023-2024 | 5330/BWD | 04/12/2023 | 542 | THE DEVELOPER | 68.62 | 0 | 56
4861 | Burdwan Division | Burdwan Sadar Sub-Division | Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for NATUNGRAM and KHETIA Piped Water Supply Scheme, Block-Burdwan-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001003/2024-2025 | 007/BWD | 02/01/2025 | 211 | M/S UNIQUE | 33.59 | 0 | 80
4862 | Burdwan Division | Durgapur Sub-DIvision | WBSEDCL quotation of Balgona piped water supply scheme under Burdwan Division, PHE Dte. [Ref. ID-503447092] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | BILL/00612/2023-2024 | 713/JJM | 05/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.68 | 0 | 0
4863 | Burdwan Division | Durgapur Sub-DIvision | Sinking of additional 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for BALGONA Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000066/2022-2023 | 2389/BWD | 10/05/2022 | 30 | ANIRUDDHA FARUQUE | 9.03 | 0 | 1
4864 | Burdwan Division | Durgapur Sub-DIvision | Placing of pipeline at "Patna and adj" villages of Balgona and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [SL-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000120/2022-2023 | 333/DSD | 27/06/2022 | 15 | R.K. ENTERPRISE | 1.11 | 0 | 0
4865 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Balgona Piped Water Supply Scheme at Balgona village (Balgona (P), Patna habs), Bhatar Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000335/2020-2021 | 1574/BWD | 22/02/2021 | 60 | M/S S. CHOUDHURY | 63.94 | 0 | 1
4866 | Burdwan Division | Durgapur Sub-DIvision | Laying of Rising main in between Tube Well and Distribution Line for PUMP HOUSE 3 (RAIL LINE er dhar ) under BOLGONA PWSS in BHATAR Block under Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000523/2025-2026 | 1019/DSD | 10/07/2025 | 15 | S.S. CONSTRUCTION | 0.82 | 0 | 0
4867 | Burdwan Division | Durgapur Sub-DIvision | Surging of existing Tube Well at Headwork site for Bolgona Water Supply Scheme , Block - Bhatar, Dist - Purba Barddhaman under Durgapur Sub Division, PHE Dte.[SL-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000623/2021-2022 | 164/DSD | 16/03/2022 | 5 | J. K. CORPORATION | 0.54 | 0 | 1
4868 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Balgona village and Balgona Habitation of Balgona piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000635/2020-2021 | 4333/BWD | 05/11/2020 | 30 | S.S. CONSTRUCTION | 4.86 | 0 | 1
4869 | Burdwan Division | Durgapur Sub-DIvision | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Haripur village and Haripur habitation of Balgona piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000697/2020-2021 | 4334/BWD | 05/11/2020 | 30 | S.S. CONSTRUCTION | 4.03 | 0 | 1
4870 | Burdwan Division | Durgapur Sub-DIvision | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Balgona village and Balgona habitation of Balgona piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000698/2020-2021 | 3347/BWD | 18/09/2020 | 30 | S.S. CONSTRUCTION | 4.86 | 0 | 1
4871 | Burdwan Division | Durgapur Sub-DIvision | Extension of pipeline at Patna village of Bolgona and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [SL-10] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000853/2022-2023 | 710/DSD | 30/12/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.65 | 0 | 0
4872 | Burdwan Division | Durgapur Sub-DIvision | Laying of additional pipeline to facilitate FHTC at Patna village of Bolgona and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [SL-11] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000854/2022-2023 | 711/DSD | 30/12/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.09 | 0 | 0
4873 | Burdwan Division | Durgapur Sub-DIvision | Sinking of additional 300 X 200 mm dia. Tube Well, 420 Mtrs. Depth by D.R. Rig method using UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) for AUGMANTATION of BHATAR & BALGONA Water Supply Scheme within Bhatar Block, Dist.- Purba Bardhaman within Durgapur Sub Division under Burdwan Division PHE Dte. [For 02 Nos. Tube well]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001092/2023-2024 | 1125/BWD | 14/03/2024 | 122 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 58.25 | 0 | 100
4874 | Burdwan Division | Durgapur Sub-DIvision | Providing Functional Household Tap Connection (FHTC) by sinking of tube well 250 x 150 mm. dia. (2 Nos.) Constn. of Pump House, Boundary Wall and Land Development within command area of BALGANA & BHATAKUL W/S. Scheme, Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001188/2024-2025 | 596/BWD | 07/02/2025 | 120 | M/S S.S. ENTERPRISE | 114.01 | 0 | 0
4875 | Central Drilling | Durgapur Sub-DIvision | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 120 mtrs. Depth) by utilising Departmental machineries for Balgana W/S Scheme, Bhatar block under Purba Burdwan District, CDD PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000010/2023-2024 | 63/CDD | 06/04/2023 | 30 | C.M. ENTERPRISE | 9.91 | 0 | 100
4876 | Durgapur W/S Division |  | Acceptance cum Formal Work Order for Big Dia Tubewell Surging by using suitable air compressor at PH-1 & PH-2 of Debshala PWSS Scheme under Durgapur W/S Division, PHE Dte. |  |  | ORD/000135/2024-2025 | 1212/DWSD | 23/08/2024 | 10 | GHOSH & ROY ENTERPRISE | 0.66 | 0 | 100
4877 | Burdwan Division |  | Restoration of village road and drains at part of RAYKONA & KAKRA for Debshala piped water supply scheme, Block-Ausgram-II under Burdwan Division, PHE Dte. [Gr.-M] |  |  | ORD/000284/2021-2022 | 668/DSD | 25/11/2021 | 15 | SAI TUBE CO. | 3.91 | 0 | 1
4878 | Burdwan Division |  | Restoration of village and drains at Kakra village for DEBSHALA piped water supply scheme, Block-Ausgram-II under Burdwan Division, PHE Dte. [Gr.-L] |  |  | ORD/000285/2021-2022 | 669/DSD | 25/11/2021 | 15 | SAI TUBE CO. | 3.97 | 0 | 1
4879 | Burdwan Division |  | Extension of Pipeline with providing Functional Household Tap Connection (FHTC) at Raibandh, Raykona & Kankora adibasipara of DEBSALA and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-C] |  |  | ORD/000454/2021-2022 | 75/DSD | 11/02/2022 | 30 | BHARAT CONSTRUCTION | 4.33 | 0 | 1
4880 | Burdwan Division |  | Extension of Pipeline with providing Functional Household Tap Connection (FHTC) at Debsala Village,Kankora & Pathuria Adibasipara of DEBSALA and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-D] |  |  | ORD/000456/2021-2022 | 76/DSD | 11/02/2022 | 30 | D.M. ENTERPRISE | 4.45 | 0 | 1
4881 | Burdwan Division |  | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Ausgram-II Block under Burdwan Division, PHE. Dte. |  |  | ORD/000472/2021-2022 | 940/BWD | 17/02/2022 | 30 | NANDY UDYOG | 11.82 | 0 | 0
4882 | Burdwan Division |  | Providing functional household tap connection (FHTC) from existing distribution system within command area of DEBSHALA piped water supply scheme at Bagbati (02 Nos. habitation), Kakra, Satla (02 Nos. habitation), Gobindapur (03 Nos Habitation), Debshala (02 Nos. Habitation Part), Kankra (Part) & Paduma (02 Nos. habitation Part) village, Ausgram-II Block under Burdwan Division, PHE Dte. |  |  | ORD/000563/2020-2021 | 4998/BWD | 10/12/2020 | 90 | SAI TUBE CO. | 59.61 | 0 | 1
4883 | Burdwan Division |  | Relaying of pipe line damaged by construction of road with drain at Kankora and installation of Valves to regulate water supply at Bilashpur & Gobindapur of DEBSALA and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte.[SL-E] |  |  | ORD/000625/2021-2022 | 166/DSD | 16/03/2022 | 30 | BHARAT CONSTRUCTION | 2.53 | 0 | 1
4884 | Burdwan Division |  | Extension of pipeline of DEBSHALA and its adjoining mouzas piped water supply scheme at Ausgram-II Block within Durgapur Sub-Division under Burdwan Division, PHE Dte. |  |  | ORD/000771/2020-2021 | 1568/BWD | 22/02/2021 | 45 | BHARAT CONSTRUCTION | 41.01 | 40.66 | 0
4885 | Burdwan Division | Burdwan Division | Laying of uPVC pipe for providing FHTC at Kanshra Village within KANSHRA Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte. [Group : A] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000045/2022-2023 | 199/AE/HQ | 06/04/2022 | 30 | DEBASHISH ENTERPRISE | 4.84 | 0 | 1
4886 | Burdwan Division | Burdwan Division | Laying of UPVC Pipeline for providing FHTC at Kanshra Mouza (Habitation) under KANSHRA Piped Water Supply Scheme, Jamalpur Development Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000067/2023-2024 | 2018/BWD | 28/04/2023 | 30 | TARAMA AGENCY | 12.58 | 0 | 0
4887 | Burdwan Division | Burdwan Division | Laying of uPVC pipe for providing FHTC at Jorbandh habitation of Kanshra Mouza within Kanshra Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E DTE. [Group: ¿C¿] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000226/2021-2022 | 1898/AE/HQ | 16/11/2021 | 30 | M/S ANAND CONSTRUCTION | 4.62 | 0 | 1
4888 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) at Paharpur & Chikonhati village within the command area of KANSHRA Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. GROUP : B | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000228/2022-2023 | 425/AE/HQ | 03/08/2022 | 30 | OM ENTERPRISE | 4.1 | 0 | 1
4889 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KANSHRA Piped Water Supply Scheme at Bishnubati (Harekrishnapur Habitation), Jotsubal (Jotsubalpaharpur & Sagar Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement no. 594/BWD of 2020-2021) | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000330/2020-2021 | 619/BWD | 25/01/2021 | 60 | ROY CONSTRUCTION | 20.42 | 0 | 1
4890 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KANSHRA Piped Water Supply Scheme at Jotkrishtai (Jotkestai Habitation), Kalna (Jotkalna Habitation) & Kanshra (Bhabanipur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte.(Agreement no. 571/BWD of 2020-2021) | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000332/2020-2021 | 441/BWD | 19/01/2021 | 60 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 19.48 | 0 | 1
4891 | Burdwan Division | Burdwan Division | Extension of pipeline for KANSHRA Piped Water Supply Scheme at Badalpur & Natungram (Habitation) in Jamalpur Development Block for providing water tap connection (FHTC) under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000406/2023-2024 | 421/AE/HQ | 02/08/2023 | 30 | DEBASHISH ENTERPRISE | 0.95 | 0 | 100
4892 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KANSHRA Piped Water Supply Scheme at Kalna (Kalnagram & Surakalna Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 639/BWD OF 2020-2021] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000433/2020-2021 | 989/BWD | 04/02/2021 | 60 | IJABUL SEKH | 22.09 | 0 | 1
4893 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KANSHRA Piped Water Supply Scheme at Kanshra (Jorbandh & Kanshra Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte.[Agreement No. 625/BWD OF 2020-2021] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000438/2020-2021 | 957/BWD | 03/02/2021 | 60 | DEBASHISH ENTERPRISE | 21.87 | 0 | 1
4894 | Burdwan Division | Burdwan Division | Providing Functional Household Tap Connection (FHTC) at Kalna village within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : C] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000460/2021-2022 | 68/AE/HQ | 11/02/2022 | 30 | MAA BHABANI CONSTRUCTION | 4.81 | 0 | 1
4895 | Burdwan Division | Burdwan Division | Laying of 90 mm dia UPVC pipe for providing FHTC at Surekalna habitation of Kalna Mouza within Kanshra piped water supply scheme, at Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-D] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000752/2021-2022 | 1899/AE/HQ | 16/11/2021 | 30 | SWASTIK ENTERPRISE | 4.75 | 0 | 1
4896 | Burdwan Division | Burdwan Division | Laying of 75 mm and 50 mm dia UPVC pipe for providing FHTC at Kalnagram habitation of Kalna Mouza within Kanshra piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-C] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000769/2021-2022 | 1857/AE/HQ | 05/10/2021 | 30 | SANJAY SK | 3.5 | 0 | 1
4897 | Burdwan Division | Burdwan Division | Interconnection between inlet & delivery pipe with main distribution pipeline within command area of KANSHRA Piped W/S. Scheme, Jamalpur Block under Burdwan Division, PHE. Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000826/2022-2023 | 214/AE/HQ | 31/03/2023 | 30 | OM ENTERPRISE | 0.87 | 0 | 100
4898 | Burdwan Division | Burdwan Division | Extension of pipeline for KANSHRA Piped Water Supply Scheme at Natungram Habitation in Jamalpur Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000827/2022-2023 | 215/AE/HQ | 31/03/2023 | 30 | DEBASHISH ENTERPRISE | 0.95 | 0 | 100
4899 | Burdwan Division | Burdwan Division | Extension of pipeline for KANSHRA Piped Water Supply Scheme at Badalpur Habitation in Jamalpur Block under Burdwan Division, PHE Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000828/2022-2023 | 216/AE/HQ | 31/03/2023 | 30 | DEBASHISH ENTERPRISE | 0.95 | 0 | 100
4900 | Burdwan Division | Burdwan Division | Construction of sluice valve chamber & supply of sluice valve for extension of pipeline for KANSHRA Piped W/S. Scheme, Jamalpur Block under Burdwan Division, PHE. Dte. | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000829/2022-2023 | 217/AE/HQ | 31/03/2023 | 30 | DEBASHISH ENTERPRISE | 0.92 | 0 | 100
4901 | Burdwan Division | Burdwan Division | Extension of pipeline for providing functional house hold tap connection at Jotsubal village within Kanshra water supply scheme under Burdwan Division, PHE Dte. [Gr.-A] | AE(HQs), Burdwan Division, PHE Dte. |  | ORD/000866/2020-2021 | 1256/AE/HQ | 15/02/2021 | 30 | ROY CONSTRUCTION | 4.84 | 0 | 1
4902 | Burdwan Division | Kalna Sub-division | Augmentation of SINHARI Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation including construction of switch room (3.60mx3.0m) for new TW site under Purbasthali II Block, District - Purba Bardhaman. | Assistant Engineer |  | ORD/000010/2022-2023 | 1940/BWD | 11/04/2022 | 365 | CONCORD ENGINEERING | 441.1 | 0 | 60
4903 | Burdwan Division | Kalna Sub-division | Sinking of additional 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SINHARI Piped Water Supply Scheme, Block - Purbasthali - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000071/2022-2023 | 2425/BWD | 11/05/2022 | 30 | M/S SYCHROTECH INDUSTRY | 9.01 | 0 | 0
4904 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000181/2024-2025 | 2296/BWD | 20/06/2024 | 616 | M/S DATTA ENTERPRISE | 579.85 | 0 | 2
4905 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Sinhari W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-C) | Assistant Engineer |  | ORD/000581/2021-2022 | 215/KSD | 24/02/2022 | 21 | LEMNISCATE | 2.92 | 0 | 1
4906 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000039/2021-2022 | 539/BWD | 27/01/2022 | 0 | Resource Division | 16.89 | 0 | 0
4907 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000153/2021-2022 | 1241/BWD | 07/03/2022 | 0 | Resource Division | 4.19 | 0 | 0
4908 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000161/2021-2022 | 1321/BWD | 08/03/2022 | 0 | Resource Division | 44.3 | 0 | 0
4909 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000213/2021-2022 | 1536/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
4910 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
4911 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1,2 &3 at Augumentation of Sinhari Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer |  | ORD/000078/2023-2024 | 2574/CMD | 06/06/2023 | 30 | P.K. ENGINEERING | 33.08 | 0 | 0
4912 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amra Piped Water Supply Scheme at Amra (2 Nos Habitation Part) & Dogachia Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte._3rd CALL. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000008/2021-2022 | 3138/BWD | 03/06/2021 | 45 | D.M. ENTERPRISE | 57.42 | 0 | 1
4913 | Burdwan Division | Burdwan Sadar Sub-Division | Providing FHTC for Dogachia Mouza [(Habitation (Village)] for AMRA piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000068/2023-2024 | 2019/BWD | 28/04/2023 | 30 | DEY NIRMAN | 20.61 | 0 | 100
4914 | Burdwan Division | Burdwan Sadar Sub-Division | Laying of 100 mm dia D.I Pipe for Road widening from 4 lane to 6 lane of NH2 at chainage 596+286 & 596+086 & 596+ 486 at Amra Water supply within Jamalpur Block,under Burdwan Division,PHE Dte". Group : A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000101/2022-2023 | 982/BSD | 16/06/2022 | 30 | DEY NIRMAN | 2.89 | 0 | 0
4915 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of concrete road and rest portion of boundary wall at Head works site of AMRA Piped Water Supply Scheme in Jamalpur Block under Burdwan Division, PHE Dte. (Length - 122 Mtr., 45 Nos Column). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000146/2022-2023 | 3100/BWD | 14/07/2022 | 30 | CHAUDHURI ENTERPRISE | 7.68 | 0 | 0
4916 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AMRA Piped Water Supply Scheme (Vill-Dogechia, Habitation- Dogechia ) at Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte.Gr.A. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000386/2021-2022 | 57/BSD | 13/01/2022 | 30 | DEY NIRMAN | 4.81 | 0 | 1
4917 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall at 3rd Tube well site of Dogachia Mouza of Amra water supply scheme under Jamalpur block under Burdwan Division, PHE Dte. [Length-59 Mtr][Gr.-F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000557/2021-2022 | 1028/BSD | 05/08/2021 | 45 | MUKHERJEE ENTERPRISE | 4.45 | 0 | 1
4918 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of pipeline at AMRA water supply scheme at different villages (Tengaberia, Badpur & Kolupukur) FHTC of Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-F] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000561/2021-2022 | 1374/BSD | 05/10/2021 | 30 | D.M. ENTERPRISE | 4.74 | 0 | 1
4919 | Burdwan Division | Burdwan Sadar Sub-Division | Repairing and replace of damaged UPVC Pipeline with installation and construction of valve chamber for control of water flow within command area of AMRA Piped W/S Scheme at Dogachia habitation,Jamalpur Development Block under Burdwan Division,PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000806/2022-2023 | 429/BSD | 15/03/2023 | 30 | DEY NIRMAN | 0.89 | 0 | 100
4920 | Burdwan Division | Central Mechanical Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Head Work Site to departmental drawing (Size 3.60 mtr x 3.00 mtr room) for MAJHIGRAM SINGOT water supply schemes under Katwa Sub-Division within Burdwan Division, PHE Dte. [ G.L to P.L Height= 1.20 Mtr] (Sl No-1) | Assistant Engineer | Junior Engineer | ORD/000273/2021-2022 | 798/KTS | 10/12/2021 | 60 | BABUL SK | 3.24 | 0 | 1
4921 | Burdwan Division | Central Mechanical Sub-Division | Route Survey and preparation of DPR for MAJHIGRAM-SINGHOT PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-05] | Assistant Engineer | Junior Engineer | ORD/000546/2021-2022 | 56/KTS | 25/01/2022 | 21 | RADIANT | 2.63 | 0 | 1
4922 | Burdwan Division | Central Mechanical Sub-Division | Construction of sanitary Latrine and water supply arrangement at Head Work Site of Majhigram Singot piped water supply schemes under Mongalkote Block under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No-01] | Assistant Engineer | Junior Engineer | ORD/000593/2021-2022 | 159/KTS | 24/02/2022 | 21 | BABUL SK | 1.76 | 0 | 1
4923 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000016/2022-2023 | 3275/BWD | 29/07/2022 | 0 | Resource Division | 34.57 | 0 | 0
4924 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000059/2021-2022 | 545/BWD | 27/01/2022 | 0 | Resource Division | 16.58 | 0 | 0
4925 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000163/2021-2022 | 1323/BWD | 08/03/2022 | 0 | Resource Division | 16 | 0 | 0
4926 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000181/2021-2022 | 1376/BWD | 09/03/2022 | 0 | Resource Division | 3.83 | 0 | 0
4927 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000219/2021-2022 | 1553/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
4928 | Burdwan Division | Central Mechanical Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
4929 | Central Mechanical | Central Mechanical Sub-Division | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 3 of Majhigram Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [ Block- Mongalkoat ] | Assistant Engineer | Junior Engineer | ORD/000013/2022-2023 | 1173/CMD | 27/06/2022 | 30 | MITRA ENTERPRISE | 9.22 | 0 | 1
4930 | Burdwan Division | Kalna Sub-division | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of December22 to February'23. | Assistant Engineer |  | BILL/00118/2023-2024 | 30/JJM | 19/04/2023 | 0 | PARTHA PRATIM ACHARYA | 1.19 | 0 | 0
4931 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sultanpur Piped Water Supply Scheme at Halbele, Hridaypur, Isabpur, Nowapara & Uplati Village (Mouza), Kalna ¿ I Block under Burdwan Division, PHE Dte.(Agreement No. 56/2020-2021 OF SE/CC/PHE. DTE.) | Assistant Engineer |  | ORD/000124/2020-2021 | 4901/BWD | 07/12/2020 | 90 | MAJILA ENTERPRISE | 94.67 | 0 | 1
4932 | Burdwan Division | Kalna Sub-division | Extension of different dia UPVC pipeline at different section of village Upalati, Hridaypur, Gopalpur, Sultanpur & Hatbele to cover up the uncovered habitation of Sultanpur PWSS within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000244/2021-2022 | 6122/BWD | 26/10/2021 | 30 | MAJILA ENTERPRISE | 14.34 | 0 | 1
4933 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 11 Nos. Piped W/S. Schemes under Kalna I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000335/2024-2025 | 3015/BWD | 05/08/2024 | 60 | HORIZEN | 29.6 | 0 | 10
4934 | Burdwan Division | Kalna Sub-division | Providing FHTC in each household from dist. System within Scheme jurisdiction in Hridaypur, Upalati, Belerhat, Gopalpur, Sultanpur, Isabpur & Naopara Village of SULTANPUR W/S. Scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000584/2021-2022 | 1357/BWD | 09/03/2022 | 30 | TAPAS KUMAR ROY | 16.69 | 0 | 1
4935 | Burdwan Division | Kalna Sub-division | Protection work of distribution system (200 mm dia) of 35 Mtr length near the head work site (Right Side) of Sultanpur & its adjoining mouzas water supply scheme by UC Bullah including Drum Sheet within Kalna Sub-Division under Burdwan Division, PHE Dte.[Gr.-E] | Assistant Engineer |  | ORD/000845/2020-2021 | 20/KSD | 07/01/2021 | 30 | DEBASHISH ENTERPRISE | 0.75 | 0 | 1
4936 | Burdwan Division | Kalna Sub-division | Quotation from WBSEDCL for Load Enhancement charges of Sajiara water supply scheme of PH-1. under Burdwan Division, PHE Dte. | Assistant Engineer |  | BILL/01725/2023-2024 | 1402/JJM | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.32 | 0 | 0
4937 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell site for SAJIARA Piped Water Supply Scheme, Block - Purbasthali - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | Assistant Engineer |  | ORD/000012/2022-2023 | 1960/BWD | 12/04/2022 | 45 | ACME CONSTRUCTION | 14.81 | 0 | 100
4938 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of SAJIARA (SM/09716), NAMA BHANDARTIKURI (SM/14917) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000394/2024-2025 | 3010/BWD | 02/08/2024 | 240 | PRATIMA CONSTRUCTION | 79.16 | 0 | 2
4939 | Burdwan Division | Kalna Sub-division | Augmentation of SAJIARA Piped Water Supply Scheme with LDS, Rising Main, Switch Room (with & without water supply & sanitary arrangements), Construction 300 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Construction of Boundary wall under Kalna Sub-Division, Block - Purbasthali - II, Dist. - Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000432/2021-2022 | 645/BWD | 01/02/2022 | 365 | UNICON INDIA | 318.07 | 0 | 0
4940 | Burdwan Division | Kalna Sub-division | Laying distribution system for augmentation of SAJIARA W/S Scheme to provide house connection within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000512/2023-2024 | 3554/BWD | 11/08/2023 | 45 | SK RAJU | 42.39 | 0 | 40
4941 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Sajiara W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-D) | Assistant Engineer |  | ORD/000516/2021-2022 | 184/KSD | 21/02/2022 | 21 | M/S R. DUTTA & CO. | 2.88 | 0 | 1
4942 | Burdwan Division | Kalna Sub-division | Work Order for "Construction of Pump house cum chlorine room without sanitary (Size 3.60 mtr x 3.00 mtr room) at 2nd Tube well site for augmentation of Sajiara Water Supply Scheme for providing Functional Household Tap Connection (FHTC) within Kalna Sub-Division under Burdwan Division, PHE Dte.^". | Assistant Engineer |  | ORD/000552/2023-2024 | 1307/KSD | 23/08/2023 | 60 | BUILD-TECH | 3.02 | 0 | 0
4943 | Burdwan Division | Kalna Sub-division | Work Order for "Construction of Pump house cum chlorine room without sanitary (Size 3.60 mtr x 3.00 mtr room) at 2nd Tube well site for augmentation of Sajiara Water Supply Scheme for providing Functional Household Tap Connection (FHTC) within Kalna Sub-Division under Burdwan Division, PHE Dte.^". | Assistant Engineer |  | ORD/000559/2023-2024 | 1307/KSD | 23/08/2023 | 60 | BUILD-TECH | 3.02 | 0 | 0
4944 | Burdwan Division | Kalna Sub-division | Laying of Rising Main for Augmentation of SAJIARA Piped Water Supply Scheme to provide house connection within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000597/2023-2024 | 3766/BWD | 29/08/2023 | 30 | CHOWDHURY CONSTRUCTION | 8.19 | 0 | 2
4945 | Burdwan Division | Kalna Sub-division | Construction of boundary wall of SAJIARA Piped water supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Length -150 Mtr, No of Columns-43 Nos. Centre to Centre- 3.5 Mtr.) With Double Tie Beam. | Assistant Engineer |  | ORD/000598/2023-2024 | 4172/BWD | 21/09/2023 | 30 | HAIDER ALI MONDAL | 14.53 | 0 | 80
4946 | Burdwan Division | Kalna Sub-division | Construction of Pump House cum chlorine room with sanitary and water supply arrangement at Head Work Site for augmentation of SAJIARA according to departmental drawing No-PHE/BD/P.H/DRG-01/DEC-2017 (Size 3.30 mtr x 3.60 mtr room with 1.2 Mtr. wide verandah) to provide house connection within Kalna Sub-Division under Burdwan Division, PHE Dte._2ND CALL | Assistant Engineer |  | ORD/000964/2023-2024 | 5713/BWD | 29/12/2023 | 60 | DEL DELTA CONSTRUCTION | 5.2 | 0 | 0
4947 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000021/2022-2023 | 3274/BWD | 29/07/2022 | 0 | Resource Division | 34.57 | 0 | 0
4948 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000031/2021-2022 | 546/BWD | 27/01/2022 | 0 | Resource Division | 15.25 | 0 | 0
4949 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000147/2021-2022 | 1244/BWD | 07/03/2022 | 0 | Resource Division | 2.64 | 0 | 0
4950 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000171/2021-2022 | 1339/BWD | 08/03/2022 | 0 | Resource Division | 53.75 | 0 | 0
4951 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000241/2021-2022 | 1565/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
4952 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
4953 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of Sajiara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer |  | ORD/000064/2023-2024 | 2567/CMD | 06/06/2023 | 30 | AMUSAR IMPEX PVT. LTD. | 21.95 | 0 | 0
4954 | Burdwan Division | Burdwan Sadar Sub-Division | Quotation for WBSEDCL for New Service connection of Sasinara Z-II TW-3 water supply scheme. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01244/2023-2024 | 1149/JJM | 29/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.03 | 0 | 0
4955 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of SASINARA ZONE-II Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 350 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under MEMARI- I Block, District:- Purba-Burdwan. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000123/2022-2023 | 2929/BWD | 28/06/2022 | 885 | ASHOK KUMAR GHOSH | 481.08 | 0 | 100
4956 | Burdwan Division | Burdwan Sadar Sub-Division | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-II W/S Scheme at Kalsi Mouza, RASULPUR W/S Scheme at 4th TW site & ALIPUR W/S Scheme at 4th TW site under Memari-I Block under within Burdwan Sub-Division, PHE Dte. [For 3 Nos. Tube well]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000159/2023-2024 | 2455/BWD | 31/05/2023 | 60 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 39.76 | 0 | 100
4957 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for Sasinara (Zone-II) & (Zone-III) W/S Scheme under Burdwan-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.2. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000491/2021-2022 | 177/BSD | 31/01/2022 | 30 | RADIANT | 3.76 | 0 | 1
4958 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Balance Functional Household Tap Connection (850nos FHTC) from existing distribution system within the command area of SASINARA ZONE-II Piped Water Supply Scheme at (Sasinara, Kalsi, Debipur, Amadpur, Maheshpur, Mobarakpur) Mouza, Construction of boundary wall at head work site, 2nd T/W & 3rd T/W site under MEMARI-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000531/2023-2024 | 3628/BWD | 21/08/2023 | 60 | A R TRADERS | 69.4 | 0 | 99
4959 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch rooms & Rising main at different TW site for SASINARA (Zone-II) Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000654/2023-2024 | 4165/BWD | 20/09/2023 | 60 | PAL CONSTRUCTION | 9.12 | 0 | 100
4960 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000044/2022-2023 | 4851/BWD | 20/10/2022 | 0 | Resource Division | 10.47 | 0 | 0
4961 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000175/2021-2022 | 1332/BWD | 08/03/2022 | 0 | Resource Division | 108.97 | 0 | 0
4962 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000195/2021-2022 | 1387/BWD | 09/03/2022 | 0 | Resource Division | 4.83 | 0 | 0
4963 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000223/2021-2022 | 1546/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
4964 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
4965 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW Site of Aug. HATKALNA & its adjoining mouzas Piped Water Supply Scheme, Block ¿ Kalna ¿ I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 01 No. Tube well]. | Assistant Engineer | JUNIOR ENGINEER | ORD/000218/2023-2024 | 2711/BWD | 08/06/2023 | 30 | AUXILIARY TUBE WELL DRILLERS | 9.89 | 0 | 90
4966 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 11 Nos. Piped W/S. Schemes under Kalna I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000335/2024-2025 | 3015/BWD | 05/08/2024 | 60 | HORIZEN | 29.6 | 0 | 10
4967 | Burdwan Division | Kalna Sub-division | Augmentation of Hatkalna Piped Water Supply Scheme with LDS, FHTC, Construction of 1000 cum capacity OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site & repairing of switch rooms under Kalna-I Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000536/2022-2023 | 5019/BWD | 10/11/2022 | 1057 | S.P. CONSTRUCTION | 976.48 | 0 | 50
4968 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Hatkalna W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-C) | Assistant Engineer | JUNIOR ENGINEER | ORD/000610/2021-2022 | 269/KSD | 15/03/2022 | 21 | ROY CHOWDHURY ASSOCIATES | 3.23 | 0 | 1
4969 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 2nd TW Site of Aug. HATKALNA & its adjoining mouzas Piped Water Supply Scheme, Block ¿ Kalna ¿ I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000699/2022-2023 | 605/BWD | 17/02/2023 | 30 | AUXILIARY TUBE WELL DRILLERS | 8.64 | 0 | 1
4970 | Burdwan Division | Kalna Sub-division | Renovation of Pump House in connection with Augmentation of Hatkalna piped Water supply (SM/10337) Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. (2 units) | Assistant Engineer | JUNIOR ENGINEER | ORD/000746/2024-2025 | 3747/BWD | 29/10/2024 | 30 | S.B.S. ENTERPRISE | 9.7 | 0 | 100
4971 | Burdwan Division | Kalna Sub-division | Construction of switch rooms & Rising main at different TW site for Hatkalna Piped Water Supply Scheme under Kalna - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000757/2023-2024 | 4736/BWD | 03/11/2023 | 422 | BISWAS ENTERPRISE | 8.38 | 0 | 100
4972 | Burdwan Division | Kalna Sub-division | Work Order for "Construction of Toilet (1.8 m x 1.8 m) with saitary arrangement in connection with Augmentation of Hatkalna pwss (SM/10337) under Kalna sub division under Burdwan Division." | Assistant Engineer | JUNIOR ENGINEER | ORD/000796/2024-2025 | 1766/KSD | 20/11/2024 | 30 | S.B.S. ENTERPRISE | 4.91 | 0 | 100
4973 | Burdwan Division | Kalna Sub-division | Work Order for "Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire in connection with Augmentation of Hatkalna PWSS ( SM/10337) Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER | ORD/000798/2024-2025 | 1767/KSD | 20/11/2024 | 30 | S.B.S. ENTERPRISE | 3.35 | 0 | 2
4974 | Burdwan Division | Kalna Sub-division | Construction of 1.5 Mtr. height boundary wall along with 750 mm. height 3 layer barbed wire and other ancillary works at Head Work Site in connection with Augmentation of Hatkalna PWSS (SM/10337) Piped Water Supply Scheme within Kalna Sub Division under Burdwan Divn., PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000813/2024-2025 | 4067/BWD | 21/11/2024 | 30 | UJJWAL MUKHERJEE | 20.99 | 0 | 100
4975 | Burdwan Division | Kalna Sub-division | Sinking of Tube well 250 x 200 mm dia Tube well 150 mtr depth by D.R. Rig method using UPVC pipe (CD) and fibre glass strainer for HATKALNA piped water supply scheme (2nd tube well site), Block-Kalna-I, Dist.-Purba Bardhaman, under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000962/2020-2021 | 1492/BWD | 18/02/2021 | 30 | C.M. ENTERPRISE | 8.68 | 0 | 1
4976 | Burdwan Division | Kalna Sub-division | Additional work viz. Carriage of different type of departmental pipes and Interconnection of Tube well and existing pipe line and Restoration of existing concrete road and laying of pipeline of HATKALNA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000969/2023-2024 | 003/BWD | 02/01/2024 | 120 | S.P. CONSTRUCTION | 162.05 | 0 | 100
4977 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000013/2022-2023 | 3279/BWD | 29/07/2022 | 0 | Resource Division | 52.8 | 0 | 0
4978 | Central Mechanical | Kalna Sub-division | QUOTATION FOR NEW SERVICE CONNECTION AT AUGMENTATION OF HAT KALNA PWSS TW 3, BLOCK KALNA-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/00727/2024-2025 | BP-2024-25-285 | 10/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.36 | 0 | 0
4979 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring of Tube Well No- 01,02 03 & 04 at Augmentation Hatkalna [Block -Kalna-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000916/2022-2023 | 1080/CMD | 03/03/2023 | 820 | P.K. ENGINEERING | 41.64 | 0 | 35
4980 | Central Mechanical | Kalna Sub-division | Supply & Installation of Chlorination System for Tube well No.-2 at Hat Kalna Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001847/2023-2024 | 377/CMSD | 29/02/2024 | 15 | SUDIKSHA CONSTRUCTION | 0.96 | 0 | 100
4981 | Central Mechanical | Kalna Sub-division | Supply & Installation of Chlorination System for Tube well No.-1 at Hat Kalna Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001866/2023-2024 | 464/CMSD | 21/03/2024 | 12 | JOYGURU ENTERPRISE | 0.96 | 0 | 100
4982 | Burdwan Division | Kalna Sub-division | New service connection quotation from WBSEDCL of Augmentation of Baidyapur Z-II (T.W.-3) under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | BILL/00098/2023-2024 | 194/JJM | 31/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.56 | 0 | 0
4983 | Burdwan Division | Kalna Sub-division | Augmentation of Baidyapur (Zone-I & II) Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 200 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including repairing of OHR, boundary walls & switch rooms under Kalna-II Block, District:- Purba-Burdwan. | Assistant Engineer | JUNIOR ENGINEER | ORD/000116/2022-2023 | 2859/BWD | 22/06/2022 | 1229 | SUPRITI ENTERPRISE | 734.07 | 0 | 60
4984 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of BAIDYAPUR (Z-I) PWSS, Block - Kalna - II and NANDAI PWSS, Block - Kalna - I Piped Water Supply Scheme, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | Assistant Engineer | JUNIOR ENGINEER | ORD/000151/2023-2024 | 2424/BWD | 30/05/2023 | 45 | KOUSIK MALLICK | 19.84 | 0 | 100
4985 | Burdwan Division | Kalna Sub-division | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | Assistant Engineer | JUNIOR ENGINEER | ORD/000304/2024-2025 | 2827/BWD | 19/07/2024 | 216 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 100
4986 | Burdwan Division | Kalna Sub-division | Construction of switch rooms & Rising main at different TW site for Baidyapur (Zone-I) Piped Water Supply Scheme under Kalna - II Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000529/2023-2024 | 3626/BWD | 21/08/2023 | 60 | M/S UNIQUE | 9.11 | 0 | 65
4987 | Burdwan Division | Kalna Sub-division | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 2nd TW Site of Aug. of BAIDYAPUR (Z-II) & its adjoining mouzas Piped Water Supply Scheme, Block ? Kalna ? II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte._2ND CALL. | Assistant Engineer | JUNIOR ENGINEER | ORD/000567/2022-2023 | 5274/BWD | 30/11/2022 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 7.33 | 0 | 0
4988 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Baidyapur W/S Scheme (Zone-I & II) within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | Assistant Engineer | JUNIOR ENGINEER | ORD/000568/2021-2022 | 203/KSD | 23/02/2022 | 21 | INDRANIL DUTTA & ASSOCIATES | 4.19 | 0 | 1
4989 | Burdwan Division | Kalna Sub-division | Additional pipe laying of HDPE pipeline & providing FHTC work at Sanpukur, Mirhat village under BAIDYAPUR Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000871/2023-2024 | 5308/BWD | 01/12/2023 | 166 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 35.01 | 0 | 1
4990 | Burdwan Division | Kalna Sub-division | Work Order for "Restoration in pipe connection of Augmentation scheme of Baidyapur Zone-II Piped Water Supply Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-3) | Assistant Engineer | JUNIOR ENGINEER | ORD/001133/2023-2024 | 2062/KSD | 23/02/2024 | 20 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 1.37 | 0 | 0
4991 | Burdwan Division | Kalna Sub-division | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001144/2024-2025 | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0
4992 | Burdwan Division | Kalna Sub-division | Work Order for "Renovation of Pump House for Augmentation 1 of Baidyapur (Zone-II) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER | ORD/001241/2023-2024 | 1953/KSD | 05/02/2024 | 25 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.59 | 0 | 100
4993 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000001/2022-2023 | 3272/BWD | 29/07/2022 | 0 | Resource Division | 31.47 | 0 | 0
4994 | Central Mechanical | Kalna Sub-division | Quotation for new service connection at Baidyapur Zone-2 PWSS PH-3 | Assistant Engineer | JUNIOR ENGINEER | BILL/00390/2024-2025 | BP-2024-25-200 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.14 | 0 | 0
4995 | Central Mechanical | Kalna Sub-division | Quotation for load enhancement at Baidyapur PH2 | Assistant Engineer | JUNIOR ENGINEER | BILL/00810/2024-2025 | BP-2024-25-302 | 24/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.35 | 0 | 0
4996 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation of BAIDYAPUR PWSS under CMD, PHE Dte., Dist.- Purba-Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/000912/2022-2023 | 1036/CMD | 02/03/2023 | 30 | BEHERA ENTERPRISE | 11.46 | 0 | 80
4997 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 5 & 6 at Augumentation of BAIDYAPUR Water Supply Scheme [BLOCK- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001618/2023-2024 | 1542/CMD | 05/03/2024 | 425 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 24.62 | 0 | 50
4998 | Central Mechanical | Kalna Sub-division | Supply and delivery of different Electro-mechanical items for Baidyapur zone-1 Water Supply Scheme PH 1 replacement T.W (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/001670/2023-2024 | 64/CMSD | 11/01/2024 | 12 | SUBRATA BHADRA | 0.96 | 0 | 100
4999 | Central Mechanical | Kalna Sub-division | House wiring, double earthing and allied works for Baidyapur zone-1 Water Supply Scheme PH 1 replacement T.W (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/001674/2023-2024 | 80/CMSD | 15/01/2024 | 12 | SUBRATA BHADRA | 0.97 | 0 | 100
5000 | Central Mechanical | Kalna Sub-division | Supply & Installation of Chlorination System for Tube well No.-1 at Baidyapur (zone-1) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001863/2023-2024 | 461/CMSD | 21/03/2024 | 12 | SUDIKSHA CONSTRUCTION | 0.96 | 0 | 100
5001 | Burdwan Division | Central Mechanical Sub-Division | Shifting of 63 KVA DTR at Naliapur village of Augmentation of Mougram Z-II water supply scheme under Burdwan Division, PHE Dte. (Ref ID-860268576, Application ID-100000077306, dt.-02/05/2023) | Assistant Engineer | Junior Engineer | BILL/00142/2023-2024 | 231/JJM/23-24 | 13/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.21 | 0 | 0
5002 | Burdwan Division | Central Mechanical Sub-Division | Augmentation of MOUGRAM (ZONE-I) Piped Water Supply Scheme with LDS, FHTC, & Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under Ketugram-II Block, District:- Purba-Burdwan. | Assistant Engineer | Junior Engineer | ORD/000087/2022-2023 | 2611/BWD | 23/05/2022 | 365 | UMWELT ENGINEER PVT LTD | 499.84 | 0 | 97
5003 | Burdwan Division | Central Mechanical Sub-Division | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day.(Sl No-1) | Assistant Engineer | Junior Engineer | ORD/000510/2023-2024 | 499/KTS | 22/05/2023 | 70 | M/S MUNMUN DEY | 0.9 | 0 | 100
5004 | Burdwan Division | Central Mechanical Sub-Division | Route Survey and Preparation of DPR for MOUGRAM (ZONE-I & II) PWSS under Ketugram-II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-07] | Assistant Engineer | Junior Engineer | ORD/000548/2021-2022 | 67/KTS | 27/01/2022 | 21 | RADIANT | 4.11 | 0 | 1
5005 | Burdwan Division | Central Mechanical Sub-Division | Continuation order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. (Sl No-1) | Assistant Engineer | Junior Engineer | ORD/000930/2023-2024 | 1016/KTS | 20/09/2023 | 23 | M/S MUNMUN DEY | 0.3 | 0 | 0
5006 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000017/2022-2023 | 3280/BWD | 29/07/2022 | 0 | Resource Division | 34.57 | 0 | 0
5007 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000177/2021-2022 | 1335/BWD | 08/03/2022 | 0 | Resource Division | 25.88 | 0 | 0
5008 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000189/2021-2022 | 1383/BWD | 09/03/2022 | 0 | Resource Division | 4.47 | 0 | 0
5009 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000229/2021-2022 | 1551/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
5010 | Burdwan Division | Central Mechanical Sub-Division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
5011 | Burdwan Division | Kalna Sub-division | Restoration of work due to laying of Water Supply Pipelines along Bonpass Village(Kamarpara) to Banpass Railway Station Road by Public Health Engineering Directorate under " Jal Jeevan Mission from 0.00 km to 1.54 km in the district of Purba Bardhaman under Burdwan Division,P.W.D." | Assistant Engineer |  | BILL/00709/2024-2025 | 866/JJM | 23/09/2024 | 0 | EXECUTIVE ENGINEER PWD BURDWAN DIVISION | 2.94 | 0 | 0
5012 | Burdwan Division | Kalna Sub-division | Restoration of damaged flanks due to laying of HDPE pipe line along the flank of Burdwan Katwa Road from 14.70 kmp to 16.20 kmp in the district of Purba Bardhaman under Bardhaman Division,P.W.D. | Assistant Engineer |  | BILL/00711/2024-2025 | 867/JJM | 23/09/2024 | 0 | EXECUTIVE ENGINEER PWD BURDWAN DIVISION | 7.9 | 0 | 0
5013 | Burdwan Division | Kalna Sub-division | Payment of vehicle bill (Car No.-WB-41H-9788) for the month of September'23. | Assistant Engineer |  | BILL/01343/2023-2024 | 899/JJM | 22/11/2023 | 0 | SK. ASRAFUDDIN | 0.4 | 0 | 0
5014 | Burdwan Division | Kalna Sub-division | Extension of pipeline in Connection to FHTC work at Gramdihi village of Gramdihi and its adjoining Mouza's Piped W/S Scheme at Bhatar Block within Durgapur (Bardhaman North)Sub-Division under Burdwan Division, P.H.E. Dte. (Gr.-A) | Assistant Engineer |  | ORD/000105/2021-2022 | 416/DSD | 02/07/2021 | 30 | DEY NIRMAN | 4.71 | 0 | 1
5015 | Burdwan Division | Kalna Sub-division | Extension of UPVC pipe line of LDS at Manderbati village and Majhipara for providing FHTC of Gramdihi and its adjoining mouzas W/S Scheme within Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-B] | Assistant Engineer |  | ORD/000263/2021-2022 | 690/DSD | 08/12/2021 | 30 | BIPLAB SAMANTA | 2.26 | 0 | 1
5016 | Burdwan Division | Kalna Sub-division | Extension of UPVC pipe line of LDS at Gholada village for providing FHTC of Gramdihi and its adjoining mouzas W/S Scheme within Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-C] | Assistant Engineer |  | ORD/000264/2021-2022 | 691/DSD | 08/12/2021 | 30 | M/S GUPTA ENTERPRISE | 4.84 | 0 | 1
5017 | Burdwan Division | Kalna Sub-division | Extension of UPVC pipe line of LDS at Bighra village for providing FHTC of Gramdihi and its adjoining mouzas W/S Scheme within Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-D] | Assistant Engineer |  | ORD/000265/2021-2022 | 692/DSD | 08/12/2021 | 30 | SHUBHRA KANTI GHOSH | 4.3 | 0 | 1
5018 | Burdwan Division | Kalna Sub-division | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer |  | ORD/000389/2021-2022 | 268/BWD | 14/01/2022 | 30 | BHARAT CONSTRUCTION | 14.17 | 0 | 1
5019 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Gramdihi Piped Water Supply Scheme at Mandarbati, Gholada & Bigra Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. (Agreement no. 792/BWD of 2020-2021) | Assistant Engineer |  | ORD/000434/2020-2021 | 1794/BWD | 26/02/2021 | 45 | M/S GUPTA ENTERPRISE | 41.94 | 0 | 1
5020 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Gramdihi Piped Water Supply Scheme at Gramdihi & Sanchalida Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. [Agreement No. 631/BWD OF 2020-2021.] | Assistant Engineer |  | ORD/000436/2020-2021 | 956/BWD | 03/02/2021 | 45 | DEY NIRMAN | 35.08 | 20.5 | 0
5021 | Burdwan Division | Kalna Sub-division | Laying Piper Line and FHTC for Gramdihi Jr. Basic School under Gramdihi Piped water supply Scheme , P.H.E Dte. Block:-Bhatar Dist: Purba Bardhaman | Assistant Engineer |  | ORD/000524/2025-2026 | 1020/DSD | 10/07/2025 | 15 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 0.15 | 0 | 0
5022 | Burdwan Division | Kalna Sub-division | Augmentation of SATGACHI Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 700 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including construction of switch-room (3.60mx3.0m) & boundary wall under Kalna-II Block, District:- Purba-Burdwan. | Assistant Engineer | JUNIOR ENGINEER | ORD/000065/2022-2023 | 2339/BWD | 10/05/2022 | 1056 | P.B. ENTERPRISE | 727.47 | 0 | 100
5023 | Burdwan Division | Kalna Sub-division | Sinking of additional 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SATGACHHI Piped Water Supply Scheme, Block - Kalna - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000069/2022-2023 | 2423/BWD | 11/05/2022 | 30 | M/S SYCHROTECH INDUSTRY | 9.01 | 0 | 100
5024 | Burdwan Division | Kalna Sub-division | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | Assistant Engineer | JUNIOR ENGINEER | ORD/000304/2024-2025 | 2827/BWD | 19/07/2024 | 216 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 100
5025 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 03 Nos. Piped W/S. Schemes under Kalna II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000336/2024-2025 | 3016/BWD | 05/08/2024 | 20 | HORIZEN | 7.55 | 0 | 100
5026 | Burdwan Division | Kalna Sub-division | Extension of 75 mm dia pipeline at Miya Para, Modhya Bohar & Bhagar Para Purba Bohar regarding FHTC under Satgachia (Zone-I) water supply scheme under Burdwan Division, PHE Dte.[Gr.-A] | Assistant Engineer | JUNIOR ENGINEER | ORD/000350/2021-2022 | 703/BSD | 11/06/2021 | 5 | M/S SAYAN CHAKRABORTY | 0.88 | 0 | 1
5027 | Burdwan Division | Kalna Sub-division | Preparation of DPR for augmentation of Satgachhi W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | Assistant Engineer | JUNIOR ENGINEER | ORD/000514/2021-2022 | 182/KSD | 21/02/2022 | 21 | M/S R. DUTTA & CO. | 3.27 | 0 | 1
5028 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000014/2022-2023 | 3273/BWD | 29/07/2022 | 0 | Resource Division | 33.26 | 0 | 0
5029 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000038/2021-2022 | 551/BWD | 27/01/2022 | 0 | Resource Division | 39.34 | 0 | 0
5030 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000038/2022-2023 | 4630/BWD | 17/10/2022 | 0 | Resource Division | 12.32 | 0 | 0
5031 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000173/2021-2022 | 1331/BWD | 08/03/2022 | 0 | Resource Division | 160.86 | 0 | 0
5032 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000194/2021-2022 | 1388/BWD | 09/03/2022 | 0 | Resource Division | 4.6 | 0 | 0
5033 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000222/2021-2022 | 1545/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0
5034 | Burdwan Division | Kalna Sub-division | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0
5035 | Central Mechanical | Kalna Sub-division | Quotation for new service connection at Satgachi PWSS PH 5 | Assistant Engineer | JUNIOR ENGINEER | BILL/00933/2024-2025 | BP-2024-25-351 | 05/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.59 | 0 | 0
5036 | Central Mechanical | Kalna Sub-division | New service connection charges for Aug. of Satgachi PWSS TW-3 | Assistant Engineer | JUNIOR ENGINEER | BILL/01393/2023-2024 | BP-2023-24-136 | 25/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.05 | 0 | 0
5037 | Central Mechanical | Kalna Sub-division | New service connection charges for Aug. of Satgachi PWSS TW-4 | Assistant Engineer | JUNIOR ENGINEER | BILL/01395/2023-2024 | BP-2023-24-137 | 25/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.67 | 0 | 0
5038 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of Satgachi Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | Assistant Engineer | JUNIOR ENGINEER | ORD/000210/2023-2024 | 3046/CMD | 20/07/2023 | 30 | AMUSAR IMPEX PVT. LTD. | 21.98 | 0 | 95
5039 | Burdwan Division | Katwa Sub-Division | Laying of pipe line (Parallel to the main line) of the existing Distribution System and Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of SRIKHANDA Piped Water Supply Scheme at Katwa-I Block under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/000023/2022-2023 | 2027/BWD | 18/04/2022 | 30 | M/S JOY | 53.12 | 0 | 1
5040 | Burdwan Division | Katwa Sub-Division | Balance work of OHR, construction Concrete Road, Functional Household Tap Connection, Road restoration etc. for Nanagar PWSS, Srikhanda PWSS, under KATWA -I Block under Katwa Sub-Divn under Burdwan Division, PHE Dte. District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/000685/2024-2025 | 3655/BWD | 21/10/2024 | 120 | HAMID SK | 121.69 | 0 | 0
5041 | Burdwan Division | Burdwan Sadar Sub-Division | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000653/2023-2024 | 4076/BWD | 13/09/2023 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 0 | 100
5042 | Burdwan Division | Burdwan Sadar Sub-Division | KHUNDKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000753/2022-2023 | 1217/BWD | 16/03/2023 | 747 | M/S JAN MAHAMMAD | 510.97 | 0 | 100
5043 | Burdwan Division | Burdwan Sadar Sub-Division | Supply of flow control devices for KHUNDKURI PWSS (SM/13465) under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000840/2024-2025 | 986/AE/HQ | 26/11/2024 | 70 | MAKALI ENGINEERING CORPORATION | 8.33 | 0 | 100
5044 | Burdwan Division | Burdwan Sadar Sub-Division | Interconnection between pump house and delivery line and Construction of boundary wall at 2nd TW site for KHUDKURI PWSS under Khandaghosh Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000869/2023-2024 | 5309/BWD | 01/12/2023 | 60 | JYOTI ENTERPRISE | 12.63 | 0 | 100
5045 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 183 | SK.ASFIA | 2.4 | 0 | 70
5046 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000074/2022-2023 | 1253/BWD | 17/03/2023 | 0 | Resource Division | 16.58 | 0 | 0
5047 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000106/2022-2023 | 1631/BWD | 06/04/2023 | 0 | Resource Division | 12.19 | 0 | 0
5048 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000705/2023-2024 | 5046/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
5049 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Khundkuri PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01035/2023-2024 | BP-2023-24-115 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.93 | 0 | 0
5050 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Khundkuri PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01036/2023-2024 | BP-2023-24-116 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.65 | 0 | 0
5051 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khundkuri Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000052/2023-2024 | 2513/CMD | 02/06/2023 | 30 | RAJIB COMPANY | 28.95 | 0 | 98
5052 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000064/2024-2025 | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0
5053 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000727/2023-2024 | 4581/BWD | 16/10/2023 | 965 | SAFECO ENTERPRISES | 1551.98 | 0 | 60
5054 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000026/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 25.59 | 0 | 0
5055 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000302/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.13 | 0 | 0
5056 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000550/2023-2024 | 4313/BWD | 29/09/2023 | 0 | Resource Division | 24.08 | 0 | 0
5057 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000588/2023-2024 | 4945/BWD | 10/11/2023 | 0 | Resource Division | 34.27 | 0 | 0
5058 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | RTOR000775/2023-2024 | 201/BWD | 10/01/2024 | 0 | Resource Division | 5.46 | 0 | 0
5059 | Central Mechanical | Durgapur Sub-DIvision | QUOTATION FOR NEW SERVICE CONNECTION FOR KALYANPUR PWSS PH-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | BILL/00194/2024-2025 | BP-2024-25-90 | 17/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.89 | 0 | 0
5060 | Central Mechanical | Durgapur Sub-DIvision | Quotation for New service connection for Kalyanpur PWSS PH 1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | BILL/00249/2024-2025 | BP-2024-25-130 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.51 | 0 | 0
5061 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR KALYANPUR PWSS. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | BILL/02589/2023-2024 | BP-2023-24-555 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.16 | 0 | 0
5062 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kalyanpur Water Supply Scheme [ Block-Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000745/2023-2024 | 4055/CMD | 29/08/2023 | 30 | T.N. BANERJEE | 27.71 | 0 | 0
5063 | Burdwan Division | Burdwan Sadar Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARASAT, JAGADABAD & KHAIDYA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000465/2023-2024 | 3460/BWD | 08/08/2023 | 783 | CONCORD EMC ENCLAVE LLP | 1526.24 | 0 | 5
5064 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000100/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.56 | 0 | 0
5065 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000376/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.37 | 0 | 0
5066 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000723/2023-2024 | 5264/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0
5067 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Khaidya PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02201/2023-2024 | BP-2023-24-396 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.66 | 0 | 0
5068 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Khaidya PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02202/2023-2024 | BP-2023-24-397 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.36 | 0 | 0
5069 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
5070 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khaidya Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000657/2023-2024 | 4000/CMD | 29/08/2023 | 642 | AHALYA ENGINEERING WORKS | 28.95 | 0 | 90
5071 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KACHUA & KAMALPUR Piped Water Supply Scheme under Purbasthali ¿ I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000133/2023-2024 | 2344/BWD | 22/05/2023 | 863 | CONCORD ENGINEERING | 470.92 | 0 | 40
5072 | Burdwan Division | Kalna Sub-division | Different Types of work involved in connection with Augmentation of SONARUDRA (SM/16349) & KACHUA (SM/13497) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000192/2024-2025 | 2430/BWD | 27/06/2024 | 480 | R.G. INFRASTRUCTURE | 240.7 | 0 | 2
5073 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000298/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 1.9 | 0 | 0
5074 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000473/2023-2024 | 3997/BWD | 08/09/2023 | 0 | Resource Division | 0.55 | 0 | 0
5075 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | RTOR000799/2023-2024 | 310/BWD | 24/01/2024 | 0 | Resource Division | 17.19 | 0 | 0
5076 | Central Mechanical | Kalna Sub-division | New service connection for KACHUA PWSS TW-1. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | BILL/02395/2023-2024 | BP-2023-24-504 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0
5077 | Central Mechanical | Kalna Sub-division | New service connection for KACHUA PWSS TW-2. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | BILL/02396/2023-2024 | BP-2023-24-505 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.03 | 0 | 0
5078 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 30
5079 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at KACHUA Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER,JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000828/2023-2024 | 4105/CMD | 29/08/2023 | 30 | MENAKA ENTERPRISE. | 20.8 | 0 | 95
5080 | Durgapur W/S Division | Durgapur Sub-DIvision | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 1
5081 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000014/2024-2025 | 1724/E/DWSD | 10/12/2024 | 0 | Resource Division | 3.95 | 0 | 0
5082 | Burdwan Division | Durgapur Sub-DIvision | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways at different TW sites for SHIBADA Piped Water Supply Scheme under Ausgram-I Block, District:- Purba Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000392/2023-2024 | 3218/BWD | 25/07/2023 | 365 | ONKAR ENTERPRISE | 319.96 | 0 | 71
5083 | Burdwan Division | Durgapur Sub-DIvision | Repairing of Sajaldhara pipeline(Colony para Uttar) for SIBDA Water Supply Scheme of Aushgram-I Block,under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001102/2023-2024 | 236/DSD | 12/03/2024 | 15 | ONKAR ENTERPRISE | 0.97 | 0 | 100
5084 | Burdwan Division | Durgapur Sub-DIvision | Sajaldhara pipeline(Colony para Dakshin) for SIBDA Water Supply Scheme of Aushgram-I Block,under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001250/2023-2024 | 242/DSD | 12/03/2024 | 15 | ONKAR ENTERPRISE | 0.98 | 0 | 100
5085 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000033/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 4.95 | 0 | 0
5086 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000307/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 15.17 | 0 | 0
5087 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000610/2023-2024 | 4915/BWD | 10/11/2023 | 0 | Resource Division | 16.68 | 0 | 0
5088 | Central Mechanical | Durgapur Sub-DIvision | Additional quotation for new service connection at Shibda PWSS PH-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00286/2024-2025 | BP-2024-25-136 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0
5089 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Shibada PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01706/2023-2024 | BP-2023-24-232 | 20/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.08 | 0 | 0
5090 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR SHIBDA PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02469/2023-2024 | BP-2023-24-528 | 13/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 16.79 | 0 | 0
5091 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0
5092 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0
5093 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Shibada Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000685/2023-2024 | 4014/CMD | 29/08/2023 | 30 | S.P. CONSTRUCTION | 29.59 | 0 | 48
5094 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Balance works related ( LDS , FHTCs, Road Restoration of Dharala Piped Water Supply Scheme under Aushgram-II Block, of Durgapur Water supply Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000189/2024-2025 | 1609/DWSD | 26/11/2024 | 180 | SARKAR AGENCY | 51.36 | 0 | 70
5095 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000013/2024-2025 | 1724/F/DWSD | 10/12/2024 | 0 | Resource Division | 5.24 | 0 | 0
5096 | Burdwan Division | Durgapur Sub-DIvision | DHARALA [RAGHUNATHPUR VILLAGE] Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under AUSGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000075/2023-2024 | 2054/BWD | 04/05/2023 | 90 | BIPLAB GUHA | 65.39 | 0 | 100
5097 | Burdwan Division | Durgapur Sub-DIvision | DHARALA [DHARALA VILLAGE] Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000755/2022-2023 | 1208/BWD | 15/03/2023 | 90 | THREE MAA ENTERPRISE | 68.82 | 0 | 100
5098 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000085/2022-2023 | 1240/BWD | 17/03/2023 | 0 | Resource Division | 2.49 | 0 | 0
5099 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000105/2022-2023 | 1641/BWD | 06/04/2023 | 0 | Resource Division | 0.78 | 0 | 0
5100 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000756/2023-2024 | 5243/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0
5101 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Dharala PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00766/2023-2024 | BP-2023-24-68 | 20/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.76 | 0 | 0
5102 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Dharala PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01778/2023-2024 | BP-2023-24-286 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.29 | 0 | 0
5103 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Dharala Water Supply Scheme [ Block- Ausgram-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000204/2023-2024 | 3048/CMD | 20/07/2023 | 651 | J.S. CONSTRUCTION. | 29.71 | 0 | 70
5104 | Burdwan Division | Kalna Sub-division | Work order for "Restoration of pipeline with other allied works at different places of Rajkhara mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | JUNIOR ENGINEER | ORD/000527/2024-2025 | 970/KSD | 31/07/2024 | 10 | S.GHOSH & ASSOCIATES PVT LTD. | 2.75 | 0 | 100
5105 | Burdwan Division | Kalna Sub-division | Work order for "Restoration of pipeline with other allied works at different places of Bagpur mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER | ORD/000528/2024-2025 | 971/KSD | 31/07/2024 | 10 | S.GHOSH & ASSOCIATES PVT LTD. | 2.84 | 0 | 100
5106 | Burdwan Division | Kalna Sub-division | Work Order for "Restoration of pipeline with other allied works at different places of Bherua mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER | ORD/000529/2024-2025 | 972/KSD | 31/07/2024 | 10 | S.GHOSH & ASSOCIATES PVT LTD. | 3.39 | 0 | 100
5107 | Burdwan Division | Kalna Sub-division | Work Order for "Restoration of pipeline with other allied works at different places of Dhaleswar mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER | ORD/000548/2024-2025 | 973/KSD | 31/07/2024 | 10 | S.GHOSH & ASSOCIATES PVT LTD. | 2.29 | 0 | 100
5108 | Burdwan Division | Kalna Sub-division | Work order for "Restoration of pipeline with other allied works at different places of Chaugharia mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER | ORD/000863/2024-2025 | 1848/KSD | 27/11/2024 | 15 | S.GHOSH & ASSOCIATES PVT LTD. | 3.17 | 0 | 100
5109 | Burdwan Division | Kalna Sub-division | Work order for "Restoration of pipeline with other allied works at different places of Narayanpur mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | JUNIOR ENGINEER | ORD/000865/2024-2025 | 1850/KSD | 27/11/2024 | 15 | S.GHOSH & ASSOCIATES PVT LTD. | 3.58 | 0 | 100
5110 | Burdwan Division | Kalna Sub-division | Work order for "Restoration of pipeline with other allied works at different places of Kulera mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | JUNIOR ENGINEER | ORD/000866/2024-2025 | 1851/KSD | 27/11/2024 | 15 | S.GHOSH & ASSOCIATES PVT LTD. | 3.64 | 0 | 100
5111 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL UNDER PATHARDANGA PWSS AND TAIPARA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE. (2 UNITS:- 1 NO FOR PATHARDANGA PWSS & 1 NO FOR TAIPARA PWSS)" | Assistant Engineer | JUNIOR ENGINEER | ORD/001141/2023-2024 | 1977/KSD | 09/02/2024 | 10 | BISWAS ENTERPRISE | 0.66 | 0 | 100
5112 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000044/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 22.25 | 0 | 0
5113 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000183/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 14.82 | 0 | 0
5114 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000628/2023-2024 | 4888/BWD | 10/11/2023 | 0 | Resource Division | 29.45 | 0 | 0
5115 | Central Mechanical | Kalna Sub-division | Quotation for New Electric Connection for Taipara W/S Scheme PH NO.-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01733/2023-2024 | BP-2023-24-248 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.1 | 0 | 0
5116 | Central Mechanical | Kalna Sub-division | Electric quotation for New Service Connection at Taipara W/S Scehem PH-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/01776/2023-2024 | BP-2023-24-288 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.67 | 0 | 0
5117 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0
5118 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Taipara Water Supply Scheme [ Block- KALNA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000762/2023-2024 | 4063/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 28.89 | 0 | 90
5119 | Burdwan Division | Kalna Sub-division | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 14 Nos. Piped W/S. Schemes under Purbasthali I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000337/2024-2025 | 3017/BWD | 05/08/2024 | 75 | HORIZEN | 38 | 0 | 100
5120 | Burdwan Division | Kalna Sub-division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of NASARATPUR Piped Water Supply Scheme at Gopinathpur (Part), Nasaratput (Part) & Paruldanga (Part) Village (Mouza), Purbasthali - I Block under Burdwan Division, PHE Dte | Assistant Engineer | JUNIOR ENGINEER | ORD/000372/2021-2022 | 211/BWD | 11/01/2022 | 60 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 76.77 | 0 | 1
5121 | Burdwan Division | Kalna Sub-division | Augmentation of NASARATPUR (Part-B) Piped Water Supply Scheme with Sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of switch rooms & Boundary walls with gates at different TW site under Purbasthali-I Block, District:- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000502/2023-2024 | 3535/BWD | 10/08/2023 | 541 | IJABUL SEKH | 512.69 | 0 | 60
5122 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of NASRATPUR PWSS (SM/14014), Purbasthali-I Block, under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001098/2024-2025 | 432/BWD | 20/01/2025 | 120 | SANDIP BISWAS | 199.5 | 0 | 0
5123 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL UNDER NASARATPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001142/2023-2024 | 1978/KSD | 09/02/2024 | 10 | BISWAS ENTERPRISE | 0.66 | 0 | 100
5124 | Central Mechanical | Kalna Sub-division | New service connection for augmentation of Nasratpur PH-I PWSS. | Assistant Engineer | JUNIOR ENGINEER | BILL/00085/2024-2025 | BP-2024-25-30 | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.19 | 0 | 0
5125 | Central Mechanical | Kalna Sub-division | New service connection for Augmentation of Nasratpur PWSS TW-2. | Assistant Engineer | JUNIOR ENGINEER | BILL/02397/2023-2024 | BP-2023-24-509 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.21 | 0 | 0
5126 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 3 & 4 at Augumentation of NASRATPUR Water Supply Scheme [BLOCK- PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001613/2023-2024 | 1544/CMD | 05/03/2024 | 453 | MS DAS ELECTRIC CO | 24.63 | 0 | 95
5127 | Burdwan Division | Durgapur Sub-DIvision | Quotation from WBSEDCL for load enhancement of Belgram water supply scheme for PH-2 under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00171/2024-2025 | 267/JJM | 21/05/2024 | 0 | WBSEDCL | 4.33 | 0 | 0
5128 | Burdwan Division | Durgapur Sub-DIvision | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMSUNDARPUR & BELGRAM Piped Water Supply Scheme under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000086/2023-2024 | 2147/BWD | 10/05/2023 | 730 | MAHMOOD ASSOCIATES PVT. LTD. | 1172.24 | 0 | 78
5129 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000028/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 141.29 | 0 | 0
5130 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000243/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.94 | 0 | 0
5131 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000577/2023-2024 | 4925/BWD | 10/11/2023 | 0 | Resource Division | 39.08 | 0 | 0
5132 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Belgram PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02192/2023-2024 | BP-2023-24-372 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.27 | 0 | 0
5133 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
5134 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Belgrem Water Supply Scheme [ Block- Galsi-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000768/2023-2024 | 4066/CMD | 29/08/2023 | 580 | PADMA ENGINEERING CO. | 27.78 | 0 | 48
5135 | Durgapur W/S Division | Durgapur Sub-DIvision | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method for Trial Bore at Uchchagram under Krishnarampur PWSS (JJM) District:- Purba-Bardhaman, Under Durgapur W/S Division , PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000153/2024-2025 | 1418/DWSD | 03/10/2024 | 20 | D.M.ENTERPRISE | 6.61 | 0 | 80
5136 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Balance work for KRISHNARAMPUR Piped Water Supply Scheme i.e , Contruction of boundary walls with gates and land development, drain and internal pathway etc. at 3rd Pump house site & FHTC work under GALSI-I Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000167/2024-2025 | 1549/DWSD | 14/11/2024 | 270 | JOY GURU ENTERPRISE | 43.27 | 0 | 100
5137 | Durgapur W/S Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000006/2024-2025 | 1724/Q/DWSD | 10/12/2024 | 0 | Resource Division | 4 | 0 | 0
5138 | Burdwan Division | Durgapur Sub-DIvision | KRISHNARAMPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000403/2023-2024 | 3234/BWD | 26/07/2023 | 791 | DUTTA ENTERPRISE | 661.41 | 0 | 80
5139 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000025/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 79.1 | 0 | 0
5140 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000388/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.75 | 0 | 0
5141 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000737/2023-2024 | 5236/BWD | 30/11/2023 | 0 | Resource Division | 18.78 | 0 | 0
5142 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000791/2023-2024 | 317/BWD | 24/01/2024 | 0 | Resource Division | 43.39 | 0 | 0
5143 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR KRISHNARAMPUR PWSS PH-1. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02868/2023-2024 | BP-2023-24-606 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.75 | 0 | 0
5144 | Central Mechanical | Durgapur Sub-DIvision | NEW SERVICE CONNECTION FOR KRISHNARAMPUR PWSS PH-2. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/02869/2023-2024 | BP-2023-24-607 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.94 | 0 | 0
5145 | Central Mechanical | Durgapur Sub-DIvision | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0
5146 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KRISHNARAMPUR Water Supply Scheme [ Block- GALSI-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000797/2023-2024 | 4085/CMD | 29/08/2023 | 30 | BENGAL CONSTRUCTION. | 40.47 | 0 | 96
5147 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BELENDA, JAMNA, PIPLON & PARGUNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000689/2023-2024 | 4388/BWD | 05/10/2023 | 667 | AKASH CONSTRUCTION | 2296.4 | 0 | 50
5148 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000364/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.04 | 0 | 0
5149 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000544/2023-2024 | 4298/BWD | 29/09/2023 | 0 | Resource Division | 136.65 | 0 | 0
5150 | Central Mechanical | Kalna Sub-division | New service connection for Parguna PH-2 PWSS. | Assistant Engineer | JUNIOR ENGINEER | BILL/00088/2024-2025 | BP-2024-25-27 | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.38 | 0 | 0
5151 | Central Mechanical | Kalna Sub-division | NEW SERVICE CONNECTION FOR PURGUNA PIPED WATER SUPPLY SCHEME. | Assistant Engineer | JUNIOR ENGINEER | BILL/02830/2023-2024 | BP-2023-24-586 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.73 | 0 | 0
5152 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 20
5153 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Parguna Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000737/2023-2024 | 4047/CMD | 29/08/2023 | 30 | SINHA ELECTRICALS | 27.78 | 0 | 90
5154 | Burdwan Division | Kalna Sub-division | UTRA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Monteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000009/2023-2024 | 1698/BWD | 12/04/2023 | 365 | M/S S.S. ENTERPRISE | 487.32 | 0 | 87
5155 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000040/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 49.01 | 0 | 0
5156 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000188/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 12.47 | 0 | 0
5157 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000568/2023-2024 | 4940/BWD | 10/11/2023 | 0 | Resource Division | 39.83 | 0 | 0
5158 | Central Mechanical | Kalna Sub-division | New service connection charges for Utra PWSS TW 2 | Assistant Engineer | JUNIOR ENGINEER | BILL/00812/2023-2024 | BP-2023-24-90 | 28/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.59 | 0 | 0
5159 | Central Mechanical | Kalna Sub-division | New service connection charges for Utra PWSS TW 1 | Assistant Engineer | JUNIOR ENGINEER | BILL/00815/2023-2024 | BP-2023-24-91 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.03 | 0 | 0
5160 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0
5161 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at UTRA Water Supply Scheme [ Block- KALNA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000140/2023-2024 | 2857/CMD | 05/07/2023 | 30 | SOUNAK ENTERPRISE | 28.48 | 0 | 90
5162 | Central Mechanical | Kalna Sub-division | Continuation order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of the Assistant Engineer, under C.M.D. P.H.E. Dte. w.e.f.-01/09/2023 to 31/10/2023 [JJM Works]. | Assistant Engineer | JUNIOR ENGINEER | ORD/000851/2023-2024 | 734/CMSD-I | 29/08/2023 | 61 | SUBRATA BHADRA | 0.79 | 0 | 50
5163 | Central Mechanical | Kalna Sub-division | Supply and Delivery of standby Chlorination System for Utra PH 1 & others Water Supply Scheme under CMD, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001598/2023-2024 | 812/CMSD | 04/10/2023 | 30 | SUBRATA BHADRA | 0.9 | 0 | 100
5164 | Central Mechanical | Kalna Sub-division | Supply and Delivery of standby Chlorination System for Utra PH 2 & others Water Supply Scheme under CMD, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001599/2023-2024 | 813/CMSD | 04/10/2023 | 30 | SUBRATA BHADRA | 0.9 | 0 | 100
5165 | Central Mechanical | Kalna Sub-division | Standby Pump Motor set for Utra PH 2 Water Supply Scheme under CMD, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001662/2023-2024 | 1074/CMSD | 15/12/2023 | 12 | M/S. S.D. CONSTRUCTION | 0.84 | 0 | 100
5166 | Central Mechanical | Kalna Sub-division | Standby Pump Motor set for UTRA PH 1 water supply scheme under CMD,PHE,Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001729/2023-2024 | 1076/CMSD | 15/12/2023 | 15 | SUDIKSHA CONSTRUCTION | 0.84 | 0 | 100
5167 | Burdwan Division | Kalna Sub-division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KONRAPUR & MASGARIA Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER | ORD/000026/2023-2024 | 1765/BWD | 17/04/2023 | 365 | M/S ASHA CONSTRUCTION | 710.72 | 0 | 43
5168 | Burdwan Division | Kalna Sub-division | Providing left out FHTC at different places of Rajipur, Kansaripur village in order to declare swajal gram under the command area of Masgoria Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte | Assistant Engineer | JUNIOR ENGINEER | ORD/000712/2024-2025 | 3718/BWD | 29/10/2024 | 83 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 8.45 | 0 | 100
5169 | Burdwan Division | Kalna Sub-division | Providing left out FHTC at different places of Bachpur village in order to declare swajal gram under the command area of Masgoria Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000713/2024-2025 | 3719/BWD | 29/10/2024 | 83 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 7.57 | 0 | 80
5170 | Burdwan Division | Kalna Sub-division | Providing leftout FHTC at different places of Malatipur village in order to declare swajal gram under the command area of Masgaria Piped Water Supply Scheme within Kalna Sub Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000764/2024-2025 | 3759/BWD | 29/10/2024 | 30 | IYASIN DAFADAR | 7.8 | 0 | 100
5171 | Burdwan Division | Kalna Sub-division | Different types of balance works involve in connection with KONRAPUR (SM/13419) & MASGORIA (SM/13318) Piped water supply scheme under Purbasthali-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/001028/2024-2025 | 142/BWD | 08/01/2025 | 120 | M/S ASHA CONSTRUCTION | 65.74 | 0 | 0
5172 | Burdwan Division | Kalna Sub-division | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR MASGARIA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER | ORD/001145/2023-2024 | 1981/KSD | 09/02/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.33 | 0 | 2
5173 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000157/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.55 | 0 | 0
5174 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000472/2023-2024 | 3996/BWD | 08/09/2023 | 0 | Resource Division | 1.64 | 0 | 0
5175 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer | JUNIOR ENGINEER | RTOR000803/2023-2024 | 294/BWD | 24/01/2024 | 0 | Resource Division | 14.63 | 0 | 0
5176 | Central Mechanical | Kalna Sub-division | New service connection charges for Masgaria PWSS TW-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01428/2023-2024 | BP-2023-24-132 | 05/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.75 | 0 | 0
5177 | Central Mechanical | Kalna Sub-division | New service connection charges for Masgaria PWSS TW-2 | Assistant Engineer | JUNIOR ENGINEER | BILL/01467/2023-2024 | BP-2023-24-165 | 26/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.2 | 0 | 0
5178 | Central Mechanical | Kalna Sub-division | Addl quotation for New service connection charges for Masgaria PWSS TW-1 | Assistant Engineer | JUNIOR ENGINEER | BILL/01729/2023-2024 | BP-2023-24-240 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.44 | 0 | 0
5179 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at MASGARIA Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000357/2023-2024 | 3505/CMD | 31/07/2023 | 30 | M/S. SWAPAN BANERJEE | 21.55 | 0 | 95
5180 | Central Mechanical | Kalna Sub-division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0
5181 | Central Mechanical | Kalna Sub-division | Supply and delivery of different Electro-mechanical items (for urgent FHTC) for masgaria Water Supply Scheme PH 2 (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/001668/2023-2024 | 07/CMSD | 02/01/2024 | 10 | DIPALI CONSTRUCTION | 0.92 | 0 | 100
5182 | Central Mechanical | Kalna Sub-division | Supply and delivery of submersible pumping machinery (for urgent FHTC) for masgaria Water Supply Scheme PH 2 (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman | Assistant Engineer | JUNIOR ENGINEER | ORD/001673/2023-2024 | 67/CMSD | 11/01/2024 | 12 | DIPALI CONSTRUCTION | 0.85 | 0 | 100
5183 | Central Mechanical | Kalna Sub-division | Emergency installation (for urgent FHTC) at Masgaria Water Supply Scheme PH 2 (part-3) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001677/2023-2024 | 84/CMSD | 15/01/2024 | 12 | DIPALI CONSTRUCTION | 0.8 | 0 | 100
5184 | Durgapur W/S Division | Durgapur Sub-DIvision | Acceptance cum Formal Work Order for Additional Distribution Pipeline work at CHAK RADHAMOHANPUR Piped Water Supply Scheme (Chak Radhamohanpur Muslimpara and Chak Radhamohanpur Hatchery Para) with LDS & FHTC work under Ausgram-II Block, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000146/2024-2025 | 1381/DWSD | 26/09/2024 | 101 | HAMID SK | 18.67 | 0 | 100
5185 | Burdwan Division | Durgapur Sub-DIvision | CHAK RADHAMOHANPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000677/2022-2023 | 453/BWD | 06/02/2023 | 240 | HAMID SK | 122.63 | 0 | 100
5186 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000079/2022-2023 | 1266/BWD | 17/03/2023 | 0 | Resource Division | 3.1 | 0 | 0
5187 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000097/2022-2023 | 1635/BWD | 06/04/2023 | 0 | Resource Division | 16.63 | 0 | 0
5188 | Burdwan Division | Durgapur Sub-DIvision | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | RTOR000593/2023-2024 | 4901/BWD | 10/11/2023 | 0 | Resource Division | 34.12 | 0 | 0
5189 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Chak Radhamohanpur PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00759/2023-2024 | BP-2023-24-59 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.13 | 0 | 0
5190 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Chak Radhamohanpur PWSS TW-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00764/2023-2024 | BP-2023-24-62 | 18/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.09 | 0 | 0
5191 | Central Mechanical | Durgapur Sub-DIvision | Addl. Quotation for new electric service connection at Chak Radhamohanpur PH NO.-2 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/01757/2023-2024 | BP-2023-24-265 | 11/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.76 | 0 | 0
5192 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chak Radhamohanpur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000040/2023-2024 | 2492/CMD | 01/06/2023 | 30 | MS DAS ELECTRIC CO | 27.73 | 0 | 40
5193 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOHAGRAM, KHERUA & JABAGRAM Piped Water Supply Scheme under Mangalkote Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000697/2022-2023 | 582/BWD | 17/02/2023 | 1049 | PUSPA ENTERPRISE | 1185.88 | 0 | 75
5194 | Burdwan Division | Central Mechanical Sub-Division | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001301/2024-2025 | 936/BWD | 11/03/2025 | 180 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0
5195 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000059/2022-2023 | 1245/BWD | 17/03/2023 | 0 | Resource Division | 9.37 | 0 | 0
5196 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000099/2022-2023 | 1639/BWD | 06/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
5197 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000706/2023-2024 | 5045/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
5198 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges of Kherua W/S Scheme TW-1 | Assistant Engineer | Junior Engineer | BILL/00688/2023-2024 | BP-2023-24-33 | 26/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.59 | 0 | 0
5199 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Kherua PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01263/2023-2024 | BP-2023-24-124 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.67 | 0 | 0
5200 | Central Mechanical | Central Mechanical Sub-Division | Additional quotation for New service connection charges for Kherua PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/01348/2023-2024 | BP-2023-24-128 | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.03 | 0 | 0
5201 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHERUA Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000047/2023-2024 | 2510/CMD | 02/06/2023 | 30 | GOENKA ENTERPRISE | 26.97 | 0 | 100
5202 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
5203 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of JOTRAGHAB Piped Water Supply Scheme at Jotraghab & Radhaballabbati Mouza), Jamalpur Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000058/2022-2023 | 2239/BWD | 02/05/2022 | 45 | MAJUMDER ENTERPRISE | 54.07 | 0 | 1
5204 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of JOTRAGHAB Piped Water Supply Scheme at (JOTKRISHTAI) Mouza under Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000486/2022-2023 | 4007/BWD | 15/09/2022 | 30 | PAL CONSTRUCTION | 13.87 | 0 | 1
5205 | Burdwan Division | Burdwan Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of JOTRAGHAB Piped Water Supply Scheme at (JOTRAGHAB, RADHABALLAB BATI, KHANPUR, JOTKRISHTAI) Mouza under Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000667/2022-2023 | 382/BWD | 31/01/2023 | 30 | KAUSHIK RAY | 21.55 | 0 | 100
5206 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of concrete road ,construction of valve chamber of JOTRAGHAB Piped Water Supply Scheme and its adjoining mouzas within JAMALPUR block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000850/2023-2024 | 2738/BSD | 28/11/2023 | 30 | A R TRADERS | 0.96 | 0 | 100
5207 | Burdwan Division | Burdwan Sadar Sub-Division | Quotation for payment of service connection charge on full deposit scheme of Jotraghab w/s scheme. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | VCH/000631/2022-2023 | 724/DW/22-23 | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.76 | 0 | 0
5208 | Burdwan Division | Burdwan Sadar Sub-Division | Quotation for payment of service connection charges for Augmentation of Jotraghab w/s scheme. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | VCH/000632/2022-2023 | 725/DW/22-23 | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.33 | 0 | 0
5209 | Burdwan Division | Central Mechanical Sub-Division | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEULIA, GOBARDHANPUR, KHARIJA-KASHIGRAM & UNIATATARPUR Piped Water Supply Scheme under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000477/2023-2024 | 3491/BWD | 09/08/2023 | 815 | POWER TOOLS & ENGINEERING | 1741.05 | 0 | 10
5210 | Burdwan Division | Central Mechanical Sub-Division | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. | Assistant Engineer | Junior Engineer | ORD/001080/2023-2024 | 22/KTS | 05/01/2024 | 70 | AJIT SAMANTA | 0.9 | 0 | 100
5211 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000242/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.44 | 0 | 0
5212 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000457/2023-2024 | 3981/BWD | 08/09/2023 | 0 | Resource Division | 44.04 | 0 | 0
5213 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000665/2023-2024 | 5086/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
5214 | Central Mechanical | Central Mechanical Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT DEULIA PWSS TW-1 | Assistant Engineer | Junior Engineer | BILL/00368/2024-2025 | BP-2024-25-189 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.69 | 0 | 0
5215 | Central Mechanical | Central Mechanical Sub-Division | Quotation for new service connection at Deulia PWSS TW-2. | Assistant Engineer | Junior Engineer | BILL/01188/2024-2025 | BP-2024-25-410 | 11/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.52 | 0 | 0
5216 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
5217 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DEULIA Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000821/2023-2024 | 4098/CMD | 29/08/2023 | 640 | CHOUDHURY ENTERPRISE | 28.94 | 0 | 43
5218 | Burdwan Division | Burdwan Sadar Sub-Division | TATARPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000375/2023-2024 | 2621/BWD | 06/06/2023 | 940 | RANADHIR SINHA | 359.46 | 0 | 50
5219 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 183 | SK.ASFIA | 2.4 | 0 | 70
5220 | Burdwan Division | Burdwan Sadar Sub-Division | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for TATARPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001116/2024-2025 | 479/BWD | 24/01/2025 | 90 | RANADHIR SINHA | 74.75 | 0 | 0
5221 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000330/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.1 | 0 | 0
5222 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000470/2023-2024 | 3994/BWD | 08/09/2023 | 0 | Resource Division | 12.51 | 0 | 0
5223 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | RTOR000696/2023-2024 | 5059/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0
5224 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Tatarpur PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01761/2023-2024 | BP-2023-24-271 | 15/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 38.7 | 0 | 0
5225 | Central Mechanical | Burdwan Sadar Sub-Division | New Service connection for Tatarpur W/S Scheme PH No.-II | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | BILL/01792/2023-2024 | BP-2023-24-309 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.61 | 0 | 0
5226 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Tatarpur Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000466/2023-2024 | 3723/CMD | 08/08/2023 | 30 | M.S. ENTERPRISE | 30.11 | 0 | 95
5227 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation for the work of Supply of one No. Diesel Driven Car ( other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub- Division, PHE Dte. (Period from 01-07-2025 to 31-08-2025). | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000168/2025-2026 | 158/RWS | 30/06/2025 | 62 | MD HASIN | 0.8 | 0 | 0
5228 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation for the work of Supply of one No. Diesel Driven Car ( other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub- Division, PHE Dte. (Period from 01-09-2025 to 31-10-2025). | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000598/2025-2026 | 197/RWS | 01/09/2025 | 61 | MD HASIN | 0.8 | 0 | 0
5229 | Burdwan Division | Burdwan Sadar Sub-Division | Land demarcation and preparation of sketch map for Haldi, Sultanpur, Berugram & Karail Piped W/S. Scheme (New Scheme) at different Blocks under JJM under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000756/2023-2024 | 842/AE/HQ | 01/11/2023 | 15 | M/S S. CHOUDHURY | 0.33 | 0 | 100
5230 | Burdwan Division | Burdwan Sadar Sub-Division | HALDI Single Village Scheme with sinking of Tube-well & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000759/2023-2024 | 4734/BWD | 03/11/2023 | 456 | ANIRUDDHA FARUQUE | 50.21 | 0 | 90
5231 | Burdwan Division | Burdwan Sadar Sub-Division | HALDI Single Village Scheme with Rising main, LDS and FHTC work under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001090/2023-2024 | 1120/BWD | 14/03/2024 | 382 | ANIRUDDHA FARUQUE | 64.85 | 0 | 75
5232 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000001/2023-2024 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 4.69 | 0 | 0
5233 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000272/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.03 | 0 | 0
5234 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000790/2023-2024 | 332/BWD | 24/01/2024 | 0 | Resource Division | 21.17 | 0 | 0
5235 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection for HALDI PWSS TW 1. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02444/2023-2024 | BP-2023-24-523 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0
5236 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR HALDI PWSS | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/02835/2023-2024 | BP-2023-24-591 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.5 | 0 | 0
5237 | Central Mechanical | Burdwan Sadar Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0
5238 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Haldi Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000653/2023-2024 | 3996/CMD | 29/08/2023 | 30 | C.M. ENTERPRISE | 28.9 | 0 | 95
5239 | Burdwan Division | Central Mechanical Sub-Division | KUNDA Piped Water Supply Scheme with balance LDS and FHTC at Kunda village, J.L No- 74 under Mongolkote Block, District:- Purba-Bardhaman. [NEW SCHEME]. | Assistant Engineer | Junior Engineer | ORD/000095/2023-2024 | 2232/BWD | 16/05/2023 | 90 | ASMA ENTERPRISE | 32.47 | 0 | 35
5240 | Burdwan Division | Central Mechanical Sub-Division | KUNDA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at Brahmapur, Jartha village (J.L No -76, 75) under Mongolkote Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | Junior Engineer | ORD/000775/2022-2023 | 1341/BWD | 22/03/2023 | 90 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 57.05 | 0 | 60
5241 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000116/2023-2024 | 1965/BWD | 26/04/2023 | 0 | Resource Division | 1.64 | 0 | 0
5242 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000148/2023-2024 | 2155/BWD | 10/05/2023 | 0 | Resource Division | 12.34 | 0 | 0
5243 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000813/2023-2024 | 302/BWD | 24/01/2024 | 0 | Resource Division | 14.25 | 0 | 0
5244 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges of Kunda W/S Scheme TW-1 | Assistant Engineer | Junior Engineer | BILL/00689/2023-2024 | BP-2023-24-34 | 26/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.56 | 0 | 0
5245 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at KUNDA Water Supply Scheme [Block - MANGALKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000056/2023-2024 | 2518/CMD | 02/06/2023 | 30 | M/S. S.R. ENTERPRISE | 21.04 | 0 | 40
5246 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0
5247 | Burdwan Division |  | Extension of pipeline with FHTC for CHHOTOBAINAN Piped Water Supply Scheme (Akina (P), Pahalanpur, Dakshin Gopalpur, Bajekumarpur, Binodpur, Momrejpur village) within Raina II Block under Burdwan Division, PHE. Dte. |  |  | ORD/000032/2022-2023 | 2163/BWD | 26/04/2022 | 45 | BRINDABAN KONAR | 71.69 | 0 | 1
5248 | Burdwan Division |  | Sinking of additional 250 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for CHHOTOBAINAN Piped Water Supply Scheme, Block - Raina - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. |  |  | ORD/000055/2022-2023 | 2233/BWD | 29/04/2022 | 30 | J. K. CORPORATION | 10.76 | 0 | 1
5249 | Burdwan Division |  | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ II Block under Burdwan Division, PHE. Dte. |  |  | ORD/000390/2021-2022 | 269/BWD | 14/01/2022 | 30 | PRONAB KUMAR DEY | 6.99 | 0 | 1
5250 | Burdwan Division |  | Extension of pipeline for Chhotobainan water supply scheme at Pahalanpur and Rupsara village within Raina-II Block under Burdwan Division, PHE Dte.[Gr.-C] |  |  | ORD/000418/2021-2022 | 1119/BSD | 24/08/2021 | 45 | BOSE ENTERPRISE | 4.67 | 0 | 1
5251 | Burdwan Division |  | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 3rd Tube Well Site (Baje Kumarpur) to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for Chhotobainan its Adjoining Mouza W/S Scheme, block -Raina-II within Burdwan Sub-Division, PHE Dte. Gr.B. |  |  | ORD/000469/2022-2023 | 1526/BSD | 05/09/2022 | 60 | BRINDABAN KONAR | 3.03 | 0 | 1
5252 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 424/BWD | 20/01/2022 | 0 | Resource Division | 5.5 | 0 | 0
5253 | Burdwan Division |  | Quotation of new connection charges of Chhotobainan water supply scheme under Burdwan Division, PHE Dte. [Application No.-5003481960, Ref ID-503178571], |  |  | VCH/000593/2022-2023 | 709/DW/22-23 | 21/10/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.37 | 0 | 0
5254 | Burdwan Division |  | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001013/2021-2022 |  | 21/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0
5255 | Burdwan Division |  | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001045/2021-2022 | 934/DW | 31/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0
5256 | Burdwan Division | Burdwan Sadar Sub-Division | Augmentation of RAYAN (PART-II) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan -I Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000183/2024-2025 | 2377/BWD | 25/06/2024 | 270 | MATRI ENTERPRISE | 697.52 | 0 | 0
5257 | Burdwan Division | Burdwan Sadar Sub-Division | Route Survey & Preparation of DPR for RAYAN -PART-II W/S Scheme under Burdwan-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000848/2024-2025 | 2585/BSD | 26/11/2024 | 45 | APEX ENGINEERING | 2.95 | 0 | 0
5258 | Burdwan Division | Burdwan Sadar Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | RTOR000002/2024-2025 | 4101/BWD | 25/11/2024 | 0 | Resource Division | 9.24 | 0 | 0
5259 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Aug. Rayan PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/01424/2023-2024 | BP-2023-24-151 | 05/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.11 | 0 | 0
5260 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Rayan Part - 2 Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000091/2023-2024 | 2595/CMD | 07/06/2023 | 30 | P.K. ENGINEERING | 24.2 | 0 | 0
5261 | Burdwan Division | Burdwan Sadar Sub-Division | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of RAMKRISHNAPUR Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000015/2023-2024 | 1730/BWD | 13/04/2023 | 60 | SUPRIYA RAY | 40.13 | 0 | 45
5262 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of switch rooms & Rising main at different TW site for RAMKRISHNAPUR Piped Water Supply Scheme under Raina - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000664/2023-2024 | 4163/BWD | 20/09/2023 | 469 | LAKSHMIKANTA DAS | 8.93 | 0 | 100
5263 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, Making and Erection of Sign Board for SAJAL GRAM in Khemta Village, Raina - I Block within Ramkrishnapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000798/2023-2024 | 877/AE/HQ | 07/11/2023 | 30 | PAPRI HAZRA | 0.76 | 0 | 100
5264 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of 3.60 mtr x 3.0 mtr size Pump House cum chlorine room with sanitary and water supply arrangement at to departmental drawing for RAMKRISHNAPUR Water Supply Scheme within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000805/2023-2024 | 4821/BWD | 08/11/2023 | 60 | SK BADIUZZAMAL | 4.32 | 0 | 0
5265 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Ramkrishnapur PWSS under Raina-I Development Block under Burdwan Division, P.H.E Dte (2nd Call) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001224/2023-2024 | 2972/BSD | 20/12/2023 | 15 | GEO-SOLUTION | 0.78 | 0 | 100
5266 | Central Mechanical | Burdwan Sadar Sub-Division | NEW SERVICE CONNECTION FOR RAMKRISHNAPUR (AUGMENTATION) PWSS TW 03 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | BILL/00119/2024-2025 | BP-2024-25-57 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.52 | 0 | 0
5267 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Ramkrishnapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000099/2023-2024 | 2599/CMD | 07/06/2023 | 680 | SOUVIK HALDER | 10.42 | 0 | 90
5268 | Burdwan Division | Durgapur Sub-DIvision | Source Augmentation of BHALKI Zone-I & Zone-II Piped Water Supply Scheme [Tube Well, Pump House, Boundary Wall, Rising Main, FHTC, etc.], Block-Ausgram-II, Dist.- Purba Bardhaman, under Burdwan Division P.H.E. Dte. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/000104/2023-2024 | 2273/BWD | 18/05/2023 | 713 | S.R. ENTERPRISE | 92.2 | 0 | 40
5269 | Burdwan Division | Durgapur Sub-DIvision | Aug. of BHALKI ZONE-I Piped Water Supply Scheme with Rising Main & Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation at Headwork TW site under Ausgram-II Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001014/2023-2024 | 474/BWD | 05/02/2024 | 510 | SK AFJAL RAHAMAN | 114.56 | 0 | 25
5270 | Burdwan Division | Durgapur Sub-DIvision | Aug. of BHALKI ZONE-II Piped Water Supply Scheme with Rising Main & Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation at Headwork TW site under Ausgram-II Block, District:- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001022/2023-2024 | 568/BWD | 08/02/2024 | 360 | SK ABDUL LALAN | 74.12 | 0 | 0
5271 | Central Mechanical | Durgapur Sub-DIvision | New service connection charges for Bhalki PWSS TW-1 | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00786/2024-2025 | BP-2024-25-298 | 17/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.63 | 0 | 0
5272 | Central Mechanical | Durgapur Sub-DIvision | Quotation for new service connection at Bhalki Zone-I/Zone-II, Aug-1. PWSS | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | BILL/00897/2024-2025 | BP-2024-25-337 | 04/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.77 | 0 | 0
5273 | Central Mechanical | Durgapur Sub-DIvision | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of BHALKI (ZONE-I & II) [AUSGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER | ORD/001088/2023-2024 | 4510/CMD | 06/10/2023 | 726 | C.M. ENTERPRISE | 24.42 | 0 | 50
5274 | Burdwan Division | Central Mechanical Sub-Division | GOPKHANJI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer | ORD/000741/2022-2023 | 1134/BWD | 13/03/2023 | 871 | POWER TOOLS & ENGINEERING | 482.85 | 0 | 74
5275 | Burdwan Division | Central Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000094/2022-2023 | 1962/BWD | 25/04/2023 | 0 | Resource Division | 37.55 | 0 | 0
5276 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Gopkhanji W/S Scheme TW-1 | Assistant Engineer | Junior Engineer | BILL/00696/2023-2024 | BP-2023-24-39 | 27/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.65 | 0 | 0
5277 | Central Mechanical | Central Mechanical Sub-Division | New service connection charges for Gopkhanji PWSS TW-2 | Assistant Engineer | Junior Engineer | BILL/00822/2023-2024 | BP-2023-24-100 | 03/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.87 | 0 | 0
5278 | Central Mechanical | Central Mechanical Sub-Division | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Assistant Engineer | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0
5279 | Central Mechanical | Central Mechanical Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GOPKHANJI Water Supply Scheme [ Block- KATWA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000127/2023-2024 | 2660/CMD | 16/06/2023 | 30 | JYOTY SOLAR POWER. | 26.98 | 0 | 100
5280 | Central Mechanical | Central Mechanical Sub-Division | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer | Junior Engineer | ORD/000564/2024-2025 | 3103/CMD | 11/12/2024 | 60 | S DUTTA | 15.06 | 0 | 0
5281 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Boundary wall at Head Works Site of LOHAI Water Supply scheme under RAINA-II Block of Burdwan Division, PHE Dte. (Length -190.00 Mtr, Col-60 Nos). | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000078/2023-2024 | 2053/BWD | 04/05/2023 | 60 | S. MITRA & CO. | 20.43 | 0 | 0
5282 | Burdwan Division | Burdwan Sadar Sub-Division | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of LOHAI Piped Water Supply Scheme within Raina II Block of Burdwan Sub-Division under Burdwan Division, PHE Dte._2ND CALL | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000149/2023-2024 | 2422/BWD | 30/05/2023 | 30 | JAI MAA DURGA & CO. | 19.37 | 0 | 50
5283 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Lohai PWSS under Raina-II Development Block under Burdwan Division, P.H.E Dte (2nd Call) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/001225/2023-2024 | 2973/BSD | 20/12/2023 | 15 | MEASURE LAND | 0.78 | 0 | 100
5284 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Lohai Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000086/2023-2024 | 2592/CMD | 07/06/2023 | 30 | SOUVIK HALDER | 11.36 | 0 | 0
5285 | Central Mechanical | Burdwan Sadar Sub-Division | Making illumination arrangement and mise works at LOHAI water supply scheme RAINA-II BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER | ORD/000471/2024-2025 | 2953/CMD | 20/11/2024 | 60 | M/S GHOSH ENTERPRISE | 9.84 | 0 | 60
5286 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000181/2024-2025 | 2296/BWD | 20/06/2024 | 616 | M/S DATTA ENTERPRISE | 579.85 | 0 | 2
5287 | Burdwan Division | Kalna Sub-division | Work order for "Route Survey & Preparation of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-I (Zone-1A) (SM/15571) under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-6) | Assistant Engineer |  | ORD/001139/2023-2024 | 2081/KSD | 29/02/2024 | 45 | APEX ENGINEERING | 2.23 | 0 | 100
5288 | Burdwan Division | Kalna Sub-division | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 51
5289 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000516/2023-2024 | 3970/BWD | 08/09/2023 | 0 | Resource Division | 18.33 | 0 | 0
5290 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000761/2023-2024 | 202/BWD | 10/01/2024 | 0 | Resource Division | 6.16 | 0 | 0
5291 | Central Mechanical | Kalna Sub-division | Quotation for meter shifting at Purbasthali PWSS PH 1. | Assistant Engineer |  | BILL/00935/2024-2025 | BP-2024-25-409 | 11/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.05 | 0 | 0
5292 | Central Mechanical | Kalna Sub-division | Supply and installation of disinfection arrangement (Gaseous Chlorination) and other works at different OHR sites of Aug. of Purbasthali Surface Water Based PWSS Zone-I under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Assistant Engineer |  | ORD/000008/2025-2026 | 1031/CMD | 25/04/2025 | 30 | EASTERN INDIA SALES & SERVICE | 147.66 | 0 | 0
5293 | Burdwan Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Ruppur Piped Water Supply Scheme at Ruppur Village (6 Nos. habitations), Biswambharpur Village & Dhuluk Village (6 Nos. habitations) Jamalpur Block under Burdwan Division, PHE Dte. |  |  | ORD/000041/2021-2022 | 3446/BWD | 29/06/2021 | 60 | NATIONAL CONSTRUCTION | 87.06 | 0 | 1
5294 | Burdwan Division |  | Extensionof pipe linefor providing functional house hold tap connection at Ruppur village(Habitation)of RUPPUR Piped Water Supply Scheme Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte".Gr.B. |  |  | ORD/000474/2021-2022 | 275/BSD | 15/02/2022 | 30 | SAMANTA CONSTRUCTION | 4.82 | 0 | 1
5295 | Burdwan Division | Kalna Sub-division | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000181/2024-2025 | 2296/BWD | 20/06/2024 | 616 | M/S DATTA ENTERPRISE | 579.85 | 0 | 2
5296 | Burdwan Division | Kalna Sub-division | Work Order for "Route Survey & Preparation of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-IV (Zone-IV B) (SM/16307) under Kalna Sub-Division under Burdwan Division, PHE Dte." Sl-3 | Assistant Engineer |  | ORD/001136/2023-2024 | 2071/KSD | 29/02/2024 | 45 | APEX ENGINEERING | 2.53 | 0 | 100
5297 | Burdwan Division | Kalna Sub-division | Work order for "Route Survey & Preparation of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-IV (Zone-IV A) (SM/16307) under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-5) | Assistant Engineer |  | ORD/001138/2023-2024 | 2080/KSD | 29/02/2024 | 45 | APEX ENGINEERING | 2.27 | 0 | 100
5298 | Burdwan Division | Kalna Sub-division | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 51
5299 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000518/2023-2024 | 3968/BWD | 08/09/2023 | 0 | Resource Division | 28.36 | 0 | 0
5300 | Burdwan Division | Kalna Sub-division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000764/2023-2024 | 203/BWD | 10/01/2024 | 0 | Resource Division | 6.16 | 0 | 0
5301 | Burdwan Division | Kalna Sub-division | Augmentation of RAHATPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Purbasthali - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000084/2023-2024 | 2114/BWD | 10/05/2023 | 60 | BARDHAMAN AQUA ENGINEERING | 18.67 | 0 | 100
5302 | Burdwan Division | Kalna Sub-division | Different Types of work involved in connection with Augmentation of RAHATPUR (SM/16306) & LAKSHMANPUR (SM/13493) Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER | ORD/000176/2024-2025 | 2069/BWD | 07/06/2024 | 240 | SAIKAT RAY | 213.73 | 0 | 2
5303 | Central Mechanical | Kalna Sub-division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of RAHATPUR[PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER | ORD/001083/2023-2024 | 4474/CMD | 05/10/2023 | 580 | S.K. ELECTRICALS | 23.71 | 0 | 100
5304 | Burdwan Division | Burdwan Sadar Sub-Division | Preparation and Submission of DPR for Augmentation of Gobindapur PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000366/2023-2024 | 1529/BSD | 17/07/2023 | 15 | CARTO | 0.78 | 0 | 100
5305 | Burdwan Division | Burdwan Sadar Sub-Division | Designing, making and erection of Sign Board for SWAJAL GRAM in Ichhabacha village of Memari-I Block under Gobindapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos Board) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000473/2025-2026 | 2338/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0
5306 | Burdwan Division | Burdwan Sadar Sub-Division | Extension of PVC water supply line for GOBINDAPUR and its adjoining Mouza W/S Scheme, Block-Memari-I within Burdwan Sub-Division, PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000623/2023-2024 | 3920/BWD | 05/09/2023 | 938 | J K CORPORATION | 27.92 | 0 | 98
5307 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 4 at Augmentation of GOBINDAPUR Water Supply Scheme [BLOCK- MEMARI-I] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer,JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001610/2023-2024 | 1538/CMD | 05/03/2024 | 60 | BEHERA ENTERPRISE | 12.33 | 0 | 0
5308 | Burdwan Division | Burdwan Sadar Sub-Division | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17 (Size 3.60 mtr x 3.00 mtr room) for TALIT its Adjoining Mouza W/S Scheme, Block -Bardhaman-I within Burdwan Sub-Division, PHE Dte. (Mouza- TALIT) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000838/2022-2023 | 500/BSD | 21/03/2023 | 45 | MAHAKE CONTRACTOR & GENERAL ORDER SUPPLIERS | 3.16 | 0 | 100
5309 | Burdwan Division | Burdwan Sadar Sub-Division | Continuation for the work of Supply of one No. Diesel Driven Car (other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. (Period from 01-03-2025 to 30-04-2025) | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001236/2024-2025 | 68/RWS | 28/02/2025 | 61 | MD HASIN | 0.8 | 0 | 0
5310 | Burdwan Division | Burdwan Sadar Sub-Division | Balance Work for extension of pipe lines to provide FHTC With Sinking of Tub well , Construction of pump house with Boundary wall & other related work for TALIT-SIMDAL (SM/18112), NABABHAT (SM-15166) and DEWANDIGHI-MIRJAPUR (SM/09494) PWSS under Burdwan Sub-Div., Block -Bwn-1, under Burdwan Division PHE Dte. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/001248/2024-2025 | 793/BWD | 03/03/2025 | 120 | M/S S.S. ENTERPRISE | 227.66 | 0 | 0
5311 | Central Mechanical | Burdwan Sadar Sub-Division | New service connection charges for Aug. Talit-Simdal PWSS TW-3 | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | BILL/00758/2023-2024 | BP-2023-24-58 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.36 | 0 | 0
5312 | Central Mechanical | Burdwan Sadar Sub-Division | Illumination arrangement & different electro-mechanical works at TALIT SIMDAL water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000480/2024-2025 | 2957/CMD | 20/11/2024 | 60 | SUDIKSHA CONSTRUCTION | 17.91 | 0 | 0
5313 | Central Mechanical | Burdwan Sadar Sub-Division | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of TALIT SIMDAL( Part-B)[BURDWAN-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer | ORD/000570/2023-2024 | 3900/CMD | 18/08/2023 | 30 | CINZANO | 22.41 | 0 | 100
5314 | Burdwan Division |  | Balance work of OHR, construction Concrete Road, Functional Household Tap Connection, Road restoration etc. for Nanagar PWSS, Srikhanda PWSS, under KATWA -I Block under Katwa Sub-Divn under Burdwan Division, PHE Dte. District:- Purba-Bardhaman. |  |  | ORD/000685/2024-2025 | 3655/BWD | 21/10/2024 | 120 | HAMID SK | 121.69 | 0 | 0
5315 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000350/2023-2024 | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.62 | 0 | 0
5316 | Burdwan Division |  | Material Requisition To Resource Division |  |  | RTOR000561/2023-2024 | 4935/BWD | 10/11/2023 | 0 | Resource Division | 56.21 | 0 | 0
5317 | Central Mechanical |  | NEW SERVICE CONNECTION FOR NANAGAR PWSS TW-2 |  |  | BILL/00130/2024-2025 | BP-2024-25-59 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.11 | 0 | 0
5318 | Central Mechanical |  | Second time additional quotation for Nanagar PWSS TW-1 |  |  | BILL/00665/2024-2025 | BP-2024-25-267 | 20/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.34 | 0 | 0
5319 | Central Mechanical |  | New service connection for NANAGAR PWSS PH-1. |  |  | BILL/02285/2023-2024 | BP-2023-24-416 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.83 | 0 | 0
5320 | Central Mechanical |  | ADDITIONAL QUOTATION NEW SERVICE CONNECTION FOR NANAGAR PWSS TW -1. |  |  | BILL/03104/2023-2024 | BP-2023-24-644 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.02 | 0 | 0
5321 | Central Mechanical |  | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman |  |  | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0
Total | [10 empty] | 558292.93 | 3689.91