## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Nadia Arsenic Division I |  | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Muragachha Zone I Part II at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Division I PHE Dte. |  |  | ORD/000016/2021-2022 | 781/NAD-I | 05/05/2021 | 60 | MONDAL ENTERPRISE | 89.68 | 133.41 | 100
2 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Radhakantapur, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Radhakantapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000013/2021-2022 | 778/NAD-I | 05/05/2021 | 60 | M/S R.K. ENTERPRISE | 97.1 | 188.25 | 100
3 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Gayeshpur Zone I at Santipur Block by retrofitting of Ground Water based PWSS for Gayeshpur Water Supply Scheme under Nadia Arsenic Division I PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000017/2021-2022 | 782/NAD-I | 05/05/2021 | 60 | APURBA MANDAL | 96.99 | 186.81 | 100
4 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000009/2021-2022 | 773/NAD-I | 04/05/2021 | 60 | H I ENTERPRISE | 95.74 | 0 | 100
5 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.¿ (Sl. No. 02) |  |  | ORD/000129/2020-2021 | 96/NAD-I | 13/01/2021 | 60 | GHOSH ENTERPRISE | 79.67 | 156.3 | 100
6 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Balance Portion of Zone-XI, (Birohi), at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000126/2020-2021 | 95/NAD-I/20-21 | 13/01/2021 | 60 | TAPU SAHA | 75.09 | 137.67 | 100
7 | Nadia Division | Krishnanagar Sub-Division | Providing additional FHTC in connection with Surface based WSS (Northern Sector) Part-III , Zone I within Krishnagar II & Nabadwip (Part) Block (Phase-A) | Assistant Engineer |  | ORD/000049/2023-2024 | 490/KSD | 25/04/2023 | 15 | TARUN KUMAR BHATTACHARYA | 0.96 | 0 | 90
8 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-I, within Krishnagar-II & Nabadwip Block (Phase-A, Retrofitting) | Assistant Engineer |  | ORD/000394/2020-2021 | 770/ND | 10/02/2021 | 90 | TARUN KUMAR BHATTACHARYA | 97.09 | 0 | 0
9 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar & Nabadwip (Part) Block (Phase-A). | Assistant Engineer |  | VCH/000514/2021-2022 | 163/PFMS | 07/09/2021 | 0 | TARUN KUMAR BHATTACHARYA | 93.03 | 0 | 0
10 | Nadia Division | Krishnanagar Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-III, Z-I, WITHIN KRISHNAGAR AND NABADWIP BLOCK , PHASE-A. | Assistant Engineer |  | VCH/000878/2021-2022 | 501/PFMS | 03/02/2022 | 0 | M/S R. DUTTA & CO. | 0.45 | 0 | 0
11 | Nadia Division | Debgram Sub-Division | Schedule for laying of pipe line and allied work upto Kaliganj BDO office under Zone-V of Surface Water Based Water Supply Scheme, Nadia District Northern Sector (Part-I) under Debagram Sub Division P.H.E Dte. | Assistant Engineer |  | ORD/000063/2022-2023 | 175/D/DSD | 18/04/2022 | 30 | TARUN KUMAR BHATTACHARYA | 2.22 | 2.05 | 0
12 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX within Kaliganj Block (Phase-B) | Assistant Engineer |  | ORD/000090/2021-2022 | 2767/ND | 14/07/2021 | 90 | M/S K.P. CONSTRUCTION | 91.11 | 80.29 | 0
13 | Nadia Division | Debgram Sub-Division | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Maidanpur ii) Kulgachhi iii) Monipota iv) Habibpur v) Magurkhali. | Assistant Engineer |  | ORD/000480/2022-2023 | 372/ Kly SD-I | 17/03/2023 | 184 | HORIZEN | 4.99 | 1.7 | 10
14 | Nadia Division | Debgram Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
15 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.5) | Assistant Engineer |  | ORD/000467/2020-2021 | 970/ND | 25/02/2021 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 97 | 0 | 100
16 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000093/2022-2023 | 4281/ND | 29/09/2022 | 0 | Resource Division | 12.5 | 0 | 0
17 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.5) | Assistant Engineer |  | VCH/000744/2021-2022 | 412/PFMS | 21/12/2021 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 89.1 | 0 | 0
18 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II, Z-VI, WITHIN NAKASHIPARA BLOCK, PHASE-B. | Assistant Engineer |  | VCH/000881/2021-2022 | 494/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.73 | 0 | 0
19 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bahadurpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000017/2020-2021 | 1058/NACD-II | 25/09/2020 | 15 | AMARENDRA NATH PANDAY | 4.99 | 0 | 0
20 | Nadia Arsenic Civil Division II |  | Work Order for the work of "Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bagakhali Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte." |  |  | ORD/000012/2020-2021 | 1053/NACD-II | 25/09/2020 | 15 | M/S TARUN GHOSH & CO. | 5 | 0 | 0
21 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Tarapur Ground Based Water Supply Scheme under Ranaghat-I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Retrofitting under JJM of Tarapur (Part-I) Piped W/S Scheme (sl.no.14) | Assistant Engineer-I | Junior Engineer-I | ORD/000052/2023-2024 | 1429/NAD-I | 24/05/2023 | 15 | SAORSA | 13.03 | 0 | 100
22 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000066/2021-2022 | 1420/NAD-I | 08/11/2021 | 60 | CHAKRABORTTI ENTERPRISE | 68.76 | 59.6 | 100
23 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall & other allied works at 2nd Tubewell site of Ground water based piped supply scheme of Tarapur under Nadia Arsenic Division-I,P.H.E. Dte. Length of Boundary wall - 57 metre. | Assistant Engineer-I | Junior Engineer-I | ORD/000132/2021-2022 | 75/NAD-I | 17/01/2022 | 20 | M/S S.K ENTERPRISE | 6.9 | 6.47 | 100
24 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-I | RTOR000011/2021-2022 | 144/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
25 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukhilnara, Zone-I Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Ukhilnara, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000047/2021-2022 | 1404NAD-I | 08/11/2021 | 60 | UNICON INDIA | 77.99 | 61.09 | 100
26 | Nadia Arsenic Division I | Nadia Arsenic Division I | Collection of Water Sample form different water supply scheme for testing at laboratory through collection to be engaged through agency under Nadia Arsenic Division- I PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000268/2022-2023 | 191/AE-I/NAD-I | 29/07/2022 | 365 | M/S ARATI ENTERPRISE | 4.78 | 4.77 | 100
27 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Haringhata & Chakdah Zone-XIII (Digha), Part-II at Haringhata Block by retrofitting of Ground Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000097/2021-2022 | 1566/NAD-I | 13/12/2021 | 90 | SATYABRATA CHAKRABORTY | 132.3 | 122.27 | 100
28 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division - I, P.H.E. Dte. for the period from 15.07.2022 to 14.07.2023 i.e. for 1(one) year. | Assistant Engineer-I | Junior Engineer-II | ORD/000255/2022-2023 | 172 / AE-I / NAD -I | 14/07/2022 | 365 | SUMAN CHAKRABORTY | 4.8 | 2.66 | 75
29 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of Existing structure and other allied works under Zone-XIII (Digha) Part-II under Surface Based PWSS for Haringhata & Chakdah(Part) under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (sl.01) | Assistant Engineer-I | Junior Engineer-II | ORD/000262/2022-2023 | 829 / NAD-I | 31/03/2023 | 15 | TARUN KUMAR BHATTACHARYA | 13.23 | 13.21 | 90
30 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division - I, P.H.E. Dte. for the period from 15.07.2020 to 14.07.2021 i.e. for 1(one) year. | Assistant Engineer-I | Junior Engineer-II | ORD/000446/2020-2021 | 155 / AE-I / NAD-I | 14/07/2020 | 365 | SUMAN CHAKRABORTY | 2.25 | 2.25 | 100
31 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II (Joykrishnapur) at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000127/2021-2022 | 52/NAD-I | 11/01/2022 | 90 | GHOSH ENTERPRISE | 270 | 247.17 | 100
32 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000003/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 25.02 | 0 | 0
33 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Teinpur Zone-II W/S scheme in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000275/2021-2022 | 5687/ND | 03/11/2021 | 90 | MALI CONSTRUCTION | 67.51 | 6.3 | 100
34 | Nadia Division | RWS Nadia Sub-Division | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H.E. Dte., Kalyani, Nadia. Period of work 01-03-2022 to 28-02-2023 | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000814/2021-2022 | 118/RSD | 28/02/2022 | 250 | SUMAN CHAKRABORTY | 3.85 | 0 | 75
35 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Karimpur- II Block | RTOR000033/2021-2022 | 440/ND | 31/01/2022 | 0 | Resource Division | 1.19 | 0 | 0
36 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Karimpur- II Block | RTOR000074/2021-2022 | 820/ND | 18/02/2022 | 0 | Resource Division | 3.44 | 0 | 0
37 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | VCH/001117/2021-2022 | 696/PFMS | 28/03/2022 | 0 | MALI CONSTRUCTION | 38.98 | 0 | 0
38 | Nadia Division | Ranaghat Sub-Division | Repairing of Pump house-I with sanitary arrangement under augmentation of Nutangram piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000303/2024-2025 | 1276(A)RSD | 04/10/2024 | 45 | SAGAR ENTERPRISE | 1.9 | 0 | 100
39 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Nutangram under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000389/2024-2025 | 1425/RSD | 19/11/2024 | 178 | SAGAR ENTERPRISE | 2.15 | 0 | 100
40 | Nadia Division | Ranaghat Sub-Division | Providing Functional Household Tap Connection (part) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (as required size), 15 mm dia Bib Cock etc. all complete at Natungram Water Supply Scheme at Hanskhali Block in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000673/2021-2022 | 696/ND | 15/02/2022 | 90 | M/S DIPAK ENTERPRISE | 68.56 | 16.75 | 99
41 | Nadia Division | Ranaghat Sub-Division | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Nutangram to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000705/2024-2025 | 136/ND | 08/01/2025 | 180 | APURBA MANDAL | 160.04 | 0 | 0
42 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000017/2023-2024 | 1862/ND | 26/04/2023 | 0 | Resource Division | 17.96 | 0 | 0
43 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000044/2022-2023 | 4314/ND | 29/09/2022 | 0 | Resource Division | 5.42 | 0 | 0
44 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000049/2021-2022 | 443/ND | 31/01/2022 | 0 | Resource Division | 0.6 | 0 | 0
45 | Nadia Division | Ranaghat Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | VCH/000140/2022-2023 | 03/PFMS | 26/04/2022 | 0 | M/S DIPAK ENTERPRISE | 0.16 | 0 | 0
46 | Nadia Division | Ranaghat Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district under Nadia division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | VCH/001128/2021-2022 | 714/PFMS | 30/03/2022 | 0 | M/S DIPAK ENTERPRISE | 50 | 0 | 0
47 | Nadia Division | Ranaghat Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | VCH/001264/2021-2022 | 730/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.76 | 0 | 0
48 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under NUTANGRAM ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. SM/09572 | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000186/2025-2026 | 1123/EMD | 04/06/2025 | 90 | SHRESTHA | 17.48 | 0 | 0
49 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery and installation of voltage stabilizar under Natungram W/s scheme under EMSD II PHED. Nadia | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000325/2021-2022 | 306/EMSD II | 05/05/2021 | 40 | SANKAR PROSAD DUTTA & CO. | 4.15 | 4.15 | 100
50 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/001771/2022-2023 | 1121/EMD | 16/03/2023 | 30 | M.S. ENTERPRISE | 65.68 | 5.87 | 90
51 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) & also construction of Soak Pit at Damodarkhali W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000029/2021-2022 | 522/NACD-II | 14/06/2021 | 45 | SHYAMAL SHIL | 51.46 | 40.46 | 100
52 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD and allied works at OHR site under Damodarkhali Piped Water Supply Scheme in Krishnagar-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000065/2024-2025 | 711/NACD-II | 07/06/2024 | 45 | GHOSH ENTERPRISE | 19.1 | 0 | 100
53 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Change of Media of AIRP at Damodarkhali H/W site under Damodarkhali W/S scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000093/2022-2023 | 36/AE-I/NACD-II | 02/05/2022 | 10 | RUPALI ELECTRONICS | 4.93 | 4.93 | 100
54 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000122/2024-2025 | 820/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.16 | 0 | 100
55 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or daaged line repair) & also construction of Soak Pit at Damodarkhali W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000141/2021-2022 | 569/NACD-II | 14/07/2021 | 45 | SHYAMAL SHIL | 6.11 | 6.11 | 100
56 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Damodarkhali W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000193/2021-2022 | 985/NACD-II | 27/12/2021 | 90 | SUPRITI ENTERPRISE | 111.19 | 111.18 | 100
57 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Arsenic cum Iron treatment Plant of Damodarkhali PWSS (Capacity- 56 m3/hr) and ancillary works of Baruihuda W/S Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000328/2023-2024 | 37/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.41 | 0 | 100
58 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | RTOR000004/2021-2022 | 955/NACD-II | 14/12/2021 | 0 | Resource Division | 64.9 | 0 | 0
59 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | OUTSTANDING BILL PAYMENT FOR SUPPLY OF MATERIALS FOR THANAPARA, DAMODARKHALI, MADHABPUR, BALIADANGA AS FRAMED BY RESOURCE DIVISION PHE DTE. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000643/2021-2022 |  | 05/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0
60 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUPPLY OF MATERIALS FOR THANAPARA,DAMODARKHALI,MADHABPUR AND BALIADANGA W/S. SCHEME UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000646/2021-2022 |  | 07/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0
61 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Outstanding as framed by Resource Division for supply of materials for augmentation/retrofitting of Thanapara, Damodarkhali & Madhabpur under Nadia Arsenic Civil Division-II, PHE dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000718/2021-2022 | 212, 213, 214 | 18/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 124.39 | 0 | 0
62 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | RESOURCE PAYMENT DAMODARKHALI | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000888/2021-2022 | 257 | 26/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 20.38 | 0 | 0
63 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | RESOURCE PAYMENT DAMODARKHALI | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000889/2021-2022 | 256 | 26/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 33.72 | 0 | 0
64 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at Digha, Birpur , sarbari & Patpukur villeges under zone VIII , Part-II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000066/2022-2023 | 309/DSD | 27/07/2022 | 30 | MONDAL PRECISION PRIVATE LIMITED | 4.78 | 3.06 | 0
65 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at Birpur Patpukur Teghari villeges under zone VIII , Part-II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000067/2022-2023 | 310/DSD | 27/07/2022 | 30 | MONDAL PRECISION PRIVATE LIMITED | 4.77 | 3.09 | 0
66 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at Birpur Petuabhanga & Digha villeges under zone VIII , Part-II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000068/2022-2023 | 311/DSD | 27/07/2022 | 30 | MONDAL PRECISION PRIVATE LIMITED | 4.84 | 3.42 | 0
67 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at Sarbari & Digha villeges under zone VIII , Part-II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000069/2022-2023 | 312/DSD | 27/07/2022 | 30 | MONDAL PRECISION PRIVATE LIMITED | 4.85 | 1.95 | 0
68 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- VII/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000313/2023-2024 | 4282/ND | 21/09/2023 | 624 | SATYABRATA CHAKRABORTY | 397.18 | 0 | 14
69 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000355/2023-2024 | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 0 | 19
70 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 50
71 | Nadia Division | Debgram Sub-Division | Providing Functional Household Tap Connection (FHTC) at Surface Water based Water Supply Scheme (Northern Sector) Part-II,Zone-VIII within Nakashipara Block(Phase-C) | Assistant Engineer |  | ORD/000418/2021-2022 | 7315/ND | 21/12/2021 | 90 | MONDAL PRECISION PRIVATE LIMITED | 180.04 | 47.52 | 100
72 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-V within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.3) | Assistant Engineer |  | ORD/000461/2020-2021 | 868/ND | 18/02/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 97.09 | 0 | 0
73 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.4) | Assistant Engineer |  | ORD/000474/2020-2021 | 888/ND | 19/02/2021 | 90 | UNICON INDIA | 96.71 | 0 | 0
74 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000084/2022-2023 | 4272/ND | 29/09/2022 | 0 | Resource Division | 24.89 | 0 | 0
75 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | Assistant Engineer |  | VCH/000337/2022-2023 | 46/PFMS | 13/06/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 72.81 | 0 | 0
76 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 50
77 | Nadia Division | Debgram Sub-Division | Providing Functional Household Tap Connection (FHTC) at Surface Water Based Water Supply Scheme (northern Sector)Part-I,Zone-VII within Kaliganj Block (Phase-C) | Assistant Engineer |  | ORD/000417/2021-2022 | 7314/ND | 21/12/2021 | 90 | ORIENT CONSTRUCTION | 180.23 | 0 | 0
78 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000030/2022-2023 | 4291/ND | 29/09/2022 | 0 | Resource Division | 24.87 | 0 | 0
79 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000176/2023-2024 | 311/ND | 15/01/2024 | 0 | Resource Division | 18.65 | 0 | 0
80 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Shyamnagar (Vill-Bishnupur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000036/2020-2021 | 1183/NACD-II | 13/11/2020 | 25 | R.M. TRADING | 4.99 | 0 | 0
81 | Nadia Division | RWS Nadia Sub-Division | Repairing of Existing Boundary Wall for 2nd Tubewell Site at Elangi Zone I water supply scheme in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000029/2024-2025 | 71/KlySD-II | 07/06/2024 | 60 | SREEMA ENTERPRISE | 2.78 | 0 | 98
82 | Nadia Division | RWS Nadia Sub-Division | Continuation of Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000050/2024-2025 | 3445/ND | 20/06/2024 | 30 | IMAGIN | 20.46 | 0 | 100
83 | Nadia Division | RWS Nadia Sub-Division | Conversion of IEP to AIRP of capacity 56 Cu.m/hr at Elangi Zone-I Water Supply Scheme within Chapra Block under Nadia Divn, PHE Dte | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000167/2024-2025 | 4822/ND | 05/09/2024 | 360 | ZEOLITE FRESH INDIA | 129.41 | 0 | 0
84 | Nadia Division | RWS Nadia Sub-Division | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000254/2024-2025 | 6305/ND | 26/09/2024 | 30 | IMAGIN | 34.21 | 0 | 100
85 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete based on actual Estimate, Proposed augmentation of Rising Main system and Providing FHTC for Elangi Zone-I Water Supply Scheme in Nadia District under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000312/2023-2024 | 4284/ND | 21/09/2023 | 630 | BALAJI UDDYOG | 204.73 | 0 | 90
86 | Nadia Division | RWS Nadia Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Elangi Zone-I Ground Based Water Supply Scheme under Chapra Block under Nadia Division P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000335/2024-2025 | 7007/ND | 26/11/2024 | 195 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 21.45 | 0 | 95
87 | Nadia Division | RWS Nadia Sub-Division | Additional Work in connection with "Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Gadigacha W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte." | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000531/2022-2023 | 218/KSD | 03/03/2023 | 30 | PAPAN ROY | 0.24 | 0.24 | 100
88 | Nadia Division | RWS Nadia Sub-Division | Repair and renovation works of R.C.C. Elevated Existing Over Head Reservoir of capacity 250 Cu.M for Elangi Zone-I Water Supply Scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000709/2023-2024 | 1299/ND | 23/02/2024 | 60 | S.S.INFRASTRUCTURE | 11.25 | 0 | 95
89 | Nadia Division | RWS Nadia Sub-Division | Repairing of Existing Boundary Wall at Head work site of Elangi Zone I water supply scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000784/2023-2024 | 1902/ND | 15/03/2024 | 45 | CHOWDHURY CONSTRUCTION | 6.8 | 0 | 70
90 | Nadia Division | RWS Nadia Sub-Division | Special repair and renovation Pump House and Allied Works at Head Work Site of Elangi Zone I water supply scheme in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000863/2023-2024 | 483/KlySD-II | 15/03/2024 | 60 | B K ENGINEERING | 3.14 | 0 | 90
91 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000001/2024-2025 | 2582/ND | 18/04/2024 | 0 | Resource Division | 22.2 | 0 | 0
92 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000019/2022-2023 | 3308/ND | 27/07/2022 | 0 | Resource Division | 5.55 | 0 | 0
93 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000020/2021-2022 | 103/ND | 06/01/2022 | 0 | Resource Division | 2.06 | 0 | 0
94 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000116/2021-2022 | 1030/ND | 03/03/2022 | 0 | Resource Division | 4.96 | 0 | 0
95 | Nadia Division | RWS Nadia Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/001052/2021-2022 | 610/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.34 | 0 | 0
96 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipment and allied works at ELANGI ZONE-II W/S Scheme Block- Chapra under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/09813] | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000145/2025-2026 | 1146/EMD | 04/06/2025 | 90 | R.N.S. TRADING | 33.06 | 0 | 0
97 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.(Zone-I) under Elangi W/S Scheme, Block-Chapra, Dist. - Nadia. NIET No.- 18 of EE//EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001752/2022-2023 | 6187/ EMD | 14/11/2022 | 30 | WESTERN ENGINEERING CO. | 7.76 | 7.76 | 100
98 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials & Soil investigation for construction of one no. 500 cum OHR of staging height 20 mtr. for augmentation of Ground Water Based Water Supply Scheme for Payradanga to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000192/2022-2023 | 4543/ND | 21/10/2022 | 1095 | AMAL DUTTA ROY, 204/1A, LINTON STREET, KOLKATTA-700014 | 504.52 | 331.95 | 96
99 | Nadia Division | Ranaghat Sub-Division | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 90 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Payradanga to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000192/2024-2025 | 5045/ND | 13/09/2024 | 540 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 237.16 | 0 | 70
100 | Nadia Division | Ranaghat Sub-Division | Balance Laying Distribution System including all complete for augmentation of Ground Water Based Water Supply Scheme for Payradanga to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000416/2023-2024 | 5223/ND | 24/11/2023 | 362 | AMAL DUTTA ROY | 128.22 | 0 | 95
101 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000028/2023-2024 | 1876/ND | 26/04/2023 | 0 | Resource Division | 5.56 | 0 | 0
102 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000061/2023-2024 | 2301/ND | 29/05/2023 | 0 | Resource Division | 22.33 | 0 | 0
103 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000106/2022-2023 | 5171/ND | 13/12/2022 | 0 | Resource Division | 13.09 | 0 | 0
104 | Nadia Division | Ranaghat Sub-Division | Providing FHTC by Augmentation of Payradanga PWSS Block: Hanskhali, District: Nadia | Assistant Engineer | Junior Engineer,Junior Engineer 3 | VCH/000351/2022-2023 | 51/PFMS | 22/06/2022 | 0 | HORIZEN | 2.78 | 0 | 0
105 | Central Drilling | Ranaghat Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Pyradanga W/S Scheme (TW-I) , Hanskhali Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000137/2023-2024 | 1236/CDD | 04/09/2023 | 270 | RAJ & ENTERPRISE | 18.7 | 0 | 100
106 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Payradanga ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. SM/10413 | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000173/2025-2026 | 1106/EMD | 04/06/2025 | 90 | A.K. ENTERPRISE | 20.79 | 0 | 0
107 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PAYRADANGA W/S Scheme, Block- Hanskhali , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/001014/2022-2023 | 502/EMD | 24/01/2023 | 30 | BARISAL TRADING CO. | 29.84 | 0 | 30
108 | Nadia Division | Tehatta Sub-Division | Construction of Arsenic-cum-Iron Removal Plant (AIRP) of 56.13 cum/Hour capacity at proposed headwork site for Augmentation of Ground Based Water Supply Scheme at Andharkota to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2024-2025 | 4480/ND | 14/08/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 189.2 | 0 | 0
109 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction Of 300 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (Excluding Pile Foundation), Pipe Connection And Cost Of Pipes, Specials & Soil Investigation all complete for Augmentation of Ground Based Water Supply Scheme at Andharkota to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000187/2022-2023 | 4466/ND | 18/10/2022 | 1460 | M/S S.S ENTERPRISE | 444.3 | 160.04 | 55
110 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House and allied works of ground based piped water supply scheme for Andherkota water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000395/2024-2025 | 7122/ND | 09/12/2024 | 450 | GHOSH CONSTRUCTION | 31.29 | 0 | 70
111 | Nadia Division | Tehatta Sub-Division | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement and consruction of Boundary wall at Head Work Site of Andherkota Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000739/2023-2024 | 1507/ND | 04/03/2024 | 360 | SADHANA CONSTRUCTION | 23.05 | 0 | 100
112 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000039/2023-2024 | 1907/ND | 27/04/2023 | 0 | Resource Division | 67.35 | 0 | 0
113 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000059/2023-2024 | 2291/ND | 29/05/2023 | 0 | Resource Division | 27.26 | 0 | 0
114 | Nadia Division | Tehatta Sub-Division | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division | Assistant Engineer | Junior Engineer | VCH/001104/2021-2022 | 674/PFMS | 24/03/2022 | 0 | RADIANT | 2.82 | 0 | 0
115 | Central Drilling | Tehatta Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 250 Mtrs. Depth) by utilising Departmental Machineries for Andharkota W/S Scheme (T/W-I) Karimpur -I Block under nadia District, CDD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000054/2023-2024 | 508/CDD | 01/06/2023 | 30 | UNIVERSAL ENTERPRISES | 18.86 | 0 | 100
116 | Eastern Mechanical | Tehatta Sub-Division | Quotation charges and security deposit for new power connection at Andharkota PH-III under Eastern Mechanical Subdivision-III, Nadia | Assistant Engineer | Junior Engineer | BILL/02246/2024-2025 | BP-175 | 13/12/2024 | 0 | WBSEDCL KARIMPUR CCC | 14.8 | 0 | 0
117 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISBATHAN W/S Scheme, Block- Karimpur-II & ANDHARKOTA W/S Scheme, Block- Karimpur-I, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/001928/2022-2023 | 1200/EMD | 22/03/2023 | 30 | KARTICK BAL | 61.1 | 0 | 70
118 | Nadia Division | RWS Nadia Sub-Division | Repairing Works (existing OHR, Pump House, Boundary wall etc.) of Madhugari Water Supply Scheme, Karimpur-I Block Under R.W.S. Nadia Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000030/2024-2025 | 3431/ND | 19/06/2024 | 360 | M/S DURGA SECURITIES & SERVICES | 22.18 | 0 | 100
119 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Madhugari to accommodate FHTC within Karimpur-I block under RWS Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000294/2022-2023 | 5334/ND | 21/12/2022 | 75 | SANJIB DEY | 74.59 | 49.08 | 60
120 | Nadia Division | RWS Nadia Sub-Division | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Madhugari PWSS within Karimpur-I Block under RWS Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000725/2023-2024 | 1254/ND | 22/02/2024 | 495 | S.S. ENTERPRISE | 19.88 | 0 | 100
121 | Nadia Division | RWS Nadia Sub-Division | Conversion of IEP to AIRP of capacity 38 Cu.m/hr at Madhugari Water Supply Scheme within Karimpur-I block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000799/2023-2024 | 1911/ND | 15/03/2024 | 600 | MONDAL PRECISION PRIVATE LIMITED | 140.38 | 0 | 65
122 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000006/2023-2024 | 1577/ND | 06/04/2023 | 0 | Resource Division | 0.41 | 0 | 0
123 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000064/2023-2024 | 2307/ND | 29/05/2023 | 0 | Resource Division | 0.62 | 0 | 0
124 | Eastern Mechanical | RWS Nadia Sub-Division | Repairing rectification of electro-mechanical works related to installation of submersible pump sets and others accessories in connection with JJM under Madhugari PWSS, Block- Karimpur-I, under EMSD-III, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000113/2024-2025 | 1220/EMSD-III | 28/06/2024 | 30 | SMILE | 2.42 | 0 | 100
125 | Eastern Mechanical | RWS Nadia Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, (Phase-II) under Madhugari ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/001772/2023-2024 | 6396/EMD | 30/10/2023 | 30 | S.P. ENTERPRISE (KOLKATA) | 16.32 | 0 | 0
126 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase -II FHTC under Jaldhara/ Jal Swapna for Dubli Z-I & II at Ranaghat -II Block by retrofitting of Ground Water Based PWSS for Dubli Water Supply scheme under Nadia Arsenic Division -I, P.H.E. Dte. (Sl. no -08) | Assistant Engineer-II | Junior Engineer-III | ORD/000010/2022-2023 | 960 / NAD-I | 07/07/2022 | 60 | BIPLAB GUHA | 55.81 | 55.44 | 85
127 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of M.S. Manifold of 1000mm thickness for improvement of Water Supply at Head Work Site under Ukhilnara Zone-I Ground Water Based Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation of Ukhilnara Zone-I W/S Scheme underJJM (sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000017/2023-2024 | 1153 /NAD-I | 28/04/2023 | 15 | GANGULY ENTERPRISE | 13.05 | 0 | 0
128 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Ukhilnara Zone-II Ground Based Water Supply Scheme under Ranaghat- I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Ukhilnara Zone-II W/S Scheme under JJM (sl.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000019/2023-2024 | 1156 /NAD-I | 28/04/2023 | 735 | K K MARKETING | 13.04 | 0 | 100
129 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 100 cum capacity and other allied works at Ukhilnara Zone-II W/S Scheme in Ranaghat -I Block under Nadia Arsenic Division -I , P.H.E.Dte. (Sl no. 17) | Assistant Engineer-II | Junior Engineer-III | ORD/000026/2022-2023 | 1320 / NAD -I | 04/08/2022 | 45 | INVENT ENGINEER'S CO - OPERATIVE SOCIETY LTD. | 11.32 | 6.45 | 100
130 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repairs and Renovation work of Arsenic cum Iron Removal Plant having Capacity 16 m3/hr including Civil Structures of Ukhilnara Zone-II W/S Sch. within Ranaghat -I Block under Nadia Arsenic Division -I , P.H.E. Dte. (SL.No. 22) | Assistant Engineer-II | Junior Engineer-III | ORD/000033/2022-2023 | 1513 / NAD-I | 26/08/2022 | 45 | SUNIL KUMAR DATTA | 7.1 | 6.78 | 100
131 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet , Pathway and all repair works at nd T/W site and other allied works at Ukhilnara Z-I W/S Scheme at Ranaghat -I Block under Nadia Arsenic Division -I, P.H.E.Dte. ( Sl. No. 23) | Assistant Engineer-II | Junior Engineer-III | ORD/000034/2022-2023 | 1514 / NAD-I | 26/08/2022 | 45 | NISHITH BANERJEE | 22.91 | 18.58 | 100
132 | Nadia Arsenic Division I | Nadia Arsenic Division I | CONSTRUCTION OF BOUNDARY WALL,TOILET ,PATHWAY AND ALL REPAIR WORKS AT 2nd T/W AND OTHER ALLIE WORKS AT DUBLI Z-II W/S SCHEME AT RANAGHAT -II BLOCK , UNDER NADIA ARSENIC DIVISION -I , P.H.E.DTE. ( SL NO.21) | Assistant Engineer-II | Junior Engineer-III | ORD/000035/2022-2023 | 1515 / NAD-I | 26/08/2022 | 45 | DAS CONSTRUCTION | 16.36 | 8.05 | 100
133 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 450 cum capacity over head reservoir and painting of all structures with repair Works & other allied works at Dubli Z-I W/S scheme in Ranaghat -II Block under Nadia Arsenic Division -I (Sl.no. 24) | Assistant Engineer-II | Junior Engineer-III | ORD/000044/2022-2023 | 1584 / NAD-I | 06/09/2022 | 45 | SATYABRATA CHAKRABORTY | 15.84 | 15.67 | 100
134 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 350 cum capacity Over Head Reservoir and Painting of all structures with repair works & other allied works at Dubli Zone -II W/S Scheme within Ranaghat -Ii Block under Nadia Arsenic Division -I, P.H.E.DTE. (Sl.no. 26) | Assistant Engineer-II | Junior Engineer-III | ORD/000047/2022-2023 | 1587 / NAD-I | 06/09/2022 | 45 | SATYABRATA CHAKRABORTY | 17.14 | 0 | 0
135 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 180 cum capacity Over Head Reservoir and painting of all structures with repair works and other allied works at Ukhilnara Zone-I W/S Scheme in Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000068/2022-2023 | 1442/NAD-I | 17/09/2022 | 45 | MONDAL ENTERPRISE | 14.98 | 14.91 | 100
136 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall Toilet Pathway and other allied works at 2nd and 3rd TW site of Dubli Zone I WS Scheme within Ranaghat II Block under NADI PHE Dte (sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000150/2022-2023 | 3328/NAD-I | 15/12/2022 | 45 | B.M. ENTERPRISE | 20.53 | 18.65 | 100
137 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation & Retrofitting work under Jal Jeevan Mission (JJM) for UKILNARA ZONE-I at Ranaghat-I Block of Ground Water based PWSS for Ukilnara Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000167/2024-2025 | 1897/NAD-I | 18/11/2024 | 300 | GANGULY ENTERPRISE | 29.52 | 0 | 0
138 | Nadia Arsenic Division I | Nadia Arsenic Division I | Improvement of AIRP for Dubli Zone-I (105 cum/hr.) W/S Scheme in connection with Augmentation of AIRP for Ground Water Based Piped Water Supply Scheme for Dubli Zone-I, under Jal Jeevan Mission at Ranaghat-II Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.14) | Assistant Engineer-II | Junior Engineer-III | ORD/000188/2023-2024 | 2151/NAD-I | 08/09/2023 | 21 | SATYABRATA CHAKRABORTY | 63.28 | 59.67 | 100
139 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting in Uzirpukuria North at Dubli Zone-I W/S Scheme under Ground Water Based PWSS for arsenic affected areas of Dubli W/S Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000200/2022-2023 | 28/AE-II/NAD-I | 10/02/2023 | 15 | BUDDHADEV MONDAL | 4.8 | 4.79 | 100
140 | Nadia Arsenic Division I | Nadia Arsenic Division I | Shifting of pipeline From Headwork site to Ukhilnara More due to widening of PWD Road under Ukhilnara Zone-I Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte (sl.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000223/2022-2023 | 106/AE-II/ NAD-I | 02/03/2023 | 15 | GANGULY ENTERPRISE | 1.86 | 1.86 | 50
141 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work from Ukhilnara More towards Payradanga Station under Ukhilnara Zone-I Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl.no. 03) | Assistant Engineer-II | Junior Engineer-III | ORD/000224/2022-2023 | 107/ AE-II/NAD-I | 02/03/2023 | 15 | GANGULY ENTERPRISE | 2.64 | 2.64 | 0
142 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC Pipeline under JJM for Ukhilnara Zone-II at Payradanga G.P. at Ranaghat-I Block of Ground Water Based PWSS for Ukhilnara Zone-II W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000270/2023-2024 | 2752/NAD-I | 11/12/2023 | 315 | GANGULY ENTERPRISE | 9.32 | 0 | 90
143 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Mistripara under Ukhilnara Zone-I Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte (sl.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000274/2022-2023 | 169 / AE-II/NAD-I | 27/03/2023 | 21 | MALI CONSTRUCTION | 2.79 | 2.33 | 100
144 | Nadia Arsenic Division I | Nadia Arsenic Division I | FHTC under Jaldhara / Jalswapna for Duttaphulia Z-II Part -II at Ranaghat-II Block by augmentation of Ground water Based PWSS for Duttaphulia Z-II W/S scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl.no. 03) | Assistant Engineer-II | Junior Engineer-III | ORD/000092/2022-2023 | 1939 /NAD-I | 12/10/2022 | 90 | M/S TARAK CHANDRA PAUL | 557.43 | 537.73 | 100
145 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Ramnagar and Duttaphulia at Hanskhali Block under Jal Jeevna Mission in connection with augmentation of Duttaphulia Zone-II W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.08) | Assistant Engineer-II | Junior Engineer-III | ORD/000186/2023-2024 | 2160/NAD-I | 11/09/2023 | 21 | MESSRS FREEDOM CONSTRUCTION | 75.74 | 0 | 100
146 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Baranbria, Srirampur, Kalupur, Kani Bamni, Bagdia Mouza inconnection with Augmentation to accommodate FHTC under JJM for Duttaphulia Zone-II Ground water based PWSS (Phase-II) Block ¿ Ranaghat-II, Dist (sl.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000241/2022-2023 | 537 / NAD-I | 13/03/2023 | 21 | M/S TARAK CHANDRA PAUL | 31.77 | 30.88 | 0
147 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000011/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 38.85 | 0 | 0
148 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Costruction of R.C.C eleveted reservoir 750 CUM all complete & Soil Investigation for Augmentation of Ground Based Water Supply Scheme at Bhaluka to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000011/2022-2023 | 1887/ND | 25/04/2022 | 1528 | M/S S.S ENTERPRISE | 786.78 | 521.26 | 80
149 | Nadia Division | Krishnanagar Sub-Division | Sinking of 1 no. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method and construction of pump house (3.6 mtr. x 3.0 mtr.) and boundary wall at 3rd tube well site for Bhaluka Water Supply Scheme under Krishnagar Sub-Division under Nadia Division, PHE Dte. (Sm/10068) | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000034/2023-2024 | 2102/ND | 15/05/2023 | 90 | B.M. ENGINEERING & CONSTRUCTION | 29.75 | 0 | 0
150 | Nadia Division | Krishnanagar Sub-Division | Construction of Additional Boundary wall and allied works at Headwork Site at Bhaluka Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000052/2025-2026 | 2289/ND | 19/05/2025 | 240 | JOYGOPAL GUPTI | 29.78 | 0 | 50
151 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of capacity 137 m3/hr at Bhaluka Water Supply Scheme within Krishnagar-I Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000191/2024-2025 | 5046/ND | 13/09/2024 | 540 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 318.54 | 0 | 70
152 | Nadia Division | Krishnanagar Sub-Division | Repair & Renovation of Pump House, Boundary wall, Store Room and allied works at 1st and 2nd Pump House at Bhaluka Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000474/2023-2024 | 152/ND | 09/01/2024 | 60 | JOYGOPAL GUPTI | 18.06 | 0 | 100
153 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000004/2022-2023 | 2160/ND | 18/05/2022 | 0 | Resource Division | 152.87 | 0 | 0
154 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000012/2022-2023 | 3306/ND | 27/07/2022 | 0 | Resource Division | 36.72 | 0 | 0
155 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000141/2021-2022 | 1388/ND | 24/03/2022 | 0 | Resource Division | 33.49 | 0 | 0
156 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | VCH/001073/2021-2022 | 636/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.5 | 0 | 0
157 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BHALUKA W/S Scheme, Block-Krishnagar-1, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000896/2022-2023 | 406/EMD | 20/01/2023 | 919 | M.S. ENTERPRISE | 29.23 | 0 | 50
158 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Raising the height of Boundary wall at H/W site and also Construction of Soak Pit at Lakshmipur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000024/2022-2023 | 03/AE-I/NACD-II | 06/04/2022 | 45 | PRABIR KUMAR ROY | 5 | 2.37 | 100
159 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Lakshmipur Water Supply Scheme in Chapra Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000069/2023-2024 | 325/1/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.11 | 0 | 100
160 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Helenchi Zone-I (Vill- Shimlibas) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000086/2021-2022 | 627/NACD-II | 10/08/2021 | 15 | M/S TARUN GHOSH & CO. | 4.51 | 4.51 | 100
161 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Lakshmipur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000096/2023-2024 | 1116/NACD-II | 06/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100
162 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Lakshmipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000125/2021-2022 | 858/NACD-II | 08/11/2021 | 45 | M/S GHOSH CONSTRUCTION | 82.39 | 82.36 | 100
163 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repairing and paitning of Overhead Reservoir and other allied works under augmentation of Lakshmipur PWSS of Chapra Block. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000203/2021-2022 | 191/AE-I/NACD-II | 29/12/2021 | 25 | PRABIR KUMAR ROY | 4.81 | 0 | 100
164 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Lakshmipur 2nd Tube Well Site under Lakshmipur Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000205/2024-2025 | 901/AE-I/NACD-II | 10/09/2024 | 210 | PARTHA DAS | 4.08 | 0 | 100
165 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Conversion of IEP to AIRP at Laksmipur Water Supply Scheme of capacity 60 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000214/2024-2025 | 1308/NACD-II | 20/09/2024 | 60 | JOY HIND TUBEWELLS | 165.22 | 0 | 0
166 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Lakshmipur (Vill- Kalyandaha, Lakshmipur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000259/2022-2023 | 1014/NACD-II | 29/11/2022 | 60 | PRABIR KUMAR ROY | 17.93 | 17.87 | 100
167 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Restoration of damaged distribution pipe line and parallel pipeline laying due to construction of PMGSY Road and Extension of Boundary Wall at Lakshmipur (Vill-Kalyandaha) Head Work Site W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000265/2022-2023 | 1020/NACD-II | 29/11/2022 | 30 | PRADIP KUMAR BANIK | 4.85 | 4.81 | 100
168 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Lakshmipur Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000306/2021-2022 | 281/AE-I/NACD-II | 04/03/2022 | 5 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.94 | 4.94 | 100
169 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Lakshmipur Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000319/2021-2022 | 303/AE-I/NACD-II | 17/03/2022 | 5 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.9 | 4.9 | 100
170 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-I,II & III within Krishnagar & Nabadwip(Part) Block (Phase-C) | Assistant Engineer |  | ORD/000282/2021-2022 | 5694/ND | 03/11/2021 | 90 | MALLICK ENTERPRISE | 86.12 | 83.6 | 0
171 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000081/2022-2023 | 4302/ND | 29/09/2022 | 0 | Resource Division | 12.75 | 0 | 0
172 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000139/2023-2024 | 293/ND | 15/01/2024 | 0 | Resource Division | 10.84 | 0 | 0
173 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000140/2023-2024 | 294/ND | 15/01/2024 | 0 | Resource Division | 20.53 | 0 | 0
174 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000141/2023-2024 | 295/ND | 15/01/2024 | 0 | Resource Division | 19.84 | 0 | 0
175 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000146/2023-2024 | 300/ND | 15/01/2024 | 0 | Resource Division | 4.4 | 0 | 0
176 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Bara Andulia(Zone-II) W/S scheme in Nadia District under Nadia Division P.H.E. Dte. [Part-A]. | Assistant Engineer | Junior Engineer 3 | ORD/000279/2021-2022 | 5691/ND | 03/11/2021 | 75 | B.M ENTERPRISE | 64.01 | 1.69 | 100
177 | Nadia Division | Krishnanagar Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
178 | Nadia Division | Krishnanagar Sub-Division | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000721/2024-2025 | 7570/ND | 27/12/2024 | 45 | IMAGIN | 19.44 | 0 | 100
179 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 3 | RTOR000077/2021-2022 | 781/ND | 18/02/2022 | 0 | Resource Division | 6.59 | 0 | 0
180 | Nadia Division | Krishnanagar Sub-Division | Providing Functional House Tap Connection from Baraandulia Zone-II Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | Assistant Engineer | Junior Engineer 3 | VCH/000923/2021-2022 | 654/PFMS | 25/02/2022 | 0 | B.M ENTERPRISE | 60 | 0 | 0
181 | Nadia Division | Krishnanagar Sub-Division | Providing Functional House Tap Connection from Baraandulia Zone-II Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | Assistant Engineer | Junior Engineer 3 | VCH/000967/2021-2022 | 575/PFMS | 04/03/2022 | 0 | B.M ENTERPRISE | 1.53 | 0 | 0
182 | Eastern Mechanical | Nadia Arsenic Civil Division II | Quotation for load enhancement and security deposit charges at PH-I of Mahespur PWSS | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/02078/2024-2025 | BP-170-24-25 | 05/12/2024 | 0 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 3.83 | 0 | 0
183 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC under Maheshpur (Source Augmentation, Maheshpur) ground water based water supply scheme under Block_ Chapra Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000032/2025-2026 | 704/EMD | 04/04/2025 | 30 | M/S DILIP MITRA | 11.4 | 0 | 0
184 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Painting works at Maheshpur Head Work site boundary wall,including road restoration work and other anciliary works at Maheshpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000022/2022-2023 | 01/AE-I/NACD-II | 06/04/2022 | 45 | TARUN GHOSH | 4.91 | 4.8 | 100
185 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Maheshpur Water Supply Scheme in Chapra Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000075/2023-2024 | 328_2/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.14 | 0 | 100
186 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Maheshpur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000098/2023-2024 | 1118/NACD-II | 06/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100
187 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Jungle cutting and Earthwork in filling at Maheshpur, Maitari and Thanarapara Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000120/2024-2025 | 818/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.76 | 0 | 100
188 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahespur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000155/2021-2022 | 881/NACD-II | 12/11/2021 | 45 | M/S ASHA CONSTRUCTION | 79.08 | 78.54 | 100
189 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Mahespur W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000158/2023-2024 | 525./AE-I/NACD-II | 18/12/2023 | 435 | RUPALI ELECTRONICS | 0.97 | 0 | 100
190 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work Order "Conversion of IEP to AIRP at Maheshpur Water Supply Scheme of capacity 53 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000281/2023-2024 | 151/NACD-II | 02/02/2024 | 415 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 157.78 | 0 | 100
191 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Maheshpur 2nd tube well Site under Maheshpur Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000329/2024-2025 | 1026/AE-I/NACD-II | 10/12/2024 | 30 | ACHARJEE & ASSOCIATES | 3.37 | 0 | 100
192 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Comprehensive augmentation in technical regards including aquifer management with extraction, compliance of Ground water contamination removal as per IS 10500 with subsequent amendments and composite RCC Cum masonry structures mouza Maheshpur under Maheshpur Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000344/2024-2025 | 1580/NACD-II | 09/12/2024 | 60 | M/S FREEDOM CONSTRUCTION | 54.01 | 0 | 60
193 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of Water Level Indicator at Maheshpur, Gongra, Madhabpur, Laxmipur, Balibanga PWSS in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000429/2024-2025 | 1192/AE-I/NACD-II | 25/02/2025 | 30 | RAJIB DUTTA | 3.83 | 0 | 0
194 | Eastern Mechanical | Nadia Arsenic Civil Division II | Load enhancement charge of Putimary P.H-I under EMSD-III, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/01851/2024-2025 | BP-160-24-25 | 14/11/2024 | 0 | W.B.S.E.D.C.L (TEHATTA CCC) | 3.06 | 0 | 0
195 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PUTIMARI(Block-Tehatt-I), NISCHINTAPUR(Block-Tehatt-I), W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000006/2023-2024 | 1504/EMD | 18/04/2023 | 30 | SRI KRISHNA NIRMAN | 10.69 | 5.24 | 80
196 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-VII under Karimpur-Jalangi ground water based water supply scheme under Block_ Karimpur-I Dist. - North 24PGS under EMD, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/002969/2023-2024 | 872/EMD | 15/03/2024 | 261 | TARUN KUMAR BHATTACHARYA | 25.34 | 0 | 100
197 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Replacement of Existing Distribution main pipeline by D.I. Pipe in the Head Work site at Puthimari Water Supply Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000003/2023-2024 | 467/NACD-II | 20/04/2023 | 30 | AMAR KRISHNA DEY | 2.82 | 2.79 | 95
198 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Putimari 2nd pump house site with Reinforced Barbed Tape , Painting ,Plaster and other allied works Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000078/2024-2025 | 167/AE-II/NACD-II | 14/06/2024 | 15 | BIPLAB KUMAR GUPTA | 0.96 | 0 | 100
199 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Putimari W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000127/2021-2022 | 861/NACD-II | 08/11/2021 | 45 | MANGES INDUSTRIAL CORPORATION. | 58.71 | 58.63 | 100
200 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD and allied works at OHR site under Puthimari Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000138/2023-2024 | 1305/NACD_II | 30/11/2023 | 30 | PRABIR KUMAR ROY | 22.3 | 0 | 95
201 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Puthimari Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Puthimari W/S Scheme in Tehatta-I Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000147/2023-2024 | 1427/NACD-II | 15/12/2023 | 20 | SIRCON ENGINEERING SERVICE | 2.67 | 0 | 100
202 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Puthimari) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000169/2023-2024 | 1298/NACD-II | 29/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
203 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Relaying of D.I. Pipeline by replacing the damaged old UPVC pipe for rising main from 1st pump house to 2nd pump house at Puthimari Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000198/2024-2025 | 314AE-II/NACD-II | 06/09/2024 | 30 | ARIT KUMAR PAL | 4.62 | 0 | 100
204 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Putimari Water Supply Scheme at Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000248/2021-2022 | 104/NACD-II | 10/02/2022 | 45 | ROY CONSTRUCTION | 10.02 | 9.96 | 100
205 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Putimari 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000260/2021-2022 | 42/AE-II/NACD-II | 17/02/2022 | 30 | SREE GURU ENTERPRISE | 4.2 | 4.16 | 100
206 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system and also dedicated pipe line including providing FHTC at left out households for Patharghata (Gobindapur, Patharghata) & Puthimari (Vill-Puthimari) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000432/2024-2025 | 247/NACD-II | 27/02/2025 | 180 | SANDIP BISWAS | 101.71 | 0 | 0
207 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000004/2024-2025 | 986/NACD-II | 23/07/2024 | 0 | Resource Division | 28.32 | 0 | 0
208 | Nadia Division | RWS Nadia Sub-Division | Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000033/2024-2025 | 3450/ND | 20/06/2024 | 45 | IMAGIN | 19.44 | 0 | 100
209 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Teinpur Zone-I to accommodate FHTC within Karimpur-II block under RWS Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000093/2022-2023 | 3380/ND | 29/07/2022 | 60 | M/S FREEDOM CONSTRUCTION | 42.67 | 26.79 | 86
210 | Nadia Division | RWS Nadia Sub-Division | Renovation and modification of AIRP (Pressure Type) & Construction of Backwash chamber for AIRP at Head Work Site in Teinpur ZONE-I PWSS under Nadia Division PHE Dte. Capacity- 15.5 cum/hr. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000551/2023-2024 | 781/ND | 05/02/2024 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 37.22 | 0 | 93
211 | Nadia Division | RWS Nadia Sub-Division | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Tenpur (Zone-I) Water Supply Scheme, Karimpur-I Block Under RWS Nadia Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000676/2023-2024 | 1175/ND | 21/02/2024 | 270 | CHOWDHURY & CO. | 25.11 | 0 | 95
212 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000023/2022-2023 | 3895/ND | 08/09/2022 | 0 | Resource Division | 16.85 | 0 | 0
213 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000072/2022-2023 | 4277/ND | 29/09/2022 | 0 | Resource Division | 1.23 | 0 | 0
214 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000107/2023-2024 | 3789/ND | 24/08/2023 | 0 | Resource Division | 1.6 | 0 | 0
215 | Nadia Division | RWS Nadia Sub-Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | VCH/000202/2022-2023 | 26/PFMS | 20/05/2022 | 0 | ENVIROTECH SOLUTIONS | 2.44 | 0 | 0
216 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/001012/2022-2023 | 500/EMD | 24/01/2023 | 30 | M/S DILIP MITRA | 64.62 | 10.18 | 85
217 | Nadia Division | RWS Nadia Sub-Division | Laying of dedicated pipeline for Pipragachhi and part of Elangi Mouza for augmentation of Elangi Water Supply Scheme in Chapra Block, Nadia under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000010/2025-2026 | 1773/ND | 21/04/2025 | 180 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 86.27 | 0 | 0
218 | Nadia Division | RWS Nadia Sub-Division | Laying Of Distribution System including Specials, Valves & Pipe Supporting Structure All Complete Based On Actual Estimate & Providing FHTC for Elangi ZONE - II Water Supply Scheme in Nadia District under Nadia Division PHE Dte.. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000702/2021-2022 | 965/ND | 28/02/2022 | 1440 | MADE & TRADE CO. | 310.84 | 73.09 | 46
219 | Nadia Division | RWS Nadia Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Elangi Zone-II PWSS under Chapra Block under Tehatta Sub- Division,P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000743/2024-2025 | 421/ND | 27/01/2025 | 360 | M/S DIPAK ENTERPRISE | 73.39 | 0 | 40
220 | Nadia Division | RWS Nadia Sub-Division | Conversion of IEP to AIRP of capacity 36 Cu.m/hr at Elangi Zone-II Water Supply Scheme within Chapra Block block under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000887/2024-2025 | 1557/ND | 28/03/2025 | 180 | APURBA MANDAL | 129.36 | 0 | 0
221 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | RTOR000053/2022-2023 | 4315/ND | 29/09/2022 | 0 | Resource Division | 2.17 | 0 | 0
222 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | RTOR000110/2023-2024 | 3791/ND | 24/08/2023 | 0 | Resource Division | 1.54 | 0 | 0
223 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | RTOR000121/2021-2022 | 1250/ND | 16/03/2022 | 0 | Resource Division | 0.86 | 0 | 0
224 | Nadia Division | RWS Nadia Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | VCH/001057/2021-2022 | 615/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.16 | 0 | 0
225 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipment and allied works at ELANGI ZONE-II W/S Scheme Block- Chapra under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/09813] | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000145/2025-2026 | 1146/EMD | 04/06/2025 | 90 | R.N.S. TRADING | 33.06 | 0 | 0
226 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under ELANGI(Zone-II) & GHORALIA (Zone-II) W/S Scheme, Block- Chapra & Shantipurrespectively , Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 05) | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/001157/2023-2024 | 1503EMD | 18/04/2023 | 30 | MA ANNAPURNA ENTERPRISE | 11.19 | 5.03 | 60
227 | Eastern Mechanical | RWS Nadia Sub-Division | Different Electro-Mechanical Extra works for completion FHTC Augmentation works at Elangi Zone-II and Ghoralia Zone-II under EMSD-III,P.H.E.Dte. Dist-Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/001504/2023-2024 | 759/EMSD-III | 24/07/2023 | 15 | MA ANNAPURNA ENTERPRISE | 0.32 | 0.32 | 100
228 | Nadia Arsenic Division I |  | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Zone IV Rukminidanga Part I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte |  |  | ORD/000020/2021-2022 | 785/NAD-I | 05/05/2021 | 60 | CHANDAN ROY | 97.05 | 181.51 | 100
229 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XIII, (Digha), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. Tender No. 204/NAD-I/2020-2021. |  |  | ORD/000169/2020-2021 | 152/NAD-I | 25/01/2021 | 60 | M/S NIBHAS SINHA | 89.4 | 175.52 | 100
230 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Automatic Chlorinator etc Augmentation to Accomodate FHTC under Digri W/S Scheme, Block- Krishnagar I , Dist. - Nadia. NIET No. 31 of EE/EMD of 2022-23 (Sl. No. 04) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/002730/2022-2023 | 1123EMD | 16/03/2023 | 30 | SOMNATH ENTERPRISE | 6.2 | 5.89 | 90
231 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repairng of FHTC work damaged due to construction work of local authorities and ancilary works at Digri Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000025/2022-2023 | 04/AE-I/NACD-II | 06/04/2022 | 45 | M/S RAJESH CONSTRUCTION | 2.3 | 2.3 | 100
232 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) & also construction of Soak Pit at Digri W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000030/2021-2022 | 523/NACD-II | 14/06/2021 | 45 | M/S GHOSH CONSTRUCTION | 52.42 | 0 | 100
233 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Change of Media of AIRP at Digri H/W site under Digri W/S scheme under Nadia Arsenic Civil Division-II P.H.E Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000092/2022-2023 | 35/AE-I/NACD-II | 02/05/2022 | 10 | RUPALI ELECTRONICS | 4.93 | 4.93 | 100
234 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnagar-I Block of Nadia District through Jadavpur University. (Name of PWSS Digri) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000093/2023-2024 | 973/NACD-II | 12/09/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100
235 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Jungle cutting and Earthwork in filling at Maheshpur, Maitari and Thanarapara Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000120/2024-2025 | 818/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.76 | 0 | 100
236 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of roof shed for AIRP room at Digri Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000122/2021-2022 | 137/AE-I/NACD-II | 28/10/2021 | 15 | M/S RAJESH CONSTRUCTION | 1.99 | 1.99 | 100
237 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Digri, (Block - Krishnagar-I) piped water supply schemes | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000153/2021-2022 | 152/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.89 | 2.89 | 100
238 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD and allied works at OHR site under Digri Piped Water Supply Scheme in Krishnagar-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000202/2023-2024 | 98/NACD-II | 22/01/2024 | 45 | M/S RAJESH CONSTRUCTION | 23.52 | 0 | 40
239 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Digri W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000213/2021-2022 | 02/NACD-II | 03/01/2022 | 45 | SOMNATH CHATTERJEE | 72.6 | 72.6 | 100
240 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Construction of roof shed for AIRP room at Digri Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000236/2021-2022 | 183/AE-I/NACD-II | 20/12/2021 | 15 | M/S RAJESH CONSTRUCTION | 1.46 | 1.46 | 100
241 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Arsenic cum Iron treatment Plant of Digri PWSS (Capacity- 75 m3/hr) and ancillary works of Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000250/2023-2024 | 220/NACD-II | 21/02/2024 | 471 | B.M. ENGINEERING & CONSTRUCTION | 125.21 | 0 | 50
242 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Digri (Vill- Pakurgachhi, Adapota Digri) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000257/2022-2023 | 1012/NACD-II | 29/11/2022 | 60 | M/S RAJESH CONSTRUCTION | 27.76 | 23.84 | 100
243 | Nadia Division | Ranaghat Sub-Division | Laying of Rising Main for Dakshinpara Zone-I W/S Scheme under JJM, Ranaghat Sub-Division, Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000141/2024-2025 | 877(A)RSD | 20/08/2024 | 15 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 2.61 | 0 | 100
244 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20 mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Dakshinpara Zone-I to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000144/2022-2023 | 4040/ND | 19/09/2022 | 900 | SHYAMAL SHIL | 112.12 | 53.44 | 97
245 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation & repair of AIRP pump house & allied works of Dakshinpara-I W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000239/2022-2023 | 463/RSD | 22/07/2022 | 30 | SREE GURU CONSTRUCATION | 2 | 0 | 100
246 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of hed work site pump house & allide works of Dakshinpara-I W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000240/2022-2023 | 463/A/RSD | 22/07/2022 | 30 | CHAYA ENTERPRISE | 2.28 | 0 | 100
247 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of pump house & allied works in the premises at pump house no-I of Dakshinpara-I W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000241/2022-2023 | 467/A/RSD | 26/07/2022 | 30 | SWARASHI CONSTRUCTION | 2.54 | 0 | 90
248 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of boundary wall & allied works in the premises at pump house no 2 of Dakshinpara-I W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000242/2022-2023 | 468/RSD | 26/07/2022 | 30 | RAJ & ENTERPRISE | 4.84 | 4.8 | 100
249 | Nadia Division | Ranaghat Sub-Division | Construction of Sludge Pond At Dakshinpara Zone-I Site for deposition of sludge from different Arsenic Removal Plants under Ranaghat Sub-Division, Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000356/2025-2026 | 4052/6091/ND | 28/08/2025 | 90 | APURBA MANDAL | 17.35 | 0 | 0
250 | Nadia Division | Ranaghat Sub-Division | Replacement of damaged & typically choked UPVC pipe line for augmentation of Ground Water Based Water Supply Scheme for Dakshinpara Zone -I PWSS of Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000377/2023-2024 | 4894/ND | 02/11/2023 | 481 | SHYAMAL SHIL | 34.58 | 0 | 96
251 | Nadia Division | Ranaghat Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Dakshinpara Zone-I PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 45.00 Cu.m/hr | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000466/2023-2024 | 133/ND | 09/01/2024 | 450 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 68.46 | 0 | 95
252 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000021/2023-2024 | 1878/ND | 26/04/2023 | 0 | Resource Division | 15.87 | 0 | 0
253 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000077/2022-2023 | 4290/ND | 29/09/2022 | 0 | Resource Division | 4.99 | 0 | 0
254 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000093/2023-2024 | 2325/ND | 29/05/2023 | 0 | Resource Division | 4.99 | 0 | 0
255 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000098/2023-2024 | 2585/ND | 13/06/2023 | 0 | Resource Division | 2.92 | 0 | 0
256 | Nadia Division | Ranaghat Sub-Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-I) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/000352/2022-2023 | 52/PFMS | 22/06/2022 | 0 | HORIZEN | 2.52 | 0 | 0
257 | Central Drilling | Ranaghat Sub-Division | : providing drilling crew and other allied works for construction of Tube well ( 300mm X200mm X 250 IVltrs. Depth) by utilising Departmental Machineries for Dakshinpara w/s scheme (Z-l' TW-l) , Hanskhali Block under Nadia District, CentraiDrilling Divlsion, P.H.E' Dte (2nd Call) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000069/2023-2024 | 1051/CDD | 16/08/2023 | 300 | MENAKA ENTERPRISE | 18.6 | 0 | 100
258 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at DAKSHINPARA (ZONE-I) W/S Scheme Block- HANSKHALI under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/10569 | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000132/2025-2026 | 1133/EMD | 04/06/2025 | 90 | MAHADEV ENTERPRISE | 36.73 | 0 | 0
259 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001008/2022-2023 | 496/EMDdt.24.01.2023 | 17/03/2023 | 656 | GLACIER ENGINEERING CO. | 66.71 | 8 | 100
260 | Eastern Mechanical | Nadia Arsenic Civil Division II | Erection of 02 nos 8mtr PCC Pole with allied works IRO Madhupur PHE I under Chapra CCC | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/02523/2023-2024 | BP-146-23-24 | 23/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.27 | 0 | 0
261 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Headworks) under Madhupur W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. NNo.- 05) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000099/2022-2023 | 5013/EMD | 03/11/2022 | 30 | M/S.A.K. BANERJEE. | 10.14 | 0 | 90
262 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Madhupur W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000100/2022-2023 | 5014/EMD | 03/11/2022 | 30 | M/S. SAJAHAN CHOWDHURY | 10.12 | 9.23 | 100
263 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Madhupur Piped Water Supply Scheme, Block: Dist. Nadia Under EMD, PHE Dte. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.-13) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000106/2022-2023 | 5020/EMD | 03/11/2022 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 41.25 | 0 | 0
264 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery of PCC Pole, M.s materials and electrical accessories including stringing and sagging of LTOH line to WBSEDCL for new service connection at PH-II under Madhupur W/S Scheme. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/002571/2022-2023 | 1137/EMSD-III | 14/08/2022 | 30 | NEW RANBEE ENGINEERING | 0.19 | 0.19 | 0
265 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply delivery of PCC Pole, MS materials and electrical accessories and installation of DTR including strings and sagging of HTOH line to WBSEDCL for new service connection at PH-I under Madhupur W/S scheme under EMSD-III | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/002988/2022-2023 | 1230EMD | 14/08/2022 | 30 | NEW RANBEE ENGINEERING | 4.03 | 0 | 100
266 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Madhupur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000002/2022-2023 | 211/NACD-II | 05/04/2022 | 60 | AMARENDRA NATH PANDAY | 5.38 | 5.33 | 100
267 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Madhupur and Sikra Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000020/2022-2023 | 245/NACD-II | 19/04/2022 | 60 | JOY HIND TUBEWELLS | 41.88 | 0 | 100
268 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Madhupur water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000035/2022-2023 | 22/AE-I/NACD-II | 13/04/2022 | 60 | AMARENDRA NATH PANDAY | 2.83 | 2.81 | 100
269 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Madhupur Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000039/2022-2023 | 26/AE-I/NACD-II | 13/04/2022 | 60 | AMARENDRA NATH PANDAY | 3.95 | 0 | 90
270 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Chapra Block of Nadia District through Jadavpur University. (Name of Scheme Madhupur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000052/2023-2024 | 857/NACD-II | 08/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
271 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction for priliminary work of the approch road at Head Works site of Madhupur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000077/2023-2024 | 416/AE-I/NACD-II | 08/08/2023 | 15 | B.D. COSNTRUCTION | 0.86 | 0 | 0
272 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Madhupur and adjoining mouzas under Madhupur Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000100/2022-2023 | 349/NACD-II | 08/06/2022 | 90 | M/S. DIVINE | 148.51 | 125.91 | 85
273 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earthwork in filling in ditches at Madhupur Water Supply Scheme at Madhupur H/W site under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000122/2022-2023 | 113/AE-I/NACD-II | 28/06/2022 | 30 | JOY HIND TUBEWELLS | 4.84 | 0 | 100
274 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 35 cum/Hour capacity for Madhupur Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000167/2024-2025 | 1146/NACD-II | 23/08/2024 | 180 | MAMATA USHA ENTERPRISE | 164.41 | 0 | 0
275 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Madhupur Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000192/2022-2023 | 622/NACD-II | 06/09/2022 | 20 | MAKALI ENGINEERING CORPORATION | 3.62 | 3.62 | 100
276 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Khaspu W/s Scheme, Madhupur W/s Scheme, Maniknagar W/s Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000299/2021-2022 | 251/AE-I/NACD-II | 25/02/2022 | 15 | G. MITRA & ASSOCIATES | 2.29 | 2.29 | 100
277 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Madhupur Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000316/2022-2023 | 80/NACD-II | 10/01/2023 | 60 | NIVEDITA CONSTRUCTION | 15.8 | 0 | 100
278 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Madhupur 2nd Tubewell site within Madhupur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000341/2022-2023 | 144/NACD-II | 17/01/2023 | 60 | GANGULY ENTERPRISE | 4.8 | 4.67 | 85
279 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Madhupur water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000380/2022-2023 | 382/NACD-II | 24/03/2023 | 1073 | SUBHASH BOSE | 119.12 | 0 | 76
280 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | RTOR000008/2022-2023 | 397/NACD-II | 04/07/2022 | 0 | Resource Division | 27.35 | 0 | 0
281 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000235/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
282 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000342/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
283 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair, Renovation of Haringhata WTP (including 500 cum Back Wash OHR) and Intake with different units and Boundary Wall of WTP under Surface W/S Scheme Haringhata-Chakdah (Part) under Nadia Arsenic Division-I PHE Dte (Sl.no. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000122/2022-2023 | 1908 / NAD-I | 29/09/2022 | 60 | TARUN KUMAR BHATTACHARYA | 55.33 | 55.13 | 100
284 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Darrappur, Zone-V under Surface W/S Scheme of Haringhata-Chakdah (Part) under NAD I PHE Dte (Sl.no. 13) | Assistant Engineer-I | Junior Engineer-I | ORD/000146/2022-2023 | 3217/ NAD-I | 30/11/2022 | 45 | CHANDAN ROY | 14.38 | 14.34 | 100
285 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V (Darrappur) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 10) | Assistant Engineer-I | Junior Engineer-I | ORD/000159/2021-2022 | 426/NAD-I | 07/03/2022 | 60 | NATIONAL CONSTRUCTION | 93.56 | 66.37 | 100
286 | Nadia Division | Krishnanagar Sub-Division | Sinking of 1 no. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method and construction of pump house (3.6 mtr. x 3.0 mtr.) and boundary wall at 3rd tube well site for Dignagar water supply scheme under Krishnagar Sub-Division under Nadia Division, PHE Dte. (Sm/10019) | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000033/2023-2024 | 2101/ND | 15/05/2023 | 504 | JOY HIND TUBEWELL'S | 29.87 | 0 | 100
287 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 700 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials. and Soil investigation for construction of one new 700 CUM OHR for Augmentation of Ground Based Water Supply Scheme at Dignagar to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000071/2022-2023 | 1648/ND | 06/04/2022 | 1001 | TARUN KUMAR BHATTACHARYA | 923.7 | 313.87 | 53
288 | Nadia Division | Krishnanagar Sub-Division | Continuation of Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-08-2023 to 31-01-2024= 184 days. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000257/2023-2024 | 736/RSD | 28/07/2023 | 184 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 3.22 | 0 | 100
289 | Nadia Division | Krishnanagar Sub-Division | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Dignagar Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000502/2023-2024 | 5559/ND | 12/12/2023 | 60 | DEY ENTERPRISE | 12.15 | 0 | 100
290 | Nadia Division | Krishnanagar Sub-Division | Conversion of IEP to AIRP of capacity 132 Cu.m/hr at Dignagar Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000795/2023-2024 | 1907/ND | 15/03/2024 | 360 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 208.9 | 0 | 50
291 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000022/2021-2022 | 377/ND | 27/01/2022 | 0 | Resource Division | 32.97 | 0 | 0
292 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000023/2021-2022 | 379/ND | 27/01/2022 | 0 | Resource Division | 50.46 | 0 | 0
293 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000036/2022-2023 | 4311/ND | 29/09/2022 | 0 | Resource Division | 35.85 | 0 | 0
294 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000143/2021-2022 | 1391/ND | 24/03/2022 | 0 | Resource Division | 32.81 | 0 | 0
295 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | Assistant Engineer | Junior Engineer,Junior Engineer 3 | VCH/001074/2021-2022 | 637/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.38 | 0 | 0
296 | Eastern Mechanical | Krishnanagar Sub-Division | WBSEDCL's Quotation for New Service Connection charges to the newly constructed Pump House - III of Dignagar W/S Scheme in Krishnagar-I Block, Dist- Nadia. (Application No. 3004728299) | Assistant Engineer | Junior Engineer,Junior Engineer 3 | BILL/00727/2024-2025 | BP-50-24-25 | 21/06/2024 | 0 | W.B.S.E.D.C.LTD (DIGNAGAR C.C.C) | 8.4 | 0 | 0
297 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at Dignagar W/S Scheme Block- Krishnanagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/10019 | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000138/2025-2026 | 1139/EMD | 04/06/2025 | 90 | INDIA ENTERPRISE | 51.72 | 0 | 0
298 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DIGNAGAR W/S Scheme, Block-Krishnagar-I , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 10) | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000902/2022-2023 | 412/EMD | 20/01/2023 | 758 | M/S GHOSH ENTERPRISE | 16.13 | 0 | 80
299 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block ( Phase -B) | Assistant Engineer |  | ORD/000281/2020-2021 | 241/ND | 15/01/2021 | 90 | TARUN KUMAR BHATTACHARYA | 96.72 | 17.64 | 0
300 | Nadia Division | Debgram Sub-Division | Construction of OHR, repair and renovation of staff room, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-I / A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. [SM/11836]. | Assistant Engineer |  | ORD/000430/2023-2024 | 5556/ND | 12/12/2023 | 1094 | M/S DIPAK ENTERPRISE, GHOSH PARA,WARD NO-4, KALYANI, NADIA-741235 WEST BENGAL | 150.28 | 0 | 5
301 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000092/2022-2023 | 4305/ND | 29/09/2022 | 0 | Resource Division | 12.6 | 0 | 0
302 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000066/2021-2022 |  | 12/04/2021 | 0 | TARUN KUMAR BHATTACHARYA | 41.39 | 0 | 0
303 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME NORTHERN SECTOR PART-2, ZONE-1 WITHIN NAKASHIPARA BLOCK PHASE-B | Assistant Engineer |  | VCH/000195/2021-2022 | 74/PPMS | 15/07/2021 | 0 | TARUN KUMAR BHATTACHARYA | 41.39 | 0 | 0
304 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000486/2021-2022 | 283/PFMS | 08/10/2021 | 0 | TARUN KUMAR BHATTACHARYA | 31.7 | 0 | 0
305 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VI Part A & Karimpur Jalangi Zone-VI Part B to accommodate FHTC and Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 200 CUM OHR for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VI Part B for Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VI (A&B) under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000091/2023-2024 | 3028/ND | 14/07/2023 | 366 | BALAJI UDDYOG, 153/2B, A.P.C. ROAD, 1ST FLOOR, KOLKATA- 700006. | 520.9 | 31.64 | 55
306 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Karimpur Jalangi Zone-VI water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000312/2024-2025 | 6839/ND | 12/11/2024 | 450 | MS MAA BHABANI ENTERPRISE | 31.29 | 0 | 50
307 | Nadia Division | Tehatta Sub-Division | Laying of additional pipe lines and allied works to increase the functionality in Brojonathpur, Gandhina villages under Karimpur-I Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000328/2025-2026 | 4685/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 46.3 | 0 | 40
308 | Nadia Division | Tehatta Sub-Division | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000329/2025-2026 | .4686/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 79.19 | 0 | 40
309 | Nadia Division | Tehatta Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-6 (I&II) W/S Scheme in Karimpur-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000400/2021-2022 | 315/TSD | 24/11/2021 | 30 | RADIANT | 4.54 | 4.54 | 100
310 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000042/2023-2024 | 1901/ND | 27/04/2023 | 0 | Resource Division | 60.25 | 0 | 0
311 | Central Drilling | Tehatta Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300 mm x 200 mm x 250Mtrs. Depth) by utilising Departmental machineries for Karimpur jalangi W/S Scheme (Z-VI TW-I & II) Karimpur-I Block under Nadia District CDD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000040/2023-2024 | 98/CDD | 17/04/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 37.28 | 0 | 100
312 | Eastern Mechanical | Tehatta Sub-Division | Quotation charges for new service connection and security deposit at Karimpur Jalangi (Zone-VI,B) PH-I under EMSD-III,Nadia | Assistant Engineer | Junior Engineer | BILL/02244/2024-2025 | BP-180 | 13/12/2024 | 0 | WBSEDCL KARIMPUR CCC | 10.19 | 0 | 0
313 | Eastern Mechanical | Tehatta Sub-Division | Quotation for new service connection and security deposit for Karimpur Jalangi Zone- 6, Part- B (H/W site) | Assistant Engineer | Junior Engineer | BILL/02314/2024-2025 | BP-196-24-25 | 17/12/2024 | 0 | WBSEDCL KARIMPUR CCC | 15.95 | 0 | 0
314 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI(Z-6) W/S Scheme, Block- Karimpur I, & KAMALPUR (Z-II) W/S Scheme, Block-Ranaghat II, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/001925/2022-2023 | 1197/EMD | 22/03/2023 | 30 | P.K. ENGINEERING | 48.95 | 0 | 0
315 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 214.69 | 47
316 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
317 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 3A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000770/2021-2022 | 120/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.63 | 4.6 | 100
318 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 1 | RTOR000116/2022-2023 | 103/ND | 05/01/2023 | 0 | Resource Division | 240.03 | 0 | 0
319 | Nadia Division | Debgram Sub-Division | Restoration of T 09 - Barabigha to fakir Danga to Arbetai under Package no. WB 14-ADB37. | Assistant Engineer |  | BILL/00448/2024-2025 | 261/PFMS | 26/09/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 14.21 | 0 | 0
320 | Nadia Division | Debgram Sub-Division | RESTORATION OF L071-BTHUADHRI PHE TO DAFADR PARA (BIL KUMARI) under Package No. WB/14/227 | Assistant Engineer |  | BILL/00512/2024-2025 | 303/PFMS | 02/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 17.55 | 0 | 0
321 | Nadia Division | Debgram Sub-Division | Restoration of Muragacha Ghosh Para to Dharmada Hospital via Mirpur Kachkuli under (RIDF XXVIII) | Assistant Engineer |  | BILL/00532/2024-2025 | 320/PFMS | 05/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 16.91 | 0 | 0
322 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
323 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 50
324 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
325 | Nadia Division | Debgram Sub-Division | Construction of OHR, staff room, chlorine room, service road, boundary wall and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-VI / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/12374]. | Assistant Engineer |  | ORD/000479/2023-2024 | 211/ND | 10/01/2024 | 730 | SARKAR CONSTRUCTION | 348.98 | 0 | 10
326 | Nadia Division | Debgram Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
327 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 6/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000801/2021-2022 | 151/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.51 | 4.51 | 100
328 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000143/2022-2023 | 100/ND | 05/01/2023 | 0 | Resource Division | 358.26 | 0 | 0
329 | Nadia Division | Debgram Sub-Division | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000165/2025-2026 | 3260/ND | 10/07/2025 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 5
330 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
331 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 50
332 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
333 | Nadia Division | Debgram Sub-Division | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-IV / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11841]. | Assistant Engineer |  | ORD/000454/2023-2024 | 6152/ND | 26/12/2023 | 1093 | SATYABRATA CHAKRABORTY | 233.13 | 0 | 5
334 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 4B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000793/2021-2022 | 143/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.63 | 3.91 | 100
335 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000122/2023-2024 | 242/ND | 11/01/2024 | 0 | Resource Division | 12.52 | 0 | 0
336 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000137/2022-2023 | 123/ND | 05/01/2023 | 0 | Resource Division | 114.87 | 0 | 0
337 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-II within Kaliganj block(Phase-B) in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000180/2020-2021 | 3587/ND | 08/12/2020 | 90 | TARUN KUMAR BHATTACHARYA | 96.83 | 86.71 | 0
338 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTOR PART-1 Z-2 | Assistant Engineer |  | VCH/001077/2020-2021 | 460/DW | 30/03/2021 | 0 | TARUN KUMAR BHATTACHARYA | 46.42 | 0 | 0
339 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-IV, within Krishnagar-II & Nabadwip Block (Phase-D, Retrofitting)" | Assistant Engineer |  | ORD/000403/2020-2021 | 779/ND | 10/02/2021 | 90 | MAHABIR PUMPS MFG PVT. LTD. | 97.11 | 23.08 | 0
340 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000166/2023-2024 | 301/ND | 15/01/2024 | 0 | Resource Division | 2.48 | 0 | 0
341 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) | Assistant Engineer |  | VCH/000519/2021-2022 | 180/PFMS | 15/09/2021 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 79.37 | 0 | 0
342 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II, Nabadwip (Part) Block (Phase-D) | Assistant Engineer |  | VCH/001009/2020-2021 |  | 25/03/2021 | 0 | MAHABIR PUMPS MFG PVT. LTD. | 11.54 | 0 | 0
343 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection for PH No.-I under Jitpur Tehatta Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00004/2022-2023 | 90/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.91 | 0 | 0
344 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection for PH No.-II under Jitpur Tehatta Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00005/2022-2023 | 89/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.2 | 0 | 0
345 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Jitpur W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000442/2022-2023 | 6259/EMD | 14/08/2022 | 30 | S.P. ENTERPRISE | 9.86 | 9.02 | 90
346 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Jitpur W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No.- 21 of EE/EMD of 2022-23 (Sl. No.- 07) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000706/2022-2023 | 6491/EMD | 30/11/2022 | 30 | RMD TRADING | 9.97 | 8.99 | 100
347 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery of PCC Pole, M.s materials and electrical accessories including stringing and sagging of LTOH line to WBSEDCL for new service connection at PH-II under Jitpur W/S Scheme. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/002572/2022-2023 | 1365/EMSD-III | 14/08/2022 | 30 | S.P. ENTERPRISE (SILIGURI) | 0.39 | 0.39 | 0
348 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply delivery of PCC Pole materials and electrical accessories and installation DTR including sagging of HTOH line to WBSEDCL for new service connection at PH-I under Jitpur W/S Scheme. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/002821/2022-2023 | 262/EMSD-III | 28/02/2023 | 30 | R.M.D. TRADING | 3.47 | 3.47 | 80
349 | Eastern Mechanical | Nadia Arsenic Civil Division II | New connection charges for Jitpur PHE I Tehatta Nadia. Memo no. 3004031024/Quot/03 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/003373/2022-2023 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.91 | 0 | 0
350 | Eastern Mechanical | Nadia Arsenic Civil Division II | New connection charges for Jitpur PHE I Tehatta Nadia. Memo no. 3004031067/Quot/03 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/003375/2022-2023 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.2 | 0 | 0
351 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Jitpur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000012/2022-2023 | 217/NACD-II | 05/04/2022 | 60 | R.M. TRADING | 5.38 | 5.37 | 100
352 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Jitpur and Suruppur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000018/2022-2023 | 243/NACD-II | 19/04/2022 | 60 | B.M. ENGINEERING & CONSTRUCTION | 42.4 | 38.59 | 100
353 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pathway at Jitpur 2nd tube well site within Jitpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000035/2023-2024 | 392./AE-I/NACD-II | 31/07/2023 | 45 | SREE GURU ENTERPRISE | 4.22 | 0 | 100
354 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Jitpur water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000048/2022-2023 | 15/AE-II/NACD-II | 11/04/2022 | 60 | R.M. TRADING | 2.83 | 2.81 | 100
355 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Jitpur ( Vill- Chalk Jaliapara) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000055/2024-2025 | 164_AE-II/NACD-II | 14/06/2024 | 15 | SUPRIO MAJUMDER | 0.96 | 0 | 100
356 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Jitpur Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000058/2022-2023 | 19/AE-II/NACD-II | 18/04/2022 | 30 | SANJIT DAS | 4.98 | 4.92 | 85
357 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Jitpur and adjoining mouzas under Jitpur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000067/2022-2023 | 297/NACD-II | 19/05/2022 | 90 | USHA CONSTRUCTION | 134.8 | 0 | 100
358 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University (Name of PWSS Jitpur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000116/2023-2024 | 1155/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
359 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Jitpur ( Vill- Chalk Jaliapara, Khaspara) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000145/2024-2025 | 247/AE-II/NACD-II | 31/07/2024 | 15 | SUBHASIS MOJUMDER | 0.99 | 0 | 100
360 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 34 cum/Hour capacity for Jitpur Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000169/2024-2025 | 1116/NACD-II | 16/08/2024 | 180 | DEBAPRASAD MONDAL | 163.12 | 0 | 0
361 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Jitpur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000196/2022-2023 | 625/NACD-II | 06/09/2022 | 20 | RAMASISH ENTERPRISE | 4.44 | 4.44 | 100
362 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Bhagakhali Zone-I & Jitpur Water Supply Scheme of capacity 27 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000289/2023-2024 | 196/NACD-II | 12/02/2024 | 781 | SANDIP BISWAS | 103.73 | 0 | 100
363 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Jitpur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000320/2022-2023 | 84/NACD-II | 10/01/2023 | 60 | BABLU MALLICK | 21.46 | 16.78 | 85
364 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Jitpur 2nd Tubwell Site within Jitpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000330/2022-2023 | 123/NACD-II | 11/01/2023 | 60 | SOURAV & CO. | 6.62 | 5.77 | 85
365 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) , Jitpur , Taranipur & Dhopahat W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000346/2024-2025 | 1627/NACD-II | 19/12/2024 | 540 | M.R. CONSTRUCTION | 117.87 | 0 | 40
366 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Jitpur water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000376/2022-2023 | 369/NACD-II | 23/03/2023 | 729 | B.M. ENGINEERING & CONSTRUCTION | 117.24 | 30 | 100
367 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Special repair of pipe line laying with casing pipe at Jitpur W/s Scheme within Tehatta-I Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000399/2024-2025 | 408/AE-II/NACD-II | 31/01/2025 | 45 | SUPRIO MAJUMDER | 0.77 | 0 | 100
368 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | RTOR000004/2022-2023 | 408/NACD-II | 04/07/2022 | 0 | Resource Division | 44.15 | 0 | 0
369 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000237/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
370 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000344/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
371 | Nadia Division | Ranaghat Sub-Division | Construction of 120.00 Cum/Hr capacity Arsenic-cum-Iron Removal plant at Bagula Zone-II Water Supply Scheme under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000078/2024-2025 | 4124/ND | 29/07/2024 | 540 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 296.58 | 0 | 70
372 | Nadia Division | Ranaghat Sub-Division | Repairing of Pump house-I with sanitary arrangement under augmentation of Bagula Zone-II piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000204/2024-2025 | 1140/RSD | 11/09/2024 | 45 | MUKHERJEE CONSTRUCTION | 1.9 | 0 | 90
373 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, construction of 550 cum capacity 20 mtr. Staging height RCC over head reservoir (including pile foundation), pipe connection and cost of pipes, specials and soil investigation for construction of one no. 550 cum OHR of staging height 20 mtr. for augmentation of Ground Water Based Water Supply Scheme for BAGULA Zone-II to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000205/2023-2024 | 3540/ND | 11/08/2023 | 731 | AMAL DUTTA ROY | 565.73 | 0 | 55
374 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Bagula Zone-II under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000378/2024-2025 | 1413/RSD | 19/11/2024 | 45 | J & T ENTERPRISE | 2.15 | 0 | 100
375 | Nadia Division | Ranaghat Sub-Division | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Bagula Zone-II Water Supply Scheme Under Ranaghat Sub-Division PHE Dte.) | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000398/2023-2024 | 5188/ND | 22/11/2023 | 90 | M/S S.K. ENTERPRISE | 6.88 | 0 | 0
376 | Nadia Division | Ranaghat Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
377 | Nadia Division | Ranaghat Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Bagula Zone-II W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000446/2021-2022 | 1066/RSD | 02/12/2021 | 30 | HORIZEN | 3.01 | 2.91 | 100
378 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000010/2024-2025 | 7558/ND | 27/12/2024 | 0 | Resource Division | 3.66 | 0 | 0
379 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000020/2023-2024 | 1865/ND | 26/04/2023 | 0 | Resource Division | 12.06 | 0 | 0
380 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000138/2023-2024 | 256/ND | 11/01/2024 | 0 | Resource Division | 25.16 | 0 | 0
381 | Central Drilling | Ranaghat Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Bagula (Z-II) PWSS W/S Scheme (TW-I) ,Hanskhali Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000141/2023-2024 | 1661/CDD | 17/10/2023 | 30 | RAJ & ENTERPRISE | 18.71 | 0 | 0
382 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augomentation in connection to Accommodate FHTC at Pump House No.-II under Bagula Zone-II ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000013/2024-2025 | 1305/EMD | 09/05/2024 | 448 | ANUPAMA ENGINEERING WORKS | 9.26 | 0 | 0
383 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Dubli Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Dubli Zone-I W/S Scheme under JJM (sl.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000018/2023-2024 | 1154 / NAD-I | 28/04/2023 | 15 | BUDDHADEV MONDAL | 13.02 | 0 | 100
384 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Arranghata Zone-II Ground Based Water Supply Scheme under Ranaghat- II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Arranghata Zone- II (Phase-I) under JJM (sl.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000020/2023-2024 | 1157/NAD-I | 28/04/2023 | 728 | BISWAS CONSTRUCTION | 13.01 | 0 | 100
385 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Dubli Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Dubli Zone-II W/S Scheme under JJM (sl.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000021/2023-2024 | 1155 / NAD-I | 28/04/2023 | 15 | BISWAS ENTERPRISE | 13.04 | 12.33 | 100
386 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying dedicated pipeline to supply water for Sabdalpur and Hosenpur under Jal Jeevan Mission (JJM) at Ranaghat-II Block of Sabdalpur Ground Water Based PWSS for under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | Assistant Engineer-II | Junior Engineer-III | ORD/000021/2025-2026 | 133/NAD-I | 22/04/2025 | 60 | MANISHIKA CONSTRUCTION | 52.42 | 0 | 0
387 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000031/2022-2023 | 1475/NAD-I | 22/08/2022 | 90 | GHOSH ENTERPRISE | 320.01 | 0 | 100
388 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC and laying dedicated pipeline for Uzirpukuria, Humaniapota, Purba Simulia Village under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dubli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | Assistant Engineer-II | Junior Engineer-III | ORD/000037/2025-2026 | 248/NAD-I | 15/05/2025 | 60 | SUMAN CHAKRABORTY | 58.02 | 0 | 0
389 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Approach Road and allied work at site of Arranghata Z-I W/S scheme within Ranaghat -II Block under Nadia Arsenic Division -I ( Sl.no. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000045/2022-2023 | 1585 / NAD-I | 06/09/2022 | 45 | B.K. ENGINEERING | 12.4 | 11.95 | 100
390 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Arranghata Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Arranghata Zone-I (Phase-II) W/S Scheme under JJM (Sl.no.05) | Assistant Engineer-II | Junior Engineer-III | ORD/000054/2023-2024 | 1425/NAD-I | 23/05/2023 | 15 | M/S BISWAS BROTHERS | 12.98 | 0 | 100
391 | Nadia Arsenic Division I | Nadia Arsenic Division I | Culvert crossing and restoration of pipeline including jointing with manifold and other allied works under Paschim Noapara Water Supply Scheme , Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000055/2024-2025 | 1555/NAD-I | 25/09/2024 | 45 | JOYGOPAL GUPTI | 6.11 | 0 | 100
392 | Nadia Arsenic Division I | Nadia Arsenic Division I | "Augmentation of Garapota PWSS by providing dedicated pipeline for Shibchandrapur and Kutaknagar mouza under Nadia Arsenic Division-I,P.H.E. Dte. as a part of Jal Jeevan Mission.(SL. No. 07)" | Assistant Engineer-II | Junior Engineer-III | ORD/000140/2024-2025 | 2007/NAD-I | 29/11/2024 | 132 | BUDDHADEV MONDAL | 57.81 | 0 | 80
393 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Chandpur More area under Ranaghat-II block Augmentation of Ground Water Based PWSS for Dhantala W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000146/2023-2024 | 369/AE-II/NAD-I | 24/08/2023 | 7 | REKHA ENTERPRISE | 2.31 | 0 | 60
394 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work under Jal Jeevan Mission (JJM) for Gourisail area under Ranaghat-II Block by Augmentation of Ground Water Based PWSS forDubli Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.22) | Assistant Engineer-II | Junior Engineer-III | ORD/000192/2023-2024 | 2207/NAD-I | 13/09/2023 | 30 | GHOSH ENTERPRISE | 95.24 | 0 | 100
395 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work including FHTC (Functional Household Tap Connection) of Garapota and Duttaphulia at Block Hanskhali under Jal Jeevna Mission in connection with augmentation of Duttaphulia Zone-II W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.07) | Assistant Engineer-II | Junior Engineer-III | ORD/000215/2023-2024 | 2253/NAD-I | 22/09/2023 | 21 | M/S A.K. CONSTRUCTION | 78.25 | 0 | 100
396 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work under Jal Jeevan Mission (JJM) for Humanipota & Kamargaria area under Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Dubli Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000267/2023-2024 | 2689/NAD-I | 05/12/2023 | 427 | TARUN GHOSH | 56.47 | 0 | 70
397 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Paschim Noapara Ground Based Water Supply Scheme under Ranaghat-I, under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E Dte. in connection with Augmentation of Paschim Noapara Water Supply Scheme under JJM (Sl.No.-04) | Assistant Engineer-II | Junior Engineer-III | ORD/000294/2022-2023 | 720/NAD-I | 27/03/2023 | 15 | DAS CONSTRUCTION | 13.04 | 0 | 100
398 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) at Jugolkishore G.P. under Jal Jeevan Mission (JJM) for Ranaghat-II Block of Goalsalua Zone-I Ground Water based PWSS under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000298/2023-2024 | 167/NAD-I | 07/02/2024 | 15 | GOUTAM DEY | 4.91 | 0 | 0
399 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara / Jal Swapna for Aranghata Zone-II Part -III under Jal Jeevan Mission at Ranaghat -II Block by retrofitting of ground Water based PWSS for Aranghata Zone-II Water Supply Scheme under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000355/2023-2024 | 461/NAD-I | 15/03/2024 | 382 | DIVINE | 329.47 | 0 | 75
400 | Nadia Arsenic Civil Division II |  | Rejuvenate the existing media of pressure filter & polishing unit by acid & soda washing and replacing some portion of activated Alumina and Catalytic media as per requirement including supply of valves, specials & pipes for AIRP of Khanjipur W/S scheme. |  |  | ORD/000007/2020-2021 | 1143/NACD-II | 03/11/2020 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 4.79 | 9.58 | 0
401 | Nadia Arsenic Civil Division II |  | Rejuvenate the existing media of pressure filter & polishing unit by acid & soda washing and replacing some portion of activated Alumina and Catalytic media as per requirement including supply of valves, specials & pipes for AIRP of Bansberia W/S scheme. |  |  | ORD/000008/2020-2021 | 1144/NACD-II | 03/11/2020 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 4.8 | 9.59 | 0
402 | Nadia Arsenic Civil Division II |  | Name of work:-Rejuvenate the existing media of pressure filtter & polishing unit by acid & soda washing and replacing some portion of activated Alumina and Catalytic media as per requirement including supply of valves, specials & pipes for AIRP of Chandpur W/S scheme. |  |  | ORD/000009/2020-2021 | 1145/NACD-II | 03/11/2020 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 4.83 | 9.65 | 0
403 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Fatepur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000068/2020-2021 | 07/NACD-II | 05/01/2021 | 75 | MITRA CONSTRUCTION | 50.76 | 0 | 0
404 | Nadia Division | Krishnanagar Sub-Division | Restoration work of jhama shoulder damaged due to laying of pipe line under JJM project for Mayapur Youth Hostel Road from 0.0 Km to 0.47 Km under Nadia Highway Division-I, P.W.D (Roads) Directorate. | Assistant Engineer |  | BILL/00651/2024-2025 | 363/PFMS | 19/12/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 0.74 | 0 | 0
405 | Nadia Division | Krishnanagar Sub-Division | RESTORATION OF ROAD FLANK OF MAHESHGANJ MAYAPUR ROAD FROM CH. 0.50 KM TO 2.50 KMP. | Assistant Engineer |  | BILL/01488/2023-2024 | 600/PFMS | 14/03/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 3.01 | 0 | 0
406 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000196/2023-2024 | 3537/ND | 11/08/2023 | 1147 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 0 | 20
407 | Nadia Division | Krishnanagar Sub-Division | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000236/2025-2026 | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0
408 | Nadia Division | Krishnanagar Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
409 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | Assistant Engineer |  | ORD/000706/2024-2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0
410 | Nadia Division | Krishnanagar Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 2 of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .03 ) | Assistant Engineer |  | ORD/000712/2021-2022 | 205/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.62 | 4.59 | 100
411 | Nadia Division | Krishnanagar Sub-Division | Additional Survey, Design Drawing & DPR Preparation for ZONE 2 of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte ( Sl.No .04 ) | Assistant Engineer |  | ORD/000713/2021-2022 | 206/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.23 | 1.23 | 100
412 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | Assistant Engineer |  | ORD/000758/2023-2024 | 1838/KSD | 28/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0
413 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000160/2022-2023 | 85/ND | 05/01/2023 | 0 | Resource Division | 208.54 | 0 | 0
414 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000196/2023-2024 | 3537/ND | 11/08/2023 | 1147 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 0 | 20
415 | Nadia Division | Krishnanagar Sub-Division | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000236/2025-2026 | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0
416 | Nadia Division | Krishnanagar Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
417 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | Assistant Engineer | Junior Engineer 5 | ORD/000706/2024-2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0
418 | Nadia Division | Krishnanagar Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 3/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .06 ) | Assistant Engineer | Junior Engineer 5 | ORD/000715/2021-2022 | 208/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.67 | 3.62 | 100
419 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 5 | RTOR000162/2022-2023 | 118/ND | 05/01/2023 | 0 | Resource Division | 20.12 | 0 | 0
420 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
421 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000355/2023-2024 | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 0 | 19
422 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
423 | Nadia Division | Debgram Sub-Division | Construction of OHR, staff room, chlorine room, service road, boundary wall and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-IX / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/12376]. | Assistant Engineer |  | ORD/000481/2023-2024 | 213/ND | 10/01/2024 | 730 | PRASUN ENTERPRISE | 256.2 | 0 | 3
424 | Nadia Division | Debgram Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
425 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 9/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000808/2021-2022 | 158/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.47 | 4.39 | 100
426 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000005/2023-2024 | 1526/ND | 04/04/2023 | 0 | Resource Division | 390.11 | 0 | 0
427 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supplying, ,installation and commissioning of different equipments at the Conference Room under Haringhata WTP to make it compatible for video conferencing facility including supply & installation of surveillance system under Office of the Executive Engineer , Nadia Arsenic Division - I , PHE Dte. under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer-I | Junior Engineer-I | ORD/000001/2022-2023 | 601/NAD-I | 20/04/2022 | 45 | ALTAVISTA TECH SOLUTIONS | 24.44 | 0 | 43
428 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 450 cum capacity Over Head Reservoir, for Chakdah WTP under Chakdah Surface W/S Scheme in Chakdah Block under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no. 08) | Assistant Engineer-I | Junior Engineer-I | ORD/000057/2022-2023 | 1637 / NAD-I | 06/09/2022 | 45 | M/S R.K. ENTERPRISE | 13.75 | 11.47 | 55
429 | Nadia Arsenic Division I | Nadia Arsenic Division I | Road Restoration under Jal Jeevan Mission (JJM) for Birohi-I and Fatepur G.P. and Haringhata Block under Providing FHTC (Functional Househod Tap Connection) under Jaldhara/Jalswapna for Zone-III (Jalkar Bhomra), Part-II at Haringhata Block by retrofitting of Surface Water Based PWSS for Haringhata & Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000081/2025-2026 | 582/NAD-I | 10/07/2025 | 60 | SUMAN CHAKRABORTY | 10.33 | 0 | 100
430 | Nadia Arsenic Division I | Nadia Arsenic Division I | Charges of entry of household data in JJM with Household Aadhar details ......... Geo Tagging ..... in different Block of Nadia District under Nadia Arsenic Division -I, P.H.E.Dte. (Sl.no.03) | Assistant Engineer-I | Junior Engineer-I | ORD/000107/2022-2023 | 163 / AE-I/NAD-I | 04/07/2022 | 90 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 100
431 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC Functional Household Tap Connection under Jal Jeevan Mission JJM Zone -V Darrappur Part -IV at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata and Chakdah Part W/S Scheme under Nadia Arsenic Division- I P.H.E Dte. (Sl. No. 17) | Assistant Engineer-I | Junior Engineer-I | ORD/000128/2022-2023 | 3041/NAD-I | 09/11/2022 | 45 | M/S DIPAK ENTERPRISE | 71.77 | 44.72 | 80
432 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service connection at PH-I under Manoharpur W/S scheme. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/02373/2023-2024 | BP-136-23-24 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.46 | 0 | 0
433 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service connection at PH-II under Manoharpur W/S scheme. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/02375/2023-2024 | BP-137-23-24 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.48 | 0 | 0
434 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery, installation and commissioning of electro-mechanical accessories in connection with installation of Clear Water Pumping machinery in MANOHARPUR PWSS, Block_ KARIMPUR-II, District- Nadia. Under EMD PHE Dte. 2024_PHED_664112_4 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/003004/2023-2024 | 926/EMD | 15/03/2024 | 30 | DIPALI CONSTRUCTION | 9.65 | 0 | 0
435 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Manoharpur ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/003362/2023-2024 | 865/EMD | 14/03/2024 | 30 | CINZANO | 22.25 | 0 | 85
436 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00017/2023-2024 | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
437 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00090/2022-2023 | 235/5 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0
438 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000001/2025-2026 | 428/NACD-II | 07/04/2025 | 180 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 30
439 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Karimpur-II Block of Nadia District through Jadavpur University. (Name of PWSS Manoharpur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000087/2023-2024 | 916/NACD-II | 01/09/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
440 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 3 nos. Tube Well at H/W site ,2nd and 3rd T/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-III & Manoharpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000136/2024-2025 | 1047/NACD-II | 07/08/2024 | 90 | B.M. ENGINEERING & CONSTRUCTION | 34.68 | 0 | 100
441 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Manoharpur water supply scheme under Nadia Arsenic Civil Division-II, PHE Dte. Dist- Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000141/2023-2024 | 1363/NACD-II | 08/12/2023 | 45 | EVEREST CONSULTANT SERVICES. | 20.96 | 0 | 80
442 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of Tube Well at H/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass Strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-II & Manoharpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000213/2024-2025 | 92/NACD-II | 20/01/2025 | 45 | JOY HIND TUBEWELLS | 11.61 | 0 | 100
443 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 2 nos. 200 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (200 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Manoharpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000277/2022-2023 | 1132/NACD-II | 16/12/2022 | 30 | GENUINE | 20.4 | 16.66 | 100
444 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Construction of 30 m3/hr capacity IEP at Manoharpur PWSS in Karimpur-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000293/2023-2024 | 399/NACD-II | 13/03/2024 | 601 | MASUM CONSTRUCTION | 19.23 | 0 | 75
445 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 75 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Thanarpara Zone-III Water Supply Scheme in Karimpur-II block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000322/2024-2025 | 1207/NACD-II | 04/09/2024 | 540 | SINGHA ROY & CO. | 215.53 | 0 | 0
446 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distraibution system including providing Functional House Hold Tap Connection (FHTC) for Manoharpur and adjoining mouzas under Manoharpur W/s Scheme of Karimpur-II Block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000343/2022-2023 | 153/NACD-II | 17/01/2023 | 30 | NATIONAL CONSTRUCTION | 40.06 | 24.47 | 75
447 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pump House cum Chlorine room with sanitary arrangement at Thanarpara Zone-III Headwork site according to departmental drawing at Thanarpara Zone-III Piped Water Supply Scheme under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000374/2024-2025 | 04/NACD-II | 02/01/2025 | 90 | SOURAV & CO. | 6.14 | 0 | 100
448 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Manoharpur & Suruppur water supply scheme under Karimpur-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000400/2024-2025 | 135/NACD-II | 09/01/2025 | 225 | NISHITH BANERJEE | 32.78 | 0 | 50
449 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000025/2022-2023 | 1088/NACD-II | 09/12/2022 | 0 | Resource Division | 0.55 | 0 | 0
450 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000031/2022-2023 | 378/NACD-II | 24/03/2023 | 0 | Resource Division | 3.14 | 0 | 0
451 | Nadia Arsenic Division I |  | Augmentation of WTP & Intake in all respect along with ancillary works to make all the units, SCADA compatible all complete at Chakdah WTP under Augmentation of Chakdah Part & Haringhata & Chakdah (Part) under Nadia Arsenic Division I, PHE Dte. (Sl. NO. 01) |  |  | ORD/000022/2025-2026 | 97/NAD-I | 17/04/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 855.87 | 0 | 0
452 | Nadia Arsenic Division I |  | Replacing of old filter media from filter bed and supply, placing by new filter media of different size, Replacing the control chamber of the filter bed , construction of shed over filter bed & installation of SCADA system and ancillary works at HARINGHATA WTP under Augmentation of HARINGHATA & CHAKDAH(Part) under Nadia Arsenic Division I, PHE Dte. (sl.02) |  |  | ORD/000023/2025-2026 | 96/NAD-I | 17/04/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 839.8 | 0 | 0
453 | Nadia Arsenic Division I |  | Emergency restoration of UPVC pipeline for functionally of FHTC connections, damaged due to restoration of roads at Nagar Ukhra ¿I & II G.P. at Haringhata Block of Surface Water Based PWSS for Zone-II (Hapania) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.06) |  |  | ORD/000063/2024-2025 | 1494/NAD-I | 18/09/2024 | 225 | MONDAL ENTERPRISE | 25.84 | 0 | 100
454 | Nadia Arsenic Division I |  | Interconnection between outlet pipe of OHR and delivery main at different H/W sites in Haringhata and Chakdah (Part) surface water based PWSS at Haringhata block in connection with JJM under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) |  |  | ORD/000067/2024-2025 | 1710/NAD-I | 21/10/2024 | 21 | TARUN KUMAR BHATTACHARYA | 36.87 | 0 | 0
455 | Nadia Arsenic Division I |  | Preparation of Detailed Project Report (DPR) for Augmentation of Surface Water Based PWSS fo Haringhata & Chakdah (Part) Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(Sl.no.02) |  |  | ORD/000246/2023-2024 | 2614/NAD-I | 22/11/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 92.86 | 0 | 100
456 | Nadia Arsenic Division I |  | Shifting and relaying of distribution pipeline under Haringhata-Chakdah(P) Zone-III from pond side to inner location for preventing bacteriological contamination of distribution water and providing secondary chlorination system and including internal electrification and yard lighting at all the 13 (thirteen) nos of existing zones of Surface Water based water supply schemes for Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000248/2024-2025 | 2804/NAD-I | 25/03/2025 | 45 | TARUN KUMAR BHATTACHARYA | 35.7 | 0 | 0
457 | Nadia Arsenic Division I |  | Augmentation work of Clariflocculator-I of Haringhata & Chakdah (Part) WTP (33.39) MLD under JJM in connection with Augmentation of Surface Water Based PWSS for Haringhata & Chakdah (Part) at Chakdah & Haringhata block in the district of Nadia under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000261/2023-2024 | 2699/NAD-I | 05/12/2023 | 21 | G.B. CONSTRUCTION | 95.48 | 0 | 100
458 | Nadia Arsenic Division I |  | Augmentation of different units in connection with augmentation of Surface Based PWSS for Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte (sl.03) |  |  | ORD/000269/2023-2024 | 2610/NAD-I | 22/11/2023 | 30 | CHOWDHURY & CO. | 95.73 | 0 | 100
459 | Nadia Arsenic Division I |  | Augmentation of Water Treatment Plant, Intake & Rising Main for Surface Water Based Piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR including Soil Test, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 26 Nos. distribution zone for Haringhata & Chakdah (Part) in Haringhata & Chakdah Block of Nadia District under Nadia Arsenic Division-I, PHE Dte |  |  | ORD/000279/2023-2024 | 2730/NAD-I | 07/12/2023 | 548 | G.B. CONSTRUCTION & UMWELT JV | 10913.55 | 0 | 3
460 | Nadia Arsenic Division I |  | Augmentation work of Filter Bed & different units of Haringhata & Chakdah (Part) WTP (33.39 MLD) under JJM in connection with augementation of Surface Water Based W/S Scheme for Haringhata &Chakdah (Part) at Chakdah & Haringhata Block in the didtrict of Nadia under Nadia Arsenic Division - I P. H.E. Dte |  |  | ORD/000282/2023-2024 | 08/NAD-I | 03/01/2024 | 25 | TARUN KUMAR BHATTACHARYA | 24.29 | 0 | 100
461 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 1167/NAD-I | 29/07/2024 | 0 | Resource Division | 438.24 | 0 | 0
462 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 2054/NAD-I | 09/12/2024 | 0 | Resource Division | 112.27 | 0 | 0
463 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 2090/NAD-I | 16/12/2024 | 0 | Resource Division | 207.24 | 0 | 0
464 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 276/NAD-I | 23/02/2024 | 0 | Resource Division | 250.42 | 0 | 0
465 | Eastern Mechanical |  | Implementation of SCADA system at Intake, WTP and OHR sites of surface based water supply scheme for Haringhata & Chakdah (Part) in the District of Nadia. |  |  | ORD/000037/2024-2025 | 1523/EMD | 07/06/2024 | 183 | G.B. CONSTRUCTION | 592.09 | 0 | 0
466 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 0 | 47
467 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 4B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000773/2021-2022 | 123/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.07 | 4.03 | 100
468 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000119/2022-2023 | 104/ND | 05/01/2023 | 0 | Resource Division | 112.63 | 0 | 0
469 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 0 | 47
470 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 6A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000776/2021-2022 | 126/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.85 | 4.8 | 100
471 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000122/2022-2023 | 76/ND | 05/01/2023 | 0 | Resource Division | 260.19 | 0 | 0
472 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Preparation of Detailed Project Report (DPR) for Gosair Char Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.03) | Assistant Engineer | Junior Engineer | ORD/000166/2022-2023 | 3286 /NAD-I | 08/12/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 2.92 | 2.87 | 100
473 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Providing, Laying of Rising Main, Laying distribution system and FHTC (Functional Household Tap Connection) under Jal Jivam Mission, Soil investigation for the work of construction of 100 cum OHR staging height 20 mtr, Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including Raft foundation), pipe connection and cost of pipes, specials, Construction of Pump house, Boundary Wall, Service and Allied Works at head work & 2nd site for Gosair Char Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I , PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000217/2023-2024 | 2370/NAD-I | 06/10/2023 | 779 | SANJOY BAKSHI | 294.57 | 0 | 60
474 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000001/2024-2025 | 845/NAD-I | 04/06/2024 | 0 | Resource Division | 1.87 | 0 | 0
475 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000024/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 3.09 | 0 | 0
476 | Eastern Mechanical | Eastern Mechanical Sub Division-II | New Service Connection for Gosaichar Water supply scheme | Assistant Engineer | Junior Engineer | BILL/02312/2024-2025 | BP-197-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (AISHTAL CCC) | 4.98 | 0 | 0
477 | Eastern Mechanical | Eastern Mechanical Sub Division-II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for New Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Gosai Char ground water based water supply scheme under Block_ Ranaghat-I Dist. - Nadia under EMD, PHE Dte. [SM/13758] | Assistant Engineer | Junior Engineer | ORD/000645/2024-2025 | 2682/EMD | 20/11/2024 | 30 | WESTERN ENGINEERING CO. | 21.26 | 0 | 0
478 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete & Construction & Soil investigation of 700 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials for augmentation of Ground Water Based Water Supply Scheme for UDAYPUR to accommodate FHTC in Santipur block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000092/2023-2024 | 3027/ND | 14/07/2023 | 1096 | SANDIP BISWAS, RAMESWAR NATH LANE, CHOWDHURYPARA, PO- KRISHNAGAR, NADIA, 741101. | 468.16 | 0 | 75
479 | Nadia Division | Ranaghat Sub-Division | Repairing of Pump house-I with sanitary arrangement under augmentation of Udaypur piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000174/2024-2025 | 1137/RSD | 11/09/2024 | 45 | MAA SARADA CONSTRUCTION | 1.9 | 0 | 100
480 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
481 | Nadia Division | Ranaghat Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Udaypur W/S Scheme in Santipur Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000438/2021-2022 | 1058/RSD | 02/12/2021 | 30 | HORIZEN | 3.35 | 2.95 | 100
482 | Nadia Division | Ranaghat Sub-Division | Construction of Pump house and Boundary wall at head work site in related to augmentation of Ground Water Based Piped Water Supply Scheme for Udaypur Water Supply scheme under Santipur Block in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000588/2023-2024 | 845/ND | 06/02/2024 | 604 | S.M. CONSTRUCTION | 24.18 | 0 | 70
483 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-II and Construction of Sanitary arrangement under Augmentation of Udaypur PWSS. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000815/2024-2025 | 206/RSD | 06/02/2025 | 45 | GITARANI ENTERPRISE | 3.19 | 0 | 100
484 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000018/2023-2024 | 1863/ND | 26/04/2023 | 0 | Resource Division | 46.68 | 0 | 0
485 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000101/2023-2024 | 3543/ND | 11/08/2023 | 0 | Resource Division | 75.5 | 0 | 0
486 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000136/2023-2024 | 254/ND | 11/01/2024 | 0 | Resource Division | 12.33 | 0 | 0
487 | Central Drilling | Ranaghat Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Udaypur W/S Scheme (T/W-I),Santipur Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000094/2023-2024 | 512/CDD | 01/06/2023 | 30 | UTTAM KUMAR CHATTERJEE | 18.88 | 0 | 0
488 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Udaypur ground water based water supply scheme under Block_Santipur Dist. - Nadia under EMD, PHE Dte.(SM/11925) | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000190/2025-2026 | 1128/EMD | 04/06/2025 | 90 | SHIVAM ENTERPRISE | 24.59 | 0 | 0
489 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 0 | 47
490 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 3B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000771/2021-2022 | 121/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.04 | 4.02 | 100
491 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000117/2022-2023 | 72/ND | 05/01/2023 | 0 | Resource Division | 91.95 | 0 | 0
492 | Nadia Division | Debgram Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 700 cum. For Surface Water Based Piped Water Supply Scheme for Zone II/A (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte.¿ | Assistant Engineer |  | ORD/000262/2023-2024 | 3999/ND | 07/09/2023 | 60 | S.B.CONSTRUCTION | 27.73 | 0 | 50
493 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- II/A (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000310/2023-2024 | 4280/ND | 21/09/2023 | 811 | ONKAR ENTERPRISE | 284.27 | 0 | 4
494 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
495 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 2/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000787/2021-2022 | 137/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.29 | 3.78 | 100
496 | Nadia Division | Debgram Sub-Division | Additional work for Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes etc. all complete for Zone- II/A (Northern Sector Part-II) under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000864/2024-2025 | 1473/ND | 25/03/2025 | 60 | ONKAR ENTERPRISE | 72.83 | 0 | 0
497 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000117/2023-2024 | 228/ND | 11/01/2024 | 0 | Resource Division | 10.18 | 0 | 0
498 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000132/2022-2023 | 93/ND | 05/01/2023 | 0 | Resource Division | 102.91 | 0 | 0
499 | Nadia Division | RWS Nadia Sub-Division | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Ber Ramchandrapur Z-II Water Supply Scheme Under R.W.S. Nadia Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000170/2024-2025 | 4579/ND | 21/08/2024 | 540 | MONDAL CONSTRUCTION | 22.28 | 0 | 80
500 | Nadia Division | RWS Nadia Sub-Division | Providing FHTC by Augmentation under jal swapna for Ber Ramchandrapur Zone-II Water Supply scheme in Karimpur-I block of Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000674/2021-2022 | 694/ND | 15/02/2022 | 90 | SUDHAMAY MAJUMDAR | 77.58 | 41.39 | 100
501 | Nadia Division | RWS Nadia Sub-Division | Additional work of Laying Distribution System and additional work of providing FHTC in connection with Augmentation of Ber Ramchandrapur Zone-II PWSS within Karimpur-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000778/2023-2024 | 1763/ND | 12/03/2024 | 420 | MALI CONSTRUCTION | 38.98 | 0 | 80
502 | Nadia Division | RWS Nadia Sub-Division | Conversion of IEP to AIRP of capacity 30 Cu.m/hr at Ber Ramchandrapur Zone-II Water Supply Scheme within Karimpur-I block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000797/2023-2024 | 1909/ND | 15/03/2024 | 600 | ASIT PRAMANIK | 124.74 | 0 | 80
503 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000114/2021-2022 | 1026/ND | 03/03/2022 | 0 | Resource Division | 2.13 | 0 | 0
504 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000127/2021-2022 | 1261/ND | 16/03/2022 | 0 | Resource Division | 1.44 | 0 | 0
505 | Nadia Division | RWS Nadia Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | VCH/001058/2021-2022 | 616/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.71 | 0 | 0
506 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No.I(Zone-II) under Berramchandrapur W/S Scheme, Block-Karimpur- 1,District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.- 05) | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000085/2022-2023 | 3913/EMD | 19/10/2022 | 30 | C.M.S. ENGINEERING CONCERN. | 10.73 | 0 | 97
507 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer etc. for Augmentation to Accomodate FHTC at Pump House No.II (Zone-II) under Ber Ramchandrapur W/S Scheme, Block-Karimpur-I, District of Nadia. NIET No. 14 of EE/EMD of 2022-23 (Sl. No. -06) | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000090/2022-2023 | 3943/EMD | 20/10/2022 | 30 | MAA TARA CONSTRUCTION | 8.2 | 8.04 | 70
508 | Nadia Division | Tehatta Sub-Division | Conversion of IEP to AIRP of capacity 60 Cu.m/hr at Kishorepur Water Supply Scheme within Karimpur-II Block block under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000112/2024-2025 | 4343/ND | 07/08/2024 | 180 | M/S R.K.ENTERPRISE | 129.29 | 0 | 0
509 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Kishorepur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000373/2024-2025 | 7059/ND | 04/12/2024 | 90 | M/S CHANDIMATA CONSTRUCTION | 30.07 | 0 | 0
510 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Kishorepur Ground Based Water Supply Scheme under Karimpur II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Kishorepur at Karimpur II Block by Augmentation of Ground Water based PWSS for Kishorepur Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000641/2024-2025 | 7367/ND | 18/12/2024 | 120 | ROY ASSOCIATES | 24.03 | 0 | 0
511 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000016/2022-2023 | 3301/ND | 27/07/2022 | 0 | Resource Division | 9.25 | 0 | 0
512 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000135/2021-2022 | 1264/ND | 16/03/2022 | 0 | Resource Division | 2.3 | 0 | 0
513 | Nadia Division | Tehatta Sub-Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001261/2021-2022 | 727/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.77 | 0 | 0
514 | Eastern Mechanical | Tehatta Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under KISHOREPUR ground water based water supply scheme under Block_ KISHOREPUR Dist. - Nadia under EMD, PHE Dte. SM/09573 | Assistant Engineer | Junior Engineer | ORD/000178/2025-2026 | 1115/EMD | 04/06/2025 | 90 | WIZARDTECH SOLUTION | 17.48 | 0 | 0
515 | Eastern Mechanical | Tehatta Sub-Division | Rejuenation of Kishorepur PWSS regarding FHTC in Karimpur II Block of Nadia Distric | Assistant Engineer | Junior Engineer | ORD/001929/2022-2023 | 927/EMD | 27/05/2022 | 304 | ABHISEK ENGINEERING CONCERN | 16.28 | 16.28 | 100
516 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000020/2021-2022 | 2154/ND | 21/05/2021 | 60 | SAKTI ENTERPRISE | 33.45 | 51.22 | 100
517 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000067/2021-2022 | 2431/ND | 14/06/2021 | 60 | JAGANNATH ENTERPRISE | 33.43 | 8.56 | 0
518 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte."(PART- C) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000114/2021-2022 | 2957/ND | 27/07/2021 | 45 | CHOWDHURY & CO. | 8.82 | 7.41 | 100
519 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Krishnanagar - I Block | RTOR000011/2021-2022 | 100/ND | 06/01/2022 | 0 | Resource Division | 1.77 | 0 | 0
520 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Krishnanagar - I Block | RTOR000089/2021-2022 | 786/ND | 18/02/2022 | 0 | Resource Division | 1.08 | 0 | 0
521 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | Assistant Engineer | Junior Engineer Krishnanagar - I Block | VCH/000474/2021-2022 | 292/PFMS | 08/10/2021 | 0 | JAGANNATH ENTERPRISE | 19.98 | 0 | 0
522 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of pipeline at Nirsinghapur Utterpara including water connection at Nirsinghapur High School and allied works under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000053/2024-2025 | 247/AE-I/NAD-I | 20/09/2024 | 30 | TUHIN CONSTRUCTION | 0.97 | 0 | 100
523 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of pipeline including FHTC connections near Nirsinghapur Health Centre at Nirsinghapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000054/2024-2025 | 248/AE-I/NAD-I | 20/09/2024 | 30 | TUHIN CONSTRUCTION | 0.96 | 0 | 100
524 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (216cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.09) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000131/2023-2024 | 1899/NAD-I | 14/08/2023 | 691 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 167.06 | 0 | 70
525 | Nadia Arsenic Division I | Nadia Arsenic Division I | Road Restoration Work along PMGSY Road under Nrisinghapur Ground Water Supply Scheme at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000259/2023-2024 | 2595/NAD-I | 17/11/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 48.14 | 0 | 100
526 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Nrisinghapur Part-II under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15553) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000160/2025-2026 | 1158/EMD | 04/06/2025 | 90 | S M ELECTRICALS | 4.34 | 0 | 0
527 | Nadia Division | Ranaghat Sub-Division | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000252/2024-2025 | 6290/ND | 26/09/2024 | 45 | IMAGIN | 19.44 | 0 | 100
528 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Krishnagar-I Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000523/2022-2023 | 1268/ND | 23/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 8.77 | 45
529 | Nadia Division | Ranaghat Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Mahishnengra Zone-I PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 60.00 | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000584/2023-2024 | 840/ND | 06/02/2024 | 420 | B.M. ENGINEERING & CONSTRUCTION | 68.23 | 0 | 80
530 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under MAHISNENGRA (Zone-I) W/S Scheme, Block- Krishnagar-1 , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 16) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/002775/2022-2023 | 416/EMDdt.20.01.23 | 17/02/2023 | 30 | GOENKA ENTERPRISE | 14.03 | 12.85 | 90
531 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000529/2022-2023 | 1272/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 48.99 | 0 | 66
532 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (16cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Gayeshpur Zone-II, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.04) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000137/2023-2024 | 1881/NAD-I | 10/08/2023 | 517 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 142.26 | 0 | 100
533 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site of Joypur and Mamjoani Water Supply Scheme in connection with Duttaphulia Zone-I under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000004/2025-2026 | 39/NAD-I | 07/04/2025 | 242 | REAL TIME | 39.28 | 0 | 50
534 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000128/2021-2022 | 53/NAD-I | 11/01/2022 | 90 | TIRUPATI ENTERPRISES | 163.2 | 155.42 | 100
535 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Mamjoani (Part-I) W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000156/2022-2023 | 225/AE-II/NAD-I | 07/12/2022 | 15 | PURNIMA ELECTRICS & DECORATORS | 2.59 | 0 | 100
536 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 120 m3/hr at Char Brahmanagar Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000119/2024-2025 | 4521/ND | 20/08/2024 | 540 | MONDAL PRECISION PRIVATE LIMITED | 296.98 | 0 | 0
537 | Nadia Division | Krishnanagar Sub-Division | Additional Laying of UPVC Pipeline for providing leftout FHTC including supplying, laying, fitting, fixing with all necessary specials, saddle piece etc. all complete for Ground Based piped water supply scheme in Char Majhdia Char Brahmanagar to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000142/2025-2026 | 3072/ND | 01/07/2025 | 180 | H I ENTERPRISE | 90.88 | 0 | 40
538 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials & valves, Laying of proposed Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC/20mm OD HDPE pipe with all necessary specials, Soil investigation for construction of one No. 600 Cum OHR, Construction of R.C.C. Elevated Reservoir of 600 Cum capacity(including pile foundation), Construction of Pump House at Proposed H/W, 2nd T/W and 3rd Tube Well site, Construction of boundary wall with gate at Proposed H/W, 2nd T/W and 3rd Tube Well site at Char Brahmanagar within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000193/2023-2024 | 3448/ND | 09/08/2023 | 1242 | H I ENTERPRISE, VILL&P.O- DHALTITHA, P.S. BASIRHAT, NORTH 24 PARGANAS, PIN-743412(WB) | 634.32 | 0 | 30
539 | Nadia Division | Krishnanagar Sub-Division | Construction Of Approach Road To The Headwork Site With Pilling Work, Land Development Of Head Worksite, Restoration Of Concrete Roads And Allied Works Of Char Brahmanagar Water Supply Scheme Under Krishnagar Subdivision Under Nadia Division PHED. | Assistant Engineer | Junior Engineer 4 | ORD/000267/2024-2025 | 6625/ND | 25/10/2024 | 150 | H I ENTERPRISE | 74.95 | 0 | 50
540 | Nadia Division | Krishnanagar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
541 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 4 | RTOR000002/2024-2025 | 3315/ND | 11/06/2024 | 0 | Resource Division | 20.41 | 0 | 0
542 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 4 | RTOR000151/2023-2024 | 262/ND | 11/01/2024 | 0 | Resource Division | 25.02 | 0 | 0
543 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 4 | RTOR000169/2022-2023 | 128/ND | 05/01/2023 | 0 | Resource Division | 119.68 | 0 | 0
544 | Central Drilling | Krishnanagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Char Brahmanagar W/S Scheme (TW-III) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000135/2023-2024 | 1657/CDD | 17/10/2023 | 30 | SNEHASISH GHOSH | 16.33 | 0 | 0
545 | Central Drilling | Krishnanagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Char Brahmanagar W/S Scheme (TW-I) ,Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000241/2023-2024 | 1655/CDD | 17/10/2023 | 289 | GENUINE | 16.88 | 0 | 100
546 | Central Drilling | Krishnanagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Char Brahmanagar W/S Scheme (TW-II) ,Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000242/2023-2024 | 1656/CDD | 17/10/2023 | 532 | GENUINE | 16.88 | 0 | 100
547 | Eastern Mechanical | Krishnanagar Sub-Division | Quotation for new service connection for Char Bramhanagar Ph-2, under Nabadwip block, District-Nadia | Assistant Engineer | Junior Engineer 4 | BILL/02313/2024-2025 | BP-203-24-25 | 17/12/2024 | 0 | WBSEDCL SWARUPGANJ C.C.C. | 9.86 | 0 | 0
548 | Eastern Mechanical | Krishnanagar Sub-Division | Quotation for new service connection for Char Bramhanagar Ph-1, under Nabadwip block, District-Nadia | Assistant Engineer | Junior Engineer 4 | BILL/02320/2024-2025 | BP-202-24-25 | 17/12/2024 | 0 | WBSEDCL SWARUPGANJ C.C.C. | 12.62 | 0 | 0
549 | Eastern Mechanical | Krishnanagar Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation NEW Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II and III under Char Brahmanagar ground water based water supply scheme under Block_ Nabadwip Dist. - Nadia under EMD, PHE Dte. (SM/16182) | Assistant Engineer | Junior Engineer 4 | ORD/000640/2024-2025 | 2677/EMD | 20/11/2024 | 30 | HINDUSTAN ENGINEERING CORPORATION(E & M) | 36.01 | 0 | 0
550 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Bankar Dhopadi W/S scheme in Nadia District under Nadia Division P.H.E. Dte." (Phase-I, Retrofitting) | Assistant Engineer |  | ORD/000119/2021-2022 | 2993/ND | 29/07/2021 | 90 | SANJIB DEY | 80.08 | 3.93 | 100
551 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000091/2021-2022 | 788/ND | 18/02/2022 | 0 | Resource Division | 0.8 | 0 | 0
552 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000094/2021-2022 | 791/ND | 18/02/2022 | 0 | Resource Division | 1.12 | 0 | 0
553 | Nadia Division | Krishnanagar Sub-Division | PROVIDING FHTC ..FROM PASILA W/S SCHEME , PHASE-1 | Assistant Engineer |  | VCH/000875/2021-2022 | 472/PFMS | 02/02/2022 | 0 | SANJIB DEY | 70.26 | 0 | 0
554 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 80
555 | Nadia Arsenic Civil Division II | Eastern Mechanical Sub Division-III | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Dharammpur (Part-B) of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000021/2023-2024 | 584/NACD_II | 17/05/2023 | 990 | PAPAN ROY | 26.96 | 0 | 0
556 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Quotation for new Service connection charges and security deposit for Labangola PWSS | Assistant Engineer | Junior Engineer | BILL/02317/2024-2025 | BP-201-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 0.1 | 0 | 0
557 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 80
558 | Nadia Arsenic Civil Division II | Eastern Mechanical Sub Division-III | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Labangola of Tehatta- II Block under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer | Junior Engineer | ORD/000025/2023-2024 | 565/NACD_II | 11/05/2023 | 90 | BIPLAB GUHA | 28.05 | 0 | 81
559 | Nadia Arsenic Civil Division II | Eastern Mechanical Sub Division-III | Providing 1 no. Guard at Labongola Mini Public Water Supply Scheme in Tehatta-II Block for guarding of various Departmental materials under Nadia Arsenic Civil Division-II,P.H.E. Dte.[Period of work :01/07/2024 to 31/10/2024] | Assistant Engineer | Junior Engineer | ORD/000158/2024-2025 | 787/AE-I/NACD-II | 01/07/2024 | 123 | ZOOM CONSTRUCTION & INTERIO | 0.91 | 0 | 0
560 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 80
561 | Nadia Arsenic Civil Division II | Eastern Mechanical Sub Division-III | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Chak Ramnagar of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer | Junior Engineer | ORD/000026/2023-2024 | 566/NACD_II | 11/05/2023 | 891 | BIDYUT KUMAR | 28.38 | 0 | 70
562 | Eastern Mechanical | Nadia Arsenic Civil Division II | Quotation for new service connection and security deposit for Java (part- A), Krishnanagar- I | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/01581/2024-2025 | BP-106-24-25 | 09/09/2024 | 0 | W.B.S.E.D.C.L (GROUP KRISHNAGAR ROAD STATION C.C.C) | 0.1 | 0 | 0
563 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000355/2023-2024 | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 80
564 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of Tube well, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Jaba (Part-A) of Krishnagar-I Block under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000369/2022-2023 | 345/NACD-II | 21/03/2023 | 821 | M/S FREEDOM CONSTRUCTION | 29.83 | 0 | 60
565 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-II, Zone-IV within Nakashipara Block (Phase-D) | Assistant Engineer |  | ORD/000207/2021-2022 | 5181/ND | 20/09/2021 | 90 | SHYAMAL SHIL | 89.79 | 85.01 | 0
566 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000057/2021-2022 | 809/ND | 18/02/2022 | 0 | Resource Division | 12.23 | 0 | 0
567 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-IV within Nakashipara Block.(Phase-D) | Assistant Engineer |  | VCH/000980/2021-2022 | 582/PFMS | 04/03/2022 | 0 | SHYAMAL SHIL | 8.22 | 0 | 0
568 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Gravity Type) of capacity 67 Cu.m/hr at Head Work Site at Kulgachi PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000005/2023-2024 | 1599/ND | 10/04/2023 | 721 | B.M. ENGINEERING & CONSTRUCTION | 72.07 | 0 | 100
569 | Eastern Mechanical | Krishnanagar Sub-Division | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at KULGACHI (Phase-II) Piped Water Supply Scheme, Block: Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001753/2023-2024 | 6364/EMD | 17/10/2023 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 49.3 | 0 | 0
570 | Eastern Mechanical | Krishnanagar Sub-Division | Supplementary works to completion of ongoing FHTC-related work under Kulgachi W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/002483/2023-2024 | 956/EMSD-II | 26/12/2023 | 10 | ABHISEK ENGINEERING CONCERN | 0.69 | 0 | 100
571 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I and II under Kulgachi WS Scheme, Block KrishnagarI, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-09) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/002969/2022-2023 | 158EMD,Dt.06.01.23 | 27/03/2023 | 30 | ABHISEK ENGINEERING CONCERN | 15.5 | 0 | 100
572 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP (Pressure Type) of capacity 95 Cu.m/hr at Head Work Site at GHORALIA ZONE- I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Ranaghat - I Block | ORD/000009/2023-2024 | 1804 / ND | 24/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 49.9 | 31.13 | 78
573 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under GHORALIA(Zone-1) W/S Scheme, Block- Shantipur , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 12) | Assistant Engineer | Junior Engineer,Junior Engineer Ranaghat - I Block | ORD/000904/2022-2023 | 414/EMDdt.20.01.23 | 17/03/2023 | 30 | D.S. ENTERPRISE | 5.99 | 5.77 | 100
574 | Eastern Mechanical | RWS Nadia Sub-Division | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Ghoralia Zone-I (Phase-II) Piped Water Supply Scheme, Block: Santipur, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Ranaghat - I Block | ORD/001758/2023-2024 | 6368/EMD | 17/10/2023 | 776 | ESENCE ENGINEERING CONCERN | 53.51 | 0 | 100
575 | Eastern Mechanical | RWS Nadia Sub-Division | Supply Delivery and installation of Changeover switch and Electrical wiring and other allied works at Ghoralia (Z-I) P/H- I W/S Scheme in the District of Nadia, Under EMSD-II PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Ranaghat - I Block | ORD/002455/2023-2024 | 983/EMSD-II | 27/12/2023 | 10 | D.S. ENTERPRISE | 0.6 | 0 | 100
576 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Gravity Type) of capacity 29 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Bankar Dhopadi PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000081/2023-2024 | 2994/ND | 13/07/2023 | 90 | TARUN KUMAR BHATTACHARYA | 70.11 | 0 | 0
577 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANKER DHOPADI W/S Scheme, Block- Nabadwip , Dist. - Nadia. NIET NO. 28 OF EE/EMD OF 2022-23 (SL. NO. 02) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001256/2022-2023 | 813/EMDdt.16.02.2023 | 16/03/2023 | 30 | UTTAM KUMAR CHATTERJEE | 14.15 | 0 | 100
578 | Eastern Mechanical | Krishnanagar Sub-Division | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Bankar Dhopadi Piped Water Supply Scheme Block_ Nabadwip Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001762/2023-2024 | 6373/EMD | 17/10/2023 | 532 | AHALYA ENGINEERING WORKS | 42.1 | 0 | 0
579 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP (Gravity Type) of capacity 117 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Fazilnagar PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000029/2023-2024 | 1787/ND | 20/04/2023 | 886 | B.M. ENGINEERING & CONSTRUCTION | 118.29 | 0 | 30
580 | Nadia Division | RWS Nadia Sub-Division | Augmentation of FHTC (Part-B) of Fazilnagar Pipe Water Supply Scheme. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000160/2024-2025 | 4903/ND | 10/09/2024 | 60 | PATHIK PABAN NANDI | 34.31 | 0 | 0
581 | Nadia Division | RWS Nadia Sub-Division | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site & 2nd Tube Well Site of Fazil Nagar [Phase-II] Ground Based Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000521/2022-2023 | 1248/ND | 22/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 29.32 | 20.9 | 70
582 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.- I under Fazilnagar W/S Scheme, Block-Karimpur-II, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000200/2022-2023 | 6189/EMDdt.14-11.2022 | 16/03/2023 | 30 | GHOSE ENGINEERING SYNDICATE | 13.61 | 0 | 100
583 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer etc. rejuvenation to Accommodate FHTC at Pump House No.- II under Fazilnagar W/S Scheme,, Block-Karimpur-II, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000517/2022-2023 | 6273/EMD | 18/11/2022 | 30 | SRI KRISHNA NIRMAN | 5.85 | 5.85 | 0
584 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer etc. rejuvenation to Accomodate FHTC at Pump House No.- III under Fazilnagar W/S Scheme, Block-Karimpur-II, Dist. - Nadia. NIET No.- 18 of EEW/EMD of 2022-23 (Sl. No.- 10) | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000518/2022-2023 | 6274/EMD | 18/11/2022 | 30 | ASHOKE ADHIKARY | 8.74 | 8.74 | 0
585 | Eastern Mechanical | RWS Nadia Sub-Division | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Fazilnagar (Phase-II) Piped Water Supply Scheme Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/001759/2023-2024 | 6370/EMD | 17/10/2023 | 30 | R.N.S. TRADING | 53.72 | 0 | 0
586 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Sabdalpur Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Sabdalpur W/S Scheme under JJM (SL.NO.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000012/2023-2024 | 1115 / NAD-I | 27/04/2023 | 15 | ASIT PRAMANIK | 13.01 | 0 | 100
587 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying dedicated pipeline to supply water for Sabdalpur and Hosenpur under Jal Jeevan Mission (JJM) at Ranaghat-II Block of Sabdalpur Ground Water Based PWSS for under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | Assistant Engineer-II | Junior Engineer-III | ORD/000021/2025-2026 | 133/NAD-I | 22/04/2025 | 60 | MANISHIKA CONSTRUCTION | 52.42 | 0 | 0
588 | Nadia Arsenic Division I | Nadia Arsenic Division I | Pipeline connection from Manifold to Distribution Main (Left Part) and Rejoining with Existing Distribution Line (Right Part) under Jal Jeevan Mission (JJM) at Ranaghat-II Block under Ground Water Based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000032/2024-2025 | 1197/NAD-I | 01/08/2024 | 60 | MANAJIT BISWAS | 9.81 | 0 | 100
589 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting Work for Provoiding FHTC at Bholadanga under Jal Jeevan Mission (JJM) at Ranaghat-II Block under Ground Water based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000033/2024-2025 | 1198/NAD-I | 01/08/2024 | 60 | M/S K..M. ENTERPRISE | 9.49 | 0 | 0
590 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet, Pathway and other allied work at Dhantala W/S Scheme within Ranaghat -II Block under Nadia Arsenic Division -I, P.H.E.Dte. ( Sl.no. 02) | Assistant Engineer-II | Junior Engineer-III | ORD/000040/2022-2023 | 1582 /NAD-I | 06/09/2022 | 45 | GHOSH CONSTRUCTION | 24.96 | 20.22 | 100
591 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Dhantala Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Dhantala W/S Scheme under JJM. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000099/2023-2024 | 1688/NAD-I | 12/07/2023 | 15 | SANJIB DEY | 13.04 | 0 | 100
592 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 350 cum capacity Over Head Reservoir Painting and repairing of H W Boundary Wall Pump House and AIRP at Sabdalpur W/S Scheme at Ranaghat-II Block under Nadia Arsenic Division-I P.H.E Dte (Sl.No.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000132/2022-2023 | 3045/NAD-I | 09/11/2022 | 45 | MONDAL CONSTRUCTION | 31.43 | 26.84 | 100
593 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall Toilet Pathway and other allied work at Sabdalpur W S Scheme within Ranaghat II Block under NAD I PHE Dte. (sl.no.04) | Assistant Engineer-II | Junior Engineer-III | ORD/000133/2022-2023 | 3034/NAD-I | 09/11/2022 | 45 | M/S LAXMI ENTERPRISE | 12.78 | 9.05 | 100
594 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Dhantala WS Scheme atRanaghat II Block under NAD I PHE Dte(sl.no.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000138/2022-2023 | 3037/NAD-I | 09/11/2022 | 45 | TAPU SAHA | 25.33 | 25.28 | 100
595 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dhantala at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000238/2022-2023 | 963 / NAD-I | 07/07/2022 | 60 | M/S K.P. CONSTRUCTION | 75.57 | 38.69 | 60
596 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Sabdalpur, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.no. 04) | Assistant Engineer-II | Junior Engineer-III | ORD/000239/2022-2023 | 966 / NAD-I | 07/07/2022 | 1998 | M/S K.P. CONSTRUCTION | 65.89 | 46.32 | 70
597 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Goalsalua Zone-I, Dhantala and Betna in connection with Augmentation of Ground Water based PWSS under Jaldhara/JalSwapna by retrofitting of Sabdalpur & Dhantala under Ranaghat-II Block district Nadia to accomodate FHTC, REpair of OHR construction of Boundary Wall and allied works. | Assistant Engineer-II | Junior Engineer-III | ORD/000283/2023-2024 | 09/NAD-I | 03/01/2024 | 21 | CHANDAN ROY | 7.89 | 0 | 100
598 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP for Ground Water Based Piped Water Supply Scheme for Dhantala (125 Cum) under Jal Jeevan Mission at Ranaghat-II Block, under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000284/2023-2024 | 2779/NAD-I | 18/12/2023 | 21 | APURBA MANDAL | 10.62 | 0 | 100
599 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000529/2022-2023 | 1272/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 48.99 | 27.06 | 66
600 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-I(Phase-II) under Bagula ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/001774/2023-2024 | 6398/EMD | 30/10/2023 | 30 | A.K. ENTERPRISE | 12.6 | 0 | 100
601 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (123cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Boalia, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000130/2023-2024 | 1898/NAD-I | 14/08/2023 | 928 | M/S R.K. ENTERPRISE | 170.25 | 0 | 75
602 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD including UPVC pipeline and allied works at OHR site under Boalia Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Schemes under Nadia Arsenic Division-I, PHE Dte. " | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000272/2023-2024 | 2745/NAD-I | 08/12/2023 | 445 | MS MAA BHABANI ENTERPRISE | 20.18 | 0 | 100
603 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Boalia Part-IV under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15544) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000165/2025-2026 | 1162/EMD | 04/06/2025 | 90 | BIJAN ENTERPRISE | 4.33 | 0 | 0
604 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Gayeshpur Zone II Part-IV under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15544) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000168/2025-2026 | 1166/EMD | 04/06/2025 | 90 | TALUKDER & CO. | 4.34 | 0 | 0
605 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill for new service connection at Shikra W/S Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/02152/2022-2023 | 149/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.26 | 0 | 0
606 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill for new service connection at Shikra under EMSD-III | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/02153/2022-2023 | 150/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.81 | 0 | 0
607 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Headworks) under Sikra W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000103/2022-2023 | 5017/EMD | 03/11/2022 | 30 | S.P. ENTERPRISE | 10.12 | 9.17 | 100
608 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Sikra W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 10) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000104/2022-2023 | 5018/EMD | 03/11/2022 | 30 | M/S DILIP MITRA | 10.12 | 9.18 | 100
609 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Sikra water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000008/2022-2023 | 206/NACD-II | 05/04/2022 | 60 | BIPLAB GUHA | 5.38 | 5.33 | 100
610 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Madhupur and Sikra Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000020/2022-2023 | 245/NACD-II | 19/04/2022 | 60 | JOY HIND TUBEWELLS | 41.88 | 0 | 100
611 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Sikra water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000034/2022-2023 | 21/AE-I/NACD-II | 13/04/2022 | 60 | BIPLAB GUHA | 2.83 | 2.81 | 100
612 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Sikra Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000041/2022-2023 | 28/AE-I/NACD-II | 13/04/2022 | 60 | SAHA ENGINEERS | 3.93 | 0 | 100
613 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction for priliminary work of the approch road at Head Works site of Sikra Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000042/2023-2024 | 407/AE-I/NACD-II | 08/08/2023 | 15 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 0.85 | 0 | 0
614 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS: Sikra) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000055/2023-2024 | 863/NACD-II | 10/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
615 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Sikra and adjoining mouzas under Sikra Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000070/2022-2023 | 360/NACD-II | 15/06/2022 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 231.09 | 177.26 | 90
616 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Panchdara Abhaynagar Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000128/2023-2024 | 468./AE-I/NACD-II | 03/10/2023 | 15 | AMIT KUMAR BOSE | 0.97 | 0 | 0
617 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 45 cum/Hour capacity for Sikra Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000188/2024-2025 | 1030/NACD-II | 02/08/2024 | 360 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 176.18 | 0 | 70
618 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Sikra Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000193/2022-2023 | 623/NACD-II | 06/09/2022 | 20 | MAKALI ENGINEERING CORPORATION | 3.9 | 3.9 | 100
619 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 45 cum/Hour capacity for Hatkhola Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000203/2024-2025 | 1152/NACD-II | 27/08/2024 | 540 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 176.21 | 0 | 66
620 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of flow control devices in the closed water conduit at Sikra PWSS in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000257/2024-2025 | 944/AE-I/NACD-II | 24/10/2024 | 7 | MAKALI ENGINEERING CORPORATION | 0.87 | 0 | 100
621 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Sikra Water Supply Scheme at Head Work Site site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000319/2022-2023 | 83/NACD-II | 10/01/2023 | 60 | SANDIP KUMAR NEOGI | 14.39 | 14.33 | 85
622 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Sikra 2nd Tubwell site within Sikra Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000340/2022-2023 | 121/NACD-II | 11/01/2023 | 60 | ASHIM ENTERPRISE | 4.9 | 4.69 | 85
623 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000348/2024-2025 | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 20
624 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Sikra) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000356/2023-2024 | 434/NACD-II | 15/03/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
625 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Sikra water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000388/2022-2023 | 395/NACD-II | 28/03/2023 | 1097 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 119.11 | 0 | 85
626 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | RTOR000013/2022-2023 | 406/NACD-II | 04/07/2022 | 0 | Resource Division | 32.18 | 0 | 0
627 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000229/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
628 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000245/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
629 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000255/2022-2023 |  | 21/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
630 | Nadia Division | RWS Nadia Sub-Division | SHIFTING OF LT OH POLE AT NASERKHULI Z-II HEAD WORK SITE PWSS | Assistant Engineer | Junior Engineer,Junior Engineer 4 | BILL/00337/2024-2025 | 242/PFMS | 13/09/2024 | 0 | WBSEDCL RANAGHAT (EAST) CCC | 0.53 | 0 | 0
631 | Nadia Division | RWS Nadia Sub-Division | Laying of distribution system including specials, valves & pipe supporting structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of ground based water supply scheme at Naserkhuli Zone-II to accommodate FHTC within Ranaghat-II Dev. Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. (sm/11547) | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000177/2022-2023 | 4382/ND | 13/10/2022 | 880 | M/S GHOSH CONSTRUCTION | 332.64 | 313.69 | 96
632 | Nadia Division | RWS Nadia Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
633 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000055/2023-2024 | 2284/ND | 29/05/2023 | 0 | Resource Division | 18.4 | 0 | 0
634 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000078/2022-2023 | 4326/ND | 29/09/2022 | 0 | Resource Division | 18.4 | 0 | 0
635 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000101/2022-2023 | 4932/ND | 25/11/2022 | 0 | Resource Division | 38.64 | 0 | 0
636 | Central Drilling | RWS Nadia Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Naserkhuli W/S Scheme (Z- II, T/W-II),Ranaghat-II Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000067/2023-2024 | 511/CDD | 01/06/2023 | 30 | UTTAM KUMAR CHATTERJEE | 18.88 | 0 | 0
637 | Nadia Division | Ranaghat Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Hudachapra to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000106/2024-2025 | 4282/ND | 05/08/2024 | 180 | MANGES INDUSTRIAL CORPORATION | 160.4 | 0 | 0
638 | Nadia Division | Ranaghat Sub-Division | Providing Left-out Functional Household tap Connection including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe and other allied works etc. all complete for augmentation of Huda Chapra W/S Scheme under Ranaghat Sub-Division of Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000296/2023-2024 | 924/RSD | 14/09/2023 | 30 | USHA CONSTRUCTION | 4.95 | 0 | 100
639 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Huda Chapra under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000381/2024-2025 | 1417/RSD | 19/11/2024 | 45 | GITARANI ENTERPRISE | 2.15 | 0 | 100
640 | Nadia Division | Ranaghat Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
641 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 mtr , Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Hudachapra Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000732/2021-2022 | 1288/ND | 17/03/2022 | 60 | USHA CONSTRUCTION | 59.49 | 53.62 | 95
642 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000026/2023-2024 | 1868/ND | 26/04/2023 | 0 | Resource Division | 19.29 | 0 | 0
643 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000051/2022-2023 | 4285/ND | 29/09/2022 | 0 | Resource Division | 0.52 | 0 | 0
644 | Nadia Division | Ranaghat Sub-Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte | Assistant Engineer | Junior Engineer,Junior Engineer 4 | VCH/001242/2021-2022 | 726/PFMS | 30/03/2022 | 0 | HORIZEN | 2.47 | 0 | 0
645 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under HUDA CHAPRA ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. SM/09817 | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000179/2025-2026 | 1116/EMD | 04/06/2025 | 90 | P.K. ENTERPRISE | 17.48 | 0 | 0
646 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Par Niamatpur Ground Based Water Supply Scheme under Ranaghat-I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Parniamatpur Part-III Piped W/S Scheme (Sl.no.26) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000049/2023-2024 | 1450/NAD-I | 26/05/2023 | 15 | SAORSA | 13.01 | 0 | 100
647 | Nadia Arsenic Division I | Nadia Arsenic Division I | Dedicated pipeline connection from Manifold to different directions of Parniamatpur Piped Water Supply Scheme at each part of the command areas at Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000072/2024-2025 | 1531/NAD-I | 23/09/2024 | 135 | SAORSA | 5.89 | 0 | 100
648 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of FHTC and Laying of balanced Pipeline at Gazipur, Tarapur, Girish Nagar, Jhau Mahal, Suresh Nagar under Tarapur GP at Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000079/2025-2026 | 580/NAD-I | 10/07/2025 | 60 | BISWAS CONSTRUCTION | 27.98 | 0 | 0
649 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Radhakantapur Ground Based Water Supply Scheme under Ranaghat-I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Radhakantapur Part-III Piped W/S Scheme (Sl.no.25) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000100/2023-2024 | 1689/NAD-I | 12/07/2023 | 15 | KESHOB ENTERPRISE | 13.04 | 0 | 100
650 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur, Birnagar Part-III at Ranaghat-I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakantapur, Parniamatpur, Birnagar Water Supply Scheme, Repair of 250 cum capacity Over Head Reservoir and other allied works at Tarapur water supply scheme. Repair of Pump House & other units of AIRP and other allied works at Kalaighata water supply scheme Construction of Boundary wall, Toilet, Pathway and other allied work at Kalaighata Water supply Scheme, Repair of Pump House and construction of Boundary Wall and other allied works at Radhakantapur water supply scheme, Repair of Over Head Reservoir and other allied works at Radhakantapur water supply scheme, Construction of Boundary wall, Toilet, Pathway andother allied work at Parniamatpur Water supply Scheme, Repair of 250 cum capacity Over Head Reservoir and other allied works at Parniamatpur water supply scheme, Repairing,Painting of Boundary wall,Toilet,Pathway and other allied works at Birnagar water supply scheme, Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boudary wall, Pump House and AIRP at Birnagar water supply scheme, under Nadia Arsenic Division-I, PHEDte. (Sl.no.02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000101/2023-2024 | 1698/NAD-I | 13/07/2023 | 365 | M/S DIPAK ENTERPRISE | 481.09 | 0 | 100
651 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Radhakantapur Mouza at Ranaghat-I Block by augmentation of Ground Water based PWSS of Radhakantapur water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000106/2022-2023 | 2053/NAD-I | 21/10/2022 | 45 | M/S DIPAK ENTERPRISE | 61.28 | 60.47 | 100
652 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of distribution pipeline at Gazipur & Tarapur Mouzas including balance FHTC connections at Tarapur PWSS at Ranaghat-I Block under Arsenic Division-I,P.H.E. Dte (Sl. No. 10) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000122/2024-2025 | 1924/NAD-I | 22/11/2024 | 320 | BISWAS CONSTRUCTION | 19.11 | 0 | 80
653 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of distribution pipeline at Khrishma, Arshikhra & Birnagar villages for balance FHTC connections under Radhakantapur PWSS at Ranaghat-I Block under Arsenic Division-I,P.H.E. Dte (Sl. No. 09) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000123/2024-2025 | 1925/NAD-I | 22/11/2024 | 300 | CHOWDHURY & CO. | 41.2 | 0 | 100
654 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting works at Paharpur Mouza at Ranaghat-I Block by augmentation of Ground Water Based PWSS of Radhakantapur W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000125/2022-2023 | 3038/NAD-I | 09/11/2022 | 45 | BISWAS CONSTRUCTION | 9.17 | 9.17 | 100
655 | Nadia Arsenic Division I | Nadia Arsenic Division I | Shifting and Laying of Pipeline under Jal Jeevan Mission (JJM) for Ganguly Para, Chatterjee Para and Augmentation works of Parniamatpur by Augmentation of Ground Water based PWSS for Parniamatpur Water Supply Scheme, Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.07) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000158/2023-2024 | 2116/NAD-I | 04/09/2023 | 21 | BUDDHADEV MONDAL | 17.56 | 17.54 | 100
656 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of pipeline at Sahidpally and different Augmentation work of Radhakantapur, Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I Block by Augmentation of Ground Water Based Piped Water Supply Scheme for Radhakantapur W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl.n.08) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000161/2023-2024 | 2119/NAD-I | 04/09/2023 | 21 | M/S DIPAK ENTERPRISE | 65.68 | 65.66 | 100
657 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of pipeline between Majherchar and Sahidpally and different Augmentation works of Tarapur and Kalaighata Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I Block by augmentation of Ground Water based PWSS for Tarapur & Kalaighata under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.13) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000164/2023-2024 | 2122/NAD-I | 04/09/2023 | 21 | M/S DIPAK ENTERPRISE | 96.43 | 96.43 | 100
658 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipeline and other allied works near House of Richa Master at Uttarpara Tarapur Mouza by retrofitting of Ground Water Based PWSS under Ranaghat-I Block by Augmentation of Tarapur Part-III W/S Scheme under Ranaghat-l Block Under Nadia Arsenic Division-I,P.H.E Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000169/2023-2024 | 423/AE-I/NAD-I | 20/09/2023 | 30 | ASHIM ENTERPRISE | 3.72 | 0 | 100
659 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of laying of UPVC pipeline and other allied works near House of Saroda Nath at Kalaighata Mouza under JJM by Augmentation of Ground Water Based PWSS of Kalaighata Part-III W/S Scheme under Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000171/2023-2024 | 419/AE-I/NAD-I | 20/09/2023 | 30 | MRINAL DASGUPTA | 4.76 | 0 | 100
660 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying and restoration of pipeline for functionalities of FHTC connection at Nandighat Village under Perniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000171/2024-2025 | 2026/NAD-I | 03/12/2024 | 120 | JYOTIRMOY ENTERPRISE | 4.99 | 0 | 100
661 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of laying of UPVC pipeline and other allied works from Kalaighata Kheyaghat to Mathpara Kali Mandir at Kalaighata Mouza under JJM by Augmentation of Ground Water Based PWSS of Kalaighata Part-III W/S Scheme under Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000173/2023-2024 | 421/AE-I/NAD-I | 20/09/2023 | 30 | MANARAMA ENTERPRISE | 4.66 | 0 | 100
662 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of laying of UPVC pipeline and other allied works at Parniamatpur Mouza under JJM by Augmentation of Ground Water Based PWSS of Parniamatpur Part-III W/S Scheme under Ranaghat-l Block Under Nadia Arsenic Division-I,P.H.E Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000174/2023-2024 | 422/AE-I/NAD-I | 20/09/2023 | 30 | M/S RANA ENTERPRISE | 3.16 | 0 | 100
663 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipelineat Uttarpara Tarapur Mouza by retrofitting of GRound Water Based PWSS under JJM at Ranaghat-I block by augmentation of Tarpur Part-III W/S Scheme under Nadia Arsenic Division-I,P.H.E Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000175/2023-2024 | 424/AE-I/NAD-I | 20/09/2023 | 30 | KUHELI ENTERPRISE | 4.82 | 0 | 100
664 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipeline at Gazipur Mouza by retrofitting of Ground Water Based PWSS under Ranaghat-I Block by Augmentation of Tarapur Part-III W/S Scheme under Ranaghat-l Block Under Nadia Arsenic Division-I,P.H.E Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000176/2023-2024 | 425/AE-I/NAD-I | 20/09/2023 | 30 | DAFADAR ENTERPRISE | 4.84 | 0 | 100
665 | Nadia Arsenic Division I | Nadia Arsenic Division I | Lyaing of UPVC Pipeline at Sureshnagar, Tarapur Mouza by retrofitting of Ground Water Based PWSS under JJM at Ranaghat-I Block by Augmentation of Tarapur Part-III W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000177/2023-2024 | 426/AE-I/NAD-I | 20/09/2023 | 30 | SAGAR ENTERPRISE | 4.81 | 0 | 100
666 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of laying of UPVC pipeline and other allied works near Colony Para Bridge at Kalaighata Mouza under JJM by Augmentation of Ground Water Based PWSS of Kalaighata Part-III W/S Scheme under Ranaghat-I Block under Nadia Arsenic | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000180/2023-2024 | 420/AE-I/NAD-I | 20/09/2023 | 30 | M/S PHANINDRA NATH ROY | 4.32 | 0 | 100
667 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation Work under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata and Parniamatpur PWSS Part- III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata and Parniamatpur Water Supply Schemes under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000190/2023-2024 | 2205/NAD-I | 13/09/2023 | 25 | M/S R.K. ENTERPRISE | 7.09 | 0 | 100
668 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, PrimarySchool, SSK & MSK under Jal Jeevan Mission (JJM) atRanaghat-I Block underRdahakantapur PWSS underAugmentation of Ground Water Based Water SupplyScheme of Tarapur, Kalaighata, Radhakantapur, Praniamatpur & Birnagar Part-III at Ranaghat-I Block (sl.06) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000212/2022-2023 | 204 /NAD-I | 15/02/2023 | 21 | SATYABRATA CHAKRABORTY | 33.07 | 0 | 35
669 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | RTOR000028/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 9.86 | 0 | 0
670 | Central Drilling | Nadia Arsenic Division I | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 300 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR TARAPUR W/S SCHEME, RANAGHAT-I BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000406/2022-2023 | 1825/CDD | 06/01/2023 | 30 | M/S SAIKAT ENTERPRISE | 15.55 | 10.29 | 0
671 | Eastern Mechanical | Nadia Arsenic Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HALALPUR KRISHNAPUR(Z-I), PAR-NIAMATPUR W/S Scheme, Block- Ranaghat-II , Dist. - Nadia NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000023/2023-2024 | 1602/EMD | 26/04/2023 | 30 | PADMA ENGINEERING CO. | 38.83 | 0 | 50
672 | Eastern Mechanical | Nadia Arsenic Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under RADHAKANTAPUR W/S Scheme, Block-RanaghatII , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No. - 06) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000026/2023-2024 | 1605/EMD | 26/04/2023 | 30 | SWAPAN KUMAR BHANJA | 19.21 | 18.95 | 100
673 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Tarapur, Kalaighata, Radhakantapur, Parniamatpur and Birnagar Part-III under Block_ Ranaghat -I Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/12023) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000162/2025-2026 | 1160/EMD | 04/06/2025 | 90 | PIONEER ELECTRICALS | 21.71 | 0 | 0
674 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XI, Chanduria, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000008/2021-2022 | 772/NAD-I | 04/05/2021 | 60 | M/S NIBHAS SINHA | 95.81 | 155.41 | 100
675 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX within Kaliganj Block (Phase-B) | Assistant Engineer |  | ORD/000090/2021-2022 | 2767/ND | 14/07/2021 | 90 | M/S K.P. CONSTRUCTION | 91.11 | 0 | 0
676 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX, within Kaliganj Block (Phase-A, Retrofitting)" | Assistant Engineer |  | ORD/000268/2020-2021 | 165/ND | 13/01/2021 | 90 | NEERMAN | 95.28 | 1.77 | 0
677 | Nadia Division | Debgram Sub-Division | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Diovision,PHE Dte,Debagram,Nadia with effect from 01.08.2021 to 31.07.2022 | Assistant Engineer |  | ORD/000952/2021-2022 | 399/DSD | 29/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0
678 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) | Assistant Engineer |  | VCH/000522/2021-2022 | 183/PFMS | 15/09/2021 | 0 | NEERMAN | 86.15 | 0 | 0
679 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase- A) | Assistant Engineer |  | VCH/000930/2021-2022 | 484/PFMS | 03/02/2022 | 0 | LEMNISCATE | 0.72 | 0 | 0
680 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block ( Phase -B) | Assistant Engineer |  | ORD/000197/2020-2021 | 4087/ND | 31/12/2020 | 90 | SATYABRATA CHAKRABORTY | 97.02 | 71.87 | 0
681 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000063/2021-2022 | 816/ND | 18/02/2022 | 0 | Resource Division | 16.68 | 0 | 0
682 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000097/2021-2022 | 822/ND | 18/02/2022 | 0 | Resource Division | 13.84 | 0 | 0
683 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- B) | Assistant Engineer |  | VCH/000932/2021-2022 | 486/PFMS | 03/02/2022 | 0 | LEMNISCATE | 0.47 | 0 | 0
684 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTOR | Assistant Engineer |  | VCH/001060/2020-2021 | 459/DW | 30/03/2021 | 0 | SATYABRATA CHAKRABORTY | 59.75 | 0 | 0
685 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) |  |  | ORD/000211/2020-2021 | 283/NAD-I | 03/02/2021 | 90 | KINGS AND CO | 93.82 | 181.06 | 100
686 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.4) | Assistant Engineer |  | ORD/000474/2020-2021 | 888/ND | 19/02/2021 | 90 | UNICON INDIA | 96.71 | 0 | 0
687 | Nadia Division | Debgram Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
688 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000060/2021-2022 | 799/ND | 18/02/2022 | 0 | Resource Division | 11.22 | 0 | 0
689 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.4) | Assistant Engineer |  | VCH/000748/2021-2022 | 351/PFMS | 08/12/2021 | 0 | UNICON INDIA | 64.21 | 0 | 0
690 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-A). | Assistant Engineer |  | VCH/001229/2021-2022 | 595/PFMS | 08/03/2022 | 0 | UNICON INDIA | 21.34 | 0 | 0
691 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Bablari Dewanganj W/S scheme in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000239/2020-2021 | 44/ND | 06/01/2021 | 90 | S.S. ENTERPRISE | 97.07 | 14.72 | 100
692 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000015/2021-2022 | 93/ND | 06/01/2022 | 0 | Resource Division | 7.71 | 0 | 0
693 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000095/2021-2022 | 792/ND | 18/02/2022 | 0 | Resource Division | 3.71 | 0 | 0
694 | Nadia Division | Krishnanagar Sub-Division | PROVIDING FHTC AT BABLARI DEYANGANJ W/S SCHEME UNDER JAL SWAPNO PROGRAM. | Assistant Engineer |  | VCH/000204/2021-2022 | 89/PPMS | 15/07/2021 | 0 | S.S. ENTERPRISE | 44.96 | 0 | 0
695 | Nadia Division | Krishnanagar Sub-Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | Assistant Engineer |  | VCH/000467/2021-2022 | 264/PFMS | 08/10/2021 | 0 | S.S. ENTERPRISE | 35.02 | 0 | 0
696 | Nadia Division | Krishnanagar Sub-Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme. | Assistant Engineer |  | VCH/000991/2020-2021 |  | 24/03/2021 | 0 | S.S. ENTERPRISE | 44.96 | 0 | 0
697 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block ( Phase -A) | Assistant Engineer |  | ORD/000285/2020-2021 | 245/ND | 15/01/2021 | 90 | H I ENTERPRISE | 97.1 | 36.81 | 0
698 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II, Z-IV, NABADWIP BLOCK, PHASE-A. | Assistant Engineer |  | VCH/000880/2021-2022 | 490/PFMS | 03/02/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 0.41 | 0 | 0
699 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT PART-2, Z-4 | Assistant Engineer |  | VCH/001074/2020-2021 | 460/DW | 30/03/2021 | 0 | H I ENTERPRISE | 72.4 | 0 | 0
700 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Ber Ramchandrapur Zone-II W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000215/2020-2021 | 4040/ND | 30/12/2020 | 60 | JOYGOPAL GUPTI | 32.2 | 3.12 | 100
701 | Nadia Division | RWS Nadia Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT BER-RAM CHANRAPUR Z-II | Assistant Engineer |  | VCH/001071/2020-2021 | 460/DW | 30/03/2021 | 0 | JOYGOPAL GUPTI | 22.23 | 0 | 0
702 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Kulgachi W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I, Retrofitting) | Assistant Engineer |  | ORD/000238/2020-2021 | 45/ND | 06/01/2021 | 90 | SHYAMAL SHIL | 92.07 | 56.93 | 0
703 | Nadia Division | Krishnanagar Sub-Division | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Maidanpur ii) Kulgachhi iii) Monipota iv) Habibpur v) Magurkhali. | Assistant Engineer |  | ORD/000480/2022-2023 | 372/ Kly SD-I | 17/03/2023 | 184 | HORIZEN | 4.99 | 0.58 | 10
704 | Nadia Division | Krishnanagar Sub-Division | Providing Functional House Tap Connection from Kulgachi Water Supply Scheme under Jal Swapno Programme | Assistant Engineer |  | VCH/000898/2021-2022 | 534/PFMS | 23/02/2022 | 0 | SHYAMAL SHIL | 54.42 | 0 | 0
705 | Nadia Arsenic Civil Division II |  | Work of Survey, Design, Drawing & DPR preparation for DAMODARKHALI Water Supply Scheme in KRISHNANAGAR-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. |  |  | ORD/000010/2021-2022 | 4/AE-I/NACD-II | 06/05/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 3.88 | 4 | 0
706 | Nadia Arsenic Civil Division II |  | Material Requisition To Resource Division |  |  | RTOR000002/2021-2022 | 852/NACD-II | 03/11/2021 | 0 | Resource Division | 119.54 | 0 | 0
707 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme(Northern Sector), Part-I,Zone-I within Kaliganj Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte. | Assistant Engineer |  | ORD/000221/2020-2021 | 4083/ND | 31/12/2020 | 90 | ALOKE ENTERPRISE | 97.02 | 0.19 | 100
708 | Nadia Division | Debgram Sub-Division | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-03-2021 to 28-02-2022 (250 working days) | Assistant Engineer |  | ORD/000501/2020-2021 | 172/RSD | 22/02/2021 | 365 | SUMAN CHAKRABORTY | 3.85 | 0.75 | 0
709 | Nadia Division | Debgram Sub-Division | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H.E. Dte., Kalyani, Nadia. Period of work 01-03-2022 to 28-02-2023 | Assistant Engineer |  | ORD/000814/2021-2022 | 118/RSD | 28/02/2022 | 250 | SUMAN CHAKRABORTY | 3.85 | 0.97 | 75
710 | Nadia Division | Debgram Sub-Division | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE | Assistant Engineer |  | VCH/000307/2021-2022 | 139/FHTC | 17/08/2021 | 0 | LEMNISCATE | 0.45 | 0 | 0
711 | Nadia Division | Debgram Sub-Division | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE | Assistant Engineer |  | VCH/000311/2021-2022 | 139/FHTC | 17/08/2021 | 0 | LEMNISCATE | 0.48 | 0 | 0
712 | Nadia Division | Debgram Sub-Division | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Division, P.H. Engineering Dte., Debagram, Nadia with effect from 01/08/22 to 31/07/23 | Assistant Engineer |  | ORD/000186/2022-2023 | 312/D/DSD | 29/07/2022 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 1.54 | 70
713 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-IV within Kaliganj block(Phase-B) in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000187/2020-2021 | 3593/ND | 08/12/2020 | 90 | M/S NIBHAS SINHA | 96.81 | 131.5 | 0
714 | Nadia Division | Debgram Sub-Division | Hiring Diesel Maxi Cub having car No WB-51/B-3194 for office of the Assistant Engineer, RWS Nadia Sub-Division, PHE Dte. for the period from 01.08.2021 to 31.07.2022 | Assistant Engineer |  | ORD/000951/2021-2022 | 896/PH | 30/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 100
715 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTORPART-1 Z-4 | Assistant Engineer |  | VCH/001078/2020-2021 | 446/DW | 25/03/2021 | 0 | M/S NIBHAS SINHA | 28.95 | 0 | 0
716 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Sakdaha (Bazarpara) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000015/2020-2021 | 1056/NACD-II | 25/09/2020 | 15 | M/S. ASIT KUMAR BISWAS | 4.98 | 0 | 0
717 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Chakdah Zone-VI (Balia), Part-II at Chakdah Block by retrofitting of Ground Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000096/2021-2022 | 1565/NAD-I | 13/12/2021 | 90 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT LTD. | 214.98 | 204.67 | 100
718 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-IV, Balia (Part-II) at Chak Amdanga, Silinda, Balia, Balarampur village at Chakdah Block retrofitting of Surface Water Based PWSS FOR Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (SL.NO.10) | Assistant Engineer-II | Junior Engineer-IV | ORD/000145/2022-2023 | 3216/NAD-I | 30/11/2022 | 30 | BIDYUT KUMAR | 31.54 | 29.46 | 100
719 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipeline and retrofitting work at different loations i.e; Halalpur Krishnapur ,Madanpur,Goalpur,Beharia and Nabla Mouzas for smooth water supply in coneection with Retrofitting under JJM of Ground Water Based PWSS of Halalpur Krishnapur Zone-I W/S Scheme at Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E Dte.(sl.no.14) | Assistant Engineer-II | Junior Engineer-III | ORD/000014/2023-2024 | 11118 / NAD-I | 27/04/2023 | 21 | CHOWDHURY & CO. | 23.38 | 23.38 | 0
720 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000080/2021-2022 | 1448/NAD-I | 12/11/2021 | 90 | DIVINE | 151.18 | 150.68 | 100
721 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repairing and renovation of Rising main and allied works at Halalpur Krishnapur Zone-I under Ranaghat-II, Block under Halalpur Krishnapur Zone-I Water Supply Scheme in the District of Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000110/2022-2023 | 253/AE-I/NAD-I | 21/10/2022 | 15 | BUDDHADEV MONDAL | 0.93 | 0.92 | 100
722 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipe line at Jaffarnagar ,near Headwork Site under Raghunathpur Hijuli-I Gram Panchayet under Halalpur Zone-I Water Supply Scheme under Ranahghat -II Block under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000113/2022-2023 | 254/AE-I/NAD-I | 21/10/2022 | 15 | BUDDHADEV MONDAL | 0.96 | 0.96 | 100
723 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, pathway and other allied works at Head Work Tubewell site of Ground water based piped supply scheme of Halalpur-Krishnapur Zone-I Piped Water Supply Scheme within Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. Length of Boundary wall - 138 metre. | Assistant Engineer-II | Junior Engineer-III | ORD/000134/2021-2022 | 76/NAD-I | 17/01/2022 | 20 | MONDAL ENTERPRISE | 9.94 | 3.22 | 100
724 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II form Puratan Chapra Primary School to Kharida Chapra Primary School at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000175/2022-2023 | 57/AE-I/NAD-I | 17/01/2023 | 15 | BANERJEE ENTERPRISE | 3.88 | 3.6 | 99
725 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II from Pragati Sangha Club to Purba Para Kalimandir at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000264/2022-2023 | 142/AE-I/NAD-I | 29/03/2023 | 15 | CONSTRUCTURE | 3.63 | 3.63 | 100
726 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II from Purba Para Kalimandir to Paschim Sangha at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000265/2022-2023 | 143/AE-I/NAD-I | 29/03/2023 | 15 | CONSTRUCTURE | 3.38 | 3.38 | 100
727 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000013/2021-2022 | 147/NAD-I | 28/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
728 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work under Jal Jeevan Mission (JJM) for Zone-IX at North, South Chandmari, Muratipur at Kanchrapara G.P. by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) W/S Scheme for Zone-IX, Chandmari, Part-II under Nadia Arsenic Division-I , PHE Dte.(SL.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000056/2023-2024 | 1465/NAD-I | 30/05/2023 | 21 | BUDDHADEV MONDAL | 22.58 | 22.58 | 0
729 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-IX (Chandmari) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000111/2021-2022 | 1613/NAD-I | 28/12/2021 | 90 | SATYABRATA CHAKRABORTY | 248.68 | 247.52 | 100
730 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Chakdah Zone-III (Mosra), Part-II at Chakdah Block by retrofitting of Ground Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000091/2021-2022 | 1539/NAD-I | 06/12/2021 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 214.03 | 212.04 | 100
731 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Gayeshpur, Zone-II at Santipur Block by retrofitting of Ground Water based PWSS for Gayeshpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000059/2021-2022 | 1417/NAD-I | 08/11/2021 | 60 | M/S R.K. ENTERPRISE | 65.48 | 61.93 | 100
732 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of Over Head Reservoir Painting at Gayeshpur Zone II WS Scheme in Santipur Block under NAD- I PHE Dte. (SL. NO. 04) | Assistant Engineer-I | Junior Engineer-II | ORD/000121/2022-2023 | 3024 / NAD-I | 07/11/2022 | 45 | BIDYUT KUMAR | 15.46 | 14.82 | 100
733 | Nadia Division | Krishnanagar Sub-Division | Preparation of DPR for Augmentation for Intake, WTP & Rising Main of Surface Water Based Water Supply Scheme for Northern Sector Part-III in Krishnagar-II & Nabadwip (Part) Block of Nadia District under Nadia Division, PHE Dte.(including Survey, Design and Estimate). | Assistant Engineer |  | ORD/000196/2022-2023 | 4547/ND | 21/10/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 9.35 | 9.35 | 100
734 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" with Utility Shifting of water pipeline in connection to the work under Nadia Highway Division - I PWD (Roads) Dte. along and across Dhubulia Mayapur Road 0.00 Kpm to 11.12 Kpm under Surface Based Water Supply Scheme (Northern Sector part III) under Krishnagar Sub Division under Nadia Divn,PHE Dte. | Assistant Engineer |  | ORD/000455/2021-2022 | 7434/ND | 27/12/2021 | 90 | H I ENTERPRISE | 193.5 | 23.32 | 100
735 | Nadia Division | Krishnanagar Sub-Division | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000722/2024-2025 | 7571/ND | 27/12/2024 | 31 | IMAGIN | 34.21 | 0 | 0
736 | Nadia Division | Krishnanagar Sub-Division | Restoration of impact zone along Dhubulia Mayapur road in connection to the work ¿Providing FHTC by retrofitting Utility Shifting of water pipeline in connection to the work under Nadia Highway Division - I PWD (Roads) Dte. along and across Dhubulia Mayapur Road 0.00 Kpm to 11.12 Kpm under Surface Based Water Supply Scheme (Northern Sector part III) under Krishnagar Sub Division under Nadia Divn,PHE Dte.¿ | Assistant Engineer |  | ORD/000727/2021-2022 | 243/KSD | 11/03/2022 | 7 | H I ENTERPRISE | 4.04 | 3.95 | 99
737 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000001/2021-2022 | 6830/ND | 17/11/2021 | 0 | Resource Division | 99.96 | 0 | 0
738 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000035/2021-2022 | 427/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
739 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000037/2021-2022 | 454/ND | 31/01/2022 | 0 | Resource Division | 2.13 | 0 | 0
740 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000080/2021-2022 | 783/ND | 18/02/2022 | 0 | Resource Division | 10.87 | 0 | 0
741 | Nadia Division | Krishnanagar Sub-Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dhubulia-Mayapur Road 0.00 Kmp to 11.12 kmp under Surface water based water supply scheme (Northern Sector Part-III ) under Krishnagar Sub-division under Nadia Division , PH.E Dte. (Block- Nabadwip and Krishnagar-II) | Assistant Engineer |  | VCH/001118/2021-2022 | 697/PFMS | 28/03/2022 | 0 | H I ENTERPRISE | 146.02 | 0 | 0
742 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara/JalSwapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-I | Junior Engineer-I | ORD/000074/2021-2022 | 1434/NAD-I | 09/11/2021 | 90 | APURBA MANDAL | 117.48 | 115.42 | 100
743 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Rabonbor mouza near Shyamal Biswas house and near Sailen Halder house under Parniamatpur Water Supply Scheme under Ranaghat-I Block under Providing FHTC under Jal Jeevan Mission (JJM) for Parniamatpur Phase-II under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000189/2022-2023 | 86/AE-I/NAD-I | 06/02/2023 | 15 | BISWAS CONSTRUCTION | 4.64 | 4.64 | 100
744 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work under Jal Jeevan Mission (JJM) at Nandighat, Sardarpara & Baganpara under Anulia G.P. under Parniamatpur Phase-II at Ranaghat-I Block by retrofitting Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.06) | Assistant Engineer-I | Junior Engineer-I | ORD/000191/2023-2024 | 2206/NAD-I | 13/09/2023 | 15 | SAORSA | 42.45 | 0 | 100
745 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Nandighat mouza (Jl No 126) under Jal Jeevan Mission (JJM) for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.01) | Assistant Engineer-I | Junior Engineer-I | ORD/000194/2023-2024 | 2240/NAD-I | 21/09/2023 | 21 | GANGULY ENTERPRISE | 11.86 | 0 | 100
746 | Nadia Arsenic Division I | Nadia Arsenic Division I | Charges of entry of household date in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division -I, P.H.E. Dte.(sl.03) | Assistant Engineer-I | Junior Engineer-I | ORD/000250/2022-2023 | 241 / AE-I / NAD-I | 29/09/2022 | 90 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 100
747 | Nadia Arsenic Division I | Nadia Arsenic Division I | Charges of entry of household date in JJM website along with Household Aadhar details and Geo tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(Sl No.-03) | Assistant Engineer-I | Junior Engineer-I | ORD/000282/2022-2023 | 309 / AE-I / NAD-I | 30/12/2022 | 90 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 0
748 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division- I, P.H.E. Dte. for the period from 15.07.2021 to 14.07.2022 i.e. for 1(one) year. | Assistant Engineer-I | Junior Engineer-I | ORD/000321/2021-2022 | 129 /AE-I/NAD-I | 14/07/2021 | 365 | SUMAN CHAKRABORTY | 4.27 | 4.16 | 100
749 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Gravity Type) of capacity 29 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Bankar Dhopadi PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000081/2023-2024 | 2994/ND | 13/07/2023 | 90 | TARUN KUMAR BHATTACHARYA | 70.11 | 0 | 0
750 | Nadia Division | Krishnanagar Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 140 cum, Repair & Renovation of Boundary wall and allied works at 1st and 2nd Pump House at Bankar Dhopadi Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000392/2023-2024 | 5127/ND | 17/11/2023 | 90 | BISWAS CONSTRUCTION | 17.56 | 0 | 80
751 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bankar Dhopadi to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000493/2021-2022 | 65/ND | 05/01/2022 | 75 | M/S S.S ENTERPRISE | 46.02 | 8.09 | 75
752 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000009/2021-2022 | 7453/ND | 27/12/2021 | 0 | Resource Division | 16.14 | 0 | 0
753 | Nadia Division | Krishnanagar Sub-Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Bankar Dhopadi to accomodate FHTC in Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/001126/2021-2022 | 712/PFMS | 30/03/2022 | 0 | M/S S.S ENTERPRISE | 17.59 | 0 | 0
754 | Eastern Mechanical | Nadia Arsenic Civil Division II | Rejuvenation of Khanjipur W/S Scheme in Tehatta- Block of Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000633/2021-2022 | 230 /EMD | 15/02/2022 | 45 | INDIA ENTERPRISE | 5.99 | 5.99 | 100
755 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KHANJIPUR , Block-Tehatta I and TALDAH , Block-Krishnaganj, Bahirgachhi (Z-II) Block-Chapra, Bagakhali (Z-II) W/S Scheme, Block-Tehatta I Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/001777/2022-2023 | 1122/EMD | 16/03/2023 | 30 | ANJAN ENTERPRISE | 46.98 | 0 | 80
756 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Khanjepur HW Site & 2nd Pump House site with Reinforced Barbed Tape,Painting,Plastering, other allied works Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000021/2024-2025 | 144/AE-II/NACD-II | 11/06/2024 | 30 | GHOSH ENTERPRISE | 4.25 | 0 | 100
757 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Tengra & Khanjipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000134/2021-2022 | 862/NACD-II | 08/11/2021 | 45 | PALCON | 47.75 | 47.71 | 100
758 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Khanjipur W/S Scheme in Tehatta-I Block under Nadia Arsenic Civil DivisionII, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000156/2023-2024 | 521/AE-I/NACD-II | 18/12/2023 | 15 | GHOSH ENTERPRISE | 0.97 | 0 | 0
759 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Khanjipur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000174/2023-2024 | 1320/NACD-II | 01/12/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
760 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Relaying of D.I. Pipeline replacing the damaged old UPVC Pipe at Khanjipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000176/2022-2023 | 469/NACD-II | 21/07/2022 | 30 | PAPAN ROY | 6.47 | 5.01 | 100
761 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Khanjipur, Bahadurpur and Mobarakpur PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000181/2024-2025 | 295_AE-II/NACD-II | 30/08/2024 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.87 | 0 | 100
762 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Khanjipur Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000268/2021-2022 | 54/AE-II/NACD-II | 17/02/2022 | 30 | SANJIB BISWAS | 3.86 | 3.84 | 100
763 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Khanjipur & Bagakhali Zone-I, W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000303/2021-2022 | 768./NACD-II | 22/09/2021 | 45 | TARUN KUMAR BHATTACHARYA | 84.44 | 0 | 100
764 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Arsenic cum Iron treatment Plant of Khanjipur PWSS (Capacity- 21 m3/hr) and ancillary works of Rajapur W/s Scheme at Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000340/2023-2024 | 38/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 61.75 | 0 | 70
765 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | RTOR000018/2022-2023 | 539/NACD-II | 12/08/2022 | 0 | Resource Division | 11.62 | 0 | 0
766 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUPPLY & DELIVARY OF MS METIRIALS & ELECTRICAL ACCESORIES INCLUD AB CABLE TO WBSEDCL FOR NEW SERVICES CONNECTION AT PH-II UNDER KHANJEPUR. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000752/2021-2022 |  | 02/02/2022 | 0 | M/S G.P. ENTERPRISE | 7.83 | 0 | 0
767 | Eastern Mechanical | Nadia Arsenic Civil Division II | Rejuvenation of Bahirgachi Zone-II W/S Scheme in chapra block of Nadia, W/O-473/EMD, T.no.06/EMD | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000258/2021-2022 | 473/EMD | 16/03/2022 | 30 | DAS ENTERPRISE | 6.02 | 6.02 | 100
768 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KHANJIPUR , Block-Tehatta I and TALDAH , Block-Krishnaganj, Bahirgachhi (Z-II) Block-Chapra, Bagakhali (Z-II) W/S Scheme, Block-Tehatta I Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/001777/2022-2023 | 1122/EMD | 16/03/2023 | 30 | ANJAN ENTERPRISE | 46.98 | 0 | 80
769 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Bahirgachhi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000098/2021-2022 | 736/NACD-II | 13/09/2021 | 45 | CHAKRABORTTY ENTERPRISE | 50.01 | 50 | 100
770 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000128/2021-2022 | 863/NACD-II | 08/11/2021 | 45 | IJABUL SEKH | 60.77 | 0 | 100
771 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Bahirgachhi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000134/2020-2021 | 274/EE/NACD-II | 22/02/2021 | 21 | SOMNATH CHATTERJEE | 30.67 | 0 | 100
772 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bahirgachhi Zone -II) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000166/2023-2024 | 1294/NACD-II | 23/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
773 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bahirgachhi Zone -II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000172/2023-2024 | 1302/NACD-II | 29/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
774 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Bahirgachi Zone-II 2nd Tube Well Site under Bahirgachi Zone-II Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000201/2024-2025 | 899/AE-I/NACD-II | 10/09/2024 | 150 | M/S FREEDOM CONSTRUCTION | 3.96 | 0 | 100
775 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bahirgachi Zone-II W/S Scheme of Chapra Block Mouza Ramnagar & Mrigipota of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000211/2023-2024 | 612/AE-I/NACD-II | 02/02/2024 | 15 | MALLICK ENTERPRISE | 0.97 | 0 | 100
776 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Path Way & Earth filling at H/w site of Bahirgachhi Zone-II Piped Water Supply Scheme under NACD - II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000239/2021-2022 | 81//AE-I/NACD-II | 27/08/2021 | 15 | SHYAMAL SHIL | 2.77 | 2.77 | 100
777 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bahirgachhi Zone-II (Vill-Mirgipota,Choruitipi) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000258/2022-2023 | 1013/NACD-II | 29/11/2022 | 45 | GHOSH & CO. | 9.65 | 9.34 | 100
778 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bahirgachhi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000274/2021-2022 | 874/NACD-II | 09/11/2021 | 45 | CHAKRABORTTY ENTERPRISE | 17.84 | 17.65 | 100
779 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Arsenic cum Iron treatment Plant of Bahirgachhi Zone-II PWSS (Capacity- 23 m3/hr) and Bhatgachhi PWSS ancillary works of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000361/2023-2024 | 35/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.51 | 0 | 80
780 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Bahirgachhi Zone-II W/s Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000371/2022-2023 | 350/NACD-II | 22/03/2023 | 20 | SAMARESH GHOSH | 0.78 | 0.78 | 100
781 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Huda Chapra Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.E. Dte.(Phase-A) | Assistant Engineer | Junior Engineer 4 | ORD/000205/2021-2022 | 5179/ND | 20/09/2021 | 75 | M/S S.S ENTERPRISE | 70.82 | 3.16 | 100
782 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 4 | RTOR000058/2021-2022 | 810/ND | 18/02/2022 | 0 | Resource Division | 5.23 | 0 | 0
783 | Nadia Division | Ranaghat Sub-Division | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | Assistant Engineer | Junior Engineer 4 | VCH/000799/2022-2023 | 166/PFMS | 26/09/2022 | 0 | M/S S.S ENTERPRISE | 9.37 | 0 | 0
784 | Nadia Division | Ranaghat Sub-Division | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | Assistant Engineer | Junior Engineer 4 | VCH/000922/2021-2022 | 563/PFMS | 25/02/2022 | 0 | M/S S.S ENTERPRISE | 50 | 0 | 0
785 | Nadia Division | Ranaghat Sub-Division | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | Assistant Engineer | Junior Engineer 4 | VCH/001016/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 4.85 | 0 | 0
786 | Nadia Division | Ranaghat Sub-Division | Providing Functional House Tap Connection from Hudachapra Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | Assistant Engineer | Junior Engineer 4 | VCH/001230/2021-2022 | 596/PFMS | 08/03/2022 | 0 | M/S S.S ENTERPRISE | 0.63 | 0 | 0
787 | Nadia Division | Kalyani Sub-Division I | Repairing and renovation of Boundary Wall at Nathna pump house no: 2 (Head Work site) under Nathna w/s zone:1, Tehatta -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000002/2023-2024 | 494/ Kly SD-I | 06/04/2023 | 30 | M/S BISWAS ENTERPRISE | 4.84 | 4.84 | 5
788 | Nadia Division | Kalyani Sub-Division I | Special repair and renovation work at Nathna pump house no: 2(Head work site) under Nathna w/s zone:1, Tehatta -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000003/2023-2024 | 495/ Kly SD-I | 06/04/2023 | 30 | M/S DREAM INFRASTRUCTURE | 2 | 1.94 | 10
789 | Nadia Division | Kalyani Sub-Division I | Special repair and renovation work at Nathna pump house no: 1 under Nathna w/s zone:1, Tehatta -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 496/ Kly SD-1 | 06/04/2023 | 30 | GANGULY ENTERPRISE | 2.37 | 2.25 | 10
790 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- III) at village Nazirpur, Bagadoba, Chhitka, Aztullanagar under Tehatta-I Block to accommodate FHTC under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1805/ND | 22/04/2025 | 180 | M/S DIPAK ENTERPRISE | 71.65 | 0 | 30
791 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution system including specials, valves & pipe supporting structure all complete & providing FHTC at Augmentation of ground water based water supply scheme for Natna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division PHe Dte. | Assistant Engineer | Junior Engineer | ORD/000086/2022-2023 | 3292/ND | 27/07/2022 | 90 | JOY HIND TUBEWELL'S | 172.64 | 0 | 100
792 | Nadia Division | Kalyani Sub-Division I | Laying additional pipe line for distribution system and rising main for Nathna Zone-II PWSS under augmentation of Nathna Zone-II PWSS (Phase-II) under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000352/2024-2025 | 7051/ND | 02/12/2024 | 270 | JOY HIND TUBEWELL'S | 100.01 | 0 | 75
793 | Nadia Division | Kalyani Sub-Division I | Collection of Household data through mobile app for FHTC Connection (Phase-II) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000694/2023-2024 | 208/KLYSD-I | 09/02/2024 | 182 | HORIZEN | 4.85 | 0 | 100
794 | Nadia Division | Kalyani Sub-Division I | Construction and installation of MANIFOLD and allied works at OHR site under Nathna Zone-II Ground Based Water Supply Scheme under Tehatta-I Block under Nadia Division, P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Nathna Zone-II at Tehatta-I Block by Augmentation of Ground Water based PWSS for Nathna Zone-II Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000742/2024-2025 | 420/ND | 27/01/2025 | 240 | NIVEDITA CONSTRUCTION | 22.08 | 0 | 0
795 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000021/2022-2023 | 3524/ND | 05/08/2022 | 0 | Resource Division | 4.6 | 0 | 0
796 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000063/2022-2023 | 4329/ND | 29/09/2022 | 0 | Resource Division | 10.55 | 0 | 0
797 | Nadia Division | Kalyani Sub-Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000356/2022-2023 | 56/PFMS | 22/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.84 | 0 | 0
798 | Nadia Division | Tehatta Sub-Division | Conversion of IEP to AIRP of capacity 30 Cu.m/hr at Kulgachi Water Supply Scheme within Tehatta-II Block block under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000126/2024-2025 | 4575/ND | 21/08/2024 | 180 | B.M. ENGINEERING & CONSTRUCTION | 129.23 | 0 | 0
799 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Pump House ,boundary wall of ground basaedpiped water supply scheme for Kulgachi water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 6837/ND | 12/11/2024 | 90 | DAS CONSTRUCTION | 11.4 | 0 | 0
800 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Kulgachi Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Kulgachi at Tehatta-II Block by Augmentation of Ground Water based PWSS for Kulgachi Water Supply Schemes under | Assistant Engineer | Junior Engineer | ORD/000645/2024-2025 | 7369/ND | 18/12/2024 | 60 | CONSTRUCTURE | 19.15 | 0 | 0
801 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000078/2023-2024 | 2299/ND | 29/05/2023 | 0 | Resource Division | 5.62 | 0 | 0
802 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000192/2022-2023 | 362/ND | 24/01/2023 | 0 | Resource Division | 0.76 | 0 | 0
803 | Nadia Division | Tehatta Sub-Division | Providing FHTC by augmentation under Jal Swapna for Kulgachi PWSS, in Tehatta-II block with in Nadia district under Nadia Division | Assistant Engineer | Junior Engineer | VCH/001138/2021-2022 | 703/PFMS | 30/03/2022 | 0 | HORIZEN | 2.45 | 0 | 0
804 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I and II under Kulgachi WS Scheme, Block KrishnagarI, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-09) | Assistant Engineer | Junior Engineer | ORD/000890/2022-2023 | 158/EMD | 06/01/2023 | 30 | ABHISEK ENGINEERING CONCERN | 16.76 | 0 | 80
805 | Nadia Division | Tehatta Sub-Division | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no 03/2022-central tax rate dt 13.07.2022 for the work of Laying Of Distribution System Including Specials, Valves & Pipe Carrying Structure All Complete, Proposed Augmentation Of Rising Main System, Providing FHTC Including Supplying, Laying, Fitting, Fixing Of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE 100, PN16) Pipe With All Necessary Specials, Saddle Piece Etc., Construction Of 500 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (Excluding Pile Foundation), Pipe Connection And Cost Of Pipes, Specials And Soil Investigation All Complete For Augmentation Of Ground Based Water Supply Scheme At Karimpur Jalangi Zone-IV To Accommodate FHTC Under Tehatta Sub-Divn Under Nadia Divn, PHE Dte." | Assistant Engineer | Junior Engineer | BILL/00219/2024-2025 | 152/PFMS | 31/07/2024 | 0 | UMWELT ENGINEER PVT LTD | 24.01 | 0 | 0
806 | Nadia Division | Tehatta Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 93.44 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-IV to accommodate FHTC within Karimpur-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000083/2024-2025 | 4168/ND | 30/07/2024 | 180 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 244.34 | 0 | 0
807 | Nadia Division | Tehatta Sub-Division | Proposed Augmentation Of Laying Distribution System Of Karimpur-Jalangi Zone-IV [Part-B] under Nadia Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000415/2023-2024 | 5145/ND | 17/11/2023 | 642 | UMWELT ENGINEER PVT LTD | 129.84 | 0 | 100
808 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Karimpur Jalangi Zone-IV Ground Based Water Supply Scheme under Karimpur- I Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Karimpur Jalangi Zone-IV at Karimpur I Block by Augmentation of Ground Water based PWSS for Karimpur Jalangi Zone-IV Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000627/2024-2025 | 7360/ND | 18/12/2024 | 60 | A.K.ADHIKARY | 23.35 | 0 | 0
809 | Nadia Division | Tehatta Sub-Division | Repairing and renovation works of Pump House and allied works of ground based piped water supply scheme for Karimpur Jalangi Zone-IV water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000654/2024-2025 | 7409/ND | 19/12/2024 | 360 | BISHAL CONSTRUCTION | 13.72 | 0 | 90
810 | Nadia Division | Tehatta Sub-Division | Laying of additional pipeline for Hazrakhali, Fulkhali, Betbaria, Marttajapur, Mollahad, Chaugachha, Haripur & Arabpur mouzas under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000831/2024-2025 | 246/ND | 14/01/2025 | 450 | JOY HIND TUBEWELL'S | 153.86 | 0 | 30
811 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000008/2023-2024 | 1851/ND | 26/04/2023 | 0 | Resource Division | 8.39 | 0 | 0
812 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000048/2023-2024 | 1912/ND | 27/04/2023 | 0 | Resource Division | 0.69 | 0 | 0
813 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000172/2022-2023 | 145/ND | 06/01/2023 | 0 | Resource Division | 20.74 | 0 | 0
814 | Nadia Division | Tehatta Sub-Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-IV PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | Assistant Engineer | Junior Engineer | VCH/000205/2022-2023 | 29/PFMS | 20/05/2022 | 0 | RADIANT | 3 | 0 | 0
815 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI (Z-IV, V & XB) W/S Scheme, Block-Karimpur I , Dist. - Nadia. NIET NO. - 33 OF EE/EMD OF 2022-23 (SL. NO. - 03) | Assistant Engineer | Junior Engineer | ORD/001926/2022-2023 | 1198/EMD | 22/03/2023 | 771 | AVINABA ENGINEERING CONCERN | 62.41 | 0 | 80
816 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 450 cum capacity 20 Mtr. staging height RCC Over Head Reservoir & Soil Investigation for Augmentation of Ground Based Water Supply Scheme at Durgapur Chowgacha to accommodate FHTC within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000189/2022-2023 | 4542/ND | 21/10/2022 | 365 | UMWELT ENGINEER PVT LTD, 140 RAJADANGA CHAKRABORTY PARA, 1ST FLOOR, KASBA, KOLKATA-700107. | 615 | 455.29 | 92
817 | Nadia Division | Krishnanagar Sub-Division | Repair & Renovation of Pump House and Construction of Boundary wall and allied works at 1st and 2nd Pump House at Durgapur Chowgacha Water Supply Scheme within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000475/2023-2024 | 153/ND | 09/01/2024 | 420 | NILAY KUMAR BHATTACHARYA | 27.41 | 0 | 100
818 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab for official use for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01.01.2023 (as and when required). | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000486/2022-2023 | 1331/KSD | 29/12/2022 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 100
819 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01/04/2023.(as and when required). | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000591/2022-2023 | 376/KSD | 28/03/2023 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0
820 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 81 m3/hr at Durgapur Chowgacha Water Supply Scheme within Krishnaganj Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000785/2023-2024 | 1897/ND | 15/03/2024 | 180 | MANGES INDUSTRIAL CORPORATION | 227.13 | 0 | 0
821 | Nadia Division | Krishnanagar Sub-Division | Construction and installation of Manifold at OHR site, Providing leftout FHTC with laying of additional distribution system and allied works in connection to the Augmentation of Durgapur Chowgacha Water Supply Scheme under Krishnaganj Block under Nadia Division, P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000809/2024-2025 | 875/ND | 25/02/2025 | 60 | M/S GHOSH CONSTRUCTION | 67.59 | 0 | 10
822 | Nadia Division | Krishnanagar Sub-Division | Construction of Additional Boundary wall and allied works at Headwork Site at Durgapur Chowgacha Water Supply Scheme within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000865/2024-2025 | 1474/ND | 25/03/2025 | 360 | NILAY KUMAR BHATTACHARYA | 15.55 | 0 | 60
823 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000002/2022-2023 | 2159/ND | 18/05/2022 | 0 | Resource Division | 11.58 | 0 | 0
824 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000060/2023-2024 | 2292/ND | 29/05/2023 | 0 | Resource Division | 24.68 | 0 | 0
825 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000095/2023-2024 | 2420/ND | 05/06/2023 | 0 | Resource Division | 12.64 | 0 | 0
826 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000097/2022-2023 | 4928/ND | 25/11/2022 | 0 | Resource Division | 11.62 | 0 | 0
827 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000108/2021-2022 | 1032/ND | 03/03/2022 | 0 | Resource Division | 22.03 | 0 | 0
828 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000140/2021-2022 | 1394/ND | 24/03/2022 | 0 | Resource Division | 28.51 | 0 | 0
829 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000195/2022-2023 | 1003/ND | 10/03/2023 | 0 | Resource Division | 16.45 | 0 | 0
830 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/001069/2021-2022 | 632/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.43 | 0 | 0
831 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC at Pump House No.- I & II under DURGAPUR CHOWGACHA W/S Scheme, Block- Krishnaganj , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 11) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000903/2022-2023 | 413/EMD | 20/01/2023 | 30 | SHRESTHA | 8.93 | 7.54 | 99
832 | Eastern Mechanical | Krishnanagar Sub-Division | Supplementary works to completion of ongoing FHTC-related work under Durgapur Chowgacha W/S Scheme (Block - Krishnaganj), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001718/2023-2024 | 755/EMSD-II | 09/10/2023 | 10 | SHRESTHA | 0.93 | 0 | 100
833 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIA Darappur, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl.No. 03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000013/2022-2023 | 965/NAD-I | 07/07/2022 | 60 | M/S K.P. CONSTRUCTION | 78.62 | 51.82 | 40
834 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House Darrappur Z-VIA under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division -I, P.H.E.Dte. (Sl.no. 06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000038/2022-2023 | 1531/ NAD-I | 30/08/2022 | 45 | MAA LAXMI ENTERPRISE | 17.21 | 17.1 | 100
835 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir, Boundary Wall, Switch Room and other allied works at Balia (Zone-VI) under Chakdah Surface W/S Scheme in Chakdah Block under Nadia Arsenic Division ? I, P. H..E. Dte (SL NO. 04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000066/2023-2024 | 1367/NAD-I | 12/05/2023 | 30 | M/S COSMOPOLITAN TRADERS | 23.55 | 0 | 100
836 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Ballavpur Zone- VII under Surface (Sl.no.07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000098/2022-2023 | 1964 / NAD-I | 14/10/2022 | 45 | D.C. RAKSHIT & SONS INDIA PVT LTD | 29.25 | 28.66 | 100
837 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-VI (BALIA) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000163/2021-2022 | 429/NAD-I | 07/03/2022 | 60 | BIDYUT KUMAR | 87.82 | 81.95 | 100
838 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VII, (Ballavpur), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000177/2021-2022 | 514/NAD-I | 28/03/2022 | 60 | MANGES INDUSTRIAL CORPORATION | 125 | 108.71 | 100
839 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Lakshmipur and Srinagar under Ballavpur W/S Scheme in connection with augmentation of Ballavpur W/S Scheme under Chakdah (Part) W/S Scheme under JJM under NadiaArsenic Division-I, PHE Dte. (sl.no.18) | Assistant Engineer-II | Junior Engineer-IV | ORD/000200/2023-2024 | 2243/NAD-I | 21/09/2023 | 15 | MANGES INDUSTRIAL CORPORATION | 9.54 | 0 | 100
840 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000009/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 14.93 | 0 | 0
841 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation Work of Zone-IV (Uttar Duttapara) Part-III under JJM in connection with Surface Water based PWSS for Haringhata and Chakdah (Part) in Haringhata Block under Nadia Arsenic Division-I, P.H.E. Dte(sl.03) | Assistant Engineer-I | Junior Engineer-I | ORD/000029/2023-2024 | 1253 / NAD-I | 04/05/2023 | 30 | CHOWDHURY & CO. | 95.64 | 95.19 | 0
842 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work for Balance Portion of Zone-XI (Birohi) and Zone-III (Jalkar Bhomra) in connection with Augmentation of Zone-III (Jalkar Bhomra) Part-III at Haringhata Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.1) | Assistant Engineer-I | Junior Engineer-I | ORD/000039/2023-2024 | 237 /AE-I/NAD-I | 18/05/2023 | 7 | BUDDHADEV MONDAL | 4.81 | 4.81 | 0
843 | Nadia Arsenic Division I | Nadia Arsenic Division I | Shifting and Laying of D.I. (K9) Pipes at Kalyani More along (NH-34) in connection with Augmenation of Zone-IV (Uttar Duttapara) Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.02) | Assistant Engineer-I | Junior Engineer-I | ORD/000040/2023-2024 | 238 /AE-I/NAD-I | 18/05/2023 | 7 | BUDDHADEV MONDAL | 4.56 | 4.56 | 0
844 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 900 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House at Jalkar Bhomra, Zone-III under Surface W/S Scheme of Haringhata-Chakdah Part under NAD I PHE Dte (Sl.no.09) | Assistant Engineer-I | Junior Engineer-I | ORD/000071/2022-2023 | 1702 / NAD-I | 09/09/2022 | 60 | GHOSH CONSTRUCTION | 33.26 | 30.48 | 100
845 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC Pipeline at different locations of Jalkar Bhomra(Zone-III),Madanpur(Zone-XII) and Birohi(Zone-XI) under Kastodanga-I & II, Madanpur-I & II and Birohi-I G.P. respectively under Haringhata & Chakdah (Part) Surface Water Supply scheme Under Nadia Arsenic Division-I,PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000077/2022-2023 | 89/ AE-I/NAD-I | 28/04/2022 | 15 | AVINABA ENGINEERING CONCERN | 4.82 | 4.82 | 100
846 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-III (Jalkar Bhomra) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte ( Sl No. 08) | Assistant Engineer-I | Junior Engineer-I | ORD/000157/2021-2022 | 424/NAD-I | 07/03/2022 | 60 | MONDAL ENTERPRISE | 90.02 | 84.48 | 100
847 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-IV (Uttar Duttapara) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl. NO. 09) | Assistant Engineer-I | Junior Engineer-I | ORD/000158/2021-2022 | 425/NAD-I | 07/03/2022 | 60 | SARKAR AGENCY | 91.65 | 91.25 | 100
848 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofiting of work in Kastodanga -II, G.P. at Jalkar Bhomra (Zone-III) under Surface Water based PWSS for arsenic affected areas of Haringhata and Chakdah (Part) Block under Nadia Arsenic Division -I P.H.E. Dte. (Sl No.-06) | Assistant Engineer-I | Junior Engineer-I | ORD/000170/2022-2023 | 166 /AE-I/ NAD-I | 04/07/2022 | 15 | MONDAL ENTERPRISE | 4.84 | 4.84 | 100
849 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) and Recoonection at Ayeshpur,Sonakhali at Birohi-I G.P & Dakshin Rajapur at Birohi-II G.P under Jal Jeevan Mission (JJM) for Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Birohi under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000203/2023-2024 | 463/AE-I/NAD-I | 05/10/2023 | 30 | MANAJIT BISWAS | 3.99 | 0 | 100
850 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 600 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Uttar Duttapara, Zone-IV under Surface W/S Scheme of Haringhata-Chakdah (Part) under JJM under Nadia Arsenic Division - I P. H.E. Dte (sl.21) | Assistant Engineer-I | Junior Engineer-I | ORD/000266/2022-2023 | 830/NAD-I | 31/03/2023 | 21 | MS MAA BHABANI ENTERPRISE | 24.42 | 24.38 | 100
851 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SHYAMNAGAR(Block-Krishnaganj), MOBARAKPUR(Block-Tehatt-I), PATHARGHAT(Block-Tehatt-I) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000007/2023-2024 | 1505/EMD | 18/04/2023 | 30 | DIPALI CONSTRUCTION | 19.37 | 0 | 90
852 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SHYAMNAGAR(Block-Krishnaganj), MOBARAKPUR(Block-Tehatt-I), PATHARGHAT(Block-Tehatt-I) W/S Scheme, Dist. - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001482/2023-2024 | 1505/EMD. | 18/04/2023 | 30 | DIPALI CONSTRUCTION | 19.37 | 6.37 | 80
853 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD and allied works at OHR site under Mobarakpur Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II, P.H.E Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000066/2024-2025 | 721/NACD-II | 07/06/2024 | 296 | GHOSH ENTERPRISE | 19.42 | 0 | 100
854 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Mobarakpur Water Supply Scheme in Tehatta-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000076/2023-2024 | 330/1/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.68 | 0 | 100
855 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Mobarakpur W/s Scheme (Vill - Haripur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000126/2020-2021 | 268/NACD-II | 22/02/2021 | 21 | SANJIB DEY | 30.48 | 0 | 100
856 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Mobarakpur W/s Scheme (Vill - Mobarakpur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000128/2020-2021 | 267/NACD-II | 22/02/2021 | 21 | CHANDAN ROY | 30.39 | 0 | 100
857 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-II Block of Nadia District through Jadavpur University. (Name of PWSS Barnia) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000160/2023-2024 | 1271/NACD-II | 09/11/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 0 | 100
858 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Mobarakpur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000164/2023-2024 | 1278/NACD-II | 14/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
859 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000232/2021-2022 | 982/EE/NACD-II | 27/12/2021 | 45 | M/S. R.K.ENTERPRISE | 152.25 | 137.15 | 100
860 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Mobarakpur 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000267/2021-2022 | 52/AE-II/NACD-II | 17/02/2022 | 30 | MUKHERJEE CONSTRUCTION | 3.47 | 3.44 | 100
861 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Mobarakpur, Binodnagar & Taranipur Water Supply Scheme of capacity 93 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000282/2023-2024 | 152/NACD-II | 02/02/2024 | 598 | B.M. ENGINEERING & CONSTRUCTION | 241.81 | 0 | 0
862 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mobarakpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000315/2021-2022 | 173/NACD-II | 21/03/2022 | 90 | PATHIK PABAN NANDI | 98.64 | 98.42 | 100
863 | Nadia Division | RWS Nadia Sub-Division | Continuation of Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer Ranaghat - I Block | ORD/000050/2024-2025 | 3445/ND | 20/06/2024 | 30 | IMAGIN | 20.46 | 0 | 100
864 | Nadia Division | RWS Nadia Sub-Division | Continuation for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer Ranaghat - I Block | ORD/000095/2024-2025 | 4141/ND | 29/07/2024 | 45 | IMAGIN | 19.44 | 0 | 100
865 | Nadia Division | RWS Nadia Sub-Division | Continuation for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer Ranaghat - I Block | ORD/000157/2024-2025 | 4689/ND | 28/08/2024 | 45 | IMAGIN | 19.44 | 0 | 100
866 | Nadia Division | RWS Nadia Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer Ranaghat - I Block | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
867 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Ranaghat - I Block | RTOR000013/2021-2022 | 96/ND | 06/01/2022 | 0 | Resource Division | 9.75 | 0 | 0
868 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Ranaghat - I Block | RTOR000082/2021-2022 | 784/ND | 18/02/2022 | 0 | Resource Division | 5.49 | 0 | 0
869 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Ranaghat - I Block | RTOR000130/2021-2022 | 1258/ND | 16/03/2022 | 0 | Resource Division | 8.29 | 0 | 0
870 | Nadia Division | RWS Nadia Sub-Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone I | Assistant Engineer | Junior Engineer Ranaghat - I Block | VCH/001061/2021-2022 | 619/PFMS | 14/03/2022 | 0 | UMWELT ENGINEERS PVT LTD | 3.96 | 0 | 0
871 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 300 cum capacity 20 mtr. staging height RCC Over Head reservoir (Excluding pile Foundation), pipe connection and cost of pipes, specials and soil investigation all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-V to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000178/2022-2023 | 4386/ND | 13/10/2022 | 1176 | APURBA MANDAL | 339.55 | 242.54 | 95
872 | Nadia Division | Tehatta Sub-Division | Repairing and renovation works of Pump House and allied works of ground based piped water supply scheme for Karimpur Jalangi Zone-V water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000375/2024-2025 | 7060/ND | 04/12/2024 | 90 | BANERJEE ENTERPRISE | 12.66 | 0 | 0
873 | Nadia Division | Tehatta Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-5 W/S Scheme in Karimpur-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000399/2021-2022 | 314/TSD | 24/11/2021 | 30 | RADIANT | 2.98 | 2.98 | 100
874 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Karimpur Jalangi Zone-V Ground Based Water Supply Scheme under Karimpur I Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Karimpur Jalangi Zone-V at Karimpur I Block by Augmentation of Ground Water based PWSS for Karimpur Jalangi Zone-V Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000750/2024-2025 | 456/ND | 29/01/2025 | 60 | DEL DELTA CONSTRUCTION | 23.39 | 0 | 0
875 | Nadia Division | Tehatta Sub-Division | Laying of additional pipeline for Hazrakhali, Fulkhali, Betbaria, Marttajapur, Mollahad, Chaugachha, Haripur & Arabpur mouzas under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000831/2024-2025 | 246/ND | 14/01/2025 | 450 | JOY HIND TUBEWELL'S | 153.86 | 0 | 30
876 | Nadia Division | Tehatta Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 49.81 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-V to accommodate FHTC under Tehatta Sub-division under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000835/2024-2025 | 4353/ND | 07/08/2024 | 180 | G.D. CONSTRUCTION AND CO. | 181.93 | 0 | 0
877 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000054/2023-2024 | 2283/ND | 29/05/2023 | 0 | Resource Division | 16.79 | 0 | 0
878 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000109/2022-2023 | 5285/ND | 19/12/2022 | 0 | Resource Division | 31.89 | 0 | 0
879 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI (Z-IV, V & XB) W/S Scheme, Block-Karimpur I , Dist. - Nadia. NIET NO. - 33 OF EE/EMD OF 2022-23 (SL. NO. - 03) | Assistant Engineer | Junior Engineer | ORD/001926/2022-2023 | 1198/EMD | 22/03/2023 | 771 | AVINABA ENGINEERING CONCERN | 62.41 | 0 | 80
880 | Nadia Division | Debgram Sub-Division | Repairing of HDPE pipeline at raw water rising main at Kashiadanga Intake point site, Gotpara site & Bypass connection system for different OHR site including with all necessary specials, valves all complete for Northern Sector Part-II under Nakashipara Block of Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000140/2025-2026 | 2976/ND | 25/06/2025 | 90 | BANERJEE CONSTRUCTION | 22.06 | 0 | 20
881 | Nadia Division | Debgram Sub-Division | Survey, Design, Construction, Supply, Erection & Commissioning of Raw Water Intake Structure (Floating Barge type), Pump House for drawing 34.52 MLD raw water from the river Hooghly with all related accessories, Substation Building with Laying of 700mm dia. DI(K9) Raw Water Pipe Line from Intake Pump House and connecting to the existing raw water main (Approx. 3450 Mtr. length), River Bank Protection works, Boundary Wall, Internal Road and Surface Water Drainage system at the Intake point on EPC-turnkey basis including 3(Three) months trial run & 6 (Six) months defect liability period and 5 (Five) year subsequent Operation and Maintenance complete for the surface water based water supply scheme for arsenic affected Block of Nakashipara in the district Nadia under PHE Dte | Assistant Engineer | Junior Engineer | ORD/000367/2023-2024 | 4774/ND | 16/10/2023 | 366 | TRADERS AND ENGINEERS PRIVATE LIMITED | 1551.6 | 0 | 7
882 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000006/2024-2025 | 6973/ND | 21/11/2024 | 0 | Resource Division | 356.75 | 0 | 0
883 | Eastern Mechanical | Debgram Sub-Division | Dismantling the existing Electro-Mechanical system from Barge and re-installation on the newly constructed Barge by providing axially split casing pumping machinery for the Surface based water supply scheme for Arsenic affected block of Nakashipara in the district of Nadia. | Assistant Engineer | Junior Engineer | ORD/000064/2024-2025 | 1541/EMD | 12/06/2024 | 183 | TRADERS & ENGINEERS PVT. LTD. | 108.54 | 0 | 0
884 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of capacity 156 m3/hr at Mahisura Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000255/2024-2025 | 6571/ND | 21/10/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 348.3 | 0 | 0
885 | Nadia Division | Krishnanagar Sub-Division | Proposed Augmentation of Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 1 No. Pump House at proposed Head Work site & Tube Well site, Construction of R.C.C. Elevated Reservoir of 900 Cum capacity (including pile foundation), and Soil Investigation for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Mahisura (Phase-II) to accommodate FHTC within Nabadwip Block under Krishnanagar Sub-division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000536/2022-2023 | 1385/ND | 29/03/2023 | 1009 | M/S GHOSH CONSTRUCTION, SUKUL ROAD,P.O.-KRISHNAGAR, DIST. NADIA, PIN-741101, WB | 401.97 | 38.02 | 40
886 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including Specials, Valves and Pipe Supporting Structure for providing FHTC in connection to Augmentation of Ground Water Based Piped Water Supply Scheme of Mahisura (Phase-II) in Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000708/2023-2024 | 1298/ND | 23/02/2024 | 90 | PATHIK PABAN NANDI | 63.92 | 0 | 80
887 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000049/2023-2024 | 1997/ND | 08/05/2023 | 0 | Resource Division | 30.69 | 0 | 0
888 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000051/2023-2024 | 1997/ND | 08/05/2023 | 0 | Resource Division | 31.11 | 0 | 0
889 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000089/2023-2024 | 2319/ND | 29/05/2023 | 0 | Resource Division | 24.61 | 0 | 0
890 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000154/2022-2023 | 126/ND | 05/01/2023 | 0 | Resource Division | 30.06 | 0 | 0
891 | Central Drilling | Krishnanagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Mahisunra W/S Scheme (Phase-II,T/W-I& II) , Nabadwip Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000072/2023-2024 | 510/CDD | 01/06/2023 | 30 | UNIVERSAL ENTERPRISES | 37.73 | 0 | 10
892 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISUNRA W/S Scheme, Block-NABADWIP, PALASIPARA W/S Scheme, Block-Tehatta-II AND TOPLA W/S Scheme, Block-Karimpur-II Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No. - 05) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001011/2022-2023 | 499/EMD | 24/01/2023 | 30 | WEST BENGAL ENGINEERING CO. | 90.14 | 6.39 | 15
893 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC under Barnia (Source Augmentation, Abhaynagar) ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000029/2025-2026 | 699/EMD | 04/04/2025 | 30 | SMILE | 10.79 | 0 | 0
894 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001768/2022-2023 | 1120/EMD | 16/03/2023 | 30 | B.T. PROJECTS PVT. LTD | 91.82 | 0 | 60
895 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Exigent Repair of Pipeline due to construction stotm water drain by PRI Body at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000005/2024-2025 | 683/AE-I/NACD-II | 03/04/2024 | 15 | USHA CONSTRUCTION | 0.96 | 0 | 100
896 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly Introduced hydraulics at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000006/2024-2025 | 685/AE-I/NACD-II | 03/04/2024 | 15 | SANJIB BISWAS | 0.97 | 0 | 100
897 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Technical framework for Conclusive ATR Regarding WBCMRO Grievance portal at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000007/2024-2025 | 686/AE-I/NACD-II | 03/04/2024 | 15 | SANJIB BISWAS | 0.97 | 0 | 100
898 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Supply of 15mm x 10mm dia M.S Bush under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000027/2022-2023 | 15/AE-I/NACD-II | 12/04/2022 | 5 | JOY HIND TUBEWELLS | 4.94 | 4.94 | 100
899 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Wall writing work in various Gram Panchayats in Tehatta-II Block at Barnia PWSS under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000046/2024-2025 | 757/AE-I/NACD-II | 19/06/2024 | 15 | IMAGIN | 0.93 | 0 | 100
900 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Switch Room (3.50 mtr x 2.70 mtr) in Barnia Public Water Suply Scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000069/2025-2026 | 108/AE-I/NACD-II | 04/06/2025 | 60 | M/S RAJESH CONSTRUCTION | 3.28 | 0 | 0
901 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000080/2025-2026 | 736/NACD-II | 18/06/2025 | 90 | JOY HIND TUBEWELLS | 186.42 | 0 | 40
902 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of flow control devices in the closed water conduit at Barnia PWSS in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000130/2025-2026 | 223/AE-I/NACD-II | 01/09/2025 | 20 | MAKALI ENGINEERING CORPORATION | 4.79 | 0 | 100
903 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD and allied works at OHR site under Barnia Piped Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000137/2023-2024 | 1304/NACD_II | 30/11/2023 | 30 | USHA CONSTRUCTION | 25.6 | 0 | 100
904 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Structural Health assesment of existing shaft type OHR of Tehatta-II Blocks ( and ancillary structures conducting Non-Destructive test and through visual observation under Nadia Arsenic Civil Division-II P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000148/2023-2024 | 1428/NACD-II | 15/12/2023 | 30 | SIRCON ENGINEERING SERVICE | 7.77 | 0 | 100
905 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 50 m3/hr capacity Iron Elimination Plant at Mouza Abhaynagar underBarnia Public Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000162/2024-2025 | 1127/NACD-II | 21/08/2024 | 601 | PAPAN ROY | 23.07 | 0 | 60
906 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly Introduced hydraulics at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000182/2023-2024 | 528/AE-I/NACD-II | 18/12/2023 | 15 | SANJIB BISWAS | 0.97 | 0 | 100
907 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Provisioning of solution as per CMRO Grievance in all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000183/2023-2024 | 529/AE-I/NACD-II | 18/12/2023 | 15 | USHA CONSTRUCTION | 0.97 | 0 | 100
908 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Technical framework for Conclusive ATR Regarding WBCMRO Grievance portal at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000184/2023-2024 | 530/AE-I/NACD-II | 18/12/2023 | 15 | SANJIB BISWAS | 0.97 | 0 | 100
909 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Exigent Repair of Pipeline due to construction stotm water drain by PRI Body at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000185/2023-2024 | 531/AE-I/NACD-II | 18/12/2023 | 15 | USHA CONSTRUCTION | 0.97 | 0 | 100
910 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection 13 numbers at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000194/2023-2024 | 556/AE-I/NACD-II | 10/01/2024 | 15 | USHA CONSTRUCTION | 0.97 | 0 | 100
911 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair and also DI Laying in distribution at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000211/2021-2022 | 993/NACD-II | 30/12/2021 | 45 | J.D.J. ENTERPRISE | 98.17 | 16.24 | 100
912 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 50 m3/hr capacity Iron Elimination Plant at Mouza UjirPur underBarnia Public Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000212/2024-2025 | 1306/NACD-II | 20/09/2024 | 364 | USHA CONSTRUCTION | 22.96 | 0 | 60
913 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | ContinuationWork order for Supply of CIDF Sluice, Non return valves and DI Mechanical collar Vavle for relaying of rising main of Barnia Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000224/2021-2022 | 212/AE-I/NACD-II | 20/01/2022 | 7 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.96 | 4.96 | 100
914 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Mouza Ujirpur under Barnia Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000237/2024-2025 | 1390/NACD-II | 22/10/2024 | 135 | GENUINE | 10.41 | 0 | 100
915 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Relaying of D.I. Pipeline replacing the damaged old UPVC Pipe at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000241/2021-2022 | 98/NACD-II | 10/02/2022 | 45 | PRABIR KUMAR ROY | 14.31 | 0 | 100
916 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000254/2021-2022 | 117/NACD-II | 15/02/2022 | 90 | M/S. R.K.ENTERPRISE | 173.44 | 0 | 100
917 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Barnia Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000280/2021-2022 | 235/AE-I/NACD-II | 17/02/2022 | 30 | SAMAR ENTERPRISE | 4.7 | 4.61 | 100
918 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum Chlorine room with sanitary and water supply arrangement at Ujirpur mouza in Barnia Piped water supply scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II, PHE Dte. Dist- Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000302/2024-2025 | 1468/NACD-II | 11/11/2024 | 179 | PRADIP KUMAR BANIK | 6.23 | 0 | 100
919 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000307/2021-2022 | 42/NACD-II | 17/01/2022 | 45 | NILAY KUMAR BHATTACHARYA | 21.05 | 0 | 100
920 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repairing of Filter units Solar Powered Community Water Purification plant at site 'Border Out post (BOP) Gede of 54 BN BSF' | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000310/2021-2022 | 282/AE-I/NACD-II | 04/03/2022 | 5 | JOY HIND TUBEWELLS | 4.98 | 4.98 | 100
921 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repairing of Filter units Solar Powered Community Water Purification plant at site 'Border Out post (BOP) Gede of 54 BN BSF' | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000311/2021-2022 | 283/AE-I/NACD-II | 04/03/2022 | 5 | JOY HIND TUBEWELLS | 4.98 | 4.98 | 100
922 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of 15mm x 10mm MS Bush (26000 nos.) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000312/2021-2022 | 284/AE-I/NACD-II | 04/03/2022 | 5 | JOY HIND TUBEWELLS | 4.94 | 4.94 | 100
923 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Barnia Water Supply Scheme of capacity 160 Cu.m/hr in Tehatta-II Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000321/2023-2024 | 218/NACD-II | 16/02/2024 | 421 | MONDAL PRECISION PRIVATE LIMITED | 363.16 | 0 | 20
924 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work order for Structural Health assesment of existing shaft type OHR of Tehatta-II Blocks ( and ancillary structures conductingNon-Destructive test and through visual observation under Nadia Arsenic Civil Division-II P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000327/2023-2024 | 114/NACD-II | 29/01/2024 | 30 | SIRCON ENGINEERING SERVICE | 0.69 | 0 | 0
925 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Provisioning of hydraulics as per IS 4985 with latest edition at within the command area of Barnia W/s Scheme at Tehatta II Development Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000329/2023-2024 | 557_AE-I/NACD-II | 10/01/2024 | 15 | USHA CONSTRUCTION | 0.97 | 0 | 100
926 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Abhaynagar and Ujirpur and Komthana mouza of Barnia W/s Scheme of Tehatta-2 Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000334/2024-2025 | 1608/NACD-II | 16/12/2024 | 270 | USHA CONSTRUCTION | 153.16 | 0 | 50
927 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Provisioning of solution as per CMRO Grievance in all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000366/2023-2024 | 669/AE-I/NACD-II | 18/03/2024 | 15 | USHA CONSTRUCTION | 0.97 | 0 | 100
928 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection 13 numbers at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000367/2023-2024 | 670/AE-I/NACD-II | 18/03/2024 | 15 | USHA CONSTRUCTION | 0.97 | 0 | 100
929 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Provisioning of hydraulics as per IS 4985 with latest edition at within the command area of Barnia W/s Scheme at Tehatta II Development Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000368/2023-2024 | 671/AE-I/NACD-II | 18/03/2024 | 15 | USHA CONSTRUCTION | 0.96 | 0 | 100
930 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum Chlorine room with sanitary and water supply arrangement at Abhaynagar mouza in Barnia Piped water supply scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II, PHE Dte. Dist- Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000379/2024-2025 | 48/NACD-II | 10/01/2025 | 270 | NAMDAR ALI | 6.22 | 0 | 100
931 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-I W/s Scheme (Vill- Sahapur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. & Barnia Pwss under Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000406/2021-2022 | 128_NACD-II | 21/02/2022 | 90 | M/S NANDY ENTERPRISES | 102.45 | 0 | 100
932 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000008/2021-2022 | 167 | 17/03/2022 | 0 | Resource Division | 20.91 | 0 | 0
933 | Nadia Division | Krishnanagar Sub-Division | Proposed Augmentation of Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 1 No. Pump House at proposed Head Work site & Tube Well site, Construction of R.C.C. Elevated Reservoir of 750 Cum capacity (including pile foundation), and Soil Investigation for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Bhimpur (Phase-II) to accommodate FHTC within Krishnagar-I Block under Krishnanagar Sub-division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000151/2023-2024 | 3218/ND | 26/07/2023 | 366 | SINGHA ROY & CO. | 339.59 | 0 | 0
934 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 136 m3/hr at Bhimpur Water Supply Scheme within Krishnagar-I Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000194/2024-2025 | 6221/ND | 23/09/2024 | 180 | GHOSH ENTERPRISE | 315.76 | 0 | 0
935 | Nadia Division | Krishnanagar Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
936 | Nadia Division | Krishnanagar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
937 | Nadia Division | Krishnanagar Sub-Division | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bhimpur Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000476/2023-2024 | 154/ND | 09/01/2024 | 358 | SUNIL KUMAR DATTA | 12.15 | 0 | 100
938 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000149/2023-2024 | 260/ND | 11/01/2024 | 0 | Resource Division | 16.52 | 0 | 0
939 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000150/2022-2023 | 84/ND | 05/01/2023 | 0 | Resource Division | 106.78 | 0 | 0
940 | Central Drilling | Krishnanagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Bhimpur (Phase-II) W/S Scheme (TW-I) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000109/2023-2024 | 1654/CDD | 17/10/2023 | 30 | MENAKA ENTERPRISE | 18.88 | 0 | 0
941 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANPUR W/S Scheme, Block- Krishnaganj, ARABPUR W/S Scheme, Block-Karimpur, BHIMPUR W/S Scheme, Block-Krishnagar AND MONIPOTA W/S Scheme, Block- Krishnagar-I, Dist. - Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001444/2023-2024 | 5127/EMD | 04/09/2023 | 666 | C.M.S. ENGINEERING CONCERN. | 70.97 | 0 | 12
942 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 900 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Tarinipur, Zone-VIII under Surface W/S Scheme of Haringhata- Chakdah (Part) under Nadia Arsenic Division-I PHE Dte (Sl.no.08) | Assistant Engineer-II | Junior Engineer-III | ORD/000058/2022-2023 | 1639 / NAD-I | 06/09/2022 | 60 | REAL TIME | 33.3 | 30.74 | 100
943 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Kumarpur, Zone-VII under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I P.H.E Dte. (Sl. No. 12) | Assistant Engineer-II | Junior Engineer-III | ORD/000103/2022-2023 | 2064/NAD-I | 28/10/2022 | 45 | GANGULY ENTERPRISE | 13.95 | 13.92 | 100
944 | Nadia Arsenic Division I | Nadia Arsenic Division I | Shifting of different dia D.I pipe and HDPE Pipe from the Office Premises of Nadia Arsenic Division -I to nearest Zone-VIII (Tarinipur) OHR site under Haringhata and Chakdah (Part) Surface Based W/S Scheme at Chakdah Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000135/2022-2023 | 267/AE-I/NAD-I | 09/11/2022 | 15 | BUDDHADEV MONDAL | 3.46 | 3.46 | 100
945 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-VIII (Tarinipur) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 06) | Assistant Engineer-II | Junior Engineer-III | ORD/000155/2021-2022 | 422/NAD-I | 07/03/2022 | 60 | M/S K.P. CONSTRUCTION | 73.17 | 67.83 | 100
946 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone- VII, Kumarpur Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 15) | Assistant Engineer-II | Junior Engineer-III | ORD/000172/2021-2022 | 439/NAD-I | 07/03/2022 | 45 | MALI CONSTRUCTION | 39.65 | 39.62 | 100
947 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work at Zone-VIII (Tarinipur) under Augmentation work of Zone-VII (Kumarpur) and Zone-VIII (Tarinipur), Part-III at Santipur Block under Surface Water Based PWSS for Haringhata & Chakdah(Part) under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000197/2023-2024 | 2242/NAD-I | 21/09/2023 | 15 | NISHITH BANERJEE | 12.9 | 0 | 100
948 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC Pipeline and other allied works under JJM at Khalderpara, Babudangapara for Kumarpur Zone-VII at Haringhata Block by retrofitting work of Surface based W/S Scheme Water PWSS of Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000242/2023-2024 | 529/AE-I/NAD-I | 24/11/2023 | 30 | M/S K..M. ENTERPRISE | 4.36 | 0 | 100
949 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) incluidng restoration of road for Tarinipur at Sarati G.P. at Kalyani under Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000243/2023-2024 | 530/AE-I/NAD-I | 24/11/2023 | 30 | M/S S.K ENTERPRISE | 4.85 | 0 | 100
950 | Nadia Division | Ranaghat Sub-Division | Providing leave out functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Fulia Township Zone-I to accommodate FHTC in Santipur block and allied works of Badkulla Zone II of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000018/2025-2026 | 1804/ND | 22/04/2025 | 180 | APURBA MANDAL | 64.83 | 0 | 90
951 | Nadia Division | Ranaghat Sub-Division | Construction of R.C.C Elevated Reservoir of 700 Cum. Capacity of staging height 20M at Head works site with Annular combined pile raft foundation for Badkulla Zone-II Water Supply Scheme under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000084/2025-2026 | 2523/ND | 29/05/2025 | 365 | SATYABRATA CHAKRABORTY | 164.42 | 0 | 0
952 | Nadia Division | Ranaghat Sub-Division | Construction of 125.00 Cum/Hr capacity Arsenic-cum-Iron Removal plant at Badkulla -II Water Supply Scheme under Ranaghat Sub-Division under Nadia Division PHED. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000104/2024-2025 | 4280/ND | 05/08/2024 | 180 | MANGES INDUSTRIAL CORPORATION | 303.09 | 0 | 0
953 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of OHR all complete for augmentation of Ground Water Based Water Supply Scheme for Badkulla Zone-II to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000149/2023-2024 | 3216/ND | 26/07/2023 | 366 | SATYABRATA CHAKRABORTY | 371.16 | 0 | 50
954 | Nadia Division | Ranaghat Sub-Division | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-1 site at Badkulla Zone-II Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000222/2024-2025 | 1186/RSD | 25/09/2024 | 75 | AVIRUP CONSTRUCTION | 4.46 | 0 | 90
955 | Nadia Division | Ranaghat Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
956 | Nadia Division | Ranaghat Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Badkulla Zone-II W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000436/2021-2022 | 1056/RSD | 02/12/2021 | 30 | RADIANT | 3.29 | 2.97 | 100
957 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000009/2024-2025 | 7557/ND | 27/12/2024 | 0 | Resource Division | 8.68 | 0 | 0
958 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000031/2023-2024 | 1881/ND | 26/04/2023 | 0 | Resource Division | 100.61 | 0 | 0
959 | Central Drilling | Ranaghat Sub-Division | Providlng drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utillsing Departmental Machineries for Badkulla W/S Scheme (Z-11,1/W-l), Hanskhali Block under Nadia District, CentralDrilling Division, P.H.E. Dte (znd Call). | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000097/2023-2024 | 1052/CDD | 16/08/2023 | 30 | MENAKA ENTERPRISE | 18.6 | 0 | 0
960 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery and Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under BADKULLA Z-II WS Scheme, Block- Hanskhali , Dist. - Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001124/2023-2024 | 4712/EMD | 04/08/2023 | 30 | KASHINATH PAL & CO. | 9.79 | 0 | 0
961 | Nadia Division | Debgram Sub-Division | Restoration work of damaged road flank of Dharmadha - Muragacha Road due to laying pipe line under ''NJJM'' Project in Nakashipara Block of Nadia District under Nadia Division, PHE Dept. of Dharmada - Muragacha Road from 0.80 kmp to 1.50 kmp (one side) & from 1.50 kmp to 3.70 kmp (both side) of Krishnagar Highway Sub-Division-I under Nadia Highway Division-I in the district of Nadia during the year 2024-2025. | Assistant Engineer |  | BILL/00250/2024-2025 |  | 26/07/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 14.83 | 0 | 0
962 | Nadia Division | Debgram Sub-Division | Restoration work of damaged road flank of Dharmadha - Muragacha Road due to laying pipe line under ''NJJM'' Project in Nakashipara Block of Nadia District under Nadia Division, PHE Dept. of Dharmada - Muragacha Road from 0.80 kmp to 1.50 kmp (one side) & from 1.50 kmp to 3.70 kmp (both side) of Krishnagar Highway Sub-Division-I under Nadia Highway Division-I in the district of Nadia during the year 2024-2025. | Assistant Engineer |  | BILL/00344/2024-2025 | 149/PFMS | 06/08/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 7.41 | 0 | 0
963 | Nadia Division | Debgram Sub-Division | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000165/2025-2026 | 3260/ND | 10/07/2025 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 5
964 | Nadia Division | Debgram Sub-Division | Reconstruction of Top Dome and other related work for 455 cum RCC elevated reservoir of Surface Water Based Water Supply Scheme for Zone-III /A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000188/2024-2025 | 6096/ND | 19/09/2024 | 90 | M/S SANJAY ADHIKARI | 9.82 | 0 | 5
965 | Nadia Division | Debgram Sub-Division | Reconstruction of Staff room, Chlorination room, Godown, Boundary wall, Service road and etc. of Surface Water Based Water Supply Scheme for Zone-III /A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000189/2024-2025 | 6097/ND | 19/09/2024 | 360 | M/S SANJAY ADHIKARI | 55.82 | 0 | 5
966 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
967 | Nadia Division | Debgram Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 455 cum. of Surface Water Based Piped Water Supply Scheme for Zone- III/ A (NORTHERN SECTOR, PART-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, PHE Dte | Assistant Engineer |  | ORD/000264/2023-2024 | 4000/ND | 07/09/2023 | 451 | M/S SANJAY ADHIKARY | 17.13 | 0 | 60
968 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000355/2023-2024 | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 0 | 19
969 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
970 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 3/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000790/2021-2022 | 140/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.91 | 3.87 | 100
971 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000119/2023-2024 | 230/ND | 11/01/2024 | 0 | Resource Division | 10.27 | 0 | 0
972 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000134/2022-2023 | 125/ND | 05/01/2023 | 0 | Resource Division | 73.72 | 0 | 0
973 | Nadia Division | Krishnanagar Sub-Division | Sinking of 1 no. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method and construction of pump house (3.6 mtr. x 3.0 mtr.) and boundary wall at 3rd tube well site for Teorkhali water supply scheme under Krishnagar Sub-Division under Nadia Division, PHE,Dte. (Sm/10728) | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000032/2023-2024 | 2100/ND | 15/05/2023 | 90 | MONDAL ENTERPRISE | 29.84 | 0 | 75
974 | Nadia Division | Krishnanagar Sub-Division | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Teorkhali W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 12) | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000351/2021-2022 | 915/KSD | 29/11/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.39 | 3.38 | 100
975 | Nadia Division | Krishnanagar Sub-Division | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 90 days w.e.f. 01/10/2023 (as and when required) | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000411/2023-2024 | 1450/KSD | 18/09/2023 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0
976 | Nadia Division | Krishnanagar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
977 | Nadia Division | Krishnanagar Sub-Division | Repair & Renovation of Pump House, Boundary wall, Store Room and allied works at 1st and 2nd Pump House at Tiorkhali Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000501/2023-2024 | 6183/ND | 27/12/2023 | 485 | BIPLAB GUHA | 17.98 | 0 | 35
978 | Nadia Division | Krishnanagar Sub-Division | Fencing for Land at Chapra Bangaljhi and Teorkhali Water supply scheme at new 3rd Tube Well site under Krishnagar Sub-Division PHED. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000532/2022-2023 | 219/KSD | 03/03/2023 | 15 | SANJIB DEY | 0.45 | 0.22 | 0
979 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000758/2023-2024 | 1838/KSD | 28/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0
980 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 104 m3/hr at Teorkhali Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000781/2023-2024 | 1895/ND | 15/03/2024 | 180 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 268.24 | 0 | 0
981 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000156/2022-2023 | 109/ND | 05/01/2023 | 0 | Resource Division | 31.18 | 0 | 0
982 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000185/2023-2024 | 625/ND | 30/01/2024 | 0 | Resource Division | 9.92 | 0 | 0
983 | Eastern Mechanical | Krishnanagar Sub-Division | New service connection at Ph-3 of Teorkhali water supply scheme, Block-Nabadwip, Dist-Nadia | Assistant Engineer | Junior Engineer,Junior Engineer 4 | BILL/00728/2024-2025 | BP-51-24-25 | 21/06/2024 | 0 | WBSEDCL SWARUPGANJ C.C.C. | 7.71 | 0 | 0
984 | Eastern Mechanical | Krishnanagar Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-III under TIORKHALI ground water based water supply scheme under Block_ KRISHNANAGAR, Dist. - Nadia under EMD, PHE Dte. [SM/10728] | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000336/2024-2025 | 2151/EMD | 30/08/2024 | 182 | SWAPAN ENTERPRISE | 13.8 | 0 | 95
985 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP (Gravity Type) of capacity 231 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Subarnabihar Zone I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000026/2023-2024 | 1784/ND | 20/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 222.99 | 0 | 65
986 | Nadia Division | RWS Nadia Sub-Division | Laying of distribution pipeline along with FHTC additionally to cover the remaining portion of Subarnabihar Zone-I Water Supply Scheme withih Krishnagar ¿I Block under Kalyani Sub-Division-II under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000035/2024-2025 | 3451/ND | 20/06/2024 | 360 | BUDDHADEV MONDAL | 65.26 | 0 | 75
987 | Nadia Division | RWS Nadia Sub-Division | Installation of Manifold, laying of dedicated pipeline and other necessary allied works for Subarnabihar Zone-I Water Supply Scheme in Krishnagar-I Block under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000048/2025-2026 | 2115/ND | 02/05/2025 | 240 | BUDDHADEV MONDAL | 88.11 | 0 | 35
988 | Nadia Division | RWS Nadia Sub-Division | Laying of delivery main for Usidpur and Subarnabihar (P) Mouza under Krishnagar-I Block in Nadia District. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000051/2025-2026 | 2288/ND | 19/05/2025 | 60 | M/S GHOSH CONSTRUCTION | 63.02 | 0 | 99
989 | Nadia Division | RWS Nadia Sub-Division | Construction of Boundary wall to protect the aditional space of Subarnabihar Zone I water Supply Scheme under nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000108/2025-2026 | 2849/ND | 18/06/2025 | 60 | M/S K.P.PAL | 6.48 | 0 | 0
990 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution System including specials, valves all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Subarnabehar Zone-I to accommodate FHTC within Krishnagar-I Block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. (SM/11506) | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000180/2022-2023 | 4383/ND | 13/10/2022 | 798 | MONDAL ENTERPRISE | 493.02 | 357.92 | 100
991 | Nadia Division | RWS Nadia Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Subarnabehar W/S Scheme in Krishnagar - I Block of Nadia District under Nadia Division. PART - A | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000316/2021-2022 | 1189/PH | 03/12/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.82 | 4.82 | 100
992 | Nadia Division | RWS Nadia Sub-Division | Repair and renovation works of R.C.C. Elevated Existing Over Head Reservoir of capacity 1000 Cu.M for Subarnabehar Zone-I Water Supply Scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000710/2023-2024 | 1300/ND | 23/02/2024 | 60 | S.S.CONSULTANCY & CONSTRUCTION | 16.66 | 0 | 96
993 | Nadia Division | RWS Nadia Sub-Division | Special repair and renovation of Existing Boundary Wall at Head work site of Subarnabihar Zone I water supply scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000711/2023-2024 | 1301/ND | 23/02/2024 | 45 | ABHAYANANDA ENTERPRISE | 6.81 | 0 | 98
994 | Nadia Division | RWS Nadia Sub-Division | Special repair and renovation of Existing Boundary Wall " for 2nd ,3rd, 4th & 5th Tube Well site at Subarnabihar Zone I water supply scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000786/2023-2024 | 1903/ND | 15/03/2024 | 45 | CONSTRUCTURE | 5.07 | 0 | 95
995 | Nadia Division | RWS Nadia Sub-Division | Special repair and renovation of pump house and allied works for Head work site (Existing) at Subarnabihar Zone I water supply scheme in Nadia District under Nadia Division PHE. Dte | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000791/2023-2024 | 472/KlySD-II | 07/03/2024 | 30 | RAIHANA ENTERPRISE | 1 | 0 | 100
996 | Nadia Division | RWS Nadia Sub-Division | Providing last mile connectivity including FHTC to cover Shyamnagar and Berij village in connection with Augmentation of Ground Water Based Piped Water Supply Scheme for Subarna Bihar ZONE-I in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000812/2023-2024 | 474/KlySD-II | 07/03/2024 | 45 | M/S BISWAS ENTERPRISE | 2.15 | 0 | 82
997 | Nadia Division | RWS Nadia Sub-Division | Special repair and renovation of pump house and allied works for 2nd ,3rd, 4th & 5th Tube Well site(Existing) at Subarnabihar Zone I water supply scheme in Nadia Distric under Nadia Division PHE. Dte | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000839/2023-2024 | 475/KlySD-II | 11/03/2024 | 60 | DAFADAR ENTERPRISE | 1.61 | 0 | 98
998 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | RTOR000022/2022-2023 | 3894/ND | 08/09/2022 | 0 | Resource Division | 82.06 | 0 | 0
999 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | RTOR000079/2022-2023 | 4328/ND | 29/09/2022 | 0 | Resource Division | 39.36 | 0 | 0
1000 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | RTOR000100/2023-2024 | 3375/ND | 04/08/2023 | 0 | Resource Division | 3.11 | 0 | 0
1001 | Eastern Mechanical | RWS Nadia Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augomentation in connection to Accommodate FHTC at Pump House No.-I under Subarnabehar Zone-I ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000019/2024-2025 | 1311/EMD | 09/05/2024 | 30 | DAS ENTERPRISE (BARANAGAR) | 12.77 | 0 | 100
1002 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- I/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000308/2023-2024 | 4278/ND | 21/09/2023 | 643 | PRASUN ENTERPRISE | 301.15 | 0 | 25
1003 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
1004 | Nadia Division | Debgram Sub-Division | Restoration of road under Augmentation of Surface Water Based PWSS at Northern Sector Part II (zone I/B) at Nakashipara block under debagram Sub Division PHE Dte. | Assistant Engineer |  | ORD/000691/2024-2025 | 1061/DSD | 30/12/2024 | 15 | S. M. S & CO | 4.84 | 0 | 100
1005 | Nadia Division | Debgram Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 350 cum for Providing FHTC (Functional Household Tap Connection) for Zone -I/B (Northern Sector Part-II) Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000714/2023-2024 | 1252/ND | 22/02/2024 | 90 | U-TURN CONSTRUCTION | 20.98 | 0 | 10
1006 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 1/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000786/2021-2022 | 136/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.94 | 3.79 | 100
1007 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000116/2023-2024 | 246/ND | 11/01/2024 | 0 | Resource Division | 6.14 | 0 | 0
1008 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000131/2022-2023 | 92/ND | 05/01/2023 | 0 | Resource Division | 89.07 | 0 | 0
1009 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte |  |  | ORD/000013/2020-2021 | 1054 /NACD-II | 25/09/2020 | 15 | PRADUT GHOSH | 4.99 | 0 | 0
1010 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Dhoradaha to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000382/2022-2023 | 382/ND | 27/01/2023 | 90 | SATYABRATA CHAKRABORTY | 457.46 | 92.44 | 65
1011 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House and allied works of ground basaedpiped water supply scheme for Dhoradaha water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000780/2024-2025 | 305/ND | 17/01/2025 | 270 | J.P. CONSTRUCTION & SUPPLIERS | 35.46 | 0 | 45
1012 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000077/2023-2024 | 2298/ND | 29/05/2023 | 0 | Resource Division | 0.92 | 0 | 0
1013 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection under AE-III Baruihuda | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/01862/2023-2024 | BP-106-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0
1014 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection under AE-III Baruihuda | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/01863/2023-2024 | BP-105-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.95 | 0 | 0
1015 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under BARUIHUDA W/S Scheme (Block : Krishnagar I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 12) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000032/2023-2024 | 1611/EMD | 26/04/2023 | 555 | M/S DAS ENTERPRISE | 19.54 | 0 | 100
1016 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing Electro Mechanical Equipments and Allied Works for Arsenic Removal Plant at BARUIHUDA Piped Water Supply Scheme, Block Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001122/2023-2024 | 4710/EMD | 04/08/2023 | 30 | DEY ENTERPRISE | 53.06 | 0 | 0
1017 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00014/2023-2024 | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.04 | 0 | 0
1018 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00087/2022-2023 | 235/1 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
1019 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Track crossing proposal with Application ID: ER-SDAH-2023-WL-82. Payment of way leave plan & survey charges | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00499/2023-2024 | 293 | 27/12/2023 | 0 | EASTERN RAILWAY | 0.14 | 0 | 0
1020 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Track crossing proposal with Application ID: ER-SDAH-2023-WL-83. Payment of way leave plan & survey charges | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00500/2023-2024 | 294 | 27/12/2023 | 0 | EASTERN RAILWAY | 0.14 | 0 | 0
1021 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Track crossing proposal with Application ID: ER-SDAH-2023-WL-84. Payment of way leave plan & survey charges | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00501/2023-2024 | 295 | 27/12/2023 | 0 | EASTERN RAILWAY | 0.2 | 0 | 0
1022 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Track crossing proposal with Application ID: ER-SDAH-2023-WL-82 payment of Wayleave Facility charge. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00578/2023-2024 | 358 | 04/03/2024 | 0 | EASTERN RAILWAY | 8.98 | 0 | 0
1023 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Track crossing proposal with Application ID: ER-SDAH-2023-WL-84 payment of Wayleave Facility charge. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00579/2023-2024 | 360 | 04/03/2024 | 0 | EASTERN RAILWAY | 12.73 | 0 | 0
1024 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Track crossing proposal with Application ID: ER-SDAH-2023-WL-83 payment of Wayleave Facility charge. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00580/2023-2024 | 359 | 04/03/2024 | 0 | EASTERN RAILWAY | 8.98 | 0 | 0
1025 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Baruihuda Water Supply Scheme in Krishnanagar-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000113/2023-2024 | 413_1AE-I/NACD-II | 08/08/2023 | 15 | MANGES INDUSTRIAL CORPORATION. | 0.98 | 0 | 0
1026 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Baruihuda water supply scheme under Krishnanagar- I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000139/2023-2024 | 1338/NACD-II | 05/12/2023 | 45 | JAYBRATO HALDER | 29.32 | 0 | 100
1027 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 92 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Baruihuda Water Supply Scheme in Krishnagar-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000193/2024-2025 | 1034/NACD-II | 05/08/2024 | 180 | GHOSH ENTERPRISE | 239.9 | 0 | 0
1028 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Baruihuda water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000255/2023-2024 | 232/NACD-II | 21/02/2024 | 45 | ARIT KUMAR PAL | 11.29 | 0 | 100
1029 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 2 nos. 300 mm X 200 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Baruihuda Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000275/2022-2023 | 175/NACD-II | 24/01/2023 | 30 | B.M. ENGINEERING & CONSTRUCTION | 27.71 | 0 | 100
1030 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Arsenic cum Iron treatment Plant of Damodarkhali PWSS (Capacity- 56 m3/hr) and ancillary works of Baruihuda W/S Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000328/2023-2024 | 37/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.41 | 0 | 100
1031 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 500 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Baruihuda water supply scheme of Krishnagar-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000389/2022-2023 | 396/NACD-II | 28/03/2023 | 731 | MANGES INDUSTRIAL CORPORATION. | 423.86 | 0 | 40
1032 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD and allied works at OHR site under Shyamnagar Piped Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000416/2024-2025 | 09/NACD-II | 06/02/2025 | 90 | SUMIT GHOSH | 105.58 | 0 | 0
1033 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of documents for way leave permission from the Eastern Railways authority at 1 no. location on Ranaghat-Krishnagar & Ranaghat -Shantipur Railway track under Baruihuda Piped Water Supply Scheme for Krishnagar-I Block under Nadia Arsenic Civil Division-II, PHE Dte.[Period of Work : 01-03-2025 to 28-02-2026] | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000425/2024-2025 | 1189/AE-I/NACD-II | 25/02/2025 | 60 | SUMAN CHAKRABORTY | 1.92 | 0 | 100
1034 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000003/2023-2024 | 75/NACD-II | 15/01/2024 | 0 | Resource Division | 12.32 | 0 | 0
1035 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000028/2022-2023 | 375/NACD-II | 24/03/2023 | 0 | Resource Division | 44.86 | 0 | 0
1036 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Nokari- Aishmali Road from CH. 2.95 Km. to CH. 6.20 Km. Restoration work arising out of damage of black top for laying of pipe line for "Integrated surface water besed PWSS for Ranaghat -I and Ranaghat -II, Block by Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00199/2024-2025 | 221/PFMS | 12/09/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 62.96 | 0 | 0
1037 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Duttaphulia-Aranghata Road from CH. 35.00 Km. to CH. 40.00 Km. Restoration estimate due to excavations for underground Water Supply pipeline by Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00200/2024-2025 | 222/PFMS | 12/09/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 60.83 | 0 | 0
1038 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Duttaphulia-Aranghata Road from CH. 40.00 Km. to CH. 44.766 Km. Restoration estimate due to the cause of excavations for underground Water Supply pipeline layout Proposal of PHE along the R/S of Quality Control sub-Division-I, under Nadia Highway Division-I, in the District Nadia during 2023-2024. | Assistant Engineer | Junior Engineer | BILL/00409/2024-2025 |  | 18/12/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 64.84 | 0 | 0
1039 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Work for revamping / upgradation of the hydraulic parameters of distribution network in reference to Raynagar and Joypur W/S Scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 75/NAD-I | 16/04/2025 | 153 | S B CONSTRUCTION | 57.7 | 0 | 75
1040 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Balance work for revamping / upgradation of the hydraulic parameters at Kalipara,Gobindapur, Jhinukghata and Raynagar mouzas in reference to Gobindapur PWSS and Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 04) | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 127/NAD-I | 22/04/2025 | 60 | CHOWDHURY & CO. | 96.3 | 0 | 0
1041 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Balance Work for revamping / upgradation of the hydraulic parameters of distribution network towards Badkulla in reference to Raynagar and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 03) | Assistant Engineer | Junior Engineer | ORD/000020/2025-2026 | 138/NAD-I | 23/04/2025 | 60 | BUDDHADEV MONDAL | 95.86 | 0 | 0
1042 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Balance work for revamping / upgradation of the hydraulic parameters at Gayesh, Daluigram & Jafar-nagar mouzas in reference to Halalpur-Krisnapur PWSS & Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000025/2025-2026 | 154/NAD-I | 28/04/2025 | 60 | TAPU SAHA | 86.49 | 0 | 0
1043 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Providing, Laying of Rising Main, Laying Distribution system and FHTC (Functional Household Tap Connection), Soil investigation for the work of construction of 100 cum OHR staging height 20 mtr. Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including Raft foundation), pipe connection and cost of pipes, specials and construction of Pump house, Boundary Wall, Service and allied Works at head work & 2nd site at Raynagar Zone-II under Jal Jeevan Mission for Raynagar Zone-II Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000109/2023-2024 | 1765/NAD-I | 24/07/2023 | 366 | MINTU CHAKRABORTY | 337.06 | 0 | 0
1044 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Balance Work to complete revamping/upgradation of the hydraulic parameters at distribution network at the part of Betna Mouza and Raynagar Mouza in reference to Raynagar PWSS under Nadia Arsenic Division-I, PHE Dte. As a part of Jal Jeevan Mission. (2nd Call) (Sl. NO. 02) | Assistant Engineer | Junior Engineer | ORD/000138/2025-2026 | 1043/NAD-I | 25/09/2025 | 120 | M/S A.K. CONSTRUCTION | 61.71 | 0 | 0
1045 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Preparation of Detailed Project Report (DPR) for Raynagar Water Supply Scheme at Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.06) | Assistant Engineer | Junior Engineer | ORD/000168/2022-2023 | 3288 / NAD-I | 08/12/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 8.5 | 8.41 | 100
1046 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | "Providing Laying of Rising Main ,Laying distribution system and FHTC Soil investigation for the work of construction of 200 cum OHR staging heigjt 20 mtr , Construction of 200 cum capacity 20 mtr . staging hieght RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and Construction of Pump house , Boundary Wall , Service and Allied Works at head work & 2nd site under Jal Jivan Mission for Raynagar Zone -II Water Supply Scheme within Ranaghat -I Block under Nadia Arsenic Division -I P.H.E.Dte." (Sl.no.02) | Assistant Engineer | Junior Engineer | ORD/000209/2023-2024 | 2292/NAD-I | 27/09/2023 | 730 | TAPU SAHA | 386.21 | 0 | 70
1047 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/02/2025 to 31/07/2025) | Assistant Engineer | Junior Engineer | ORD/000254/2024-2025 | 17/AE-1/NAD-I | 31/01/2025 | 181 | M/S DIPAK ENTERPRISE | 0.86 | 0 | 0
1048 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000021/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 8.49 | 0 | 0
1049 | Eastern Mechanical | Eastern Mechanical Sub Division-II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for NEW Tube Well in connection to Accommodate FHTC at Pump House No.-I and II (Zone-I and II) under Raynagar ground water based water supply scheme under Block_ Ranaghat-II Dist. - Nadia under EMD, PHE Dte. (SM/14234) | Assistant Engineer | Junior Engineer | ORD/000653/2024-2025 | 2690/EMD | 20/11/2024 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 46.24 | 0 | 0
1050 | Nadia Division | Ranaghat Sub-Division | Construction of R.C.C Elevated Reservoir of 700 Cum. Capacity of staging height 20M at Head works site with Annular combined pile raft foundation for Badkulla Zone-II Water Supply Scheme under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000084/2025-2026 | 2523/ND | 29/05/2025 | 365 | SATYABRATA CHAKRABORTY | 164.42 | 0 | 0
1051 | Nadia Division | Ranaghat Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 125 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Badkulla-I to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000105/2024-2025 | 4281/ND | 05/08/2024 | 180 | GHOSH ENTERPRISE | 301.62 | 0 | 0
1052 | Nadia Division | Ranaghat Sub-Division | Construction of Jhama Bats Road from Mamjoan road to headwork site of Badkulla-I water supply scheme under Ranaghat Sub Division under Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000139/2024-2025 | 876(A)RSD | 20/08/2024 | 31 | M/S TARAK CHANDRA PAUL | 4.9 | 0 | 100
1053 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 700 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for Construction of OHR all complete for augmentation of Ground Water Based Water Supply Scheme for Badkulla Zone-I to accommodate FHTC in Hanskhali block under Ranaghat Sub-Division of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000150/2023-2024 | 3217/ND | 26/07/2023 | 706 | M/S TARAK CHANDRA PAUL | 676.67 | 0 | 82
1054 | Nadia Division | Ranaghat Sub-Division | Repairing of Pump house-I with sanitary arrangement under augmentation of Badkulla Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000173/2024-2025 | 1136/RSD | 11/09/2024 | 45 | M/S DREAM INFRASTRUCTURE | 1.9 | 0 | 100
1055 | Nadia Division | Ranaghat Sub-Division | Supplying and laying of distribution system for Augmentation of Ground water based water supply scheme for Badkulla-I to accommodate FHTC under Ranaghat Sub-Division PHED. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000236/2024-2025 | 6502/ND | 03/10/2024 | 179 | M/S TARAK CHANDRA PAUL | 87.28 | 0 | 70
1056 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
1057 | Nadia Division | Ranaghat Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
1058 | Nadia Division | Ranaghat Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Badkulla Zone-I W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000433/2021-2022 | 1053/RSD | 02/12/2021 | 30 | RADIANT | 3.29 | 2.94 | 100
1059 | Nadia Division | Ranaghat Sub-Division | Construction of 130m Boundary Wall(2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Badkulla Zone-I PWSS at H/W site under Ranaghat Sub -Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000782/2024-2025 | 458/ND | 29/01/2025 | 90 | M/S 2S CONSTRUCTION | 11.35 | 0 | 75
1060 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000008/2024-2025 | 7556/ND | 27/12/2024 | 0 | Resource Division | 4.29 | 0 | 0
1061 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000030/2023-2024 | 1872/ND | 26/04/2023 | 0 | Resource Division | 140.17 | 0 | 0
1062 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BADKULLA (ZONE-I) W/S Scheme, Block- Hanskhali , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000895/2022-2023 | 405/EMD | 20/01/2023 | 30 | S.G. ENTERPRISE | 30.45 | 0 | 0
1063 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali BlocK,. under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000528/2022-2023 | 1271/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 48.99 | 0 | 40
1064 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under BADKULLA ZONE-I ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte.(SM/15276) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000187/2025-2026 | 1125/EMD | 04/06/2025 | 90 | INDIA ENTERPRISE | 31.42 | 0 | 0
1065 | Nadia Division | Ranaghat Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Banpur PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte. Capacity 70.00 Cu.m/hr | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000465/2023-2024 | 132/ND | 09/01/2024 | 361 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 82.08 | 0 | 98
1066 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Santipur & Krishnaganj Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000530/2022-2023 | 1273/ND | 23/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 0 | 95
1067 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANPUR W/S Scheme, Block- Krishnaganj, ARABPUR W/S Scheme, Block-Karimpur, BHIMPUR W/S Scheme, Block-Krishnagar AND MONIPOTA W/S Scheme, Block- Krishnagar-I, Dist. - Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/001444/2023-2024 | 5127/EMD | 04/09/2023 | 666 | C.M.S. ENGINEERING CONCERN. | 70.97 | 0 | 12
1068 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Banpur ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15280) | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/001455/2024-2025 | 228/EMD | 06/02/2025 | 30 | BINAPANI ENTERPRISE | 11.76 | 0 | 0
1069 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Bill for Restoration work due to laying of pipe line on PMGSY road for HARADHAN GORAGACHA under WBSRDA Nadia division (Length 4.00 km.) under office of the Executive Engineer, Nadia Arsenic Division - I, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00232/2024-2025 | 277/PFMS | 30/09/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 25.08 | 0 | 0
1070 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Repair of different type road different Water Supply Scheme under Shantipur block and Habibpur G.P. under Dakshin Bishnupur PWSS under Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000012/2025-2026 | 124/NAD-I | 22/04/2025 | 30 | RAKESH ENTERPRISE | 20.44 | 0 | 0
1071 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation Work for Hiring of additional vehicle for supervision of JJM works including identification of land for JJM projects under Nadia Arsenic Division-I, P.H.E. Dte. W.e.f. 01/08/2025 to 31/01/2026. | Assistant Engineer | Junior Engineer | ORD/000108/2025-2026 | 110/AE-I/NAD-I | 31/07/2025 | 184 | OM TRANSPORT | 0.86 | 0 | 0
1072 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE-100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle peice etc. all complete with Rising Main System incluidng specials & Valves & Laying of Distribution System including Specials, Valves & Pipe Supporting Structure, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials, Construction of Boundary Wall [H/W Site (160.0 m length), 2nd T/W Site (45.0 m length)], Pump House for H/W Site (4.88 M X 3.60 M), 2nd T/W Site (3.60 M X 3.0 M), Land Development and allied works with Approach Road (105.0 m Length and 3.0 m Wide), Restoration Work for Bituminous Road and Soil Investigation for the work of Construction of RCC Elevated Reservoir of capacity 300 m3 Staging Height 20 Mtr. at Ground Water Based PWSS for Dakshin Bishnupur in Ranaghat-I Block of Nadia District under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000108/2023-2024 | 1764/NAD-I | 24/07/2023 | 1096 | SUPRITI ENTERPRISE | 566.66 | 83.61 | 60
1073 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Preparation of Detailed Project Report (DPR) for Dakshin Bishnupur Water Supply Scheme atRanaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (sl.02) | Assistant Engineer | Junior Engineer | ORD/000172/2022-2023 | 47/ NAD-I | 09/12/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 5.28 | 5.15 | 100
1074 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Augmentation for providing FHTC (Functional Household Tap Connection) at Narasinghanagar, Chapatala & Beharia Mouzas in Beharia PWSS and different Mouzas under Dakshin Bishnupur PWSS under Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000177/2024-2025 | 2173/NAD-1 | 30/12/2024 | 60 | SUMAN CHAKRABORTY | 96.23 | 0 | 0
1075 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Collection of Household Details at prescribed Format through Mobile App/Hard Copy including Geo- Reference as directed by EIC and submission of same to PHE Dte in soft copy at different piped water supply scheme under Nadia Arsenic Division-I, PHED. Name of PWSS:- 1) Haringhata (Zone-I & II) 2) Gobindapur 3) Haringhata Zone-V Part-IV 4) CHakdah Zone-XII 5) Arranghata 6) Haringhata Zone-I, II & III 7) Par Naimatpur (Phase-I) 8) Par Naimatpur (Phase-II) 9) Par Naimatpur (Phase-III) 10) Ramnagar 11) Chakdah Zone-VI & VI A & VII 13) Sabdalpur 14) Haringhata Zone-II 15) Chakdah Zone-X 17) Haringhata Zone-I & Zone- II 18) Chakdah Zone-II & IV VII & VIII & X 19) Halalpur-Krishnapur 20) Dakshin Bishnupur. | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 380/AE-I/NAD-I | 31/08/2023 | 90 | TECH VISION | 4.89 | 0 | 100
1076 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Culvert crossing including restoration of damaged pipeline including laying of dedicated pipeline towords Bagdia, Barajiakur & Bhatangachi Village (Babla GP, Dakshin Majdia) and allied works at Dakshin Bishnupur PWSS under Nadia Arsenic Division, PHE Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000196/2024-2025 | 2321/NAD-I | 15/01/2025 | 90 | CHOWDHURY & CO. | 24.28 | 0 | 100
1077 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Supply of vehicle on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division-I, P.H.E. Dte. (Period from 15/01/2025 to 14/07/2025). | Assistant Engineer | Junior Engineer | ORD/000217/2024-2025 | 05/AE-I/NAD-I | 14/01/2025 | 181 | SUMAN CHAKRABORTY | 0.86 | 0 | 0
1078 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division - I, P.H.E. Dte. for the period from 15.07.2022 to 14.07.2023 i.e. for 1(one) year. | Assistant Engineer | Junior Engineer | ORD/000255/2022-2023 | 172 / AE-I / NAD -I | 14/07/2022 | 365 | SUMAN CHAKRABORTY | 4.8 | 0 | 75
1079 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation work order for Supply and installation of sign board related to JJM Matters at different piped water supply schemes under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000281/2023-2024 | 07/AE-I/NAD-I | 04/01/2024 | 30 | BIBHAS PAL | 0.88 | 0 | 100
1080 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation Work Order 1(One) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer, Nadia Arsenic Division-I, P.H.E. Dte. for the period from 15.07.2023 to 14.01.2024 i.e, for 6 months. | Assistant Engineer | Junior Engineer | ORD/000294/2023-2024 | 292/AE-I/NAD-I | 14/07/2023 | 184 | SUMAN CHAKRABORTY | 0.98 | 0 | 0
1081 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000015/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 13.77 | 0 | 0
1082 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000018/2023-2024 | 2106/NAD-I | 01/09/2023 | 0 | Resource Division | 72.02 | 0 | 0
1083 | Eastern Mechanical | Eastern Mechanical Sub Division-II | New Service Connection for DAKSHIN BISHUNUPUR Water supply scheme | Assistant Engineer | Junior Engineer | BILL/02311/2024-2025 | BP-198-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (AISHTAL CCC) | 4.9 | 0 | 0
1084 | Eastern Mechanical | Eastern Mechanical Sub Division-II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Dakshin Bishnupur ground water based water supply scheme under Block_ Ranaghat_I Dist. - Nadia under EMD, PHE Dte. (SM/14242) | Assistant Engineer | Junior Engineer | ORD/001465/2024-2025 | 236/EMD | 06/02/2025 | 30 | SHIVAM ENTERPRISE | 21.04 | 0 | 0
1085 | Nadia Division | Krishnanagar Sub-Division | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no- 03/2022- Central Tax Rate dt- 13.07.2022 of Providing Functional Household Tap Connection (FHTC) at Surface water-based Water Supply Scheme (Northern Sector) part- III, Zone-IV within Krishnagar & Nabadwip (Part) Block, (Phase-E ) | Assistant Engineer |  | BILL/00245/2024-2025 | 157/PFMS | 04/08/2024 | 0 | GHOSH ENTERPRISE | 2.55 | 0 | 0
1086 | Nadia Division | Krishnanagar Sub-Division | Making cabinet for keeping file and other official records at General Section & Divisional Accountant Room and Cash Section of Nadia Division Office building Kalyani nadia. | Assistant Engineer |  | ORD/000012/2022-2023 | 360/Kly SD-I | 25/04/2022 | 30 | CHINMOY BISWAS | 4.99 | 0 | 100
1087 | Nadia Division | Krishnanagar Sub-Division | Laying of New pipe line in connection with FHTC at surface water based water supply scheme Nortern Sector Part-III, within Krishnagar -II Block(Phase-E) (Sl.No. 02) | Assistant Engineer |  | ORD/000059/2022-2023 | 574/KSD | 13/06/2022 | 15 | GHOSH ENTERPRISE | 4.99 | 4.98 | 100
1088 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Sonda (Zone-I) W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting). | Assistant Engineer |  | ORD/000236/2020-2021 | 47/ND | 06/01/2021 | 90 | TARUN KUMAR BHATTACHARYA | 93.83 | 0 | 0
1089 | Nadia Division | Krishnanagar Sub-Division | Providing Functional Household Tap Connection(FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-III,Zone-IV within Krishnagar & Nabadwip(Part) Block(Phase-E) | Assistant Engineer |  | ORD/000385/2021-2022 | 7206/ND | 15/12/2021 | 90 | GHOSH ENTERPRISE | 178.58 | 48.05 | 100
1090 | Nadia Division | Krishnanagar Sub-Division | Laying of New UPVC pipe line in connection with "Providing FHTC at P.H.E. Dte. surface water based water supply scheme Nortern Sector Part-III, Zone-IV within Krishnagar Block(Phase-E)" Sl.No .02 | Assistant Engineer |  | ORD/000698/2021-2022 | 167/KSD | 23/02/2022 | 15 | GHOSH ENTERPRISE | 4.94 | 4.89 | 100
1091 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000079/2021-2022 | 807/ND | 18/02/2022 | 0 | Resource Division | 16.81 | 0 | 0
1092 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000142/2023-2024 | 296/ND | 15/01/2024 | 0 | Resource Division | 7.3 | 0 | 0
1093 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000143/2023-2024 | 297/ND | 15/01/2024 | 0 | Resource Division | 5.76 | 0 | 0
1094 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000144/2023-2024 | 298/ND | 15/01/2024 | 0 | Resource Division | 12.95 | 0 | 0
1095 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000145/2023-2024 | 299/ND | 15/01/2024 | 0 | Resource Division | 13.29 | 0 | 0
1096 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) | Assistant Engineer |  | VCH/001120/2021-2022 | 699/PFMS | 28/03/2022 | 0 | GHOSH ENTERPRISE | 100 | 0 | 0
1097 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-IV within Krishnagar-II and Nabadwip (Part) Block. (Phase-E) | Assistant Engineer |  | VCH/001239/2021-2022 | 724/PFMS | 30/03/2022 | 0 | GHOSH ENTERPRISE | 15.83 | 0 | 0
1098 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000051/2021-2022 | 1408/NAD-I | 08/11/2021 | 60 | SANDIP BISWAS | 68.26 | 67.73 | 100
1099 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Dhantala Part-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000108/2021-2022 | 1610/NAD-I | 28/12/2021 | 90 | UMWELT ENGINEER PVT. LTD. | 164.47 | 163.67 | 100
1100 | Nadia Arsenic Division I | Nadia Arsenic Division I | Revamping / upgardation of hydraulic parameter of distribution network and providing FHTC for Doula, Debipur Chandpur Biraberia Dhantala & Notungram and Hizuli (Part) Village and under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dhantala PWSS & Hizuli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000112/2025-2026 | 800/NAD-I | 18/08/2025 | 90 | BIDYUT KUMAR | 182.15 | 0 | 0
1101 | Nadia Division | RWS Nadia Sub-Division | Repairing Works (existing OHR, Pump House, Boundary wall etc.) of Madhugari Water Supply Scheme, Karimpur-I Block Under R.W.S. Nadia Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000030/2024-2025 | 3431/ND | 19/06/2024 | 360 | M/S DURGA SECURITIES & SERVICES | 22.18 | 0 | 100
1102 | Nadia Division | RWS Nadia Sub-Division | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site & 2nd Tube Well Site of Madhugari [Phase-III] Ground Based Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000517/2022-2023 | 1194/ND | 21/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 28.53 | 19.04 | 70
1103 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000106/2023-2024 | 3788/ND | 24/08/2023 | 0 | Resource Division | 3.21 | 0 | 0
1104 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MADHUGARI W/S Scheme, Block- Karimpur-1 , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 20) | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000910/2022-2023 | 420/EMDdt.20.01.2023 | 17/03/2023 | 30 | KARUNAMOY ENGINEERING | 9.86 | 0 | 100
1105 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SAKDA (Block-Krishnaganj), BAHADURPUR(Block-Tehatt-I), BETBERIA(Block-Chapra) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000009/2023-2024 | 1507/EMD | 18/04/2023 | 30 | SWAPAN KUMAR BHANJA | 14.69 | 4.88 | 100
1106 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply and delivery of PCC Pole, MS material and allied works to WBSEDC Ltd. for Bahadurpur PWSS, W/O-879/EMSD-III, T.No.45/SD-III | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000459/2022-2023 | 879/EMSD-III | 29/07/2022 | 30 | M/S G.P. ENTERPRISE | 0.75 | 0 | 0
1107 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply & delivery of PCC pole MS material and allied electrical accessories to WBSEDCL Ltd ( Nazirpur CCC) for Bahadurpur PWSS PH.- II under EMSD III Dist. Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000603/2022-2023 | 879/EMSD III | 29/07/2022 | 4 | M/S. G.P. ENTERPRISE | 0.75 | 0.75 | 100
1108 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Bahadurpur HW Site & 2nd pump house site with Reinforced Barbed Tape , Flooring ,Plaster ,Painting, Pathway , and other allied works Under Nadia Arsenic Division-II,P.H.E.Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000025/2024-2025 | 148/AE-II/NACD-II | 11/06/2024 | 420 | SREE GURU ENTERPRISE | 2.55 | 0 | 0
1109 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Bahadurpur Water Supply Scheme in Tehatta-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000073/2023-2024 | 327/1/AE-I/NACD-II | 13/07/2023 | 7 | RISHAN ENGINEERING CONSULTANCY | 0.86 | 0 | 100
1110 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000080/2025-2026 | 736/NACD-II | 18/06/2025 | 90 | JOY HIND TUBEWELLS | 186.42 | 0 | 40
1111 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Krishnagar & Bahadurpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000135/2021-2022 | 867/NACD-II | 08/11/2021 | 45 | MITRA CONSTRUCTION | 46.77 | 46.68 | 100
1112 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Bahadurpur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000173/2023-2024 | 1303/NACD-II | 29/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
1113 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Krishnagar & Bahadurpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000177/2021-2022 | 948/NACD-II | 09/12/2021 | 45 | MITRA CONSTRUCTION | 45.4 | 45.38 | 100
1114 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipeline repair) at Krishnagar & Bahadurpur (Vill- Krishnagar, Chak Chilakhali) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000215/2021-2022 | 08/NACD-II | 04/01/2022 | 45 | MITRA CONSTRUCTION | 34.08 | 0 | 100
1115 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Collection on House Hold Details at prescribed Format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte. In soft copy for different PWSS under Nadia Arsenic Civil Division-II, PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000235/2021-2022 | 216/AE-I/NACDII | 01/02/2022 | 5 | JOY GOPAL GUPTI | 4.91 | 4.91 | 100
1116 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Bahadurpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000256/2022-2023 | 1011/NACD-II | 29/11/2022 | 60 | NAMDAR ALI | 12.93 | 12.73 | 90
1117 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Bahadurpur 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000258/2021-2022 | 40/AE-II/NACD-II | 17/02/2022 | 30 | TAPAN SAHA | 4.45 | 4.41 | 100
1118 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Bahadurpur & Rajapur Water Supply Scheme of capacity 16 Cu.m/hr under in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000308/2023-2024 | 424/NACD-II | 15/03/2024 | 420 | CHAKRABORTTI ENTERPRISE | 92.52 | 0 | 70
1119 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000348/2024-2025 | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 20
1120 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUPPLY OF 11 KV AB CABLE & ALLIED ELECTRICAL ACCESSORIES TO WBSEDCL NAZIRPUR CCC FOR BAHADURPUR PWSS | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | VCH/000072/2022-2023 | 30 | 26/04/2022 | 0 | T. N. BANERJEE | 2.05 | 0 | 0
1121 | Nadia Division | Tehatta Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
1122 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Dhoradaha to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000382/2022-2023 | 382/ND | 27/01/2023 | 90 | SATYABRATA CHAKRABORTY | 457.46 | 93.98 | 65
1123 | Nadia Division | Tehatta Sub-Division | Providing FHTC including Laying Distribution System in connection with J.J.M. Work under village Baruipota, Teinpur to cover up left out portion under Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000708/2024-2025 | 134/ND | 08/01/2025 | 360 | M/S FREEDOM CONSTRUCTION | 57.04 | 0 | 70
1124 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Dhoradaha Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division, P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Dhoradaha at Karimpur-II Block by Augmentation of Ground Water based PWSS for Dhoradaha Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000738/2024-2025 | 416/ND | 27/01/2025 | 240 | BANERJEE CONSTRUCTION | 23.41 | 0 | 40
1125 | Nadia Division | Tehatta Sub-Division | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangemen and Consruction of Boundary wall at Tube well No-3 Site at Dhoradaha Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000754/2023-2024 | 1629/ND | 07/03/2024 | 364 | BANERJEE ENTERPRISE | 12.74 | 0 | 70
1126 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House and allied works of ground basaedpiped water supply scheme for Dhoradaha water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000780/2024-2025 | 305/ND | 17/01/2025 | 270 | J.P. CONSTRUCTION & SUPPLIERS | 35.46 | 0 | 45
1127 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000040/2023-2024 | 1905/ND | 27/04/2023 | 0 | Resource Division | 105.7 | 0 | 0
1128 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000075/2023-2024 | 2296/ND | 29/05/2023 | 0 | Resource Division | 26.74 | 0 | 0
1129 | Nadia Division | Tehatta Sub-Division | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001102/2021-2022 | 672/PFMS | 24/03/2022 | 0 | RADIANT | 3.09 | 0 | 0
1130 | Central Drilling | Tehatta Sub-Division | Providing Drilling Crew and other allied works for construction of Tube Well (300mm x 200mm x250 Mtrs. Depth) by utilising Departmental machineries for Dhoradaha W/S Scheme (T/W-I) karimpur-II Block under Nadia District, CDD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 136/CDD | 17/04/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 18.87 | 0 | 100
1131 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-VII, within Kaliganj Block (Phase-B, Retrofitting)" | Assistant Engineer |  | ORD/000266/2020-2021 | 163/ND | 13/01/2021 | 90 | M/S DIPAK ENTERPRISE | 97.11 | 58.4 | 0
1132 | Nadia Division | Debgram Sub-Division | Laying of pipeline from Mira Bazar Baroari temple to traffic more under Mira - I G.P under Zone -VII of Surface Water Based Water Supply Scheme (Northern Sector), Part-I, within Kaliganj Block under Debagram Sub Division, P.H.Engineering Dte.(S.I. No -03.) | Assistant Engineer |  | ORD/000609/2021-2022 | 585/DSD | 31/12/2021 | 30 | AVINABA ENGINEERING CONCERN | 0.64 | 0.6 | 0
1133 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT PART-1 Z-VII | Assistant Engineer |  | VCH/001062/2020-2021 | 459/DW | 30/03/2021 | 0 | M/S DIPAK ENTERPRISE | 64.73 | 0 | 0
1134 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Itla W/S scheme in Nadia District under Nadia Division P.H.E. Dte." (Phase-I, Retrofitting) | Assistant Engineer |  | ORD/000117/2021-2022 | 2992/ND | 29/07/2021 | 90 | JOYGOPAL GUPTI | 82.18 | 97.91 | 0
1135 | Nadia Division | Krishnanagar Sub-Division | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN-METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC ALL COMPLETE AT ITLA W/S SCHEME UNDER NADIA DIVISION, PHE , DTE . PHASE-1, RETROFITTING PART-B. | Assistant Engineer |  | VCH/000202/2021-2022 | 67/PPMS | 15/07/2021 | 0 | M/S K.P. CONSTRUCTION | 23.03 | 0 | 0
1136 | Nadia Division | Krishnanagar Sub-Division | PROVIDING FHTC AT ITLA W/S SCHEME (PHASE-I RETROFITTING). | Assistant Engineer |  | VCH/000874/2020-2021 |  | 13/03/2021 | 0 | M/S K.P. CONSTRUCTION | 23.03 | 0 | 0
1137 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VII within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.4) | Assistant Engineer |  | ORD/000459/2020-2021 | 866/ND | 18/02/2021 | 90 | ALOKE ENTERPRISE | 97.09 | 0 | 0
1138 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000085/2022-2023 | 4303/ND | 29/09/2022 | 0 | Resource Division | 0.02 | 0 | 0
1139 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VII within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.4) | Assistant Engineer |  | VCH/000749/2021-2022 | 353/PFMS | 08/12/2021 | 0 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 83.87 | 0 | 0
1140 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VII within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000936/2021-2022 | 488/PFMS | 03/02/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 0.41 | 0 | 0
1141 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VII within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000937/2021-2022 | 493/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.47 | 0 | 0
1142 | Nadia Arsenic Division I | Nadia Arsenic Division I | Inter-Connection with M.S Pipeline to Distribution Pipeline of Surface Water Based Piped Water Supply Scheme for arsenic affected areas of Haringhata & Chakdah (Part) (Hapania Zone-II) under Haringhata Block under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. Tender No.-04/NAD-I/2021-2022. | Assistant Engineer-I | Junior Engineer-II | ORD/000041/2021-2022 | 87/AE-I/NAD-I | 05/05/2021 | 30 | SATYABRATA CHAKRABORTY | 4.17 | 8.34 | 0
1143 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying work of Upvc pipeline at Hapania,Singa, Thansara and other Mouzas under Nagarukhra -II G.P. under Zone-II (Hapania) under Surface Based Haringhata & Chakdah (Part) W/S Scheme under Haringhata Block in the district of Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000078/2022-2023 | 88 /AE-I/NAD-I | 28/04/2022 | 15 | TARUN KUMAR BHATTACHARYA | 4.84 | 0 | 100
1144 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 06) | Assistant Engineer-I | Junior Engineer-II | ORD/000205/2020-2021 | 154/NAD-I | 25/01/2021 | 60 | SATYABRATA CHAKRABORTY | 95.8 | 191.26 | 100
1145 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Anandapur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-A) | Assistant Engineer |  | ORD/000319/2020-2021 | 398/ND | 22/01/2021 | 45 | BIDYUT KUMAR | 32.35 | 4.03 | 0
1146 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Anandapur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-B) | Assistant Engineer |  | ORD/000320/2020-2021 | 399/ND | 22/01/2021 | 45 | SUBHASIS MAJUMDER | 32.36 | 2.6 | 100
1147 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Anandapur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-C) | Assistant Engineer |  | ORD/000324/2020-2021 | 400/ND | 22/01/2021 | 45 | JOYGOPAL GUPTI | 32.34 | 2.04 | 0
1148 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Topla W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-A) | Assistant Engineer |  | ORD/000330/2020-2021 | 404/ND | 22/01/2021 | 45 | NILAY KUMAR BHATTACHARYA | 32.33 | 19.62 | 0
1149 | Nadia Division | Tehatta Sub-Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) | Assistant Engineer |  | VCH/000059/2021-2022 |  | 12/04/2021 | 0 | SUBHASIS MAJUMDER | 16.31 | 0 | 0
1150 | Nadia Division | Tehatta Sub-Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) | Assistant Engineer |  | VCH/000060/2021-2022 |  | 12/04/2021 | 0 | BIDYUT KUMAR | 14.57 | 0 | 0
1151 | Nadia Division | Tehatta Sub-Division | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT ANANDAPUR W/S SCHEME PHASE-1 UNDER NADIA DIVISION, PHE , DTE. | Assistant Engineer |  | VCH/000211/2021-2022 | 83/PPMS | 15/07/2021 | 0 | SUBHASIS MAJUMDER | 16.31 | 0 | 0
1152 | Nadia Division | Tehatta Sub-Division | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT ANANDAPUR W/S SCHEME PHASE-1,PART-A RETROFITTING, UNDER NADIA DIVISION, PHE , DTE. | Assistant Engineer |  | VCH/000216/2021-2022 | 76/PPMS | 15/07/2021 | 0 | BIDYUT KUMAR | 14.57 | 0 | 0
1153 | Nadia Division | Tehatta Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME ATPART-C | Assistant Engineer |  | VCH/001066/2020-2021 | 460/DW | 30/03/2021 | 0 | JOYGOPAL GUPTI | 18.33 | 0 | 0
1154 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Patharghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000065/2020-2021 | 06/NACD-II | 05/01/2021 | 60 | APURBA MANDAL | 47.69 | 94.39 | 0
1155 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Betberia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000023/2020-2021 | 1065/NACD-II | 25/09/2020 | 15 | NAMDAR ALI | 4.99 | 0 | 0
1156 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-VII within Kaliganj block(Phase-A) in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000186/2020-2021 | 3592/ND | 08/12/2020 | 90 | PROJECT INDIA | 96.53 | 36.25 | 0
1157 | Nadia Division | Debgram Sub-Division | Hiring Diesel Luxury Car on daily basis (for 12 months from 01.02.2021 to 31.01.2022) for the office use of the Assistant Engineer, Kalyani Sub Division II, P.H.E. Dte | Assistant Engineer |  | ORD/000463/2020-2021 | 198 / KLYSD -II | 29/01/2021 | 365 | SUMAN CHAKRABORTY | 4.8 | 2.56 | 0
1158 | Nadia Division | Debgram Sub-Division | PROVIDING HOUSE CONNECTION INCLUDING SUPPLY OF 15MM DIA GI/PVC PIPE OF AVERAGE LENGTH OF 10MM DIA CUM GUN-METAL FERRULE, SADDLE PIECE 15MM AT KALIGANJ BLOCK | Assistant Engineer |  | VCH/000788/2020-2021 | 382/DW | 04/02/2021 | 0 | PROJECT INDIA | 78.41 | 0 | 0
1159 | Nadia Division | RWS Nadia Sub-Division | Providing FHTC (Functional Household Tap Connection) by Augmentation under Jal Swapna for Ghoralia Zone-II Water Supply Scheme in Santipur Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Santipur Block | ORD/000599/2021-2022 | 337/ND | 25/01/2022 | 90 | S.S. ENTERPRISE | 108.63 | 77.14 | 98
1160 | Nadia Division | RWS Nadia Sub-Division | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Santipur Block | ORD/000722/2024-2025 | 7571/ND | 27/12/2024 | 31 | IMAGIN | 34.21 | 0 | 0
1161 | Nadia Division | RWS Nadia Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir capacity of 136 CUM, existing Pump Houses and construction of shed for CWR at Existing Headwork site along with other allied Works at Ghoralia Zone II water supply scheme under Tehatta Subdivision of Nadia Division. | Assistant Engineer | Junior Engineer,Junior Engineer Santipur Block | ORD/000791/2024-2025 | 763/ND | 19/02/2025 | 180 | M/S ARATI ENTERPRISE | 27.7 | 0 | 60
1162 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Santipur Block | RTOR000014/2021-2022 | 94/ND | 06/01/2022 | 0 | Resource Division | 0.66 | 0 | 0
1163 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Santipur Block | RTOR000084/2021-2022 | 819/ND | 18/02/2022 | 0 | Resource Division | 6.28 | 0 | 0
1164 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Santipur Block | RTOR000131/2021-2022 | 1260/ND | 16/03/2022 | 0 | Resource Division | 0.66 | 0 | 0
1165 | Nadia Division | RWS Nadia Sub-Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II | Assistant Engineer | Junior Engineer,Junior Engineer Santipur Block | VCH/001060/2021-2022 | 618/PFMS | 14/03/2022 | 0 | UMWELT ENGINEERS PVT LTD | 2.84 | 0 | 0
1166 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000050/2021-2022 | 1407/NAD-I | 08/11/2021 | 60 | M/S PRADIP KUMAR PAL | 69.04 | 66.46 | 100
1167 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Ramnagar Ground Based Water Supply Scheme under Hnaskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Ramnagar (Part-I) under JJM (Sl.no.08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000111/2023-2024 | 1773/NAD-I | 26/07/2023 | 15 | SUMAN CHAKRABORTY | 13.01 | 0 | 90
1168 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey, Design Drawing & DPR Preparation for Augmentation of RAMNAGAR Water Supply Scheme in Hanskhali Block under Nadia Arsenic Division-1, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000122/2023-2024 | 318/AE-II/NAD-I | 14/07/2023 | 7 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 4.4 | 3.62 | 100
1169 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000014/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0
1170 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukhilnara, Zone-I, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Ukhilnara, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000048/2021-2022 | 1405/NAD-I | 08/11/2021 | 60 | M/S UMA CONSTRUCTION | 63.86 | 49.51 | 100
1171 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repairing, painting of Boundary wall, Pump House and other llied work at Ukhilnara Zone-II (2nd T/W Site) Water supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000075/2023-2024 | 291/AE-I/NAD-I | 12/07/2023 | 7 | GANGULY ENTERPRISE | 4.7 | 4.66 | 100
1172 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-I | RTOR000006/2021-2022 | 139/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
1173 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Chakdah Zone-I (Palagachha) at Chakdah Block by retrofitting of Ground Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000092/2021-2022 | 1540/NAD-I | 06/12/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 164.35 | 139.41 | 100
1174 | Nadia Arsenic Division I | Nadia Arsenic Division I | Shifting and repairing of clear water rising main and distribution pipeline from Palagacha more to Singher Bagan more along NH-34 of Surface based ChakdahW/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (sl.05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000235/2022-2023 | 500 / NAD-I | 10/03/2023 | 21 | BUDDHADEV MONDAL | 32.9 | 32.88 | 100
1175 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-XII, (Madanpur) at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000118/2021-2022 | 11/NAD-I | 05/01/2022 | 90 | UMWELT ENGINEER PVT. LTD. | 378.71 | 378.54 | 100
1176 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission for Madanpur at Madanpur-I G.P by retrofitting of Surface Water based Piped Water Supply Scheme for Haringhata- Chakdah(Part) in connection with retrofitting work ofZone-X (Subarnapur),Part-II under Nadia Arsenic Division-I, PHE Dte. (sl.13) | Assistant Engineer-I | Junior Engineer-II | ORD/000022/2023-2024 | 1158 / NAD-I | 28/04/2023 | 21 | CHOWDHURY & CO. | 92.76 | 58.29 | 100
1177 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of Distribution Pipeline at Buddhapark Crossing at WBHDCL Road and other allied works under Jal Jeevan Mission (JJM) for Zone-X, (Subarnapur) at Subarnapur Mouza at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-X, (Subarnapur) Part-II under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-II | ORD/000080/2023-2024 | 1701/NAD-I | 13/07/2023 | 25 | M/S DIPAK ENTERPRISE | 93.64 | 93.64 | 100
1178 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of Clear Water Rising Main at Majher Char Crossing at WBHDCL Road and other allied works under Jal Jeevan Mission (JJM) for Zone-X, (Subarnapur) at Subarnapur Mouza at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-X, (Subarnapur) Part-II under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 03) | Assistant Engineer-I | Junior Engineer-II | ORD/000081/2023-2024 | 1702/NAD-I | 13/07/2023 | 21 | M/S DIPAK ENTERPRISE | 89.84 | 61.1 | 100
1179 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-X (Subarnapur) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000112/2021-2022 | 1614/NAD-I | 28/12/2021 | 90 | GHOSH BROTHERS | 356.08 | 152.92 | 90
1180 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Zone-IX (Chandmari) at Kanchrapara G.P. and Zone-X (Subarnapur) under Jal Jeevan Mission (JJM) by retrofitting of Surface Water Based PWSS for Haringhata & Chakdah (Part) for Zone-X (Subarnapur) Part-II under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (SL.03) | Assistant Engineer-I | Junior Engineer-II | ORD/000236/2022-2023 | 501 / NAD-I | 10/03/2023 | 21 | BUDDHADEV MONDAL | 30.99 | 30.99 | 100
1181 | Nadia Division | RWS Nadia Sub-Division | URGENT RESTORATION OF CARRIAGE WAY & FLANF OF BADKULLA- ARANGHATA ROAD AT CH. 5.7 KM. " ARISING DUE TO LAYING OF PHED W/S SCHEME PIPE LINE, HIGHWAY DIVISION -II, PW ROADS. | Assistant Engineer |  | BILL/00528/2023-2024 | 242/1/PFMS | 18/08/2023 | 0 | OTHERS | 0.98 | 0 | 0
1182 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Muktadaha Zone-II W/S scheme in Nadia District under Nadia Division P.H.E. Dte | Assistant Engineer |  | ORD/000276/2021-2022 | 5688/ND | 03/11/2021 | 60 | CHOWDHURY & CO. | 39.38 | 30.52 | 100
1183 | Nadia Division | RWS Nadia Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
1184 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000113/2021-2022 | 1024/ND | 03/03/2022 | 0 | Resource Division | 0.7 | 0 | 0
1185 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Digri (Vill-Digri) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000045/2020-2021 | 1192/NACD-II | 13/11/2020 | 25 | M/S RAJESH CONSTRUCTION | 4.99 | 0 | 0
1186 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Kamalpur Z-I Water Supply scheme Ranaghat-II block in Nadia District under Nadia Division P.H.E. Dte.(Phase-A) | Assistant Engineer | Junior Engineer 2 | ORD/000202/2021-2022 | 5176/ND | 20/09/2021 | 90 | CHANDAN ROY | 88.23 | 87.01 | 0
1187 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000055/2021-2022 | 798/ND | 18/02/2022 | 0 | Resource Division | 7.77 | 0 | 0
1188 | Nadia Division | Ranaghat Sub-Division | Providing Functional House Tap Connection from Kamalpur Zone I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | Assistant Engineer | Junior Engineer 2 | VCH/001012/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 7.21 | 0 | 0
1189 | Nadia Division | Tehatta Sub-Division | LAYING OF PIPELINE UNDER PALASHIPARA PWSS FROM PALASHIPARA BAZAR TO BURNIA BUS STAND. | Assistant Engineer | Junior Engineer | BILL/00527/2023-2024 | 241/1/PFMS | 18/08/2023 | 0 | OTHERS | 49.99 | 0 | 0
1190 | Nadia Division | Tehatta Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 57 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Anandapur to accommodate FHTC within Karimpur-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000093/2024-2025 | 4229/ND | 02/08/2024 | 180 | B.M. ENGINEERING & CONSTRUCTION | 191.51 | 0 | 0
1191 | Nadia Division | Tehatta Sub-Division | Laying of additional pipeline for Fazilnagar Mouza and Anandapur Mouza under Fazilnagar PWSS and Anandapur PWSS under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2024-2025 | 4904/ND | 10/09/2024 | 90 | PATHIK PABAN NANDI | 37.63 | 0 | 0
1192 | Nadia Division | Tehatta Sub-Division | Laying of additional pipe lines and allied works to increase the functionality in Brojonathpur, Gandhina villages under Karimpur-I Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000328/2025-2026 | 4685/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 46.3 | 0 | 40
1193 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Anandapur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000342/2024-2025 | 7036/ND | 29/11/2024 | 420 | SAFTI PRIVATE LIMITED | 29.2 | 0 | 65
1194 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground basaedpiped water supply scheme for Anandapur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000400/2024-2025 | 7124/ND | 09/12/2024 | 90 | M/S A.K.CONSTRUCTION | 31.58 | 0 | 0
1195 | Nadia Division | Tehatta Sub-Division | LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE CARRYING STRUCTURE ALL COMPLETE, PROPOSED AUGMENTATION OF RISING MAIN SYSTEM AND PROVIDING FHTC INCLUDING SUPPLYING, LAYING, FITTING, FIXING OF 15MM NB PVC (SCHEDULE 80)/20MM OD HDPE (PE100, PN16) PIPE WITH ALL NECESSARY SPECIALS, SADDLE PIECE ETC. ALL COMPLETE FOR AUGMENTATION OF GROUND BASED WATER SUPPLY SCHEME AT ANANDAPUR TO ACCOMMODATE FHTC UNDER TEHATTA SUB-DIVN UNDER NADIA DIVN, PHE DTE | Assistant Engineer | Junior Engineer | ORD/000690/2021-2022 | 896/ND | 23/02/2022 | 90 | IJABUL SK. | 205.15 | 182.17 | 95
1196 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000042/2022-2023 | 4312/ND | 29/09/2022 | 0 | Resource Division | 10.92 | 0 | 0
1197 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000045/2021-2022 | 453/ND | 31/01/2022 | 0 | Resource Division | 0.6 | 0 | 0
1198 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000133/2021-2022 | 1255/ND | 16/03/2022 | 0 | Resource Division | 1.1 | 0 | 0
1199 | Nadia Division | Tehatta Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001263/2021-2022 | 729/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.23 | 0 | 0
1200 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.I & II under Anandapur W/S Scheme, Block-Karimpur- 1, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/000171/2022-2023 | 6182/EMD | 14/11/2022 | 30 | H.K. DAS & CO. | 14.64 | 13.81 | 0
1201 | Nadia Division | Kalyani Sub-Division I | Supplying, Laying, Fitting & Fixing of Distribution System including all type of specials, valves,pipes all complete, Augmentation of Rising Main, Providing FHTC including Supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 4.88 mtr. x 3.66 mtr. Size pump house including Sanitary Arrangement at H/W Site and 2nd Tube Well Site, Construction of OHR of 300 Cum capacity, Soil investigation for construction of OHR of 300 Cum capacity, Construction Of Boundary Wall At HW Site, Construction Of Boundary Wall At 2nd Tube Well Site And Construction Of Service Road At 2nd Tube Well Site for Natna Zone-II to accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000203/2023-2024 | 3538/ND | 11/08/2023 | 748 | JOY HIND TUBEWELL'S, BELEDANGA GHOSHPARA 2ND LANE, P.O. KRISHNAGAR, DIST. NADIA. PIN-741101. | 560.77 | 0 | 55
1202 | Nadia Division | Kalyani Sub-Division I | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 53 m3/hr at Nathna Zone-II Water Supply Scheme within Tehatta-I Block under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000341/2024-2025 | 7106/ND | 06/12/2024 | 360 | JOY HIND TUBEWELL'S | 185.75 | 0 | 0
1203 | Nadia Division | Kalyani Sub-Division I | Laying additional pipe line for distribution system and rising main for Nathna Zone-II PWSS under augmentation of Nathna Zone-II PWSS (Phase-II) under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000352/2024-2025 | 7051/ND | 02/12/2024 | 270 | JOY HIND TUBEWELL'S | 100.01 | 0 | 75
1204 | Nadia Division | Kalyani Sub-Division I | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
1205 | Nadia Division | Kalyani Sub-Division I | Collection of Household data through mobile app for FHTC Connection (Phase-I), under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000687/2023-2024 | 207/KLYSD-I | 09/02/2024 | 182 | HORIZEN | 4.85 | 0 | 100
1206 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000038/2023-2024 | 1886/ND | 26/04/2023 | 0 | Resource Division | 10.67 | 0 | 0
1207 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000179/2022-2023 | 157/ND | 06/01/2023 | 0 | Resource Division | 27.89 | 0 | 0
1208 | Nadia Division | Kalyani Sub-Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000288/2022-2023 | 12/PFMS | 11/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.18 | 0 | 0
1209 | Central Drilling | Kalyani Sub-Division I | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Nathna W/S Scheme (Z-II,T/W-I & II) , Tehatta-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000070/2023-2024 | 902/CDD | 18/07/2023 | 120 | SANKAR PRASAD DUTTA & CO. | 37.16 | 0 | 50
1210 | Eastern Mechanical | Kalyani Sub-Division I | Quotation for new service connection at Pump House No-II under Natna w/s Scheme, Dist-Nadia. | Assistant Engineer | Junior Engineer | BILL/05672/2023-2024 | BP-378-23-24 | 22/03/2024 | 0 | W.B.S.E.D.C.L (TEHATTA CCC) | 5.88 | 0 | 0
1211 | Eastern Mechanical | Kalyani Sub-Division I | Quotation for new service connection at Pump House No-I under Natna w/s scheme, Dist-Nadia. | Assistant Engineer | Junior Engineer | BILL/05673/2023-2024 | BP-377-23-24 | 22/03/2024 | 0 | W.B.S.E.D.C.L (TEHATTA CCC) | 6.29 | 0 | 0
1212 | Eastern Mechanical | Kalyani Sub-Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Nathna ground water based water supply scheme under Block_ Tehatta-I Dist. - Nadia under EMD, PHE Dte. SM/10416 | Assistant Engineer | Junior Engineer | ORD/000188/2025-2026 | 1126/EMD | 04/06/2025 | 90 | DITHI ENTERPRISE | 16.89 | 0 | 0
1213 | Eastern Mechanical | Kalyani Sub-Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MADHPUR W/S Scheme, Block- Karimpur-I AND NATNA W/S Scheme, Block- Tehatta-I, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/001009/2022-2023 | 497/EMD | 24/01/2023 | 730 | KARTICK BAL | 56.7 | 0 | 30
1214 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VII to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000098/2022-2023 | 3403/ND | 01/08/2022 | 1088 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 326.43 | 278.26 | 98
1215 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Karimpur Jalangi Zone-VIPart-A & B W/S to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000229/2025-2026 | 2035/ND | 29/04/2025 | 90 | BALAJI UDDYOG | 111.41 | 0 | 0
1216 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Karimpur Jalangi Zone-VII water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000372/2024-2025 | 7058/ND | 04/12/2024 | 450 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 31.24 | 0 | 40
1217 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000047/2023-2024 | 1900/ND | 27/04/2023 | 0 | Resource Division | 14.22 | 0 | 0
1218 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000066/2022-2023 | 4316/ND | 29/09/2022 | 0 | Resource Division | 21.75 | 0 | 0
1219 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000186/2022-2023 | 150/ND | 06/01/2023 | 0 | Resource Division | 2.34 | 0 | 0
1220 | Nadia Division | Tehatta Sub-Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-VII to accommodate FHTC in Karimpur-I block with in Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000207/2022-2023 | 31/PFMS | 20/05/2022 | 0 | RADIANT | 2.99 | 0 | 0
1221 | Eastern Mechanical | Tehatta Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-VII under Karimpur-Jalangi ground water based water supply scheme under Block_ Karimpur-I Dist. - North 24PGS under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002969/2023-2024 | 872/EMD | 15/03/2024 | 261 | TARUN KUMAR BHATTACHARYA | 25.34 | 0 | 100
1222 | Nadia Division | Tehatta Sub-Division | Laying of additional pipeline for Madhpur PWSS".under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000076/2024-2025 | 4078/ND | 26/07/2024 | 360 | SUBHASIS MAJUMDER | 16.52 | 0 | 40
1223 | Nadia Division | Tehatta Sub-Division | Renovation of AIRP (Gravity Type) of capacity 31.44 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Madhpur PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000546/2022-2023 | 1456/ND | 31/03/2023 | 360 | APURBA MANDAL | 58.68 | 0 | 21
1224 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Madhpur Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Madhpur at Karimpur-II Block by Augmentation of Ground Water based PWSS for Madhpur Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000642/2024-2025 | 7368/ND | 18/12/2024 | 60 | K.K. MARKETING | 17.61 | 0 | 0
1225 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000059/2022-2023 | 4319/ND | 29/09/2022 | 0 | Resource Division | 4.87 | 0 | 0
1226 | Nadia Division | Tehatta Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MADHPUR Block in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001077/2021-2022 | 640/PFMS | 16/03/2022 | 0 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 2.95 | 0 | 0
1227 | Eastern Mechanical | Tehatta Sub-Division | Supplementary quotation for argumentation of DTR from 25KVA to 63KVA at Madhpur Ref. ID 860261053 | Assistant Engineer | Junior Engineer | BILL/01337/2022-2023 | 137/PFMS/EMD | 23/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.89 | 0 | 0
1228 | Eastern Mechanical | Tehatta Sub-Division | New Service Connection for madhpur Aplication No.3004022790 | Assistant Engineer | Junior Engineer | BILL/01338/2022-2023 | 138/PFMS/EMD | 23/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.01 | 0 | 0
1229 | Eastern Mechanical | Tehatta Sub-Division | New Service connection for Madhpur w/s scheme p.h No 2 | Assistant Engineer | Junior Engineer | ORD/000007/2022-2023 | 2865/EMD | 21/07/2022 | 30 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.34 | 0 | 0
1230 | Eastern Mechanical | Tehatta Sub-Division | New Service connection for Madhpur w/s scheme p.h No 1 | Assistant Engineer | Junior Engineer | ORD/000008/2022-2023 | 2866/EMD | 21/07/2022 | 30 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.01 | 0 | 0
1231 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MADHPUR W/S Scheme, Block- Karimpur-I AND NATNA W/S Scheme, Block- Tehatta-I, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/001009/2022-2023 | 497/EMD | 24/01/2023 | 730 | KARTICK BAL | 56.7 | 0 | 30
1232 | Eastern Mechanical | Tehatta Sub-Division | New Service connection bill for Madhupur W/s scheme | Assistant Engineer | Junior Engineer | VCH/001926/2022-2023 | BP-2022-23-24 | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.34 | 0 | 0
1233 | Eastern Mechanical | Tehatta Sub-Division | New Service connection bill for Madhpur W/s scheme | Assistant Engineer | Junior Engineer | VCH/001927/2022-2023 | BP-2022-23-25 | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.01 | 0 | 0
1234 | Nadia Division | Krishnanagar Sub-Division | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no 03/2022-Central Tax Rate dt 13/7/2022 of Laying and Distribution system including specials,valves and pipe carrying structure all complete,proposed augmentation of rising main system and providing FHTC including supplying ,laying,fitting,fixing of 15mm NB PVC(Schedule 80)/20mm OD HDPE (PE 100,PN 16) pipe with all necessary specials,saddle piece etc all complete for augmentation of ground based water supply scheme at Pansila to accomodate FHTC within Nabadwip block under Krishnagar Sub-Division under Nadia Divn,PHE Dte | Assistant Engineer | Junior Engineer,Junior Engineer 2 | BILL/00247/2024-2025 | 151/PFMS | 31/07/2024 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 18.57 | 0 | 0
1235 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Gravity Type) of capacity 93 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Pansila PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000085/2023-2024 | 2998/ND | 13/07/2023 | 90 | TARUN KUMAR BHATTACHARYA | 90.1 | 0 | 0
1236 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Pansila to accommodate FHTC within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000101/2022-2023 | 3418/ND | 02/08/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 452.17 | 350.08 | 95
1237 | Nadia Division | Krishnanagar Sub-Division | Laying of UPVC Pipeline and providing FHTC including supplying, laying, fitting, fixing with all necessary specials, saddle piece etc. all complete for Ground Based piped water supply scheme in Bankar Dhopadi village to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000139/2025-2026 | 2975/ND | 25/06/2025 | 120 | SARKAR CONSTRUCTION | 91.91 | 0 | 0
1238 | Nadia Division | Krishnanagar Sub-Division | Construction and installation of Manifold at OHR site and allied works in connection to the Augmentation of Pansila Water Supply Scheme under Nabadwip Block under Nadia Division, P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000335/2025-2026 | 5355/6043/ND | 03/12/2025 | 60 | KESHOB ENTERPRISE | 28.71 | 0 | 0
1239 | Nadia Division | Krishnanagar Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 450 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Pansila Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000393/2023-2024 | 5122/ND | 17/11/2023 | 90 | INDUSTRIAL CONSTRUCTION | 29.08 | 0 | 70
1240 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000029/2022-2023 | 4088/ND | 21/09/2022 | 0 | Resource Division | 84.05 | 0 | 0
1241 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000067/2022-2023 | 4321/ND | 29/09/2022 | 0 | Resource Division | 17.77 | 0 | 0
1242 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Pansila Block: Nabadwip, Dist: Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/000198/2022-2023 | 22/PFMS | 20/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.18 | 0 | 0
1243 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PANSILA W/S Scheme, Block-Nabadwip , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001013/2022-2023 | 501/EMDdt.24.01.2023 | 16/03/2023 | 30 | ASHOKE ADHIKARY | 15.59 | 11.92 | 100
1244 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under CHANDERGHAT(Block-Tehatt-I), FATEPUR(Block-Tehatt-I), KADIPUR(Block-Krishnaganj) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000008/2023-2024 | 1506/EMD | 18/04/2023 | 30 | BARISAL TRADING CO. | 17.08 | 0 | 100
1245 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Chanderghat Water Supply Scheme in Tehatta-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000070/2023-2024 | 325_2/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.43 | 0 | 100
1246 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chenderghat W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000168/2021-2022 | 835/NACD-II | 28/10/2021 | 45 | SINGHA ROY & CO. | 23.48 | 23.43 | 100
1247 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Restoration of damaged distribution pipe line laying, broken due to construction of Drain by the local panchayat at Chanderghat (Purba para) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000179/2022-2023 | 521/NACD-II | 05/08/2022 | 30 | CHANDAN ROY | 11.7 | 11.16 | 100
1248 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chanderghat W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000216/2021-2022 | 919/NACD-II | 26/11/2021 | 45 | SINGHA ROY & CO. | 11.55 | 11.54 | 100
1249 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at MobarakpurW/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000220/2021-2022 | 50/NACD-II | 19/01/2022 | 90 | PATHIK PABAN NANDI | 127.95 | 0 | 100
1250 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Chanderghat Water Supply Scheme at Head Work site under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000244/2021-2022 | 100/NACD-II | 10/02/2022 | 45 | M/S FREEDOM CONSTRUCTION | 11.26 | 11.17 | 100
1251 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) under Chanderghat Mouza at Chanderghat Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000254/2023-2024 | 231/NACD-II | 21/02/2024 | 45 | SAFTI PRIVATE LIMITED | 21.65 | 0 | 60
1252 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Chanderhat Water Supply Scheme of capacity 53 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000288/2023-2024 | 178/NACD-II | 08/02/2024 | 60 | TARUN KUMAR BHATTACHARYA | 161.99 | 0 | 0
1253 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Chanderghat PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000305/2024-2025 | 357/AE-II/NACD-II | 19/11/2024 | 7 | MAKALI ENGINEERING CORPORATION | 0.99 | 0 | 100
1254 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Bara Andulia(Zone-I) W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(PART-A) | Assistant Engineer |  | ORD/000278/2021-2022 | 5690/ND | 03/11/2021 | 90 | H I ENTERPRISE | 98.23 | 95.03 | 0
1255 | Nadia Division | Krishnanagar Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
1256 | Nadia Division | Krishnanagar Sub-Division | Laying Of Additional Distribution System Including Specials to provide FHTC at Leftout Household in connection with JJM In Ground Based Piped Water Supply Scheme at Bara Andulia Zone I To Accommodate FHTC Within Chapra Block Under Krishnanagar Sub-division Under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000316/2025-2026 | 4504/ND | 18/09/2025 | 90 | S.S.INFRASTRUCTURE | 68.11 | 0 | 0
1257 | Nadia Division | Krishnanagar Sub-Division | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000721/2024-2025 | 7570/ND | 27/12/2024 | 45 | IMAGIN | 19.44 | 0 | 100
1258 | Nadia Division | Krishnanagar Sub-Division | Hiring Diesel Luxury Car on daily basis (for12 months from 01.02.2022 to 31.01.2023) for the office use of the Assistant Engineer, Kalyani Sub - Division - II, P.H.E. Dte. | Assistant Engineer |  | ORD/000735/2021-2022 | 144/ Kly SD-II | 31/01/2022 | 365 | SUMAN CHAKRABORTY | 4.8 | 0 | 65
1259 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Kalyani Sub-Division-I, PHE Dte. | Assistant Engineer |  | ORD/000750/2021-2022 | 287/Kly SD-I | 31/03/2022 | 365 | SATYABRATA CHAKRABORTY | 4.8 | 0 | 100
1260 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000034/2021-2022 | 441/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
1261 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000078/2021-2022 | 782/ND | 18/02/2022 | 0 | Resource Division | 4.39 | 0 | 0
1262 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000104/2021-2022 | 1022/ND | 03/03/2022 | 0 | Resource Division | 7.9 | 0 | 0
1263 | Nadia Division | RWS Nadia Sub-Division | Health Check up of existing Over Head Reservoir(OHR) based on inspection and Non-destructive Test (NDT) at Iswarchandrapur PWSS, Tehatta-II Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Tehatta - II Block | ORD/000017/2024-2025 | 3374/ND | 14/06/2024 | 15 | JADAVPUR UNIVERSITY | 3.48 | 0 | 100
1264 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Iswarchandrapur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Tehatta - II Block | ORD/000095/2022-2023 | 3382/ND | 29/07/2022 | 90 | M/S SHIL & CO. | 79.62 | 75 | 98
1265 | Nadia Division | RWS Nadia Sub-Division | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Iswarchandrapur Water Supply Scheme Under RWS Nadia Sub-Divn.PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Tehatta - II Block | ORD/000679/2023-2024 | 1178/ND | 21/02/2024 | 90 | U-TURN CONSTRUCTION | 25.12 | 0 | 75
1266 | Nadia Division | RWS Nadia Sub-Division | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Iswarchandrapur PWSS within Tehatta-II Block under RWS Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Tehatta - II Block | ORD/000726/2023-2024 | 1255/ND | 22/02/2024 | 45 | M/S SHIL & CO. | 6.19 | 0 | 95
1267 | Nadia Division | RWS Nadia Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 30 cum/hr at Iswarchandrapur water supply scheme including 3 Months Trial Run & 3 Years O&M within Tehatta-II block under RWS Nadia Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Tehatta - II Block | ORD/000735/2023-2024 | 1491/ND | 04/03/2024 | 180 | SATYABRATA CHAKRABORTY | 162.34 | 0 | 45
1268 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Tehatta - II Block | RTOR000060/2022-2023 | 4308/ND | 29/09/2022 | 0 | Resource Division | 5.94 | 0 | 0
1269 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Tehatta - II Block | RTOR000178/2022-2023 | 155/ND | 06/01/2023 | 0 | Resource Division | 0.96 | 0 | 0
1270 | Nadia Division | RWS Nadia Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ISWARCHANDRAPUR to Accommodate FHTC in Tehatta-II block of Nadia district under Nadia division P.H.E. Dte | Assistant Engineer | Junior Engineer,Junior Engineer Tehatta - II Block | VCH/000289/2022-2023 | 13/PFMS | 11/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.6 | 0 | 0
1271 | Eastern Mechanical | RWS Nadia Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under ISWARCHANDRAPUR ground water based water supply scheme under Block_ Tehatta-I Dist. - Nadia under EMD, PHE Dte. SM/10423 | Assistant Engineer | Junior Engineer,Junior Engineer Tehatta - II Block | ORD/000185/2025-2026 | 1122/EMD | 04/06/2025 | 90 | M/S DILIP MITRA | 16.93 | 0 | 0
1272 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No.- I AND II under Iswarchandrapur W/S Scheme, Block Tehatta II, Dist. Nadia. NIET No. 23 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer,Junior Engineer Tehatta - II Block | ORD/000884/2022-2023 | 152/EMD | 06/01/2023 | 30 | M/S. G.P. ENTERPRISE | 21.36 | 21.09 | 0
1273 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD andallied works at OHR site under Matikumra Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Matikumra (Phase-I) Piped W/S Scheme (Sl.no.20) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000050/2023-2024 | 1449/NAD-I | 26/05/2023 | 15 | M/S DIPAK ENTERPRISE | 13.02 | 0 | 100
1274 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of FHTC and Laying of balanced Pipeline at the command areas of Gayeshpur, Panpara (Part) and Matikumra Mouza under Matikumra Water Supply scheme Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000070/2025-2026 | 531/NAD-I | 03/07/2025 | 60 | M/S DIPAK ENTERPRISE | 49.93 | 0 | 0
1275 | Nadia Arsenic Division I | Nadia Arsenic Division I | FHTC under Jaldhara/Jalswapna for Matikumra Phasa -I at Ranaghat -II Block by augmentation of Ground Water Based PWSS Matikumra Ws scheme under Nadia Arsenic Division -I , P.H.E.Dte. (Sl.no.05) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000091/2022-2023 | 1938/NAD-I | 12/10/2022 | 90 | SATYABRATA CHAKRABORTY | 416.57 | 308.7 | 100
1276 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP of Ground Water Based Piped Water Supply Scheme for Goalpur Zone-II, (30 cum/hr) including augmentation of Matikumra Water Supply Scheme under Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000144/2024-2025 | 1882/NAD-I | 11/11/2024 | 180 | BALAJI UDDYOG | 129.1 | 0 | 0
1277 | Nadia Arsenic Division I | Nadia Arsenic Division I | Reconnection at Ukhilnara Chowmatha, laying of pipeline from Ukhilnara Zone-I headwork site to Ukhilnara Chowmatha at Payrandanga G.P in Ukhilnara Zone-I PWSS & Reparing and laying of pipeline at Golabazar ,Matikumra Bazar and 2nd T/W site at Nokari G.P under Jal Jeevan Mission (JJM) for Ranaghat-I & Ranaghat-II Block by retrofitting of Ground Water based PWSS for Matikumra Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000299/2023-2024 | 90/AE-I/NAD-I | 22/02/2024 | 30 | GANGULY ENTERPRISE | 3.88 | 0 | 100
1278 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Matikumra (Phase-I) under Block_ Ranaghat-II Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/10661) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000154/2025-2026 | 1155/EMD | 04/06/2025 | 90 | KASHINATH PAL & CO. | 4.34 | 0 | 0
1279 | Eastern Mechanical | Nadia Arsenic Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II and III (Zone-I) (Phase-I) under Matikumra ground water based water supply scheme under Block_ Ranaghat-II Dist. - Nadia under EMD, PHE Dte. (SM/10661) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000649/2024-2025 | 2686/EMD | 20/11/2024 | 30 | M/S DILIP MITRA | 31.76 | 0 | 0
1280 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHtC (Functional Household Tap Connection) under Jaldhara/jalswapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I ,PHE Dte | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | BILL/00189/2024-2025 | 213/PFMS | 26/09/2024 | 0 | GHOSH ENTERPRISE | 13.73 | 0 | 0
1281 | Nadia Arsenic Division I | Nadia Arsenic Division I | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Debagram ii)Dhantala iii)Dubli Zone-I iv)Dubli Zone-II v)Zone-IX (Chandmari) vi)Zone-XII (Madanpur) vii)Nabla | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000006/2023-2024 | 168/AE-I/NAD-I | 12/04/2023 | 15 | TECH VISION | 4.84 | 3.1 | 41
1282 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall and pathway and Toilet at 2nd, 3rd and 4th Tubewell site of Aranghata and 3rd site of Debogram water supply Scheme in Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. Under JJM. (Sl. No. 09) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000029/2025-2026 | 155/NAD-I | 28/04/2025 | 60 | GOUTAM DEY | 34.34 | 0 | 0
1283 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000031/2022-2023 | 1475/NAD-I | 22/08/2022 | 90 | GHOSH ENTERPRISE | 320.01 | 256.29 | 100
1284 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of additional pipelines and FHTC at south west part of Betna W/S Scheme under JJM at Betna W/S Scheme inconnection with Betna and Debogram water supply scheme under Ranaghat - II block within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 09) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000059/2024-2025 | 1621/NAD-I | 27/09/2024 | 182 | M/S A.K. CONSTRUCTION | 68.67 | 0 | 75
1285 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of existing pipelines at Debagram, Ranaghat-II Block in connection with providing FHTC undr JJM under Debagram W/S Scheme under Nadia Arsenic Division-I , PHE Dte. (Sl. No. 09) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000072/2023-2024 | 1385/NAD-I | 16/05/2023 | 21 | GHOSH ENTERPRISE | 23.15 | 21.9 | 0
1286 | Nadia Arsenic Division I | Nadia Arsenic Division I | Surging of existing Tube Well situated at the 3rd Tube Well site at Debogram Water Supply Scheme in Connection with Jal Jeevan Mission under Hanskhali Block to increase the yield of the Tube Well under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 03) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000080/2024-2025 | 205/AE-II/NAD-I | 24/09/2024 | 7 | SUMAN CHAKRABORTY | 0.64 | 0 | 0
1287 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC and laying dedicated pipeline for Sijdia, Dakhin Rameswarpur,Anatapur, Mithapur & aismali Village in connection with Debagram Water Supply Scheme under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000080/2025-2026 | 581/NAD-I | 10/07/2025 | 60 | SUMAN CHAKRABORTY | 96.78 | 0 | 0
1288 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting works at Debogramunder Debogram W/S Schemeunder JJM under Ranaghat- II Block under Nadia Arsenic Division-I,P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000147/2023-2024 | 375/AE-II/NAD-I | 29/08/2023 | 7 | JYOTIRMOY ENTERPRISE | 3.76 | 0 | 100
1289 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of Debagram, Ranaghat-II Block in connection with providing FHTC under Debagram W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000151/2023-2024 | 2096/NAD-I | 31/08/2023 | 15 | UMWELT ENGINEER PVT. LTD. | 23.14 | 0 | 100
1290 | Nadia Arsenic Division I | Nadia Arsenic Division I | Continuation Work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000199/2024-2025 | 18/AE-I/NAD-I | 31/01/2025 | 89 | SUMAN CHAKRABORTY | 4.85 | 0 | 0
1291 | Nadia Arsenic Division I | Nadia Arsenic Division I | Field Level Survey of different School/Anganwadi Centre (AWC) by GPs enabled Mobile Application for uploading of data at IMIS website in Nadia District under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000220/2023-2024 | 467/AE-I/NAD-I | 09/10/2023 | 630 | TECH VISION | 1.15 | 0 | 100
1292 | Nadia Arsenic Division I | Nadia Arsenic Division I | Renovation of IEP (155m3/hr.) at Debogram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000227/2023-2024 | 2298/NAD-I | 29/09/2023 | 491 | M/S DIPAK ENTERPRISE | 15.81 | 0 | 100
1293 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Debagram Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Debagram W/S Scheme (Phase-I) under JJM(Sl.no.01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000297/2022-2023 | 719/NAD-I | 27/03/2023 | 15 | CHANDAN ROY | 12.95 | 12.52 | 100
1294 | Nadia Arsenic Division I | Nadia Arsenic Division I | Continuation Work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000354/2023-2024 | 448/AE-I/NAD-I | 29/09/2023 | 91 | SUMAN CHAKRABORTY | 4.85 | 0 | 100
1295 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | RTOR000010/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 22.55 | 0 | 0
1296 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Debagram (Phase-I) under Block_ Ranaghat-II Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/10662) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000166/2025-2026 | 1163/EMD | 04/06/2025 | 90 | S.S.ENTERPRISES | 4.34 | 0 | 0
1297 | Eastern Mechanical | Nadia Arsenic Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II , III and IV (Phase-I) under DEBGRAM ground water based water supply scheme under Block_ Ranaghat-II Dist. Nadia under EMD, PHE Dte. (SM/10662) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000641/2024-2025 | 2678/EMD | 20/11/2024 | 30 | DEY ENTERPRISE | 41.01 | 0 | 0
1298 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution System including Specials & Valves, Pipe supporting structure all complete based on actual estimate & Providing FHTC at Murutia Water Supply Scheme in Nadia District under Nadia Division. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000704/2021-2022 | 967/ND | 28/02/2022 | 1350 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 469.7 | 158.52 | 65
1299 | Nadia Division | RWS Nadia Sub-Division | Construction and Installation of 120.00 cum capacity Arsenic-Cum-Iron Removal Plant (AIRP) at Murutia PWSS including 3 Months Trial Run & 3 Years O&M under Nadia Division, P.H.E. Dte | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000705/2023-2024 | 1250/ND | 22/02/2024 | 720 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 300.56 | 0 | 60
1300 | Nadia Division | RWS Nadia Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Murutia PWSS under Karimpur-II Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM) . | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000744/2024-2025 | 422/ND | 27/01/2025 | 120 | M/S SANJAY ADHIKARI | 29.73 | 0 | 0
1301 | Nadia Division | RWS Nadia Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House and allied works for Muktadaha Zone-II PWSS and Murutia PWSS within Karimpur-I Block and Karimpur-II Block Under Tehatta Sub-Division under Nadia Division P.H.E. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000790/2024-2025 | 762/ND | 19/02/2025 | 90 | DEBASIS SAMADDAR | 74.08 | 0 | 0
1302 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000054/2022-2023 | 4271/ND | 29/09/2022 | 0 | Resource Division | 27.23 | 0 | 0
1303 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000125/2021-2022 | 1256/ND | 16/03/2022 | 0 | Resource Division | 88.59 | 0 | 0
1304 | Nadia Division | RWS Nadia Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | VCH/001063/2021-2022 | 621/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.44 | 0 | 0
1305 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I under Murutia W/S Scheme, Block Karimpur-II, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-03) | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000886/2022-2023 | 154/EMD | 06/01/2023 | 30 | TALUKDER & CO. | 13.64 | 13.33 | 20
1306 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer etc. rejuvenation to Accommodate FHTC at Pump House No. II under Murutia W/S Scheme, Block Karimpur -II, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-04) | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000887/2022-2023 | 155/EMD | 06/01/2023 | 30 | K.S.P. ENTERPRISE | 8.76 | 0 | 100
1307 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer etc. rejuvenation to Accommodate FHTC at Pump House No. III under Murutia WS Scheme, Block KarimpurII, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-05) | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000888/2022-2023 | 156/EMD | 06/01/2023 | 30 | MUKHERJEE ART CENTRE | 8.75 | 8.75 | 98
1308 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SAKDA (Block-Krishnaganj), BAHADURPUR(Block-Tehatt-I), BETBERIA(Block-Chapra) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000009/2023-2024 | 1507/EMD | 18/04/2023 | 30 | SWAPAN KUMAR BHANJA | 14.69 | 4.88 | 100
1309 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Betberia Water Supply Scheme in Chapra Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000074/2023-2024 | 328/1/AE-I/NACD-II | 13/07/2023 | 7 | RISHAN ENGINEERING CONSULTANCY | 0.46 | 0 | 100
1310 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Betberia) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000101/2023-2024 | 1146/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100
1311 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Betbaria W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000104/2020-2021 | 167/NACD-II | 09/02/2021 | 21 | B.M. ENGINEERING & CONSTRUCTION | 59.73 | 0 | 100
1312 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Betberia W/S Scheme & Hridaypur W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000135/2024-2025 | 748_NACD-II | 14/06/2024 | 45 | SAFTI PRIVATE LIMITED | 18.22 | 0 | 100
1313 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Betberia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000138/2021-2022 | 865/NACD-II | 08/11/2021 | 45 | SHIBU BISWAS | 53.1 | 53.07 | 100
1314 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Structural Health assesment of existing shaft type OHR of Chapra Blocks and ancillary structures conducting Non Destructive test and through visual observation under Nadia Arsenic Civil Division-II P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000187/2023-2024 | 1434/NACD-II | 15/12/2023 | 30 | RISHAN ENGINEERING CONSULTANCY | 8.46 | 0 | 100
1315 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Betberia 2nd tube well Site under Betberia Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000207/2024-2025 | 904/AE-I/NACD-II | 10/09/2024 | 30 | ARIT KUMAR PAL | 4.83 | 0 | 0
1316 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Betberia Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000260/2022-2023 | 1015/NACD-II | 29/11/2022 | 60 | BISHAL CONSTRUCTION | 9.95 | 9.76 | 90
1317 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Betberia 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000285/2021-2022 | 240/AE-I/NACD-II | 17/02/2022 | 30 | SAHA ENGINEERS | 4.04 | 4.04 | 100
1318 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Betberia Water Supply Scheme of capacity 39Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000291/2023-2024 | 397/NACD-II | 13/03/2024 | 60 | M/S. R.K.ENTERPRISE | 150.86 | 0 | 0
1319 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Betberia Headwork Site under Betberia Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000331/2024-2025 | 1028/AE-I/NACD-II | 10/12/2024 | 30 | JAYBRATO HALDER | 3.53 | 0 | 0
1320 | Eastern Mechanical | Nadia Arsenic Civil Division II | Quotation for load enhancement at Pump House No-I of Shyamanagar (Krishnaganj Block) w/s scheme under EMSD-III,PHE Dte.,Nadia | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/01328/2024-2025 | BP-73-24-25 | 30/07/2024 | 0 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 0.44 | 0 | 0
1321 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SHYAMNAGAR(Block-Krishnaganj), MOBARAKPUR(Block-Tehatt-I), PATHARGHAT(Block-Tehatt-I) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000007/2023-2024 | 1505/EMD | 18/04/2023 | 30 | DIPALI CONSTRUCTION | 19.37 | 0 | 90
1322 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SHYAMNAGAR(Block-Krishnaganj), MOBARAKPUR(Block-Tehatt-I), PATHARGHAT(Block-Tehatt-I) W/S Scheme, Dist. - Nadia. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001482/2023-2024 | 1505/EMD. | 18/04/2023 | 30 | DIPALI CONSTRUCTION | 19.37 | 6.37 | 80
1323 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Relaying of rising main and other necessary allied works at Shyamnagar Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000007/2025-2026 | 21/AE-I/NACD-II | 11/04/2025 | 60 | NISHITH BANERJEE | 3.66 | 0 | 0
1324 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Shyamnagar Water Supply Scheme in Krishnaganj Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000066/2023-2024 | 323_2/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 2.29 | 0 | 100
1325 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Shyamnagar Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000123/2022-2023 | 59/AE-II/NACD-II | 28/06/2022 | 30 | R.M. TRADING | 2.74 | 2.72 | 100
1326 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection(Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10mm dia gun-Metal ferrule,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline(parallel or extension) at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000127/2020-2021 | 271/EE/NACD-II | 22/02/2021 | 21 | SANDIP BISWAS | 52.44 | 0 | 100
1327 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000131/2021-2022 | 870/NACD-II | 08/11/2021 | 45 | BIDYUT KUMAR | 34.62 | 34.61 | 100
1328 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of RCC Column for supporting pipeline for future extension ( Near Khalbualia Bridge) alongwith Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000137/2022-2023 | 453/NACD-II | 14/07/2022 | 45 | SANJIB DEY | 8.58 | 0 | 100
1329 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | New pipeline laying by providing 200 mm dia D.I. pipe over existing columns to cross the PWD Bridge and PVC pipe for supplying water to Khalboalia village under krishnaganj Block and also Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at ( Vill- Khalboalia) Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000178/2022-2023 | 520/NACD-II | 05/08/2022 | 60 | SANJIB DEY | 96.93 | 0 | 100
1330 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Shyamnagar Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000248/2023-2024 | 25/AE-II/NACD-II | 15/02/2024 | 15 | SUMIT GHOSH | 0.97 | 0 | 0
1331 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Shyamnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000261/2020-2021 | 190/NACD-II | 15/02/2021 | 21 | SANDIP BISWAS | 36.12 | 0 | 100
1332 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Shyamnagar Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000263/2021-2022 | 46/AE-II/NACD-II | 17/02/2022 | 30 | R.M. TRADING | 4.97 | 4.97 | 100
1333 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Shyamnagar Water Supply Scheme of capacity 67 Cu.m/hr in Krishnaganj Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000286/2023-2024 | 185/NACD-II | 09/02/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 194.41 | 0 | 100
1334 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work Order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Falia) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000296/2021-2022 | 112/NACD-II | 11/02/2022 | 90 | MONDAL ENTERPRISE | 45.84 | 0 | 100
1335 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Shyamnagar W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000301/2022-2023 | 1199/NACD-II | 23/12/2022 | 15 | R.M. TRADING | 0.89 | 0 | 100
1336 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 nonmagnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Shyamnagar PWSS in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000311/2024-2025 | 362/AE-II/NACD-II | 19/11/2024 | 7 | PUNGENT ENGINEERING PVT LTD | 0.98 | 0 | 100
1337 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work with Reinforced Barbed Tape , OverHead Reservoir Plaster , Painting and other allied works at Shyamnagar HeadWork site and 2nd Pump house site under Shyamnagar Piped Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000345/2024-2025 | 1639/NACD-II | 23/12/2024 | 449 | SAMAR ENTERPRISE | 10.13 | 0 | 100
1338 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD and allied works at OHR site under Shyamnagar Piped Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000416/2024-2025 | 09/NACD-II | 06/02/2025 | 90 | SUMIT GHOSH | 105.58 | 0 | 0
1339 | Nadia Division | RWS Nadia Sub-Division | Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000033/2024-2025 | 3450/ND | 20/06/2024 | 45 | IMAGIN | 19.44 | 0 | 100
1340 | Nadia Division | RWS Nadia Sub-Division | Additional work of Laying Distribution System and additional work of providing FHTC in connection with Augmentation of Teinpur Zone - III PWSS within Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000060/2024-2025 | 3904/ND | 16/07/2024 | 315 | PRADIP KUMAR BANIK | 20.67 | 0 | 70
1341 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Teinpur Zone-III to accommodate FHTC within Karimpur-II block under RWS Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000137/2022-2023 | 3819/ND | 05/09/2022 | 90 | B.S. ENTERPRISE | 102.68 | 0 | 95
1342 | Nadia Division | RWS Nadia Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site of Teinpur zone-III PWSS under Karimpur-II Block under RWS Sub Division under Nadia Division-,P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000298/2024-2025 | 6756/ND | 11/11/2024 | 180 | M/S S.K. ENTERPRISE | 24.3 | 0 | 95
1343 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP and Construction of Backwash chamber for AIRP at Head Work Site at Teinpur Zone-III PWSS under Nadia Division PHE Dte. Capacity- 40.30 cum/hr | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000552/2023-2024 | 782/ND | 05/02/2024 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 83.94 | 0 | 70
1344 | Nadia Division | RWS Nadia Sub-Division | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Tenpur (Zone-III) Water Supply Scheme, Karimpur-I Block Under RWS Nadia Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000677/2023-2024 | 1176/ND | 21/02/2024 | 720 | B K ENGINEERING | 29.16 | 0 | 65
1345 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000026/2022-2023 | 3897/ND | 08/09/2022 | 0 | Resource Division | 26.95 | 0 | 0
1346 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000074/2022-2023 | 4278/ND | 29/09/2022 | 0 | Resource Division | 2.44 | 0 | 0
1347 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000109/2023-2024 | 3790/ND | 24/08/2023 | 0 | Resource Division | 1.6 | 0 | 0
1348 | Nadia Division | RWS Nadia Sub-Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-III) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | VCH/000201/2022-2023 | 25/PFMS | 20/05/2022 | 0 | ENVIROTECH SOLUTIONS | 2.55 | 0 | 0
1349 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/001012/2022-2023 | 500/EMD | 24/01/2023 | 30 | M/S DILIP MITRA | 64.62 | 10.18 | 85
1350 | Nadia Division | Tehatta Sub-Division | Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Jone-XB to accommodate FHTC Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000342/2022-2023 | 242/ND | 13/01/2023 | 818 | CHOWDHURY & CO. | 79.52 | 0 | 90
1351 | Nadia Division | Tehatta Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-10B W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000407/2021-2022 | 321/TSD | 24/11/2021 | 30 | RADIANT | 2.44 | 2.44 | 100
1352 | Nadia Division | Tehatta Sub-Division | Sinking of 01 no Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Karimpur Jalangi PWSS Zone-X(B) Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000691/2023-2024 | 1226/ND | 22/02/2024 | 330 | MANISHIKA CONSTRUCTION | 17.38 | 0 | 100
1353 | Nadia Division | Tehatta Sub-Division | Construction of barbed wire fencing with concrete pillars at Hatisala Karimpur-Jalangi Zone-X(B) water supply scheme (New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM | Assistant Engineer | Junior Engineer | ORD/000730/2023-2024 | 1120/TSD | 21/02/2024 | 7 | NIVEDITA CONSTRUCTION | 1.46 | 0 | 100
1354 | Nadia Division | Tehatta Sub-Division | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement at H.W Site and consruction of Boundary wall at Head Work Site At Karimpur Jalangi Zone- X(B) Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000760/2023-2024 | 1633/ND | 07/03/2024 | 720 | M/S BAPI ENTERPRISE | 24.15 | 0 | 80
1355 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000071/2023-2024 | 2313/ND | 29/05/2023 | 0 | Resource Division | 5.45 | 0 | 0
1356 | Eastern Mechanical | Tehatta Sub-Division | Quotation charges for new service connection and security deposit at Karimpur Jalangi Zone-X,B (Hatisala) PH-II under EMSD-III,Nadia | Assistant Engineer | Junior Engineer | BILL/02239/2024-2025 | BP-179 | 13/12/2024 | 0 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 7.19 | 0 | 0
1357 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI (Z-IV, V & XB) W/S Scheme, Block-Karimpur I , Dist. - Nadia. NIET NO. - 33 OF EE/EMD OF 2022-23 (SL. NO. - 03) | Assistant Engineer | Junior Engineer | ORD/001926/2022-2023 | 1198/EMD | 22/03/2023 | 771 | AVINABA ENGINEERING CONCERN | 62.41 | 0 | 80
1358 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamgachi Zone-I to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-I) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000301/2022-2023 | 5353/ND | 22/12/2022 | 1086 | JAL PRAVAHIKA PRIVATE LIMITED | 240.61 | 55.66 | 85
1359 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamgachi Zone-II to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-I) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000302/2022-2023 | 5352/ND | 22/12/2022 | 1080 | TANMOY ROY CHOWDHURY | 221.89 | 162.85 | 85
1360 | Nadia Division | Ranaghat Sub-Division | Repairing of Pump house-I with sanitary arrangement under augmentation of Kamgachi Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000302/2024-2025 | 1276/RSD | 04/10/2024 | 45 | SAGAR ENTERPRISE | 1.9 | 0 | 100
1361 | Nadia Division | Ranaghat Sub-Division | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-1 site at Kamgachi Zone-I Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000318/2024-2025 | 1279(A)RSD | 04/10/2024 | 75 | M/S SAYAN ENTERPRISE | 4.46 | 0 | 0
1362 | Nadia Division | Ranaghat Sub-Division | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Banpur ii) Dakshinpara (Zone-I)iii) Dakshinpara (Zone-II) iv) Kamgachi (Zone-I)(Part-I) v)Kamgachi (Zone-I)(Part-II)vi)Kamgachi (Zone-II)(Part-I) vii) Kamgachi (Zone-II)(Part-II) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000440/2022-2023 | 246/Kly SD-I | 27/02/2023 | 181 | HORIZEN | 4.99 | 0 | 100
1363 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000033/2023-2024 | 1870/MD | 26/04/2023 | 0 | Resource Division | 53.35 | 0 | 0
1364 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000053/2023-2024 | 2124/ND | 16/05/2023 | 0 | Resource Division | 71.38 | 0 | 0
1365 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000066/2023-2024 | 2309/ND | 29/05/2023 | 0 | Resource Division | 28.03 | 0 | 0
1366 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000113/2023-2024 | 27/ND | 03/01/2024 | 0 | Resource Division | 61.68 | 0 | 0
1367 | Nadia Division | Ranaghat Sub-Division | Augmentation of Ground Water Based Kamgachi PWSS Part to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/000204/2022-2023 | 28/PFMS | 20/05/2022 | 0 | RADIANT | 3.53 | 0 | 0
1368 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KAMGACHI(Z-I) W/S Scheme, Block- RANAGHAT I , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 07) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000016/2023-2024 | 1579/EMD | 24/04/2023 | 30 | CINZANO | 32.65 | 0 | 0
1369 | Eastern Mechanical | Nadia Arsenic Civil Division II | Shifting of S/S Structure at Sbibniwas under KNJCCC at PH-II Z-I under Helenchi W/S Scheme. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/01881/2023-2024 |  | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.96 | 0 | 0
1370 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/001771/2022-2023 | 1121/EMD | 16/03/2023 | 30 | M.S. ENTERPRISE | 65.68 | 8.84 | 90
1371 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Chakdignagar ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl. No. 7) | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/003198/2023-2024 | 948/EMD | 18/03/2024 | 410 | KARTICK BAL | 22.35 | 0 | 90
1372 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Shifting of S/S structure at Sbibniwas under KNJ CCC related to Helenchi Zone -I PH-2 | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00350/2023-2024 | 164 | 14/09/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.96 | 0 | 0
1373 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution System including providing FHTC at left out households and repairing of damaged Pipeline for Helenchi Zone-I W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000110/2025-2026 | 940/NACD-II | 28/07/2025 | 60 | SANJOY BAKSHI | 22.92 | 0 | 0
1374 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Approach Road with land Development at Helenchi Zone-I Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000130/2022-2023 | 66/AE-II/NACD-II | 28/06/2022 | 30 | NISHITH BANERJEE | 2.35 | 2.29 | 100
1375 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Helenchi Zone-I, (Block-Krishnaganj) piped water supply schemes | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000154/2021-2022 | 153/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.91 | 2.91 | 100
1376 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-I, (Vill- Sibnibash) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000206/2021-2022 | 991/NACD-II | 30/12/2021 | 45 | JOY GOPAL GUPTI | 95.14 | 95.14 | 100
1377 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-I, (Vill- Sibnibash) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000233/2021-2022 | 64/NACD-II | 25/01/2022 | 45 | JOY GOPAL GUPTI | 21.43 | 21.43 | 100
1378 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Helenchi Zone-I Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000242/2023-2024 | 18/AE-II/NACD-II | 15/02/2024 | 15 | M/S SHILL & CO. | 0.97 | 0 | 100
1379 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Helenchi ZoneI Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000251/2021-2022 | 105/NACD-II | 10/02/2022 | 45 | NISHITH BANERJEE | 8.61 | 8.6 | 100
1380 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Helenchi Zone-III Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000261/2021-2022 | 43/AE-II/NACD-II | 17/02/2022 | 30 | SUMIT GHOSH | 4.29 | 4.28 | 100
1381 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of boundary wall with grill gate and barbed wire fencing at Helenchi Zone-I water supply scheme Head work site under Nadia Arsenic Civil Division-II, PHE Dte, Nadia District. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000261/2022-2023 | 1016/NACD-II | 29/11/2022 | 60 | SANJIB BISWAS | 18.63 | 18.43 | 95
1382 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-I W/s Scheme (Vill- Krishnapur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000277/2021-2022 | 125/NACD-II | 21/02/2022 | 90 | A.P. POWER & CONCRETE | 105.67 | 86.15 | 100
1383 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Helenchi Zone-I W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000297/2022-2023 | 1195/NACD-II | 23/12/2022 | 15 | DYNAMIC CONSTRUCTION | 1.05 | 0 | 100
1384 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Helanchi zone-I PWSS in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000307/2024-2025 | 359/AE-II/NACD-II | 19/11/2024 | 7 | MAKALI ENGINEERING CORPORATION | 0.95 | 0 | 100
1385 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Functional House Hold Tap Connection for left out Household regarding Har Ghar Jal Certification including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Vill- Par Chandan Nagar, Shibnibas, Pabakhali) Helenchi Zone-I W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000348/2022-2023 | 148/NACD-II | 17/01/2023 | 20 | A.K ADHIKARY | 5.95 | 5.95 | 100
1386 | Nadia Division | Ranaghat Sub-Division | Construction and installation of MANIFOLD and allied works at Head Works site under Dakshinpara Zone-II Ground Based Water Supply Scheme under Hanskhali Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000072/2025-2026 | 2433/ND | 26/05/2025 | 90 | M/S S.K. ENTERPRISE | 12.34 | 0 | 0
1387 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of head work site pump house & allied works of Dakshinpara-II W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000225/2022-2023 | 555/RSD | 30/08/2022 | 30 | DURGADAS BASU | 2.15 | 1.78 | 85
1388 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of pump house & allied works in the premises at pump house no-I of Dakshinpara-II W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000226/2022-2023 | 555/A/RSD | 30/08/2022 | 30 | TINA CONSTRUCTION | 2.5 | 0 | 80
1389 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of boundary wall & allied works in the premises at pump house no 2 of Dakshinpra-II W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000243/2022-2023 | 468/A/RSD | 26/07/2022 | 30 | MASUM CONSTRUCTION | 3.15 | 3.13 | 90
1390 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation & repair of AIRP pump house & allied works of Dakshinpara-II W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000244/2022-2023 | 476/RSD | 27/07/2022 | 30 | CONSTRUCTURE | 1.96 | 0 | 90
1391 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying,laying,fitting,fixing of 15mm NB PVC(schedule 80/20 mm) OD HDPE(PE 100 , PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply scheme for dakshinpara Zone-II to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000292/2022-2023 | 5331/ND | 21/12/2022 | 45 | NEERMAN | 96.27 | 7.55 | 91
1392 | Nadia Division | Ranaghat Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Dakshinpara-II PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 35.00 Cu.m/hr | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000467/2023-2024 | 134/ND | 09/01/2024 | 450 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 60.46 | 0 | 91
1393 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000022/2023-2024 | 1866/ND | 26/04/2023 | 0 | Resource Division | 19.87 | 0 | 0
1394 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000065/2023-2024 | 2308/ND | 29/05/2023 | 0 | Resource Division | 1.48 | 0 | 0
1395 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000110/2022-2023 | 23/ND | 03/01/2023 | 0 | Resource Division | 8.8 | 0 | 0
1396 | Nadia Division | Ranaghat Sub-Division | PROVIDING FHTC BY AUGMENTATION FOR DAKSHINPARA (ZONE-II) PWSS BLOCK: HANSKHALI DISTRICT: NADIA | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/000353/2022-2023 | 53/PFMS | 22/06/2022 | 0 | HORIZEN | 2.53 | 0 | 0
1397 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at DAKSHINPARA (ZONE-II) W/S Scheme Block- HANSKHALI under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/10571 | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000140/2025-2026 | 1141/EMD | 04/06/2025 | 90 | PADMA ENGINEERING CO. | 32.63 | 0 | 0
1398 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001008/2022-2023 | 496/EMDdt.24.01.2023 | 17/03/2023 | 656 | GLACIER ENGINEERING CO. | 66.71 | 8 | 100
1399 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Uttar Tajpur W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000242/2020-2021 | 60/ND | 07/01/2021 | 90 | SARKAR AGENCY | 96.79 | 54.04 | 100
1400 | Nadia Division | RWS Nadia Sub-Division | Continuation for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. | Assistant Engineer |  | ORD/000541/2022-2023 | 470/Kly SD-1 | 31/03/2023 | 91 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 4.89 | 4.89 | 20
1401 | Nadia Division | RWS Nadia Sub-Division | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Diovision,PHE Dte,Debagram,Nadia with effect from 01.08.2021 to 31.07.2022 | Assistant Engineer |  | ORD/000952/2021-2022 | 399/DSD | 29/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 1.87 | 0
1402 | Nadia Division | RWS Nadia Sub-Division | Providing Functional Household Tap Connection from Utter Tajpur W/S Scheme (Phase-I) of Retrofitting under Jal Swapno Programme | Assistant Engineer |  | VCH/000472/2021-2022 | 268/PFMS | 08/10/2021 | 0 | LEMNISCATE | 16.36 | 0 | 0
1403 | Nadia Division | RWS Nadia Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT UTTAR TAJPUR | Assistant Engineer |  | VCH/001064/2020-2021 | 459/DW | 30/03/2021 | 0 | SARKAR AGENCY | 42.99 | 0 | 0
1404 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Duttaphulia Zone-I Part-II at Ranaghat-II Block by augmentation of Ground Water based PWSS for Duttaphulia Zone-I Water SUpply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000073/2022-2023 | 1784/NAD-I | 22/09/2022 | 90 | MANGES INDUSTRIAL CORPORATION | 424.43 | 367.39 | 100
1405 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Bhatbhanha, Kulgachi chak, Daluabari, Andipur Chak, Uttar Rameswarpur, Kalipur, Andipur, Kalinanagar, Kulgacchi Mouza inconnection with Augmentation to accomodate FHTC under JJM for Duttaphulia Zone- I Ground water based piped water supply scheme (Phase- II ) Block- Ranaghat -II under JJM Dist- Nadia under Nadia Arsenic Division-I , PHE Dte. (sl.14) | Assistant Engineer-II | Junior Engineer-III | ORD/000263/2022-2023 | 831 / NAD-I | 31/03/2023 | 45 | MANGES INDUSTRIAL CORPORATION | 41.26 | 38.04 | 38
1406 | Nadia Arsenic Division I | Nadia Arsenic Division I | Continuation Work order for ¿Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.¿ | Assistant Engineer-II | Junior Engineer-III | ORD/000281/2022-2023 | 144/AE-I/NAD-I | 31/03/2023 | 90 | SUMAN CHAKRABORTY | 4.85 | 4.85 | 100
1407 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jaldhara/ Jal Swapna for matikumra Phase -II at Ranaghat -II Block by augmentation of Ground Water bassed PWSS for Matikumra Water Supply Sch. under Nadia Arsenic Division -I , P.H.E.Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-III | ORD/000082/2022-2023 | 1769 / NAD-I | 20/09/2022 | 90 | KINGS AND CO | 436.53 | 425.81 | 65
1408 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission for Madanpur at Madanpur-I G.P by retrofitting of Surface Water based Piped Water Supply Scheme for Haringhata- Chakdah(Part) in connection with retrofitting work ofZone-X (Subarnapur),Part-II under Nadia Arsenic Division-I, PHE Dte. (sl.13) | Assistant Engineer-II | Junior Engineer-III | ORD/000022/2023-2024 | 1158 / NAD-I | 28/04/2023 | 21 | CHOWDHURY & CO. | 92.76 | 0 | 100
1409 | Nadia Arsenic Division I | Nadia Arsenic Division I | Road Restoration under for Madanpur-I and Madanpur-II GP at Kalyani Block under providing FHTC (Functional Household Tap Connection) under Jaldhara/Jalswapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water Based PWSS for Haringhata & Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 06) | Assistant Engineer-II | Junior Engineer-III | ORD/000032/2025-2026 | 166/NAD-I | 29/04/2025 | 30 | MANAJIT BISWAS | 31.06 | 0 | 100
1410 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 410 cum Over Head Reservoir (Two Nos) Painting and repairing of H/W Boundary Wall, Pump House at Madanpur Zone-XII under Surface W/S Scheme Haringhata-Chakdah (Part) under Nadia Arsenic Division-I PHE Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-III | ORD/000070/2022-2023 | 1692 / NAD-I | 08/09/2022 | 45 | CHOWDHURY & CO. | 36.08 | 36.01 | 100
1411 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of Clear Water Rising Main at Majher Char Crossing at WBHDCL Road and other allied works under Jal Jeevan Mission (JJM) for Zone-X, (Subarnapur) at Subarnapur Mouza at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-X, (Subarnapur) Part-II under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 03) | Assistant Engineer-II | Junior Engineer-III | ORD/000081/2023-2024 | 1702/NAD-I | 13/07/2023 | 21 | M/S DIPAK ENTERPRISE | 89.84 | 28.74 | 100
1412 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 700 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Chandmari Zone-XI under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte | Assistant Engineer-II | Junior Engineer-III | ORD/000143/2022-2023 | 3154 / NAD-I | 25/11/2022 | 60 | NEERMAN | 25.87 | 25.78 | 99
1413 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work for Zone-XII (Madanpur) at Madanpur G.P at Chakdah block under Jal Jeevan Mission (JJM) by Augmentation of Surface Water Based PWSS for Haringhata-Chakdah (Part) for Zone-XII (Madanpur) Part-III under Nadia Arsenic Division-I, PHE Dte. (SL no-01) | Assistant Engineer-II | Junior Engineer-III | ORD/000171/2022-2023 | 37/AE-I/NAD-I | 07/01/2023 | 15 | BUDDHADEV MONDAL | 4.84 | 4.84 | 100
1414 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XII (Madanpur) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000173/2021-2022 | 464/NAD-I | 10/03/2022 | 60 | H I ENTERPRISE | 93.56 | 88.78 | 100
1415 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XI (Chandmari) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 14) | Assistant Engineer-II | Junior Engineer-III | ORD/000175/2021-2022 | 466/NAD-I | 10/03/2022 | 60 | CALCON CONSTRUCTION | 91.89 | 87.21 | 100
1416 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XII at Madanpur I & II G.P at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-XII, Madanpur,Part-III under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 12) | Assistant Engineer-II | Junior Engineer-III | ORD/000176/2022-2023 | 34/NAD-I | 17/01/2023 | 60 | CHOWDHURY & CO. | 96.1 | 96.09 | 90
1417 | Nadia Arsenic Division I | Nadia Arsenic Division I | Grouting and Renovation of 700 cum capacity OverHead Reservoir at Chandmari,Zone-IX under Surface water supply scheme of Haringhata-Chakdah(Part) under Nadia Arsenic Division - I P. H.E. Dte (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000198/2023-2024 | 469/AE-I/NAD-I | 09/10/2023 | 30 | NEERMAN | 4.79 | 0 | 100
1418 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, PrimarySchool, SSk & MSK under Jal Jeevan Mission (JJM) atHaringhata Block under Zone-IX (Chandmari) underAugmentation of Zone-IV (Chandmari) & Zone-XIIMadanpur, Part-III at Surface Water Based Water Suupply Scheme of Haringhata & Chakdah (Part)Water Supply Scheme of Haringhata & Chakdah (Part)under Nadia Arsenic Division-I, PHE Dte. (SL.NO.05) | Assistant Engineer-II | Junior Engineer-III | ORD/000207/2022-2023 | 178/ NAD-I | 09/02/2023 | 21 | M/S KALIMATA ENTERPRISE | 20.46 | 0 | 100
1419 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing domestic Water Supply to the 36 nos. temporary dwelling units constructed near Buddha Park, Kalyani for rehabilitation of families of Majher Char area including W/S at Sahidpally and Majherchar at Kanchrapara GP at Kalyani block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) W/S Scheme for Zone-XI Chandmari under Nadia Arsenic Division-I, PHE Dte. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000232/2023-2024 | 2300/NAD-I | 29/09/2023 | 21 | M/S DIPAK ENTERPRISE | 12.7 | 0 | 100
1420 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 176.7 | 47
1421 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 2C of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000769/2021-2022 | 119/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.38 | 3.34 | 100
1422 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 1 | RTOR000115/2022-2023 | 102/ND | 05/01/2023 | 0 | Resource Division | 61.79 | 0 | 0
1423 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- V/A (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000341/2023-2024 | 4526/ND | 04/10/2023 | 626 | MONDAL ENTERPRISE | 614.58 | 0 | 25
1424 | Nadia Division | Debgram Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 273 cum. for Surface Water Based Piped Water Supply Scheme for Zone- V/ A (NORTHERN SECTOR, PART-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000369/2023-2024 | 4738/ND | 13/10/2023 | 60 | BIDYUT KUMAR | 14.83 | 0 | 20
1425 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
1426 | Nadia Division | Debgram Sub-Division | Construction of OHR, chlorine room, service road, repairing of boundary wall, store room, and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone- V / A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11843]. | Assistant Engineer |  | ORD/000452/2023-2024 | 5468/ND | 08/12/2023 | 711 | MINTU CHAKRABORTY | 244.4 | 0 | 5
1427 | Nadia Division | Debgram Sub-Division | Reconstruction of Boundary wall, Staff room, Chlorination room, Godown etc. of Surface Water Based Water Supply Scheme for Zone-V/A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000694/2024-2025 | 89/ND | 07/01/2025 | 90 | MINTU CHAKRABORTY | 51.27 | 0 | 5
1428 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 5A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000795/2021-2022 | 145/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.63 | 4.61 | 100
1429 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000124/2023-2024 | 238/ND | 11/01/2024 | 0 | Resource Division | 30.56 | 0 | 0
1430 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000139/2022-2023 | 121/ND | 05/01/2023 | 0 | Resource Division | 82.72 | 0 | 0
1431 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electric Bill payment of WBSEDCL for the month of january 2023 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00792/2022-2023 | BP-133-22-23 | 31/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.24 | 0 | 0
1432 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electric Bill payment of WBSEDCL for the month of january 2023 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00794/2022-2023 | BP-132-22-23 | 31/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.38 | 0 | 0
1433 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) & II under Maniknagar W/S Scheme (Block : Shantipur) Dist.- Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 05) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001785/2022-2023 | 1124/EMD | 16/03/2023 | 30 | NITESH MANAGEMENT | 18.84 | 18.83 | 90
1434 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Maniknagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000006/2022-2023 | 204/NACD-II | 05/04/2022 | 60 | NISHITH BANERJEE | 5.37 | 5.35 | 100
1435 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of D.I. pipeline with allied works at Maniknagar Piped Water Supply Scheme in Shantipur Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000012/2025-2026 | 42_AE-I/NACD-II | 29/04/2025 | 90 | SURAJIT KUMAR GHOSH | 0.96 | 0 | 100
1436 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement for Tube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Maniknagar water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000030/2022-2023 | 17/AE-I/NACD-II | 13/04/2022 | 60 | NISHITH BANERJEE | 2.83 | 2.6 | 100
1437 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection for Swajal village at Mahatopara of Maniknagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000038/2024-2025 | 752/AE-I/NACD-II | 19/06/2024 | 15 | S.M. ENTERPRISE | 0.91 | 0 | 100
1438 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection for Swajal village at Kapalipara of Maniknagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000039/2024-2025 | 753/AE-I/NACD-II | 19/06/2024 | 15 | ACHARJEE & ASSOCIATES | 0.91 | 0 | 100
1439 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Maniknagar Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000040/2022-2023 | 27/AE-I/NACD-II | 13/04/2022 | 60 | BIDYUT KUMAR | 4.69 | 2.63 | 100
1440 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection for Swajal village at Maniknagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000040/2024-2025 | 754/AE-I/NACD-II | 19/06/2024 | 331 | DAFADAR ENTERPRISE | 0.85 | 0 | 100
1441 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Maniknagar Water Supply Scheme in Shantipur Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000048/2023-2024 | 414/AE-I/NACD-II | 08/08/2023 | 15 | JOY HIND TUBEWELLS | 0.96 | 0 | 100
1442 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Santipur Block of Nadia District through Jadavpur University. (Name of PWSS: Maniknagar) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000053/2023-2024 | 858/NACD-II | 08/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
1443 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Maniknagar and adjoining mouzas under Maniknagar Water Supply Scheme of Santipur Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000085/2022-2023 | 336/NACD-II | 02/06/2022 | 90 | M/S ROY CHOWDHURY & CO. | 107.96 | 89.25 | 100
1444 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Paninala and Maniknagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000135/2022-2023 | 432/NACD-II | 07/07/2022 | 60 | JOY HIND TUBEWELLS | 43.35 | 0 | 100
1445 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earth work in filling in ditches at Maniknagar H/W Site for development of land in connection with proposed T/W Sinking & Pump House construction at Maniknagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000174/2022-2023 | 466/NACD-II | 20/07/2022 | 20 | SAHA ENGINEERS | 7.48 | 7.47 | 100
1446 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Maniknagar Water Supply Scheme of Santipur Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000195/2022-2023 | 624/NACD-II | 06/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.85 | 3.85 | 100
1447 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of flow control devices in the closed water conduit at Maniknagar PWSS in Santipur Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000262/2024-2025 | 946/AE-I/NACD-II | 24/10/2024 | 7 | MAKALI ENGINEERING CORPORATION | 0.77 | 0 | 100
1448 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 250 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Maniknagar water supply scheme of Sanitpur Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000283/2022-2023 | 1138/NACD-II | 16/12/2022 | 720 | JOY HIND TUBEWELLS | 95.18 | 30 | 100
1449 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Construction of 35 m3/hr capacity IEP at Maniknagar PWSS in Shantipur Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000292/2023-2024 | 314/NACD-II | 01/03/2024 | 306 | PRITI ENTERPRISE | 19.86 | 0 | 80
1450 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary Wall with grill gate at Head Work site of Maniknagar Water Supply Scheme Santipur Block under Nadia Arsenic Civil Division - II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000317/2022-2023 | 81/NACD-II | 09/01/2023 | 60 | SURAJIT KUMAR GHOSH | 14.21 | 11.13 | 80
1451 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary Wall with grill gate at 2nd Tube well site of Maniknagar W/s Scheme of Santipur Block under Nadia Arsenic Civil Division - II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000339/2022-2023 | 119/NACD-II | 11/01/2023 | 60 | SAHA CONSTRUCTION & GENERAL ORDER SUPPLIERS | 4.39 | 4.32 | 85
1452 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000009/2022-2023 | 403/NACD-II | 04/07/2022 | 0 | Resource Division | 39.71 | 0 | 0
1453 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | VCH/000231/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
1454 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | VCH/000338/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
1455 | Eastern Mechanical | Nadia Arsenic Civil Division II | Load enhancement charges and security deposit for Chakdignagar PWSS PH-II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/02155/2024-2025 | BP-173-24-25 | 05/12/2024 | 0 | W.B.S.E.D.C.L (GROUP KRISHNAGAR ROAD STATION C.C.C) | 3.06 | 0 | 0
1456 | Eastern Mechanical | Nadia Arsenic Civil Division II | NEW SERVICE CONNECTION CHARGES FOR WBSEDCL UNDER CHAKDINAGAR PHE-II P.O. KALIRHAT | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/02540/2023-2024 | BP-149-23-24 | 24/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.95 | 0 | 0
1457 | Eastern Mechanical | Nadia Arsenic Civil Division II | New service connection for Chakdinagar PH-I P.O.- Kalirhat | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/04043/2023-2024 | BP-248-23-24 | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.87 | 0 | 0
1458 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Chakdignagar ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl. No. 7) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/003198/2023-2024 | 948/EMD | 18/03/2024 | 410 | KARTICK BAL | 22.35 | 0 | 90
1459 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery, installation and commissioning of electro-mechanical accessories in connection with installation of Clear Water Pumping machinery in Chakdignagar PWSS, Block- Krishnagar-I, District- Nadia. Under EMD PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/003257/2023-2024 | 810./EMD | 11/03/2024 | 30 | M/S. G.P. ENTERPRISE | 9.66 | 0 | 0
1460 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00016/2023-2024 | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
1461 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00089/2022-2023 | 235/4 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0
1462 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Chakdignagar Water Supply Scheme in Krishnanagar-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000032/2024-2025 | 743/AE-I/NACD-II | 18/06/2024 | 15 | SAMAR ENTERPRISE | 2.45 | 0 | 100
1463 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Chakdignagar water supply scheme under Krishnanagar- I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000134/2023-2024 | 1252/NACD-II | 08/11/2023 | 45 | SHYAM SUNDAR SAHA | 26.42 | 0 | 100
1464 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Chakdignagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000201/2023-2024 | 94/NACD-II | 22/01/2024 | 360 | ZOOM CONSTRUCTION & INTERIO | 20.02 | 0 | 90
1465 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing 1 no. Guard at Chakdignagar Head work Water Supply Scheme for guarding of various Departmental materials under Nadia Arsenic Civil Division-II,P.H.E. Dte.[Period of work :01/02/2024 to 31/05/2024] | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000230/2023-2024 | 600/AE-I/NACD-II | 31/01/2024 | 121 | M/S S.K. CONSTRUCTION | 0.96 | 0 | 100
1466 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 2 nos. 200 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (200 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Chakdignagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000276/2022-2023 | 1131/NACD-II | 16/12/2022 | 30 | JOY HIND TUBEWELLS | 20.39 | 0 | 100
1467 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Additional instrumentation with augmentation of backwashing system with appropriate wattage including recirculation in compliance with 12699: 1989 as well as reaffirmation there into for contamination removal of various valent systems at Chakdignagar Piped Water Supply Scheme in Krishnagar-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000315/2024-2025 | 1512/NACD-II | 25/11/2024 | 30 | SANDIP BISWAS | 20.55 | 0 | 0
1468 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distraibution system including providing Functional House Hold Tap Connection (FHTC) for Chakdignagar and adjoining mouzas under Chakdignagar W/s Scheme of Krishnagar-I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000342/2022-2023 | 152/NACD-II | 17/01/2023 | 960 | JOY GOPAL GUPTI | 36.69 | 29.93 | 100
1469 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Provisioning of automation as well as adsorption technology with augmentation of backwashing system with appropriate wattage including recirculation in compliance with 12699: 1989 as well as reaffirmation there into for contamination removal of various valent systems at Chak Dignagar corresponding Piped Water Supply Scheme in Krishnagar I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000401/2024-2025 | 41/NACD-II | 10/01/2025 | 30 | SANDIP BISWAS | 39.26 | 0 | 0
1470 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000005/2023-2024 | 78/NACD-II | 15/01/2024 | 0 | Resource Division | 2.85 | 0 | 0
1471 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000024/2022-2023 | 1087/NACD-II | 09/12/2022 | 0 | Resource Division | 0.44 | 0 | 0
1472 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000032/2022-2023 | 380/NACD-II | 24/03/2023 | 0 | Resource Division | 2.85 | 0 | 0
1473 | Nadia Arsenic Division I | Nadia Arsenic Division I | Structural stability report for repair/reconstruction of existing overhead reservoir at Baganchara Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-II | BILL/00483/2023-2024 | 379/PFMS | 06/12/2023 | 0 | JADAVPUR UNIVERSITY | 1.77 | 0 | 0
1474 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of AIRP capacity (111m3/hr) in connection with augmentation of Ground Water Based PWSS for Baganchara under Jal Jeevan Mission at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000024/2024-2025 | 1079/NAD-I | 15/07/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 278.95 | 0 | 65
1475 | Nadia Arsenic Division I | Nadia Arsenic Division I | DI Rising main line at Baganchara PWSS under Santipur Block in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000030/2024-2025 | 232/AE-I/NAD-I | 25/07/2024 | 623 | MANARAMA ENTERPRISE | 3.96 | 0 | 85
1476 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for providing FHTC (Functional Household Tap Connection) under JJM (Jal Jeevan Mission) by Augmentation of Baganchra under Ground Water Based PWSS for Baganchra Water Supply Scheme at Santipur Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000036/2022-2023 | 221/AE-I/NAD-I | 02/09/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.78 | 4.78 | 100
1477 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site for Baganchara Piped Water Supply Schemes under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000040/2024-2025 | 1314/NAD-I | 22/08/2024 | 60 | K K MARKETING | 13.01 | 0 | 0
1478 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE(PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Laying of Distribution System Including Specials, Valves & Pipe Supporting Structure, Construction of Boundary Wall, Chlorine Room, and Approach Road (60.0m Length and 3.0m Wide) and Toilet at Head Work Site and 2nd T/W Site and Repair of 450 cum capacity Over Head Reservoir, Painting and Pump House at Ground Water Based Piped Water Supply Scheme for Baganchara in Santipur Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | Assistant Engineer-I | Junior Engineer-II | ORD/000128/2023-2024 | 1896/NAD-I | 14/08/2023 | 731 | KINGS AND CO | 706.54 | 0 | 22
1479 | Nadia Arsenic Division I | Nadia Arsenic Division I | MS pipeline connection with rising main, Over head reservoir including making provision for AIRP connection under Baganchhara PWSS, Shantipur block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000142/2024-2025 | 316/AE-I/NAD-I | 06/12/2024 | 30 | MANARAMA ENTERPRISE | 1.82 | 0 | 100
1480 | Nadia Arsenic Division I | Nadia Arsenic Division I | Surging of existing Tube Well Situated at Head Site of Baganchara Water Supply Scheme in connection with Jal Jeevan Mission under Santipur Block to increase the yield of the tube well under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000304/2023-2024 | 69/AE-I/NAD-I | 12/02/2024 | 15 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 0.64 | 0 | 100
1481 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-II | RTOR000026/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 30.8 | 0 | 0
1482 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Muragachha Zone-II Ground Based Water Supply Scheme under Hanskhali Block under Nadia Arsenic Division-I,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Muragachha Zone-I & Zone-II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Schemes under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000023/2024-2025 | 1135/NAD-I | 24/07/2024 | 60 | GHOSH & CO | 17.57 | 0 | 100
1483 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Murgachha Zone-I Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under 1304536.00 26091.00 Initially Nil, Rs. 1005/- per copy of tender document including 2911(ii) to be purchased by the successful bidder at 15 Days Page 3Muragachha Zone-I & II (Part-III) Piped W/S Scheme (sl.16) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000024/2023-2024 | 1160 / NAD-I | 28/04/2023 | 734 | SANJIB DEY | 13.05 | 0 | 100
1484 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of AIRP capacity (104m3/hr) in connection with augmentation of Ground Water Based PWSS for Chupria Zone-I under Jal Jeevan Mission at Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000025/2024-2025 | 1118/NAD-I | 19/07/2024 | 180 | HARBAUER INDIA PRIVATE LIMITED | 265.04 | 0 | 0
1485 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jalswapna / Jaldhara for Muragachha Z-I & II ( Part -III) at Hanskhali Block by Augmentation of Ground Water based pipe PWSS for Muragachha W/S Scheme. under Nadia Arsenic Division -I, P.H.E. Dte. (Sl .no. 06) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000124/2022-2023 | 2050 / NAD-I | 21/10/2022 | 831 | MONDAL PRECISION PRIVATE LIMITED | 282.77 | 166.38 | 100
1486 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP (Pressure Type) at Muragachha Zone-II W/S Scheme under Hanskhali Block of capacity 75 cum/hr. under augmentation of Muragachha Zone-II W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000142/2023-2024 | 2043/NAD-I | 24/08/2023 | 542 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 144.1 | 0 | 100
1487 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP (Pressure Type) at Muragachha, Zone-I W/S Scheme under Hanskahli Block of capacity 65 cum/hr. under augmentation of Muragachha, Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte (Sl.no.07) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000145/2023-2024 | 2046/NAD-I | 24/08/2023 | 542 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 132.46 | 0 | 100
1488 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of damages pipeline and other allied work at 2nd site of Muragachha Zone-I, water supply scheme, Block- Hanskhali under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000233/2023-2024 | 497/AE-I/NAD-I | 31/10/2023 | 7 | DAYANIDHI CONSTRUCTIONS | 0.97 | 0 | 100
1489 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of damages pipeline and other allied work at 2nd site of Muragachha Zone-II, water supply scheme, Block- Hanskhali under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000234/2023-2024 | 498/AE-I/NAD-I | 31/10/2023 | 7 | M/S T.S. ENTERPRISE | 0.95 | 0 | 100
1490 | Nadia Division | Debgram Sub-Division | Restoration of Bholadanga welcome gate to Bangoria over Bridge via NH 34 | Assistant Engineer |  | BILL/00511/2024-2025 | 302/PFMS | 02/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 20.27 | 0 | 0
1491 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
1492 | Nadia Division | Debgram Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 700 cum. for Providing FHTC (Functional Household Tap Connection) for Zone IX/A Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000258/2023-2024 | 4007/ND | 07/09/2023 | 60 | CHANDAN ROY | 27.44 | 0 | 37
1493 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000355/2023-2024 | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 0 | 19
1494 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
1495 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 9/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000807/2021-2022 | 157/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.66 | 4.63 | 100
1496 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000134/2023-2024 | 248/ND | 11/01/2024 | 0 | Resource Division | 7.22 | 0 | 0
1497 | Nadia Division | Ranaghat Sub-Division | Additional work of Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Magurkhali to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000111/2024-2025 | 4344/ND | 07/08/2024 | 479 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 78.93 | 0 | 60
1498 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of boundary wall & allied works in the premises at pump house no 1of Magurkhali W/S scheme of Ranaghat-II block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000233/2022-2023 | 560/RSD | 31/08/2022 | 30 | M/S ARNAB CONSTRUCTION | 4.68 | 0 | 100
1499 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of boundary wall & allied works in the premises at pump house no 3 of Magurkhali W/S scheme of Ranaghat-II block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000234/2022-2023 | 560/A/RSD | 31/08/2022 | 30 | ASOKE KUMAR DUTTA | 4.49 | 2.17 | 100
1500 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
1501 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Magurkhali to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000299/2022-2023 | 5355/ND | 22/12/2022 | 1161 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 586.94 | 40.39 | 90
1502 | Nadia Division | Ranaghat Sub-Division | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-2 site at Magurkhali Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000304/2024-2025 | 1280/RSD | 04/10/2024 | 75 | R.R.ENTERPRISE | 4.45 | 0 | 100
1503 | Nadia Division | Ranaghat Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Magurkhali W/S Scheme in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000443/2021-2022 | 1063/RSD | 02/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.76 | 4.76 | 100
1504 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Magurkhali under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000889/2024-2025 | 201/RSD | 06/02/2025 | 45 | SAYANTAN PANDEY | 2.15 | 0 | 100
1505 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000012/2024-2025 | 7560/ND | 27/12/2024 | 0 | Resource Division | 8.2 | 0 | 0
1506 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000068/2023-2024 | 2311/ND | 29/05/2023 | 0 | Resource Division | 44.59 | 0 | 0
1507 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000111/2022-2023 | 24/ND | 03/01/2023 | 0 | Resource Division | 24.14 | 0 | 0
1508 | Central Drilling | Ranaghat Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Magurkhali W/S Scheme (T/W-I), Ranaghat-II Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000099/2023-2024 | 901/CDD | 18/07/2023 | 30 | UTTAM KUMAR CHATTERJEE | 18.6 | 0 | 0
1509 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAGURKHALI W/S Scheme, Block- RANAGHAT II , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000017/2023-2024 | 1580/EMD | 24/04/2023 | 753 | ESENCE ENGINEERING CONCERN | 21.64 | 0 | 100
1510 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000196/2023-2024 | 3537/ND | 11/08/2023 | 1147 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 0 | 20
1511 | Nadia Division | Krishnanagar Sub-Division | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000236/2025-2026 | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0
1512 | Nadia Division | Krishnanagar Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
1513 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | Assistant Engineer | Junior Engineer 3 | ORD/000706/2024-2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0
1514 | Nadia Division | Krishnanagar Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 4/C of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .10 ) | Assistant Engineer | Junior Engineer 3 | ORD/000719/2021-2022 | 212/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.48 | 4.44 | 100
1515 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 3 | RTOR000165/2022-2023 | 87/ND | 05/01/2023 | 0 | Resource Division | 200.92 | 0 | 0
1516 | Nadia Division | Debgram Sub-Division | Restoration work of road damage due to laying pipe line under ¿NJJM¿ Project in Nakashipara Block of Nadia District under Nadia Division, PHE Dept. of Arbetai ¿ Sahapara Road from 9.80 kmp to 11.88 kmp of Krishnagar Sub-Division-I under Nadia Highway Division-I in the district Nadia during the year 2024-2025. | Assistant Engineer |  | BILL/00249/2024-2025 |  | 26/07/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 12.59 | 0 | 0
1517 | Nadia Division | Debgram Sub-Division | Restoration work of road damage due to laying pipe line under ¿NJJM¿ Project in Nakashipara Block of Nadia District under Nadia Division, PHE Dept. of Arbetai ¿ Sahapara Road from 9.80 kmp to 11.88 kmp of Krishnagar Sub-Division-I under Nadia Highway Division-I in the district Nadia during the year 2024-2025. | Assistant Engineer |  | BILL/00343/2024-2025 | 148/PFMS | 28/08/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 6.3 | 0 | 0
1518 | Nadia Division | Debgram Sub-Division | RESTORATION OF ROAD FLANK OF ARBETAI SAHAPARA ROAD FROM CH. 0.00 KM TO 9.80 KMP. | Assistant Engineer |  | BILL/01489/2023-2024 | 601/PFMS | 14/03/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 28.69 | 0 | 0
1519 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- V/C (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000343/2023-2024 | 4528/ND | 04/10/2023 | 896 | M/S DIPAK ENTERPRISE | 645.85 | 0 | 50
1520 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
1521 | Nadia Division | Debgram Sub-Division | Construction of OHR, staff room, chlorine room, service road and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-V / C (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/12373]. | Assistant Engineer |  | ORD/000471/2023-2024 | 148/ND | 09/01/2024 | 729 | MINTU CHAKRABORTY | 252.66 | 0 | 10
1522 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000126/2023-2024 | 237/ND | 11/01/2024 | 0 | Resource Division | 23.66 | 0 | 0
1523 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000141/2022-2023 | 98/ND | 05/01/2023 | 0 | Resource Division | 149.04 | 0 | 0
1524 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 0 | 47
1525 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 8A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000780/2021-2022 | 130/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.26 | 4.16 | 100
1526 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000126/2022-2023 | 107/ND | 05/01/2023 | 0 | Resource Division | 128.41 | 0 | 0
1527 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bahirgachhi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000024/2020-2021 | 1066/NACD-II | 25/09/2020 | 15 | BINOY DAS | 4.99 | 0 | 0
1528 | Nadia Division | Debgram Sub-Division | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000165/2025-2026 | 3260/ND | 10/07/2025 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 5
1529 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
1530 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000355/2023-2024 | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 0 | 19
1531 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
1532 | Nadia Division | Debgram Sub-Division | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-III / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11839]. | Assistant Engineer |  | ORD/000443/2023-2024 | 6112/ND | 21/12/2023 | 1095 | MONDAL ENTERPRISE | 201.12 | 0 | 5
1533 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 3/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000791/2021-2022 | 141/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.35 | 3.34 | 100
1534 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000120/2023-2024 | 231/ND | 11/01/2024 | 0 | Resource Division | 2.04 | 0 | 0
1535 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000135/2022-2023 | 95/ND | 05/01/2023 | 0 | Resource Division | 59.33 | 0 | 0
1536 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone X-A to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000344/2022-2023 | 254/ND | 16/01/2023 | 720 | SANJUKTA ENGINEERS | 157.12 | 23.02 | 98
1537 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Karimpur Jalangi Zone-X (A) Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Karimpur Jalangi Zone-X (A) at Karimpur-II Block by Augmentation of Ground Water based PWSS for Karimpur Jalangi Zone-X (A) Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000740/2024-2025 | 418/ND | 27/01/2025 | 420 | S.B.CONSTRUCTION | 23.54 | 0 | 50
1538 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000009/2023-2024 | 1852/ND | 26/04/2023 | 0 | Resource Division | 22.01 | 0 | 0
1539 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000074/2023-2024 | 2324/ND | 29/05/2023 | 0 | Resource Division | 0.92 | 0 | 0
1540 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000187/2022-2023 | 142/ND | 06/01/2023 | 0 | Resource Division | 27.61 | 0 | 0
1541 | Nadia Division | Debgram Sub-Division | Jack pushing & pipe crossing work at Jugpur Mouza under Northern Sector Part-II under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000002/2025-2026 | 1645/ND | 07/04/2025 | 90 | MONDAL ENTERPRISE | 95.97 | 0 | 1
1542 | Nadia Division | Debgram Sub-Division | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000165/2025-2026 | 3260/ND | 10/07/2025 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 5
1543 | Nadia Division | Debgram Sub-Division | Reconstruction of Top Dome and other related work for 273 cum RCC elevated reservoir of Surface Water Based Water Supply Scheme for Zone-V /A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000190/2024-2025 | 6098/ND | 19/09/2024 | 90 | BIDYUT KUMAR | 13.22 | 0 | 10
1544 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- V/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000342/2023-2024 | 4527/ND | 04/10/2023 | 782 | KINGS & CO. | 672.01 | 0 | 25
1545 | Nadia Division | Debgram Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 1000 m3. for Surface Water Based Piped Water Supply Scheme for Zone- V/ B (NORTHERN SECTOR, PART-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000368/2023-2024 | 4739/ND | 13/10/2023 | 60 | U-TURN CONSTRUCTION | 35.83 | 0 | 65
1546 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
1547 | Nadia Division | Debgram Sub-Division | Construction of Additional Boundary Wall ( 85.00 m Length ), Service Road and other related work for 1000 cum RCC elevated reservior of Surface Water Based Water Supply Scheme for Zone-V/B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000451/2024-2025 | 7246/ND | 12/12/2024 | 60 | U-TURN CONSTRUCTION | 17.16 | 0 | 0
1548 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 5B-A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000796/2021-2022 | 146/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.91 | 4.75 | 100
1549 | Nadia Division | Debgram Sub-Division | Additional Route Survey, Design Drawing & DPR Preparation for ZONE 5B-A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000797/2021-2022 | 147/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.84 | 0.78 | 100
1550 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 5B-B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000798/2021-2022 | 148/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.04 | 4.04 | 100
1551 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000125/2023-2024 | 236/ND | 11/01/2024 | 0 | Resource Division | 19.68 | 0 | 0
1552 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000140/2022-2023 | 119/ND | 05/01/2023 | 0 | Resource Division | 253.22 | 0 | 0
1553 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Krishnagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000029/2020-2021 | 1071/NACD-II | 25/09/2020 | 15 | PAPAN ROY | 4.97 | 0 | 0
1554 | Nadia Division | Krishnanagar Sub-Division | Sinking of 2 nos. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method at headwork and 2nd tube well site for Indrakpur water supply scheme under Krishnagar Sub-Division under Nadia Division, PHE DTe. (SM/13820) | Assistant Engineer | Junior Engineer 1 | ORD/000037/2023-2024 | 2104/ND | 15/05/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 32.6 | 24.86 | 70
1555 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials & valves, Proposed Laying of Rising Main System, Providing FHTC, Construction of 200 cum capacity R.C.C. Elevated Reservoir including Soil investigation, Construction of Pump House, Boundary Wall and Service Road at Head Work Site & 2nd Tubewell Site at Indrakpur Water Supply Scheme to accommodate FHTC under Krishnagar Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000042/2023-2024 | 1721/ND | 17/04/2023 | 624 | M/S GHOSH CONSTRUCTION | 267.51 | 106.99 | 100
1556 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 30 m3/hr at Indrakpur Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000295/2024-2025 | 6735/ND | 05/11/2024 | 540 | B.M. ENGINEERING & CONSTRUCTION | 159.53 | 0 | 5
1557 | Nadia Division | Krishnanagar Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
1558 | Nadia Division | Krishnanagar Sub-Division | Collection of Household data through mobile app for FHTC Connection of Ground Water Based Indrakpur, Gadigachha, Karimpur-Jalangi (Zone-VI), Sandha, Udaypur PWSS, Mini PWSS at Gazna (Part) and Surface Based PWSS for Northern Sector (Part-I) (Zone-IA) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000338/2023-2024 | 984/KLYSD-I | 11/09/2023 | 90 | TECHVISION | 4.85 | 0 | 100
1559 | Nadia Division | Krishnanagar Sub-Division | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 90 days w.e.f. 01/10/2023 (as and when required) | Assistant Engineer | Junior Engineer 1 | ORD/000411/2023-2024 | 1450/KSD | 18/09/2023 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0
1560 | Nadia Division | Krishnanagar Sub-Division | Survey, Design and Preparation of DPR in connection with Indrakpur piped water supply scheme in Nabadwip Block under Krishnanagar Sub Division under Nadia Division, PHE Dte | Assistant Engineer | Junior Engineer 1 | ORD/000586/2023-2024 | 49/KSD | 15/01/2024 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.82 | 0 | 80
1561 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at leftout in connection to the Ground Based Piped Water Supply Scheme at Indrakpur to accomodate FHTC within Nabadwip Block under Krishnagar Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000771/2023-2024 | 1761/ND | 12/03/2024 | 271 | M/S GHOSH CONSTRUCTION | 12.79 | 0 | 100
1562 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 1 | RTOR000011/2023-2024 | 1854/ND | 26/04/2023 | 0 | Resource Division | 15.8 | 0 | 0
1563 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 1 | RTOR000154/2023-2024 | 269/ND | 11/01/2024 | 0 | Resource Division | 5.7 | 0 | 0
1564 | Eastern Mechanical | Krishnanagar Sub-Division | Supplementary quotation for revised estimate due to row issue I.F.O. PHE Dte. for 3PH NSC to pump house-II at Indrakpur | Assistant Engineer | Junior Engineer 1 | BILL/01699/2024-2025 | BP-119-24-25 | 20/09/2024 | 0 | WBSEDCL NABADWIP CCC | 1.91 | 0 | 0
1565 | Eastern Mechanical | Krishnanagar Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Indrakpur ground water based water supply scheme under Block_ Nabadwip Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/001987/2023-2024 | 6968/EMD | 15/12/2023 | 91 | S.G. TECHNICAL SERVICES | 28.7 | 0 | 95
1566 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000010/2021-2022 | 2051/ND | 13/05/2021 | 60 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 41.49 | 30.78 | 100
1567 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000013/2021-2022 | 2049/ND | 13/05/2021 | 60 | S.K. CONSTRUCTION | 43.81 | 34.72 | 100
1568 | Nadia Division | RWS Nadia Sub-Division | laying of distribution pipe line 125 mm dia UPVC pipe etc. for Providing functional household tap connection at Dakhin Jhitkipota zone- I W/S scheme under Nadia Division PHED. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000064/2022-2023 | 214/PH | 12/07/2022 | 30 | TAPU SAHA | 4.2 | 4.2 | 100
1569 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000107/2021-2022 | 2912/ND | 23/07/2021 | 45 | PAPAN ROY | 8.8 | 7.12 | 100
1570 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (121cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone-II, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte (Sl.no.01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000141/2023-2024 | 2029/NAD-I | 23/08/2023 | 569 | MONDAL PRECISION PRIVATE LIMITED | 173.98 | 0 | 35
1571 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Gobindapur Zone-II Part-II under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15550) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000150/2025-2026 | 1152/EMD | 04/06/2025 | 90 | M/S DAS ENTERPRISE | 4.34 | 0 | 0
1572 | Nadia Division | Ranaghat Sub-Division | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000252/2024-2025 | 6290/ND | 26/09/2024 | 45 | IMAGIN | 19.44 | 0 | 100
1573 | Nadia Division | Ranaghat Sub-Division | Replacemt of damaged & typically choked UPVC pipe line for augmentation of Ground Water Based Water Supply Scheme for Gazna PWSS of Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. (Balance) A- Part. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000370/2023-2024 | 4802/ND | 17/10/2023 | 623 | SANDIP BISWAS | 99.5 | 0 | 96
1574 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tube well (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000524/2022-2023 | 1269/ND | 23/03/2023 | 780 | JOY HIND TUBEWELL'S | 65.37 | 0 | 100
1575 | Eastern Mechanical | Ranaghat Sub-Division | New single phase service connection at Gazna (Part) water supply scheme at Hanskhali block, Dist.-Nadia | Assistant Engineer | Junior Engineer,Junior Engineer 2 | BILL/00332/2024-2025 | BP-21-24-25 | 21/05/2024 | 0 | W.B.S.E.D.C.LTD (BAGULA C.C.C) | 0.26 | 0 | 0
1576 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augomentation in connection to Accommodate FHTC at Pump House No.-I/II under Gazna ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000014/2024-2025 | 1306/EMD | 09/05/2024 | 30 | RAJ & ENTERPRISE | 7.67 | 0 | 100
1577 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Gazna ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15539) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001461/2024-2025 | 232/EMD | 06/02/2025 | 30 | MAA KALI ENTERPRISE | 11.76 | 0 | 0
1578 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (71cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Ramnagar, under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.10) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000120/2023-2024 | 1795/NAD-I | 31/07/2023 | 30 | ASIT PRAMANIK | 93.55 | 0 | 0
1579 | Nadia Division | Ranaghat Sub-Division | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000252/2024-2025 | 6290/ND | 26/09/2024 | 45 | IMAGIN | 19.44 | 0 | 100
1580 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000527/2022-2023 | 1270/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 65.32 | 0 | 0
1581 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Contact Tank for Conversion of IEP to AIRP at Goalpur PWSS under Shantipur Block under Nadia Arasenic Division-I, P.H.E.Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000031/2024-2025 | 233/AE-I/NAD-I | 25/07/2024 | 189 | SATYABRATA CHAKRABORTY | 3.37 | 0 | 100
1582 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Goalpur Zone-II, Ground Based Water Supply Scheme under Santipur under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E Dte.in connection with Augmentation under JJM under Goalpur Zone-II, Part-III, Piped Water Supply Scheme (Sl.No.-35) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000110/2023-2024 | 1772/NAD-I | 26/07/2023 | 15 | MANISHIKA CONSTRUCTION | 13.04 | 0 | 100
1583 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP of Ground Water Based Piped Water Supply Scheme for Goalpur Zone-II, (30 cum/hr) including augmentation of Matikumra Water Supply Scheme under Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, P.H.E. Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000144/2024-2025 | 1882/NAD-I | 11/11/2024 | 180 | BALAJI UDDYOG | 129.1 | 0 | 0
1584 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation Work at Umapur and Goalpur Mouzas at Santipur Block by Augmentation of Ground Water based PWSS for Goalpur Zone-II, Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Goalpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.04) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000157/2023-2024 | 2115/NAD-I | 04/09/2023 | 15 | BUDDHADEV MONDAL | 50.03 | 38.63 | 100
1585 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection inbetween new pump to rising main line , Pathway & delivery line from manifold to distribution line at Shantipur Block of ground water based PWSS for Goalpur Zone-II water supply scheme in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000201/2023-2024 | 450/AE-I/NAD-I | 29/09/2023 | 30 | CONSTRUCTURE | 4.83 | 0 | 100
1586 | Nadia Arsenic Division I | Nadia Arsenic Division I | Dedicated line at Dhakuria and delivery line from manifold to distribution line at Shantipur Block of ground water based PWSS for Goalpur Zone-I water supply scheme in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 04) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000202/2023-2024 | 451/AE-I/NAD-I | 29/09/2023 | 30 | M/S G.M ASSOCIATES | 4.82 | 0 | 100
1587 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP at Goalpur Zone-I Water Supply Scheme under Shantipur Block of capacity 15 Cu.m/hr inconnection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000237/2023-2024 | 2344/NAD-I | 03/10/2023 | 1062 | SATYABRATA CHAKRABORTY | 67.28 | 0 | 100
1588 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Goalpur Zone II Part-II under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15546) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000169/2025-2026 | 1167/EMD | 04/06/2025 | 90 | SHRESTHA | 4.34 | 0 | 0
1589 | Eastern Mechanical | Nadia Arsenic Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-II under Goalpur ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/001768/2023-2024 | 6392/EMD | 30/10/2023 | 30 | ASHUTOSH DAS & CO. | 11.76 | 0 | 100
1590 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (30cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Nabla, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000127/2023-2024 | 1885/NAD-I | 11/08/2023 | 984 | APURBA MANDAL | 89.6 | 0 | 38
1591 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Nabla Part-IV under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15547) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000156/2025-2026 | 1156/EMD | 04/06/2025 | 90 | S M ELECTRICALS | 4.34 | 0 | 0
1592 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD andallied works at OHR site under Behria Ground Based Water Supply Scheme under Santipur under Office of Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation under JJM under Beharia Part-III, Piped Water Supply Scheme (Sl.no.33) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000046/2023-2024 | 1364/NAD-I | 12/05/2023 | 15 | DEBASISH DEY | 12.2 | 0 | 100
1593 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (119cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Beharia, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (sl.no.01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000136/2023-2024 | 1880/NAD-I | 10/08/2023 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 158.74 | 0 | 100
1594 | Nadia Division | Ranaghat Sub-Division | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000252/2024-2025 | 6290/ND | 26/09/2024 | 45 | IMAGIN | 19.44 | 0 | 100
1595 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tube well (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000524/2022-2023 | 1269/ND | 23/03/2023 | 780 | JOY HIND TUBEWELL'S | 65.37 | 0 | 100
1596 | Nadia Division | Ranaghat Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Fatepur PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 45.00 Cu.m/hr. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000583/2023-2024 | 839/ND | 06/02/2024 | 455 | ZEOLITE FRESH INDIA | 58.36 | 0 | 60
1597 | Nadia Division | Ranaghat Sub-Division | Supplying and laying of distribution system including providing Functional Household Tap Connection (FHTC) for Augmentation of Purbakhamar Simulia Piped Water Supply Scheme under Ranaghat Sub-Division, under Nadia Division, PHE Dte.. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000417/2023-2024 | 5224/ND | 24/11/2023 | 755 | B.M. ENGINEERING & CONSTRUCTION | 215.24 | 0 | 75
1598 | Nadia Division | Ranaghat Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Purba Khamarsimulia PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 105.00 Cu.m/hr | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000469/2023-2024 | 136/ND | 09/01/2024 | 90 | M/S R.K.ENTERPRISE | 99.27 | 0 | 0
1599 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tube well (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000524/2022-2023 | 1269/ND | 23/03/2023 | 780 | JOY HIND TUBEWELL'S | 65.37 | 0 | 100
1600 | Nadia Division | Ranaghat Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Monipota PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 65.00 Cu.m/hr | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000468/2023-2024 | 135/ND | 09/01/2024 | 360 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 74.19 | 0 | 50
1601 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Krishnagar-I Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000523/2022-2023 | 1268/ND | 23/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 0 | 45
1602 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANPUR W/S Scheme, Block- Krishnaganj, ARABPUR W/S Scheme, Block-Karimpur, BHIMPUR W/S Scheme, Block-Krishnagar AND MONIPOTA W/S Scheme, Block- Krishnagar-I, Dist. - Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001444/2023-2024 | 5127/EMD | 04/09/2023 | 666 | C.M.S. ENGINEERING CONCERN. | 70.97 | 0 | 12
1603 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Monipota ground water based water supply scheme under Block_ Krishnanagar_I Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15135) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001463/2024-2025 | 234/EMD | 06/02/2025 | 30 | M/S.A.K. BANERJEE. | 11.76 | 0 | 0
1604 | Nadia Division | Debgram Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Joania PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 55.00 Cu.m/hr | Assistant Engineer | Junior Engineer | ORD/000491/2023-2024 | 6008/ND | 14/12/2023 | 720 | ASIT PRAMANIK | 64.95 | 0 | 80
1605 | Nadia Division | Debgram Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Krishnagar-I Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000523/2022-2023 | 1268/ND | 23/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 15.94 | 45
1606 | Eastern Mechanical | Debgram Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No.- I AND II under Joania WS Scheme, Block Krishnagar I, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-06) | Assistant Engineer | Junior Engineer | ORD/000889/2022-2023 | 157/EMDdt.06.01.2023 | 08/02/2023 | 726 | MASSK ENGINEERING WORKS | 14.9 | 0 | 100
1607 | Eastern Mechanical | Debgram Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Banpur ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15280) | Assistant Engineer | Junior Engineer | ORD/001455/2024-2025 | 228/EMD | 06/02/2025 | 30 | BINAPANI ENTERPRISE | 11.76 | 0 | 0
1608 | Eastern Mechanical | Debgram Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Joania ground water based water supply scheme under Block_ Krishnanagar_I Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15138) | Assistant Engineer | Junior Engineer | ORD/001462/2024-2025 | 233/EMD | 06/02/2025 | 30 | SHRESTHA | 11.76 | 0 | 0
1609 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muratipur at Kanchrapara G.P. and Hapania at Nagrukhra-II G.P. by retrofitting of surface water based PWSS Water Supply Scheme for Haringhata-Chakdah (Part) in connection with retrofitting work of Zone-II, Hapania Part-II under Nadia Arsenic Division-I, PHE Dte. (sl.02) | Assistant Engineer-I | Junior Engineer-II | ORD/000031/2023-2024 | 1255 /NAD-I | 04/05/2023 | 30 | BUDDHADEV MONDAL | 37.15 | 37.14 | 0
1610 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-II (Hapania) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000109/2021-2022 | 1611/NAD-I | 28/12/2021 | 90 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT LTD. | 404.05 | 389.71 | 100
1611 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying UPVC pipeline at different location of Z-II ( Hapania ) under Nagarukhra -I & II G.P. under Surface Based Haringhata & Chakdah (Part) Surface Water Supply scheme under Nadia Arsenic -I, P.H.E. Dte. (01) | Assistant Engineer-I | Junior Engineer-II | ORD/000112/2022-2023 | 88 / AE-I/NAD-I | 28/04/2022 | 15 | TARUN KUMAR BHATTACHARYA | 4.84 | 4.8 | 100
1612 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-II , Hapania at Nagarukhra G.P at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-II, Hapania, Part-III under Nadia Arsenic Division-I, PHE Dte. (sl. 18) | Assistant Engineer-I | Junior Engineer-II | ORD/000221/2022-2023 | 303 /NAD-I | 27/02/2023 | 60 | MONDAL ENTERPRISE | 96.62 | 0 | 74
1613 | Nadia Division | Krishnanagar Sub-Division | Construction of Pump House (3.6Mtr. X 3.0 Mtr.) and allied works at 3rd T/W Site at Chapra Bangaljhi Water Supply Scheme Under Krishnagar Sub-dividion Under Nadia Division. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000059/2023-2024 | 733/KSD | 07/06/2023 | 60 | BABLU MALLICK | 4.98 | 0 | 100
1614 | Nadia Division | Krishnanagar Sub-Division | Construction of Boundary Wall and allied works at 3rd T/W Site Chapra Bangaljhi Water Supply Scheme Under Krishnagar Sub-dividion Under Nadia Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000078/2023-2024 | 734/KSD | 07/06/2023 | 60 | AMIT KARMAKAR | 4.95 | 0 | 100
1615 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme, Construction of 900 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 900 CUM OHR at Chapra Bangaljhi to accommodate FHTC within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000188/2022-2023 | 4540/ND | 21/10/2022 | 1462 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 689.72 | 153.34 | 60
1616 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab for official use for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01.01.2023 (as and when required). | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000486/2022-2023 | 1331/KSD | 29/12/2022 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 100
1617 | Nadia Division | Krishnanagar Sub-Division | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Chapra Bangaljhi Water Supply Scheme within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000503/2023-2024 | 6210/ND | 28/12/2023 | 60 | S.B.CONSTRUCTION | 12.16 | 0 | 20
1618 | Nadia Division | Krishnanagar Sub-Division | Fencing for Land at Chapra Bangaljhi and Teorkhali Water supply scheme at new 3rd Tube Well site under Krishnagar Sub-Division PHED. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000532/2022-2023 | 219/KSD | 03/03/2023 | 15 | SANJIB DEY | 0.45 | 0.22 | 0
1619 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01/04/2023.(as and when required). | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000591/2022-2023 | 376/KSD | 28/03/2023 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0
1620 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 174 m3/hr at Chapra Bangaljhi Water Supply Scheme within Chapra Block under Krishnagar Sub- Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000787/2023-2024 | 1898/ND | 15/03/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 385.52 | 0 | 0
1621 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000003/2022-2023 | 2158/ND | 18/05/2022 | 0 | Resource Division | 107.67 | 0 | 0
1622 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000094/2023-2024 | 2326/ND | 29/05/2023 | 0 | Resource Division | 16.29 | 0 | 0
1623 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000099/2022-2023 | 4930/ND | 25/11/2022 | 0 | Resource Division | 108.85 | 0 | 0
1624 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000138/2021-2022 | 1395/ND | 24/03/2022 | 0 | Resource Division | 46.6 | 0 | 0
1625 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | VCH/001141/2021-2022 | 705/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.04 | 0 | 0
1626 | Central Drilling | Krishnanagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for ChapraBangaljhi W/S Scheme (T/W-III & IV) , Chapra Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000102/2023-2024 | 131/CDD | 17/04/2023 | 503 | PADMA ENGINEERING & CO. | 37.3 | 0 | 50
1627 | Eastern Mechanical | Krishnanagar Sub-Division | Quotation for new service connection charges and security deposit for PH-3 under Chapra Bangaljhi w/s scheme,under EMSD-III,PHE Dte,Nadia | Assistant Engineer | Junior Engineer,Junior Engineer 3 | BILL/01812/2024-2025 | BP-156-24-25 | 06/11/2024 | 0 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 4.99 | 0 | 0
1628 | Eastern Mechanical | Krishnanagar Sub-Division | Quotation charges and security deposit for new power connection at Pump House -IV of Chapra Bangaljhi w/s scheme under EMSD-III,PHE Dte., Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | BILL/02315/2024-2025 | BP-194-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 4.84 | 0 | 0
1629 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under CHAPRA BANGALJHI W/S Scheme, Block-CHAPRA , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 07) | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000900/2022-2023 | 410/EMD | 20/01/2023 | 712 | ASHUTOSH DAS & CO. | 37.79 | 0 | 50
1630 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali BlocK,. under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000528/2022-2023 | 1271/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 48.99 | 0 | 40
1631 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-II (Phase-II) under Badkulla ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001771/2023-2024 | 6395/EMD | 30/10/2023 | 30 | M/S. G.P. ENTERPRISE | 12.61 | 0 | 100
1632 | Nadia Division | RWS Nadia Sub-Division | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site & 2nd Tube Well Site of Ber Ramchandrapur Zone-II [Phase-II] Ground Based Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000516/2022-2023 | 1193/ND | 21/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 28.7 | 18.62 | 70
1633 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000105/2023-2024 | 3787/ND | 24/08/2023 | 0 | Resource Division | 2.94 | 0 | 0
1634 | Eastern Mechanical | RWS Nadia Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I & II Zone-II(Phase-II) under Ber Ramchandrapur ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/001769/2023-2024 | 6393/EMD | 30/10/2023 | 30 | SHIVAM ENTERPRISE | 16.27 | 0 | 0
1635 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP (Gravity Type) of capacity 231 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Subarnabihar Zone I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000026/2023-2024 | 1784/ND | 20/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 222.99 | 139.92 | 65
1636 | Eastern Mechanical | RWS Nadia Sub-Division | Providing, installation and commissioning of Electro-Mechanical Equipment and allied works for Arsenic Removal Plant in connection to Accommodate FHTC under Subarna Behar ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia, under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/001433/2024-2025 | 184/EMD | 29/01/2025 | 204 | DAS ENTERPRISE (M) | 51.34 | 0 | 0
1637 | Nadia Division | RWS Nadia Sub-Division | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Teinpur Zone-IV PWSS within Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000006/2024-2025 | 3260/ND | 10/06/2024 | 450 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 82.42 | 0 | 80
1638 | Nadia Division | RWS Nadia Sub-Division | Renovation and modification of AIRP (Pressure Type) of capacity 20.87 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site in Teinpur Zone IV PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000008/2023-2024 | 1807/ND | 24/04/2023 | 547 | MONDAL PRECISION PRIVATE LIMITED | 39.12 | 0 | 90
1639 | Eastern Mechanical | RWS Nadia Sub-Division | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Teinpur Zone-IV (Phase-II) Piped Water Supply Scheme Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/001749/2023-2024 | 6360/EMD | 17/10/2023 | 30 | M/S SAJAHAN CHOWDHURY | 42.1 | 0 | 0
1640 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Gravity Type) of capacity 93 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Pansila PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000085/2023-2024 | 2998/ND | 13/07/2023 | 90 | TARUN KUMAR BHATTACHARYA | 90.1 | 0 | 0
1641 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PANSILA W/S Scheme, Block-Nabadwip , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001013/2022-2023 | 501/EMDdt.24.01.2023 | 16/03/2023 | 30 | ASHOKE ADHIKARY | 15.59 | 2.37 | 100
1642 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-III within Nakashipara Block ( Phase -B) | Assistant Engineer |  | ORD/000284/2020-2021 | 244/ND | 15/01/2021 | 90 | UMWELT ENGINEERS PVT LTD | 97.08 | 24.58 | 0
1643 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT PART-II, Z-III | Assistant Engineer |  | VCH/001073/2020-2021 | 460/DW | 30/03/2021 | 0 | UMWELT ENGINEERS PVT LTD | 77.39 | 0 | 0
1644 | Nadia Division | Kalyani Sub-Division I | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-112 | Assistant Engineer |  | BILL/00515/2024-2025 | 306/PFMS | 02/10/2024 | 0 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 4.99 | 0 | 0
1645 | Nadia Division | Kalyani Sub-Division I | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-136 | Assistant Engineer |  | BILL/00516/2024-2025 | 307/PFMS | 02/10/2024 | 0 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 6.59 | 0 | 0
1646 | Nadia Division | Kalyani Sub-Division I | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 0 | 47
1647 | Nadia Division | Kalyani Sub-Division I | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000185/2024-2025 | 6095/ND | 19/09/2024 | 240 | UMWELT ENGINEER PVT LTD | 225.66 | 0 | 75
1648 | Nadia Division | Kalyani Sub-Division I | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
1649 | Nadia Division | Kalyani Sub-Division I | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000236/2025-2026 | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0
1650 | Nadia Division | Kalyani Sub-Division I | Collection of Household data through mobile app for FHTC Connection of Surface Based PWSS for Northern Sector (Part-I) (Zone-IXA to Zone-IXB) under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000353/2023-2024 | 913/KLYSD-I | 29/08/2023 | 184 | TECHVISION | 0.97 | 0 | 100
1651 | Nadia Division | Kalyani Sub-Division I | Refixing of Existing FHTC with Ferrule Connection at Surface Water Based W/S Scheme for Arsenic Affected Areas of Nadia District (Northern Sector Part-I) under Nadia Division, PHED. | Assistant Engineer |  | ORD/000504/2023-2024 | 559/ND | 25/01/2024 | 450 | UMWELT ENGINEER PVT LTD | 207.02 | 0 | 51
1652 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000170/2022-2023 | 131/ND | 06/01/2023 | 0 | Resource Division | 1214.5 | 0 | 0
1653 | Eastern Mechanical | Kalyani Sub-Division I | Quotation for earnest Money deposit for bulk power supply for Kaliganj GLR Project. | Assistant Engineer |  | BILL/00383/2024-2025 | BP-24-24-25 | 21/05/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 0.05 | 0 | 0
1654 | Eastern Mechanical | Kalyani Sub-Division I | Service connection charges and Security deposit for new bulk power supply to Kaliganj GLR, Nadia, Pin code- 741136. | Assistant Engineer |  | BILL/01309/2024-2025 | BP-79-24-25 | 02/08/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 39.52 | 0 | 0
1655 | Eastern Mechanical | Kalyani Sub-Division I | Quotation for new service connection charges and security deposit for Juranpur OHR site. | Assistant Engineer |  | BILL/01769/2024-2025 | BP-144-24-25 | 28/10/2024 | 0 | WBSEDCL.MATIARY.CCC | 3.86 | 0 | 0
1656 | Eastern Mechanical | Kalyani Sub-Division I | Quotation for new service connection charges and security deposit for Dakshin Hazrapota OHR site. | Assistant Engineer |  | BILL/01770/2024-2025 | BP-145-24-25 | 28/10/2024 | 0 | WBSEDCL.MATIARY.CCC | 11.45 | 0 | 0
1657 | Eastern Mechanical | Kalyani Sub-Division I | Quotation for new service connection charges and security deposit for Bathangachi OHR (Zone-6B) site. | Assistant Engineer |  | BILL/01771/2024-2025 | BP-146-24-25 | 28/10/2024 | 0 | WBSEDCL.PALASSEY.CCC | 4.28 | 0 | 0
1658 | Eastern Mechanical | Kalyani Sub-Division I | New Service connection and security deposit for Debagram (Zone- 5B) OHR site. | Assistant Engineer |  | BILL/01772/2024-2025 | BP-147-24-25 | 28/10/2024 | 0 | WBSEDCL DEBOGRAM CCC | 3.81 | 0 | 0
1659 | Eastern Mechanical | Kalyani Sub-Division I | New Service connection and security deposit for Asachiya (Zone- 3B) OHR site. | Assistant Engineer |  | BILL/01773/2024-2025 | BP-148-24-25 | 28/10/2024 | 0 | WBSEDCL DEBOGRAM CCC | 3.65 | 0 | 0
1660 | Eastern Mechanical | Kalyani Sub-Division I | New Service connection and security deposit for Ghoraikhetra (zone- 4B) OHR site. | Assistant Engineer |  | BILL/01774/2024-2025 | BP-149-24-25 | 28/10/2024 | 0 | WBSEDCL DEBOGRAM CCC | 3.42 | 0 | 0
1661 | Eastern Mechanical | Kalyani Sub-Division I | Quotation for new service connection and security deposit for Bhurulia OHR (Zone- 7B) site, plaseey. | Assistant Engineer |  | BILL/01775/2024-2025 | BP-150-24-25 | 28/10/2024 | 0 | WBSEDCL.PALASSEY.CCC | 4.47 | 0 | 0
1662 | Eastern Mechanical | Kalyani Sub-Division I | Quotation for new service connection and security deposit for Chhota chandghar OHR (Zone-9B) site | Assistant Engineer |  | BILL/01776/2024-2025 | BP-151-24-25 | 28/10/2024 | 0 | WBSEDCL.PALASSEY.CCC | 7.98 | 0 | 0
1663 | Eastern Mechanical | Kalyani Sub-Division I | Providing Axially Split Centrifugal Pumping machinery for GLR alongwith secondary disinfection arrangement for surface water based water supply scheme, Arsenic Affected Area, Northern Sector, Part-I (Block - Kaliganj) in the district of Nadia, P. H. E. Dte. | Assistant Engineer |  | ORD/001688/2023-2024 | 6262/EMD | 10/10/2023 | 600 | ORIENTAL ENGINEERING CO. | 271.65 | 0 | 25
1664 | Eastern Mechanical | Kalyani Sub-Division I | Augmentation of pumping machinery and electrical equipments at Intake, WTP alongwith implementation of SCADA System for surface water based water supply scheme, Arsenic affected area, Northern Sector, Part-I (Block - Kaliganj) in the district of Nadia, P. H. E. Dte. | Assistant Engineer |  | ORD/001689/2023-2024 | 6263/EMD | 10/10/2023 | 600 | ORIENTAL ENGINEERING CO. | 308.87 | 0 | 25
1665 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/001771/2022-2023 | 1121/EMD | 16/03/2023 | 30 | M.S. ENTERPRISE | 65.68 | 5.87 | 90
1666 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnagar-I Block of Nadia District through Jadavpur University. (Name of PWSS Bansberia) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000092/2023-2024 | 1058/NACD-II | 20/09/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100
1667 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Arsenic cum Iron treatment Plant of Bansberia PWSS (Capacity- 31 m3/hr) and ancillary works of Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000199/2023-2024 | 89/NACD-II | 18/01/2024 | 60 | MONDAL PRECISION PRIVATE LIMITED | 78.06 | 0 | 100
1668 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Bansbaria (Vill- Poragachha) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000225/2020-2021 | 288/NACD-II | 23/02/2021 | 21 | SANDIP BISWAS | 35.39 | 0 | 100
1669 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation work at Bansberia Head Work Site under Bansberia Piped Water Supply Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000228/2024-2025 | 926/AE-I/NACD-II | 30/09/2024 | 30 | JYOTIRMOY ENTERPRISE | 4.61 | 0 | 0
1670 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair due to construction of road) at Bansbaria W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000264/2022-2023 | 1019/NACD-II | 29/11/2022 | 60 | S.B. CONSTRUCTION | 27.03 | 27.03 | 100
1671 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of Water Level Indicator at Bansberia in Krishnagar-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000413/2024-2025 | 1158/AE-I/NACD-II | 31/01/2025 | 45 | M/S S.K. CONSTRUCTION | 0.77 | 0 | 100
1672 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 0 | 47
1673 | Nadia Division | Debgram Sub-Division | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000185/2024-2025 | 6095/ND | 19/09/2024 | 240 | UMWELT ENGINEER PVT LTD | 225.66 | 0 | 75
1674 | Nadia Division | Debgram Sub-Division | Collection of Household data through mobile app for FHTC Connection of Surface Based PWSS for Northern Sector (Part-I) (Zone-VA to Zone-VIIIB) under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000340/2023-2024 | 994/KLYSD-I | 14/09/2023 | 90 | TECHVISION | 4.85 | 0 | 100
1675 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 6B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000777/2021-2022 | 127/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.26 | 4.23 | 100
1676 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000123/2022-2023 | 105/ND | 05/01/2023 | 0 | Resource Division | 223 | 0 | 0
1677 | Nadia Division | Tehatta Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Hasnpukuria Zone-II to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000260/2024-2025 | 4700/ND | 29/08/2024 | 540 | MONDAL PRECISION PRIVATE LIMITED | 181.28 | 0 | 0
1678 | Nadia Division | Tehatta Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Hasnpukuria Zone-I to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000261/2024-2025 | 4701/ND | 29/08/2024 | 360 | MONDAL PRECISION PRIVATE LIMITED | 181.86 | 0 | 0
1679 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Hanspukuria Zone-I water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000307/2024-2025 | 6836/ND | 12/11/2024 | 90 | BUDDHADEV MONDAL | 32.88 | 0 | 0
1680 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Hanspukuria Zone-I to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000311/2022-2023 | 5351/ND | 22/12/2022 | 731 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 203.73 | 177.3 | 95
1681 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 300 cum capacity 20 mtr. height RCC over head reservoir (with pile foundation), pipe connection and cost of pipes, specials. and Soil investigation for construction of one No. 300 Cum OHR of staging height 20 mtr. for Augmentation of Ground Based Water Supply Scheme at Hanspukuria Zone-II to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000392/2022-2023 | 480/ND | 02/02/2023 | 731 | M/S DIPAK ENTERPRISE, GHOSH PARA,WORD NO.-4, KALYANI, NADIA-741235 WEST BENGAL | 291.32 | 98.59 | 65
1682 | Nadia Division | Tehatta Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Hanspukuria W/S Scheme in Tehatta-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000451/2021-2022 | 298/TSD | 24/11/2021 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 4.07 | 4.07 | 100
1683 | Nadia Division | Tehatta Sub-Division | Construction of barbed wire fencing with concrete pillars at Hanspukuria Zone-II (2nd T.W). water supply scheme( New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | Assistant Engineer | Junior Engineer | ORD/000582/2022-2023 | 931/TSD | 14/03/2023 | 7 | PRABIR KUMAR ROY | 0.46 | 0.46 | 0
1684 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Hanspukuria Zone-I Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division, P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Hanspukuria Zone-I at Tehatta-II Block by Augmentation of Ground Water based PWSS for Hanspukuria Zone-I Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000625/2024-2025 | 7358/ND | 18/12/2024 | 60 | SAHA CONSTRUCTION & CO | 20.43 | 0 | 25
1685 | Nadia Division | Tehatta Sub-Division | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Headwork site , Hanspukuria Zone-II PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000662/2023-2024 | 1097/ND | 19/02/2024 | 30 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 17.39 | 0 | 100
1686 | Nadia Division | Tehatta Sub-Division | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at 2nd Tubewell site , Hanspukuria Zone-II PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000688/2023-2024 | 1224/ND | 22/02/2024 | 240 | M/S DIPAK ENTERPRISE | 17.38 | 0 | 100
1687 | Nadia Division | Tehatta Sub-Division | Construction of barbed wire fencing with concrete pillars at Hanspukuria Zone-II water supply scheme 1st T.W. H.W.Site (New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | Assistant Engineer | Junior Engineer | ORD/000728/2023-2024 | 1117/TSD | 21/02/2024 | 7 | PRABIR KUMAR ROY | 2.13 | 0 | 100
1688 | Nadia Division | Tehatta Sub-Division | Construction Of Pump House (5.4m X 3.6m) & (3.6m X 3.0m) Including Sanitary Arrangement At Head Work Site & 2nd tube well Site and construction of Boundary wall at Head works site & 2nd tube well site of Hanspukuria Zone - II Ground water based water supply scheme under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000756/2023-2024 | 1630/ND | 07/03/2024 | 180 | J.P. CONSTRUCTION & SUPPLIERS | 34.04 | 0 | 65
1689 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000003/2024-2025 | 3503/ND | 24/06/2024 | 0 | Resource Division | 12.39 | 0 | 0
1690 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000067/2023-2024 | 2310/ND | 29/05/2023 | 0 | Resource Division | 13.8 | 0 | 0
1691 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000181/2022-2023 | 153/ND | 06/01/2023 | 0 | Resource Division | 154.79 | 0 | 0
1692 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000197/2022-2023 | 1026/ND | 13/03/2023 | 0 | Resource Division | 1.39 | 0 | 0
1693 | Eastern Mechanical | Tehatta Sub-Division | Quotation for New service connection charges and security deposit for Hanspukuria 2nd T/W. | Assistant Engineer | Junior Engineer | BILL/02156/2024-2025 | BP-172-24-25 | 05/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 3.02 | 0 | 0
1694 | Eastern Mechanical | Tehatta Sub-Division | Quotation charges and security deposit for new power connection at Hanspukuria (Zone-II) head worksite under Eastern Mechanical Subdivision-III, Nadia | Assistant Engineer | Junior Engineer | BILL/02255/2024-2025 | BP-193-24-25 | 16/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 9.18 | 0 | 0
1695 | Eastern Mechanical | Tehatta Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Hanspukuria ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. SM/11918 | Assistant Engineer | Junior Engineer | ORD/000176/2025-2026 | 1109/EMD | 04/06/2025 | 90 | ANJAN ENTERPRISE | 20.8 | 0 | 0
1696 | Eastern Mechanical | Tehatta Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well and New Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II , III , IV Zone-I & Pump House No.-I ,II (Zone-II) under Hanspukuria ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. (SM/11918) | Assistant Engineer | Junior Engineer | ORD/001467/2024-2025 | 238/EMD | 06/02/2025 | 30 | DEY ENTERPRISE | 72.07 | 0 | 25
1697 | Nadia Division | Debgram Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 137 cum. for Providing FHTC (Functional Household Tap Connection) for Zone -I/A (Northern Sector, Part-II) Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte.¿ | Assistant Engineer |  | ORD/000260/2023-2024 | 3998/ND | 07/09/2023 | 60 | M/S ARATI ENTERPRISE | 13.1 | 0 | 65
1698 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- I/A (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000311/2023-2024 | 4281/ND | 21/09/2023 | 642 | PRASUN ENTERPRISE | 268.05 | 0 | 25
1699 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
1700 | Nadia Division | Debgram Sub-Division | Construction of OHR, repair and renovation of staff room, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-I / A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. [SM/11836]. | Assistant Engineer |  | ORD/000430/2023-2024 | 5556/ND | 12/12/2023 | 1094 | M/S DIPAK ENTERPRISE, GHOSH PARA,WARD NO-4, KALYANI, NADIA-741235 WEST BENGAL | 150.28 | 0 | 5
1701 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 1/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000785/2021-2022 | 135/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.91 | 3.8 | 100
1702 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000115/2023-2024 | 235/ND | 11/01/2024 | 0 | Resource Division | 3.79 | 0 | 0
1703 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000130/2022-2023 | 91/ND | 05/01/2023 | 0 | Resource Division | 64.78 | 0 | 0
1704 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Kishorpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retrofitting) | Assistant Engineer |  | ORD/000092/2021-2022 | 2769/ND | 14/07/2021 | 90 | SANDIP BISWAS | 96.61 | 0 | 100
1705 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000048/2021-2022 | 433/ND | 31/01/2022 | 0 | Resource Division | 1 | 0 | 0
1706 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Kishorpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retrofitting) | Assistant Engineer |  | VCH/000794/2021-2022 | 421/PFMS | 19/01/2022 | 0 | SANDIP BISWAS | 93.47 | 0 | 0
1707 | Central Drilling | Tehatta Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KISHOREPUR W/S (REPLACEMENT TW-HW) IN KARIMPUR-II BLOCK UNDER NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer |  | ORD/000097/2022-2023 | 281/CMSD-II (D) | 01/06/2022 | 15 | UNIVERSAL ENTERPRISES | 2.07 | 1.63 | 0
1708 | Central Drilling | Tehatta Sub-Division | PROVIDING 200 MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KISHOREPUR W/S (REPLACEMENT TW-HW) KARIMPUR -II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer |  | ORD/000098/2022-2023 | 282/CMSD-II (D) | 01/06/2022 | 15 | UNIVERSAL ENTERPRISES | 4.44 | 0 | 0
1709 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-III, within Kaliganj Block (Phase-C, Retrofitting) | Assistant Engineer |  | ORD/000263/2020-2021 | 161/ND | 13/01/2021 | 90 | M/S NIBHAS SINHA | 97.11 | 41.46 | 0
1710 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC SURFCE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-I, Z-III, WITHIN KALIGANJ BLOCK, PHASE-C | Assistant Engineer |  | VCH/000876/2021-2022 | 475/PFMS | 03/02/2022 | 0 | M/S NIBHAS SINHA | 4.67 | 0 | 0
1711 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME (NORTHERN SECTOR) PART-I, ZONE-III WITHIN KALIGANJ BLOCK (PHASE-C) | Assistant Engineer |  | VCH/000909/2020-2021 |  | 17/03/2021 | 0 | M/S NIBHAS SINHA | 50.76 | 0 | 0
1712 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME ATPART-1 Z-3 | Assistant Engineer |  | VCH/001065/2020-2021 | 460/DW | 30/03/2021 | 0 | M/S NIBHAS SINHA | 50.76 | 0 | 0
1713 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, Shimurali, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000022/2021-2022 | 865/NAD-I | 15/06/2021 | 60 | ALOK ENTERPRISE | 80.87 | 80.7 | 100
1714 | Nadia Arsenic Division I |  | Hiring of 1 (One) no Diesel Luxury Taxi/Maxi Cab/Motor Cab on Daily basis for monitoring of JJM works and progress of JJM works (Such as identification of land etc) under the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000182/2023-2024 | 383/AE-I/NAD-I | 01/09/2023 | 182 | ANURADHA DHARA | 2.4 | 0.62 | 20
1715 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000009/2021-2022 | 773/NAD-I | 04/05/2021 | 60 | H I ENTERPRISE | 95.74 | 106.72 | 100
1716 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukilnara Zone - II at Ranaghat - I Block by retrofitting of Ground Water based PWSS for Ukilnara - Zone - II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl. No.-08) Tender No. 234/NAD-I/2020-2021. |  |  | ORD/000189/2020-2021 | 292/NAD-I | 04/02/2021 | 45 | M/S UMA CONSTRUCTION | 43.74 | 25.38 | 100
1717 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-II Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. -01) Tender no.- 230/NAD-I/2020-2021. |  |  | ORD/000192/2020-2021 | 290/NAD-I | 04/02/2021 | 45 | CHANDAN ROY | 43.9 | 0 | 100
1718 | Nadia Arsenic Division I |  | Supply of 1(one )no. Motor Cab ( Luxury Taxi) on hire basis for official use of the Executive Engineer , Nadia Arsenic Division -I, P.H.E.Dte. for the period from ( 15.07.22 to 14.07.23i.e. for 1(one) year .(sl.01) |  |  | ORD/000304/2021-2022 | 173 / AE-I/NAD-I | 14/07/2021 | 365 | AVINABA ENGINEERING CONCERN | 5.34 | 4.07 | 100
1719 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I, Ukhilnara -II, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000391/2020-2021 | 292 / NAD-I | 04/02/2021 | 45 | M/S UMA CONSTRUCTION | 43.74 | 1.9 | 60
1720 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara Jal Swapna for Zone IX Ghetugachi Part II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte |  |  | ORD/000018/2021-2022 | 783/NAD-I | 05/05/2021 | 60 | TAPU SAHA | 68.94 | 131.63 | 100
1721 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XII, Balagarichar, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000010/2021-2022 | 774/NAD-I | 04/05/2021 | 60 | PALCON | 39.63 | 76.69 | 100
1722 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XII, Balagarichar, Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000011/2021-2022 | 775/NAD-I | 04/05/2021 | 60 | PRIYA CONSTRUCTION | 66.11 | 124.65 | 100
1723 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara/JalSwapna for Sabdalpur, at Ranaghat-II Block by retrofitting of Ground Water Based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000023/2021-2022 | 954/NAD-I | 09/07/2021 | 90 | TARUN KUMAR BHATTACHARYA | 182.15 | 238.68 | 100
1724 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VIII within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.8) | Assistant Engineer |  | ORD/000460/2020-2021 | 867/ND | 18/02/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 97.09 | 27.09 | 0
1725 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000164/2023-2024 | 233/ND | 11/01/2024 | 0 | Resource Division | 8.75 | 0 | 0
1726 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000482/2021-2022 |  | 04/10/2021 | 0 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 60.5 | 0 | 0
1727 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000613/2021-2022 | 282/PFMS | 08/10/2021 | 0 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 60.5 | 0 | 0
1728 | Nadia Division | Debgram Sub-Division | PROVIDIDING FHTC AT SURFACE WATER BAESD WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II,ZONE-VIII, WITHIN NAKASHIPARA BLOCK, PHASE-B. | Assistant Engineer |  | VCH/000888/2021-2022 | 487/PFMS | 03/02/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 0.41 | 0 | 0
1729 | Nadia Division | Debgram Sub-Division | PROVIDIDING FHTC AT SURFACE WATER BAESD WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II,ZONE-VIII, WITHIN NAKASHIPARA BLOCK, PHASE-B. | Assistant Engineer |  | VCH/000889/2021-2022 | 492/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.47 | 0 | 0
1730 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. Tender No.- 217/NAD-I/2020-2021. |  |  | ORD/000168/2020-2021 | 277/NAD-I | 03/02/2021 | 90 | H I ENTERPRISE | 90.31 | 177.47 | 100
1731 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Badlangi Padmamala Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer |  | ORD/000006/2021-2022 | 2045/ND | 13/05/2021 | 60 | TAPU SAHA | 42.45 | 0 | 100
1732 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Badlangi Padmamala Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer |  | ORD/000007/2021-2022 | 2046/ND | 13/05/2021 | 60 | TAPU SAHA | 42.45 | 68.03 | 100
1733 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Badlangi Padmamala Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | Assistant Engineer |  | ORD/000059/2021-2022 | 2390/ND | 10/06/2021 | 45 | BIPLAB GUHA | 9.23 | 17.76 | 100
1734 | Nadia Division | RWS Nadia Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
1735 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000021/2021-2022 | 104/ND | 06/01/2022 | 0 | Resource Division | 0.86 | 0 | 0
1736 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000027/2022-2023 | 4019/ND | 16/09/2022 | 0 | Resource Division | 24.55 | 0 | 0
1737 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000053/2021-2022 | 436/ND | 31/01/2022 | 0 | Resource Division | 0.63 | 0 | 0
1738 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000109/2021-2022 | 1027/ND | 03/03/2022 | 0 | Resource Division | 6.33 | 0 | 0
1739 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | Assistant Engineer |  | VCH/000610/2021-2022 | 279/PFMS | 08/10/2021 | 0 | TAPU SAHA | 33.12 | 0 | 0
1740 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-VIII, within Kaliganj Block (Phase-B, Retrofitting)" | Assistant Engineer |  | ORD/000267/2020-2021 | 164/ND | 13/01/2021 | 90 | MAHABIR PUMPS MFG PVT. LTD. | 97.11 | 9.26 | 100
1741 | Nadia Division | Debgram Sub-Division | Laying of main distribution pipeline at zone-III and VIII of Surface water based water supply scheme, part-I within Kaliganj Block damaged during 4- laning of NH-34. | Assistant Engineer |  | ORD/000824/2021-2022 | 56/DSD | 07/02/2022 | 15 | TARUN KUMAR BHATTACHARYA | 3.43 | 3.25 | 0
1742 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) | Assistant Engineer |  | VCH/000536/2021-2022 | 305/PFMS | 01/11/2021 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 30 | 0 | 0
1743 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) | Assistant Engineer |  | VCH/000914/2021-2022 | 554/PFMS | 23/02/2022 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 25 | 0 | 0
1744 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B). | Assistant Engineer |  | VCH/000945/2020-2021 |  | 20/03/2021 | 0 | MAHABIR PUMPS MFG PVT. LTD. | 22.98 | 0 | 0
1745 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block (Phase-B) | Assistant Engineer |  | VCH/000984/2021-2022 | 586/PFMS | 04/03/2022 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 4.18 | 0 | 0
1746 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT PART-I Z-VIII | Assistant Engineer |  | VCH/001070/2020-2021 | 460/DW | 30/03/2021 | 0 | MAHABIR PUMPS MFG PVT. LTD. | 22.98 | 0 | 0
1747 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-V, within Kaliganj Block (Phase-B, Retrofitting)" | Assistant Engineer |  | ORD/000265/2020-2021 | 162/ND | 13/01/2021 | 90 | M/S SHIL & CO. | 97.11 | 8.37 | 0
1748 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-B) | Assistant Engineer |  | VCH/000477/2021-2022 | 286/PFMS | 08/10/2021 | 0 | M/S SHIL & CO. | 18.5 | 0 | 0
1749 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME(NORTHERN SECTOR)PART-I,ZONE-V, WITHIN KALIGANJ BLOCK (PHASE-B,RETROFITTING) | Assistant Engineer |  | VCH/000871/2020-2021 |  | 12/03/2021 | 0 | M/S SHIL & CO. | 63.52 | 0 | 0
1750 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-V within Kaliganj Block (Phase-B) | Assistant Engineer |  | VCH/001018/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 5.97 | 0 | 0
1751 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME PART -1 Z-V | Assistant Engineer |  | VCH/001061/2020-2021 | 459/DW | 30/03/2021 | 0 | M/S SHIL & CO. | 63.52 | 0 | 0
1752 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-III, within Krishnagar-II & Nabadwip Block (Phase-A, Retrofitting)" | Assistant Engineer |  | ORD/000398/2020-2021 | 774/ND | 10/02/2021 | 90 | M/S S & P CONSTRUCTION | 97.07 | 41.73 | 0
1753 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II Nabadwip (Part) Block (Phase-A). | Assistant Engineer |  | VCH/000443/2021-2022 |  | 29/09/2021 | 0 | M/S S & P CONSTRUCTION | 73.75 | 0 | 0
1754 | Nadia Division | Krishnanagar Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME NORTHERN SECTOR , PART-3, ZONE-3 WITHIN KRISHNAGAR-2 NABADWIP BLOCK PHASE-A | Assistant Engineer |  | VCH/000586/2021-2022 | 239/PFMS | 05/10/2021 | 0 | M/S S & P CONSTRUCTION | 73.75 | 0 | 0
1755 | Nadia Division | Krishnanagar Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-III, Z-III, WITHIN KRISHNAGAR-2 AND NABADWIP BLOCK, PHASE-A. | Assistant Engineer |  | VCH/000884/2021-2022 | 499/PFMS | 03/02/2022 | 0 | M/S R. DUTTA & CO. | 0.46 | 0 | 0
1756 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX within Kaliganj Block (Phase-C) | Assistant Engineer |  | ORD/000091/2021-2022 | 2768/ND | 14/07/2021 | 90 | M/S K.P. CONSTRUCTION | 92.27 | 19.29 | 100
1757 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX within Kaliganj Block (Phase-C) | Assistant Engineer |  | VCH/000743/2021-2022 | 410/PFMS | 21/12/2021 | 0 | M/S K.P. CONSTRUCTION | 71.05 | 0 | 0
1758 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-III, within Krishnagar-II & Nabadwip Block (Phase-B, Retrofitting)" | Assistant Engineer |  | ORD/000399/2020-2021 | 775/ND | 10/02/2021 | 90 | UNICON INDIA | 97.6 | 0 | 0
1759 | Nadia Division | Krishnanagar Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME NORTHERN SECTOR PART-II, ZONE-III, WITHIN KRISHNAGAR-II AND NABADWIP BLOCK PHASE-B RETROFITTING. | Assistant Engineer |  | VCH/000197/2021-2022 | 87/PPMS | 15/07/2021 | 0 | UNICON INDIA | 29.58 | 0 | 0
1760 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II, Nabadwip (Part) Block (Phase-B) | Assistant Engineer |  | VCH/000608/2021-2022 | 271/PFMS | 08/10/2021 | 0 | UNICON INDIA | 61.22 | 0 | 0
1761 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block ( Phase -A) in Nadia District under Nadia Division P.H.E. Dte. SLNo.7 | Assistant Engineer | je1 | ORD/000468/2020-2021 | 894/ND | 19/02/2021 | 90 | ALOKE ENTERPRISE | 97.09 | 25.6 | 0
1762 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer | je1 | RTOR000091/2022-2023 | 4318/ND | 29/09/2022 | 0 | Resource Division | 12.46 | 0 | 0
1763 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) | Assistant Engineer | je1 | VCH/000476/2021-2022 |  | 04/10/2021 | 0 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 59.73 | 0 | 0
1764 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) | Assistant Engineer | je1 | VCH/000612/2021-2022 | 281/PFMS | 08/10/2021 | 0 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 59.73 | 0 | 0
1765 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection(Part) including supply of 15mm dia PVC pipe of average length of 15mm,10mm dia Gun-Metal Ferrule,Saddle piece(as required size) 15mm dia cock etc. all complete from Fatepur W/S Scheme in Nadia District under Nadia Division P.H.E.Dte. | Assistant Engineer |  | ORD/000219/2020-2021 | 4081/ND | 31/12/2020 | 90 | MONDAL PRECISION PRIVATE LIMITED | 96.54 | 160.93 | 0
1766 | Nadia Division | Ranaghat Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Executive Engineer, Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000749/2021-2022 | 286/Kly SD-I | 31/03/2022 | 365 | ARROWTOWN DEALERS PVT. LTD | 4.8 | 2.91 | 0
1767 | Nadia Division | Ranaghat Sub-Division | EXTENSION OF PIPE LINE FOR FHTC KALIGANJ, PART-1 Z-IV | Assistant Engineer |  | VCH/000374/2021-2022 | 174/FHTC | 10/09/2021 | 0 | UMWELT ENGINEERS PVT LTD | 4.71 | 0 | 0
1768 | Nadia Division | Ranaghat Sub-Division | EXTENSION OF PIPE LINE FOR FHTC KALIGANJ, PART-1 Z-IV | Assistant Engineer |  | VCH/000375/2021-2022 | 174/FHTC | 10/09/2021 | 0 | UMWELT ENGINEERS PVT LTD | 4.58 | 0 | 0
1769 | Nadia Division | Ranaghat Sub-Division | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PIPE G.I/PVC PIPE OF AVERAGE LENGTH OF 10MM DIA GUN-METAL FERRULE, SADDLE PIECE 15MM DIA BIB COCK ETC AT SUBERNA BIHAR W/S SCHEME PART-B | Assistant Engineer |  | VCH/000963/2021-2022 | 473/DW | 07/02/2022 | 0 | ROY CONSTRUCTION | 0.73 | 0 | 0
1770 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-V within Kaliganj block(Phase-A) in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000182/2020-2021 | 3588/ND | 08/12/2020 | 90 | TARUN KUMAR BHATTACHARYA | 96.83 | 178.16 | 0
1771 | Nadia Division | Debgram Sub-Division | Hiring Diesel Luxury Car on daily basis (for 12 months from 01.02.2021 to 31.01.2022) for the office use of the Assistant Engineer, Kalyani Sub Division II, P.H.E. Dte | Assistant Engineer |  | ORD/000463/2020-2021 | 198 / KLYSD -II | 29/01/2021 | 365 | SUMAN CHAKRABORTY | 4.8 | 0.91 | 0
1772 | Nadia Division | Debgram Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Executive Engineer, Nadia Division, PHE Dte. (Period- 01/04/2023 to 30/09/2023) | Assistant Engineer |  | ORD/000548/2022-2023 | 465/ Kly SD-1 | 31/03/2023 | 183 | ARROWTOWN DEALERS PVT. LTD | 2.4 | 0.54 | 0
1773 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000028/2021-2022 | 448/ND | 31/01/2022 | 0 | Resource Division | 1.26 | 0 | 0
1774 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000059/2021-2022 | 812/ND | 18/02/2022 | 0 | Resource Division | 7.7 | 0 | 0
1775 | Nadia Division | Debgram Sub-Division | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE | Assistant Engineer |  | VCH/000309/2021-2022 | 139/FHTC | 17/08/2021 | 0 | LEMNISCATE | 0.47 | 0 | 0
1776 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PIPE G.I/PVC PIPE OF AVERAGE LENGTH OF 10MM DIA GUN-METAL FERRULE, SADDLE PIECE 15MM DIA BIB COCK ETC AT SUBERNA BIHAR W/S SCHEME PART-B | Assistant Engineer |  | VCH/000963/2021-2022 | 473/DW | 07/02/2022 | 0 | ROY CONSTRUCTION | 0.73 | 0 | 0
1777 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Bhanderkhola W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I, Retrofitting) | Assistant Engineer |  | ORD/000237/2020-2021 | 46/ND | 06/01/2021 | 90 | S.S. ENTERPRISE | 93.24 | 6.85 | 100
1778 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000099/2021-2022 | 1017/ND | 03/03/2022 | 0 | Resource Division | 5.55 | 0 | 0
1779 | Nadia Division | Krishnanagar Sub-Division | 1ST RA FOR PROVIDING FHTC BHANDERKHOLA W/S SCHEME, PHASE-1, RETROFITTING. | Assistant Engineer |  | VCH/000198/2021-2022 | 88/PPMS | 15/07/2021 | 0 | S.S. ENTERPRISE | 53.42 | 0 | 0
1780 | Nadia Division | Krishnanagar Sub-Division | Providing Functional House Tap Connection from Bhanderkhola Water Supply Scheme under Jal Swapno Programme (Phase-I) | Assistant Engineer |  | VCH/000468/2021-2022 |  | 04/10/2021 | 0 | S.S. ENTERPRISE | 29.31 | 0 | 0
1781 | Nadia Division | Krishnanagar Sub-Division | Providing Functional House Tap Connection from Bhanderkhola Water Supply Scheme under Jal Swapno Programme (Phase-I) | Assistant Engineer |  | VCH/000607/2021-2022 | 265/PFMS | 08/10/2021 | 0 | S.S ENTERPRISE | 29.31 | 0 | 0
1782 | Nadia Division | Krishnanagar Sub-Division | Providing Functional House Tap Connection from Bhanderkhola Water Supply Scheme under Jal Swapno Programme (Phase-I). | Assistant Engineer |  | VCH/000992/2020-2021 |  | 24/03/2021 | 0 | S.S. ENTERPRISE | 53.42 | 0 | 0
1783 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall and pathway and Toilet at 2nd, 3rd and 4th Tubewell site of Aranghata and 3rd site of Debogram water supply Scheme in Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. Under JJM. (Sl. No. 09) | Assistant Engineer-II | Junior Engineer-III | ORD/000029/2025-2026 | 155/NAD-I | 28/04/2025 | 60 | GOUTAM DEY | 34.34 | 0 | 0
1784 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000093/2021-2022 | 1541/NAD-I | 06/12/2021 | 90 | JOY HIND TUBE WELLS | 123.89 | 122.54 | 100
1785 | Nadia Arsenic Division I | Nadia Arsenic Division I | Work for revamping / upgradation of the hydraulic parameters at Head work site to Shibnarayanpur and allied works in reference to Aranghata Zone-I water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (2nd Call) [Sl. No. 04] | Assistant Engineer-II | Junior Engineer-III | ORD/000106/2025-2026 | 720/NAD-I | 29/07/2025 | 60 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 49.04 | 0 | 0
1786 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) at Patkabari, Hatibanda and Uttor Bishnupur under Jaldhara Jal Swapna from Arranghata Zone-I PWSS Part-III at Ranaghat-II Block by retrofitting under under Nadia Arsenic Division- I, P.H.E Dte. (Sl. No. 14) | Assistant Engineer-II | Junior Engineer-III | ORD/000130/2022-2023 | 3044/NAD-I | 09/11/2022 | 30 | M/S R.K. ENTERPRISE | 32.39 | 28.34 | 100
1787 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet, Pathway OHR Repair and other allied work in connection with Augmentation of Arranghata Zone-I water supply Scheme within Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. (sl.no.16) | Assistant Engineer-II | Junior Engineer-III | ORD/000244/2022-2023 | 569/NAD-I | 16/03/2023 | 60 | REAL TIME | 59.28 | 55.62 | 100
1788 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Bhayna Zone-I Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000117/2021-2022 | 10/NAD-I | 05/01/2022 | 90 | TARUN KUMAR BHATTACHARYA | 202.09 | 201.23 | 100
1789 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Bhayna Zone-I water supply scheme in Hanskhali Block in Nadia District under JJM under Nadia Arsenic Division-I , PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000170/2023-2024 | 427/AE-I/NAD-I | 20/09/2023 | 30 | PALCON | 1.5 | 0 | 100
1790 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000017/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0
1791 | Nadia Arsenic Division I | Nadia Arsenic Division I | Surging of exisiting Tube Well Situated at 2nd Tube Well Site of Saguna Water Supply Scheme in connection with Jal Jeevan Mission under Santipur Block to increase the yield of the tube well under Nadia Arsenic Division-I P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000012/2024-2025 | 192/AE-I/NAD-I | 21/06/2024 | 15 | APURBA MANDAL | 0.64 | 0 | 0
1792 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-II at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000056/2021-2022 | 1413/NAD-I | 08/11/2021 | 60 | M/S TARAK CHANDRA PAUL | 79.19 | 79.14 | 100
1793 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bagakhali Zone-I W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte |  |  | ORD/000022/2020-2021 | 1064/NACD-II | 25/09/2020 | 15 | DEBASISH DEY | 5 | 0 | 0
1794 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Matiary W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000011/2020-2021 | 1062/NACD-II | 25/09/2020 | 15 | ROY CONSTRUCTION | 4.99 | 0 | 0
1795 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Boalia at Santipur Block by retrofitting of Ground Water based PWSS for Boalia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000090/2021-2022 | 1538/NAD-I | 06/12/2021 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 430.7 | 432.06 | 100
1796 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-II | RTOR000016/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0
1797 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Itaberia at Hanskhali Block by retrofitting of Ground Water based PWSS for Itaberia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000052/2021-2022 | 1409/NAD-I | 08/11/2021 | 60 | CHANDAN ROY | 89.54 | 89.4 | 100
1798 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey, Design Drawing for Augmentation of ITABERIA Water Supply Scheme in Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000266/2023-2024 | 494/AE-II/NAD-I | 24/11/2023 | 7 | SUMAN CHAKRABORTY | 2.83 | 0 | 100
1799 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site of Joypur and Mamjoani Water Supply Scheme in connection with Duttaphulia Zone-I under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000004/2025-2026 | 39/NAD-I | 07/04/2025 | 242 | REAL TIME | 39.28 | 0 | 50
1800 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Joypur Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000057/2021-2022 | 1415/NAD-I | 08/11/2021 | 60 | M/S S.CHOUDHURY | 84.96 | 84.62 | 100
1801 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Ghetugachi G.P for Surface water based P.W.S.S for Chakdah ( Part ) in connection with providing FHTC at Barberia ( Zone- VIII ) Part- II under JJM within Chakdah Block under Nadia Arsenic Division-I , PHE Dte. (Sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000091/2023-2024 | 1685/NAD-I | 12/07/2023 | 21 | TAPAS GHOSH | 22.22 | 20.79 | 100
1802 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000119/2021-2022 | 12/NAD-I | 05/01/2022 | 90 | UMWELT ENGINEER PVT. LTD. | 299.45 | 89.42 | 98
1803 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 800 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Barberia Zone-VIII under Surface W/S Scheme of Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.05) | Assistant Engineer-II | Junior Engineer-III | ORD/000123/2022-2023 | 1385/NAD-I | 12/08/2022 | 45 | TARUN KUMAR BHATTACHARYA | 32.36 | 32.3 | 100
1804 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Mukundupur of Balagarichar W/S Scheme and Dakshin Panchpota, Kadambagachi of Barberia W/S Scheme in connection with providing FHTC Zone-VIII (Barberia) Part-II under Barberia W/S Scheme under Jal Jeevan Mission under Chakdah (Part) W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.10) | Assistant Engineer-II | Junior Engineer-III | ORD/000189/2023-2024 | 2154/NAD-I | 08/09/2023 | 764 | SUMAN CHAKRABORTY | 91.29 | 54.84 | 100
1805 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection in between outlet pipe of OHR and delivery main at different H/W site in Chakdah SurfaceWater Based PWSS at Chakdah Block under JJM under Nadia Arsenic Division-I,PHE Dte. (sl.15) | Assistant Engineer-II | Junior Engineer-III | ORD/000259/2022-2023 | 826/NAD-I | 31/03/2023 | 45 | BIPLAB GUHA | 39.73 | 20.78 | 58
1806 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Paschim Sambhupur mouza (JI No 133) under Jal Jeevan Mission (JJM) for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000001/2023-2024 | 163/AE-I/NAD-I | 10/04/2023 | 15 | GANGULY ENTERPRISE | 0.97 | 0.97 | 0
1807 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Sibpur mouza (JI No 134) under Jal Jeevan Mission (JJM) for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground water based PWSS for parniamatpur Water Supply Scheme under Nadia Arsenic division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000002/2023-2024 | 164/AE-I/NAD-I | 10/04/2023 | 15 | MS ENTERPRISE | 0.97 | 0.97 | 100
1808 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Dakshin Haradham mouza (JI No 137) under Jal Jeevan Mission (JJM) for parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000003/2023-2024 | 165/AE-I/NAD-I | 11/04/2023 | 15 | MS ENTERPRISE | 0.97 | 0.97 | 0
1809 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur, Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000064/2021-2022 | 1418/NAD-I | 08/11/2021 | 60 | TAPU SAHA | 69.94 | 65.19 | 99
1810 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Rabonbor mouza near Sampa Biswas house and near Abodh Halder house under Parniamatpur Water Supply Scheme under Ranaghat-I Block under Providing FHTC under Jal Jeevan Mission (JJM) for Parniamatpur Phase-II under Nadia Arsenic Division-I, P.H.E. Dte. (SL No-2) | Assistant Engineer-I | Junior Engineer-I | ORD/000188/2022-2023 | 85/AE-1/NAD-I | 06/02/2023 | 15 | GANGULY ENTERPRISE | 4.83 | 4.51 | 100
1811 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Haradham village under Parniamatpur W/S Scheme under Ranaghat-I Block under Providing FHTC under Jal Jeevan Mission (JJM) for Parniamatpur Phase-I under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2022-2023 | 84/AE-1/NAD-I | 03/02/2023 | 15 | AURGHA BHATTACHARYA | 2.05 | 1.89 | 100
1812 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-I | RTOR000010/2021-2022 | 143/NAD-I | 28/01/2022 | 0 | Resource Division | 0.8 | 0 | 0
1813 | Nadia Arsenic Division I | Nadia Arsenic Division I | Balance work for revamping/upgradation of the hydraulic parameters at Hatisala and Goalsalua mouzas in reference to Goalsalua mouzas in reference to Goalsalua W/S Scheme under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 03) | Assistant Engineer-II | Junior Engineer-III | ORD/000036/2025-2026 | 170/NAD-I | 29/04/2025 | 60 | PAPAN ROY | 44.03 | 0 | 0
1814 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Goalsalua Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Goalsalua Zone-I under JJM.(sl.no.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000041/2023-2024 | 1123 / NAD-I | 27/04/2023 | 15 | MANAJIT BISWAS | 13.03 | 0 | 100
1815 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua, Zone-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Goalsalua Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000046/2021-2022 | 1403/NAD-I | 08/11/2021 | 45 | BIDYUT KUMAR | 53.89 | 53.63 | 100
1816 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall at H/W site of Goalsalua, Zone-I Water Supply Scheme under Nadia Arsenic Division-I,P.H.E. Dte. Length of Boundary wall - 208 metre. | Assistant Engineer-II | Junior Engineer-III | ORD/000131/2021-2022 | 72/NAD-I | 17/01/2022 | 30 | NISHITH BANERJEE | 19.68 | 17.09 | 100
1817 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing & other allied works near Bankim Nagar station (BNCA to PNCB) in between Mast No - 77/24 and 77/26 in the district of Nadia to provide FHTC at Kesaipur under Goalsalua PWSS under Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. (2nd Call) [Sl. No. 03] | Assistant Engineer-II | Junior Engineer-III | ORD/000141/2025-2026 | 1042/NAD-I | 25/09/2025 | 90 | SUMAN CHAKRABORTY | 39.44 | 0 | 0
1818 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of additional pipeline for providing FHTC (Functional Household Tap Connection)at Salua Gatepara & pipeline connection with Manifold under JJM at Ranaghat-II Block of Ground Water Based PWSS for Goalsalua Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000165/2024-2025 | 327/AE-II/NAD-I | 09/12/2024 | 15 | GOUTAM DEY | 4 | 0 | 0
1819 | Nadia Division | Krishnanagar Sub-Division | Additional Laying of UPVC Pipeline and providing FHTC including supplying, laying, fitting, fixing of 15 mm NB PVC pipe with all necessary specials, saddle piece etc.in connection to the Augmentation of Ground Based piped water supply scheme at Bablari-Dewanganj to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000016/2023-2024 | 1847/ND | 26/04/2023 | 60 | A.K.ADHIKARY | 15.77 | 0 | 95
1820 | Nadia Division | Krishnanagar Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
1821 | Nadia Division | Krishnanagar Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 250 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bablari Dewanganj Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000396/2023-2024 | 5125/ND | 17/11/2023 | 90 | SANJIB DEY | 24.91 | 0 | 98
1822 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bablari Dewanganj to accommodate FHTC within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000600/2021-2022 | 338/ND | 25/01/2022 | 90 | JOY HIND TUBEWELL'S | 156.61 | 62.98 | 80
1823 | Nadia Division | Krishnanagar Sub-Division | Providig FHTC at leftout household in connection to the Augmentation of Ground Based piped water supply scheme at Bablari Dewanganj to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000721/2023-2024 | 1372/ND | 28/02/2024 | 315 | A.K.ADHIKARY | 21.74 | 0 | 70
1824 | Nadia Division | Krishnanagar Sub-Division | Conversion of IEP to AIRP of capacity 46 Cu.m/hr at Bablari Dewanganj Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000794/2023-2024 | 1906/ND | 15/03/2024 | 680 | DEBASIS SAMADDAR | 104.21 | 0 | 70
1825 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000037/2022-2023 | 4293/ND | 29/09/2022 | 0 | Resource Division | 4.16 | 0 | 0
1826 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. | Assistant Engineer | Junior Engineer 2 | VCH/001066/2021-2022 | 629/PFMS | 16/03/2022 | 0 | UMWELT ENGINEERS PVT LTD | 3.23 | 0 | 0
1827 | Eastern Mechanical | Krishnanagar Sub-Division | Supply delivery & installation of submersible P/m alongwith allaied electrical mechanical works voltage stabilizer and automatic chlorinator etc. rejuvenation to Accomodate FHTC at P.h no.I & II under Bablari Dewanganj w/s scheme Block--Nabawdip Dist- Nadia | Assistant Engineer | Junior Engineer 2 | ORD/002729/2022-2023 | 6183/EMD | 14/11/2022 | 30 | M.S. ENTERPRISE | 15.63 | 14.89 | 75
1828 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001771/2022-2023 | 1121/EMD | 16/03/2023 | 30 | M.S. ENTERPRISE | 65.68 | 21.17 | 90
1829 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Helenchi Zone - III H/W and 2nd Pump house site with Reinforced Barbed Tape , Plaster and other allied works. Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000017/2024-2025 | 139/AE-II/NACD-II | 11/06/2024 | 211 | BASUDEB SAHA | 3.56 | 0 | 100
1830 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000122/2024-2025 | 820/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.16 | 0 | 100
1831 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-III W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000124/2021-2022 | 857/NACD-II | 08/11/2021 | 45 | S.K. CONSTRUCTION | 95.18 | 95.18 | 100
1832 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Helenchi Zone - III HeadWork site in Krishnaganj Block with Overhead Reservoir with Plaster,Painting and other allied works under Nadia Arsenic Division-II,P.H.E.Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000236/2024-2025 | 1377/NACD-II | 04/10/2024 | 119 | TAPAN SAHA | 7.56 | 0 | 100
1833 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Helenchi Zone-III Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000243/2023-2024 | 19/AE-II/NACD-II | 15/02/2024 | 15 | M/S SREE KRISHNA ENTERPRISE. | 0.97 | 0 | 0
1834 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Arsenic cum Iron treatment Plant of Helenchi Z-III PWSS (Capacity- 49 m3/hr) and ancillary works of Krishnaganj Block under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000256/2023-2024 | 233/NACD-II | 21/02/2024 | 60 | B.M. ENGINEERING & CONSTRUCTION | 96.32 | 0 | 5
1835 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Helenchi Zone-III W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000299/2022-2023 | 1197/NACD-II | 23/12/2022 | 15 | SUMIT GHOSH | 1.61 | 0 | 100
1836 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD, dedicated line and Distribution network for new FHTC at Taldaha Piped Water Supply Scheme and laying distribution network for FHTC and Repairing of Top Dome and related work for 250 cum RCC elevated reservoir at Helenchi Zone- III in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000324/2024-2025 | 1571/NACD-II | 06/12/2024 | 270 | BIDYUT KUMAR | 105.92 | 0 | 40
1837 | Eastern Mechanical | Nadia Arsenic Civil Division II | Rejuvenation of Helenchi Zone-II W/S scheme in Krishnganj Block of Nadia under EMSD-III PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000921/2021-2022 | 472/ EMD | 16/03/2022 | 30 | BINAPANI ENTERPRISE | 5.38 | 5.38 | 100
1838 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001771/2022-2023 | 1121/EMD | 16/03/2023 | 30 | M.S. ENTERPRISE | 65.68 | 0 | 90
1839 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Retrofitting of OHR, AIRP of Helenchi Zone-II as well as providing of FHTC as per consultation with ISA under Krishnaganj BLock in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000130/2023-2024 | 1213/NACD-II | 17/10/2023 | 60 | M/S FREEDOM CONSTRUCTION | 93.16 | 0 | 90
1840 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000132/2021-2022 | 871/NACD-II | 08/11/2021 | 45 | JOY HIND TUBEWELLS | 82.99 | 82.99 | 100
1841 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Arsenic cum Iron treatment Plant of Helenchi Z-II PWSS (Capacity- 39 m3/hr) and ancillary works of Krishnaganj Block under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000189/2023-2024 | 36/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 120.13 | 0 | 100
1842 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Helenchi ZoneII Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000252/2021-2022 | 106/NACD-II | 10/02/2022 | 45 | BASUDEB SAHA | 5.37 | 5.21 | 100
1843 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-I W/s Scheme (Vill- Krishnapur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000277/2021-2022 | 125/NACD-II | 21/02/2022 | 90 | A.P. POWER & CONCRETE | 105.67 | 0 | 100
1844 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Special repairing for house connection and relaying of UPVC pipe line at Helenchi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000295/2021-2022 | 59/AE-II/NACD-II | 23/02/2022 | 15 | VAI ENTERPRISE | 4.97 | 4.97 | 100
1845 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Helenchi Zone-II W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000298/2022-2023 | 1196/NACD-II | 23/12/2022 | 15 | BABLU MALLICK | 0.85 | 0.83 | 100
1846 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Helanchi zone-II PWSS in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000303/2024-2025 | 355/AE-II/NACD-II | 19/11/2024 | 7 | MAKALI ENGINEERING CORPORATION | 0.98 | 0 | 100
1847 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Functional House Hold Tap Connection for left out Household regarding Har Ghar Jal Certification including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Vill- Khatura) Helenchi Zone-II W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000349/2022-2023 | 149/NACD-II | 17/01/2023 | 20 | ZOOM CONSTRUCTION & INTERIO | 4.23 | 0 | 100
1848 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work with Reinforced Barbed Tape ,Overhead Reservoir Plaster , Painting and other allied works at Helenchi Zone - II Headwork site and 2nd Pump house site under Helenchi Zone-II Piped Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000389/2024-2025 | 08/NACD-II | 06/01/2025 | 60 | M/S INDUSTRIAL CONSTRUCTION | 9.66 | 0 | 100
1849 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000004/2023-2024 | 76/NACD-II | 15/01/2024 | 0 | Resource Division | 5.36 | 0 | 0
1850 | Nadia Division | RWS Nadia Sub-Division | providing house connection including supply of 15mm dia G.I/ PVC pipe of average length of 15 mtr, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete at Muktadaha Zone - I W/S scheme under Nadia Division P.H.Engineering Dte. (Part-A) | Assistant Engineer |  | ORD/000153/2021-2022 | 927/PH | 10/08/2021 | 15 | B.M ENTERPRISE | 1.38 | 1.26 | 100
1851 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Muktadaha zone - I W/S scheme under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000198/2021-2022 | 5143/ND | 15/09/2021 | 75 | M/S NIBHAS SINHA | 68.32 | 42.45 | 100
1852 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000073/2021-2022 | 806/ND | 18/02/2022 | 0 | Resource Division | 4.94 | 0 | 0
1853 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000106/2021-2022 | 1031/ND | 03/03/2022 | 0 | Resource Division | 8.59 | 0 | 0
1854 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Muktadaha Zone-I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | Assistant Engineer |  | VCH/000495/2022-2023 | 82/PFMS | 13/07/2022 | 0 | SANJIB DEY | 1.8 | 0 | 0
1855 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Muktadaha Zone-I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | Assistant Engineer |  | VCH/001020/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 4.58 | 0 | 0
1856 | Nadia Division | RWS Nadia Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir, Pump House, Boundary Wall and Construction of Service Road for Badlangi Padmamala Zone-I Water Supply Scheme under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000445/2023-2024 | 6113/ND | 21/12/2023 | 360 | CHOWDHURY & CO | 27.25 | 0 | 90
1857 | Nadia Division | RWS Nadia Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site of Badlangi Padmamala Zone-I Water Supply scheme under RWS Sub Division under Nadia Division-,P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000672/2024-2025 | 7451/ND | 20/12/2024 | 270 | ROY ASSOCIATES | 85.97 | 0 | 25
1858 | Nadia Division | RWS Nadia Sub-Division | Collection of Household data through mobile app for FHTC Connection (Phase-VI), under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000698/2023-2024 | 222/KLYSD-I | 09/02/2024 | 182 | HORIZEN | 4.85 | 0 | 100
1859 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution system including specials & valves,Pipe supporting structure all complete based on actual estimate & providing FHTC for Badlangi Padmamala Zone-I Water Supply Scheme in Nadia District under Nadia Division.. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000705/2021-2022 | 954/ND | 25/02/2022 | 90 | APURBA MANDAL | 239.05 | 192.16 | 88
1860 | Nadia Division | RWS Nadia Sub-Division | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Badlangi Padmamala Zone-I PWSS within Chapra Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000727/2023-2024 | 1305/ND | 23/02/2024 | 180 | S.S. ENTERPRISE | 53.77 | 0 | 100
1861 | Nadia Division | RWS Nadia Sub-Division | Conversion of IEP to AIRP of capacity 62 Cu.m/hr at Badlangi Padmamala Zone-I Water Supply Scheme within Chapra block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000800/2023-2024 | 1912/ND | 15/03/2024 | 180 | B.M. ENGINEERING & CONSTRUCTION | 174.54 | 0 | 35
1862 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | RTOR000047/2022-2023 | 4297/ND | 29/09/2022 | 0 | Resource Division | 0.01 | 0 | 0
1863 | Nadia Division | RWS Nadia Sub-Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | VCH/001054/2021-2022 | 612/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.69 | 0 | 0
1864 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I & II Z-I under Bayra W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/001914/2022-2023 | 6186 EMD | 14/08/2022 | 30 | MA ANNAPURNA ENTERPRISE | 5.47 | 0 | 100
1865 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator etc. Rejuvention to accommodate FHTC) at Z-I under Badelangi Padmamala W/S Scheme Block Chapra under District of Nadia) | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/002001/2022-2023 | 6186 / EMD | 14/08/2022 | 30 | MA ANNAPURNA ENTERPRISE | 5.47 | 5.47 | 0
1866 | Nadia Division | Krishnanagar Sub-Division | Construction of 2 nos Pump House (3.6mtr. X 3.0 mtr.) at 1st & 2nd T/W site for Gobrapota water supply scheme under Krishnagar Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000009/2024-2025 | 3263/ND | 10/06/2024 | 45 | M/S RAJESH CONSTRUCTION | 12.17 | 0 | 0
1867 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete and Construction Of 350 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (With Pile Foundation), Pipe Connection And Cost Of Pipes, Specials, Soil investigation for the work of construction of 350 cum OHR staging height 20 mtr., Construction Of 1 (One) No. Pump House (4.88m X 3.66m) Including Sanitary Arrangement And Construction Of Boundary Wall for Augmentation of Ground Based Water Supply Scheme at GOBRAPOTA to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000199/2023-2024 | 3509/ND | 10/08/2023 | 366 | M/S GHOSH CONSTRUCTION, SUKUL ROAD, P.O-KRISHNAGAR, DIST.NADIA, PIN-741101, WB | 587.44 | 0 | 0
1868 | Nadia Division | Krishnanagar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
1869 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000152/2022-2023 | 122/ND | 05/01/2023 | 0 | Resource Division | 99.77 | 0 | 0
1870 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000153/2023-2024 | 264/ND | 11/01/2024 | 0 | Resource Division | 17.22 | 0 | 0
1871 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/000293/2022-2023 | 15/PFMS | 11/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.8 | 0 | 0
1872 | Central Drilling | Krishnanagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Gobrapota W/S Scheme (TW-I) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000134/2023-2024 | 1658/CDD | 17/10/2023 | 30 | MENAKA ENTERPRISE | 18.88 | 0 | 0
1873 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under Gobrapota Naldaha W/S Scheme, Block- Krishnagar-I , Dist. - Nadia. NIET No. 33 of EE/EMD of 2022-23 (Sl. No.- 10) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001919/2022-2023 | 1175/EMD | 21/03/2023 | 30 | SWAPAN KUMAR BHANJA | 18.62 | 14.2 | 75
1874 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Pathway and all repair works at 2nd T/W Site and all repair works at H/W site of Saguna under Nadia Arsenic Division-I, PHE Dte. ( Sl.no 11) | Assistant Engineer-I | Junior Engineer-I | ORD/000053/2022-2023 | 1592 / NAD-I | 06/09/2022 | 45 | PAPAN ROY | 11.31 | 8.33 | 85
1875 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting pipeline works for providing FHTC (Functional Household Tap Connection) at Aluipara & Srirampur para under JJM at Shantipur Block of Ground Water Based PWSS for Saguna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer-I | Junior Engineer-I | ORD/000057/2024-2025 | 1543/NAD-I | 23/09/2024 | 405 | TAPAS GHOSH | 10.69 | 0 | 80
1876 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 350 cum capacity Over Head Reservoir and other allied works at Paschim Noapara W/S Scheme in Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte.(Sl.no.07) | Assistant Engineer-I | Junior Engineer-I | ORD/000069/2022-2023 | 1443/NAD-I | 17/09/2022 | 45 | MONDAL ENTERPRISE | 12.83 | 11.65 | 100
1877 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 450 cum capacity Over Head Reservoir and other allied works at Saguna WS Scheme in Santipur Block under NAD I PHE Dte (Sl.no.04) | Assistant Engineer-I | Junior Engineer-I | ORD/000105/2022-2023 | 2049 / NAD-I | 21/10/2022 | 45 | M/S ARATI ENTERPRISE | 14.01 | 13.2 | 100
1878 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Pathway and all repair works at 2nd T/W site and all repair works at H/W site of Paschim Noapara W/S Scheme under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.02) | Assistant Engineer-I | Junior Engineer-I | ORD/000111/2022-2023 | 2009/NAD-I | 19/10/2022 | 30 | J & T ENTERPRISE | 6.93 | 6.73 | 100
1879 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Saguna Part-III at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 12) | Assistant Engineer-I | Junior Engineer-I | ORD/000169/2021-2022 | 437/NAD-I | 07/03/2022 | 60 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 63.41 | 52.13 | 100
1880 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Paschim Noapara, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000180/2021-2022 | 517/NAD-I | 28/03/2022 | 60 | GHOSH BROTHERS | 171.71 | 106.69 | 100
1881 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Hijuli, Ghoshpara, Aluipara & adjacent areas of Shantipur Block by retrofitting of Ground Water Based PWSS for Saguna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000273/2023-2024 | 2744/NAD-I | 08/12/2023 | 705 | DEBASIS SAMADDAR | 57.4 | 0 | 70
1882 | Nadia Arsenic Division I | Nadia Arsenic Division I | Pipeline connection with Manifold to dedicated line under Jal Jeevan Mission (JJM) at Shantipur Block under Ground Water based PWSS for Saguna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000302/2023-2024 | 95/AE-I/NAD-I | 27/02/2024 | 15 | ROY ASSOCIATES | 2.89 | 0 | 100
1883 | Nadia Division | Debgram Sub-Division | Filling fine sand over upvc pipeline for road restoration work at nimtala juranpur road(both side of road) in connection with augmentation of surface water based w/s scheme for Arsenic affected areas of Nadia district( Northern sector part-I) under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000003/2024-2025 | 918KlySD-I | 07/06/2024 | 15 | UMWELT ENGINEER PVT LTD | 13.46 | 0 | 100
1884 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at Sherpur Village zone-VI Phase- C, Part- I , Surface water based Water Supply Scheme, Nadia Northern Sector , Kaliganj Block. | Assistant Engineer |  | ORD/000060/2022-2023 | 175/A/DSD | 18/04/2022 | 30 | BALAJEE ENTERPRISE | 1.54 | 1.52 | 100
1885 | Nadia Division | Debgram Sub-Division | Providing Functional Household Tap Connection (FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-VI within Kaliganj Block(Phase-C) | Assistant Engineer |  | ORD/000356/2021-2022 | 7058/ND | 06/12/2021 | 90 | BALAJEE ENTERPRISE | 176.9 | 169.22 | 0
1886 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at zone-VI Phase- C, Part- I , Surface water based Water Supply Scheme, Nadia Northern Sector , Kaliganj Block. | Assistant Engineer |  | ORD/000816/2021-2022 | 48/DSD | 07/02/2022 | 15 | BALAJEE ENTERPRISE | 4.95 | 4.93 | 100
1887 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000039/2021-2022 | 429/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
1888 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000082/2022-2023 | 4309/ND | 29/09/2022 | 0 | Resource Division | 24.88 | 0 | 0
1889 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete by augmentation of Purba Khamarsimulia Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000099/2022-2023 | 3404/ND | 01/08/2022 | 724 | B.M. ENGINEERING & CONSTRUCTION | 330.45 | 0 | 92
1890 | Nadia Division | Ranaghat Sub-Division | Supplying and laying of distribution and rising main for Augmentation of Ground water based water supply scheme of Purba Khamarsimulia under Hanskhali Block under Ranaghat Sub-Division under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000099/2025-2026 | 2264/ND | 15/05/2025 | 90 | B.M. ENGINEERING & CONSTRUCTION | 75.28 | 0 | 0
1891 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
1892 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Purba Khamarsimulia under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000391/2024-2025 | 1427/RSD | 19/11/2024 | 45 | MANARAMA ENTERPRISE | 2.15 | 0 | 100
1893 | Nadia Division | Ranaghat Sub-Division | Supplying and laying of distribution system including providing Functional Household Tap Connection (FHTC) for Augmentation of Purbakhamar Simulia Piped Water Supply Scheme under Ranaghat Sub-Division, under Nadia Division, PHE Dte.. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000417/2023-2024 | 5224/ND | 24/11/2023 | 755 | B.M. ENGINEERING & CONSTRUCTION | 215.24 | 0 | 75
1894 | Nadia Division | Ranaghat Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Purba Khamarsimulia PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 105.00 Cu.m/hr | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000469/2023-2024 | 136/ND | 09/01/2024 | 90 | M/S R.K.ENTERPRISE | 99.27 | 0 | 0
1895 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000029/2023-2024 | 1879/ND | 26/04/2023 | 0 | Resource Division | 13.4 | 0 | 0
1896 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000061/2022-2023 | 4320/ND | 29/09/2022 | 0 | Resource Division | 0.02 | 0 | 0
1897 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000097/2023-2024 | 2584/ND | 13/06/2023 | 0 | Resource Division | 15.12 | 0 | 0
1898 | Nadia Division | Ranaghat Sub-Division | Providing FHTC by Augmentation of Ground Water Based Piped Water Supply Scheme for PURBA KHAMAR SIMULIA Block: Hanskhali, Dist: Nadia | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/000285/2022-2023 | 10/PFMS | 11/05/2022 | 0 | HORIZEN | 2.89 | 0 | 0
1899 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I , II under Purba Khamar Simulia ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000016/2024-2025 | 1308/EMD | 09/05/2024 | 30 | SHIVAM ENTERPRISE | 23.6 | 0 | 100
1900 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at PURBA KHAMAR SIMULIA W/S Scheme Block- Hanskhali under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10422] | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000146/2025-2026 | 1147/EMD | 04/06/2025 | 90 | M.S. ENTERPRISE | 51.04 | 0 | 0
1901 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Madhabpur Water Supply Scheme in Chapra Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000071/2023-2024 | 326/1/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.61 | 0 | 100
1902 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Madhabpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000136/2021-2022 | 864/NACD-II | 08/11/2021 | 45 | H. I. ENTERPRISE | 56.74 | 56.72 | 100
1903 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Madhabpur W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000157/2023-2024 | 523/AE-I/NACD-II | 18/12/2023 | 15 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 0.96 | 0 | 100
1904 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Raising the height of the Boundary wall with Barbed Weir fencing with angle and also fabrication of new Grill Gate for protection work at Madhabpur Water Supply Scheme H/W site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000177/2022-2023 | 477/NACD-II | 27/07/2022 | 45 | SAMAR ENTERPRISE | 4.99 | 4.72 | 100
1905 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Madhabpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000187/2020-2021 | 281/NACD-II | 22/02/2021 | 21 | JOY HIND TUBEWELLS | 60 | 0 | 100
1906 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Madhabpur W/S Scheme Village:- Ichhapur under Habitation of Ichhapur,Bat Tala and Bagdipara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000236/2023-2024 | 637/AE-I/NACD-II | 12/02/2024 | 15 | SUJAUDDIN SHAIKH | 0.97 | 0 | 100
1907 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Madhabpur W/S Scheme Village:- Ichhapur under Habitation of Amtalapara,purbapara and bakultala in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000237/2023-2024 | 638/AE-I/NACD-II | 12/02/2024 | 15 | PRADUT GHOSH | 0.96 | 0 | 100
1908 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Madhabpur W/S Scheme Village:- Ichhapur under Habitation of Baroyaritala in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000241/2023-2024 | 639/AE-I/NACD-II | 12/02/2024 | 15 | RAJIB DUTTA | 0.96 | 0 | 100
1909 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Madhabpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000263/2020-2021 | 274/NACD-II | 22/02/2021 | 21 | JOY HIND TUBEWELLS | 60.6 | 0 | 100
1910 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 2 nos. 300 mm X 200 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at new proposed site of Gongra Zone-I and Zone-II in Chapra Block under Gongra Public Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000317/2024-2025 | 1527/NACD-II | 27/11/2024 | 270 | SANDIP BISWAS | 21.68 | 0 | 55
1911 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Madhabpur W/S Scheme village:- Patia under Habitation of Halder Para and Uttar Para in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000353/2024-2025 | 1096/AE-I/NACD-II | 31/12/2024 | 90 | SUJAUDDIN SHAIKH | 0.94 | 0 | 100
1912 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Madhabpur W/S Scheme village:- Patia under Habitation of Purba Para and Biswas Para in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000354/2024-2025 | 1097/AE-I/NACD-II | 31/12/2024 | 120 | SHYAMAL KANTI GHOSH | 0.97 | 0 | 100
1913 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | OUTSTANDING BILL PAYMENT FOR SUPPLY OF MATERIALS FOR THANAPARA, DAMODARKHALI, MADHABPUR, BALIADANGA AS FRAMED BY RESOURCE DIVISION PHE DTE. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000643/2021-2022 |  | 05/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0
1914 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUPPLY OF MATERIALS FOR THANAPARA,DAMODARKHALI,MADHABPUR AND BALIADANGA W/S. SCHEME UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000646/2021-2022 |  | 07/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0
1915 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Outstanding as framed by Resource Division for supply of materials for augmentation/retrofitting of Thanapara, Damodarkhali & Madhabpur under Nadia Arsenic Civil Division-II, PHE dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000718/2021-2022 | 212, 213, 214 | 18/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 124.39 | 0 | 0
1916 | Eastern Mechanical | Nadia Arsenic Civil Division II | NEW SERVICE CONNECTION CHARGES FOR KARUIGACHHI W/S SCHEME P .H NO I &II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000010/2022-2023 | 2868/EMD | 21/07/2022 | 30 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.24 | 0 | 0
1917 | Eastern Mechanical | Nadia Arsenic Civil Division II | NEW SERVICE CONNECTION FOR KARUIGACHI W/S SCHEME FOR P.H NO 1 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000011/2022-2023 | 2869/EMD | 21/07/2022 | 30 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0
1918 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Headworks) under Karuigachhi W/S Scheme Dist.-Nadia. NIET NO.- 16 of EE/EMD OF 2022-23 (Sl. No.- 03) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000097/2022-2023 | 5011/EMD | 03/11/2022 | 30 | M/S. G.P. ENTERPRISE | 10.13 | 9.13 | 100
1919 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Karuigachhi W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000098/2022-2023 | 5012/EMD | 03/11/2022 | 30 | JAL PRAVAHIKA PVT. LTD. | 10.11 | 0 | 100
1920 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply delivery of PCC Pole MS materials and electrical accessories including stringing and sagging of LTOH line to WBSEDCL for new connectionat PH-II under Karuigachi W/S Scheme. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/002600/2022-2023 | 1395/SD-III | 14/08/2022 | 30 | R.N.S. TRADING | 1.03 | 1.03 | 0
1921 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply delivery of PCC Pole M.s materials and Electrical accessories and installation DTR of HTOH line to WBSEDCL for new service connection at PH-I under Karuigachi W/S Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/002688/2022-2023 | 1227/EMSD-III | 21/10/2022 | 30 | M/S G.P. ENTERPRISE | 5.17 | 5.17 | 10
1922 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service connection bill for KARUIGACHHI PIPED WATER SUPPLY SCHEME | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/001930/2022-2023 | BP-2022-23-28 | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0
1923 | Eastern Mechanical | Nadia Arsenic Civil Division II | New service connection charges bill KARUIGACHHI W/s Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/001931/2022-2023 | BP-2022-23-29 | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.16 | 0 | 0
1924 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Karuigachhi water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000004/2022-2023 | 210/NACD-II | 05/04/2022 | 60 | NIVEDITA CONSTRUCTION | 5.38 | 5.33 | 100
1925 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Bhatgachhi and Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000021/2022-2023 | 246/NACD-II | 19/04/2022 | 60 | JOY HIND TUBEWELLS | 41.88 | 0 | 100
1926 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Karuigachhi water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000032/2022-2023 | 19/AE-I/NACD-II | 13/04/2022 | 60 | NIVEDITA CONSTRUCTION | 2.83 | 2.81 | 100
1927 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Karuigachhi Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000038/2022-2023 | 25/AE-I/NACD-II | 13/04/2022 | 1020 | SURAJIT KUMAR GHOSH | 4.28 | 0 | 90
1928 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Karuigachi Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000039/2023-2024 | 404/AE-I/NACD-II | 08/08/2023 | 15 | SANDIP BISWAS | 0.97 | 0 | 100
1929 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Karuigachhi and adjoining mouzas under Karuigachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000069/2022-2023 | 303/NACD-II | 20/05/2022 | 90 | JOY HIND TUBEWELLS | 152.87 | 0 | 100
1930 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Karuigachhi) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000088/2023-2024 | 917/NACD-II | 01/09/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
1931 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Construction of approch road at Head Works site of Karuigachi Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000131/2024-2025 | 837_AE-I/NACD-II | 01/08/2024 | 15 | SANDIP BISWAS | 0.93 | 0 | 100
1932 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Conversion of IEP to AIRP at Balidanga Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block including other works at Bhatgachhi & Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000137/2024-2025 | 1048/NACD-II | 07/08/2024 | 60 | DEBASIS SAMADDAR | 185.55 | 0 | 0
1933 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Karuigachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000191/2022-2023 | 621/NACD-II | 06/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.96 | 3.96 | 100
1934 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 38 cum/Hour capacity for Karuigachhi Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000211/2024-2025 | 1153/NACD-II | 27/08/2024 | 180 | PUSPA ENTERPRISE | 168.65 | 0 | 0
1935 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Jitpur W/s Scheme, Kanainagar W/s Scheme, Karuigachhi W/s Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000298/2021-2022 | 250/AE-I/NACD-II | 25/02/2022 | 15 | PROSENJIT DAS | 2.44 | 2.44 | 100
1936 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Mrigi W/s Scheme, Panchdara Abhaynagar W/s Scheme, Paninala W/s Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000300/2021-2022 | 252/AE-I/NACD-II | 25/02/2022 | 15 | PROSENJIT DAS | 2.44 | 0 | 100
1937 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Karuigachhi Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000315/2022-2023 | 79/NACD-II | 10/01/2023 | 60 | A.S. CONSTRUCTION | 14.61 | 0 | 85
1938 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Karuigachhi 2nd Tubwell site within Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000338/2022-2023 | 118/NACD-II | 11/01/2023 | 60 | MAYA ENTERPRISE | 4.78 | 4.41 | 85
1939 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Karuigachi) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000355/2023-2024 | 433/NACD-II | 15/03/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
1940 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Construction of approch road at Head Works site of Karuigachi Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000534/2024-2025 | 1165/AE-I/NACD-II | 31/01/2025 | 15 | SANDIP BISWAS | 0.97 | 0 | 100
1941 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | RTOR000006/2022-2023 | 396/NACD-II | 04/07/2022 | 0 | Resource Division | 38.34 | 0 | 0
1942 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000232/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
1943 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000339/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
1944 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-V within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.2) | Assistant Engineer |  | ORD/000465/2020-2021 | 971/ND | 25/02/2021 | 90 | UMWELT ENGINEERS PVT LTD | 97 | 171.23 | 0
1945 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000096/2021-2022 | 818/ND | 18/02/2022 | 0 | Resource Division | 4.12 | 0 | 0
1946 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-A). | Assistant Engineer |  | VCH/001007/2020-2021 |  | 25/03/2021 | 0 | UMWELT ENGINEERS PVT LTD | 59.66 | 0 | 0
1947 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe line and other allied works etc all complete for AUGMENTATION Of GANGNAPUR W/S scheme (for Gangnapur & Korabari Mouza) under Ranaghat Sub Division of Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000108/2022-2023 | 3530/ND | 05/08/2022 | 90 | APURBA MANDAL | 393.18 | 388.5 | 80
1948 | Nadia Division | Ranaghat Sub-Division | Laying of different dia UPVC pipe and other allied works etc. all complete for augmentation of Gangnapur W/S Scheme (for Gangnapur and Korabari Mouza) under Ranaghat Sub-Division of Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000294/2023-2024 | 920/RSD | 13/09/2023 | 40 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 3.91 | 0 | 100
1949 | Nadia Division | Ranaghat Sub-Division | Balance Laying of different dia UPVC pipe and other allied works etc. all complete for augmentation of Gangnapur W/S Scheme (for Gangnapur and Korabari Mouza) under Ranaghat Sub-Division of Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000295/2023-2024 | 923/RSD | 14/09/2023 | 30 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 4.59 | 0 | 100
1950 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
1951 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000068/2022-2023 | 4289/ND | 29/09/2022 | 0 | Resource Division | 24.31 | 0 | 0
1952 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000108/2022-2023 | 5202/ND | 14/12/2022 | 0 | Resource Division | 38.66 | 0 | 0
1953 | Nadia Division | Ranaghat Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GANGNAPUR to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | VCH/000197/2022-2023 | 21/PFMS | 20/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.87 | 0 | 0
1954 | Central Drilling | Ranaghat Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Gangnapur W/S Scheme (TW-I) , Ranaghat-II Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000138/2023-2024 | 1234/CDD | 04/09/2023 | 30 | DEV AND COMPANY | 18.88 | 0 | 0
1955 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC at under GANGNAPUR W/S Scheme, Block-Ranaghat , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 11) | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000020/2023-2024 | 1583/EMD | 24/04/2023 | 30 | A.S. ENTERPRISE | 25.94 | 0 | 0
1956 | Nadia Division | Kalyani Sub-Division I | Repairing and renovation of pump house, compressor room , boundary , extension of drain & other allied works at Ber ramchandrapur pump house no: 1 under Ber ramchandrapur zone:1 Karimpur -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000111/2022-2023 | 676/ Kly SD-I | 26/07/2022 | 30 | CHOWDHURY & CO. | 4 | 3.99 | 100
1957 | Nadia Division | Kalyani Sub-Division I | Repairing and renovation of pump house, dismantling part of boundary wall & re - construction it, land development , & construction of bath room with other allied works at Ber ramchandrapur pump house no: II under Ber ramchandrapur zone:1 Karimpur -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000112/2022-2023 | 677/ Kly SD-I | 26/07/2022 | 30 | RAJAT ENTERPRISE | 4.98 | 4.98 | 100
1958 | Nadia Division | Kalyani Sub-Division I | Interconnection of newly sunk tubewell at 2nd Pump House including cleaning of rising main and allied works at Ber Ramchandrapur Zone-I Water Supply Scheme, Karimpur-I Block, Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000303/2022-2023 | 1162/Kly SD-1 | 16/12/2022 | 15 | SANDIP BISWAS | 0.95 | 0.95 | 100
1959 | Nadia Division | Kalyani Sub-Division I | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Ber Ramchandrapur Z-I Water Supply Scheme Under R.W.S. Nadia Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000675/2023-2024 | 1174/ND | 21/02/2024 | 360 | REAL TIME | 32.25 | 0 | 75
1960 | Nadia Division | Kalyani Sub-Division I | Laying of distribution system including specials, Valves & Pipe supporting structure all complete based on actual estimate & providing FHTC for Ber Ramchandrapur Zone-I Water Supply Scheme in Nadia District under Nadia Division. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000725/2021-2022 | 1207/ND | 14/03/2022 | 90 | SANDIP BISWAS | 115.92 | 115.91 | 100
1961 | Nadia Division | Kalyani Sub-Division I | Additional work of Laying Distribution System and additional work of providing FHTC in connection with Augmentation of Ber Ramchandrapur Zone-I PWSS within Karimpur-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000770/2023-2024 | 1760/ND | 12/03/2024 | 225 | CHINMOY BISWAS | 16.86 | 0 | 100
1962 | Nadia Division | Kalyani Sub-Division I | Conversion of IEP to AIRP of capacity 32 Cu.m/hr at Ber Ramchandrapur Zone-I Water Supply Scheme within Karimpur-I block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000796/2023-2024 | 1908/ND | 15/03/2024 | 120 | M/S R.K.ENTERPRISE | 124.95 | 0 | 0
1963 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000007/2022-2023 | 2506/ND | 08/06/2022 | 0 | Resource Division | 2.86 | 0 | 0
1964 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000105/2021-2022 | 1033/ND | 03/03/2022 | 0 | Resource Division | 4.64 | 0 | 0
1965 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000126/2021-2022 | 1263/ND | 16/03/2022 | 0 | Resource Division | 5.58 | 0 | 0
1966 | Nadia Division | Kalyani Sub-Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | VCH/001062/2021-2022 | 620/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.78 | 0 | 0
1967 | Central Drilling | Kalyani Sub-Division I | PROVIDING DRILLING CREWS & OTHER MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 120 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR BERRAMCHANDRAPUR ZONE-I W/S SCH (2ND TUBE WELL SITE), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-I (D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000164/2022-2023 | 375/CMSD-I | 05/08/2022 | 15 | UNIVERSAL ENTERPRISES | 3.7 | 3.7 | 0
1968 | Central Drilling | Kalyani Sub-Division I | PROVIDING 300MM & 200MM NOMNAL DIA UPVC PIPE CONFORMING TO IS 12818:2010 & OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BERRAMCHANDRAPUR ZONE-I (2ND TUBE WELL) W/S SCH, KARIMPUR BLOCK UNDER NADIA DISTRICT CMSD-I (D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000165/2022-2023 | 376/CMSD-I | 05/08/2022 | 15 | UNIVERSAL ENTERPRISES | 3.8 | 3.8 | 0
1969 | Central Drilling | Kalyani Sub-Division I | SUPPLY & DELIVERY PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED & OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BERRAMCHANDRAPUR ZONE-I (2ND TUBE WELL SITE) W/S SCH, KARIMPUR BLOCK UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000166/2022-2023 | 377/CMSD-I | 05/08/2022 | 15 | UNIVERSAL ENTERPRISES | 2.07 | 1.7 | 0
1970 | Eastern Mechanical | Kalyani Sub-Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under BERRAMCHANDRAPUR (Zone-I) W/S Scheme, Block- Karimpur-I , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000899/2022-2023 | 409/EMD | 20/01/2023 | 30 | SHIVAM ENTERPRISE | 15.53 | 14.87 | 100
1971 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., construction of 400 cum capacity 20 mtr. staging height rcc over head reservoir (including pile foundation), pipe connection and cost of pipes, specials. and soil investigation all complete for Augmentation of Ground Based Water Supply Scheme at Gopinathpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000149/2022-2023 | 4226/ND | 27/09/2022 | 1311 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 766.15 | 346.25 | 65
1972 | Nadia Division | Tehatta Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
1973 | Nadia Division | Tehatta Sub-Division | Conversion of IEP to AIRP of capacity 120 Cu.m/hr at Gopinathpur Water Supply Scheme within Tehatta-II Block block under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000316/2024-2025 | 6841/ND | 12/11/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 172.22 | 0 | 0
1974 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground basaed piped water supply scheme for Gopinathpur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000401/2024-2025 | 7125/ND | 09/12/2024 | 90 | REAL TIME | 37.78 | 0 | 0
1975 | Nadia Division | Tehatta Sub-Division | Laying pipe line of rising main at Gopinathpur Under Augmentation of Gopinathpur PWSS under Tehatta Sub-Division Under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000679/2024-2025 | 7452/ND | 20/12/2024 | 270 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 54.97 | 0 | 0
1976 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Gopinathpur Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Gopinathpur at Tehatta-II Block by Augmentation of Ground Water based PWSS for Tehatta-II Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000741/2024-2025 | 419/ND | 27/01/2025 | 60 | DAS CONSTRUCTION | 26.96 | 0 | 0
1977 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000102/2022-2023 | 5101/ND | 08/12/2022 | 0 | Resource Division | 3.64 | 0 | 0
1978 | Nadia Division | Tehatta Sub-Division | PROVIDING FHTC BY AUGMENTATION FOR GOPINATHPUR PWSS BLOCK: TEHATTA - II DISTRICT: NADIA | Assistant Engineer | Junior Engineer | VCH/000348/2022-2023 | 48/PFMS | 22/06/2022 | 0 | HORIZEN | 2.8 | 0 | 0
1979 | Eastern Mechanical | Tehatta Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at GOPINATHPUR W/S Scheme Block- Tehatta-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10688] | Assistant Engineer | Junior Engineer | ORD/000137/2025-2026 | 1138/EMD | 04/06/2025 | 90 | ABHISEK ENGINEERING CONCERN | 52.38 | 0 | 0
1980 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/001008/2022-2023 | 496/EMDdt.24.01.2023 | 17/03/2023 | 656 | GLACIER ENGINEERING CO. | 66.71 | 36.31 | 100
1981 | Nadia Division | Tehatta Sub-Division | Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 250 CUM OHR at Bareya Zone-II W/S. scheme under Nadia Division P.H.E. Dte. in the District of Nadia . | Assistant Engineer | Junior Engineer | ORD/000068/2024-2025 | 3980/ND | 22/07/2024 | 365 | CHOWDHURY & CO. | 130.34 | 0 | 0
1982 | Nadia Division | Tehatta Sub-Division | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement and construction of Boundary wall at Head Work Site of Bareya Zone-II Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000072/2024-2025 | 4076/ND | 26/07/2024 | 540 | MANAJIT BISWAS | 22.65 | 0 | 40
1983 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Bareya Zone-I to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000074/2024-2025 | 4077/ND | 26/07/2024 | 420 | SANJIB DEY | 58.82 | 0 | 75
1984 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bareya Zone-II to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000075/2024-2025 | 4074/ND | 26/07/2024 | 540 | CHOWDHURY & CO. | 185.28 | 0 | 10
1985 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Bareya Zone-I Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division, P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Bareya Zone-I at Tehatta-II Block by Augmentation of Ground Water based PWSS for Bareya Zone-I Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2025-2026 | 2460/ND | 27/05/2025 | 60 | S.D. CONSTRUCTION | 23.36 | 0 | 0
1986 | Nadia Division | Tehatta Sub-Division | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 54 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Bareya Zone-I to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000091/2024-2025 | 4315/ND | 06/08/2024 | 540 | MONDAL PRECISION PRIVATE LIMITED | 186.88 | 0 | 0
1987 | Nadia Division | Tehatta Sub-Division | Repairing and renovation works of Pump House and allied works of ground based piped water supply scheme for Bareya Zone-I water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000273/2024-2025 | 6695/ND | 29/10/2024 | 90 | SHREEOM ENTERPRISE | 13.79 | 0 | 0
1988 | Nadia Division | Tehatta Sub-Division | Construction of barbed wire fencing with concrete pillars at Baraya Zone-II (2nd T.W). water supply scheme( New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | Assistant Engineer | Junior Engineer | ORD/000581/2022-2023 | 930/TSD | 14/03/2023 | 7 | PRABIR KUMAR ROY | 0.7 | 0.69 | 0
1989 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Bareya Zone-II Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Bareya Zone-II at Bareya Zone-II Block by Augmentation of Ground Water based PWSS for Bareya Zone-II Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000630/2024-2025 | 7361/ND | 18/12/2024 | 60 | M/S DURGA SECURITIES & SERVICES | 20.41 | 0 | 0
1990 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bareya Zone-I to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000731/2021-2022 | 1249/ND | 16/03/2022 | 468 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 196.39 | 189.23 | 100
1991 | Nadia Division | Tehatta Sub-Division | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangement and construction of boundary wall at Tube well No-2 Site at Bareya Water Supply Scheme(Z-II) Under Tehatta Sub-Division PHE Dte.) | Assistant Engineer | Junior Engineer | ORD/000747/2023-2024 | 1625/ND | 07/03/2024 | 360 | ROY ASSOCIATES | 12.15 | 0 | 0
1992 | Nadia Division | Tehatta Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 42 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Bareya Zone-II to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000849/2024-2025 | 4143/ND | 29/07/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 173.48 | 0 | 0
1993 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000175/2022-2023 | 152/ND | 06/01/2023 | 0 | Resource Division | 26.67 | 0 | 0
1994 | Nadia Division | Tehatta Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001265/2021-2022 | 731/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.17 | 0 | 0
1995 | Nadia Division | Tehatta Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001266/2021-2022 | 732/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.26 | 0 | 0
1996 | Central Drilling | Tehatta Sub-Division | Sinking of 80 mm dia. Shallow Tube Well for requirement of drilling water for Baraia PWSS, District - Nadia and other PWSS under CMSD-II (D), CDD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2023-2024 | 91/CMSD-II | 17/04/2023 | 684 | PADMA ENGINEERING & CO. | 0.89 | 0 | 15
1997 | Central Drilling | Tehatta Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Baraia W/S Scheme (T/W-I & II) , Tehatta-II Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000140/2023-2024 | 132/CDD | 17/04/2023 | 837 | PADMA ENGINEERING & CO. | 37.3 | 0 | 50
1998 | Eastern Mechanical | Tehatta Sub-Division | Quotation charges and security deposit for new power connection at Baraia(Zone-II) PH-II under Eastern Mechanical Subdivision-III, Nadia | Assistant Engineer | Junior Engineer | BILL/02259/2024-2025 | BP-176 | 13/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 4.04 | 0 | 0
1999 | Eastern Mechanical | Tehatta Sub-Division | Quotation charges and security deposit for new power connection at Baraia(Zone-II) head worksite under Eastern Mechanical Subdivision-III, Nadia | Assistant Engineer | Junior Engineer | BILL/02319/2024-2025 | BP-195-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 14.83 | 0 | 0
2000 | Eastern Mechanical | Tehatta Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under BARAIA ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. SM/10269 | Assistant Engineer | Junior Engineer | ORD/000181/2025-2026 | 1118/EMD | 04/06/2025 | 90 | GHOSH AND GHOSH | 17.48 | 0 | 0
2001 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.- I & II under Baraia W/S Scheme, Block-Tehatta-II, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/000898/2022-2023 | 408/EMD | 20/01/2023 | 30 | PADMA ENGINEERING CO. | 22.18 | 21.91 | 55
2002 | Nadia Division | Kalyani Sub-Division I | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no 03/2022 central tax rate dt-13.07.2022 | Assistant Engineer | Junior Engineer | BILL/00214/2024-2025 | 126/PFMS | 23/07/2024 | 0 | H I ENTERPRISE | 24.42 | 0 | 0
2003 | Nadia Division | Kalyani Sub-Division I | Sinking of Tube Well at Tehatta PH-2 including dismantling of old pump house for entry of tube well rig, construction of pump house and boundary wall under Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatta (Phase-II) at Tehatta-I block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000001/2023-2024 | 1545/ND | 05/04/2023 | 540 | JOY HIND TUBEWELL'S | 36.83 | 11.46 | 100
2004 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- III) at village Nazirpur, Bagadoba, Chhitka, Aztullanagar under Tehatta-I Block to accommodate FHTC under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1805/ND | 22/04/2025 | 180 | M/S DIPAK ENTERPRISE | 71.65 | 0 | 30
2005 | Nadia Division | Kalyani Sub-Division I | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 135 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Tehatta to accommodate FHTC within Tehatta-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000094/2024-2025 | 4230/ND | 02/08/2024 | 180 | TARUN KUMAR BHATTACHARYA | 315.65 | 0 | 0
2006 | Nadia Division | Kalyani Sub-Division I | Laying of additional pipeline for Tehatta PWSS".under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000123/2024-2025 | 4576/ND | 21/08/2024 | 360 | SHYAMAL SHIL | 21.44 | 0 | 50
2007 | Nadia Division | Kalyani Sub-Division I | Augmentation of rising main system, providing FHTC, construction of 700 cum capacity 20 mtr. staging height RCC over head reservoir (including pile foundation), pipe connection and cost of pipes, specials and soil investigation for augmentation of ground water based piped water supply scheme for Tehatta Phase-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000388/2022-2023 | 478/ND | 02/02/2023 | 789 | H I ENTERPRISE, VILL&P.O- DHALTITHA, P.S. BASIRHAT, NORTH 24 PARGANAS, PIN-743412(WB) | 354.33 | 72.06 | 90
2008 | Nadia Division | Kalyani Sub-Division I | Collection of Household data through mobile app for FHTC Connection at followingschemes under Nadia Division PHE Dte.Schemes: i) Hanspukuria (Zone-II) ii) Tehatta (Phase-II) iii) Dhoradaha iv)Karimpur Jalangi(Zone-XA) v)Karimpur Jalangi(Zone-XB) vi) Hanspukuria (Zone-I) | Assistant Engineer | Junior Engineer | ORD/000479/2022-2023 | 371/ Kly SD-I | 17/03/2023 | 184 | HORIZEN | 4.96 | 3.28 | 100
2009 | Nadia Division | Kalyani Sub-Division I | Construction and installation of MANIFOLD and allied works at OHR site under Tehatta (Phase-2) Ground Based Water Supply Scheme under Tehatta-I Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Tehatta (Phase-2) at Tehatta- I Block by Augmentation of Ground Water based PWSS for Tehatta (Phase-2) Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000634/2024-2025 | 7362/ND | 18/12/2024 | 60 | MANISHIKA CONSTRUCTION | 20.92 | 0 | 0
2010 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000079/2023-2024 | 2322/ND | 29/05/2023 | 0 | Resource Division | 16.74 | 0 | 0
2011 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000180/2022-2023 | 143/ND | 06/01/2023 | 0 | Resource Division | 107.61 | 0 | 0
2012 | Eastern Mechanical | Kalyani Sub-Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube well and Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I,II,III,IV under Tehatta ground water based water supply scheme under Block_ Tehatta-I Dist. - Nadia under EMD, PHE Dte. [SM/10597] | Assistant Engineer | Junior Engineer | ORD/000024/2025-2026 | 694/EMD | 04/04/2025 | 30 | C.M.S. ENGINEERING CONCERN. | 51.99 | 0 | 0
2013 | Nadia Arsenic Division I | Nadia Arsenic Division I | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Chupria Zone-I ii)Garapota iii)Itaberia iv)Muragachha Zone-I v)Muragachha Zone-II vi)Zone-I (Palagachha) vii)Zone-II (joykrishnapur) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000007/2023-2024 | 169/AE-I/NAD-I | 12/04/2023 | 1275 | TECH VISION | 4.84 | 1.49 | 100
2014 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Chupria Zone-I Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Chupria Zone-I W/S Scheme under JJM (SL.NO.12) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000015/2023-2024 | 1116 / NAD-I | 27/04/2023 | 15 | SAHA CONSTRUCTION &CO | 13.05 | 0 | 100
2015 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jaldhara/Jalswapna for Gobindapur Z-I Santipur Bolck by Augmentation of Ground Water Based PWSS for Chupria (Zone -I) Part -I at Hanskhali Block by retrofitting of Grond Water based PWSS for CHUPRIA Water Supply Sceme under Nadia Arsenic Division-I , P.H.E.Dte (Sl.no.01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000066/2022-2023 | 1673 / NAD-I | 07/09/2022 | 539 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 565.67 | 456.96 | 85
2016 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet, Pathway and other allied work at H/W Site (Length-135.0 m) and 2nd T/W Site (Length-55.0m) in Chupria Zone-I water supply Scheme within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. (SL.NO.17) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000183/2022-2023 | 104 / NAD-I | 31/01/2023 | 45 | GOPAL KIRTYANIA | 24.03 | 23.95 | 40
2017 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Chupria Zone-I under Jal Jeevan Mission (JJM) for Chupria Zone-I W/S Scheme at Hanskhali Block in connection with augmentation of Ground Water based W/S Scheme for Chupria Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl.no.19) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000184/2023-2024 | 2155/NAD-I | 08/09/2023 | 21 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 71.93 | 0 | 80
2018 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 450 cum capacity Over Head Reservoir ,Painting and Pump House at Chupria, Zone-I under Surface W/S Scheme in Hanskhali Block under Nadia Arsenic Division-I, P. H.E. Dte (Sl. No.16) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000190/2022-2023 | 153/NAD-I | 07/02/2023 | 30 | PAPAN ROY | 13.66 | 13.61 | 100
2019 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation & repair of IEP pump house & allide works of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000235/2022-2023 | 461/RSD | 22/07/2022 | 30 | RENUKA ENTERPRISE | 1.49 | 1.22 | 90
2020 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of head work site pump house & allied works of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000236/2022-2023 | 461/A/RSD | 22/07/2022 | 30 | PALLAB KARMAKAR | 2.25 | 1.92 | 90
2021 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of pump house & allied works in the premises at pump house no-I of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000237/2022-2023 | 462/RSD | 22/07/2022 | 30 | JYOTIRMOY ENTERPRISE | 2.54 | 0 | 85
2022 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of boundary wall & allied works in the premises at pump house no 2 of Barakulta W/S scheme of Ranaghat-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000238/2022-2023 | 462/A/RSD | 22/07/2022 | 30 | M/S LOKENATH ENTERPRISE | 2.84 | 0 | 95
2023 | Nadia Division | Ranaghat Sub-Division | River crossing at Anjana River Barakulta including construction of anchor block Barakulta W/S Scheme of Ranaghat -I block under Ranaghat Sub-Division,P.H.E.Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000291/2022-2023 | 5330/ND | 21/12/2022 | 45 | CHOWDHURY & CO. | 15.3 | 15.29 | 100
2024 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
2025 | Nadia Division | Ranaghat Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Barakulta W/S Scheme in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000442/2021-2022 | 1062/RSD | 02/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.76 | 4.16 | 100
2026 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000071/2022-2023 | 4322/ND | 29/09/2022 | 0 | Resource Division | 19.74 | 0 | 0
2027 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000104/2022-2023 | 5103/ND | 08/12/2022 | 0 | Resource Division | 154.18 | 0 | 0
2028 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-IV, (Rukminidanga), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000003/2022-2023 | 644/NAD-I | 29/04/2022 | 336 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT LTD. | 359.23 | 314.08 | 100
2029 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Rukminidanga ZoneV at under Chakdah Surface WS Scheme in Chakdah Block under NAD I PHE Dte (Sl.no.05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000060/2022-2023 | 1596/NAD-I | 06/09/2022 | 60 | SAHA ENGINEERS | 28.04 | 23.37 | 100
2030 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000005/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 26.12 | 0 | 0
2031 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC and laying dedicated pipeline for Kamargaria & Debogram Village in connection with Debagram Water Supply Scheme within Nadia Arsenic Division-I, PHE Dte under Jal Jeevan Mission. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-III | ORD/000027/2025-2026 | 157/NAD-I | 28/04/2025 | 60 | M/S A.K. CONSTRUCTION | 82.68 | 0 | 0
2032 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/JalSwapna for Debogram Phase-II at Ranaghat-II Block by augmentation of Ground Water based PWSS for Debogram Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000049/2022-2023 | 1688/NAD-I | 08/09/2022 | 90 | UMWELT ENGINEER PVT. LTD. | 399.59 | 0 | 99
2033 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC and laying dedicated pipeline for Sijdia, Dakhin Rameswarpur,Anatapur, Mithapur & aismali Village in connection with Debagram Water Supply Scheme under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000080/2025-2026 | 581/NAD-I | 10/07/2025 | 60 | SUMAN CHAKRABORTY | 96.78 | 0 | 0
2034 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of additional pipelines under JJM at Garapota W/S Scheme in connection with Debagram W/ Scheme under Ranaghat-II block within Hanskhali Block Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000306/2024-2025 | 229/AE-II/NAD-I | 12/11/2024 | 15 | JAGADANADAPUR CO-OPT LABOUR CONTTRACT AND CONSTRUTION SOCITY LTD. | 4.85 | 0 | 0
2035 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill for new service connection at Dhopotto-I | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/02145/2022-2023 | 142/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.47 | 0 | 0
2036 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill for new service connection at dhopahat-II W/S Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/02146/2022-2023 | 143/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.48 | 0 | 0
2037 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Dhopahat Piped Water SupplyScheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 16) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000420/2022-2023 | 6253/EMD | 19/11/2022 | 30 | S.G. ENTERPRISE | 40.81 | 0 | 0
2038 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Dhopahat W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000455/2022-2023 | 6263/EMD | 19/11/2022 | 864 | BARISAL TRADING CO. | 9.88 | 0 | 10
2039 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Dhopahat W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No.- 21 of EE/EMD of 2022-23 (Sl. No.-01) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000519/2022-2023 | 6369/EMD | 23/11/2022 | 30 | ABHISEK ENGINEERING CONCERN | 10 | 0 | 80
2040 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Dhopahat water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000003/2022-2023 | 212/NACD-II | 05/04/2022 | 60 | NAMDAR ALI | 5.37 | 5.36 | 100
2041 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Dhopahat Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. (Sl. No. 01) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000015/2022-2023 | 220/NACD-II | 05/04/2022 | 30 | GOUTAM HALDER | 5.37 | 2.53 | 100
2042 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Dhopahat and Khaspu Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000017/2022-2023 | 242/NACD-II | 19/04/2022 | 60 | AUXILIARY TUBE WELL DRILLERS | 43.18 | 29.26 | 100
2043 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Dhopahat water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000050/2022-2023 | 17/AE-II/NACD-II | 11/04/2022 | 60 | NAMDAR ALI | 2.83 | 0 | 100
2044 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Dhopahat and adjoining mouzas under Dhopahat Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000057/2022-2023 | 288/NACD-II | 12/05/2022 | 90 | SINGHA ROY & CO. | 253.93 | 213.88 | 85
2045 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Dhopahat) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000057/2023-2024 | 869/NACD-II | 10/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
2046 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000080/2025-2026 | 736/NACD-II | 18/06/2025 | 90 | JOY HIND TUBEWELLS | 186.42 | 0 | 40
2047 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earth work in filling in ditches at Dhopahat 2nd Tube Well Site for development of land in connection with proposed T/W Sinking & Pump House construction at Dhopahat Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000128/2022-2023 | 64/AE-II/NACD-II | 28/06/2022 | 20 | GHOSH ENTERPRISE | 3.2 | 3.2 | 100
2048 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Dhopahat Water Supply Scheme H/W site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000180/2022-2023 | 522/NACD-II | 05/08/2022 | 60 | CHANDAN ROY | 27.92 | 16.71 | 85
2049 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Dhopahat Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000203/2022-2023 | 632/NACD-II | 06/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.84 | 4.84 | 100
2050 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 87 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Matiary Water Supply Scheme in Krishnaganj block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000217/2024-2025 | 1311/NACD-II | 20/09/2024 | 180 | JOY HIND TUBEWELLS | 232.26 | 0 | 0
2051 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Dhopahat Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000223/2024-2025 | 1312/NACD-II | 20/09/2024 | 360 | JOY HIND TUBEWELLS | 181.56 | 0 | 0
2052 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Dhopahat 2nd Tubwell Site within Dhopahat Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000329/2022-2023 | 122/NACD-II | 11/01/2023 | 60 | BASUDEB SAHA | 6.57 | 0 | 85
2053 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) , Jitpur , Taranipur & Dhopahat W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000346/2024-2025 | 1627/NACD-II | 19/12/2024 | 540 | M.R. CONSTRUCTION | 117.87 | 0 | 40
2054 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Additional Earth work in filling in ditches at Dhopahat 2nd Tube Well Site for development of land in connection by hand roller in connection with proposed T/W Sinking & Pump House construction at Dhopahat Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000367/2022-2023 | 284./NACD-II | 01/03/2023 | 20 | M/S SHAIKH ENTERPRISE | 2.45 | 2.45 | 100
2055 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Dhopahat water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000374/2022-2023 | 360/NACD-II | 22/03/2023 | 1096 | SINGHA ROY & CO. | 143.35 | 34.64 | 27
2056 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pump House cum Chlorine room with sanitary arrangement at Thanarpara Zone-II Headwork site according to departmental drawing at Thanarpara Zone-II & Dhopahat Piped Water Supply Scheme under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000465/2024-2025 | 403_NACD-II | 26/03/2025 | 150 | ROY CONSTRUCTION | 6.14 | 0 | 100
2057 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | RTOR000002/2022-2023 | 398/NACD-II | 04/07/2022 | 0 | Resource Division | 47.43 | 0 | 0
2058 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000244/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
2059 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000350/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
2060 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 214.78 | 47
2061 | Nadia Division | Debgram Sub-Division | Preparation of DPR for Augmentation for Intake, WTP & Rising Main of Surface Water Based Water Supply Scheme for Northern Sector Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte.(including Survey, Design and Estimate). | Assistant Engineer | Junior Engineer 1 | ORD/000194/2022-2023 | 4525/ND | 21/10/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 15.1 | 15.1 | 0
2062 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 1A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000764/2021-2022 | 114/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.16 | 3.94 | 100
2063 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 1 | RTOR000112/2022-2023 | 71/ND | 05/01/2023 | 0 | Resource Division | 345.52 | 0 | 0
2064 | Nadia Division | Debgram Sub-Division | Restoration Work of road damaged of Debagram Tehattaghat Road from 0.00 Kmp. to 14.00 kmp., Under Plassey Highway Sub-Division Under Nadia Highway Division No.-I in the District Of Nadia During the Year 2024-2025. | Assistant Engineer |  | BILL/00268/2024-2025 |  | 02/08/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 8.88 | 0 | 0
2065 | Nadia Division | Debgram Sub-Division | Restoration Work of road damaged of Debagram Tehattaghat Road from 0.00 Kmp. to 14.00 kmp., Under Plassey Highway Sub-Division Under Nadia Highway Division No.-I in the District Of Nadia During the Year 2024-2025. | Assistant Engineer |  | BILL/00342/2024-2025 | 160/PFMS | 13/08/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 4.44 | 0 | 0
2066 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 231.37 | 47
2067 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
2068 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 2B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000768/2021-2022 | 118/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.38 | 4.33 | 100
2069 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000114/2022-2023 | 101/ND | 05/01/2023 | 0 | Resource Division | 170.21 | 0 | 0
2070 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001768/2022-2023 | 1120/EMD | 16/03/2023 | 30 | B.T. PROJECTS PVT. LTD | 91.82 | 0 | 60
2071 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Matiary H/W and 2nd Pump house site with Reinforced Barbed Tape , Plaster , Painting and other allied works.Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000018/2024-2025 | 140./AE-II/NACD-II | 11/06/2024 | 30 | MUKHERJEE CONSTRUCTION | 4.83 | 0 | 100
2072 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Matiary W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000034/2021-2022 | 527/NACD-II | 14/06/2021 | 45 | S.K. CONSTRUCTION | 64 | 63.98 | 100
2073 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHRSpecially) under Krishnaganj Block of Nadia District through Jadavpur University. (Name of PWSS Matiary) | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000087/2024-2025 | 866/NACD-II | 04/07/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
2074 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Pump house repair at Gongra W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000097/2021-2022 | 735/NACD-II | 13/09/2021 | 45 | APURBA MANDAL | 65.58 | 65.49 | 100
2075 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Jungle cutting and Earthwork in filling at Maheshpur, Maitari and Thanarapara Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000120/2024-2025 | 818/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.76 | 0 | 100
2076 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Matiary, (Block-Krishnaganj) piped water supply schemes | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000150/2021-2022 | 149/AE-I/NACD-II | 16/11/2021 | 10 | UMWELT ENGINEER PVT LTD. | 3.02 | 3.02 | 100
2077 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Exigent connection of higher specification components as per IS Code 8329 with its latest version in the mouza in the JL No. 52 at Matiari Piped Water Supply Scheme under Krishnaganj Development Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000197/2024-2025 | 313AE-II/NACD-II | 06/09/2024 | 390 | A.K ADHIKARY | 3.49 | 0 | 100
2078 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 87 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Matiary Water Supply Scheme in Krishnaganj block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000217/2024-2025 | 1311/NACD-II | 20/09/2024 | 180 | JOY HIND TUBEWELLS | 232.26 | 0 | 0
2079 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair, & also Rising Main replacement by DI pipe) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000226/2021-2022 | 984/NACD-II | 27/12/2021 | 90 | MONDAL ENTERPRISE | 149.3 | 149.25 | 100
2080 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Matiari Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000244/2023-2024 | 20/AE-II/NACD-II | 15/02/2024 | 15 | SANJIB DEY | 0.97 | 0 | 100
2081 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Matiary Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000271/2021-2022 | 45/AE-II/NACD-II | 17/02/2022 | 30 | BABLU MALLICK | 4.18 | 4.09 | 100
2082 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000292/2021-2022 | 127/NACD-II | 21/02/2022 | 90 | MALLICK ENTERPRISE | 159.32 | 0 | 100
2083 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Matiary W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000295/2022-2023 | 1193/NACD-II | 23/12/2022 | 15 | ROY CONSTRUCTION | 1.71 | 1.59 | 100
2084 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Pump house repair at Gongra W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000313/2021-2022 | 859/EE/NACD-II | 08/11/2021 | 45 | PRIYA CONSTRUCTION | 53.27 | 53.18 | 100
2085 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000003/2024-2025 | 985/NACD-II | 23/07/2024 | 0 | Resource Division | 15.62 | 0 | 0
2086 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000006/2021-2022 | 81/NACD-II | 01/02/2022 | 0 | Resource Division | 112.78 | 0 | 0
2087 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including Specials, Valves & Pipe Supporting Structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. and Construction of boundary wall at head work site all complete for Augmentation of Ground Based Water Supply Scheme at Bhimpur (Phase-I) to accommodate FHTC with Krishnagar-I Block under Krishnagar Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000153/2023-2024 | 3219/ND | 26/07/2023 | 90 | RADIANT | 585.67 | 0 | 0
2088 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000148/2023-2024 | 259/ND | 11/01/2024 | 0 | Resource Division | 21.56 | 0 | 0
2089 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000149/2022-2023 | 83/ND | 05/01/2023 | 0 | Resource Division | 148.12 | 0 | 0
2090 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-I) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/000355/2022-2023 | 55/PFMS | 22/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.91 | 0 | 0
2091 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of AIRP capacity (111m3/hr) in connection with augmentation of Ground Water Based PWSS for Baganchara under Jal Jeevan Mission at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000024/2024-2025 | 1079/NAD-I | 15/07/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 278.95 | 0 | 65
2092 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Nabla Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Nabla Part-III Piped W/S Scheme (sl.no.21) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000026/2023-2024 | 1162 / NAD-I | 28/04/2023 | 15 | CHOWDHURY & CO. | 13.07 | 0 | 100
2093 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site for Gayeshpur Zone-I & Gobindapur Zone-I PWSS at Shantipur Block providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water Based PWSS for PWSS for Boalia, Nabla, Gayeshpur W/S Schemes under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000042/2024-2025 | 1338/NAD-I | 23/08/2024 | 300 | B.S. ENTERPRISE | 26.73 | 0 | 65
2094 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipeline including providing FHTC at Goalpur and Boalia W/S Scheme, Shnatipur Block under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 05) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000058/2024-2025 | 1566/NAD-I | 26/09/2024 | 495 | CONSTRUCTURE | 13.85 | 0 | 78
2095 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jaldhara/Jalswapna for Gobindapur Z-I Santipur Bolck by Augmentation of Ground Water Based PWSS for Gobindapur Z-I W/S scheme under Nadia Arsenic Division-I , P.H.E.Dte (Sl.no.04) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000065/2022-2023 | 1672 / NAD-I | 07/09/2022 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 534.08 | 0 | 70
2096 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (216cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.09) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000131/2023-2024 | 1899/NAD-I | 14/08/2023 | 691 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 167.06 | 0 | 70
2097 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Boalia, Part-III at Santipur Block bY Augmentation of Ground Water Based PWSS for Boalia W/S Scheme, Providing FHTC under Jal Jeevan Mission (JJM) for Gayeshpur Zone-I, Part-III at Santipur Block by Augmentation of Ground Water Based PWSS for Gayeshpur W/S Scheme, Providing FHTC under Jal Jeevan Mission (JJM) for Gayeshpur Zone-II, Part-III at Santipur Block by Augmentation of Ground Water Based PWSS for Gayeshpur W/S Scheme, Construction of Boundary wall, Toilet, Pathway and other allied work at Boalia Water Supply Scheme within Santipur Block, Construction of Boundary wall, Toilet, Pathway and other allied work at Gayeshpur Zone-I Water Supply Scheme, Construction of Boundary wall, Toilet, Pathway and other allied work at Gayeshpur Zone-II Water Supply Scheme, Repair of 550 cum capacity Over Head Reservoir and other allied works at Boalia water supply scheme AND Repair of 250 cum capacity Over Head Reservoir and other allied works at Gayeshpur Zone-I water supply scheme underNadia Arsenic Division-I , PHE Dte. (Sl.no. 03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000102/2023-2024 | 1697/NAD-I | 13/07/2023 | 1095 | JAL PRAVHAHIKA PVT. LTD., | 493.44 | 67.15 | 45
2098 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of Manifold and allied works at OHR site under for Goalpur Zone-I PWSS including augmentation works under Gayeshpur Zone-I PWSS at Shantipur Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000137/2024-2025 | 1968/NAD-I | 28/11/2024 | 300 | M/S DREAM INFRASTRUCTURE | 16.83 | 0 | 80
2099 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | RTOR000012/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 6.22 | 0 | 0
2100 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | RTOR000027/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 4.31 | 0 | 0
2101 | Eastern Mechanical | Nadia Arsenic Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under GAYESPUR (Z-I) W/S Scheme, Block- Shantipur , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 07) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000027/2023-2024 | 1606/EMD | 26/04/2023 | 30 | STANDARD ENGINEERING | 15.65 | 0 | 100
2102 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Boalia, Nabla, Gayeshpur Z-1 and Gayeshpur Z II, Part III under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/12021) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000171/2025-2026 | 1169/EMD | 04/06/2025 | 90 | SWAPAN ENTERPRISE | 17.35 | 0 | 0
2103 | Eastern Mechanical | Nadia Arsenic Division I | Supply & delivery of automatically controlled Diaphragm type Chlorinator at Gayeshpur Zone-I P/H-I W/S Sch for accommodate FHTC work, Under ESMD-II PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/001714/2023-2024 | 752/EMSD-II | 09/10/2023 | 10 | STANDARD ENGINEERING | 0.9 | 0 | 100
2104 | Nadia Division | Debgram Sub-Division | Health Check up of existing Over Head Reservoir(OHR) based on inspection and Non-destructive Test (NDT) at Northern Sector Part-I (Zone-5A) PWSS at Kaligunj Block under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000103/2024-2025 | 4279/ND | 05/08/2024 | 15 | JADAVPUR UNIVERSITY | 3.48 | 0 | 100
2105 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 165.6 | 47
2106 | Nadia Division | Debgram Sub-Division | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000236/2025-2026 | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0
2107 | Nadia Division | Debgram Sub-Division | Collection of Household data through mobile app for FHTC Connection of Surface Based PWSS for Northern Sector (Part-I) (Zone-IB to Zone-IVB) under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000339/2023-2024 | 985/KLYSD-I | 11/09/2023 | 90 | TECHVISION | 4.85 | 0 | 100
2108 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 5A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000774/2021-2022 | 124/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.88 | 4.88 | 100
2109 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000120/2022-2023 | 74/ND | 05/01/2023 | 0 | Resource Division | 66.06 | 0 | 0
2110 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of Pipeline for FHTC works under Surface Water Based PWSS Saguna Zone-VI (Part-II) for arsenic affected areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000020/2024-2025 | 1117/NAD-I | 19/07/2024 | 300 | APURBA MANDAL | 95.96 | 0 | 85
2111 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Laying Of Distribution System Including Specials, Valves & Pipe Supporting Structure, Construction Of Boundary Wall (675m Length), Chlorine Room, Drain (I300 m Length) and Approach Road (60.0m Length and 3.0m Wide),Construction of 600 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials and Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 600 m3 Staging Height 20Mtr. at Surface Water Based Piped Water Supply Scheme for Saguna ZONE-VI (PART-II) in Chakdah Block of Nadia Districtunder Nadia Arsenic Division-I, PHE Dte. (Sl.no.09) | Assistant Engineer-II | Junior Engineer-IV | ORD/000105/2023-2024 | 1690/NAD-I | 13/07/2023 | 1095 | APURBA MANDAL | 529.72 | 0 | 30
2112 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for providing FHTC (Functional Household Tap Connection) under JJM (Jal Jeevan Mission) by Augmentation of Zone-VI (Saguna) Part -II of Surface Water Based PWSS for Haringhata and Chakdah (Part) at Chakdah Block at Nadia District under Nadia Arsenic Division -I, P.H.E. Dte.(Sl.No.-02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000243/2022-2023 | 169 / AE-I/NAD-I | 08/07/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.81 | 4.81 | 100
2113 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000019/2023-2024 | 02/NAD-I | 02/01/2024 | 0 | Resource Division | 128.4 | 0 | 0
2114 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000025/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 18.48 | 0 | 0
2115 | Nadia Division | Krishnanagar Sub-Division | RESTORATION OF ROAD FROM SALIGRAM POST OFFICE - CHUPIPOTA VILLAGE under Package No. WB/14/135 | Assistant Engineer | Junior Engineer 5 | BILL/00504/2024-2025 | 300/PFMS | 02/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 10.95 | 0 | 0
2116 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000196/2023-2024 | 3537/ND | 11/08/2023 | 1147 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 0 | 20
2117 | Nadia Division | Krishnanagar Sub-Division | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000236/2025-2026 | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0
2118 | Nadia Division | Krishnanagar Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
2119 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | Assistant Engineer | Junior Engineer 5 | ORD/000706/2024-2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0
2120 | Nadia Division | Krishnanagar Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 3/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .05 ) | Assistant Engineer | Junior Engineer 5 | ORD/000714/2021-2022 | 207/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.42 | 4.37 | 100
2121 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | Assistant Engineer | Junior Engineer 5 | ORD/000758/2023-2024 | 1838/KSD | 28/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0
2122 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 5 | RTOR000161/2022-2023 | 86/ND | 05/01/2023 | 0 | Resource Division | 222.47 | 0 | 0
2123 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 650 Cum Capacity 20 Mtr. Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Palsunda to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000014/2023-2024 | 1720/ND | 17/04/2023 | 1096 | MONDAL ENTERPRISE, MASJID BARI ROAD,UTTAR BALURIA, P.O.NABAPALLY, P.S. BARASAT NORTH 24 PGS. | 593.41 | 259.62 | 45
2124 | Nadia Division | Kalyani Sub-Division I | Laying distribution system for providing FHTC at Baruipara Mouza in connection with Augmentation of Ground Based Water Supply Scheme at Palsunda to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000041/2024-2025 | 3453/ND | 20/06/2024 | 90 | CHOWDHURY & CO. | 75.01 | 0 | 100
2125 | Nadia Division | Kalyani Sub-Division I | Laying of 63mm dia UPVC Pipe line for Revision of drawing to accommodate FHTC & Construction of Jhama Bats Road for the approach way to headwork site of Palsunda water supply scheme under Kalyani Sub Division I under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000048/2024-2025 | 3454/ND | 20/06/2024 | 60 | MONDAL ENTERPRISE | 54.5 | 0 | 98
2126 | Nadia Division | Kalyani Sub-Division I | Lying distribution system for providing FHTC at Palsunda Mouza in connection with Augmentation of Ground Based Water Supply Scheme at Palsunda to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000049/2024-2025 | 3455/ND | 20/06/2024 | 90 | MONDAL ENTERPRISE | 96.94 | 0 | 100
2127 | Nadia Division | Kalyani Sub-Division I | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 120 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Polsunda to accommodate FHTC within Tehatta-II block under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000085/2024-2025 | 4191/ND | 31/07/2024 | 180 | MONDAL ENTERPRISE | 297.09 | 0 | 0
2128 | Nadia Division | Kalyani Sub-Division I | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Palsunda W/S Scheme in Tehatta-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000393/2021-2022 | 308/TSD | 24/11/2021 | 30 | RADIANT | 3.08 | 2.95 | 100
2129 | Nadia Division | Kalyani Sub-Division I | Construction of retaining wall at the head work site of Palsunda Water supply scheme at Tehatta-II Block in Connection with augmentation of Palsunda PWSS under Kalyani Sub Division-I under Nadia Division.P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000678/2024-2025 | 7447/ND | 20/12/2024 | 90 | MONDAL ENTERPRISE | 38.39 | 0 | 100
2130 | Nadia Division | Kalyani Sub-Division I | Making barbed wire fencing with concrete pillars at Polsunda water supply scheme (New Land)H.W.Site under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000724/2023-2024 | 1116/TSD | 21/02/2024 | 7 | PRABIR KUMAR ROY | 2.94 | 0 | 100
2131 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000046/2023-2024 | 1908/ND | 27/04/2023 | 0 | Resource Division | 144.56 | 0 | 0
2132 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000091/2023-2024 | 2300/ND | 29/05/2023 | 0 | Resource Division | 31.86 | 0 | 0
2133 | Eastern Mechanical | Kalyani Sub-Division I | Quotation charges and security deposit for new power connection at Palsunda-III head worksite under Eastern Mechanical Subdivision-III, Nadia | Assistant Engineer | Junior Engineer,Junior Engineer 1 | BILL/02261/2024-2025 | BP-183 | 13/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 7.79 | 0 | 0
2134 | Eastern Mechanical | Kalyani Sub-Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under KARIMPUR JALANGI(Z-8) W/S Scheme, Block- Karimpur II, PALSONDHA W/S Scheme, Block- Tehatta II, & MAIDANPUR W/S Scheme, Block- Chapra, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001923/2022-2023 | 1179/EMD | 21/03/2023 | 940 | CREATIVE WATER & PROCESS TECHNOLOGIES PVT. LTD. | 77.9 | 0 | 85
2135 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection at Pump House-I under Binodnagar Water Supply Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/01877/2023-2024 | BP-109-23-24 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0
2136 | Eastern Mechanical | Nadia Arsenic Civil Division II | Quotation for new Service connection at P.H-II under Binodnagar W/S Scheme, Dist-Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/04634/2023-2024 | BP-283-23-24 | 16/02/2024 | 0 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 4.61 | 0 | 0
2137 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under BINODNAGAR W/S Scheme (Block : Tehatta I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 10) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000030/2023-2024 | 1609/EMD | 26/04/2023 | 30 | ABHISEK ENGINEERING CONCERN | 18.99 | 0 | 80
2138 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at BINODNAGAR Piped Water SupplyScheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001121/2023-2024 | 4709/EMD | 04/08/2023 | 30 | M/S DILIP MITRA | 40.82 | 0 | 0
2139 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00019/2023-2024 | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
2140 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00092/2022-2023 | 235/7 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0
2141 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000001/2025-2026 | 428/NACD-II | 07/04/2025 | 180 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 30
2142 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Binodnagar Water Supply Scheme in Tehatta-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000043/2023-2024 | 408/AE-I/NACD-II | 08/08/2023 | 15 | B.M. ENGINEERING & CONSTRUCTION | 0.97 | 0 | 100
2143 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Binodnagar) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000082/2023-2024 | 888/NACD-II | 18/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
2144 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Binodnagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000111/2023-2024 | 1170/NACD-II | 11/10/2023 | 45 | R.M. TRADING | 11.32 | 0 | 90
2145 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Installation of Sign Board for Demarcation of Land for Binodnagar & other PWSS at Tehatta-I, Barnia & other PWSS at Tehatta-II, Karimpur-II, Jayrampur & other PWSS at Karimpur-I & Maniknagar PWSS at Shantipur Block under Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000128/2025-2026 | 02/AE-I/NACD-II | 02/04/2025 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 3.75 | 0 | 0
2146 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Binodnagar water supply scheme under Tehatta- I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000135/2023-2024 | 1253/NACD-II | 08/11/2023 | 667 | SURAJIT KUMAR GHOSH | 34.92 | 0 | 100
2147 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Binodnagar and Putimari PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000180/2024-2025 | 294_AE-II/NACD-II | 30/08/2024 | 20 | MAKALI ENGINEERING CORPORATION | 4.17 | 0 | 100
2148 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Binodnagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000278/2022-2023 | 1133/NACD-II | 16/12/2022 | 30 | GENUINE | 21.45 | 8.52 | 100
2149 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Mobarakpur, Binodnagar & Taranipur Water Supply Scheme of capacity 93 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000282/2023-2024 | 152/NACD-II | 02/02/2024 | 598 | B.M. ENGINEERING & CONSTRUCTION | 241.81 | 0 | 0
2150 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 46.51 cum/Hour capacity for Binodnagar Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000296/2024-2025 | 1475/NACD-II | 12/11/2024 | 395 | B.M. ENGINEERING & CONSTRUCTION | 177.87 | 0 | 0
2151 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Binodnagar Water Supply Scheme and other necessary allied works in this connection of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000390/2022-2023 | 397/NACD-II | 28/03/2023 | 903 | B.M. ENGINEERING & CONSTRUCTION | 298.5 | 0 | 52
2152 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000019/2022-2023 | 1089/NACD-II | 09/12/2022 | 0 | Resource Division | 33.57 | 0 | 0
2153 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000029/2022-2023 | 374/NACD-II | 24/03/2023 | 0 | Resource Division | 11.09 | 0 | 0
2154 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supplimentary Quotation for new service connection against Application No-3004365000 for NSC at Rajapur P.H-II w/s scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00070/2024-2025 | BP-07-24-25 | 23/04/2024 | 0 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 0.74 | 0 | 0
2155 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection at Pump House-I under Rajapur Water Supply Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/01878/2023-2024 | BP-111-23-24 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.88 | 0 | 0
2156 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection at Pump House-II under Rajapur Water Supply Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/01879/2023-2024 | BP-110-23-24 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.66 | 0 | 0
2157 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at RAJAPUR Piped Water Supply Scheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001123/2023-2024 | 4711/EMD | 04/08/2023 | 30 | INDIA ENTERPRISE | 40.8 | 0 | 0
2158 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00020/2023-2024 | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
2159 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00093/2022-2023 | 235/8 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0
2160 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000001/2025-2026 | 428/NACD-II | 07/04/2025 | 180 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 30
2161 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction for priliminary work of the approch road at Head Works site of Rajapur Water Supply Scheme in Tehatta-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000045/2023-2024 | 410/AE-I/NACD-II | 08/08/2023 | 15 | JOY HIND TUBEWELLS | 0.97 | 0 | 0
2162 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000080/2025-2026 | 736/NACD-II | 18/06/2025 | 90 | JOY HIND TUBEWELLS | 186.42 | 0 | 40
2163 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Rajapur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000100/2023-2024 | 1132/NACD-II | 09/10/2023 | 45 | SANJIT DAS | 11.34 | 0 | 90
2164 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University (Name of PWSS Rajapur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000115/2023-2024 | 1154/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
2165 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 53.24 cum/Hour capacity for Rajapur Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000261/2024-2025 | 1399/NACD-II | 23/10/2024 | 360 | JOY HIND TUBEWELLS | 185.73 | 0 | 0
2166 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Rajapur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000281/2022-2023 | 1136/NACD-II | 16/12/2022 | 30 | AUXILIARY TUBE WELL DRILLERS | 21.03 | 18.4 | 100
2167 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Bahadurpur & Rajapur Water Supply Scheme of capacity 16 Cu.m/hr under in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000308/2023-2024 | 424/NACD-II | 15/03/2024 | 420 | CHAKRABORTTI ENTERPRISE | 92.52 | 0 | 70
2168 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Rajapur water supply scheme under Tehatta- I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000332/2023-2024 | 408/NACD-II | 13/03/2024 | 315 | DEBASIS SAMADDAR | 26.21 | 0 | 1
2169 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Arsenic cum Iron treatment Plant of Khanjipur PWSS (Capacity- 21 m3/hr) and ancillary works of Rajapur W/s Scheme at Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000340/2023-2024 | 38/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 61.75 | 0 | 70
2170 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Rajapur Water Supply Scheme and other necessary allied works in this connection of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000392/2022-2023 | 401/NACD-II | 28/03/2023 | 1094 | JOY HIND TUBEWELLS | 442.76 | 0 | 40
2171 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000001/2023-2024 | 74/NACD-II | 15/01/2024 | 0 | Resource Division | 12.69 | 0 | 0
2172 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000021/2022-2023 | 1091/NACD-II | 09/12/2022 | 0 | Resource Division | 27.83 | 0 | 0
2173 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000030/2022-2023 | 376/NACD-II | 24/03/2023 | 0 | Resource Division | 12.69 | 0 | 0
2174 | Nadia Division | Ranaghat Sub-Division | Route Survey, Design of Distribution Network and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno for Anjangarh Water Supply Scheme in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000043/2023-2024 | 424/RSD | 08/05/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.45 | 2.45 | 0
2175 | Nadia Division | Ranaghat Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Anjangarh to accommodate FHTC within Ranaghat-I block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2024-2025 | 4126/ND | 29/07/2024 | 180 | G.D. CONSTRUCTION AND CO. | 161.1 | 0 | 0
2176 | Nadia Division | Ranaghat Sub-Division | Area development at Anjangarh W/S Scheme under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000127/2024-2025 | 767(C)RSD | 23/07/2024 | 60 | ANJALI ENTERPRISE | 3 | 0 | 100
2177 | Nadia Division | Ranaghat Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme forAnjangarh Water Supply scheme under Ranaghat Block in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000401/2023-2024 | 5210/ND | 23/11/2023 | 450 | M/S A.K.CONSTRUCTION | 26.37 | 0 | 95
2178 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials SOIL INVESTIGATION FOR CONSTRUCTION OF OHR all complete for Ground Water Based Water Supply Scheme for Anjangarh to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000448/2022-2023 | 963/ND | 09/03/2023 | 815 | M/S BISWAS BROTHERS, VIVEKNAGAR, P.O-NOAPARA, P.S-BARASAT, KOLKATA-700125 | 135.42 | 78.87 | 95
2179 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000035/2023-2024 | 1871/ND | 26/04/2023 | 0 | Resource Division | 11.91 | 0 | 0
2180 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000099/2023-2024 | 2586/ND | 13/06/2023 | 0 | Resource Division | 11.91 | 0 | 0
2181 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000157/2023-2024 | 272/ND | 11/01/2024 | 0 | Resource Division | 3.55 | 0 | 0
2182 | Central Drilling | Ranaghat Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR ANJANGARH W/S SCHEME (TW-I & II), RANAGHAT-I BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000124/2023-2024 | 1230/CDD | 04/09/2023 | 30 | MENAKA ENTERPRISE | 37.76 | 0 | 100
2183 | Eastern Mechanical | Ranaghat Sub-Division | New Service connection Charges for ANJANGARH Piped Water supply scheme PUMP House No- II | Assistant Engineer | Junior Engineer | BILL/00608/2024-2025 | BP-37-24-25 | 31/05/2024 | 0 | WBSEDCL BADKULLA CCC | 3.8 | 0 | 0
2184 | Eastern Mechanical | Ranaghat Sub-Division | NEW SERVICE CONNECTION CHARGES FOR ANJANGARH PWSS PH-I (HEAD WORK SITE) | Assistant Engineer | Junior Engineer | BILL/00737/2024-2025 | BP-52-24-25 | 21/06/2024 | 0 | WBSEDCL BADKULLA CCC | 7.88 | 0 | 0
2185 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Anjangarh ground water based water supply scheme under Block_ Ranaghat-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002814/2023-2024 | 803/EMD | 11/03/2024 | 475 | S.G. ENTERPRISE | 25.38 | 0 | 85
2186 | Eastern Mechanical | Ranaghat Sub-Division | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Anjangarh Piped Water Supply Scheme Block_ Ranaghat-I Dist. - Nadia under EMD, PHE Dte. 2024_PHED_664112_3 | Assistant Engineer | Junior Engineer | ORD/003003/2023-2024 | 925/EMD | 15/03/2024 | 30 | DEY ENTERPRISE | 42.34 | 0 | 0
2187 | Nadia Division | Tehatta Sub-Division | Renovation of AIRP (Gravity Type) of capacity 31.44 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Madhpur PWSS under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000546/2022-2023 | 1456/ND | 31/03/2023 | 360 | APURBA MANDAL | 58.68 | 0 | 21
2188 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000183/2022-2023 | 141/ND | 06/01/2023 | 0 | Resource Division | 1.24 | 0 | 0
2189 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Ber Ramchandrapur Zone-I W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000241/2020-2021 | 59/ND | 07/01/2021 | 75 | JOY HIND TUBEWELL'S | 55.08 | 1.98 | 100
2190 | Nadia Division | RWS Nadia Sub-Division | Retrofitting of Providing FHTC at Ground Water based Ber Ramchandrapur Zone-I Water Supply Scheme within Karimpur-I Block (Phase-1). | Assistant Engineer |  | VCH/000379/2021-2022 | 232/PFMS | 05/10/2021 | 0 | MALI CONSTRUCTION | 2.35 | 0 | 0
2191 | Nadia Division | RWS Nadia Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT BER-RAM CHANDRAPUR Z-1 | Assistant Engineer |  | VCH/001072/2020-2021 | 460/DW | 30/03/2021 | 0 | JOY HIND TUBEWELL'S | 40.81 | 0 | 0
2192 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Goalsalua Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000129/2021-2022 | 77/NAD-I | 17/01/2022 | 90 | M/S NIBHAS SINHA | 110.34 | 106.66 | 100
2193 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, pathway and others allied works at Head Work site of Goalsalua, Zone-II under Nadia Arsenic Division-I, P.H.E. Dte. Length of Boundary wall - 156 metre. | Assistant Engineer-II | Junior Engineer-III | ORD/000133/2021-2022 | 73/NAD-I | 17/01/2022 | 30 | D.K. CONSTRUCTION | 17.59 | 13.75 | 95
2194 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying Dedicated Pipe line to supply water for Pachberia Coloni Area under Goalsalua Zone II Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 06) | Assistant Engineer-II | Junior Engineer-III | ORD/000168/2024-2025 | 1949/NAD-I | 27/11/2024 | 480 | BIPLAB GUHA | 70.82 | 0 | 52
2195 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentaton of Distribution pipeline at Rajapur , Kesaipur village under Goalsalua Zone II water supply scheme at Ranaghat-II Block by providing FHTCs & dedicated pipeline from common manifold under Nadia Arsenic Division-I, PHE Dte as a part of JJM. (Sl. NO. 05) | Assistant Engineer-II | Junior Engineer-III | ORD/000170/2024-2025 | 2057/NAD-I | 09/12/2024 | 60 | SUMIT GHOSH | 91.9 | 0 | 0
2196 | Nadia Division | RWS Nadia Sub-Division | Additional Laying of UPVC Pipeline and providing FHTC including supplying, laying, fitting, fixing of 15 mm NB PVC pipe with all necessary specials, saddle piece etc.in connection to the Augmentation of Ground Based piped water supply scheme at Bablari-Dewanganj to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000016/2023-2024 | 1847/ND | 26/04/2023 | 60 | A.K.ADHIKARY | 15.77 | 13.78 | 95
2197 | Nadia Division | RWS Nadia Sub-Division | Sinking of 1 No. Big Dia Tubewell 300mm. x 200mm & 200 mtr deep by Direct Rotary Rig Method using PVC pipe & UPVC deep well screen (RDS) pipes with Ribs etc. including inter connection of Rising Main System for Paschim Bhatjangla Zone-II Water Supply Scheme at Head Work Site under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000187/2024-2025 | 5035/ND | 13/09/2024 | 45 | ZEST INFRACON | 16.29 | 0 | 60
2198 | Nadia Division | RWS Nadia Sub-Division | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Banpur ii) Dakshinpara (Zone-I)iii) Dakshinpara (Zone-II) iv) Kamgachi (Zone-I)(Part-I) v)Kamgachi (Zone-I)(Part-II)vi)Kamgachi (Zone-II)(Part-I) vii) Kamgachi (Zone-II)(Part-II) | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000440/2022-2023 | 246/Kly SD-I | 27/02/2023 | 181 | HORIZEN | 4.99 | 3.4 | 100
2199 | Nadia Division | RWS Nadia Sub-Division | Additional work of Laying Distribution System and additional work of Providing FHTC in connection with Augmentation of Paschim Bhatjangla Zone-II Water Supply Scheme under RWS Nadia Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000472/2023-2024 | 147/ND | 09/01/2024 | 450 | M/S A.K. ENTERPRISE | 33.76 | 0 | 70
2200 | Nadia Division | RWS Nadia Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
2201 | Nadia Division | RWS Nadia Sub-Division | Providing FHTC by augmentation under Jal Swapna for Paschim Bhatjangla Zone-II Water Supply Scheme in Krishnagar-I Block of Nadia District. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000496/2021-2022 | 67/ND | 05/01/2022 | 90 | JAGANNATH ENTERPRISE | 68.71 | 46.42 | 100
2202 | Nadia Division | RWS Nadia Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir, Pump House, Boundary Wall and Construction of Service Road for Paschim Bhatjangla Zone-II Water Supply Scheme under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000669/2023-2024 | 6117/ND | 21/12/2023 | 540 | KESHOB ENTERPRISE | 29.88 | 0 | 80
2203 | Nadia Division | RWS Nadia Sub-Division | Construction Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 31.00 cum/hr at Paschim Bhatjangla water supply scheme including 3 Months Trial Run & 3 Years O&M within Krishnagar-I block under RWS Nadia Sub-division under Nadia Division, P.H.E. Dte | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000707/2023-2024 | 1251/ND | 22/02/2024 | 180 | APURBA MANDAL | 163.44 | 0 | 45
2204 | Nadia Division | RWS Nadia Sub-Division | Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000769/2023-2024 | 1821/ND | 14/03/2024 | 31 | IMAGIN | 34.21 | 0 | 60
2205 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | RTOR000041/2022-2023 | 4294/ND | 29/09/2022 | 0 | Resource Division | 1.21 | 0 | 0
2206 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | RTOR000132/2021-2022 | 1262/ND | 16/03/2022 | 0 | Resource Division | 1.72 | 0 | 0
2207 | Nadia Division | RWS Nadia Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | VCH/001050/2021-2022 | 608/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.82 | 0 | 0
2208 | Eastern Mechanical | RWS Nadia Sub-Division | Deposit works, and new service connection under bhatjangla W/S Scheme. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | BILL/03721/2023-2024 | BP-240-23-24 | 04/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.21 | 0 | 0
2209 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer etc for Augmentation to Accommodate FHTC at Pump House No.II Zone II under Paschim Bhatjangla WS Scheme, Block Krishnagar 1, Dist. Nadia under Eastern Mechanical Division, PHE Dte. NIET No.- 22 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000705/2022-2023 | 6505/EMD | 01/12/2022 | 30 | M/S. PS & ASSOCIATES | 4.38 | 4.28 | 90
2210 | Eastern Mechanical | RWS Nadia Sub-Division | Supplementary works to completion of ongoing FHTC-related work at PH-I of Paschim Bhatjangla (Zone - II) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/001404/2023-2024 | 616/EMSD-II | 24/08/2023 | 15 | STANDARD ENGINEERING | 0.21 | 0 | 100
2211 | Eastern Mechanical | RWS Nadia Sub-Division | Supplimentary works to completion of ongoing FHTC-related work at PH-II of Paschim Bhatjangla (Zone-II) W/S Scheme (Block - Krishnagar - I), PHE Dte., dist.- Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/002019/2023-2024 | 593/EMSD-II | 21/08/2023 | 15 | M/S. PS & ASSOCIATES | 0.15 | 0 | 100
2212 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No.I(Zone-II) under Paschim Bhatjangla W/S Scheme, Block-Krishnagar 1, District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/002695/2022-2023 | 3912EMD | 19/10/2022 | 30 | STANDARD ENGINEERING | 7.97 | 7.97 | 80
2213 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Quotation for new service connection charges and security deposit for Satiakhali part- A | Assistant Engineer | Junior Engineer | BILL/02316/2024-2025 | BP-199-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 0.1 | 0 | 0
2214 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 80
2215 | Nadia Arsenic Civil Division II | Eastern Mechanical Sub Division-III | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Shatikhali (Part-A) of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer | Junior Engineer | ORD/000022/2023-2024 | 562/NACD-II | 11/05/2023 | 990 | M/S GHOSH CONSTRUCTION | 30.05 | 0 | 80
2216 | Nadia Arsenic Division I |  | SHIFTING OF POLE AT GANGNAPUR PHE |  |  | BILL/00124/2024-2025 | 100/PFMS | 11/07/2024 | 0 | W.B.S.E.D.C.L (GANGNAPURC.C.C) | 0.41 | 0 | 0
2217 | Nadia Arsenic Division I |  | Bill for Wayleave/Track crossing proposal with Application ID ER-SDAH-2023-WL-32 in IR-RBCS has been approved in-principle subject to the payment of Wayleave facility. |  |  | BILL/00131/2023-2024 | 147/PFMS | 04/07/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.91 | 0 | 0
2218 | Nadia Arsenic Division I |  | Bill for Wayleave/Track crossing proposal with Application ID ER-SDAH-2023-WL-31 in IR-RBCS has been approved in-principle subject to the payment of Wayleave facility. |  |  | BILL/00132/2023-2024 | 146/PFMS | 04/07/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 6.15 | 0 | 0
2219 | Nadia Arsenic Division I |  | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-49 in IR-RBCS is pending for payment. |  |  | BILL/00191/2023-2024 | 179/PFMS | 04/08/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.15 | 0 | 0
2220 | Nadia Arsenic Division I |  | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-50 in IR-RBCS is pending for payment. |  |  | BILL/00192/2023-2024 | 178/PFMS | 04/08/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.22 | 0 | 0
2221 | Nadia Arsenic Division I |  | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-51 in IR-RBCS is pending for payment. |  |  | BILL/00193/2023-2024 | 180/PFMS | 04/08/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.3 | 0 | 0
2222 | Nadia Arsenic Division I |  | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-52 in IR-RBCS is pending for payment. |  |  | BILL/00194/2023-2024 | 177/PFMS | 04/08/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0
2223 | Nadia Arsenic Division I |  | Bill for Taherpur flag to Badkulla station railway crossing for JJM works under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00273/2023-2024 | 220/PFMS | 20/09/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.25 | 0 | 0
2224 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-49 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00278/2023-2024 | 221/PFMS | 20/09/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 9.96 | 0 | 0
2225 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-50 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00279/2023-2024 | 240/PFMS | 20/09/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 14.94 | 0 | 0
2226 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-51 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00381/2023-2024 | 340/PFMS | 13/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 19.06 | 0 | 0
2227 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-73 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00438/2023-2024 | 345/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0
2228 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-74 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00439/2023-2024 | 346/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0
2229 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-72 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00440/2023-2024 | 347/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0
2230 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-71 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00441/2023-2024 | 348/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0
2231 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-75 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00442/2023-2024 | 349/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.32 | 0 | 0
2232 | Nadia Arsenic Division I |  | Shifting of Electric Pole from the proposed GLR Site inside the Campus of water Management Research Station, Begopara (Patuli) Ranaghat-II Block, under Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00506/2023-2024 | 396/PFMS | 18/12/2023 | 0 | WBSEDCL | 0.06 | 0 | 0
2233 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-71 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00561/2023-2024 | 437/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.35 | 0 | 0
2234 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-72 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00562/2023-2024 | 438/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.27 | 0 | 0
2235 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-73 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00563/2023-2024 | 439/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.27 | 0 | 0
2236 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-74 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00564/2023-2024 | 441/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 4.93 | 0 | 0
2237 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-75 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00565/2023-2024 | 442/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 20.56 | 0 | 0
2238 | Nadia Arsenic Division I |  | Carriage of DI pipes including Pipe carrying structure, road restoration, repair of damaged UPVC pipeline, crossing of pipeline by jack pushing, pathway and allied works related to Integrated Surface Water Based Water Supply Scheme under Ranaghat-I & II Blocks under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 04) |  |  | ORD/000111/2025-2026 | 786/NAD-I | 12/08/2025 | 120 | AMAL DUTTA ROY | 559.99 | 0 | 0
2239 | Nadia Arsenic Division I |  | Supply of documents for way leave permission from the Eastern Railways authority at 2 nos of locations on Ranaghat-Krishnagar, Ranaghat -Shantipur&Ranaghat-Bongaon Railway track under Intregrated surface Water Based PWSS for Ranaghat-I & II Block under Nadia Arsenic Division-I, PHE Dte. Intersection Name: 1) AV24- AV28 Birnagar Rail Gate) 2) AV61- AV64 Taherpur Rail Gate) |  |  | ORD/000114/2023-2024 | 309/AE-I/NAD-I | 28/07/2023 | 90 | SUMAN CHAKRABORTY | 3.84 | 0 | 100
2240 | Nadia Arsenic Division I |  | Preparation of Detailed Project Report (DPR) for Integrated Surface Water Based PWSS for Ranaghat-I & Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) |  |  | ORD/000116/2023-2024 | 1610/NAD-I | 22/06/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 57.65 | 57.65 | 100
2241 | Nadia Arsenic Division I |  | Laying of DI Rising Main of Ranaghat I & II Block, Construction of 4 Nos. 100 Cum GLR, 1 No 50 Cum GLR, Construction of 900, 500, 150& 2 Nos. 1500 M3 OHR at Different Location, 6 Nos. Chlorine Room & 5 Nos. Pump House of Integrated Surface Water Based PWSS for Ranaghat-I and Ranaghat-II Block under Nadia Arsenis Division-I P.H.E. Dte (Sl.no.01) |  |  | ORD/000135/2023-2024 | 1897/NAD-I | 14/08/2023 | 1095 | AMAL DUTTA ROY | 3770.77 | 0 | 90
2242 | Nadia Arsenic Division I |  | Laying and repairing of damaged UPVC pipeline of different existing piped water supply schemes under PHED at Ranaghat-I & II Block due to laying of DI Secondary Rising main under Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block, including restoration of village roads by Jhama Metal, Rail/National Way Crossing of pipeline, Pipe Carriage and allied works Under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000174/2024-2025 | 1748/NAD-I | 24/10/2024 | 270 | AMAL DUTTA ROY | 474.38 | 0 | 80
2243 | Nadia Arsenic Division I |  | Name of Work: Supply of documents for way leave permission from the Eastern Railways authority at 9 nos of locations on Ranaghat- Krishnagar, Ranaghat- Shantipur & Ranaghat-Bongaon Railway track under Intregrated Surface Water Based PWSS for Ranaghat-I & II Block under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000236/2023-2024 | 2343/NAD-I | 03/10/2023 | 25 | SATYABRATA CHAKRABORTY | 17.28 | 0 | 100
2244 | Nadia Arsenic Division I |  | Pond side earth protection with Eucalyptus bullah piling at Kamgachi GLR Site within Ranaght-II Block under Nadia Arsenic Division-I,P.H.E. Dte. |  |  | ORD/000303/2023-2024 | 96/AE-I/NAD-I | 27/02/2024 | 15 | R R ENTERPRISE | 4.38 | 0 | 100
2245 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1085/NAD-I | 25/04/2023 | 0 | Resource Division | 1599.91 | 0 | 0
2246 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1874/NAD-I | 10/08/2023 | 0 | Resource Division | 1012.08 | 0 | 0
2247 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1887/NAD-I | 11/08/2023 | 0 | Resource Division | 1117.16 | 0 | 0
2248 | Eastern Mechanical |  | Earnest money for new service connection at Ranaghat GLR-1 of integrated surface water based PWSS. |  |  | BILL/01919/2023-2024 | BP-126-23-24 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.05 | 0 | 0
2249 | Eastern Mechanical |  | New Service Connection and security deposit for new bulk power supply at Kamgachi Zone-I W/S Scheme. |  |  | BILL/04121/2023-2024 | BP-258-23-24 | 29/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 43.18 | 0 | 0
2250 | Eastern Mechanical |  | Providing Electro-Mechanical Equipment for 11/0.433 KV Sub-station along with pumping station and disinfection arrangement for GLR-I at Kamgachi under Surface based Water Supply Scheme for Ranaghat-I Block in the District of Nadia. |  |  | ORD/001685/2023-2024 | 6260/EMD | 10/10/2023 | 629 | WEST BENGAL ENGINEERING CO. | 733.62 | 0 | 53
2251 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP (Gravity Type) of capacity 93.00 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Senpur PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000028/2023-2024 | 1786/ND | 20/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 234.23 | 91.06 | 57
2252 | Eastern Mechanical | RWS Nadia Sub-Division | WBSEDCL's Quotation of new service connection in Bulk contract demand to the Head Work site under Senpur W/S Scheme in Krishnagar-I Block , PHE Dte. Nadia (Application No.3004752314) | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | BILL/00749/2024-2025 | BP-53-24-25 | 21/06/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 3.47 | 0 | 0
2253 | Eastern Mechanical | RWS Nadia Sub-Division | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Senpur (Phase-II) Piped Water Supply Scheme, Block: Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/001751/2023-2024 | 6362/EMD | 17/10/2023 | 30 | TARUN KUMAR BHATTACHARYA | 53.52 | 0 | 0
2254 | Nadia Arsenic Division I | Nadia Arsenic Division I | Work for revamping / upgradation of the hydraulic parameters at Mamjoani mouzas in reference to Mamjoani water supply scheme & Duttaphulia water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 07) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000007/2025-2026 | 76/NAD-1 | 16/04/2025 | 240 | JOYGOPAL GUPTI | 96.49 | 0 | 57
2255 | Nadia Arsenic Division I | Nadia Arsenic Division I | Work for revamping / upgradation of the hydraulic parameters at Kamdanga and Nasra Mouza in reference to Nasra and Aranghata water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000028/2025-2026 | 158/NAD-I | 28/04/2025 | 60 | SAFTI PRIVATE LIMITED | 77.16 | 0 | 0
2256 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Duttaphulia Zone-I Ground Based Water Supply Scheme under Ranaghat- II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Duttaphulia Zone-I (Phase-I) under JJM (Sl.no.10) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000044/2023-2024 | 1365 /NAD-I | 12/05/2023 | 15 | M/S ARATI ENTERPRISE | 13.04 | 0 | 100
2257 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Duttaphulia Zone-I (Part-I) at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Duttaphulia Zone-I Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000094/2022-2023 | 1941/NAD-I | 13/10/2022 | 90 | MONDAL ENTERPRISE | 323.87 | 244.15 | 95
2258 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for preparation of DPR for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for DUTTAPULIA ZONE-I Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic-I Division, PHE Dte. (Sl. No.-07) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000207/2021-2022 | 68/AE-II/N.A.D.-I | 24/02/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 4.74 | 4.74 | 100
2259 | Nadia Arsenic Division I | Nadia Arsenic Division I | Distribution Design for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Duttapulia Zone - I Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000224/2021-2022 | 69/AE-II/NAD-I | 24/02/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 3.5 | 3.5 | 100
2260 | Nadia Arsenic Division I | Nadia Arsenic Division I | Renovation of IEP (110m3/hr.) at Duttaphulia Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000229/2023-2024 | 2297/NAD-I | 29/09/2023 | 491 | SATYABRATA CHAKRABORTY | 14.82 | 0 | 100
2261 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at .Barberia Colony Paschimpara, Dakshinpara, Kushberia, Paschim para Mouza inconnection with Augmentation to accommodate FHTC under JJM for Duttaphulia Zone- I Ground water based piped water supply scheme (Phase- I) Block- Ranaghat -II under JJM Dist- Nadia under Nadia Arsenic Division-I, PHE Dte. (sl.no10) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000245/2022-2023 | 570/NAD-I | 16/03/2023 | 21 | MONDAL ENTERPRISE | 34.86 | 28.92 | 0
2262 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | RTOR000012/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 14.67 | 0 | 0
2263 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Duttapulia, Zone-I (Phase-I) under Block_ Ranaghat-II, Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/10663) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000167/2025-2026 | 1165/EMD | 04/06/2025 | 90 | TAMAL ENTERPRISE | 4.34 | 0 | 0
2264 | Eastern Mechanical | Nadia Arsenic Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II and III (Zone-I) (Phase-I) under Duttapulia ground water based water supply scheme under Block_ Ranaghat-II Dist. - Nadia under EMD, PHE Dte. (SM/10663) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000642/2024-2025 | 2679/EMD | 20/11/2024 | 30 | GHOSE ENGINEERING SYNDICATE | 32.64 | 0 | 0
2265 | Nadia Division | Ranaghat Sub-Division | Construction of 87.00 mtr long Boundary Wall (2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-II, Pump House no-III under Ranaghat Sub-Div , Nadia Division PHE. Dte. | Assistant Engineer |  | ORD/000082/2025-2026 | 2465/ND | 27/05/2025 | 180 | DEY ENTERPRISE | 9.28 | 0 | 0
2266 | Nadia Division | Ranaghat Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 210 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Fulia Township Zone-II to accommodate FHTC within Santipur block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000090/2024-2025 | 4314/ND | 06/08/2024 | 540 | MONDAL PRECISION PRIVATE LIMITED | 452.47 | 0 | 0
2267 | Nadia Division | Ranaghat Sub-Division | Construction and installation of MANIFOLD and allied works at Head Works site under Fulia Zone-II Ground Based Water Supply Scheme under Santipur Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | Assistant Engineer |  | ORD/000157/2025-2026 | 3255/ND | 10/07/2025 | 90 | MANARAMA ENTERPRISE | 11.7 | 0 | 0
2268 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials,saddle piece etc. all complete Construction Of 1000 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection And Cost Of Pipes, Specials & Soil Investigation For Construction Of One No. 1000 Cum OHR Of Staging Height 20 Mtr. for augmentation of Ground Water Based Water Supply Scheme For Fulia Township Zone-II to accommodate FHTC in Santipur block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000204/2023-2024 | 3539/ND | 11/08/2023 | 731 | AMAL DUTTA ROY | 915.05 | 0 | 81
2269 | Nadia Division | Ranaghat Sub-Division | Route Survey, Design of Distribution Network and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno for Fulia Township (Zone-II) Water Supply Scheme in Santipur Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000242/2023-2024 | 421/RSD | 08/05/2023 | 15 | HORIZEN | 3.1 | 3.1 | 100
2270 | Nadia Division | Ranaghat Sub-Division | Fencing with R.C.C. pillar (9 nos Govt. Land) at different locations under Fulia Zone- I & II water supply scheme under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000290/2023-2024 | 911/RSD | 13/09/2023 | 15 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 3.22 | 0 | 100
2271 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
2272 | Nadia Division | Ranaghat Sub-Division | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Tube well No-3 site at Fulia Zone-II Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | Assistant Engineer |  | ORD/000297/2023-2024 | 925/RSD | 14/09/2023 | 75 | HANDICRAFT CONSTRUCTION | 4.46 | 0 | 100
2273 | Nadia Division | Ranaghat Sub-Division | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Tube well No-4 site at Fulia Zone-II Water supply scheme under Ranaghat Sub - Division, PHE Dte. | Assistant Engineer |  | ORD/000298/2023-2024 | 926/RSD | 14/09/2023 | 75 | B K ENGINEERING | 4.46 | 0 | 100
2274 | Nadia Division | Ranaghat Sub-Division | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Tube well No-6 site at Fulia Zone-II Water supply scheme under Ranaghat Sub - Division, PHE Dte. | Assistant Engineer |  | ORD/000299/2023-2024 | 927/RSD | 14/09/2023 | 75 | SREE GURU CONSTRUCATION | 4.46 | 0 | 100
2275 | Nadia Division | Ranaghat Sub-Division | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Fulia Zone-II Water Supply Scheme Under Ranaghat Sub-Division PHE Dte.) | Assistant Engineer |  | ORD/000399/2023-2024 | 5189/ND | 22/11/2023 | 90 | MRINAL DASGUPTA | 6.89 | 0 | 100
2276 | Nadia Division | Ranaghat Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
2277 | Nadia Division | Ranaghat Sub-Division | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Tube well No-5 site at Fulia Zone-II Water supply scheme under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000650/2023-2024 | 124/RSD | 29/01/2024 | 60 | M/S ASIT ROY BHOWMICK | 4.36 | 0 | 100
2278 | Nadia Division | Ranaghat Sub-Division | Construction of 94.00 mtr long Boundary Wall (2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-II, Pump House no-VI under Ranaghat Sub-Div , Nadia Division PHE. Dte. | Assistant Engineer |  | ORD/000772/2024-2025 | 659/ND | 11/02/2025 | 90 | SADHANA CONSTRUCTION CO. | 8.07 | 0 | 0
2279 | Nadia Division | Ranaghat Sub-Division | Construction of 49.00 mtr long Boundary Wall (2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-II, Pump House no-V under Ranaghat Sub-Division, Nadia Division PHE. Dte. | Assistant Engineer |  | ORD/000797/2024-2025 | 88/RSD | 14/01/2025 | 75 | M/S KM ENTERPRISE | 5.43 | 0 | 0
2280 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000004/2024-2025 | 3688/ND | 03/07/2024 | 0 | Resource Division | 44.99 | 0 | 0
2281 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000014/2024-2025 | 7562/ND | 27/12/2024 | 0 | Resource Division | 51.02 | 0 | 0
2282 | Central Drilling | Ranaghat Sub-Division | Providing drilling crew and other allied works lbr construction olTube Well (300mm X200rrnr X 250 Mtrs. Depth) by utilising Depanmental Machineries for Fulia Tor'r,nship WiS Scherne (Z- Il, 'l'/W-l),Santipur Block r-rnder Nadia District, Central Drilling Division, P.H E. Dte. | Assistant Engineer |  | ORD/000093/2023-2024 | 1006/CDD | 09/08/2023 | 30 | UTTAM KUMAR CHATTERJEE | 18.88 | 0 | 0
2283 | Central Drilling | Ranaghat Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBEWELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR FULIA TOWNSHIP W/S SCHEME (Z-II, TW-I), SANTIPUR BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | Assistant Engineer |  | ORD/000111/2023-2024 | 878/CDD | 11/07/2023 | 30 | UTTAM KUMAR CHATTERJEE | 18.88 | 0 | 100
2284 | Central Drilling | Ranaghat Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Badkulla/FULIA TOWNSHIP (Z-II) PWSS W/S Scheme(TW-II) , under Nadia District, Central Drilling Division, P.H.E. Dte | Assistant Engineer |  | ORD/000143/2023-2024 | 1660/CDD | 17/10/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 18.85 | 0 | 100
2285 | Eastern Mechanical | Ranaghat Sub-Division | service connection charges for fulia township | Assistant Engineer |  | BILL/00975/2024-2025 | BP-65-24-25 | 10/07/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 9.54 | 0 | 0
2286 | Eastern Mechanical | Ranaghat Sub-Division | New power connection charges for FULIA Water supply scheme -II, Pump House No-III | Assistant Engineer |  | BILL/02293/2024-2025 | BP-188-24-25 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 3.46 | 0 | 0
2287 | Eastern Mechanical | Ranaghat Sub-Division | New Power connection charges for FULIA Water supply scheme Z-II Pump House No- V | Assistant Engineer |  | BILL/02294/2024-2025 | BP-189-24-25 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 3.85 | 0 | 0
2288 | Eastern Mechanical | Ranaghat Sub-Division | New power connection charges for FULIA Water Supply scheme Z - II , Pump House No - II | Assistant Engineer |  | BILL/02295/2024-2025 | BP-190-24-25 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 3.52 | 0 | 0
2289 | Eastern Mechanical | Ranaghat Sub-Division | New Power Connection Charges for FULIA Water Supply Scheme Z-II, Pump House - IV | Assistant Engineer |  | BILL/02296/2024-2025 | BP-191-24-25 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 7.91 | 0 | 0
2290 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, II , III, IV , V and VI (New) , Zone-II under Fulia Town Ship ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. [SM-18374] | Assistant Engineer |  | ORD/000341/2024-2025 | 2156/EMD | 30/08/2024 | 30 | CONCORD EMC ENCLAVE LLP | 75.36 | 0 | 0
2291 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-II, within Krishnagar-II & Nabadwip Block (Phase-A, Retrofitting)" | Assistant Engineer |  | ORD/000396/2020-2021 | 772/ND | 10/02/2021 | 90 | IJABUL SK. | 97.11 | 18.25 | 0
2292 | Nadia Division | Krishnanagar Sub-Division | PROVIDIDING FHTC AT SURFACE WATER BAESD WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II,ZONE-VIII, WITHIN KRISHNAGAR-II & NABADWIP ( PART) BLOCK, PHASE-A. | Assistant Engineer |  | VCH/000890/2021-2022 | 500/PFMS | 03/02/2022 | 0 | M/S R. DUTTA & CO. | 0.47 | 0 | 0
2293 | Nadia Division | Krishnanagar Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT PART-3 Z-2 | Assistant Engineer |  | VCH/001076/2020-2021 | 460/DW | 30/03/2021 | 0 | IJABUL SK. | 73.34 | 0 | 0
2294 | Nadia Division | Ranaghat Sub-Division | Providing Functional Household Tap Connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Habibpur to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-I) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000341/2022-2023 | 240/ND | 13/01/2023 | 812 | M/S DIPAK ENTERPRISE | 401.25 | 334.94 | 95
2295 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000032/2023-2024 | 1869/ND | 26/04/2023 | 0 | Resource Division | 28.48 | 0 | 0
2296 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000070/2023-2024 | 2293/ND | 29/05/2023 | 0 | Resource Division | 21.56 | 0 | 0
2297 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000102/2023-2024 | 3542/ND | 11/08/2023 | 0 | Resource Division | 105.14 | 0 | 0
2298 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000193/2022-2023 | 695/ND | 17/02/2023 | 0 | Resource Division | 69.17 | 0 | 0
2299 | Nadia Division | Ranaghat Sub-Division | Augmentation of Ground Water Based Habibpur PWSS to accommodate FHTC in Ranaghat-I block with in Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/000354/2022-2023 | 54/PFMS | 22/06/2022 | 0 | RADIANT | 3.21 | 0 | 0
2300 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HABIBPUR W/S Scheme, Block-Ranaghat I , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000015/2023-2024 | 1578/EMD | 24/04/2023 | 799 | BIDYUT KUMAR MUKHERJEE | 12.79 | 0 | 100
2301 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Work of Survey, Design, Drawing & DPR preparation for BAHIRGACHHI ZONE-II Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000007/2021-2022 | 1/AE-I/NACD-II | 06/05/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.66 | 5.31 | 100
2302 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Work of Survey, Design, Drawing & DPR preparation for BANSBERIA Water Supply Scheme in KRISHNANAGAR-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000008/2021-2022 | 2/AE-I/NACD-II | 06/05/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.94 | 5.87 | 100
2303 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Work of Survery, Design, Drawing & DPR preparation for CHANDPUR Water Supply Scheme in KRISHNANAGAR-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000009/2021-2022 | 3/AE-I/NACD-II | 06/05/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.92 | 5.84 | 100
2304 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Work of Survey, Design, Drawing & DPR preparation for HELENCHI ZONE-III Water Supply Scheme in KRISHNAGANJ Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000011/2021-2022 | 5/AE-I/NACD-II | 06/05/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 4.29 | 8.58 | 100
2305 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Work of Survey, Design, Drawing & DPR preparation for HELENCHI ZONE-II Water Supply Scheme in KRISHNAGANJ Block of Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000012/2021-2022 | 6/AE-I/NACD-II | 06/05/2021 | 7 | UMWELT ENGINEER PVT LTD. | 3.15 | 6.3 | 100
2306 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagbaria W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000026/2021-2022 | 519/NACD-II | 14/06/2021 | 45 | M/S SHILL & CO. | 55.01 | 75.3 | 100
2307 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Tengra Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000059/2023-2024 | 320_1/AE-I/NACD-II | 13/07/2023 | 7 | RISHAN ENGINEERING CONSULTANCY | 0.86 | 0 | 100
2308 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Refixing of existing ferrule connection broken due to heavy vehicular traffic including road restoration work at Madhabpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-Il P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000076/2021-2022 | 15/AE-II/NACD-II | 13/08/2021 | 10 | JOY HIND TUBEWELLS | 3.43 | 6.85 | 100
2309 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-II) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Helenchi Zone-III ( Village- Bhajanghat) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000077/2021-2022 | 16/AE-II/NACD-II | 13/08/2021 | 15 | SUMIT GHOSH | 4.96 | 9.9 | 100
2310 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Digri (Vill- Digri) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000087/2021-2022 | 687/NACD-II | 03/09/2021 | 10 | M/S RAJESH CONSTRUCTION | 4.99 | 9.97 | 100
2311 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also Bamboo Pilling at Baranaldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000100/2021-2022 | 737/NACD-II | 13/09/2021 | 45 | M/S ANUBHAB CONSTRUCTION | 62.35 | 124.69 | 100
2312 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr,Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Barnia (Vill- Avaynagar) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000107/2021-2022 | 130/AE-I/NACD-II | 14/09/2021 | 15 | M/S FREEDOM CONSTRUCTION | 4.5 | 8.99 | 100
2313 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000109/2021-2022 | 767/NACD-II | 22/09/2021 | 45 | JOY HIND TUBEWELLS | 94.04 | 188.28 | 100
2314 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Supply of 10 mm NB Gun-metal Ferrule conforming to IS:2692-1989 for Water Tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped Water Supply Scheme within Nadia Arsenic Civil Division-II PHE Dte. at NACD-II office godown, Krishnagar, Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000112/2021-2022 | 477/NACD-II | 07/05/2021 | 10 | INDIA PIPE FITTING CO. | 4.73 | 9.46 | 100
2315 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Supply of 10 mm NB Gun-metal Ferrule conforming to IS:2692-1989 for Water Tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped Water Supply Scheme within Nadia Arsenic Civil Division-II PHE Dte. at NACD-II office godown, Krishnagar, Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000113/2021-2022 | 488/NACD-II | 13/05/2021 | 10 | INDIA PIPE FITTING CO. | 4.73 | 9.46 | 100
2316 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Special repairing works of damaged old pipe line at Brittihuda including anciliary FHTC works at Arangsarisa of Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000121/2021-2022 | 136/AE-I/NACD-II | 28/10/2021 | 15 | JOY HIND TUBEWELLS | 5 | 10 | 100
2317 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and installation of Corona Guard (Brand- Eureka Forbes)(6 nos) and disinfection work at different office chambers at Nadia arsenic Civil Division-II, PHE Dte. Krishnagar, Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000290/2020-2021 | 312/NACD-II | 05/03/2021 | 5 | ABHISEK ENGINEERING CONCERN | 4.91 | 9.82 | 100
2318 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Tengra 2nd tube well Site under Tengra Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000328/2024-2025 | 1025/AE-I/NACD-II | 10/12/2024 | 30 | SHOVON KUMAR MODAK | 4.05 | 0 | 0
2319 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Conversion of IEP to AIRP at Tengra Water Supply Scheme of capacity 36Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000386/2024-2025 | 1360/NACD-II | 30/09/2024 | 60 | SUMIT GHOSH | 165.15 | 0 | 0
2320 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of 75mm dia pipeline alongwith FHTC reconnection Tengra W/S Scheme at Chapra block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000441/2024-2025 | 1204/AE-I/NACD-II | 27/02/2025 | 45 | ASHIM ENTERPRISE | 0.96 | 0 | 0
2321 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC under Brittihuda (Source Augmentation, Pritambarpur) ground water based water supply scheme under Block_ Chapra Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000030/2025-2026 | 702/EMD | 04/04/2025 | 30 | M/S. G.P. ENTERPRISE | 11.6 | 0 | 0
2322 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001768/2022-2023 | 1120/EMD | 16/03/2023 | 30 | B.T. PROJECTS PVT. LTD | 91.82 | 0 | 60
2323 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD and allied works at OHR site under Brittihuda Piped Water Supply Scheme under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000005/2023-2024 | 468/NACD-II | 20/04/2023 | 30 | M/S GHOSH CONSTRUCTION | 29.12 | 24.73 | 85
2324 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Route survey engaging qualified surveyors with modern instruments viz-GPS, Total station, DGPS, Auto levels etc over the command area of Brittihuda Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Brittihuda W/S Scheme in chapra Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000020/2023-2024 | 550/NACD_II | 11/05/2023 | 20 | MALLICK ENTERPRISE | 10.11 | 10.11 | 100
2325 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Provisioning of Alignment by Augmenting the Prevailing Mouza's at Brittihuda W/S Scheme for Pitambarpur, Dipchandrapur, village in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000048/2024-2025 | 720/NACD-II | 07/06/2024 | 180 | MALLICK ENTERPRISE | 127.03 | 0 | 100
2326 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000054/2022-2023 | 224/NACD-II | 05/04/2022 | 90 | MALLICK ENTERPRISE | 154.65 | 154.65 | 100
2327 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, Pincode:- 741101,West Bengal. (From 01/07/2024 to 30/06/2025) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000059/2024-2025 | 792/AE-I/NACD-II | 01/07/2024 | 365 | BABLU KUMAR SINGH | 4.98 | 0 | 0
2328 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Road Reastoration work along Brittihuda Ghosh Para of Brittihuda Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000076/2025-2026 | 115/AE-I/NACD-II | 04/06/2025 | 30 | SUMIT GHOSH | 4.78 | 0 | 0
2329 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000080/2025-2026 | 736/NACD-II | 18/06/2025 | 90 | JOY HIND TUBEWELLS | 186.42 | 0 | 40
2330 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and renovation works of R.C.C. Elevated Reservoir 900 cum for providing FHTC (Functional Household Tap Connection) for Brittihuda Water Supply Scheme in Chapra Block in Nadia District under Nadia Arsenic Civil Division- II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000109/2025-2026 | 939/NACD-II | 28/07/2025 | 90 | M/S.K.P.CONSTRUCTION | 29.21 | 0 | 0
2331 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of flow control devices in the closed water conduit at Brittihuda PWSS in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000131/2025-2026 | 224/AE-I/NACD-II | 01/09/2025 | 20 | MAKALI ENGINEERING CORPORATION | 4.57 | 0 | 100
2332 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 50 m3/hr capacity Iron Elimination Plant Mouza-Pitambarpur under habitation Balirmathpara under Brittihuda Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000139/2025-2026 | 1173/NACD-II | 09/09/2025 | 61 | SANJIB DEY | 23.07 | 0 | 0
2333 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Balance Laying of a dedicated UPVC pipeline for supplying drinking water from newly constructed manifold at Head Works site towards Arangsarisha, Deulia Village of Brittihuda W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000145/2023-2024 | 1414/NACD-II | 14/12/2023 | 90 | M/S GHOSH CONSTRUCTION | 151.57 | 0 | 100
2334 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Brittihuda PWSS in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000155/2023-2024 | 520/AE-I/NACD-II | 18/12/2023 | 7 | MAKALI ENGINEERING CORPORATION | 0.58 | 0 | 0
2335 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Balance Laying UPVC pipeline for supplying drinking water including FHTC works and reconnection of existing FHTCs of Brittihuda W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. as per door to door survey conducted by ISA Team. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000177/2023-2024 | 1460/NACD-II | 22/12/2023 | 630 | SANDIP BISWAS | 133.29 | 0 | 100
2336 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Brittihuda Head Work site under Brittihuda Zone-III Water Supply Scheme under Nadia Arsenic Civil Division-II, PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000243/2024-2025 | 1397/NACD-II | 22/10/2024 | 281 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 10.84 | 0 | 100
2337 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Baliadanga W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000276/2021-2022 | 124/NACD-II | 21/02/2022 | 90 | SINGHA ROY & CO. | 138.93 | 0 | 100
2338 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Gongra Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000284/2023-2024 | 176/NACD-II | 07/02/2024 | 60 | ACQUA CONSTRUCTION CONSORTIUM | 177.79 | 0 | 0
2339 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Brittihuda 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000286/2021-2022 | 241/AE-I/NACD-II | 17/02/2022 | 30 | TAPAS GHOSH | 3.41 | 3.36 | 100
2340 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Brittihuda 3rd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000287/2021-2022 | 242/AE-I/NACD-II | 17/02/2022 | 30 | SURAJIT KUMAR GHOSH | 3.41 | 3.37 | 100
2341 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Brittihuda 4th site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000288/2021-2022 | 243/AE-I/NACD-II | 17/02/2022 | 30 | CHINMOY BISWAS | 3.41 | 3.39 | 100
2342 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Brittihuda 5th site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000289/2021-2022 | 244/AE-I/NACD-II | 17/02/2022 | 30 | M/S RAJESH CONSTRUCTION | 4.05 | 3.99 | 100
2343 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000292/2021-2022 | 127/NACD-II | 21/02/2022 | 90 | MALLICK ENTERPRISE | 159.32 | 159.1 | 100
2344 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Brittihuda Water Supply Scheme of capacity 220 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000322/2023-2024 | 235/NACD-II | 21/02/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 446.92 | 0 | 90
2345 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Brittihuda 4th tube well Site under Brittihuda Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000326/2024-2025 | 1022/AE-I/NACD-II | 10/12/2024 | 120 | TAPAS GHOSH | 4.16 | 0 | 100
2346 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Brittihuda 5th tube well Site under Brittihuda Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000327/2024-2025 | 1023/AE-I/NACD-II | 10/12/2024 | 30 | PRADUT GHOSH | 4.11 | 0 | 0
2347 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution Pipeline along with Parallal Line along with FHTC reconnection and leftout FHTC at Brittihuda W/s Scheme at Chapra block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000343/2024-2025 | 1568/NACD-II | 06/12/2024 | 450 | SANJIB DEY | 101.89 | 0 | 45
2348 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Brittihuda W/s Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000357/2022-2023 | 296/NACD-II | 09/03/2023 | 20 | BISWANATH DAS | 2.05 | 0 | 85
2349 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From-01/03/2023 to 31/03/2023) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000359/2022-2023 | 253/NACD-II | 27/02/2023 | 31 | BABLU KUMAR SINGH | 0.42 | 0.38 | 100
2350 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse with sanitary and water supply arrangement at Pitambarpur mouza in Brittihuda Piped water supply scheme in Chapra Block under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000368/2024-2025 | 1617/NACD-II | 18/12/2024 | 30 | M/S ARATI ENTERPRISE | 6.19 | 0 | 0
2351 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Conversion of IEP to AIRP at Tengra Water Supply Scheme of capacity 36Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000386/2024-2025 | 1360/NACD-II | 30/09/2024 | 60 | SUMIT GHOSH | 165.15 | 0 | 0
2352 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 50 m3/hr capacity Iron Elimination Plant at Mouza-Pitambarpur under habitation Mallickpara under Brittihuda Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000388/2024-2025 | 131/NACD-II | 29/01/2025 | 59 | MALLICK ENTERPRISE | 23.07 | 0 | 0
2353 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From 01/03/2022 to 28/02/2023) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000402/2021-2022 | 55//AE-II/NACD-II | 17/02/2022 | 365 | SAJAL SAHA | 4.98 | 0.72 | 100
2354 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From-01/03/2022 to 28/02/2023) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000405/2021-2022 | 276//AE-I/NACD-II | 25/02/2022 | 12 | BABLU KUMAR SINGH | 4.98 | 2.32 | 100
2355 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of Water Level Indicator at Brittihuda,Mahatpur,Bahirgachhi Zone-1,Bahirgachhi Zone-II,Bagberia,Betberia PWSS in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000427/2024-2025 | 1191/AE-I/NACD-II | 25/02/2025 | 45 | MAYA ENTERPRISE | 4.58 | 0 | 0
2356 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum Chlorine room with sanitary and water supply arrangement at Gokhrapota mouza in Brittihuda Piped water supply scheme in Chapra Block under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000452/2024-2025 | 344/NACD-II | 13/03/2025 | 30 | SOMNATH GHOSH | 6.22 | 0 | 65
2357 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000035/2022-2023 | 373/NACD-II | 24/03/2023 | 0 | Resource Division | 12.32 | 0 | 0
2358 | Nadia Arsenic Division I |  | Restoration of damages pipelines at PWD Bridge at Raninagar village in Balagorichar (Zone-XII) under augmentation of surface water based PWSS for Chakdah Part at Chakdah Block under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000005/2024-2025 | 143/AE-II/NAD-I | 07/06/2024 | 330 | MESSRS FREEDOM CONSTRUCTION | 4.05 | 0 | 100
2359 | Nadia Arsenic Division I |  | Construction of pathway and allied works for WTP Chakdah in connection with Augmentation of Chakdah WTP under JJM within Chakdah Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) |  |  | ORD/000064/2024-2025 | 1709/NAD-I | 21/10/2024 | 21 | MALI CONSTRUCTION | 39.68 | 0 | 0
2360 | Nadia Arsenic Division I |  | Preparation of Detailed Project Report (DPR) for Augmentation of Surface Water Based PWSS for Chakdah (Part) Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.01) |  |  | ORD/000123/2023-2024 | 1829/NAD-I | 07/08/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 74.61 | 74.61 | 100
2361 | Nadia Arsenic Division I |  | Augmentation of Water Treatment Plant, Intake & Rising Main for Surface Water Based Piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR including Soil Test, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 29 Nos. distribution zone for Chakdah (Part) in Chakdah Block of Nadia District under Nadia Arsenic Division-I, PHE Dte (Sl.no 01) |  |  | ORD/000166/2023-2024 | 2110/NAD-I | 01/09/2023 | 547 | GBC INFRASTRUCTURE PRIVATE LIMITED | 8630 | 0 | 10
2362 | Nadia Arsenic Division I |  | Continuation work order of Casual hiring of vehicle on an as and when required basis for Jal-Jeevan Mission site inspection under Nadia arsenic Division-I, PHE Dte. |  |  | ORD/000255/2024-2025 | 500/AE-II/NAD-I | 28/03/2025 | 184 | BUDDHADEV MONDAL | 0.86 | 0 | 0
2363 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 1952/NAD-I | 28/11/2024 | 0 | Resource Division | 38.55 | 0 | 0
2364 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1884/NAD-I | 11/08/2023 | 0 | Resource Division | 3612.51 | 0 | 0
2365 | Eastern Mechanical |  | Implementation of SCADA system at Intake, WTP and OHR sites of surface based water supply scheme for Chakdah (Part) in the district of Nadia. |  |  | ORD/001636/2023-2024 | 6193/EMD | 05/10/2023 | 183 | G.B. CONSTRUCTION | 615.17 | 0 | 0
2366 | Eastern Mechanical |  | Supply, delivery & installation of Rotary Assembly for Horizontal split case pump at Chakdah WTP, Pump No.-V, under Eastern Mechanical Division, P.H.E. Dte. |  |  | ORD/001775/2023-2024 | 6399/EMD | 30/10/2023 | 90 | ORIENTAL ENGINEERING CO. | 9.85 | 0 | 100
2367 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bhanderkhola to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000017/2022-2023 | 2079/ND | 11/05/2022 | 90 | M/S GHOSH CONSTRUCTION | 180.3 | 175.6 | 100
2368 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Gravity Type) of capacity 58 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Bhanderkhola PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000084/2023-2024 | 2997/ND | 13/07/2023 | 90 | TARUN KUMAR BHATTACHARYA | 87.75 | 0 | 68
2369 | Nadia Division | Krishnanagar Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 250 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bhanderkhola Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000394/2023-2024 | 5126/ND | 17/11/2023 | 90 | ONKAR ENTERPRISE | 24.91 | 0 | 100
2370 | Nadia Division | Krishnanagar Sub-Division | Providig FHTC at leftout household in connection to the Augmentation of Ground Based piped water supply scheme at Bhanderkhola to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000720/2023-2024 | 1371/ND | 28/02/2024 | 60 | M/S GHOSH CONSTRUCTION | 32.47 | 0 | 100
2371 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000006/2022-2023 | 2163/ND | 18/05/2022 | 0 | Resource Division | 76.79 | 0 | 0
2372 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000010/2022-2023 | 3235/ND | 21/07/2022 | 0 | Resource Division | 1.26 | 0 | 0
2373 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000013/2022-2023 | 3304/ND | 27/07/2022 | 0 | Resource Division | 10.78 | 0 | 0
2374 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000062/2023-2024 | 2302/ND | 29/05/2023 | 0 | Resource Division | 6.23 | 0 | 0
2375 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHANDAR KHOLA in Krishnagar I Block with in , Nadia district under Nadia Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/001075/2021-2022 | 638/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.23 | 0 | 0
2376 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 0 | 47
2377 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 8B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000781/2021-2022 | 131/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.1 | 3.05 | 100
2378 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000127/2022-2023 | 114/ND | 05/01/2023 | 0 | Resource Division | 106.06 | 0 | 0
2379 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Fazilnagar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte."(PART- B) | Assistant Engineer |  | ORD/000022/2021-2022 | 2156/ND | 21/05/2021 | 60 | IJABUL SK. | 42.68 | 61.87 | 100
2380 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Fazilnagar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer |  | ORD/000023/2021-2022 | 2155/ND | 21/05/2021 | 60 | A.P. POWER & CONCRETE | 42.43 | 32.04 | 100
2381 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Fazilnagar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | Assistant Engineer |  | ORD/000112/2021-2022 | 2930/ND | 26/07/2021 | 45 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 7.58 | 6.37 | 0
2382 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000014/2022-2023 | 3302/ND | 27/07/2022 | 0 | Resource Division | 17.79 | 0 | 0
2383 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000098/2021-2022 | 1016/ND | 03/03/2022 | 0 | Resource Division | 15.9 | 0 | 0
2384 | Central Drilling | RWS Nadia Sub-Division | PROVIDING 300MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KISHOREPUR W/S (REPLACEMENT TW-HW), KARIMPUR II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer |  | ORD/000067/2022-2023 | 283/CMSD-II (D) | 01/06/2022 | 15 | DEV ENTERPRISE | 4.39 | 0 | 0
2385 | Central Drilling | RWS Nadia Sub-Division | PROVIDING 200MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer |  | ORD/000068/2022-2023 | 286/CMSD-II (D) | 01/06/2022 | 15 | DEV ENTERPRISE | 4.44 | 0 | 0
2386 | Central Drilling | RWS Nadia Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER BASED & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT FAZILNAGAR W/S (REPLACEMENT TW-II) IN KARIMPUR-II BLOCK UNDER NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer |  | ORD/000069/2022-2023 | 277/CMSD-II (D) | 01/06/2022 | 15 | DEV ENTERPRISE | 2.07 | 0 | 0
2387 | Central Drilling | RWS Nadia Sub-Division | PROVIDING DRILLING CREWS & OTHER MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer |  | ORD/000070/2022-2023 | 284/CMSD-II (D) | 01/06/2022 | 15 | DEV ENTERPRISE | 3.52 | 0 | 0
2388 | Central Drilling | RWS Nadia Sub-Division | PROVIDING 200MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer |  | ORD/000071/2022-2023 | 286/CMSD-II(D) | 01/06/2022 | 15 | DEY ENTERPRISE | 4.44 | 1.1 | 0
2389 | Central Drilling | RWS Nadia Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT FAZILNAGAR W/S (REPLACEMENT TW-II) IN KARIMPUR--II BLOCK UNDER NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer |  | ORD/000072/2022-2023 | 277/CMSD-II(D) | 01/06/2022 | 15 | DEY ENTERPRISE | 2.07 | 1.63 | 0
2390 | Central Drilling | RWS Nadia Sub-Division | PROVIDING DRILLING CREWS & OTHER MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer |  | ORD/000073/2022-2023 | 284/CMSD-II(D) | 01/06/2022 | 15 | DEY ENTERPRISE | 3.52 | 3.52 | 0
2391 | Central Drilling | RWS Nadia Sub-Division | PROVIDING 300 MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KISHOREPUR W/S (REPLACEMENT TW-HW), KARIMPUR -II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer |  | ORD/000074/2022-2023 | 283/CMSD-II(D) | 01/06/2022 | 15 | DEY ENTERPRISE | 4.39 | 3.94 | 0
2392 | Central Drilling | RWS Nadia Sub-Division | MISCELLANEOUS REPAIRING OF KORES/DR/1000 (MP09GF2033) AND SUPPORT TRUCK (WMK4719) UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer |  | ORD/000239/2021-2022 | 161/CMSD-II (D) | 07/07/2021 | 15 | CHAKRABORTY MINING & ENGINEERING | 0.75 | 0.75 | 0
2393 | Central Drilling | RWS Nadia Sub-Division | REPAIRING OF MUD PUMP FLUID CHAMBER, TRANSMISSION LINE AND OTHERS WORKS ALONG WITH SUPPLY OF DRILLING ACCESSORYU OF RIG MACHINE- JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. | Assistant Engineer |  | ORD/000273/2021-2022 | 72/CMSD-I | 30/03/2022 | 15 | PADMA ENGINEERING & CO. | 4 | 0.83 | 0
2394 | Central Drilling | RWS Nadia Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Assistant Engineer |  | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0.23 | 0
2395 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIA, Darappur, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000007/2021-2022 | 771/NAD-I | 04/05/2021 | 60 | M/S DIPAK ENTERPRISE | 96.96 | 191.19 | 100
2396 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Birnagar, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Birnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000002/2021-2022 | 766/NAD-I | 04/05/2021 | 60 | CALCON CONSTRUCTION | 63.98 | 78.39 | 100
2397 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Baruipara W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retrofitting) | Assistant Engineer |  | ORD/000105/2021-2022 | 2876/ND | 20/07/2021 | 90 | CHAKRABORTTI ENTERPRISE | 93.37 | 133.35 | 0
2398 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jalswapna for Zone-VIII, (Barberia), Part-I at Chakdah Block by retrofitting of Surface Water Based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) |  |  | ORD/000207/2020-2021 | 312/NAD-I | 08/02/2021 | 90 | MONDAL PRECESION PVT. LTD. | 95.18 | 125.29 | 100
2399 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Banpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-B | Assistant Engineer |  | ORD/000343/2020-2021 | 504/ND | 27/01/2021 | 45 | SUMAN CHAKRABORTY | 35.26 | 13.59 | 0
2400 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Banpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-C | Assistant Engineer |  | ORD/000345/2020-2021 | 505/ND | 27/01/2021 | 45 | SUMAN CHAKRABORTY | 35.26 | 62.05 | 0
2401 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Banpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-A | Assistant Engineer |  | ORD/000349/2020-2021 | 503/ND | 27/01/2021 | 45 | PALCON | 23.44 | 0 | 0
2402 | Nadia Division | Ranaghat Sub-Division | onal Household Tap Connection from Banpur Water Scheme (for Banpur & Fulbari Mouzas) under Jal Swapno Programme | Assistant Engineer |  | VCH/000068/2021-2022 |  | 13/04/2021 | 0 | SUMAN CHAKRABORTY | 15.79 | 0 | 0
2403 | Nadia Division | Ranaghat Sub-Division | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT BANPUR W/S SCHEME PART-A, UNDER NADIA DIVISION, PHE , DTE. | Assistant Engineer |  | VCH/000215/2021-2022 | 75/PPMS | 15/07/2021 | 0 | PALCON | 17.37 | 0 | 0
2404 | Nadia Division | Ranaghat Sub-Division | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT BANPUR W/S SCHEME PART-B, UNDER NADIA DIVISION, PHE , DTE. | Assistant Engineer |  | VCH/000217/2021-2022 | 77/PPMS | 15/07/2021 | 0 | SUMAN CHAKRABORTY | 15.79 | 0 | 0
2405 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Gazna W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-A | Assistant Engineer |  | ORD/000346/2020-2021 | 506/ND | 27/01/2021 | 45 | SANJOY BAKSHI | 13.11 | 0 | 0
2406 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Gazna W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-B | Assistant Engineer |  | ORD/000347/2020-2021 | 507/ND | 27/01/2021 | 45 | APURBA MANDAL | 37.85 | 69.39 | 100
2407 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Gazna W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-C | Assistant Engineer |  | ORD/000348/2020-2021 | 508/ND | 27/01/2021 | 45 | APURBA MANDAL | 37.85 | 71.79 | 100
2408 | Nadia Division | Ranaghat Sub-Division | Replacemt of damaged & typically choked UPVC pipe line for augmentation of Ground Water Based Water Supply Scheme for Gazna PWSS of Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. (Balance) A- Part. | Assistant Engineer |  | ORD/000370/2023-2024 | 4802/ND | 17/10/2023 | 623 | SANDIP BISWAS | 99.5 | 0 | 96
2409 | Nadia Division | Ranaghat Sub-Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme | Assistant Engineer |  | VCH/000942/2021-2022 | 515/PFMS | 03/02/2022 | 0 | APURBA MANDAL | 3.12 | 0 | 0
2410 | Nadia Division | Ranaghat Sub-Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme | Assistant Engineer |  | VCH/000993/2020-2021 |  | 24/03/2021 | 0 | APURBA MANDAL | 34.69 | 0 | 0
2411 | Nadia Division | Ranaghat Sub-Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme. | Assistant Engineer |  | VCH/000994/2020-2021 |  | 24/03/2021 | 0 | APURBA MANDAL | 34.35 | 0 | 0
2412 | Nadia Division | Ranaghat Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT GAZNA W/S SCHEME | Assistant Engineer |  | VCH/001067/2020-2021 | 460/DW | 30/03/2021 | 0 | SANJOY BAKSHI | 12.7 | 0 | 0
2413 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Lakshmipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000067/2020-2021 | 1361/NACD-II | 29/12/2020 | 60 | APURBA MANDAL | 44.32 | 88.07 | 0
2414 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme(Northern Sector),Part-I,Zone-I Within Kaliganj Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte. | Assistant Engineer |  | ORD/000216/2020-2021 | 4080/ND | 31/12/2020 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 97.03 | 173.99 | 0
2415 | Nadia Division | Debgram Sub-Division | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-03-2021 to 28-02-2022 (250 working days) | Assistant Engineer |  | ORD/000501/2020-2021 | 172/RSD | 22/02/2021 | 365 | SUMAN CHAKRABORTY | 3.85 | 1.02 | 0
2416 | Nadia Division | Debgram Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Executive Engineer, Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000749/2021-2022 | 286/Kly SD-I | 31/03/2022 | 365 | ARROWTOWN DEALERS PVT. LTD | 4.8 | 1.49 | 0
2417 | Nadia Division | Debgram Sub-Division | Additional work for extension of pipe line at Hutguchha, basorkhola & Kaliganj for Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Kaliganj Block (Phase-c). | Assistant Engineer |  | VCH/000955/2021-2022 | 562/DW | 25/02/2022 | 0 | M/S NIBHAS SINHA | 4.65 | 0 | 0
2418 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme(Northern Sector),Part-I,Zone-IV within Kaliganj Block(Phase-A) in Nadia District under Nadia Division,P.H.E.Dte. | Assistant Engineer |  | ORD/000220/2020-2021 | 4082/ND | 31/12/2020 | 90 | UMWELT ENGINEERS PVT LTD | 96.95 | 185.04 | 0
2419 | Nadia Division | Debgram Sub-Division | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE | Assistant Engineer |  | VCH/000308/2021-2022 | 139/FHTC | 17/08/2021 | 0 | LEMNISCATE | 0.44 | 0 | 0
2420 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-III within Kaliganj block(Phase-A) in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000184/2020-2021 | 3590/ND | 08/12/2020 | 90 | M/S S & P CONSTRUCTION | 97.06 | 144.5 | 0
2421 | Nadia Division | Debgram Sub-Division | Continuation of Hiring Diesel cab having contract permit from regional transport authority for the office use of the Assistant Engineer, Kalyani Sub-Division-1, Nadia Division PHE Dte at D.C Building, Kalyani, Nadia w.e.f 01/10/2021 to 31/03/2022 (6 months)) | Assistant Engineer |  | ORD/000272/2021-2022 | 441/Kly SD-I | 30/09/2021 | 182 | SATYABRATA CHAKRABORTY | 2.4 | 0.54 | 0
2422 | Nadia Division | Debgram Sub-Division | Hiring Diesel Maxi Cub having car No WB-51/B-3194 for office of the Assistant Engineer, RWS Nadia Sub-Division, PHE Dte. for the period from 01.08.2021 to 31.07.2022 | Assistant Engineer |  | ORD/000951/2021-2022 | 896/PH | 30/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 0.51 | 100
2423 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTORPART-1 Z-3 | Assistant Engineer |  | VCH/001079/2020-2021 | 447/DW | 25/03/2021 | 0 | M/S S & P CONSTRUCTION | 18.28 | 0 | 0
2424 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Masunda village at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000065/2021-2022 | 1419/NAD-I | 08/11/2021 | 60 | PRIYA CONSTRUCTION | 77.38 | 75.9 | 100
2425 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Paschim Noapara at Ranaghat-I Block by augmentation of Ground Water Based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte . (Sl.no.12) | Assistant Engineer-I | Junior Engineer-I | ORD/000221/2023-2024 | 2409/NAD-I | 10/10/2023 | 30 | JOYGOPAL GUPTI | 86.45 | 0 | 100
2426 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall and pathway Head work site of Duttaphulia Zone- II and Dubli Zone- I water supply Scheme in Ranaghat-II Block in connection with Duttaphulia Zone-I W/S Scheme under JJM under Nadia Arsenic Division-I,P.H.E. Dte. (sl.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000019/2025-2026 | 137/NAD-I | 23/04/2025 | 60 | CFS MANAGEMENT PRIVATE LIMITED | 38.99 | 0 | 0
2427 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functioanal Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Dubli, Zone-I at Ranaghat-II Block by retrofitting of GRound Water based PWSS for Dubli, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000105/2021-2022 | 1587/NAD-I | 22/12/2021 | 90 | SUPRITI ENTERPRISE | 205.54 | 193.94 | 100
2428 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dubli, Zone-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dubli Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000075/2021-2022 | 1435/NAD-I | 09/11/2021 | 90 | MONDAL ENTERPRISE | 147.05 | 146.55 | 100
2429 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000012/2021-2022 | 145/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
2430 | Nadia Division | Ranaghat Sub-Division | PAYMENT FOR NGO LAB. | Assistant Engineer | Junior Engineer 2 | BILL/00730/2023-2024 | 280/PFMS | 19/09/2023 | 0 | BINAY BADAL DINESH CLUB | 0.4 | 0 | 0
2431 | Nadia Division | Ranaghat Sub-Division | PAYMENT FOR NGO LAB | Assistant Engineer | Junior Engineer 2 | BILL/00731/2023-2024 | 281/PFMS | 19/09/2023 | 0 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.4 | 0 | 0
2432 | Nadia Division | Ranaghat Sub-Division | Continuation work order for Engagement of 01 no of Chemist /Analyst for operation and maintenance of physico-Chemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF: 01/06/2023 to 31/08/2023 (Three months) | Assistant Engineer | Junior Engineer 2 | ORD/000060/2023-2024 | 656/KLYSD-I | 24/05/2023 | 92 | JOYDEV JANA | 0.5 | 0.17 | 70
2433 | Nadia Division | Ranaghat Sub-Division | Continuation work order for Engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/06/2023 to 31/08/2023 (Three months) | Assistant Engineer | Junior Engineer 2 | ORD/000061/2023-2024 | 657/KlySD-I | 24/05/2023 | 92 | GOUTAM DAM | 0.5 | 0.17 | 70
2434 | Nadia Division | Ranaghat Sub-Division | Continuation work order for Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte. WEF: 01/06/2023 to 31/08/2023 (Three months) | Assistant Engineer | Junior Engineer 2 | ORD/000062/2023-2024 | 658/KLYSD-I | 24/05/2023 | 92 | SUCHITRA GHOSH | 0.23 | 0.08 | 70
2435 | Nadia Division | Ranaghat Sub-Division | Continuation work order for Engagement of 01 no of Chemist cum Operator of Atomic Absorption Spectrophotometer (AAS) at Nadia District Water Testing Laboratory under Nadia Division, P.H.E Dte WEF: 01/07/2023 to 30/09/2023 (Three months). | Assistant Engineer | Junior Engineer 2 | ORD/000063/2023-2024 | 710/KlySD-I | 19/06/2023 | 92 | M/S S.K. ENTERPRISE | 0.8 | 0.8 | 100
2436 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Kamalpur Z-II Water Supply scheme Ranaghat-II block in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000246/2021-2022 | 5701/ND | 03/11/2021 | 1123 | PRIYA CONSTRUCTION | 63.6 | 49.83 | 100
2437 | Nadia Division | Ranaghat Sub-Division | Continuation work order for Engagement of 01 no of Chemist /Analyst for operation and maintenance of physico-Chemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF:01/09/2023 to 30/11/2023 (Three months) | Assistant Engineer | Junior Engineer 2 | ORD/000252/2023-2024 | 900/KLYSD-I | 25/08/2023 | 92 | JOYDEV JANA | 0.5 | 0.17 | 100
2438 | Nadia Division | Ranaghat Sub-Division | Continuation work order for Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte. WEF: 01/09/2023 to 30/11/2023 (Three months) | Assistant Engineer | Junior Engineer 2 | ORD/000253/2023-2024 | 902/KLYSD-I | 28/08/2023 | 92 | SUCHITRA GHOSH | 0.23 | 0.08 | 100
2439 | Nadia Division | Ranaghat Sub-Division | Continuation work order for Engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/09/2023 to 30/11/2023 (Three months) | Assistant Engineer | Junior Engineer 2 | ORD/000254/2023-2024 | 901/KlySD-I | 25/08/2023 | 92 | GOUTAM DAM | 0.5 | 0.17 | 100
2440 | Nadia Division | Ranaghat Sub-Division | Engagement of 01 no of Chemist cum Operator of Atomic Absorption Spectrophotometer (AAS) at Nadia District Water Testing Laboratory under Nadia Division, P.H.E Dte WEF: 01/01/2023 to 31/03/2023 (Three months). | Assistant Engineer | Junior Engineer 2 | ORD/000310/2022-2023 | 1231/Kly SD-I | 30/12/2022 | 90 | M/S S.K. ENTERPRISE | 0.8 | 0.27 | 0
2441 | Nadia Division | Ranaghat Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
2442 | Nadia Division | Ranaghat Sub-Division | laying of distribution pipe line180mm dia UPVC pipe etc. for Providing functional household tap connection at Naserkuli zone- I W/S scheme under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000721/2021-2022 | 1464/PH | 03/03/2022 | 10 | SAIKAT GHOSH | 1.26 | 1.26 | 100
2443 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000069/2021-2022 | 802/ND | 18/02/2022 | 0 | Resource Division | 2.2 | 0 | 0
2444 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 mtr , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Nutungram Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000243/2021-2022 | 5700/ND | 03/11/2021 | 60 | A.P. POWER & CONCRETE | 46.05 | 45.83 | 0
2445 | Nadia Division | Ranaghat Sub-Division | Providing Left-out Functional Household tap Connection including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe and other allied works etc. all complete for augmentation of Natungram W/S Scheme under Ranaghat Sub-Division of Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000293/2023-2024 | 919/RSD | 13/09/2023 | 545 | J & T ENTERPRISE | 1.2 | 0 | 100
2446 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 4 | RTOR000010/2021-2022 | 102/ND | 06/01/2022 | 0 | Resource Division | 6.62 | 0 | 0
2447 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 4 | RTOR000025/2021-2022 | 438/ND | 31/01/2022 | 0 | Resource Division | 0.62 | 0 | 0
2448 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 4 | RTOR000087/2021-2022 | 813/ND | 18/02/2022 | 0 | Resource Division | 2.2 | 0 | 0
2449 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 4 | RTOR000120/2021-2022 | 1059/ND | 04/03/2022 | 0 | Resource Division | 8.22 | 0 | 0
2450 | Nadia Division | Ranaghat Sub-Division | Providing Functional House Tap Connection from NutangramWater Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | Assistant Engineer | Junior Engineer 4 | VCH/001022/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 2.04 | 0 | 0
2451 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Joyghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000026/2020-2021 | 1068/NACD-II | 25/09/2020 | 15 | BIPLAB GUHA | 4.99 | 0 | 0
2452 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Barnia (Vill- Barnia) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000042/2020-2021 | 1189/NACD-II | 13/11/2020 | 25 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 4.99 | 0 | 0
2453 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Chapra Bangaljhi W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(PART-A) | Assistant Engineer |  | ORD/000280/2021-2022 | 5692/ND | 03/11/2021 | 90 | M/S GHOSH CONSTRUCTION | 86.03 | 83.18 | 0
2454 | Nadia Division | Krishnanagar Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
2455 | Nadia Division | Krishnanagar Sub-Division | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000721/2024-2025 | 7570/ND | 27/12/2024 | 45 | IMAGIN | 19.44 | 0 | 100
2456 | Nadia Division | Krishnanagar Sub-Division | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000722/2024-2025 | 7571/ND | 27/12/2024 | 31 | IMAGIN | 34.21 | 0 | 0
2457 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 174 m3/hr at Chapra Bangaljhi Water Supply Scheme within Chapra Block under Krishnagar Sub- Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000787/2023-2024 | 1898/ND | 15/03/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 385.52 | 0 | 0
2458 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000027/2021-2022 | 426/ND | 31/01/2022 | 0 | Resource Division | 3.58 | 0 | 0
2459 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000073/2021-2022 | 1414/NAD-I | 08/11/2021 | 45 | JOY HIND TUBE WELLS | 44.57 | 44.25 | 100
2460 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between 1st and 2nd Tubewell Rising Main at Chupria Zone-II W/S Scheme in Hanskhali block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000214/2023-2024 | 2371/NAD-I | 06/10/2023 | 21 | BISWAS CONSTRUCTION | 14.67 | 0 | 100
2461 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000009/2021-2022 | 142/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
2462 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Joypur Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000058/2021-2022 | 1416/NAD-I | 08/11/2021 | 60 | GHOSH ENTERPRISE | 86.93 | 86.53 | 100
2463 | Nadia Arsenic Division I | Nadia Arsenic Division I | Wall writing on smooth wall surface (Preferably on Govt. premises / Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and two coat best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Nadia all completed as per direction of EIC. | Assistant Engineer-II | Junior Engineer-IV | ORD/000331/2023-2024 | 466/NAD-I | 15/03/2024 | 92 | IMAGIN | 11.2 | 0 | 100
2464 | Nadia Arsenic Division I | Nadia Arsenic Division I | Balance work for revamping / upgradation of the hydraulic parameters at Kalipara,Gobindapur, Jhinukghata and Raynagar mouzas in reference to Gobindapur PWSS and Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000018/2025-2026 | 127/NAD-I | 22/04/2025 | 60 | CHOWDHURY & CO. | 96.3 | 0 | 0
2465 | Nadia Arsenic Division I | Nadia Arsenic Division I | Balance work for revamping / upgradation of the hydraulic parameters at Gobindapur Colony and Hijuli mauza in reference to Gobindapur PWSS and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission (Sl. NO. 08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000051/2025-2026 | 231/NAD-I | 13/05/2025 | 60 | TARUN GHOSH | 89.24 | 0 | 0
2466 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Part-I (Gobindapur) at Hanskhali Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000125/2021-2022 | 50/NAD-I | 11/01/2022 | 90 | M/S DIPAK ENTERPRISE | 128.71 | 128.56 | 100
2467 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Land Development, Construction of Pathway & other allied works at Headwork site of Gobindapur (Hanskhali) under Hanskhali Dev. Block water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte. Length of Boundary wall - 145 mtr. metre. | Assistant Engineer-II | Junior Engineer-IV | ORD/000130/2021-2022 | 74/NAD-I | 17/01/2022 | 30 | NISHITH BANERJEE | 16.71 | 0 | 70
2468 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Hanskhali BDO, BL&LRO, Ration Deptt, Animal Husbandary,Health etc, at Hanskhali Block by retrofitting of Ground Water based PWSS for Gobindapur (Hanskhali) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000134/2022-2023 | 266/AE-I/NAD-I | 09/11/2022 | 15 | BUDDHADEV MONDAL | 4.66 | 4.66 | 100
2469 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for preparation of DPR for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for GOBINDAPUR ZONE-I Water Supply Scheme under Nadia Arsenic-I Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000410/2020-2021 | 59/AE-I/N.A.D.-I | 24/02/2021 | 30 | UMWELT ENGINEER PVT. LTD. | 4.6 | 4.6 | 100
2470 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for preparation of DPR for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for GOBINDAPUR ZONE-II Water Supply Scheme of Nadia District under Nadia Arsenic-I Division, PHE Dte. (Sl. No.-04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000411/2020-2021 | 61/AE-I/N.A.D.-I | 24/02/2021 | 30 | UMWELT ENGINEER PVT. LTD. | 3.68 | 3.68 | 100
2471 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000123/2021-2022 | 48/NAD-I | 11/01/2022 | 90 | M/S MALLICK ENTERPRISE | 126.06 | 125.49 | 100
2472 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-I Water Supply Scheme, Phase-I at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000004/2022-2023 | 645/NAD-I | 29/04/2022 | 90 | M/S R.K. ENTERPRISE | 260.46 | 213.67 | 100
2473 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000008/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 19.86 | 0 | 0
2474 | Nadia Division | Krishnanagar Sub-Division | Special repair and renovation of 1st Pump House and Allied Works ," and Earthwork infilling in !st Tubewell site of Dafarpota -I Water supply scheme under Krishnagar Sub-Division PHED Sl.01 | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 512/KSD | 30/05/2022 | 30 | DEBASHISH DEY | 3.37 | 0 | 100
2475 | Nadia Division | Krishnanagar Sub-Division | Providing balance FHTC Of Retrofitting (Phase-I) Under JJM in Ground Based piped water supply scheme at Dafarpota Zone I to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000056/2024-2025 | 3896/ND | 16/07/2024 | 60 | SINGHA ROY & CO. | 34.11 | 0 | 0
2476 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000017/2021-2022 | 97/ND | 06/01/2022 | 0 | Resource Division | 7.54 | 0 | 0
2477 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000017/2022-2023 | 3305/ND | 27/07/2022 | 0 | Resource Division | 1.41 | 0 | 0
2478 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000139/2021-2022 | 1393/ND | 24/03/2022 | 0 | Resource Division | 30.99 | 0 | 0
2479 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000149/2021-2022 | 1450/ND | 25/03/2022 | 0 | Resource Division | 18.89 | 0 | 0
2480 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001068/2021-2022 | 631/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.21 | 0 | 0
2481 | Eastern Mechanical | Krishnanagar Sub-Division | New Service Connection at Pump House I Zone-I under Dafarpota W/S Scheme. | Assistant Engineer | Junior Engineer | BILL/02678/2023-2024 | BP-164-23-24 | 11/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.57 | 0 | 0
2482 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Zone-I under Dafarpota W/S Scheme, Block-Krishnagar 1, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (SSl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/000179/2022-2023 | 6185/EMD | 14/11/2022 | 30 | GHOSH AND GHOSH | 10.82 | 9.36 | 80
2483 | Eastern Mechanical | Krishnanagar Sub-Division | Supplementary works to completion of ongoing FHTC-related work at PH-I of Dafarpota (Zone-I) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/001399/2023-2024 | 603/EMSD-II | 22/08/2023 | 15 | GHOSH AND GHOSH | 0.52 | 0 | 100
2484 | Nadia Division | Krishnanagar Sub-Division | Repair and renovation works of R.C.C. Elevaced Reservoir 50 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Sonda Zone II Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000420/2023-2024 | 5368/ND | 04/12/2023 | 90 | REAL TIME | 21.55 | 0 | 100
2485 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80) / 20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Sonda-II to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000492/2021-2022 | 64/ND | 05/01/2022 | 45 | ROY CONSTRUCTION | 15.67 | 13.4 | 95
2486 | Nadia Division | Krishnanagar Sub-Division | Conversion of IEP to AIRP of capacity 9 Cu.m/hr at Sonda Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000792/2023-2024 | 1904/ND | 15/03/2024 | 60 | SUMIT GHOSH | 63.49 | 0 | 0
2487 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000008/2021-2022 | 7452/ND | 27/12/2021 | 0 | Resource Division | 9.44 | 0 | 0
2488 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000048/2022-2023 | 4298/ND | 29/09/2022 | 0 | Resource Division | 0.33 | 0 | 0
2489 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No. I (Zone-II) under Sonda W/S Scheme, Block-Krishnagar 1, District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.-02) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000083/2022-2023 | 3911/EMD | 19/10/2022 | 30 | DAS ENTERPRISE | 9.39 | 0 | 0
2490 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer etc. for Augmentation to Accomodate FHTC at Pump House No.II(Zone-II) under Sonda W/S Scheme, Block-Krishnagar 1, District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.01) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000089/2022-2023 | 3942/EMD | 20/10/2022 | 863 | BIJAN ENTERPRISE | 5.34 | 0 | 50
2491 | Eastern Mechanical | Krishnanagar Sub-Division | Supplementary works to completion of ongoing FHTC-related work at PH-I of Sonda (Zone - II) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001489/2023-2024 | 687/EMSD-II | 13/09/2023 | 15 | DAS ENTERPRISE (BARANAGAR) | 0.99 | 0 | 100
2492 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No. I (Zone-II) under Sonda W/S Scheme, Block-Krishnagar 1, District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.-02) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/002598/2022-2023 | 3911EMD | 09/10/2022 | 30 | DAS ENTERPRISE (BARANAGAR) | 9.39 | 8.37 | 0
2493 | Eastern Mechanical | Krishnanagar Sub-Division | Supplementary works to completion of ongoing FHTC-related work at PH-I of Sonda (Zone - II) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/002945/2022-2023 | 687/EMSD-IIDt.13/09/2023 | 14/08/2022 | 30 | DAS ENTERPRISE (BARANAGAR) | 0.99 | 0.99 | 100
2494 | Nadia Division | Tehatta Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 206 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur to accommodate FHTC within Karimpur-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000081/2024-2025 | 4166/ND | 30/07/2024 | 360 | HARBAUER INDIA (P) LTD. | 444.71 | 0 | 30
2495 | Nadia Division | Tehatta Sub-Division | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000254/2024-2025 | 6305/ND | 26/09/2024 | 30 | IMAGIN | 34.21 | 0 | 100
2496 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Karimpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte."(Phase-1 Retro fitting) " | Assistant Engineer |  | ORD/000602/2021-2022 | 350/ND | 25/01/2022 | 1080 | TARUN KUMAR BHATTACHARYA | 404.96 | 363.29 | 100
2497 | Nadia Division | Tehatta Sub-Division | Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. | Assistant Engineer |  | ORD/000759/2021-2022 | 289/Kly SD-I | 31/03/2022 | 90 | SUMAN CHAKRABORTY | 4.89 | 0 | 100
2498 | Nadia Division | Tehatta Sub-Division | Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000769/2023-2024 | 1821/ND | 14/03/2024 | 31 | IMAGIN | 34.21 | 0 | 60
2499 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Karimpur W/S to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000793/2024-2025 | 7465/ND | 20/12/2024 | 90 | CHOWDHURY & CO. | 128.29 | 0 | 0
2500 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000004/2021-2022 | 7048/ND | 06/12/2021 | 0 | Resource Division | 35.82 | 0 | 0
2501 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000083/2021-2022 | 785/ND | 18/02/2022 | 0 | Resource Division | 16.47 | 0 | 0
2502 | Eastern Mechanical | Nadia Arsenic Civil Division II | Rejuvanation of Taldaha W/ Scheme in krishnaganj block nadia under EMSD-III Phe Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000693/2021-2022 | 231/EMD | 15/02/2022 | 212 | ABHISEK ENGINEERING CONCERN | 7.43 | 7.43 | 100
2503 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KHANJIPUR , Block-Tehatta I and TALDAH , Block-Krishnaganj, Bahirgachhi (Z-II) Block-Chapra, Bagakhali (Z-II) W/S Scheme, Block-Tehatta I Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001777/2022-2023 | 1122/EMD | 16/03/2023 | 30 | ANJAN ENTERPRISE | 46.98 | 0 | 80
2504 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Taldaha H/W and 2nd Pump house site with Reinforced Barbed Tape, Plaster and other allied works. Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000014/2024-2025 | 136/AE-II/NACD-II | 11/06/2024 | 570 | NIVEDITA CONSTRUCTION | 2.81 | 0 | 100
2505 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Wall writing work in various Gram Panchayats in Krishnaganj Block at Taldaha PWSS under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000047/2024-2025 | 758/AE-I/NACD-II | 19/06/2024 | 15 | IMAGIN | 0.93 | 0 | 100
2506 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnaganj Block of Nadia District through Jadavpur University. (Name of PWSS Taldaha) | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000088/2024-2025 | 867/NACD-II | 04/07/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
2507 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair) at Taldaha ( Vill- Gopipur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000099/2023-2024 | 1131/NACD-II | 09/10/2023 | 540 | DAS ENTERPRISE | 16.11 | 0 | 100
2508 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Jungle cutting and Earthwork in filling at Taldaha,Sakdaha and Brittihuda Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000121/2024-2025 | 819/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.53 | 0 | 100
2509 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Taldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000129/2021-2022 | 868/NACD-II | 08/11/2021 | 45 | SANJOY BAKSHI | 62.77 | 62.73 | 100
2510 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Arsenic cum Iron treatment Plant of Taldaha PWSS (Capacity- 43 m3/hr) and ancillary works of Krishnaganj Block under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000200/2023-2024 | 90/NACD-II | 18/01/2024 | 60 | MONDAL PRECISION PRIVATE LIMITED | 94.35 | 0 | 99
2511 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur & Taldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000222/2021-2022 | 52/NACD-II | 20/01/2022 | 45 | B.M. ENGINEERING & CONSTRUCTION | 27.75 | 26.75 | 100
2512 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Taldaha Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000245/2023-2024 | 21/AE-II/NACD-II | 15/02/2024 | 15 | SHYAMAL SHIL | 0.97 | 0 | 0
2513 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Taldaha Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000265/2021-2022 | 50/AE-II/NACD-II | 17/02/2022 | 30 | GHOSH ENTERPRISE | 4.04 | 4 | 100
2514 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Taldaha W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000293/2022-2023 | 1191/NACD-II | 23/12/2022 | 15 | BABLU MALLICK | 1.13 | 0.8 | 100
2515 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD, dedicated line and Distribution network for new FHTC at Taldaha Piped Water Supply Scheme and laying distribution network for FHTC and Repairing of Top Dome and related work for 250 cum RCC elevated reservoir at Helenchi Zone- III in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000324/2024-2025 | 1571/NACD-II | 06/12/2024 | 270 | BIDYUT KUMAR | 105.92 | 0 | 40
2516 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Functional House Hold Tap Connection for left out Household regarding Har Ghar Jal Certification including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Vill- Goari, Gopipur & Mathurapur) Taldaha W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000344/2022-2023 | 145/NACD-II | 17/01/2023 | 20 | CHANDRA NATH GHOSH | 2.27 | 2.26 | 100
2517 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000006/2023-2024 | 79/NACD-II | 15/01/2024 | 0 | Resource Division | 6.16 | 0 | 0
2518 | Nadia Division | Debgram Sub-Division | Providing Functional Household Tap connection(FHTC)at Surface Water Based Water Supply Scheme(Northern Sector) Part-II,Zone-I,II &III within Nakashipara Block(Phase-C) | Assistant Engineer |  | ORD/000383/2021-2022 | 7204/ND | 15/12/2021 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 189.26 | 63.92 | 100
2519 | Nadia Division | Debgram Sub-Division | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-III / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11839]. | Assistant Engineer |  | ORD/000443/2023-2024 | 6112/ND | 21/12/2023 | 1095 | MONDAL ENTERPRISE | 201.12 | 0 | 5
2520 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at zone-I II & III, Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000819/2021-2022 | 51/DSD | 07/02/2022 | 15 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.85 | 4.83 | 100
2521 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at zone-I II & III, Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000821/2021-2022 | 53/DSD | 07/02/2022 | 15 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.68 | 4.63 | 100
2522 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000067/2021-2022 | 800/ND | 18/02/2022 | 0 | Resource Division | 22.04 | 0 | 0
2523 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000162/2023-2024 | 229/ND | 11/01/2024 | 0 | Resource Division | 16.4 | 0 | 0
2524 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) | Assistant Engineer |  | VCH/001108/2021-2022 | 680/PFMS | 25/03/2022 | 0 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 59 | 0 | 0
2525 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within Nakashipara Block. (Phase-C) | Assistant Engineer |  | VCH/001109/2021-2022 | 688/PFMS | 29/03/2022 | 0 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 51.63 | 0 | 0
2526 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 50
2527 | Nadia Division | Debgram Sub-Division | Providing Functional household Tap Connection (FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-II, Zone-VI & IX within Nakashipara Block (Phase-D) | Assistant Engineer |  | ORD/000391/2021-2022 | 7255/ND | 17/12/2021 | 90 | MAHAVIR PUMPS MFG PVT. LTD. | 180.19 | 74.78 | 100
2528 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000062/2021-2022 | 814/ND | 18/02/2022 | 0 | Resource Division | 10.98 | 0 | 0
2529 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000163/2023-2024 | 232/ND | 11/01/2024 | 0 | Resource Division | 19.22 | 0 | 0
2530 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000165/2023-2024 | 233/ND | 11/01/2024 | 0 | Resource Division | 20.91 | 0 | 0
2531 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | Assistant Engineer |  | VCH/000210/2022-2023 | 35/PFMS | 23/05/2022 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 51.4 | 0 | 0
2532 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | Assistant Engineer |  | VCH/001086/2021-2022 | 654/PFMS | 21/03/2022 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 33 | 0 | 0
2533 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | Assistant Engineer |  | VCH/001092/2021-2022 | 660/PFMS | 23/03/2022 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 4.34 | 0 | 0
2534 | Nadia Division | Krishnanagar Sub-Division | Providing balance FHTC Of Retrofitting (Phase-I) Under JJM in Ground Based piped water supply scheme at Dafarpota Zone I to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000056/2024-2025 | 3896/ND | 16/07/2024 | 60 | SINGHA ROY & CO. | 34.11 | 0 | 0
2535 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Daforpota (Zone-I) W/S scheme in Nadia District under Nadia Division, PHE Dte. (Phase-I, Retrofitting) (Part-A) | Assistant Engineer | Junior Engineer 1 | ORD/000200/2021-2022 | 5145/ND | 15/09/2021 | 75 | SOMNATH CHATTERJEE | 63.36 | 59.97 | 0
2536 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Cab having contract permit from regional transport authority for office use of the Executive Engineer, Nadia Division, P.H.E. Dte. for a period of 183 ( One Hundred Eighty Three) Days on (F.N). | Assistant Engineer | Junior Engineer 1 | ORD/000453/2023-2024 | 689/KLYSD-I | 01/06/2023 | 183 | AVINABA ENGINEERING CONCERN | 2.4 | 0 | 100
2537 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 1 | RTOR000070/2021-2022 | 803/ND | 18/02/2022 | 0 | Resource Division | 6.6 | 0 | 0
2538 | Nadia Division | Krishnanagar Sub-Division | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | Assistant Engineer | Junior Engineer 1 | VCH/001013/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 6.11 | 0 | 0
2539 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-II, Zone-VI within Nakashipara Block (Phase-C) | Assistant Engineer |  | ORD/000208/2021-2022 | 5182/ND | 20/09/2021 | 90 | TARUN KUMAR BHATTACHARYA | 86.53 | 23.52 | 100
2540 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at zone-VI Phase- C, Part- II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000815/2021-2022 | 47/DSD | 07/02/2022 | 15 | TARUN KUMAR BHATTACHARYA | 2.19 | 1.12 | 0
2541 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000032/2022-2023 | 4275/ND | 29/09/2022 | 0 | Resource Division | 0.02 | 0 | 0
2542 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) | Assistant Engineer |  | VCH/000908/2021-2022 | 548/PFMS | 23/02/2022 | 0 | TARUN KUMAR BHATTACHARYA | 35 | 0 | 0
2543 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) | Assistant Engineer |  | VCH/000968/2021-2022 | 576/PFMS | 04/03/2022 | 0 | TARUN KUMAR BHATTACHARYA | 21.16 | 0 | 0
2544 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Dakshinpara Z-I Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.E. Dte.(Phase-A) | Assistant Engineer | Junior Engineer 2 | ORD/000203/2021-2022 | 5177/ND | 20/09/2021 | 90 | M/S KALIMATA ENTERPRISE | 88.33 | 87.91 | 0
2545 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000018/2021-2022 | 99/ND | 06/01/2022 | 0 | Resource Division | 2.65 | 0 | 0
2546 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000054/2021-2022 | 793/ND | 18/02/2022 | 0 | Resource Division | 8.77 | 0 | 0
2547 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000117/2021-2022 | 1035/ND | 03/03/2022 | 0 | Resource Division | 15.16 | 0 | 0
2548 | Nadia Division | Ranaghat Sub-Division | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | Assistant Engineer | Junior Engineer 2 | VCH/001011/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 8.13 | 0 | 0
2549 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000020/2020-2021 | 1061/NACD-II | 25/09/2020 | 15 | TAPAS GHOSH | 4.99 | 0 | 0
2550 | Nadia Arsenic Civil Division II |  | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000159/2021-2022 | 902/NACD-II | 22/11/2021 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 73.33 | 0 | 0
2551 | Nadia Arsenic Civil Division II |  | Material Requisition To Resource Division |  |  | RTOR000001/2021-2022 | 608/NACD-II | 04/08/2021 | 0 | Resource Division | 59.68 | 0 | 0
2552 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Baliadanga W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000019/2020-2021 | 1060/NACD-II | 25/09/2020 | 15 | SHYAMAL KANTI GHOSH | 4.99 | 0 | 0
2553 | Nadia Division | RWS Nadia Sub-Division | Reimbursement of Additional GST due to enhancement of rate from 12% to 18% vide notification no. 03/2022 central Tax Rate dt. 13.07.2022. of Laying of Distribution System including specials & valves,pipe supporting structure all complete and Providing FHTC including supplying,laying,fitting,fixing of 15mm NB PVC(schedule 80)/20mm OD HDPE(PE100,PN16) pipe with all necessary specials,10mm gun metal ferrule,saddle piece etc. by retroffitting under Jal Swapna for Badlangi Padmamala Zone-II Water Supply Scheme in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | BILL/00246/2024-2025 | 150/PFMS | 31/07/2024 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 6.5 | 0 | 0
2554 | Nadia Division | RWS Nadia Sub-Division | Additional work of Laying Distribution System and additional work of providing FHTC in connection with Augmentation of Badlangi Padmamala Zone - II PWSS in Bania Khari & Chotta Andulia Mouza within Chapra Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000066/2024-2025 | 3899/ND | 16/07/2024 | 180 | J.P. CONSTRUCTION & SUPPLIERS | 75.72 | 0 | 60
2555 | Nadia Division | RWS Nadia Sub-Division | Collection of Household data through mobile app for FHTC Connection (Phase-VII), under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000158/2024-2025 | 1220/KlySD-I | 09/08/2024 | 184 | TECHVISION | 4.85 | 0 | 100
2556 | Nadia Division | RWS Nadia Sub-Division | Collection of Household data through mobile app for FHTC Connection (Phase-VIII), under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000159/2024-2025 | 1221/KlySD-I | 09/08/2024 | 184 | TECHVISION | 4.85 | 0 | 100
2557 | Nadia Division | RWS Nadia Sub-Division | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000254/2024-2025 | 6305/ND | 26/09/2024 | 30 | IMAGIN | 34.21 | 0 | 100
2558 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution System including specials & valves, pipe supporting structure all complete and Providing FHTC including supplying,laying,fitting, fixing of 15mm NB PVC(schedule 80)/ 20mm OD HDPE(PE100,PN16) pipe with all necessary specials,10mm gun metal ferrule,saddale piece etc.by retrofitting under Jal Swapna for Badlangi Padmamala Zone-II Water Supply Scheme in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000671/2021-2022 | 662/ND | 11/02/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 458.3 | 260.85 | 78
2559 | Nadia Division | RWS Nadia Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site of Badlangi Padmamala Zone-I Water Supply scheme under RWS Sub Division under Nadia Division-,P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000672/2024-2025 | 7451/ND | 20/12/2024 | 270 | ROY ASSOCIATES | 85.97 | 0 | 25
2560 | Nadia Division | RWS Nadia Sub-Division | Withdrawing and Shifting of UPVC with repairing of FHTC pipeline for widening of PWD roads from Elemnagar to Hridaypur under Badlangi Padmamala Zone-II Water Supply Scheme within Chapra Block in Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000693/2024-2025 | 88/ND | 07/01/2025 | 45 | S.S.INFRASTRUCTURE | 14.79 | 0 | 100
2561 | Nadia Division | RWS Nadia Sub-Division | Collection of Household data through mobile app for FHTC Connection (Phase-V), under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000697/2023-2024 | 221/KLYSD-I | 09/02/2024 | 182 | TECHVISION | 4.85 | 0 | 100
2562 | Nadia Division | RWS Nadia Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir, Pump House, Boundary Wall and Construction of Srevice Road for Badlangi Padmamala Zone-II Water Supply Scheme under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000719/2023-2024 | 1303/ND | 23/02/2024 | 90 | B.S. ENTERPRISE | 34.23 | 0 | 100
2563 | Nadia Division | RWS Nadia Sub-Division | Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000769/2023-2024 | 1821/ND | 14/03/2024 | 31 | IMAGIN | 34.21 | 0 | 60
2564 | Nadia Division | RWS Nadia Sub-Division | Conversion of IEP to AIRP of capacity 120 Cu.m/hr at Badlangi Padmamala Zone-II Water Supply Scheme within Chapra block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000801/2023-2024 | 1913/ND | 15/03/2024 | 720 | MONDAL PRECISION PRIVATE LIMITED | 194.64 | 0 | 20
2565 | Nadia Division | RWS Nadia Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site of Badlangi Padmamala Zone-II Water Supply scheme under RWS Sub Division under Nadia Division-,P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000808/2024-2025 | 874/ND | 25/02/2025 | 240 | S.D. CONSTRUCTION | 25.17 | 0 | 40
2566 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | RTOR000046/2022-2023 | 4296/ND | 29/09/2022 | 0 | Resource Division | 22.45 | 0 | 0
2567 | Nadia Division | RWS Nadia Sub-Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | VCH/001053/2021-2022 | 611/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.18 | 0 | 0
2568 | Nadia Division | RWS Nadia Sub-Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | VCH/001116/2021-2022 | 695/PFMS | 28/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 38.35 | 0 | 0
2569 | Eastern Mechanical | RWS Nadia Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under BADELANGI PADMAMALA ZONE-II ground water based water supply scheme under Block_ CHAPRA Dist. - Nadia under EMD, PHE Dte. SM/09450 | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/000177/2025-2026 | 1113/EMD | 04/06/2025 | 90 | BIDYUT KUMAR MUKHERJEE | 20.78 | 0 | 0
2570 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I & II Z-II under Bayra W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/001913/2022-2023 | 6184 EMD | 14/08/2022 | 30 | TALUKDER & CO. | 8.94 | 0 | 100
2571 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator etc. Rejuvention to accommodate FHTC) at PH-I & II (Zone-II) under Badelangi Padmamala W/S Scheme Block Chapra under District of Nadia) | Assistant Engineer | Junior Engineer,Junior Engineer Chapra Block | ORD/002002/2022-2023 | 6184 / EMD | 14/08/2022 | 30 | TALUKDER & CO. | 8.94 | 8.94 | 0
2572 | Nadia Division | Krishnanagar Sub-Division | RESTORATION OF ROAD FROM MOHISURA TO BANKAR DHOPADI under Package No. WB/14/116 | Assistant Engineer | Junior Engineer,Junior Engineer 2 | BILL/00531/2024-2025 | 321/PFMS | 05/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 6.38 | 0 | 0
2573 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of capacity 156 m3/hr at Mahisura Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000255/2024-2025 | 6571/ND | 21/10/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 348.3 | 0 | 0
2574 | Nadia Division | Krishnanagar Sub-Division | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period of 90 days w.e.f 01/07/2023 (as and when required). | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000410/2023-2024 | 800/KSD | 16/06/2023 | 92 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0
2575 | Nadia Division | Krishnanagar Sub-Division | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Mahisura Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000489/2023-2024 | 6116/ND | 21/12/2023 | 60 | DEL DELTA CONSTRUCTION | 11.42 | 0 | 100
2576 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including Specials, Valves & Pipe Supporting Structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. and Construction of boundary wall at head work site all complete for Augmentation of Ground Based Water Supply Scheme at Mahisura (Phase-I) to accommodate FHTC with Nabadwip Block under Krishnagar Sub-Division, PHE Dte. (SM/10418) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000538/2022-2023 | 1388/ND | 29/03/2023 | 90 | PATHIK PABAN NANDI | 373.94 | 298.55 | 60
2577 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000088/2023-2024 | 2317/ND | 29/05/2023 | 0 | Resource Division | 15.4 | 0 | 0
2578 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000153/2022-2023 | 124/ND | 05/01/2023 | 0 | Resource Division | 14.44 | 0 | 0
2579 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-I) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/000291/2022-2023 | 14/PFMS | 11/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.6 | 0 | 0
2580 | Nadia Division | Kalyani Sub-Division I | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 135 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Tehatta to accommodate FHTC within Tehatta-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000094/2024-2025 | 4230/ND | 02/08/2024 | 180 | TARUN KUMAR BHATTACHARYA | 315.65 | 0 | 0
2581 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution system including specials, valves & pipe supporting structure all complete & Providing FHTC at Augmentation of Ground Water Based Water Supply Scheme for Tehatta(Phase-I) to accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000102/2022-2023 | 3419/ND | 02/08/2022 | 90 | H I ENTERPRISE | 465.49 | 460.45 | 93
2582 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000028/2022-2023 | 4020/ND | 16/09/2022 | 0 | Resource Division | 70.86 | 0 | 0
2583 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000064/2022-2023 | 4288/ND | 29/09/2022 | 0 | Resource Division | 0.04 | 0 | 0
2584 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000168/2022-2023 | 112/ND | 05/01/2023 | 0 | Resource Division | 2.19 | 0 | 0
2585 | Nadia Division | Kalyani Sub-Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Tehatata (Phase-I) to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000199/2022-2023 | 23/PFMS | 20/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.14 | 0 | 0
2586 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-IX(A) to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000085/2022-2023 | 3278/ND | 26/07/2022 | 90 | A ONE CONSTRUCTION | 138.52 | 133.22 | 99
2587 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Karimpur Jalangi Zone-IX A Ground Based Water Supply Scheme under Karimpur II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Karimpur Jalangi Zone-IX A at Karimpur II Block by Augmentation of Ground Water based PWSS for Karimpur Jalangi Zone-IX A Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000640/2024-2025 | 7366/ND | 18/12/2024 | 60 | SUBIR KUMAR DEY | 21.9 | 0 | 0
2588 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000020/2022-2023 | 3523/ND | 05/08/2022 | 0 | Resource Division | 25.05 | 0 | 0
2589 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000065/2022-2023 | 4300/ND | 29/09/2022 | 0 | Resource Division | 9.31 | 0 | 0
2590 | Nadia Division | Tehatta Sub-Division | Augmentation of Ground Water Based Karimpur-Jalangi PWSS Zone-IX(A) to accommodate FHTC in Karimpur-II block with in Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000206/2022-2023 | 30/PFMS | 20/05/2022 | 0 | RADIANT | 2.61 | 0 | 0
2591 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No. I , II under KARIMPUR JALANGI Zone X A WS Scheme, Block Karimpur-II, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-14) | Assistant Engineer | Junior Engineer | ORD/000894/2022-2023 | 162/EMD | 06/01/2023 | 30 | S.B.ENTERPRISE | 9.73 | 0 | 70
2592 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under Karimpur jalangi (Zone-IX,A & B) W/S Scheme, Block-Tehatta-II, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 19) | Assistant Engineer | Junior Engineer | ORD/002779/2022-2023 | 419EMD | 20/01/2023 | 30 | SINHA ELECTRICALS | 14.88 | 13.14 | 85
2593 | Nadia Arsenic Division I | Nadia Arsenic Division I | Work for revamping / upgradation of the hydraulic parameters at Mamjoani mouzas in reference to Mamjoani water supply scheme & Duttaphulia water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 07) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000007/2025-2026 | 76/NAD-1 | 16/04/2025 | 240 | JOYGOPAL GUPTI | 96.49 | 0 | 57
2594 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase -II FHTC under Jaldhara/ Jal Swapna for Ramnagar at Hanskhali Block by retrofitting of Ground Water Based PWSS for Ramnagar Water Supply scheme under Nadia Arsenic Division -I, P.H.E. Dte. (Sl. no -05) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000015/2022-2023 | 962 / NAD-I | 07/07/2022 | 60 | M/S K.P. CONSTRUCTION | 81.96 | 55.58 | 100
2595 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall Pathway Toilet and all repair works at 2 nd TW Site and all repair works at HW site of Ramnagar WS Scheme under NAD I PHE Dte (Sl.no.03) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000063/2022-2023 | 1595 / NAD-I | 06/09/2022 | 45 | SANJIB DEY | 10.06 | 8.56 | 93
2596 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet Pathway and all repair works at 2nd T W allied site and all repair works at HW site of Mamjoani under NAD I PHE Dte (Sl.no.08) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000097/2022-2023 | 1963 / NAD-I | 14/10/2022 | 60 | D.K. CONSTRUCTION | 13.16 | 11.7 | 0
2597 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Mamjoani Part-III at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 13) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000171/2021-2022 | 438/NAD-I | 07/03/2022 | 600 | SHYAMAL SHIL | 88.34 | 70.07 | 100
2598 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Chupria Zone-II Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Chupria Zone-II W/S Scheme under JJM (SL.NO.13) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000013/2023-2024 | 1117 / NAD-I | 27/04/2023 | 715 | MONDAL ENTERPRISE | 12.96 | 0 | 100
2599 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jaldhara / Jalswapna for Garapota P-III at Hanskhali block by retrofitting of Ground Water Based PWSS W/S Scheme under Nadia Arsenic Division -I , P.H.E. Dte. (Sl. No. 12) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000032/2022-2023 | 1512 / NAD-I | 26/08/2022 | 21 | SAHA ENGINEERS | 43.43 | 43.43 | 100
2600 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Kautaknagar, Ramdulalpur, under Mayurhat-I G.P. for Ground Water Based PWSS at Hanskhali Block in connection with augmenttaion of Garapota W/S Scheme under Jal Jeevna Mission (JJM) under Nadia Arsenic Division-I , PHE Dte. (Sl.no.09) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000048/2023-2024 | 1457 /NAD-I | 29/05/2023 | 21 | TAPU SAHA | 21.99 | 21.99 | 100
2601 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall Toilet Pathway and other allied work at Chupria Zone II WS Scheme within Hanskhali Block under NAD- I PHE Dte (Sl.no.01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000062/2022-2023 | 1594 /NAD-I | 06/09/2022 | 45 | SUBIR KUMAR DEY | 12.65 | 12.59 | 100
2602 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Garapota Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Garapota W/S Scheme under JJM (Sl.no 08) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000082/2023-2024 | 1072/NAD-I | 24/04/2023 | 738 | SWAPAN KUMAR BISWAS | 12 | 0 | 100
2603 | Nadia Arsenic Division I | Nadia Arsenic Division I | Operation & Maintenance of Distribution System and Rising Main Pipeline (CI/DI/UPVC) and Iron Elimination Plant of Different Ground Based Piped Water Supply Scheme for arsenic affected areas of Joypur, Itaberia, Chupria Z-I, Chupria Z-II, Gobindapur ( Hanskhali ) and Garapota & adjoining mouzas for the period of 1 year under Nadia Arsenic Division - I, P.H. Engineering Dte. (Sl.no. 01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000083/2022-2023 | 1920 / NAD-I | 30/09/2022 | 365 | APURBA MANDAL | 28.6 | 0 | 0
2604 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir, Painting of Pump House in connection with Augmentation of Garapota W/S Scheme in Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl.no.23) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000097/2023-2024 | 892/NAD-I | 04/04/2023 | 30 | S B CONSTRUCTION | 26.31 | 16.15 | 75
2605 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP (Pressure Type) at Garapota W/S Scheme under Hanskhali Block of capacity 120 cum/hr. under augmentation of Garapota W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.05) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000133/2023-2024 | 1901/NAD-I | 14/08/2023 | 592 | HARBAUER INDIA PRIVATE LIMITED | 166.14 | 0 | 56
2606 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Chupria Zone-II Part-III at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 08) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000166/2021-2022 | 434/NAD-I | 07/03/2022 | 60 | M/S SHIL AND CO. | 45.66 | 43.22 | 100
2607 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 450 cum capacity Over Head Reservoir ,Painting and Pump House at Chupria, Zone-II underSurface W/S Scheme in Hanskhali Block under NadiaArsenic Division - I P. H.E. Dte (Sl.no.14) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000191/2022-2023 | 154 /NAD-I | 07/02/2023 | 30 | APURBA MANDAL | 22.4 | 22.33 | 45
2608 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet, Pathway and other allied work at Head Work T/W site in connectionwith Augmentation of Chupria Zone-II water supply Scheme within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. (SL.19) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000248/2022-2023 | 579/NAD-I | 17/03/2023 | 15 | DIPANKAR DUTTA | 18.87 | 8.18 | 48
2609 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet, Pathway and other allied work at Head Work T/W site in connection with Augmentation of Garapota water supply Scheme within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. ( sl.no.12) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000249/2022-2023 | 580/NAD-I | 17/03/2023 | 21 | ONKAR ENTERPRISE | 19.03 | 0 | 100
2610 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Garapota Bazar to H/O Chayan Biswas, Boro Chupria & Paschim Garapota to H/O Sanjiban Biswas, Boro Chupria at Hanskhali Block by retrofitting of Ground Water Based PWSS for Chupria W/S Scheme underNadia Arsenic Division-I, P.H.E. Dte. (Sl.20) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000267/2022-2023 | 827 / NAD-I | 31/03/2023 | 30 | JAGADANADAPUR CO-OPT LABOUR CONTTRACT AND CONSTRUTION SOCITY LTD. | 32.85 | 20.68 | 0
2611 | Eastern Mechanical | Nadia Arsenic Division I | Shifting of LT OH line by erection of 2nos PCC pole 8meter long at Garapota (Ph-1) at Hanskhali block, Dist.-Nadia | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | BILL/00334/2024-2025 | BP-20-24-25 | 21/05/2024 | 0 | W.B.S.E.D.C.LTD (BAGULA C.C.C) | 0.41 | 0 | 0
2612 | Eastern Mechanical | Nadia Arsenic Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under GARAPOTA,BHAYNA(Z-I), BHAYNA(Z-II) & MAMJOANI W/S Scheme, Block-HANSKHALI , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000025/2023-2024 | 1604/EMD | 26/04/2023 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 61.43 | 0 | 80
2613 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supply and installation of Butterfly Valve at Back Wash OHR at Palagachha under JJM under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000045/2023-2024 | 246/AE-II/NAD-I | 18/05/2023 | 7 | SATYABRATA CHAKRABORTY | 2.76 | 2.65 | 100
2614 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 350 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Palagacha Zone-I under Chakdah Surface W/S Scheme in Chakdah Block under NAD I PHE Dte (Sl.no.10) | Assistant Engineer-II | Junior Engineer-IV | ORD/000064/2022-2023 | 1597/NAD-I | 06/09/2022 | 45 | M/S PRADIP KUMAR PAL | 12.72 | 0 | 100
2615 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for clear water rising main & distribution main at Palagachha Zone-I W/S Scheme in connection with Augmentation of Palagachha (Zone-I) & Masra (Zone-III) under JJM under Nadia Arsenic Division-I , PHE Dte. (Sl. No. 12)" | Assistant Engineer-II | Junior Engineer-IV | ORD/000077/2023-2024 | 1411/NAD-I | 18/05/2023 | 21 | THE TOWER CONSTRUCTION | 36.38 | 25.37 | 75
2616 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting works at Balir math and Palagachha (Zone-I) W/S Scheme under Surface Water Based PWSS for Chakdah (Part) water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 09) | Assistant Engineer-II | Junior Engineer-IV | ORD/000126/2022-2023 | 3042/NAD-I | 09/11/2022 | 60 | BUDDHADEV MONDAL | 9.28 | 9.27 | 100
2617 | Nadia Arsenic Division I | Nadia Arsenic Division I | Shifting of UPVC distribution main pipe line from Palagacha more to WTP of Palagacha (Zone-I) W/S Scheme under Chakdah Surface W/S Scheme under Nadia Arsenic Division-I PHE Dte.(sl.no.03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000127/2022-2023 | 1424 / NAD-I | 12/08/2022 | 30 | G.B. CONSTRUCTION | 29.6 | 24.88 | 0
2618 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Masra (Zone- III) under Chakdah Surface WS Scheme in Chakdah Block under NAD I PHE Dte (Sl.no.09) | Assistant Engineer-II | Junior Engineer-IV | ORD/000136/2022-2023 | 1969 / NAD-I | 14/10/2022 | 60 | RAM KRISHNA CHAKRABORTY | 26.49 | 23.33 | 100
2619 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Node Point 180 to 180 at Lalpur of Palagacha (Zone-I) W/S Scheme under Chakdah Surface W/S Scheme at Chakdah Block under Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E. Dte | Assistant Engineer-II | Junior Engineer-IV | ORD/000148/2023-2024 | 376/AE-II/NAD-I | 29/08/2023 | 7 | M/S K..M. ENTERPRISE | 4.71 | 0 | 100
2620 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Masra (Zone-III), (Part-II) Water Supply Scheme under Chakdah (Part) Surface Water Based W/S Scheme under Nadia Arsenic Division-I, PHE Dte. Sl. No.- 11 | Assistant Engineer-II | Junior Engineer-IV | ORD/000151/2022-2023 | 3329/NAD-I | 15/12/2022 | 45 | KESHOB ENTERPRISE | 28.27 | 27.95 | 0
2621 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase-III FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III (Masra), at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000152/2022-2023 | 3446/NAD-I | 21/12/2022 | 30 | SUMIT GHOSH | 39.83 | 0 | 100
2622 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofittng work at Mahanala due to construction of N.H.-34 road under Palagacha (Zone-I ) within Chakdah Surface W/S Scheme under JJM under Nadia Arsenic Division-I ,PHE Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000154/2023-2024 | 2113/NAD-I | 01/09/2023 | 15 | K K MARKETING | 6.82 | 0 | 100
2623 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at RanjanPally, Lalpur and Singher Bagan under Palagacha W/S Scheme under JJM within Chakdah Block under Nadia Arsenic Division-I, PHE Dte. (Sl.no.05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000160/2023-2024 | 2118/NAD-I | 04/09/2023 | 15 | MANAJIT BISWAS | 13.58 | 13.07 | 100
2624 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Palagachha Zone-I Chakdah Block Palagachha (Zone-I) & Mosra (Zone-III) at Chakdah Block, Dist- Nadia of Surface Water Based PWSS for Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000177/2022-2023 | 33/NAD-I | 17/01/2023 | 15 | SUNIL KUMAR DATTA | 11.95 | 10.98 | 100
2625 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-I, (Palagachha), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000179/2021-2022 | 516/NAD-I | 28/03/2022 | 60 | SHYAMAL SHIL | 134.14 | 134.07 | 100
2626 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, PrimarySchool, SSK & MSK under Jal Jeevan Mission (JJM) atMosra (Zone-III) Kalyani Block under Palagachha (Zone-I) & Mosra (Zone-III) Dist.-Nadia of Surface Water Based PWSS for Chakdah (Part) Surface Water Based Water Supply Scheme of Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. (sl.no. 07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000215/2022-2023 | 242 / NAD-I | 17/02/2023 | 15 | M/S S.K ENTERPRISE | 10.79 | 9.26 | 60
2627 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at DD Brick Field at Palagacha in connection with augmentation of Zone-I, Palagacha W/S Scheme under Surface Water Based PWSS for Chakdah (Part) under Jal Jeevan Mission under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte.(sl.03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000275/2022-2023 | 170//AE-II/NAD-I | 27/03/2023 | 21 | K K MARKETING | 4.48 | 4.28 | 0
2628 | Eastern Mechanical | Nadia Arsenic Civil Division II | Quotation charges and security deposit for new power connection at Joyghata Mini scheme under Eastern Mechanical Subdivision-III, Nadia | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/02249/2024-2025 | BP-174 | 13/12/2024 | 0 | WBSEDCL KARIMPUR CCC | 0.09 | 0 | 0
2629 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejuvenation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under JOYGHATA ground water based water supply scheme under Block_ KRISHNAGANJ Dist. - Nadia under EMD, PHE Dte. [SM/09252] | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000647/2024-2025 | 2684/EMD | 20/11/2024 | 285 | M/S GHOSH ENTERPRISE | 20.24 | 0 | 100
2630 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Joyghata H/W and 2nd Pump house site with Reinforced Barbed Tape , Plaster , Painting and other allied works.Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000015/2024-2025 | 137/AE-II/NACD-II | 11/06/2024 | 30 | PRADIP KUMAR BANIK | 2.97 | 0 | 100
2631 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Joyghata Water Supply Scheme in Krishnaganj Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000065/2023-2024 | 323/1/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.18 | 0 | 100
2632 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnaganj Block of Nadia District through Jadavpur University. (Name of PWSS Joyghata) | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000085/2024-2025 | 862/NACD-II | 03/07/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
2633 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also construction of Soak Pit at Joyghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000099/2021-2022 | 738/NACD-II | 13/09/2021 | 45 | CHANDAN ROY | 46.43 | 46.24 | 100
2634 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000122/2024-2025 | 820/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.16 | 0 | 100
2635 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Joyghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000129/2020-2021 | 269/NACD-II | 22/02/2021 | 21 | SUBHASIS MOJUMDER | 46.67 | 0 | 100
2636 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Joyghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000130/2021-2022 | 869/NACD-II | 08/11/2021 | 45 | USHA CONSTRUCTION | 63.38 | 63.37 | 100
2637 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Reparing and renovation of inside of OHR at Joyghata Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000131/2022-2023 | 67/AE-II/NACD-II | 28/06/2022 | 30 | BIPLAB GUHA | 2.9 | 2.9 | 100
2638 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at 2nd TW site of Joyghata W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000143/2024-2025 | 245/AE-II/NACD-II | 31/07/2024 | 15 | SUBHASIS MOJUMDER | 0.85 | 0 | 100
2639 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Joyghata W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000144/2024-2025 | 246/AE-II/NACD-II | 31/07/2024 | 15 | SUPRIO MAJUMDER | 0.86 | 0 | 100
2640 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Newly added pipeline at Joyghata Piped Water Supply Scheme ( Vill- Joyghata) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000192/2023-2024 | 555/AE-I/NACD-II | 10/01/2024 | 15 | BIPLAB GUHA | 0.97 | 0 | 100
2641 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Exigent connection of higher specification components as per IS Code 8329 with its latest version in the mouza in the JL No. 008 at Joyghata Piped Water Supply Scheme under Krishnaganj Development Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000196/2024-2025 | 312AE-II/NACD-II | 06/09/2024 | 359 | PAPAN ROY | 3.31 | 0 | 100
2642 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Joyghata Head Work site in Krishnaganj Block with Overhead Reservoir painting, Plaster, Painting and other allied works under Nadia Arsenic Division-II,P.H.E.Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000216/2024-2025 | 1310/NACD-II | 20/09/2024 | 88 | SANJIT DAS | 7.64 | 0 | 100
2643 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Joyghata Water Supply Scheme at Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000246/2021-2022 | 102/NACD-II | 10/02/2022 | 45 | BIPLAB GUHA | 6.45 | 6.37 | 100
2644 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Joyghata Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000249/2023-2024 | 22/AE-II/NACD-II | 15/02/2024 | 15 | SUPRIO MAJUMDER | 0.97 | 0 | 100
2645 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Joyghata 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000266/2021-2022 | 51/AE-II/NACD-II | 17/02/2022 | 30 | PARTHA DAS | 4.47 | 4.44 | 100
2646 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Joyghata Water Supply Scheme of capacity 64 Cu.m/hr under Krishnaganj Block & Jayrampur water Supply Scheme under Karimpur-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000283/2023-2024 | 140/NACD-II | 01/02/2024 | 600 | GHOSH ENTERPRISE | 202.08 | 0 | 0
2647 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Joyghata W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000300/2022-2023 | 1198/NACD-II | 23/12/2022 | 15 | SUBHASIS MOJUMDER | 2.49 | 2.41 | 100
2648 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Joyghata Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000308/2021-2022 | 108/AE-II/NACD-II | 04/03/2022 | 5 | MAKALI ENGINEERING CORPORATION | 4.89 | 4.89 | 100
2649 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Joyghata Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000316/2021-2022 | 112/AE-II/NACD-II | 10/03/2022 | 5 | MAKALI ENGINEERING CORPORATION | 4.75 | 4.75 | 100
2650 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Functional House Hold Tap Connection for left out Household regarding Har Ghar Jal Certification including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Vill- Ghuguragachhi) Joyghata W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000347/2022-2023 | 147/NACD-II | 17/01/2023 | 20 | CHANDRA NATH GHOSH | 3.15 | 0 | 100
2651 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000002/2024-2025 | 984/NACD-II | 23/07/2024 | 0 | Resource Division | 16.59 | 0 | 0
2652 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SAKDA (Block-Krishnaganj), BAHADURPUR(Block-Tehatt-I), BETBERIA(Block-Chapra) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000009/2023-2024 | 1507/EMD | 18/04/2023 | 30 | SWAPAN KUMAR BHANJA | 14.69 | 4.88 | 100
2653 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Sakdaha H/W and 2nd Pump house site with Reinforced Barbed Tape , Plaster , Painting , and other allied works.Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000016/2024-2025 | 138/AE-II/NACD-II | 11/06/2024 | 201 | BABLU MALLICK | 3.96 | 0 | 100
2654 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing of Hydraulic Connectivity in the Left out habitations at sakdaha water supply scheme as per IS Code 10500:2012 in the Block of Krishnaganj, Nadia Under Nadia Arsenic Civil Division-II, P.H.E Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000029/2024-2025 | 129/AE-II/NACD-II | 10/06/2024 | 15 | SHYAMAL SHIL | 4.85 | 0 | 100
2655 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Provisioning of Har Ghar Jal an Integral Component of Jal Jeevan Mission with necessary addition and alteration at sakdaha water supply scheme in the Krishnagar Sadar Sub Division, Nadia under Nadia Arsenic Civil Division-II, P.H.E Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000030/2024-2025 | 130/AE-II/NACD-II | 10/06/2024 | 15 | SHYAMAL SHIL | 4.83 | 0 | 100
2656 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum Work Order "Sinking of 2 nos. 300 mm X 200 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at the new proposed sites of Sakdah Zone-I and Zone-II in Krishnaganj Block under Sakdah Public Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. Alternate Site - Thanapara Zone-II 2nd T/w Site, Maliapota, Patharghata." | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000032/2025-2026 | 570/NACD-II | 08/05/2025 | 135 | B.M. ENGINEERING & CONSTRUCTION | 21.67 | 0 | 40
2657 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Additional work for the Sakdaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000054/2024-2025 | 162/AE-II/NACD-II | 14/06/2024 | 15 | M/S. ASIT KUMAR BISWAS | 0.51 | 0 | 100
2658 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Sakdaha Water Supply Scheme in Krishnaganj Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000064/2023-2024 | 322_2/AE-I/NACD-II | 13/07/2023 | 7 | RISHAN ENGINEERING CONSULTANCY | 0.71 | 0 | 100
2659 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnaganj Block of Nadia District through Jadavpur University. (Name of PWSS Sakdaha) | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000086/2024-2025 | 863/NACD-II | 03/07/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
2660 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Jungle cutting and Earthwork in filling at Taldaha,Sakdaha and Brittihuda Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000121/2024-2025 | 819/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.53 | 0 | 100
2661 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Sakdaha Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000246/2023-2024 | 23/AE-II/NACD-II | 15/02/2024 | 225 | SHYAMAL SHIL | 0.97 | 0 | 100
2662 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Sakdaha Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000249/2021-2022 | 107/NACD-II | 10/02/2022 | 45 | SAMAR ENTERPRISE | 5.63 | 5.34 | 100
2663 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Sakdaha (Vill- Bhagaban pur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000291/2020-2021 | 297./NACD-II | 25/02/2021 | 15 | M/S. ASIT KUMAR BISWAS | 4.67 | 2.14 | 100
2664 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Sakdaha W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000294/2022-2023 | 1192/NACD-II | 23/12/2022 | 15 | M/S. ASIT KUMAR BISWAS | 1.33 | 1.27 | 100
2665 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Sakdaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000302/2021-2022 | 734./NACD-II | 13/09/2021 | 45 | M/S K.P. CONSTRUCTION | 50.23 | 50.12 | 100
2666 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Sakdaha Water Supply Scheme of capacity 30 Cu.m/hr in Krishnaganj Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000307/2023-2024 | 423/NACD-II | 15/03/2024 | 607 | JOY GOPAL GUPTI | 84.47 | 0 | 82
2667 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Sakdaha Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000309/2021-2022 | 109/AE-II/NACD-II | 04/03/2022 | 5 | MAKALI ENGINEERING CORPORATION | 4.98 | 4.98 | 100
2668 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Supply of CIDF Sluice valve and DI specials for vavle to facilitate Functional House Hold Connection of Sakdaha Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000317/2021-2022 | 113/AE-II/NACD-II | 10/03/2022 | 5 | MAKALI ENGINEERING CORPORATION | 4.93 | 4.93 | 100
2669 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC at under FATEPUR W/S Scheme, Block-Hanskhali , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 10) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000019/2023-2024 | 1582/EMD | 24/04/2023 | 30 | PERPETUAL ENTERPRISE | 11.05 | 0 | 100
2670 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Fatepur H.W site with Reinforced Barbed Tape ,Plaster ,Painting ,Valve Slab, Concreting, and other allied works Under Nadia Arsenic Division-II,P.H.E.Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000026/2024-2025 | 149./AE-II/NACD-II | 11/06/2024 | 30 | SUJAUDDIN SHAIKH | 4.13 | 0 | 100
2671 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Fatepur Water Supply Scheme in Tehatta_I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000063/2023-2024 | 322/1/AE-I/NACD-II | 13/07/2023 | 7 | RISHAN ENGINEERING CONSULTANCY | 0.71 | 0 | 100
2672 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Fatepur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000240/2023-2024 | 155/NACD-II | 05/02/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
2673 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Fatepur Water Supply Scheme at Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000245/2021-2022 | 101/NACD-II | 10/02/2022 | 45 | CHANDAN ROY | 10.75 | 10.73 | 100
2674 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Fatepur 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000257/2021-2022 | 38/AE-II/NACD-II | 17/02/2022 | 30 | M/S. ASIT KUMAR BISWAS | 3.19 | 3.16 | 100
2675 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Fatepur Water Supply Scheme of capacity 26 Cu.m/hr in Tehatta -I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000287/2023-2024 | 186/NACD-II | 09/02/2024 | 60 | MONDAL ENTERPRISE | 111.31 | 0 | 0
2676 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000348/2024-2025 | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 20
2677 | Eastern Mechanical | Nadia Arsenic Civil Division II | New service connection charges for Paninala Ph. 2 J1-43 kh-950 | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/01860/2022-2023 | 141/PFMS/EMD | 06/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.69 | 0 | 0
2678 | Eastern Mechanical | Nadia Arsenic Civil Division II | New service connection charges for Paninala Ph. 1 J1-43 kh-1378 | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/01862/2022-2023 | 140/PFMS/EMD | 06/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.64 | 0 | 0
2679 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Headworks) under Paninala W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. NNo.- 07) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000101/2022-2023 | 5015/EMD | 03/11/2022 | 30 | HARA PROSAD DAS | 10.11 | 0 | 100
2680 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Paninala W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000102/2022-2023 | 5016/EMD | 03/11/2022 | 30 | NEW RANBEE ENGINEERING | 10.13 | 0 | 90
2681 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Paninala Piped Water Supply Scheme, Block: Dist. Nadia Under EMD, PHE Dte. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.-14) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000110/2022-2023 | 6040/EMD | 07/11/2022 | 30 | M/S S.R. ENTERPRISE | 41.38 | 0 | 0
2682 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Paninala water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000005/2022-2023 | 203/NACD-II | 05/04/2022 | 60 | SUMIT GHOSH | 5.37 | 5.32 | 100
2683 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Paninala Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. (Sl. No. 02) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000016/2022-2023 | 221/NACD-II | 05/04/2022 | 30 | TAPAS GHOSH | 5.64 | 0 | 100
2684 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement for Tube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Paninala water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000029/2022-2023 | 16/AE-I/NACD-II | 13/04/2022 | 60 | SUMIT GHOSH | 2.83 | 2.81 | 100
2685 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Krishnagar-I Block of Nadia District through Jadavpur University. (Name of PWSS Paninala) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000083/2023-2024 | 889/NACD-II | 18/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
2686 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Hridaypur) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000084/2023-2024 | 892/NACD-II | 21/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 0 | 100
2687 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Paninala and adjoining mouzas under Paninala Water Supply Scheme of Krishnagar-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000115/2022-2023 | 376/NACD-II | 22/06/2022 | 90 | KINGS & CO. | 242.52 | 162.45 | 90
2688 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Paninala and Maniknagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000135/2022-2023 | 432/NACD-II | 07/07/2022 | 60 | JOY HIND TUBEWELLS | 43.35 | 0 | 100
2689 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction for priliminary work of the approch road at Head Works site of Paninala Water Supply Scheme in Krishnagar-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000150/2023-2024 | 515/AE-I/NACD-II | 18/12/2023 | 15 | M/S GHOSH CONSTRUCTION | 0.97 | 0 | 100
2690 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 31 cum/Hour capacity for Paninala Water Supply Scheme within Krishnagar-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000166/2024-2025 | 1145/NACD-II | 23/08/2024 | 180 | MAMATA USHA ENTERPRISE | 160.26 | 0 | 0
2691 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Paninala Water Supply Scheme of Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000190/2022-2023 | 620/NACD-II | 06/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.94 | 3.94 | 100
2692 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of flow control devices in the closed water conduit at Paninala PWSS in Krishnagar-I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000263/2024-2025 | 947/AE-I/NACD-II | 24/10/2024 | 7 | MAKALI ENGINEERING CORPORATION | 0.98 | 0 | 100
2693 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earth work in filling in ditches and Drum Sheet Walling at Paninala Water Supply Scheme under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000268/2022-2023 | 1070/NACD-II | 08/12/2022 | 30 | TAPAS GHOSH | 16.37 | 0 | 100
2694 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of a single Storied Warehouse with Steel Truss Roof at Paninala Water Supply Scheme Head Work Site under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000296/2023-2024 | 325/NACD-II | 04/03/2024 | 540 | AMIT KARMAKAR | 40.55 | 0 | 60
2695 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Paninala Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000318/2022-2023 | 82/NACD-II | 10/01/2023 | 60 | ZOOM CONSTRUCTION & INTERIO | 17.3 | 17.29 | 85
2696 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Paninala 2nd Tubewell site within Paninala Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000328/2022-2023 | 120/NACD-II | 11/01/2023 | 60 | SREE GURU ENTERPRISE | 5.14 | 3.54 | 65
2697 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Paninala water supply scheme of Krishnagar-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000387/2022-2023 | 394/NACD-II | 28/03/2023 | 696 | M/S GHOSH CONSTRUCTION | 118.89 | 0 | 100
2698 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000011/2022-2023 | 401/NACD-II | 04/07/2022 | 0 | Resource Division | 55.85 | 0 | 0
2699 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | VCH/000242/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
2700 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | VCH/000348/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
2701 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Restoration by UPVC Pipeline for replacing the damaged pipeline at Barnia Bazar and also construction of RCC slab for at Barnia Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000120/2021-2022 | 135/AE-I/NACD-II | 28/10/2021 | 15 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 3.21 | 3.2 | 100
2702 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000140/2020-2021 | 275/EE/NACD-II | 22/02/2021 | 21 | USHA CONSTRUCTION | 51.53 | 0 | 100
2703 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia (Village- Charakpota) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000142/2021-2022 | 824/NACD-II | 25/10/2021 | 45 | JOY HIND TUBEWELLS | 68.53 | 68.53 | 100
2704 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Barnia, (Block -Tehatta-II) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000149/2021-2022 | 148/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 3.63 | 3.63 | 100
2705 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of CIDF Sluice, Non return valves and DI Mechanical collar Vavle for relaying of rising main of Barnia Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000162/2021-2022 | 165/AE-I/NACD-II | 22/11/2021 | 7 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.97 | 4.97 | 100
2706 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000165/2021-2022 | 850/NACD-II | 02/11/2021 | 45 | JOY HIND TUBEWELLS | 73.72 | 73.72 | 100
2707 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Barnia (Phase-II), (Block -Tehatta-II) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000172/2021-2022 | 751/NACD-II | 15/09/2021 | 10 | SIRCON ENGINEERING SERVICE | 4.73 | 4.73 | 100
2708 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair and also DI Laying in distribution at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000211/2021-2022 | 993/NACD-II | 30/12/2021 | 45 | J.D.J. ENTERPRISE | 98.17 | 78.66 | 100
2709 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000232/2021-2022 | 982/EE/NACD-II | 27/12/2021 | 45 | M/S. R.K.ENTERPRISE | 152.25 | 14.58 | 100
2710 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Relaying of D.I. Pipeline replacing the damaged old UPVC Pipe at Barnia W/s Scheme in Nadia District under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000241/2021-2022 | 98/NACD-II | 10/02/2022 | 45 | PRABIR KUMAR ROY | 14.31 | 13.74 | 100
2711 | Nadia Arsenic Civil Division II |  | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. |  |  | ORD/000122/2024-2025 | 820/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.16 | 0 | 100
2712 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Patharghata (Vill- Gabindapur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000209/2021-2022 | 994/NACD-II | 30/12/2021 | 45 | MALLICK ENTERPRISE | 46 | 45.98 | 100
2713 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Patharghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-Il, P,H.E. Dte." |  |  | ORD/000291/2021-2022 | 126/NACD-II | 21/02/2022 | 90 | J.D. CONSTRUCTION | 106.8 | 106.79 | 100
2714 | Nadia Arsenic Civil Division II |  | Laying of distribution system and also dedicated pipe line including providing FHTC at left out households for Patharghata (Gobindapur, Patharghata) & Puthimari (Vill-Puthimari) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000432/2024-2025 | 247/NACD-II | 27/02/2025 | 180 | SANDIP BISWAS | 101.71 | 0 | 0
2715 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 450 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 450 CUM OHR all complete for Augmentation of Ground Based Water Supply Scheme at Krishnagar Rural to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000182/2022-2023 | 4413/ND | 14/10/2022 | 1083 | DAFFODIL | 488.87 | 244.62 | 70
2716 | Nadia Division | Krishnanagar Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
2717 | Nadia Division | Krishnanagar Sub-Division | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Krishnagar Rural Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000473/2023-2024 | 151/ND | 09/01/2024 | 60 | MONDAL ENTERPRISE | 12.12 | 0 | 100
2718 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab for official use for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01.01.2023 (as and when required). | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000486/2022-2023 | 1331/KSD | 29/12/2022 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 100
2719 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01/04/2023.(as and when required). | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000591/2022-2023 | 376/KSD | 28/03/2023 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0
2720 | Nadia Division | Krishnanagar Sub-Division | Emergent laying of UPVC pipe 90mm Dia and 110mm Dia on Baikuntha sarak from 2no Pumphouse to khayaghat para due to existing pipeline damaged at the time of construction of PMGSY road and Providing FHTC from Krishnagar Rural water supply Scheme under Krishnagar Sub-Division P.H.E Dte under Nadia Division P.H.E Dte | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000724/2021-2022 | 245/KSD | 11/03/2022 | 7 | GOUTAM HALDER | 4.98 | 4.97 | 100
2721 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 86 m3/hr at Krishnagar Rural Water Supply Scheme within Krishnagar-I Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000782/2023-2024 | 1896/ND | 15/03/2024 | 720 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 234.28 | 0 | 70
2722 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000057/2023-2024 | 2289/ND | 29/05/2023 | 0 | Resource Division | 22.96 | 0 | 0
2723 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000098/2022-2023 | 4929/ND | 25/11/2022 | 0 | Resource Division | 36.28 | 0 | 0
2724 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KRISHNAGAR (Rural) to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | Assistant Engineer | Junior Engineer,Junior Engineer 3 | VCH/000196/2022-2023 | 20/PFMS | 20/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.51 | 0 | 0
2725 | Eastern Mechanical | Krishnanagar Sub-Division | Providing, installation and commissioning of Electro-Mechanical Equipments and allied works for submersible pumping machinery of Pump House No.-I and II for Augumentation Tube Well and Arsenic Removal Plant in connection to Accommodate FHTC under Krishnagar(Rural) ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. [SM/10440] | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000339/2024-2025 | 2154/EMD | 30/08/2024 | 30 | HARA PROSAD DAS | 48.83 | 0 | 0
2726 | Nadia Division | Tehatta Sub-Division | Laying of additional pipeline for Arabpur PWSS"under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000120/2024-2025 | 4532/ND | 20/08/2024 | 180 | BIDYUT KUMAR | 12.99 | 0 | 100
2727 | Nadia Division | Tehatta Sub-Division | Laying of additional pipeline for Fazilnagar Mouza and Phulkhali Mouza under Fazilnagar PWSS and Arabpur PWSS".under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000162/2024-2025 | 4905/ND | 10/09/2024 | 90 | PATHIK PABAN NANDI | 41.67 | 0 | 0
2728 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground basedpiped water supply scheme for Arabpur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000306/2024-2025 | 6835/ND | 12/11/2024 | 90 | CHOWDHURY & CO. | 32.85 | 0 | 100
2729 | Nadia Division | Tehatta Sub-Division | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000329/2025-2026 | .4686/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 79.19 | 0 | 40
2730 | Nadia Division | Tehatta Sub-Division | Laying of additional pipeline for Hazrakhali, Fulkhali, Betbaria, Marttajapur, Mollahad, Chaugachha, Haripur & Arabpur mouzas under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000831/2024-2025 | 246/ND | 14/01/2025 | 450 | JOY HIND TUBEWELL'S | 153.86 | 0 | 30
2731 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000070/2022-2023 | 4276/ND | 29/09/2022 | 0 | Resource Division | 7.53 | 0 | 0
2732 | Nadia Division | Tehatta Sub-Division | PROVIDING FHTC BY AUGMENTATION FOR ARABPUR PWSS BLOCK: KARIMPUR - I DISTRICT: NADIA | Assistant Engineer | Junior Engineer | VCH/000195/2022-2023 | 19/PFMS | 20/05/2022 | 0 | HORIZEN | 2.67 | 0 | 0
2733 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANPUR W/S Scheme, Block- Krishnaganj, ARABPUR W/S Scheme, Block-Karimpur, BHIMPUR W/S Scheme, Block-Krishnagar AND MONIPOTA W/S Scheme, Block- Krishnagar-I, Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/001444/2023-2024 | 5127/EMD | 04/09/2023 | 666 | C.M.S. ENGINEERING CONCERN. | 70.97 | 0 | 12
2734 | Nadia Division | RWS Nadia Sub-Division | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Teinpur Zone-IV PWSS within Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000006/2024-2025 | 3260/ND | 10/06/2024 | 450 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 82.42 | 0 | 80
2735 | Nadia Division | RWS Nadia Sub-Division | Renovation and modification of AIRP (Pressure Type) of capacity 20.87 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site in Teinpur Zone IV PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000008/2023-2024 | 1807/ND | 24/04/2023 | 547 | MONDAL PRECISION PRIVATE LIMITED | 39.12 | 0 | 90
2736 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20 mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Teinpur Zone-IV to accommodate FHTC within Karimpur-II block under RWS Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000094/2022-2023 | 3381/ND | 29/07/2022 | 90 | CHOWDHURY & CO. | 71.97 | 62.47 | 100
2737 | Nadia Division | RWS Nadia Sub-Division | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Tenpur (Zone-IV) Water Supply Scheme, Karimpur-I Block Under RWS Nadia Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000678/2023-2024 | 1177/ND | 21/02/2024 | 270 | PAPAN ROY | 25.46 | 0 | 75
2738 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000024/2022-2023 | 3898/ND | 08/09/2022 | 0 | Resource Division | 18.84 | 0 | 0
2739 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000075/2022-2023 | 4324/ND | 29/09/2022 | 0 | Resource Division | 2.3 | 0 | 0
2740 | Nadia Division | RWS Nadia Sub-Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | VCH/000200/2022-2023 | 24/PFMS | 20/05/2022 | 0 | ENVIROTECH SOLUTIONS | 2.43 | 0 | 0
2741 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/001012/2022-2023 | 500/EMD | 24/01/2023 | 30 | M/S DILIP MITRA | 64.62 | 10.18 | 85
2742 | Central Drilling | Nadia Arsenic Civil Division II | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KRISHNAGAR W/S SCH, UNDER NADIA DISTRICT, CDD, PHE DTE. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000354/2022-2023 | 509/CMSD-II | 11/11/2022 | 7 | M/S SAIKAT ENTERPRISE | 0.98 | 0.75 | 0
2743 | Central Drilling | Nadia Arsenic Civil Division II | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR KRISHNAGAR W/S SCH, UNDER NADIA DISTRICT, CDD, PHE DTE. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000355/2022-2023 | 1195/CDD | 11/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 10.22 | 9.44 | 0
2744 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I/II, under Krishnanagar ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. [SM/09264] | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000023/2025-2026 | 693/EMD | 04/04/2025 | 30 | JOYSHREE CONCERN | 13.82 | 0 | 0
2745 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Krishnagar Water Supply Scheme in Tehatta-II Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000068/2023-2024 | 324_2/AE-I/NACD-II | 13/07/2023 | 7 | RISHAN ENGINEERING CONSULTANCY | 0.61 | 0 | 100
2746 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-II Block of Nadia District through Jadavpur University. (Name of PWSS Krishnagar) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000102/2023-2024 | 1147/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100
2747 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Conversion of IEP to AIRP at Krishnagar Water Supply Scheme of capacity 21 Cu.m/hr in Tehatta-II Block under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000160/2024-2025 | 1125/NACD-II | 21/08/2024 | 299 | BIPLAB GUHA | 85.92 | 0 | 60
2748 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipe line repair) at Krishnagar & Bahadurpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000177/2021-2022 | 948/NACD-II | 09/12/2021 | 45 | MITRA CONSTRUCTION | 45.4 | 0 | 100
2749 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged pipeline repair) at Krishnagar & Bahadurpur (Vill- Krishnagar, Chak Chilakhali) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000215/2021-2022 | 08/NACD-II | 04/01/2022 | 45 | MITRA CONSTRUCTION | 34.08 | 34.06 | 100
2750 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) of Pascim Para , Ramchandrapur Ghat habitation at Krishnanagar W/s Scheme at Tehatta-2 Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000234/2023-2024 | 642/AE-I/NACD-II | 12/02/2024 | 15 | PRITI ENTERPRISE | 0.93 | 0 | 100
2751 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) of Muslim Para habitation at Krishnanagar W/s Scheme at Tehatta-2 Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000235/2023-2024 | 643/AE-I/NACD-II | 12/02/2024 | 15 | PRITI ENTERPRISE | 0.9 | 0 | 100
2752 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Upgradation of D.G panel Board of NACD-II office building from 40 KVA to 63.5 KVA at Krishnagar under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000237/2021-2022 | 217/AE-I/NACD-II | 01/02/2022 | 7 | ABHISEK ENGINEERING CONCERN | 4.78 | 4.78 | 100
2753 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) of Purba Para habitation at Krishnanagar W/s Scheme at Tehatta-2 Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000238/2023-2024 | 640/AE-I/NACD-II | 12/02/2024 | 15 | BABLU MALLICK | 0.96 | 0 | 0
2754 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) of Ramchandrapur habitation at Krishnanagar W/s Scheme at Tehatta-2 Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000239/2023-2024 | 641/AE-I/NACD-II | 12/02/2024 | 15 | TAPAN SAHA | 0.91 | 0 | 100
2755 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Krishnagar Water Supply Scheme at Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000247/2021-2022 | 103/NACD-II | 10/02/2022 | 45 | DEBASISH DEY | 12.04 | 11.96 | 100
2756 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earth work in filling at H/W site of Krishnagar ( Eastern site) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000278/2021-2022 | 233/AE-I/NACD-II | 17/02/2022 | 7 | CHANDAN ROY | 4.95 | 4.94 | 100
2757 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earth work in filling at H/W site of Krishnagar (Western site) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000279/2021-2022 | 234/AE-I/NACD-II | 17/02/2022 | 7 | PAPAN ROY | 4.98 | 4.97 | 100
2758 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Earth work in filling at H/W site of Krishnagar ( Eastern site) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000328/2021-2022 | 306/AE-I/NACD-II | 23/03/2022 | 7 | CHANDAN ROY | 4.95 | 4.94 | 100
2759 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Earth work in filling at H/W site of Krishnagar (Western site) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000329/2021-2022 | 307/AE-I/NACD-II | 23/03/2022 | 7 | PAPAN ROY | 4.96 | 4.96 | 100
2760 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under SHYAMNAGAR(Block-Krishnaganj), MOBARAKPUR(Block-Tehatt-I), PATHARGHAT(Block-Tehatt-I) W/S Scheme, Dist. - Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/001482/2023-2024 | 1505/EMD. | 18/04/2023 | 30 | DIPALI CONSTRUCTION | 19.37 | 6.41 | 80
2761 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I , II Zone-I under Rajapura ground water based water supply scheme under Block_ Sandeshkhali-I Dist. - North 24PGS under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl no. 12) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/003196/2023-2024 | 944/EMD | 18/03/2024 | 30 | PADMA ENGINEERING CO. | 25.48 | 0 | 0
2762 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal. (From 01/04/2024 to 30/06/2024) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000004/2024-2025 | 505/NACD-II | 01/04/2024 | 91 | BABLU KUMAR SINGH | 1.24 | 0 | 0
2763 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Patharghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000035/2021-2022 | 528/NACD-II | 14/06/2021 | 45 | M/S K.P. CONSTRUCTION | 47.57 | 32.75 | 0
2764 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also construction of Steps with earth filling at Patharghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000133/2021-2022 | 872/NACD-II | 08/11/2021 | 45 | SANDIP BISWAS | 75.41 | 75.37 | 100
2765 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD and allied works at OHR site under Patharghata Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000136/2023-2024 | 1254/NACD-II | 08/11/2023 | 30 | SAHA ENGINEERS | 20.63 | 0 | 100
2766 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Patherghata) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000168/2023-2024 | 1297/NACD-II | 29/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
2767 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Patharghata (Phase-II), (Block -Tehatta-I) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000175/2021-2022 | 758/NACD-II | 16/09/2021 | 10 | SIRCON ENGINEERING SERVICE | 4.64 | 4.64 | 100
2768 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Patharghata W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000179/2023-2024 | 527/AE-I/NACD-II | 18/12/2023 | 15 | TOTAN DAS | 0.97 | 0 | 0
2769 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Damaged pipe line repair and piling work at Patharghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000256/2021-2022 | 37/AE-II/NACD-II | 17/02/2022 | 30 | SAHA ENGINEERS | 4.69 | 4.69 | 100
2770 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Patharghata Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000269/2021-2022 | 53/AE-II/NACD-II | 17/02/2022 | 30 | SURAJIT KUMAR GHOSH | 4.26 | 4.25 | 100
2771 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Patharghata W/s Scheme in Nadia District under Nadia Arsenic Civil Division-Il, P,H.E. Dte." | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000291/2021-2022 | 126/NACD-II | 21/02/2022 | 90 | J.D. CONSTRUCTION | 106.8 | 0 | 100
2772 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Conversion of IEP to AIRP at Patharghata Water Supply Scheme of capacity 96 Cu.m/hr in Tehatta - I Block under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000295/2024-2025 | 1396/NACD-II | 22/10/2024 | 360 | JOY HIND TUBEWELLS | 258.38 | 0 | 0
2773 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000395/2022-2023 | 413/NACD-II | 30/03/2023 | 366 | BABLU KUMAR SINGH | 4.98 | 2.24 | 60
2774 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000400/2022-2023 | 413/NACD-II | 30/03/2023 | 366 | BABLU KUMAR SINGH | 4.98 | 0 | 0
2775 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system and also dedicated pipe line including providing FHTC at left out households for Patharghata (Gobindapur, Patharghata) & Puthimari (Vill-Puthimari) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000432/2024-2025 | 247/NACD-II | 27/02/2025 | 180 | SANDIP BISWAS | 101.71 | 0 | 0
2776 | Nadia Division | Krishnanagar Sub-Division | Laying of dedicated pipeline for Pipragachhi and part of Elangi Mouza for augmentation of Elangi Water Supply Scheme in Chapra Block, Nadia under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000010/2025-2026 | 1773/ND | 21/04/2025 | 180 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 86.27 | 0 | 0
2777 | Nadia Division | Krishnanagar Sub-Division | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Maidanpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 02) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000341/2021-2022 | 905/KSD | 29/11/2021 | 15 | HORIZEN | 3.2 | 2.61 | 93
2778 | Nadia Division | Krishnanagar Sub-Division | Laying distribution system [LDS] for providing Functional Household Tap Connection (FHTC), Rising main with Inter-Connection in between Tube wells including specials and valves, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and Soil Investigation for Construction of One No. 300 Cum OHR of Staging Height 20 Mtr. by Augmentation for Maidanpur Piped Water Supply Scheme within Chapra Block under Krishnagar Sub Divn. under Nadia Divn. PHE Dte. in the District of Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000390/2022-2023 | 479/ND | 02/02/2023 | 850 | JOY HIND TUBEWELL'S | 332.37 | 188.33 | 80
2779 | Nadia Division | Krishnanagar Sub-Division | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Maidanpur Water Supply Scheme within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000500/2023-2024 | 157/ND | 09/01/2024 | 60 | M/S S.K. ENTERPRISE | 18.07 | 0 | 90
2780 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000080/2023-2024 | 2320/ND | 29/05/2023 | 0 | Resource Division | 13.63 | 0 | 0
2781 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000155/2022-2023 | 127/ND | 05/01/2023 | 0 | Resource Division | 11.98 | 0 | 0
2782 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under KARIMPUR JALANGI(Z-8) W/S Scheme, Block- Karimpur II, PALSONDHA W/S Scheme, Block- Tehatta II, & MAIDANPUR W/S Scheme, Block- Chapra, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001923/2022-2023 | 1179/EMD | 21/03/2023 | 940 | CREATIVE WATER & PROCESS TECHNOLOGIES PVT. LTD. | 77.9 | 0 | 85
2783 | Nadia Division | Tehatta Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 26.25 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-IX B to accommodate FHTC within Karimpur-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000340/2024-2025 | 7105/ND | 06/12/2024 | 360 | JOY HIND TUBEWELL'S | 151.86 | 0 | 0
2784 | Nadia Division | Tehatta Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-9B W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000404/2021-2022 | 319/TSD | 24/11/2021 | 30 | RADIANT | 2.42 | 2.42 | 100
2785 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction Of 200 Cum Capacity 20 Mtr. Height RCC Over Head Reservoir (without pile foundation), Pipe Connection and cost of Pipes, Specials and Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of cum. O.H.R. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-IXB to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000446/2022-2023 | 965/ND | 09/03/2023 | 1396 | SHYAMAL SHIL, PALLISREE, P.O.KRISHNAGAR, DIST- NADIA,PIN-741101 | 175.66 | 42.49 | 45
2786 | Nadia Division | Tehatta Sub-Division | Sinking of 01 no Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Karimpur Jalangi PWSS Zone-IX(B) Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000663/2023-2024 | 1098/ND | 19/02/2024 | 270 | BUDDHADEV MONDAL | 17.38 | 0 | 100
2787 | Nadia Division | Tehatta Sub-Division | Construction of barbed wire fencing with concrete pillars at Karimpur-Jalangi Zone-IX(B). water supply scheme (New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | Assistant Engineer | Junior Engineer | ORD/000731/2023-2024 | 1121/TSD | 21/02/2024 | 7 | NIVEDITA CONSTRUCTION | 1.51 | 0 | 100
2788 | Nadia Division | Tehatta Sub-Division | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement and Construction of Boundary wall at Head Work Site at Karimpur - Jalangi (IX-B )Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000759/2023-2024 | 1632/ND | 07/03/2024 | 506 | MONDAL ENTERPRISE | 23.85 | 0 | 15
2789 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000043/2023-2024 | 1902/ND | 27/04/2023 | 0 | Resource Division | 18.83 | 0 | 0
2790 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI (Z-IX B) W/S Scheme, Block-Karimpur II , Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/001924/2022-2023 | 1180/EMD | 21/03/2023 | 30 | MA ANNAPURNA ENTERPRISE | 12.87 | 11 | 10
2791 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under Karimpur jalangi (Zone-IX,A & B) W/S Scheme, Block-Tehatta-II, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 19) | Assistant Engineer | Junior Engineer | ORD/002779/2022-2023 | 419EMD | 20/01/2023 | 30 | SINHA ELECTRICALS | 14.88 | 1.34 | 85
2792 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 275.37 | 47
2793 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
2794 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 1B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000766/2021-2022 | 116/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.79 | 3.76 | 100
2795 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 1 | RTOR000113/2022-2023 | 113/ND | 05/01/2023 | 0 | Resource Division | 297.54 | 0 | 0
2796 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 0 | 47
2797 | Nadia Division | Debgram Sub-Division | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000185/2024-2025 | 6095/ND | 19/09/2024 | 240 | UMWELT ENGINEER PVT LTD | 225.66 | 0 | 75
2798 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 7A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000778/2021-2022 | 128/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.32 | 4.18 | 100
2799 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000124/2022-2023 | 77/ND | 05/01/2023 | 0 | Resource Division | 126.75 | 0 | 0
2800 | Nadia Division | Debgram Sub-Division | Laying of additional upvc pipeline and installation of sluice valves at Zone -7A of Surface water based water supply scheme Northern Sector in Nadia District, Part- II under Debagram Sub- Division undrer Nadia Division ,PHE Dte. | Assistant Engineer |  | ORD/000007/2024-2025 | 3261/ND | 10/06/2024 | 363 | MINTU CHAKRABORTY | 96.03 | 0 | 4
2801 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- VII/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000313/2023-2024 | 4282/ND | 21/09/2023 | 624 | SATYABRATA CHAKRABORTY | 397.18 | 0 | 14
2802 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
2803 | Nadia Division | Debgram Sub-Division | Construction of OHR, staff room, chlorine room, service road, boundary wall and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-VII / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000480/2023-2024 | 212/ND | 10/01/2024 | 730 | PRASUN ENTERPRISE | 262.05 | 0 | 5
2804 | Nadia Division | Debgram Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
2805 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 7/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000803/2021-2022 | 153/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.32 | 4.27 | 100
2806 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000130/2023-2024 | 233/ND | 11/01/2024 | 0 | Resource Division | 8.75 | 0 | 0
2807 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000145/2022-2023 | 79/ND | 05/01/2023 | 0 | Resource Division | 870.46 | 0 | 0
2808 | Nadia Division | Debgram Sub-Division | Laying of additional upvc pipeline and installation of sluice valves at Zone -7A of Surface water based water supply scheme Northern Sector in Nadia District, Part- II under Debagram Sub- Division undrer Nadia Division ,PHE Dte. | Assistant Engineer |  | ORD/000007/2024-2025 | 3261/ND | 10/06/2024 | 363 | MINTU CHAKRABORTY | 96.03 | 0 | 4
2809 | Nadia Division | Debgram Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 900 cum. For Providing FHTC (Functional Household Tap Connection) for Zone VII/A (NORTHERN SECTOR PART-II) Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000261/2023-2024 | 4005/ND | 07/09/2023 | 540 | TARUN KUMAR BHATTACHARYA | 43.67 | 0 | 1
2810 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- VII/A (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000309/2023-2024 | 4279/ND | 21/09/2023 | 638 | MINTU CHAKRABORTY | 476.23 | 0 | 24
2811 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 7/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000802/2021-2022 | 152/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.47 | 4.44 | 100
2812 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000129/2023-2024 | 241/ND | 11/01/2024 | 0 | Resource Division | 6.45 | 0 | 0
2813 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000144/2022-2023 | 78/ND | 05/01/2023 | 0 | Resource Division | 168.95 | 0 | 0
2814 | Eastern Mechanical | Nadia Arsenic Civil Division II | New connection charges for Kanainagra PHE I | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00222/2022-2023 | 106/PFMS/EMD | 16/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.95 | 0 | 0
2815 | Eastern Mechanical | Nadia Arsenic Civil Division II | New connection charges for Kanainagra PHE II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00224/2022-2023 | 107/PFMS/EMD | 16/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.57 | 0 | 0
2816 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electriciyy bill pay for the new service connection at Kanaigar PHE II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/02157/2022-2023 | 153/PFMS/EMD | 13/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.76 | 0 | 0
2817 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electriciyy bill pay for the new service connection at Kanaigar PHE I | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/02158/2022-2023 | 154/PFMS/EMD | 13/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.63 | 0 | 0
2818 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Kanainagar W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000452/2022-2023 | 6262/EMD | 19/11/2022 | 30 | TARUN KUMAR BHATTACHARYA | 10.05 | 0 | 100
2819 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Kanainagar W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No.- 21 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000520/2022-2023 | 6370/EMD | 23/11/2022 | 30 | S.R. CONCERN | 10.05 | 9.1 | 100
2820 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Kanainagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000009/2022-2023 | 207/NACD-II | 05/04/2022 | 60 | A.K ADHIKARY | 5.37 | 5.35 | 100
2821 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Kanainagar and Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000019/2022-2023 | 244/NACD-II | 19/04/2022 | 60 | B.M. ENGINEERING & CONSTRUCTION | 42.4 | 0 | 100
2822 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Kanainagar water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000045/2022-2023 | 12/AE-II/NACD-II | 11/04/2022 | 60 | A.K ADHIKARY | 2.83 | 2.81 | 100
2823 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Kanainagar Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000049/2023-2024 | 415/AE-I/NACD-II | 08/08/2023 | 15 | B.M. ENGINEERING & CONSTRUCTION | 0.97 | 0 | 100
2824 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Kanainagar Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000059/2022-2023 | 20/AE-II/NACD-II | 18/04/2022 | 30 | CHINMOY BISWAS | 4.98 | 0 | 100
2825 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Kanainagar and adjoining mouzas under Kanainagar Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000072/2022-2023 | 340/NACD-II | 03/06/2022 | 1064 | B.M. ENGINEERING & CONSTRUCTION | 285.26 | 0 | 90
2826 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Kanainagar and Dhopahat PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000182/2024-2025 | 296_AE-II/NACD-II | 30/08/2024 | 20 | MAKALI ENGINEERING CORPORATION | 4.81 | 0 | 100
2827 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Kanainagar Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000198/2022-2023 | 627/NACD-II | 06/09/2022 | 20 | MAKALI ENGINEERING CORPORATION | 4.94 | 4.94 | 100
2828 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Kanainagar Water Supply Scheme Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000321/2022-2023 | 85/NACD-II | 10/01/2023 | 60 | SUMIT GHOSH | 14.7 | 11.76 | 85
2829 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Bagakhali Zone-I and Bagakhali Zone-II Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000325/2024-2025 | 1562/NACD-II | 05/12/2024 | 360 | DEBASIS SAMADDAR | 157.57 | 0 | 40
2830 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Kanainagar 2nd Tubewell Site within Kanainagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000331/2022-2023 | 124/NACD-II | 11/01/2023 | 60 | CHINMOY BISWAS | 5.66 | 5.36 | 85
2831 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000348/2024-2025 | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 20
2832 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Kanainagar water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000377/2022-2023 | 370/NACD-II | 23/03/2023 | 740 | B.M. ENGINEERING & CONSTRUCTION | 143.29 | 0 | 35
2833 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Smoothening of site by filling of land with excavated earth in the ditch and compaction by hand roller at Kanainagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000403/2024-2025 | 410/AE-II/NACD-II | 31/01/2025 | 45 | ROY ENTERPRISE | 0.94 | 0 | 100
2834 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 54 cum/Hour capacity for Kanainagar Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000406/2024-2025 | 165/NACD-II | 06/02/2025 | 180 | TARUN KUMAR BHATTACHARYA | 186.86 | 0 | 0
2835 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | RTOR000005/2022-2023 | 409/NACD-II | 04/07/2022 | 0 | Resource Division | 51.88 | 0 | 0
2836 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000240/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
2837 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000346/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
2838 | Eastern Mechanical | Nadia Arsenic Civil Division II |  | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00001/2022-2023 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.1 | 0 | 0
2839 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection for Pump House -I under Suruppur W/S Scheme at Tehatta Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00002/2022-2023 | 93/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.1 | 0 | 0
2840 | Eastern Mechanical | Nadia Arsenic Civil Division II | New service connection charges at P.H No. II under Suruppur Tehatta Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00003/2022-2023 | 94/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.23 | 0 | 0
2841 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Suruppur W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 11) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000432/2022-2023 | 6257/EMD | 19/11/2022 | 30 | M/S DILIP MITRA | 9.96 | 0 | 80
2842 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Suruppur W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No.- 21 OF EE/EMD OF 2022-23 (Sl. No.- 12) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000702/2022-2023 | 6490/EMD | 30/11/2022 | 30 | DEBJYOTI BASU | 9.96 | 9.91 | 87
2843 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply delivery of PCC pole, M.s and electrical accessories including stringing of LTOH line to wbsedcl for new service connection at PH-II under Suruppur W/S Scheme. under EMSD-III | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/002409/2022-2023 | 1366/EMSD-III | 14/08/2022 | 30 | DEBJYOTI BASU | 0.72 | 0.72 | 0
2844 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery of PCC pole,M.S materials and Electricalaccessories and Installation DTR including stringing andSagging of HTOH line to WBSEDCL for newconnection at Pump House-1 under Suruppur water supplyscheme,under EMSD-III,PHE Dte,Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/003025/2022-2023 | 264SD-III | 28/02/2023 | 30 | M/S DILIP MITRA | 3.71 | 0 | 100
2845 | Eastern Mechanical | Nadia Arsenic Civil Division II | New connection charges for Swaruppur PHE I Tehatta Nadia. Memo no. 3004031081/Quot/03 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/003367/2022-2023 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.1 | 0 | 0
2846 | Eastern Mechanical | Nadia Arsenic Civil Division II | New connection charges for Swaruppur PHE I Tehatta Nadia. Memo no. 3004031086/Quot/03 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/003371/2022-2023 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.23 | 0 | 0
2847 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Suruppur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000011/2022-2023 | 216/NACD-II | 05/04/2022 | 60 | TAPAN SAHA | 5.38 | 5.32 | 100
2848 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Jitpur and Suruppur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000018/2022-2023 | 243/NACD-II | 19/04/2022 | 60 | B.M. ENGINEERING & CONSTRUCTION | 42.4 | 0 | 100
2849 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Suruppur water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000047/2022-2023 | 14/AE-II/NACD-II | 11/04/2022 | 60 | TAPAN SAHA | 2.83 | 2.81 | 100
2850 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Suruppur Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000063/2022-2023 | 25/AE-II/NACD-II | 18/04/2022 | 30 | BASUDEB SAHA | 4.41 | 0 | 100
2851 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Suruppur and adjoining mouzas under Suruppur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000068/2022-2023 | 302/NACD-II | 20/05/2022 | 90 | JOY GOPAL GUPTI | 104.51 | 66.53 | 85
2852 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Suruppur Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000129/2023-2024 | 467./AE-I/NACD-II | 03/10/2023 | 15 | MAJUMDER SYNDICATE | 0.97 | 0 | 0
2853 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Toilet with sanitary and water supply arrangement at Suruppur 2nd tube well site within Suruppur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000157/2024-2025 | 168/AE-II/NACD-II | 14/06/2024 | 15 | D.K.CONSTRUCTION | 0.97 | 0 | 0
2854 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Suruppur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000201/2022-2023 | 630/NACD-II | 06/09/2022 | 20 | MAKALI ENGINEERING CORPORATION | 3.42 | 3.42 | 100
2855 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 22 cum/Hour capacity for Suruppur Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000202/2024-2025 | 1236/NACD-II | 10/09/2024 | 540 | SINGHA ROY & CO. | 146.67 | 0 | 0
2856 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Suruppur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000326/2022-2023 | 90/NACD-II | 10/01/2023 | 960 | PARTHA DAS | 17.71 | 0 | 85
2857 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Suruppur 2nd Tubewell Site within Suruppur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000335/2022-2023 | 129/NACD-II | 11/01/2023 | 60 | SANJIT DAS | 5.83 | 5.76 | 80
2858 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 250 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Suruppur water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000352/2022-2023 | 160/NACD-II | 17/01/2023 | 853 | JOY HIND TUBEWELLS | 94.17 | 0 | 10
2859 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Manoharpur & Suruppur water supply scheme under Karimpur-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000400/2024-2025 | 135/NACD-II | 09/01/2025 | 225 | NISHITH BANERJEE | 32.78 | 0 | 50
2860 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | RTOR000014/2022-2023 | 410/NACD-II | 04/07/2022 | 0 | Resource Division | 35.99 | 0 | 0
2861 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000233/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
2862 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000340/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
2863 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supply, delivery and storage at site of automatically controlled diapharm type Chlorinatore dosing pump. Under Augmentation of Ground Water Based PWSS for Bhayna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000003/2024-2025 | 141/AE-II/NAD-I | 07/06/2024 | 30 | MANARAMA ENTERPRISE | 2.89 | 0 | 100
2864 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Bhayna Zone-II Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Bhayna Zone-I & Zone-II (Part-III) Piped W/S Scheme (Sl.no.29) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000042/2023-2024 | 1361 /NAD-I | 12/05/2023 | 15 | NISHITH BANERJEE | 13.04 | 0 | 100
2865 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet , Pathway and other allied works at Bhayana Z-I W/S Scheme within Hanshkhali Block under Nadia Arsenic Division -I, P.H.E.Dte. ( Sl.No. 20) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000046/2022-2023 | 1586 / NAD-I | 06/09/2022 | 45 | CHANDAN ROY | 13.37 | 12.05 | 100
2866 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Bhayna Zone-I GroundWater Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation in connection with JJM under Bhayna Zone-I & Zone-II Part-III Piped W/S Scheme (Sl.no28) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000047/2023-2024 | 1451/NAD-I | 26/05/2023 | 15 | PALCON | 12.98 | 0 | 100
2867 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between Common Manifold and distribution main at Bhayna Zone-I W/S Scheme under JJM in connection with Garapota and Bhayna W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl. no. 03) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000051/2024-2025 | 1501/NAD-I | 18/09/2024 | 45 | B.S. ENTERPRISE | 19.54 | 0 | 100
2868 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhayna Zone-I & II Part-III at Hanskhali block by Augmentation of Ground water based PWSS for Bhayna W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000095/2023-2024 | 1686/NAD-I | 12/07/2023 | 790 | TAPU SAHA | 390.82 | 0 | 80
2869 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP (Pressure Type) at Bhayna Zone-I W/S Scheme under Hanskhali Block of capacity 125 cum/hr. under augmentation of Bhayna Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.02) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000143/2023-2024 | 2044/NAD-I | 24/08/2023 | 548 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 165.95 | 0 | 94
2870 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | RTOR000010/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 12.32 | 0 | 0
2871 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | RTOR000029/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 8.62 | 0 | 0
2872 | Central Drilling | Nadia Arsenic Division I | Hiring of Diesel driven motor cab (BS-IV & above) having contract carriage permit along with driver for the office of the Assistant Engineer, S&WSD, CDD, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000026/2023-2024 | 79/S&WSD | 27/07/2023 | 60 | NAGENDRA PATRA | 0.44 | 0 | 33
2873 | Central Drilling | Nadia Arsenic Division I | Continuation for hiring of Diesel driven Motor Cab(BS-IV & Above) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000144/2023-2024 | 117/S&WSD | 30/10/2023 | 61 | NAGENDRA PATRA | 0.29 | 0 | 50
2874 | Central Drilling | Nadia Arsenic Division I | Hiring of Diesel driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000183/2023-2024 | 164/S&WSD | 19/12/2023 | 183 | NAGENDRA PATRA | 0.86 | 0 | 63
2875 | Central Drilling | Nadia Arsenic Division I | Providing drilling crew and other allied works for construction of Tube Well (250mm x 150mm x 300mtrs Depth ) by utilising Departmental Machineries for Bhayna W/S Scheme(Z-II)Ranaghat-I Block under Nadia District ,CDD,PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000454/2022-2023 | 1826/CDD | 06/01/2023 | 30 | M/S SAIKAT ENTERPRISE | 15.55 | 10.73 | 100
2876 | Eastern Mechanical | Nadia Arsenic Division I | New Service connection at bagula under Bhayna W/S Scheme. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | BILL/03358/2023-2024 | BP-211-23-24 | 17/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.15 | 0 | 0
2877 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Halalpur-Krishnapur Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Halalpur-Krishnapur Zone-I & II (Part-III) Piped W/S Scheme (sl.19) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000025/2023-2024 | 1161 / NAD-I | 28/04/2023 | 15 | B.S. ENTERPRISE | 13.04 | 12.61 | 100
2878 | Nadia Arsenic Division I | Nadia Arsenic Division I | Balance work for revamping / upgradation of the hydraulic parameters at Gayesh, Daluigram & Jafar-nagar mouzas in reference to Halalpur-Krisnapur PWSS & Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000025/2025-2026 | 154/NAD-I | 28/04/2025 | 60 | TAPU SAHA | 86.49 | 0 | 0
2879 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection of M.S pipeline with Manifold at Halalpur Krishnapur Z-1 Water Supply Scheme including fixing of Sign Board for dematcation of Land at different location under the judisdiction of Nadia Arsenic Division-I ,PHE Dte. under JJM. (Sl. No. 08) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000034/2025-2026 | 168/NAD-I | 29/04/2025 | 60 | BUDDHADEV MONDAL | 9.81 | 0 | 60
2880 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Halalpur-Krishnapur Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Muragachha Zone-I & II (Part-III) Piped W/S Scheme (Sl.no.18) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000051/2023-2024 | 1430/NAD-I | 24/05/2023 | 15 | D.K. CONSTRUCTION | 12.98 | 0 | 100
2881 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM), Construction of Boundary wall, Toilet, Pathway and other allied work at Head Work Site & 2nd T/W Site, Repair of 350 cum capacity Over Head Reservoir, Painting and Pump House at Halalpur Krishnapur Zone-I & Repair of 180 cum capacity Over Head Reservoir, Painting and repairing of H/W Boudary wall, Pump House at Halapur Zone-II for Halalpur Krishnapur Zone-I & II at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000098/2023-2024 | 1742/NAD-I | 19/07/2023 | 90 | SATYABRATA CHAKRABORTY | 377.65 | 0 | 40
2882 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II from Kharida Chapra Primary School to Purba Sangha at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Retrofitting of Ground Water Based PWSS of Halalpur- Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000218/2022-2023 | 100/AE-I/NAD-i | 20/02/2023 | 15 | MONDAL ENTERPRISE | 3.56 | 3.56 | 0
2883 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | RTOR000016/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 15.4 | 0 | 0
2884 | Central Drilling | Nadia Arsenic Division I | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 300 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR HALALPUR-KRISHNAPUR W/S SCHEME (Z-I), RANAGHAT BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000395/2022-2023 | 1451/CDD | 30/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 15.55 | 10.4 | 0
2885 | Eastern Mechanical | Nadia Arsenic Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HALALPUR KRISHNAPUR (Z-II),GOALSALUA(Z-I) & GOALSALUA(Z-II) W/S Scheme, Block- Ranaghat-II , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000022/2023-2024 | 1601/EMD | 26/04/2023 | 30 | M/S DILIP MITRA | 56.44 | 0 | 100
2886 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Halalpur Krishnapur Zone-I and Zone II Part III under Block_ Ranaghat II Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/12020) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000152/2025-2026 | 1154/EMD | 04/06/2025 | 90 | KASHINATH PAL & CO. | 8.68 | 0 | 0
2887 | Nadia Division | Ranaghat Sub-Division | "Restoration work arising out of damage of Hard Shoulder for Laying of UPVC Pipe Line by Nadia Division, PHED" under Nadia Highway Division No-II in the District of Nadia during the year 2023-24 Pt.-II "NH Tarapur to Balagarhghat Road from Ch 0.00 Km to Ch1.80 Km". | Assistant Engineer | Junior Engineer 2 | BILL/00394/2024-2025 | 228/PFMS | 11/09/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-II, P.W. (ROADS) DIRECTORATE | 6 | 0 | 0
2888 | Nadia Division | Ranaghat Sub-Division | Balanced UPVC pipe line for Providing Functional Household Tap Connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Habibpur to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000035/2025-2026 | 2156/ND | 06/05/2025 | 90 | M/S DIPAK ENTERPRISE | 164.59 | 0 | 0
2889 | Nadia Division | Ranaghat Sub-Division | Construction of Boundary wall at Habibpur W/S Scheme under Ranaghat Sub-Division, Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000136/2024-2025 | 875/RSD | 20/08/2024 | 31 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 3.78 | 0 | 100
2890 | Nadia Division | Ranaghat Sub-Division | Guard Room Repair at Habibpur water supply scheme under Ranaghat Sub-Division under Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000150/2024-2025 | 794/RSD | 02/08/2024 | 20 | SKYLINE CONSTRUCTION | 0.94 | 0 | 100
2891 | Nadia Division | Ranaghat Sub-Division | Toilet construction of Guard Room of Habibpur water supply scheme under Ranaghat Sub-Division under Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000151/2024-2025 | 795/RSD | 02/08/2024 | 20 | SKYLINE CONSTRUCTION | 0.82 | 0 | 100
2892 | Nadia Division | Ranaghat Sub-Division | Plumbing & allied Works for toilet & guard room at Habibpur under Ranaghat Sub-Division under Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000152/2024-2025 | 795(A)RSD | 02/08/2024 | 20 | SKYLINE CONSTRUCTION | 0.95 | 0 | 100
2893 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Habibpur to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-II) | Assistant Engineer | Junior Engineer 2 | ORD/000248/2022-2023 | 4990/ND | 30/11/2022 | 856 | M/S GHOSH CONSTRUCTION | 335.48 | 230.93 | 100
2894 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Habibpur under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000674/2024-2025 | 1416/RSD | 19/11/2024 | 45 | SARKAR ENTERPRISE | 2.16 | 0 | 80
2895 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000063/2023-2024 | 2306/ND | 29/05/2023 | 0 | Resource Division | 26.43 | 0 | 0
2896 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000190/2022-2023 | 158/ND | 06/01/2023 | 0 | Resource Division | 22.47 | 0 | 0
2897 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Mini Piped Water Supply Scheme Gazna (Part) (100 Households) to accommodate FHTC in Hanskhali block & Providing FHTC and allied works for- Ground Water Based Mini Piped Water Supply Scheme in Arsenic affected area at Uttar Bishnupur, Block : -Ranaghat-II, Nadia District under Nadia Division P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2,Junior Engineer 4 | ORD/000090/2023-2024 | 3024/ND | 14/07/2023 | 366 | ABDUL ALIM MONDAL | 79.83 | 0 | 78
2898 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2,Junior Engineer 4 | RTOR000158/2023-2024 | 273/ND | 11/01/2024 | 0 | Resource Division | 0.6 | 0 | 0
2899 | Eastern Mechanical | Ranaghat Sub-Division | Supply, & Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for Mini Piped Water Supply Scheme[Gazna(part) Block-Hanskhali, Uttar Bishnupur Block-Ranaghat-II, Augmentation to Accomodate FHTC , Dist. - Nadia. under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2,Junior Engineer 4 | ORD/000015/2024-2025 | 1307/EMD | 09/05/2024 | 388 | ORIENTAL ENGINEERING CO. | 12.61 | 0 | 45
2900 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supply, delivery and installation commissioning of Domestic Ultrasonic (153 RWM) type water meter with Software for data communication at Patkabari, Hatibhanda, Madna, Jaganath, Sahapur & Dhakuria village under augmentation of ground watwer based PWSS for Itaberia W/S Scheme Part-III under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, PHE Dte. (Sl.04) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000015/2025-2026 | 131/NAD-I | 22/04/2025 | 60 | SHANTA COLIBRI (INDIA) PVT. LTD. | 5.43 | 0 | 0
2901 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (60cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Itaberia, under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.06) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000138/2023-2024 | 1969/NAD-I | 21/08/2023 | 30 | B.M. ENGINEERING & CONSTRUCTION | 112.08 | 0 | 0
2902 | Eastern Mechanical | Nadia Arsenic Division I | Load enhancement of Bhayna Z-1 (Ph-1) water supply scheme at Hanskhali block, Dist.-Nadia | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | BILL/00333/2024-2025 | BP-22-24-25 | 21/05/2024 | 0 | W.B.S.E.D.C.LTD (BAGULA C.C.C) | 1.28 | 0 | 0
2903 | Nadia Division | Tehatta Sub-Division | Renovation of AIRP (Pressure Type) of capacity 93 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Topla PWSS under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000213/2023-2024 | 3584/ND | 14/08/2023 | 90 | APURBA MANDAL | 68.26 | 0 | 0
2904 | Nadia Division | Ranaghat Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Dakshinpara-II PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 35.00 Cu.m/hr | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000467/2023-2024 | 134/ND | 09/01/2024 | 450 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 60.46 | 0 | 91
2905 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000527/2022-2023 | 1270/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 65.32 | 0 | 0
2906 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001008/2022-2023 | 496/EMDdt.24.01.2023 | 17/03/2023 | 656 | GLACIER ENGINEERING CO. | 66.71 | 1.39 | 100
2907 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Dakshinpara Zone-II ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15538) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001458/2024-2025 | 230/EMD | 06/02/2025 | 30 | SK ENTERPRISE | 11.76 | 0 | 0
2908 | Nadia Division | Ranaghat Sub-Division | SHIFTING OF HTOH LINE AT DAKSHINPARA ZONE-I WATER SUPPLY SCHEME. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | BILL/01215/2023-2024 | 539/PFMS | 13/02/2024 | 0 | WBSEDCL | 1.86 | 0 | 0
2909 | Nadia Division | Ranaghat Sub-Division | SHIFTING OF HTOH LINE AT DAKSHINPARA ZONE-I WATER SUPPLY SCHEME. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | BILL/01216/2023-2024 | 540/PFMS | 13/02/2024 | 0 | WBSEDCL | 2.28 | 0 | 0
2910 | Nadia Division | Ranaghat Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Dakshinpara Zone-I PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 45.00 Cu.m/hr | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000466/2023-2024 | 133/ND | 09/01/2024 | 450 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 68.46 | 0 | 95
2911 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tube well (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000524/2022-2023 | 1269/ND | 23/03/2023 | 780 | JOY HIND TUBEWELL'S | 65.37 | 0 | 100
2912 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001008/2022-2023 | 496/EMDdt.24.01.2023 | 17/03/2023 | 656 | GLACIER ENGINEERING CO. | 66.71 | 1.39 | 100
2913 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Dakshinpara Zone-I ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. (Phase-II) (SM/15139) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001456/2024-2025 | 229/EMD | 06/02/2025 | 30 | M/S CHANDIMATA ELECTRICALS | 11.76 | 0 | 0
2914 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP (Gravity Type) of capacity 28 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at GHORALIA ZONE-II PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Santipur Block | ORD/000011/2023-2024 | 1805 / ND | 24/04/2023 | 90 | MONDAL PRECISION PRIVATE LIMITED | 58.81 | 0 | 75
2915 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under ELANGI(Zone-II) & GHORALIA (Zone-II) W/S Scheme, Block- Chapra & Shantipurrespectively , Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 05) | Assistant Engineer | Junior Engineer,Junior Engineer Santipur Block | ORD/001157/2023-2024 | 1503EMD | 18/04/2023 | 30 | MA ANNAPURNA ENTERPRISE | 11.19 | 5.03 | 60
2916 | Eastern Mechanical | RWS Nadia Sub-Division | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Ghoralia Zone-II (Phase-II) Piped Water Supply Scheme, Block: Santipur, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Santipur Block | ORD/001757/2023-2024 | 6367/EMD | 17/10/2023 | 30 | ABHISEK ENGINEERING CONCERN | 42.09 | 0 | 0
2917 | Nadia Division | RWS Nadia Sub-Division | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Teinpur Zone-IV PWSS within Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000006/2024-2025 | 3260/ND | 10/06/2024 | 450 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 82.42 | 0 | 80
2918 | Nadia Division | RWS Nadia Sub-Division | Laying of 160 mm dia HDPE pipe line, 75 mm & 125 mm UPVC Pipe line for Augmentation of Rising Main System for distribution pipeline with interconnection along with road restoration at village Dogachhi, Block Karimpur-II under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000017/2025-2026 | 1803/ND | 22/04/2025 | 180 | SUBHASH BOSE | 32.54 | 0 | 51
2919 | Nadia Division | RWS Nadia Sub-Division | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site of Teinpur Zone-I [Phase-II] Ground Based Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000518/2022-2023 | 1217/ND | 21/03/2023 | 60 | JOY HIND TUBEWELL'S | 14.38 | 9.29 | 85
2920 | Nadia Division | RWS Nadia Sub-Division | Renovation and modification of AIRP (Pressure Type) & Construction of Backwash chamber for AIRP at Head Work Site in Teinpur ZONE-I PWSS under Nadia Division PHE Dte. Capacity- 15.5 cum/hr. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000551/2023-2024 | 781/ND | 05/02/2024 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 37.22 | 0 | 93
2921 | Eastern Mechanical | RWS Nadia Sub-Division | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Tenipur Zone-I Piped Water Supply Scheme, Block: Karimpur-II Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/001909/2023-2024 | 6733/EMD | 29/11/2023 | 30 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.1 | 0 | 0
2922 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/002611/2023-2024 | 500EMD | 24/01/2024 | 30 | M/S DILIP MITRA | 64.62 | 0 | 85
2923 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP (Pressure Type ) of capacity 33.75 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Muktadaha Zone I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000025/2023-2024 | 1783/ND | 20/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 201.98 | 130.5 | 90
2924 | Nadia Division | RWS Nadia Sub-Division | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000329/2025-2026 | .4686/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 79.19 | 0 | 40
2925 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at Muktadaha zone I (PHASE-II) W/S Scheme Block- Karimpur-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/17207 | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000141/2025-2026 | 1142/EMD | 04/06/2025 | 90 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT LTD) | 32.62 | 0 | 0
2926 | Eastern Mechanical | RWS Nadia Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejuvenation Tube Well in connection to Accommodate FHTC at Pump House No.-I /II (Zone-I) under Muktadaha ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. (SM/09815) | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000650/2024-2025 | 2687/EMD | 20/11/2024 | 74 | MA ANNAPURNA ENTERPRISE | 14.39 | 0 | 100
2927 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VII, (Ballabhpur) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000120/2021-2022 | 13/NAD-I | 05/01/2022 | 90 | H I ENTERPRISE | 243.49 | 241.76 | 100
2928 | Eastern Mechanical |  | NEW SERVICE CONNECTION CHARGES FOR RANAGHAT-II GLR (PATULI) |  |  | BILL/00738/2024-2025 | BP-54-24-25 | 21/06/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 69.14 | 0 | 0
2929 | Eastern Mechanical |  | Providing Mechanical / Electrical Equipment for 11/0.433 KV Sub-station along with pumping station and disinfection arrangement at Ranaghat-II Block GLR Site of surface water based water supply scheme, Arsenic Affected Area, in the district of Nadia, P. H. E. Dte. |  |  | ORD/002489/2023-2024 | 83/EMD | 11/01/2024 | 721 | WEST BENGAL ENGINEERING CO. | 852.36 | 0 | 25
2930 | Eastern Mechanical |  | Providing pumping machinery and electrical equipment for secondary Boosting station at different OHR sites in Ranaghat-II block in connection with integrated surface water based PWSS in the Dist. of Nadia , P.H.E, Dte. |  |  | ORD/002634/2023-2024 | 312/EMD | 07/02/2024 | 182 | A.G ENTERPRISE. | 110.43 | 0 | 0
2931 | Nadia Division | Krishnanagar Sub-Division | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-111 | Assistant Engineer | Junior Engineer 3 | BILL/00517/2024-2025 | 309/PFMS | 02/10/2024 | 0 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 8.94 | 0 | 0
2932 | Nadia Division | Krishnanagar Sub-Division | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-134 | Assistant Engineer | Junior Engineer 3 | BILL/00518/2024-2025 | 310/PFMS | 02/10/2024 | 0 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 5.09 | 0 | 0
2933 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000196/2023-2024 | 3537/ND | 11/08/2023 | 1147 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 0 | 20
2934 | Nadia Division | Krishnanagar Sub-Division | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000236/2025-2026 | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0
2935 | Nadia Division | Krishnanagar Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
2936 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | Assistant Engineer | Junior Engineer 3 | ORD/000706/2024-2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0
2937 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 3 | RTOR000166/2022-2023 | 88/ND | 05/01/2023 | 0 | Resource Division | 1297.82 | 0 | 0
2938 | Nadia Division | Tehatta Sub-Division | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Betai Zone-I ii) Karimpur Jalangi Zone-IXB iii)Fatepur iv)Anjangarh v)Kamalpur Zone-II vi) Shyamnagar vii)Karimpur Jalangi Zone-VIII | Assistant Engineer | Junior Engineer | ORD/000007/2023-2024 | 497/ Kly SD-I | 06/04/2023 | 183 | TECHVISION | 4.96 | 1.58 | 100
2939 | Nadia Division | Tehatta Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-8(I&II) W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000402/2021-2022 | 317/TSD | 24/11/2021 | 30 | RADIANT | 4.72 | 4.72 | 100
2940 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Karimpur Jalangi Zone-VIII water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000411/2024-2025 | 7128/ND | 09/12/2024 | 360 | THE TOWER CONSTRUCTION | 34.05 | 0 | 60
2941 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 250 cum capacity 20 mtr. height RCC Over Head Reservoir (excluding pile foundation), pipe connection and cost of pipes, specials and Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of 250 cum. O.H.R. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VIII to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. (SM/10473) | Assistant Engineer | Junior Engineer | ORD/000428/2022-2023 | 843/ND | 28/02/2023 | 1220 | M/S TAPAS KUMAR CHAKRABORTY | 545.01 | 0 | 40
2942 | Nadia Division | Tehatta Sub-Division | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangemen and consruction of Boundary wall at 3rd Tube Well Site of Karimpur-Jalangi Zone- (VIII) Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000746/2023-2024 | 1624/ND | 07/03/2024 | 360 | SAMAR ENTERPRISE | 10.92 | 0 | 100
2943 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000010/2023-2024 | 1853/ND | 26/04/2023 | 0 | Resource Division | 33.06 | 0 | 0
2944 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000082/2023-2024 | 2285/ND | 29/05/2023 | 0 | Resource Division | 25.03 | 0 | 0
2945 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000185/2022-2023 | 148/ND | 06/01/2023 | 0 | Resource Division | 43.02 | 0 | 0
2946 | Central Drilling | Tehatta Sub-Division | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 250 mtrs depth) by utilising departmental machineries for karimpur jalangi w/s scheme, (zone- IV & VIII), karimpur-I & II block under Nadia district, CDD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000068/2023-2024 | 137/CDD | 17/04/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 37.28 | 0 | 100
2947 | Eastern Mechanical | Tehatta Sub-Division | Quotation charges for new service connection and security deposit at Karimpur Jalangi Zone-VIII (Barbakpur) PH-III under EMSD-III,Nadia | Assistant Engineer | Junior Engineer | BILL/02240/2024-2025 | BP-177 | 13/12/2024 | 0 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 5.28 | 0 | 0
2948 | Eastern Mechanical | Tehatta Sub-Division | Quotation charges for new service connection and security deposit at Karimpur Jalangi Zone-IX,B (Garaimari) PH-II under EMSD-III,Nadia | Assistant Engineer | Junior Engineer | BILL/02300/2024-2025 | BP-192-24-25 | 16/12/2024 | 0 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 10.76 | 0 | 0
2949 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under KARIMPUR JALANGI(Z-8) W/S Scheme, Block- Karimpur II, PALSONDHA W/S Scheme, Block- Tehatta II, & MAIDANPUR W/S Scheme, Block- Chapra, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/001923/2022-2023 | 1179/EMD | 21/03/2023 | 940 | CREATIVE WATER & PROCESS TECHNOLOGIES PVT. LTD. | 77.9 | 0 | 85
2950 | Eastern Mechanical | Nadia Arsenic Civil Division II | Quotation for load enhancement and security deposit charges at PH-I of Bagberia PWSS,Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/02079/2024-2025 | BP-169-24-25 | 05/12/2024 | 0 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 3.46 | 0 | 0
2951 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Bagberia Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000067/2023-2024 | 324/1/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.21 | 0 | 100
2952 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bagberia) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000097/2023-2024 | 1117/NACD-II | 06/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100
2953 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte in soft copy for different PWSS under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000183/2022-2023 | 164/AE-I/NACD-II | 28/07/2022 | 92 | JOY GOPAL GUPTI | 4.75 | 4.75 | 100
2954 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000186/2023-2024 | 532/AE-I/NACD-II | 18/12/2023 | 15 | SUBHANKAR ROY | 0.97 | 0 | 100
2955 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:- Dangna under Habitation of Ghosh Para in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000218/2023-2024 | 618/AE-I/NACD-II | 02/02/2024 | 15 | ST. ANTHONY ENTERPRISE | 0.96 | 0 | 100
2956 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:- Dangna under Habitation of Muslimpara and Ghosh Para in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000219/2023-2024 | 619/AE-I/NACD-II | 02/02/2024 | 15 | SUBHANKAR ROY | 0.93 | 0 | 100
2957 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Masjidpara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000220/2023-2024 | 620/AE-I/NACD-II | 02/02/2024 | 15 | SHOVON KUMAR MODAK | 0.97 | 0 | 100
2958 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Clubpara and Dilar Para &Rajbangsi Para in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dt | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000221/2023-2024 | 621/AE-I/NACD-II | 02/02/2024 | 15 | NAMDAR ALI | 0.97 | 0 | 100
2959 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Daspara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000222/2023-2024 | 622/AE-I/NACD-II | 02/02/2024 | 15 | BINOY DAS | 0.93 | 0 | 100
2960 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Karmakar Para and HajraPara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000223/2023-2024 | 623/AE-I/NACD-II | 02/02/2024 | 15 | SHYAMAL KANTI GHOSH | 0.93 | 0 | 100
2961 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Schoolpara ,Hatpara, Christanpara in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte¿ | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000224/2023-2024 | 624/AE-I/NACD-II | 02/02/2024 | 15 | SREE GURU ENTERPRISE | 0.93 | 0 | 100
2962 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:-Bagberia under Habitation of Baganpara Part in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000225/2023-2024 | 625/AE-I/NACD-II | 02/02/2024 | 15 | NIVEDITA CONSTRUCTION | 0.91 | 0 | 100
2963 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Bagberia & Hatkhola Water Supply Scheme of capacity 35 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000290/2023-2024 | 197/NACD-II | 12/02/2024 | 90 | SINGHA ROY & CO. | 159.46 | 0 | 30
2964 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:- Bagberia under Habitation of Gajantala in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000338/2023-2024 | 596/AE-I/NACD-II | 29/01/2024 | 15 | BK ENGINEERING | 0.91 | 0 | 100
2965 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Bagberia W/S Scheme Village:- Bagberia under Habitation of Baganpara Part in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000339/2023-2024 | 597/AE-I/NACD-II | 29/01/2024 | 15 | PARTHA DAS | 0.91 | 0 | 0
2966 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Bagberia 2nd tube well Site under Bagberia Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000347/2024-2025 | 1024/AE-I/NACD-II | 10/12/2024 | 30 | M/S FREEDOM CONSTRUCTION | 4.76 | 0 | 0
2967 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of Diesel SUV car for office use of the Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte. Krishnagar, Nadia. for the period 01.11.2022 to 31.03.2023.(Five months) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000356/2022-2023 | 785//NACD-II | 28/10/2022 | 151 | TARUN KUMAR BHATTACHARYA | 2.07 | 0 | 100
2968 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | RTOR000003/2021-2022 | 910/NACD-II | 24/11/2021 | 0 | Resource Division | 7.39 | 0 | 0
2969 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | RTOR000007/2021-2022 | 133 | 25/02/2022 | 0 | Resource Division | 92.34 | 0 | 0
2970 | Nadia Division | RWS Nadia Sub-Division | Laying of additional pipeline as per the revised drawing for augmentation of Subarnabihar Zone-II Water Supply Scheme in Krishnagar-I Block under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000050/2025-2026 | 2287/ND | 19/05/2025 | 90 | M/S GHOSH CONSTRUCTION | 91.02 | 0 | 0
2971 | Nadia Division | RWS Nadia Sub-Division | Supplying, Laying, Fitting & Fixing of Distribution System including all type of specials, valves, pipes all complete, Proposed augmentation of Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction & Soil investigation of 350 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (With Pile Foundation), Pipe Connection and Cost of Pipes, Specials, Construction of 1 (One) No. Pump House (4.88m X 3.66m) Including Sanitary Arrangement, HW Site & 1 (One) No. Pump House (4.88m X 3.66m) Including Sanitary Arrangement Tw Site-2, Construction of Boundary Wall, Service Road (60 Mtr. Length X 3 Mtr. Width) at Head Work Site & Service Road (15 Mtr. Length X 2 Mtr. Width) at Tube Well Site for Subarna Behar ZONE-II in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000163/2023-2024 | 3194/ND | 26/07/2023 | 1096 | M/S GHOSH CONSTRUCTION, SUKUL ROAD, P.O-KRISHNAGAR, DIST.NADIA, PIN-741101, WB | 440.53 | 0 | 5
2972 | Nadia Division | RWS Nadia Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Subarnabehar W/S Scheme in Krishnagar - I Block of Nadia District under Nadia Division. PART - B | Assistant Engineer | Junior Engineer | ORD/000317/2021-2022 | 1190/PH | 03/12/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.69 | 1.68 | 100
2973 | Nadia Division | RWS Nadia Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
2974 | Nadia Division | RWS Nadia Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 65 m3/hr at Subarnabihar Zone-II Water Supply Scheme including 3 Months Trial Run & 3 Years O&M within Krishnanagar-I Block under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000723/2023-2024 | 1354/ND | 27/02/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 204.6 | 0 | 0
2975 | Nadia Division | RWS Nadia Sub-Division | continuation order of Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Subarnabehar zone - II W/S Scheme in Krishnagar - I Block of Nadia District under Nadia Division. | Assistant Engineer | Junior Engineer | ORD/000757/2021-2022 | 1198/PH | 07/12/2021 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.6 | 1.6 | 100
2976 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000191/2022-2023 | 241/ND | 13/01/2023 | 0 | Resource Division | 85.16 | 0 | 0
2977 | Eastern Mechanical | RWS Nadia Sub-Division | WBSEDCL Quotation for New Service Connection to the newly Head Work Site under SUBARNA BEHAR (ZONE-II) W/S Scheme in KRISHNAGAR - 1 Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3005020477) | Assistant Engineer | Junior Engineer | BILL/02151/2024-2025 | BP-170-24-25 | 05/12/2024 | 0 | W.B.S.E.D.C.L (GROUP KRISHNAGAR ROAD STATION C.C.C) | 6.39 | 0 | 0
2978 | Nadia Division | Ranaghat Sub-Division | Providing additional functional household tap connection including repairing of existing FHTC at Joania water supply scheme under Ranaghat Sub-Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000148/2024-2025 | 654/RSD | 18/06/2024 | 210 | ROMI TRADERS | 0.97 | 0 | 90
2979 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of head work site pump house & allied works of Joania W/S scheme of Krishnanagar block under Ranaghat Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000228/2022-2023 | 556/A/RSD | 30/08/2022 | 30 | ANJALI ENTERPRISE | 2.22 | 0 | 90
2980 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of pump house & allied works in the premises at Pump house no-II of Joania W/S scheme of Krishnanagar-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000229/2022-2023 | 557/RSD | 30/08/2022 | 30 | K.K. MARKETING | 2.62 | 2.25 | 100
2981 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation & repair of CWR pump house & allied works of Joania W/S scheme of Krishnanagar block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000230/2022-2023 | 557/A/RSD | 30/08/2022 | 30 | M/S ASIT ROY BHOWMIK | 2 | 1.83 | 90
2982 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
2983 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection ( Final part ) including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe line and other allied works etc all complete for JOANIA W/S scheme (for Hazrapal, Joania, Kursi, Malipota, Sardanga, Tiabali Mouza) under Ranaghat Sub Division of Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000741/2021-2022 | 1374/ND | 23/03/2022 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 230.28 | 158.17 | 86
2984 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000012/2023-2024 | 1882/ND | 26/04/2023 | 0 | Resource Division | 14.1 | 0 | 0
2985 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000056/2022-2023 | 4287/ND | 29/09/2022 | 0 | Resource Division | 4.29 | 0 | 0
2986 | Nadia Division | Ranaghat Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/001081/2021-2022 | 644/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.51 | 0 | 0
2987 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at JOANIA W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/09789 | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000135/2025-2026 | 1136/EMD | 04/06/2025 | 90 | M/S DILIP MITRA | 36.67 | 0 | 0
2988 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No.- I AND II under Joania WS Scheme, Block Krishnagar I, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-06) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000889/2022-2023 | 157/EMDdt.06.01.2023 | 08/02/2023 | 726 | MASSK ENGINEERING WORKS | 14.9 | 0 | 100
2989 | Nadia Division | Tehatta Sub-Division | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide notification no 03/2022-central tax rate dt 13.07.2022 for the work of Laying Of Distribution System Including Specials, Valves & Pipe Carrying Structure All Complete ,rising main with interconnction in between tubewell including specials and valves, Providing FHTC Including Supplying, Laying, Fitting, Fixing Of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE 100, PN16) Pipe With All Necessary Specials, Saddle Piece Etc., Construction Of 400 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (including Pile Foundation), Pipe Connection And Cost Of Pipes, Specials And Soil Investigation All Complete For Augmentation Of Ground Based Water Supply Scheme At Palashipara to Accommodate FHTC Under Tehatta Sub-Divn Under Nadia Divn, PHE Dte | Assistant Engineer | Junior Engineer | BILL/00218/2024-2025 | 131/PFMS | 27/07/2024 | 0 | GHOSH ENTERPRISE | 25.43 | 0 | 0
2990 | Nadia Division | Tehatta Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 120 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Palshipara to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000092/2024-2025 | 4228/ND | 02/08/2024 | 180 | B.M. ENGINEERING & CONSTRUCTION | 296.87 | 0 | 0
2991 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Rising main with Inter-Connection in between Tube wells including specials and valves, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 400 cum capacity 20 mtr. staging height RCC Over Head Reservoir (including pile Foundation), pipe connection and cost of pipes, specials and Soil investigation all complete for Augmentation of Ground Based Water Supply Scheme at Palashipara to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000202/2022-2023 | 4412 /ND | 14/10/2022 | 841 | GHOSH ENTERPRISE, B-2/183, KALYANI. P.O.& P.S. KALYANI, DIST.NADIA, PIN-741235,W.B | 514.08 | 368.85 | 95
2992 | Nadia Division | Tehatta Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
2993 | Nadia Division | Tehatta Sub-Division | Construction of barbed wire fencing with concrete pillars at Palashipara (3rd T.W). water supply scheme( New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | Assistant Engineer | Junior Engineer | ORD/000583/2022-2023 | 932/TSD | 14/03/2023 | 7 | PRABIR KUMAR ROY | 0.65 | 0.63 | 0
2994 | Nadia Division | Tehatta Sub-Division | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangement and Consruction of Boundary wall at 3rd Tube well Site at Palashipara Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000668/2023-2024 | 1100/ND | 19/02/2024 | 360 | ROY CONSTRUCTION | 11.29 | 0 | 90
2995 | Nadia Division | Tehatta Sub-Division | Sinking of 01 no Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Palashipara Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000689/2023-2024 | 1225/ND | 22/02/2024 | 244 | M/S DIPAK ENTERPRISE | 17.38 | 0 | 100
2996 | Nadia Division | Tehatta Sub-Division | Laying distribution system for Augmentation of Ground Water Based Pipe Water supply scheme at Palashipara PWSS [Part-B] of Under Tehatta Sub-Division under under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000809/2023-2024 | 1914/ND | 15/03/2024 | 357 | GHOSH ENTERPRISE | 66.07 | 0 | 20
2997 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000058/2023-2024 | 2290/ND | 29/05/2023 | 0 | Resource Division | 34.16 | 0 | 0
2998 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000174/2022-2023 | 140/ND | 06/01/2023 | 0 | Resource Division | 7.35 | 0 | 0
2999 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000196/2022-2023 | 1025/ND | 13/03/2023 | 0 | Resource Division | 30.79 | 0 | 0
3000 | Nadia Division | Tehatta Sub-Division | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA | Assistant Engineer | Junior Engineer | VCH/000347/2022-2023 | 47/PFMS | 22/06/2022 | 0 | HORIZEN | 2.7 | 0 | 0
3001 | Eastern Mechanical | Tehatta Sub-Division | Quotation charges and security deposit for new power connection at Palashipara PH-III head worksite under Eastern Mechanical Subdivision-III, Nadia | Assistant Engineer | Junior Engineer | BILL/02257/2024-2025 | BP-178 | 13/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 3.49 | 0 | 0
3002 | Eastern Mechanical | Tehatta Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at PALASHIPARA W/S Scheme Block- Tehatta-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10691] | Assistant Engineer | Junior Engineer | ORD/000139/2025-2026 | 1140/EMD | 04/06/2025 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 52.38 | 0 | 0
3003 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISUNRA W/S Scheme, Block-NABADWIP, PALASIPARA W/S Scheme, Block-Tehatta-II AND TOPLA W/S Scheme, Block-Karimpur-II Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No. - 05) | Assistant Engineer | Junior Engineer | ORD/001011/2022-2023 | 499/EMD | 24/01/2023 | 30 | WEST BENGAL ENGINEERING CO. | 90.14 | 6.39 | 15
3004 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC(functional household tap connection ) by retrofitting under''Jalswapno"with utility shifting of water pipeline in connection to the work under Nadia Highway Division -I PWD(Roads) Dte. along Dharmada-Muragachha road3.00 kmp to 6.00kmp under surface based Water Supply scheme(Northern sector part III) under Krishnagar sub-division under Nadia Divn,PHE Dte. | Assistant Engineer |  | ORD/000283/2021-2022 | 5695/ND | 03/11/2021 | 90 | APURBA MANDAL | 75.34 | 2.35 | 100
3005 | Nadia Division | Krishnanagar Sub-Division | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.12.2023 to 31.12.2023 | Assistant Engineer |  | ORD/000456/2023-2024 | 1260/KLYSD-I | 30/11/2023 | 31 | SUMAN CHAKRABORTY | 4.89 | 0 | 100
3006 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000002/2021-2022 | 6831/ND | 17/11/2021 | 0 | Resource Division | 1.13 | 0 | 0
3007 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000034/2022-2023 | 4310/ND | 29/09/2022 | 0 | Resource Division | 8.09 | 0 | 0
3008 | Nadia Division | Krishnanagar Sub-Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surface water based water supply scheme (Northern Sector Part-III ) under Krishnagar Sub-division under Nadia Division, PH.E Dte. (Block- Krishnagar-II) | Assistant Engineer |  | VCH/000915/2021-2022 | 555/PFMS | 23/02/2022 | 0 | APURBA MANDAL | 67.83 | 0 | 0
3009 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Madhugari W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer |  | ORD/000024/2021-2022 | 2157/ND | 21/05/2021 | 45 | M/S KRISHNA MONDAL | 21.2 | 16.08 | 100
3010 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Madhugari W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte."(PART- B) | Assistant Engineer |  | ORD/000025/2021-2022 | 2158/ND | 21/05/2021 | 45 | M/S KRISHNA MONDAL | 21.21 | 16.7 | 0
3011 | Nadia Division | RWS Nadia Sub-Division | Detailed study of Households/Habitations of Chhota Naldaha, Chilakhali, Chupria, Maheshpur, Nutangram, Pumlia, Sahebnagar, Tehatta, Uttampur and Teinpur Villages under Nadia District under the jurisdiction of Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000403/2023-2024 | 1209/KLYSD-I | 17/11/2023 | 15 | TECHVISION | 2.79 | 0 | 100
3012 | Nadia Division | RWS Nadia Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
3013 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Birnagar, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Birnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000001/2021-2022 | 765/NAD-I | 04/05/2021 | 60 | UNICON INDIA | 93.41 | 133.1 | 100
3014 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Part-II at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000012/2021-2022 | 777/NAD-I | 05/05/2021 | 60 | J.D.J. ENTERPRISE | 97.11 | 29.74 | 50
3015 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Mouza-Beharia at Santipur Block by augmentation of Ground Water Based PWSS for Beharia W/S Scheme under Nadia Arsenic Division-I, PHE Dte (SL.NO.03) |  |  | ORD/000148/2022-2023 | 3326 / NAD-I | 16/12/2022 | 45 | CHOWDHURY & CO. | 67.83 | 60.38 | 100
3016 | Nadia Arsenic Division I |  | Pipeline connection with manifold to dedicated line under Jal Jeevan Mission (JJM) at Shantipur Block by retrofitting o Ground Water based PWSS for Beharia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. ¿ 01) |  |  | ORD/000290/2023-2024 | 28/AE-I/NAD-I | 19/01/2024 | 15 | DEBASHISH DEY | 0.96 | 0 | 100
3017 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000009/2021-2022 | 773/NAD-I | 04/05/2021 | 60 | H I ENTERPRISE | 95.74 | 59.38 | 100
3018 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VII, (Kumarpur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) Tender No. - 208/NAD-I/2020-2021. |  |  | ORD/000128/2020-2021 | 91/NAD-I | 13/01/2021 | 45 | APURBA MANDAL | 46.77 | 19.08 | 100
3019 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Badlangi Padmamala Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | Assistant Engineer | Junior Engineer Chapra Block | ORD/000009/2021-2022 | 2050/ND | 13/05/2021 | 45 | SUMIT GHOSH | 12.28 | 22.55 | 100
3020 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Badlangi Padmamala Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer | Junior Engineer Chapra Block | ORD/000011/2021-2022 | 2047/ND | 13/05/2021 | 60 | ONKAR ENTERPRISE | 41.53 | 57.46 | 100
3021 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Badlangi Padmamala Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer | Junior Engineer Chapra Block | ORD/000012/2021-2022 | 2048/ND | 13/05/2021 | 60 | GHOSH CONSTRUCTION | 41.53 | 0 | 100
3022 | Nadia Division | RWS Nadia Sub-Division | Continuation for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000058/2022-2023 | 578/ Kly SD-I | 30/06/2022 | 92 | SUMAN CHAKRABORTY | 4.89 | 4.89 | 0
3023 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution System including specials & valves, pipe supporting structure all complete and Providing FHTC including supplying,laying,fitting, fixing of 15mm NB PVC(schedule 80)/ 20mm OD HDPE(PE100,PN16) pipe with all necessary specials,10mm gun metal ferrule,saddale piece etc.by retrofitting under Jal Swapna for Badlangi Padmamala Zone-II Water Supply Scheme in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000671/2021-2022 | 662/ND | 11/02/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 458.3 | 0 | 78
3024 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Chapra Block | RTOR000015/2022-2023 | 3300/ND | 27/07/2022 | 0 | Resource Division | 22.42 | 0 | 0
3025 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Chapra Block | RTOR000016/2021-2022 | 95/ND | 06/01/2022 | 0 | Resource Division | 3.22 | 0 | 0
3026 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Chapra Block | RTOR000052/2021-2022 | 435/ND | 31/01/2022 | 0 | Resource Division | 2.39 | 0 | 0
3027 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Badlangi Padmamala Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | Assistant Engineer | Junior Engineer Chapra Block | VCH/000609/2021-2022 | 277/PFMS | 08/10/2021 | 0 | GHOSH CONSTRUCTION | 29.07 | 0 | 0
3028 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Madhpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retrofitting) | Assistant Engineer |  | ORD/000245/2021-2022 | 5361/ND | 30/09/2021 | 60 | M/S CHANDIMATA CONSTRUCTION | 55.05 | 48.6 | 0
3029 | Nadia Division | Tehatta Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
3030 | Nadia Division | Tehatta Sub-Division | Madhpur Water Supply Scheme Balance work of FHTC. | Assistant Engineer |  | ORD/000726/2021-2022 | 200/TSD | 14/03/2022 | 10 | M/S CHANDIMATA CONSTRUCTION | 4.41 | 4.41 | 100
3031 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000068/2021-2022 | 801/ND | 18/02/2022 | 0 | Resource Division | 4.41 | 0 | 0
3032 | Nadia Division | Tehatta Sub-Division | PROVIDING HOUSE CONNECTION INCLUDING SUPPLY OF 15MM DIA G.I/UPVC PIPE OF AVERAGE LENGTH OF 15 MTR. 10MM DIA GUN-METAL FERRULE, SADDLE PICE (AS REQUIRED SIZE), 15MM DIA BIB COCK ETC ALL COMPLETE AT MADHPUR W/S SCHEME UNDER NADIA DIVISION, PHE DTE (PART-A) | Assistant Engineer |  | VCH/000832/2020-2021 |  | 26/02/2021 | 0 | GHOSH ENTERPRISE | 23.95 | 0 | 0
3033 | Nadia Division | Tehatta Sub-Division | PROVIDING HOUSE CONNECTION INCLUDING SUPPLY OF 15MM DIA G.I/UPVC PIPE OF AVERAGE LENGTH OF 15 MTR. 10MM DIA GUN-METAL FERRULE, SADDLE PICE (AS REQUIRED SIZE), 15MM DIA BIB COCK ETC ALL COMPLETE AT MADHPUR W/S SCHEME UNDER NADIA DIVISION, PHE DTE (PART-B) | Assistant Engineer |  | VCH/000833/2020-2021 |  | 26/02/2021 | 0 | CHAKRABORTTI ENTERPRISE | 23.9 | 0 | 0
3034 | Nadia Division | Tehatta Sub-Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | Assistant Engineer |  | VCH/001019/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 4.09 | 0 | 0
3035 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Barakulta W/S scheme(for Byaspur & Takshali Mouzas) in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000028/2021-2022 | 2192/ND | 24/05/2021 | 90 | TARUN KUMAR BHATTACHARYA | 86.32 | 16 | 100
3036 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000089/2022-2023 | 4330/ND | 29/09/2022 | 0 | Resource Division | 8.96 | 0 | 0
3037 | Nadia Division | Ranaghat Sub-Division | Providing Functional Household Tap Connection from Barakulta Water Supply Scheme (For Byaspur & Takshali Mouzas) under Jal Swapno Program in Nadia District | Assistant Engineer | Junior Engineer 2 | VCH/000606/2021-2022 | 263/PFMS | 08/10/2021 | 0 | TARUN KUMAR BHATTACHARYA | 68.99 | 0 | 0
3038 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Daforpota (Zone-II) W/S scheme in Nadia District under Nadia Division P.H.E. Dte." (Phase - I, Retrofitting) | Assistant Engineer |  | ORD/000120/2021-2022 | 2994/ND | 29/07/2021 | 60 | SANJOY BAKSHI | 24.91 | 38.49 | 0
3039 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000092/2021-2022 | 789/ND | 18/02/2022 | 0 | Resource Division | 2.37 | 0 | 0
3040 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-IV, within Krishnagar-II & Nabadwip Block (Phase-A, Retrofitting)" | Assistant Engineer |  | ORD/000400/2020-2021 | 776/ND | 10/02/2021 | 90 | SATYABRATA CHAKRABORTY | 97.11 | 43.78 | 0
3041 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II Nabadwip (Part) Block (Phase-A). | Assistant Engineer |  | VCH/000520/2021-2022 | 181/PFMS | 15/09/2021 | 0 | SATYABRATA CHAKRABORTY | 74.21 | 0 | 0
3042 | Nadia Division | Krishnanagar Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-III, Z-IV, WITHIN KRISHNAGAR-2 AND NABADWIP BLOCK, PHASE-A. | Assistant Engineer |  | VCH/000879/2021-2022 | 498/PFMS | 03/02/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 0.82 | 0 | 0
3043 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II Nabadwip (Part) Block (Phase-A). | Assistant Engineer |  | VCH/000986/2020-2021 |  | 24/03/2021 | 0 | SATYABRATA CHAKRABORTY | 21.89 | 0 | 0
3044 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Pansila W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting) (Part-1). | Assistant Engineer |  | ORD/000003/2021-2022 | 2027/ND | 12/05/2021 | 60 | TARUN KUMAR BHATTACHARYA | 35.26 | 31.73 | 100
3045 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Pansila W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting)" (Part-2) | Assistant Engineer |  | ORD/000004/2021-2022 | 2028/ND | 12/05/2021 | 45 | TARUN KUMAR BHATTACHARYA | 23.76 | 21.17 | 0
3046 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Pansila W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting) (Part-3) | Assistant Engineer |  | ORD/000005/2021-2022 | 2029/ND | 12/05/2021 | 60 | TARUN KUMAR BHATTACHARYA | 35.27 | 28.21 | 100
3047 | Nadia Division | Krishnanagar Sub-Division | Continuation for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. | Assistant Engineer |  | ORD/000279/2022-2023 | 1072/Kly SD-I | 30/11/2022 | 90 | SUMAN CHAKRABORTY | 4.89 | 4.89 | 0
3048 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000090/2021-2022 | 787/ND | 18/02/2022 | 0 | Resource Division | 1.1 | 0 | 0
3049 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-III within Nakashipara Block ( Phase -A) | Assistant Engineer |  | ORD/000283/2020-2021 | 243/ND | 15/01/2021 | 90 | MADE & TRADE CO. | 96.84 | 192.02 | 0
3050 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II, Z-III, WITHIN NAKASHIPARA BLOCK, PHASE-A. | Assistant Engineer |  | VCH/000883/2021-2022 | 497/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.45 | 0 | 0
3051 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-III within Nakashipara Block (Phase-A). | Assistant Engineer |  | VCH/000990/2020-2021 |  | 24/03/2021 | 0 | MADE & TRADE CO. | 89.45 | 0 | 0
3052 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block ( Phase -A) | Assistant Engineer |  | ORD/000282/2020-2021 | 242/ND | 15/01/2021 | 90 | MONDAL PRECISION PRIVATE LIMITED | 96.61 | 31.18 | 100
3053 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- II/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000357/2023-2024 | 4651/ND | 10/10/2023 | 720 | SATYABRATA CHAKRABORTY | 484.95 | 0 | 15
3054 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) | Assistant Engineer |  | VCH/000924/2021-2022 | 565/PFMS | 25/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.45 | 0 | 0
3055 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) | Assistant Engineer |  | VCH/000990/2021-2022 | 592/PFMS | 04/03/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 62.51 | 0 | 0
3056 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-IV within Nakashipara Block(Phase-C) in Nadia District under Nadia Division P.H.E.Dte.(SL.1) | Assistant Engineer |  | ORD/000466/2020-2021 | 972/ND | 25/02/2021 | 90 | UMWELT ENGINEERS PVT LTD | 97 | 27.21 | 0
3057 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000095/2022-2023 | 4282/ND | 29/09/2022 | 0 | Resource Division | 12.52 | 0 | 0
3058 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) | Assistant Engineer |  | VCH/000483/2021-2022 |  | 04/10/2021 | 0 | UMWELT ENGINEERS PVT LTD | 62.5 | 0 | 0
3059 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000611/2021-2022 | 280/PFMS | 08/10/2021 | 0 | UMWELT ENGINEERS PVT LTD | 62.5 | 0 | 0
3060 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bagberia (Vill-Bagberia) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte |  |  | ORD/000038/2020-2021 | 1185/NACD-II | 13/11/2020 | 25 | M/S GHOSH CONSTRUCTION | 4.99 | 0 | 0
3061 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-II W/S Scheme, Phase-II at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000002/2022-2023 | 643/NAD-I | 29/04/2022 | 90 | UNICON INDIA | 335.39 | 0 | 10
3062 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenatioin under Jal Jeevan Mission Aranghata Zone- II W/S Scheme, Part - II at Ranaghat- II Block under Nadia Arsenic Division-I, PHE Dte. (Sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000104/2023-2024 | 1696/NAD-I | 13/07/2023 | 982 | ORIENT CONSTRUCTION | 311.77 | 0 | 90
3063 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara / Jal Swapna for Aranghata Zone-II Part -III under Jal Jeevan Mission at Ranaghat -II Block by retrofitting of ground Water based PWSS for Aranghata Zone-II Water Supply Scheme under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000355/2023-2024 | 461/NAD-I | 15/03/2024 | 382 | DIVINE | 329.47 | 0 | 75
3064 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000014/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 24.52 | 0 | 0
3065 | Nadia Division | Debgram Sub-Division | FHTC in connection with Utility Shifting of Water pipeline in connection to the work under Nadia Highway Division-I(PWD Road) dte. along Dharmadah-Muragachha Road 0.00 Kmp to 3.00 Kmp under surface water based water supply scheme (Northern Sector Part-II) under Debagram Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer |  | ORD/000447/2021-2022 | 7329/ND | 22/12/2021 | 90 | TARUN KUMAR BHATTACHARYA | 108.36 | 7.15 | 98
3066 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000081/2021-2022 | 808/ND | 18/02/2022 | 0 | Resource Division | 6.92 | 0 | 0
3067 | Nadia Division | Debgram Sub-Division | FHTC in connection with Utility Shifting of Water pipeline in connection to the work under Nadia Highway Division-I(PWD Road) dte. along Dharmadah-Muragachha Road 0.00 Kmp to 3.00 Kmp under surface water based water supply scheme (Northern Sector Part-II) under Debagram Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer |  | VCH/000800/2022-2023 | 216/PFMS | 28/09/2022 | 0 | TARUN KUMAR BHATTACHARYA | 87.14 | 0 | 0
3068 | Nadia Division | Krishnanagar Sub-Division | LAYING OF PIPELINE UNDER PALASHIPARA PWSS FROM PALASHIPARA BAZAR TO BURNIA BUS STAND. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | BILL/00527/2023-2024 | 241/1/PFMS | 18/08/2023 | 0 | OTHERS | 49.99 | 0 | 0
3069 | Nadia Division | Krishnanagar Sub-Division | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-134, (1) AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION, (2) AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | BILL/00563/2024-2025 | 311/PFMS | 02/10/2024 | 0 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 0 | 0 | 0
3070 | Nadia Division | Krishnanagar Sub-Division | Continuation of Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000050/2024-2025 | 3445/ND | 20/06/2024 | 30 | IMAGIN | 20.46 | 0 | 100
3071 | Nadia Division | Krishnanagar Sub-Division | Repair and renovation works of R.C.C. Elevaced Reservoir 350 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Dakshin Jhitkipota Zone-II Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000168/2024-2025 | 4580/ND | 21/08/2024 | 495 | MONDAL CONSTRUCTION | 20.42 | 0 | 0
3072 | Nadia Division | Krishnanagar Sub-Division | Continuation for Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.07.2023 to 31.08.2023 (Two Month). | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000246/2023-2024 | 2831/ND | 28/06/2023 | 61 | CLIFFORD FACILITY SERVICES PVT. LTD | 2.73 | 2.73 | 100
3073 | Nadia Division | Krishnanagar Sub-Division | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000254/2024-2025 | 6305/ND | 26/09/2024 | 30 | IMAGIN | 34.21 | 0 | 100
3074 | Nadia Division | Krishnanagar Sub-Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities. [Phase-II] | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000661/2023-2024 | 6161/ND | 26/12/2023 | 183 | IMAGIN | 74.48 | 0 | 100
3075 | Nadia Division | Krishnanagar Sub-Division | LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE SUPPORTING STRUCTURE ALL COMPLETE BASED ON ACTUAL ESTIMATE & PROVIDING FHTC FOR DAKHIN JHITKAPOTA ZONE - II WATER SUPPLY SCHEME IN NADIA DISTRICT UNDER NADIA DIVISION. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000691/2021-2022 | 923/ND | 24/02/2022 | 90 | SATYABRATA CHAKRABORTY | 282.53 | 109.62 | 68
3076 | Nadia Division | Krishnanagar Sub-Division | Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000769/2023-2024 | 1821/ND | 14/03/2024 | 31 | IMAGIN | 34.21 | 0 | 60
3077 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | RTOR000045/2022-2023 | 4295/ND | 29/09/2022 | 0 | Resource Division | 12.3 | 0 | 0
3078 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | RTOR000050/2023-2024 | 1998/ND | 08/05/2023 | 0 | Resource Division | 0.92 | 0 | 0
3079 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | RTOR000051/2021-2022 | 444/ND | 31/01/2022 | 0 | Resource Division | 1.39 | 0 | 0
3080 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | VCH/001049/2021-2022 | 607/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.82 | 0 | 0
3081 | Eastern Mechanical | Krishnanagar Sub-Division | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. bill for the month of Juluy under AE/EMSD-II Bhatjangla Dist Nadia | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | BILL/01577/2023-2024 |  | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.09 | 0 | 0
3082 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at DAKSHIN JHITKIPOTA ZONE-II W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/09451] | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000144/2025-2026 | 1145/EMD | 04/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 38.68 | 0 | 0
3083 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under DAKSHIN JHITKIPOTA(Z-1I) W/S Scheme, Block-Krishnagar-I, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000901/2022-2023 | 411EMD | 20/01/2023 | 30 | M.S.C. ENTERPRISE | 14.9 | 13.74 | 90
3084 | Nadia Division | Kalyani Sub-Division I | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 83 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Betai Zone-II to accommodate FHTC under Tehatta Sub-division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000155/2024-2025 | 4350/ND | 07/08/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 227.43 | 0 | 0
3085 | Nadia Division | Kalyani Sub-Division I | Construction of 4.88 mtr. x 3.66 mtr. Size pump house including Sanitary Arrangement at third Tube well site under Betai Zone I Water Supply Scheme under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000315/2023-2024 | 4322/ND | 26/09/2023 | 90 | TOTAN DAS | 6.75 | 0 | 100
3086 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System Including Specials, Valves & Pipe Supporting Structure All Complete, Augmentation Of Rising Main System, Providing FHTC, Construction Of 550 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (With Pile Foundation), Pipe Connection And Cost Of Pipes, Specials And Soil Investigation For Construction Of One No. 550 Cum OHR Of Staging Height 20 Mtr Under Augmentation Of Ground Water Based Water Supply Scheme For Betai Zone-I To Accommodate FHTC under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000430/2022-2023 | 875/ND | 01/03/2023 | 732 | M/S S.S ENTERPRISE | 610.04 | 174.95 | 54
3087 | Nadia Division | Kalyani Sub-Division I | Collection of Household data through mobile app for FHTC Connection (Phase-IV), under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000696/2023-2024 | 210/KLYSD-I | 09/02/2024 | 182 | HORIZEN | 4.85 | 0 | 100
3088 | Nadia Division | Kalyani Sub-Division I | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 122 cum/hour capacity for Augmentation of Ground Based Water Supply Scheme at Betai Zone-I to accommodate FHTC including 3 Months Trial Run & 3 Years O&M under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000736/2023-2024 | 1492/ND | 04/03/2024 | 720 | MONDAL PRECISION PRIVATE LIMITED | 302.94 | 0 | 0
3089 | Nadia Division | Kalyani Sub-Division I | Construction of Boundary wall at Head Work Site & 2nd Tube Well ,3rd Tube Well site of Betai Zone- I Ground water based water supply scheme under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000752/2023-2024 | 1627/ND | 07/03/2024 | 361 | GANGULY ENTERPRISE | 23.18 | 0 | 40
3090 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000083/2023-2024 | 2316/ND | 29/05/2023 | 0 | Resource Division | 27.29 | 0 | 0
3091 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000177/2022-2023 | 156/ND | 06/01/2023 | 0 | Resource Division | 40.09 | 0 | 0
3092 | Nadia Division | Kalyani Sub-Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000286/2022-2023 | 11/PFMS | 11/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.93 | 0 | 0
3093 | Central Drilling | Kalyani Sub-Division I | Continuation for Hiring of Diesel Driven Motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub Division-ll (D),CDD, P.H.Enginering Dte. for supervision of JJM Related works. | Assistant Engineer | Junior Engineer | ORD/000028/2024-2025 | 153/CMSD-II(D) | 30/07/2024 | 184 | MD NIZAMUDDIN | 0.87 | 0 | 0
3094 | Central Drilling | Kalyani Sub-Division I | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Betai W/S Scheme (Z-I,T/W-I) , Tehatta-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000071/2023-2024 | 898/CDD | 18/07/2023 | 237 | DIPALI CONSTUCTION | 18.57 | 0 | 100
3095 | Eastern Mechanical | Kalyani Sub-Division I | Quotation for new service connection at P.H-III under Betai Zone-I W/S Scheme, Dist-Nadia | Assistant Engineer | Junior Engineer | BILL/04633/2023-2024 | BP-284-23-24 | 16/02/2024 | 0 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 10.9 | 0 | 0
3096 | Eastern Mechanical | Kalyani Sub-Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Betai Zone-I ground water based water supply scheme under Block_Tehatta-I Dist. - Nadia under EMD, PHE Dte. SM/10414 | Assistant Engineer | Junior Engineer | ORD/000194/2025-2026 | 1119/EMD | 04/06/2025 | 90 | MA ANNAPURNA ENTERPRISE | 24.48 | 0 | 0
3097 | Eastern Mechanical | Kalyani Sub-Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BETAI (ZONE-I) W/S Scheme, Block-Tehatta-I, Dist. - Nadia. NIET NO. 25 OF EE/EMD OF 2022-23 (SL. NO. 05) | Assistant Engineer | Junior Engineer | ORD/001254/2022-2023 | 811/EMD | 16/02/2023 | 685 | A.K. ENTERPRISE | 24.7 | 18.36 | 80
3098 | Nadia Division | RWS Nadia Sub-Division | Repairing Works Of Tenpur (Zone-II) Water Supply Scheme,Karimpur-I Block Under RWS Nadia Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000010/2024-2025 | 3264/ND | 10/06/2024 | 540 | DURGADAS BASU | 25.29 | 0 | 45
3099 | Nadia Division | RWS Nadia Sub-Division | Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000033/2024-2025 | 3450/ND | 20/06/2024 | 45 | IMAGIN | 19.44 | 0 | 100
3100 | Nadia Division | RWS Nadia Sub-Division | Sinking of 1 no. Tubewell 300mm. x 200mm. dia and 150 mtr deep by direct rotary rig method for Teinpur Zone-II PWSS within Karimpur-II block under RWS Nadia sub-division under Nadia Division, PHE Dte. (SM / 10472) | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000038/2023-2024 | 2105/ND | 15/05/2023 | 45 | MANISHIKA CONSTRUCTION | 14.18 | 12.16 | 100
3101 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Teinpur Zone-II to accommodate FHTC within Karimpur-II block under RWS Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000135/2022-2023 | 3818/ND | 05/09/2022 | 810 | CHANDAN ROY | 183.58 | 148.46 | 100
3102 | Nadia Division | RWS Nadia Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site of Teinpur zone-II PWSS under Karimpur-II Block under RWS Sub Division under Nadia Division-,P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000329/2024-2025 | 7003/ND | 26/11/2024 | 360 | DURGADAS BASU | 22.95 | 0 | 40
3103 | Nadia Division | RWS Nadia Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House and allied works for Fazilnagar within Karimpur-II Block Under Tehatta Sub-Division under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000773/2024-2025 | 660/ND | 11/02/2025 | 270 | U-TURN CONSTRUCTION | 50.44 | 0 | 70
3104 | Nadia Division | RWS Nadia Sub-Division | Conversion of IEP to AIRP of capacity 32 Cu.m/hr at Teinpur Zone-II Water Supply Scheme within Karimpur-II block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000798/2023-2024 | 1910/ND | 15/03/2024 | 120 | MONDAL ENTERPRISE | 124.86 | 0 | 30
3105 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000025/2022-2023 | 3896/ND | 08/09/2022 | 0 | Resource Division | 39.48 | 0 | 0
3106 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000073/2022-2023 | 4327/ND | 29/09/2022 | 0 | Resource Division | 2.69 | 0 | 0
3107 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | RTOR000108/2023-2024 | 3786/ND | 24/08/2023 | 0 | Resource Division | 1.6 | 0 | 0
3108 | Nadia Division | RWS Nadia Sub-Division | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-II) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | VCH/000203/2022-2023 | 27/PFMS | 20/05/2022 | 0 | ENVIROTECH SOLUTIONS | 2.56 | 0 | 0
3109 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/001012/2022-2023 | 500/EMD | 24/01/2023 | 30 | M/S DILIP MITRA | 64.62 | 10.18 | 85
3110 | Nadia Division | Kalyani Sub-Division I | Laying distribution system for providing FHTC at Mahisbathan Mouza in connection with Augmentation of Ground Based Water Supply Scheme at Mahisbathan to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000037/2024-2025 | 3468/ND | 21/06/2024 | 270 | BUDDHADEV MONDAL | 90.43 | 0 | 100
3111 | Nadia Division | Kalyani Sub-Division I | Laying distribution system for providing FHTC at Rahamatpur Mouza in connection with Augmentation of Ground Based Water Supply Scheme at Mahisbathan to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000038/2024-2025 | 3469/ND | 21/06/2024 | 270 | BUDDHADEV MONDAL | 71.37 | 0 | 100
3112 | Nadia Division | Kalyani Sub-Division I | Laying of UPVC Pipe line for Revision of drawing to accommodate FHTC & Construction of Jhama Bats Road for the approach way to headwork site of Mahisbathan water supply scheme under Kalyani Sub Division I under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000040/2024-2025 | 3452/ND | 20/06/2024 | 60 | M/S DIPAK ENTERPRISE | 45.59 | 0 | 50
3113 | Nadia Division | Kalyani Sub-Division I | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Mahisbathan Water Supply Scheme Under Kalyani Sub Division I PHE Dte) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000121/2024-2025 | 4531/ND | 20/08/2024 | 180 | M/S BISWAS ENTERPRISE | 6.96 | 0 | 0
3114 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete And Construction of 550 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 550 CUM OHR for Augmentation of Ground Based Water Supply Scheme at Mahisbathan to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000194/2023-2024 | 3449/ND | 09/08/2023 | 731 | M/S DIPAK ENTERPRISE, GHOSH PARA,WARD NO-4, KALYANI, NADIA-741235 WEST BENGAL | 560.56 | 283.85 | 55
3115 | Nadia Division | Kalyani Sub-Division I | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
3116 | Nadia Division | Kalyani Sub-Division I | Construction of boundary wall and repairing of pump house cum chlorin room at head work site,2nd tubewell site and alide work under Mahisbathan PWSS kalyani sub division-I under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000836/2024-2025 | 280/ND | 16/01/2025 | 90 | ZOOM CONSTRUCTION & INTERIO | 45.1 | 0 | 0
3117 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000044/2023-2024 | 1904/ND | 27/04/2023 | 0 | Resource Division | 57.16 | 0 | 0
3118 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000111/2023-2024 | 4221/ND | 19/09/2023 | 0 | Resource Division | 42 | 0 | 0
3119 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000147/2021-2022 | 1397/ND | 24/03/2022 | 0 | Resource Division | 31.75 | 0 | 0
3120 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000188/2022-2023 | 149/ND | 06/01/2023 | 0 | Resource Division | 43.07 | 0 | 0
3121 | Nadia Division | Kalyani Sub-Division I | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/001103/2021-2022 | 673/PFMS | 24/03/2022 | 0 | RADIANT | 2.79 | 0 | 0
3122 | Central Drilling | Kalyani Sub-Division I | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Mahisbathan W/S Scheme (TW-I), Karimpur-II Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000136/2023-2024 | 1235/CDD | 04/09/2023 | 487 | SUNRISE ENGINEERING CORPORATION | 18.85 | 0 | 100
3123 | Eastern Mechanical | Kalyani Sub-Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Mahishbathan ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. SM/10076 | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000174/2025-2026 | 1107/EMD | 04/06/2025 | 90 | S.P CONSTRUCTION | 20.8 | 0 | 0
3124 | Eastern Mechanical | Kalyani Sub-Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISBATHAN W/S Scheme, Block- Karimpur-II & ANDHARKOTA W/S Scheme, Block- Karimpur-I, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001928/2022-2023 | 1200/EMD | 22/03/2023 | 30 | KARTICK BAL | 61.1 | 0 | 70
3125 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 950 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Chanduria Zone-XI under Surface W/S Scheme of Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte.( Sl.no . 04) | Assistant Engineer-II | Junior Engineer-III | ORD/000056/2022-2023 | 1636/NAD-I | 06/09/2022 | 45 | M/S R.K. ENTERPRISE | 37.67 | 37.52 | 100
3126 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of Chanduria Zone XI at Priyanagar New Kautukpur Kautukpur Jibannagar village under Chakdah Block of PWSS for Chakdah Surface water supply scheme under NAD I PHE Dte ( Sl.no. 09) | Assistant Engineer-II | Junior Engineer-III | ORD/000095/2022-2023 | 1960 / NAD-I | 12/10/2022 | 60 | MADE AND TRADE CO. | 15.76 | 15.75 | 100
3127 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000119/2021-2022 | 12/NAD-I | 05/01/2022 | 90 | UMWELT ENGINEER PVT. LTD. | 299.45 | 209.36 | 98
3128 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X (Shimurali) Part III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-III | ORD/000162/2021-2022 | 431/NAD-I | 07/03/2022 | 60 | CHAKRABORTTI ENTERPRISE | 67.64 | 61.1 | 100
3129 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XI (Chanduria) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | Assistant Engineer-II | Junior Engineer-III | ORD/000164/2021-2022 | 432/NAD-I | 07/03/2022 | 60 | SANJOY BAKSHI | 78.61 | 78.29 | 100
3130 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of Barberia, Zone-VIII, at Chakdah Block of PWSS for Chakdah Surface Water Supply Scheme under Nadia arsenic Division-I, P.H.E. Dte. (Sl No.-01) | Assistant Engineer-II | Junior Engineer-III | ORD/000169/2022-2023 | 87/ AE-II/ NAD-I | 30/06/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 3.89 | 3.89 | 100
3131 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Zone-VIII (Barberia) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000170/2021-2022 | 430/NAD-I | 07/03/2022 | 60 | SANDIP BISWAS | 85.12 | 76.25 | 100
3132 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BALIBANGA, GONGRA, LAKSHMIPUR, MAHESHPUR & TENGRA(Block-Chapra) W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000004/2023-2024 | 1502/EMD | 18/04/2023 | 30 | M.S.C. ENTERPRISE | 8.84 | 0 | 70
3133 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Baliadanga Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000058/2023-2024 | 320/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 0.96 | 0 | 100
3134 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000122/2024-2025 | 820/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.16 | 0 | 100
3135 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Conversion of IEP to AIRP at Balidanga Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block including other works at Bhatgachhi & Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000137/2024-2025 | 1048/NACD-II | 07/08/2024 | 60 | DEBASIS SAMADDAR | 185.55 | 0 | 0
3136 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying UPVC pipeline for supplying drinking water to Baliadanga village including reconnection of existing FHTCs in Chapra Block of Baliadanga W/S Scheme under Nadia Arsenic Civil Division-II, PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000152/2023-2024 | 517/AE-I/NACD-II | 18/12/2023 | 15 | JOY HIND TUBEWELLS | 0.97 | 0 | 100
3137 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Baliadanga W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000159/2023-2024 | 526./AE-I/NACD-II | 18/12/2023 | 15 | SHYAMAL KANTI GHOSH | 0.97 | 0 | 100
3138 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Balibanga) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000167/2023-2024 | 1295/NACD-II | 23/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
3139 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Baliadanga ( Vill- Baro Baliadanga) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000217/2021-2022 | 38/NACD-II | 14/01/2022 | 45 | TARUN GHOSH | 79.94 | 79.93 | 100
3140 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Baliadanga W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000276/2021-2022 | 124/NACD-II | 21/02/2022 | 90 | SINGHA ROY & CO. | 138.93 | 138.92 | 100
3141 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | OUTSTANDING BILL PAYMENT FOR SUPPLY OF MATERIALS FOR THANAPARA, DAMODARKHALI, MADHABPUR, BALIADANGA AS FRAMED BY RESOURCE DIVISION PHE DTE. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000643/2021-2022 |  | 05/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0
3142 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUPPLY OF MATERIALS FOR THANAPARA,DAMODARKHALI,MADHABPUR AND BALIADANGA W/S. SCHEME UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000646/2021-2022 |  | 07/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0
3143 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Outstanding bill payment | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000746/2021-2022 |  | 02/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 19.04 | 0 | 0
3144 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | RESOURCES PAYMENT FOR MATERIALS | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000867/2021-2022 | 223 | 02/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 19.04 | 0 | 0
3145 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection for PH No.-I under Khaspur Tehatta Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00006/2022-2023 | 91/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0
3146 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection for PH No.-II under Khaspur Tehatta Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00007/2022-2023 | 92/EMD | 26/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.5 | 0 | 0
3147 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Khaspu W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000444/2022-2023 | 6260/EMD | 19/11/2022 | 30 | A.D. CONCERN | 10 | 0 | 100
3148 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Khaspu W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 05) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000447/2022-2023 | 6261/EMD | 19/11/2022 | 30 | SHIVAM ENTERPRISE | 9.98 | 9.06 | 90
3149 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply delivery of PCC pole, M.S materials and electrical accessories including stringing and sagging of LTOH line to WBSEDCL for new service connection P.H No. II under Khaspur w/s scheme under EMSD III, PHE Dte. Dhubulia Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/002526/2022-2023 | 108/EMSDIII18.01.23 | 14/08/2022 | 122 | MA ANNAPURNA ENTERPRISE | 3.12 | 3.12 | 0
3150 | Eastern Mechanical | Nadia Arsenic Civil Division II | PCC pole M.S materials and electrical accessories including stringing and sagging of HTOH line to WBSEDCL for new service connection at PH-I under Khaspu W/S scheme. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/002573/2022-2023 | 103/EMSD-I | 18/01/2023 | 30 | SHIVAM ENTERPRISE | 3.8 | 3.8 | 0
3151 | Eastern Mechanical | Nadia Arsenic Civil Division II | New connection charges for Khaspur PHE I Tehatta Nadia. Memo no. 3004031098/Quot/03 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/003376/2022-2023 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0
3152 | Eastern Mechanical | Nadia Arsenic Civil Division II | New connection charges for Khaspur PHE I Tehatta Nadia. Memo no. 3004031111/Quot/03 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/003377/2022-2023 |  | 21/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.5 | 0 | 0
3153 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Khaspu water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000011/2023-2024 | 526/NACD-II | 08/05/2023 | 694 | BIDYUT KUMAR | 117.34 | 32.55 | 65
3154 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Khaspu water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000013/2022-2023 | 218/NACD-II | 05/04/2022 | 60 | PAPAN ROY | 5.37 | 5.37 | 100
3155 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Dhopahat and Khaspu Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000017/2022-2023 | 242/NACD-II | 19/04/2022 | 60 | AUXILIARY TUBE WELL DRILLERS | 43.18 | 9.78 | 100
3156 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Khaspu Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000047/2023-2024 | 412/AE-I/NACD-II | 08/08/2023 | 15 | BIDYUT KUMAR | 0.97 | 0 | 100
3157 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Khaspu water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000049/2022-2023 | 16/AE-II/NACD-II | 11/04/2022 | 60 | PAPAN ROY | 2.83 | 2.81 | 100
3158 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS: Khaspu) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000056/2023-2024 | 862/NACD-II | 10/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
3159 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Khaspu Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000060/2022-2023 | 21/AE-II/NACD-II | 18/04/2022 | 30 | A.K ADHIKARY | 4.14 | 0 | 100
3160 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Khaspu and adjoining mouzas under Khaspur Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000065/2022-2023 | 293/NACD-II | 18/05/2022 | 90 | SUDHAMAY MAJUMDAR | 169.33 | 147.1 | 100
3161 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000080/2025-2026 | 736/NACD-II | 18/06/2025 | 90 | JOY HIND TUBEWELLS | 186.42 | 0 | 40
3162 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earth work in filling in ditches at Khaspu 2nd Tube Well Site for development of land in connection with proposed T/W Sinking & Pump House construction at Khaspu Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000126/2022-2023 | 62/AE-II/NACD-II | 28/06/2022 | 15 | BASUDEB SAHA | 0.6 | 0.6 | 100
3163 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Khaspu, Patharghata and Chanderghat PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000179/2024-2025 | 293_AE-II/NACD-II | 30/08/2024 | 20 | MAKALI ENGINEERING CORPORATION | 4.83 | 0 | 100
3164 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Khaspu Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000197/2022-2023 | 626/NACD-II | 06/09/2022 | 20 | RAMASISH ENTERPRISE | 4.6 | 4.6 | 100
3165 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 34 cum/Hour capacity for Khaspu Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000222/2024-2025 | 1191/NACD-II | 02/09/2024 | 540 | MONDAL PRECISION PRIVATE LIMITED | 164.15 | 0 | 35
3166 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-III Water Supply Scheme 3rd Tube Well site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000312/2024-2025 | 1503/NACD-II | 21/11/2024 | 268 | PARTHA DAS | 6.01 | 0 | 100
3167 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Khaspu Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000322/2022-2023 | 86/NACD-II | 10/01/2023 | 60 | BURIMA CONSTRUCTION | 16.35 | 16.34 | 100
3168 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 75 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Thanarpara Zone-III Water Supply Scheme in Karimpur-II block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000322/2024-2025 | 1207/NACD-II | 04/09/2024 | 540 | SINGHA ROY & CO. | 215.53 | 0 | 0
3169 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Khaspu 2nd Tubewell Site within Khaspu Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000332/2022-2023 | 125/NACD-II | 11/01/2023 | 60 | SHYAMAL KANTI GHOSH | 6.31 | 5.06 | 85
3170 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Khaspu) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000357/2023-2024 | 435/NACD-II | 15/03/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
3171 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | RTOR000007/2022-2023 | 405/NACD-II | 04/07/2022 | 0 | Resource Division | 35.72 | 0 | 0
3172 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000243/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
3173 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000349/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
3174 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System including specials, valves & pipe Supporting structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. and Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 400 CUM OHR , all complete for Augmentation of Ground Based Water Supply Scheme at Betai Zone-II to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000003/2022-2023 | 1956/ND | 28/04/2022 | 1441 | M/S S.S ENTERPRISE | 601.69 | 278.85 | 90
3175 | Nadia Division | Kalyani Sub-Division I | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 83 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Betai Zone-II to accommodate FHTC under Tehatta Sub-division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000155/2024-2025 | 4350/ND | 07/08/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 227.43 | 0 | 0
3176 | Nadia Division | Kalyani Sub-Division I | Collection of Household data through mobile app for FHTC Connection (Phase-III), under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000695/2023-2024 | 209/KLYSD-I | 09/02/2024 | 182 | TECHVISION | 4.86 | 0 | 100
3177 | Nadia Division | Kalyani Sub-Division I | Construction of Boundary wall at Head Work Site and 2nd Tube Well Site of Betai Zone-II Ground water based water supply scheme under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000753/2023-2024 | 1628/ND | 07/03/2024 | 360 | NAMDAR ALI | 21.11 | 0 | 12
3178 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000008/2022-2023 | 2507/ND | 08/06/2022 | 0 | Resource Division | 4.25 | 0 | 0
3179 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000018/2022-2023 | 3307/ND | 27/07/2022 | 0 | Resource Division | 30.17 | 0 | 0
3180 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000046/2021-2022 | 445/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
3181 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000101/2021-2022 | 1019/ND | 03/03/2022 | 0 | Resource Division | 22.52 | 0 | 0
3182 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000134/2021-2022 | 1253/ND | 16/03/2022 | 0 | Resource Division | 19.78 | 0 | 0
3183 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000145/2021-2022 | 1392/ND | 24/03/2022 | 0 | Resource Division | 16.87 | 0 | 0
3184 | Nadia Division | Kalyani Sub-Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000519/2022-2023 | 87/PFMS | 22/07/2022 | 0 | M/S S.S ENTERPRISE | 187.3 | 0 | 0
3185 | Nadia Division | Kalyani Sub-Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001262/2021-2022 | 728/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.09 | 0 | 0
3186 | Eastern Mechanical | Kalyani Sub-Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Betai Zone-II ground water based water supply scheme under Block_Tehatta-II Dist. - Nadia under EMD, PHE Dte. SM/10034 | Assistant Engineer | Junior Engineer | ORD/000183/2025-2026 | 1120/EMD | 04/06/2025 | 90 | M/S CHANDIMATA ELECTRICALS | 24.48 | 0 | 0
3187 | Eastern Mechanical | Kalyani Sub-Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Betai Zone-I ground water based water supply scheme under Block_Tehatta-I Dist. - Nadia under EMD, PHE Dte. SM/10414 | Assistant Engineer | Junior Engineer | ORD/000194/2025-2026 | 1119/EMD | 04/06/2025 | 90 | MA ANNAPURNA ENTERPRISE | 24.48 | 0 | 0
3188 | Nadia Division | Tehatta Sub-Division | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Narayanpur ii) Palsunda iii) Dogachhi Zone-II iv)Dogachhi Zone-I | Assistant Engineer | Junior Engineer | ORD/000067/2023-2024 | 679/KlySD-I | 31/05/2023 | 6 | TECHVISION | 4.79 | 0 | 100
3189 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Narayanpur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000315/2024-2025 | 6840/ND | 12/11/2024 | 360 | BISWAS CONSTRUCTION | 34.64 | 0 | 100
3190 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 200 Cum Capacity 20 Mtr. height RCC Over Head Reservoir (Excluding Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for construction of one no. 200 Cum OHR of Staging Height 20 Mtr. for Augmentation of Ground Based Water Supply Scheme at Narayanpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000437/2022-2023 | 966/ND | 09/03/2023 | 1096 | M/S S.S ENTERPRISE | 759.95 | 0 | 55
3191 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000085/2023-2024 | 2287/ND | 29/05/2023 | 0 | Resource Division | 21 | 0 | 0
3192 | Nadia Division | Tehatta Sub-Division | Augmentation of ground water based Narayanpur PWSS to accommodate FHTC in Karimpur-II Block within Nadia District under Nadia Division | Assistant Engineer | Junior Engineer | VCH/001101/2021-2022 | 671/PFMS | 24/03/2022 | 0 | RADIANT | 3.13 | 0 | 0
3193 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur-Krishnapur, Zone-II, Part-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur-Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000003/2021-2022 | 767/NAD-I | 04/05/2021 | 60 | IJABUL SEKH | 94.5 | 187.11 | 100
3194 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" in connection with " Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Pansila W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte." | Assistant Engineer |  | ORD/000465/2021-2022 | 7506/ND | 29/12/2021 | 60 | S.B.CONSTRUCTION | 12.31 | 10.54 | 0
3195 | Nadia Division | Krishnanagar Sub-Division | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000722/2024-2025 | 7571/ND | 27/12/2024 | 31 | IMAGIN | 34.21 | 0 | 0
3196 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000039/2022-2023 | 4268/ND | 29/09/2022 | 0 | Resource Division | 0.92 | 0 | 0
3197 | Nadia Division | Krishnanagar Sub-Division | Additional FHTC by retrofitting unfer jalswapno in connection with shifting of existing pipeline for implementation of widening and strengthening work of Swarupganj UBI more to Anandabas Road from 0.00 km to 6.10 km under NH Divn-I RIDF-XXV within Bankar Dhopadi Water supply scheme under Krishnagar Sub-Division PHED. (Sl.No. 01) | Assistant Engineer | Junior Engineer 2 | ORD/000053/2022-2023 | 573/KSD | 13/06/2022 | 60 | SUBHASIS MAJUMDER | 4.57 | 3.76 | 97
3198 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" in connection with " Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Bankar Dhopadi W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte." | Assistant Engineer | Junior Engineer 2 | ORD/000411/2021-2022 | 7294/ND | 20/12/2021 | 60 | SK RAJU | 32.6 | 5.33 | 0
3199 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000005/2021-2022 | 7451/ND | 27/12/2021 | 0 | Resource Division | 11.31 | 0 | 0
3200 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000038/2022-2023 | 4325/ND | 29/09/2022 | 0 | Resource Division | 1.26 | 0 | 0
3201 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH Divn-I RIDF-XXV within Bankar Dhopadi W/S Scheme under Krishnagar Sub- Divn under Nadia Divn, PHE Dte | Assistant Engineer | Junior Engineer 2 | VCH/001124/2021-2022 | 710/PFMS | 30/03/2022 | 0 | OTHERS | 17.48 | 0 | 0
3202 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery and installation of submersible pumping machinery along with other allied electro-mechanical works voltage stabilizer etc. Augmentation to accommodate FHTC at for newly sunk TW (TW No. - IV) at Thanarpara water supply scheme, Karimpur II Block, Nadia under E.M.D. PHE Dte. NIET No.- 25 of EE/EMD of 2022-23 (Sl. No.- 21) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000731/2022-2023 | 6805/EMD | 21/12/2022 | 30 | SMILE | 8.71 | 8.71 | 0
3203 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Manoharpur ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/003362/2023-2024 | 865/EMD | 14/03/2024 | 30 | CINZANO | 22.25 | 0 | 85
3204 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with Nadia Arsenic Civil Division-II, P.H.E. Dte. (From 01/04/2024 to 30/06/2024) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000001/2024-2025 | 78/AE-II/NACD-II | 01/04/2024 | 91 | TARUN KUMAR BHATTACHARYA | 1.24 | 0 | 0
3205 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000001/2025-2026 | 428/NACD-II | 07/04/2025 | 180 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 30
3206 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Executive Engineer, of Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,WestBengal (From 01/04/2024 to 30/06/2024) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000003/2024-2025 | 504/NACD-II | 01/04/2024 | 91 | TARUN KUMAR BHATTACHARYA | 1.24 | 0 | 0
3207 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 1 nos. of 300 mm X 200 mm dia, 180 mtr deep Tube Well (as replacement of old defunct T/W) by Direct Rotary Method with UPVC pipe (CD) & strainer, (300 mm dia 36 mtr. long housing pipe &200 mm dia 30 mtr. long strainer) at Thanapara 3rd Tube Well site and 3rd Pump House site and also Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) under Thanapara (Vill.- Gourbhanga) at Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000016/2023-2024 | 546/NACD-II | 11/05/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 40.55 | 40.4 | 100
3208 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Thanapara H/W site with Pathway ,Plastering ,Pump House Painting, Flooring,, PVC Water tank other allied works Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000022/2024-2025 | 145./AE-II/NACD-II | 11/06/2024 | 30 | SOURAV & CO. | 2.91 | 0 | 0
3209 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000028/2022-2023 | 202/NACD-II | 01/04/2022 | 90 | JOY HIND TUBEWELLS | 151.4 | 151.35 | 100
3210 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Wall writing work in various Gram Panchayats in Karimpur-II Block at Thanapara PWSS under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000045/2024-2025 | 756/AE-I/NACD-II | 19/06/2024 | 15 | IMAGIN | 0.93 | 0 | 100
3211 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Piling work in between 4th Pump House to 3rd Pump House pond site for rising main pipe line protection at Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000050/2024-2025 | 141/AE-II/NACD-II | 11/06/2024 | 30 | VAI ENTERPRISE | 1.26 | 0 | 100
3212 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Thanapara 2nd & 4th pump house site with Reinforced Barbed Tape, Pathway, Plaster and other allied works Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000051/2024-2025 | 160/AE-II/NACD-II | 14/06/2024 | 30 | TAPAN SAHA | 2.61 | 0 | 100
3213 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000052/2022-2023 | 222/NACD-II | 05/04/2022 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 36.28 | 57.15 | 100
3214 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000054/2022-2023 | 224/NACD-II | 05/04/2022 | 90 | MALLICK ENTERPRISE | 154.65 | 0 | 100
3215 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Executive Engineer, under Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, Pincode:- 741101,West Bengal. (From 01/07/2024 to 30/06/2025) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000058/2024-2025 | 791/AE-I/NACD-II | 01/07/2024 | 365 | TARUN KUMAR BHATTACHARYA | 4.98 | 0 | 0
3216 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with nadia Arsenic Civil Division-II, P.H.E. Dte.under Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, Pincode:- 741101,West Bengal. (From 01/07/2024 to 30/06/2025) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000063/2024-2025 | 204/AE-II/NACD-II | 01/07/2024 | 365 | TARUN KUMAR BHATTACHARYA | 4.98 | 0 | 0
3217 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Karimpur-II Block of Nadia District through Jadavpur University. (Name of PWSS Thanapara) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000086/2023-2024 | 911/NACD-II | 29/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
3218 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of 2nd site locations under Karimpur-II Block of Nadia District through Jadavpur University. (Name of Scheme Thanapara) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000118/2024-2025 | 971/NACD-II | 19/07/2024 | 21 | JADAVPUR UNIVERSITY | 4.78 | 0 | 100
3219 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of 3rd site locations under Karimpur-II Block of Nadia District through Jadavpur University. (Name of Scheme Thanapara) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000119/2024-2025 | 972/NACD-II | 19/07/2024 | 21 | JADAVPUR UNIVERSITY | 4.78 | 0 | 100
3220 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Jungle cutting and Earthwork in filling at Maheshpur, Maitari and Thanarapara Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000120/2024-2025 | 818/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.76 | 0 | 100
3221 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with nadia Arsenic Civil Division-II, P.H.E. Dte. (From 01/07/2023 to 31/03/2024) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000132/2023-2024 | 202/1/AE-II/NACD-II | 30/06/2023 | 275 | TARUN KUMAR BHATTACHARYA | 3.74 | 0 | 30
3222 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 3 nos. Tube Well at H/W site ,2nd and 3rd T/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-III & Manoharpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000136/2024-2025 | 1047/NACD-II | 07/08/2024 | 90 | B.M. ENGINEERING & CONSTRUCTION | 34.68 | 0 | 100
3223 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000142/2023-2024 | 1379/NACD-II | 11/12/2023 | 541 | M.R. CONSTRUCTION | 68.49 | 0 | 50
3224 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Thanapara Zone-II Water Supply Scheme in Karimpur-II Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000147/2024-2025 | 249/AE-II/NACD-II | 31/07/2024 | 15 | B.M. ENGINEERING & CONSTRUCTION | 0.97 | 0 | 0
3225 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.GrF.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Thanarpara PWSS in Karimpur-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000154/2023-2024 | 519/AE-I/NACD-II | 18/12/2023 | 7 | MAKALI ENGINEERING CORPORATION | 0.58 | 0 | 100
3226 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Karimpur-II Block of Nadia District through Jadavpur University. (Name of PWSS Thanapara) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000165/2023-2024 | 1279/NACD-II | 14/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
3227 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000194/2022-2023 | 71/AE-II/NACD-II | 28/06/2022 | 365 | TARUN KUMAR BHATTACHARYA | 2.07 | 2.87 | 50
3228 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement at Thanapara Zone-III Tube Well No-2 area according to departmental drawing (Size 3.60 mtr x 3.00 mtr ) under Thanapara Zone-III Piped water supply scheme in Karimpur-II Block under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000195/2024-2025 | 309AE-II/NACD-II | 06/09/2024 | 90 | MUKHERJEE CONSTRUCTION | 4.18 | 0 | 100
3229 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD and allied works at OHR site under Thanarpara Piped Water Supply Scheme in Karimpur-II Block under Nadia Arsenic Civil Division-II, P.H.E Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000197/2023-2024 | 87/NACD-II | 18/01/2024 | 318 | B.M. ENGINEERING & CONSTRUCTION | 24.4 | 0 | 85
3230 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement at Thanapara Zone-III Tube Well No-3 area according to departmental drawing (Size 3.60 mtr x 3.00 mtr ) under Thanapara Zone-III Piped water supply scheme in Karimpur-II Block under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000210/2024-2025 | 310AE-II/NACD-II | 06/09/2024 | 90 | NISHITH BANERJEE | 4.18 | 0 | 100
3231 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repairing and Renovation of I.E Plant at Thanapara Water Supply Scheme - Capacity - 166 cum/hr, Block -Karimpur-II under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000212/2022-2023 | 747/NACD-II | 29/09/2022 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 9.69 | 9.65 | 100
3232 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of Tube Well at H/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass Strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-II & Manoharpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000213/2024-2025 | 92/NACD-II | 20/01/2025 | 45 | JOY HIND TUBEWELLS | 11.61 | 0 | 100
3233 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Thanapara Head Work site in Karimpur-II Block with Overhead Reservoir with Plaster, Painting and other allied works Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000215/2024-2025 | 1309/NACD-II | 20/09/2024 | 30 | S.B. CONSTRUCTION | 6.41 | 0 | 100
3234 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Supply of CIDF Sluice, Non return valves and DI Mechanical collar Vavle for relaying of rising main of Thanapara Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000223/2021-2022 | 213/AE-I/NACD-II | 20/01/2022 | 7 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 4.98 | 100
3235 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000253/2021-2022 | 116/NACD-II | 15/02/2022 | 90 | JOY HIND TUBEWELLS | 153.21 | 153.21 | 100
3236 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara ( Vill-Thanapara, Kalopur, Subhrajpur, Char Gourbhanga) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000263/2022-2023 | 1018/NACD-II | 29/11/2022 | 60 | A.P. POWER & CONCRETE | 31.49 | 28.56 | 85
3237 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000274/2022-2023 | 1129/NACD-II | 16/12/2022 | 60 | MUKHERJEE CONSTRUCTION | 17.21 | 17.2 | 95
3238 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement at Thanapara Tube Well No-4 area according to departmental drawing (Size 3.60 mtr x 3.00 mtr ) of Thanapara water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000294/2021-2022 | 58/AE-II/NACD-II | 23/02/2022 | 45 | M/S SANTOSHI MAA ENTERPRISE | 3.82 | 2.82 | 100
3239 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work Order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Falia) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000296/2021-2022 | 112/NACD-II | 11/02/2022 | 90 | MONDAL ENTERPRISE | 45.84 | 45.8 | 100
3240 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Saguna) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000301/2021-2022 | 03./NACD-II | 03/01/2022 | 45 | M/S SHILL & CO. | 88.07 | 88.01 | 100
3241 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-III Water Supply Scheme 3rd Tube Well site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000312/2024-2025 | 1503/NACD-II | 21/11/2024 | 268 | PARTHA DAS | 6.01 | 0 | 100
3242 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mobarakpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000315/2021-2022 | 173/NACD-II | 21/03/2022 | 90 | PATHIK PABAN NANDI | 98.64 | 0 | 100
3243 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 75 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Thanarpara Zone-III Water Supply Scheme in Karimpur-II block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000322/2024-2025 | 1207/NACD-II | 04/09/2024 | 540 | SINGHA ROY & CO. | 215.53 | 0 | 0
3244 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Construction of 50 m3/hr capacity IEP at Thanarpara Zone-II PWSS in Karimpur-II Block under Nadia Arsenic Civil Division-II, P.H.E. Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000337/2023-2024 | 432/NACD-II | 15/03/2024 | 671 | EVEREST CONSULTANT SERVICES. | 23.11 | 0 | 50
3245 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-III & Taranipur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000338/2024-2025 | 1398/NACD-II | 22/10/2024 | 90 | PAPAN ROY | 16.66 | 0 | 60
3246 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) , Jitpur , Taranipur & Dhopahat W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000346/2024-2025 | 1627/NACD-II | 19/12/2024 | 540 | M.R. CONSTRUCTION | 117.87 | 0 | 40
3247 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000350/2022-2023 | 150/NACD-II | 17/01/2023 | 20 | DUTTA CONSTRUCTION | 2.68 | 0 | 100
3248 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From 01/03/2023 to 31/03/2023) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000358/2022-2023 | 252/NACD-II | 27/02/2023 | 31 | SAJAL SAHA | 0.42 | 0.4 | 100
3249 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with nadia Arsenic Civil Division-II, P.H.E. Dte. (From 01/07/2023 to 31/03/2024) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000358/2023-2024 | 202/1/AE-II/NACD-II | 30/06/2023 | 275 | TARUN KUMAR BHATTACHARYA | 3.74 | 0 | 0
3250 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-I (Vill-Natidanga, Char Adityapur, Thanarpara) and Thanarpara Zone-II (Vill- Sobharajpur, Saguna) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000372/2023-2024 | 1281/NACD-II | 16/11/2023 | 90 | SUJATA CONSTRUCTION | 270.68 | 0 | 0
3251 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pump House cum Chlorine room with sanitary arrangement at Thanarpara Zone-III Headwork site according to departmental drawing at Thanarpara Zone-III Piped Water Supply Scheme under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000374/2024-2025 | 04/NACD-II | 02/01/2025 | 90 | SOURAV & CO. | 6.14 | 0 | 100
3252 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Executive Engineer, of Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000394/2022-2023 | 412/NACD-II | 30/03/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.98 | 0 | 20
3253 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Executive Engineer, of Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000398/2022-2023 | 412./NACD-II | 30/03/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.98 | 0 | 0
3254 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From 01/03/2022 to 28/02/2023) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000402/2021-2022 | 55//AE-II/NACD-II | 17/02/2022 | 365 | SAJAL SAHA | 4.98 | 1.39 | 100
3255 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Urgent piling work for protection of hydraulic main in between 4th Pump House to 3rd Pump House pond site at Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000404/2024-2025 | 411/AE-II/NACD-II | 31/01/2025 | 45 | VAI ENTERPRISE | 0.99 | 0 | 100
3256 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of Tube Well at H/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass Strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-II & Jayrampur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000408/2024-2025 | 149/NACD-II | 04/02/2025 | 45 | MANISHIKA CONSTRUCTION | 11.56 | 0 | 0
3257 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pump House cum Chlorine room with sanitary arrangement at Thanarpara Zone-II Headwork site according to departmental drawing at Thanarpara Zone-II & Dhopahat Piped Water Supply Scheme under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000465/2024-2025 | 403_NACD-II | 26/03/2025 | 150 | ROY CONSTRUCTION | 6.14 | 0 | 100
3258 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | RTOR000001/2024-2025 | 983/NACD-II | 23/07/2024 | 0 | Resource Division | 16.39 | 0 | 0
3259 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | RTOR000034/2022-2023 | 372/NACD-II | 24/03/2023 | 0 | Resource Division | 12.32 | 0 | 0
3260 | Nadia Division | Kalyani Sub-Division I | Renovation of AIRP (Gravity Type) of capacity 45 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Uttar Tajpur PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000010/2023-2024 | 1806 / ND | 24/04/2023 | 90 | APURBA MANDAL | 85.67 | 0 | 60
3261 | Nadia Division | Kalyani Sub-Division I | Repairing and renovation of pump house, extension of boundary wall , & construction of drain with other allied works at Uttar tajpur pump house no: I under Uttar tajpur W/S , Karimpur -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000113/2022-2023 | 678/Kly SD-I | 26/07/2022 | 30 | S.M. ENTERPRISE | 4.83 | 4.83 | 100
3262 | Nadia Division | Kalyani Sub-Division I | Repairing and renovation of pump house, Dismantling of boundary wall & re-construction , & construction of bath room with other allied works at Uttar tajpur pump house no: II under Uttar tajpur W/S, Karimpur -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000114/2022-2023 | 679/ Kly SD-I | 26/07/2022 | 30 | K.K. MARKETING | 4.99 | 4.99 | 100
3263 | Nadia Division | Kalyani Sub-Division I | Interconnection of newly sunk tubewell at 2nd Pump House including cleaning of rising main and delivery pipeline of Utter Tajpur Water Supply Scheme, Karimpur-I Block, Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000161/2022-2023 | 873/Kly SD-I | 20/09/2022 | 15 | M/S SHAIKH ENTERPRISE | 1 | 1 | 100
3264 | Nadia Division | Kalyani Sub-Division I | Laying of additional pipe lines and allied works to increase the functionality in Brojonathpur, Gandhina villages under Karimpur-I Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000328/2025-2026 | 4685/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 46.3 | 0 | 40
3265 | Nadia Division | Kalyani Sub-Division I | Providing FHTC including Laying Distribution System in connection with J.J.M. Work under village Madhugari to cover up left out portion under Karimpur-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000423/2024-2025 | 7165/ND | 10/12/2024 | 300 | S.S. ENTERPRISE | 58.08 | 0 | 65
3266 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System including specials, valves & pipe carrying structure all complete based on actual Estimate & Providing FHTC for Uttar Tajpur water supply scheme in Nadia District under Nadia Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000730/2021-2022 | 1246/ND | 16/03/2022 | 90 | M/S MALLICK ENTERPRISE | 167.79 | 167.77 | 100
3267 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000107/2021-2022 | 1029/ND | 03/03/2022 | 0 | Resource Division | 4.4 | 0 | 0
3268 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000124/2021-2022 | 1252/ND | 16/03/2022 | 0 | Resource Division | 1.18 | 0 | 0
3269 | Nadia Division | Kalyani Sub-Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | VCH/001065/2021-2022 | 623/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.13 | 0 | 0
3270 | Central Drilling | Kalyani Sub-Division I | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000075/2022-2023 | 285/CMSD-II(D) | 01/06/2022 | 15 | OSMAN SEKH | 2.07 | 1.63 | 0
3271 | Central Drilling | Kalyani Sub-Division I | PROVIDING 200 MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT FAZILNAGAR W/S SCHEME (REPLACEMENT TW-III) KARIMPUR-II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000076/2022-2023 | 278/CMSD-II(D) | 01/06/2022 | 15 | OSMAN SEKH | 4.44 | 0.79 | 0
3272 | Central Drilling | Kalyani Sub-Division I | PROVIDING 300MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT FAZILNAGAR P/W SCHEME (REPLACEMENT TW-III), KARIMPUR -II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000077/2022-2023 | 279/CMSD-II(D) | 01/06/2022 | 15 | OSMAN SEKH | 4.39 | 4.05 | 0
3273 | Central Drilling | Kalyani Sub-Division I | PROVIDING DRILLING CREWS & OTHER MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MMX200MMX250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR FAZILNAGAR W/S SCHEME (REPLACEMENT TW-III), KARIMPUR-II BLOCK UNDER NADIA DISTRICT, CMSD-II(D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000078/2022-2023 | 276/CMSD-II(D) | 01/06/2022 | 35213 | OSMAN SEKH | 3.52 | 1.85 | 0
3274 | Central Drilling | Kalyani Sub-Division I | Continuation for hiring of diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the DIC, CMSD-II(D), CDD PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000304/2022-2023 | 549/CMSD-II(D) | 19/12/2022 | 7 | ASHUTOSH PAL | 0.28 | 0.28 | 0
3275 | Central Drilling | Kalyani Sub-Division I | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 250 mtrs. Depth) by utilising Departmental machineries for Kharagpur SG Hospital W/S Scheme, under Paschim Midnapore District, CDD PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000434/2022-2023 | 1350/CDD | 24/11/2022 | 30 | PADMA ENGINEERING & CO. | 18.38 | 3.67 | 0
3276 | Eastern Mechanical | Kalyani Sub-Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I & II, under Uttartajpur ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. [SM/09812] | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000338/2024-2025 | 2153/EMD | 30/08/2024 | 366 | RAJ & ENTERPRISE | 14.54 | 0 | 80
3277 | Eastern Mechanical | Kalyani Sub-Division I | Supply delivery & installation of submersible pumping machinery and allied works for newly sunk Tube well (replacement) at PH No. II in connection with ongoing FHTC works by Civil wing under Uttar Tajpur PWSS Dist. Nadia | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/001930/2022-2023 | 196/EMSD II | 29/07/2022 | 243 | T.N. BANERJEE | 3 | 3 | 100
3278 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KHANJIPUR , Block-Tehatta I and TALDAH , Block-Krishnaganj, Bahirgachhi (Z-II) Block-Chapra, Bagakhali (Z-II) W/S Scheme, Block-Tehatta I Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001777/2022-2023 | 1122/EMD | 16/03/2023 | 30 | ANJAN ENTERPRISE | 46.98 | 0 | 80
3279 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Bagakhali Zone-II H/W site with Earth work in filling in foundation trenches or plinth with good earth . Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000013/2024-2025 | 134/AE-II/NACD-II | 11/06/2024 | 30 | SURAJIT KUMAR GHOSH | 4.85 | 0 | 100
3280 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Relaying of D.I. Pipeline by replacing the damaged old UPVC Pipe for rising main from 1st pump house to 2nd pump house at Bagakhali Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000019/2024-2025 | 142/AE-II/NACD-II | 11/06/2024 | 30 | SANJIB BISWAS | 4.17 | 0 | 100
3281 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-I (vILL- Sahapur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000053/2022-2023 | 223/NACD-II | 05/04/2022 | 90 | NANDY ENTERPRISES | 20.12 | 0 | 100
3282 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Bagakhali Zone-II) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000103/2023-2024 | 1148/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100
3283 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000128/2021-2022 | 863/NACD-II | 08/11/2021 | 45 | IJABUL SEKH | 60.77 | 60.44 | 100
3284 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earth work in filling in ditches at Bagakhali Zone-II H/W Site at Bagakhali Zone-II Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000129/2022-2023 | 65/AE-II/NACD-II | 28/06/2022 | 15 | TARUN GHOSH | 0.56 | 0.56 | 100
3285 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Bagakhali Zone-II, (Block -Tehatta-I) piped water supply schemes | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000144/2021-2022 | 143/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.57 | 2.57 | 100
3286 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well (as replacement of old defunct T/W) by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Bagakhali Zone-II Head Work site under Bagakhali Zone-II Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000196/2023-2024 | 83/NACD-II | 16/01/2024 | 45 | SANDIP BISWAS | 10.4 | 0 | 100
3287 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bagakhali Zone-II W/S Scheme of Tehatta-I Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000215/2023-2024 | 615/AE-I/NACD-II | 02/02/2024 | 15 | LAKSHMI CONSTRUCTION | 0.79 | 0 | 100
3288 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Bagakhali Zone - II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000230/2020-2021 | 283/NACD-II | 23/02/2021 | 21 | BIDYUT KUMAR | 19.4 | 0 | 100
3289 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Bagakhali Zone-II Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000255/2022-2023 | 1010/NACD-II | 29/11/2022 | 60 | GOUTAM HALDER | 14.43 | 14.41 | 90
3290 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Bagakhali Zone-II 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000270/2021-2022 | 39/AE-II/NACD-II | 17/02/2022 | 30 | SOURAV & CO. | 3.13 | 3.09 | 100
3291 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Bagakhali Z-II Water Supply Scheme of capacity 30 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000295/2023-2024 | 384/NACD-II | 12/03/2024 | 90 | SHYAMAL SHIL | 94.56 | 0 | 0
3292 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well ( as replacement of old defunct T/W) by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Bagakhali Zone-II 2nd Tubewell site under Bagakhali Zone-II Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000310/2023-2024 | 344/NACD-II | 06/03/2024 | 45 | SHYAMAL SHIL | 10.4 | 0 | 100
3293 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Bagakhali Zone-I and Bagakhali Zone-II Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000325/2024-2025 | 1562/NACD-II | 05/12/2024 | 360 | DEBASIS SAMADDAR | 157.57 | 0 | 40
3294 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Bagakhali Zone-II Headwork site in Tehatta-I Block with Overhead reservoir Painting, Plaster and other allied works under Nadia Arsenic Civil Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000390/2024-2025 | 133/NACD-II | 29/01/2025 | 30 | GHOSH ENTERPRISE | 6.18 | 0 | 100
3295 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Relaying of damaged pipe line due to laying of rising main from 1st pump to 2nd pump and also reconnection of FHTC at Bagakhali Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. (Part-A) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000395/2024-2025 | 406/AE-II/NACD-II | 31/01/2025 | 45 | SANJIB BISWAS | 0.99 | 0 | 100
3296 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001768/2022-2023 | 1120/EMD | 16/03/2023 | 30 | B.T. PROJECTS PVT. LTD | 91.82 | 0 | 60
3297 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Bara Naldaha ( Vill- Colonypara, Baranaldaha) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000017/2023-2024 | 547/NACD-II | 11/05/2023 | 60 | SUBHASIS MOJUMDER | 37.82 | 0 | 60
3298 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Barbed wire fencing & painting of Headwork site and 2nd T/W site Boundary wall of Baranaldaha PWSS at Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000033/2024-2025 | 744/AE-I/NACD-II | 18/06/2024 | 30 | A.S.CONSTRUCTION | 4.25 | 0 | 0
3299 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Head Work site and 2nd T/W site of Baranaldaha PWSS at Tehatta-II Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000034/2024-2025 | 745/AE-I/NACD-II | 18/06/2024 | 193 | TAPAN SAHA | 4.69 | 0 | 100
3300 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and renovation of Boundary wall with Grill Gate and Barbed wire fencing and Painting of Pump House, Boundary Wall at HW site of Krishnagar Water Supply Scheme and BaraNaldaha Water Supply Scheme of Tehatta -II Block Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000072/2025-2026 | 111/AE-I/NACD-II | 04/06/2025 | 60 | BASUDEB SAHA | 4.35 | 0 | 0
3301 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary Wall at North & Eastern side with Grill Gate and Barbed wire fencing at 2nd TubeWell site of Krishnagar Water Supply Scheme and Baranaldaha water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000073/2025-2026 | 112/AE-I/NACD-II | 04/06/2025 | 60 | PAPAN ROY | 4.5 | 0 | 0
3302 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary Wall at South & Western side with Grill Gate and Barbed wire fencing at 2nd TubeWell site of Krishnagar water Supply Scheme and Baranaldaha water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000074/2025-2026 | 113/AE-I/NACD-II | 04/06/2025 | 60 | PARTHA DAS | 4.5 | 0 | 0
3303 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work Order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also Bamboo Pilling at Baranaldaha (Vill- Choto Naldaha) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000143/2021-2022 | 825/NACD-II | 25/10/2021 | 45 | M/S ANUBHAB CONSTRUCTION | 60.17 | 60.14 | 100
3304 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Baranaldaha, (Block -Tehatta-II) piped water supply schemes | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000148/2021-2022 | 147/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.87 | 2.87 | 100
3305 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-II Block of Nadia District through Jadavpur University. (Name of PWSS Baranaldaha) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000162/2023-2024 | 1285/NACD-II | 21/11/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 0 | 100
3306 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Damaged pipe line repair due to construction of drain at Baranaldaha W/s Scheme (Vill- Baranaldaha) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000185/2022-2023 | 600/NACD-II | 01/09/2022 | 30 | TAPAN SAHA | 9.7 | 9.62 | 100
3307 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Baranaldaha W/S Scheme in Tehatta-II Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000213/2023-2024 | 611/AE-I/NACD-II | 02/02/2024 | 15 | ECOCARE | 0.92 | 0 | 100
3308 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Baranaldaha (Vill- Kolony para) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000227/2021-2022 | 890/NACD-II | 16/11/2021 | 45 | M/S ANUBHAB CONSTRUCTION | 52.36 | 52.2 | 100
3309 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Bara Naldaha Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000281/2021-2022 | 236/AE-I/NACD-II | 17/02/2022 | 365 | BIPLAB GUHA | 4.84 | 4.83 | 100
3310 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Baranaldah Water Supply Scheme of capacity 67 Cu.m/hr in Tehatta-II Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000324/2023-2024 | 206/NACD-II | 15/02/2024 | 90 | RITE WATER SOLUTION (INDIA) PRIVATE LIMITED | 176.73 | 0 | 0
3311 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Comprehensive augmentation in technical regards including aquifer management with extraction, compliance of Ground water contamination removal as per IS 10500 with subsequent amendments and composite RCC Cum masonry structures at Mouza- Baranaldaha (Habitation - Colony Para) under Baranaldaha Piped Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000335/2024-2025 | 1618/NACD-II | 18/12/2024 | 240 | JOY HIND TUBEWELLS | 52.9 | 0 | 60
3312 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD and allied works at OHR site under Bara Naldaha Piped Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000388/2023-2024 | 145/NACD-II | 06/02/2024 | 45 | M/S S. K. ENTERPRISE | 28.62 | 0 | 100
3313 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repairing of Distribution system of UPVC pipes, bamboo pilling & earth filling at Pashimpara under Baranaldaha Ground water based PWSS under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000398/2021-2022 | 32 /AE-I/NACD-II | 24/06/2021 | 10 | TAPAN SAHA | 2.08 | 2.08 | 100
3314 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000110/2022-2023 | 3528/ND | 05/08/2022 | 90 | M/S NANDY ENTERPRISE | 475.17 | 309.5 | 95
3315 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
3316 | Nadia Division | Ranaghat Sub-Division | Surging of 01(One) nos. 150 x 100mm dia tube well at second tube well site of Anulia water supply scheme under Ranaghat Sub-Division Nadia Division P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000303/2023-2024 | 931/RSD | 14/09/2023 | 7 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 0.55 | 0 | 100
3317 | Nadia Division | Ranaghat Sub-Division | Estimate for Surging of 01(One) nos. 150 x 100mm dia tube well Head works site of Anulia water supply scheme under Ranaghat Sub-Division Nadia Division P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000304/2023-2024 | 932/RSD | 14/09/2023 | 7 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 0.55 | 0 | 100
3318 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Anulia under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000802/2024-2025 | 1410/RSD | 19/11/2024 | 45 | SURJA ENTERPRISE | 2.15 | 0 | 0
3319 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000052/2023-2024 | 2123/ND | 16/05/2023 | 0 | Resource Division | 77.07 | 0 | 0
3320 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000062/2022-2023 | 4331/ND | 29/09/2022 | 0 | Resource Division | 0.06 | 0 | 0
3321 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000096/2022-2023 | 4882/ND | 23/11/2022 | 0 | Resource Division | 73.95 | 0 | 0
3322 | Nadia Division | Ranaghat Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/000334/2022-2023 | 43/PFMS | 09/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.93 | 0 | 0
3323 | Eastern Mechanical | Ranaghat Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works etc. rejuvenation to Accommodate FHTC at Pump House No.I and II under Anulia WS Scheme, Block Ranaghat 1, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-10) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000891/2022-2023 | 159/EMD | 06/01/2023 | 30 | KARTICK BAL | 27.77 | 24.21 | 40
3324 | Nadia Division | Ranaghat Sub-Division | Construction and installation of MANIFOLD and allied works at Head Works site under Monipota Ground Based Water Supply Scheme under Krishnagar-I Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000069/2025-2026 | 2401/ND | 23/05/2025 | 90 | R M TRADING | 11.91 | 0 | 0
3325 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of head work site pump house & allied works of Monipota W/S scheme of Krishnanagar-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000231/2022-2023 | 558/RSD | 30/08/2022 | 600 | ROMI TRADERS | 2.22 | 0 | 80
3326 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation & repair of CWR pump house & allied works of Monipota W/S scheme of Krishnanagar block under Ranaghat Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000232/2022-2023 | 558/A/RSD | 30/08/2022 | 510 | M/S PHANINDRA NATH ROY | 2 | 0 | 85
3327 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Monipota to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000380/2022-2023 | 376/ND | 27/01/2023 | 795 | SUMAN CHAKRABORTY | 196.42 | 120.17 | 100
3328 | Nadia Division | Ranaghat Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Monipota PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 65.00 Cu.m/hr | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000468/2023-2024 | 135/ND | 09/01/2024 | 360 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 74.19 | 0 | 50
3329 | Nadia Division | Ranaghat Sub-Division | Construction of 51m Boundary Wall (2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Monipota PWSS at PH-2 site. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000795/2024-2025 | 85/RSD | 14/01/2025 | 75 | BISHAL CONSTRUCTION | 4.6 | 0 | 0
3330 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Monipota under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000890/2024-2025 | 202/RSD | 06/02/2025 | 45 | SAYANTAN PANDEY | 2.15 | 0 | 70
3331 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000027/2023-2024 | 1874/ND | 26/04/2023 | 0 | Resource Division | 12.46 | 0 | 0
3332 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000076/2023-2024 | 2297/ND | 29/05/2023 | 0 | Resource Division | 10.28 | 0 | 0
3333 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000096/2023-2024 | 2583/ND | 13/06/2023 | 0 | Resource Division | 21.74 | 0 | 0
3334 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000194/2022-2023 | 696/ND | 17/02/2023 | 0 | Resource Division | 21.74 | 0 | 0
3335 | Nadia Division | Ranaghat Sub-Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/000350/2022-2023 | 50/PFMS | 22/06/2022 | 0 | HORIZEN | 2.69 | 0 | 0
3336 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at MONIPOTA W/S Scheme Block- KRISHNAGAR - I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10567 | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000143/2025-2026 | 1144/EMD | 04/06/2025 | 90 | GOENKA ENTERPRISE | 37.8 | 0 | 0
3337 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Monipota ground water based water supply scheme under Block_ Krishnanagar_I Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15135) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001463/2024-2025 | 234/EMD | 06/02/2025 | 30 | M/S.A.K. BANERJEE. | 11.76 | 0 | 0
3338 | Nadia Arsenic Division I | Nadia Arsenic Division I | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Matikumra ii)Duttaphulia Zone-I iii)Duttaphulia Zone-II | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000004/2023-2024 | 166/AE-I/NAD-I | 12/04/2023 | 15 | TECH VISION | 4.84 | 4.84 | 40
3339 | Nadia Arsenic Division I | Nadia Arsenic Division I | Restoration of damages pipelines from Duttaphulia more to BSF camp in Ranaghat- II, Block under Nadia Arsenic Division-I,PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000004/2024-2025 | 142/AE-II/NAD-I | 07/06/2024 | 30 | BUDDHADEV MONDAL | 4.19 | 0 | 100
3340 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC and laying dedicated pipeline for Gangsara & Duttaphulia Village in connection Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme , Under Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. (Sl.05) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000006/2025-2026 | 74/NAD-I | 16/04/2025 | 60 | SHYAMAL SHIL | 94.18 | 0 | 0
3341 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall and pathway Head work site of Duttaphulia Zone- II and Dubli Zone- I water supply Scheme in Ranaghat-II Block in connection with Duttaphulia Zone-I W/S Scheme under JJM under Nadia Arsenic Division-I,P.H.E. Dte. (sl.02) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000019/2025-2026 | 137/NAD-I | 23/04/2025 | 60 | CFS MANAGEMENT PRIVATE LIMITED | 38.99 | 0 | 0
3342 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Duttaphulia Zone-II (Part-I) at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Duttaphulia Zone-I Water SUpply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000030/2022-2023 | 1463/NAD-I | 18/08/2022 | 1123 | APURBA MANDAL | 321.95 | 223.49 | 85
3343 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Duttaphulia Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Duttaphulia Zone-II (Phase-I) under JJM (Sl.no.09) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000037/2023-2024 | 1362 / NAD-I | 12/05/2023 | 15 | DULAL MAJUMDER | 13.03 | 0 | 100
3344 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Duttaphulia Mouza inconnection with Augmentation to accomodate FHTC under JJM for Duttaphulia Zone- II Ground water based piped watrer supply scheme ( Phase- I ) Block- Ranaghat -II Dist- Nadia under Nadia Arsenic Division-I , P.H.E Dte.(Sl.No. 08)" | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000078/2023-2024 | 1384/NAD-I | 16/05/2023 | 30 | MESSRS FREEDOM CONSTRUCTION | 72.08 | 71.49 | 100
3345 | Nadia Arsenic Division I | Nadia Arsenic Division I | Surging of existing Tube Well situated at thr 2nd Tube Well site at Duttaphulia Zone-II Water Supply Scheme in Connection with Jal Jeevan Mission under Hanskhali Block to increase the yield of the Tube Well under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000078/2024-2025 | 201/AE-II/NAD-I | 24/09/2024 | 7 | BUDDHADEV MONDAL | 0.64 | 0 | 100
3346 | Nadia Arsenic Division I | Nadia Arsenic Division I | Surging of existing Tube Well situated at the 5th Tube Well site at Duttaphulia Zone-II Water Supply Scheme in Connection with Jal Jeevan Mission under Hanskhali Block to increase the yield of the Tube Well under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 02) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000079/2024-2025 | 204/AE-II/NAD-I | 24/09/2024 | 7 | M/S DIPAK ENTERPRISE | 0.64 | 0 | 100
3347 | Nadia Arsenic Division I | Nadia Arsenic Division I | Work for revamping / upgradation of the hydraulic parameters at Sahapur Battala, Patikabari, Hatibanda, Uttor Bhayna mouzas in reference to Duttaphulia Zone - II and Bhayna Zone - I water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (SL.01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000216/2024-2025 | 2434/NAD-I | 06/02/2025 | 186 | B.S. ENTERPRISE | 113.05 | 0 | 100
3348 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Duttapulia Zone - II Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000225/2021-2022 | 70/AE-II/NAD-I | 24/02/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 4.67 | 4.67 | 100
3349 | Nadia Arsenic Division I | Nadia Arsenic Division I | Distribution Design for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Duttapulia Zone - II Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000226/2021-2022 | 71/AE-II/NAD-I | 24/02/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 4.8 | 4.8 | 100
3350 | Nadia Arsenic Division I | Nadia Arsenic Division I | Renovation of I E P (225m3/hr.) at Duttaphulia Zone II W/S Scheme under Nadia Arsenic Division - I , PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000230/2023-2024 | 2299/NAD-I | 29/09/2023 | 491 | SATYABRATA CHAKRABORTY | 19.29 | 0 | 100
3351 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | RTOR000007/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 20.94 | 0 | 0
3352 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | RTOR000030/2023-2024 | 68/NAD-I | 16/01/2024 | 0 | Resource Division | 3.72 | 0 | 0
3353 | Eastern Mechanical | Nadia Arsenic Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II , III , IV and V (Zone-II) (Phase-I) under Duttapulia ground water based water supply scheme under Block_ Ranaghat-II Dist. - Nadia under EMD, PHE Dte. (SM/10659) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000643/2024-2025 | 2680/EMD | 20/11/2024 | 222 | S.S.ENTERPRISES | 50.99 | 0 | 0
3354 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Topla Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Topla at Karimpur-II Block by Augmentation of Ground Water based PWSS for Topla Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000098/2025-2026 | 2263/ND | 15/05/2025 | 60 | SOURAV & CO | 23.57 | 0 | 0
3355 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Rising main from First Tube Well, 2nd Tube well with 3rd tube well and Inter-Connection in between Tube wells and OHR including specials and valves and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Topla to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. (SM/11511) | Assistant Engineer | Junior Engineer | ORD/000179/2022-2023 | 4387/ND | 13/10/2022 | 90 | M/S DIPAK ENTERPRISE | 314.83 | 229.19 | 75
3356 | Nadia Division | Tehatta Sub-Division | Renovation of AIRP (Pressure Type) of capacity 93 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Topla PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000213/2023-2024 | 3584/ND | 14/08/2023 | 90 | APURBA MANDAL | 68.26 | 0 | 0
3357 | Nadia Division | Tehatta Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Topla W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000389/2021-2022 | 305/TSD | 24/11/2021 | 30 | HORIZEN | 3.19 | 2.81 | 100
3358 | Nadia Division | Tehatta Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Topla water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000403/2024-2025 | 7126/ND | 09/12/2024 | 270 | MONDAL ENTERPRISE | 34.35 | 0 | 80
3359 | Nadia Division | Tehatta Sub-Division | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Habibpur(PART-II) ii) Madhugari (Phase-II) iii) Krishnaganj (Phase-I) iv) Naserkuli (Zone-I) v) Topla | Assistant Engineer | Junior Engineer | ORD/000439/2022-2023 | 245/ Kly SD-I | 27/02/2023 | 181 | HORIZEN | 4.96 | 3.63 | 100
3360 | Nadia Division | Tehatta Sub-Division | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at 3rd Tube well Site Topla PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000683/2024-2025 | 7481/ND | 23/12/2024 | 30 | ZEST INFRACON | 17.55 | 0 | 0
3361 | Nadia Division | Tehatta Sub-Division | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangement At Tube well No-3 Site and construction of Boundary wall at 3rd Tube Well Site At Topla Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000761/2023-2024 | 1634/ND | 07/03/2024 | 720 | BISWAS ENTERPRISE | 11.78 | 0 | 80
3362 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000056/2023-2024 | 2288/ND | 29/05/2023 | 0 | Resource Division | 18.41 | 0 | 0
3363 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000080/2022-2023 | 4317/ND | 29/09/2022 | 0 | Resource Division | 18.41 | 0 | 0
3364 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000103/2022-2023 | 5102/ND | 08/12/2022 | 0 | Resource Division | 45.9 | 0 | 0
3365 | Central Drilling | Tehatta Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR TOPLA W/S SCH, KARIMPUR-II BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000382/2022-2023 | 1197/CDD | 11/11/2022 | 30 | ASHUTOSH DAS & CO | 10.19 | 7.45 | 0
3366 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISUNRA W/S Scheme, Block-NABADWIP, PALASIPARA W/S Scheme, Block-Tehatta-II AND TOPLA W/S Scheme, Block-Karimpur-II Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No. - 05) | Assistant Engineer | Junior Engineer | ORD/001011/2022-2023 | 499/EMD | 24/01/2023 | 30 | WEST BENGAL ENGINEERING CO. | 90.14 | 6.39 | 15
3367 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 0 | 47
3368 | Nadia Division | Debgram Sub-Division | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000185/2024-2025 | 6095/ND | 19/09/2024 | 240 | UMWELT ENGINEER PVT LTD | 225.66 | 0 | 75
3369 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 7B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000779/2021-2022 | 129/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.82 | 4.81 | 100
3370 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000125/2022-2023 | 106/ND | 05/01/2023 | 0 | Resource Division | 168.02 | 0 | 0
3371 | Nadia Division | Debgram Sub-Division | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000165/2025-2026 | 3260/ND | 10/07/2025 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 5
3372 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
3373 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 50
3374 | Nadia Division | Debgram Sub-Division | Temporary arrangement of Reservoir (Vat), Drinking Water Arrangement, 40 mm Temporary Tubewell and Temporary Latrine at different C.P.M.F. / S.P.F. Camp for the ensuing General Assembly Election 2021 within Kaliganj PS under Debagram Sub-Divn, PHE Dte (Gr-1-Kaliganj karmatirtha Near panighata, newly constructed building) | Assistant Engineer |  | ORD/000523/2020-2021 | 143/DSD | 19/03/2021 | 7 | GHOSH ENTERPRISE | 3.29 | 0 | 100
3375 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 4C of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000794/2021-2022 | 144/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.26 | 4.23 | 100
3376 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000123/2023-2024 | 240/ND | 11/01/2024 | 0 | Resource Division | 9.87 | 0 | 0
3377 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000138/2022-2023 | 97/ND | 05/01/2023 | 0 | Resource Division | 107.24 | 0 | 0
3378 | Eastern Mechanical | Nadia Arsenic Civil Division II | New connection charges for Mrigi PHE II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00226/2022-2023 | 109/PFMS/EMD | 16/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.29 | 0 | 0
3379 | Eastern Mechanical | Nadia Arsenic Civil Division II | New connection charges for Mrigi PHE I | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00228/2022-2023 | 108/PFMS/EMD | 16/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.37 | 0 | 0
3380 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electriciyy bill pay for the new service connection at Migri PHE II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/02155/2022-2023 |  | 03/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.22 | 0 | 0
3381 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electriciyy bill pay for the new service connection at Migri PHE I | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/02156/2022-2023 |  | 03/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.41 | 0 | 0
3382 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill pay for the new service connection at Mrigi PHE II | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/02322/2022-2023 | 151/PFMS/EMD | 13/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.22 | 0 | 0
3383 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill pay for the new service connection at Mrigi PHE I | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/02323/2022-2023 | 152/PFMS/EMD | 13/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.41 | 0 | 0
3384 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Mrigi Piped Water SupplyScheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 20) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000461/2022-2023 | 6265/EMD | 19/11/2022 | 30 | CONCORD ENGINEERING | 41.28 | 0 | 0
3385 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Mrigi water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000010/2022-2023 | 208/NACD-II | 05/04/2022 | 60 | ROY CONSTRUCTION | 5.37 | 5.37 | 100
3386 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Kanainagar and Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000019/2022-2023 | 244/NACD-II | 19/04/2022 | 60 | B.M. ENGINEERING & CONSTRUCTION | 42.4 | 0 | 100
3387 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Mrigi water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000046/2022-2023 | 13/AE-II/NACD-II | 11/04/2022 | 60 | ROY CONSTRUCTION | 2.83 | 2.83 | 100
3388 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Mrigi and adjoining mouzas under Mrigi Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000056/2022-2023 | 284/NACD-II | 11/05/2022 | 90 | CHANDA CONSTRUCTION | 217.71 | 162.98 | 90
3389 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Smoothening of site by land filling of existing undulation by filling the ditches at Mrigi 2nd Tube Well Site for development of land and compaction by hand roller in connection with T/W Sinking at Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte.(Phase-I) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000056/2024-2025 | 165_AE-II/NACD-II | 14/06/2024 | 30 | M/S RAJESH CONSTRUCTION | 0.97 | 0 | 100
3390 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earthwork for protection of the existing structures and hydraulic arrangement in the ongoing Mrigi Public Water Supply Scheme (Phase-II) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000057/2024-2025 | 166/AE-II/NACD-II | 14/06/2024 | 15 | R.M.TRADING | 0.95 | 0 | 100
3391 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Mrigi Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000061/2022-2023 | 22/AE-II/NACD-II | 18/04/2022 | 30 | R.M. TRADING | 3.73 | 1.67 | 85
3392 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Mrigi) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000114/2023-2024 | 1153/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
3393 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earth work in filling in ditches at Mrigi 2nd Tube Well Site for development of land in connection with proposed T/W Sinking & Pump House construction at Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000124/2022-2023 | 60/AE-II/NACD-II | 28/06/2022 | 15 | SURAJIT KUMAR GHOSH | 2.26 | 2.26 | 100
3394 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Smoothening of site by land filling of existing undulation by filling the ditches at Mrigi 2nd Tube Well Site for development of land and compaction by hand roller in connection with T/W Sinking at Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte.(Phase-II) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000146/2024-2025 | 248/AE-II/NACD-II | 31/07/2024 | 15 | R.M.TRADING | 0.95 | 0 | 100
3395 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Mrigi Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000151/2023-2024 | 516/AE-I/NACD-II | 18/12/2023 | 15 | CHANDA CONSTRUCTION | 0.97 | 0 | 100
3396 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Smoothening of site by land filling of existing undulation by filling the ditches at Mrigi 2nd Tube Well Site for development of land and compaction by hand roller in connection with T/W Sinking at Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000153/2023-2024 | 518/AE-I/NACD-II | 18/12/2023 | 15 | R.M. TRADING | 0.96 | 0 | 100
3397 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earthwork for protection of the existing structures and hydraulic arrangement in the ongoing Mrigi Public Water Supply Scheme (Phase-III) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000177/2024-2025 | 291AE-II/NACD-II | 30/08/2024 | 15 | M/S RAJESH CONSTRUCTION | 0.96 | 0 | 100
3398 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Mrigi Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000199/2022-2023 | 628/NACD-II | 06/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.14 | 4.14 | 100
3399 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 34 cum/Hour capacity for Mrigi Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000200/2024-2025 | 1069/NACD-II | 12/08/2024 | 180 | MANGES INDUSTRIAL CORPORATION. | 164.31 | 0 | 0
3400 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Geotechnical protection work to counterbalance the uneven earth pressure in consultation with relevant I.S. Codes in Mrigi Water Supply Scheme in Tehatta -I Block in Nadia District under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000227/2023-2024 | 164/NACD-II | 07/02/2024 | 15 | TARUN GHOSH | 12.36 | 0 | 100
3401 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Mrigi W/s Scheme, Panchdara Abhaynagar W/s Scheme, Paninala W/s Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000300/2021-2022 | 252/AE-I/NACD-II | 25/02/2022 | 15 | PROSENJIT DAS | 2.44 | 2.44 | 100
3402 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Mrigi PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000306/2024-2025 | 358/AE-II/NACD-II | 19/11/2024 | 7 | MAKALI ENGINEERING CORPORATION | 0.93 | 0 | 100
3403 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Mrigi Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000323/2022-2023 | 87/NACD-II | 10/01/2023 | 60 | PRADUT GHOSH | 16.44 | 0 | 85
3404 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Mrigi 2nd Tubewell Site within Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000333/2022-2023 | 126/NACD-II | 11/01/2023 | 60 | GHOSH ENTERPRISE | 9 | 0 | 85
3405 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Mrigi water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000386/2022-2023 | 393/NACD-II | 28/03/2023 | 731 | CHANDA CONSTRUCTION | 113 | 0 | 88
3406 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | RTOR000010/2022-2023 | 402/NACD-II | 04/07/2022 | 0 | Resource Division | 26.26 | 0 | 0
3407 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000241/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
3408 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000347/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
3409 | Nadia Division | Ranaghat Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Bagula Zone-I to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000107/2024-2025 | 4341/ND | 07/08/2024 | 180 | AMIT KUMAR BOSE | 181.56 | 0 | 0
3410 | Nadia Division | Ranaghat Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
3411 | Nadia Division | Ranaghat Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Bagula Zone-I W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000429/2021-2022 | 1049/RSD | 02/12/2021 | 30 | HORIZEN | 3.01 | 2.59 | 100
3412 | Nadia Division | Ranaghat Sub-Division | Construction of 111.60 m Boundary Wall(2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Bagula Zone-I PWSS 1st Tube Well site under Ranaghat Sub -Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000751/2024-2025 | 459/ND | 29/01/2025 | 90 | BUDDHADEV MONDAL | 9.5 | 0 | 0
3413 | Nadia Division | Ranaghat Sub-Division | Construction of 55.0 m Boundary Wall (2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Bagula Zone-I PWSS 2nd Tube Well site. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000794/2024-2025 | 84/RSD | 14/01/2025 | 75 | B P ENTERPRISE | 4.87 | 0 | 0
3414 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000007/2024-2025 | 7563/ND | 27/12/2024 | 0 | Resource Division | 31.61 | 0 | 0
3415 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000019/2023-2024 | 1864/ND | 26/04/2023 | 0 | Resource Division | 58.87 | 0 | 0
3416 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000137/2023-2024 | 255/ND | 11/01/2024 | 0 | Resource Division | 10.78 | 0 | 0
3417 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
3418 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000355/2023-2024 | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 0 | 19
3419 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
3420 | Nadia Division | Debgram Sub-Division | Construction of OHR, staff room, chlorine room, service road, boundary wall and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-VIII / C (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11743]. | Assistant Engineer |  | ORD/000421/2023-2024 | 5369/ND | 04/12/2023 | 730 | KINGS & CO,11/1H/4, PRIYANATH MUKHERJEE ROAD, KOLKATA-700002. | 224.26 | 0 | 1
3421 | Nadia Division | Debgram Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
3422 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 8/C of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000806/2021-2022 | 156/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.85 | 3.81 | 100
3423 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000004/2023-2024 | 1525/ND | 04/04/2023 | 0 | Resource Division | 113.96 | 0 | 0
3424 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000133/2023-2024 | 247/ND | 11/01/2024 | 0 | Resource Division | 10.06 | 0 | 0
3425 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection under Ae, EMSD-III, Taranipur PH_I | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/01871/2023-2024 | BP-108-23-24 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.34 | 0 | 0
3426 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection under Ae, EMSD-III, Taranipur PH_I | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/01872/2023-2024 | BP-107-23-24 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.78 | 0 | 0
3427 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under TARINIPUR W/S Scheme (Block : Tehatta I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000028/2023-2024 | 1607/EMD | 26/04/2023 | 616 | SHIVAM ENTERPRISE | 18.99 | 0 | 70
3428 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at TARINIPUR Piped Water Supply Scheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001119/2023-2024 | 4707/EMD | 04/08/2023 | 30 | HARA PROSAD DAS | 51.92 | 0 | 0
3429 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00021/2023-2024 | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
3430 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00094/2022-2023 | 235/9 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0
3431 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000001/2025-2026 | 428/NACD-II | 07/04/2025 | 180 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 30
3432 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Taranipur Water Supply Scheme in Tehatta-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000046/2023-2024 | 411/AE-I/NACD-II | 08/08/2023 | 15 | B.M. ENGINEERING & CONSTRUCTION | 0.97 | 0 | 100
3433 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Taranipur water supply scheme under Nadia Arsenic Civil Division-II, PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000143/2023-2024 | 1386/NACD-II | 12/12/2023 | 45 | CHINMOY BISWAS | 11.33 | 0 | 100
3434 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Taranipur water supply scheme under Tehatta- I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000228/2023-2024 | 165/NACD-II | 07/02/2024 | 60 | M/S K.P. CONSTRUCTION | 32.46 | 0 | 100
3435 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Tarinipur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000282/2022-2023 | 1137/NACD-II | 16/12/2022 | 30 | AUXILIARY TUBE WELL DRILLERS | 21.03 | 19.17 | 100
3436 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Mobarakpur, Binodnagar & Taranipur Water Supply Scheme of capacity 93 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000282/2023-2024 | 152/NACD-II | 02/02/2024 | 598 | B.M. ENGINEERING & CONSTRUCTION | 241.81 | 0 | 0
3437 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Construction of 50 m3/hr capacity IEP at Taranipur PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000294/2023-2024 | 324/NACD-II | 04/03/2024 | 61 | NEER UDYOG | 23.2 | 0 | 0
3438 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Conversion of IEP to AIRP at Patharghata Water Supply Scheme of capacity 96 Cu.m/hr in Tehatta - I Block under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000295/2024-2025 | 1396/NACD-II | 22/10/2024 | 360 | JOY HIND TUBEWELLS | 258.38 | 0 | 0
3439 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Additional instrumentation with augmentation of backwashing system with appropriate wattage including recirculation in compliance with 12699: 1989 as well as reaffirmation there into for contamination removal of various valent systems at Taranipur Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000323/2024-2025 | 1521/NACD-II | 26/11/2024 | 30 | NEER UDYOG | 31.56 | 0 | 0
3440 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Bagakhali Zone-I and Bagakhali Zone-II Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000325/2024-2025 | 1562/NACD-II | 05/12/2024 | 360 | DEBASIS SAMADDAR | 157.57 | 0 | 40
3441 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-III & Taranipur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000338/2024-2025 | 1398/NACD-II | 22/10/2024 | 90 | PAPAN ROY | 16.66 | 0 | 60
3442 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) , Jitpur , Taranipur & Dhopahat W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000346/2024-2025 | 1627/NACD-II | 19/12/2024 | 540 | M.R. CONSTRUCTION | 117.87 | 0 | 40
3443 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Incorporation of the system of adsorption by Inorganic sustances for multivalent metalloid expulsion for improving potability in coordination with IS 10500 With latest edition at Taranipur Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000378/2024-2025 | 47/NACD-II | 10/01/2025 | 30 | NEER UDYOG | 29.92 | 0 | 0
3444 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Taranipur Water Supply Scheme and other necessary allied works in this connection of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000393/2022-2023 | 402/NACD-II | 28/03/2023 | 904 | B.M. ENGINEERING & CONSTRUCTION | 345.19 | 0 | 43
3445 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000020/2022-2023 | 1090/NACD-II | 09/12/2022 | 0 | Resource Division | 63.84 | 0 | 0
3446 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000026/2022-2023 | 379/NACD-II | 24/03/2023 | 0 | Resource Division | 11.38 | 0 | 0
3447 | Nadia Arsenic Division I |  | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Garapota, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Garapota, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Garapota Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000104/2021-2022 | 1586/NAD-I | 22/12/2021 | 90 | TAPU SAHA | 116 | 115.29 | 100
3448 | Nadia Division | Debgram Sub-Division | Providing Functional Household Tap Connection(FHTC) at Surface Water Based Water Supply Scheme(Northern Sector) Part-II,Zone-VA & VB within NAKASHIPARA BLOCK(PHASE-C) | Assistant Engineer |  | ORD/000326/2021-2022 | 7051/ND | 06/12/2021 | 90 | GHOSH BROTHERS | 179.71 | 154.65 | 100
3449 | Nadia Division | Debgram Sub-Division | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000722/2024-2025 | 7571/ND | 27/12/2024 | 31 | IMAGIN | 34.21 | 0 | 0
3450 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000040/2021-2022 | 455/ND | 31/01/2022 | 0 | Resource Division | 1.49 | 0 | 0
3451 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000083/2022-2023 | 4280/ND | 29/09/2022 | 0 | Resource Division | 24.76 | 0 | 0
3452 | Nadia Division | Ranaghat Sub-Division | Route Survey, Design of Distribution Network and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno for Fulia Township (Zone-III) Water Supply Scheme in Santipur Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000044/2023-2024 | 423/RSD | 08/05/2023 | 15 | HORIZEN | 2.7 | 2.7 | 0
3453 | Nadia Division | Ranaghat Sub-Division | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Fulia Township Zone-III to accommodate FHTC within Santipur block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000096/2024-2025 | 4231/ND | 02/08/2024 | 180 | SATYABRATA CHAKRABORTY | 160.53 | 0 | 0
3454 | Nadia Division | Ranaghat Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme to Accommodate FHTC, Construction & Soil Investigation of 100 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials for FULIA Zone-III of Nadia District under Nadia Division PHE Dte | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000160/2023-2024 | 3222/ND | 26/07/2023 | 1096 | SANJOY BAKSHI, 11,AHIBHUSAN HALDER LANE, SASTITALA.PO-KRISHNAGAR,DIST-NADIA, PIN-741101 | 237.03 | 0 | 51
3455 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
3456 | Nadia Division | Ranaghat Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
3457 | Nadia Division | Ranaghat Sub-Division | Construction of 137.00 mtr long Boundary Wall(2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125 mm thick brick panel wall and 200x300 m tie beam at GL including M.S gate at Fulia Zone-III H/W under Ranaghat Sub-Div , Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000771/2024-2025 | 658/ND | 11/02/2025 | 90 | MUKHERJEE CONSTRUCTION | 11.66 | 0 | 0
3458 | Nadia Division | Ranaghat Sub-Division | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Head work Site At Fulia Zone-III Water Supply Scheme Under Ranaghat Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000775/2024-2025 | 662/ND | 11/02/2025 | 90 | ABHAYANANDA ENTERPRISE | 6.88 | 0 | 100
3459 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000037/2023-2024 | 1885/ND | 26/04/2023 | 0 | Resource Division | 7.4 | 0 | 0
3460 | Central Drilling | Ranaghat Sub-Division | Providing clriiling crew and other allied rvorks for constructioti of Tube Well (300mm X200rnrr X 250 Mtrs. Depth) by utilising Depaftmental Machineries for Fulia Township W/S Scheme (Z- lll, T/W-l),santipur Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000095/2023-2024 | 514/CDD | 01/06/2023 | 611 | S B S ENTERPRISE | 18.88 | 0 | 100
3461 | Eastern Mechanical | Ranaghat Sub-Division | New power connection charges for FULIA Water Supply scheme Z-III , Pump House NO-I (HEAD WORKSITE) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | BILL/02291/2024-2025 | BP-184 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 9.47 | 0 | 0
3462 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of Electro-Mechanical Equipments and allied works for submersible pumping machinery of Pump House No.-I and II (New) for Augumentation Tube Well and Arsenic Removal Plant in connection to Accommodate FHTC under Fulia Town Ship (Zone-III) ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. [SM-13878] | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000342/2024-2025 | 2157/EMD | 30/08/2024 | 30 | PADMA ENGINEERING CO. | 26.83 | 0 | 0
3463 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site of Joypur and Mamjoani Water Supply Scheme in connection with Duttaphulia Zone-I under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000004/2025-2026 | 39/NAD-I | 07/04/2025 | 242 | REAL TIME | 39.28 | 0 | 50
3464 | Nadia Arsenic Division I | Nadia Arsenic Division I | "Work for revamping / upgradation of the hydraulic parameters in distribution network from OHR towards Joypur Pry School in reference to Hijuli and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission.(SI. No. 02) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000005/2025-2026 | 40/NAD-I | 07/04/2025 | 60 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD | 93.13 | 0 | 0
3465 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (86cum/hr ) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Joypur under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte.(Sl.no.07) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000129/2023-2024 | 1886/NAD-I | 11/08/2023 | 30 | APURBA MANDAL | 139.79 | 0 | 32
3466 | Nadia Division | Ranaghat Sub-Division | Continuation for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. Period from 01.07.2023 to 30.09.2023. | Assistant Engineer | Junior Engineer 2 | ORD/000103/2023-2024 | 725/KLYSD-I | 22/06/2023 | 92 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 4.89 | 0 | 100
3467 | Nadia Division | Ranaghat Sub-Division | Renovation of Partly-Gravity & Partly-Pressure Type AIRP of Capacity 25 Cu. M./ Hr. and Construction of Back Wash Chamber for AIRP at Head Work Site at Kamalpur Zone-II Piped water Supply Scheme under Ranaghat Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000544/2022-2023 | 1457/ND | 31/03/2023 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 58.65 | 31.87 | 100
3468 | Nadia Division | Ranaghat Sub-Division | Renovation of Partly-Gravity & Partly-Pressure Type AIRP of Capacity 145 Cu. M./ Hr. and Construction of Back Wash Chamber for AIRP at Head Work Site at Kamalpur Zone-I PWSS under Ranaghat Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000210/2023-2024 | 3583/ND | 14/08/2023 | 521 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 135.06 | 0 | 100
3469 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
3470 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | "Work for revamping / upgradation of the hydraulic parameters in distribution network from OHR towards Joypur Pry School in reference to Hijuli and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission.(SI. No. 02) | Assistant Engineer | Junior Engineer | ORD/000005/2025-2026 | 40/NAD-I | 07/04/2025 | 60 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD | 93.13 | 0 | 0
3471 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Balance work for revamping / upgradation of the hydraulic parameters at Gobindapur Colony and Hijuli mauza in reference to Gobindapur PWSS and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission (Sl. NO. 08) | Assistant Engineer | Junior Engineer | ORD/000051/2025-2026 | 231/NAD-I | 13/05/2025 | 60 | TARUN GHOSH | 89.24 | 0 | 0
3472 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Work revamping / upgradation of the hydraulic parameters at distribution network at the part of Malsadaha, Ulasi, Silberia, Nasra (P) and Hijuli (P) Mouzas in reference to Hijuli and Nasra PWSS under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. NO. 02) | Assistant Engineer | Junior Engineer | ORD/000060/2025-2026 | 359/NAD-I | 09/06/2025 | 90 | M/S DIPAK ENTERPRISE | 246.94 | 0 | 0
3473 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Shifting of Manifold and interconnection between old and new OHR and revamping /upgradation of hydraulic parameter in the distribution network at bhayna (P) paschim harin danga and hijuli part In connection with hijuli PWSS under Nadia Arsenic Division I, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000107/2025-2026 | 721/NAD-I | 29/07/2025 | 60 | TAPU SAHA | 51.24 | 0 | 0
3474 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Revamping / upgardation of hydraulic parameter of distribution network and providing FHTC for Doula, Debipur Chandpur Biraberia Dhantala & Notungram and Hizuli (Part) Village and under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dhantala PWSS & Hizuli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer | Junior Engineer | ORD/000112/2025-2026 | 800/NAD-I | 18/08/2025 | 90 | BIDYUT KUMAR | 182.15 | 0 | 0
3475 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Balance Work for revamping/upgradation of the hydraulic parameters at distribution network at the part of Satpota and Hijuli (P) in connection with Hijuli PWSS under Nadia Arsenic Division-I, PHE Dte. As a part of Jal Jeevan Mission. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000142/2025-2026 | 1044/NAD-I | 25/09/2025 | 90 | NISHITH BANERJEE | 36.07 | 0 | 0
3476 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Preparation of Detailed Project Report (DPR) for Hijuli Water Supply Scheme at Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.04) | Assistant Engineer | Junior Engineer | ORD/000180/2022-2023 | 39 /NAD-I | 17/01/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 14.36 | 14.25 | 100
3477 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/08/2025 to 30/09/2025) | Assistant Engineer | Junior Engineer | ORD/000197/2025-2026 | 144 | 30/07/2025 | 61 | M/S DIPAK ENTERPRISE | 0.29 | 0 | 0
3478 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/08/2024 to 31/01/2025) | Assistant Engineer | Junior Engineer | ORD/000249/2024-2025 | 228/AE-I/NAD-I | 24/07/2024 | 184 | M/S DIPAK ENTERPRISE | 0.86 | 0 | 0
3479 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Rising Main System including specials & valves. & LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE SUPPORTING STRUCTURE, Construction of 300/100/200/200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials , Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 300/100/200/200 m3 Staging Height 20 Mtr, CONSTRUCTION OF BOUNDARY WALL [ H/W Site(160.0 m length), 2nd T/W Site(50.0 m length)], Pump House for H/W Site(5.4 M X 3.60 M),2nd T/W Site(3.60 M X 3.0 M) , Land Development and aliied works with Approach Road (105.0m Length and 3.0m Wide), RESTORATION WORK FOR BITUMINOUS ROAD, Hijuli (Zone-I,II,III & IV) Ground Water Based Piped Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000225/2023-2024 | 2351/NAD-I | 03/10/2023 | 730 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 1541.25 | 0 | 3
3480 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/02/2025 to 31/07/2025) | Assistant Engineer | Junior Engineer | ORD/000287/2024-2025 | 14/AE-I/NAD-I | 30/01/2025 | 181 | M/S DIPAK ENTERPRISE | 0.86 | 0 | 0
3481 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000023/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 31.88 | 0 | 0
3482 | Eastern Mechanical | Eastern Mechanical Sub Division-II | Providing Boundary Illumination with allied works at Hijuli under Block_ Ranaghat-II Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/14243) | Assistant Engineer | Junior Engineer | ORD/000170/2025-2026 | 1168/EMD | 04/06/2025 | 90 | SHRESTHA | 4.34 | 0 | 0
3483 | Nadia Division | Debgram Sub-Division | Filling fine sand over upvc pipeline for road restoration work at nimtala juranpur road(both side of road) in connection with augmentation of surface water based w/s scheme for Arsenic affected areas of Nadia district( Northern sector part-I) under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000003/2024-2025 | 918KlySD-I | 07/06/2024 | 15 | UMWELT ENGINEER PVT LTD | 13.46 | 0 | 100
3484 | Nadia Division | Debgram Sub-Division | Providing Functional Household Tap Connection(FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-III & IX within KALIGANJ BLOCK(Phase-D). | Assistant Engineer |  | ORD/000325/2021-2022 | 7052/ND | 06/12/2021 | 90 | TARUN KUMAR BHATTACHARYA | 180.22 | 168.03 | 0
3485 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000065/2021-2022 | 796/ND | 18/02/2022 | 0 | Resource Division | 16.5 | 0 | 0
3486 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000179/2023-2024 | 314/ND | 15/01/2024 | 0 | Resource Division | 11.76 | 0 | 0
3487 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000180/2023-2024 | 315/ND | 15/01/2024 | 0 | Resource Division | 16.25 | 0 | 0
3488 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000181/2023-2024 | 316/ND | 15/01/2024 | 0 | Resource Division | 7.11 | 0 | 0
3489 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000182/2023-2024 | 317/ND | 15/01/2024 | 0 | Resource Division | 8.18 | 0 | 0
3490 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 80
3491 | Nadia Arsenic Civil Division II | Eastern Mechanical Sub Division-III | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Chak Rudranagar of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer | Junior Engineer | ORD/000024/2023-2024 | 564/NACD-II | 11/05/2023 | 960 | A.K ADHIKARY | 22.6 | 0 | 70
3492 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 80
3493 | Nadia Arsenic Civil Division II | Eastern Mechanical Sub Division-III | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Jayghata of Karimpur- II Block under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer | Junior Engineer | ORD/000028/2023-2024 | 568/NACD-II | 11/05/2023 | 990 | GIYASUDDIN SEKH | 30.27 | 0 | 90
3494 | Nadia Division | Debgram Sub-Division | Gotpara Piped Water Supply in Kaliganj Block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000087/2023-2024 | 3022/ND | 14/07/2023 | 624 | CHOWDHURY & CO. | 78.2 | 0 | 30
3495 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR preparation for Gotpara water supply scheme under Debagram Sub- Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000319/2023-2024 | 319/DSD | 17/08/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.28 | 0 | 100
3496 | Nadia Division | Debgram Sub-Division | Sinking of 1 No. 250mm. X 150mm. Dia 200 Mtr. deep Tube Well by Direct Rotary Rig Method using UPVC pipe having 250 mm Dia 48 Mtr. Long Housing Pipe & 150 mm. Dia Well Pipe & Deep Well Screen Pipe (RDS Strainer) at Gotpara Pipe Water Supply Scheme, at Nakashipara Block under Debagram Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000387/2023-2024 | 5117/ND | 17/11/2023 | 30 | B.M. ENGINEERING & CONSTRUCTION | 11.88 | 0 | 100
3497 | Nadia Division | Debgram Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 10 m3/hr at Gotpara Water Supply Scheme within Nakashipara Block under Debagram Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000790/2023-2024 | 1901/ND | 15/03/2024 | 180 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 132.89 | 0 | 0
3498 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000161/2023-2024 | 276/ND | 11/01/2024 | 0 | Resource Division | 4.29 | 0 | 0
3499 | Eastern Mechanical | Debgram Sub-Division | Quotation for New Connection at PH-I under Goat Para W/S Scheme under EMSD-III,PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01079/2024-2025 | BP-68-24-25 | 15/07/2024 | 0 | WBSEDCL BETHUADAHARI (NORTH) CCC | 9.3 | 0 | 0
3500 | Eastern Mechanical | Debgram Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I under Gotpara ground water based water supply scheme under Block_ Nakashipara Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002819/2023-2024 | 807/EMD | 11/03/2024 | 448 | RMD TRADING | 11.78 | 0 | 90
3501 | Eastern Mechanical | Debgram Sub-Division | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at GOTPARA Piped Water Supply Scheme Block_ Nakashipara Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002821/2023-2024 | 811/EMD | 11/03/2024 | 30 | R.N.S. TRADING | 42.44 | 0 | 0
3502 | Nadia Division | Debgram Sub-Division | Noachar Piped Water Supply in Kaliganj Block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000093/2023-2024 | 3023/ND | 14/07/2023 | 630 | CHOWDHURY & CO. | 64.66 | 30.42 | 100
3503 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR preparation for Noachar water supply scheme under Debagram Sub- Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000320/2023-2024 | 321/DSD | 17/08/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.05 | 0 | 100
3504 | Nadia Division | Debgram Sub-Division | Sinking of 1 No. 250mm. X 150mm. Dia 200 Mtr. deep Tube Well by Direct Rotary Rig Method using UPVC pipe having 250 mm Dia 48 Mtr. Long Housing Pipe & 150 mm. Dia Well Pipe & Deep Well Screen Pipe (RDS Strainer) at Noachar Pipe Water Supply Scheme, at Kaliganj Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000388/2023-2024 | 5118/ND | 17/11/2023 | 30 | B.M. ENGINEERING & CONSTRUCTION | 11.88 | 0 | 100
3505 | Nadia Division | Debgram Sub-Division | Construction of Jhama Bats Road for the approach way to headwork site of Noachar water supply scheme under Kalyani Sub Division I under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000522/2023-2024 | 105/KLYSD-I | 25/01/2024 | 30 | CHOWDHURY & CO. | 4.92 | 0 | 100
3506 | Nadia Division | Debgram Sub-Division | Construction of 10.00 cum/hr capacity Arsenic-Cum-Iron Removal Plant (AIRP) at Noachar PWSS including 3 Months Trial Run & 3 Years O&M under Kaliganj Block under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000738/2023-2024 | 1494/ND | 04/03/2024 | 180 | SATYABRATA CHAKRABORTY | 133.17 | 0 | 0
3507 | Nadia Division | Debgram Sub-Division | Laying distribution system for providing FHTC at Noarchar Mouza in connection with Augmentation of Ground Based Water Supply Scheme at Noachar to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000779/2023-2024 | 1764/ND | 12/03/2024 | 45 | CHOWDHURY & CO. | 9.73 | 0 | 100
3508 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000104/2023-2024 | 3642/ND | 16/08/2023 | 0 | Resource Division | 1.43 | 0 | 0
3509 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000112/2023-2024 | 4222/ND | 19/09/2023 | 0 | Resource Division | 1.64 | 0 | 0
3510 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000160/2023-2024 | 275/ND | 11/01/2024 | 0 | Resource Division | 2.33 | 0 | 0
3511 | Eastern Mechanical | Debgram Sub-Division | Quotation for new service connection at Nayachar water supply scheme. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | BILL/00800/2024-2025 | BP-58-24-25 | 02/07/2024 | 0 | WBSEDCL DAINHAT CCC | 3.13 | 0 | 0
3512 | Eastern Mechanical | Debgram Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I under Noachar ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. [SM/17686] | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000337/2024-2025 | 2152/EMD | 30/08/2024 | 275 | C.M.S. ENGINEERING CONCERN. | 11.49 | 0 | 80
3513 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP (Gravity Type) of capacity 45 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Uttar Tajpur PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000010/2023-2024 | 1806 / ND | 24/04/2023 | 90 | APURBA MANDAL | 85.67 | 0 | 60
3514 | Nadia Division | RWS Nadia Sub-Division | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Uttartajpur PWSS within Karimpur-I Block underTehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000478/2024-2025 | 7264/ND | 13/12/2024 | 45 | GOUTAM DEY | 12.19 | 0 | 0
3515 | Eastern Mechanical | RWS Nadia Sub-Division | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at UTTAR TAJPUR (PHASE-II) Piped Water Supply Scheme, Block:KARIMPUR-II, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/001748/2023-2024 | 6359/EMD | 17/10/2023 | 30 | SANKAR PRASAD DUTTA & CO | 41.45 | 0 | 0
3516 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Semi-Gravity Type) of capacity 34 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Sonda Zone-I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000082/2023-2024 | 2995/ND | 13/07/2023 | 628 | TARUN KUMAR BHATTACHARYA | 62.48 | 0 | 40
3517 | Eastern Mechanical | Krishnanagar Sub-Division | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Sonada Zone-I Piped Water Supply Scheme Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/001750/2023-2024 | 6361/EMD | 17/10/2023 | 30 | A.G ENTERPRISE. | 41.9 | 0 | 0
3518 | Nadia Division | RWS Nadia Sub-Division | Laying of 160 mm dia HDPE pipe line, 75 mm & 125 mm UPVC Pipe line for Augmentation of Rising Main System for distribution pipeline with interconnection along with road restoration at village Dogachhi, Block Karimpur-II under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000017/2025-2026 | 1803/ND | 22/04/2025 | 180 | SUBHASH BOSE | 32.54 | 0 | 51
3519 | Nadia Division | RWS Nadia Sub-Division | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site of Teinpur Zone-III [Phase-II] Ground Based Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000520/2022-2023 | 1219/ND | 21/03/2023 | 60 | JOY HIND TUBEWELL'S | 14.37 | 9.34 | 80
3520 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP and Construction of Backwash chamber for AIRP at Head Work Site at Teinpur Zone-III PWSS under Nadia Division PHE Dte. Capacity- 40.30 cum/hr | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000552/2023-2024 | 782/ND | 05/02/2024 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 83.94 | 0 | 70
3521 | Eastern Mechanical | RWS Nadia Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-III(Phase-II) under Teinpur ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. N.I.E.T No. 20 of EE / EMD of 2023-2024 (2023_PHED_554048_21) | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/001907/2023-2024 | 6787/EMD | 30/11/2023 | 30 | T.D.K. ENTERPRISE | 8.45 | 0 | 0
3522 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Gravity Type) of capacity 95 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at DAKSHIN JHITKAPOTA ZONE I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000086/2023-2024 | 2999/ND | 13/07/2023 | 630 | B.M. ENGINEERING & CONSTRUCTION | 97.4 | 0 | 50
3523 | Eastern Mechanical | Krishnanagar Sub-Division | Supplementary works to completion of ongoing FHTC-related work under Dakshin Jhitkipota (Zone-I) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/001716/2023-2024 | 754/EMSD-II | 09/10/2023 | 10 | SRI KRISHNA NIRMAN | 0.63 | 0 | 100
3524 | Eastern Mechanical | Krishnanagar Sub-Division | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at DAKSHIN JHITKAPOTA ZONE-I (PHASE-II) Piped Water Supply Scheme, Block: Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/001754/2023-2024 | 6365/EMD | 17/10/2023 | 30 | M.S. ENTERPRISE | 53.53 | 0 | 0
3525 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accommodate FHTC under DAKSHIN JHITKIPOTA(Z-1) W/S Scheme, Block-Krishnagar-I, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/001920/2022-2023 | 1176/EMD | 21/03/2023 | 30 | SRI KRISHNA NIRMAN | 14.96 | 13.63 | 99
3526 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Gravity Type) of capacity 58 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Bhanderkhola PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000084/2023-2024 | 2997/ND | 13/07/2023 | 90 | TARUN KUMAR BHATTACHARYA | 87.75 | 0 | 68
3527 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I AND II under Bhandarkhola W/S Scheme, Block KrishnagarI, Dist. Nadia. NIET No. 23 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000885/2022-2023 | 153/EMD | 06/01/2023 | 30 | P.K. ENTERPRISE | 15.11 | 13.41 | 65
3528 | Eastern Mechanical | Krishnanagar Sub-Division | Suplimentary works to completion of ongoing FHTC-related work at BHANDERKHOLA W/S Scheme (Block-Krishnagar-I) PHE Dte.,Dist.-Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001485/2023-2024 | 666/EMSD-II | 05/09/2023 | 15 | P.K. ENTERPRISE | 0.69 | 0 | 100
3529 | Eastern Mechanical | Krishnanagar Sub-Division | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at BHANDAR KHOLA (Phase-II) Piped Water Supply Scheme Block_ KRISHNANAGAR-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001760/2023-2024 | 6371/EMD | 17/10/2023 | 685 | GLACIER ENGINEERING CO. | 47.26 | 0 | 40
3530 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP (Gravity Type) of capacity 104 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at PASCHIM BHATJUNGLA ZONE I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000027/2023-2024 | 1785/ND | 20/04/2023 | 722 | B.M. ENGINEERING & CONSTRUCTION | 120.62 | 64.89 | 70
3531 | Nadia Division | RWS Nadia Sub-Division | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Paschim Bhatjangla Zone-I PWSS within Krishnagar-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000073/2024-2025 | 4073/ND | 26/07/2024 | 625 | SANDIP BISWAS | 148.49 | 0 | 70
3532 | Eastern Mechanical | RWS Nadia Sub-Division | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Paschim Bhatjungla Zone-I (Phase-II) Piped Water Supply Scheme Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/001761/2023-2024 | 6372/EMD | 17/10/2023 | 30 | MAHADEV ENTERPRISE | 53.53 | 0 | 0
3533 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/001771/2022-2023 | 1121/EMD | 16/03/2023 | 30 | M.S. ENTERPRISE | 65.68 | 5.87 | 90
3534 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline at Chandpur Pwss ( Vill- Chandpur, Krishnagar-I) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000018/2023-2024 | 548/NACD-II | 11/05/2023 | 60 | M/S SREE KRISHNA ENTERPRISE. | 7.31 | 7.12 | 100
3535 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Special reparing of damaged distribution pipe line due to construction of drain at Damodakhali and Chandpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000023/2022-2023 | 02/AE-I/NACD-II | 06/04/2022 | 45 | M/S SREE KRISHNA ENTERPRISE. | 5 | 5 | 100
3536 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Krishnagar-I Block of Nadia District through Jadavpur University. (Name of PWSS Chandpur) | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000091/2023-2024 | 1057/NACD-II | 20/09/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100
3537 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chandpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000140/2021-2022 | 856/NACD-II | 08/11/2021 | 45 | M/S ANUBHAB CONSTRUCTION | 71.49 | 71.48 | 100
3538 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Arsenic cum Iron treatment Plant of Chandpur PWSS (Capacity- 30 m3/hr) and ancillary works of Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000198/2023-2024 | 88/NACD-II | 18/01/2024 | 60 | MONDAL PRECISION PRIVATE LIMITED | 79.46 | 0 | 90
3539 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chandpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000228/2021-2022 | 27/NACD-II | 10/01/2022 | 45 | M/S ANUBHAB CONSTRUCTION | 9.28 | 9.28 | 100
3540 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation work at Chandpur Head Work Site & 2nd tube well under Chandpur Piped Water Supply Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000341/2024-2025 | 1056/AE-I/NACD-II | 19/12/2024 | 30 | TOTAN DAS | 4.27 | 0 | 0
3541 | Eastern Mechanical | Nadia Arsenic Civil Division II | Quotation for load enhancement of power supply at PH-I of Nischintapur W/S scheme ,under EMSD-III, PHE Dte., Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/02017/2024-2025 | BP-163-24-25 | 25/11/2024 | 0 | W.B.S.E.D.C.L (TEHATTA CCC) | 4.34 | 0 | 0
3542 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PUTIMARI(Block-Tehatt-I), NISCHINTAPUR(Block-Tehatt-I), W/S Scheme, Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000006/2023-2024 | 1504/EMD | 18/04/2023 | 30 | SRI KRISHNA NIRMAN | 10.69 | 5.24 | 80
3543 | Eastern Mechanical | Nadia Arsenic Civil Division II | Drawal of HT OH power line incld. errection of PCC pole inst. of electrical Transformer & supply of materials under supervision of WBSEDCL for new service connection at PH- II under Nischintapur w/s scheme NACD II under EMD PHE dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000477/2021-2022 | 4426/ EMD | 30/06/2021 | 365 | ABHISEK ENGINEERING CONCERN | 1.08 | 1.08 | 100
3544 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Nischintapur Water Supply Scheme in Tehatta-I Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000061/2023-2024 | 321_1/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.43 | 0 | 100
3545 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Nischintapur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000095/2021-2022 | 733/NACD-II | 13/09/2021 | 45 | USHA CONSTRUCTION | 66.93 | 66.91 | 100
3546 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Reparing of vertical distribution line and also renovation of inside of OHR at Nischintapur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000138/2022-2023 | 454/NACD-II | 14/07/2022 | 30 | A.K ADHIKARY | 4.92 | 4.92 | 100
3547 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Nischintapur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000139/2021-2022 | 866/NACD-II | 08/11/2021 | 45 | TAPU SAHA | 51.28 | 47 | 100
3548 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Nischintapur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000170/2023-2024 | 1299/NACD-II | 29/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 0
3549 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Nischintapur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000171/2023-2024 | 1301/NACD-II | 29/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
3550 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Soak Pit and land development and also concrete road construction for smooth movement within OHR site at Nischintapur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000255/2021-2022 | 36/AE-II/NACD-II | 17/02/2022 | 30 | A.K ADHIKARY | 4.99 | 4.98 | 100
3551 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Nischintapur Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000264/2021-2022 | 49/AE-II/NACD-II | 17/02/2022 | 30 | NAMDAR ALI | 4.56 | 4.54 | 100
3552 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of D.I. Pipeline as rising main from 2nd Tube Well Site to head work site and also construction of column for supporting the pipeline at Nischintapur Water Supply Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000271/2022-2023 | 1082/NACD-II | 09/12/2022 | 30 | SUPER CONSTRUCTION | 7.15 | 0 | 100
3553 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Nischintapur Water Supply Scheme of capacity 62 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000318/2023-2024 | 216/NACD-II | 16/02/2024 | 421 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 207.27 | 0 | 72
3554 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection under AE-III Bhatgachi | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/01861/2023-2024 | BP-101-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.39 | 0 | 0
3555 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service connection for BHATGACHHI w/s scheme p.h No:-1 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000009/2022-2023 | 2867/EMD | 21/07/2022 | 30 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.2 | 0 | 0
3556 | Eastern Mechanical | Nadia Arsenic Civil Division II | NEW SERVICE CONNECTION CHARGES FOR BHATGACHHI W/S SCHEME P.H. NO P.H. NO 1 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000012/2022-2023 | 2870/EMD | 21/07/2022 | 30 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.04 | 0 | 0
3557 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Bhatgachhi W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000096/2022-2023 | 5010/EMD | 03/11/2022 | 760 | R.N.S. TRADING | 10.2 | 0 | 80
3558 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro-mechanical works,Voltage Stabilizar and Automatic Chlorinator ( in connection with Aug.work related to FHTC) at Pump Hose No.I(Headworks) under Bhatgachhi W/S Scheme District of Nadia NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000108/2022-2023 | 5093/EMD | 04/11/2022 | 30 | KUNDU ELECTRICAL ENTERPRISE | 10.11 | 9.17 | 90
3559 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply delivery of PCC Pole M.s materials and Electrical accessories and installation DTR of HTOH line to WBSEDCL for new service connection at PH-I under Bhatgachi W/S Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/002687/2022-2023 | 1231/EMSD-III | 21/10/2022 | 30 | KUNDU ELECTRICAL ENTERPRISE | 4.19 | 4.19 | 10
3560 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service connection bill for BHATGACHHI PIPED WATER SUPPLY SCHEME | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/001928/2022-2023 | BP-2022-23-26 | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.04 | 0 | 0
3561 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service connection bill for BHATGACHHI PIPED WATER SUPPLY SCHEME | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/001929/2022-2023 | BP-2022-23-27 | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.16 | 0 | 0
3562 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Bhatgachhi water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000001/2022-2023 | 209/NACD-II | 05/04/2022 | 60 | PRADIP KUMAR BANIK | 5.38 | 5.32 | 100
3563 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Bhatgachhi and Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000021/2022-2023 | 246/NACD-II | 19/04/2022 | 60 | JOY HIND TUBEWELLS | 41.88 | 0 | 100
3564 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement for Tube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Bhatgachhi water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000031/2022-2023 | 18/AE-I/NACD-II | 13/04/2022 | 60 | PRADIP KUMAR BANIK | 2.83 | 2.81 | 100
3565 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Bhatgachhi Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000036/2022-2023 | 23/AE-I/NACD-II | 13/04/2022 | 60 | SOURAV & CO. | 4.53 | 0 | 90
3566 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction for priliminary work of the approch road at Head Works site of Bhatgachhi Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000040/2023-2024 | 405/AE-I/NACD-II | 08/08/2023 | 15 | SUDHAMAY MAJUMDAR | 0.96 | 0 | 0
3567 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Bhatgachhi and adjoining mouzas under Bhatgachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000074/2022-2023 | 299/NACD-II | 19/05/2022 | 90 | SATYABRATA CHAKRABORTY | 236.84 | 199.25 | 100
3568 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bhatgachhi) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000081/2023-2024 | 887/NACD-II | 18/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
3569 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earthwork in filling in approach road at Bhatgachhi Water Supply Scheme at Bhatgachhi H/W site under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000121/2022-2023 | 112/AE-I/NACD-II | 28/06/2022 | 30 | M/S RAJESH CONSTRUCTION | 4.83 | 4.81 | 100
3570 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Conversion of IEP to AIRP at Balidanga Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block including other works at Bhatgachhi & Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000137/2024-2025 | 1048/NACD-II | 07/08/2024 | 60 | DEBASIS SAMADDAR | 185.55 | 0 | 0
3571 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations new vested land under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bhatgachhi) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000149/2024-2025 | 1068/NACD-II | 12/08/2024 | 21 | JADAVPUR UNIVERSITY | 4.78 | 0 | 100
3572 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Additional Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Bhatgachhi and adjoining mouzas under Bhatgachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000181/2022-2023 | 523/NACD-II | 05/08/2022 | 60 | INVENT ENGINEER'S COOP SOCIETY LTD. | 71.56 | 66.55 | 100
3573 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Bhatgachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000189/2022-2023 | 619/NACD-II | 06/09/2022 | 20 | RAMASISH ENTERPRISE | 4.39 | 4.39 | 100
3574 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 43 cum/Hour capacity for Bhatgachhi Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000191/2024-2025 | 1151/NACD-II | 27/08/2024 | 180 | SINGHA ROY & CO. | 173.86 | 0 | 0
3575 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Bhatgachhi W/s Scheme, Dhopahat W/s Scheme, Hatkhola W/s Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000297/2021-2022 | 249/AE-I/NACD-II | 25/02/2022 | 15 | PROSENJIT DAS | 2.44 | 2.44 | 100
3576 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Bhatgachhi Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000313/2022-2023 | 77/NACD-II | 10/01/2023 | 305 | M/S FREEDOM CONSTRUCTION | 14.78 | 10.57 | 86
3577 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Construction of 100 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir at Head Works site of Tengra Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000325/2023-2024 | 337/NACD-II | 05/03/2024 | 365 | CHATTERJEE CONSTRUCTION | 94.23 | 0 | 0
3578 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Bhatgachhi 2nd Tubwell site within Bhatgachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000327/2022-2023 | 116/NACD-II | 11/01/2023 | 60 | M/S SANTOSHI MAA ENTERPRISE | 5.12 | 4.84 | 85
3579 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Renovation of Arsenic cum Iron treatment Plant of Bahirgachhi Zone-II PWSS (Capacity- 23 m3/hr) and Bhatgachhi PWSS ancillary works of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000361/2023-2024 | 35/NACD-II | 09/01/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.51 | 0 | 80
3580 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Bhatgachhi water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000373/2022-2023 | 355/NACD-II | 22/03/2023 | 366 | SUDHAMAY MAJUMDAR | 116.75 | 0 | 5
3581 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | RTOR000001/2022-2023 | 399/NACD-II | 04/07/2022 | 0 | Resource Division | 51.43 | 0 | 0
3582 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000238/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
3583 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000239/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
3584 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000345/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
3585 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara /Jal Swapna for Zone-I, (Palagachha) Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. Tender No. 219/NAD-I/2020-2021. | Assistant Engineer-II | Junior Engineer-IV | ORD/000172/2020-2021 | 313/NAD-I | 08/02/2021 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 97.1 | 176.58 | 100
3586 | Nadia Division | Debgram Sub-Division | Restoration of T 02 - Bethuadahari to Thegahri Ghat under Package no. WB 14-197. | Assistant Engineer |  | BILL/00449/2024-2025 | 262/PFMS | 26/09/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 2.51 | 0 | 0
3587 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
3588 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000355/2023-2024 | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 0 | 19
3589 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
3590 | Nadia Division | Debgram Sub-Division | Construction of OHR, staff room, chlorine room, service road, repairing of boundary wall and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-VIII / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11742]. | Assistant Engineer |  | ORD/000422/2023-2024 | 5370/ND | 04/12/2023 | 741 | GHOSH CONSTRUCTION | 172.65 | 0 | 10
3591 | Nadia Division | Debgram Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
3592 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 8/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000805/2021-2022 | 155/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.29 | 3.22 | 100
3593 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000003/2023-2024 | 1524/ND | 04/04/2023 | 0 | Resource Division | 66.26 | 0 | 0
3594 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000132/2023-2024 | 245/ND | 11/01/2024 | 0 | Resource Division | 9.65 | 0 | 0
3595 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
3596 | Nadia Division | Debgram Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 900 cum. For Providing FHTC (Functional Household Tap Connection) for Zone -VI/A (NORTHERN SECTOR, PART-II) Water Supply Scheme in Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000263/2023-2024 | 4004/ND | 07/09/2023 | 540 | CHOWDHURY & CO. | 33.53 | 0 | 1
3597 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 50
3598 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 6/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000799/2021-2022 | 149/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.35 | 4.34 | 100
3599 | Nadia Division | Debgram Sub-Division | Additional Survey, Design Drawing & DPR Preparation for ZONE 6/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000800/2021-2022 | 150/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.87 | 0.83 | 98
3600 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000127/2023-2024 | 239/ND | 11/01/2024 | 0 | Resource Division | 3.51 | 0 | 0
3601 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000142/2022-2023 | 99/ND | 05/01/2023 | 0 | Resource Division | 282.19 | 0 | 0
3602 | Nadia Division | Debgram Sub-Division | Restoration of road Chakundi More to Chakundi Ghat. | Assistant Engineer |  | BILL/00510/2024-2025 | 304/PFMS | 02/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 8.17 | 0 | 0
3603 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 225.3 | 47
3604 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
3605 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 4A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000772/2021-2022 | 122/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.82 | 4.74 | 100
3606 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000118/2022-2023 | 73/ND | 05/01/2023 | 0 | Resource Division | 359 | 0 | 0
3607 | Nadia Division | Ranaghat Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Fatepur W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000430/2021-2022 | 1050/RSD | 02/12/2021 | 30 | HORIZEN | 2.74 | 2.59 | 100
3608 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of OHR all complete for augmentation of Ground Water Based Water Supply Scheme for Fatepur to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000447/2022-2023 | 964/ND | 09/03/2023 | 1057 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 175.81 | 37.14 | 92
3609 | Nadia Division | Ranaghat Sub-Division | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Fatepur PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 45.00 Cu.m/hr. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000583/2023-2024 | 839/ND | 06/02/2024 | 455 | ZEOLITE FRESH INDIA | 58.36 | 0 | 60
3610 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000024/2023-2024 | 1875/ND | 26/04/2023 | 0 | Resource Division | 17.01 | 0 | 0
3611 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000086/2023-2024 | 2314/ND | 29/05/2023 | 0 | Resource Division | 3.28 | 0 | 0
3612 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at Fatepur W/S Scheme Block- Hanskhali under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/10428 | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000148/2025-2026 | 1149/EMD | 04/06/2025 | 90 | DEY ENTERPRISE | 33.38 | 0 | 0
3613 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Elangi Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | Assistant Engineer |  | ORD/000061/2021-2022 | 2392/ND | 10/06/2021 | 45 | A.K.ADHIKARY | 8.44 | 16.46 | 100
3614 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Elangi Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer |  | ORD/000110/2021-2022 | 2910/ND | 23/07/2021 | 60 | CHOWDHURY CONSTRUCTION | 36.18 | 30.83 | 100
3615 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Elangi Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer |  | ORD/000111/2021-2022 | 2911/ND | 23/07/2021 | 60 | CHOWDHURY CONSTRUCTION | 36.15 | 30.8 | 100
3616 | Nadia Division | RWS Nadia Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Fulia Township W/S Scheme in Santipur Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000437/2021-2022 | 1057/RSD | 02/12/2021 | 30 | HORIZEN | 3.31 | 3.18 | 0
3617 | Nadia Division | RWS Nadia Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
3618 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000047/2021-2022 | 432/ND | 31/01/2022 | 0 | Resource Division | 0.6 | 0 | 0
3619 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000111/2021-2022 | 1034/ND | 03/03/2022 | 0 | Resource Division | 1.94 | 0 | 0
3620 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-II, within Krishnagar-II & Nabadwip Block (Phase-B, Retrofitting)" | Assistant Engineer |  | ORD/000397/2020-2021 | 773/ND | 10/02/2021 | 90 | M/S S.S ENTERPRISE | 96.42 | 136.86 | 0
3621 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IV, (Uttar Duttapara), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 02) Tender No.- 211/NAD-I/2020-2021. |  |  | ORD/000178/2020-2021 | 282/NAD-I | 03/02/2021 | 90 | MONDAL ENTERPRISE | 93.33 | 184.52 | 100
3622 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur-Krishnapur, Zone-II, Part-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur-Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000004/2021-2022 | 768/NAD-I | 04/05/2021 | 60 | MALI CONSTRUCTION | 34.25 | 67.61 | 100
3623 | Nadia Arsenic Division I |  | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis of mass emission standard like Bharat Stage - III and Higher and purchased on or after 01.05.2008 with diesel / LPG / CNG Engine, non-air-conditioned for official use of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. [For the period of 6 (six) Months] |  |  | ORD/000062/2023-2024 | 0262/AE-I/NAD-I | 31/05/2023 | 183 | MUKHERJEE CONSTRUCTION | 0.88 | 0 | 100
3624 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block ( Phase -A) | Assistant Engineer |  | ORD/000199/2020-2021 | 4088/ND | 31/12/2020 | 90 | M/S ASOKE GHOSH & BROTHER | 96.89 | 5.18 | 100
3625 | Nadia Division | Debgram Sub-Division | Laying of pipeline at Kaliganj Bazar under Kaliganj G.P under Zone -VI of Surface Water Based Water Supply Scheme, Nadia District Northern Sector (Part-I) under Debagram Sub Division P.H.E Dte.(S.I. No - 04.) | Assistant Engineer |  | ORD/000610/2021-2022 | 586/DSD | 31/12/2021 | 30 | AVINABA ENGINEERING CONCERN | 0.49 | 0.47 | 0
3626 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000173/2023-2024 | 308/ND | 15/01/2024 | 0 | Resource Division | 2.02 | 0 | 0
3627 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000174/2023-2024 | 309/ND | 15/01/2024 | 0 | Resource Division | 1.52 | 0 | 0
3628 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000175/2023-2024 | 310/ND | 15/01/2024 | 0 | Resource Division | 5.69 | 0 | 0
3629 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- A) | Assistant Engineer |  | VCH/000064/2021-2022 |  | 12/04/2021 | 0 | M/S ASOKE GHOSH & BROTHER | 30.57 | 0 | 0
3630 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VI within Kaliganj Block (Phase- A) | Assistant Engineer |  | VCH/000145/2022-2023 | 08/PFMS | 26/04/2022 | 0 | M/S ASOKE GHOSH & BROTHER | 49.45 | 0 | 0
3631 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME NORTHERN SECTOR PART-I,ZONE-VI,WITHIN KALIGANJ BLOCK PHASE-A | Assistant Engineer |  | VCH/000207/2021-2022 | 82/PPMS | 15/07/2021 | 0 | M/S ASOKE GHOSH & BROTHER | 30.57 | 0 | 0
3632 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block ( Phase -A) | Assistant Engineer |  | ORD/000280/2020-2021 | 240/ND | 15/01/2021 | 90 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 97 | 92.19 | 0
3633 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-A) | Assistant Engineer |  | VCH/000464/2021-2022 | 276/PFMS | 08/10/2021 | 0 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 47.85 | 0 | 0
3634 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-A) | Assistant Engineer |  | VCH/000925/2021-2022 | 566/PFMS | 25/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.46 | 0 | 0
3635 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 4) tender No. - 215/NAD-I/2020-2021. |  |  | ORD/000177/2020-2021 | 284/NAD-I | 03/02/2021 | 90 | SINGHA ROY & CO. | 97.07 | 191.72 | 100
3636 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-IX within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.1) | Assistant Engineer |  | ORD/000458/2020-2021 | 865/ND | 18/02/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 96.79 | 0 | 0
3637 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000088/2022-2023 | 4304/ND | 29/09/2022 | 0 | Resource Division | 12.27 | 0 | 0
3638 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-IX within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.1) | Assistant Engineer |  | VCH/000750/2021-2022 | 354/PFMS | 08/12/2021 | 0 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 87.39 | 0 | 0
3639 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000355/2023-2024 | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 0 | 19
3640 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block ( Phase -B) in Nadia District under Nadia Division P.H.E. Dte. SL.No.2 | Assistant Engineer |  | ORD/000478/2020-2021 | 890/ND | 19/02/2021 | 90 | ORIENT CONSTRICTION | 96.79 | 26.67 | 0
3641 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000087/2022-2023 | 4274/ND | 29/09/2022 | 0 | Resource Division | 12.5 | 0 | 0
3642 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000478/2021-2022 |  | 04/10/2021 | 0 | ORIENT CONSTRUCTION | 62.5 | 0 | 0
3643 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000614/2021-2022 | 291/PFMS | 08/10/2021 | 0 | ORIENT CONSTRUCTION | 62.5 | 0 | 0
3644 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000938/2021-2022 | 489PFMS | 03/02/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 0.43 | 0 | 0
3645 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000939/2021-2022 | 491/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.71 | 0 | 0
3646 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000014/2021-2022 | 2052/ND | 13/05/2021 | 60 | H I ENTERPRISE | 42.6 | 65.58 | 100
3647 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000015/2021-2022 | 2053/ND | 13/05/2021 | 45 | SREEMA ENTERPRISE | 9.72 | 2.82 | 0
3648 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000109/2021-2022 | 2909/ND | 23/07/2021 | 75 | AMARENDRANATH PANDEY | 40.18 | 28.87 | 0
3649 | Nadia Division | RWS Nadia Sub-Division | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.10.2023 to 30.11.2023 | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000414/2023-2024 | 1034/KLYSD-I | 29/09/2023 | 30 | SUMAN CHAKRABORTY | 4.89 | 0 | 100
3650 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Krishnanagar - I Block | RTOR000115/2021-2022 | 1028/ND | 03/03/2022 | 0 | Resource Division | 10.98 | 0 | 0
3651 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-II Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | Assistant Engineer | Junior Engineer Krishnanagar - I Block | VCH/000489/2021-2022 | 284/PFMS | 08/10/2021 | 0 | SREEMA ENTERPRISE | 6.5 | 0 | 0
3652 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VII, (Kumarpur), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. Tender No.- 202/NAD-I/2020-2021. |  |  | ORD/000171/2020-2021 | 156/NAD-I | 25/01/2021 | 60 | TAPU SAHA | 84.28 | 165.46 | 100
3653 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Sonda (Zone-II) W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting) | Assistant Engineer |  | ORD/000214/2020-2021 | 4041/ND | 30/12/2020 | 60 | BIDYUT KUMAR | 20.48 | 0 | 0
3654 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000093/2021-2022 | 790/ND | 18/02/2022 | 0 | Resource Division | 0.3 | 0 | 0
3655 | Nadia Division | Krishnanagar Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT SONDA Z-1 | Assistant Engineer |  | VCH/001063/2020-2021 | 459/DW | 30/03/2021 | 0 | BIDYUT KUMAR | 17.23 | 0 | 0
3656 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Sonda (Zone-I) W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting). | Assistant Engineer |  | ORD/000236/2020-2021 | 47/ND | 06/01/2021 | 90 | TARUN KUMAR BHATTACHARYA | 93.83 | 65.53 | 0
3657 | Nadia Division | Krishnanagar Sub-Division | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.10.2023 to 30.11.2023 | Assistant Engineer |  | ORD/000414/2023-2024 | 1034/KLYSD-I | 29/09/2023 | 30 | SUMAN CHAKRABORTY | 4.89 | 0 | 100
3658 | Nadia Division | Krishnanagar Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
3659 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000088/2021-2022 | 811/ND | 18/02/2022 | 0 | Resource Division | 1.19 | 0 | 0
3660 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VII within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.6) | Assistant Engineer |  | ORD/000462/2020-2021 | 869/ND | 18/02/2021 | 90 | ALOKE ENTERPRISE | 97.09 | 81.15 | 0
3661 | Nadia Division | Debgram Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
3662 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Taldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000066/2020-2021 | 08/NACD-II | 05/01/2021 | 90 | SINGHA ROY & CO. | 61.3 | 60.04 | 0
3663 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Zone-V, (Purba Bishnupur) Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl. NO. 04) Tender No. 218/NAD-I/2020-2021. | Assistant Engineer-II | Junior Engineer-IV | ORD/000170/2020-2021 | 311/NAD-I | 08/02/2021 | 90 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 97.1 | 165.71 | 100
3664 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Purba Bishnupur Zone -V of Surface Water Based PWSS for Chakdah Part Water Supply Scheme under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte.( Sl.no. 06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000283/2022-2023 | 1473/NAD-I | 22/08/2022 | 60 | APURBA MANDAL | 1.77 | 1.55 | 0
3665 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bansberia (Vill-Bansberia) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000041/2020-2021 | 1188/NACD-II | 13/11/2020 | 25 | S.B. CONSTRUCTION | 4.98 | 0 | 0
3666 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Maheshpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000027/2020-2021 | 1069/NACD-II | 25/09/2020 | 15 | PARTHA DAS | 4.99 | 0 | 0
3667 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Gongra (Vill-Gongra) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000046/2020-2021 | 1193/NACD-II | 13/11/2020 | 25 | JOY GOPAL GUPTI | 4.99 | 0 | 0
3668 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Tengra (Vill-Tengra) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000049/2020-2021 | 1196/NACD-II | 13/11/2020 | 25 | SANJOY BAKSHI | 4.99 | 0 | 0
3669 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000016/2021-2022 | 2152/ND | 21/05/2021 | 60 | ORIENT CONSTRUCTION | 42.68 | 12.75 | 100
3670 | Nadia Division | RWS Nadia Sub-Division | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Paschim Bhatjangla Zone-I PWSS within Krishnagar-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000073/2024-2025 | 4073/ND | 26/07/2024 | 625 | SANDIP BISWAS | 148.49 | 0 | 70
3671 | Nadia Division | RWS Nadia Sub-Division | Sinking of 1 No. Big Dia Tubewell 300mm. x 200mm & 200 mtr deep by Direct Rotary Rig Method using PVC pipe & UPVC deep well screen (RDS) pipes with Ribs etc. including inter connection of Rising Main System for Paschim Bhatjangla Zone-II Water Supply Scheme at Head Work Site under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000187/2024-2025 | 5035/ND | 13/09/2024 | 45 | ZEST INFRACON | 16.29 | 0 | 60
3672 | Nadia Division | RWS Nadia Sub-Division | laying of distribution pipe line75mm dia and 63 mm dia UPVC pipe etc. for Providing functional household tap connection at Paschim Bhatjangla zone- I W/S scheme (Part - A) under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000240/2021-2022 | 1070/PH | 04/10/2021 | 15 | ORIENT CONSTRUCTION | 4.79 | 4.79 | 100
3673 | Nadia Division | RWS Nadia Sub-Division | Providing (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Paschim Bhatjangla Zone -I water supply scheme in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000601/2021-2022 | 336/ND | 25/01/2022 | 90 | PUSPA ENTERPRISE | 314.25 | 267.8 | 95
3674 | Nadia Division | RWS Nadia Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir, Pump House, Boundary Wall and Construction of Service Road for Paschim Bhatjangla Zone-I Water Supply Scheme under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000670/2023-2024 | 543/ND | 24/01/2024 | 611 | G.S. CONSTRUCTION & CO | 39.9 | 0 | 60
3675 | Nadia Division | RWS Nadia Sub-Division | Construction Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 31.00 cum/hr at Paschim Bhatjangla water supply scheme including 3 Months Trial Run & 3 Years O&M within Krishnagar-I block under RWS Nadia Sub-division under Nadia Division, P.H.E. Dte | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000707/2023-2024 | 1251/ND | 22/02/2024 | 180 | APURBA MANDAL | 163.44 | 0 | 45
3676 | Nadia Division | RWS Nadia Sub-Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | VCH/001059/2021-2022 | 617/PFMS | 14/03/2022 | 0 | UMWELT ENGINEERS PVT LTD | 3.94 | 0 | 0
3677 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur, Part-II, at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000063/2021-2022 | 1421/NAD-I | 08/11/2021 | 60 | M/S ASHA CONSTRUCTION | 77.3 | 73.4 | 100
3678 | Nadia Arsenic Division I |  | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Muragachha Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) |  |  | ORD/000176/2021-2022 | 497/NAD-I | 22/03/2022 | 60 | DIVINE | 144.2 | 144.13 | 100
3679 | Nadia Arsenic Division I |  | Laying of additional; pipelines at Garapota W/S Scheme under JJM within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000035/2024-2025 | 183/AE-II/NAD-I | 09/08/2024 | 7 | M/S ADIL CONSTRUCTION | 0.92 | 0 | 100
3680 | Nadia Arsenic Division I |  | Laying of additional pipelines and reconnection of damages FHTC at Garapota W/S Scheme under JJM within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000036/2024-2025 | 184/AE-II/NAD-I | 09/08/2024 | 7 | M/S ADIL CONSTRUCTION | 0.93 | 0 | 100
3681 | Nadia Arsenic Division I |  | Laying of additional pipelines at Node Point 27 to 32 at Garapota W/S Scheme under JJM within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte |  |  | ORD/000037/2024-2025 | 185/AE-II/NAD-I | 09/08/2024 | 7 | M/S ADIL CONSTRUCTION | 0.92 | 0 | 100
3682 | Nadia Arsenic Division I |  | Interconnection between Common Manifold and distribution main at Bhayna Zone-I W/S Scheme under JJM in connection with Garapota and Bhayna W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl. no. 03) |  |  | ORD/000051/2024-2025 | 1501/NAD-I | 18/09/2024 | 45 | B.S. ENTERPRISE | 19.54 | 0 | 100
3683 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Garapota Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000053/2021-2022 | 1410/NAD-I | 08/11/2021 | 60 | B.M. ENGINEERING & CONSTRUCTION | 86.04 | 84.75 | 100
3684 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 140/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
3685 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IV, (Uttar Duttapara), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000124/2021-2022 | 49/NAD-I | 11/01/2022 | 90 | KINGS AND CO | 223.23 | 223.17 | 100
3686 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Naserkuli Zone-II W/S scheme in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000277/2021-2022 | 5689/ND | 03/11/2021 | 90 | S.S. ENTERPRISE | 87.5 | 61.9 | 100
3687 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000026/2021-2022 | 439/ND | 31/01/2022 | 0 | Resource Division | 1.19 | 0 | 0
3688 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000029/2021-2022 | 430/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
3689 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Naserkuli Zone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | Assistant Engineer |  | VCH/000316/2022-2023 | 41/PFMS | 27/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.2 | 0 | 0
3690 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Naserkuli Zone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | Assistant Engineer |  | VCH/000317/2022-2023 | 42/PFMS | 27/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.49 | 0 | 0
3691 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Naserkuli Zone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | Assistant Engineer |  | VCH/000357/2022-2023 | 57/PFMS | 22/06/2022 | 0 | S.S. ENTERPRISE | 12.54 | 0 | 0
3692 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Murutia W/S scheme in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000274/2021-2022 | 5686/ND | 03/11/2021 | 90 | SANJIB DEY | 88.14 | 65 | 100
3693 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000024/2021-2022 | 437/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
3694 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000076/2021-2022 | 780/ND | 18/02/2022 | 0 | Resource Division | 3.29 | 0 | 0
3695 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000110/2021-2022 | 1025/ND | 03/03/2022 | 0 | Resource Division | 24.31 | 0 | 0
3696 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Murutia WaterSupply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | Assistant Engineer |  | VCH/001021/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 3.05 | 0 | 0
3697 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Kadipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000028/2020-2021 | 1070/NACD-II | 25/09/2020 | 15 | SANJIT DAS | 4.99 | 0 | 0
3698 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-XI,(Chanduria) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000122/2021-2022 | 15/NAD-I | 05/01/2022 | 90 | MADE AND TRADE CO. | 441.26 | 379.43 | 100
3699 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work under Jal Jeevan Mission (JJM) for Brambhapara, Manasapota (Nirmalpally, Sahapara) Brambhapara, Chanduria (Sahapara) area under Chakdah Block by Augmentation of Surface Water Based W/S Scheme for Arsenic affected areas of Chakdah (Part Block) of Nadia District Zone-XI (Chanduria) under Nadia Arsenic Division-I, PHE Dte. (Sl.no.20) | Assistant Engineer-II | Junior Engineer-III | ORD/000193/2023-2024 | 2190/NAD-I | 13/09/2023 | 15 | PRADIP KUMAR BANIK | 14.14 | 0 | 100
3700 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection from node point 105 to node point 16 for augmentation work at Koutakpur, Jibannagar and Kajibagan under Zone-XI, Chanduria W/S Scheme under Jal Jeevan Mission under Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte (sl.7) | Assistant Engineer-II | Junior Engineer-III | ORD/000258/2022-2023 | 457/ NAD-I | 06/03/2023 | 21 | ABDUL ALIM MONDAL | 32.03 | 32.03 | 0
3701 | Nadia Division | Ranaghat Sub-Division | Construction and installation of MANIFOLD and allied works at Head Works site under Mahishnengra Zone-I Ground Based Water Supply Scheme under Krishnagar-I Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM). | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000068/2025-2026 | 2400/ND | 23/05/2025 | 90 | MAA SARADA CONSTRUCTION | 12.28 | 0 | 0
3702 | Nadia Division | Ranaghat Sub-Division | Repairing of Pump house-I with sanitary arrangement under augmentation of Mahishnengra Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000209/2024-2025 | 1148/RSD | 11/09/2024 | 45 | SUNNY ENTERPRISE | 1.88 | 0 | 90
3703 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
3704 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (part) including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe line and other allied works etc all complete for MAHISHNENGRA ZONE I W/S scheme (for Mahisnengra, Beraberia, Tegharia, Jatrapur Mouza) under Ranaghat Sub Division of Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000701/2021-2022 | 963/ND | 28/02/2022 | 90 | M/S TARAK CHANDRA PAUL | 208.33 | 62.39 | 98
3705 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000015/2023-2024 | 1861/ND | 26/04/2023 | 0 | Resource Division | 26.26 | 0 | 0
3706 | Nadia Division | Ranaghat Sub-Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/000318/2022-2023 | 37/PFMS | 27/05/2022 | 0 | M/S TARAK CHANDRA PAUL | 144.73 | 0 | 0
3707 | Nadia Division | Ranaghat Sub-Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/001079/2021-2022 | 642/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.49 | 0 | 0
3708 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at MAHISNENGRA ZONE - I W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/09570 | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000131/2025-2026 | 1132/EMD | 04/06/2025 | 270 | JAL PRAVAHIKA PVT. LTD. | 36.52 | 0 | 0
3709 | Nadia Division | Ranaghat Sub-Division | Construction and installation of MANIFOLD and allied works at Head Works site under Gazna Ground Based Water Supply Scheme under Hanskhali Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM). | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000221/2025-2026 | 3639/ND | 04/08/2025 | 90 | K.K. MARKETING | 11.85 | 0 | 0
3710 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation of head work site pump house & allied works of Gazna W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000227/2022-2023 | 556/RSD | 30/08/2022 | 30 | RUBI ENTERPRISE | 2.28 | 1.76 | 90
3711 | Nadia Division | Ranaghat Sub-Division | Special repair & renovation & repair of AIRP pump house & allide works of Gazna W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000245/2022-2023 | 476/A/RSD | 27/07/2022 | 30 | M/S DEBANANDA CONSTRUCTION | 1.99 | 1.97 | 50
3712 | Nadia Division | Ranaghat Sub-Division | Laying 160 mm dia UPVC pipe line inplace of damaged 160 mm dia from gazna Madhya Para to Gazna Para for smooth running of augmentation of Ground Water Supply Scheme for Gazna in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000293/2022-2023 | 5333/ND | 21/12/2022 | 868 | SANDIP BISWAS | 17.06 | 13.69 | 95
3713 | Nadia Division | Ranaghat Sub-Division | Replacemt of damaged & typically choked UPVC pipe line for augmentation of Ground Water Based Water Supply Scheme for Gazna PWSS of Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. (Balance) A- Part. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000370/2023-2024 | 4802/ND | 17/10/2023 | 623 | SANDIP BISWAS | 99.5 | 0 | 96
3714 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (part) including supply of 15mm dia PVC pipe of average length of 15 mtr, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Gazna Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000687/2021-2022 | 895/ND | 23/02/2022 | 90 | SANDIP BISWAS | 143.12 | 52.49 | 100
3715 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000003/2021-2022 | 6909/ND | 24/11/2021 | 0 | Resource Division | 0.68 | 0 | 0
3716 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000025/2023-2024 | 1873/ND | 26/04/2023 | 0 | Resource Division | 17.01 | 0 | 0
3717 | Nadia Division | Ranaghat Sub-Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/000139/2022-2023 | 01/PFMS | 26/04/2022 | 0 | SANDIP BISWAS | 30.08 | 0 | 0
3718 | Nadia Division | Ranaghat Sub-Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/001122/2021-2022 | 708/PFMS | 30/03/2022 | 0 | SANDIP BISWAS | 60 | 0 | 0
3719 | Nadia Division | Ranaghat Sub-Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/001241/2021-2022 | 725/PFMS | 30/03/2022 | 0 | HORIZEN | 2.78 | 0 | 0
3720 | Eastern Mechanical | Ranaghat Sub-Division | Supply, & Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for Mini Piped Water Supply Scheme[Gazna(part) Block-Hanskhali, Uttar Bishnupur Block-Ranaghat-II, Augmentation to Accomodate FHTC , Dist. - Nadia. under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000015/2024-2025 | 1307/EMD | 09/05/2024 | 388 | ORIENTAL ENGINEERING CO. | 12.61 | 0 | 45
3721 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at GAZNA W/S Scheme Block- HANSKHALI under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/09571 | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000149/2025-2026 | 1150/EMD | 04/06/2025 | 90 | KARTICK BAL | 36.98 | 0 | 0
3722 | Nadia Division | Debgram Sub-Division | Schedule for Laying additional distribution pipeline for providing FHTC at Dhnanajoypur, Dhaparia and Radhanagar villages under zone-VII , Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000061/2022-2023 | 175/B/DSD | 18/04/2022 | 30 | CALCON CONSTRUCTIONS | 4.97 | 4.68 | 100
3723 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- VII/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000313/2023-2024 | 4282/ND | 21/09/2023 | 624 | SATYABRATA CHAKRABORTY | 397.18 | 0 | 14
3724 | Nadia Division | Debgram Sub-Division | Providing Functional Household Tap connection(FHTC)at Surface Water Based Water Supply Scheme(Northern Sector) Part-II,Zone-VII within Nakashipara Block(Phase-C) | Assistant Engineer |  | ORD/000384/2021-2022 | 7205/ND | 15/12/2021 | 90 | CALCON CONSTRUCTION | 179.4 | 63.59 | 100
3725 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at Dhaparia, Dhananjoypur & Shibpur zone-VII , Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000817/2021-2022 | 49/DSD | 07/02/2022 | 15 | CALCON CONSTRUCTIONS | 4.79 | 4.76 | 100
3726 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at Dhnanajoypur and Radhanagar villages under zone-VII , Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000818/2021-2022 | 50/DSD | 07/02/2022 | 15 | CALCON CONSTRUCTIONS | 4.75 | 4.71 | 100
3727 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000061/2021-2022 | 795/ND | 18/02/2022 | 0 | Resource Division | 7.22 | 0 | 0
3728 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000066/2021-2022 | 797/ND | 18/02/2022 | 0 | Resource Division | 11 | 0 | 0
3729 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) | Assistant Engineer |  | VCH/001119/2021-2022 | 698/PFMS | 28/03/2022 | 0 | CALCON CONSTRUCTIONS | 83.66 | 0 | 0
3730 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at Ballavpara, Basatpur, Kanua, Juranpur Bhagyabantapur, Gobra zone-I & II , Part- I Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Kaliganj Block. | Assistant Engineer |  | ORD/000062/2022-2023 | 175/C/DSD | 18/04/2022 | 30 | JAL PRAVAHIKA PRIVATE LIMITED | 4.85 | 4.8 | 100
3731 | Nadia Division | Debgram Sub-Division | Providing Functional Household Tap Connection (FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-I,II & IV within KALIGANJ BLOCK(Phase-C) | Assistant Engineer |  | ORD/000327/2021-2022 | 7050/ND | 06/12/2021 | 90 | JAL PRAVAHIKA PRIVATE LIMITED | 180.28 | 26.9 | 100
3732 | Nadia Division | Debgram Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
3733 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000038/2021-2022 | 428/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
3734 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000044/2021-2022 | 447/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
3735 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000085/2021-2022 | 817/ND | 18/02/2022 | 0 | Resource Division | 10.98 | 0 | 0
3736 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000168/2023-2024 | 303/ND | 15/01/2024 | 0 | Resource Division | 10.96 | 0 | 0
3737 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000169/2023-2024 | 304/ND | 15/01/2024 | 0 | Resource Division | 23.27 | 0 | 0
3738 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000170/2023-2024 | 305/ND | 15/01/2024 | 0 | Resource Division | 3.81 | 0 | 0
3739 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000171/2023-2024 | 306/ND | 15/01/2024 | 0 | Resource Division | 8.98 | 0 | 0
3740 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000172/2023-2024 | 307/ND | 15/01/2024 | 0 | Resource Division | 12.39 | 0 | 0
3741 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000183/2023-2024 | 318/ND | 15/01/2024 | 0 | Resource Division | 3.27 | 0 | 0
3742 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | Assistant Engineer |  | VCH/000208/2022-2023 | 33/PFMS | 23/05/2022 | 0 | JAL PRAVAHIKA PRIVATE LIMITED | 50.46 | 0 | 0
3743 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | Assistant Engineer |  | VCH/001085/2021-2022 | 653/PFMS | 21/03/2022 | 0 | JAL PRAVAHIKA PRIVATE LIMITED | 55 | 0 | 0
3744 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | Assistant Engineer |  | VCH/001096/2021-2022 | 664/PFMS | 23/03/2022 | 0 | JAL PRAVAHIKA PRIVATE LIMITED | 42.43 | 0 | 0
3745 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Dakshinpara Z-II Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.E. Dte.(Phase-A) | Assistant Engineer | Junior Engineer 2 | ORD/000204/2021-2022 | 5178/ND | 20/09/2021 | 90 | JOY HIND TUBEWELL'S | 88.3 | 87.92 | 0
3746 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000019/2021-2022 | 101/ND | 06/01/2022 | 0 | Resource Division | 0.88 | 0 | 0
3747 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000056/2021-2022 | 794/ND | 18/02/2022 | 0 | Resource Division | 8.92 | 0 | 0
3748 | Nadia Division | Ranaghat Sub-Division | Providing Functional House Tap Connection from Dakshinpara Zone-II Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-A) | Assistant Engineer | Junior Engineer 2 | VCH/001015/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 8.27 | 0 | 0
3749 | Nadia Division | Krishnanagar Sub-Division | LAYING OF PIPELINE UNDER PALASHIPARA PWSS FROM PALASHIPARA BAZAR TO BURNIA BUS STAND. | Assistant Engineer | Junior Engineer,Junior Engineer 5 | BILL/00527/2023-2024 | 241/1/PFMS | 18/08/2023 | 0 | OTHERS | 49.99 | 0 | 0
3750 | Nadia Division | Krishnanagar Sub-Division | Repair and renovation works of R.C.C. Elevaced Reservoir 450 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Dakshin Jhitkipota Zone-I Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 5 | ORD/000020/2024-2025 | 3265/ND | 10/06/2024 | 228 | NEERMAN | 24.9 | 0 | 100
3751 | Nadia Division | Krishnanagar Sub-Division | LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS & VALVES, PIPE SUPPORTING STRUCTURE ALL COMPLETE BASED ON ACTUAL ESTIMATE & PROVIDING FHTC FOR DAKHIN JHITKIPOTA ZONE - I WATER SUPPLY SCHEME IN NADIA DISTRICT UNDER NADIA DIVISION. | Assistant Engineer | Junior Engineer,Junior Engineer 5 | ORD/000692/2021-2022 | 922/ND | 24/02/2022 | 1080 | TAPU SAHA | 284.92 | 228.67 | 100
3752 | Nadia Division | Krishnanagar Sub-Division | RETROFITTING UNDER JAL SWAPNA FOR DAKSHIN JHITKIPOTA ZONE-I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 5 | VCH/001051/2021-2022 | 609/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.92 | 0 | 0
3753 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at DAKSHIN JHITKIPOTA ZONE-II W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/09451] | Assistant Engineer | Junior Engineer,Junior Engineer 5 | ORD/000144/2025-2026 | 1145/EMD | 04/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 38.68 | 0 | 0
3754 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accommodate FHTC under DAKSHIN JHITKIPOTA(Z-1) W/S Scheme, Block-Krishnagar-I, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer,Junior Engineer 5 | ORD/001920/2022-2023 | 1176/EMD | 21/03/2023 | 30 | SRI KRISHNA NIRMAN | 14.96 | 0 | 99
3755 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Helenchi Zone-I (Vill-Krishnapur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000055/2020-2021 | 1179/NACD-II | 13/11/2020 | 15 | CHINMOY BISWAS | 4.99 | 0 | 0
3756 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- III) at village Nazirpur, Bagadoba, Chhitka, Aztullanagar under Tehatta-I Block to accommodate FHTC under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1805/ND | 22/04/2025 | 180 | M/S DIPAK ENTERPRISE | 71.65 | 0 | 30
3757 | Nadia Division | Tehatta Sub-Division | Repairing and renovation works of Pump House and allied works of ground based piped water supply scheme for Nazirpur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer | ORD/000437/2024-2025 | 7061/ND | 04/12/2024 | 150 | BISWAS ENTERPRISE | 12.53 | 0 | 100
3758 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. and construction of 400 cum capacity 20 mtr. staging height RCC over head reservoir (including pile foundation), pipe connection and cost of pipes, specials and soil investigation for construction of one no. 400 cum OHR of staging height 20 mtr all complete for Augmentation of Ground Based Water Supply Scheme at Nazirpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000662/2021-2022 | 634/ND | 10/02/2022 | 90 | IJABUL SK. | 354.81 | 120.52 | 70
3759 | Nadia Division | Tehatta Sub-Division | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 76 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Nazirpur to accommodate FHTC within Tehatta-I block underTehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000724/2024-2025 | 207/ND | 13/01/2025 | 180 | TRANS ORGANICS INDIA PVT LTD | 217.81 | 0 | 0
3760 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000043/2022-2023 | 4313/ND | 29/09/2022 | 0 | Resource Division | 20.05 | 0 | 0
3761 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000050/2021-2022 | 434/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
3762 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000136/2021-2022 | 1265/ND | 16/03/2022 | 0 | Resource Division | 11.72 | 0 | 0
3763 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000144/2021-2022 | 1390/ND | 24/03/2022 | 0 | Resource Division | 16.87 | 0 | 0
3764 | Nadia Division | Tehatta Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | Assistant Engineer | Junior Engineer | VCH/000143/2022-2023 | 06/PFMS | 26/04/2022 | 0 | IJABUL SK. | 40.83 | 0 | 0
3765 | Nadia Division | Tehatta Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | Assistant Engineer | Junior Engineer | VCH/001078/2021-2022 | 641/PFMS | 16/03/2022 | 0 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 3.6 | 0 | 0
3766 | Nadia Division | Tehatta Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district under Nadia division. | Assistant Engineer | Junior Engineer | VCH/001145/2021-2022 | 718/PFMS | 30/03/2022 | 0 | IJABUL SK. | 50 | 0 | 0
3767 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No.I under Nazirpur W/S Scheme District -Nadia NIET No.- 13 of EE/EMD of 2022-23 (Sl. No.-05) | Assistant Engineer | Junior Engineer | ORD/000082/2022-2023 | 3805/EMD | 14/10/2022 | 30 | A.K. ENTERPRISE | 13.23 | 13.23 | 100
3768 | Nadia Division | Ranaghat Sub-Division | Construction of 100m Boundary Wall(2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Mahisnengra Zone-II PWSS at H/W site under Ranaghat Sub -Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000080/2025-2026 | 2462/ND | 27/05/2025 | 180 | ABHAYANANDA ENTERPRISE | 8.74 | 0 | 100
3769 | Nadia Division | Ranaghat Sub-Division | Repairing of Pump house-I with sanitary arrangement under augmentation of Mahishnengra Zone-II piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000291/2024-2025 | 1277/RSD | 04/10/2024 | 45 | MANARAMA ENTERPRISE | 1.9 | 0 | 100
3770 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
3771 | Nadia Division | Ranaghat Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
3772 | Nadia Division | Ranaghat Sub-Division | LAYING OF RISING MAIN AT MAHISNENGRA ZONE II WATER SUPPLY SCHEME UNDER RANAGHAT SUB DIVISION OF NADIA DIVISION, P.H.E. DTE. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000689/2021-2022 | 107/RSD | 23/02/2022 | 15 | M/S BISWAS ENTERPRISE | 1.83 | 1.42 | 90
3773 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000016/2023-2024 | 1880/ND | 26/04/2023 | 0 | Resource Division | 4.39 | 0 | 0
3774 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000119/2021-2022 | 1057/ND | 04/03/2022 | 0 | Resource Division | 3.96 | 0 | 0
3775 | Nadia Division | Ranaghat Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/001080/2021-2022 | 643/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.5 | 0 | 0
3776 | Eastern Mechanical | Ranaghat Sub-Division | WBSEDCL Quotation for New Service Connection to the ongoing AIRP premises under ZONE - II of MAHISNENGRA W/S Scheme in Krishnagar - I Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3004547497) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | BILL/00072/2024-2025 | BP-05-24-25 | 23/04/2024 | 0 | W.B.S.E.D.C.LTD (CHITRASALI C.C.CENTER) | 6.79 | 0 | 0
3777 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at MAHISNENGRA Zone-II W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/09787 | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000133/2025-2026 | 1134/EMD | 04/06/2025 | 90 | MAHAMAYA ENTERPRISE. | 36.66 | 0 | 0
3778 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Gravity Type) of capacity 57 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Itla PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000083/2023-2024 | 2996/ND | 13/07/2023 | 900 | TARUN KUMAR BHATTACHARYA | 82.59 | 0 | 50
3779 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Itla to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000738/2021-2022 | 1313/ND | 21/03/2022 | 90 | SHIBU BISWAS | 145.51 | 144.13 | 100
3780 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000049/2022-2023 | 4323/ND | 29/09/2022 | 0 | Resource Division | 25.29 | 0 | 0
3781 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000102/2021-2022 | 1020/ND | 03/03/2022 | 0 | Resource Division | 2.21 | 0 | 0
3782 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000128/2021-2022 | 1259/ND | 16/03/2022 | 0 | Resource Division | 8.04 | 0 | 0
3783 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/001071/2021-2022 | 634/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.59 | 0 | 0
3784 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under ITLA W/S Scheme, Block- Krishnagar-1 , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 15) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000905/2022-2023 | 415/EMD | 20/01/2023 | 30 | ANJAN ENTERPRISE | 14.53 | 13.46 | 80
3785 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Itaberia Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Itaberia W/S Scheme under JJM (sl.no.11) | Assistant Engineer-II | Junior Engineer-IV | ORD/000016/2023-2024 | 1122 /NAD-I | 27/04/2023 | 15 | B.S. ENTERPRISE | 13.04 | 0 | 100
3786 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of AIRP capacity (104m3/hr) in connection with augmentation of Ground Water Based PWSS for Chupria Zone-I under Jal Jeevan Mission at Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000025/2024-2025 | 1118/NAD-I | 19/07/2024 | 180 | HARBAUER INDIA PRIVATE LIMITED | 265.04 | 0 | 0
3787 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 450 cum capacity Over Head Reservoir, Painting and Pump House at Gobindapur W/S Scheme in Hanskhali Block under Nadia Arsenic Division-I, P.H.E Dte. (Sl. No. 10) | Assistant Engineer-II | Junior Engineer-IV | ORD/000039/2022-2023 | 1589/NAD-I | 05/09/2022 | 45 | APURBA MANDAL | 14.41 | 14.38 | 40
3788 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at ITABERIA W/S Scheme & Betna W/S Scheme at Hanskhali Block under Nadia Arsenic Division-I , P.H.E.Dte. (Sl.no. 10) | Assistant Engineer-II | Junior Engineer-IV | ORD/000043/2022-2023 | 1583/NAD-I | 06/09/2022 | 45 | SATYABRATA CHAKRABORTY | 28.26 | 28.19 | 100
3789 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet , Pathway and other allied work at Gobindapur (Hanskhali) W/S Scheme within Hanskhali Block under Nadia Arsenic Division -I, P.H.E.Dte.(Sl.no. 02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000048/2022-2023 | 1588 / NAD-I | 06/09/2022 | 45 | GOPAL KIRTYANIYA | 11.82 | 11.76 | 100
3790 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet, pathway and other allied work at Joypur W/S scheme within Hanskhali Block under Nadia Arsenic Division -I, P.H.E.Dte.( Sl.no.01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000052/2022-2023 | 1590 / NAD-I | 06/09/2022 | 45 | M/S DREAM INFRASTRUCTURE | 12.41 | 12.35 | 100
3791 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet, Pathway and all repair works at Itaberia W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (sl.no.03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000055/2022-2023 | 1638 / NAD-I | 06/09/2022 | 45 | APURBA MANDAL | 12.04 | 11.99 | 100
3792 | Nadia Arsenic Division I | Nadia Arsenic Division I | 'Construction and installation of MANIFOLD and allied works at OHR site under Gobindapur Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E [he. in connection with Augmentation of Gobindapur W/S Scheme under JIM (SL No. 10)". | Assistant Engineer-II | Junior Engineer-IV | ORD/000068/2023-2024 | 1071/NAD-I | 24/04/2023 | 733 | APURBA MANDAL | 13.03 | 0 | 100
3793 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 350 cum capacity Over Head Reservoir, Painting of Boundary Wall of Head Work Site, Pump House and AIRP at Joypur W/S Scheme in Hanskhali Block under Nadia Arsenic Division - I P. H.E. Dte (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000074/2023-2024 | 1258/NAD-I | 04/05/2023 | 15 | GHOSH CONSTRUCTION | 21.34 | 0 | 100
3794 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Itaberia WS Scheme in Hanskhali Block under NAD I PHE Dte (Sl.no.12) | Assistant Engineer-II | Junior Engineer-IV | ORD/000109/2022-2023 | 2058 / NAD-I | 21/10/2022 | 45 | M/S D.C. RAKSHIT & COMPANY | 19.77 | 19.63 | 100
3795 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Itaberia PWSS Hanskhali Block (Part-I) by Augmentation of Itaberia, Gobindapur & Joypur at Hanskhali Block, Dist- Nadia under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000157/2022-2023 | 3489/NAD-I | 02/01/2023 | 21 | BUDDHADEV MONDAL | 19.22 | 18.72 | 99
3796 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Gobindapur PWSS Hanskhali Block (Part-II) by Augmentation of Itaberia, Gobindapur & Joypur at Hanskhali Block, Dist- Nadia under Nadia Arsenic Division-I, PHE Dte (sl.no.04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000161/2022-2023 | 3513/NAD-I | 09/01/2023 | 21 | M/S DIPAK ENTERPRISE | 19.75 | 0 | 100
3797 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Joypur PWSS Hanskhali Block (Part-III) by Augmentation of Itaberia, Gobindapur & Joypur at Hanskhali Block, Dist- Nadia Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.no.02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000162/2022-2023 | 3514/NAD-I | 09/01/2023 | 21 | SUBIR KUMAR DEY | 19.99 | 0 | 100
3798 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Joypur Part-III at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000165/2021-2022 | 433/NAD-I | 07/03/2022 | 60 | M/S GHOSH CONSTRUCTION | 60.4 | 56.94 | 100
3799 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Teinpur zone - I W/S scheme under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000195/2021-2022 | 5141/ND | 15/09/2021 | 60 | SAHA ENGINEERS | 37 | 26.29 | 100
3800 | Nadia Division | RWS Nadia Sub-Division | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 11-11-2022 to 31-01-2023= 80 days. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000469/2022-2023 | 678/RSD | 04/11/2022 | 80 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 1.19 | 0 | 75
3801 | Nadia Division | RWS Nadia Sub-Division | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H.E. Dte., Kalyani, Nadia. Period of work 01-03-2022 to 28-02-2023 | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000814/2021-2022 | 118/RSD | 28/02/2022 | 250 | SUMAN CHAKRABORTY | 3.85 | 0 | 75
3802 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Karimpur- II Block | RTOR000072/2021-2022 | 805/ND | 18/02/2022 | 0 | Resource Division | 3.33 | 0 | 0
3803 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Teinpur Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | VCH/001017/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 3.08 | 0 | 0
3804 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Naserkuli zone- I W/S scheme under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000199/2021-2022 | 5144/ND | 15/09/2021 | 90 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 87.52 | 77.98 | 100
3805 | Nadia Division | RWS Nadia Sub-Division | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-02-2023 to 31-07-2023= 183 days. | Assistant Engineer |  | ORD/000512/2022-2023 | 92/RSD | 01/02/2023 | 183 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 3.2 | 0 | 25
3806 | Nadia Division | RWS Nadia Sub-Division | Hiring Diesel Luxury Car on daily basis (for12 months from 01.02.2022 to 31.01.2023) for the office use of the Assistant Engineer, Kalyani Sub - Division - II, P.H.E. Dte. | Assistant Engineer |  | ORD/000735/2021-2022 | 144/ Kly SD-II | 31/01/2022 | 365 | SUMAN CHAKRABORTY | 4.8 | 0 | 65
3807 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000036/2021-2022 | 446/ND | 31/01/2022 | 0 | Resource Division | 1.19 | 0 | 0
3808 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000075/2021-2022 | 821/ND | 18/02/2022 | 0 | Resource Division | 5.5 | 0 | 0
3809 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | Assistant Engineer |  | VCH/000314/2022-2023 | 39/PFMS | 27/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.36 | 0 | 0
3810 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | Assistant Engineer |  | VCH/000315/2022-2023 | 40/PFMS | 27/05/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.04 | 0 | 0
3811 | Nadia Division | Krishnanagar Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Krishnaganj W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(PART-A) | Assistant Engineer | Junior Engineer 1 | ORD/000281/2021-2022 | 5693/ND | 03/11/2021 | 90 | NILAY KUMAR BHATTACHARYA | 85.63 | 84.56 | 0
3812 | Nadia Division | Krishnanagar Sub-Division | Providing balance FHTC of Phase I (Retrofitting) of Krishnaganj Water Supply Scheme in Nadia District Under Krishnagar Sub-Division, of Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000296/2022-2023 | 5335/ND | 21/12/2022 | 90 | NILAY KUMAR BHATTACHARYA | 96.45 | 88.61 | 100
3813 | Nadia Division | Krishnanagar Sub-Division | Laying Of Additional Distribution System Including Specials, Valves to provide FHTC at Leftout Household, Inter Connection of Rising Main in connection to Retrofitting (Phase-I) under JJM In Ground Based Piped Water Supply Scheme at Krishnaganj Majhdia to accommodate FHTC within Krishnaganj Block under Krishnanagar Sub-division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000772/2023-2024 | 1762/ND | 12/03/2024 | 518 | NILAY KUMAR BHATTACHARYA | 30.36 | 0 | 100
3814 | Nadia Division | Krishnanagar Sub-Division | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.01.2024 to 31.01.2024 | Assistant Engineer | Junior Engineer 1 | ORD/000827/2023-2024 | 1359/KLYSD-I | 28/12/2023 | 31 | SUMAN CHAKRABORTY | 4.89 | 0 | 100
3815 | Nadia Division | Krishnanagar Sub-Division | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.02.2024 to 31.03.2024 | Assistant Engineer | Junior Engineer 1 | ORD/000864/2023-2024 | 115/KlySD-I | 31/01/2024 | 29 | SUMAN CHAKRABORTY | 4.89 | 0 | 100
3816 | Nadia Division | Krishnanagar Sub-Division | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.03.2024 to 31.03.2024 | Assistant Engineer | Junior Engineer 1 | ORD/000946/2023-2024 | 326/KlySD-I | 29/02/2024 | 31 | SUMAN CHAKRABORTY | 4.89 | 0 | 100
3817 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Shifting of 01 no existing 63 KVA, 11/0.4 KV DTR I.R.O PHE Brittihuda PWSS head works site, Brittihuda under Chapra CCC. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/00216/2024-2025 | 133 | 06/09/2024 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.68 | 0 | 0
3818 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000028/2021-2022 | 521/NACD-II | 14/06/2021 | 45 | JOY HIND TUBEWELLS | 74.36 | 0 | 100
3819 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000072/2021-2022 | 547/NACD-II | 07/07/2021 | 45 | JOY HIND TUBEWELLS | 73.68 | 0 | 100
3820 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000073/2021-2022 | 562/NACD-II | 13/07/2021 | 45 | JOY HIND TUBEWELLS | 73.59 | 0 | 100
3821 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Piling work at Krishnagar Karimpur Road side for pipe line protection at Brittihuda Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000119/2021-2022 | 134/AE-I/NACD-II | 28/10/2021 | 15 | TAPAS GHOSH | 4.96 | 4.96 | 100
3822 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Jungle cutting and Earthwork in filling at Taldaha,Sakdaha and Brittihuda Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000121/2024-2025 | 819/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.53 | 0 | 100
3823 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Relaying of D.I. Pipeline replacing the damaged old HDPE Rising Main Pipe line at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000123/2021-2022 | 140/AE-I/NACD-II | 01/11/2021 | 15 | GOUTAM HALDER | 3.37 | 3.37 | 100
3824 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Brittihuda, (Block -Chapra) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000146/2021-2022 | 145/AE-I/NACD-II | 16/11/2021 | 10 | UMWELT ENGINEER PVT LTD. | 3.89 | 3.89 | 100
3825 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Special repairing works of damaged old pipe line at Brittihuda including ancillary FHTC works at Arangsarisa of Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000164/2021-2022 | 168/AE-I/NACD-II | 23/11/2021 | 15 | JOY HIND TUBEWELLS | 4.99 | 4.99 | 100
3826 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Brittihuda (Phase-II), (Block -Chapra) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000174/2021-2022 | 757/NACD-II | 16/09/2021 | 10 | SIRCON ENGINEERING SERVICE | 4.95 | 4.95 | 100
3827 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also construction of steps with earth filling at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000191/2021-2022 | 983/NACD-II | 27/12/2021 | 90 | IJABUL SEKH | 177.61 | 177.39 | 100
3828 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Making of Office Furniture including supply of Split type Air Conditioner and other allied works under Retrofitting of the Brittihuda PWSS under Chapra Block | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000196/2021-2022 | 184/AE-I/NACD-II | 29/12/2021 | 20 | SURAJIT KUMAR GHOSH | 4.89 | 4.89 | 100
3829 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rejuvenation of the offiec room including supply of Split type Air Conditioner and other allied works under Retrofitting of the Brittihuda PWSS under Chapra Block. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000197/2021-2022 | 185/AE-I/NACD-II | 29/12/2021 | 20 | SURAJIT KUMAR GHOSH | 4.97 | 3.3 | 100
3830 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair ) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000229/2021-2022 | 995/EE/NACD-II | 30/12/2021 | 45 | CHANDA CONSTRUCTION | 98.72 | 0 | 100
3831 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" in connection with " Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Gadigacha W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte." | Assistant Engineer |  | ORD/000405/2021-2022 | 7292/ND | 20/12/2021 | 60 | PAPAN ROY | 23.86 | 22.4 | 95
3832 | Nadia Division | Krishnanagar Sub-Division | Restoration of impact zone along Swarupganj UBI more to Anandabas road in connection to the work Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" in connection with " Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Gadigacha and other W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. Sl.No. 03 | Assistant Engineer |  | ORD/000723/2021-2022 | 244/KSD | 11/03/2022 | 7 | PAPAN ROY | 4.44 | 1.02 | 97
3833 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000006/2021-2022 | 7449/ND | 27/12/2021 | 0 | Resource Division | 34.46 | 0 | 0
3834 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000040/2022-2023 | 4269/ND | 29/09/2022 | 0 | Resource Division | 2.51 | 0 | 0
3835 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000043/2021-2022 | 449/ND | 31/01/2022 | 0 | Resource Division | 0.81 | 0 | 0
3836 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001768/2022-2023 | 1120/EMD | 16/03/2023 | 30 | B.T. PROJECTS PVT. LTD | 91.82 | 0 | 60
3837 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Route survey engaging qualified surveyors with modern instruments viz-GPS, Total station, DGPS, Auto levels etc over the command area of Mahatpur Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Mahatpur W/S Scheme in chapra Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000019/2023-2024 | 549/NACD_II | 11/05/2023 | 20 | LAKSHMI CONSTRUCTION | 9.09 | 9.09 | 100
3838 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Reparing and painting of Overhead Reservoir and pump house of Gongra Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000026/2022-2023 | 05/AE-I/NACD-II | 04/04/2022 | 45 | GOUTAM HALDER | 5 | 5 | 100
3839 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing FHTC at leftout household alongwith necessary pipeline at Ichapur and Paliyanpur village under Madhabpur Water Supply Scheme and Mahatpur Water Supply Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000075/2025-2026 | 114/AE-I/NACD-II | 04/06/2025 | 30 | ACHARJEE & ASSOCIATES | 4.61 | 0 | 0
3840 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and renovation works of R.C.C. Elevated Reservoir 800 cum for providing FHTC (Functional Household Tap Connection) for Mahatpur Water Supply Scheme in Chapra Block in Nadia District under Nadia Arsenic Civil Division- II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000108/2025-2026 | 938/NACD-II | 28/07/2025 | 90 | SANJOY BAKSHI | 27.51 | 0 | 0
3841 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of pipeline Including some Additional work at Mahatpur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000128/2024-2025 | 833_AE-I/NACD-II | 01/08/2024 | 15 | BABA LOKNATH ENTERPRISE | 0.97 | 0 | 100
3842 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD and allied works at OHR site under Mahatpur Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000140/2023-2024 | 1367/NACD-II | 08/12/2023 | 30 | M/S GHOSH CONSTRUCTION | 45.3 | 0 | 100
3843 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Structural Health assesment of existing shaft type OHR of Chapra Blocks and ancillary structures conducting Non-Destructive test and through visual observation under Nadia Arsenic Civil Division-II P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000149/2023-2024 | 1429/NACD-II | 15/12/2023 | 30 | SIRCON ENGINEERING SERVICE | 8.46 | 0 | 0
3844 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 50 m3/hr capacity Iron Elimination Plant at mouza Kathgara ,habitation Muslim Para under Mahatpur Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000192/2024-2025 | 997/NACD-II | 25/07/2024 | 542 | TAPU SAHA | 23.06 | 0 | 80
3845 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Collection of Household Details at Prescribed Format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte. in soft copy for Bagakhali Zone-I & Mahatpur PWSS under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000199/2024-2025 | 898/AE-I/NACD-II | 09/09/2024 | 60 | JOY GOPAL GUPTI | 3.5 | 0 | 100
3846 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Mouza Mahatpur,Habitation of Bhagabanpur under Mahatpur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000218/2024-2025 | 1189/NACD-II | 02/09/2024 | 360 | SANDIP BISWAS | 10.4 | 0 | 88
3847 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Mouza Mahatpur,Habitation of Jamredanga under Mahatpur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000219/2024-2025 | 1188/NACD-II | 02/09/2024 | 360 | SANDIP BISWAS | 10.4 | 0 | 85
3848 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD)& strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Mouza Kathgara,Habitation of Muslim Para under Mahatpur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000227/2024-2025 | 1322/NACD-II | 20/09/2024 | 45 | DHELA BABA ENTERPRISES | 10.4 | 0 | 0
3849 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Approximate expenditure for land registration and subsequent mutation process as compliance for PHED and Land Commissioner aiuthories to overcome the stalemate and initiation of due diligence processes in Krishnaganj Block under Nadia Arsenic Civil Division-II under Nadia District PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000232/2024-2025 | 933/AE-I/NACD-II | 04/10/2024 | 7 | SOMNATH GHOSH | 0.75 | 0 | 100
3850 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Approximate expenditure for land registration and subsequent mutation process as compliance for PHED and Land Commissioner aiuthories to overcome the stalemate and initiation of due diligence processes in Krishnanagar-I Block under Nadia Arsenic Civil Division II under Nadia District PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000235/2024-2025 | 936/AE-I/NACD-II | 04/10/2024 | 7 | SOMNATH GHOSH | 0.75 | 0 | 100
3851 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum Chlorine room with sanitary and water supply arrangement at Kathgara Muslimpara mouza in Mahatpur Piped water supply scheme in Chapra Block under Nadia Arsenic Civil Division-II ,PHE Dte.Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000238/2024-2025 | 1391/NACD-II | 22/10/2024 | 30 | BABLU MALLICK | 6.22 | 0 | 1
3852 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Mahatpur Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000250/2021-2022 | 108/NACD-II | 10/02/2022 | 45 | PARTHA DAS | 8.55 | 8.5 | 100
3853 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at MAHATPUR ( Vill- MAHATPUR AND SURROUNDING AREA) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000251/2023-2024 | 221/NACD-II | 21/02/2024 | 360 | SAFTI PRIVATE LIMITED | 37.2 | 0 | 100
3854 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at TENGRA W/S Scheme in Tengra Village Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000252/2023-2024 | 660/AE-I/NACD-II | 21/02/2024 | 15 | ASHIM ENTERPRISE | 3.91 | 0 | 100
3855 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000254/2021-2022 | 117/NACD-II | 15/02/2022 | 90 | M/S. R.K.ENTERPRISE | 173.44 | 172.38 | 100
3856 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Mahatpur 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000282/2021-2022 | 237/AE-I/NACD-II | 17/02/2022 | 30 | ROY CONSTRUCTION | 3.85 | 3.83 | 100
3857 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Mahatpur 3rd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000283/2021-2022 | 238/AE-I/NACD-II | 17/02/2022 | 30 | SHYAMAL KANTI GHOSH | 3.84 | 3.8 | 100
3858 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Mahatpur 4th site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000284/2021-2022 | 239/AE-I/NACD-II | 17/02/2022 | 30 | BASUDEB SAHA | 3.81 | 3.79 | 100
3859 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary Wall at OHR Head Work site of Madhabpur W/s Scheme under Nadia Arsenic Civil Division - II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000292/2020-2021 | 20./AE-II/NACD-II | 19/02/2021 | 10 | B.M. ENGINEERING & CONSTRUCTION | 4.96 | 4.62 | 100
3860 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000307/2021-2022 | 42/NACD-II | 17/01/2022 | 45 | NILAY KUMAR BHATTACHARYA | 21.05 | 21.05 | 100
3861 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Mahatpur Water Supply Scheme of capacity 172 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000320/2023-2024 | 217/NACD-II | 16/02/2024 | 660 | HARBAUER INDIA (P) LTD | 358.83 | 0 | 50
3862 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Mahatpur 2nd tube well Site under Mahatpur Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000330/2024-2025 | 1027/AE-I/NACD-II | 10/12/2024 | 30 | SUPRIO MAJUMDER | 3.2 | 0 | 0
3863 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Electrical and Civil works and other allied works under retrofitting of Mahatpur PWSS under Chapra Block. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000333/2021-2022 | 308/AE-I/NACD-II | 23/03/2022 | 20 | CHINMOY BISWAS | 4.92 | 4.92 | 100
3864 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Strengthening Work of existing boundary wall at Mahatpur Headwork site at Mahatpur Piped water supply scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000342/2024-2025 | 1057/AE-I/NACD-II | 19/12/2024 | 30 | ST. ANTHONY ENTERPRISE | 3.96 | 0 | 100
3865 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Piling work at Krishnagar Karimpur Road side for pipe line protection at Brittihuda Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000343/2021-2022 | 211./AE-I/NACD-II | 20/01/2022 | 15 | TAPAS GHOSH | 4.92 | 4.92 | 100
3866 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repairing and paitning of Overhead Reservoir and other allied works under augmentation of Lakshmipur PWSS of Chapra Block. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000344/2021-2022 | 191./AE-I/NACD-II | 29/12/2021 | 25 | PRABIR KUMAR ROY | 4.81 | 4.81 | 100
3867 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000348/2024-2025 | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 20
3868 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional School Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000372/2022-2023 | 351/NACD-II | 22/03/2023 | 20 | SAMARESH GHOSH | 1.1 | 0.87 | 90
3869 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Tengra & Mahatpur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000377/2023-2024 | 411/NACD-II | 13/03/2024 | 21 | JADAVPUR UNIVERSITY | 4.78 | 0 | 100
3870 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under chapra Block of Nadia District through Jadavpur University. (Name of PWSS Gongra & Mahatpur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000385/2023-2024 | 1267_NACD-II | 09/11/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
3871 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Conversion of IEP to AIRP at Tengra Water Supply Scheme of capacity 36Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000386/2024-2025 | 1360/NACD-II | 30/09/2024 | 60 | SUMIT GHOSH | 165.15 | 0 | 0
3872 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum Chlorine room with sanitary and water supply arrangement at Bhagabanpur mouza in Mahatpur Piped water supply scheme in Chapra Block under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000391/2024-2025 | 132/NACD-II | 29/01/2025 | 30 | SHYAMAL KANTI GHOSH | 6.22 | 0 | 0
3873 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including laying of pipeline at TENGRA W/S Scheme in Tengra Village Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000414/2023-2024 | 673_AE-I/NACD-II | 28/03/2024 | 15 | ASHIM ENTERPRISE | 2.98 | 0 | 0
3874 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of pipeline along reconnection due to construction of drain and land erosion at Mahatpur W/S Scheme in Chapra block in Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000443/2024-2025 | 1206/AE-I/NACD-II | 27/02/2025 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 0.92 | 0 | 100
3875 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 50 m3/hr capacity Iron Elimination Plant at mouza Mahatpur ,habitation Jamredanga under Mahatpur Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000497/2024-2025 | 273/NACD-II | 03/03/2025 | 61 | SIRCON ENGINEERING SERVICES | 23.06 | 0 | 0
3876 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | RESOURCE PAYMENT MAHATPUR | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | VCH/000887/2021-2022 | 258 | 26/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 61 | 0 | 0
3877 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP (Pressure Type ) of capacity 33.75 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Muktadaha Zone I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000025/2023-2024 | 1783/ND | 20/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 201.98 | 0 | 90
3878 | Nadia Division | RWS Nadia Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Ground Based Water Supply Scheme under Karimpur-I Block under Nadia Division, P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000297/2025-2026 | 3336/ND | 15/07/2025 | 180 | THE TOWER CONSTRUCTION | 31.3 | 0 | 20
3879 | Nadia Division | RWS Nadia Sub-Division | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000329/2025-2026 | .4686/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 79.19 | 0 | 40
3880 | Nadia Division | RWS Nadia Sub-Division | Laying of distribution system including specials,valves & pipe supporting structure all complete based on actual estimate & Providing FHTC for Muktadaha Zone-I Water Supply Scheme under Nadia Division. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000740/2021-2022 | 1314/ND | 21/03/2022 | 90 | UMWELT ENGINEERS PVT LTD | 257.59 | 228.85 | 95
3881 | Nadia Division | RWS Nadia Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Mukatadaha Zone-I PWSS under Karimpur-I Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM) . | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000762/2024-2025 | 425/ND | 27/01/2025 | 300 | GOPAL KIRTYANIYA | 32.88 | 0 | 95
3882 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000052/2022-2023 | 4286/ND | 29/09/2022 | 0 | Resource Division | 9.62 | 0 | 0
3883 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000122/2021-2022 | 1254/ND | 16/03/2022 | 0 | Resource Division | 10.25 | 0 | 0
3884 | Nadia Division | RWS Nadia Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | VCH/001055/2021-2022 | 613/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.52 | 0 | 0
3885 | Eastern Mechanical | RWS Nadia Sub-Division | Quotation for Load enhacement charges and security deposit for Muktadaha Zone- 1, PH- 1 site. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | BILL/01778/2024-2025 | BP-143-24-25 | 28/10/2024 | 0 | W.B.S.E.D.C.L (KARIMPUR C.C.C) | 0.18 | 0 | 0
3886 | Nadia Division | RWS Nadia Sub-Division | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000254/2024-2025 | 6305/ND | 26/09/2024 | 30 | IMAGIN | 34.21 | 0 | 100
3887 | Nadia Division | RWS Nadia Sub-Division | laying of distribution pipe line including supply of 63mm dia UPVC pipe at Fazlnagar W/S scheme under Nadia Division P.H.E. Directorate. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000318/2021-2022 | 1191/PH | 03/12/2021 | 10 | A.P. POWER & CONCRETE | 0.61 | 0.57 | 100
3888 | Nadia Division | RWS Nadia Sub-Division | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000329/2025-2026 | .4686/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 79.19 | 0 | 40
3889 | Nadia Division | RWS Nadia Sub-Division | Providing FHTC by Augmentation under jal swapna for Muktadaha Zone-II Water Supply scheme in Karimpur-I block of Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000672/2021-2022 | 695/ND | 15/02/2022 | 60 | M/S KRISHNA MONDAL | 43.92 | 38.44 | 99
3890 | Nadia Division | RWS Nadia Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 30 m3/hr capacity for Augmentation of Ground Based Water Supply Scheme at Muktadaha Zone-II including 3 Months Trial Run & 3 Years O&M to accommodate FHTC under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000737/2023-2024 | 1493/ND | 04/03/2024 | 720 | MONDAL PRECISION PRIVATE LIMITED | 162.44 | 0 | 0
3891 | Nadia Division | RWS Nadia Sub-Division | Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000769/2023-2024 | 1821/ND | 14/03/2024 | 31 | IMAGIN | 34.21 | 0 | 60
3892 | Nadia Division | RWS Nadia Sub-Division | Repairing and renovation of Elevated Reservoir , Pump House and allied works for Muktadaha Zone-II PWSS and Murutia PWSS within Karimpur-I Block and Karimpur-II Block Under Tehatta Sub-Division under Nadia Division P.H.E. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000790/2024-2025 | 762/ND | 19/02/2025 | 90 | DEBASIS SAMADDAR | 74.08 | 0 | 0
3893 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000032/2021-2022 | 452/ND | 31/01/2022 | 0 | Resource Division | 1.56 | 0 | 0
3894 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000055/2022-2023 | 4299/ND | 29/09/2022 | 0 | Resource Division | 0.79 | 0 | 0
3895 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000123/2021-2022 | 1251/ND | 16/03/2022 | 0 | Resource Division | 1.42 | 0 | 0
3896 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000148/2021-2022 | 1449/ND | 25/03/2022 | 0 | Resource Division | 9.36 | 0 | 0
3897 | Nadia Division | RWS Nadia Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | VCH/001056/2021-2022 | 614/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.57 | 0 | 0
3898 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer etc. for Augmentation to Accomodate FHTC at Pump House No.II (Zone-II) under Muktadaha W/S Scheme in Karimpur-I Block of Nadia District. NIET NO.- 13 of EE/EMD of 2022-23 (Sl. No.-02) | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000079/2022-2023 | 3802/EMD | 14/10/2022 | 30 | AMIT DAS | 5.96 | 5.96 | 90
3899 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator etc. for Augmentation to Accommodate FHTC at Pump House No.I Zone II under Muktadaha WS Scheme, Dist. Nadia under Eastern Mechanical Division, PHE Dte. NIET No. 22 OF EE/EMD OF 2022-23 (Sl. No.- 02) | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000704/2022-2023 | 6504/EMD | 01/12/2022 | 30 | WESTERN ENGINEERING CO. | 10.49 | 0 | 100
3900 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Nischintapur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000030/2020-2021 | 1072/NACD-II | 25/09/2020 | 15 | A.K ADHIKARY | 4.98 | 0 | 0
3901 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/001768/2022-2023 | 1120/EMD | 16/03/2023 | 30 | B.T. PROJECTS PVT. LTD | 91.82 | 0 | 60
3902 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work order for Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal. (From 01/04/2024- 30/06/2024) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000002/2024-2025 | 503/NACD-II | 01/04/2024 | 91 | SAJAL SAHA | 1.24 | 0 | 0
3903 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Bagakhali Zone-I H/W site with Plaster , Concrete and other allied works. Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000028/2024-2025 | 135/AE-II/NACD-II | 11/06/2024 | 30 | DEBASISH DEY | 2.79 | 0 | 0
3904 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Collection of Household Details at Prescribed Format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte. in soft copy for Bagakhali Zone-I PWSS under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000036/2024-2025 | 747/AE-I/NACD-II | 18/06/2024 | 60 | JOY GOPAL GUPTI | 4.84 | 0 | 98
3905 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Order for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte in soft copy for different PWSS under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000038/2023-2024 | 589/NACD-II | 22/05/2023 | 90 | JOY GOPAL GUPTI | 5.51 | 5.51 | 100
3906 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Bagakhali Zone-II H/W site with Plaster , Concrete,Earthwork in filling and other allied works under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000049/2024-2025 | 133/AE-II/NACD-II | 11/06/2024 | 30 | VAI ENTERPRISE | 4.81 | 0 | 0
3907 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-I (vILL- Sahapur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000053/2022-2023 | 223/NACD-II | 05/04/2022 | 90 | NANDY ENTERPRISES | 20.12 | 20 | 100
3908 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, Pincode:- 741101,West Bengal. (From 01/07/2024 to 30/06/2025) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000062/2024-2025 | 203/AE-II/NACD-II | 01/07/2024 | 365 | SAJAL SAHA | 4.98 | 0 | 0
3909 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Repair and Renovation work at Bagakhali Zone-I 2nd Pump house site with Reinforced Barbed Tape , Plaster and other allied works. Under Under Nadia Arsenic Division-II, P.H.E.Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000077/2024-2025 | 163/AE-II/NACD-II | 14/06/2024 | 15 | UJJWAL ROY | 0.63 | 0 | 100
3910 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bagakhali Zone-I) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000104/2023-2024 | 1149/NACD-II | 10/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100
3911 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Bagakhali Zone-I, (Block -Tehatta-I) piped water supply schemes | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000145/2021-2022 | 144/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 3.11 | 3.11 | 100
3912 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair and also piling work) at Bagakhali Zone-I ( Vill- Chhatina) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000208/2021-2022 | 996/NACD-II | 30/12/2021 | 45 | SANJIB DEY | 97.06 | 96.43 | 100
3913 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bagakhali Zone-I W/S Scheme of Tehatta-I Block Mouza Bagakhali,Sahapur,Chatiana of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000216/2023-2024 | 616/AE-I/NACD-II | 02/02/2024 | 15 | MALLICK ENTERPRISE | 0.93 | 0 | 100
3914 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bagakhali Zone-I W/S Scheme of Tehatta-I Block Mouza Ramjibanpur & Gopalpur of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000217/2023-2024 | 617/AE-I/NACD-II | 02/02/2024 | 15 | MALLICK ENTERPRISE | 0.86 | 0 | 100
3915 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair ) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000229/2021-2022 | 995/EE/NACD-II | 30/12/2021 | 45 | CHANDA CONSTRUCTION | 98.72 | 98.7 | 100
3916 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000230/2021-2022 | 01/EE/NACD-II | 03/01/2022 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 95.95 | 95.91 | 100
3917 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Bagakhali Zone-I Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000254/2022-2023 | 1009/NACD-II | 29/11/2022 | 60 | DEBASISH DEY | 15.07 | 15.01 | 95
3918 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Bagakhali Zone-I 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000259/2021-2022 | 41/AE-II/NACD-II | 17/02/2022 | 30 | SHYAM SUNDAR SAHA | 4.08 | 4.05 | 100
3919 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Bhagakhali Zone-I & Jitpur Water Supply Scheme of capacity 27 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000289/2023-2024 | 196/NACD-II | 12/02/2024 | 781 | SANDIP BISWAS | 103.73 | 0 | 100
3920 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Khanjipur & Bagakhali Zone-I, W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000303/2021-2022 | 768./NACD-II | 22/09/2021 | 45 | TARUN KUMAR BHATTACHARYA | 84.44 | 40.26 | 100
3921 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Bagakhali Zone-I PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000304/2024-2025 | 356/AE-II/NACD-II | 19/11/2024 | 7 | MAKALI ENGINEERING CORPORATION | 0.98 | 0 | 100
3922 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Bagakhali Zone-I and Bagakhali Zone-II Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000325/2024-2025 | 1562/NACD-II | 05/12/2024 | 360 | DEBASIS SAMADDAR | 157.57 | 0 | 40
3923 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte in soft copy for different PWSS under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000354/2022-2023 | 207./NACD-II | 07/02/2023 | 90 | JOY GOPAL GUPTI | 5.51 | 5.51 | 95
3924 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000396/2022-2023 | 414/NACD-II | 30/03/2023 | 366 | SAJAL SAHA | 4.98 | 2.55 | 100
3925 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000397/2022-2023 | 414./NACD-II | 30/03/2023 | 366 | SAJAL SAHA | 4.98 | 0 | 0
3926 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-I W/s Scheme (Vill- Sahapur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. & Barnia Pwss under Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000406/2021-2022 | 128_NACD-II | 21/02/2022 | 90 | M/S NANDY ENTERPRISES | 102.45 | 0 | 100
3927 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone X-A to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000344/2022-2023 | 254/ND | 16/01/2023 | 720 | SANJUKTA ENGINEERS | 157.12 | 82.54 | 98
3928 | Nadia Division | Tehatta Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-10A W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000406/2021-2022 | 320/TSD | 24/11/2021 | 30 | RADIANT | 2.66 | 2.66 | 100
3929 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000073/2023-2024 | 2295/ND | 29/05/2023 | 0 | Resource Division | 11.4 | 0 | 0
3930 | Central Drilling | Tehatta Sub-Division | PROVIDING 300MM NOMINAL DIA UPVC PIPE CONFIRMING TO IS:12818:2010 AND OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL KARIMPUR-I BLOCK UNDER NADIA DIVISION CMSD-II (D), CDD PHE DTE | Assistant Engineer | Junior Engineer | ORD/000130/2022-2023 | 287/CMSD -II (D) | 01/06/2022 | 15 | UNIVERSAL ENTERPRISES | 4.39 | 4.05 | 0
3931 | Central Drilling | Tehatta Sub-Division | PROVIDING 200MM NOMINAL DIA UPCVC PIPE CONFIRMING TO IS: 12818:2010 AND OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL KARIMPUR -II BLOCK UNDER NADIA DISTRICT CMSD-II(D) ,CDD PHE DTE | Assistant Engineer | Junior Engineer | ORD/000131/2022-2023 | 282/ CMSD-II (D) | 01/06/2022 | 15 | UNIVERSAL ENTERPRISES | 4.44 | 0.72 | 0
3932 | Central Drilling | Tehatta Sub-Division | PROVIDING DRILLING CREWS AND OTHER MATERIALS FOR CONSTRUTION OF TUBE WELL 300 MM X 200MM X250 MTR DEPTH BY DEPARTMENTAL RIG MACHINE FOR KARIMPUR -II BLOCK UNDER NADIA DIST, CMSD-II(D) ,CDD,PHE DTE | Assistant Engineer | Junior Engineer | ORD/000132/2022-2023 | 280/CMSD-II (D) | 01/06/2022 | 15 | UNIVERSAL ENTERPRISES | 3.52 | 3.52 | 0
3933 | Central Drilling | Tehatta Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JALANGI W/S SCH, KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000316/2022-2023 | 1198/CDD | 11/11/2022 | 30 | DIPALI CONSTUCTION | 10.17 | 7.44 | 0
3934 | Central Drilling | Tehatta Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JALANGI W/S SCH, NADIA DISTRICT UNDER CMSD-II(D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000329/2022-2023 | 536/CMSD-II | 02/12/2022 | 10 | DIPALI CONSTUCTION | 0.98 | 0.74 | 0
3935 | Central Drilling | Tehatta Sub-Division | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR JALANGI W/S SCH NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000350/2022-2023 | 542/CMSD-II | 07/12/2022 | 10 | ASHUTOSH DAS & CO | 0.98 | 0.7 | 0
3936 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No. I , II under KARIMPUR JALANGI Zone X A WS Scheme, Block Karimpur-II, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-14) | Assistant Engineer | Junior Engineer | ORD/000894/2022-2023 | 162/EMD | 06/01/2023 | 30 | S.B.ENTERPRISE | 9.73 | 0 | 70
3937 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 15 m3/hr at Gede Water Supply Scheme within Krishnaganj Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000195/2024-2025 | 6222/ND | 23/09/2024 | 180 | GHOSH ENTERPRISE | 137.17 | 0 | 0
3938 | Nadia Division | Krishnanagar Sub-Division | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Gede W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 03) | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000342/2021-2022 | 906/KSD | 29/11/2021 | 15 | HORIZEN | 2.48 | 2.39 | 100
3939 | Nadia Division | Krishnanagar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
3940 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000150/2023-2024 | 261/ND | 11/01/2024 | 0 | Resource Division | 3.31 | 0 | 0
3941 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000151/2022-2023 | 120/ND | 05/01/2023 | 0 | Resource Division | 10.97 | 0 | 0
3942 | Central Drilling | Krishnanagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Gede W/S Scheme (TW-I) , Krishanjganj Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000132/2023-2024 | 1233/CDD | 04/09/2023 | 370 | DEV AND COMPANY | 18.88 | 0 | 100
3943 | Eastern Mechanical | Krishnanagar Sub-Division | WBSEDCL Quotation for New Service Connection to the newly constructed Head Work Site under GEDE W/S Scheme in Krishnaganj Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3004956395) | Assistant Engineer | Junior Engineer,Junior Engineer 4 | BILL/01889/2024-2025 | BP-165-24-25 | 25/11/2024 | 0 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 6.04 | 0 | 0
3944 | Eastern Mechanical | Krishnanagar Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Gede ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte. SM/10573 | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000180/2025-2026 | 1117/EMD | 04/06/2025 | 90 | KUNDU ELECTRICAL ENTERPRISE | 17.48 | 0 | 0
3945 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under GEDE W/S Scheme, Block- Krishnaganj , Dist. - Nadia. NIET No. 33 of EE/EMD of 2022-23 (Sl. No. -08) | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/001921/2022-2023 | 1177/EMD | 21/03/2023 | 30 | PS AND ASSOCIATES | 13.6 | 0 | 0
3946 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP (Gravity Type) of capacity 93.00 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Senpur PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000028/2023-2024 | 1786/ND | 20/04/2023 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 234.23 | 41.65 | 57
3947 | Nadia Division | RWS Nadia Sub-Division | Renovation of Settling Tank including construction of column and RCC wall inside the Settling Tank in Senpur Water Supply Scheme under RWS Nadia Sub Division under Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000070/2024-2025 | 3989/ND | 22/07/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 17.12 | 0 | 100
3948 | Nadia Division | RWS Nadia Sub-Division | Additional work of providing FHTC and additional work of Laying Distribution System at Shimultala village within Krishnanagar-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000105/2025-2026 | 2851/ND | 18/06/2025 | 75 | SANDIP BISWAS | 46.75 | 0 | 0
3949 | Nadia Division | RWS Nadia Sub-Division | Construction Of Chlorine storage Room (2m X 2m) At H/w Site of 13nos PWSS Under RWS Nadia Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000107/2025-2026 | 2853/ND | 18/06/2025 | 60 | ANJALI ENTERPRISE | 10.53 | 0 | 0
3950 | Nadia Division | RWS Nadia Sub-Division | Additional work of Laying of pipe line including providing FHTC and all allied work in connection with Augmentation of Senpur PWSS within Krishnagar-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000172/2024-2025 | 5036/ND | 13/09/2024 | 450 | ROY ASSOCIATES | 56.45 | 0 | 20
3951 | Nadia Division | RWS Nadia Sub-Division | Repair and Renovation Works of OHR, Boundary Wall at Head Work Site and Tube Well Site, Pump House at Head Work Site and Tube Well Sites, Contruction of Service Road at Head Work Site of Senpur Water Supply Scheme within Krishnagar -I Block under RWS Nadia Sub-Division under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000233/2024-2025 | 6410/ND | 01/10/2024 | 360 | M/S INDUSTRIAL CONSTRUCTION | 29.02 | 0 | 50
3952 | Nadia Division | RWS Nadia Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site of Senpur Piped Water Supply Scheme under RWS Nadia Sub Division, Nadia, P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000299/2024-2025 | 6757/ND | 11/11/2024 | 60 | B.S. ENTERPRISE | 24.86 | 0 | 60
3953 | Nadia Division | RWS Nadia Sub-Division | Laying of Distribution system including specials, valves & pipe supporting structure all complete based on actual estimate & providing FHTC for Senpur Water supply Scheme in Nadia District under Nadia Division. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000711/2021-2022 | 1065/ND | 04/03/2022 | 90 | RADIANT | 388.55 | 280.25 | 80
3954 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | RTOR000103/2021-2022 | 1021/ND | 03/03/2022 | 0 | Resource Division | 15.96 | 0 | 0
3955 | Nadia Division | RWS Nadia Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | VCH/001064/2021-2022 | 622/PFMS | 14/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.12 | 0 | 0
3956 | Eastern Mechanical | RWS Nadia Sub-Division | WBSEDCL's Quotation of New Service Connection in Bulk Contract Demand to the Head Work Site under Senpur W/S Scheme in Krishnagar - I Block, PHE Dte., Dist.- Nadia. (Application No. 3004752314) | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | BILL/00726/2024-2025 |  | 18/06/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 3.47 | 0 | 0
3957 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No.I under Senpur W/S Scheme in Krishnagar-I Block of Nadia District. NIET No.- 13 of EE/EMD of 2022-23 (Sl. No.-03) | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000080/2022-2023 | 3803/EMD | 14/10/2022 | 30 | S.S.ENTERPRISES | 10.65 | 9.26 | 10
3958 | Eastern Mechanical | RWS Nadia Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer etc. for Augmentation to Accomodate FHTC at Pump House No.II under Senpur W/S Scheme in Krishnagar-I Block of Nadia District. NIET NO.- 13 of EE/EMD of 2022-23 (Sl. No.-04) | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/000081/2022-2023 | 3804/EMD | 14/10/2022 | 30 | BISALAXMI ENTERPRISE | 6.12 | 6.02 | 0
3959 | Eastern Mechanical | RWS Nadia Sub-Division | Supplementary works to completion of ongoing FHTC-related work at PH-II of Senpur W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/001405/2023-2024 | 598/EMSD-II | 22/08/2023 | 15 | BISALAXMI ENTERPRISE | 0.27 | 0 | 100
3960 | Eastern Mechanical | RWS Nadia Sub-Division | Supplementary works to completion of ongoing FHTC-related work at PH-I of Senpur W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer Krishnanagar - I Block | ORD/001715/2023-2024 | 753/EMSD-II | 09/10/2023 | 10 | S.S.ENTERPRISES | 0.88 | 0 | 100
3961 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 500 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall Pump House at Digha Zone-XIII under Surface W/S Scheme of Haringhata-Chakdah Part under NAD-I PHE Dte (Sl.no.06) | Assistant Engineer-I | Junior Engineer-II | ORD/000072/2022-2023 | 1691/NAD-I | 08/09/2022 | 60 | CHOWDHURY & CO. | 28.14 | 27.56 | 100
3962 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 900 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House at Subarnapur Zone XI under Surface WS Scheme of Haringhata Chakdah Part under NAD -I PHE Dte (sl.no.07) | Assistant Engineer-I | Junior Engineer-II | ORD/000131/2022-2023 | 3035 /NAD-I | 09/11/2022 | 60 | DIVINE | 33.26 | 30.28 | 100
3963 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 600 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Birohi Zone-XI under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | Assistant Engineer-I | Junior Engineer-II | ORD/000141/2022-2023 | 3157/NAD-I | 25/11/2022 | 60 | ONKAR ENTERPRISE | 24.53 | 24.44 | 100
3964 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XIII (Digha) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 11) | Assistant Engineer-I | Junior Engineer-II | ORD/000160/2021-2022 | 427/NAD-I | 07/03/2022 | 60 | SANJIB DEY | 81.56 | 77.79 | 100
3965 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-X (Subarnapur) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No. 15) | Assistant Engineer-I | Junior Engineer-II | ORD/000161/2021-2022 | 428/NAD-I | 07/03/2022 | 60 | IJABUL SEKH | 95.12 | 94.63 | 100
3966 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work for Zone-XI (Birohi) at Haringhata Block under Jal Jeevan Mission (JJM) by Augmentation of Surface Water Based PWSS for Haringhata Zone-X, (Subarnapur), Zone-XI (Birohi) and Zone-XIII (Digha) Part-III under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000173/2022-2023 | 38/AE-I/NAD-I | 07/01/2023 | 15 | J & T ENTERPRISE | 4.83 | 4.83 | 100
3967 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XI (Birohi) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 13) | Assistant Engineer-I | Junior Engineer-II | ORD/000174/2021-2022 | 465/NAD-I | 10/03/2022 | 60 | GHOSH CONSTRUCTION | 91.98 | 87.29 | 100
3968 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work for Zone-X (Subarnapur) at Haringhata Block under Jal Jeevan Mission (JJM) by Augmentation of Surface Water Based PWSS for Haringhata & Chakdah (Part) for Zone-X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha) Part-III under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000174/2022-2023 | 39/AE-I/NAD-I | 07/01/2023 | 15 | M/S DIPAK ENTERPRISE | 4.83 | 4.83 | 100
3969 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of Pipeline at Ayeshpur More (Near Petrol Pump) at NH-34 and other allied works under JalJeevan Mission (JJM) for Zone-XI at Birohi at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-XI, Birohi under JJM underNadia Arsenic Division-I, PHE Dte. (SL.02) | Assistant Engineer-I | Junior Engineer-II | ORD/000246/2022-2023 | 512 / NAD-I | 10/03/2023 | 30 | M/S DIPAK ENTERPRISE | 64.25 | 7.83 | 35
3970 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of Pipeline at Birohi More(Underpass) at NH-34 and other allied works under Jal Jeevan Mission (JJM) for Zone-XI at Birohi at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-XI,Birohi under JJM under Nadia Arsenic Division-I, PHE Dte. (SL.09) | Assistant Engineer-I | Junior Engineer-II | ORD/000247/2022-2023 | 513 /NAD-I | 10/03/2023 | 30 | M/S DIPAK ENTERPRISE | 66.19 | 66.18 | 100
3971 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission for Zone-XIII, (Digha), Part-III at Haringhata Block by augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.22) | Assistant Engineer-I | Junior Engineer-II | ORD/000261/2022-2023 | 828/NAD-I | 31/03/2023 | 21 | NISHITH BANERJEE | 14.03 | 0 | 100
3972 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Baruipara to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000132/2022-2023 | 3798/ND | 02/09/2022 | 1260 | M/S S.S ENTERPRISE | 732.02 | 490.7 | 74
3973 | Nadia Division | Tehatta Sub-Division | Additional pipeline for increasing Functionality in Basatipara, Mojlishpur and Borojangal villages through MANIFOLD under Karimpur-I Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM). | Assistant Engineer | Junior Engineer | ORD/000158/2025-2026 | 3256/ND | 10/07/2025 | 180 | GOPAL KIRTYANIYA | 15.51 | 0 | 20
3974 | Nadia Division | Tehatta Sub-Division | Laying of additional pipe lines and allied works to increase the functionality in Brojonathpur, Gandhina villages under Karimpur-I Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000328/2025-2026 | 4685/4533/P-3/ND | 09/10/2025 | 90 | JOY HIND TUBEWELL'S | 46.3 | 0 | 40
3975 | Nadia Division | Tehatta Sub-Division | Name of Work : Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Baruipara W/S Scheme in Karimpur-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000368/2021-2022 | 289/TSD | 24/11/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.82 | 4.82 | 100
3976 | Nadia Division | Tehatta Sub-Division | Laying pipe line for distribution system and rising main for Baruipara PWSS under augmentation of Baruipara PWSS under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000474/2024-2025 | 7262/ND | 13/12/2024 | 450 | M/S S.S ENTERPRISE | 54.36 | 0 | 0
3977 | Nadia Division | Tehatta Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Baruipara Ground Based Water Supply Scheme under Karimpur-I Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Baruipara at Karimpur-I Block by Augmentation of Ground Water based PWSS for Baruipara Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000638/2024-2025 | 7364/ND | 18/12/2024 | 60 | M/S ARATI ENTERPRISE | 23.38 | 0 | 0
3978 | Nadia Division | Tehatta Sub-Division | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangement and consruction of Boundary wall at 4th Tube Well Site of Baruipara Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000751/2023-2024 | 1626/ND | 07/03/2024 | 810 | BISHAL CONSTRUCTION | 10.94 | 0 | 100
3979 | Nadia Division | Tehatta Sub-Division | Providing FHTC & Alied Pipelines and other Works for left out habitation under Karimpur -I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000792/2024-2025 | 7464/ND | 20/12/2024 | 90 | APURBA MANDAL | 299.14 | 0 | 0
3980 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000007/2023-2024 | 1850/ND | 26/04/2023 | 0 | Resource Division | 56.81 | 0 | 0
3981 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000058/2022-2023 | 4307/ND | 29/09/2022 | 0 | Resource Division | 41.46 | 0 | 0
3982 | Central Drilling | Tehatta Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Baruipara W/S Scheme (T/W-I) , Karimpur-I Block under Nadia District, Central Drilling Division, P.H.E. Dte.(2ed Call) | Assistant Engineer | Junior Engineer | ORD/000092/2023-2024 | 507/CDD | 01/06/2023 | 303 | UNIVERSAL ENTERPRISES | 18.86 | 0 | 100
3983 | Eastern Mechanical | Tehatta Sub-Division | Quotation charges for new service connection and security deposit at Baruipara PH-IV under EMSD-III,Nadia | Assistant Engineer | Junior Engineer | BILL/02256/2024-2025 | BP-182 | 13/12/2024 | 0 | WBSEDCL KARIMPUR CCC | 3.86 | 0 | 0
3984 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No. I,II III under Baruipara WS Scheme, Block Karimpur I, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-13) | Assistant Engineer | Junior Engineer | ORD/000893/2022-2023 | 161-EMD | 06/01/2023 | 726 | P.K. ENGINEERING | 22.81 | 0 | 100
3985 | Eastern Mechanical | Tehatta Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-IV under Baruipara ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. 2024_PHED_664112_2 | Assistant Engineer | Junior Engineer | ORD/003002/2023-2024 | 924/EMD | 15/03/2024 | 30 | P.K. ENTERPRISE | 7.36 | 0 | 60
3986 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
3987 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamgachi Zone-II to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-II) | Assistant Engineer | Junior Engineer 2 | ORD/000300/2022-2023 | 5354/ND | 22/12/2022 | 1080 | JOY HIND TUBEWELL'S | 340.71 | 268.53 | 100
3988 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamgachi Zone-I to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-II) | Assistant Engineer | Junior Engineer 2 | ORD/000317/2022-2023 | 16/ND | 03/01/2023 | 1078 | KINGS & CO. | 415.48 | 242.44 | 85
3989 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000034/2023-2024 | 1884/ND | 26/04/2023 | 0 | Resource Division | 44.93 | 0 | 0
3990 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000069/2023-2024 | 2312/ND | 29/05/2023 | 0 | Resource Division | 42.04 | 0 | 0
3991 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2 | RTOR000114/2023-2024 | 28/ND | 03/01/2024 | 0 | Resource Division | 32.2 | 0 | 0
3992 | Nadia Division | RWS Nadia Sub-Division | Laying of distribution system including specials, valves & pipe supporting structure all complete and providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of ground based water supply scheme at Naserkhuli Zone-I to accommodate FHTC within Ranaghat-II Dev. block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000151/2022-2023 | 4238/ND | 28/09/2022 | 883 | SUPRITI ENTERPRISE | 533.43 | 0 | 100
3993 | Nadia Division | RWS Nadia Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
3994 | Nadia Division | RWS Nadia Sub-Division | Repairing of PH-III and Construction of Sanitary arrangement under augmentation of Naserkuli Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000387/2024-2025 | 1423/RSD | 19/11/2024 | 45 | M. ENTERPRISE | 2.14 | 0 | 100
3995 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000100/2022-2023 | 4931/ND | 25/11/2022 | 0 | Resource Division | 166.85 | 0 | 0
3996 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill for new service connection at Sanatanpur PH- II,LJ no. 24 KH-1609, Plot-160 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00110/2023-2024 | 21/PFMS/EMD | 11/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.68 | 0 | 0
3997 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill for new service connection at Sanatanpur PH- I,LJ no. 24 KH-995, Plot-658 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00111/2023-2024 | 20/PFMS/EMD | 08/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.98 | 0 | 0
3998 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under SANATANPUR W/S Scheme (Block : Hanskhali) Dist.- Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000012/2023-2024 | 1575/EMD | 24/04/2023 | 30 | PADMA ENGINEERING CO. | 18.99 | 18.42 | 100
3999 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Sanatanpur Piped Water SupplyScheme, Block: Hanskhali, Dist. Nadia Under EMD, PHE Dte. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000014/2023-2024 | 1577/EMD | 24/04/2023 | 30 | M/S. G.P. ENTERPRISE | 41.76 | 0 | 0
4000 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Sanatanpur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000014/2022-2023 | 219/NACD-II | 05/04/2022 | 60 | CHANDAN ROY | 5.38 | 5.33 | 100
4001 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Sanatnpur water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000051/2022-2023 | 18/AE-II/NACD-II | 11/04/2022 | 60 | CHANDAN ROY | 2.83 | 2.82 | 100
4002 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of of site locations under Hanskhali Block of Nadia District through Jadavpur University. (Name of Scheme Sanatanpur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000054/2023-2024 | 868/NACD-II | 10/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
4003 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Sanatanpur Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000064/2022-2023 | 24/AE-II/NACD-II | 18/04/2022 | 30 | ARIT KUMAR PAL | 4.96 | 0 | 100
4004 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Sanatanpur and adjoining mouzas under Sanatanpur Water Supply Scheme of Hanskhali Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000071/2022-2023 | 305/NACD-II | 20/05/2022 | 90 | A.P. POWER & CONCRETE | 139.9 | 86.56 | 100
4005 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction for priliminary work of the approch road at Head Works site of Sanatanpur Water Supply Scheme in Hanskhali Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000112/2023-2024 | 416_1/AE_I/NACD-II | 08/08/2023 | 15 | KANIKA CONSTRUCTION | 0.99 | 0 | 0
4006 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earth work in filling in ditches at Sanatanpur H/W site & 2nd Tube Well Site for development of land in connection with proposed T/W Sinking & Pump House construction at Sanatanpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000127/2022-2023 | 63/AE-II/NACD-II | 28/06/2022 | 20 | SUMIT GHOSH | 1.23 | 0 | 100
4007 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Sanatanpur and Hatkhola Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000136/2022-2023 | 433/NACD-II | 07/07/2022 | 60 | B.M. ENGINEERING & CONSTRUCTION | 42.16 | 0 | 100
4008 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Sanatanpur Water Supply Scheme of Hanskhali Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000202/2022-2023 | 631/NACD-II | 06/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.57 | 3.57 | 100
4009 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 87 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Matiary Water Supply Scheme in Krishnaganj block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000217/2024-2025 | 1311/NACD-II | 20/09/2024 | 180 | JOY HIND TUBEWELLS | 232.26 | 0 | 0
4010 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 35 cum/Hour capacity for Sanatanpur Water Supply Scheme within Hanskhali block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000220/2024-2025 | 1190/NACD-II | 02/09/2024 | 180 | MONDAL PRECISION PRIVATE LIMITED | 165.43 | 0 | 0
4011 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Shyamnagar Water Supply Scheme of capacity 67 Cu.m/hr in Krishnaganj Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000286/2023-2024 | 185/NACD-II | 09/02/2024 | 60 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 194.41 | 0 | 100
4012 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Sanatanpur W/s Scheme, Sikra W/s Scheme, Suruppur W/s Scheme | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000304/2021-2022 | 253/AE-I/NACD-II | 25/02/2022 | 15 | G. MITRA & ASSOCIATES | 2.29 | 2.29 | 100
4013 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Sanatanpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000325/2022-2023 | 89/NACD-II | 10/01/2023 | 60 | NISHITH BANERJEE | 18.62 | 18.55 | 85
4014 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Additional Parallal Pipeline Laying of Distribution system for smooth supply of water without damaging the higher dia pipelines and Providing Functional House Hold Tap Connection (FHTC) for Sanatanpur and adjoining mouzas under Sanatanpur Water Supply Scheme of Hanskhali Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000346/2022-2023 | 151/NACD-II | 17/01/2023 | 20 | GHOSH ENTERPRISE | 8.77 | 8.76 | 90
4015 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Sanatanpur water supply scheme of Haskhali Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000385/2022-2023 | 383/NACD-II | 24/03/2023 | 1096 | SUBHASH BOSE | 119.12 | 0 | 35
4016 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Urgent piling work for protection of hydraulic main in between 4th Pump House to 3rd Pump House pond site at Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000404/2024-2025 | 411/AE-II/NACD-II | 31/01/2025 | 45 | VAI ENTERPRISE | 0.99 | 0 | 100
4017 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000012/2022-2023 | 404/NACD-II | 04/07/2022 | 0 | Resource Division | 55.89 | 0 | 0
4018 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | VCH/000236/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
4019 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | VCH/000343/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
4020 | Nadia Division | Krishnanagar Sub-Division | Restoration of road from Dhubulia 33 KV Substation to Sujanpur (WB-14-250) | Assistant Engineer |  | BILL/00505/2024-2025 | 301/PFMS | 02/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 18.01 | 0 | 0
4021 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000196/2023-2024 | 3537/ND | 11/08/2023 | 1147 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 0 | 20
4022 | Nadia Division | Krishnanagar Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
4023 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | Assistant Engineer |  | ORD/000706/2024-2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0
4024 | Nadia Division | Krishnanagar Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 1/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .02 ) | Assistant Engineer |  | ORD/000710/2021-2022 | 204/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.6 | 4.57 | 100
4025 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000159/2022-2023 | 116/ND | 05/01/2023 | 0 | Resource Division | 314.2 | 0 | 0
4026 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 0 | 47
4027 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 9A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000782/2021-2022 | 132/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.51 | 4.44 | 100
4028 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000128/2022-2023 | 108/ND | 05/01/2023 | 0 | Resource Division | 297.12 | 0 | 0
4029 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) |  |  | ORD/000127/2020-2021 | 90/NAD-I | 22/01/2021 | 60 | APURBA MANDAL | 70.37 | 140.04 | 100
4030 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. (Sl no.-02) Tender No. 229/NAD-I/2020-2021. |  |  | ORD/000186/2020-2021 | 291/NAD-I | 04/02/2021 | 45 | CHANDAN ROY | 42.81 | 4.87 | 0
4031 | Nadia Division | Kalyani Sub-Division II | New Service Connection charges for Uttar Bishunupur Mini Piped water supply scheme | Assistant Engineer | Junior Engineer 2,Junior Engineer 4 | BILL/00416/2024-2025 | 243/PFMS | 13/09/2024 | 0 | W.B.S.E.D.C.L (GROUP ARANGHATA C.C.C) | 0.21 | 0 | 0
4032 | Nadia Division | Kalyani Sub-Division II | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Mini Piped Water Supply Scheme Gazna (Part) (100 Households) to accommodate FHTC in Hanskhali block & Providing FHTC and allied works for- Ground Water Based Mini Piped Water Supply Scheme in Arsenic affected area at Uttar Bishnupur, Block : -Ranaghat-II, Nadia District under Nadia Division P.H.E Dte. | Assistant Engineer | Junior Engineer 2,Junior Engineer 4 | ORD/000090/2023-2024 | 3024/ND | 14/07/2023 | 366 | ABDUL ALIM MONDAL | 79.83 | 0 | 78
4033 | Nadia Division | Kalyani Sub-Division II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 2,Junior Engineer 4 | RTOR000156/2023-2024 | 271/ND | 11/01/2024 | 0 | Resource Division | 0.6 | 0 | 0
4034 | Nadia Division | Tehatta Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 200 Cum Capacity 20 Mtr. height RCC Over Head Reservoir (Excluding Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for construction of one no. 200 Cum OHR of Staging Height 20 Mtr. for Augmentation of Ground Based Water Supply Scheme at Narayanpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000437/2022-2023 | 966/ND | 09/03/2023 | 1096 | M/S S.S ENTERPRISE | 759.95 | 128.49 | 55
4035 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000045/2023-2024 | 1906/ND | 27/04/2023 | 0 | Resource Division | 18.64 | 0 | 0
4036 | Nadia Division | Tehatta Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000087/2023-2024 | 2315/ND | 29/05/2023 | 0 | Resource Division | 0.92 | 0 | 0
4037 | Eastern Mechanical | Tehatta Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under NARAYANPUR W/S Scheme, Block- Karimpur II , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer | ORD/000018/2023-2024 | 1581/EMD | 24/04/2023 | 30 | CHANDIMATA ELECTRICALS | 15.43 | 0 | 0
4038 | Nadia Division | Debgram Sub-Division | RESTORATION OF ROAD FLANK OF DEBAGRAM KATWAGHAT ROAD FROM CH. 0.00 KM TO 17.40 KMP. | Assistant Engineer | Junior Engineer 1 | BILL/01487/2023-2024 | 599/PFMS | 14/03/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 8.33 | 0 | 0
4039 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 205.5 | 47
4040 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 2A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000767/2021-2022 | 117/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.13 | 4.09 | 100
4041 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Augmentation of pipeline and FHTC including repair of Boundary wall at Saguna, Aluipara & Hijuli Mouzas and Parbatipur & Gopalpur Mouzas under Parbatipur Piped Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000011/2025-2026 | 123/NAD-I | 22/04/2025 | 60 | CHOWDHURY & CO. | 85.69 | 0 | 0
4042 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Interconnection of pipeline from manifold to different direction of distrtibution pipeline including laying of balance pipeline and FHTC along with allied works at Nrisinghapur (Chandkuri) under Parbatipur Piped Water Supply Scheme at Parbatipur & Gopalpur Mouzas under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 03) | Assistant Engineer | Junior Engineer | ORD/000052/2025-2026 | 529/NAD-I | 03/07/2025 | 90 | CHOWDHURY & CO. | 192.83 | 0 | 0
4043 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Laying of Rising Main, Laying distribution system and Providing FHTC (Functional Household Tap Connection), Soil Investigation for the work of construction of 400 cum OHR staging height 20 mtr. Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and construction of Pump House, Boundary Wall, Service Road and other allied Works at Head Work & 2nd site under Jal Jeevan Mission for Parbatipur Zone-II Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte.(Sl. NO. 06) | Assistant Engineer | Junior Engineer | ORD/000094/2023-2024 | 1740/NAD-I | 19/07/2023 | 1095 | H I ENTERPRISE | 628.88 | 0 | 61
4044 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Laying of Rising Main, Laying distribution system and Providing FHTC (Functional Household Tap Connection), Soil investigation for the work of construction of 400 cum OHR staging height 20 mtr., Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and Construction of Pump house, Boundary Wall, Service Road and other allied Works at Head work & 2nd site under Jal Jeevan Mission for Parbatipur Zone- I Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000096/2023-2024 | 1743/NAD-I | 19/07/2023 | 730 | M/S TARAK CHANDRA PAUL | 633.23 | 0 | 54
4045 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Laying of pipeline for functionally of FHTC including new FHTC connection at Phuliapara, Durlav para, Narasinghanagar, Chapatala & Beharia Mouza under Fulia G.P. & Gopalpur & Parbatipur mouza under Parbatipur PWSS under Nadia Arsenic Division-I, P.H.E. Dte. (2nd Call) [Sl. No. 04] | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 664/NAD-I | 21/07/2025 | 120 | BUDDHADEV MONDAL | 87.35 | 0 | 0
4046 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Preparation of Detailed Project Report (DPR) for Parbatipur Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(SL.05) | Assistant Engineer | Junior Engineer | ORD/000181/2022-2023 | 66 / NAD-I | 20/01/2023 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 10.97 | 10.87 | 100
4047 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000003/2024-2025 | 847/NAD-I | 04/06/2024 | 0 | Resource Division | 37.63 | 0 | 0
4048 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000005/2024-2025 | 1750/NAD-I | 25/10/2024 | 0 | Resource Division | 39 | 0 | 0
4049 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000020/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 33.39 | 0 | 0
4050 | Eastern Mechanical | Eastern Mechanical Sub Division-II | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation NEW Tube Well in connection to Accommodate FHTC at Pump House No.-I & II (Zone-I and II) under Parbatipur ground water based water supply scheme under Block_ Ranaghat-I Dist. - Nadia under EMD, PHE Dte. (SM/14422) | Assistant Engineer | Junior Engineer | ORD/000651/2024-2025 | 2688/EMD | 20/11/2024 | 30 | GOENKA ENTERPRISE | 47.91 | 0 | 0
4051 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 80
4052 | Nadia Arsenic Civil Division II | Eastern Mechanical Sub Division-III | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Dharammpur (Part-A) of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 583/NACD-II | 17/05/2023 | 1080 | PAPAN ROY | 25.74 | 0 | 25
4053 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Quotation for New service connection charges and security deposit for Satiakhali Part- B. | Assistant Engineer | Junior Engineer | BILL/02318/2024-2025 | BP-200-24-25 | 17/12/2024 | 0 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 0.79 | 0 | 0
4054 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 80
4055 | Nadia Arsenic Civil Division II | Eastern Mechanical Sub Division-III | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Shatikhali (Part-B) of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer | Junior Engineer | ORD/000023/2023-2024 | 563/NACD-II | 11/05/2023 | 90 | ASIT PRAMANIK | 29.47 | 0 | 0
4056 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Quotation for new service connection and security deposit at Java (Part-B) PWSS, Krishnanagar- I | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer | BILL/01582/2024-2025 | BP-107-24-25 | 09/09/2024 | 0 | W.B.S.E.D.C.L (GROUP KRISHNAGAR ROAD STATION C.C.C) | 0.1 | 0 | 0
4057 | Eastern Mechanical | Eastern Mechanical Sub Division-III | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer | ORD/000355/2023-2024 | 4491/EMD | 14/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 80
4058 | Nadia Arsenic Civil Division II | Eastern Mechanical Sub Division-III | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Jaba (Part-B) of Krishnagar-I Block under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer | ORD/000027/2023-2024 | 567/NACD_II | 11/05/2023 | 813 | SUMIT GHOSH | 28.39 | 0 | 100
4059 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Improvement of connecting road within Ichapur Road and the Head Works site of Madhabpur and Bahirgachhi Zone-I Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000004/2025-2026 | 17/AE-I/NACD-II | 11/04/2025 | 60 | GHOSH ENTERPRISE | 4.84 | 0 | 0
4060 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bahirgachi Zone-I) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000095/2023-2024 | 1115/NACD-II | 06/10/2023 | 21 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100
4061 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Bahirgachi Zone-I, (Block - Chapra) piped water supply schemes | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000152/2021-2022 | 151/AE-I/NACD-II | 16/11/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.61 | 2.61 | 100
4062 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bahirgachi Zone-I W/S Scheme of Chapra Block Mouza Mathurapur & Kukradaha of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000212/2023-2024 | 613/AE-I/NACD-II | 02/02/2024 | 15 | MALLICK ENTERPRISE | 0.97 | 0 | 100
4063 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bahirgachi Zone-I W/S Scheme of Chapra Block Mouza Bahirgachi of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000214/2023-2024 | 614/AE-I/NACD-II | 02/02/2024 | 15 | P. BISWAS & CO | 0.45 | 0 | 100
4064 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bahirgachhi Zone-I ( Vill-Kukra Daha) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000215/2022-2023 | 821/NACD-II | 10/11/2022 | 60 | ABDUL ALIM MONDAL | 14.27 | 14.23 | 100
4065 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline at BAHIRGACHI ZONE-I ( Vill- BAHIRGACHI AND SURROUNDING AREA) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000253/2023-2024 | 230/NACD-II | 21/02/2024 | 45 | SAFTI PRIVATE LIMITED | 38.98 | 0 | 0
4066 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of CIDF Sluice valve and DI specials for vavle for facilitate Functional House Hold Connection of Bahirgachhi Zone-I Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000305/2021-2022 | 280/AE-I/NACD-II | 04/03/2022 | 5 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.88 | 4.88 | 100
4067 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Bahirgachi Z-I Water Supply Scheme of capacity 40 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000316/2023-2024 | 207/NACD-II | 15/02/2024 | 90 | SATYABRATA CHAKRABORTY | 143.08 | 0 | 0
4068 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Supply of CIDF Sluice valve and DI specials for vavle for facilitate Functional House Hold Connection of Bahirgachhi Zone-I Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000318/2021-2022 | 302/AE-I/NACD-II | 17/03/2022 | 5 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.77 | 4.77 | 100
4069 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Pipe Line along with FHTC reconnection due to construction of drain at Bagmara Bazar at Bahirgachi Zone I W/s Scheme at Chapra block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000359/2024-2025 | 1099/AE-I/NACD-II | 31/12/2024 | 30 | SUBHAJIT SAHA | 0.96 | 0 | 100
4070 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Bahirgachhi Zone-I W/s Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000370/2022-2023 | 349/NACD-II | 22/03/2023 | 20 | SAMARESH GHOSH | 1.04 | 1.03 | 85
4071 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Comprehensive augmentation in technical regards including aquifer management with extraction, compliance of Ground water contamination removal as per IS 10500 with subsequent amendments and composite RCC Cum masonry structures at Mouza- Mathurapur (under Bahirgachi zone I Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000450/2024-2025 | 330/NACD-II | 11/03/2025 | 60 | TARUN GHOSH | 54.03 | 0 | 0
4072 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Gravity Type) of capacity 57 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Itla PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000083/2023-2024 | 2996/ND | 13/07/2023 | 900 | TARUN KUMAR BHATTACHARYA | 82.59 | 0 | 50
4073 | Eastern Mechanical | Krishnanagar Sub-Division | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at ITLA (PHASE-II) Piped Water Supply Scheme, Block: KRISHNANAGAR-I, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/001756/2023-2024 | 6366/EMD | 17/10/2023 | 728 | JAL PRAVAHIKA PVT. LTD. | 41.6 | 0 | 100
4074 | Nadia Division | RWS Nadia Sub-Division | Laying of 160 mm dia HDPE pipe line, 75 mm & 125 mm UPVC Pipe line for Augmentation of Rising Main System for distribution pipeline with interconnection along with road restoration at village Dogachhi, Block Karimpur-II under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000017/2025-2026 | 1803/ND | 22/04/2025 | 180 | SUBHASH BOSE | 32.54 | 0 | 51
4075 | Nadia Division | RWS Nadia Sub-Division | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site of Teinpur Zone-II [Phase-II] Ground Based Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/000519/2022-2023 | 1218/ND | 21/03/2023 | 60 | JOY HIND TUBEWELL'S | 14.37 | 9.13 | 85
4076 | Eastern Mechanical | RWS Nadia Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-II(Phase-II) under Teinpur ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer Karimpur- II Block | ORD/001770/2023-2024 | 6394/EMD | 30/10/2023 | 30 | D.S. ENTERPRISE | 8.45 | 0 | 0
4077 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna, Zone-I, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000005/2021-2022 | 769/NAD-I | 04/05/2021 | 60 | MALLICK ENTERPRISE | 97.12 | 185.73 | 100
4078 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000015/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0
4079 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between node point 1 to node point 105 in connection with augmentation work at Priyanagar under Zone-XI, Chanduria W/S Scheme under Jal Jeevan Mission under Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte.(SL.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000010/2023-2024 | 535 /NAD-I | 13/04/2023 | 21 | ABDUL ALIM MONDAL | 33.72 | 33.72 | 0
4080 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of rising main and distribution pipeline in revised alignment along NH-34 for Simurali (Zone-X), Chanduria (Zone-XII), Joykrishnapur (Zone-II) in connection with providing FHTC for Simurali(Zone-X), Chanduria (Zone-XII), Joykrishnapur (Zone-II) under JJM by Augmentation of Surface Water Based PWSS for Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, P.H.E.Dte. (sl.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000030/2023-2024 | 1254/ NAD-I | 04/05/2023 | 21 | BUDDHADEV MONDAL | 42.85 | 42.82 | 0
4081 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jack Pushing of Clearwater Rising Main Pipeline at Chakdah Chowmataha Crossing along NH-12 and other allied works under Jal Jeevan Mission (JJM) for Joykrishnapur (Zone-II), Chanduria (Zone-XI), Simurali (Zone-X), Ghetugachi (Zone-IX), Baraberia (Zone-VIII), Rukminidanga (Zone-IV) at Chakdah Block under Surface Water based PWSS for Chakdah Water Supply Scheme in connection with Providing FHTC for Joykrishnapur (Zone-II), Chanduria (Zone-XI), Simurali (Zone-X), Ghetugachi (Zone-IX), Baraberia (Zone-VIII), Rukminidanga (Zone-IV) under Nadia Arsenic Division-I, PHE Dte. (Sl.no.13) | Assistant Engineer-II | Junior Engineer-III | ORD/000036/2023-2024 | 1276 / NAD-I | 08/05/2023 | 21 | GBC INFRASTRUCTURE PRIVATE LIMITED | 58.64 | 58.53 | 0
4082 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Simurali Zone-XI under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no. 06) | Assistant Engineer-II | Junior Engineer-III | ORD/000054/2022-2023 | 1433 / NAD-I | 16/08/2022 | 45 | ONKAR ENTERPRISE | 29.88 | 29.51 | 100
4083 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Sanyalchar bablatala to Sanyalchar High School under Chanduria(Zone-XI) W/S Scheme in connection with augmentation of Chanduria W/S Scheme under Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E Dte (sl.no.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000057/2023-2024 | 1459/NAD-I | 29/05/2023 | 21 | SHYAMAL SHIL | 13.29 | 12.42 | 100
4084 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection from Node point 178 to node point 188 for Augmentation work at Tetulberia, Khorgachi,mollabelia village under Joykrishna ( Zone- II ) Water supply scheme under Jal Jeevan Mission for Chakdah Water bsaed PWSS within Chakdah Block ( Part ) under Nadia Arsenic Division-I, PHE Dte.(SL.07) | Assistant Engineer-II | Junior Engineer-III | ORD/000069/2023-2024 | 1383/NAD-I | 16/05/2023 | 21 | M/S A.K. CONSTRUCTION | 25.14 | 20.15 | 100
4085 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Tangra & Bagdob for augmentation of Surface water based PWSS for providing FHTC at Purba Bishnupur ( Zone V) of Surfac water based piped water supply scheme for Chakdah ( Part ) under JJM within Chakdah Block under Nadia Arsenic Division-I , PHE Dte. (SL.No.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000076/2023-2024 | 1400/NAD-I | 16/05/2023 | 25 | CHANDAN ROY | 47.15 | 0 | 100
4086 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between node point 3 and 76 of Balagarichar W/S Scheme for augmentation work at Uttar Ghughia village under Chakdah (Part) Water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-III | ORD/000079/2023-2024 | 1412/NAD-I | 18/05/2023 | 30 | MESSRS FREEDOM CONSTRUCTION | 62.36 | 0 | 100
4087 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall and pathway and Room at Head work site of Joykrishnapur OHR Site (Zone-II), Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Jeeva Mission for Zone-II (Joykrishnapur) Part-II, Providing FHTC under Jal Jeevan Mission (JJM) Zone -VIII (Barberia) Part-IV, Providing FHTC under Jal Jeevan Mission (JJM) Zone-X (Simurali) Part-IV and Providing FHTC under Jal Jeevan Mission (JJM) Zone-IV (Rukminidanga) Part-III at Chakdah Block by Augmentation of Surface Water Based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000106/2023-2024 | 1709/NAD-I | 14/07/2023 | 892 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 608.25 | 88.74 | 75
4088 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work Kajir baganunder Chanduria (Zone-XI) W/S Scheme in connection with augmentation of Chanduria W/S Scheme under Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000149/2023-2024 | 377/AE-II/NAD-I | 29/08/2023 | 7 | ASHIM ENTERPRISE | 1.17 | 0 | 100
4089 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Pathway from Madnapur PWD road to Tantipara and allied works in connection with Augmentation of Surface Water Based W/S Scheme for Arsenic affected areas of Chakdah (Part Block) of Nadia district Zone-X (Chanduria) under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000150/2023-2024 | 378/AE-II/NAD-I | 29/08/2023 | 7 | GREEN VIEW PROJECT INDIA | 2.5 | 0 | 100
4090 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Inayetpur and Ektarpur under Simurali (Zone-IX) W/S Scheme under Surface based Chakdah (Part) Water Supply Scheme under JJM under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000155/2023-2024 | 2114/NAD-I | 01/09/2023 | 15 | BIDYUT KUMAR | 30.26 | 0 | 100
4091 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between node 6 to node 382, node 340 to node 355 and providing FHTC (Functional Household Tap Connection) for augmentation work at Suturgachi, Simurali Railgate and Santipally in connection with augmentation of Simurali Zone-X W/S Scheme under Chakdah (Part) W/S Scheme under Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (Sl.no.17) | Assistant Engineer-II | Junior Engineer-III | ORD/000159/2023-2024 | 2117/NAD-I | 04/09/2023 | 21 | BUDDHADEV MONDAL | 74.38 | 65.22 | 100
4092 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of approach road at the Head Work site of Goruimari W/S Scheme under Chakdah Surface PWSS under JJM within Chakdah Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-II | Junior Engineer-III | ORD/000176/2024-2025 | 2111/NAD-I | 18/12/2024 | 236 | M/S LAXMI ENTERPRISE | 18.35 | 0 | 100
4093 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between Inlet and outlet pipe and OHR and bypass arrangement at Joykrishnapur ( Zone- II ) under Chakdah surface water supply scheme inconnection with augmentation of Joykrishnapur W/S Scheme under JJM under Nadia Arsenic Division- I P.H.E Dte(Sl.no.15) | Assistant Engineer-II | Junior Engineer-III | ORD/000185/2023-2024 | 2156/NAD-I | 08/09/2023 | 21 | TARUN KUMAR BHATTACHARYA | 13.76 | 0 | 100
4094 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between Washout/Overflowpipe and delivery pipe at Baeberia H/W site under Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of surface water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000257/2023-2024 | 516/AE-II/NAD-I | 05/12/2023 | 7 | BUDDHADEV MONDAL | 2.53 | 0 | 100
4095 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of at Manosapota and Malichaghar at Chanduria under Chanduria (Zone-XI) W/S Scheme under Surface based Chakdah (Part) W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000263/2023-2024 | 2725/NAD-I | 06/12/2023 | 21 | SUMAN CHAKRABORTY | 18.82 | 0 | 100
4096 | Nadia Arsenic Division I | Nadia Arsenic Division I | Replacement of pipeline and allied works under Jal Jeevan Mission (JJM) for Chanduria area under Chakdah Block by augmentation of Surface Water Based W/S Scheme for arsenic affected areas of Chakdah (Part Block) of Nadia Dist. Zone-XI (Chanduria) under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000280/2023-2024 | 10/AE-II/NAD-I | 04/01/2024 | 7 | PRADIP KUMAR BANIK | 2.68 | 0 | 100
4097 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 0 | 47
4098 | Nadia Division | Debgram Sub-Division | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000185/2024-2025 | 6095/ND | 19/09/2024 | 240 | UMWELT ENGINEER PVT LTD | 225.66 | 0 | 75
4099 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 9B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000783/2021-2022 | 133/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.23 | 4.19 | 100
4100 | Nadia Division | Debgram Sub-Division | Schedule for Additional Survey, Design Drawing & DPR Preparation for ZONE 9B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000784/2021-2022 | 134/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.81 | 0.75 | 98
4101 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000129/2022-2023 | 90/ND | 05/01/2023 | 0 | Resource Division | 147.73 | 0 | 0
4102 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Bahirgachhi Zone-I (Vill- Bahirgachhi) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000039/2020-2021 | 1186/NACD-II | 13/11/2020 | 25 | ST. ANTHONY ENTERPRISE | 4.98 | 0 | 0
4103 | Nadia Arsenic Civil Division II |  | QUOTATION FOR NISCHINTAPUR WATER SUPPLY SCHEME |  |  | VCH/000291/2021-2022 |  | 28/09/2021 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 1.78 | 0 | 0
4104 | Nadia Arsenic Civil Division II |  | Quotation for Nischintapur W/S scheme |  |  | VCH/000899/2020-2021 |  | 28/09/2020 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 1.78 | 0 | 0
4105 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Monipota W/S scheme(for Bishnupur and Raotara Mouza) in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000026/2021-2022 | 2190/ND | 24/05/2021 | 90 | PROJECT INDIA | 92.56 | 1.56 | 100
4106 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000090/2022-2023 | 4332/ND | 29/09/2022 | 0 | Resource Division | 8.13 | 0 | 0
4107 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Monipota W/S scheme(for Bishnupur and Raotara Mouza) in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | VCH/000747/2021-2022 | 350/PFMS | 08/12/2021 | 0 | PROJECT INDIA | 92.59 | 0 | 0
4108 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Joania W/S scheme(for Hazrapole, Kursi, Joania & Malipota Mouzas) in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000027/2021-2022 | 2191/ND | 24/05/2021 | 90 | UMWELT ENGINEERS PVT LTD | 93.31 | 31.67 | 0
4109 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000118/2021-2022 | 1058/ND | 04/03/2022 | 0 | Resource Division | 8.47 | 0 | 0
4110 | Nadia Division | Ranaghat Sub-Division | Providing Functional Household Tap Connection from Joania Water Scheme (for Hazrapole, Kursi, Joania & Malipota Mouzas) under Jal Swapno Programme in Nadia District. | Assistant Engineer |  | VCH/000521/2021-2022 | 182/PFMS | 15/09/2021 | 0 | UMWELT ENGINEERS PVT LTD | 61.06 | 0 | 0
4111 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-I, within Krishnagar-II & Nabadwip Block (Phase-B, Retrofitting)" | Assistant Engineer |  | ORD/000395/2020-2021 | 771/ND | 10/02/2021 | 90 | TARUN KUMAR BHATTACHARYA | 97.08 | 0 | 0
4112 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000167/2023-2024 | 302/ND | 15/01/2024 | 0 | Resource Division | 2.48 | 0 | 0
4113 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar-II, Nabadwip (Part) Block (Phase-B) | Assistant Engineer |  | VCH/000585/2021-2022 | 235/PFMS | 05/10/2021 | 0 | TARUN KUMAR BHATTACHARYA | 82.3 | 0 | 0
4114 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Zone VII Ballavapur Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte | Assistant Engineer-II | Junior Engineer-III | ORD/000021/2021-2022 | 786/NAD-I | 05/05/2021 | 60 | H I ENTERPRISE | 97 | 179.07 | 100
4115 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Muragachha, Zone-I, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000006/2021-2022 | 770/NAD-I | 04/05/2021 | 60 | MONDAL ENTERPRISE | 68.28 | 100 | 100
4116 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Radhakantapur, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Radhakantapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000015/2021-2022 | 780/NAD-I | 05/05/2021 | 60 | TAPU SAHA | 88.27 | 165.66 | 0
4117 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Part-I at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000014/2021-2022 | 779/NAD-I | 05/05/2021 | 60 | GHOSH CONSTRUCTION | 97.11 | 97.07 | 100
4118 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block ( Phase -A) | Assistant Engineer |  | ORD/000200/2020-2021 | 4089ND | 31/12/2020 | 90 | UMWELT ENGINEERS PVT LTD | 96.87 | 14.61 | 0
4119 | Nadia Division | Debgram Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Executive Engineer, Nadia Division, PHE Dte. (Period- 01/04/2023 to 30/09/2023) | Assistant Engineer |  | ORD/000548/2022-2023 | 465/ Kly SD-1 | 31/03/2023 | 183 | ARROWTOWN DEALERS PVT. LTD | 2.4 | 0 | 0
4120 | Nadia Division | Debgram Sub-Division | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Diovision,PHE Dte,Debagram,Nadia with effect from 01.08.2021 to 31.07.2022 | Assistant Engineer |  | ORD/000952/2021-2022 | 399/DSD | 29/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 1.19 | 0
4121 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-VIII within Kaliganj Block [Phase-A] | Assistant Engineer |  | VCH/000931/2021-2022 | 485/PFMS | 03/02/2022 | 0 | LEMNISCATE | 0.48 | 0 | 0
4122 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME ATPART-1 Z-8 | Assistant Engineer |  | VCH/001069/2020-2021 | 460/DW | 30/03/2021 | 0 | OTHERS | 80.19 | 0 | 0
4123 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-IV, within Krishnagar-II & Nabadwip Block (Phase-B, Retrofitting)" | Assistant Engineer |  | ORD/000401/2020-2021 | 777/ND | 10/02/2021 | 90 | PROJECT INDIA | 97.04 | 192.48 | 0
4124 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000041/2021-2022 | 442/ND | 31/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
4125 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar- II & Nabadwip (Part) Block (Phase-B). | Assistant Engineer |  | VCH/000989/2020-2021 |  | 24/03/2021 | 0 | PROJECT INDIA | 49.93 | 0 | 0
4126 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block ( Phase -C) in Nadia District under Nadia Division P.H.E. Dte Sl.No.3 | Assistant Engineer |  | ORD/000475/2020-2021 | 889/ND | 19/02/2021 | 90 | TARUN KUMAR BHATTACHARYA | 96.89 | 4.27 | 0
4127 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at zone- Nagla, Raripara, Badbelgao, Bholadangavilleges under VI & IX , Part- II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block | Assistant Engineer |  | ORD/000809/2021-2022 | 159/DSD | 17/03/2022 | 30 | MAHAVIR PUMPS MFG PVT. LTD. | 4.24 | 4.21 | 0
4128 | Nadia Division | Debgram Sub-Division | Laying additional distribution pipeline for providing FHTC at Dogachhia, Deluigachi, Jalsukha and Saligram villages of zone VI & IX , Part- II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000810/2021-2022 | 160/DSD | 17/03/2022 | 30 | MAHAVIR PUMPS MFG PVT. LTD. | 3.92 | 3.91 | 0
4129 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000086/2022-2023 | 4273/ND | 29/09/2022 | 0 | Resource Division | 12.54 | 0 | 0
4130 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME N/ SECTOR PART-2, Z-9, NAKASHIPARA BLOCK, PHASE--C | Assistant Engineer |  | VCH/000605/2021-2022 | 262/PFMS | 08/10/2021 | 0 | TARUN KUMAR BHATTACHARYA | 84.44 | 0 | 0
4131 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000016/2021-2022 | 2152/ND | 21/05/2021 | 60 | ORIENT CONSTRUCTION | 42.68 | 19.83 | 100
4132 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000019/2021-2022 | 2153/ND | 21/05/2021 | 45 | M/S SHUBHA ENTERPRISE | 10.99 | 0 | 100
4133 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000021/2021-2022 | 2151/ND | 21/05/2021 | 60 | BOSE & CO | 42.67 | 32.08 | 100
4134 | Nadia Division | RWS Nadia Sub-Division | Laying of parallel new UPVC pipe line in Sansad-X in Deypara GP opposite Jahangirpur Helipada ground to complte FHTC under Paschim Bhatjungla Zone-I W/S scheme under RWS Nadia Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000108/2021-2022 | 2908/ND | 23/07/2021 | 60 | BIPLAB GUHA | 23.33 | 22.97 | 100
4135 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Krishnanagar - I Block | RTOR000086/2021-2022 | 815/ND | 18/02/2022 | 0 | Resource Division | 11 | 0 | 0
4136 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | Assistant Engineer | Junior Engineer Krishnanagar - I Block | VCH/000895/2021-2022 | 531/PFMS | 23/02/2022 | 0 | M/S SHUBHA ENTERPRISE | 11.19 | 0 | 0
4137 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Subarnabehar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | Assistant Engineer |  | ORD/000017/2021-2022 | 2391/ND | 10/06/2021 | 45 | ROY CONSTRUCTION | 9.03 | 16.29 | 100
4138 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Subarnabehar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer |  | ORD/000018/2021-2022 | 2159/ND | 21/05/2021 | 60 | M/S S.S ENTERPRISE | 42.27 | 9.23 | 0
4139 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Subarnabehar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer |  | ORD/000063/2021-2022 | 2432/ND | 14/06/2021 | 60 | SANJOY BAKSHI | 42.57 | 61.63 | 100
4140 | Nadia Division | RWS Nadia Sub-Division | Laying of D I Pipe line in place of UPVC pipe including other allied works from OHR to both side of head work site for providing FHTC under Jal Swapna at Subarnabehar w/s scheme under Nadia Division PHED. | Assistant Engineer |  | ORD/000065/2022-2023 | 215/PH | 12/07/2022 | 30 | SURAJIT KUMAR GHOSH | 4.65 | 0 | 92
4141 | Nadia Division | RWS Nadia Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Subarnabehar W/S Scheme in Krishnagar - I Block of Nadia District under Nadia Division. PART - B | Assistant Engineer |  | ORD/000317/2021-2022 | 1190/PH | 03/12/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.69 | 0 | 100
4142 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | Assistant Engineer |  | VCH/000475/2021-2022 | 288/PFMS | 08/10/2021 | 0 | M/S S.S ENTERPRISE | 21.54 | 0 | 0
4143 | Nadia Division | RWS Nadia Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY AT SUBERNABIHAR W/S , PHASE-1 | Assistant Engineer |  | VCH/000885/2021-2022 | 482/PFMS | 03/02/2022 | 0 | SHYAMAL SHIL | 3.94 | 0 | 0
4144 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX, (Chandmari), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 01) Tender No.- 205/NAD-I/2020-2021. |  |  | ORD/000179/2020-2021 | 157/NAD-I | 25/01/2021 | 60 | GHOSH ENTERPRISE | 97.08 | 194.13 | 100
4145 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-I, (Fatepur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 03) |  |  | ORD/000185/2020-2021 | 159/NAD-I | 25/01/2021 | 60 | TARUN KUMAR BHATTACHARYA | 96.53 | 189.63 | 100
4146 | Nadia Arsenic Division I |  | Reconnection of Functional household tap connection including additional restoration and renovation work of pump house, boundary wall and path way at Zone-I,Fatepur under Surface based Water Supply PWSS of Haringhata & Chakdah (Part) under Haringhata Block under Nadia Arsenic Division-I,P.H.E Dte |  |  | ORD/000288/2023-2024 | 31/AE-I/NAD-I | 19/01/2024 | 30 | SHYAMAL SHIL | 3.2 | 0 | 100
4147 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 04) Tender No. 196/NAD-I/2020-2021. | Assistant Engineer-I | Junior Engineer-II | ORD/000180/2020-2021 | 155/NAD-I | 25/01/2021 | 60 | UNICON INDIA | 97.03 | 190.37 | 100
4148 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Zone-VI, (Balia) Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl. NO. 02) Tender No. - 225/NAD-I/2020-2021. | Assistant Engineer-II | Junior Engineer-IV | ORD/000176/2020-2021 | 314/NAD-I | 08/02/2021 | 90 | UMWELT ENGINEER PVT. LTD. | 97.05 | 155.86 | 100
4149 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Arabpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte."(Phase-I Retro fitting)(PART-A) | Assistant Engineer |  | ORD/000326/2020-2021 | 401/ND | 22/01/2021 | 45 | CHANDAN ROY | 32.17 | 3.76 | 0
4150 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Arabpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte."(Phase-I Retro fitting)(PART-B) | Assistant Engineer |  | ORD/000328/2020-2021 | 402/ND | 22/01/2021 | 45 | USHA CONSTRUCTION | 32.19 | 8.48 | 0
4151 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Arabpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte."(Phase-I Retro fitting)(PART-C) | Assistant Engineer |  | ORD/000329/2020-2021 | 403/ND | 22/01/2021 | 45 | SANJIB DEY | 32.2 | 5.25 | 0
4152 | Nadia Division | Tehatta Sub-Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | Assistant Engineer |  | VCH/000061/2021-2022 | 78/PFMS | 15/07/2021 | 0 | SANJIB DEY | 9.86 | 0 | 0
4153 | Nadia Division | Tehatta Sub-Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | Assistant Engineer |  | VCH/000062/2021-2022 |  | 12/04/2021 | 0 | CHANDAN ROY | 14.57 | 0 | 0
4154 | Nadia Division | Tehatta Sub-Division | use Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | Assistant Engineer |  | VCH/000063/2021-2022 |  | 12/04/2021 | 0 | USHA CONSTRUCTION | 20.02 | 0 | 0
4155 | Nadia Division | Tehatta Sub-Division | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT ARABPUR W/S SCHEME PHASE-1, PART-B, RETROFITTING, UNDER NADIA DIVISION, PHE , DTE. | Assistant Engineer |  | VCH/000212/2021-2022 | 68/PPMS | 15/07/2021 | 0 | USHA CONSTRUCTION | 20.02 | 0 | 0
4156 | Nadia Division | Tehatta Sub-Division | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT ARABPUR W/S SCHEME PHASE-1, PART-A,RETROFITTING UNDER NADIA DIVISION, PHE , DTE. | Assistant Engineer |  | VCH/000213/2021-2022 | 79/PPMS | 15/07/2021 | 0 | CHANDAN ROY | 14.57 | 0 | 0
4157 | Nadia Division | Tehatta Sub-Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | Assistant Engineer |  | VCH/000485/2021-2022 | 287/PFMS | 08/10/2021 | 0 | CHANDAN ROY | 8.5 | 0 | 0
4158 | Nadia Division | Tehatta Sub-Division | Providing Functional House Tap Connection from Arabpur Water Supply Scheme under Jal Swapno Programme (Phase-I) | Assistant Engineer |  | VCH/000487/2021-2022 | 289/PFMS | 08/10/2021 | 0 | SANJIB DEY | 12 | 0 | 0
4159 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-IV, within Krishnagar-II & Nabadwip Block (Phase-C, Retrofitting)" | Assistant Engineer |  | ORD/000402/2020-2021 | 778/ND | 10/02/2021 | 90 | MAHABIR PUMPS MFG PVT. LTD. | 97.12 | 24.73 | 100
4160 | Nadia Division | Krishnanagar Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
4161 | Nadia Division | Krishnanagar Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME (N/S), PART-III, ZONE-IV, WITHIN KRISHAGAR -II & NABADWIP BLOCK PHASE-C | Assistant Engineer |  | VCH/000654/2021-2022 | 304/PFMS | 01/11/2021 | 0 | MAHAVIR PUMPS MFG PVT. LTD. | 65 | 0 | 0
4162 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Elangi Zone-I W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000243/2020-2021 | 61/ND | 07/01/2021 | 90 | S.K. CONSTRUCTION | 96.72 | 95.73 | 100
4163 | Nadia Division | RWS Nadia Sub-Division | Retrofitting of Providing FHTC at Ground Water based Elangi Water Supply Scheme Zone-1(Phase-1) | Assistant Engineer |  | VCH/000494/2022-2023 | 81/PFMS | 13/07/2022 | 0 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 3.86 | 0 | 0
4164 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Topla W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-A) | Assistant Engineer |  | ORD/000330/2020-2021 | 404/ND | 22/01/2021 | 45 | NILAY KUMAR BHATTACHARYA | 32.33 | 0 | 0
4165 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Topla W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-B) | Assistant Engineer |  | ORD/000331/2020-2021 | 405/ND | 22/01/2021 | 45 | SANDIP BISWAS | 32.33 | 22.61 | 0
4166 | Nadia Division | Tehatta Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Topla W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-C) | Assistant Engineer |  | ORD/000332/2020-2021 | 406/ND | 22/01/2021 | 45 | SOMNATH CHATTERJEE | 32.31 | 22.45 | 0
4167 | Nadia Division | Tehatta Sub-Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) | Assistant Engineer |  | VCH/000070/2021-2022 |  | 16/04/2021 | 0 | NILAY KUMAR BHATTACHARYA | 12.07 | 0 | 0
4168 | Nadia Division | Tehatta Sub-Division | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN-METAL FERRULE ........AT TOPLA W/S SCHEME PHASE-I RETROFITTING | Assistant Engineer |  | VCH/000200/2021-2022 | 72/PPMS | 15/07/2021 | 0 | SANDIP BISWAS | 9.28 | 0 | 0
4169 | Nadia Division | Tehatta Sub-Division | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN-METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC ALL COMPLETE AT TOPLA W/S SCHEME UNDER NADIA DIVISION, PHE , DTE . PHASE-1, RETROFITTING PART-B. | Assistant Engineer |  | VCH/000201/2021-2022 | 69/PPMS | 15/07/2021 | 0 | NILAY KUMAR BHATTACHARYA | 12.07 | 0 | 0
4170 | Nadia Division | Tehatta Sub-Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) | Assistant Engineer |  | VCH/001023/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 11.34 | 0 | 0
4171 | Nadia Division | Tehatta Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME ATTOPLA W/S SCHEME | Assistant Engineer |  | VCH/001068/2020-2021 | 460/DW | 30/03/2021 | 0 | SOMNATH CHATTERJEE | 18.55 | 0 | 0
4172 | Nadia Division | Debgram Sub-Division | :Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block ( Phase -B) | Assistant Engineer |  | ORD/000286/2020-2021 | 246/ND | 15/01/2021 | 90 | M/S S.S ENTERPRISE | 96.93 | 7.55 | 0
4173 | Nadia Division | Debgram Sub-Division | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-IV / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11841]. | Assistant Engineer |  | ORD/000454/2023-2024 | 6152/ND | 26/12/2023 | 1093 | SATYABRATA CHAKRABORTY | 233.13 | 0 | 5
4174 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME NORTHERN SECTOR PART-II,ZONE-IV,WITHIN NAKASHIPARA BLOCK PHASE-B. | Assistant Engineer |  | VCH/000205/2021-2022 | 90/PPMS | 15/07/2021 | 0 | M/S S.S ENTERPRISE | 69.17 | 0 | 0
4175 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000480/2021-2022 | 293/PFMS | 08/10/2021 | 0 | M/S S.S ENTERPRISE | 17.6 | 0 | 0
4176 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II, Z-IV, WITHIN NAKASHIPARA BLOCK, PHASE-B. | Assistant Engineer |  | VCH/000882/2021-2022 | 496/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.71 | 0 | 0
4177 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-B). | Assistant Engineer |  | VCH/001008/2020-2021 |  | 25/03/2021 | 0 | M/S S.S ENTERPRISE | 69.17 | 0 | 0
4178 | Nadia Division | Debgram Sub-Division | Continuation for Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.05.2023 to 30.06.2023 (Two Month). | Assistant Engineer |  | ORD/000047/2023-2024 | 1939/ND | 28/04/2023 | 61 | CLIFFORD FACILITY SERVICES PVT. LTD | 2.73 | 1.36 | 50
4179 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-V within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.3) | Assistant Engineer |  | ORD/000461/2020-2021 | 868/ND | 18/02/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 97.09 | 0 | 0
4180 | Nadia Division | Debgram Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
4181 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000094/2022-2023 | 4333/ND | 29/09/2022 | 0 | Resource Division | 12.52 | 0 | 0
4182 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME NORTHERN SECTOR PART-II, ZONE-V,WITHIN NAKASHIPARA BLOCK PHASE-B. | Assistant Engineer |  | VCH/000210/2021-2022 | 84/PPMS | 15/07/2021 | 0 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 63.71 | 0 | 0
4183 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000913/2021-2022 | 553/PFMS | 23/02/2022 | 0 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 21.99 | 0 | 0
4184 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000940/2021-2022 | 495/PFMS | 03/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 0.46 | 0 | 0
4185 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chandpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000140/2021-2022 | 856/NACD-II | 08/11/2021 | 45 | M/S ANUBHAB CONSTRUCTION | 71.49 | 0 | 100
4186 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-III within Kaliganj block(Phase-B) in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000185/2020-2021 | 3591/ND | 08/12/2020 | 90 | IJABUL SK. | 97.01 | 159.39 | 0
4187 | Nadia Division | Debgram Sub-Division | Hiring Diesel Maxi Cub having car No WB-51/B-3194 for office of the Assistant Engineer, RWS Nadia Sub-Division, PHE Dte. for the period from 01.08.2021 to 31.07.2022 | Assistant Engineer |  | ORD/000951/2021-2022 | 896/PH | 30/07/2021 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 1.26 | 100
4188 | Nadia Division | Debgram Sub-Division | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE | Assistant Engineer |  | VCH/000310/2021-2022 | 139/FHTC | 17/08/2021 | 0 | LEMNISCATE | 0.69 | 0 | 0
4189 | Nadia Division | Debgram Sub-Division | CONSTRUCTION OF 2 NOS. PORTICO AND OTHER ALLIED WORK FOR NEW OFFICE BUILDING FOR ACCOMMODATING DIVISION OFFICE ALONG WITH 4 NOS SUB. DIVSIONAL OFFICES FOR MONITORING OF JAL SWAPNO PROGRAM. | Assistant Engineer |  | VCH/001152/2021-2022 | 685/OBDW | 30/03/2022 | 0 | AMBRUS CONSTRUCTION | 4.98 | 0 | 0
4190 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-B). | Assistant Engineer |  | VCH/001194/2021-2022 | 594/DW | 11/03/2022 | 0 | RADIANT | 3.17 | 0 | 0
4191 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Chanderghat (Vill-Chanderghat) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000031/2020-2021 | 1177/NACD-II | 13/11/2020 | 25 | CHANDAN ROY | 4.98 | 0 | 0
4192 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Saguna Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Saguna (Part-I) under JJM(Sl.no.12) | Assistant Engineer-I | Junior Engineer-II | ORD/000053/2023-2024 | 1426/NAD-I | 23/05/2023 | 15 | ROY ASSOCIATES | 13.04 | 0 | 100
4193 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-I at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000055/2021-2022 | 1412/NAD-I | 08/11/2021 | 60 | H I ENTERPRISE | 87.11 | 83.82 | 100
4194 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-II W/S Scheme, Phase-II at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000002/2022-2023 | 643/NAD-I | 29/04/2022 | 90 | UNICON INDIA | 335.39 | 0 | 10
4195 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-I Water Supply Scheme, Phase-I at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000004/2022-2023 | 645/NAD-I | 29/04/2022 | 90 | M/S R.K. ENTERPRISE | 260.46 | 0 | 100
4196 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000087/2021-2022 | 1480/NAD-I | 24/11/2021 | 90 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 167.42 | 131.2 | 100
4197 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000014/2021-2022 | 146/NAD-I | 28/01/2022 | 0 | Resource Division | 0.6 | 0 | 0
4198 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X (Shimurali) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000126/2021-2022 | 51/NAD-I | 11/01/2022 | 90 | APURBA MANDAL | 203.19 | 202.99 | 100
4199 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection under Jaldhara/Jal Swapna for Dhantala Part-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000045/2021-2022 | 1402/NAD-I | 08/11/2021 | 60 | M/S DIPAK ENTERPRISE | 85.84 | 85.5 | 100
4200 | Nadia Arsenic Division I | Nadia Arsenic Division I | Revamping / upgardation of hydraulic parameter of distribution network and providing FHTC for Doula, Debipur Chandpur Biraberia Dhantala & Notungram and Hizuli (Part) Village and under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dhantala PWSS & Hizuli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000112/2025-2026 | 800/NAD-I | 18/08/2025 | 90 | BIDYUT KUMAR | 182.15 | 0 | 0
4201 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000005/2021-2022 | 138/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
4202 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-III (Jalkar Bhomra) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000110/2021-2022 | 1612/NAD-I | 28/12/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 304.75 | 300.59 | 100
4203 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-II | RTOR000021/2022-2023 | 3502/NAD-I | 05/01/2023 | 0 | Resource Division | 15.41 | 0 | 0
4204 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-I (Fatepur) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000113/2021-2022 | 1615/NAD-I | 28/12/2021 | 90 | BKB INFRA PROJECTS PRIVATE LIMITED | 244.09 | 200.03 | 100
4205 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Baranaldaha (Vill-Dakshin Para) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. |  |  | ORD/000144/2020-2021 | 208/NACD-II | 19/02/2021 | 15 | TAPAN SAHA | 4.94 | 0 | 0
4206 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials & valves, pipe Supporting structure all complete, Proposed augmentation of Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Soil investigation for construction of one No. 450 Cum OHR, Construction of R.C.C. Elevated Reservoir of 450 Cum capacity(including pile foundation) at Gadigachha in Nabadwip Block under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000088/2023-2024 | 3026/ND | 14/07/2023 | 1096 | JOY HIND TUBEWELL'S | 431.93 | 0 | 45
4207 | Nadia Division | Krishnanagar Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
4208 | Nadia Division | Krishnanagar Sub-Division | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Gadigacha W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 14) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000353/2021-2022 | 917/KSD | 29/11/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.23 | 4.18 | 0
4209 | Nadia Division | Krishnanagar Sub-Division | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 90 days w.e.f. 01/10/2023 (as and when required) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000411/2023-2024 | 1450/KSD | 18/09/2023 | 90 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0
4210 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000758/2023-2024 | 1838/KSD | 28/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0
4211 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 81 m3/hr at Gadigacha Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000780/2023-2024 | 1894/ND | 15/03/2024 | 180 | G.D. CONSTRUCTION AND CO. | 226.16 | 0 | 0
4212 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000155/2023-2024 | 270/ND | 11/01/2024 | 0 | Resource Division | 23.16 | 0 | 0
4213 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000171/2022-2023 | 132/ND | 06/01/2023 | 0 | Resource Division | 29.03 | 0 | 0
4214 | Central Drilling | Krishnanagar Sub-Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HOWRAH DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000172/2020-2021 | 86/ CMSD-II (D) | 24/02/2021 | 30 | ASHUTOSH DAS & CO | 4.83 | 3.83 | 0
4215 | Eastern Mechanical | Krishnanagar Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Gadigachha ground water based water supply scheme under Block_Nabadwip Dist. - Nadia under EMD, PHE Dte. SM/09223 | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000189/2025-2026 | 1127/EMD | 04/06/2025 | 90 | ASHUTOSH DAS & CO. | 36.75 | 0 | 0
4216 | Nadia Division | Debgram Sub-Division | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Naserkuli Zone-II ii) Subarna Behar Zone-I iii) Mahisunra Phase- I iv)Mahisunra Phase-II v)Bablari Dewanganj | Assistant Engineer |  | ORD/000066/2023-2024 | 673/KlySd-I | 30/05/2023 | 184 | HORIZEN | 4.62 | 3.37 | 100
4217 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-II, Zone-II within Nakashipara Block (Phase-B) | Assistant Engineer |  | ORD/000244/2021-2022 | 5364/ND | 30/09/2021 | 90 | TARUN KUMAR BHATTACHARYA | 86.48 | 1.64 | 100
4218 | Nadia Division | Debgram Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
4219 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000033/2022-2023 | 4283/ND | 29/09/2022 | 0 | Resource Division | 12.57 | 0 | 0
4220 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000042/2021-2022 | 451/ND | 31/01/2022 | 0 | Resource Division | 3.98 | 0 | 0
4221 | Nadia Division | Debgram Sub-Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) | Assistant Engineer |  | VCH/000360/2022-2023 | 60/PFMS | 22/06/2022 | 0 | TARUN KUMAR BHATTACHARYA | 5.49 | 0 | 0
4222 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC ..FROM NORTHRN SECTOR , PART-II, Z-II, PHASE-B, WITHIN NAKASHIPARA BLOCK W/S SCHEME | Assistant Engineer |  | VCH/000874/2021-2022 | 471/PFMS | 02/02/2022 | 0 | TARUN KUMAR BHATTACHARYA | 71.78 | 0 | 0
4223 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Paschim Noapara, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000049/2021-2022 | 1406/NAD-I | 08/11/2021 | 60 | IJABUL SEKH | 83.14 | 82.5 | 100
4224 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0
4225 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000054/2021-2022 | 1411/NAD-I | 08/11/2021 | 60 | SANJOY BAKSHI | 73.62 | 70.47 | 100
4226 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-V&VIII within Kaliganj Block (Phase-C) | Assistant Engineer |  | ORD/000206/2021-2022 | 5180/ND | 20/09/2021 | 90 | SATYABRATA CHAKRABORTY | 89.77 | 85.38 | 0
4227 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000031/2022-2023 | 4292/ND | 29/09/2022 | 0 | Resource Division | 12.54 | 0 | 0
4228 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000177/2023-2024 | 312/ND | 15/01/2024 | 0 | Resource Division | 2.62 | 0 | 0
4229 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000178/2023-2024 | 313/ND | 15/01/2024 | 0 | Resource Division | 5.4 | 0 | 0
4230 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000184/2023-2024 | 319/ND | 15/01/2024 | 0 | Resource Division | 12.55 | 0 | 0
4231 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-II W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte |  |  | ORD/000132/2021-2022 | 871/NACD-II | 08/11/2021 | 45 | JOY HIND TUBEWELLS | 82.99 | 0 | 100
4232 | Nadia Arsenic Civil Division II |  | Providing Functional House Hold Tap Connection (FHTC) including supply of 15 mm dia GI/PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at Helenchi Zone-III (Vill-Bhajanghat) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte |  |  | ORD/000033/2020-2021 | 1180/NACD-II | 13/11/2020 | 25 | SUMIT GHOSH | 4.99 | 0 | 0
4233 | Nadia Division | Kalyani Sub-Division I | Augmentation of Distribution System of Ground Based Piped Water Supply Scheme at Shyamnagar to accommodate FHTC within Tehatta I Block under Kalyani Sub Division I under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000306/2023-2024 | 4276/ND | 21/09/2023 | 60 | MONDAL ENTERPRISE | 20.56 | 20.56 | 100
4234 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 500 cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (Including Pile Foundation), Pipe Connection And Cost of Pipes, Specials and Soil Investigation for Augmentation of Ground Based Water Supply Scheme at Shyamnagar to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000429/2022-2023 | 844/ND | 28/02/2023 | 1096 | MONDAL ENTERPRISE, MASJID BARI ROAD,UTTAR BALURIA, P.O.NABAPALLY, P.S. BARASAT NORTH 24 PGS. | 580.91 | 355.33 | 58
4235 | Nadia Division | Kalyani Sub-Division I | Repair & Renovation of Pump House, Boundary wall and allied works at Head Work site under Shyamnagar PWSS under Tehatta-I Block in Nadia District Under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000667/2023-2024 | 1099/ND | 19/02/2024 | 60 | K.K. MARKETING | 9.87 | 0 | 100
4236 | Nadia Division | Kalyani Sub-Division I | Construction and Installation of 120.00 cum capacity Arsenic-Cum-Iron Removal Plant (AIRP) at Shyamnagar PWSS including 3 Months Trial Run & 3 Years O&M under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000743/2023-2024 | 1588/ND | 06/03/2024 | 180 | MONDAL ENTERPRISE | 300.5 | 0 | 50
4237 | Nadia Division | Kalyani Sub-Division I | Repair & Renovation of Pump House and Construction of Boundary wall, Service Road and allied works at 2nd T.W site under Shyamnagar PWSS under Tehatta-I Block in Nadia District Under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000762/2023-2024 | 1725/ND | 12/03/2024 | 60 | BABLU MALLICK | 10.44 | 0 | 100
4238 | Nadia Division | Kalyani Sub-Division I | Laying distribution system for providing FHTC at Chilakhali Mouza in connection with Augmentation of Ground Based Water Supply Scheme at Shyamnagar to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000765/2023-2024 | 1818/ND | 14/03/2024 | 90 | M/S.ROY CHOWDHURY & CO | 54.33 | 0 | 100
4239 | Nadia Division | Kalyani Sub-Division I | Construction of Jhama Bats Road from Palassey Betai road to headwork site of Shyamnagar water supply scheme under Kalyani Sub Division I under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000816/2023-2024 | 481KLYSD-I | 15/03/2024 | 30 | MONDAL ENTERPRISE | 6.03 | 0 | 100
4240 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000081/2023-2024 | 2318/ND | 29/05/2023 | 0 | Resource Division | 24.17 | 0 | 0
4241 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000146/2021-2022 | 1389/ND | 24/03/2022 | 0 | Resource Division | 29.18 | 0 | 0
4242 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000184/2022-2023 | 151/ND | 06/01/2023 | 0 | Resource Division | 1.84 | 0 | 0
4243 | Nadia Division | Kalyani Sub-Division I | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/001136/2021-2022 | 702/PFMS | 30/03/2022 | 0 | HORIZEN | 2.8 | 0 | 0
4244 | Eastern Mechanical | Kalyani Sub-Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC at under SHYAMNAGAR W/S Scheme, Block-Tehatta I , Dist. - Nadia. NIET No. 36 of EE/EMD of 2022-23 (Sl. No.- 12) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000021/2023-2024 | 1584/EMD | 24/04/2023 | 30 | P.K. ENTERPRISE | 16.13 | 15.47 | 80
4245 | Nadia Division | RWS Nadia Sub-Division | Laying distribution system for providing FHTC (Functional Household Tap Connection) by Augmentation & Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Fazil Nagar Piped Water Supply Scheme at Karimpur - II block under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000015/2022-2023 | 2005/ND | 05/05/2022 | 90 | PATHIK PABAN NANDI | 271.88 | 219.13 | 100
4246 | Nadia Division | RWS Nadia Sub-Division | Renovation of AIRP (Gravity Type) of capacity 117 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Fazilnagar PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000029/2023-2024 | 1787/ND | 20/04/2023 | 886 | B.M. ENGINEERING & CONSTRUCTION | 118.29 | 0 | 30
4247 | Nadia Division | RWS Nadia Sub-Division | Repairing of Existing Damage Pipe line from Fazilnagar towards Charmoktarpur via Pearpur under Fazilnagar PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000077/2024-2025 | 4087/ND | 26/07/2024 | 60 | PATHIK PABAN NANDI | 33.36 | 0 | 0
4248 | Nadia Division | RWS Nadia Sub-Division | Augmentation of FHTC (Part-B) of Fazilnagar Pipe Water Supply Scheme. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000160/2024-2025 | 4903/ND | 10/09/2024 | 60 | PATHIK PABAN NANDI | 34.31 | 0 | 0
4249 | Nadia Division | RWS Nadia Sub-Division | Laying of additional pipeline for Fazilnagar Mouza and Anandapur Mouza under Fazilnagar PWSS and Anandapur PWSS under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000161/2024-2025 | 4904/ND | 10/09/2024 | 90 | PATHIK PABAN NANDI | 37.63 | 0 | 0
4250 | Nadia Division | RWS Nadia Sub-Division | Laying of additional pipeline for Fazilnagar Mouza and Phulkhali Mouza under Fazilnagar PWSS and Arabpur PWSS".under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000162/2024-2025 | 4905/ND | 10/09/2024 | 90 | PATHIK PABAN NANDI | 41.67 | 0 | 0
4251 | Nadia Division | RWS Nadia Sub-Division | Construction and installation of MANIFOLD and allied works at OHR site under Fazilnagar PWSS under Karimpur-II Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM). | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000746/2024-2025 | 424/ND | 27/01/2025 | 360 | REAL TIME | 34.74 | 0 | 60
4252 | Nadia Division | RWS Nadia Sub-Division | Repairing existing Damage Pipe line from Fazilnagar Durgamandir Towards Lalnagar Under Fazilnagar PWSS.under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000767/2023-2024 | 1820/ND | 14/03/2024 | 90 | PATHIK PABAN NANDI | 29.99 | 0 | 0
4253 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000030/2021-2022 | 431/ND | 31/01/2022 | 0 | Resource Division | 0.76 | 0 | 0
4254 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | RTOR000057/2022-2023 | 4306/ND | 29/09/2022 | 0 | Resource Division | 17.81 | 0 | 0
4255 | Nadia Division | RWS Nadia Sub-Division | Providing FHTC by augmentation under Jal Swapna for Fazil Nagar PWSS in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | VCH/001151/2021-2022 | 704/PFMS | 30/03/2022 | 0 | TECHVISION | 2.87 | 0 | 0
4256 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Betna Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I, P.H.E Dte. in connection with Augmentation of Betna W/S Scheme under JJM (Sl.No.05) | Assistant Engineer-II | Junior Engineer-III | ORD/000067/2023-2024 | 1378/NAD-I | 15/05/2023 | 25 | TAPAS GHOSH | 12.52 | 0 | 90
4257 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall Toilet Pathway and other work at Goalsalua Zone II WS Scheme within Ranaghat II Block under NAD-I PHE Dte ( Sl.no.05) | Assistant Engineer-II | Junior Engineer-III | ORD/000093/2022-2023 | 1940 / NAD-I | 12/10/2022 | 60 | BUDDHADEV MONDAL | 12.94 | 6.89 | 50
4258 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall Toilet Pathway and other allied work at Betna WS Scheme within Hanskhali Block under NAD I PHE Dte(Sl.no.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000096/2022-2023 | 1961/ NAD-I | 12/10/2022 | 45 | BANERJEE ENTERPRISE | 11.54 | 6.92 | 0
4259 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir Painting and Pump House at Goalsalua Zone II WS Scheme in Ranaghat II Block under NAD I PHE Dte (Sl.no.07) | Assistant Engineer-II | Junior Engineer-III | ORD/000137/2022-2023 | 3036 /NAD-I | 09/11/2022 | 60 | TAPU SAHA | 20.13 | 17.91 | 100
4260 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP (Pressure Type) at Betna W/S Scheme under Hanskhali Block of capacity 50 cum/hr. under Nadia under augmentation of Betna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (SL.no.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000144/2023-2024 | 2045/NAD-I | 24/08/2023 | 542 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 130.98 | 0 | 100
4261 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet, Pathway and other allied work at Goalsalua Zone-I Water Supply Scheme within Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. ( SL.NO.13) | Assistant Engineer-II | Junior Engineer-III | ORD/000149/2022-2023 | 3327/NAD-I | 15/12/2022 | 45 | M/S AKSHAY HALDER | 11.93 | 5.86 | 100
4262 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Goalsalua Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Goalsalua Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 09) | Assistant Engineer-II | Junior Engineer-III | ORD/000167/2021-2022 | 435/NAD-I | 07/03/2022 | 30 | MANISHIKA CONSTRUCTION | 23.94 | 20.88 | 100
4263 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Betna Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Betna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 10) | Assistant Engineer-II | Junior Engineer-III | ORD/000168/2021-2022 | 436/NAD-I | 07/03/2022 | 30 | B.M. ENTERPRISE | 25.11 | 21.53 | 100
4264 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chak Dakshinpara & Fulbari villages at Hanskhali Block by retrofitting of Ground Water based PWSS for Betna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl No. - 11) Tender No.- 224/NAD-I/2020-2021. | Assistant Engineer-II | Junior Engineer-III | ORD/000175/2020-2021 | 294/NAD-I | 04/02/2021 | 45 | K.P. CONSTRUCTION | 43.55 | 18.21 | 0
4265 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangment in High School, PrimarySchool, SSK & MSK under Jal Jeevan Mission (JJM) atGoalsalua (Zone-I) PWSS, Ranaghat-II Block by Augmentation of Goalsalua Zone-I &II underRanaghat-II Block & Betnaunder Hanskhali Block under Nadia Arsenic Division-I, PHE Dte (sl.10) | Assistant Engineer-II | Junior Engineer-III | ORD/000213/2022-2023 | 205 /NAD-I | 15/02/2023 | 689 | M/S ASOKE GHOSH & BROTHERS | 90.79 | 0 | 30
4266 | Eastern Mechanical | Nadia Arsenic Division I | Load enhancement at Betna ph-1 at Hanskhali Block, Dist.-Nadia | Assistant Engineer-II | Junior Engineer-III | BILL/00543/2024-2025 | BP-27-24-25 | 24/05/2024 | 0 | W.B.S.E.D.C.LTD (CHITRASALI C.C.CENTER) | 1.27 | 0 | 0
4267 | Eastern Mechanical | Nadia Arsenic Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HALALPUR KRISHNAPUR (Z-II),GOALSALUA(Z-I) & GOALSALUA(Z-II) W/S Scheme, Block- Ranaghat-II , Dist. - Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000022/2023-2024 | 1601/EMD | 26/04/2023 | 30 | M/S DILIP MITRA | 56.44 | 0 | 100
4268 | Eastern Mechanical | Nadia Arsenic Division I | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BETNA W/S Scheme, Block-Hanskhali , Dist. - Nadia. NIET No. 39 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer-II | Junior Engineer-III | ORD/000024/2023-2024 | 1603/EMD | 26/04/2023 | 30 | TALUKDER & CO. | 14.46 | 13.07 | 100
4269 | Eastern Mechanical | Nadia Arsenic Division I | Rejuvenation of Goalsalua (Z-i) PWSS regarding FHTC in Ranaghat II Block of Nadia Dist. | Assistant Engineer-II | Junior Engineer-III | ORD/002488/2022-2023 | 926/EMD | 27/05/2022 | 365 | SUSANTA KUMAR DAS | 12.16 | 12.16 | 0
4270 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase-III FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX Ghetugachi, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl. no. 02) | Assistant Engineer-II | Junior Engineer-III | ORD/000012/2022-2023 | 964/NAD-I | 07/07/2022 | 60 | B.S. ENTERPRISE | 65.97 | 0 | 100
4271 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipeline at different location of Zone-II (Hapania) under Nagarukhra-I & II G.P. under 'surface water based piped water supply scheme of HARINGHATA & CHAKDAHA under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000017/2022-2023 | 88/AE-I/NAD-I | 28/04/2022 | 15 | TARUN KUMAR BHATTACHARYA | 4.84 | 0 | 90
4272 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipeline at different location of Jalkar Bhomra (Zone-III) Madanpur (Zone-XII) Birohi (Zone-XI) under Kastodanga-I & II Madanpur-I & II Birohi-I G.P. respectively under 'surface water based piped water supply scheme of HARINGHATA & CHAKDAHA under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000018/2022-2023 | 89/AE-I/NAD-I | 28/04/2022 | 15 | AVINABA ENGINEERING CONCERN | 4.82 | 0 | 85
4273 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 800 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Purba Bishnupur Zone-V under Chakdah Surface WS Scheme in Chakdah Block under NAD-I PHE Dte (Sl.no.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000059/2022-2023 | 1670/ NAD-I | 07/09/2022 | 60 | TAPU SAHA | 33.13 | 29.11 | 100
4274 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Tangra & Bagdob for augmentation of Surface water based PWSS for providing FHTC at Purba Bishnupur ( Zone V) of Surfac water based piped water supply scheme for Chakdah ( Part ) under JJM within Chakdah Block under Nadia Arsenic Division-I , PHE Dte. (SL.No.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000076/2023-2024 | 1400/NAD-I | 16/05/2023 | 25 | CHANDAN ROY | 47.15 | 0 | 100
4275 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 350 cum capacity Over Head Reservoir Two Nos Painting and repairing of HW Boundary Wall, Pump House at Ghetugachi Zone IX under urface WS Scheme of Chakdah Part under NAD I PHE Dte (Sl.no.12) | Assistant Engineer-II | Junior Engineer-III | ORD/000102/2022-2023 | 1985 / NAD-I | 18/10/2022 | 45 | U TURN CONSTRUCTION | 22.32 | 20.02 | 100
4276 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work along Simurali-Kalibazar Road of Ghetugachi (Zone-IX) Water Supply Scheme under Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.08) | Assistant Engineer-II | Junior Engineer-III | ORD/000126/2023-2024 | 1839/NAD-I | 07/08/2023 | 15 | PURNIMA ELECTRICS & DECORATORS | 9.19 | 7.72 | 100
4277 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-V, (Purba Bishnupur), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000178/2021-2022 | 515/NAD-I | 28/03/2022 | 60 | APURBA MANDAL | 156.91 | 155.28 | 100
4278 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000004/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 20.28 | 0 | 0
4279 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repairing of existing structure of WTP and it's different units and other allied works under Zone-I (Fatepur) & Zone-II (Hapania) under Surface Based PWSS for Harinnghata & Chakdah (Part) under JJM under Zone-I & Zone-II, Part-III under Nadia Arsenic Division-I, PHE Dte. (Sl.10 | Assistant Engineer-I | Junior Engineer-II | ORD/000033/2023-2024 | 998 /NAD-I | 17/04/2023 | 25 | SUMAN CHAKRABORTY | 45.59 | 45.49 | 0
4280 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of Clear Water Rising Main at Kalyani More Crossing at NH-34 and other allied works under Jal Jeevan Mission (JJM) for Zone-I Fatepur at Haringhta Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme for Zone-I, (Fatepur), Part-III under Nadia Arsenic Division-I, PHE Dte. (Sl.no.08) | Assistant Engineer-I | Junior Engineer-II | ORD/000035/2023-2024 | 1283 /NAD-I | 08/05/2023 | 30 | GBC INFRASTRUCTURE PRIVATE LIMITED | 55.87 | 55.81 | 0
4281 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work at Bhabanipur Mouza under JJM in connection with Augmentation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000058/2023-2024 | 268/AE-I/NAD-I | 05/06/2023 | 7 | MALI CONSTRUCTION | 0.9 | 0.9 | 100
4282 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work at Satyapole Mouza under JJM in connection with Augmenation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte | Assistant Engineer-I | Junior Engineer-II | ORD/000059/2023-2024 | 269/AE-I/NAD-I | 05/06/2023 | 7 | M/S ARATI ENTERPRISE | 0.89 | 0.89 | 100
4283 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work at Panchkahania Mouza under JJM in connection with Augmentation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000060/2023-2024 | 266/AE-I/NAD-I | 05/06/2023 | 7 | M/S ARATI ENTERPRISE | 0.93 | 0.93 | 100
4284 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work at Behara Mouza under JJM in connection with Augmentation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000061/2023-2024 | 267/AE-I/NAD-I | 05/06/2023 | 7 | MALI CONSTRUCTION | 0.91 | 0.91 | 100
4285 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House at Fatepur ZoneI under Surface WS Scheme of Haringhata Chakdah Part under NAD I PHE Dte (Sl.no.05) | Assistant Engineer-I | Junior Engineer-II | ORD/000081/2022-2023 | 1817/ NAD-I | 26/09/2022 | 60 | SHYAMAL SHIL | 25.68 | 25.11 | 100
4286 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 1100 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Hapania Zone-II under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte.(Sl. No. 04) | Assistant Engineer-I | Junior Engineer-II | ORD/000153/2022-2023 | 3447/NAD-I | 21/12/2022 | 45 | B.S. ENTERPRISE | 37.53 | 0 | 100
4287 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-II (Hapania) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | Assistant Engineer-I | Junior Engineer-II | ORD/000156/2021-2022 | 423/NAD-I | 07/03/2022 | 60 | SUMAN CHAKRABORTY | 85.3 | 80.85 | 100
4288 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-I (Fatepur) at Haringhta Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-I, Fatepur,Part-III under Nadia Arsenic Division-I, PHE Dte. (sl.no.15) | Assistant Engineer-I | Junior Engineer-II | ORD/000163/2022-2023 | 3515 / NAD-I | 09/01/2023 | 60 | MALI CONSTRUCTION | 97.06 | 65.22 | 70
4289 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repairing of existing structure of WTP and other alliedworks under Zone-I (Fatepur) & Zone-II (Hapania)under Surface Water Based PWSS for Haringhata&Chakdah(Part) under Zone-I (Fatepur) & Zone-II(Hapania), Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (sl.11) | Assistant Engineer-I | Junior Engineer-II | ORD/000211/2022-2023 | 200 / NAD-I | 15/02/2023 | 60 | SUMAN CHAKRABORTY | 63.13 | 62.91 | 55
4290 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work for Zone-I (Fatepur) G.P. at Haringhata Block under Jal Jeevna Mission (JJM) by Augmentation of Surface Water Based PWSS forHaringhata & Chakdah (Part) for Zone-I (Fatepur) Part-III under Nadia Arsenic Division-I, PHE Dte. (SL.09) | Assistant Engineer-I | Junior Engineer-II | ORD/000219/2022-2023 | 259/NAD-I | 20/02/2023 | 60 | BKB INFRA PROJECTS PRIVATE LIMITED | 40.51 | 0 | 100
4291 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-II , Hapania at Nagarukhra G.P at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-II, Hapania, Part-III under Nadia Arsenic Division-I, PHE Dte. (sl. 18) | Assistant Engineer-I | Junior Engineer-II | ORD/000221/2022-2023 | 303 /NAD-I | 27/02/2023 | 60 | MONDAL ENTERPRISE | 96.62 | 59.47 | 74
4292 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Gongra W/s Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000001/2023-2024 | 438/NACD-II | 12/04/2023 | 20 | BIPLAB BHOWMICK | 1.47 | 0 | 100
4293 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Maheshpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000033/2021-2022 | 526/NACD-II | 14/06/2021 | 45 | TARUN GHOSH | 66.44 | 132.76 | 100
4294 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Gongra Water Supply Scheme in CHAPRA Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000060/2023-2024 | 320_2/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.29 | 0 | 100
4295 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase -I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipe line (Parallel or extension or damaged line repair) and Bamboo Pilling at Mahatpur(Vill- Pukura) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000081/2021-2022 | 641/NACD-II | 13/08/2021 | 45 | NILAY KUMAR BHATTACHARYA | 59.57 | 119.1 | 100
4296 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Chenderghat W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000094/2021-2022 | 732/NACD-II | 13/09/2021 | 45 | SINGHA ROY & CO. | 65.96 | 131.79 | 100
4297 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-III W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000108/2021-2022 | 766/NACD-II | 22/09/2021 | 45 | SANDIP BISWAS | 84.78 | 169.54 | 100
4298 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Pump house repair at Gongra W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000137/2021-2022 | 859/NACD-II | 08/11/2021 | 45 | PRIYA CONSTRUCTION | 53.27 | 0 | 0
4299 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Gongra Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000284/2023-2024 | 176/NACD-II | 07/02/2024 | 60 | ACQUA CONSTRUCTION CONSORTIUM | 177.79 | 0 | 0
4300 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Pump house repair at Gongra W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000313/2021-2022 | 859/EE/NACD-II | 08/11/2021 | 45 | PRIYA CONSTRUCTION | 53.27 | 0 | 100
4301 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 2 nos. 300 mm X 200 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at new proposed site of Gongra Zone-I and Zone-II in Chapra Block under Gongra Public Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000317/2024-2025 | 1527/NACD-II | 27/11/2024 | 270 | SANDIP BISWAS | 21.68 | 0 | 55
4302 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000348/2024-2025 | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 20
4303 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Reparing of damaged Rising Main at Kadipur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000041/2024-2025 | 755/AE-I/NACD-II | 19/06/2024 | 15 | SANJIT DAS | 0.87 | 0 | 100
4304 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000052/2022-2023 | 222/NACD-II | 05/04/2022 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 36.28 | 36.2 | 100
4305 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur (Vill- Mukundapur, Kadaghata,Chak Pratappur) W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000070/2024-2025 | 726/NACD-II | 10/06/2024 | 359 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 105.56 | 0 | 55
4306 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Survey, Design, Drawing & DPR preparation for Kadipur Water Supply Scheme in Krishnaganj Block of Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000072/2023-2024 | 326_2/AE-I/NACD-II | 13/07/2023 | 7 | SIRCON ENGINEERING SERVICE | 1.29 | 0 | 100
4307 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur & Taldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000111/2021-2022 | 769/NACD-II | 22/09/2021 | 45 | B.M. ENGINEERING & CONSTRUCTION | 88.87 | 88.86 | 100
4308 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Kadipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000124/2020-2021 | 265/NACD-II | 22/02/2021 | 21 | NILAY KUMAR BHATTACHARYA | 55.81 | 0 | 100
4309 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000126/2021-2022 | 860/NACD-II | 08/11/2021 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 36.37 | 36.31 | 100
4310 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur & Taldaha W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000222/2021-2022 | 52/NACD-II | 20/01/2022 | 45 | B.M. ENGINEERING & CONSTRUCTION | 27.75 | 0 | 100
4311 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Kadipur Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000247/2023-2024 | 24/AE-II/NACD-II | 15/02/2024 | 15 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 0.97 | 0 | 100
4312 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Kadipur Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000262/2021-2022 | 44/AE-II/NACD-II | 17/02/2022 | 30 | SANJIT DAS | 4.99 | 4.99 | 100
4313 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Soak pit for disposing of back wash water from IEP and also construction of pathway for smooth movement at Kadipur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000262/2022-2023 | 1017/NACD-II | 29/11/2022 | 20 | SANJIT DAS | 2 | 1.99 | 100
4314 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Kadipur W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000296/2022-2023 | 1194/NACD-II | 23/12/2022 | 15 | SANJIT DAS | 2.07 | 2.04 | 100
4315 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Kadipur PWSS in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000310/2024-2025 | 363/AE-II/NACD-II | 19/11/2024 | 7 | SSPR VALVE MANUFACTURING PVT. LTD. | 0.98 | 0 | 100
4316 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Functional House Hold Tap Connection for left out Household regarding Har Ghar Jal Certification including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Vill- Mukundapur) Kadipur W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000345/2022-2023 | 146/NACD-II | 17/01/2023 | 20 | CHANDRA NATH GHOSH | 1.61 | 1.61 | 100
4317 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction Of 750 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (Including Pile Foundation), Pipe Connection And Cost Of Pipes, Specials & Soil Investigation For Construction Of One No. 750 Cum Ohr Of Staging Height 20 Mtr. for Augmentation of Ground Based Water Supply Scheme at Bara Andulia-I to accommodate FHTC within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000016/2022-2023 | 2055/ND | 10/05/2022 | 1697 | TARUN KUMAR BHATTACHARYA | 640.03 | 232.73 | 48
4318 | Nadia Division | Krishnanagar Sub-Division | Laying Of Additional Distribution System Including Specials to provide FHTC at Leftout Household in connection with JJM In Ground Based Piped Water Supply Scheme at Bara Andulia Zone I To Accommodate FHTC Within Chapra Block Under Krishnanagar Sub-division Under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000316/2025-2026 | 4504/ND | 18/09/2025 | 90 | S.S.INFRASTRUCTURE | 68.11 | 0 | 0
4319 | Nadia Division | Krishnanagar Sub-Division | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period of 90 days w.e.f 01/07/2023 (as and when required). | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000410/2023-2024 | 800/KSD | 16/06/2023 | 92 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0
4320 | Nadia Division | Krishnanagar Sub-Division | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bara Andulia Zone I Water Supply Scheme within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000488/2023-2024 | 6115/ND | 21/12/2023 | 485 | SAHA ENGINEERS | 12.16 | 0 | 20
4321 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 120 m3/hr at Bara Andulia Zone-I Water Supply Scheme within Chapra Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000788/2023-2024 | 1899/ND | 15/03/2024 | 360 | HARBAUER INDIA (P) LTD. | 300.5 | 0 | 20
4322 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000001/2022-2023 | 2161/ND | 18/05/2022 | 0 | Resource Division | 214.18 | 0 | 0
4323 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000050/2022-2023 | 4270/ND | 29/09/2022 | 0 | Resource Division | 8.85 | 0 | 0
4324 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000142/2021-2022 | 1396/ND | 24/03/2022 | 0 | Resource Division | 33.5 | 0 | 0
4325 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | Assistant Engineer | Junior Engineer,Junior Engineer 3 | VCH/001067/2021-2022 | 630/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.11 | 0 | 0
4326 | Central Drilling | Krishnanagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 lVltrs' Depth) by utilizing Departmental Machineries for Bara Andulia w/s scheme (Z-t, T/w-l & ll) , Chapra Block under Nadia District, Central Drilling Division, p.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000127/2023-2024 | 1227/CDD | 04/09/2023 | 300 | MENAKA ENTERPRISE | 37.76 | 0 | 50
4327 | Eastern Mechanical | Krishnanagar Sub-Division | Quotation for new service connection charges and security deposit for PH-4 under Bara-Andulia(Zone-I) w/s scheme, Under EMSD-III,PHE Dte,Nadia | Assistant Engineer | Junior Engineer,Junior Engineer 3 | BILL/01811/2024-2025 | BP-157-24-25 | 06/11/2024 | 0 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 5.06 | 0 | 0
4328 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BARA ANDULIA W/S Scheme, Block- Chapra , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000897/2022-2023 | 407/EMD | 20/01/2023 | 30 | CONCORD ENGINEERING | 26.28 | 0 | 0
4329 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair, & also Rising Main replacement by DI pipe) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000036/2021-2022 | 529/NACD-II | 14/06/2021 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 78.79 | 78.72 | 100
4330 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Thanapara, (Block -Karimpur-II) piped water supply schemes | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000151/2021-2022 | 150/AE-I/NACD-II | 16/11/2021 | 10 | UMWELT ENGINEER PVT LTD. | 3.88 | 3.88 | 100
4331 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply of CIDF Sluice, Non return valves and DI Mechanical collar Vavle for relaying of rising main of Thanapara Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000163/2021-2022 | 166/AE-I/NACD-II | 22/11/2021 | 7 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.97 | 4.97 | 100
4332 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Thanapara (Phase-II), (Block -Karimpur-II) piped water supply schemes | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000171/2021-2022 | 750/NACD-II | 15/09/2021 | 10 | SIRCON ENGINEERING SERVICE | 4.94 | 4.94 | 100
4333 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Saguna) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000214/2021-2022 | 03/NACD-II | 03/01/2022 | 45 | M/S SHILL & CO. | 88.07 | 0 | 100
4334 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair, & also Rising Main replacement by DI pipe) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000226/2021-2022 | 984/NACD-II | 27/12/2021 | 90 | MONDAL ENTERPRISE | 149.3 | 0 | 100
4335 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000230/2021-2022 | 01/EE/NACD-II | 03/01/2022 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 95.95 | 0 | 100
4336 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 1 no. 300 mm X 200 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at 4th pump house site with UPVC pipe (CD) & strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000234/2021-2022 | 91/NACD-II | 08/02/2022 | 45 | JOY HIND TUBEWELLS | 12.33 | 12.33 | 100
4337 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000238/2021-2022 | 902./NACD-II | 22/11/2021 | 45 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 73.33 | 73.31 | 100
4338 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Thanapara Water Supply Scheme 4th Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000242/2021-2022 | 99/NACD-II | 10/02/2022 | 45 | TAPAN SAHA | 7.74 | 6.6 | 100
4339 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Thanapara Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000272/2021-2022 | 47/AE-II/NACD-II | 17/02/2022 | 30 | BISHAL CONSTRUCTION | 4.9 | 4.69 | 100
4340 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Thanapara Water Supply Scheme 3rd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000273/2021-2022 | 48/AE-II/NACD-II | 17/02/2022 | 30 | BIPLAB BHOWMICK | 3.64 | 3.63 | 100
4341 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Saguna) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000301/2021-2022 | 03./NACD-II | 03/01/2022 | 45 | M/S SHILL & CO. | 88.07 | 0 | 100
4342 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | OUTSTANDING BILL PAYMENT FOR SUPPLY OF MATERIALS FOR THANAPARA, DAMODARKHALI, MADHABPUR, BALIADANGA AS FRAMED BY RESOURCE DIVISION PHE DTE. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000643/2021-2022 |  | 05/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0
4343 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUPPLY OF MATERIALS FOR THANAPARA,DAMODARKHALI,MADHABPUR AND BALIADANGA W/S. SCHEME UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000646/2021-2022 |  | 07/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0
4344 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Outstanding as framed by Resource Division for supply of materials for augmentation/retrofitting of Thanapara, Damodarkhali & Madhabpur under Nadia Arsenic Civil Division-II, PHE dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000718/2021-2022 | 212, 213, 214 | 18/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 124.39 | 0 | 0
4345 | Nadia Division | Ranaghat Sub-Division | Construction and installation of MANIFOLD and allied works at Head Works site under Kamalpur Zone-I Ground Based Water Supply Scheme under Ranaghat-II Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000065/2025-2026 | 2374/ND | 22/05/2025 | 90 | AREOCON | 11.89 | 0 | 0
4346 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamalpur Zone-I to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000128/2022-2023 | 3697/ND | 26/08/2022 | 90 | HANNAN BUILDERS PRIVATE LIMITED | 592.18 | 546.44 | 95
4347 | Nadia Division | Ranaghat Sub-Division | Laying 315 mm and 110 mm dia uPVC pipe line in place of damaged 315 mm and 110 mm dia uPVC pipe from Purba Naoapara to Kamalpur for smooth running of Ground Water Based Water Supply Scheme for Kamalpur Zone-I in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000289/2023-2024 | 910/RSD | 13/09/2023 | 30 | M/S BISWAS ENTERPRISE | 4.72 | 0 | 0
4348 | Nadia Division | Ranaghat Sub-Division | Repairing of Pump house-I with sanitary arrangement under augmentation of Kamalpur Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000293/2024-2025 | 1278(A)RSD | 04/10/2024 | 45 | KUHELI ENTERPRISE | 1.89 | 0 | 0
4349 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Kamalpur Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000382/2024-2025 | 1418/RSD | 19/11/2024 | 45 | RENUKA ENTERPRISE | 2.15 | 0 | 100
4350 | Nadia Division | Ranaghat Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Kamalpur Zone-I W/S Scheme in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000440/2021-2022 | 1060/RSD | 02/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.64 | 4.64 | 100
4351 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-III and Construction of Sanitary arrangement under augmentation of Kamalpur Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000675/2024-2025 | 1419/RSD | 19/11/2024 | 45 | MAA ENTERPRISE | 2.15 | 0 | 100
4352 | Nadia Division | Ranaghat Sub-Division | Additional Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Kamalpur Zone-I W/S Scheme in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000742/2021-2022 | 1119/RSD | 21/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.78 | 0.56 | 100
4353 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000013/2023-2024 | 1859/ND | 26/04/2023 | 0 | Resource Division | 84.8 | 0 | 0
4354 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000069/2022-2023 | 4301/ND | 29/09/2022 | 0 | Resource Division | 0.05 | 0 | 0
4355 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000105/2022-2023 | 5104/ND | 08/12/2022 | 0 | Resource Division | 188.62 | 0 | 0
4356 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at KAMALPUR ZONE-I W/S Scheme Block- Ranaghat-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10525] | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000136/2025-2026 | 1137/EMD | 04/06/2025 | 90 | H.K. DAS & CO. | 52.38 | 0 | 0
4357 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of R.C.C. Elevated Reservoir of 600 Cum capacity (including pile foundation), Soil Investigation for construction of OHR, Construction of 1 No. Pump House at proposed Head Work site and Construction of boundary wall with gate all complete for Augmentation of Ground Based Water Supply Scheme at Bara Andulia Zone-II to accommodate FHTC within Chapra block under Krishnanagar Sub-division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000154/2023-2024 | 3220/ND | 26/07/2023 | 366 | GHOSH ENTERPRISE | 467.16 | 0 | 0
4358 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 116 m3/hr at Bara Andulia Zone-II Water Supply Scheme within Chapra Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000384/2024-2025 | 7090/ND | 05/12/2024 | 180 | APURBA MANDAL | 288.79 | 0 | 0
4359 | Nadia Division | Krishnanagar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
4360 | Nadia Division | Krishnanagar Sub-Division | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bara Andulia Zone II Water Supply Scheme within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000477/2023-2024 | 155/ND | 09/01/2024 | 240 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 12.15 | 0 | 75
4361 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000147/2023-2024 | 258/ND | 11/01/2024 | 0 | Resource Division | 10.9 | 0 | 0
4362 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000148/2022-2023 | 82/ND | 05/01/2023 | 0 | Resource Division | 234.57 | 0 | 0
4363 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte.. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | VCH/001072/2021-2022 | 635/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.6 | 0 | 0
4364 | Central Drilling | Krishnanagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilizing Departmental Machineries for Bara Andulia W/S Scheme (Z-II, T/W-I) , Chapra Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000128/2023-2024 | 1231/CDD | 04/09/2023 | 30 | MENAKA ENTERPRISE | 18.88 | 0 | 0
4365 | Eastern Mechanical | Krishnanagar Sub-Division | Quotation for new service connection charges and security deposit for PH-3 under Bara-Andulia(Zone-I) w/s scheme, Under EMSD-III,PHE Dte,Nadia | Assistant Engineer | Junior Engineer,Junior Engineer 3 | BILL/01810/2024-2025 | BP-158-24-25 | 06/11/2024 | 0 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 3.71 | 0 | 0
4366 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery and Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under Bara Andulia Z-II) WS Scheme, Block-Chapra , Dist. - Nadia. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/001125/2023-2024 | 4713/EMD | 04/08/2023 | 30 | INDTECH ASSOCIATES | 29.24 | 0 | 60
4367 | Eastern Mechanical | Nadia Arsenic Civil Division II | Shifting of 1 Nos. PCC pole along with LTOH line for obstruction in construction work by PHE dept. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/01759/2023-2024 | BP-91-23-24 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.12 | 0 | 0
4368 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill for new service connection at panchdhara abhaynagar | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/02147/2022-2023 | 146/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.71 | 0 | 0
4369 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill for new service connection at panchdhara abhaynagar | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/02148/2022-2023 | 147/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.52 | 0 | 0
4370 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill for new service connection at Panchdhara Abhaynagar | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/02149/2022-2023 | 148/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.13 | 0 | 0
4371 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.III under Panchdara W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 15) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000424/2022-2023 | 6254/EMD | 19/11/2022 | 30 | HARA PROSAD DAS | 10 | 0 | 70
4372 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Panchdara W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 14) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000427/2022-2023 | 6255/EMD | 19/11/2022 | 30 | MASSK ENGINEERING WORKS | 9.96 | 0 | 80
4373 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Panchdara W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 13) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000429/2022-2023 | 6256/EMD | 19/11/2022 | 30 | BISALAXMI ENTERPRISE | 9.99 | 0 | 100
4374 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00013/2023-2024 | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
4375 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00086/2022-2023 | 235/2 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0
4376 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Restoration of road flank of Plassey Betai road from 12.50 Kmp to 16.50 Kmp at Panchdhara Avaynagar w/s. scheme Block Tehatta-II under Nadia Arsenic Civil Division II, PHE Dte against estimate order No. 1450 DT. 21.08.2023 & this office memo no. 890/ NACD-II dt. 21.08.2023 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00333/2023-2024 |  | 07/09/2023 | 0 | EXECUTIVE ENGINEER,NADIA HIGHWAY DIVISION NO-I, P.W.(ROADS) DIRECTORATE | 39.9 | 0 | 0
4377 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Regarding restoration of flank of Plassey Betai Road from 12.50 Kmp to 16.50 Kmp | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | BILL/00356/2023-2024 | 152 | 08/09/2023 | 0 | EXECUTIVE ENGINEER,NADIA HIGHWAY DIVISION NO-I, P.W.(ROADS) DIRECTORATE | 20 | 0 | 0
4378 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 600 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Panchdara Abhaynagar water supply scheme of Tehatta-II Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000012/2023-2024 | 540/NACD-II | 10/05/2023 | 366 | AMIT KUMAR BOSE | 155.99 | 0 | 0
4379 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Panchdara Abhaynagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000042/2022-2023 | 256/NACD-II | 25/04/2022 | 60 | PARTHA DAS | 5.37 | 5.37 | 100
4380 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Panchdara Abhaynagar water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000043/2022-2023 | 10/AE-II/NACD-II | 11/04/2022 | 60 | PARTHA DAS | 2.83 | 2.83 | 100
4381 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-3 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Panchdara Abhaynagar water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000044/2022-2023 | 11/AE-II/NACD-II | 11/04/2022 | 60 | PARTHA DAS | 2.83 | 2.83 | 100
4382 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Panchdara Abhyanagar Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000062/2022-2023 | 23/AE-II/NACD-II | 18/04/2022 | 1191 | PARTHA DAS | 4.96 | 0 | 100
4383 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Earth work in filling in ditches at Panchdara Abhaynagar H/W Site for development of land in connection with proposed T/W Sinking & Pump House construction at Panchdara Abhaynagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000125/2022-2023 | 61/AE-II/NACD-II | 28/06/2022 | 20 | VAI ENTERPRISE | 4.75 | 4.74 | 100
4384 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 3 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site and 3rd Tubewell site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Panchdara Abhaynagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000134/2022-2023 | 431/NACD-II | 07/07/2022 | 45 | JOY HIND TUBEWELLS | 32.55 | 0 | 100
4385 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Panchdara Abhynagar and adjoining mouzas under Panchdara Abhynagar Water Supply Scheme of Tehatta-II Block, under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000173/2022-2023 | 460/NACD-II | 18/07/2022 | 90 | GHOSH BROTHERS | 520.23 | 350.38 | 80
4386 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-II Block of Nadia District through Jadavpur University. (Name of PWSS Panchdhara Abhynagar) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000175/2023-2024 | 1263/NACD-II | 09/11/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 0 | 100
4387 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 113 cum/Hour capacity for Panchdara Abhaynagar Water Supply Scheme within Tehatta-II block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000189/2024-2025 | 1031/NACD-II | 02/08/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 282.81 | 0 | 0
4388 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Panchdara Abhaynagar Water Supply Scheme of Tehatta-II Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000200/2022-2023 | 629/NACD-II | 06/09/2022 | 20 | RAMASISH ENTERPRISE | 6.88 | 6.88 | 100
4389 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Panchdhara Abhaynagar Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000324/2022-2023 | 88/NACD-II | 10/01/2023 | 60 | SHYAM SUNDAR SAHA | 15.89 | 0 | 90
4390 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Panchdhara Abhaynagar 2nd Tubewell Site within Panchdhara Abhaynaga Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000334/2022-2023 | 127/NACD-II | 11/01/2023 | 60 | VAI ENTERPRISE | 5.7 | 0 | 90
4391 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Panchdhara Abhaynagar 3rd Tubewell Site within Panchdhara Abhaynaga Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000336/2022-2023 | 128/NACD-II | 11/01/2023 | 60 | JOY GURU ENTERPRISE | 4.5 | 4.2 | 90
4392 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | RTOR000007/2023-2024 | 80/NACD-II | 15/01/2024 | 0 | Resource Division | 13.52 | 0 | 0
4393 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | RTOR000015/2022-2023 | 400/NACD-II | 04/07/2022 | 0 | Resource Division | 40.34 | 0 | 0
4394 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | RTOR000017/2022-2023 | 416/NACD-II | 05/07/2022 | 0 | Resource Division | 3 | 0 | 0
4395 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000234/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
4396 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 4, Nadia Arsenic Civil Division-II | VCH/000341/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
4397 | Nadia Division | RWS Nadia Sub-Division | Laying of D I Pipe line in place of UPVC pipe including other allied works from OHR to both side of head work site for providing FHTC under Jal Swapna at Subarnabehar w/s scheme under Nadia Division PHED. | Assistant Engineer |  | ORD/000065/2022-2023 | 215/PH | 12/07/2022 | 30 | SURAJIT KUMAR GHOSH | 4.65 | 2.66 | 92
4398 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Senpur W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000244/2020-2021 | 62/ND | 07/01/2021 | 90 | M/S KALIMATA ENTERPRISE | 96.97 | 0 | 100
4399 | Nadia Division | RWS Nadia Sub-Division | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 60 | BIBHAS PAL | 96.01 | 0 | 81
4400 | Nadia Division | RWS Nadia Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT SENPUR W/S SCHEME | Assistant Engineer |  | VCH/001075/2020-2021 | 460/DW | 30/03/2021 | 0 | M/S KALIMATA ENTERPRISE | 67.02 | 0 | 0
4401 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Banpur to accommodate FHTC in Krishnaganj block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000145/2022-2023 | 4041/ND | 19/09/2022 | 590 | A.P. POWER & CONCRETE | 146.68 | 137.1 | 96
4402 | Nadia Division | Ranaghat Sub-Division | Repairing of Pump house-I with sanitary arrangement under augmentation of Banpur piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000177/2024-2025 | 1143/RSD | 11/09/2024 | 45 | ILA CONSTRUCTION | 1.89 | 0 | 85
4403 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
4404 | Nadia Division | Ranaghat Sub-Division | Laying distribution system for augmentation of Ground Water Based Water Supply Scheme for Banpur to accommodate FHTC in Krishnaganj block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000314/2023-2024 | 4321/ND | 26/09/2023 | 60 | A.P. POWER & CONCRETE | 27.65 | 0 | 100
4405 | Nadia Division | Ranaghat Sub-Division | Balance Laying distribution system for augmentation of Ground Water Based Water Supply Scheme for Banpur to accommodate FHTC in Krishnaganj block of Nadia District under Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000645/2023-2024 | 123/RSD | 29/01/2024 | 30 | A.P. POWER & CONCRETE | 4.76 | 0 | 100
4406 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-II and Construction of Sanitary arrangement under Augmentation of Banpur PWSS. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000814/2024-2025 | 205/RSD | 06/02/2025 | 45 | ABHAYANANDA ENTERPRISE | 2.52 | 0 | 100
4407 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000023/2023-2024 | 1867/ND | 26/04/2023 | 0 | Resource Division | 23.96 | 0 | 0
4408 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000076/2022-2023 | 4279/ND | 29/09/2022 | 0 | Resource Division | 8.45 | 0 | 0
4409 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000092/2023-2024 | 2323/ND | 29/05/2023 | 0 | Resource Division | 8.45 | 0 | 0
4410 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 3 | RTOR000107/2022-2023 | 5172/ND | 13/12/2022 | 0 | Resource Division | 6.18 | 0 | 0
4411 | Nadia Division | Ranaghat Sub-Division | PROVIDING FHTC BY AUGMENTATION FOR MONIPOTA PWSS BLOCK: KRISHNAGAR - I DISTRICT: NADIA | Assistant Engineer | Junior Engineer,Junior Engineer 3 | VCH/000349/2022-2023 | 49/PFMS | 22/06/2022 | 0 | HORIZEN | 2.69 | 0 | 0
4412 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at BANPUR W/S Scheme Block- KRISHNAGANJ under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10568] | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000142/2025-2026 | 1143/EMD | 04/06/2025 | 90 | AHALYA ENGINEERING WORKS | 37.79 | 0 | 0
4413 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Nabla, Part-IV at Santipur block by retrofitting/augmentation of Ground Water Based PWSS for Nabla W/S scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 18) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000025/2022-2023 | 1319/NAD-I | 04/08/2022 | 30 | CHOWDHURY & CO. | 55.7 | 55.69 | 100
4414 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD andallied works at OHR site under Behria Ground Based Water Supply Scheme under Santipur under Office of Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation under JJM under Beharia Part-III, Piped Water Supply Scheme (Sl.no.33) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000046/2023-2024 | 1364/NAD-I | 12/05/2023 | 15 | DEBASISH DEY | 12.2 | 0 | 100
4415 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 100 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Goalpur, Zone-I W/S Scheme of Santipur Block under NAD- I, PHE Dte ( Sl.no.18) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000067/2022-2023 | 1725 / NAD-I | 13/09/2022 | 45 | MONDAL ENTERPRISE | 11.12 | 11.09 | 100
4416 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall Toilet Pathway and other allied work at Goalpur Zone I WS Scheme within Santipur Block under Nadia Arsenic Division-I, PHE Dte ( Sl.No.02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000074/2022-2023 | 1798 / NAD-I | 26/09/2022 | 45 | N.H. ENTERPRISE | 14.18 | 14.08 | 100
4417 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 136 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall Pump House and AIRP at Nabla W/S Scheme Santipur Block under NAD- I PHE Dte (Sl.no.03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000075/2022-2023 | 1799 /NAD-I | 26/09/2022 | 45 | M/S S & P CONSTRUCTION | 15.29 | 15.24 | 100
4418 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Beharia WS Scheme Santipur Block under NAD PHE Dte (Sl.no.01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000076/2022-2023 | 1831 / NAD-I | 27/09/2022 | 45 | PALCON | 24.15 | 24.1 | 100
4419 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall , Toilet, Pathway and other allied work at Goalpur Z-II WAter Supply scheme within Santipur block under Nadia Arsenic Division -I , P.H.E.Dte. ( Sl.no. 01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000080/2022-2023 | 219 / AE-I/NAD-I | 02/09/2022 | 30 | BUDDHADEB MONDAL | 0.97 | 0.97 | 100
4420 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet, Pathway and other allied work at Beharia W/S Scheme within Santipur Block under NAD I PHE Dte (sl.no.16) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000119/2022-2023 | 2010 / NAD-I | 19/10/2022 | 45 | S S CONSUTANCYAND CONSTRUCTION | 13.08 | 13.05 | 100
4421 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet, Pathway and other allied work at Nabla W/S Scheme within Santipur Block under NAD I PHE Dte (sl.no. 15) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000140/2022-2023 | 3093/NAD-I | 21/11/2022 | 45 | G S CONSTRUCTION AND CO. | 14.24 | 14.12 | 100
4422 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House and AIRP at Goalpur Zone-II under Nadia Arsenic Division -I, P.H.E.DTE. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000142/2022-2023 | 3157 / NAD-I | 25/11/2022 | 60 | DAS CONSTRUCTION | 11.08 | 11.04 | 100
4423 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Beharia, Nabla, Goalpur Zone-I and Goalpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla, Goalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000154/2021-2022 | 421/NAD-I | 07/03/2022 | 60 | CHOWDHURY & CO. | 95.27 | 90.4 | 100
4424 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Malipota. Phulia Para at Santipur block by retrofitting of Ground Water Based PWSS for Beharia W/S Scheme under Nadia Arsenic Division- I, PHE Dte (Sl.no.12) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000163/2023-2024 | 2121/NAD-I | 04/09/2023 | 21 | CHOWDHURY & CO. | 12.91 | 0 | 100
4425 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP at Goalpur Zone-I Water Supply Scheme under Shantipur Block of capacity 15 Cu.m/hr inconnection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000237/2023-2024 | 2344/NAD-I | 03/10/2023 | 1062 | SATYABRATA CHAKRABORTY | 67.28 | 0 | 100
4426 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work of laying of UPVC and M.S. pipeline and other allied works at Goalpur mouza under Jal Jeevan Mission (JJM) under Goalpur Zone-II, Part-III at Santipur Block under Ground Water Based PWSS for Goalpur Zone-II under Nadia Arsenic Division-I, P.H.E. Dte. (sl.17) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000240/2022-2023 | 536 / NAD-I | 13/03/2023 | 21 | CHOWDHURY & CO. | 14.94 | 14.94 | 30
4427 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Back Wash Water Holding Tank and Land development and allied works at Head work site of Goalpur Zone-I PWSS under Shantipur Block under Nadia Arsenic Division- I P.H.E Dte | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000289/2023-2024 | 32/AE-I/NAD-I | 19/01/2024 | 601 | SATYABRATA CHAKRABORTY | 4.82 | 0 | 100
4428 | Central Drilling | Nadia Arsenic Division I | Providing Drilling Crew and other allied works for construction of TW (250mm x 150mm x 300mtr. depth) by utilising Departmental Machineries for Goalpur WS Scheme (Z-II), Santipur-I Block under Nadia District, CDD,PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000331/2022-2023 | 1452/CDD | 30/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 15.55 | 10.86 | 0
4429 | Nadia Division | Ranaghat Sub-Division | Urgent basis carriage of different dia DI Pipe which is supply by Resource Division at different water supply scheme under Ranaghat Sub-Division, Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000153/2024-2025 | 796/RSD | 02/08/2024 | 15 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 0.98 | 0 | 100
4430 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Kamalpur Z-II Water Supply scheme Ranaghat-II block in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000246/2021-2022 | 5701/ND | 03/11/2021 | 1123 | PRIYA CONSTRUCTION | 63.6 | 0 | 100
4431 | Nadia Division | Ranaghat Sub-Division | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Kamalpur Zone-II under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000383/2024-2025 | 1420/RSD | 19/11/2024 | 45 | M/S DAYANIDHI CONSTRUCTIONS | 2.15 | 0 | 100
4432 | Nadia Division | Ranaghat Sub-Division | Augmentation of Ground Water Based piped Water Supply scheme for Kamalpur Zone-II to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000431/2022-2023 | 893/ND | 02/03/2023 | 810 | CHOWDHURY & CO. | 94.41 | 0 | 85
4433 | Nadia Division | Ranaghat Sub-Division | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Kamalpur Zone-II W/S Scheme in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000441/2021-2022 | 1061/RSD | 02/12/2021 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.64 | 2.95 | 100
4434 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000001/2023-2024 | 1516/ND | 04/04/2023 | 0 | Resource Division | 0.96 | 0 | 0
4435 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000014/2023-2024 | 1860/ND | 26/04/2023 | 0 | Resource Division | 12.64 | 0 | 0
4436 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000084/2023-2024 | 2286/ND | 29/05/2023 | 0 | Resource Division | 1.29 | 0 | 0
4437 | Eastern Mechanical | Ranaghat Sub-Division | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at KAMALPUR ZONE-II W/S Scheme Block- Ranaghat-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/10596] | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000147/2025-2026 | 1148/EMD | 04/06/2025 | 90 | M/S. G.P. ENTERPRISE | 29.62 | 0 | 0
4438 | Nadia Arsenic Division I | Nadia Arsenic Division I | Collection of Household data through mobile app for FHTC Connection at Following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Nrisinghapur ii)Gobindapur Zone-I iii)Gobindapur Zone-II | Assistant Engineer-I | Junior Engineer-II | ORD/000005/2023-2024 | 167/AE-I/NAD-I | 12/04/2023 | 15 | HORIZEN | 4.84 | 4.84 | 44
4439 | Nadia Arsenic Division I | Nadia Arsenic Division I | Reconnection at Beledanga, Uttarpara, Chandkuri, Harinadi, Sahebdanga laying of pipeline and rising main at Beledanga, Uttarpara, Chandkuri, Harinadi, Sahebdanga under Harinadi G.P. & supply of Sluice Valve with construction of chamber at H/W site and 2nd, 3rd, 4th Pump House under Jal Jeevan Mission (JJM) for Santipur Block by retrofitting of Ground Water Based PWSS for Nrisinghapur W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-I | Junior Engineer-II | ORD/000017/2024-2025 | 1039/NAD-I | 08/07/2024 | 300 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 7.72 | 0 | 100
4440 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Nrisinghapur Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM of Nrisinghapur Piped W/S Scheme (sl.15) | Assistant Engineer-I | Junior Engineer-II | ORD/000023/2023-2024 | 1159 /NAD-I | 28/04/2023 | 15 | CHOWDHURY & CO. | 13.02 | 0 | 0
4441 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jaldhara/Jal Swapna for Nrisinghapur at Santipur Block by augmentation of Ground water Based PWSS for Nrisinghapur W/S Scheme under Nadia Arsenic Division -I ,P.H.E.Dte.(Sl.No.05) | Assistant Engineer-I | Junior Engineer-II | ORD/000050/2022-2023 | 1689 / NAD-I | 08/09/2022 | 45 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 864.56 | 0 | 75
4442 | Nadia Arsenic Division I | Nadia Arsenic Division I | Road Restoration Work along PMGSY Road under Nrisinghapur Ground Water Supply Scheme at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000259/2023-2024 | 2595/NAD-I | 17/11/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 48.14 | 0 | 100
4443 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-II | RTOR000019/2022-2023 | 3155/NAD_I | 25/11/2022 | 0 | Resource Division | 57.42 | 0 | 0
4444 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jaldhara/Jalswapna for Gobindapur Z-I Santipur Bolck by Augmentation of Ground Water Based PWSS for Gobindapur Z-I W/S scheme under Nadia Arsenic Division-I , P.H.E.Dte (Sl.no.04) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000065/2022-2023 | 1672 / NAD-I | 07/09/2022 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 534.08 | 329.34 | 70
4445 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work at villages Panchpota, Koehua Para, Bagdia, Beale Danda, Promoth Nagar in connection with Augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone-I at Santipur Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.No.05) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000070/2023-2024 | 1379/NAD-I | 15/05/2023 | 30 | ALOK ENTERPRISE | 49.8 | 0 | 80
4446 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP (Pressure Type) at Gobindapur, Zone-I W/S Scheme under Santipur Block of capacity 110 cum/hr. under augmentation of Gobindapur, Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl.no.06) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000134/2023-2024 | 1902/NAD-I | 14/08/2023 | 818 | MULTITEX ENGINEERING INDUSTRIES | 159.34 | 0 | 60
4447 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of Rising main line at Gobindapur zone-I in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (sL.NO.16) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000238/2023-2024 | 2301/NAD-I | 29/09/2023 | 15 | M/S DIPAK ENTERPRISE | 18.43 | 0 | 100
4448 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting Pipeline work for providing FHTC (Functional Household Tap Connection) and dedicated line from manifold at Shantipur Block of Ground Water Based PWSS for Gobindapur (Zne-I & II) W/S Scheme inconnection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000271/2023-2024 | 2751/NAD-I | 11/12/2023 | 983 | SAHA ENGINEERS | 15.75 | 0 | 85
4449 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | RTOR000020/2022-2023 | 3155/NAD_I | 25/11/2022 | 0 | Resource Division | 52.05 | 0 | 0
4450 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | RTOR000022/2022-2023 | 108/NAD-I | 31/01/2023 | 0 | Resource Division | 92.4 | 0 | 0
4451 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at GOBINDAPUR ZONE-I under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/10660) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000151/2025-2026 | 1153/EMD | 04/06/2025 | 90 | M/S DAS ENTERPRISE | 4.34 | 0 | 0
4452 | Eastern Mechanical | Nadia Arsenic Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well at Pump House No.-I and II ,Zone-I and New Tube Well at Pump House No.-III, Zone-I in connection to Accommodate FHTC under Gobindapur ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. [SM-10660] | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000644/2024-2025 | 2681/EMD | 20/11/2024 | 30 | M/S. G.P. ENTERPRISE | 20.56 | 0 | 0
4453 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair Renovation of Chakdah WTP and intake with different units and Boundary Wall of WTP under Surface W/S Scheme of Chakdah (Part) block under Nadia Arsenic Division-I PHE Dte (Sl. NO. 09) | Assistant Engineer-II | Junior Engineer-III | ORD/000037/2022-2023 | 1533/NAD-I | 31/08/2022 | 60 | PALCON | 52.63 | 44.03 | 95
4454 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at BalagariChar Zone-XII under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte (Sl.no.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000079/2022-2023 | 1763 / NAD-I | 19/09/2022 | 45 | BISHALAXMI ENTERPRISE | 20.08 | 19.34 | 100
4455 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between node point 3 and 76 of Balagarichar W/S Scheme for augmentation work at Uttar Ghughia village under Chakdah (Part) Water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-III | ORD/000079/2023-2024 | 1412/NAD-I | 18/05/2023 | 30 | MESSRS FREEDOM CONSTRUCTION | 62.36 | 0 | 100
4456 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase-III FHTC ((Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-XII, (Balagarichar) at Chakdah Block by retrofitting of Surface Water Based PWSS for Chakdah (Part) Water Supply under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 12) | Assistant Engineer-II | Junior Engineer-III | ORD/000129/2022-2023 | 3043/NAD-I | 09/11/2022 | 45 | M/S A.K. CONSTRUCTION | 33.39 | 32.59 | 100
4457 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Gobindapur Zone-II at Santipur Block by retrofitting of Ground Water based PWSS for Gobindapur W/S Scheme under Nadia Arsenic Division-I, P.H.E Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-II | ORD/000008/2022-2023 | 765/NAD-I | 07/06/2022 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 637.9 | 632.37 | 100
4458 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Gobindapur Zone-II Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with Retrofitting under JJM under Gobindapur Zone-II Piped W/S Scheme (Sl.no.32) | Assistant Engineer-I | Junior Engineer-II | ORD/000043/2023-2024 | 1363/ NAD-I | 12/05/2023 | 15 | SANDIP ROY | 12.75 | 0 | 100
4459 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House repair, Construction of Rigid Pavement and Boundary Wall for 2nd & 3rd T/W site at Gobindapur Zone-II Water Supply Scheme in Santipur Block under Nadia Arsenic Division-I, PHE Dte. (sl.no.14) | Assistant Engineer-I | Junior Engineer-II | ORD/000154/2022-2023 | 3448 / NAD-I | 21/12/2022 | 1572 | THE CALCUTTA CONSTRUCTION | 38.03 | 14.71 | 100
4460 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-II | RTOR000006/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 28.78 | 0 | 0
4461 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-II | RTOR000011/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 12.69 | 0 | 0
4462 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service Connection under AE-III Hridaypur | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/01859/2023-2024 | BP-96-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.64 | 0 | 0
4463 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service connection under AE-III Hridaypur | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/01860/2023-2024 | BP-95-23-24 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.17 | 0 | 0
4464 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under HRIDAYPUR W/S Scheme (Block : Tehatta I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 11) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000031/2023-2024 | 1610/EMD | 26/04/2023 | 30 | SARKAR ELECTRICAL | 19 | 0 | 0
4465 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at HRIDAYPUR Piped Water Supply Scheme, Block_ Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl. No.19) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/003197/2023-2024 | 946/EMD | 18/03/2024 | 30 | M.S. ENTERPRISE | 52.66 | 0 | 0
4466 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/00015/2023-2024 | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.04 | 0 | 0
4467 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/00088/2022-2023 | 235/3 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
4468 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 400 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Hridaypur Water Supply Scheme and other necessary allied works in this connection of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000002/2023-2024 | 466/NACD-II | 20/04/2023 | 366 | RADIANT | 591.46 | 0 | 26
4469 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Hridaypur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000085/2023-2024 | 892/NACD-II | 21/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
4470 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including laying of pipeline at Betberia W/S Scheme & Hridaypur W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000135/2024-2025 | 748_NACD-II | 14/06/2024 | 45 | SAFTI PRIVATE LIMITED | 18.22 | 0 | 100
4471 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Securitization arrangement by composite RCC Masonry structures without harming the T & P in the proposed sites of Hridaypur water supply scheme under Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000144/2023-2024 | 1396/NACD-II | 13/12/2023 | 45 | PAPAN ROY | 25.75 | 0 | 0
4472 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in Hridaypur Piped Water Supply Scheme and other schemes in different Blocks in the District of Nadia under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000165/2024-2025 | 873/AE-I/NACD-II | 23/08/2024 | 45 | TECH VISION | 4.77 | 0 | 100
4473 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 73 cum/Hour capacity for Hridaypur Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000168/2024-2025 | 1052/NACD-II | 07/08/2024 | 180 | ALOK ENTERPRISE (A UNIT OF SAKETTREXIM PVT LTD.) | 212.91 | 0 | 0
4474 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Hridaypur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000279/2022-2023 | 1134/NACD-II | 16/12/2022 | 30 | JOY HIND TUBEWELLS | 21.46 | 0 | 100
4475 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Portal framed structural arrangement as well as Water supply/Sanitation arrangement and left out hydraulics in the proposed sites of Hridaypur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II, PHE Dte. Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000326/2023-2024 | 431/NACD-II | 15/03/2024 | 45 | BIPLAB BHOWMICK | 11.31 | 0 | 0
4476 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | RTOR000002/2023-2024 | 77/NACD-II | 15/01/2024 | 0 | Resource Division | 17.35 | 0 | 0
4477 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | RTOR000023/2022-2023 | 1085/NACD-II | 09/12/2022 | 0 | Resource Division | 26.69 | 0 | 0
4478 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | RTOR000027/2022-2023 | 377/NACD-II | 24/03/2023 | 0 | Resource Division | 17.35 | 0 | 0
4479 | Nadia Division | Debgram Sub-Division | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000165/2025-2026 | 3260/ND | 10/07/2025 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 5
4480 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
4481 | Nadia Division | Debgram Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 900 cum. for Providing FHTC (Functional Household Tap Connection) for Zone -IV/A (NORTHERN SECTOR, PART-II) Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000265/2023-2024 | 4001/ND | 07/09/2023 | 60 | JOY HIND TUBEWELL'S | 33.19 | 0 | 45
4482 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 50
4483 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 4A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000792/2021-2022 | 142/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.94 | 3.94 | 100
4484 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000121/2023-2024 | 244/ND | 11/01/2024 | 0 | Resource Division | 7.83 | 0 | 0
4485 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000136/2022-2023 | 96/ND | 05/01/2023 | 0 | Resource Division | 297.03 | 0 | 0
4486 | Nadia Division | Krishnanagar Sub-Division | RESTORATION OF ROAD FROM JHITKIPOTA - BANAGRAM ARPAN MUKHERJEE ROAD under Package No. WB/14/157 | Assistant Engineer | Junior Engineer 3 | BILL/00507/2024-2025 | 299/PFMS | 02/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 7.71 | 0 | 0
4487 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000196/2023-2024 | 3537/ND | 11/08/2023 | 1147 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 0 | 20
4488 | Nadia Division | Krishnanagar Sub-Division | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000236/2025-2026 | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0
4489 | Nadia Division | Krishnanagar Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
4490 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | Assistant Engineer | Junior Engineer 3 | ORD/000706/2024-2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0
4491 | Nadia Division | Krishnanagar Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 4/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .07) | Assistant Engineer | Junior Engineer 3 | ORD/000716/2021-2022 | 209/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.81 | 4.75 | 100
4492 | Nadia Division | Krishnanagar Sub-Division | Additional Survey, Design Drawing & DPR Preparation for ZONE 4/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. (Sl.No .08 ) | Assistant Engineer | Junior Engineer 3 | ORD/000717/2021-2022 | 210/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.23 | 1.23 | 100
4493 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | Assistant Engineer | Junior Engineer 3 | ORD/000758/2023-2024 | 1838/KSD | 28/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0
4494 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 3 | RTOR000163/2022-2023 | 110/ND | 05/01/2023 | 0 | Resource Division | 104.9 | 0 | 0
4495 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill for new service connection at Hatkhola under EMSD-III | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/02150/2022-2023 | 144/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.55 | 0 | 0
4496 | Eastern Mechanical | Nadia Arsenic Civil Division II | Electricity bill for new service connection at Hatkhola under EMSD-III | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | BILL/02151/2022-2023 | 145/PFMS/EMD | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3 | 0 | 0
4497 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under HATKHOLA W/S Scheme (Block : Chapra) Dist.- Nadia. NIET No.-36 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000011/2023-2024 | 1574/EMD | 24/04/2023 | 30 | BISALAXMI ENTERPRISE | 18.99 | 18.19 | 100
4498 | Eastern Mechanical | Nadia Arsenic Civil Division II | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at HATKHOLA Piped Water SupplyScheme, Block: Chapra, Dist. Nadia Under EMD, PHE Dte. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000013/2023-2024 | 1576/EMD | 24/04/2023 | 30 | M/S. SAJAHAN CHOWDHURY | 40.81 | 0 | 0
4499 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Hatkhola water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000007/2022-2023 | 205/NACD-II | 05/04/2022 | 60 | JAYBRATO HALDER | 5.37 | 5.32 | 100
4500 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement for Tube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Hatkhola water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000033/2022-2023 | 20/AE-I/NACD-II | 13/04/2022 | 60 | JAYBRATO HALDER | 2.83 | 2.81 | 100
4501 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Rising Main of Hatkhola Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000037/2022-2023 | 24/AE-I/NACD-II | 13/04/2022 | 60 | M/S. ASIT KUMAR BISWAS | 4.14 | 0 | 100
4502 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction for priliminary work of the approch road at Head Works site of Hatkhola Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000041/2023-2024 | 406/AE-I/NACD-II | 08/08/2023 | 15 | MITRA CONSTRUCTION | 0.85 | 0 | 100
4503 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Hatkhola and adjoining mouzas under Hatkhola Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000066/2022-2023 | 298/NACD-II | 19/05/2022 | 90 | TIRUPATI ENTERPRISES | 188.27 | 170.2 | 100
4504 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Hatkhola) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000080/2023-2024 | 880/NACD_II | 17/08/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100
4505 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Construction for priliminary work of the approch road at Head Works site of Hatkhola Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000130/2024-2025 | 836_AE-I/NACD-II | 01/08/2024 | 15 | MITRA CONSTRUCTION | 0.84 | 0 | 0
4506 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Sanatanpur and Hatkhola Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000136/2022-2023 | 433/NACD-II | 07/07/2022 | 60 | B.M. ENGINEERING & CONSTRUCTION | 42.16 | 0 | 100
4507 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Hatkhola Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000188/2022-2023 | 618/NACD-II | 06/09/2022 | 20 | MAKALI ENGINEERING CORPORATION | 3.86 | 3.86 | 100
4508 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 45 cum/Hour capacity for Hatkhola Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000203/2024-2025 | 1152/NACD-II | 27/08/2024 | 540 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 176.21 | 0 | 66
4509 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Bagberia & Hatkhola Water Supply Scheme of capacity 35 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000290/2023-2024 | 197/NACD-II | 12/02/2024 | 90 | SINGHA ROY & CO. | 159.46 | 0 | 30
4510 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Hatkhola Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000314/2022-2023 | 78/NACD-II | 10/01/2023 | 60 | JAYBRATO HALDER | 16.97 | 16.94 | 85
4511 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Construction of 100 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir at Head Works site of Tengra Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000325/2023-2024 | 337/NACD-II | 05/03/2024 | 365 | CHATTERJEE CONSTRUCTION | 94.23 | 0 | 0
4512 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Hatkhola 2nd Tubwell site within Hatkhola Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000337/2022-2023 | 117/NACD-II | 11/01/2023 | 60 | SOMNATH GHOSH | 5.04 | 4.6 | 100
4513 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000348/2024-2025 | 1657/NACD-II | 30/12/2024 | 360 | CHANDAN ROY | 149.25 | 0 | 20
4514 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Hatkhola) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000354/2023-2024 | 420/NACD-II | 14/03/2024 | 21 | JADAVPUR UNIVERSITY | 5.9 | 0 | 100
4515 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Hatkhola water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000375/2022-2023 | 361/NACD-II | 22/03/2023 | 366 | MITRA CONSTRUCTION | 117.35 | 25.92 | 53
4516 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | RTOR000003/2022-2023 | 407/NACD-II | 04/07/2022 | 0 | Resource Division | 33.97 | 0 | 0
4517 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000230/2022-2023 |  | 20/09/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
4518 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 2, Nadia Arsenic Civil Division-II | VCH/000337/2022-2023 | 141 | 01/11/2022 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
4519 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service connection at PH-I under Jayrampur W/S scheme. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/02376/2023-2024 | BP-138-23-24 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.52 | 0 | 0
4520 | Eastern Mechanical | Nadia Arsenic Civil Division II | New Service connection at PH-II under Jayrampur W/S scheme. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/02378/2023-2024 | BP-138-23-24 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.08 | 0 | 0
4521 | Eastern Mechanical | Nadia Arsenic Civil Division II | Supply, delivery, installation and commissioning of electro-mechanical accessories in connection with installation of Clear Water Pumping machinery in JAYRAMPUR PWSS, Block_ KARIMPUR-I, District- Nadia. Under EMD PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/002822/2023-2024 | 812/EMD | 11/03/2024 | 30 | STANDARD ENGINEERING | 9.68 | 0 | 0
4522 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00018/2023-2024 | 23 | 19/04/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0
4523 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | BILL/00091/2022-2023 | 235/6 | 21/02/2023 | 0 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0
4524 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of approch road at Head Works site of Jayrampur Water Supply Scheme in Karimpur-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000044/2023-2024 | 409/AE-I/NACD-II | 08/08/2023 | 15 | BASUDEB SAHA | 0.97 | 0 | 0
4525 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Jayrampur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000133/2023-2024 | 1251/NACD-II | 08/11/2023 | 45 | BASUDEB SAHA | 11.38 | 0 | 100
4526 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Karimpur-I Block of Nadia District through Jadavpur University. (Name of PWSS Jayrampur) | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000163/2023-2024 | 1289/NACD-II | 21/11/2023 | 21 | JADAVPUR UNIVERSITY | 4.78 | 0 | 100
4527 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Jayrampur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000280/2022-2023 | 1135/NACD-II | 16/12/2022 | 30 | JOY HIND TUBEWELLS | 21.46 | 0 | 100
4528 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Conversion of IEP to AIRP at Joyghata Water Supply Scheme of capacity 64 Cu.m/hr under Krishnaganj Block & Jayrampur water Supply Scheme under Karimpur-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000283/2023-2024 | 140/NACD-II | 01/02/2024 | 600 | GHOSH ENTERPRISE | 202.08 | 0 | 0
4529 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Construction of 25 m3/hr capacity IEP at Jayrampur PWSS in Karimpur-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000331/2023-2024 | 313/NACD-II | 01/03/2024 | 61 | HYDROTECH ASSOCIATES | 18.68 | 0 | 0
4530 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Acceptance cum work order "Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Jayrampur water supply scheme under Karimpur-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia." | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000333/2023-2024 | 409/NACD-II | 13/03/2024 | 540 | JAYBRATO HALDER | 33.53 | 0 | 70
4531 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Incorporation of the system of adsorption by Inorganic sustances for multivalent metalloid expulsion for improving potability in coordination with IS 10500 With latest edition at Jayrampur Piped Water Supply Scheme in Karimpur-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000375/2024-2025 | 1650/NACD-II | 27/12/2024 | 30 | HYDROTECH ASSOCIATES | 20.92 | 0 | 0
4532 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 100 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Jayrampur PWSS of Karimpur-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000391/2022-2023 | 400/NACD-II | 28/03/2023 | 366 | M/S. R.M. CONSTRUCTION | 173.44 | 0 | 10
4533 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Sinking of Tube Well at H/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass Strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-II & Jayrampur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000408/2024-2025 | 149/NACD-II | 04/02/2025 | 45 | MANISHIKA CONSTRUCTION | 11.56 | 0 | 0
4534 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000022/2022-2023 | 1086/NACD-II | 09/12/2022 | 0 | Resource Division | 16.04 | 0 | 0
4535 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | RTOR000033/2022-2023 | 381/NACD-II | 24/03/2023 | 0 | Resource Division | 5.57 | 0 | 0
4536 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000196/2023-2024 | 3537/ND | 11/08/2023 | 1147 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 0 | 20
4537 | Nadia Division | Krishnanagar Sub-Division | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000236/2025-2026 | 3829/ND | 13/08/2025 | 120 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0
4538 | Nadia Division | Krishnanagar Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
4539 | Nadia Division | Krishnanagar Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 4/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. (Sl.No .09 ) | Assistant Engineer | Junior Engineer 3 | ORD/000718/2021-2022 | 211/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.04 | 3.99 | 100
4540 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 3 | RTOR000164/2022-2023 | 111/ND | 05/01/2023 | 0 | Resource Division | 216.05 | 0 | 0
4541 | Nadia Division | Krishnanagar Sub-Division | RESTORATION OF ROAD FROM SONDANGA INDRAPALLY TO BALAINAGAR under Package No. WB/14/ADB/36 | Assistant Engineer | Junior Engineer 4 | BILL/00530/2024-2025 | 319/PFMS | 05/10/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 2.02 | 0 | 0
4542 | Nadia Division | Krishnanagar Sub-Division | Restoration work of Core Side in Stretches of Road Damaged due to laying of pipe line under JJM project for Dhubulia Belpukur Road from 0.0 Km to 5.30 Km under Nadia Highway Division-I, P.W.D (Roads) Directorate. | Assistant Engineer | Junior Engineer 4 | BILL/00654/2024-2025 | 362/PFMS | 19/12/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 9.39 | 0 | 0
4543 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000196/2023-2024 | 3537/ND | 11/08/2023 | 1147 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 0 | 20
4544 | Nadia Division | Krishnanagar Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
4545 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | Assistant Engineer | Junior Engineer 4 | ORD/000706/2024-2025 | 2666/KSD | 31/12/2024 | 365 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0
4546 | Nadia Division | Krishnanagar Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 1/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. (Sl.No .01 ) | Assistant Engineer | Junior Engineer 4 | ORD/000709/2021-2022 | 203/KSD | 04/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.92 | 4.91 | 100
4547 | Nadia Division | Krishnanagar Sub-Division | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | Assistant Engineer | Junior Engineer 4 | ORD/000758/2023-2024 | 1838/KSD | 28/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0
4548 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer 4 | RTOR000158/2022-2023 | 115/ND | 05/01/2023 | 0 | Resource Division | 299.06 | 0 | 0
4549 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials & valves, pipe supporting structure all complete based on actual., proposed augmentation of Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete. , Construction of R.C.C. Elevated Reservoir of 550 Cum capacity(including pile foundation) , Soil investigation for construction of one No. 550 Cum OHR, Construction of 1 No. Pump House at proposed Head Work site and Construction of boundary wall with gate for Tungi Water Supply Scheme in Krishnagunj Block of Nadia District under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000202/2023-2024 | 3520/ND | 10/08/2023 | 1240 | MANGES INDUSTRIAL CORPORATION | 494.78 | 0 | 25
4550 | Nadia Division | Krishnanagar Sub-Division | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Tungi W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 01) | Assistant Engineer | Junior Engineer | ORD/000340/2021-2022 | 904/KSD | 29/11/2021 | 15 | HORIZEN | 3.86 | 2.74 | 100
4551 | Nadia Division | Krishnanagar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
4552 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 120 cum/hr at Tungi water supply scheme including 3 Months Trial Run & 3 Years O&M within krishnaganj block under Krishnagar Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000722/2023-2024 | 1304/ND | 23/02/2024 | 540 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 300.57 | 0 | 50
4553 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000152/2023-2024 | 263/ND | 11/01/2024 | 0 | Resource Division | 35.85 | 0 | 0
4554 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000157/2022-2023 | 117/ND | 05/01/2023 | 0 | Resource Division | 28.88 | 0 | 0
4555 | Central Drilling | Krishnanagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Tungi W/S Scheme (TW-I) , Krishanjganj Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000131/2023-2024 | 1232/CDD | 04/09/2023 | 454 | PADMA ENGINEERING & CO. | 18.88 | 0 | 100
4556 | Eastern Mechanical | Krishnanagar Sub-Division | WBSEDCL Quotation for New Service Connection to the newly Head Work Site under TUNGI W/S Scheme in Krishnaganj Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3004956363) | Assistant Engineer | Junior Engineer | BILL/01890/2024-2025 | BP-167-24-25 | 25/11/2024 | 0 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 4.96 | 0 | 0
4557 | Eastern Mechanical | Krishnanagar Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Tungi ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte. SM/12363 | Assistant Engineer | Junior Engineer | ORD/000367/2025-2026 | 1124/EMD | 04/06/2025 | 90 | SHREE BISHNU CONSTRUCTION | 31.04 | 0 | 0
4558 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works etc. rejuvenation to Accomodate FHTC at Pump House No.I and II under Tungi WS Scheme, Block Krishnaganj, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-11) | Assistant Engineer | Junior Engineer | ORD/000892/2022-2023 | 160/EMD | 06/01/2023 | 30 | KUNDU ELECTRICAL ENTERPRISE | 21.11 | 19.47 | 10
4559 | Eastern Mechanical | Krishnanagar Sub-Division | Supplementary works to completion of ongoing FHTC-related work at PH-I & II of Tungi W/S Scheme (Block - Krishnaganj), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/001391/2023-2024 | 599/EMSD-II | 22/08/2023 | 15 | KUNDU ELECTRICAL ENTERPRISE | 0.87 | 0.82 | 100
4560 | Nadia Division | Debgram Sub-Division | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 1100 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 0 | 47
4561 | Nadia Division | Debgram Sub-Division | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000185/2024-2025 | 6095/ND | 19/09/2024 | 240 | UMWELT ENGINEER PVT LTD | 225.66 | 0 | 75
4562 | Nadia Division | Debgram Sub-Division | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 5B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000775/2021-2022 | 125/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.94 | 3.94 | 100
4563 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000121/2022-2023 | 75/ND | 05/01/2023 | 0 | Resource Division | 293.45 | 0 | 0
4564 | Nadia Division | Debgram Sub-Division | Additional work for Providing FHTC, Supplying, laying of distribution system including with all necessary specials, UPVC/HDPE Pipes etc. all complete for Zone- II/B (Northern Sector Part-II) under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000106/2025-2026 | 2852/ND | 18/06/2025 | 75 | SATYABRATA CHAKRABORTY | 68.32 | 0 | 0
4565 | Nadia Division | Debgram Sub-Division | Preparation of DPR for Augmentation for Intake, WTP & Rising Main of Surface Water Based Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte.(including Survey, Design and Estimate). | Assistant Engineer |  | ORD/000195/2022-2023 | 4546/ND | 21/10/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 17.77 | 17.77 | 0
4566 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- II/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000357/2023-2024 | 4651/ND | 10/10/2023 | 720 | SATYABRATA CHAKRABORTY | 484.95 | 0 | 15
4567 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
4568 | Nadia Division | Debgram Sub-Division | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-II / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11838]. | Assistant Engineer |  | ORD/000478/2023-2024 | 210/ND | 10/01/2024 | 365 | SARKAR CONSTRUCTION | 271.6 | 0 | 5
4569 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 2/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000789/2021-2022 | 139/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.72 | 3.71 | 100
4570 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000133/2022-2023 | 94/ND | 05/01/2023 | 0 | Resource Division | 264.51 | 0 | 0
4571 | Nadia Division | Debgram Sub-Division | Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Jone-XB to accommodate FHTC Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000342/2022-2023 | 242/ND | 13/01/2023 | 818 | CHOWDHURY & CO. | 79.52 | 18.43 | 90
4572 | Nadia Division | Debgram Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-X B to accommodate FHTC within Karimpur-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000723/2024-2025 | 206/ND | 13/01/2025 | 180 | TRANS ORGANICS INDIA PVT LTD | 161.36 | 0 | 0
4573 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000072/2023-2024 | 2294/ND | 29/05/2023 | 0 | Resource Division | 0.92 | 0 | 0
4574 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000173/2022-2023 | 144/ND | 06/01/2023 | 0 | Resource Division | 5.67 | 0 | 0
4575 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Gravity Type) of capacity 67 Cu.m/hr at Head Work Site at Kulgachi PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000005/2023-2024 | 1599/ND | 10/04/2023 | 721 | B.M. ENGINEERING & CONSTRUCTION | 72.07 | 0 | 100
4576 | Nadia Division | Krishnanagar Sub-Division | Providing FHTC at leftout household in connection to the Augmentation of Ground Based piped water supply scheme at Kulgachi to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000057/2024-2025 | 3897/ND | 16/07/2024 | 60 | MANAJIT BISWAS | 25.71 | 0 | 0
4577 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Kulgachi to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000072/2022-2023 | 3153/ND | 15/07/2022 | 90 | M/S DIPAK ENTERPRISE | 250 | 246.78 | 86
4578 | Nadia Division | Krishnanagar Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
4579 | Nadia Division | Krishnanagar Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 350 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Kulgachi Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000395/2023-2024 | 5124/ND | 17/11/2023 | 90 | BUDDHADEV MONDAL | 27.76 | 0 | 100
4580 | Nadia Division | Krishnanagar Sub-Division | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Maidanpur ii) Kulgachhi iii) Monipota iv) Habibpur v) Magurkhali. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000480/2022-2023 | 372/ Kly SD-I | 17/03/2023 | 184 | HORIZEN | 4.99 | 0 | 10
4581 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000005/2022-2023 | 2162/ND | 18/05/2022 | 0 | Resource Division | 24.2 | 0 | 0
4582 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000011/2022-2023 | 3303/ND | 27/07/2022 | 0 | Resource Division | 4.82 | 0 | 0
4583 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000100/2021-2022 | 1018/ND | 03/03/2022 | 0 | Resource Division | 4.31 | 0 | 0
4584 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000182/2022-2023 | 146/ND | 06/01/2023 | 0 | Resource Division | 0.76 | 0 | 0
4585 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KULGACHHI in KRISHNAGAR-I Block with in Nadia district under Nadia Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/001076/2021-2022 | 639/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.54 | 0 | 0
4586 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I and II under Kulgachi WS Scheme, Block KrishnagarI, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-09) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/002969/2022-2023 | 158EMD,Dt.06.01.23 | 27/03/2023 | 30 | ABHISEK ENGINEERING CONCERN | 15.5 | 0 | 100
4587 | Nadia Division | Krishnanagar Sub-Division | Sinking of 2 nos. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method at headwork and 2nd tube well site for Sandha (SAF) water supply scheme under Krishnagar Sub-division under Nadia Division, PHE Dte. (SM/15520) | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000035/2023-2024 | 2103/ND | 15/05/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 32.45 | 26.36 | 100
4588 | Nadia Division | Krishnanagar Sub-Division | Survey , Design and preperation of DPR in connection with Sandha piped water supply scheme in Krishnanagar I Block under Krishnanagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000055/2023-2024 | 680/KSD | 26/05/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.51 | 2.45 | 100
4589 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials & valves, Laying of proposed Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, repair and renovation works of R.C.C. Elevaced Reservoir of 90 and 270 Cum capacity, repair and renovation works of Pump Houses and other allied works at Sandha (State Arm Force) within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000089/2023-2024 | 3025/ND | 14/07/2023 | 366 | CHANDAN ROY, 35, M. M. GHOSH STREET, P.O. -KRISHNAGAR, DIST. NADIA, PIN -741101. | 247.85 | 53.53 | 55
4590 | Nadia Division | Krishnanagar Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
4591 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 50 m3/hr at Sandha SAP Water Supply Scheme within Krishnagar-I Block under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000789/2023-2024 | 1900/ND | 15/03/2024 | 360 | JOY HIND TUBEWELL'S | 184.49 | 0 | 0
4592 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000159/2023-2024 | 274/ND | 11/01/2024 | 0 | Resource Division | 12.03 | 0 | 0
4593 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 4 | RTOR000167/2022-2023 | 89/ND | 05/01/2023 | 0 | Resource Division | 14.87 | 0 | 0
4594 | Eastern Mechanical | Krishnanagar Sub-Division | New Service Connection charge for PH.No. 1 under Sandhya, 9th Battalian | Assistant Engineer | Junior Engineer,Junior Engineer 4 | BILL/04194/2023-2024 | BP-268-23-24 | 09/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.36 | 0 | 0
4595 | Eastern Mechanical | Krishnanagar Sub-Division | New Service Connection charge for PH.No. 2 under Sandhya, 9th Battalian | Assistant Engineer | Junior Engineer,Junior Engineer 4 | BILL/04195/2023-2024 | BP-267-23-24 | 09/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.07 | 0 | 0
4596 | Eastern Mechanical | Krishnanagar Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under SANDHA ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/001986/2023-2024 | 6967/EMD | 15/12/2023 | 564 | CINZANO | 27.44 | 0 | 90
4597 | Nadia Division | Ranaghat Sub-Division | Providing leave out functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Fulia Township Zone-I to accommodate FHTC in Santipur block and allied works of Badkulla Zone II of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000018/2025-2026 | 1804/ND | 22/04/2025 | 180 | APURBA MANDAL | 64.83 | 0 | 90
4598 | Nadia Division | Ranaghat Sub-Division | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete Construction Of 700 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection And Cost Of Pipes, Specials & Soil Investigation For Construction Of One No. 700 Cum OHR Of Staging Height 20 Mtr. for augmentation of Ground Water Based Water Supply Scheme For Fulia Township Zone-I to accommodate FHTC in Santipur block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000195/2023-2024 | 3450/ND | 09/08/2023 | 731 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 746.37 | 86.77 | 85
4599 | Nadia Division | Ranaghat Sub-Division | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-2 site at Fulia Zone-I Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000219/2024-2025 | 1184/RSD | 25/09/2024 | 75 | ASHIM ENTERPRISE | 4.46 | 0 | 100
4600 | Nadia Division | Ranaghat Sub-Division | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 60 | IMAGIN | 96.97 | 0 | 0
4601 | Nadia Division | Ranaghat Sub-Division | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Fulia Zone-I Water Supply Scheme Under Ranaghat Sub-Division PHE Dte.) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000363/2023-2024 | 4698/ND | 11/10/2023 | 90 | M/S BISWAS ENTERPRISE | 6.88 | 0 | 100
4602 | Nadia Division | Ranaghat Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
4603 | Nadia Division | Ranaghat Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 135 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Fulia Township Zone-I to accommodate FHTC within Santipur block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000707/2024-2025 | 137/ND | 08/01/2025 | 180 | MONDAL ENTERPRISE | 245 | 0 | 0
4604 | Nadia Division | Ranaghat Sub-Division | Construction of 56.00 mtr long Boundary Wall (2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-I Pump House-III under Ranaghat Sub-Division, Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000796/2024-2025 | 87/RSD | 14/01/2025 | 75 | ROMI TRADERS | 4.77 | 0 | 0
4605 | Nadia Division | Ranaghat Sub-Division | Construction of 44 mtr long Boundary Wall(2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-I Pump House-II under Ranaghat Sub-Div, Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000915/2024-2025 | 86/RSD | 14/01/2025 | 75 | BRICK FARM | 4.05 | 0 | 0
4606 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000013/2024-2025 | 7561/ND | 27/12/2024 | 0 | Resource Division | 23.37 | 0 | 0
4607 | Nadia Division | Ranaghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000036/2023-2024 | 1883/ND | 26/04/2023 | 0 | Resource Division | 33.17 | 0 | 0
4608 | Central Drilling | Ranaghat Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 250 Mtrs. Depth) by utilising departmental machineries for Fulia Township W/S Scheme (Z-I, T/W I & II). Santipur Block under Nadia District, Central Drilling Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000035/2023-2024 | 515/CDD | 01/06/2023 | 455 | UNIVERSAL ENTERPRISES | 37.73 | 0 | 100
4609 | Central Drilling | Ranaghat Sub-Division | sinking of 80mm dia. Shallow tubewell for requirement of drilling water for Fulia Township (Z-I) PWSS, District Nadia and other PWSS under CMSD-II (D), CDD, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000073/2023-2024 | 103/CMSD-II(D) | 20/04/2023 | 15 | UNIVERSAL ENTERPRISES | 0.88 | 0 | 0
4610 | Central Drilling | Ranaghat Sub-Division | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Fulia Township W/S Scheme (Z- I, T/W-III),Santipur Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000096/2023-2024 | 516/CDD | 01/06/2023 | 611 | M/S S.K.GHOSH & CO. | 18.88 | 0 | 0
4611 | Eastern Mechanical | Ranaghat Sub-Division | New Power Connection charges for FULIA Water Supply Scheme Z -I , Pump House No- II | Assistant Engineer | Junior Engineer,Junior Engineer 2 | BILL/02297/2024-2025 | BP-185 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 5.36 | 0 | 0
4612 | Eastern Mechanical | Ranaghat Sub-Division | New Power Connection Charges for FULIA Water Supply Scheme Z - I , HEAD WORK SITE (PH-I) | Assistant Engineer | Junior Engineer,Junior Engineer 2 | BILL/02298/2024-2025 | BP-186 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 14.29 | 0 | 0
4613 | Eastern Mechanical | Ranaghat Sub-Division | New Power Connection Charges for FULIA Water Supply Scheme Z- I , Pump House No- III | Assistant Engineer | Junior Engineer,Junior Engineer 2 | BILL/02299/2024-2025 | BP-187 | 13/12/2024 | 0 | W.B.S.E.D.C.L (FULIA C.C.C) | 5.21 | 0 | 0
4614 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, II and III , Zone-I under Fulia Town Ship (Zone-I) ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. [SM-15522] | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000340/2024-2025 | 2155/EMD | 30/08/2024 | 377 | KARTICK BAL | 42.39 | 0 | 70
4615 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (78cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Saguna, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.11) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000140/2023-2024 | 1903/NAD-I | 14/08/2023 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 141.34 | 0 | 100
4616 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Saguna under Block_ Santipur Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/15542) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000161/2025-2026 | 1159/EMD | 04/06/2025 | 90 | DEEP ENTERPRISE | 4.32 | 0 | 0
4617 | Nadia Arsenic Division I | Nadia Arsenic Division I | Dedicated pipeline towards Durgapur Mouza and adjacent areas including allied works for Birnagar PWSS at Ranaghat-I Block of Ground Water Based PWSS for Birnagar W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.No. 01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000135/2024-2025 | 1966/NAD-I | 28/11/2024 | 60 | M/S DIPAK ENTERPRISE | 82.96 | 0 | 100
4618 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for at Madanpur-I & II G.P. and different augmentation works of Radhakantapur and Birnagar Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I block by augmentation of Ground Water Based PWSS for Radhakantapur and Birnagar under Nadia Arsenic Division-I, PHE Dte. (Sl.no.11) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000162/2023-2024 | 2120/NAD-I | 04/09/2023 | 714 | CHOWDHURY & CO. | 96.13 | 0 | 70
4619 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work of 2 no Gobindanagar near Indira More & Birnagar at Ranaghat-I Block under augmentation of Ground Water Based PWSS of Birnagar Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.16) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000165/2023-2024 | 2123/NAD-I | 04/09/2023 | 21 | CHOWDHURY & CO. | 75.32 | 75.22 | 100
4620 | Nadia Arsenic Division I | Nadia Arsenic Division I | Preparation of Detailed Project Report (DPR) for Birnagar (Part) Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000167/2022-2023 | 3287 / NAD-I | 08/12/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 3.74 | 3.65 | 100
4621 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | RTOR000002/2024-2025 | 846/NAD-I | 04/06/2024 | 0 | Resource Division | 1.52 | 0 | 0
4622 | Eastern Mechanical | Nadia Arsenic Division I | Providing Boundary Illumination with allied works at Birnagar (Part) under Block_ Ranaghat-I Under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/14196) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000163/2025-2026 | 1161/EMD | 04/06/2025 | 90 | WESTERN ENGINEERING CO. | 4.31 | 0 | 0
4623 | Nadia Division | Krishnanagar Sub-Division | Construction of Pump House (3.6mtr. X 3.0 mtr.) and Boundary Wall at 3rd T/W site for Krishnaganj Majhdia water supply scheme under Krishnagar Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000008/2024-2025 | 3262/ND | 10/06/2024 | 45 | D.K. CONSTRUCTION | 17.11 | 0 | 80
4624 | Nadia Division | Krishnanagar Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 450 cum, Repair & Renovation of Pump House, Store, Guard Room, Boundary wall and allied works at 1st and 2nd Pump House at Krishnaganj Majhdia Water Supply Scheme within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000391/2023-2024 | 5123/ND | 17/11/2023 | 90 | CHOWDHURY & CO. | 34.94 | 0 | 98
4625 | Nadia Division | Krishnanagar Sub-Division | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period of 90 days w.e.f 01/07/2023 (as and when required). | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000410/2023-2024 | 800/KSD | 16/06/2023 | 92 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0
4626 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Krishnaganj Majdia to accommodate FHTC within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000703/2021-2022 | 966/ND | 28/02/2022 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 495.71 | 302.62 | 82
4627 | Nadia Division | Krishnanagar Sub-Division | Construction and installation of Manifold and allied works at OHR site in connection to Retrofitting (Phase-I) Under JJM In Ground Based Piped Water Supply Scheme at Krishnaganj Majhdia To Accommodate FHTC Within Krishnaganj Block Under Krishnanagar Sub-division Under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000749/2024-2025 | 496/ND | 30/01/2025 | 300 | CHOWDHURY & CO. | 39.44 | 0 | 0
4628 | Nadia Division | Krishnanagar Sub-Division | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 103 m3/hr at Krishnaganj Majhdia Water Supply Scheme within Krishnaganj Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000776/2023-2024 | 1892/ND | 15/03/2024 | 180 | B.M. ENGINEERING & CONSTRUCTION | 266.82 | 0 | 0
4629 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000031/2021-2022 | 450/ND | 31/01/2022 | 0 | Resource Division | 3.58 | 0 | 0
4630 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000112/2021-2022 | 1023/ND | 03/03/2022 | 0 | Resource Division | 11.25 | 0 | 0
4631 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000129/2021-2022 | 1257/ND | 16/03/2022 | 0 | Resource Division | 16.73 | 0 | 0
4632 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/000451/2022-2023 | 67/PFMS | 28/06/2022 | 0 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 87.34 | 0 | 0
4633 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | VCH/001070/2021-2022 | 633/PFMS | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.99 | 0 | 0
4634 | Central Drilling | Krishnanagar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Krishnaganj Majdia W/S Scheme (TW-I) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000122/2023-2024 | 1659/CDD | 17/10/2023 | 180 | MENAKA ENTERPRISE | 18.88 | 0 | 100
4635 | Eastern Mechanical | Krishnanagar Sub-Division | WBSEDCL Quotation for New Service Connection to the newly constructed Pump House No. - III under KRISHNAGANJ MAJDIA W/S Scheme in Krishnaganj Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3004847470) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | BILL/01476/2024-2025 | BP-88-24-25 | 28/08/2024 | 0 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 0.56 | 0 | 0
4636 | Eastern Mechanical | Krishnanagar Sub-Division | WBSEDCL SUPPLEMENTARY Quotation for New Service Connection to the newly constructed Pump House No. - III under KRISHNAGANJ MAJDIA W/S Scheme in Krishnaganj Block, P.H.E. Dte., Dist.- Nadia. (Application ID. 100000120534) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | BILL/01891/2024-2025 | BP-164-24-25 | 25/11/2024 | 0 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 3.49 | 0 | 0
4637 | Eastern Mechanical | Krishnanagar Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Krishnaganj Majhdia ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte. SM/09799 | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000175/2025-2026 | 1108/EMD | 04/06/2025 | 90 | S.P. ENTERPRISE (KOLKATA) | 20.79 | 0 | 0
4638 | Eastern Mechanical | Krishnanagar Sub-Division | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works etc. rejuvenation to Accomodate FHTC at Pump House No.I & II under Krishnaganj Majdia W/S Scheme, Block- Krishnaganj, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 07) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000194/2022-2023 | 6188/EMD | 14/11/2022 | 30 | S.G. TECHNICAL SERVICES | 12 | 0 | 0
4639 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Work for revamping / upgradation of the hydraulic parameters at Kamdanga and Nasra Mouza in reference to Nasra and Aranghata water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000028/2025-2026 | 158/NAD-I | 28/04/2025 | 60 | SAFTI PRIVATE LIMITED | 77.16 | 0 | 0
4640 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Work revamping / upgradation of the hydraulic parameters at distribution network at the part of Malsadaha, Ulasi, Silberia, Nasra (P) and Hijuli (P) Mouzas in reference to Hijuli and Nasra PWSS under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. NO. 02) | Assistant Engineer | Junior Engineer | ORD/000060/2025-2026 | 359/NAD-I | 09/06/2025 | 90 | M/S DIPAK ENTERPRISE | 246.94 | 0 | 0
4641 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Preparation of Detailed Project Report (DPR) for Nasra Water Supply Scheme at Ranaghat-II Block atNadia District under Nadia Arsenic Division-I,P.H.E. Dte. (sl.04) | Assistant Engineer | Junior Engineer | ORD/000182/2022-2023 | 38/ NAD-I | 16/01/2023 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 6.74 | 6.67 | 100
4642 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Rising Main System including specials & valves. & LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE SUPPORTING STRUCTURE, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials at Ground Water Based Piped Water Supply Scheme for Nasra (Zone-I), Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials at Ground Water Based Piped Water Supply Scheme for Nasra (Zone-II), CONSTRUCTION OF BOUNDARY WALL [ H/W Site(160.0 m length),2nd T/W Site(45.0 m length),3rd T/W(45.0 m length),4th T/W(45.0 m length)],Pump House for H/W Site(4.88 M X 3.60 M),2nd T/W Site(3.60 M X 3.0 M) ,Land Development,Restoration of Bituminous Road and aliied works with Approach Road (195.0m Length and 3.0m Wide), Soil investigation for the work of construction of R.C.C. Elevated Reserviour of Capacity 300 m3 of Height 20 Mtr. for Nasra (Zone-I), Soil investigation for the work of construction of R.C.C. Elevated Reserviour of Capacity 200 m3 of Height 20 Mtr. for Nasra (Zone-II) and RESTORATION WORK FOR BITUMINOUS ROAD at Ground Water Based Piped Water Supply Scheme for Nasra (Zone-I&II) in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000239/2023-2024 | 2381/NAD-I | 06/10/2023 | 1095 | BIDYUT KUMAR | 804.39 | 0 | 70
4643 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000022/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 19.27 | 0 | 0
4644 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000033/2023-2024 | 294/NAD-I | 28/02/2024 | 0 | Resource Division | 16.87 | 0 | 0
4645 | Eastern Mechanical | Eastern Mechanical Sub Division-II | Providing Boundary Illumination with allied works at Nasra under Block_ Ranaghat-II under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia (SM/14244) | Assistant Engineer | Junior Engineer | ORD/000158/2025-2026 | 1157/EMD | 04/06/2025 | 90 | S M ELECTRICALS | 4.34 | 0 | 0
4646 | Nadia Division | Ranaghat Sub-Division | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000252/2024-2025 | 6290/ND | 26/09/2024 | 45 | IMAGIN | 19.44 | 0 | 100
4647 | Nadia Division | Ranaghat Sub-Division | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.08.2025 to 31.01.2026 | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000332/2025-2026 | 1488/KlySD-I | 30/07/2025 | 184 | SUMAN CHAKRABORTY | 4.89 | 0 | 0
4648 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000527/2022-2023 | 1270/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 65.32 | 0 | 0
4649 | Nadia Division | Ranaghat Sub-Division | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.04.2025 to 31.07.2025 | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000909/2024-2025 | 584/KlySD-I | 28/03/2025 | 122 | SUMAN CHAKRABORTY | 4.89 | 0 | 100
4650 | Eastern Mechanical | Ranaghat Sub-Division | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Pairadanga ground water based water supply scheme under Block_ Hanskali_I Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15277) | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/001466/2024-2025 | 237/EMD | 06/02/2025 | 30 | ABHISEK ENGINEERING CONCERN | 23.53 | 0 | 0
4651 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 4 | ORD/000527/2022-2023 | 1270/ND | 23/03/2023 | 60 | AUXILIARY TUBEWELL DRILLERS | 65.32 | 0 | 0
4652 | Nadia Division | RWS Nadia Sub-Division | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Teinpur zone - III W/S scheme under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000196/2021-2022 | 5142/ND | 15/09/2021 | 90 | BIDYUT KUMAR | 85.7 | 69.53 | 100
4653 | Nadia Division | RWS Nadia Sub-Division | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 11-11-2022 to 31-01-2023= 80 days. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000469/2022-2023 | 678/RSD | 04/11/2022 | 80 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 1.19 | 0 | 75
4654 | Nadia Division | RWS Nadia Sub-Division | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-02-2023 to 31-07-2023= 183 days. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000512/2022-2023 | 92/RSD | 01/02/2023 | 183 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 3.2 | 0 | 25
4655 | Nadia Division | RWS Nadia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer Karimpur- II Block | RTOR000071/2021-2022 | 804/ND | 18/02/2022 | 0 | Resource Division | 8.78 | 0 | 0
4656 | Nadia Division | RWS Nadia Sub-Division | Providing Functional House Tap Connection from Teinpur Zone-III Water Supply Scheme (Phase-I) of Retrofitting under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | VCH/001014/2021-2022 | 606/PFMS | 11/03/2022 | 0 | OTHERS | 8.14 | 0 | 0
4657 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-V,(Purba Bishnupur) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000121/2021-2022 | 14/NAD-I | 05/01/2022 | 90 | M/S TARAK CHANDRA PAUL | 277.36 | 277.33 | 100
4658 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Purba Bishnupur Zone V of Surface Water based PWSS for Chakdah Part water supply scheme under NAD - I PHE Dte (SL.06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000256/2022-2023 | 1473 / NAD-I | 22/08/2022 | 60 | APURBA MANDAL | 32.4 | 27.39 | 100
4659 | Nadia Division | Ranaghat Sub-Division | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Santipur & Krishnaganj Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 3 | ORD/000530/2022-2023 | 1273/ND | 23/03/2023 | 60 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 26.02 | 95
4660 | Nadia Division | Debgram Sub-Division | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-135 | Assistant Engineer |  | BILL/00514/2024-2025 | 308/PFMS | 02/10/2024 | 0 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 12.52 | 0 | 0
4661 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
4662 | Nadia Division | Debgram Sub-Division | Augmentation of Water Treatment Plant (augmented to 34.52 MLD), repairing & renovation of Rising Main from WTP to different ESR and zonal OHR and soil test, design & construction of Boosting Station along with allied civil work including 6 (six) months trial run for Surface Water Based Piped Water Supply Scheme for Northern Sector, Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000366/2023-2024 | 4773/ND | 16/10/2023 | 913 | GB CONSTRUCTION | 6109.51 | 0 | 9
4663 | Nadia Division | Debgram Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
4664 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000189/2022-2023 | 147/ND | 06/01/2023 | 0 | Resource Division | 1858.7 | 0 | 0
4665 | Eastern Mechanical | Debgram Sub-Division | Quotation for earnest money deposit for Bulk power supply at Nakashipara GLR project. | Assistant Engineer |  | BILL/00384/2024-2025 | BP-23-24-25 | 21/05/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 0.05 | 0 | 0
4666 | Eastern Mechanical | Debgram Sub-Division | Quotation for New HT Bulk connection at Nakashipara GLR Project under Easter Mechanical Division, Dist-Nadia | Assistant Engineer |  | BILL/01150/2024-2025 | BP-69-24-25 | 26/07/2024 | 0 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 39.38 | 0 | 0
4667 | Eastern Mechanical | Debgram Sub-Division | Quotation for New power connection at Gachha OHR ( Zone-IX/B) under Northern Sector, Part-II SWB Project. | Assistant Engineer |  | BILL/01326/2024-2025 | BP-76-24-25 | 30/07/2024 | 0 | MURAGACHA DHARMADA CCC | 0.3 | 0 | 0
4668 | Eastern Mechanical | Debgram Sub-Division | Quotation for New power connection at Gopalpur OHR ( Zone-II/B) under Northern Sector, Part-II SWB Project. | Assistant Engineer |  | BILL/01327/2024-2025 | BP-75-24-25 | 30/07/2024 | 0 | MURAGACHA DHARMADA CCC | 0.3 | 0 | 0
4669 | Eastern Mechanical | Debgram Sub-Division | Quotation for New power connection at Digha OHR ( Zone-VIII/C) under Northern Sector, Part-II SWB Project. | Assistant Engineer |  | BILL/01329/2024-2025 | BP-77-24-25 | 30/07/2024 | 0 | MURAGACHA DHARMADA CCC | 0.3 | 0 | 0
4670 | Eastern Mechanical | Debgram Sub-Division | Quotation for New power connection at Teghari OHR ( Zone-VIII/B) under Northern Sector Part-II SWB Project. | Assistant Engineer |  | BILL/01330/2024-2025 | BP-74-24-25 | 30/07/2024 | 0 | MURAGACHA DHARMADA CCC | 0.3 | 0 | 0
4671 | Eastern Mechanical | Debgram Sub-Division | Quotation for new service connection and security deposit at Kalibus OHR (Zone-VII/B) under Northern Sector, Part-II SWB Project,PHE Dte. | Assistant Engineer |  | BILL/01577/2024-2025 | BP-108-24-25 | 09/09/2024 | 0 | WBSEDCL BETHUADAHARI CCC | 3.95 | 0 | 0
4672 | Eastern Mechanical | Debgram Sub-Division | Quotation for service connection charge and security deposit for new power connection at Majhergram OHR Site under Northern Sector, Part-II SWB Project , PHE Dte. | Assistant Engineer |  | BILL/01578/2024-2025 | BP-109-24-25 | 09/09/2024 | 0 | WBSEDCL BETHUADAHARI (NORTH) CCC | 3.86 | 0 | 0
4673 | Eastern Mechanical | Debgram Sub-Division | Quotation for service connection charge and security deposit for new power connection at Sonadanga OHR Site under Northern Sector, Part-II SWB Project , PHE Dte. | Assistant Engineer |  | BILL/01579/2024-2025 | BP-110-24-25 | 09/09/2024 | 0 | WBSEDCL BETHUADAHARI (NORTH) CCC | 3.74 | 0 | 0
4674 | Eastern Mechanical | Debgram Sub-Division | Quotation for service connection charge and security deposit for new power connection at Bilkumarik OHR(Zone-VI/B) Site under Northern Sector, Part-II SWB Project , PHE Dte. | Assistant Engineer |  | BILL/01580/2024-2025 | BP-111-24-25 | 09/09/2024 | 0 | WBSEDCL DEBOGRAM CCC | 2.64 | 0 | 0
4675 | Eastern Mechanical | Debgram Sub-Division | Augmentation of pumping machinery and electrical equipments at WTP along with implementation of SCADA System for surface water based water supply scheme, Arsenic affected area, Northern Sector, Part-II (Block - Nakasipara) in the district of Nadia, P. H. E. Dte. | Assistant Engineer |  | ORD/001687/2023-2024 | 6261/EMD | 10/10/2023 | 630 | MACHINE SUPLIERS SYNDICATE (P) LTD. | 234.62 | 0 | 40
4676 | Eastern Mechanical | Debgram Sub-Division | Providing Axially Split Centrifugal Pumping machinery for GLR along with secondary disinfection arrangement for surface water based water supply scheme, Arsenic Affected Area, Northern Sector, Part-II (Block - Nakasipara) in the district of Nadia, P. H. E. Dte. | Assistant Engineer |  | ORD/001690/2023-2024 | 6264/EMD | 10/10/2023 | 752 | WEST BENGAL ENGINEERING CO. | 276.03 | 0 | 60
4677 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Bamboo Pilling at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000032/2021-2022 | 525/NACD-II | 14/06/2021 | 45 | NILAY KUMAR BHATTACHARYA | 68.03 | 0 | 100
4678 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000122/2024-2025 | 820/AE-I/NACD-II | 25/07/2024 | 7 | BABA LOKNATH ENTERPRISE | 0.16 | 0 | 100
4679 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Mahatpur, (Block -Chapra) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000147/2021-2022 | 146/AE-I/NACD-II | 16/11/2021 | 10 | UMWELT ENGINEER PVT LTD. | 3.79 | 3.79 | 100
4680 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Preparation of DPR for augmentation of existing Mahatpur (Phase-II), (Block -Chapra) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000173/2021-2022 | 756/NACD-II | 16/09/2021 | 10 | SIRCON ENGINEERING SERVICE | 4.84 | 4.84 | 100
4681 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also construction of steps with earth filling at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000189/2021-2022 | 981/NACD-II | 27/12/2021 | 90 | SINGHA ROY & CO. | 145.05 | 144.95 | 100
4682 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Electrical and Civil works and other allied works under retrofitting of Mahatpur PWSS under Chapra Block | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000198/2021-2022 | 186/AE-I/NACD-II | 29/12/2021 | 20 | CHINMOY BISWAS | 4.96 | 4.96 | 100
4683 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Installation of Electrical appliances and other allied works under retrofitting of Mahatpur PWSS under Chapra Block. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000204/2021-2022 | 192/AE-I/NACD-II | 29/12/2021 | 20 | CHINMOY BISWAS | 4.84 | 4.84 | 100
4684 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair ) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000207/2021-2022 | 992/NACD-II | 30/12/2021 | 45 | SANDIP BISWAS | 97.95 | 97.86 | 100
4685 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Mahatpur (Vill- Jamnidanga) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000227/2020-2021 | 289/NACD-II | 23/02/2021 | 21 | JOY HIND TUBEWELLS | 41.12 | 0 | 100
4686 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Relaying of Rising Main by D.I. pipeline replacing the damaged old UPVC Pipe at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division -II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000240/2021-2022 | 97/NACD-II | 10/02/2022 | 45 | M/S RAJESH CONSTRUCTION | 13.55 | 13.55 | 100
4687 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Construction of Boundary wall with Grill Gate at Mahatpur Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000250/2021-2022 | 108/NACD-II | 10/02/2022 | 45 | PARTHA DAS | 8.55 | 0 | 100
4688 | Nadia Arsenic Civil Division II | Nadia Arsenic Civil Division II | Material Requisition To Resource Division | Assistant Engineer -I (HQ), Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | RTOR000005/2021-2022 | 990/NACD-II | 28/12/2021 | 0 | Resource Division | 93.39 | 0 | 0
4689 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution system for providing FHTC at Dafarpota (Zone-II) Water Supply Scheme in Nadia District under Krishnagar Sub-Division ,P.H.E.Dte. | Assistant Engineer |  | ORD/000297/2022-2023 | 5336/ND | 21/12/2022 | 30 | PURNIMA ELECTRICS & DECORATORS | 12.79 | 7.61 | 100
4690 | Nadia Division | Krishnanagar Sub-Division | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.10.2023 to 30.11.2023 | Assistant Engineer |  | ORD/000414/2023-2024 | 1034/KLYSD-I | 29/09/2023 | 30 | SUMAN CHAKRABORTY | 4.89 | 0 | 100
4691 | Nadia Division | Krishnanagar Sub-Division | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.12.2023 to 31.12.2023 | Assistant Engineer |  | ORD/000456/2023-2024 | 1260/KLYSD-I | 30/11/2023 | 31 | SUMAN CHAKRABORTY | 4.89 | 0 | 100
4692 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Dafarpota Zone-II to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000495/2021-2022 | 66/ND | 05/01/2022 | 75 | SUMAN CHAKRABORTY | 52.5 | 18.72 | 90
4693 | Nadia Division | Krishnanagar Sub-Division | Repair and renovation works of R.C.C. Elevaced Reservoir 50 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Dafarpota Zone II Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000506/2023-2024 | 6083/ND | 19/12/2023 | 90 | M/S CHANDIMATA CONSTRUCTION | 21.51 | 0 | 0
4694 | Nadia Division | Krishnanagar Sub-Division | Emergent Repairing work in connection with Augmentation of Ground Based piped water supply scheme at Bablari Dewanganj W/S scheme within Nabadwip block under Krishnaganj Sub-Division under Nadia Division. | Assistant Engineer |  | ORD/000533/2022-2023 | 220/KSD | 03/03/2023 | 15 | SAMAR ENTERPRISE | 0.3 | 0 | 100
4695 | Nadia Division | Krishnanagar Sub-Division | Continuation of Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-02-2024 to 31-07-2024= 182 days. | Assistant Engineer |  | ORD/000718/2023-2024 | 125/RSD | 29/01/2024 | 182 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 3.18 | 0 | 50
4696 | Nadia Division | Krishnanagar Sub-Division | Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000769/2023-2024 | 1821/ND | 14/03/2024 | 31 | IMAGIN | 34.21 | 0 | 60
4697 | Nadia Division | Krishnanagar Sub-Division | Conversion of IEP to AIRP of capacity 10 Cu.m/hr at Daforpota Zone-II Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000793/2023-2024 | 1905/ND | 15/03/2024 | 540 | SANDIP BISWAS | 63.46 | 0 | 70
4698 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000012/2021-2022 | 98/ND | 06/01/2022 | 0 | Resource Division | 5.53 | 0 | 0
4699 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000035/2022-2023 | 4284/ND | 29/09/2022 | 0 | Resource Division | 2.66 | 0 | 0
4700 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | Assistant Engineer |  | VCH/001130/2021-2022 | 713/PFMS | 30/03/2022 | 0 | SUMAN CHAKRABORTY | 27.16 | 0 | 0
4701 | Nadia Division | Krishnanagar Sub-Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | Assistant Engineer |  | VCH/001143/2021-2022 | 706/PFMS | 30/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.63 | 0 | 0
4702 | Nadia Division | Debgram Sub-Division | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 365 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 52
4703 | Nadia Division | Debgram Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 900 cum. for Surface Water Based Piped Water Supply Scheme for Zone- VIII/ A (NORTHERN SECTOR, PART-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000259/2023-2024 | 4006/ND | 07/09/2023 | 541 | SHYAMAL SHIL | 33.56 | 0 | 55
4704 | Nadia Division | Debgram Sub-Division | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer |  | ORD/000355/2023-2024 | 4588/ND | 06/10/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 0 | 19
4705 | Nadia Division | Debgram Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 60 | IMAGIN | 96.97 | 0 | 40
4706 | Nadia Division | Debgram Sub-Division | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 240 | BIBHAS PAL | 96.01 | 0 | 30
4707 | Nadia Division | Debgram Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZONE 8/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000804/2021-2022 | 154/DSD | 17/03/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.41 | 4.36 | 100
4708 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000002/2023-2024 | 1523/ND | 04/04/2023 | 0 | Resource Division | 77.13 | 0 | 0
4709 | Nadia Division | Debgram Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000131/2023-2024 | 243/ND | 11/01/2024 | 0 | Resource Division | 5.33 | 0 | 0
4710 | Nadia Division | Krishnanagar Sub-Division | Renovation of AIRP (Semi-Gravity Type) of capacity 34 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Sonda Zone-I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000082/2023-2024 | 2995/ND | 13/07/2023 | 628 | TARUN KUMAR BHATTACHARYA | 62.48 | 0 | 40
4711 | Nadia Division | Krishnanagar Sub-Division | Repair and renovation works of R.C.C. Elevated Reservoir 180 cum and allied works at 1st Pump House at Sonda Zone I Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000432/2023-2024 | 5591/ND | 14/12/2023 | 292 | DAS CONSTRUCTION | 14.12 | 0 | 100
4712 | Nadia Division | Krishnanagar Sub-Division | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Sonda-I to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000491/2021-2022 | 63/ND | 05/01/2022 | 60 | M/S A.K.CONSTRUCTION | 33.87 | 10.03 | 100
4713 | Nadia Division | Krishnanagar Sub-Division | Construction and installation of Manifold at OHR site and allied works in connection to the Augmentation of Sonda Zone II Water Supply Scheme under Krishnagar I Block under Nadia Division, P.H.E Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000748/2024-2025 | 495/ND | 30/01/2025 | 180 | N.H. ENTERPRISE | 32.38 | 0 | 0
4714 | Nadia Division | Krishnanagar Sub-Division | Conversion of IEP to AIRP of capacity 9 Cu.m/hr at Sonda Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | ORD/000792/2023-2024 | 1904/ND | 15/03/2024 | 60 | SUMIT GHOSH | 63.49 | 0 | 0
4715 | Nadia Division | Krishnanagar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 2 | RTOR000007/2021-2022 | 7450/ND | 27/12/2021 | 0 | Resource Division | 11.02 | 0 | 0
4716 | Nadia Division | Krishnanagar Sub-Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/000141/2022-2023 | 04/PFMS | 26/04/2022 | 0 | M/S A.K.CONSTRUCTION | 0.73 | 0 | 0
4717 | Nadia Division | Krishnanagar Sub-Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 2 | VCH/000146/2022-2023 | 01/PFMS | 26/04/2022 | 0 | M/S A.K.CONSTRUCTION | 11.48 | 0 | 0
4718 | Nadia Arsenic Division I |  | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Zone IX Ghetugachi Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte |  |  | ORD/000019/2021-2022 | 784/NAD-I | 05/05/2021 | 60 | GHOSH ENTERPRISE | 92.92 | 173.95 | 100
4719 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System and allied works for Dogachi Piped Water Supply Scheme Zone-I in connection with Augmentation of Ground Based Water Supply Scheme at Dogachi Zone-I to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000005/2025-2026 | 1663/ND | 08/04/2025 | 60 | MALI CONSTRUCTION | 26.66 | 0 | 0
4720 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 350 Cum Capacity 20 Mtr. Height RCC Over Head Reservoir (Excluding Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Dogachhi Zone-I to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000012/2023-2024 | 1719/ND | 17/04/2023 | 989 | JOY HIND TUBEWELL'S | 441.71 | 209.17 | 70
4721 | Nadia Division | Kalyani Sub-Division I | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement At H.W Site & another Pump House (3.6m X 3.0m) Including Sanitary Arrangemet At 2nd Tube well site at Dogachi zone II Water Supply Scheme Under Kalyani Sub Division I PHE Dte.) | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000028/2024-2025 | 3423/ND | 19/06/2024 | 90 | NIVEDITA CONSTRUCTION | 12.43 | 0 | 100
4722 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System at Dogachi Mouza for Dogachi Piped Water Supply Scheme Zone-II in connection with Augmentation of Ground Based Water Supply Scheme at Dogachi PWSS to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000067/2024-2025 | 3990/ND | 22/07/2024 | 60 | SUNIL KUMAR DATTA | 20.07 | 0 | 100
4723 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System for Dogachi Piped Water Supply Scheme Zone-I in connection with Augmentation of Ground Based Water Supply Scheme at Dogachi Zone-I to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000071/2024-2025 | 3991/ND | 22/07/2024 | 144 | MALI CONSTRUCTION | 40.01 | 0 | 70
4724 | Nadia Division | Kalyani Sub-Division I | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 77 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Dogachi Zone-I to accommodate FHTC under Nadia Division, PHE DTE. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000154/2024-2025 | 4349/ND | 07/08/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 218.56 | 0 | 70
4725 | Nadia Division | Kalyani Sub-Division I | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Headwork site, Dogachhi Zone-II PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000343/2024-2025 | 4574/ND | 21/08/2024 | 30 | ZEST INFRACON | 17.4 | 0 | 0
4726 | Nadia Division | Kalyani Sub-Division I | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at 2nd Tubewell site, Dogachhi Zone-II PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000344/2024-2025 | 4573/ND | 21/08/2024 | 30 | ZEST INFRACON | 17.4 | 0 | 0
4727 | Nadia Division | Kalyani Sub-Division I | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Dogachhi W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000397/2021-2022 | 312/TSD | 24/11/2021 | 30 | RADIANT | 3.4 | 3.4 | 100
4728 | Nadia Division | Kalyani Sub-Division I | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 300 Cum Capacity 20 Mtr. Height RCC Over Head Reservoir (Excluding Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Dogachhi Zone-II to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000539/2022-2023 | 1398/ND | 29/03/2023 | 1008 | SUBHASH BOSE | 312.69 | 0 | 20
4729 | Nadia Division | Kalyani Sub-Division I | Construction of barbed wire fencing with concrete pillars at Dogachhi-Zone-II. water supply scheme(Sahebpara) (New Land 2nd T.W) under Tehatta Sub-Division PHE Dte. in JJM project . | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000584/2022-2023 | 932/1/TSD | 14/03/2023 | 7 | NIVEDITA CONSTRUCTION | 0.71 | 0.71 | 0
4730 | Nadia Division | Kalyani Sub-Division I | Construction of barbed wire fencing with concrete pillars at Dogachhi Zone-II (H/W) Site. water supply scheme(Sahebpara New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000729/2023-2024 | 1118/TSD | 21/02/2024 | 7 | NIVEDITA CONSTRUCTION | 1.71 | 0 | 100
4731 | Nadia Division | Kalyani Sub-Division I | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 51 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Dogachi Zone-II to accommodate FHTC within Karimpur-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000826/2024-2025 | 5078/ND | 17/09/2024 | 180 | MANGES INDUSTRIAL CORPORATION | 183.53 | 0 | 0
4732 | Nadia Division | Kalyani Sub-Division I | (Horizontal) boring and Drum Sheet Walling for Dogachi Piped Water Supply Scheme Zone-I at Karimpur-II, Block at Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000841/2023-2024 | 370/KlySD-I | 01/03/2024 | 31 | JOY HIND TUBEWELL'S | 13.42 | 0 | 100
4733 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000041/2023-2024 | 1903/ND | 27/04/2023 | 0 | Resource Division | 92.46 | 0 | 0
4734 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000090/2023-2024 | 2321/ND | 29/05/2023 | 0 | Resource Division | 34.62 | 0 | 0
4735 | Nadia Division | Kalyani Sub-Division I | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Junior Engineer 1 | RTOR000103/2023-2024 | 3641/ND | 16/08/2023 | 0 | Resource Division | 12.39 | 0 | 0
4736 | Central Drilling | Kalyani Sub-Division I | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR DOGACHI (ZONE-I) W/S SCH, KARIMPUR-II BLOCK, UNDER NADIA DISTRICT, CDD, PHE DTE. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000376/2022-2023 | 1196/CDD | 11/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 10.22 | 7.76 | 0
4737 | Central Drilling | Kalyani Sub-Division I | Supply and delivery of Pea size Gravels at site for construction of Tube Well (300mm X 200mm X 150 Mtrs. Depth) by utilising Departmental Machineries for Dogachi Zone-I W/S Scheme, Karimpur-II Block under Nadia District under CMSD-II(D), CDD, PHE, Dte. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000485/2022-2023 | 535/CMSD-II | 02/12/2022 | 380 | M/S SAIKAT ENTERPRISE | 0.98 | 0 | 100
4738 | Central Drilling | Kalyani Sub-Division I | ADDITIONAL TRANSPORTATION OF DEPARTMENTAL RIG UNIT NO. SUPER RR WITH COMPRESSOR AND PUMP UNIT FROM DOGACHI UNDERCMSD-II (D), CDD, PHE DTE. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000506/2022-2023 | 562/CMSD-II | 30/12/2022 | 10 | PADMA ENGINEERING & CO. | 0.75 | 0 | 100
4739 | Eastern Mechanical | Kalyani Sub-Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube well and Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-Z-I & II under Dogachi ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. [SM/13039] | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000022/2025-2026 | 692/EMD | 04/04/2025 | 30 | PADMA ENGINEERING CO. | 50.38 | 0 | 0
4740 | Eastern Mechanical | Kalyani Sub-Division I | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II of Z-I & Z-II under DOGACHI ground water based water supply scheme under Block_ KARIMPUR-II Dist. - Nadia under EMD, PHE Dte. SM/13039 | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000184/2025-2026 | 1121/EMD | 04/06/2025 | 90 | A.G ENTERPRISE. | 41.59 | 0 | 0
4741 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of Pipeline for FHTC works under Surface Water Based PWSS Saguna Zone-VI (Part-II) for arsenic affected areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000020/2024-2025 | 1117/NAD-I | 19/07/2024 | 300 | APURBA MANDAL | 95.96 | 0 | 85
4742 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Laying of Distribution System Including Specials, Valves & Pipe Supporting Structure, Construction of Boundary Wall (675m Length), Chlorine Room, Drain (I300 m Length) and Approach Road (60.0m Length and 3.0m Wide), Construction of 900 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials and Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 900 m3 Staging Height 20Mtr. at Surface Water Based Piped Water Supply Scheme for Saguna ZONE-VI(PART-I) in Chakdah Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000103/2023-2024 | 1708/NAD-I | 14/07/2023 | 366 | MONDAL ENTERPRISE | 676.94 | 0 | 0
4743 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for providing FHTC (Functional Household Tap Connection) under JJM (Jal Jeevan Mission) by Augmentation of Zone-VI (Saguna) Part -I of Surface Water Based PWSS for Haringhata and Chakdah (PArt) at Chakdah Block at Nadia District under Nadia Arsenic Division -I, P.H.E. Dte.(Sl.No.-01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000242/2022-2023 | 168 / AE-I / NAD-I | 08/07/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.78 | 4.78 | 100
4744 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000013/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 31.72 | 0 | 0
4745 | Nadia Division | Debgram Sub-Division | Providing FHTC at Surface Water Based Water Supply Scheme(northern sector),Part-I,Zone-II within Kaliganj block(Phase-A) in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000183/2020-2021 | 3589/ND | 08/12/2020 | 90 | MONDAL ENTERPRISE | 97.01 | 90.15 | 0
4746 | Nadia Division | Debgram Sub-Division | Hiring of Diesel Ambassador Car/maxi cab for the office of the Assistant Engineer, Debagram Sub-Division, P.H. Engineering Dte., Debagram, Nadia with effect from 01/08/22 to 31/07/23 | Assistant Engineer |  | ORD/000186/2022-2023 | 312/D/DSD | 29/07/2022 | 365 | TARUN KUMAR BHATTACHARYA | 4.8 | 1.11 | 70
4747 | Nadia Division | Debgram Sub-Division | PREPERATION OF DETAILS PROJECT FOR FHTC AT SURFACE WATER BASED W/S SCHEME ( N.SECTOR) , PART-II, ZONE-I, PHASE-A & B UNDER , NADIA DIVISION , PHE ,DTE | Assistant Engineer |  | VCH/000306/2021-2022 | 139/FHTC | 17/08/2021 | 0 | LEMNISCATE | 0.46 | 0 | 0
4748 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PIPE G.I/PVC PIPE OF AVERAGE LENGTH OF 10MM DIA GUN-METAL FERRULE, SADDLE PIECE 15MM DIA BIB COCK ETC AT SUBERNA BIHAR W/S SCHEME PART-B | Assistant Engineer |  | VCH/000963/2021-2022 | 473/DW | 07/02/2022 | 0 | ROY CONSTRUCTION | 0.73 | 0 | 0
4749 | Nadia Division | Debgram Sub-Division | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT NORTHERN SECTOR PART-1 Z-2 | Assistant Engineer |  | VCH/001080/2020-2021 | 445/DW | 25/03/2021 | 0 | MONDAL ENTERPRISE | 44.33 | 0 | 0
Total | [10 empty] | 782147.18 | 64558.18